## Sheet1
Prioritization Period | Weekday | Important Dates | Requestor | Dean's / Vice Chancellor's Delegate | Facilities Services
Summer 2019
| Friday | 2019-05-03 |  |  | COMMUNICATION: Preview Email sent to Delegate to review existing list of un-prioritized project requests for Summer 2019.
| Wednesday | 2019-05-15 | DEADLINE: Last Day to submit minor renovation Project Requests online to be submitted for prioritization by Org Leadership.
|  | May 15 - 31, 2019 |  |  | MEETING: Scheduled one-on-one meetings with Dean's Delegate and FS representatives to review scope of existing project requests.
| Monday | 2019-06-10 |  | DEADLINE: Last Day to submit prioritized list of minor renovation projects by Dean's Delegate to begin work in Summer 2019. All un-prioritized projects will remain on HOLD until next prioritization period.
| Thursday | 2019-06-13 |  |  | COMMUNICATION: Email sent to requestors regarding the status of their submitted projects.
| Monday | 2019-06-24 | First Day of Class
| Monday | 2019-07-01 |  |  | UPDATE: Work begins on prioritized projects.
Fall 2019
| Friday | 2019-07-12 |  |  | COMMUNICATION: Preview Email sent to Delegate to review existing list of un-prioritized project requests for Fall 2019.
| Monday | 2019-07-22 | DEADLINE: Last Day to submit minor renovation Project Requests online to be submitted for prioritization by Org Leadership.
|  | Jul 22 - Aug 09, 2019 |  |  | MEETING: Scheduled one-on-one meetings with Delegate and FS representatives to review scope of existing project requests.
| Monday | 2019-08-26 |  | DEADLINE: Last Day to submit prioritized list of minor renovation projects by Delegate to begin work in Fall 2019. All un-prioritized projects will remain on HOLD until next prioritization period.
| Tuesday | 2019-08-27 |  |  | COMMUNICATION: Email sent to requestors regarding the status of their submitted projects.
| Monday | 2019-09-23 |  |  | UPDATE: Work begins on prioritized projects.
| Thursday | 2019-09-26 | First Day of Class
Winter 2020
| Friday | 2019-10-25 |  |  | COMMUNICATION: Preview Email sent to Delegate to review existing list of un-prioritized project requests for Winter 2020.
| Monday | 2019-11-04 | DEADLINE: Last Day to submit minor renovation Project Requests online to be submitted for prioritization by Org Leadership.
|  | Nov 4 - Nov 22, 2019 |  |  | MEETING: Scheduled one-on-one meetings with Delegate and FS representatives to review scope of existing project requests.
Prioritization Period |  | Important Dates | Requestor | Dean's / Vice Chancellor's Delegate | Facilities Services
Winter 2020
| Monday | 2019-12-02 |  | DEADLINE: Last Day to submit prioritized list of minor renovation projects by Delegate to begin work in Winter 2020. All un-prioritized projects will remain on HOLD until next prioritization period.
| Tuesday | 2019-12-03 |  |  | COMMUNICATION: Email sent to requestors regarding the status of their submitted projects.
| Friday | 2020-01-03 |  |  | UPDATE: Work begins on prioritized projects.
| Saturday | 2020-01-04 | First Day of Class
Spring 2020
| Friday | 2020-01-17 |  |  | COMMUNICATION: Preview Email sent to Delegate to review existing list of un-prioritized project requests for Spring 2020.
| Monday | 2020-02-03 | DEADLINE: Last Day to submit minor renovation Project Requests online to be submitted for prioritization by Org Leadership.
|  | Feb 03 - Feb 14, 2020 |  |  | MEETING: Scheduled one-on-one meetings with Delegate and FS representatives to review scope of existing project requests.
| Monday | 2020-03-02 |  | DEADLINE: Last Day to submit prioritized list of minor renovation projects by Delegate to begin work in Spring 2020. All un-prioritized projects will remain on HOLD until next prioritization period.
| Tuesday | 2020-03-03 |  |  | COMMUNICATION: Email sent to requestors regarding the status of their submitted projects.
| Monday | 2019-03-25 |  |  | UPDATE: Work begins on prioritized projects.
| Wednesday | 2019-03-27 | First Day of Class
Prioritization Period |  | Important Dates | Requestor | Dean's / Vice Chancellor's Delegate | Facilities Services
Summer 2020
| Friday | 2021-04-16 |  |  | COMMUNICATION: Preview Email sent to Delegate to review existing list of un-prioritized project requests for Summer 2019.
| Monday | 2021-04-26 | DEADLINE: Last Day to submit minor renovation Project Requests online to be submitted for prioritization by Org Leadership.
|  | Apr 26 - May 15, 2021 |  |  | MEETING: Scheduled one-on-one meetings with Delegate and FS representatives to review scope of existing project requests.
| Tuesday | 2021-05-25 |  | DEADLINE: Last Day to submit prioritized list of minor renovation projects by Delegate to begin work in Summer 2019. All un-prioritized projects will remain on HOLD until next prioritization period.
| Wednesday | 2021-05-26 |  |  | COMMUNICATION: Email sent to requestors regarding the status of their submitted projects.
| Monday | 2020-06-22 | First Day of Class
| Wednesday | 2020-07-01 |  |  | UPDATE: Work begins on prioritized projects.
Fall 2020
| Friday | 2021-07-16 |  |  | COMMUNICATION: Preview Email sent to Delegate to review existing list of un-prioritized project requests for Fall 2019.
| Monday | 2020-08-03 | DEADLINE: Last Day to submit minor renovation Project Requests online to be submitted for prioritization by Org Leadership.
|  | Aug 3 - 14, 2020 |  |  | MEETING: Scheduled one-on-one meetings with Delegate and FS representatives to review scope of existing project requests.
| Monday | 2020-08-31 |  | DEADLINE: Last Day to submit prioritized list of minor renovation projects by Delegate to begin work in Fall 2019. All un-prioritized projects will remain on HOLD until next prioritization period.
| Tuesday | 2020-09-01 |  |  | COMMUNICATION: Email sent to requestors regarding the status of their submitted projects.
| Monday | 2020-09-28 |  |  | UPDATE: Work begins on prioritized projects.
| Thursday | 2020-10-01 | First Day of Class
Winter 2021
| Friday | 2020-10-23 |  |  | COMMUNICATION: Preview Email sent to Delegate to review existing list of un-prioritized project requests for Winter 2020.
| Monday | 2020-11-09 | DEADLINE: Last Day to submit minor renovation Project Requests online to be submitted for prioritization by Org Leadership.
|  | Nov 9 - 25, 2020 |  |  | MEETING: Scheduled one-on-one meetings with Delegate and FS representatives to review scope of existing project requests.
| Monday | 2021-12-06 |  | DEADLINE: Last Day to submit prioritized list of minor renovation projects by Delegate to begin work in Winter 2020. All un-prioritized projects will remain on HOLD until next prioritization period.
Prioritization Period |  | Important Dates | Requestor | Dean's / Vice Chancellor's Delegate | Facilities Services
Winter 2021
| Tuesday | 2021-12-07 |  |  | COMMUNICATION: Email sent to requestors regarding the status of their submitted projects.
| Monday | 2021-01-04 |  |  | UPDATE: Work begins on prioritized projects.
| Monday | 2021-01-04 | First Day of Class
Spring 2021
| Friday | 2021-01-15 |  |  | COMMUNICATION: Preview Email sent to Delegate to review existing list of un-prioritized project requests for Spring 2020.
| Monday | 2021-01-25 | DEADLINE: Last Day to submit minor renovation Project Requests online to be submitted for prioritization by Org Leadership.
|  | Jan 25 - Feb 12, 2021 |  |  | MEETING: Scheduled one-on-one meetings with Delegate and FS representatives to review scope of existing project requests.
| Monday | 2021-02-22 |  | DEADLINE: Last Day to submit prioritized list of minor renovation projects by Delegate to begin work in Spring 2020. All un-prioritized projects will remain on HOLD until next prioritization period.
| Tuesday | 2021-02-23 |  |  | COMMUNICATION: Email sent to requestors regarding the status of their submitted projects.
| Wednesday | 2021-03-24 |  |  | UPDATE: Work begins on prioritized projects.
| Friday | 2021-03-26 | First Day of Class
Summer 2021
| Friday | 2021-04-16 |  |  | COMMUNICATION: Preview Email sent to Delegate to review existing list of un-prioritized project requests for Summer 2019.
| Monday | 2021-04-26 | DEADLINE: Last Day to submit minor renovation Project Requests online to be submitted for prioritization by Org Leadership.
|  | Apr 26 - May 14, 2021 |  |  | MEETING: Scheduled one-on-one meetings with Delegate and FS representatives to review scope of existing project requests.
| Tuesday | 2021-05-25 |  | DEADLINE: Last Day to submit prioritized list of minor renovation projects by Delegate to begin work in Summer 2019. All un-prioritized projects will remain on HOLD until next prioritization period.
| Wednesday | 2021-05-26 |  |  | COMMUNICATION: Email sent to requestors regarding the status of their submitted projects.
| Monday | 2021-06-21 | First Day of Class
| Thursday | 2021-07-01 |  |  | UPDATE: Work begins on prioritized projects.

## Sheet2
1 | Sunday
2 | Monday
3 | Tuesday
4 | Wednesday
5 | Thursday
6 | Friday
7 | Saturday