## Active Project Summary
Integrated Project Summary Report
[6 empty] | Total Active PD&C Projects |  | 121
[6 empty] | Total Active FS Projects |  | 61
Last Updated | 2019-09-01 | Project Summary |  |  |  | Project Status |  |  |  |  | Project Details
Organization | Project Ref No. | Project Service Unit | Project Title | Building | Room | Request Date | Current Status | Next Steps | START Date | COMPLETE Date | Project Description | PD&C Org Priority No. | FS Org Priority No. | For New Faculty Hire? | Contact / Requestor | Proj Manager
ATHLETICS | 19P000309 | FS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | ATH DANCE |  | 2018-09-12 | IN PROGRESS |  |  |  | FS to coordinate with customer to scope the work. |  | 7 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 3407 | PD&C | Athletics Media Room | S LCKRM/CONC |  | 2018-08-23 | In Programming | Create SOW | 2020-03-02 | 2020-06-26 | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | 2 |  |  | Johnathan Jensen | Fernando Nunez
ATHLETICS | 2696 | PD&C | Soccer Stadium Fencing (E Side) |  |  | 2014-04-10 | In coordination with Mobility Hub | To be coord. with Rec Mall work |  |  | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | 3 |  |  | Joe Erbland | Gerald Caraig
ATHLETICS | 3408 | PD&C | Harrison Field Netting | SOFTBALL STG |  | 2018-01-23 | Per department: Project is on hold until further notice. | OnHold by Cust Til Furthr Notice |  |  | Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | 99 |  |  | Joseph Erbland | Fernando Nunez
ATHLETICS | 19P000646 | FS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING | ATH DANCE | 20R, 20S | 2019-05-23 | IN PROGRESS | [5 empty] | 1 |  | JOSEPH ERBLAND | Dan Lerman
ATHLETICS | 19P000277 | FS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | ATH DANCE |  | 2018-09-12 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE |  |  |  | FS to coordinate with customer to scope the work. |  | 10 |  | JOHNATHAN JENSEN | Dan Lerman
ATHLETICS | 19P000311 | FS | SL5 ATHLETICS 150-KEYLESS ENTRY | ATH DANCE | 0150 | 2018-10-02 | Project Intake |  |  |  | Keyless entry system |  | R2 |  | JOHNATHAN JENSEN | DAN LERMAN
BAS | 3430 | PD&C | TAPS Cust Svc Lobby Upgrades | PARKING SERV |  | 2018-05-17 | On hold | Customer Approval & Funding |  |  | Upgrades to Customer Service Lobby – Need to complete Tenant Improvement project upgrade customer service counter in Parking Services Building. Want to replace current counter to allow for; modern computer equipment, dividers between customers’ transaction spaces, under counter space for filing cabinets and check writing space. Please coordinate with Auxiliaries’ primary PM John Franklin. | 2 |  |  | Andrew Stewart | Dave Bomba
BAS | 3354 | PD&C | Lot 4/Barn Area ADA Improvements |  |  | 2017-08-15 | In Design | Bidding | 2019-09-01 | 2019-11-01 | Lot 4/Barn Area ADA Improvements - The proposed project will relocate an existing crosswalk that is not ADA compliant and provide path of travel improvements and additional ADA parking capacity in Parking Lot 4. The existing crosswalk located at West Campus Drive and Parking Lot 4 (north) was identified in the Draft ADA Transition Plan to be out of compliance. A Pedestrian Safety Study by Fehr & Peers completed in June 2008 identified the relocation of this crosswalk to approximately 100 feet east to provide a more visible, safe, pedestrian crossing. To increase pedestrian safety further, the crosswalk will be designed as a speed table. Additionally, Transportation and Parking Services proposes to create additional ADA parking spaces in Parking Lot 4 that exceed the required number, with hardscape and path of travel improvements that will connect to the new crosswalk. The improved crosswalk will correct required path of travel deficiencies from a parking lot that provides access to numerous publicly accessible buildings, as well as allow the Barn Expansion project to obtain Division of State Architect (DSA) approval once construction is completed. The funds to complete the crosswalk replacement will be requested from Campus ADA funds. Parking Lot 4 improvements will come from will come from TAPS. Although this project supports the Barn Renovation, its conception and need is not tied to the Barn project. The crosswalk improvements and additional ADA parking is needed to meet our ADA parking requirements and serve the growing demand on campus. This project is desired regardless of the Barn Renovation project. | 3 |  |  | Andrew Stewart | John Franklin
BAS | 3376 | PD&C | West Lothian Roof Replacement Design | LOTHIAN HALL |  | 2017-09-28 | In Close-out | Complete Close-out | 2019-06-01 | 2019-08-01 | Provide Schematic Design, Design Development and professional cost estimate to replace the existing single-ply membrane roof system on the Lothian West residence hall wings plus Common Area applications. Existing roofing is past its useful life and starting to experience multiple leaks that are damaging living spaces below. Design effort should select the most appropriate roof material for this roof plan. The intent is to design this year (alongside the Lothian East design) and construct immediately following the Lothian East roof replacement. | 4 |  |  | Richard Geiger | John Franklin
BAS | 3383 | PD&C | W Lothian Air Handler Replacemt | LOTHIAN HALL |  | 2017-10-03 | In Close-out | Complete Close-out | 2019-06-01 | 2019-08-01 | Existing air handler equipment in West Lothian is original to the building and past its service life. Provide HVAC professional services to develop options for Air Handler replacement that meet UC Carbon Neutral 2025 goal. Each option analysis should include pros and cons for energy consumption, reliability, serviceability and system installation cost projections. At least one option should explore potential conversion to individual package units as practical. | 5 |  |  | Richard Geiger | John Franklin
BAS | 3453 | PD&C | ECS N&S Playground Shade & Turf |  |  | 2018-07-03 | Dept approval/funding | Dept approval/funding |  |  | Provide Schematic Design, Design Development and Professional Cost Estimate for the alteration of existing shade structures, provision for additional shade structures, refinish interior metal fencing, and the replacement of existing grass with synthetic turf at the Early Childhood Services north and south playground areas. Prepare drawings so that they can be bid and constructed as separate projects. | 7 |  |  | Richard Geiger | John Franklin
BAS | 3459 | PD&C | A-I Hardscape Landscape Design-Study | ABER INVER |  | 2018-07-16 | Architect design meetings scheduled. | Complete Design | 2020-05-01 | 2020-09-01 | Provide Schematic Design and Design Development drawings for a selective renovation of all hardscape and landscape around the perimeter of the Aberdeen-Inverness housing complex. Scope to include (but not limited to) widening of South Walk and replace its asphalt with concrete pavers, upgrade hardscape and landscape at Horseshoe, replace selected lawn areas with hardscape, seating and solar umbrellas at east and west lawns of Building E, consider new bike storage along South Walk, consider modifying slopped lawn between Building A and Linden St., generally reduce lawn areas and replace with sustainable planting, prune or replace unkempt trees, replace selected light fixtures to match Dundee fixtures, and generally freshen the landscaping so that it is harmonious with the new Dundee development. Design to be packaged in phases, with the South Walk and Dundee-facing landscape to be ready in Phase 1 for construction timing alongside Dundee-Glasgow landscaping in Spring of 2020. | 8 |  |  | Richard Geiger | Jason Espinoza
BAS | 3462 | PD&C | A-I Restaurant & Lobby Reconfiguration | ABER INVER |  | 2018-07-17 | Project currently on hold pending approval | Approval & Funding |  |  | Provide Schematic Design and Design Development drawings for the complete reconfiguration of Building C including kitchen, dining space, and common areas. The restaurant and kitchen areas are largely original to the building and well past their useful life. The new, replacement, Glasgow restaurant coming on-line in Fall 2020 will allow a needed reprogramming and modernization of this space. Preliminary Program for this space includes a smaller Catering Kitchen, Meeting Rooms, new KUCR studio as well as a modernization and upgrade of the Lobby and other Common Areas. Documents to be assembled for a Fall 2020 construction start. | 9 |  |  | Richard Geiger | Jason Espinoza
BAS | 3463 | PD&C | Landscape Strategic Plan for Housing Services |  |  | 2018-07-17 | Project on-hold | On hold per Auxiliary Services |  |  | Provide a comprehensive study of existing landscape areas within Auxiliary Services and provide specific and actionable recommendations for their conversion to sustainable landscaping by location. Study to include all Resident Hall and Apartment properties and include conceptual cost estimates, by location, for proposed landscape conversions. | 11 |  |  | Richard Geiger | Jason Espinoza
BAS | 3460 | PD&C | A-I Restroom Replacement - Reconfig | ABER INVER |  | 2018-07-19 | On-hold | Bidding in Late-Nov. | 2020-03-01 | 2020-09-01 | Provide Schematic Design and Design Development drawings for the complete replacement of the restrooms in all four resident hall wings. Existing restroom fixtures and finishes are largely original to the building and long past their service life, causing serious leaks between floors. New restrooms will be reconfigured to meet current accessibility code. Documents to be assembled for phased construction, one wing per summer, with the first building (D-Wing) to be constructed in Summer 2019. | 12 |  |  | Richard Geiger | Jason Espinoza
BAS | 3467 | PD&C | Plaza Porch/Stair Structural Repairs | THE PLAZA |  | 2018-07-31 | PSA issued, coordinating site inspections. | Site Inspections |  |  | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | 13 |  |  | Richard Geiger | Jason Espinoza
BAS | 3466 | PD&C | Oban Porch and Stair Repair | OBAN APTS A |  | 2018-07-31 | Final Report Review | Project Planning with Aux. Svcs. |  |  | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | 14 |  |  | Richard Geiger | Jason Espinoza
BAS | 3382 | PD&C | West Lothian Restroom & Common Area Design | LOTHIAN HALL |  | 2017-09-29 | Project pushed to 2021 | Project pushed to 2021 |  |  | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | 15 |  |  | Richard Geiger | D.Hecht/J.Franklin
BAS | 2868 | PD&C | West Lothian Elevator Renovation |  |  | 2015-04-08 | In Close-out | Complete Close-out | 2019-06-01 | 2019-08-01 |  | 16 |  |  | Richard Geiger | John Franklin
BAS | 3392 | PD&C | Bicycle Master Plan Study |  |  | 2017-11-13 | Pre-Programming | Funding |  |  | Bicycle Master Plan Study. This CPMS project is for the funding and creation of a Bicycle Master Plan Study for the UCR Campus. It is not for a specific capital project. | 17 |  |  | Irma Henderson | Melissa Garrety
BAS | 3472 | PD&C | Lot 20 Trash Enclosure Relocation |  |  | 2018-08-15 | In Design | Award Contract | 2019-09-01 | 2019-10-01 | Construct a new CMU trash enclosure with water and power in a different location of Lot 21 to replace the existing enclosure that will be demolished to make way for the Dundee Residence Hall construction. Include hose bib for cleaning and power for future compactor installation. New enclosure needs to be on line BEFORE site construction can start on Dundee-Glasgow in January 2019. | 18 |  |  | Richard Geiger | John Franklin
BAS | 3397 | PD&C | Dundee Residence Hall and Glasgow Dining | ABER INVER |  | 2017-11-21 | In Construction | Complete Construction | 2019-01-01 | 2020-08-01 | (Lot 22/Dundee-Glasgow) A newly proposed student housing development, including a single phase 760-bed residence hall and an 830-seat dining facility located on the existing Parking Lot 22 site south of Linden Street. The project is anticipated to be completed by Fall/Winter 2020. Funding for predevelopment activities including CEQA and staff augmentation to be determined. | 20 |  |  | Richard Geiger | Thomas Toepfer
BAS | 3203 | PD&C | Plaza Structural Seismic Study |  |  | 2016-10-10 | Design Development for Bldgs. C, E & F | Design development |  |  | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | 21 |  |  | Richard Geiger | Jason Espinoza
BAS | 3490 | PD&C | Parking Structure 1 |  |  | 2018-12-06 | In Design | Selection of Design Build Team | 2019-12-01 | 2021-02-01 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | 23 |  |  | Irma Henderson | Daneca Stevens
BAS | 3503 | PD&C | Falkirk Stair/Front Porch Repair |  |  | 2019-02-01 | In Bidding | Complete Close-out | 2019-06-01 | 2019-08-01 | Repair or replace four sets of entry stairs and landings that are long past their service life and are a life safety concern. Consider replacing these wood structures with steel to ease future maintenance. Apartments affected are #3RS, #11MN, #15A and #16FG. | 24 |  |  | Richard Geiger | John Franklin
BAS | 2508 | PD&C | Barn Expansion |  |  | 2013-07-05 | In construction | Complete Construction | 2018-06-01 | 2019-12-01 | Project 950493 Barn has completed the DPP process and we are now adding this to CPMS to capture expenses related to the Program Process which occurred in FY11-12 and FY12-13. Please move all expenditures from A01233-70003-76 Cost Center to JR142 to a plant account. | 28 |  |  | Susan Marshburn | D.Hecht/J.Franklin
BAS | 3519 | PD&C | CBTL Permit Inspections |  |  | 2019-04-04 | In Close-out | Complete Close-out |  |  | CBTL PERMIT INSPECTIONS - The Coffee Bean & Tea Leaf restaurant is being leased by a CBTL franchisee (currently this is operated by UCR). They have submitted drawings to do a light remodel of the space. Permit and inspection services are needed to support their remodel. | 29 |  |  | Richard Geiger | John Franklin
BAS | 3421 | PD&C | A-I Boiler Replacement | ABER INVER |  | 2018-03-19 | On Hold-Funding | CIB Approval |  |  | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | 30 |  |  | Richard Geiger | John Franklin
BAS | 3426 | PD&C | Lothian Boiler Replacement | LOTHIAN HALL |  | 2018-03-19 | On hold | On hold |  |  | The boiler equipment at Lothian is original to the building and past its useful life. Design, procure and install a replacement boiler that incorporates the latest energy saving and management technology that can be cost-effectively installed as a direct replacement to the existing unit. | 32 |  |  | Richard Geiger | John Franklin
BAS | 3533 | PD&C | Solar Rooftop Initiative |  |  | 2019-06-03 | Programming | Design |  |  | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. | 35 |  |  | Richard Geiger | John Franklin
BAS | 3286 | PD&C | Falkirk Apartments Seismic Improvements | FALKIRK 1 |  | 2017-03-29 | Construction | Complete Construction | 2019-08-01 | 2019-11-01 | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | 36 |  |  | Richard Geiger | J.Franklin/J.Espinoza
BAS | 19P000232 | FS | SL5 BANNOCKBURN J-104 BREAK ROOM UPGRADE | BANNOCK I | I0105 | 2018-09-04 | IN PROGRESS |  |  |  | Scheduled work with trades anticipated 60% completion by Jun 15th. |  | 6 |  | RICHARD GEIGER | John Peraino
BAS | 19P000687 | FS | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | HUB | Various | 2019-06-26 | PLAN DEVELOPMENT/CHECK |  |  |  | Provide estimate to install key card access control |  | R1 |  | MANNY SANCHEZ | Dan Lerman
BCOE | 19P000638 | FS | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM | BOURNS | B207 | 2019-05-16 | IN PROGRESS |  |  |  | renovate lab |  | 1 |  | LOUIS SANDOVAL | Dan Lerman
BCOE | 19P000619 | FS | SL5 BOURNS, RM A0311- NEW FLOORING/PAINT FOR INCOMING FACULTY | BOURNS | A0311 | 2019-05-14 | IN PROGRESS | [5 empty] | 1 | YES | LOUIS SANDOVAL | Paul Ditty
BCOE | 19P000621 | FS | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY | BOURNS | A0308 | 2019-05-14 | QUEUE TO START | [5 empty] | 10 | YES | LOUIS SANDOVAL | Paul Ditty
BCOE | 19P000477 | FS | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT | CHUNG HALL | 457 | 2019-01-30 | QUEUE TO START | [5 empty] | 11 |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000625 | FS | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM | BOURNS | A0108 | 2019-05-15 | QUEUE TO START | [5 empty] | 4 |  | LOUIS SANDOVAL | Paul Ditty
BCOE | 19P000526 | FS | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT | CHUNG HALL | 0202 & 0203 | 2019-03-12 | QUEUE TO START | [5 empty] | 6 |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000620 | FS | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY | BOURNS | A0304 | 2019-05-14 | QUEUE TO START | [5 empty] | 9 | YES | LOUIS SANDOVAL | Paul Ditty
BCOE | 3428 | PD&C | MS&E Cleanroom Expansion | MAT SCI ENGR |  | 2018-04-04 | Award Contract - September | Award Contract | 2019-11-01 | 2020-01-01 | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | 1 |  |  | Margaret Souder | Scott Donnell
BCOE | 3300 | PD&C | R'Garden - Solar Installation |  |  | 2017-05-03 | Work to be inspected by A&E. | Relocation |  |  | Electrician to do the following wiring of our solar panels and inverters out at the R’Garden at UCR. The H model cyboinverter to be used powers the lower heating element of the water heater. The thermostat of the lower heating element must then be set to be higher than the upper heating element. The two output lines are to be connected to an AC switch or switchable AC outlet and the lower element water heater. | 2 |  |  | Arvin Tam | Scott Donnell
BCOE | 19P000600 | FS | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | BOURNS | B0316 | 2019-05-09 | PLAN DEVELOPMENT/CHECK |  |  |  | renovate/refresh lab space |  | 2 |  | KATHALENA COCKER | Dan Lerman
BCOE | 19P000601 | FS | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY | BOURNS | B0328E | 2019-05-09 | PLAN DEVELOPMENT/CHECK |  |  |  | Renopvate lab space, Patch/paint, Re-finish, re-surface – existing cabinets/casework. Re-finish, bench-tops. Clean existing Chemical fume hood. Repair or replace self-closing chemical/flammables storage cabinet. Repair or replace bench shelves as needed. Clean and wax floors. |  | 3 |  | KATHALENA COCKER | Dan Lerman
CAP.PROG. | 3540 | PD&C | BCOE Advising Move |  |  | 2019-07-25 | New | Furniture Delivery | 2019-09-01 | 2019-09-01 | Relocation expenses for BCOE advising including: $75k furniture, $10k moving expenses, $3k misc. Renovations were also approved and were completed by Facilities under SLA. Also includes relocation of VCBAS from Skye to Student Services at $1,010 and move expenses for Student Disability from Costo to Student Services at $25k. | 2 |  |  | Sharyl Murdock | Sharyl Murdock
CAP.PROG. | 3233 | PD&C | Mobility HUB Central Campus Linkages |  |  | 2016-12-16 | On Hold | Leadership Direction |  |  | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. | 3 |  |  | Jaime Enghbrecht | Gerald Caraig
CAP.PROG. | 2916 | PD&C | Solar Greenhouse |  |  | 2015-08-04 | In Construction | Complete Construction | 2019-09-01 | 2019-09-01 | Construction of a solar powered greenhouse. | 4 |  |  | Matt Barth | Scott Donnell
CAP.PROG. | 3234 | PD&C | UC Intellicenter 2nd Floor TI |  |  | 2016-12-21 | In Close-out | Complete Punchlist & Close Out | 2018-11-05 | 2019-03-29 | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. | 6 |  |  | John White | Fernando Nunez
CAP.PROG. | 3120 | PD&C | Arts Walk Sculpture (Ext Campus Art Project) |  |  | 2016-05-26 | Contractor removing rejected concrete | Complete Construction | 2019-02-01 | 2019-11-01 | Sculpture design concept - hiring a consultant to revise an artist design concept for a proposed outdoor art piece to be placed between the Arts building and the CHASS Interdisciplinary buildings. | 8 |  |  | Uma Ramasubramanian | Jason Espinoza
CAP.PROG. | 3119 | PD&C | Plant Growth Environment Facility |  |  | 2016-05-25 | In Construction | Site utilities & ret. Wall | 2019-04-01 | 2020-08-01 | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. | 9 |  |  | Michelle Baniqued | Rowan Reid
CAP.PROG. | 3293 | PD&C | USDA Head House - Public Restroom | GERMPLASM |  | 2017-05-22 | Pending Lease | USDA Scope & Design |  |  | Provide an accessible public restroom facility in or adjacent to the USDA Head House Building in Ag Ops. Restroom will serve individuals and groups touring the UCR and USDA Citrus Facilities. Three options have been proposed, and need to be considered and evaluated to recommend a feasible solution for USDA. The work would be managed and paid by USDA, including the design, bidding and construction. UCR staff needs to review the proposed plans and specifications per the agreement with USDA, and provide the review, inspection and approvals. The USDA representative is Marylou Polek. | 14 |  |  | Mary Lou Polek | Scott Donnell
CAP.PROG. | 3319 | PD&C | Student Success Center |  |  | 2017-06-01 | In Design Development | Start Construction | 2019-11-01 | 2021-08-01 | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. | 16 |  |  | Michelle Baniqued | Mihai Gavan
CAP.PROG. | 3452 | PD&C | Long Range Dev Plan - 2018 |  |  | 2018-07-16 | In Programming | Complete Programming |  |  | New Long Range Development Plan (LRDP), with all required technical studies | 16 |  |  | Jacqueline Norman | Uma R.
CAP.PROG. | 3005 | PD&C | Batchelor Hall Interior Improvements | BATCHELOR |  | 2016-02-02 | In Design | CM at Risk Selection | 2020-01-01 | 2021-11-01 | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | 17 |  |  | Sharyl Murdock | Rowan Reid
CAP.PROG. | 3393 | PD&C | South Neighborhood Dist. Study |  |  | 2017-11-15 | In Close-out | Follow Up on Study Reports |  |  | South Neighborhood District Study per discussions with the Provost/VCPB, July 2017. The South District Planning Study needs to provide guidance for future development in the South District that is inclusive of: **University aspirations to develop the South District to define the campus’ presence along the adjacent freeway (CA-60/215). **Development capacity, optimal building heights and conceptual massing presented both in metrics and a three dimensional format. **Broad parking strategy to meet the needs of the district in alignment with the campus’ overall parking management strategy and alternative transportation solutions. **High level understanding of infrastructure needs (electrical, domestic, fire and storm water, sanitary sewer, building heating and cooling) to meet the needs of the campus’ desired development capacity for district. **Pedestrian and vehicular connectivity. **East and South Campus Drive improvements | 18 |  |  | Uma Ramasubramanian | Fernando Nunez
CAP.PROG. | 3366 | PD&C | Genomics Ramps |  |  | 2017-11-16 | In Design | Bidding | 2019-11-01 | 2019-12-01 | Genomics Accessibility Improvements - The proposed project will create an accessible sidewalk connection from the Genomics Building to the University Lab and University Office Building. Currently, there is no accessible north sidewalk linkage east of the Genomics Building. The project will demolish and replace approximately 300 square feet of asphalt to bring it up to grade. Two ADA ramps will be added to sidewalk extensions of approximately 300 square feet that connect across a driveway. Existing landscaping and irrigation will be removed and replaced. No trees will be impacted by this work. | 19 |  |  | Jaime Engbrecht | Gerald Caraig
CAP.PROG. | 3458 | PD&C | KUCR Replacement Project |  |  | 2018-07-16 | PM to update schedule | PM to update schedule |  |  | Proposed replacement of KUCR radio station facility | 20 |  |  | Blythe Wilson | Blythe Wilson
CAP.PROG. | 2970d | PD&C | ADA Improvements/Transition Plan-Phase 4 |  |  | 2015-12-02 | In Programming | Award package 1 & 3 | 2019-11-01 | 2019-12-01 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) | 20 |  |  | Blythe Wilson | Scott Donnell
CAP.PROG. | 2970a | PD&C | ADA Improvements/Transition Plan-Phase 1 |  |  | 2015-12-02 | Bidding | Award package 1 & 3 | 2018-09-01 | 2020-01-01 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) | 20 |  |  | Blythe Wilson | Scott Donnell
CAP.PROG. | 2970c | PD&C | ADA Improvements/Transition Plan-Phase 3 |  |  | 2015-12-02 | In Programming | Award package 1 & 3 | 2019-11-01 | 2019-12-01 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) | 20 |  |  | Blythe Wilson | Scott Donnell
CAP.PROG. | 3401 | PD&C | SOM Clinical Skills & Simulation Suite | ORBACH LIB |  | 2017-12-03 | Working on Construction Docs | Project approval & bidding | 2019-12-01 | 2020-09-01 | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | 21 |  |  | Mihai Gavan | Mihai Gavan
CAP.PROG. | 2952 | PD&C | Pierce Hall Interiors | PIERCE |  | 2015-09-11 | In Construction | Completion of phase one 3/15/20 | 2019-01-02 | 2021-06-01 | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | 22 |  |  | Jon Harvey | Dave Bomba
CAP.PROG. | 3395 | PD&C | Recreation Fields Replacement |  |  | 2017-12-03 | Third party cost estimator needed | On Hold |  |  | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. | 23 |  |  | Tameesha Hayes | Daneca Stevens
CAP.PROG. | 3438 | PD&C | Iowa Street Widening |  |  | 2018-08-22 | City to determine schedule | City to determine schedule | 2020-01-01 | 2020-09-01 | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. | 24 |  |  | Dave Bomba | Dave Bomba
CAP.PROG. | 3175 | PD&C | DM16-Chilled Water Coils Multiple Buildings |  |  | 2016-10-11 | In Close-out | Complete Close-out | 2019-01-01 | 2019-08-01 | Replace multiple leaking/degraded cooling coils across campus to prevent complete shutdown of building air handlers during the hot summer months. Buildings include: Student Services, Chemical Sciences, Genomics, Psychology, Entomology and MSE. | 99 |  |  | Melissa Garrety | Scott Donnell
CHANCELLOR | 19P000407 | FS | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | HINDERAKER | 1101 | 2018-12-11 | HOLD - FACILITIES SERVICES |  |  |  | Install a new wall at open space 1101-D to create a private office. |  | 1 |  | ALEXIS RAMBAUD
CHASS | 19P000337 | FS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | PSYCHOLOGY1 | 3210 | 2018-10-11 | IN PROGRESS |  |  |  | Remove whiteboard (in front of room), mount LED mount, add double duplex and electrical power behind LED, patch and paint wall |  | 1 |  | TOYA ADAMS | Dan Lerman
CHASS | 19P000575 | FS | SL5 WATKINS HALL PAINT/FLOORING | WATKINS | 1309A | 2019-04-17 | QUEUE TO START | [5 empty] | 1 |  | PAUL RICHARDSON | Paul Ditty
CHASS | 19P000574 | FS | SL5 FACULTY OFFICE PAINTING | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | 2019-04-12 | QUEUE TO START | [5 empty] | 3 |  | JILL CANTONWINE | Paul Ditty
CHASS | 19P000419 | FS | SL5 CHASS INT SOUTH 2117-CARD ACCESS | CHASS INT S | 2117 | 2018-12-18 | IN PROGRESS |  |  |  | Remove Door and wall leading to 2117 Media Library and reconfigure to allow enterance into 2117 A & J without having to go through 2117C. |  | 2 |  | PAUL RICHARDSON | DAN LERMAN
CHASS | 19P000609 | FS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR | WATKINS | 1229 | 2019-05-10 | IN PROGRESS | [5 empty] | 4 |  | PAUL RICHARDSON | Paul Ditty
CHASS | 19P000448 | FS | SL5 ARTS 333- PATCH AND PAINT | ARTS | 333 | 2019-01-14 | QUEUE TO START | [5 empty] | 8 |  | SONJA SEKELY-ROWLAND | Paul Ditty
CHASS | 19P000608 | FS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE | WATKINS | 1345 | 2019-05-10 | QUEUE TO START | [5 empty] | 9 |  | BECKY CAMPBELL | Paul Ditty
CHASS | 3280 | PD&C | Athletics Dance Bldg Repairs | ATH DANCE |  | 2017-05-31 | On-hold/Funding | Department Approval/Funding |  |  | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | 2 |  |  | Paul Richardson | Fernando Nunez
CHASS | 3535 | PD&C | Watkins 1311 Renovation |  | 1311 | 2019-07-10 | New location LS-452 determined, fume hood installation | Bidding |  |  | This request is for a new faculty hire. -Remove north countertop and sink. Install stainless counter and two sinks. -Install eye wash station -Install laminate flooring, remove existing. (Abatement) -Paint space to campus interior standard. -Remove east counter and replace with stainless. -Remove fume hood, discard. -Install new fume hood. | 3 |  |  | Paul Richardson | Jason Espinoza
CHASS | 3060 | PD&C | CHASS Intl N. - Paint 3rd Floor | CHASS INT N |  | 2016-05-20 | Project on Hold | On Hold |  |  | Paint and patch the following CHASS INTN rooms to existing color: 3036 3038 3042 3046 3050 3049 3047 3033 3033B 3025 3021 3019 3015 3013 3011 3002 3008 3012 3014 3016 3018 3020 3022 Hallway outside of 3033 Hallway to main entrance to floor Hallway outside 3005 | 4 |  |  | Paul Richardson | Fernando Nunez
CHASS | 3469 | PD&C | Carillon Repair & Maintenance | BELLTOWER |  | 2018-08-16 | Need to secure funding | Secure Funding | 2019-09-01 | 2019-09-01 | Design, fabrication and replacement of bell beams for bells 24, 26, 28, 30 and 32. Design, fabrication and installation of bracing to brace the 5 other bells beams that are cracking, and corrective maintenance on the clappers & head pieces-this would include complete removal, cleaning, reaming, bushing and lubricating before re-installing and clean and lubricate the transmission system as much as possible without complete disassembly to make the instrument easier to play. | 5 |  |  | Reasey Heang | Daneca Stevens
CHASS | 3441 | PD&C | CHASS INTS 1121 Exercise Room |  |  | 2018-06-22 | In Funding | Design | 2020-01-01 | 2020-02-01 | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | 15 |  |  | Anna Finn | Daneca Stevens
CHASS | 18P000343 | FS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER | THTR WKSH | 0400A | 2018-03-16 | IN PROGRESS | [5 empty] | 22 |  | PAUL RICHARDSON | Dan Lerman
CHASS | 19P000415 | FS | SL5 PSYCHOLOGY -PSY BLDG- MINOR RENOVATION | PSYCHOLOGY1 | 2124A,B,C,D | 2018-12-17 | IN PROGRESS |  |  |  | Doorway with side window connecting 2124C to 2124B, as well as another doorway to connect 2124C to 2124D. |  | 3 |  | Jay Melashenko | Dan Lerman
CHASS | 19P000421 | FS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | OLMSTED | 2139I | 2018-12-19 | PLAN DEVELOPMENT/CHECK |  |  |  | Install door to access hallway directly |  | 5 | YES | TOYA ADAMS | Dan Lerman
CHASS | 19P000589 | FS | SL5 HMSS OFFICE 3405 RENOVATIONS | HUM & SOC SC | 3405 | 2019-04-23 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE |  |  |  | Construct partion, pending CBO approval, in room 3405. |  | 8 |  | PAUL RICHARDSON | Dan Lerman
CHASS | 19P000540 | FS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | HUM & SOC SC | 1202 | 2019-03-20 | PLAN DEVELOPMENT/CHECK |  |  |  | Remove metal roll up window, replace carpet, remove round column cover-reframe square. |  | 9 |  | JENNIFER MORGAN | Dan Lerman
CNAS | 19P000639 | FS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK | CHEMICAL SCI | 0435 | 2019-05-17 | PLAN DEVELOPMENT/CHECK |  |  |  | Make modifications to accommodate new PI |  | 1 |  | BARBARA OUTZEN | Dan Lerman
CNAS | 18P000453 | FS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | DELFINO HHSE |  | 2018-05-25 | HOLD - FACILITIES SERVICES |  |  |  | FS to coordinate with client to scope the work. |  | 17 |  | MATTHEW ULRICH | Dan Lerman
CNAS | 19P000622 | FS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK | FAWCETT LAB | 204 | 2019-05-15 | IN PROGRESS |  |  |  | Replace doors & frame |  | 2 |  | MATTHEW ULRICH | Dan Lerman
CNAS | 19P000613 | FS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT | COLL BLDG NO | 0203B | 2019-05-14 | QUEUE TO START | [5 empty] | 3 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000539 | FS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | PHYSICS | 1132 | 2019-03-19 | PROJECT INTAKE |  |  |  | Install utilities for new equipment |  | 3 |  | MAYELA CASTILLO | Dan Lerman
CNAS | 19P000508 | FS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | BOYCE | 3410 | 2019-02-21 | PROJECT INTAKE |  |  |  | RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE |  | 4 |  | CHERYL GERRY | Dan Lerman
CNAS | 19P000615 | FS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT | COLL BLDG NO | 203 AND 204 | 2019-05-14 | QUEUE TO START | [5 empty] | 5 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000523 | FS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | SPIETH | 3366 | 2019-03-12 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE |  |  |  | Placed on HOLD by customer until next Quarter (Fall 2019) |  | 9 |  | ESTELLA DAVALOS | Paul Ditty
CNAS | 19P000193 | FS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | GENOMICS | 4231 | 2018-08-20 | PLAN DEVELOPMENT/CHECK |  |  |  | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. |  | 41 |  | AIMEE GONZALES | Dan Lerman
CNAS | 19P000377 | FS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | SCHNEIDER |  | 2018-11-08 | HOLD - FACILITIES SERVICES |  |  |  | Replace the gates on the Schneider House driveway, which secure the property, with the taller iron gates that used to be installed at the Gardens entrance. This will require new fence posts and hinges as well. The taller gates are stored along the side of the garage at Schneider House, and Facilities staff can come see them anytime. Please note this is a safety and security project. |  | R2 |  | AMBER RHEMREV | Dan Lerman
CNAS | 3228 | PD&C | Retrofit Screenhouse to Greenhouse | RUBIDOUX SCR |  | 2016-12-06 | In Design | Bidding | 2019-12-01 | 2020-03-01 | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. Location can be discussed with Greg Greer | 1 |  |  | Cheryl Gerry, D. McWilliams | Scott Donnell
CNAS | 3367 | PD&C | Field 16 Greenhouse Demo & Replacement |  |  | 2017-09-15 | In Construction | Complete Close-out | 2019-01-30 | 2019-08-01 | Replace GH1 and GH2 with a greenhouse from the Greenhouse Megastore. Conduct geotechnical investigation, prepare drawings and conduct asbestos and lead sampling. | 1 |  |  | Sue Lee, D. McWilliams | Dave Bomba
CNAS | 3390 | PD&C | Field 11C-D CVC Screenhouse |  |  | 2018-01-08 | In Design | Bidding | 2019-12-01 | 2020-02-01 | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. | 2 |  |  | Tracey Kahn, D. McWilliams | Scott Donnell
CNAS | 3542 | PD&C | Chapman Rm 9 Fume Hood Install |  | 9 | 2019-08-01 | Funding | Procurement |  |  | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | 3 |  |  | Rick Redak | Scott Donnell
CNAS | 3547 | PD&C | USDA Germplsm Apprvls, Permits |  | First Flr | 2019-05-16 | Plan check & inspection | Plan check & inspection |  |  | The request is to accomplish the necessary UCR-based permit and planning applications, reviews, and approvals, as well as to coordinate requisite utility connections (such as sewer and irrigation) for a Federally-funded renovation project at the USDA Germplasm Facility located on West Campus. | 4 |  |  | MaryLou Polek | Scott Donnell
CNAS | 1990a | PD&C | Natural Reserves-Boyd Deep Canyon |  |  | 2015-10-09 | Under construction | Complete Construction | 2019-05-01 | 2019-11-16 | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. | 99 |  |  | Chris Tracy, D. McWilliams | Rowan Reid
CNAS | 2353 | PD&C | Natural Reserves-Sweeney Granite Mountain |  |  | 2015-11-23 | In construction | Complete Construction | 2019-01-14 | 2019-12-01 | This project will add structurally independent facilities for an administration building and researcher housing to provide meeting/office space and short term sleeping quarters. Additionally, the existing laboratory building and staff residence will be extensively renovated. High priority is focused on high insulation values, high wind resistance, rodent proofing, and pursue as much passive cooling and heating as possible with an eye toward low maintenance and high durability. Both new construction and renovation projects are to be sealed to prevent rodent intrusion. The new structures must withstand the harsh environment of extreme temperatures and very high winds. All site improvements shall be done with minimal disturbance to the desert environment. The overarching goal of the project is to provide a sustainable structure that respects its environment and is low maintenance while using best practice design standards. | 99 |  |  | Jim Andre, D. McWilliams | Rowan Reid
CNAS | 1990b | PD&C | Natural Reserves-Boyd Deep Canyon-Road |  |  | 2018-06-22 | On Hold | Bidding | 2019-11-01 | 2019-12-01 | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. | 99 |  |  | Chris Tracy, D. McWilliams | Rowan Reid
CNAS | 19P000547 | FS | SL5 SPIETH HALL 1363-RENOVATION | SPIETH | 1363 | 2019-03-26 | Project Intake |  |  |  | Make minor lab improvements for new PI |  | R3 | YES | ESTELLA DAVALOS | DAN LERMAN
CNAS | 19P000555 | FS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK | SAT CHIL PL | 0 | 2019-04-03 | IN PROGRESS |  |  |  | INSTALL OF FENCE FOR RAIN COLLECTOR AT TES TANK |  | R4 |  | AMBER RHEMREV | DAN LERMAN
CNAS | 19P000474 | FS | SL5 HEADHOUSE 8-AC INSTALLATION | GREENHOUSE #8 | 881 | 2019-01-29 | Project Intake |  |  |  | HEADHOUSE 8 REQUEST FOR AC INSTALLATION |  | R5 |  | NANCY FERGUSON | DAN LERMAN
CNAS | 19P000504 | FS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH | 2349 | 2019-02-20 | Project Intake |  |  |  | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB |  | R6 |  | ESTELLA DAVALOS | DAN LERMAN
CNAS | 19P000514 | FS | SL5 SKYE 268-PROJECTOR INSTALL | SKYE HALL | 0268 | 2019-02-27 | QUEUE TO START |  |  |  | Instal projector and relocate screen. |  | R7 |  | JAMES MARBERRY | DAN LERMAN
CNAS | 19P000543 | FS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION | CHEMICAL SCI | 342 | 2019-03-21 | PROJECT INTAKE |  |  |  | TV Bracket &Power/Network box. |  | R8 |  | JEFFERY MATUTE | DAN LERMAN
CNAS | 19P000594 | FS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS | ENTOMOLOGY | 171 | 2019-04-26 | Project Intake |  |  |  | Take down a dividing wall in this office and move the desks to their old location and rehang the overhead desk bins back into their old locations with inserts still in the walls. |  | R9 |  | WILLIAM SUTTON | DAN LERMAN
FAC-PLNG-DESIGN-CONST | 19P000467 | FS | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | WATKINS | 2101 | 2019-01-22 | HOLD - FACILITIES SERVICES |  |  |  | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM |  | 1 |  | Monty Anderson | Dan Lerman
FAC-PLNG-DESIGN-CONST | 19P000466 | FS | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | SPROUL | 2225 | 2019-01-22 | HOLD - FACILITIES SERVICES |  |  |  | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM |  | 1 |  | Monty Anderson | Dan Lerman
FAC-PLNG-DESIGN-CONST | 3498 | PD&C | DM(FY18) Manhole C6 Modification |  |  | 2019-02-25 | In Construction | Complete Construction | 2019-08-01 | 2019-09-01 | Construct new sanitary sewer lines, New manhole, pipe connections, demo existing manhole. | 2 |  |  | Ron Rector | Gerald Caraig
FAC-PLNG-DESIGN-CONST | 3527 | PD&C | Central Utility Plant Fire Alarm |  |  | 2019-05-08 | In Construction | Complete Project | 2019-07-01 | 2020-03-01 | Replace aging and non-replaceable fire alarm system, and conduit. Conduit is damaged and only 10% of wiring is usable. ( fire alarm system and devices are failing and they are not supported by manufacture ) -Run new conduit from propane tanks to fire alarm system -Install new terminal box at propane tanks. -Pull twenty two, 14 awg THHN wires in new conduit and terminate in junction box. -Replace 25 year old fire alarm panel, parts are not available to maintain system. -Add ada compliant horn/strobes thru out structure. -Add code compliant indicating devices thru out structure. -Replace 8 flame detectors -Replace all fire sprinkler devices on riser. -Flow switch. -Pressure switches. -Tamper switches. -Replace high capacity sounder at propane tanks. -Engineering, and drawings to be submitted to fire marshal for approval. | 4 |  |  | Ben Kochevar | Scott Donnell
FAC-PLNG-DESIGN-CONST | 3528 | PD&C | Entomology Museum Fire Alarm |  |  | 2019-05-14 | In Construction | Complete Project | 2019-07-01 | 2019-12-01 | Deferred Maintenance Project. Fire alarm system and devices are failing and they are not supported by manufacture. -Replace fire alarm system and all existing fire alarm peripheral devices. -Engineering, and drawings to be submitted to fire marshal for approval. | 5 |  |  | Ben Kochevar | Scott Donnell
FAC-PLNG-DESIGN-CONST | 3529 | PD&C | (DMFI) Physics 2000 Renewal |  |  | 2019-05-15 | In Construction | Complete Construction | 2019-07-01 | 2019-09-01 | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | 6 |  |  | Scott Donnell | Scott Donnell
FAC-PLNG-DESIGN-CONST | 2687 | PD&C | DM(FY14) Bourns Fire Alarm Sys Replcmt | BOURNS |  | 2019-06-18 | In Design | Receive revised 100% Specs | 2019-12-02 | 2020-05-29 | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | 7 |  |  | ----- | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3476 | PD&C | DM(FY17-19) Tunnel System Plumbing |  |  | 2018-10-17 | Pre-Programming | FS Direction |  |  | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. | 8 |  |  | Mihai Gavan | Mihai Gavan
FAC-PLNG-DESIGN-CONST | 3275 | PD&C | DM-Fiber Optic Infrastructure Upgrade |  |  | 2017-04-12 | Bidding | Award Contract | 2019-11-01 | 2020-04-01 | Repair, replace and upgrade the fiber optic infrastructure network that includes 50+ buildings across campus. Also includes work to main hubs, sub hubs and make available spare fiber for future utilization. | 9 |  |  | ----- | Daneca Stevens
FAC-PLNG-DESIGN-CONST | 3437 | PD&C | UCPD Generator Replacement |  |  | 2018-10-08 | In Construction | Complete Construction | 2019-07-01 | 2019-12-27 | Replace unsupported 125kw generator with new - Critical Facility | 10 |  |  | Ron Rector | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3035a | PD&C | DM(FY15) Roofing - Spieth Hall/LSP |  |  | 2016-02-25 | In design | Bidding | 2019-12-01 | 2020-01-01 | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | 10 |  |  | John White | Scott Donnell
FAC-PLNG-DESIGN-CONST | 3270 | PD&C | DM(FY16) Chapman Hall - Replace HVAC System | CHAPMAN |  | 2017-03-07 | In Close-out | Complete Close-out |  |  | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | 11 |  |  | Fernando Nunez | Scott Donnell
FAC-PLNG-DESIGN-CONST | 3271 | PD&C | DM(FY16) Life Sci/Spieth Hall Elevator Renewal |  |  | 2017-03-07 | Bidding | Award Contract | 2019-10-21 | 2020-08-28 | Scope of work includes the number 3 and 4 elevators of Spieth Hall. Project budget is $344,898.00. Estimated construction cost is $250,400.00. | 12 |  |  | Scott Donnell | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3272 | PD&C | DM(FY16) Athletic/Dance Elevator Renewal | ATH DANCE |  | 2017-03-07 | Bidding | Award Contract | 2019-10-21 | 2020-08-28 | Project budget is $219,371.00. Estimated construction cost is $169,020.00. | 13 |  |  | Scott Donnell | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3064 | PD&C | DM(FY16) Botanic Gardens Basin Silt Removal | BOTAN INFO C |  | 2016-04-20 | On hold | Funding |  |  | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | 41 |  |  | Toshio Ishida | Scott Donnell
FAC-PLNG-DESIGN-CONST | 2682 | PD&C | DM(FY14) Rivera Library Arches/Arcade Repair |  |  | 2016-05-06 | Bids received, award on hold due to DM funding | Funding |  |  | Paint and replace roof. | 99 |  |  | Susan Marshburn | Jason Espinoza
FAC-PLNG-DESIGN-CONST | 2671 | PD&C | DM(FY14) Elevator Mods-Various Bldgs |  |  | 2016-01-05 | Bidding | Award Contract | 2019-10-21 | 2020-08-28 | Provide Vertical Transportation Consulting, Mechanical, Electrical, Fire Alarm and Architectural/Structural Construction document design and specifications for the modernization of two (2) elevators at Webber and Watkins buildings which is included in the base design and one (1) elevator at the Entomology Museum is included as an add alternate. | 99 |  |  | Scott Donnell | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 2805 | PD&C | West Campus Water Well |  |  |  | On Hold | CEQA |  |  | Drill a water well on AGOPS property. This will be funded out of Energy Savings and Minor Cap Approval has been signed. | 99 |  |  | Ken Muelleer | Scott Donnell
GRADUATE DIVISION | 19P000572 | FS | SL5 PATCH, PAINT, AND CARPET UOB 152 | UNIV OFC BLD | 152 | 2019-04-11 | IN PROGRESS | [5 empty] | 1 |  | CYNTHIA CARDENAS | Paul Ditty
GSOE | 19P000628 | FS | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE | SPROUL | 2129 | 2019-05-15 | QUEUE TO START | [5 empty] | 1 |  | SALLY TAVIZON | Paul Ditty
GSOE | 19P000627 | FS | SL5 SPROUL HALL, RM 2120 - PATCH/PAINT FACULTY OFFICE | SPROUL | 2120 | 2019-05-15 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | [5 empty] | 2 |  | SALLY TAVIZON | Paul Ditty
ITS | 19P000433 | FS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | COMPUTING | 161 | 2019-01-07 | PLAN DEVELOPMENT/CHECK |  |  |  | Install complet card reader system for 4- doors |  | R1 |  | SHEILA MABEE | DAN LERMAN
ITS | 3396 | PD&C | C&C Rear Patio Tables/Shade | ITS CENTER |  | 2017-11-16 | In Programming | Complete Project Study |  |  | Installation of new exterior concrete slab and patio cover at the Computing and Communications Modular Buildings. The existing site will be cleared of all landscape to provide clear area to install concrete slab and address any grade/drainage issues. The addition of a proposed permanent patio cover is to be installed with full electrical options (lights, outlets, ceiling fans) to provide shade for future events and exterior lunch area. Shrubs along the street at the East side of the area are to be removed to provide a vendor/service ramp for events with the inclusion of lighted concrete seating within the space. | 99 |  |  | Sheila Mabee | Fernando Nunez
LIBR | 3481 | PD&C | Riv/Orb Libraries Fire Suppression-Estimate |  |  | 2018-11-27 | Client approval/funding | Client approval/funding |  |  | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. | 1 |  |  | David Schuster | John Franklin
LIBR | 3413 | PD&C | Rivera Libr Gender Incl Restroom | RIVERA LIB |  | 2018-03-26 | On Hold | Funding Design |  |  | Convert existing non-ADA multi-stall women's restroom to compliant ADA gender inclusive restroom. The project also involves the conversion of an existing non-ADA men's restroom to women's compliant ADA restroom. | 3 |  |  | David Schuster | Dave Bomba
PALM DESERT GRAD CTR | 3104 | PD&C | Palm Desert Campus Access Evaluation | HECKMANN PH2 |  | 2016-05-12 | In Programming | Funding |  |  | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | 1 |  |  | Zelda Glenn | Scott Donnell
PALM DESERT GRAD CTR | 2747 | PD&C | Heckmann Ctr-Landscaping (Donor Orchard) | HECKMAN ICEM |  | 2014-08-18 | In Programming | Design |  |  | UCR Palm Desert would like to replace the current turf grass with water-wise, sustainable landscaping. In return for the opportunity to use a “living laboratory” classroom for training, UC Cooperative Extension Master Gardener program has agreed to collaborate with UCR to revise and sustain the landscaping. The first phase will be to create an orchard to highlight UCR’s contributions to agricultural research in the Coachella Valley. The orchard will be located at the entrance to the Heckmann building, north of the walkway. UCR Physical Plant/Grounds to provide estimate for: • Project oversight • Project plan and drawings • Organic material to add to soil • Irrigation materials and installation • Edging for path • Weed cloth • Decomposed granite with stabilizer for ground cover • Decomposed granite with stabilizer for pathway • Concrete pad for art including bolting apparatus • Arbor for grapes • Flow system-fertigation • All other labor and materials other than kiosk, plant signage, turf and tree removal (current landscape maintenance vendor can remove) and plant materials and plant installation | 2 |  |  | Mike Lawrence | Scott Donnell
PLANNING & BUDGET | 19P000414 | FS | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | POLICE BLDG | 100 | 2018-12-17 | PLAN DEVELOPMENT/CHECK |  |  |  | Install new exhaust fans in both shower rooms |  | 1 |  | KELLY DUNCAN | Dan Lerman
PLANNING & BUDGET | 19P000665 | FS | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | TELEPHONE |  | 2019-07-03 | IN PROGRESS |  |  |  | Existing telephone-communications building on University Ave requires repairs and renovation in preparation for new use as fire safety offices. |  | 2 |  | Carmen Long | Dan Lerman
PLANNING & BUDGET | 3516 | PD&C | Student Health & Counseling Center (SHCC) |  |  | 2019-03-04 | In Programming | Workgroups | 2021-01-04 | 2022-06-01 | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. | 1 |  |  | Michelle Baniqued | Gerald Caraig
PLANNING & BUDGET | 3520 | PD&C | College Building South Seismic Improvements |  |  | 2019-04-02 | On-hold pending UCOP decision | On-hold pending UCOP decision |  |  | Full building seismic retrofit to College Building South. | 2 |  |  | Michelle Baniqued | Jason Espinoza
PLANNING & BUDGET | 3515 | PD&C | DM(FY18) Elec Substation & Infra. Renewal |  |  | 2019-03-08 | In Programming | Field Data Gathering |  |  |  | 3 |  |  | Ron Rector | J.Franklin/G.Caraig
PLANNING & BUDGET | 3521 | PD&C | Life Sci Unit 2 Seismic Improvements |  |  | 2019-04-02 | On-hold pending UCOP decision | On-hold pending UCOP decision |  |  | Full building seismic retrofit of Life Sciences Unit 2. | 3 |  |  | Michelle Baniqued | Jason Espinoza
PLANNING & BUDGET | 3523 | PD&C | 1907 Mt Rubidoux Facility Study |  |  | 2019-04-22 | Study in Progress | Complete Study | 2019-06-01 | 2019-10-01 | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. | 5 |  |  | Melissa Garrety | Scott Donnell
PLANNING & BUDGET | 3504 | PD&C | Silver Oaks Womens Health TI Fees |  |  | 2019-02-14 | SOM to manage project | SOM to manage project |  |  | UCR Health will be acquiring new off-campus leased space by expanding into an adjacent medical office suite located at 19330 Jesse Ln #160, Riverside, CA 92508. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. | 7 |  |  | Brandon Barbosa | Brandon Barbosa
PLANNING & BUDGET | 3510 | PD&C | SOMED Data Center Study |  |  | 2019-03-04 | Programming | Complete Study |  |  | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | 8 |  |  | Daneca Stevens | Daneca Stevens
PLANNING & BUDGET | 3501 | PD&C | DMFI(17-19) Watkins 1000 Lecture Hall Reno |  |  | 2019-03-04 | In Bidding | Award Contract |  |  | Renovation of Watkins 1000 lecture hall, to include lighting, HVAC, flooring, paint, and seating upgrades. This requests appears as projects Q-T on the approved 2017-2019 DMFI Program list. | 9 |  |  | Scott Donnell | Scott Donnell
PLANNING & BUDGET | 3508 | PD&C | SOM New Academic Facility |  |  | 2019-03-04 | Programming | Bidding | 2021-03-01 | 2023-02-01 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. | 10 |  |  | Melissa Garrety | Mihai Gavan
PLANNING & BUDGET | 3507 | PD&C | Undergrad Class Labs & Studios Teaching Facility |  |  | 2019-03-04 | Pre-programming | Programming | 2021-03-01 | 2023-01-01 |  | 11 |  |  | Michelle Baniqued | Blythe Wilson
PLANNING & BUDGET | 3492 | PD&C | W.Campus Irrigation System Study |  |  | 2019-03-04 | Study in process | Complete Study |  |  | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. | 12 |  |  | Scott Donnell | Scott Donnell
PLANNING & BUDGET | 3499 | PD&C | Creekside Terrace Analysis |  |  | 2019-02-14 | In Design | CEQA |  |  | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. | 13 |  |  | Blythe Wilson | Dave Bomba
PLANNING & BUDGET | 3505 | PD&C | Orange County Psychiatry |  |  | 2019-02-19 | SOM to manage project | SOM to manage project |  |  | UCR Health will be acquiring new off-campus leased space by moving into an adjacent medical office suite located at The Airport Tower, 18881 Von Karman Ave #1227, Irvine, CA 92612. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. | 14 |  |  | Brandon Barbosa | Brandon Barbosa
PLANNING & BUDGET | 3474 | PD&C | RUSD STEM High School |  |  | 2018-10-31 | Real Estate project | Regents Approval of Ground Lease | 2020-07-01 | 2022-06-01 |  | 17 |  |  | ----- | Thomas Toepfer
PLANNING & BUDGET | 2900 | PD&C | Batchelor Hall Systems Renewal | BATCHELOR |  | 2015-12-15 | In Design | Contractor Review of Building | 2020-01-01 | 2021-11-01 | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | 18 |  |  | Sharyl Murdock | Rowan Reid
PLANNING & BUDGET | 2839 | PD&C | Multidisciplinary Research Building |  |  | 2015-04-01 | Coordinating 2nd Phase Move-in & Related TI's | 2nd Phse Move/TI | 2016-07-01 | 2018-09-28 | External financing provided for this project. Total approved budget is $150,000,000. Confirmed per CPMX and BEA#978864 Xfer Tax Exemp Comm Paper. Funding received 7/25/2016. | 19 |  |  | Jon Harvey | Mihai Gavan
PLANNING & BUDGET | 2899 | PD&C | Pierce Hall Improvements | PIERCE |  | 2015-08-06 | In Construction | Phase I Completion | 2019-01-01 | 2020-02-01 | Replacement of Mechanical, Plumbing and Electrical Infrastructure | 21 |  |  | Jon Harvey | Dave Bomba
PLANNING & BUDGET | 2368 | PD&C | Creekside Drainage Channel |  |  | 2016-05-19 | In Programming | Design |  |  | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. | 22 |  |  | Katie Sanchez | Gerald Caraig
PLANNING & BUDGET | 3470 | PD&C | 2018 Campus Seismic Audit |  |  | 2018-11-06 | New Study | Complete Review |  |  | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. | 23 |  |  | Drew Hecht | Drew Hecht
PLANNING & BUDGET | 3110 | PD&C | Ag Ops Cell Tower - New |  |  |  | Project is not funded/never routed to the Dispatcher. 90% CD's completed. | License Agreement Final Review | 2019-09-01 | 2020-07-01 | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. | 99 |  |  | Marianne Valenti | Yvonne Lujan
PLANNING & BUDGET | 2774 | PD&C | Highlander Hall Demolition |  |  | 2015-01-22 | Complete Construction | Complete Construction | 2018-08-01 | 2019-09-01 | Demolition of the Highlander Hall Building | 99 |  |  | Blythe Wilson | Scott Donnell
PLANNING & BUDGET | 3195 | PD&C | North District Pre-Development Study |  |  | 2016-10-26 | In Construction | Complete Construction | 2019-07-01 | 2021-08-01 | Development of UCR North District Development, located near the housing development north of Linden St. | 99 |  |  | Raoula Amescua | Drew Hecht
PROVOST/EVC | 19P000473 | FS | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 | HINDERAKER | 1100 | 2019-01-29 | QUEUE TO START | [5 empty] | 1 |  | THERESA WAGNER | Paul Ditty
SoB | 2725 | PD&C | School of Business Professional Schools Study |  |  | 2016-12-15 | Basis of technical design | Design Development | 2021-01-01 | 2022-10-01 | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. | 1 |  |  | Leo Gonzalez | Jason Espinoza
SoB | 3415 | PD&C | Anderson South Renovation | ANDERSON 2 (S) |  | 2018-02-26 | Funding | Department funding | 2019-10-01 | 2019-10-30 | Per the sketched drawings that Dave Bomba was provided, please provide a proposal of what it would take to renovate Anderson South as follows: **1. Remove 1st Fl South side of Corridor wall and doors between 102 suite entrance and 106 suite entrance as well as adjoining walls within 102C. **2. Create a closet/wall, ideally, behind the existing door of the 102 Entrance running to the wall shared by 102A to include the best location for a door. Essentially, enclosing the window of 102, if possible. **3. Creating a closet under the stairwell between 1st floor and basement level, having entrance door flush with the bottom step of the stairwell. **4. Remove the West wall and door framing of room 001A, leaving an open look and no corridor in suite 001. | 2 |  |  | Laurie Gustafson | Dave Bomba
SoB | 3237 | PD&C | Anderson Hall N. Access Imp. | ANDERSON 1 (N) |  | 2016-12-19 | In design | Re-bid | 2020-01-01 | 2020-01-01 | ADA handrails installation at walkway and ramp on the East sidewalk by the bench of Anderson north, down the steep ramp leading to Anderson South. We have been working with Shelly Frohrip from HR and Mary-Alice Avila of A&E on this so they will have some information regarding the purpose. 11/15/17 The handicapped parking and POT are now included. Project approved, waiting for funding. | 3 |  |  | Angela Chang | Scott Donnell
SoB | 3345 | PD&C | Anderson N & S - Landscaping |  |  | 2017-07-18 | On hold until ADA path of travel is completed | Completion of 3237 |  |  | DESIGN SVC & LANDSCAPE Construction request as follows for updated CURB APPEAL of Anderson North/South: 1. Roses Garden in middle of Stair landing/court to be removed and replaced with Grass 2. Add Large Planters (Metal or Cement) with Citrus Trees (either Kumquat/Lemon/Orange/Etc) on ledges that are at top section of front steps to deter skateboarders from jumping off of these ledges. 3. Remove dead trees on North and south ends of front lawn 4. Remove plants around granite sign in front lawn and replace with grass 5. Remove flowers and grass at both corners of front lawn around Citrus Trees and replace with DG and low growing flowering plants. 6. Pull all Ivy and crown vetch and add Pavers to East/Back side of Anderson Hall within landscaped/planter areas where ADA walkway runs and replace with nice picnic tables to include umbrellas and/or lounge seating around Anderson North for students. 7. Add DG in all areas where space is open/available surrounding outdoor seating area in back of building. 7. Remove all hedges surrounding alcove/arched areas along buildings. | 4 |  |  | Angela Chang | Dave Bomba
SOM | 3052 | PD&C | SOM Trailer Expansion |  |  | 2016-03-07 | Completing Change Orders | Complete Change Orders | 2017-08-01 | 2018-02-01 | Replace the (2) modular units with one 96' x 60' building and provide access from the SOM-ED building via concrete ramp; Re-vamp the entire site for accessibility. Signed Major Cap Approval for $150k augmentation received 10/25/17 - total project $2,250,000. | 99 |  |  | Sharyl Murdock | Scott Donnell
VC-RED | 19P000225 | FS | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | UV BLDG A | 0204A | 2018-08-28 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE |  |  |  | FS to coordinate with client to scope the work. |  | 3 |  | CRYSTAL JIMENEZ | Dan Lerman
VC-RED | 3326 | PD&C | Genomics 1120A - Power & UPS | GENOMICS |  | 2017-06-13 | On-hold | Secure Funding |  |  | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | 1 |  |  | T.Girke, L.Manor, D.McWilliams | Daneca Stevens
VC-STU.AFF. | 18P000214 | FS | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | HEALTH SERV |  | 2017-12-08 | HOLD - FACILITIES SERVICES | [7 empty] | GLORIA VERA | Dan Lerman
VC-STU.AFF. | 18P000198 | FS | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | HUB | 0 | 2017-11-21 | PLAN DEVELOPMENT/CHECK |  |  |  | Install new Wall lights |  | 1 |  | BRENDAN OBRIEN | Dan Lerman
VC-STU.AFF. | 19P000455 | FS | SL5 FILL AND PAINT OVER HOLES ON WALL | HEALTH SERV | 100 | 2019-01-17 | QUEUE TO START | [5 empty] | 1 |  | PAMELA BOCKSTADTER | Paul Ditty
VC-STU.AFF. | 19P000534 | FS | SL5 PATCH WALLS AND PAINT | HEALTH SERV | 334 | 2019-03-15 | QUEUE TO START | [5 empty] | 2 |  | PAMELA BOCKSTADTER | Paul Ditty
VC-STU.AFF. | 19P000483 | FS | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED | HEALTH SERV | 404, 407, 412, 405 & 411 | 2019-02-01 | QUEUE TO START | [5 empty] | 3 |  | GLORIA VERA | Paul Ditty
VC-STU.AFF. | 3471 | PD&C | HUB Electrical Sub-Meter Study | HUB |  | 2018-08-20 | Circuit Tracing of the designated spaces | Design | 2020-01-01 | 2020-04-01 | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | 1 |  |  | Brendan O'Brien | J.Espinoza/G.Caraig
VC-STU.AFF. | 3486 | PD&C | HUB 353/381, Costo 111 Add'l Wall/Doorway | HUB |  | 2018-11-26 | On-hold | Approval/Funding |  |  | Please evaluate additional wall/door way requests for HUB 353/381 and Costo Hall 111. | 2 |  |  | Brendan O'Brien | Daneca Stevens
VC-STU.AFF. | 3385 | PD&C | SRC North Gym Replace Interior Lights | SRC NORTH |  | 2017-10-31 | In Construction | Complete Construction | 2019-06-24 | 2019-08-30 | Replace old technology sodium vapor light fixtures in SRC North Gymnasium with new technology LED light fixtures. Some flexibility available in the schedule. Selected vendor will need to phase work to minimize the effect on SRC operations and programming. | 3 |  |  | Lindy Fenex | Fernando Nunez
VC-STU.AFF. | 3512 | PD&C | Hinderaker VCSA Office |  | 2108ACDEF | 2019-03-19 | Programming | Design | 2020-07-01 | 2020-10-01 | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | 5 |  |  | Christina Wong | Daneca Stevens
VC-STU.AFF. | 2829 | PD&C | SRC South - New Storage Building | SRC SOUTH |  | 2015-01-23 | Coordinate with MRB Logistics | Coordinate with MRB Logistics |  |  | New storage building immediately south of SRC South Pool Building; approximately 20' x 40'; one roll up door and one standard door; electrical power required - number of outlets to be defined in design; concrete walkway and door pads required; non-potable water may be required if quick couplers are not available in nearby landscaping; please see attachment for location: approximately at gridlines T and 9.4 - dotted outline of building is labeled "FUTURE STORAGE" - located immediately south of the SRC POOL EQUIPMENT BUILDING. | 6 |  |  | Lindy Fenex | Mihai Gavan
VC-STU.AFF. | 3534 | PD&C | SRC North Cooling Towers Replcmt |  |  | 2019-06-06 | In funding | Secure Funding | 2019-12-01 | 2020-01-01 | Replacement of the 2 Cooling towers in the Student Recreation Center North. The towers are 25 plus years old and in needed of replacement to keep the HVAC system running efficiently. | 8 |  |  | Michael Eason | John Franklin
VC-STU.AFF. | 3524 | PD&C | Stdnt Srvs Bldg 1st Floor Reno |  |  | 2019-04-16 | Programming | Design |  |  | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | 9 |  |  | Laura Riley | Daneca Stevens
VC-UNIV.ADV. | 19P000564 | FS | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | HINDERAKER | 1156 | 2019-04-08 | QUEUE TO START |  |  |  | 1156C (AVC Johnny Cruz) – Patch molly holes, touch-up paint. 1156A (Jules Bernstein) – Remove (2) black & white photos from wall. Patch molly holes, touch-up paint. 1156B – Install picture frame (UCR campus map) onto wall. Suite 1159 – Patch holes. Remove film reels. Paint one accent wall “UCR Blue”. 1159B (Christy Zwicke) - Patch molly holes, touch-up paint. |  | 1 |  | Lisa Cusick | Paul Ditty
VC-UNIV.ADV. | 2245 | PD&C | Campus Directory & Blade Signs |  |  | 2014-03-27 | Pending funding source approval | Project Approval & Funding |  |  | Remove and replace campus directories at strategic locations throughout the campus. | 99 |  |  | Margene Mastin-Schepps | Fernando Nunez
To view projects for a specific organization ONLY, click on the filter options HERE.

## Project Detail
Project Status Report | [5 empty] | Last Updated | 2019-09-01
PD&C
SOM Trailer Expansion
Project Reference No. | 3052
PD&C
Financials
Project Manager | Scott Donnell | Organization | SOM | Prioritization Designate | Brandon Barbosa | PD&C Approved Budget | 2250000
Contact/ Requestor | Sharyl Murdock | Building |  | Project Service Unit | PD&C | FS Recharge Actuals To Date
CPMS # | 3052 | Room |  | PD&C Org Priority No. | 99 | Core / Non-Core | #N/A
FS # |  | Request Date | 2016-03-07 | FS Org Priority No.
For Faculty Hire
Project Description | Replace the (2) modular units with one 96' x 60' building and provide access from the SOM-ED building via concrete ramp; Re-vamp the entire site for accessibility. Signed Major Cap Approval for $150k augmentation received 10/25/17 - total project $2,250,000.
PD&C
Project Status
Project Status | Completing Change Orders |  |  |  | START Date |  | 2017-08-01
Next Steps | Complete Change Orders |  |  |  | COMPLETION Date |  | 2018-02-01
IRT Status
PD&C
Campus Impact (i.e. excessive noise / limited access / utility shutdown)
Description
Impact Start
Impact End
PD&C
PM Notes |  | Project Manager | Scott Donnell | PM Email | scott.donnell@ucr.edu | PM Phone | 951-827-4706
PD&C
BZM Scope |  | Reviewer |  | BZM Email |  | BZM Phone
Scope Completed
To view more detailed information for a specific project, type in the Project Reference No. or clear the field and then scroll through the dropdown list HERE.

## FS Closed Projects
(CLOSED) FS Project Summary Report | [7 empty] | **Closed FS Projects include projects that have been Completed, Canceled by FS, Canceled by Client and projects in IRT Review.
Total Closed FS Projects |  | 279
Last Updated | 2019-09-01 | Project Summary
Organization | Project Ref No. | Project Service Unit | Project Title | Building | Room | Request Date | Current Status | Completed Date | Fiscal Year | FS Org Priority No. | For New Faculty Hire? | Contact | Proj Manager
ATHLETICS | 18P000346 | FS | SL5 ATHLETICS INSTALL WALL VOLLEYBALL OFFICES | ATH DANCE |  | 2018-03-18 | COMPLETE | 2018-11-08 | FY 18-19 |  |  | JOHNATHAN JENSEN | Dan Lerman
ATHLETICS | 18P000484 | FS | SL5 INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | SOFTBALL STG |  | 2018-06-26 | TO BE PERFORMED BY PD&C | 2019-02-01 |  |  |  | JOSEPH ERBLAND | Dan Lerman
ATHLETICS | 18P000328 | FS | SL5 HINDERAKER BASEMENT OFFICE REPAIR | HINDERAKER |  | 2018-03-01 | COMPLETE | 2018-07-11 | FY 18-19 |  |  | JOHNATHAN JENSEN | Dan Lerman
ATHLETICS | 19P000027 | FS | SL5 ATHLETICS PATCH & PAINT ROOM | ATH DANCE | 0120C | 2018-07-16 | COMPLETE | 2018-09-19 | FY 18-19 |  |  | JOSEPH ERBLAND | Dan Lerman
ATHLETICS | 19P000265 | FS | SL5 ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 | ATH DANCE |  | 2018-09-11 | COMPLETE | 2019-01-11 | FY 18-19 | 1 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 19P000271 | FS | SL5 ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 | ATH DANCE | 3 | 2018-09-12 | COMPLETE | 2019-05-07 | FY 18-19 | 11 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 19P000295 | FS | SL5 PATCH & PAINT | ATH DANCE | 50B | 2018-09-12 | COMPLETE | 2019-01-11 | FY 18-19 | 12 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 19P000272 | FS | SL5 NEED URINAL DIVIDERS | ATH DANCE | 50E | 2018-09-12 | CANCELED BY FS | 2019-01-24 |  | 13 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000270 | FS | SL5 ATH DANCE-WEIGHT ROOM DROP DOWN CEILING | ATH DANCE | 78 | 2018-09-12 | COMPLETE | 2019-02-14 | FY 18-19 | 14 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000274 | FS | SL5 RIV SPORTS CPX - REPLACE URINALS | RIV SPORTS CPX |  | 2018-09-12 | CANCELED BY FS | 2019-01-24 |  | 15 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000276 | FS | SL5 TRACK BLEACH-PUBLIC RESTROOMS UPGRADE | TRACK BLEACH |  | 2018-09-12 | TO BE PERFORMED BY PD&C | 2018-11-20 |  | 16 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000266 | FS | SL5 ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | ATH DANCE |  | 2018-09-11 | CANCELED BY FS | 2018-12-13 |  | 2 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 19P000647 | FS | SL5 ATHLETICS AND DANCE, BASEMENT- LOCKER ROOM REFRESH | ATH DANCE | Men's & Women's Locker Rooms | 2019-05-23 | CANCELED BY FS | 2019-06-19 |  | 2 |  | JOSEPH ERBLAND | Dan Lerman
ATHLETICS | 19P000252 | FS | SL5 ATH DANCE SHOWER DOORS | ATH DANCE | 0050K | 2018-09-10 | COMPLETE | 2019-05-31 | FY 18-19 | 3 |  | JOSEPH ERBLAND | Dan Lerman
ATHLETICS | 19P000268 | FS | SL5 ATH DANCE - PATCH AND PAINT 20C | ATH DANCE | 20C | 2018-09-11 | COMPLETE | 2019-05-07 | FY 18-19 | 4 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 19P000269 | FS | SL5 ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | ATH DANCE |  | 2018-09-12 | CANCELED BY FS | 2018-10-04 |  | 5 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000275 | FS | SL5 SOFTBALL STG PRESS BOX AC ADDITION | SOFTBALL STG |  | 2018-09-12 | CANCELED BY CLIENT | 2019-02-14 |  | 6 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000273 | FS | SL5 ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS | ATH DANCE |  | 2018-09-12 | COMPLETE | 2019-05-07 | FY 18-19 | 9 |  | JOHNATHAN JENSEN | Paul Ditty
BAS | 18W009630 | FS | SL5 BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | PHYS PL STOR | 100 | 2018-01-22 | CANCELED BY CLIENT | 2019-03-28 |  |  |  | JUDY HODGE | Dan Lerman
BAS | 18P000094 | FS | SL5 OBAN LAUNDRY ROOM RENOVATION | OBAN OFFICE | 100 | 2017-09-08 | TO BE PERFORMED BY PD&C | 2019-01-19 |  |  |  | EDWIN MELGAR-MEJIA | Enrico Baez
BAS | 18P000369 | FS | SL5 BOYCE X-RAY IRRADIATOR PROJECT | BOYCE | 1407 | 2018-03-27 | CANCELED BY CLIENT | 2018-12-14 |  |  |  | KAREN JANIGA | Dan Lerman
BAS | 18P000282 | FS | SL5 EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 | POLICE BLDG |  | 2018-01-25 | COMPLETE | 2018-08-10 | FY 18-19 |  |  | LISA MARTIN | Dan Lerman
BAS | 18W011772 | FS | SL5 PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | PRINT MOD |  | 2018-03-12 | CANCELED BY CLIENT | 2018-07-03 |  |  |  | PRISCILLA MARTIN | Dan Lerman
BAS | 18P000373 | FS | SL5 POLICE BLDG PAINTING IN DISPATCH AREA | POLICE BLDG | 100 | 2018-04-02 | COMPLETE | 2018-07-14 | FY 18-19 |  |  | KELLY DUNCAN | Paul Ditty
BAS | 18P000459 | FS | SL5 BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 | THE BARN |  | 2018-05-31 | COMPLETE | 2018-09-21 | FY 18-19 |  |  | GUSTAVO PLASCENCIA | Dan Lerman
BAS | 18P000432 | FS | SL5 BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 | BANNOCK H | H0101 | 2018-05-04 | COMPLETE | 2018-07-13 | FY 18-19 |  |  | EDWIN MELGAR-MEJIA | Paul Ditty
BAS | 19P000208 | FS | SL5 PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | THE PLAZA |  | 2018-08-14 | CANCELED BY CLIENT | 2018-09-17 |  |  |  | CARLA CHAPPLE | Dan Lerman
BAS | 19P000247 | FS | SL5 LOTHIAN FIRST FLOOR COMMON AREA FLOORING | LOTHIAN HALL |  | 2018-09-10 | COMPLETE | 2018-10-22 | FY 18-19 |  |  | RICHARD GEIGER | Jess Hernandez
BAS | 19P000222 | FS | SL5 PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER | PRINT MOD |  | 2018-10-02 | COMPLETE | 2018-10-01 | FY 18-19 |  |  | RICHARD GEIGER | Paul Ditty
BAS | 19P000317 | FS | SL5 HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 | PENTLAND A |  | 2018-10-03 | CANCELED BY FS | 2019-01-14 |  |  |  | RICHARD GEIGER
BAS | 18P000106 | FS | SL5 HOUSING PROJECT - OBAN REC ROOM REMODEL | OBAN OFFICE | 100 | 2017-09-14 | TO BE PERFORMED BY PD&C | 2019-01-19 |  |  |  | EDWIN MELGAR-MEJIA | Enrico Baez
BAS | 19P000192 | FS | SL5 MAIL-PAINTING | MAIL |  | 2018-08-20 | COMPLETE | 2018-11-08 | FY 18-19 | 10 |  | PRISCILLA MARTIN | Paul Ditty
BAS | 19P000236 | FS | SL5 EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION | ABER INVER | A0100 | 2018-09-04 | COMPLETE | 2019-04-04 | FY 18-19 | 10 |  | EDWIN MELGAR-MEJIA | John Peraino
BAS | 19P000235 | FS | SL5 RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | ABER INVER | A0100 | 2018-09-04 | CANCELED BY CLIENT | 2019-04-04 |  | 11 |  | EDWIN MELGAR-MEJIA | John Peraino
BAS | 19P000015 | FS | SL5 POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING | POLICE TRLR | 1 | 2018-07-10 | COMPLETE | 2018-11-08 | FY 18-19 | 11 |  | KELLY DUNCAN | Paul Ditty
BAS | 19P000233 | FS | SL5 PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | MAIL | 884 | 2018-09-04 | CANCELED BY FS | 2018-09-24 |  | 12 |  | AMY EVERETT
BAS | 18P000363 | FS | SL5 PAINT STOREHOUSE ADMINISTRATIVE OFFICE | CORP B |  | 2018-03-26 | COMPLETE | 2018-11-08 | FY 18-19 | 13 |  | ERICA HENDERSON | Paul Ditty
BAS | 19P000227 | FS | SL5 DINING STORAGE ROOM CONVERSION | BANNOCK J | J0100 | 2018-08-17 | COMPLETE | 2019-05-16 | FY 18-19 | 2 |  | DARCI LOMBARD | John Peraino
BAS | 19P000224 | FS | SL5 PAINT EXTERIOR RAMP AT HUB MODULAR | PRINT MOD |  | 2018-08-28 | COMPLETE | 2019-05-07 | FY 18-19 | 3 |  | MIKE CLEMONS | Paul Ditty
BAS | 19P000308 | FS | SL5 ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK | ABER INVER |  | 2018-09-11 | COMPLETE | 2019-04-04 | FY 18-19 | 4 |  | EDWIN MELGAR-MEJIA | John Peraino
BAS | 19P000307 | FS | SL5 LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK | LOTHIAN HALL |  | 2018-09-11 | COMPLETE | 2019-01-01 | FY 18-19 | 5 |  | EDWIN MELGAR-MEJIA | John Peraino
BAS | 18P000483 | FS | SL5 INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | P1 |  | 2018-06-26 | CANCELED BY CLIENT | 2018-12-03 |  | 7 |  | AMANDA GREY | Enrico Baez
BAS | 19P000022 | FS | SL5 HUB--PAINT TWO WALL AS SCOTTY'S HUB | HUB | 101 | 2018-07-12 | COMPLETE | 2018-09-17 | FY 18-19 | 8 |  | DIANE THOMAS | Paul Ditty
BAS | 19P000215 | FS | SL5 SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 | HUB | 346 | 2018-08-24 | COMPLETE | 2018-12-12 | FY 18-19 | 9 |  | GUSTAVO PLASCENCIA | John Peraino
BAS | 18P000095 | FS | SL5 THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS | THE PLAZA | A0013 | 2017-09-08 | CANCELED BY CLIENT | 2018-06-08 |  | C |  | EDWIN MELGAR-MEJIA | Enrico Baez
BCOE | 19P000028 | FS | SL5 BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS | BOURNS | A0169 | 2018-07-16 | COMPLETE | 2019-05-01 | FY 18-19 |  |  | ROBERT LOPEZ-A | Dan Lerman
BCOE | 18P000349 | FS | SL5 PHYSICS INSTALL PARTITION WALL FOR LAB ROOM | PHYSICS | 1037 | 2018-03-18 | COMPLETE | 2018-07-11 | FY 18-19 |  | YES | LOUIS SANDOVAL | Dan Lerman
BCOE | 18P000321 | FS | SL5 STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST | STUDENT SERV | 1228 | 2018-02-22 | COMPLETE | 2018-08-10 | FY 18-19 |  |  | ROBERT LOPEZ-A | Enrico Baez
BCOE | 18P000315 | FS | SL5 BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB | BOURNS | B0235 | 2018-02-16 | COMPLETE | 2018-08-23 | FY 18-19 |  | YES | LOUIS SANDOVAL | Dan Lerman
BCOE | 18P000472 | FS | SL5 WCH PATCH AND PAINT WALL | CHUNG HALL | 458 | 2018-06-12 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | JANNA LE BLANC | Paul Ditty
BCOE | 18P000427 | FS | SL5 BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER | BOURNS | A0373 | 2018-05-01 | COMPLETE | 2018-07-11 | FY 18-19 |  | YES | LOUIS SANDOVAL | Dan Lerman
BCOE | 18P000454 | FS | SL5 BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS | BOURNS | A0346 | 2018-05-29 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 18P000394 | FS | SL5 BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK | BOURNS | A0159A | 2018-04-12 | COMPLETE | 2019-02-01 | FY 18-19 |  | YES | ROBERT LOPEZ-A | Dan Lerman
BCOE | 18P000425 | FS | SL5 BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - | BOURNS | A0379 | 2018-05-01 | COMPLETE | 2018-07-25 | FY 18-19 |  | YES | LOUIS SANDOVAL | Dan Lerman
BCOE | 18P000429 | FS | SL5 INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 | BOURNS | B0262 B0256 | 2018-04-10 | COMPLETE | 2018-09-19 | FY 18-19 |  | YES | KEVIN SCHULTE | Dan Lerman
BCOE | 18P000426 | FS | SL5 BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER | BOURNS | A0375 | 2018-05-01 | COMPLETE | 2018-07-25 | FY 18-19 |  | YES | LOUIS SANDOVAL | Dan Lerman
BCOE | 18P000267 | FS | SL5 CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT | CHUNG HALL | 103 | 2018-01-16 | COMPLETE | 2018-07-11 | FY 18-19 |  |  | ROBERT LOPEZ-A | Dan Lerman
BCOE | 18P000391 | FS | SL5 PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN | CHUNG HALL | 446 449 | 2018-04-10 | COMPLETE | 2018-09-10 | FY 18-19 |  | YES | ROBERT LOPEZ-A | Dan Lerman
BCOE | 19P000388 | FS | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | SKYE HALL | 308 | 2018-11-26 | COMPLETE | 2019-07-15 | FY 19-20 | 0 |  | SHARYL MURDOCK | Dan Lerman
BCOE | 19P000445 | FS | SL5 BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT | BOURNS | B0328D | 2019-01-11 | CANCELED BY FS | 2019-02-27 |  | 0 |  | MARGARET SOUDER
BCOE | 19P000278 | FS | SL5 REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR | BOURNS | A0165 | 2018-08-03 | COMPLETE | 2018-10-04 | FY 18-19 | 1 | YES | NANCY FORD | Dan Lerman
BCOE | 19P000453 | FS | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT | CHUNG HALL | 447 | 2019-01-17 | COMPLETE | 2019-02-08 | FY 18-19 | 1 | YES | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000059 | FS | SL5 CHUNG HALL 201 SECURITY SYSTEM INSTALL | CHUNG HALL | 201 | 2018-07-17 | CANCELED BY FS | 2018-07-30 |  | 10 |  | MAGARET SOUDER | Dan Lerman
BCOE | 19P000029 | FS | SL5 CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | CHUNG HALL | 205 | 2018-07-16 | CANCELED BY CLIENT | 2018-09-18 |  | 11 |  | ROBERT LOPEZ-A | Dan Lerman
BCOE | 19P000316 | FS | SL5 CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL | CHUNG HALL | 449 | 2018-10-03 | COMPLETE | 2018-12-14 | FY 18-19 | 12 |  | ROBERT LOPEZ-A | Dan Lerman
BCOE | 19P000046 | FS | SL5 PATCH AND PAINT PLUS REPLACE BLINDS | BOURNS | A0131 | 2018-07-23 | COMPLETE | 2018-11-08 | FY 18-19 | 2 | YES | NANCY FORD | Paul Ditty
BCOE | 19P000442 | FS | SL5 WINSTON CHUNG- PATCH/PAINT ROOM 319 | CHUNG HALL | 319 | 2019-01-09 | COMPLETE | 2019-03-04 | FY 18-19 | 2 |  | BILL BINGHAM | Paul Ditty
BCOE | 19P000487 | FS | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES | BOURNS | A219, A211, A241 | 2019-02-05 | COMPLETE | 2019-07-22 | FY 19-20 | 2 |  | DEANNA VORHEES | Paul Ditty
BCOE | 19P000175 | FS | SL5 PAINTING | BOURNS | A0303 | 2018-08-09 | COMPLETE | 2018-10-10 | FY 18-19 | 3 | YES | ROBERT CHAVARRIA-VIVAR | Paul Ditty
BCOE | 19P000312 | FS | SL5 VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP | STUDENT SERV | 1227 | 2018-10-03 | COMPLETE | 2019-03-04 | FY 18-19 | 3 |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000597 | FS | SL5 PATCH AND PAINT WALLS | CHUNG HALL | 355, 356, 351, & 353 | 2019-05-03 | COMPLETE | 2019-07-16 | FY 19-20 | 3 |  | SARA GALLOWAY | Paul Ditty
BCOE | 19P000322 | FS | SL5 CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT | CHUNG HALL | 103 | 2018-10-05 | COMPLETE | 2019-03-04 | FY 18-19 | 4 |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000205 | FS | SL5 LABORATORY RENOVATION FOR NEW FACULTY | BOURNS | A0328 | 2018-08-23 | COMPLETE | 2019-02-18 | FY 18-19 | 4 | YES | MARGARET SOUDER | Dan Lerman
BCOE | 19P000250 | FS | SL5 BOURNS A303-PAINT AND PATCH WALL | BOURNS | A0303 | 2018-09-10 | COMPLETE | 2018-10-10 | FY 18-19 | 5 | YES | JUANA GUERRERO | Paul Ditty
BCOE | 19P000558 | FS | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT | BOURNS | A0265 | 2019-04-03 | COMPLETE | 2019-07-09 | FY 19-20 | 5 |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000424 | FS | SL5 CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET | CHUNG HALL | 445 | 2018-12-20 | COMPLETE | 2019-03-04 | FY 18-19 | 5 |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000060 | FS | SL5 CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | CHUNG HALL | 223 & 224 | 2018-05-15 | TO BE PERFORMED BY PD&C | 2019-02-01 |  | 6 |  | MAGARET SOUDER | Dan Lerman
BCOE | 19P000565 | FS | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS | BOURNS | A0133 | 2019-04-08 | CANCELED BY CLIENT | 2019-07-30 |  | 7 |  | NANCY FORD | Paul Ditty
BCOE | 19P000129 | FS | SL5 HANG MONITORS AND BOARDS | CHUNG HALL | 103 | 2018-08-06 | COMPLETE | 2018-12-14 | FY 18-19 | 8 |  | RICHARD BAIN | Dan Lerman
BCOE | 18P000226 | FS | SL5 BOURNS FUME HOOD INSTALLATION | BOURNS | B0235A | 2017-12-11 | COMPLETE | 2019-02-14 | FY 18-19 | 8 | YES | LOUIS SANDOVAL | Dan Lerman
BCOE | 19P000588 | FS | SL5 BOURNS A-WING 1ST FLOOR - PATCH & PAINT OFFICES | BOURNS | A127 Office, A129 Office, A131 Office, A133 Office, A135 Office, A137 Office, A139 Office, and A141 Office | 2019-04-22 | COMPLETE | 2019-06-28 | FY 18-19 | 8 |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000035 | FS | SL5 WCH--INSTALL NEW LED DISPLAY IN OFFICE | CHUNG HALL | 354 | 2018-07-16 | COMPLETE | 2018-11-19 | FY 18-19 | 9 |  | SARA GALLOWAY | Dan Lerman
BCOE | 19P000023 | FS | SL5 PAINT ACCENT WALL | CHUNG HALL | 354 | 2018-07-13 | CANCELED BY CLIENT | 2018-09-18 |  | 9 |  | SARA GALLOWAY | Paul Ditty
BCOE | 19P000026 | FS | SL5 WCH PATCH AND PAINT WALLS | CHUNG HALL | 354 | 2018-07-16 | CANCELED BY CLIENT | 2018-09-18 |  | 9 |  | SARA GALLOWAY | Paul Ditty
BCOE | 18P000439 | FS | SL5 CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING | CHUNG HALL | 315 | 2018-05-15 | COMPLETE | 2018-09-10 | FY 18-19 | Complete |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 18P000438 | FS | SL5 CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING | CHUNG HALL | 415 | 2018-05-14 | COMPLETE | 2018-09-10 | FY 18-19 | Complete |  | ROBERT LOPEZ-A | Paul Ditty
CAMPUS | 19P000296 | FS | SL5 MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB | MAT SCI ENGR |  | 2018-09-25 | COMPLETE | 2019-02-28 | FY 18-19 |  |  | MILLY PAREDEZ | Dan Lerman
CAMPUS | 19P000188 | FS | SL5 PAINT - HALLWAY DOORS & INSIDE RESTROOMS | LIFE SCIENCE | CR2500 | 2018-08-16 | CANCELED BY FS | 2018-12-13 |  |  |  | ESTELLA DAVALOS | Paul Ditty
CAMPUS | 19P000212 | FS | SL5 REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | LIFE SCIENCE | CR2500A | 2018-08-24 | CANCELED BY FS | 2018-12-13 |  |  |  | ESTELLA DAVALOS
CAMPUS | 19P000211 | FS | SL5 LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | LIFE SCIENCE | 2545 | 2018-08-24 | CANCELED BY FS | 2018-12-13 |  |  |  | ESTELLA DAVALOS
CAMPUS | 18P000121 | FS | SL5 PHYSICS HYDRATION STATION - PHYSICS HALL | PHYSICS | 0 | 2017-09-21 | CANCELED BY FS | 2019-05-01 |  |  |  | JAZMIN CHAVEZ | Dan Lerman
CAMPUS | 18P000435 | FS | SL5 HMSS HYDRATION STATION REQUEST | HUM & SOC SC | 3600 | 2018-05-10 | COMPLETE | 2019-04-15 | FY 18-19 |  |  | NELDA THOMAS | Dan Lerman
CAMPUS | 18P000122 | FS | SL5 MS&E HYDRATION STATION - MS&E HALL | PHYSICS | 0 | 2017-09-21 | CANCELED BY FS | 2018-04-02 |  |  |  | JAZMIN CHAVEZ | Dan Lerman
CAMPUS | 19P000284 | FS | SL5 GEOLOGY ACCOMMODATION DOCK DOORS | GEOLOGY |  | 2018-08-07 | COMPLETE | 2019-01-10 | FY 18-19 | Canceled |  | DEBORAH TERAO | Chris Pillen
CAP.PROG. | 19P000396 | FS | SL5 TRAILER #14 - CAMPUS INITIATED - STRUCTURE | T14 |  | 2019-01-31 | COMPLETE | 2019-02-28 | FY 18-19 | 0 |  | SHARYL MURDOCK | Dan Lerman
CHANCELLOR | 18P000421 | FS | SL5 HINDERAKER PAINT AND PATCH WALL | HINDERAKER | 2120 | 2018-04-30 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | CANDICE GOMEZ | Paul Ditty
CHANCELLOR | 18P000329 | FS | SL5 SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST | SKYE HALL | 170 | 2018-03-12 | COMPLETE | 2018-09-18 | FY 18-19 |  |  | DA LAN DINH | Dan Lerman
CHANCELLOR | 18P000209 | FS | SL5 VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 | STUDENT SERV | 0 | 2017-11-30 | CANCELED BY CLIENT | 2019-05-16 |  |  |  | ANGIE GRAY | Dan Lerman
CHANCELLOR | 18P000410 | FS | SL5 HINDERAKER PAINT AND PATCH WALL | HINDERAKER | 3148B | 2018-04-25 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | CANDICE GOMEZ | Paul Ditty
CHANCELLOR | 18P000414 | FS | SL5 CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL | STUDENT SERV | 0 | 2018-04-26 | COMPLETE | 2019-05-07 | FY 18-19 | 1 |  | DANIELLE GARCIA | Paul Ditty
CHANCELLOR | 19P000375 | FS | SL5 PATCH AND PAINT HOLES | SKYE HALL | 365 | 2018-11-07 | COMPLETE | 2019-02-01 | FY 18-19 | 1 |  | FELECIA GARRETT | Paul Ditty
CHANCELLOR | 18P000487 | FS | SL5 SKYE HALL PATCH HOLES AND PAINT | SKYE HALL | 349 | 2018-06-28 | COMPLETE | 2018-10-22 | FY 18-19 | 2 |  | SONIA ZAMORA | Paul Ditty
CHANCELLOR | 19P000420 | FS | SL5 PATCH AND PAINT WALL | SKYE HALL | 325 | 2018-12-19 | COMPLETE | 2019-02-08 | FY 18-19 | 3 |  | REYNA ALARCON | Paul Ditty
CHANCELLOR | 19P000122 | FS | SL5 REMOVE, PATCH & PAINT AND HANG | STUDENT SERV | 2222 | 2018-08-02 | COMPLETE | 2018-10-22 | FY 18-19 | 3 |  | CHRISTINE SMITH | Paul Ditty
CHANCELLOR | 18P000297 | FS | SL5 SKYE HALL CHECK LOCATION FOR TV INSTALL | SKYE HALL | 390 | 2018-02-02 | COMPLETE | 2019-02-01 | FY 18-19 | 4 |  | CANDICE GOMEZ | Dan Lerman
CHASS | 18P000389 | FS | SL5 PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A | PSYCHOLOGY1 | 2122 | 2018-04-10 | COMPLETE | 2018-11-08 | FY 18-19 |  | YES | ERICA RAMIREZ | Paul Ditty
CHASS | 18P000416 | FS | SL5 HMSS UWP INSTRUCTOR OFFICE PAINTING | HUM & SOC SC | 3002 | 2018-04-27 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | JILL CANTONWINE | Paul Ditty
CHASS | 18P000415 | FS | SL5 PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | OLMSTED | 0 | 2018-05-08 | CANCELED BY CLIENT | 2018-12-14 |  |  | YES | RYAN LIPINSKI | Dan Lerman
CHASS | 18P000445 | FS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 | ARTS | 225 | 2018-05-21 | COMPLETE | 2018-09-10 | FY 18-19 |  | YES | SUSAN KOMURA | Paul Ditty
CHASS | 18P000367 | FS | SL5 CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE | CHASS INT N | 3033 | 2018-03-27 | COMPLETE | 2018-07-14 | FY 18-19 |  |  | SARAH NOSCE | Paul Ditty
CHASS | 18P000353 | FS | SL5 PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT | PSYCHOLOGY1 | 1111A | 2018-03-20 | COMPLETE | 2018-08-23 | FY 18-19 |  |  | ERICA RAMIREZ | Paul Ditty
CHASS | 19P000313 | FS | SL5 HUMANITIIES SOCSCI - PATCH HOLES & PAINT - | HUM & SOC SC | 1203 | 2018-10-03 | COMPLETE | 2018-11-01 | FY 18-19 |  |  | CHRISTY GRAY | Paul Ditty
CHASS | 18P000314 | FS | SL5 CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR | CA MUS PHOTO | 1000 | 2018-02-16 | COMPLETE | 2018-07-25 | FY 18-19 |  |  | EMILY PAPAVERO | Dan Lerman
CHASS | 18P000344 | FS | SL5 CHASS INTS PAINT MULTIPLE ROOMS - FACULTY | CHASS INT S | 2117E | 2018-03-18 | COMPLETE | 2018-09-10 | FY 18-19 |  | YES | PAUL RICHARDSON | Dan Lerman
CHASS | 18P000294 | FS | SL5 HMSS REMOVE DOOR, INSTALL WALL | HUM & SOC SC | 3610 | 2018-02-01 | CANCELED BY CLIENT | 2018-07-16 |  |  |  | PAUL RICHARDSON | Dan Lerman
CHASS | 19P000056 | FS | SL5 HMSS CAPABILITY OF MOUNTING A TV | HUM & SOC SC | 1212 | 2017-10-03 | COMPLETE | 2018-12-14 | FY 18-19 |  |  | ALLISON ROGERS | Dan Lerman
CHASS | 18W016588 | FS | PATCH AND PAINT FOR FACULTY | SPROUL | 4105 | 2018-06-19 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | DAMARIS CARLOS | Paul Ditty
CHASS | 18P000318 | FS | SL5 CHASS INT S FLAT SCREEN INSTALLATION | CHASS INT S |  | 2018-02-21 | COMPLETE | 2019-04-15 | FY 18-19 |  |  | RYAN MARIANO | Dan Lerman
CHASS | 18P000417 | FS | SL5 HMSS UWP INSTRUCTIONAL OFFICE PAINTING | HUM & SOC SC | 2106 | 2018-04-27 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | JILL CANTONWINE | Paul Ditty
CHASS | 19P000364 | FS | SL5 PATCH AND PAINT | CHASS INT S | 3106 | 2018-10-30 | COMPLETE | 2019-03-15 | FY 18-19 |  |  | FRANCESCA MOREIRA | Paul Ditty
CHASS | 18P000387 | FS | SL5 HMSS PATCH/PAINT | HUM & SOC SC | 3600 | 2018-04-10 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | PAUL RICHARDSON | Paul Ditty
CHASS | 18P000300 | FS | SL5 ARTS PATCH AND PAINT - DANCE HALLWAYS | ARTS |  | 2018-02-02 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | SARAH NOSCE | Paul Ditty
CHASS | 18P000295 | FS | SL5 CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL | CHASS INT S | 2117J | 2018-02-01 | COMPLETE | 2018-09-21 | FY 18-19 |  | YES | PAUL RICHARDSON | Dan Lerman
CHASS | 18W001170 | FS | SL5 ARTS: PAINT CLASSROOMS | ARTS | 407 | 2017-07-25 | COMPLETE | 2018-09-24 | FY 18-19 |  |  | SUSAN KOMURA | Paul Ditty
CHASS | 18P000205 | FS | SL5 CHASS INT S CREATE DOOR | CHASS INT S | 2117H | 2017-11-27 | COMPLETE | 2018-09-21 | FY 18-19 |  | YES | PAUL RICHARDSON | Dan Lerman
CHASS | 19P000253 | FS | SL5 ARTS RENOVATION | ARTS | 157 | 2018-04-17 | COMPLETE | 2018-09-21 | FY 18-19 |  |  | PAUL RICHARDSON | Dan Lerman
CHASS | 18P000396 | FS | SL5 WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | WATKINS | 2122 | 2018-04-13 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | DAMARIS CARLOS | Paul Ditty
CHASS | 18P000111 | FS | SL5 KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 | CHASS INT S |  | 2017-09-15 | COMPLETE | 2018-07-13 | FY 18-19 |  |  | RYAN MARIANO | Jason Williams
CHASS | 18P000383 | FS | SL5 HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT | HUM & SOC SC | 1302 | 2018-04-06 | COMPLETE | 2018-08-10 | FY 18-19 |  | YES | ALLISON ROGERS | Paul Ditty
CHASS | 18P000420 | FS | SL5 COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | WATKINS | 0 | 2018-04-27 | CANCELED BY CLIENT | 2018-07-02 |  |  | YES | PAUL RICHARDSON
CHASS | 18P000201 | FS | SL5 ARTS REMOVE COUNTERTOP/SHELVES | ARTS | 0106A | 2017-11-21 | COMPLETE | 2018-08-23 | FY 18-19 |  | YES | PAUL RICHARDSON | Dan Lerman
CHASS | 18P000468 | FS | SL5 WATKINS 1222/1223 PATCH/PAINT | WATKINS | 1222 | 2018-06-11 | COMPLETE | 2018-08-10 | FY 18-19 |  | YES | PAUL RICHARDSON | Paul Ditty
CHASS | 18P000469 | FS | SL5 WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS | WATKINS | 1317 | 2018-06-11 | COMPLETE | 2018-07-25 | FY 18-19 |  | YES | PAUL RICHARDSON | Paul Ditty
CHASS | 18P000418 | FS | SL5 HMSS OFFICE PAINTING | HUM & SOC SC | 2002 | 2018-04-27 | COMPLETE | 2018-07-14 | FY 18-19 |  | YES | JILL CANTONWINE | Paul Ditty
CHASS | 19P000220 | FS | SL5 ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT | ARTS | 333 | 2018-08-28 | COMPLETE | 2018-12-14 | FY 18-19 | 1 |  | SONJA SEKELY-ROWLAND | Dan Lerman
CHASS | 19P000361 | FS | SL5 OLMSTED-PATCH & PAINT/REPLACE CARPET | OLMSTED |  | 2018-10-29 | COMPLETE | 2019-05-09 | FY 18-19 | 1 |  | TOYA ADAMS | Paul Ditty
CHASS | 18P000481 | FS | SL5 CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 | CHASS INT S | 3104 | 2018-06-25 | COMPLETE | 2018-10-22 | FY 18-19 | 10 |  | PAUL RICHARDSON | Paul Ditty
CHASS | 19P000606 | FS | SL5 PAINT ROOM | WATKINS | 1213 | 2019-05-10 | CANCELED BY CLIENT | 2019-06-14 |  | 10 |  | BECKY CAMPBELL | Paul Ditty
CHASS | 19P000378 | FS | SL5 PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 | HUM & SOC SC | 1613 | 2018-11-13 | COMPLETE | 2019-03-04 | FY 18-19 | 10 |  | SHELLEE STEWART | Paul Ditty
CHASS | 19P000400 | FS | SL5 CREATE DOOR INTO HALLWAY | CHASS INT S | 2117A | 2018-12-06 | CANCELED BY FS | 2019-05-21 |  | 103 |  | PAUL RICHARDSON | Dan Lerman
CHASS | 19P000306 | FS | SL5 HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 | CHASS INT N | 4017 | 2018-10-01 | COMPLETE | 2019-03-04 | FY 18-19 | 11 |  | RYAN MARIANO | Paul Ditty
CHASS | 19W002930 | FS | HOLD - SL5 PATCH HOLES & PAINT - HUMANITIIES SOCSCI | HUM & SOC SC | 1203 | 2018-08-17 | COMPLETE | 2018-11-08 | FY 18-19 | 11 |  | CHRISTY GRAY | Paul Ditty
CHASS | 19P000585 | FS | SL5 HUMANITIES SS, RM 3604- PATCH/PAINT WEST WALL | HUM & SOC SC | 3604 | 2019-04-19 | COMPLETE | 2019-06-28 | FY 18-19 | 11 |  | DARA CERDA | Paul Ditty
CHASS | 19P000355 | FS | SL5 HYDRATION STATION FOR THE SECOND FLOOR WATKINS | WATKINS | 2122D | 2018-10-22 | CANCELED BY FS | 2019-04-24 |  | 112 |  | CYNTHIA REDFIELD | Dan Lerman
CHASS | 19P000603 | FS | SL5 CHASS INT N, RM 3046- PATCH AND PAINT - NEW FACULTY OFFICE | CHASS INT N | 3046 | 2019-05-10 | COMPLETE | 2019-06-18 | FY 18-19 | 12 | YES | SARAH NOSCE | Paul Ditty
CHASS | 19P000195 | FS | SL5 HUM & SOC SC-ROOM PAINTING | HUM & SOC SC | 2003 | 2018-08-21 | COMPLETE | 2018-11-08 | FY 18-19 | 12 |  | CHRISTY GRAY | Paul Ditty
CHASS | 19P000640 | FS | SL5 NEW FACULTY - PATCH & PAINT SPROUL 3108 | SPROUL | 3108 | 2019-05-20 | COMPLETE | 2019-06-20 | FY 18-19 | 13 | YES | MELISA VICARIO | Paul Ditty
CHASS | 19P000216 | FS | SL5 HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT | HUM & SOC SC | 1214 | 2018-08-27 | COMPLETE | 2018-11-08 | FY 18-19 | 13 |  | ALLISON ROGERS | Paul Ditty
CHASS | 19P000221 | FS | SL5 PATCH, PAINTING, AND REGULAR CLEANING OF A126A | OLMSTED | A0126A | 2018-08-28 | COMPLETE | 2018-11-08 | FY 18-19 | 14 |  | TOYA ADAMS | Paul Ditty
CHASS | 19P000643 | FS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | 2019-05-21 | COMPLETE | 2019-07-16 | FY 19-20 | 14 |  | CHRISTY GRAY | Paul Ditty
CHASS | 19P000196 | FS | SL5 PAINT OFFICE AT UNIVERSITY THEATER | THTR WKSH |  | 2018-08-21 | COMPLETE | 2018-11-08 | FY 18-19 | 15 |  | JULIE SALGADO | Paul Ditty
CHASS | 19P000171 | FS | SL5 HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST | HUM & SOC SC | 1614 | 2018-08-09 | COMPLETE | 2019-05-07 | FY 18-19 | 16 |  | SHELLEE STEWART | Paul Ditty
CHASS | 18W016621 | FS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP | HUM & SOC SC | 3403 | 2018-06-20 | COMPLETE | 2018-11-08 | FY 18-19 | 17 |  | CYNTHIA CARRASCO CANNON | Paul Ditty
CHASS | 19P000201 | FS | SL5 PATCH AND PAINT THE WALLS | CHASS INT S | 3111A | 2018-08-22 | COMPLETE | 2018-11-08 | FY 18-19 | 18 |  | RYAN MARIANO | Paul Ditty
CHASS | 18P000385 | FS | SL5 HMSS INSTALL TV IN CONFERENCE ROOM | HUM & SOC SC | 1001E | 2018-03-06 | COMPLETE | 2019-03-18 | FY 18-19 | 19 |  | JILL CANTONWINE | Dan Lerman
CHASS | 19P000607 | FS | SL5 PAINT FACULTY OFFICE | WATKINS | 1312 | 2019-05-10 | CANCELED BY CLIENT | 2019-07-16 |  | 2 | YES | BECKY CAMPBELL | Paul Ditty
CHASS | 19P000362 | FS | SL5 PATCH & PAINT/REPLACE CARPET (HALLWAY) | OLMSTED |  | 2018-10-29 | COMPLETE | 2019-03-04 | FY 18-19 | 2 |  | TOYA ADAMS | Paul Ditty
CHASS | 18W008762 | FS | SL5 HUMANITIES: PATCH & PAINT | HUM & SOC SC | 2415 | 2018-01-02 | COMPLETE | 2018-11-08 | FY 18-19 | 20 |  | ANDREW ALONSO | Paul Ditty
CHASS | 18P000126 | FS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS | HUM & SOC SC | 3611 | 2017-09-28 | COMPLETE | 2019-07-01 | FY 19-20 | 21 |  | DARA CERDA | Dan Lerman
CHASS | 19P000173 | FS | SL5 PAINT/PATCH UNIVERSITY THEATER LOBBY | THTR WKSH | 0400A | 2018-08-09 | COMPLETE | 2018-11-08 | FY 18-19 | 23 |  | PAUL RICHARDSON | Paul Ditty
CHASS | 19P000356 | FS | SL5 PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT | HUM & SOC SC | 4401 | 2018-10-24 | COMPLETE | 2019-03-04 | FY 18-19 | 3 |  | ALLISON ROGERS | Paul Ditty
CHASS | 19P000063 | FS | SL5 NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS | PSYCHOLOGY1 | 2124 | 2018-07-31 | COMPLETE | 2018-09-26 | FY 18-19 | 3 | YES | TOYA ADAMS | Paul Ditty
CHASS | 19P000605 | FS | SL5 PAINT NEW MAILROOM | WATKINS | 1320E | 2019-05-10 | CANCELED BY CLIENT | 2019-07-16 |  | 4 |  | BECKY CAMPBELL | Paul Ditty
CHASS | 19P000350 | FS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | PSYCHOLOGY1 | 3121, 1133 | 2018-10-17 | COMPLETE |  |  | 4 | YES | TOYA ADAMS | Dan Lerman
CHASS | 19P000371 | FS | SL5 URGENT PATCH AND PAINT IN CHAIR'S OFFICE | HUM & SOC SC | 1213 | 2018-11-05 | COMPLETE | 2019-03-04 | FY 18-19 | 4 |  | ALLISON ROGERS | Paul Ditty
CHASS | 19P000011 | FS | SL5 PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED | PSYCHOLOGY1 | 2111A | 2018-07-03 | COMPLETE | 2018-10-10 | FY 18-19 | 4 | YES | LORENA QUINTANA | Paul Ditty
CHASS | 19P000604 | FS | SL5 HUMANITIES SS, RM 7704- PAINT OFFICE BY JULY 1, 2019 | HUM & SOC SC | 7704 | 2019-05-10 | COMPLETE | 2019-06-20 | FY 18-19 | 5 |  | ALLISON ROGERS | Paul Ditty
CHASS | 18P000419 | FS | SL5 COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | WATKINS | 1320C&E | 2018-04-27 | CANCELED BY CLIENT | 2019-02-14 |  | 5 | YES | PAUL RICHARDSON | Dan Lerman
CHASS | 19P000357 | FS | SL5 PATCH AND PAINT WALLS, TIME SENSITIVE | HUM & SOC SC | 1302 | 2018-10-25 | COMPLETE | 2019-03-04 | FY 18-19 | 5 |  | ALLISON ROGERS | Paul Ditty
CHASS | 19P000642 | FS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | 2019-05-21 | COMPLETE | 2019-07-16 | FY 19-20 | 6 |  | CHRISTY GRAY | Paul Ditty
CHASS | 18P000444 | FS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 | ARTS | 242 | 2018-05-21 | COMPLETE | 2018-09-21 | FY 18-19 | 6 | YES | SUSAN KOMURA | Paul Ditty
CHASS | 19P000314 | FS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP | HUM & SOC SC | 3403 | 2018-10-03 | COMPLETE | 2019-02-01 | FY 18-19 | 6 |  | CYNTHIA CARRASCO CANNON | Paul Ditty
CHASS | 19P000207 | FS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | OLMSTED |  | 2018-08-23 | COMPLETE |  |  | 7 |  | TOYA ADAMS | Dan Lerman
CHASS | 19P000552 | FS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS | HUM & SOC SC | 1001 B, C, and D | 2019-03-27 | COMPLETE | 2019-07-09 | FY 19-20 | 7 |  | JILL CANTONWINE | Paul Ditty
CHASS | 19P000300 | FS | SL5 HUM & SOC SC--URGENT: PAINT AND PATCH WALLS | HUM & SOC SC | 4403 | 2018-09-26 | COMPLETE | 2019-03-04 | FY 18-19 | 7 |  | ANDREA HERAZ | Paul Ditty
CHASS | 19P000286 | FS | SL5 FACULTY OFFICES: TOUCH UP PAINT | HUM & SOC SC | 2005 | 2018-09-17 | COMPLETE | 2019-03-04 | FY 18-19 | 8 |  | JILL CANTONWINE | Paul Ditty
CHASS | 19P000194 | FS | SL5 PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 | HUM & SOC SC | 3304 | 2018-08-20 | COMPLETE | 2018-11-08 | FY 18-19 | 8 |  | CHRISTY GRAY | Paul Ditty
CHASS | 19P000061 | FS | SL5 PSYCHOLOGY 1111H-PATCH HOLES IN WALL | PSYCHOLOGY1 | 1111H | 2018-07-30 | COMPLETE | 2019-01-11 | FY 18-19 | 9 |  | TOYA ADAMS | Paul Ditty
CHASS | 19P000429 | FS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | COLL BLDG SO | 103 | 2019-01-03 | COMPLETE | 2019-07-26 | FY 19-20 | 9 |  | RENEE DEGUIRE | Paul Ditty
CHASS | 19P000226 | FS | SL5 PAINT OFFICE HMNSS 3304 | HUM & SOC SC | 3304 | 2018-08-28 | CANCELED BY CLIENT | 2018-10-01 |  | Canceled |  | LEANN GILMER | Paul Ditty
CNAS | 18P000118 | FS | SL5 OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT | OLMSTED | 1337 | 2017-09-20 | COMPLETE | 2018-07-25 | FY 18-19 |  |  | MELISSA GOMEZ | Dan Lerman
CNAS | 19P000213 | FS | SL5 NEEDS FOR NEW WALL DISPLAY (MONITOR) | BIOLOGICAL SCI | 3101 | 2018-08-24 | CANCELED BY CLIENT | 2018-10-01 |  |  |  | ESTELLA DAVALOS
CNAS | 18W000455 | FS | SL5 CHAPMAN CLEAN WINDOWS | CHAPMAN | 12 | 2017-07-11 | COMPLETE | 2018-07-11 | FY 18-19 |  |  | WILLIAM SUTTON | Dan Lerman
CNAS | 18P000256 | FS | SL5 BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES | BOYCE | 3451 | 2017-12-22 | COMPLETE | 2018-09-21 | FY 18-19 |  |  | CHERYL GERRY | Dan Lerman
CNAS | 18P000247 | FS | SL5 PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 | PHYSICS | 3023 | 2017-12-20 | COMPLETE | 2018-07-14 | FY 18-19 |  |  | MAYELA CASTILLO | Paul Ditty
CNAS | 18W011161 | FS | SL5 REPLACE CARPET | SCIENCE LAB1 | 301 | 2018-02-23 | COMPLETE | 2018-07-11 | FY 18-19 |  |  | DEBORAH TERAO | Dan Lerman
CNAS | 18P000227 | FS | SL5 BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL | BATCHELOR | 4128 | 2017-12-12 | COMPLETE | 2018-11-08 | FY 18-19 |  | YES | APRIL MEINZER | Dan Lerman
CNAS | 18W011672 | FS | SL5 ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY | ENTOMOLOGY | 268 | 2018-03-08 | COMPLETE | 2018-07-25 | FY 18-19 |  | YES | WILLIAM SUTTON | Paul Ditty
CNAS | 18P000392 | FS | SL5 BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 | BATCHELOR | 0 | 2018-04-12 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | MATTHEW ULRICH | Paul Ditty
CNAS | 18P000434 | FS | SL5 BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY | BOYCE | 4478 | 2018-05-09 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | CHERYL GERRY | Paul Ditty
CNAS | 18P000027 | FS | SL5 CHAPMAN PREP AND PAINT LAB | CHAPMAN | 12 | 2018-03-05 | COMPLETE | 2018-07-12 | FY 18-19 |  |  | WILLIAM SUTTON | Dan Lerman
CNAS | 19P000346 | FS | SL5 I&Q--PAINTING ROOMS IN THE I&Q | EAST I&Q FAC |  | 2018-10-16 | COMPLETE | 2019-01-09 | FY 18-19 |  |  | IMAD BAYOUN | Paul Ditty
CNAS | 18P000117 | FS | SL5 PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION | WEBBER | 1303 | 2017-12-21 | COMPLETE | 2018-09-10 | FY 18-19 |  |  | MELISSA GOMEZ | Dan Lerman
CNAS | 19W007474 | FS | SL5 BG - RAILROAD TIE WALLS | BOTANIC GARDENS |  | 2018-11-07 | CANCELED BY FS | 2019-03-11 |  |  |  | AMBER RHEMREV
CNAS | 19P000319 | FS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | ENTOMOLOGY | 139 | 2018-10-04 | CANCELED BY CLIENT | 2018-10-04 |  |  |  | WILLIAM SUTTON | Paul Ditty
CNAS | 19P000058 | FS | SL5 Assess Feasiblity of Removing/Replacing Growth Chambers | GH HH | 18 | 2018-03-28 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | APRIL MEINZER | Dan Lerman
CNAS | 18P000030 | FS | SL5 CHAPMAN PREP AND PAINT FROM WATER DAMAGE | CHAPMAN | 100 | 2017-07-11 | COMPLETE | 2018-11-08 | FY 18-19 |  |  | WILLIAM SUTTON | Dan Lerman
CNAS | 18P000029 | FS | SL5 CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS | CHAPMAN | 1 | 2017-07-11 | COMPLETE | 2018-07-11 | FY 18-19 |  |  | WILLIAM SUTTON | Dan Lerman
CNAS | 18P000028 | FS | SL5 CHAPMAN PATCH AND PAINT | CHAPMAN | 0010A | 2017-07-11 | COMPLETE | 2018-07-12 | FY 18-19 |  |  | WILLIAM SUTTON | Dan Lerman
CNAS | 19P000185 | FS | SL5 NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE | PIERCE | 206 (originially identified as Room 204) | 2018-06-18 | COMPLETE | 2018-12-14 | FY 18-19 |  | YES | BARBARA OUTZEN | Dan Lerman
CNAS | 19P000186 | FS | SL5 NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION | PIERCE | 319 | 2018-06-18 | COMPLETE | 2018-11-08 | FY 18-19 |  | YES | BARBARA OUTZEN | Dan Lerman
CNAS | 19P000189 | FS | SL5 PHYSICS- WALL HOLES PATCH | PHYSICS | 3036 | 2018-08-16 | CANCELED BY CLIENT | 2018-10-18 |  |  |  | JAZMIN CHAVEZ | Dan Lerman
CNAS | 18W011692 | FS | SL5 ENTOMOLOGY; PAINT/PATCH LAB | ENTOM MUSEUM | 211 | 2018-03-08 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | WILLIAM SUTTON | Paul Ditty
CNAS | 18P000288 | FS | SL5 SKYE HALL OFFICE SUITE PAINTING | SKYE HALL | 208 | 2018-01-31 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | JAMES MARBERRY | Paul Ditty
CNAS | 18P000312 | FS | SL5 URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 | CAMP LOC NOT IN BLDG |  | 2018-02-13 | CANCELED BY FS | 2018-09-19 |  |  |  | AMBER RHEMREV | Dan Lerman
CNAS | 18P000310 | FS | SL5 ADD INTERCOM/BUZZ IN SYSTEM | COLL BLDG NO | 201 | 2018-02-12 | COMPLETE | 2018-10-22 | FY 18-19 |  |  | RONDA INZUNZA | Dan Lerman
CNAS | 18P000341 | FS | SL5 PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL | PHYSICS | 1132 | 2018-03-14 | COMPLETE | 2018-12-14 | FY 18-19 |  |  | MAYELA CASTILLO | Dan Lerman
CNAS | 18P000356 | FS | SL5 ENTOMOLOGY PATCH AND PATCH | ENTOMOLOGY | 278 | 2018-03-20 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | WILLIAM SUTTON | Paul Ditty
CNAS | 18P000296 | FS | SL5 SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES | SKYE HALL | 266 | 2018-02-02 | COMPLETE | 2019-01-01 | FY 18-19 |  |  | JAMES MARBERRY | Dan Lerman
CNAS | 18P000293 | FS | SL5 SKYE HALL COPIER ROOM PATCH AND PAINT | SKYE HALL | 278 | 2018-01-31 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | JAMES MARBERRY | Paul Ditty
CNAS | 18P000287 | FS | SL5 SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING | SKYE HALL | 208 | 2018-01-31 | COMPLETE | 2018-09-21 | FY 18-19 |  |  | JAMES MARBERRY | Dan Lerman
CNAS | 19P000287 | FS | SL5 URGENT: PAINT SHOP TO PATCH AND PAINT | MAT SCI ENGR | 229 | 2018-09-19 | COMPLETE | 2018-10-22 | FY 18-19 |  |  | HONG XU | Paul Ditty
CNAS | 18P000292 | FS | SL5 SKYE HALL PAINT MULTIPLE FACULTY OFFICES | SKYE HALL | 228 | 2018-01-31 | COMPLETE | 2018-08-24 | FY 18-19 |  | YES | JAMES MARBERRY | Paul Ditty
CNAS | 19P000390 | FS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE | BOYCE | 5494 | 2018-11-29 | COMPLETE | 2019-07-01 | FY 19-20 | 0 | YES | APRIL MEINZER | Dan Lerman
CNAS | 19P000358 | FS | SL5 GEOLOGY - ACCOMMODATION REQUEST | GEOLOGY |  | 2018-10-26 | COMPLETE | 2019-04-15 | FY 18-19 | 0 |  | RONDA INZUNZA | Dan Lerman
CNAS | 19P000298 | FS | SL5 SPIETH - PREP LAB FOR FACULTY SEARCH | SPIETH | 1363 | 2018-09-26 | COMPLETE | 2019-05-15 | FY 18-19 | 0 |  | ESTELLA DAVALOS | Dan Lerman
CNAS | 19P000449 | FS | SL5 PAINT OFFICE AREA OF 229A FOR RELOCATION | FAWCETT LAB | 229A | 2019-01-14 | COMPLETE | 2019-04-05 | FY 18-19 | 0 |  | CHERYL GERRY | Paul Ditty
CNAS | 19P000505 | FS | SL5 CHAPMAN HALL PAINT OFFICE WALL WHERE BOOK CASE WAS REMOVED | CHAPMAN | 10B | 2019-02-25 | COMPLETE | 2019-05-10 | FY 18-19 | 0 |  | WILLIAM SUTTON | Paul Ditty
CNAS | 19P000440 | FS | SL5 GH#21--INSTALLATION OF GROW POD BEHIND GREENHOUSE #21 | GH21 |  | 2019-01-08 | COMPLETE | 2019-05-31 | FY 18-19 | 0 |  | APRIL MEINZER | Dan Lerman
CNAS | 19P000299 | FS | SL5 SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 | SPIETH | 3378 | 2018-09-26 | COMPLETE | 2019-02-08 | FY 18-19 | 1 |  | ESTELLA DAVALOS | Paul Ditty
CNAS | 18P000473 | FS | SL5 PIERCE NEW CARPET & PAINT FACULTY OFFICE | PIERCE | 202 | 2018-06-12 | COMPLETE | 2018-09-26 | FY 18-19 | 1 | YES | BARBARA OUTZEN | Paul Ditty
CNAS | 19P000347 | FS | SL5 SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT | SPIETH | 3320 | 2018-10-16 | COMPLETE | 2019-03-04 | FY 18-19 | 10 |  | ESTELLA DAVALOS | Paul Ditty
CNAS | 19P000571 | FS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 | SCIENCE LAB1 | 215 & 322 | 2019-04-10 | COMPLETE | 2019-07-30 | FY 19-20 | 10 |  | DEBORAH TERAO | Paul Ditty
CNAS | 19P000244 | FS | SL5 PATCH & PAINT GEOLOGY | GEOLOGY | 2258A | 2018-09-06 | COMPLETE | 2018-10-22 | FY 18-19 | 10 | YES | AMBER RHEMREV | Paul Ditty
CNAS | 19P000324 | FS | SL6 SPIETH HALL ASSESS AIR VENT OR PURIFIER FOR LAB | SPIETH | 1312 | 2018-10-05 | CANCELED BY FS | 2019-04-04 |  | 106 |  | ESTELLA DAVALOS | Dan Lerman
CNAS | 19P000367 | FS | SL5 SCILAB 1 0211- PATCH & PAINT | SCIENCE LAB1 | 211 | 2018-10-31 | COMPLETE | 2019-03-04 | FY 18-19 | 11 |  | DEBORAH TERAO | Paul Ditty
CNAS | 18P000223 | FS | SL5 Provide requisite utility infrastructure to support 4 add'l chambers (on order). | FAWCETT LAB |  | 2017-12-11 | COMPLETE | 2019-02-01 | FY 18-19 | 11 |  | APRIL MEINZER | Dan Lerman
CNAS | 19P000438 | FS | SL5 BOTANIC GARDENS RAILROAD TIE WALLS | BOTAN INFO C |  | 2019-01-08 | CANCELED BY FS | 2019-03-05 |  | 118 |  | AMBER RHEMREV | Dan Lerman
CNAS | 18P000269 | FS | SL5 BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED | BATCHELOR | 1123 | 2018-01-16 | CANCELED BY CLIENT | 2019-03-18 |  | 12 |  | APRIL MEINZER | Dan Lerman
CNAS | 19P000137 | FS | SL5 LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM | LIFE SCIENCE | 2545 | 2018-08-08 | COMPLETE | 2019-03-04 | FY 18-19 | 12 |  | ESTELLA DAVALOS | Paul Ditty
CNAS | 18P000354 | FS | SL5 GH16-25 COOLING SYSTEM REPAIR | GH 16 25 |  | 2018-03-20 | CANCELED BY FS | 2018-07-25 |  | 13 |  | MARK TANKERSLEY | Dan Lerman
CNAS | 19P000045 | FS | SL5 PREPARE LOCATION AND UTILITIES FOR INSTALL | BOYCE | 2407 | 2018-07-23 | COMPLETE | 2018-11-08 | FY 18-19 | 14 |  | MATTHEW ULRICH | Dan Lerman
CNAS | 19P000106 | FS | SL5 PHYICS 1134 - UTILITIES REQUEST | PHYSICS | 1134 | 2018-08-01 | COMPLETE | 2019-06-15 | FY 18-19 | 15 |  | MAYELA CASTILLO | Dan Lerman
CNAS | 19P000170 | FS | SL5 INSTALL NEW IRRADIATOR INSTRUMENT | MAT SCI ENGR | 51 | 2018-08-08 | COMPLETE | 2019-02-14 | FY 18-19 | 16 |  | DEBORAH MCWILLIAMS | Dan Lerman
CNAS | 19P000292 | FS | SL5 GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER | GEOLOGY |  | 2018-08-10 | COMPLETE | 2019-03-28 | FY 18-19 | 18 |  | AMBER RHEMREV | Dan Lerman
CNAS | 19P000043 | FS | SL5 SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | SCIENCE LAB1 | 309 | 2018-07-20 | CANCELED BY CLIENT | 2018-10-23 |  | 19 |  | AMBER RHEMREV | Dan Lerman
CNAS | 19P000340 | FS | SL5 PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE | SKYE HALL | 349 | 2018-10-12 | COMPLETE | 2019-02-08 | FY 18-19 | 2 |  | VICTORIA AVALOS | Paul Ditty
CNAS | 19P000618 | FS | SL5 COLLEGE BLDG NO, RM 205 AND 205A- PAINT | COLL BLDG NO | 205 AND 205A | 2019-05-14 | CANCELED BY FS | 2019-06-11 |  | 2 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000341 | FS | SL5 PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL | PIERCE |  | 2018-10-12 | COMPLETE | 2019-02-08 | FY 18-19 | 2 |  | BARBARA OUTZEN | Paul Ditty
CNAS | 19P000214 | FS | SL5 PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT | PHYSICS | 3005 | 2018-08-24 | COMPLETE | 2018-10-10 | FY 18-19 | 2 | YES | MAYELA CASTILLO | Paul Ditty
CNAS | 19P000283 | FS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | CHUNG HALL | ROOF | 2018-09-05 | COMPLETE |  |  | 20 |  | DEBORAH MCWILLIAMS | Dan Lerman
CNAS | 18P000388 | FS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | SPIETH | 0317A | 2018-04-10 | COMPLETE | 2019-08-14 | FY 19-20 | 22 |  | ESTELLA DAVALOS | Dan Lerman
CNAS | 18P000480 | FS | SL5 BG - LOWER RESTROOMS-PAINTING-FLOORS | BOTGDN RSTRM |  | 2018-06-25 | CANCELED BY FS | 2018-09-01 |  | 23 |  | AMBER RHEMREV | Paul Ditty
CNAS | 18P000486 | FS | SL5 PHYSICS 3027/3028 RENOVATION | PHYSICS | 3027 | 2018-06-28 | COMPLETE | 2019-08-01 | FY 19-20 | 24 |  | MAYELA CASTILLO | Dan Lerman
CNAS | 19P000210 | FS | SL5 CHEMICAL SCI Install Door In Doorway | CHEMICAL SCI | 0225A | 2018-08-24 | COMPLETE | 2019-07-01 | FY 19-20 | 25 |  | BARBARA OUTZEN | Dan Lerman
CNAS | 18P000099 | FS | SL5 EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 | GEOLOGY |  | 2017-09-08 | COMPLETE | 2019-04-19 | FY 18-19 | 26 |  | LAURIE GRAHAM | Dan Lerman
CNAS | 17W012504 | FS | PAINT Business OFFICE AND CONF. ROOM | ENTOMOLOGY | 170 | 2017-05-04 | COMPLETE | 2018-10-22 | FY 18-19 | 27 |  | WILLIAM SUTTON | Paul Ditty
CNAS | 18P000257 | FS | SL5 SKYE HALL MOUNT 55 | SKYE HALL | 209 | 2017-12-22 | COMPLETE | 2019-02-01 | FY 18-19 | 28 |  | JAMES MARBERRY | Dan Lerman
CNAS | 18P000284 | FS | SL5 SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT | SKYE HALL | 277 | 2018-01-31 | COMPLETE | 2018-09-21 | FY 18-19 | 29 |  | JAMES MARBERRY | Paul Ditty
CNAS | 18P000258 | FS | SL5 SKYE HALL HALLWAY MOUNT | SKYE HALL | 212 | 2017-12-22 | COMPLETE | 2019-02-01 | FY 18-19 | 29 |  | JAMES MARBERRY | Dan Lerman
CNAS | 19P000006 | FS | SL5 MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 | MAT SCI ENGR | 310 | 2018-07-02 | COMPLETE | 2019-03-18 | FY 18-19 | 3 | YES | MAYELA CASTILLO | Dan Lerman
CNAS | 19P000301 | FS | SL5 SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH | SCIENCE LAB1 | 214 | 2018-09-27 | COMPLETE | 2019-02-08 | FY 18-19 | 3 |  | AMBER RHEMREV | Paul Ditty
CNAS | 18P000347 | FS | SL5 GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) | GEOLOGY | 0 | 2018-03-18 | COMPLETE | 2019-04-15 | FY 18-19 | 31 |  | AMBER RHEMREV | Dan Lerman
CNAS | 19P000055 | FS | SL5 CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM | COLL BLDG SO | 207 | 2018-05-18 | COMPLETE | 2019-04-15 | FY 18-19 | 32 |  | LISA DUNMORE | Dan Lerman
CNAS | 18W013160 | FS | BEES- PATCH & PAINT 2460D & 2460F | GEOLOGY | 2460 | 2018-04-06 | COMPLETE | 2018-10-22 | FY 18-19 | 33 |  | DEBORAH TERAO | Paul Ditty
CNAS | 19P000191 | FS | SL5 PATCH AND PAINT HINDERAKER BASEMENT | HINDERAKER |  | 2018-08-20 | COMPLETE | 2018-11-08 | FY 18-19 | 34 |  | RONDA INZUNZA | Paul Ditty
CNAS | 18P000464 | FS | SL5 PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED | COLL BLDG NO | 201 | 2018-08-16 | COMPLETE | 2019-01-11 | FY 18-19 | 35 |  | RONDA INZUNZA | Paul Ditty
CNAS | 18P000436 | FS | SL5 COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS | COLL BLDG SO | 210 | 2018-05-10 | COMPLETE | 2019-01-11 | FY 18-19 | 36 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000174 | FS | SL5 BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT | BATCHELOR | 2112 | 2018-07-24 | COMPLETE | 2019-05-01 | FY 18-19 | 37 |  | AMY RICKS | Dan Lerman
CNAS | 19P000042 | FS | SL5 COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL | COLL BLDG SO | 200 | 2018-07-20 | COMPLETE | 2019-01-11 | FY 18-19 | 38 |  | LISA DUNMORE | Paul Ditty
CNAS | 19P000049 | FS | SL5 PHYSICS PATCH & PAINT | PHYSICS | 3036 | 2018-07-25 | COMPLETE | 2019-01-11 | FY 18-19 | 39 |  | JAZMIN CHAVEZ | Paul Ditty
CNAS | 18W011691 | FS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | ENTOMOLOGY | 139 | 2018-03-08 | CANCELED BY CLIENT | 2018-12-17 |  | 4 | YES | WILLIAM SUTTON | Paul Ditty
CNAS | 19P000614 | FS | SL5 COLLEGE BLDG NO, RM 202- PAINT | COLL BLDG NO | 0202 | 2019-05-14 | CANCELED BY FS | 2019-07-16 |  | 4 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000318 | FS | SL5 GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE | GEOLOGY | 420 | 2018-10-04 | COMPLETE | 2019-02-08 | FY 18-19 | 4 |  | KAREN CATO | Paul Ditty
CNAS | 19P000031 | FS | SL5 BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) | BIOLOGICAL SCI | 3101 | 2018-07-16 | COMPLETE | 2019-06-15 | FY 18-19 | 40 |  | ESTELLA DAVALOS | Dan Lerman
CNAS | 19P000102 | FS | SL5 PATCH & PAINT FRONT CORNER OF OFFICE | LIFE SCIENCE | 2930 | 2018-08-01 | COMPLETE | 2019-01-11 | FY 18-19 | 42 |  | ESTELLA DAVALOS | Paul Ditty
CNAS | 19P000133 | FS | SL5 PATCH HOLES AND PAINT | BATCHELOR | 2203 | 2018-08-07 | COMPLETE | 2019-05-07 | FY 18-19 | 43 |  | MATTHEW ULRICH | Paul Ditty
CNAS | 19P000197 | FS | SL5 PATCH AND PAINT OFFICE, LOBBY AND HALL | COLL BLDG NO | 0203B | 2018-08-21 | CANCELED BY CLIENT | 2019-05-07 |  | 44 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000184 | FS | SL5 REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES | GEOLOGY | 1270 | 2018-08-14 | COMPLETE | 2019-04-15 | FY 18-19 | 45 |  | LAURIE GRAHAM | Dan Lerman
CNAS | 19P000246 | FS | SL5 PHYSICS - PATCH AND PAINT | PHYSICS | 3007N | 2018-09-07 | COMPLETE | 2018-10-10 | FY 18-19 | 46 |  | MAYELA CASTILLO | Paul Ditty
CNAS | 19P000242 | FS | SL5 PAINT OFFICE | COLL BLDG NO | 210 | 2018-09-06 | COMPLETE | 2019-01-11 | FY 18-19 | 47 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000231 | FS | SL5 OLMH 1428 PATCH AND PAINT | OLMSTED | 1428 | 2018-08-30 | COMPLETE | 2019-01-11 | FY 18-19 | 48 |  | ANDREW CABRERO | Paul Ditty
CNAS | 19P000243 | FS | SL5 GENOMICS 1206 - PATCH AND PAINT WALLS | GENOMICS | 1206 | 2018-09-06 | COMPLETE | 2019-05-07 | FY 18-19 | 49 |  | AIMEE GONZALES | Paul Ditty
CNAS | 19P000285 | FS | SL5 PAINT AND PATCH PI OFFICE | ENTOMOLOGY | 269 | 2018-09-17 | COMPLETE | 2019-05-07 | FY 18-19 | 5 |  | WILLIAM SUTTON | Paul Ditty
CNAS | 19P000062 | FS | SL5 MSE 169-MINOR RENOVATION - NEW FACULTY | MAT SCI ENGR | 169 | 2018-07-30 | COMPLETE | 2019-02-01 | FY 18-19 | 5 | YES | MAYELA CASTILLO | Dan Lerman
CNAS | 19P000176 | FS | SL5 PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY | PHYSICS | 1112 | 2018-08-10 | COMPLETE | 2019-01-15 | FY 18-19 | 50 |  | MAYELA CASTILLO | Paul Ditty
CNAS | 19W003012 | FS | SL5 FIX RESTROOMS (PAINT AND FLOORS) | CHAPMAN | 5 | 2018-08-17 | CANCELED BY FS | 2018-12-13 |  | 51 |  | WILLIAM SUTTON | Paul Ditty
CNAS | 19P000126 | FS | SL5 CHEMICAL SCIENCE - MINOR RENOVATIONS | CHEMICAL SCI | 455 | 2018-08-03 | COMPLETE | 2018-12-14 | FY 18-19 | 6 | YES | KEVIN KOU | Dan Lerman
CNAS | 19P000616 | FS | SL5 COLLEGE BLDG NO, RM 208- PAINT | COLL BLDG NO | 208 | 2019-05-14 | CANCELED BY FS | 2019-07-16 |  | 6 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000230 | FS | SL5 NEW FACULTY OFFICE FOR PATCHWORK/PAINT | GEOLOGY | 1242A | 2018-08-30 | COMPLETE | 2018-10-10 | FY 18-19 | 7 | YES | KAREN CATO | Paul Ditty
CNAS | 19P000360 | FS | SL5 GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING | GEOLOGY | 1444 | 2018-10-29 | COMPLETE | 2019-03-04 | FY 18-19 | 7 |  | KAREN CATO | Paul Ditty
CNAS | 19P000617 | FS | SL5 COLLEGE BLDG NO, RM 212- PAINT | COLL BLDG NO | 212 | 2019-05-14 | CANCELED BY FS | 2019-07-16 |  | 7 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000251 | FS | SL5 CHEM SCI 428-PATCH DRY WALL HOLES | CHEMICAL SCI | 428 | 2018-09-10 | COMPLETE | 2018-10-10 | FY 18-19 | 8 | YES | KEVIN KOU | Paul Ditty
CNAS | 19P000369 | FS | SL5 PIERCE - PAINT IS PEELING OFF WALLS | PIERCE | 3341 | 2018-11-01 | COMPLETE | 2019-05-07 | FY 18-19 | 8 |  | MATTHEW ULRICH | Paul Ditty
CNAS | 19P000482 | FS | SL5 PIERCE HALL- PAINT/PATCH HOLES IN 1219C AND 1220D | PIERCE | 1219C | 2019-02-01 | COMPLETE | 2019-06-28 | FY 18-19 | 8 |  | JACQUELINE HAMILTON | Paul Ditty
CNAS | 19P000291 | FS | SL5 MSE HELIUM RECOVERY SYSTEM | MAT SCI ENGR | 205 | 2017-07-24 | COMPLETE | 2018-12-14 | FY 18-19 | 9 |  | MAYELA CASTILLO | Dan Lerman
CNAS | 19P000288 | FS | SL5 COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS | COLL BLDG NO | 202 | 2018-09-19 | COMPLETE | 2019-03-04 | FY 18-19 | 9 |  | RONDA INZUNZA | Paul Ditty
CNAS | 18P000221 | FS | SL5 Provide add'l HVAC capacity to maintain lower temp | BOYCE | 4414 | 2017-12-11 | COMPLETE | 2018-12-14 | FY 18-19 | 9 |  | APRIL MEINZER | Dan Lerman
CNAS | 19P000234 | FS | SL5 PHYSICS 3005-WALL HOLES PATCH | PHYSICS | 3005N | 2018-09-04 | CANCELED BY FS | 2018-09-19 |  | Canceled |  | JAZMIN CHAVEZ | Paul Ditty
CNAS | 19P000127 | FS | SL5 PIERCE PATCH & PAINT | PIERCE | 2301 | 2018-08-03 | CANCELED BY CLIENT | 2018-09-21 |  | Canceled |  | MICHELLE KING | N/A
CNAS | 19P000413 | FS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | BATCHELOR | 3111 | 2018-12-17 | CANCELED BY CLIENT |  |  | R1 |  | MATTHEW ULRICH | Dan Lerman
ENROLLMENT SERVICES | 19P000428 | FS | SL5 STUDENT SERVICES AVC OFFICE PREPARATION | STUDENT SERV | 3102 | 2019-01-03 | CANCELED BY CLIENT | 2019-01-22 |  | 0 |  | ANGIE GRAY
ENROLLMENT SERVICES | 19P000370 | FS | SL5 PATCH AND PAINT CAMPUS TOURS | STUDENT SERV | 1137 | 2018-11-01 | COMPLETE | 2019-02-01 | FY 18-19 | 1 |  | ELIZABETH TATUM | Paul Ditty
ENROLLMENT SERVICES | 19P000384 | FS | SL5 PATCH HOLES IN WALL AND PAINT | STUDENT SERV | 2234 | 2018-11-20 | COMPLETE | 2019-02-08 | FY 18-19 | 1 |  | CHRISTINE SMITH | Paul Ditty
FAC-PLNG-DESIGN-CONST | 19P000560 | FS | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION | UV BLDG B | 0240B | 2019-04-04 | COMPLETE |  |  | R1 |  | LESLIE ROSE | Dan Lerman
FAC-PLNG-DESIGN-CONST | 19P000645 | FS | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT | BOTANIC GARDENS |  | 2019-05-22 | CANCELED BY FS | 2019-08-29 |  | R2 |  | RONALD ANDERSON | DAN LERMAN
GRAD.DIV | 19P000411 | FS | SL5 PAINT, CARPET AND BLINDS | UNIV OFC BLD | 150 | 2018-12-14 | COMPLETE | 2019-03-04 | FY 18-19 | 1 | YES | CYNTHIA CARDENAS | Paul Ditty
GRAD.DIV | 19P000399 | FS | SL5 NEW CARPET + WALL PAINT | UNIV OFC BLD | 100 | 2018-12-06 | COMPLETE | 2019-05-07 | FY 18-19 | 2 |  | CYNTHIA CARDENAS | Paul Ditty
GSOE | 18P000313 | FS | SL5 SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 | SPROUL |  | 2018-02-15 | COMPLETE | 2018-10-22 | FY 18-19 |  |  | KAREN NAPLES | Dan Lerman
GSOE | 18P000274 | FS | SL5 SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 | EADY CENTER |  | 2018-01-18 | COMPLETE | 2019-02-14 | FY 18-19 |  |  | KAREN NAPLES | Dan Lerman
GSOE | 19P000054 | FS | SL5 PATCH & PAINT OFFICE | SPROUL | 2131 | 2018-07-26 | COMPLETE | 2018-10-10 | FY 18-19 | 1 | YES | KAREN NAPLES | Paul Ditty
GSOE | 19P000237 | FS | SL5 PATCH AND PAINT OFFICE - SPROUL 1206 | SPROUL | 1206 | 2018-09-05 | COMPLETE | 2019-04-15 | FY 18-19 | 2 |  | KAREN NAPLES | Dan Lerman
GSOE | 19P000217 | FS | SL5 PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 | SPROUL | 1359 | 2018-08-27 | COMPLETE | 2019-04-15 | FY 18-19 | 3 |  | KAREN NAPLES | Dan Lerman
GSOE | 19P000229 | FS | SL5 RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR | SPROUL |  | 2018-08-29 | COMPLETE | 2019-06-15 | FY 18-19 | 4 |  | KAREN NAPLES | Dan Lerman
ITS | 18W007453 | FS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. | ITS CENTER | 100 | 2017-11-30 | CANCELED BY FS | 2019-07-22 |  |  |  | SHEILA MABEE | Dan Lerman
ITS | 19P000293 | FS | SL5 PAINT ESTIMATE REQUEST | TELEPHONE |  | 2018-08-21 | CANCELED BY CLIENT | 2018-10-24 |  |  |  | TAMI FRIEDRICH | Paul Ditty
ITS | 18P000474 | FS | SL5 MS&E ELECTRICAL MODIFICATIONS FOR ITS | MAT SCI ENGR | 119 | 2018-06-13 | COMPLETE | 2019-03-28 | FY 18-19 |  |  | MICHAEL CAPRIOTTI | Robert Corey
ITS | 19W002419 | FS | SL5 ITS CENTER - INSTALL CARD READER ACCESS | ITS CENTER | 161 | 2018-08-09 | CANCELED BY FS | 2019-01-08 |  |  |  | SHEILA MABEE
ITS | 18P000471 | FS | SL5 WCH INSTALL SECURITY FENCE | CHUNG HALL | 134 | 2018-06-12 | COMPLETE | 2018-09-19 | FY 18-19 |  |  | TAMI FRIEDRICH | Dan Lerman
ITS | 19P000373 | FS | SL5 URGENT-INSTALL RECPTACLE, ENCLOSURE & MOUNT BRACKET | GERMPLASM | 881 | 2018-11-07 | COMPLETE | 2019-02-26 | FY 18-19 | 0 |  | TAMI FRIEDRICH | Dan Lerman
ITS | 18P000252 | FS | SL5 CHASS INT S REPLACE ELECTRICAL SCREENS | CHASS INT S | 2130 | 2017-12-21 | CANCELED BY CLIENT | 2019-01-24 |  | 1 |  | JORGE MACIAS | Dan Lerman
ITS | 18P000382 | FS | SL5 ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 | WATKINS |  | 2018-04-05 | COMPLETE | 2019-01-15 | FY 18-19 | 2 |  | PHYLLIS FRANCO | Dan Lerman
ITS | 18P000381 | FS | SL5 ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 | WATKINS |  | 2018-04-05 | COMPLETE | 2019-01-15 | FY 18-19 | 3 |  | SHEILA MABEE | Dan Lerman
ITS | 19P000021 | FS | SL5 ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS | ITS CENTER |  | 2018-07-12 | COMPLETE | 2019-04-15 | FY 18-19 | 4 |  | SHEILA MABEE | Dan Lerman
ITS | 18P000194 | FS | SL5 TELEPHONE WINDOW REPLACEMENT | TELEPHONE | 101 | 2017-11-20 | CANCELED BY CLIENT | 2018-10-19 |  | 5 |  | TAMI FRIEDRICH | Dan Lerman
LIBR | 18P000273 | FS | SL5 RIVERA LIB -RESTROOM REFRESH PROJECT | RIVERA LIB |  | 2018-01-18 | TO BE PERFORMED BY PD&C | 2018-12-13 |  | 1 |  | DAVID SCHUSTER | Dan Lerman
PLANNING & BUDGET | 18P000390 | FS | SL5 UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD | UV BLDG B | 0240B | 2018-04-10 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | LESLIE ROSE | Paul Ditty
PLANNING & BUDGET | 17P000254 | FS | SL5 FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS | CORP PP WHSE | 0106B | 2017-06-07 | CANCELED BY CLIENT | 2019-04-05 |  |  |  | DALAN DINH | Dan Lerman
PLANNING & BUDGET | 19P000209 | FS | SL5 OLD EH&S SITE- FS ANNEX A REMODEL | ENV H AND S | 100 | 2018-08-24 | COMPLETE | 2019-07-01 | FY 19-20 |  |  | FRANCES RAVE | Craig/Chris Pillen
PLANNING & BUDGET | 18P000324 | FS | SL5 HINDERAKER PATCH AND PAINT | HINDERAKER | 4118 | 2018-02-26 | COMPLETE | 2018-07-11 | FY 18-19 |  |  | MILLY PAREDEZ | Paul Ditty
PLANNING & BUDGET | 19P000241 | FS | SL5 PATCH/PAINT IN OFFICE 2122 HINDERAKER | HINDERAKER | 2122 | 2018-09-06 | CANCELED BY CLIENT | 2018-09-13 |  | 1 |  | MILLY PAREDEZ | Paul Ditty
PLANNING & BUDGET | 19P000401 | FS | SL5 PATCH HOLES IN WALL AND PAINT | HINDERAKER | 4148E | 2018-12-18 | COMPLETE | 2019-02-08 | FY 18-19 | 1 |  | SHANNON TIMMONS | Paul Ditty
PLANNING & BUDGET | 19P000425 | FS | SL5 PAINT VIDEO PRODUCTION SUITE & HANG ITEMS | HINDERAKER | 1159A | 2018-12-20 | COMPLETE | 2019-03-04 | FY 18-19 | 3 |  | LISA CUSICK | Paul Ditty
PLANNING & BUDGET | 19P000599 | FS | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS | CORP B | 126 | 2019-05-09 | COMPLETE | 2019-07-22 | FY 19-20 | R1 |  | HELMA AVILA | Paul Ditty
PLANNING & BUDGET | 19P000573 | FS | SL5 UNIVERSITY VILLAGE PAINT /REMOVE NAILS | UV BLDG B | 0208L | 2019-04-11 | CANCELED BY CLIENT | 2019-06-14 |  | R2 |  | JUDITH ABBEY | Paul Ditty
PLANNING & BUDGET - AUXILIARY | 19P000535 | FS | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV | BANNOCK H | H0108 | 2019-03-14 | COMPLETE | 2019-07-26 | FY 19-20 | R1 |  | EDWIN MELGAR-MEJIA | DAN LERMAN
PROVOST/EVC | 19P000386 | FS | SL5 ROOM CHANGES | STUDENT SERV | 3106A | 2018-11-20 | COMPLETE | 2019-04-15 | FY 18-19 | 0 |  | STEPHANIE ARCINIEGA | Dan Lerman
PROVOST/EVC | 19P000434 | FS | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | SKYE HALL | 136 | 2019-01-07 | COMPLETE | 2019-07-22 | FY 19-20 | 2 |  | THERESA WAGNER | Paul Ditty
SoB | 19P000017 | FS | SL5 ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD | ANDERSON 1 (N) | 0001B | 2018-07-11 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | ANGELA CHANG | Dan Lerman
SoB | 18P000482 | FS | SL5 CARD ACCESS SYSTEM ANDERSON SOUTH | ANDERSON 2 (S) |  | 2018-06-26 | COMPLETE | 2018-08-02 | FY 18-19 |  |  | ANGELA CHANG | Dan Lerman
SoB | 19P000053 | FS | SL5 ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S | ANDERSON 1 (N) |  | 2018-04-13 | COMPLETE | 2018-10-22 | FY 18-19 |  |  | ANGELA CHANG | Dan Lerman
SoB | 18P000428 | FS | SL5 OLMSTED RM 2352 PATCH/PAINT | OLMSTED | 2352 | 2018-05-02 | COMPLETE | 2018-08-17 | FY 18-19 |  |  | ANGELA CHANG | Paul Ditty
SoB | 18P000351 | FS | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | ANDERSON 2 (S) | 21 | 2018-03-19 | COMPLETE | 2019-08-01 | FY 19-20 |  |  | ANGELA CHANG | Dan Lerman
SoB | 19P000033 | FS | SL5 OLMSTED PATCH/PAINT | OLMSTED | 2301 | 2018-07-16 | CANCELED BY CLIENT | 2018-10-01 |  |  |  | ANGELA CHANG | Paul Ditty
SoB | 19P000018 | FS | SL5 ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER | ANDERSON 1 (N) | 0001B | 2018-07-11 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | ANGELA CHANG | Paul Ditty
SoB | 18P000463 | FS | SL5 ANDERSON HALL PATCH/PAINT-102C | ANDERSON 1 (N) | 0102C | 2018-06-04 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | ANGELA CHANG | Paul Ditty
SoB | 19P000521 | FS | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT | ANDERSON 1 (N) | 138 | 2019-03-08 | COMPLETE | 2019-07-09 | FY 19-20 | 1 |  | ANGELA CHANG | Paul Ditty
SoB | 19P000030 | FS | SL5 OLMSTED PATCH/PAINT | OLMSTED | 2301 | 2018-07-16 | COMPLETE | 2018-10-10 | FY 18-19 | 1 |  | ANGELA CHANG | Paul Ditty
SOB | 19P000451 | FS | SL5 ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 | ANDERSON 1 (N) | 58 | 2019-01-15 | COMPLETE | 2019-02-01 | FY 18-19 | 1 | YES | ANGELA CHANG | Paul Ditty
SoB | 19P000280 | FS | SL5 ANDERSON HALL PAINT ONLY | ANDERSON 2 (S) | 113 | 2018-09-13 | COMPLETE | 2019-02-01 | FY 18-19 | 2 |  | ANGELA CHANG | Paul Ditty
SoB | 19P000353 | FS | SL5 OLMSTED PATCH/PAINT-2348 | OLMSTED | 2340 | 2018-10-19 | COMPLETE | 2019-05-07 | FY 18-19 | 3 |  | ANGELA CHANG | Paul Ditty
SOM | 18W006022 | FS | INSTALL CURTAIN ROD IN RESEARCH SPACE | SOM RSCH | 336 | 2017-10-27 | COMPLETE | 2018-07-11 | FY 18-19 |  |  | TARA BARTHOL | Dan Lerman
SOM | 18P000380 | FS | SL5 SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | SOM RSCH | 330 | 2018-04-05 | CANCELED BY CLIENT | 2018-08-22 |  |  |  | TARA BARTHOL | Dan Lerman
SOM | 18P000261 | FS | SL5 WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR | WEBBER | 1143 | 2017-12-22 | COMPLETE | 2018-09-10 | FY 18-19 |  |  | LOURDES ESCAMILLA | Dan Lerman
SOM | 19S000833 | FS | Add access control to entry doors | HECKMAN ICEM | Entry Doors | 2018-07-17 | CANCELED BY CLIENT | 2018-09-19 |  |  |  | BRANDON BARBOSA | Dan Lerman
SOM | 18P000400 | FS | SL5 Covert suite 1116 and suite 1126 to office space | WEBBER | 1116 & 1126 | 2018-04-14 | CANCELED BY FS | 2018-07-10 |  |  |  | BRANDON BARBOSA | Dan Lerman
SOM | 19P000009 | FS | SL5 SOME -- PAINT, SPACKLE AND CLEANING NEEDED | SOM EDUC | 2615 | 2018-07-02 | COMPLETE | 2018-10-10 | FY 18-19 | 1 | YES | BEVERLEY HERBERT | Paul Ditty
SOM | 19P000354 | FS | SL5 WEBBER 2130A-PAINT CHERI'S NEW OFFICE | WEBBER | 2130A | 2018-10-19 | COMPLETE | 2019-05-07 | FY 18-19 | 1 |  | DOMINIC SALAZAR | Paul Ditty
SOM | 19P000408 | FS | SL5 PATCH & PAINT - 2605 SOM ED | SOM EDUC | 2605 | 2018-12-12 | COMPLETE | 2019-02-08 | FY 18-19 | 1 | YES | DEBORAH TRUJILLO | Paul Ditty
SOM | 19P000410 | FS | SL5 PAINT OFFICES AT UC PATH | INTELLICTR |  | 2018-12-14 | CANCELED BY CLIENT | 2019-06-06 |  | 2 |  | DEBORAH TRUJILLO | Paul Ditty
SOM | 19P000248 | FS | SL5 SOME--SOME INSTALL ELECTRICAL 1682 | SOM EDUC | 1682 | 2018-09-10 | COMPLETE | 2019-02-14 | FY 18-19 | 2 |  | DEBORAH TRUJILLO
SOM | 19P000249 | FS | SL5 SOME-INSTALL LOCKERS | SOM EDUC |  | 2018-09-07 | CANCELED BY FS | 2019-02-01 |  | 3 |  | DEBORAH TRUJILLO | Dan Lerman
SOM | 19P000245 | FS | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY | SOM RSCH |  | 2018-09-07 | COMPLETE | 2019-07-01 | FY 19-20 | 4 |  | DEBORAH TRUJILLO | Dan Lerman
SOM | 19P000032 | FS | SL5 Reconfigure recepetion desk to fit two FTEs. | SOM EDUC | 2608 | 2018-07-17 | COMPLETE | 2019-05-01 | FY 18-19 | 5 |  | BRANDON BARBOSA | Dan Lerman
SOM | 18P000485 | FS | SL5 SOMR PATCHING AND PAINTING | SOM RSCH |  | 2018-06-28 | COMPLETE | 2018-10-10 | FY 18-19 | 6 | YES | DANA ABOU ABBAS | Paul Ditty
SOM | 19P000012 | FS | SL5 SOME--PATCH & PAINT | SOM EDUC | 2638 | 2018-07-06 | COMPLETE | 2018-10-10 | FY 18-19 | 7 | YES | MARISELA MARTINEZ | Paul Ditty
SOM | 19P000014 | FS | SL5 SOME - PATCH & PAINT | SOM EDUC | 2609 | 2018-07-09 | COMPLETE | 2018-10-10 | FY 18-19 | 8 | YES | MARISELA MARTINEZ | Paul Ditty
SPP | 18P000470 | FS | SL5 Student Check-in Lobby | CHASS INT S | 4133 Corridor | 2018-06-11 | COMPLETE | 2018-08-23 | FY 18-19 |  |  | LUIS ALVAREZ | Dan Lerman
SPP | 19P000458 | FS | SL5 CHASS INTS-BUILD PERM DRYWALL DIVIDER OR APPROVE BKM AIRWALL | CHASS INT S | 4146 | 2019-01-19 | COMPLETE | 2019-06-17 | FY 18-19 | 0 |  | LUIS ALVAREZ | Dan Lerman
SPP | 19P000255 | FS | SL5 CHASS INT N REMODEL - 4022 PATCH AND PAINT | CHASS INT N | 4022 | 2018-09-10 | COMPLETE | 2018-10-10 | FY 18-19 | 1 | YES | CHRISTINA WONG | Paul Ditty
SPP | 19P000263 | FS | SL5 CHASS NORTH REMODEL - 4009 PATCH AND PAINT | CHASS INT N | 4009 | 2018-09-11 | COMPLETE | 2018-11-08 | FY 18-19 | 2 | YES | CHRISTINA WONG | Paul Ditty
SPP | 19P000256 | FS | SL5 CHASS REMODEL - 4146 PATCH AND PAINT | CHASS INT S | 4146 | 2018-09-10 | COMPLETE | 2019-01-04 | FY 18-19 | 3 | YES | CHRISTINA WONG
SPP | 18P000270 | FS | SL5 CHASS INT S- EVALUATION FOR REMODEL | CHASS INT S | 4133 | 2018-01-16 | CANCELED BY CLIENT | 2018-04-24 |  | 4 | YES | CHRISTINA WONG | Dan Lerman
UNDERGRAD ED | 18P000478 | FS | SL5 CARPET, PAINT, & AIR HANDLING MODIFICATION | HINDERAKER | 1120H | 2018-06-16 | COMPLETE | 2018-10-22 | FY 18-19 |  |  | TRACEY SCHOLTEMEYER | Dan Lerman
VC-RED | 18P000442 | FS | SL5 FAWCETT LAB 203 PATCH & PAINT | FAWCETT LAB | 203 | 2018-05-18 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | CRYSTAL JIMENEZ | Paul Ditty
VC-RED | 18W015691 | FS | SL5 BOYCE CONNECT WASHER AND DRYER | BOYCE | 6444 | 2018-05-30 | COMPLETE | 2018-07-11 | FY 18-19 |  |  | DIERK BIGGS
VC-RED | 18P000476 | FS | SL5 BOYCE CONNECT WASHER & DRYER | BOYCE | 6444 | 2018-06-14 | CANCELED BY CLIENT | 2018-07-11 |  |  |  | DIERK BIGGS | Dan Lerman
VC-RED | 18W013973 | FS | SL5 BSL3 FACILITY- ASSEMBLE AND INSTALL | UNIV OFC BLD |  | 2018-04-19 | COMPLETE | 2018-09-24 | FY 18-19 |  |  | CRYSTAL JIMENEZ | Enrico Baez
VC-RED | 18P000379 | FS | SL5 UOB PATCH AND PAINT | UNIV OFC BLD |  | 2018-04-05 | COMPLETE | 2018-08-24 | FY 18-19 |  |  | CRYSTAL JIMENEZ | Paul Ditty
VC-RED | 19P000553 | FS | SL5 SPIETH HALL PATCH AND PAINT | SPIETH | 341 | 2019-04-01 | COMPLETE | 2019-07-26 | FY 19-20 | 1 |  | JOHNNY PHAN | Paul Ditty
VC-RED | 19P000439 | FS | SL5 SPIETH PATCH AND PAINT ROOM 335 | SPIETH | 335 | 2019-01-08 | COMPLETE | 2019-03-04 | FY 18-19 | 1 |  | JOHNNY PHAN | Paul Ditty
VC-RED | 19P000044 | FS | SL5 PATCH AND PAINT | SPIETH | 345 | 2018-07-23 | COMPLETE | 2018-10-10 | FY 18-19 | 1 |  | JOHNNY PHAN | Paul Ditty
VC-RED | 19P000495 | FS | SL5 UOB RM 209- PATCH & PAINT | UNIV OFC BLD | 209 | 2019-02-08 | COMPLETE |  |  | 2 |  | CRYSTAL JIMENEZ | Paul Ditty
VC-RED | 19W003050 | FS | SL5 SPEITH HALL - PATCH & PAINT HOLE IN WALL | SPIETH | 0359A | 2018-08-21 | COMPLETE | 2018-10-10 | FY 18-19 | 2 |  | JOHNNY PHAN | Paul Ditty
VC-RED | 19P000181 | FS | SL5 PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS | UNIV OFC BLD | 249 | 2018-08-14 | COMPLETE | 2018-10-19 | FY 18-19 | 4 |  | GLORIA GALLEGO | Paul Ditty
VC-STU.AFF. | 18P000215 | FS | SL5 STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 | HEALTH SERV |  | 2017-12-08 | COMPLETE | 2019-06-17 | FY 18-19 |  |  | PAMELA HAGGINS | Dan Lerman
VC-STU.AFF. | 18P000456 | FS | SL5 HUB--UTILITY METERS | HUB |  | 2018-05-30 | TO BE PERFORMED BY PD&C | 2019-01-24 |  |  |  | BRENDAN OBRIEN | Dan Lerman
VC-STU.AFF. | 18P000337 | FS | SL5 MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET | HEALTH SERV | 414 | 2018-03-12 | COMPLETE | 2018-12-14 | FY 18-19 |  |  | GLORIA VERA | Dan Lerman
VC-STU.AFF. | 19P000431 | FS | SL5 STUDENT SERVICES REMOVE NAILS AND PATCH WALL | STUDENT SERV | 2128 | 2019-01-04 | CANCELED BY CLIENT | 2019-06-24 |  | 1 |  | VALERIE SANCHEZ | Paul Ditty
VC-STU.AFF. | 19P000380 | FS | SL5 PATCH AND PAITN- WALL PAINT IS PEELING | HEALTH SERV | 404 | 2018-11-19 | COMPLETE | 2019-03-04 | FY 18-19 | 1 |  | SAMANTHA HARRIS | Paul Ditty
VC-STU.AFF. | 19P000405 | FS | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED | HEALTH SERV | 0100D | 2018-12-11 | COMPLETE | 2019-05-07 | FY 18-19 | 2 |  | PAMELA BOCKSTADTER | Paul Ditty
VC-STU.AFF. | 18P000348 | FS | SL5 HUB ADD 3RD FLOOR WALLS | HUB | 0353E | 2018-03-18 | TO BE PERFORMED BY PD&C | 2019-02-01 |  | 2 |  | BRENDAN OBRIEN | Dan Lerman
VC-STU.AFF. | 19P000037 | FS | SL5 HEALTH SERVICE BLDG--PATCH WORK AND PAINTING | HEALTH SERV |  | 2018-07-17 | COMPLETE | 2018-10-22 | FY 18-19 | 3 |  | GLORIA VERA | Paul Ditty
VC-STU.AFF. | 19P000124 | FS | SL5 PAINT ROOMS 115 AND 116 | COSTO HALL | 125 | 2018-08-02 | COMPLETE | 2018-10-22 | FY 18-19 | 4 |  | LINDA KELLEY | Paul Ditty
VC-STU.AFF. | 19P000172 | FS | SL5 HEALTH SERV- PAINT RESTROOM IN LABORATORY | HEALTH SERV | 0113A | 2018-08-09 | COMPLETE | 2018-11-08 | FY 18-19 | 5 |  | PAMELA BOCKSTADTER | Paul Ditty
VC-UNIV.ADV. | 19P000238 | FS | SL5 PATCH & PAINT HINDERAKER 1136 | HINDERAKER | 1136 | 2018-09-05 | COMPLETE | 2019-01-11 | FY 18-19 | 1 |  | NAYSIA CALDWELL | Paul Ditty
VC-UNIV.ADV. | 18P000281 | FS | SL5 ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS | ALUM VISITOR | 2202 | 2018-01-24 | COMPLETE | 2019-03-28 | FY 18-19 | 2 |  | TRUDY COHEN | John Peraino
VC-UNIV.ADV. | 19P000326 | FS | SL5 HINDERAKER - PATCH & PAINT | HINDERAKER | 1136 | 2018-10-08 | COMPLETE | 2019-02-08 | FY 18-19 | 2 |  | NAYSIA CALDWELL | Paul Ditty
VC-UNIV.ADV. | 19P000417 | FS | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY | UV BLDG A | 201 | 2018-12-18 | CANCELED BY CLIENT |  |  | R1 |  | NAYSIA CALDWELL | DAN LERMAN

## Data Validation (hidden)
|  | 1 |  | Data As Of (Scheduled Data Pull) | Date of Previous Report | Proj_Mgr | PM_Ph | PM_Email | Dept |  |  |  |  | CAAN | Official | Building | CNC
0 | 18P000346 | 3052 | 3052 | 2018-10-31 | 2018-10-15 | B. Wilson/J. Franklin | 951-827-1485 | blythe.wilson@ucr.edu | PDC | A | 1 | Project Ref No. | Proj_Ref_No | P5186 | BIOLOGICAL SCIENCES | BIOLOGIC SCI | CORE
0 | 18P000484 |  |  | 2018-11-16 | 2018-10-31 | Blair Fickett |  |  | PDC | B | 2 |  | CPMS_No | P5187 | LATH HOUSE BUILDING B | LATH B FLD16 | CORE
0 | 18P000328 |  |  | 2018-12-01 | 2018-11-16 | Blythe Wilson | 951-827-1485 | blythe.wilson@ucr.edu | PDC | C | 3 |  | Work_Order_No | P5188 | MITE WASHER BUILDING C | MITE C FLD16 | CORE
0 | 19P000027 |  |  | 2018-12-16 | 2018-12-01 | CAS |  |  | PDC | D | 4 |  | IRT | P5189 | COMMON COVERED WORKHOUSE BLDG A (PART OF WEST CAMPUS I&Q) | COM WRK FD16 | NON-CORE
0 | 19P000265 |  |  | 2019-01-01 | 2018-12-16 | Chris Pillen | 951-827-4214 | christopher.pillen@ucr.edu | FS | E | 5 | Organization | Org | P5190 | PLANT TRANSFORMATION FACILITY | PLANT TRANSF | CORE
0 | 19P000646 |  |  | 2019-01-16 | 2019-01-01 | Cliff Stokes |  |  | FORMER | F | 6 | Project Title | Project_Title | P5192 | EAST CAMPUS INSECTARY AND QUARANTINE FACILITY GREENHOUSE | EAST I&Q GH | CORE
0 | 19P000277 |  |  | 2019-02-01 | 2019-01-16 | Craig/Chris Pillen | 951-827-4214 | christopher.pillen@ucr.edu | FS | G | 7 | Project Description | Project_Description | P5194 | WINSTON CHUNG HALL | CHUNG HALL | CORE
0 | 19P000271 |  |  | 2019-02-16 | 2019-02-01 | D. Hecht/J. Franklin | 951-827-7358 | drew.hecht@ucr.edu | PDC | H | 8 | Building | t_CPMS_Data.Building | P5195 | MATERIALS SCIENCE & ENGINEERING | MAT SCI ENGR | CORE
0 | 19P000295 |  |  | 2019-03-01 | 2019-02-16 | Dan Lerman | 951-827-6224 | daniel.lerman@ucr.edu | FS | I | 9 |  | t_Building.Building | P5196 | GENOMICS BUILDING | GENOMICS | CORE
0 | 19P000272 |  |  | 2019-03-16 | 2019-03-01 | Daryl Korluck |  |  | FORMER | J | 10 | Room | Room | P5197 | ALUMNI & VISITORS CENTER | ALUM VISITOR | NON-CORE
0 | 19P000270 |  |  | 2019-04-01 | 2019-03-16 | Dave Bomba | 951-827-1412 | dave.bomba@ucr.edu | PDC | K | 11 | Current Status | Current_Status | P5198 | UCR CHILD DEVELOPMENT CENTER NORTH | CHILD DEV N | CORE
0 | 19P000274 |  |  | 2019-04-16 | 2019-04-01 | Drew Hecht | 951-827-7358 | drew.hecht@ucr.edu | PDC | L | 12 |  | Org_Name | P5199 | HIGHLANDER UNION 2 ACTIVITY CENTER | HUB 2 | NON-CORE
0 | 19P000276 |  |  | 2019-05-01 | 2019-04-16 | Enrico Baez | 951-827-4214 | enrico.baez@ucr.edu | FS | M | 13 | Organization Leader | Org_Leadership | P5200 | GREENHOUSE #9 | GH09 | CORE
0 | 19P000266 |  |  | 2019-05-16 | 2019-05-01 | Enrico Baez - Managing Contractor | 951-827-4214 | enrico.baez@ucr.edu | FS | N | 14 | Prioritization Designate | Org_Contact | P5205 | UNIVERSITY OFFICE BUILDING | UNIV OFC BLD | CORE
0 | 19P000647 |  |  | 2019-06-01 | 2019-05-16 | Fernando Nunez | 951-827-2466 | fernando.nunez@ucr.edu | PDC | O | 15 | Contact | Contact | P5210 | GREENHOUSE #15 | GH15 | CORE
0 | 19P000252 |  |  | 2019-06-16 | 2019-06-01 | George MacMullin |  |  | FORMER | P | 16 |  | Contact_2 | P5215 | HOMER D. CHAPMAN HALL | CHAPMAN | CORE
0 | 19P000268 |  |  | 2019-07-01 | 2019-06-16 | Jacqueline Norman | 951-827-6316 | jacqueline.norman@ucr.edu | PDC | Q | 17 | Project Manager | Proj_Mgr | P5216 | CHICKEN COOP #1 | CHICK COOP 1 | NON-CORE
0 | 19P000269 |  |  | 2019-07-16 | 2019-07-01 | Jason Williams |  | jason.williams@ucr.edu | FS | R | 18 | PD&C Org Priority No. | Org_Priority | P5217 | PHYSICAL PLANT STORAGE UNIT | PHYS PL STOR | CORE
0 | 19P000275 |  |  | 2019-08-01 | 2019-07-16 | Jerrod Walters | 951-827-6955 | jerrod.walters@ucr.edu | PDC | S | 19 | FS Org Priority No. | FS_Priority | P5218 | THE COTTAGE | COTTAGE | NON-CORE
0 | 19P000309 |  |  | 2019-08-16 | 2019-08-01 | Jess Hernandez | 951-827-4214 | jesus.hernandez@ucr.edu | FS | T | 20 | For Faculty Hire | For_Faculty_Hire | P5219 | WORKMAN'S COTTAGE #2 | WORKMN COT 2 | NON-CORE
0 | 19P000273 |  |  | 2019-09-01 | 2019-08-16 | John Franklin | 951-827-6953 | john.franklin@ucr.edu | PDC | U | 21 | PD&C Approved Budget | Approved_Budget | P5220 | WORKMAN'S COTTAGE #3 | WORKMN COT 3 | NON-CORE
0 | 19P000311 |  |  | 2019-09-16 | 2019-09-01 | John Peraino | 951-827-2121 | john.peraino@ucr.edu | FS | V | 22 | FS Recharge Actuals To Date | FS_Recharge_Costs | P5224 | UNIVERSITY BOOKSTORE | BOOKSTORE | NON-CORE
0 | 3407 |  |  | 2019-10-01 | 2019-09-16 | Marianne Valenti |  |  | FORMER | W | 23 | Request Date | Project_Initiated | P5230 | STORAGE SHED #8 | STOR 8 | CORE
0 | 2696 |  |  | 2019-10-16 | 2019-10-01 | Mihai Gavan | 951-827-6959 | mihai.gavan@ucr.edu | PDC | X | 24 | Next Steps | Next_Major_Milestone | P5231 | COLLEGE BUILDING SOUTH | COLL BLDG SO | CORE
0 | 3408 |  |  | 2019-11-01 | 2019-10-16 | Mihai Gavan-MRB1 |  | mihai.gavan@ucr.edu | PDC | Y | 25 | Start Date | Const_Start | P5241 | ENVIRONMENTAL HEALTH AND SAFETY BUILDING | ENV H AND S | CORE
0 | 18W009630 |  |  | 2019-11-16 | 2019-11-01 | N/A | 951-827-4214 |  |  | Z | 26 | Complete Date | Construction_Completion | P5242 | LATHHOUSE #1 | LATH 1 | CORE
0 | 18P000094 |  |  | 2019-12-01 | 2019-11-16 | Not Assigned | 951-827-4214 |  |  | AA | 27 | Impact Description | Impact_Description | P5251 | THEATRE WORKSHOP | THTR WKSH | CORE
0 | 18P000369 |  |  | 2019-12-16 | 2019-12-01 | Paul Ditty | 951-827-4214 | paul.ditty@ucr.edu | FS | AB | 28 | Impact Date Start | Impact_Date_Start | P5253 | MAIL BUILDING | MAIL | CORE
0 | 18P000282 |  |  | 2020-01-01 | 2019-12-16 | R. Amescua/D. Hecht |  | raoul.amescua@ucr.edu | PDC | AC | 29 | Impact Date End | Impact_Date_End | P5254 | BOTANIC GARDENS INFORMATION CENTER | BOTAN INFO C | NON-CORE
0 | 18W011772 |  |  | 2020-01-16 | 2020-01-01 | R. Amescua/J. Kaplan |  | raoul.amescua@ucr.edu | PDC | AD | 30 | Project Service Unit | PM_Notes | P5255 | BOTANY & PLANT SCIENCES FIELDHOUSE FIELD 15A | BOT FLDHS15A | NON-CORE
0 | 18P000373 |  |  | 2020-02-01 | 2020-01-16 | Raoul Amescua | 951-827-6951 | raoul.amescua@ucr.edu | PDC | AE | 31 |  | PM_Date | P5256 | ENTOMOLOGY MUSEUM | ENTOM MUSEUM | CORE
0 | 18P000459 |  |  | 2020-02-16 | 2020-02-01 | Robert Corey |  |  | FORMER | AF | 32 |  | Scope_Date | P5258 | GLASSHOUSE FIELD 16 #45 | GH 16 45 | CORE
0 | 18P000432 |  |  | 2020-03-01 | 2020-02-16 | Ron Veloz | 951-827-4214 | ron.veloz@ucr.edu | FS | AG | 33 |  | Scope_Reviewer | P5259 | GREENHOUSE #2A | GH02A | CORE
0 | 19P000208 |  |  | 2020-03-16 | 2020-03-01 | Rowan Reid | 951-827-5825 | rowan.reid@ucr.edu | PDC | AH | 34 |  | Scope_Notes | P5260 | GLASSHOUSE FIELD 16 #46 | GH 16 46 | CORE
0 | 19P000247 |  |  | 2020-04-01 | 2020-03-16 | Scott Donnell | 951-827-4706 | scott.donnell@ucr.edu | PDC | AI | 35 |  | Scope_Complete | P5261 | MARLAN & ROSEMARY BOURNS HALL | BOURNS | CORE
0 | 19P000222 |  |  | 2020-04-16 | 2020-04-01 | Tameesha Hayes |  |  | FORMER | AJ | 36 |  | Owner | P5263 | UNIVERSITY LABORATORY BUILDING | UNIV LAB BLD | CORE
0 | 19P000317 |  |  |  |  | Uma R. | 951-827-5610 | uma.ramasubramanian@ucr.edu | PDC | AK | 37 |  | IRT? | P5265 | TRAILER #10A | T10A | CORE
0 | 18P000106 |  |  |  |  | xxxxx |  |  |  | AL | 38 |  | Requested Year | P5266 | TRAILER #9A | T9A | CORE
0 | 19P000192 |  |  |  |  | Yvonne Lujan | 951-827-5154 | yvonne.lujan@ucr.edu | PDC | AM | 39 |  | Data Pulled On | P5267 | GLASSHOUSE FIELD 16 #26 | GH 16 26 | CORE
0 | 19P000236 | [12 empty] | P5268 | STORAGE SHED #5 | STOR 5 | CORE
0 | 19P000235 | [12 empty] | P5269 | GLASSHOUSE FIELD 16 #27 | GH 16 27 | CORE
0 | 19P000015 | [12 empty] | P5270 | GARAGE COTTAGE #3 | GAR C3 | CORE
0 | 19P000233 | [12 empty] | P5271 | BARN STABLE | BARN STABLE | NON-CORE
0 | 18P000363 | [12 empty] | P5272 | PARKING SERVICES BUILDING | PARKING SERV | NON-CORE
0 | 19P000227 | [12 empty] | P5273 | GLASSHOUSE FIELD 16 #22 | GH 16 22 | CORE
0 | 19P000224 | [12 empty] | P5274 | GARAGE COTTAGE #1 | GAR C1 | CORE
0 | 19P000308 | [12 empty] | P5275 | GREENHOUSE #6 | GH06 | CORE
0 | 19P000307 | [12 empty] | P5276 | GREENHOUSE #7 | GH07 | CORE
0 | 19P000232 | [12 empty] | P5277 | GREENHOUSE #8 | GH08 | CORE
0 | 18P000483 | [12 empty] | P5278 | GREENHOUSE #10 | GH10 | CORE
0 | 19P000022 | [12 empty] | P5279 | GREENHOUSE #11 | GH11 | CORE
0 | 19P000215 | [12 empty] | P5280 | GREENHOUSE #12 | GH12 | CORE
0 | 18P000095 | [12 empty] | P5281 | GREENHOUSE #13 | GH13 | CORE
0 | 19P000687 | [12 empty] | P5282 | GREENHOUSE #21 | GH21 | CORE
0 | 3430 | [12 empty] | P5284 | GREENHOUSE #16 | GH16 | CORE
0 | 3354 | [12 empty] | P5285 | RESTROOMS & TICKET BOOTH BUILDING | TICKET BOOTH | CORE
0 | 3376 | [12 empty] | P5286 | RESTROOM / MAINTENANCE | RSTRM/MAINT | CORE
0 | 3383 | [12 empty] | P5287 | STORAGE BUILDING PLANT PATHOLOGY FIELD 16E | STOR PL PATH | CORE
0 | 3453 | [12 empty] | P5288 | NEMATOLOGY MICROPLOT STORAGE BUILDING FIELD 15A | NEM MICRO ST | CORE
0 | 3459 | [12 empty] | P5289 | EAST CAMPUS INSECTARY AND QUARANTINE FACILITY | EAST I&Q FAC | CORE
0 | 3462 | [12 empty] | P5290 | HAY BARN | HAY BN | CORE
0 | 3463 | [12 empty] | P5291 | TURF PLOT STORAGE AGRICULTURAL OPERATIONS | TURF PL STOR | CORE
0 | 3460 | [12 empty] | P5292 | STORAGE BUILDING AT LOADING DOCK OF PIERCE HALL | STOR PRCE | CORE
0 | 3467 | [12 empty] | P5293 | GLASSHOUSE FIELD 16 #25 | GH 16 25 | CORE
0 | 3466 | [12 empty] | P5295 | CENTRAL UTILITY PLANT | CNTRL UTL PL | CORE
0 | 3382 | [12 empty] | P5296 | GLASSHOUSE FIELD 16 #9 | GH 16 09 | CORE
0 | 2868 | [12 empty] | P5297 | GLASSHOUSE FIELD 16 #23 | GH 16 23 | CORE
0 | 3392 | [12 empty] | P5298 | SHED BUILDING FIELD 16 #25 | SHED 16 25 | CORE
0 | 3472 | [12 empty] | P5299 | GLASSHOUSE FIELD 16 #10 | GH 16 10 | CORE
0 | 3397 | [12 empty] | P5300 | GLASSHOUSE FIELD 16 #11 | GH 16 11 | CORE
0 | 3203 | [12 empty] | P5302 | EQUIPMENT SHED | EQUIP SHED | CORE
0 | 3490 | [12 empty] | P5304 | INSECTICIDE COMPOUNDING & STORAGE BUILDING | INSECT COMP | CORE
0 | 3503 | [12 empty] | P5305 | STORED PRODUCTS INSECTICIDE BUILDING | SPI | CORE
0 | 2508 | [12 empty] | P5307 | HUMANITIES & SOCIAL SCIENCES | HUM & SOC SC | CORE
0 | 3519 | [12 empty] | P5308 | SOUTH LOCKERROOM & CONCESSION STAND | S LCKRM/CONC | CORE
0 | 3421 | [12 empty] | P5310 | WEST LOCKERROOM & CLUBHOUSE CONCESSION STAND | W LCKRM/CONC | CORE
0 | 3426 | [12 empty] | P5311 | JEANETTE AND RUPERT COSTO HALL | COSTO HALL | NON-CORE
0 | 3533 | [12 empty] | P5312 | LATHHOUSE #32 | LATH 32 | CORE
0 | 3286 | [12 empty] | P5315 | LATHHOUSE #36 | LATH 36 | CORE
0 | 19P000028 | [12 empty] | P5316 | LIFE SCIENCES | LIFE SCIENCE | CORE
0 | 18P000349 | [12 empty] | P5319 | HERBARIUM | HERBARIUM | CORE
0 | 18P000321 | [12 empty] | P5321 | STORAGE SHED #37 | STOR 37 | CORE
0 | 18P000315 | [12 empty] | P5322 | TOMAS RIVERA LIBRARY | RIVERA LIB | CORE
0 | 18P000472 | [12 empty] | P5323 | HERMAN T. SPIETH HALL | SPIETH | CORE
0 | 18P000427 | [12 empty] | P5324 | STORAGE SHED #49 | STOR 49 | CORE
0 | 18P000454 | [12 empty] | P5325 | A. GARY ANDERSON HALL 1 | ANDERSON 1 | CORE
0 | 18P000394 | [12 empty] | P5326 | COBALT 60 BUILDING #38 | COBALT 60 | CORE
0 | 18P000425 | [12 empty] | P5327 | PHYSICAL PLANT STORAGE UNIT 2 | PHYS PL STR2 | CORE
0 | 18P000429 | [12 empty] | P5328 | HAZARDOUS WASTE STORAGE UNIT 1 | HAZ WST STR1 | CORE
0 | 18P000426 | [12 empty] | P5329 | HAZARDOUS WASTE STORAGE UNIT 2 | HAZ WST STR2 | CORE
0 | 18P000267 | [12 empty] | P5330 | TRAILER #21 3984 | T21 3984 | CORE
0 | 18P000391 | [12 empty] | P5334 | ATHLETICS AND DANCE BUILDING | ATH DANCE | CORE
0 | 19P000388 | [12 empty] | P5335 | GEOLOGY BUILDING | GEOLOGY | CORE
0 | 19P000445 | [12 empty] | P5336 | GLASSHOUSE FIELD 16 #24A | GH 16 24A | CORE
0 | 19P000278 | [12 empty] | P5337 | GLASSHOUSE FIELD 16 #24B | GH 16 24B | CORE
0 | 19P000638 | [12 empty] | P5338 | GLASSHOUSE FIELD 16 #24C | GH 16 24C | CORE
0 | 19P000619 | [12 empty] | P5339 | GLASSHOUSE FIELD 16 #24D | GH 16 24D | CORE
0 | 19P000453 | [12 empty] | P5340 | PUMPHOUSE #2 | PUMP 2 | CORE
0 | 19P000059 | [12 empty] | P5341 | ALFRED M. BOYCE HALL | BOYCE | CORE
0 | 19P000621 | [12 empty] | P5342 | HERBERT JOHN WEBBER HALL | WEBBER | CORE
0 | 19P000477 | [12 empty] | P5343 | ABERDEEN-INVERNESS RESIDENCE HALL | ABER INVER | NON-CORE
0 | 19P000029 | [12 empty] | P5344 | GLASSHOUSE FIELD 16 #28 | GH 16 28 | CORE
0 | 19P000316 | [12 empty] | P5345 | ASBESTOS ABATEMENT & EMERGENCY RESPONSE EQUIP/SUPPLY | ABAT EMG RSP | NON-CORE
0 | 19P000046 | [12 empty] | P5346 | DECAY STORAGE UNIT 1 | DECAY STOR 1 | CORE
0 | 19P000442 | [12 empty] | P5347 | DECAY STORAGE UNIT 2 | DECAY STOR 2 | CORE
0 | 19P000487 | [12 empty] | P5348 | WAREHOUSE #2 | WHSE 2 | CORE
0 | 19P000600 | [12 empty] | P5349 | FARM GROUP E WAREHOUSE #1 | FARM E | CORE
0 | 19P000175 | [12 empty] | P5350 | GROWTH CHAMBER BUILDING | GRTH CH BLDG | CORE
0 | 19P000312 | [12 empty] | P5351 | ENTOMOLOGY POULTRY BUILDING | ENT PLTRY BD | CORE
0 | 19P000601 | [12 empty] | P5353 | INSECT LABORATORY #39 | INSECT 39 | CORE
0 | 19P000597 | [12 empty] | P5354 | GORDON S. WATKINS HALL | WATKINS | CORE
0 | 19P000625 | [12 empty] | P5355 | SCREENHOUSE BOTANY | SCRNHSE BOT | CORE
0 | 19P000322 | [12 empty] | P5356 | STORAGE SHED #6 | STOR 6 | CORE
0 | 19P000205 | [12 empty] | P5357 | A. GARY ANDERSON HALL 2 | ANDERSON 2 | CORE
0 | 19P000250 | [12 empty] | P5358 | THE BARN | BARN | NON-CORE
0 | 19P000558 | [12 empty] | P5359 | SUPERINTENDENT'S GARAGE | SUPERINT GAR | NON-CORE
0 | 19P000424 | [12 empty] | P5360 | SUPERINTENDENT'S COTTAGE | SUPERINT COT | NON-CORE
0 | 19P000526 | [12 empty] | P5361 | INSECT LABORATORY #44 | INSECT 44 | CORE
0 | 19P000060 | [12 empty] | P5363 | PLANT DRYING BUILDING | PLNT DRY BLD | CORE
0 | 19P000565 | [12 empty] | P5364 | CORPORATION YARD PHYSICAL PLANT WAREHOUSE | CORP PP WHSE | CORE
0 | 19P000129 | [12 empty] | P5365 | PENTLAND HILLS RESIDENCE HALL A | PENTLAND A | NON-CORE
0 | 18P000226 | [12 empty] | P5367 | SATELLITE CHILLER PLANT | SAT CHIL PL | CORE
0 | 19P000588 | [12 empty] | P5369 | PENTLAND HILLS RESIDENCE HALL | PENTLAND I | NON-CORE
0 | 19P000620 | [12 empty] | P5371 | GLASSHOUSE FIELD 16 #47 | GH 16 47 | CORE
0 | 19P000035 | [12 empty] | P5372 | CHASS INTERDISCIPLINARY SOUTH | CHASS INT S | CORE
0 | 19P000023 | [12 empty] | P5373 | PSYCHOLOGY BUILDING | PSYCHOLOGY1 | CORE
0 | 19P000026 | [12 empty] | P5374 | GREENHOUSE #1 RESEARCH | GH01 RESRCH | CORE
0 | 18P000439 | [12 empty] | P5375 | GLASSHOUSE FIELD 16 #48 | GH 16 48 | CORE
0 | 18P000438 | [12 empty] | P5376 | TRAILER CNAS (Surge Trailer) | T CNAS | CORE
0 | 3428 | [12 empty] | P5377 | SHED BUILDING TRACTOR | SHED TRACTOR | CORE
0 | 3300 | [12 empty] | P5378 | GREENHOUSE #2 RESEARCH | GH03 RESRCH | CORE
0 | 19P000296 | [12 empty] | P5380 | CAMPUS SURGE | CAMPUS SURGE | CORE
0 | 19P000188 | [12 empty] | P5381 | COMPUTING & COMMUNICATIONS CENTER | ITS CENTER | CORE
0 | 19P000212 | [12 empty] | P5382 | COMPUTING & COMMUNICATIONS ELECTRIC CART CARPORT | ITS CARPORT | CORE
0 | 19P000211 | [12 empty] | P5383 | UNIVERSITY LECTURE HALL | UNIV LEC HAL | CORE
0 | 18P000121 | [12 empty] | P5385 | TRAILER BIOMEDICAL SCIENCES #1 | T BIOMED1 | CORE
0 | 18P000435 | [12 empty] | P5386 | EH&S TRIPLE WIDE TRAILER | T EH&S | CORE
0 | 18P000122 | [12 empty] | P5387 | VIVARIA TRAILER | T VIVARIA | CORE
0 | 19P000284 | [12 empty] | P5388 | ENVIRONMENTAL HEALTH AND SAFETY EXPANSION | ENV HLTHSFTY | CORE
0 | 19P000396 | [12 empty] | P5391 | BOTANIC GARDENS RESTROOM | BOTGDN RSTRM | NON-CORE
0 | 3540 | [12 empty] | P5393 | METEOROLOGICAL BUILDING | METEOR BLDG | CORE
0 | 3233 | [12 empty] | P5396 | UCR CHILD DEVELOPMENT SOUTH | CHILD DEV S | NON-CORE
0 | 2916 | [12 empty] | P5397 | SCHOOL OF EDUCATION CLINIC | EDUC CLINIC | CORE
0 | 3234 | [12 empty] | P5398 | PARKING TRAILER 1 | PARKING T1 | NON-CORE
0 | 3120 | [12 empty] | P5399 | PARKING TRAILER 2 | PARKING T2 | NON-CORE
0 | 3119 | [12 empty] | P5400 | PARKING TRAILER 3 | PARKING T3 | NON-CORE
0 | 3293 | [12 empty] | P5402 | Arabadopsis 1 | ARAB 1 | NON-CORE
0 | 3319 | [12 empty] | P5403 | CHASS INTERDISCIPLINARY NORTH | CHASS INT N | CORE
0 | 3452 | [12 empty] | P5404 | HIGHLANDER UNION BUILIDNG | HUB | NON-CORE
0 | 3005 | [12 empty] | P5405 | HIGHLANDER UNION COFFEE PAVILION | HUB COFFEE | NON-CORE
0 | 3393 | [12 empty] | P5406 | SCHOOL OF MEDICINE HEALTH SCIENCE RESEARCH BUILDING | SOM RSCH | CORE
0 | 3366 | [12 empty] | P5408 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16A | GH 16-54 ENT | CORE
0 | 3458 | [12 empty] | P5409 | STORAGE SHED #1 | STOR 1 | CORE
0 | 2970d | [12 empty] | P5410 | STORAGE SHED #2 | STOR 3 | CORE
0 | 2970a | [12 empty] | P5411 | ARTS BUILDING FINE ARTS SEISMIC FACILITY | ARTS | CORE
0 | 2970c | [12 empty] | P5412 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16B | GH 16-55 ENT | CORE
0 | 3401 | [12 empty] | P5413 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16C | GH 16-56 ENT | CORE
0 | 2952 | [12 empty] | P5414 | CHEMICAL SCIENCES | CHEMICAL SCI | CORE
0 | 3395 | [12 empty] | P5415 | CANYON CREST KIOSK | KIOSK 2 | NON-CORE
0 | 3438 | [12 empty] | P5416 | SCIENCE LABORATORIES 1 | SCIENCE LAB1 | CORE
0 | 3175 | [12 empty] | P5417 | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | ENTOMOLOGY | CORE
0 | 18P000421 | [12 empty] | P5418 | RAYMOND L. ORBACH SCIENCE LIBRARY | ORBACH LIB | CORE
0 | 18P000329 | [12 empty] | P5419 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16D | GH 16-57 ENT | CORE
0 | 18P000209 | [12 empty] | P5420 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16E | GH 16-58 ENT | CORE
0 | 18P000410 | [12 empty] | P5421 | BOTANIC GARDENS HOUSE | BOT GDN HSE | NON-CORE
0 | 19P000407 | [12 empty] | P5422 | GLASSHOUSE FIELD 8 AIR POLLUTION | GH5 | CORE
0 | 18P000414 | [12 empty] | P5423 | GLASSHOUSE FIELD 7 AIR POLLUTION | GH4 | CORE
0 | 19P000375 | [12 empty] | P5424 | LATHHOUSE #8 | LATH 8 | CORE
0 | 18P000487 | [12 empty] | P5425 | LATHHOUSE #3 | LATH 3 | CORE
0 | 19P000420 | [12 empty] | P5426 | HEADHOUSE STORAGE BUILDING | HH STOR | CORE
0 | 19P000122 | [12 empty] | P5427 | SOIL FACILITY BUILDING | SOIL BLDG | CORE
0 | 18P000297 | [12 empty] | P5428 | STORAGE BUILDING RADIOACTIVE MATERIAL | STOR RA | CORE
0 | 18P000389 | [12 empty] | P5430 | AGRICULTURE EXPERIMENT STATION STORAGE BUILDING | AES STOR | CORE
0 | 18P000416 | [12 empty] | P5434 | GLASSHOUSE FIELD 16 #50 | GH 16 50 | CORE
0 | 18P000415 | [12 empty] | P5435 | EHS STORAGE 1 | EHS STOR 1 | CORE
0 | 18P000445 | [12 empty] | P5436 | EHS STORAGE 2 | EHS STOR 2 | CORE
0 | 18P000367 | [12 empty] | P5437 | EHS STORAGE 3 | EHS STOR 3 | CORE
0 | 18P000353 | [12 empty] | P5438 | EHS STORAGE 4 | EHS STOR 4 | CORE
0 | 19P000313 | [12 empty] | P5439 | EHS STORAGE 5 | EHS STOR 5 | CORE
0 | 18P000314 | [12 empty] | P5440 | 4558 SANDANO STREET | 4558 SANDANO | NON-CORE
0 | 18P000344 | [12 empty] | P5441 | 4566 SANDANO STREET | 4566 SANDANO | NON-CORE
0 | 18P000294 | [12 empty] | P5442 | 1871 ESCALANTE WAY | 1871 ESCALAN | NON-CORE
0 | 19P000056 | [12 empty] | P5443 | 4531 SANDANO STREET | 4531 SANDANO | NON-CORE
0 | 18W016588 | [12 empty] | P5444 | 4522 SANDANO STREET | 4522 SANDANO | NON-CORE
0 | 18P000318 | [12 empty] | P5445 | 4538 SANDANO STREET | 4538 SANDANO | NON-CORE
0 | 18P000417 | [12 empty] | P5446 | POLICE TRAILER | POLICE TRLR | CORE
0 | 19P000364 | [12 empty] | P5449 | GENOMICS SHED | GENOM SHED | CORE
0 | 18P000387 | [12 empty] | P5451 | EDGEMOOR HOUSE | EDGEMOOR HSE | NON-CORE
0 | 18P000300 | [12 empty] | P5452 | EDGEMOOR GARAGE | EDGEMOOR GAR | NON-CORE
0 | 18P000295 | [12 empty] | P5453 | GARAGE COTTAGE #2 | GAR C2 | CORE
0 | 18W001170 | [12 empty] | P5455 | TRAILER CECERT 1 | T CECERT 1 | NON-CORE
0 | 18P000205 | [12 empty] | P5457 | PRINTING MODULAR | PRINT MOD | NON-CORE
0 | 19P000253 | [12 empty] | P5460 | WOODSHED | WOODSHED | CORE
0 | 18P000396 | [12 empty] | P5461 | FIELD LABORATORY | FLDLAB | CORE
0 | 18P000111 | [12 empty] | P5462 | TRAILER CECERT 2 | T CECERT 2 | NON-CORE
0 | 18P000383 | [12 empty] | P5464 | STORAGE SHED #2 | STOR 2 | CORE
0 | 18P000420 | [12 empty] | P5466 | BIO CONTROL CULTURE BUILDING REPLACEMENT | BIO CTRL BLD | CORE
0 | 18P000201 | [12 empty] | P5467 | RICHARD J HECKMANN INTL CENTER FOR ENTREPRENEURIAL MGMT | HECKMAN ICEM | NON-CORE
0 | 18P000468 | [12 empty] | P5468 | HECKMANN CENTER COMPLEX PH 2 | HECKMANN PH2 | NON-CORE
0 | 18P000469 | [12 empty] | P5469 | VERLEY BARN | VERLEY BARN | CORE
0 | 18P000418 | [12 empty] | P5470 | GLEN MOR HOUSING A | GLEN MOR A | NON-CORE
0 | 19P000220 | [12 empty] | P5471 | GLEN MOR HOUSING B | GLEN MOR B | NON-CORE
0 | 19P000361 | [12 empty] | P5472 | GLEN MOR HOUSING C1 | GLEN MOR C1 | NON-CORE
0 | 19P000575 | [12 empty] | P5473 | GLEN MOR HOUSING D | GLEN MOR D | NON-CORE
0 | 19P000337 | [12 empty] | P5474 | GLEN MOR HOUSING E | GLEN MOR E | NON-CORE
0 | 18P000481 | [12 empty] | P5475 | GLEN MOR HOUSING C2 | GLEN MOR C2 | NON-CORE
0 | 19P000606 | [12 empty] | P5476 | TRAILER ANTHROPOLOGY | T ANTHROP | CORE
0 | 19P000378 | [12 empty] | P5478 | GLASSHOUSE FIELD 3 AIR POLLUTION | GH AP FL2 | CORE
0 | 19P000400 | [12 empty] | P5479 | GLASSHOUSE FIELD 3 AIR POLLUTION | GH AP FL3 | CORE
0 | 19P000306 | [12 empty] | P5480 | IVAN HINDERAKER HALL | HINDERAKER | CORE
0 | 19W002930 | [12 empty] | P5481 | GREENHOUSE #14 | GH14 | CORE
0 | 19P000585 | [12 empty] | P5482 | PATRICK BOYDEN LABORATORY | BOYDEN LAB | CORE
0 | 19P000355 | [12 empty] | P5483 | GREENHOUSE #17 | GH17 | CORE
0 | 19P000603 | [12 empty] | P5484 | CORPORATION YARD D CAR SHELTER | CORP CAR SHD | CORE
0 | 19P000195 | [12 empty] | P5485 | CORPORATION YARD C | CORP C | CORE
0 | 19P000640 | [12 empty] | P5486 | CORPORATION YARD B | CORP B | CORE
0 | 19P000216 | [12 empty] | P5487 | CORPORATION YARD A | CORP A | CORE
0 | 19P000221 | [12 empty] | P5488 | CHANCELLOR'S RESIDENCE | CHANC HOUSE | NON-CORE
0 | 19P000643 | [12 empty] | P5489 | FARM A | FARM A | CORE
0 | 19P000196 | [12 empty] | P5490 | FARM B | FARM B | CORE
0 | 19P000171 | [12 empty] | P5491 | GARAGE 4 CAR | GARAGE 4 CAR | NON-CORE
0 | 18W016621 | [12 empty] | P5492 | SHED BUILDING FIELD 11A | SHED FLD 11A | CORE
0 | 19P000201 | [12 empty] | P5493 | TRAILER #14 | T14 | CORE
0 | 18P000385 | [12 empty] | P5495 | HEALTH SERVICE BUILDING | HEALTH SERV | CORE
0 | 19P000607 | [12 empty] | P5496 | PHYSICAL EDUCATION UTILITY BUILDING | PE UTIL BLDG | CORE
0 | 19P000362 | [12 empty] | P5497 | JOHN W. OLMSTED HALL | OLMSTED | CORE
0 | 19P000419 | [12 empty] | P5498 | HUMANITIES BUILDING | HUMANITIES | CORE
0 | 18W008762 | [12 empty] | P5499 | GLASSHOUSE FIELD 16 #21 | GH 16 21 | CORE
0 | 18P000126 | [12 empty] | P5500 | VEGETABLE CROPS STOREHOUSE | VEG CROP STR | CORE
0 | 18P000343 | [12 empty] | P5501 | LEON DEXTER BATCHELOR HALL | BATCHELOR | CORE
0 | 19P000173 | [12 empty] | P5502 | LOTHIAN RESIDENCE HALL | LOTHIAN HALL | NON-CORE
0 | 19P000356 | [12 empty] | P5503 | HOWARD SAMUEL FAWCETT LABORATORY | FAWCETT LAB | CORE
0 | 19P000063 | [12 empty] | P5504 | PHYSICS BUILDING | PHYSICS | CORE
0 | 19P000574 | [12 empty] | P5505 | GEODESIC DOME BOTANIC GARDENS | GEODESIC DM | CORE
0 | 19P000415 | [12 empty] | P5506 | COLD BOXES ROOF BUILDING | COLD BX ROOF | CORE
0 | 19P000605 | [12 empty] | P5507 | CUSTODIAL & GROUNDS BUILDING | CUST AND GRD | CORE
0 | 19P000350 | [12 empty] | P5508 | W. CONWAY PIERCE HALL | PIERCE | CORE
0 | 19P000609 | [12 empty] | P5509 | TRAILER #7 AIR POLLUTION | T7 AP | CORE
0 | 19P000371 | [12 empty] | P5511 | STUDENT RECREATION CENTER NORTH | SRC NORTH | NON-CORE
0 | 19P000011 | [12 empty] | P5513 | GREENHOUSE #18 | GH18 | CORE
0 | 19P000604 | [12 empty] | P5514 | GREENHOUSE #19 | GH19 | CORE
0 | 18P000419 | [12 empty] | P5515 | GREENHOUSE #20 | GH20 | CORE
0 | 19P000357 | [12 empty] | P5516 | GLASSHOUSE FIELD 15A #40 | GH 15A-40 | CORE
0 | 19P000421 | [12 empty] | P5517 | COLLEGE BUILDING NORTH | COLL BLDG NO | CORE
0 | 19P000642 | [12 empty] | P5518 | AGRICULTURE ENGINEERING SHOP | AG ENG SHOPS | CORE
0 | 18P000444 | [12 empty] | P5519 | GLASSHOUSE FIELD 15A #41 | GH 15A-41 | CORE
0 | 19P000314 | [12 empty] | P5520 | MIDGE CONTROL BUILDING | MIDGE CONTRL | CORE
0 | 19P000207 | [12 empty] | P5521 | STORAGE DOCK | STORAGE DOCK | CORE
0 | 19P000552 | [12 empty] | P5522 | GLASSHOUSE FIELD 15A #42 | GH 15A-42 | CORE
0 | 19P000300 | [12 empty] | P5523 | ROBERT GORDON SPROUL HALL | SPROUL | CORE
0 | 19P000589 | [12 empty] | P5524 | GLASSHOUSE FIELD 15A #43 | GH 15A-43 | CORE
0 | 19P000448 | [12 empty] | P5525 | HORTICULTURE GREENHOUSE D1 | GH 16 49 | CORE
0 | 19P000286 | [12 empty] | P5526 | HORTICULTURE GREENHOUSE D2 | GH 16 51 | CORE
0 | 19P000194 | [12 empty] | P5527 | HORTICULTURE GREENHOUSE D3 | GH 16 52 | CORE
0 | 19P000061 | [12 empty] | P5528 | LATHHOUSE LIFE SCIENCES EXPERIMENTAL AREA | LATH LS | CORE
0 | 19P000540 | [12 empty] | P5529 | GLASSHOUSE FIELD 15A #48 | GH 15A-48 | CORE
0 | 19P000608 | [12 empty] | P5530 | BELLTOWER | BELLTOWER | CORE
0 | 19P000429 | [12 empty] | P5531 | HORTICULTURE GREENHOUSE D4 | GH 16 53 | CORE
0 | 19P000226 | [12 empty] | P5532 | TELEPHONE BUILDING | TELEPHONE | CORE
0 | 3280 | [12 empty] | P5533 | CANYON CREST HOUSING 3458 AVOCADO AVENUE | CC AVOC 3458 | NON-CORE
0 | 3535 | [12 empty] | P5534 | MULTIPURPOSE BUILDING BOTANIC GARDEN | MULTI PURP | NON-CORE
0 | 3060 | [12 empty] | P5535 | LATHHOUSE B | LATH B | CORE
0 | 3469 | [12 empty] | P5539 | AGRONOMY FIELD HEADQUARTERS BUILDING | AGRON FLDHSE | CORE
0 | 3441 | [12 empty] | P5540 | GLASSHOUSE #1 PLASTIC COVERED | GH PLASTC 01 | CORE
0 | 18P000118 | [12 empty] | P5541 | GLASSHOUSE #2 PLASTIC COVERED | GH PLASTC 02 | CORE
0 | 19P000213 | [12 empty] | P5542 | GLASSHOUSE #3 PLASTIC COVERED FIELD 16 | GH PLA 16-03 | CORE
0 | 18W000455 | [12 empty] | P5543 | GLASSHOUSE #4 PLASTIC COVERED | GH PLASTC 04 | CORE
0 | 18P000256 | [12 empty] | P5544 | GLASSHOUSE #5 PLASTIC COVERED | GH PLASTC 05 | CORE
0 | 18P000247 | [12 empty] | P5545 | GLASSHOUSE #6 PLASTIC COVERED | GH PLASTC 06 | CORE
0 | 18W011161 | [12 empty] | P5546 | GLASSHOUSE #7 PLASTIC COVERED | GH PLASTC 07 | CORE
0 | 18P000227 | [12 empty] | P5547 | GLASSHOUSE #8 PLASTIC COVERED | GH PLASTC 08 | CORE
0 | 18W011672 | [12 empty] | P5548 | AGRICULTURAL OPERATIONS STORAGE SHED #9 | AGOPS SHED 9 | CORE
0 | 18P000392 | [12 empty] | P5549 | BOTANY & PLANT SCIENCE STORAGE FACILITY | BOT STOR 8C | NON-CORE
0 | 18P000434 | [12 empty] | P5550 | GLASSHOUSE #51 | GH 51 | CORE
0 | 18P000027 | [12 empty] | P5551 | GLASSHOUSE FIELD 16 #30 | GH 16 30 | CORE
0 | 19P000346 | [12 empty] | P5552 | GLASSHOUSE FIELD 16 #29 | GH 16 29 | CORE
0 | 18P000117 | [12 empty] | P5553 | GLASSHOUSE #52 | GH 52 | CORE
0 | 19W007474 | [12 empty] | P5554 | ENTOMOLOGY FUMIGATOR | ENT FUMIGATR | CORE
0 | 19P000319 | [12 empty] | P5559 | TRAILER PHYSICAL PLANT | T PHYS PLANT | CORE
0 | 19P000058 | [12 empty] | P5561 | BIOMEDICAL SCIENCES UNIT 2 TRAILER | T BIOMED2 | CORE
0 | 18P000030 | [12 empty] | P5562 | BOTANY & PLANT SCIENCE GREENHOUSE-POLY | GH BOT POLY | CORE
0 | 18P000029 | [12 empty] | P5564 | KIOSK/INFORMATION BOOTH | KIOSK | NON-CORE
0 | 18P000028 | [12 empty] | P5565 | GREENHOUSE BOTANIC GARDENS | GH BOT GDNS | NON-CORE
0 | 19P000185 | [12 empty] | P5566 | POLICE BUILDING | POLICE BLDG | CORE
0 | 19P000186 | [12 empty] | P5567 | GLASSHOUSE FIELD 16 #20 | GH 16 20 | CORE
0 | 19P000189 | [12 empty] | P5568 | HEADHOUSE BOTANIC GARDENS | HHSE BOT GDN | CORE
0 | 18W011692 | [12 empty] | P5571 | METAL RESEARCH BUILDING | METAL RSHBLD | CORE
0 | 18P000288 | [12 empty] | P5573 | CONTROL TEMPERATURE STRUCTURE | CONTROL TEMP | NON-CORE
0 | 18P000312 | [12 empty] | P5575 | STORED PRODUCTS TEST BUILDING | STOR PR TEST | CORE
0 | 18P000310 | [12 empty] | P5579 | PUMPHOUSE #4 | PUMP 4 | CORE
0 | 18P000341 | [12 empty] | P5581 | HOUSING ADMINISTRATION | HOUSING ADM | NON-CORE
0 | 18P000356 | [12 empty] | P5582 | VOLATILE LIQUID STORAGE BUILDING | VOLA LIQ STG | CORE
0 | 18P000296 | [12 empty] | P5583 | GLASSHOUSE #16 PLASTIC COVERED | GH PLASTC 16 | CORE
0 | 18P000293 | [12 empty] | P5584 | GLASSHOUSE #14 PLASTIC COVERED | GH PLASTC 14 | CORE
0 | 18P000287 | [12 empty] | P5585 | GLASSHOUSE #13 PLASTIC COVERED | GH PLASTC 13 | CORE
0 | 19P000287 | [12 empty] | P5586 | GLASSHOUSE #12 PLASTIC COVERED | GH PLASTC 12 | CORE
0 | 18P000292 | [12 empty] | P5587 | GLASSHOUSE #15 PLASTIC COVERED | GH PLASTC 15 | CORE
0 | 19P000390 | [12 empty] | P5588 | SCHOOL OF MEDICINE - EDUCATION BUILDING | SOM EDUC | CORE
0 | 19P000358 | [12 empty] | P5589 | CORPORATION YARD COMPRESSED GAS STORAGE BUILDING | CORP GAS STG | CORE
0 | 19P000298 | [12 empty] | P5590 | BANNOCKBURN VILLAGE BLDG A | BANNOCK A | NON-CORE
0 | 19P000449 | [12 empty] | P5591 | BANNOCKBURN VILLAGE BLDG B | BANNOCK B | NON-CORE
0 | 19P000505 | [12 empty] | P5592 | BANNOCKBURN VILLAGE BLDG C | BANNOCK C | NON-CORE
0 | 19P000440 | [12 empty] | P5593 | BANNOCKBURN VILLAGE BLDG D | BANNOCK D | NON-CORE
0 | 19P000299 | [12 empty] | P5594 | BANNOCKBURN VILLAGE BLDG E | BANNOCK E | NON-CORE
0 | 19P000639 | [12 empty] | P5595 | BANNOCKBURN VILLAGE BLDG F | BANNOCK F | NON-CORE
0 | 18P000473 | [12 empty] | P5596 | BANNOCKBURN VILLAGE BLDG G | BANNOCK G | NON-CORE
0 | 19P000347 | [12 empty] | P5597 | BANNOCKBURN VILLAGE BLDG H | BANNOCK H | NON-CORE
0 | 19P000571 | [12 empty] | P5598 | BANNOCKBURN VILLAGE BLDG I | BANNOCK I | NON-CORE
0 | 19P000244 | [12 empty] | P5599 | BANNOCKBURN VILLAGE BLDG J | BANNOCK J | NON-CORE
0 | 19P000324 | [12 empty] | P5600 | BANNOCKBURN VILLAGE BLDG K | BANNOCK K | NON-CORE
0 | 19P000367 | [12 empty] | P5601 | BANNOCKBURN VILLAGE BLDG L | BANNOCK L | NON-CORE
0 | 18P000223 | [12 empty] | P5602 | BANNOCKBURN VILLAGE BLDG M | BANNOCK M | NON-CORE
0 | 19P000438 | [12 empty] | P5603 | BANNOCKBURN VILLAGE BLDG N | BANNOCK N | NON-CORE
0 | 18P000269 | [12 empty] | P5604 | BANNOCKBURN VILLAGE BLDG O | BANNOCK O | NON-CORE
0 | 19P000137 | [12 empty] | P5605 | BANNOCKBURN VILLAGE BLDG P | BANNOCK P | NON-CORE
0 | 18P000354 | [12 empty] | P5606 | BANNOCKBURN VILLAGE BLDG Q | BANNOCK Q | NON-CORE
0 | 19P000045 | [12 empty] | P5607 | BANNOCKBURN VILLAGE BLDG R | BANNOCK R | NON-CORE
0 | 19P000106 | [12 empty] | P5608 | BANNOCKBURN VILLAGE BLDG S | BANNOCK S | NON-CORE
0 | 19P000170 | [12 empty] | P5609 | BANNOCKBURN VILLAGE BLDG T | BANNOCK T | NON-CORE
0 | 18P000453 | [12 empty] | P5610 | BANNOCKBURN VILLAGE BLDG U | BANNOCK U | NON-CORE
0 | 19P000292 | [12 empty] | P5611 | BANNOCKBURN VILLAGE BLDG V | BANNOCK V | NON-CORE
0 | 19P000043 | [12 empty] | P5614 | STUDENT SUPPORT SERVICES BUILDING | STUDENT SERV | CORE
0 | 19P000340 | [12 empty] | P5616 | SCHOOL OF MEDICINE DINING FACILITY | SOM DINING | CORE
0 | 19P000618 | [12 empty] | P5620 | 5029 MONACHELLO LANE | 5029 MONACHE | NON-CORE
0 | 19P000341 | [12 empty] | P5621 | 5037 MONACHELLO LANE | 5037 MONACHE | NON-CORE
0 | 19P000622 | [12 empty] | P5622 | 5045 MONACHELLO LANE | 5045 MONACHE | NON-CORE
0 | 19P000214 | [12 empty] | P5623 | 1670 OROBLANCO AVE | 1670 OROBLAN | NON-CORE
0 | 19P000283 | [12 empty] | P5624 | 1654 OROBLANCO AVE | 1654 OROBLAN | NON-CORE
0 | 18P000388 | [12 empty] | P5625 | 1640 OROBLANCO AVE | 1640 OROBLAN | NON-CORE
0 | 18P000480 | [12 empty] | P5626 | 1626 OROBLANCO AVE | 1626 OROBLAN | NON-CORE
0 | 18P000486 | [12 empty] | P5628 | 1606 OROBLANCO AVE | 1606 OROBLAN | NON-CORE
0 | 19P000210 | [12 empty] | P5629 | 1598 OROBLANCO AVE | 1598 OROBLAN | NON-CORE
0 | 18P000099 | [12 empty] | P5630 | 1590 OROBLANCO AVE | 1590 OROBLAN | NON-CORE
0 | 17W012504 | [12 empty] | P5631 | 1582 OROBLANCO AVE | 1582 OROBLAN | NON-CORE
0 | 18P000257 | [12 empty] | P5632 | 5141 PIXIE WAY | 5141 PIXIE | NON-CORE
0 | 18P000284 | [12 empty] | P5633 | 5133 PIXIE WAY | 5133 PIXIE | NON-CORE
0 | 18P000258 | [12 empty] | P5634 | 5125 PIXIE WAY | 5125 PIXIE | NON-CORE
0 | 19P000006 | [12 empty] | P5636 | PENTLAND HILLS RESIDENCE HALL BC | PENTLAND BC | NON-CORE
0 | 19P000539 | [12 empty] | P5637 | PENTLAND HILLS RESIDENCE HALL D | PENTLAND D | NON-CORE
0 | 19P000613 | [12 empty] | P5638 | PENTLAND HILLS RESIDENCE HALL E | PENTLAND E | NON-CORE
0 | 19P000301 | [12 empty] | P5639 | PENTLAND HILLS RESIDENCE HALL FG | PENTLAND FG | NON-CORE
0 | 18P000347 | [12 empty] | P5640 | PENTLAND HILLS RESIDENCE HALL H | PENTLAND H | NON-CORE
0 | 19P000055 | [12 empty] | P5641 | PENTLAND HILLS RESIDENCE HALL J | PENTLAND J | NON-CORE
0 | 18W013160 | [12 empty] | P5642 | PENTLAND HILLS RESIDENCE HALL K | PENTLAND K | NON-CORE
0 | 19P000191 | [12 empty] | P5643 | PENTLAND HILLS RESIDENCE HALL L | PENTLAND L | NON-CORE
0 | 18P000464 | [12 empty] | P5644 | PENTLAND HILLS RESIDENCE HALL M | PENTLAND M | NON-CORE
0 | 18P000436 | [12 empty] | P5645 | PENTLAND HILLS RESIDENCE HALL N | PENTLAND N | NON-CORE
0 | 19P000174 | [12 empty] | P5646 | PENTLAND HILLS RESIDENCE HALL O | PENTLAND O | NON-CORE
0 | 19P000042 | [12 empty] | P5647 | PENTLAND HILLS RESIDENCE HALL P | PENTLAND P | NON-CORE
0 | 19P000049 | [12 empty] | P5648 | PENTLAND HILLS RESIDENCE HALL Q | PENTLAND Q | NON-CORE
0 | 19P000508 | [12 empty] | P5649 | 5117 PIXIE WAY | 5117 PIXIE | NON-CORE
0 | 18W011691 | [12 empty] | P5650 | 5109 PIXIE WAY | 5109 PIXIE | NON-CORE
0 | 19P000614 | [12 empty] | P5651 | 5108 PIXIE WAY | 5108 PIXIE | NON-CORE
0 | 19P000318 | [12 empty] | P5652 | 5116 PIXIE WAY | 5116 PIXIE | NON-CORE
0 | 19P000031 | [12 empty] | P5653 | 5124 PIXIE WAY | 5124 PIXIE | NON-CORE
0 | 19P000193 | [12 empty] | P5654 | 5132 PIXIE WAY | 5132 PIXIE | NON-CORE
0 | 19P000102 | [12 empty] | P5655 | 1531 OROBLANCO AVE | 1531 OROBLAN | NON-CORE
0 | 19P000133 | [12 empty] | P5657 | 1563 OROBLANCO AVE | 1563 OROBLAN | NON-CORE
0 | 19P000197 | [12 empty] | P5658 | 1571 OROBLANCO AVE | 1571 OROBLAN | NON-CORE
0 | 19P000184 | [12 empty] | P5659 | 1579 OROBLANCO AVE | 1579 OROBLAN | NON-CORE
0 | 19P000246 | [12 empty] | P5660 | 1595 OROBLANCO AVE | 1595 OROBLAN | NON-CORE
0 | 19P000242 | [12 empty] | P5661 | OBAN APARTMENTS BLDG A | OBAN APTS A | NON-CORE
0 | 19P000231 | [12 empty] | P5662 | OBAN APARTMENTS BLDG B | OBAN APTS B | NON-CORE
0 | 19P000243 | [12 empty] | P5663 | OBAN APARTMENTS BLDG C | OBAN APTS C | NON-CORE
0 | 19P000285 | [12 empty] | P5664 | OBAN APARTMENTS BLDG D | OBAN APTS D | NON-CORE
0 | 19P000615 | [12 empty] | P5665 | OBAN APARTMENTS BLDG E | OBAN APTS E | NON-CORE
0 | 19P000062 | [12 empty] | P5666 | OBAN APARTMENTS BLDG F | OBAN APTS F | NON-CORE
0 | 19P000176 | [12 empty] | P5667 | OBAN APARTMENTS BLDG G | OBAN APTS G | NON-CORE
0 | 19W003012 | [12 empty] | P5668 | OBAN APARTMENTS BLDG H | OBAN APTS H | NON-CORE
0 | 19P000126 | [12 empty] | P5669 | OBAN APARTMENTS BLDG J | OBAN APTS J | NON-CORE
0 | 19P000616 | [12 empty] | P5670 | OBAN APARTMENTS OFFICE BLDG | OBAN OFFICE | NON-CORE
0 | 19P000230 | [12 empty] | P5671 | FALKIRK APARTMENTS 1 | FALKIRK 1 | NON-CORE
0 | 19P000360 | [12 empty] | P5672 | FALKIRK APARTMENTS 2 | FALKIRK 2 | NON-CORE
0 | 19P000617 | [12 empty] | P5673 | FALKIRK APARTMENTS 3 | FALKIRK 3 | NON-CORE
0 | 19P000251 | [12 empty] | P5674 | FALKIRK APARTMENTS 4 | FALKIRK 4 | NON-CORE
0 | 19P000369 | [12 empty] | P5675 | FALKIRK APARTMENTS 5 | FALKIRK 5 | NON-CORE
0 | 19P000482 | [12 empty] | P5676 | FALKIRK APARTMENTS 6 | FALKIRK 6 | NON-CORE
0 | 19P000291 | [12 empty] | P5677 | FALKIRK APARTMENTS 7 | FALKIRK 7 | NON-CORE
0 | 19P000288 | [12 empty] | P5678 | FALKIRK APARTMENTS 8 | FALKIRK 8 | NON-CORE
0 | 19P000523 | [12 empty] | P5679 | FALKIRK APARTMENTS 9 | FALKIRK 9 | NON-CORE
0 | 18P000221 | [12 empty] | P5680 | FALKIRK APARTMENTS 10 | FALKIRK 10 | NON-CORE
0 | 19P000234 | [12 empty] | P5681 | FALKIRK APARTMENTS 11 | FALKIRK 11 | NON-CORE
0 | 19P000127 | [12 empty] | P5682 | FALKIRK APARTMENTS 12 | FALKIRK 12 | NON-CORE
0 | 19P000413 | [12 empty] | P5683 | FALKIRK APARTMENTS 13 | FALKIRK 13 | NON-CORE
0 | 19P000377 | [12 empty] | P5684 | FALKIRK APARTMENTS 14 | FALKIRK 14 | NON-CORE
0 | 19P000547 | [12 empty] | P5685 | FALKIRK APARTMENTS 15 | FALKIRK 15 | NON-CORE
0 | 19P000555 | [12 empty] | P5686 | FALKIRK APARTMENTS 16 | FALKIRK 16 | NON-CORE
0 | 19P000474 | [12 empty] | P5687 | FALKIRK APARTMENTS 17 | FALKIRK 17 | NON-CORE
0 | 19P000504 | [12 empty] | P5688 | FALKIRK APARTMENTS 18 | FALKIRK 18 | NON-CORE
0 | 19P000514 | [12 empty] | P5689 | FALKIRK APARTMENTS 19 | FALKIRK 19 | NON-CORE
0 | 19P000543 | [12 empty] | P5690 | FALKIRK APARTMENTS LR1 | FALKIRK LR1 | NON-CORE
0 | 19P000594 | [12 empty] | P5691 | FALKIRK APARTMENTS LR2 | FALKIRK LR2 | NON-CORE
0 | 3228 | [12 empty] | P5692 | FALKIRK APARTMENTS LR3 | FALKIRK LR3 | NON-CORE
0 | 3367 | [12 empty] | P5693 | FALKIRK APARTMENTS OFFICE | FALKIRK OFF | NON-CORE
0 | 3390 | [12 empty] | P5694 | FALKIRK APARTMENTS MOD | FALKIRK MOD | NON-CORE
0 | 3542 | [12 empty] | P5695 | STUDENT RECREATION CENTER SOUTH | SRC SOUTH | NON-CORE
0 | 3547 | [12 empty] | P5696 | STUDENT RECREATION CENTER POOL EQUIPMENT BUILDING | SRC POOLBLDG | NON-CORE
0 | 1990a | [12 empty] | P5698 | UCR BUILDING | UCR BUILDING
0 | 2353 | [12 empty] | P5699 | OP BUILDING | OP BUILDING
0 | 1990b | [12 empty] | P5704 | GLASSHOUSE FIELD 15 #35 | GH 15-35 | CORE
0 | 19P000428 | [12 empty] | P5705 | PRESS BOX | PRESS BOX | NON-CORE
0 | 19P000370 | [12 empty] | P5706 | CONSTRUCTION TRAILER | T CONSTRUCT | CORE
0 | 19P000384 | [12 empty] | P5708 | DELFINO FAMILY PLANT LABORATORY | DELFINO HHSE | CORE
0 | 19P000467 | [12 empty] | P5709 | RUBIDOUX SOIL HOUSE 1 | RUBID SOIL 1 | NON-CORE
0 | 19P000466 | [12 empty] | P5710 | RUBIDOUX GREENHOUSE | RUBIDOUX GRH | CORE
0 | 19P000560 | [12 empty] | P5711 | RUBIDOUX QUARANTINE FACILITY | RUBIDOUX QUA | CORE
0 | 19P000645 | [12 empty] | P5712 | RUBIDOUX SCREENHOUSE | RUBIDOUX SCR | CORE
0 | 3498 | [12 empty] | P5713 | RUBIDOUX LABORATORY #2 | RUBIDOX LAB2 | CORE
0 | 3527 | [12 empty] | P5714 | RUBIDOUX LABORATORY #1 | RUBIDOUX LAB | CORE
0 | 3528 | [12 empty] | P5715 | THE PLAZA APARTMENTS | THE PLAZA | NON-CORE
0 | 3529 | [12 empty] | P5717 | 2100 ATLANTA AVENUE RIVERSIDE | ATLANTA | CORE
0 | 2687 | [12 empty] | P5718 | MOURADICK FARM LABORATORY BUILDING | MOURADK LAB | CORE
0 | 3476 | [12 empty] | P5719 | MOURADICK FARM SHOP BUILDING | MOURADK SHOP | CORE
0 | 3275 | [12 empty] | P5720 | CALIFORNIA MUSEUM OF PHOTOGRAPHY BUILDING | CA MUS PHOTO | CORE
0 | 3437 | [12 empty] | P5721 | RUBIDOUX GARAGE | RUBIDOUX GAR | CORE
0 | 3035a | [12 empty] | P5722 | UC RIVERSIDE UNIVERSITY EXTENSION CENTER | UCR EXTEN CT | NON-CORE
0 | 3270 | [12 empty] | P5724 | TRAILER PLANT PATH2 | T PLNT PATH2 | CORE
0 | 3271 | [12 empty] | P5725 | PHILIP BOYD DEEP CANYON RESERVE RESEARCH LAB | DC RES LAB | NON-CORE
0 | 3272 | [12 empty] | P5726 | PHILIP BOYD DEEP CANYON RESERVE ADMIN BLDG | DC ADMIN BLD | NON-CORE
0 | 3064 | [12 empty] | P5727 | PHILIP BOYD DEEP CANYON RESERVE CAR PORT | DC CAR PORT | NON-CORE
0 | 2682 | [12 empty] | P5728 | PHILIP BOYD DEEP CANYON RESERVE RESIDENCE | DC RESIDENCE | NON-CORE
0 | 2671 | [12 empty] | P5729 | MOTTE RIMROCK RESERVE RESIDENCE | MOTTE RESDNC | NON-CORE
0 | 2805 | [12 empty] | P5730 | GRANITE MOUNTAIN RESERVE DORNERS CAMP CHATEAU | GR MT DORNER | NON-CORE
0 | 19P000411 | [12 empty] | P5731 | DEEP CANYON COTTAGE/OFFICE/STORAGE | DC COTTAGE | NON-CORE
0 | 19P000399 | [12 empty] | P5732 | PHILIP BOYD DEEP CANYON RESERVE WILBUR MAYHEW BLDG | DC MAYHEW BL | NON-CORE
0 | 19P000572 | [12 empty] | P5733 | SIBYL & AL ALLANSON CENTER LABORATORY | GM ALLAN LAB | NON-CORE
0 | 18P000313 | [12 empty] | P5734 | SIBYL & AL ALLANSON CENTER RESEARCHER CABIN | GM ALLAN CAB | NON-CORE
0 | 18P000274 | [12 empty] | P5735 | SIBYL & AL ALLANSON CENTER EAST RESEARCHER CABIN | GM ALLAN ECB | NON-CORE
0 | 19P000054 | [12 empty] | P5736 | SIBYL & AL ALLANSON CENTER WEST RESEARCHER CABIN | GM ALLAN WCB | NON-CORE
0 | 19P000628 | [12 empty] | P5737 | T PLANT PATH3 | T PLNT PATH3 | CORE
0 | 19P000237 | [12 empty] | P5739 | EMERSON OAKS RESERVE RESTROOM | EMERSON RR | CORE
0 | 19P000627 | [12 empty] | P5740 | GRANITE MOUNTAIN BIN 1 | GR MT BIN 1 | NON-CORE
0 | 19P000217 | [12 empty] | P5741 | GRANITE MOUNTAIN BIN 2 | GR MT BIN 2 | NON-CORE
0 | 19P000229 | [12 empty] | P5742 | GRANITE MOUNTAIN BIN 3 | GR MT BIN 3 | NON-CORE
0 | 18W007453 | [12 empty] | P5743 | GRANITE MOUNTAIN ROLL-UP BIN | GR MT ROLLUP | NON-CORE
0 | 19P000293 | [12 empty] | P5744 | GRANITE MOUNTAIN STAPLES-ICE HOUSE (HISTORIC) | GR MT ICEHSE | NON-CORE
0 | 18P000474 | [12 empty] | P5745 | GRANITE MOUNTAIN TACK HOUSE | GR MT TACK | NON-CORE
0 | 19W002419 | [12 empty] | P5746 | GRANITE MOUNTAIN WORKSHOP | GR MT SHOP | NON-CORE
0 | 18P000471 | [12 empty] | P5747 | GRANITE MOUNTAIN ALLANSON CENTER RESEARCH CABIN | GM ALLAN ICB | NON-CORE
0 | 19P000373 | [12 empty] | P5748 | GRANITE MOUNTAIN ALLANSON CENTER MEETING/STUDY ROOM | GM ALLAN MR | NON-CORE
0 | 18P000252 | [12 empty] | P5749 | GRANITE MOUNTAIN ALLANSON CENTER BIN | GM ALLAN BIN | NON-CORE
0 | 18P000382 | [12 empty] | P5750 | MOTTE SHED 4 | MOTTE SHED 4 | NON-CORE
0 | 18P000381 | [12 empty] | P5751 | BOYD DEEP CANYON SHOP | DC SHOP | NON-CORE
0 | 19P000021 | [12 empty] | P5753 | MOTTE-RIMROCK RESERVE SHED #1 | MOTTE SHED 1 | NON-CORE
0 | 18P000194 | [12 empty] | P5754 | MOTTE-RIMROCK RESERVE SHED #2 | MOTTE SHED 2 | NON-CORE
0 | 19P000433 | [12 empty] | P5755 | MOTTE-RIMROCK RESERVE SHED #3 | MOTTE SHED 3 | NON-CORE
0 | 3396 | [12 empty] | P5757 | CULVER CENTER FOR THE ARTS | CULVER ROUSE | CORE
0 | 18P000273 | [12 empty] | P5779 | GRANITE MOUNTAIN RESEARCH TRAILER | GR MT RS TR | NON-CORE
0 | 3481 | [12 empty] | P5781 | JAMES SAN JACINTO MTN RESERVE LOLOMI LODGE | JR LOLOMI LG | NON-CORE
0 | 3413 | [12 empty] | P5782 | JAMES SAN JACINTO MTN RESERVE GARAGE | JAMES R GARG | NON-CORE
0 | 3104 | [12 empty] | P5784 | JAMES SAN JACINTO MTN RESERVE TRAILFINDERS LODGE | JR TRAIL FLG | NON-CORE
0 | 2747 | [12 empty] | P5785 | GRANITE MOUNTAIN RESEARCH TRAILER | GR MT RES TR | NON-CORE
0 | 18P000390 | [12 empty] | P5786 | GRANITE MOUNTAIN RESERVE STAPLES RANCH HOUSE | GR MT STAPLE | NON-CORE
0 | 17P000254 | [12 empty] | P5787 | GRANITE MOUNTAIN RESERVE RESIDENCE | GR MT RESIDN | NON-CORE
0 | 19P000209 | [12 empty] | P5788 | HUMAN RESOURCES | HUMAN RSOURC | CORE
0 | 18P000324 | [12 empty] | P5789 | DEEP CANYON AGARE HILL RESEARCH BEDROOM | DC AGARE | NON-CORE
0 | 19P000241 | [12 empty] | P5799 | GRANITE MOUNTAIN RESIDENCE 2 | GR MT RESID2 | NON-CORE
0 | 19P000401 | [12 empty] | P5801 | JR EQUIPMENT SHED 1 | JR SHED 1 | NON-CORE
0 | 19P000414 | [12 empty] | P5802 | JR EQUIPMENT SHED 2 | JR SHED 2 | NON-CORE
0 | 19P000665 | [12 empty] | P5804 | EMERSON MAIN RESIDENCE | EMERSON RES | NON-CORE
0 | 19P000425 | [12 empty] | P5805 | JAMES SAN JACINTO RESERVE CABIN | JR CABIN | NON-CORE
0 | 19P000599 | [12 empty] | P5806 | MOTTE-RIMROCK RESERVE SHOP | MOTTE SHOP | NON-CORE
0 | 19P000573 | [12 empty] | P5807 | JAMES RESERVE CLASSROOM | JR CLASSROOM | NON-CORE
0 | 3516 | [12 empty] | P5808 | JAMES RESERVE CABIN C | JR CABIN C | NON-CORE
0 | 3520 | [12 empty] | P5809 | JAMES RESERVE CABIN B | JR CABIN B | NON-CORE
0 | 3515 | [12 empty] | P5810 | JAMES RESERVE CABIN A | JR CABIN A | NON-CORE
0 | 3521 | [12 empty] | P5817 | LATHHOUSE 4 | LATHHOUSE 4 | NON-CORE
0 | 3523 | [12 empty] | P5820 | FMRI | FMRI | CORE
0 | 3504 | [12 empty] | P5821 | SOLAR GREENHOUSE | SOLAR GREENH | NON-CORE
0 | 3510 | [12 empty] | P5825 | SCHOOL OF MEDICINE TRAILER | T MEDICINE | NON-CORE
0 | 3501 | [12 empty] | P5829 | 4125 WATKINS DRIVE | 4125 WATKINS | NON-CORE
0 | 3508 | [12 empty] | P5900 | UNIVERSITY VILLAGE BUILDING E | UV BLDG E | NON-CORE
0 | 3507 | [12 empty] | P5901 | 1935 CHICAGO AVENUE | 1935 CHICAGO | NON-CORE
0 | 3492 | [12 empty] | P5905 | 555 E TACHEVAH | 555 TACHEVAH | NON-CORE
0 | 3499 | [12 empty] | P5906 | CE-CERT CHASSIS DYNAMOMETER FACILITY | DYNAMOMETER | CORE
0 | 3505 | [12 empty] | P5912 | TRAILER STUDENT HEALTH | T STU HEALTH | CORE
0 | 3474 | [12 empty] | P5913 | 1190 COLUMBIA CE-CERT LEASE | 1190COLUMBIA | NON-CORE
0 | 2900 | [12 empty] | P5914 | EL MIRADOR MEDICAL PLAZA | EL MIRADOR | NON-CORE
0 | 2839 | [12 empty] | P5915 | 1111 CITRUS STREET | 1111 CITRUS | NON-CORE
0 | 2899 | [12 empty] | P5916 | UNIVERSITY VILLAGE BUILDING B | UV BLDG B | NON-CORE
0 | 2368 | [12 empty] | P5917 | INTELLICENTER - UC PATH | INTELLICTR | NON-CORE
0 | 3470 | [12 empty] | P5918 | 4510 BROCKTON AVENUE | 4510BROCKTON | NON-CORE
0 | 3110 | [12 empty] | P5919 | 1955 CHICAGO AVENUE | 1955 CHICAGO | NON-CORE
0 | 2774 | [12 empty] | P5920 | FROST STUDIO | FROST STUDIO | NON-CORE
0 | 3195 | [12 empty] | P5921 | 266 FROST COURT MAIN HOUSE | 266 FROST HOUSE | NON-CORE
0 | 19P000535 | [12 empty] | P5922 | FROST APT | FROST APT | NON-CORE
0 | 19P000386 | [12 empty] | P5923 | FROST GARAGE | FROST GARAGE | NON-CORE
0 | 19P000473 | [12 empty] | P5924 | FROST SHED 1 | FROST SHED 1 | NON-CORE
0 | 19P000434 | [12 empty] | P5925 | FROST LAUND | FROST LAUND | NON-CORE
0 | 19P000017 | [12 empty] | P5926 | FROST SHED 2 | FROST SHED 2 | NON-CORE
0 | 18P000482 | [12 empty] | P5927 | FROST BARN | FROST BARN | NON-CORE
0 | 19P000053 | [12 empty] | P5928 | 285 FROST CT | 285 FROST CT | NON-CORE
0 | 18P000428 | [12 empty] | P5930 | 286 FROST COURT | 286 FROST | NON-CORE
0 | 18P000351 | [12 empty] | P5932 | CITRUS TOWER | CITRUS TOWER | NON-CORE
0 | 19P000033 | [12 empty] | P5933 | PROGENCY PSYCHIATRIC GROUP | PROGENCY | NON-CORE
0 | 19P000018 | [12 empty] | P5934 | ORANGE COUNTY PSYCHIATRY | 18881 VONKAR | NON-CORE
0 | 18P000463 | [12 empty] | P5935 | SILVER OAKS WOMENS HEALTH | 19330 JESSE | NON-CORE
0 | 19P000521 | [12 empty] | P5936 | EVANS PARK NEUROLOGY | 4500BROCKTON | NON-CORE
0 | 19P000030 | [12 empty] | P5937 | APPLE VALLEY NEUROSURGERY | 16143KOKANEE | NON-CORE
0 | 19P000451 | [12 empty] | P5938 | 3333 14TH ST | 3333 14th ST | NON-CORE
0 | 19P000280 | [12 empty] | P5950 | GLEN MOR F | GLEN MOR F | NON-CORE
0 | 19P000353 | [12 empty] | P5951 | GLEN MOR G | GLEN MOR G | NON-CORE
0 | 2725 | [12 empty] | P5952 | GLEN MOR H | GLEN MOR H | NON-CORE
0 | 3415 | [12 empty] | P5953 | GLEN MOR I | GLEN MOR I | NON-CORE
0 | 3237 | [12 empty] | P5954 | GLEN MOR J | GLEN MOR J | NON-CORE
0 | 3345 | [12 empty] | P5955 | GLEN MOR K | GLEN MOR K | NON-CORE
0 | 18W006022 | [12 empty] | P5956 | GLEN MOR L | GLEN MOR L | NON-CORE
0 | 18P000380 | [12 empty] | P5957 | GLEN MOR M | GLEN MOR M | NON-CORE
0 | 18P000261 | [12 empty] | P5959 | BIG SPRINGS PARKING STRUCTURE | BIG SPR PARK | NON-CORE
0 | 19S000833 | [12 empty] | P5980 | CE-CERT OFFICE BUILDING | 1084COLUMBIA | NON-CORE
0 | 18P000400 | [12 empty] | P5981 | CE-CERT CHAMBER BUILDING | 1086COLUMBIA | NON-CORE
0 | 19P000009 | [12 empty] | P5983 | 1200 COLUMBIA AVENUE, RIVERSIDE | 1200COLUMBIA | NON-CORE
0 | 19P000354 | [12 empty] | P5985 | MOTTE RIMROCK RESERVE TRAILER | MOTTE TRAILR | NON-CORE
0 | 19P000408 | [12 empty] | P5986 | USDA SALINITY LABORATORY | SALINITY LAB | NON-CORE
0 | 19P000410 | [12 empty] | P5987 | UNIVERSITY VILLAGE OFFICE LEASE | UV BLDG A | NON-CORE
0 | 19P000248 | [12 empty] | P5990 | CHAVEZ COMCT | CHAVEZ COMCT
0 | 19P000249 | [12 empty] | P5991 | STONEHAVEN APARTMENTS | STONEHAVEN | NON-CORE
0 | 19P000245 | [12 empty] | P5994 | USDA CLONAL GERMPLASM RESPOSITORY | GERMPLASM | CORE
0 | 19P000032 | [12 empty] | P5998 | INTERNATIONAL VILLAGE (UNEX) | INTER VILLAG | NON-CORE
0 | 18P000485 | [12 empty] | PG650 | SUBSTATION | SUBSTATION
0 | 19P000012 | [12 empty] | T MRB1 | MRB1 T1 | MRB1 T1
0 | 19P000014 | [12 empty] | T MRB2 | MRB1 T2 | MRB1 T2
1 | 3052 | [12 empty] | T MRB3 | MRB1 T3 | MRB1 T3
0 | 18P000470 | [12 empty] | Z1005 | SOFTBALL STG | SOFTBALL STG
0 | 19P000458 | [12 empty] | Z1016 | FIELD 9 SHED | FIELD 9 SHED
0 | 19P000255 | [12 empty] | Z1017 | T MORSE HALL | T MORSE HALL
0 | 19P000263 | [12 empty] | Z1018 | T SEELEY HAL | T SEELEY HAL
0 | 19P000256 | [12 empty] | Z1019 | SHIP 29 | SHIP 29
0 | 18P000270 | [12 empty] | Z1020 | T SBUR HALL | T SBUR HALL
0 | 18P000478 | [12 empty] | Z1021 | STOR 14-1 | STOR 14-1
0 | 18P000442 | [12 empty] | Z1023 | COLD 1 | COLD 1
0 | 18W015691 | [12 empty] | Z1024 | COLD 2 | COLD 2
0 | 18P000476 | [12 empty] | Z1025 | COLD 3 | COLD 3
0 | 18W013973 | [12 empty] | Z1026 | COLD 4 | COLD 4
0 | 18P000379 | [12 empty] | Z1027 | COLD 5 | COLD 5
0 | 19P000553 | [12 empty] | Z1028 | COLD 6 | COLD 6
0 | 19P000439 | [12 empty] | Z1029 | COLD 7 | COLD 7
0 | 19P000044 | [12 empty] | Z1030 | T2 FIELD 14-1 | T2 FIELD 14-1
0 | 19P000495 | [12 empty] | Z1031 | SHED 20 | SHED 20
0 | 19W003050 | [12 empty] | Z1032 | T1 STOR | T1 STOR
0 | 19P000225 | [12 empty] | Z1033 | 21 1623 STOR | 21 1623 STOR
0 | 19P000181 | [12 empty] | Z1034 | STOR 23 | STOR 23
0 | 3326 | [12 empty] | Z1035 | 21 1775 STOR | 21 1775 STOR
0 | 18P000215 | [12 empty] | Z1036 | 21 1776 STOR | 21 1776 STOR
0 | 18P000214 | [12 empty] | Z1037 | STOR 26 | STOR 26
0 | 18P000456 | [12 empty] | Z1038 | 21 1595 STOR | 21 1595 STOR
0 | 18P000337 | [12 empty] | Z1039 | STOR 3 | STOR 3
0 | 19P000431 | [12 empty] | Z1040 | STOR 4 | STOR 4
0 | 19P000380 | [12 empty] | Z1041 | STOR 5 | STOR 5
0 | 18P000198 | [12 empty] | Z1042 | STOR 6 | STOR 6
0 | 19P000455 | [12 empty] | Z1043 | STOR 21 6075 | STOR 21 6075
0 | 19P000405 | [12 empty] | Z1044 | SHED 21 | SHED 21
0 | 19P000534 | [12 empty] | Z1046 | COLD STOR | COLD STOR
0 | 18P000348 | [12 empty] | Z1048 | GH 15-49 | GH 15-49
0 | 19P000037 | [12 empty] | Z1049 | SHED 30 | SHED 30
0 | 19P000483 | [12 empty] | Z1050 | SHED 31 | SHED 31
0 | 19P000124 | [12 empty] | Z1051 | SHED 32 | SHED 32
0 | 19P000172 | [12 empty] | Z1052 | FENCE 1 | FENCE 1
0 | 3471 | [12 empty] | Z1053 | STOR 33 | STOR 33
0 | 3486 | [12 empty] | Z1054 | STOR 34 | STOR 34
0 | 3385 | [12 empty] | Z1055 | FENCE 2 | FENCE 2
0 | 3512 | [12 empty] | Z1056 | COOP 1 | COOP 1
0 | 2829 | [12 empty] | Z1057 | COOP 4 | COOP 4
0 | 3534 | [12 empty] | Z1058 | FENCE 4 | FENCE 4
0 | 3524 | [12 empty] | Z1059 | FENCE 3 | FENCE 3
0 | 19P000238 | [12 empty] | Z1060 | COOP 3 | COOP 3
0 | 19P000564 | [12 empty] | Z1061 | COOP 2 | COOP 2
0 | 18P000281 | [12 empty] | Z1062 | SCREEN 35 | SCREEN 35
0 | 19P000326 | [12 empty] | Z1063 | STOR CANVAS | STOR CANVAS
0 | 19P000417 | [12 empty] | Z1064 | SHED 8 | SHED 8
0 | 2245 | [12 empty] | Z1065 | SHED 36 | SHED 36
0 | [13 empty] | Z1066 | CARGO 1 | CARGO 1
0 | [13 empty] | Z1067 | SHED 37 | SHED 37
0 | [13 empty] | Z1068 | SHED 38 | SHED 38
0 | [13 empty] | Z1069 | SHED 39 | SHED 39
0 | [13 empty] | Z1070 | SCREEN 1 | SCREEN 1
0 | [13 empty] | Z1071 | CARGO 2 | CARGO 2
0 | [13 empty] | Z1072 | SHED 40 | SHED 40
0 | [13 empty] | Z1073 | CANOPY FUM | CANOPY FUM
[14 empty] | Z1074 | STOR 38 | STOR 38
[14 empty] | Z1075 | STOR 39 | STOR 39
[14 empty] | Z1076 | STOR 40 | STOR 40
[14 empty] | Z1077 | STOR 41 | STOR 41
[14 empty] | Z1078 | STOR 42 | STOR 42
[14 empty] | Z1079 | STOR 43 | STOR 43
[14 empty] | Z1080 | SCREEN 2 | SCREEN 2
[14 empty] | Z1081 | SHED 41 | SHED 41
[14 empty] | Z1089 | SHED 42 | SHED 42
[14 empty] | Z1090 | GH K1 | GH K1
[14 empty] | Z1093 | PICNIC 1 | PICNIC 1
[14 empty] | Z1094 | PICNIC 2 | PICNIC 2
[14 empty] | Z1096 | METEOR 9C | METEOR 9C
[14 empty] | Z1097 | SHED 8 | SHED 8
[14 empty] | Z1098 | TURF FERTIL | TURF FERTIL
[14 empty] | Z1099 | SHED 9 | SHED 9
[14 empty] | Z1100 | COLD BOX 2 | COLD BOX 2
[14 empty] | Z1101 | INST TOWER | INST TOWER
[14 empty] | Z1102 | PUMP 5 | PUMP 5
[14 empty] | Z1103 | PUMP SHED | PUMP SHED
[14 empty] | Z1104 | TANK STORAGE | TANK STORAGE
[14 empty] | Z1105 | METAL SHED 1 | METAL SHED 1
[14 empty] | Z1106 | METAL SHED 2 | METAL SHED 2
[14 empty] | Z1107 | METAL SHED 3 | METAL SHED 3
[14 empty] | Z1108 | METAL SHED 4 | METAL SHED 4
[14 empty] | Z1109 | METAL SHED 5 | METAL SHED 5
[14 empty] | Z1110 | METAL SHED 6 | METAL SHED 6
[14 empty] | Z1111 | METAL SHED 7 | METAL SHED 7
[14 empty] | Z1112 | METAL SHED 8 | METAL SHED 8
[14 empty] | Z1113 | SOC BLEACHER | SOC BLEACHER
[14 empty] | Z1114 | SOC TRAILER1 | SOC TRAILER1
[14 empty] | Z1115 | SOC TRAILER2 | SOC TRAILER2
[14 empty] | Z1116 | TRACK BLEACH | TRACK BLEACH
[14 empty] | Z1117 | LATH C | LATH C
[14 empty] | Z1118 | LATH 10 | LATH 10
[14 empty] | Z1119 | STEAM GENER | STEAM GENER
[14 empty] | Z1121 | FENCE 6 | FENCE 6
[14 empty] | Z1122 | FENCE 7 | FENCE 7
[14 empty] | Z1123 | METAL TANK 1 | METAL TANK 1
[14 empty] | Z1124 | METAL STOR 1 | METAL STOR 1
[14 empty] | Z1125 | METAL STOR 2 | METAL STOR 2
[14 empty] | Z1126 | COLD 8 | COLD 8
[14 empty] | Z1127 | COLD 9 | COLD 9
[14 empty] | Z1128 | METAL CANOPY | METAL CANOPY
[14 empty] | Z1129 | SHED 45 | SHED 45
[14 empty] | Z1133 | BOT GDN SHD | BOT GDN SHD
[14 empty] | Z1134 | BOT GDN SHD2 | BOT GDN SHD2
[14 empty] | Z1136 | HSNG STOR | HSNG STOR
[14 empty] | Z1137 | CVAR SHADE 1 | CVAR SHADE 1
[14 empty] | Z1138 | CVAR PAD 1 | CVAR PAD 1
[14 empty] | Z1139 | CVAR T1 | CVAR T1
[14 empty] | Z1140 | CVAR OLD ICE | CVAR OLD ICE
[14 empty] | Z1141 | CVAR T LAB | CVAR T LAB
[14 empty] | Z1142 | CVAR STOR 2 | CVAR STOR 2
[14 empty] | Z1143 | CVAR FUEL | CVAR FUEL
[14 empty] | Z1144 | CVAR GH 1 | CVAR GH 1
[14 empty] | Z1145 | CVAR GH 2 | CVAR GH 2
[14 empty] | Z1146 | CVAR INSECT 1 | CVAR INSECT 1
[14 empty] | Z1147 | CVAR INSECT 2 | CVAR INSECT 2
[14 empty] | Z1148 | CVAR INSECT 3 | CVAR INSECT 3
[14 empty] | Z1149 | CVAR SHED 1 | CVAR SHED 1
[14 empty] | Z1150 | CVAR PAD 2 | CVAR PAD 2
[14 empty] | Z1151 | CVAR SHED 2 | CVAR SHED 2
[14 empty] | Z1152 | CVAR SHADE 2 | CVAR SHADE 2
[14 empty] | Z1153 | CVAR STOR 2 | CVAR STOR 2
[14 empty] | Z1154 | CVAR SHADE 3 | CVAR SHADE 3
[14 empty] | Z1155 | CVAR FENCE 1 | CVAR FENCE 1
[14 empty] | Z1156 | CVAR PUMP | CVAR PUMP
[14 empty] | Z1157 | CVAR CONT 1 | CVAR CONT 1
[14 empty] | Z1158 | CVAR CONT 2 | CVAR CONT 2
[14 empty] | Z1159 | CVAR CONT 3 | CVAR CONT 3
[14 empty] | Z2000 | BSL3 LAB | BSL3 LAB

## Planning (hidden)
Project Planning
Last Updated | 2019-09-01
Organization | Total Open Projects | % of Total Projects | Total Approved Budget | Total FS Recharge Cost
ACADEMIC SENATE | 0 | #DIV/0! | 0 | 0
ATHLETICS | 0 | #DIV/0! | 0 | 0
BAS | 0 | #DIV/0! | 0 | 0
BCOE | 0 | #DIV/0! | 0 | 0
CAP.PROG. | 0 | #DIV/0! | 0 | 0
CAS | 0 | #DIV/0! | 0 | 0
CHASS | 0 | #DIV/0! | 0 | 0
CNAS | 0 | #DIV/0! | 0 | 0
FAC-PLNG-DESIGN-CONST | 0 | #DIV/0! | 0 | 0
ITS | 0 | #DIV/0! | 0 | 0
LIBR | 0 | #DIV/0! | 0 | 0
PALM DESERT | 0 | #DIV/0! | 0 | 0
SOB | 0 | #DIV/0! | 0 | 0
SOM | 0 | #DIV/0! | 0 | 0
SoPP | 0 | #DIV/0! | 0 | 0
VC-RED | 0 | #DIV/0! | 0 | 0
VC-STU.AFF. | 0 | #DIV/0! | 0 | 0
VC-UNIV.ADV. | 0 | #DIV/0! | 0 | 0
Totals | 0 | #DIV/0! | 0 | 0
Total Open Projects by Request Date
Organization | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | In Review | Totals
ACADEMIC SENATE | [7 empty] | 0
ATHLETICS | [7 empty] | 0
BAS | [7 empty] | 0
BCOE | [7 empty] | 0
CAP.PROG. | [7 empty] | 0
CAS | [7 empty] | 0
CHASS | [7 empty] | 0
CNAS | [7 empty] | 0
FAC-PLNG-DESIGN-CONST | [7 empty] | 0
ITS | [7 empty] | 0
LIBR | [7 empty] | 0
PALM DESERT | [7 empty] | 0
SOB | [7 empty] | 0
SOM | [7 empty] | 0
SoPP | [7 empty] | 0
VC-RED | [7 empty] | 0
VC-STU.AFF. | [7 empty] | 0
VC-UNIV.ADV. | [7 empty] | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## q_Report_Integrated (hidden)
Proj_Ref_No | CPMS_No | Work_Order_No | IRT | Org | Project_Title | Project_Description | Building | Room | Current_Status | Org_Leadership | Org_Contact (Prioritization Designate) | Contact | Contact_2 | Proj_Mgr | Org_Priority | FS_Priority | FS_Priority_Last | For_Faculty_Hire | Approved_Budget | FS_Recharge_Costs | Project_Initiated | Next_Major_Milestone | Const_Start | Construction_Completion | Impact_Description | Impact_Date_Start | Impact_Date_End | PM_Notes | Scope_Date | Scope_Reviewer | Scope_Notes | Scope_Complete | Completed Date | Owner | IRT? | Requested Year | Data Pulled On | FY | Recharge?
18P000484 |  | 18P000484 | FALSE | ATHLETICS | SL5 INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | Project will be managed by A&E for completion. | SOFTBALL STG |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-26 | [6 empty] | 2/1/19, DL; This is a PD&C Project due to IRT walk. Project will exceed $50,000……….. |  | Enrico Baez | 12/6/18 EB Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | NO | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01
19P000276 |  | 19P000276 | FALSE | ATHLETICS | SL5 TRACK BLEACH-PUBLIC RESTROOMS UPGRADE |  | TRACK BLEACH |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 16 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 11/20/18 EB Project cancelled, will be addressed by PD&C. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB conducted site visit, Client wants additional toilet in mens room, changing table and lighting improvements. ADA Issues. Also spoke with Scott Donnell he has project . | YES | 2018-11-20 | FS | FALSE | 2018 | 2019-08-01
1990a | 1990a |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | Under construction | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2193000 |  | 2015-10-09 | Complete Construction | 2019-05-01 | 2019-11-16 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
19P000571 |  | 19P000571 | FALSE | CNAS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 |  | SCIENCE LAB1 | 215 & 322 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2019-04-10 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000265 |  | 19P000265 | FALSE | ATHLETICS | SL5 ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000646 |  | 19P000646 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING |  | ATH DANCE | 20R, 20S | PROJECT INTAKE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-23 | [8 empty] | Dan Lerman |  |  |  | FS | FALSE | 2019 | 2019-08-01
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  | 10 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 4/18/19, DL; Per Enrico, we are waiting for a proposal from HCI and approved funding from Athletics. We should have the proposal in 2- weeks…. | 2018-09-27 | Enrico Baez | 1/14/19 E Baez. Per "Monty" Athletics are to pay for this project. Joe Erbland emailed to determine if funding has been approved. Waiting on response. ---11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. --- 10/3/2018 EB Install keyless entry system for building exterior. ---9/24/18 EB Site visit scheduled with John Jensen for 9/27 | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000271 |  | 19P000271 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 |  | ATH DANCE | 3 | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000295 |  | 19P000295 | FALSE | ATHLETICS | SL5 PATCH & PAINT |  | ATH DANCE | 50B | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 12 | 18 - 19 | FALSE |  |  | 2018-09-12 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000272 |  | 19P000272 | FALSE | ATHLETICS | SL5 NEED URINAL DIVIDERS | FS to coordinate with customer to scope the work. | ATH DANCE | 50E | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 13 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 3/7/19 O-ANS: Project no longer moving forward per Ron Rector and placed on DM list. 1/15/19 E Baez. Per "Monty" project cancelled to be placed on Deferred Maint. List. Emailed Chris P. to provide renovation cost and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Install dividers for urinals. Wall is tile. |  | 2019-01-24 | FS | FALSE | 2018 | 2019-08-01
19P000270 |  | 19P000270 | FALSE | ATHLETICS | SL5 ATH DANCE-WEIGHT ROOM DROP DOWN CEILING |  | ATH DANCE | 78 | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 14 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project is 100% Complete….. |  | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB remove all t-bar ceiling components. Will need relocation of supply and return registers, lighting Alarms, Etc. |  | 2019-02-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000274 |  | 19P000274 | FALSE | ATHLETICS | SL5 RIV SPORTS CPX - REPLACE URINALS | FS to coordinate with customer to scope the work. | RIV SPORTS CPX |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 15 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-10-15 | Enrico Baez | 1/14/19 E Baez. Per "Monty" this project to go on deferred maint. list. emailed Chris Pillen to provide coast and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27. 10/3/18 EB not time to visit on 9/27. will schedule follow up meeting. 10/15/18 EB conducted site visit, 11 urinals to be replaced. | YES | 2019-01-24 | FS | FALSE | 2018 | 2019-08-01
19P000388 |  | 19P000388 | FALSE | BCOE | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | BCOE Advising is being reassigned to space on the 3rd floor of Skye (at the recommendation of the University Space Committee). | SKYE HALL | 308 | COMPLETE | Christopher Lynch | Maggie Souder | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-26 | [6 empty] | 7/15/19, DL; This project is 100% Complete………..7/1/19, DL; This project ois 95% Complete. Floor covering install will start this Wednesday…………6/17/19, DL; This project is almost complete. Target complete date is July 1st….…..5/31/19, DL; We are making good progress on this project. we are on tract to be copmplete with this project on or before July 1st……5/15/19, DL; Work is in progress and we are on schedule for th3 6/28/19 complete date…….5/1/19, DL; We will start this project this week. 4/15/19, DL; Plans were approved today. We will work on material and schedule the work. We will start this project shortly after May 1st…….3/18/19, DL; We are working on plans and plan to apply for building permit an plan review process next week | 2019-02-13 | Ron Veloz | 03/04/19 O-RVL: Updating notes on FAMIS & Access DB. Scoping is completed. After discussing the project with Monty and Dan, this project does not require an estimate and will be covered under Core since it is required for student advising and department operations. RV has communicated this to Sharyl Murdock on 03/04/19. RV Reassigning from O-RVL to O-UA1. Intake was completed on 02/13/19. ~ 02/22/19 O-RVL: RV walked the site with Enrico to survey carpet. Enrico suggested a deep extraction. RV contacted Custodial to sample a section to determine if cleaning the carpet could enhance the appearance. Pending response for Gena L. ~ 02/21/19 O-RVL Spoke with Monty about carpet conditions. Will walk with Enrico for second opinion. ~ 02/13/19 O-RVL: Completed intake. 01/28/19 O-RVL: Jobwalk scheduled with Hour Glass Co 1/28/19 11:30am ~ 01/25/19 O-RVL: Met Maggie & Sharyl M at Skye to review the SOW for new walls, sliding glass door and interior viewing window. RV will contact a glazing vendor the week of 01/27 to request a quote to install new storefront windows and sliding glass door within a storefront frame or Western Integrated Frame ~ 01/23/19 O-RVL: RV emailed Sharyl for meeting date and time. Pending response. Received response on ~ 01/23 from Sharyl. She will schedule the meeting/site visit. Pending invitation. ~ 1/22/19 O-RVL: Acknowledged request. Will schedule a site visit with Sharyl Murdock. Left voice message and emailed Sharyl (01/22) to schedule a site visit. Proj # is not in the Data base, unable update notes. ~ 01/22/19 RV spoke with Sharyl and will receive an email with updates. ~ 01/22/19 RV received email with updates from Sharyl and added to the project folder. ~ MA 1/7/19: Assigning to Ron Veloz for Estimation process with BCOE partners. | YES | 2019-07-15 | FS | FALSE | 2018 | 2019-08-01 | FY 19-20
19P000647 |  | 19P000647 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- LOCKER ROOM REFRESH |  | ATH DANCE | Men's & Women's Locker Rooms | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-23 | [6 empty] | 6/19/19 O-ANS: Combined with project 19P000646 since work in the same area. Dan Lerman to perform scope. |  | Dan Lerman |  |  | 2019-06-19 | FS | FALSE | 2019 | 2019-08-01
19P000266 |  | 19P000266 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | n/a | N/A | 2018-12-13 | FS | FALSE | 2018 | 2019-08-01
19P000638 |  | 19P000638 | FALSE | BCOE | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM |  | BOURNS | B207 | PROJECT INTAKE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-16 | [8 empty] | Ron Veloz | 07/01/19 O-RVL: Pending intake/site visit to confirm SOW. |  |  | FS | FALSE | 2019 | 2019-08-01
19P000268 |  | 19P000268 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT 20C |  | ATH DANCE | 20C | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000269 |  | 19P000269 | FALSE | ATHLETICS | SL5 ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | Project is not within the purview for completion; condition is fair and usable. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 5 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18…..This is a cooman area. Is this recharge work……. | 2018-09-27 | Enrico Baez | 2/5/19 E. Baez. Common spaces are managed by Facilities Services. Any work done in corridors, stairwells and open spaces will be assessed by FS. 11/20/18 E. Baez-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB-Request for installing vinyl flooring. Remove and replace existing Terrazo and ceramic floor tile in 1st floor lobby and stairs to basement. | YES | 2018-10-04 | FS | FALSE | 2018 | 2019-08-01
19P000275 |  | 19P000275 | FALSE | ATHLETICS | SL5 SOFTBALL STG PRESS BOX AC ADDITION | FS to coordinate with customer to scope the work. | SOFTBALL STG |  | CANCELED BY CLIENT | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 6 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project was canceled by Johnathan J. as there is not funding at this time…………DL, 10/4/18; I checked on this recently and this is not a building, it is stoarge and should be recharge work…. | 2018-09-27 | Enrico Baez | 2/5/2019 E Baez Client wants a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. Client will need to fund this project as this is not a core building 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Client want a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. |  | 2019-02-14 | FS | FALSE | 2018 | 2019-08-01
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | IN PROGRESS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 3/28/19, Doors are in the process of being …. DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez | 10/3/2018 EB approx. 16-20 doors need repair. Sand, patch, repair as needed. Re-varnish. ---9/24/18 EB Site visit scheduled with John Jensen for 9/27 | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000273 |  | 19P000273 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000618 |  | 19P000618 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 205 AND 205A- PAINT |  | COLL BLDG NO | 205 AND 205A | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | In Programming | Tamica Smith Jones | Joseph Erbland | Johnathan Jensen |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2018-08-23 | Create SOW | 2020-01-01 | 2020-04-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. |  |  | In coordination with Mobility Hub | Tamica Smith Jones | Joseph Erbland | Joe Erbland |  | Gerald Caraig | 3 |  |  | FALSE | 0 |  | 2014-04-10 | To be coord. with Rec Mall work | [11 empty] | PD&C | FALSE | 2014 | 2019-08-01
3408 | 3408 |  | FALSE | ATHLETICS | Harrison Field Netting | Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | SOFTBALL STG |  | Per department: Project is on hold until further notice. | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2018-01-23 | OnHold by Cust Til Furthr Notice | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
19P000247 |  | 19P000247 | FALSE | BAS | SL5 LOTHIAN FIRST FLOOR COMMON AREA FLOORING |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Jess Hernandez |  |  |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez |  |  | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000432 |  | 18P000432 | FALSE | BAS | SL5 BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 |  | BANNOCK H | H0101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-05-04 | [8 empty] | Paul Ditty |  | N/A | 2018-07-13 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000209 |  | 19P000209 | FALSE | PLANNING & BUDGET | SL5 OLD EH&S SITE- FS ANNEX A REMODEL |  | ENV H AND S | 100 | COMPLETE | Gerry Bomotti | Sharyl Murdock | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 2018-08-24 | [6 empty] | 7/1/19, DL; This project is 100% Complte….6/17/19, DL; This project is almost complete. Target complete date is 6/26………….5/31/19, DL; This project is in progress. Our goal is to have the projected completed by June 28th……. 5/15/19, DL; We are schedule to start the demo tomorrow. Project timeline is 3-4 weeks….3/28/19, DL; Gunther is working on plans……3/18/19, DL; Conducted site visit with Chris, Hassan and Francis last week. We will work on plans and permits…….9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen | Chris walked the project with Craig Kasten on 9/6/18. | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-08-01 | FY 19-20
18W011772 |  | 18W011772 | FALSE | BAS | SL5 PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | Canceled per customer on priority list 7/3/18 | PRINT MOD |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Dan Lerman |  |  | Canceled | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/29/18; Pasted from WO; install an outside electrical outlet based on the attached amazon specs. also estimate for removing and sealing the outside vent from the copier. fyi_the copier will be moving within the next few months…..DL, 7/11/18; Need to verfy scope and schedule the work...... |  | Enrico Baez | fyi_the copier will be moving within the next few months | YES | 2018-07-03 | FS | FALSE | 2018 | 2019-08-01
19P000222 |  | 19P000222 | FALSE | BAS | SL5 PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000369 |  | 18P000369 | FALSE | BAS | SL5 BOYCE X-RAY IRRADIATOR PROJECT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 1407 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | KAREN JANIGA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-27 | [6 empty] | 12/14/18, DL; This project was cancelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……DL, 5/9/18; Need to work on plans/permits…..DL, 6/16/18; Meeting with Bob and confirmed what is needed. I will work with Gunther on plans. Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall…..DL, 11/7/18; Material is on site. We will schedule the work soon…… |  | Ron Veloz | DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……Need to work on plans….10/17/18 RV: This project was previously scoped and in Plan development. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-01
18P000373 |  | 18P000373 | FALSE | BAS | SL5 POLICE BLDG PAINTING IN DISPATCH AREA |  | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  |  | 8 | FALSE |  |  | 2018-04-02 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18W009630 |  | 18W009630 | FALSE | BAS | SL5 BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. | PHYS PL STOR | 100 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | JUDY HODGE |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-22 | [6 empty] | 3/28/19, DL; This project is cancelled per Judy Hodge….DL, 6/16/18; Project includes demo wall/door install new wall, dry wall, paint, door, eletrical outlets, lighting, smoke relocation, lighting motion, new t-bar, relocate heat pump, andn install new carpet…...DL, 7/11/18; Need to work on plans….. Target complete date is late Fall..... |  | Enrico Baez | See work order 18W012349 scoped and annotated in FAMMIS. 6/11/18 EB- Add wall to current space and eliminate exisiting wall. Relocate exisiting A/C on wall. Minor electrical DND 7/14 Hold per customer on prioritization; per Corp Yard Space Planning | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-08-01
19P000208 |  | 19P000208 | FALSE | BAS | SL5 PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | Canceled per customer on priority list 9/17/18 | THE PLAZA |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | CARLA CHAPPLE |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-14 | [8 empty] | Enrico Baez |  | NO | 2018-09-17 | FS | FALSE | 2018 | 2019-08-01
19P000232 |  | 19P000232 | FALSE | BAS | SL5 BANNOCKBURN J-104 BREAK ROOM UPGRADE | Scheduled work with trades anticipated 60% completion by Jun 15th. | BANNOCK I | I0105 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | John Peraino |  | 6 |  | FALSE |  |  | 2018-09-04 | [6 empty] | 6/14/19, JP; Project on schedule to be completed June 30th 2019. 05/16/19 O-ANS: Project to be 60% completed by June 15th per John P. 04/04/19 JP: This project placed on hold per Housing/Edwin. Finishing up the cabinet and lighting order, will be submitting to purchasing today. Scheduling installation of VCT flooring pending per Tony’s Flooring, will have date this week. New ceiling tiles have been delivered and will be installed when relocating of electrical components are complete. Awaiting confirmation and clearance from Jess to proceed with cutting into walls to facilitate electrical modifications |  | Enrico Baez | 9/19/19 EB-conducted site visit. Entered Scop in FAMMIS and in BZM projects on shared drive. Requires pluming for sink and disposal, electrical, lighting upgrade. | YES |  | FS | FALSE | 2018 | 2019-08-01
18P000106 |  | 18P000106 | FALSE | BAS | SL5 HOUSING PROJECT - OBAN REC ROOM REMODEL |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 3 | FALSE |  |  | 2017-09-14 | [6 empty] | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. DL, 7/11/18; Per Susan this project is back on track. Project is scoped. Gunther will start working on the plans and permits. Once we have the approved permit. still need to check in with Susan on a few items.....Target complet date will be mid- fall...... |  | Enrico Baez | Scope of work has changed and project to be routed to Google IRT/CPMS for completion. EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. 8/22/18 Met with BoB Brumbaugh, Scope of work has changed with additional items. Fire alarm panel relocation, possible building HVAC upgrade. Ask he route project through CPMS and make laundry room and Rec. room one project. | YES | 2019-01-19 | FS | FALSE | 2017 | 2019-08-01
18P000094 |  | 18P000094 | FALSE | BAS | SL5 OBAN LAUNDRY ROOM RENOVATION |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2017-09-08 | [6 empty] | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on bid. 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/12 EB- rec'd approval to contract with Design West to consult on electrical panel upgrade. |  | Enrico Baez | Scope of work has changed and project to be routed to Google IRT/CPMS for completion. 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold. MN 3/20: pending approval from customer on 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/11/18 EB-requested drawings from Gunter per Desgn Wests request. 7/11/18EB-waiting for Desgn West to complete site survey. 8/7/18 EB-Met with Robert Brumbaugh. Scope has changed with additional requirements. Improve HVAC, replace VCT, bathroom remodle. Advised to submit CPMS for A&E. | YES | 2019-01-19 | FS | FALSE | 2017 | 2019-08-01
19P000317 |  | 19P000317 | FALSE | BAS | SL5 HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 | conversation with Susan Marshburn and Bob Brumbaugh. | PENTLAND A |  | CANCELED BY FS | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER | [5 empty] | FALSE |  |  | 2018-10-03 | [9 empty] | D. Dinh : Project canceled; customer collaborating with John Peraino using a TMA work order per |  | 2019-01-14 | FS | FALSE | 2018 | 2019-08-01
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY |  | BOURNS | B0316 | PROJECT INTAKE | Christopher Lynch | Maggie Souder | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-09 | [8 empty] | Ron Veloz | 07/01/19 O-RVL: Pending intake/walk. |  |  | FS | FALSE | 2019 | 2019-08-01
19P000192 |  | 19P000192 | FALSE | BAS | SL5 MAIL-PAINTING |  | MAIL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000235 |  | 19P000235 | FALSE | BAS | SL5 RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | Customer to determine scope of work. | ABER INVER | A0100 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 11 |  | FALSE |  |  | 2018-09-04 | [6 empty] | JP 04/04/19 Project cancelled per Housing/Lisa | 2018-11-01 | Enrico Baez | 11/26/18EB-Tranfered FAMIS work order to John Peraino's bench. Estimate to customer needed, prior to moving forward with project. 11/26/18 EB-SCOPE entered Aberdeen Inverness • Paint acoustic panels. Customer to provide color specification. • Remove carpet and replace with customer specified vinyl plank flooring. Replace base board • Cut door to accept 16” x 7” glass lite. Frame as needed. • Paint door • Replace surface mounted light fixture with LED surface mounted fixture. Customer to approve design. • Clean, paint or replace A/C vents. • Remove louvered vent in wall for abandoned water cooler. Install sheet metal cover, paint to match new wall color. Pentland Hills -Rooms 105 and 107 • Install full height acoustic panels on three walls. • 4th wall on East side of each room gets mirror. Height of mirror to be flush with top edge of door casing. Mirror width to be between inside corner of wall and switch plate cover. Provide cut out in mirror for thermostat installation. • Replace all ceiling tiles. • Replace 2’ x 2’ ceiling light with 2’ x 4’ LED fixture-customer to approve design. Pentland Hills -Rooms 105 and 107 • Remove carpet and replace with vinyl plank flooring, replace base board • Fire rated doors to be replaced with fire rated doors with small lite, approx. dimensions 16’ x 7”. • Paint as needed. Lothian • Install full height acoustic panels on three walls. • 4th wall gets mirror height to be even with door casing height. Customer to determine location. • Replace all ceiling tiles. • Replace ceiling lights with LED fixtures. • Remove all carpet in rooms and replace with vinyl plank and new base board-customer to specify style and color. • Replace door wire reinforced glass with clear, non-reinforced fire rated glass. • Paint as needed. Suggested Vendor for sound absorbing paneling. Riverside Acoustics Contact: Keith Atkins 951-682-6123 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 Met with Bob and Lisa, no firm plans or ideas in place. Lisa will schedule site walk once they have determined what they want. 11/1/18 Conducted site visit with Bob and Lisa. | YES | 2019-04-04 | FS | FALSE | 2018 | 2019-08-01
19P000015 |  | 19P000015 | FALSE | BAS | SL5 POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING |  | POLICE TRLR | 1 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-07-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000233 |  | 19P000233 | FALSE | BAS | SL5 PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | FS to coordinate with customer to scope the work. | MAIL | 884 | CANCELED BY FS | Gerry Bomotti | Georgianne Carlson | AMY EVERETT |  |  |  | 12 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Enrico Baez | Per Enrico, creating two individual WO's for Tile repair (19W004955) and door painting (19W004956). | YES | 2018-09-24 | FS | FALSE | 2018 | 2019-08-01
18P000363 |  | 18P000363 | FALSE | BAS | SL5 PAINT STOREHOUSE ADMINISTRATIVE OFFICE |  | CORP B |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | ERICA HENDERSON |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-03-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000613 |  | 19P000613 | FALSE | CNAS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT |  | COLL BLDG NO | 0203B | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000224 |  | 19P000224 | FALSE | BAS | SL5 PAINT EXTERIOR RAMP AT HUB MODULAR |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | MIKE CLEMONS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000601 |  | 19P000601 | FALSE | BCOE | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY |  | BOURNS | B0328E | PROJECT INTAKE | Christopher Lynch | Maggie Souder | KATHALENA COCKER |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-05-09 | [8 empty] | Ron Veloz | 07/01/19 O-RVL: Pending intake / site visit |  |  | FS | FALSE | 2019 | 2019-08-01
19P000615 |  | 19P000615 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT |  | COLL BLDG NO | 203 AND 204 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000617 |  | 19P000617 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 212- PAINT |  | COLL BLDG NO | 212 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-01
18P000483 |  | 18P000483 | FALSE | BAS | SL5 INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | FS to coordinate with customer to scope the work. | P1 |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | AMANDA GREY |  | Enrico Baez |  | 7 |  | FALSE |  |  | 2018-06-26 | [6 empty] | Waiting for Amanda Grey to verify ownership of chain link fence. Once confirmed will contract with De Anza to install 36" wide gate. | 2018-08-29 | Enrico Baez | 12/3/18 EB-Cancelled request per email from Amanda Gray. Will resubmit request when funding is available. 10/1/18 EB-Contract De Anza Fence to have a gate installed at chain link fence leading to storm culvert in parking lot 1. | YES | 2018-12-03 | FS | FALSE | 2018 | 2019-08-01
19P000022 |  | 19P000022 | FALSE | BAS | SL5 HUB--PAINT TWO WALL AS SCOTTY'S HUB |  | HUB | 101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | DIANE THOMAS |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-07-12 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-09-17 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000060 |  | 19P000060 | FALSE | BCOE | SL5 CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | CHUNG HALL | 223 & 224 | TO BE PERFORMED BY PD&C | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 6 | 4 | FALSE |  |  | 2018-05-15 | [6 empty] | 2/1/19, DL; Thios is a PD&C project. Maggie S. is aware this project may be a $130,00. project……DL, 7/25/18; This project is complicated and plans/permits will be required. This project will also require Air Hanlers to be shut down so Vibration dampners can be instlled. We will work on the plans in the next 45 days. This project should be scheduled during the Winter. We may also need to rent a large portable air handler to ensure the Large server room can maintain temp……. Project #19P000060 to replace REF CPMS # 9043. DL, 11/7/18; Sent Maggie an email on 11/7/18 informing her this project is well beyond our scope and $50K threshold. |  | Dan Lerman | DD 7/17: IRT Scoped with Dan present. Attached to FS Project. REF CMPS 9043 | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01
18P000095 |  | 18P000095 | FALSE | BAS | SL5 THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS |  | THE PLAZA | A0013 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  | C | HOLD | FALSE |  |  | 2017-09-08 | [6 empty] | 4/11/EB-On Hold per Robert Brumbaugh. 6/8 EB-emailed R. Brumbaugh for status update. |  | Enrico Baez | Canceled per customer on priortization list. 4/11/EB-On Hold per Robert Brumbaugh. DND 7/14 Hold per customer on prioritization | YES | 2018-06-08 | FS | FALSE | 2017 | 2019-08-01
18P000126 |  | 18P000126 | FALSE | CHASS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS |  | HUM & SOC SC | 3611 | COMPLETE | Milagros Pena | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 2017-09-28 | [6 empty] | 7/1/19,DL; This project is 100% Complete…..5/15/19, DL; Work is scheduled to start on 6/19/19…….5/1/19, DL; Plans are approved. Need to order material and schedule the work…..3/18/19, DL; Plans submitted to PD&C today…..02/2819, DL; Gunther will work on plans over the next three weeks to submit for a building permit. We will schedule the work if and after the plans are approved. If approved the door and window will more than likely have a 3- month lead time…………….12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS. Remove double doors and install single door.Remove small West wall. Relocate t-stat. Ceiling work. Replace carpeting. | YES | 2019-07-01 | FS | FALSE | 2017 | 2019-08-01 | FY 19-20
3286 | 3286 |  | FALSE | BAS | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | In Bidding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 1 |  |  | FALSE | 2985000 |  | 2017-03-29 | Award Bid | 2019-07-01 | 2019-11-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3403 | 3403 |  | FALSE | BAS | Parking Lot 23 Addition | Parking Lot 23 Expansion - The goal of the project is to add additional parking capacity to Parking Lot 23 to serve that area of the campus. Current parking capacity in this area will be impacted by the closures of Lot 22 and Crest Housing parking area. Additional capacity will be need for employee parking. |  |  | On Hold | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Daneca Stevens | 5 |  |  | FALSE | 92000 |  | 2018-05-17 | Funding | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3430 | 3430 |  | FALSE | BAS | TAPS Cust Svc Lobby Upgrades | Upgrades to Customer Service Lobby – Need to complete Tenant Improvement project upgrade customer service counter in Parking Services Building. Want to replace current counter to allow for; modern computer equipment, dividers between customers’ transaction spaces, under counter space for filing cabinets and check writing space. Please coordinate with Auxiliaries’ primary PM John Franklin. | PARKING SERV |  | On hold until Summer 2019 | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Dave Bomba | 6 |  |  | FALSE | 0 |  | 2018-05-17 | On hold until Summer 2019 | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3354 | 3354 |  | FALSE | BAS | Lot 4/Barn Area ADA Improvements | Lot 4/Barn Area ADA Improvements - The proposed project will relocate an existing crosswalk that is not ADA compliant and provide path of travel improvements and additional ADA parking capacity in Parking Lot 4. The existing crosswalk located at West Campus Drive and Parking Lot 4 (north) was identified in the Draft ADA Transition Plan to be out of compliance. A Pedestrian Safety Study by Fehr & Peers completed in June 2008 identified the relocation of this crosswalk to approximately 100 feet east to provide a more visible, safe, pedestrian crossing. To increase pedestrian safety further, the crosswalk will be designed as a speed table. Additionally, Transportation and Parking Services proposes to create additional ADA parking spaces in Parking Lot 4 that exceed the required number, with hardscape and path of travel improvements that will connect to the new crosswalk. The improved crosswalk will correct required path of travel deficiencies from a parking lot that provides access to numerous publicly accessible buildings, as well as allow the Barn Expansion project to obtain Division of State Architect (DSA) approval once construction is completed. The funds to complete the crosswalk replacement will be requested from Campus ADA funds. Parking Lot 4 improvements will come from will come from TAPS. Although this project supports the Barn Renovation, its conception and need is not tied to the Barn project. The crosswalk improvements and additional ADA parking is needed to meet our ADA parking requirements and serve the growing demand on campus. This project is desired regardless of the Barn Renovation project. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | John Franklin | 7 |  |  | FALSE | 50000 |  | 2017-08-15 | Bidding | 2019-09-01 | 2019-11-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3439 | 3439 |  | FALSE | BAS | TAPS Strategic Master Plan Study | STUDY - Transportation And Parking Master Plan Study This study initiated by TAPS is part of a comprehensive planning effort within Auxiliaries to develop a strategic transportation and parking plan that will guide the university’s transportation and parking efforts over the next decade. This is complementary to the campus Physical Master Plan Study and will help inform the future new LRDP. |  |  | Postponed until Mid-2019 | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Michelle Baniqued | 8 |  |  | FALSE | 0 |  | 2018-06-05 | Postponed until Mid-2019 | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3376 | 3376 |  | FALSE | BAS | West Lothian Roof Replacement Design | Provide Schematic Design, Design Development and professional cost estimate to replace the existing single-ply membrane roof system on the Lothian West residence hall wings plus Common Area applications. Existing roofing is past its useful life and starting to experience multiple leaks that are damaging living spaces below. Design effort should select the most appropriate roof material for this roof plan. The intent is to design this year (alongside the Lothian East design) and construct immediately following the Lothian East roof replacement. | LOTHIAN HALL |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 9 |  |  | FALSE | 0 |  | 2017-09-28 | Complete Construction | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3383 | 3383 |  | FALSE | BAS | W Lothian Air Handler Replacemt | Existing air handler equipment in West Lothian is original to the building and past its service life. Provide HVAC professional services to develop options for Air Handler replacement that meet UC Carbon Neutral 2025 goal. Each option analysis should include pros and cons for energy consumption, reliability, serviceability and system installation cost projections. At least one option should explore potential conversion to individual package units as practical. | LOTHIAN HALL |  | Complete Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 10 |  |  | FALSE | 883000 |  | 2017-10-03 | Complete Construction | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3453 | 3453 |  | FALSE | BAS | ECS N&S Playground Shade & Turf | Provide Schematic Design, Design Development and Professional Cost Estimate for the alteration of existing shade structures, provision for additional shade structures, refinish interior metal fencing, and the replacement of existing grass with synthetic turf at the Early Childhood Services north and south playground areas. Prepare drawings so that they can be bid and constructed as separate projects. |  |  | Dept approval/funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 12 |  |  | FALSE | 0 |  | 2018-07-03 | Dept approval/funding | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3459 | 3459 |  | FALSE | BAS | A-I Hardscape Landscape Design-Study | Provide Schematic Design and Design Development drawings for a selective renovation of all hardscape and landscape around the perimeter of the Aberdeen-Inverness housing complex. Scope to include (but not limited to) widening of South Walk and replace its asphalt with concrete pavers, upgrade hardscape and landscape at Horseshoe, replace selected lawn areas with hardscape, seating and solar umbrellas at east and west lawns of Building E, consider new bike storage along South Walk, consider modifying slopped lawn between Building A and Linden St., generally reduce lawn areas and replace with sustainable planting, prune or replace unkempt trees, replace selected light fixtures to match Dundee fixtures, and generally freshen the landscaping so that it is harmonious with the new Dundee development. Design to be packaged in phases, with the South Walk and Dundee-facing landscape to be ready in Phase 1 for construction timing alongside Dundee-Glasgow landscaping in Spring of 2020. | ABER INVER |  | Architect design meetings scheduled. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 13 |  |  | FALSE | 160000 |  | 2018-07-16 | Complete Design | 2020-02-01 | 2020-09-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
3462 | 3462 |  | FALSE | BAS | A-I Restaurant & Lobby Reconfiguration | Provide Schematic Design and Design Development drawings for the complete reconfiguration of Building C including kitchen, dining space, and common areas. The restaurant and kitchen areas are largely original to the building and well past their useful life. The new, replacement, Glasgow restaurant coming on-line in Fall 2020 will allow a needed reprogramming and modernization of this space. Preliminary Program for this space includes a smaller Catering Kitchen, Meeting Rooms, new KUCR studio as well as a modernization and upgrade of the Lobby and other Common Areas. Documents to be assembled for a Fall 2020 construction start. | ABER INVER |  | Architectral selection contract negotiations | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 14 |  |  | FALSE | 100000 |  | 2018-07-17 | Complete Design | 2020-06-01 | 2021-06-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
3463 | 3463 |  | FALSE | BAS | Landscape Strategic Plan for Housing Services | Provide a comprehensive study of existing landscape areas within Auxiliary Services and provide specific and actionable recommendations for their conversion to sustainable landscaping by location. Study to include all Resident Hall and Apartment properties and include conceptual cost estimates, by location, for proposed landscape conversions. |  |  | Project on-hold | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 15 |  |  | FALSE | 0 |  | 2018-07-17 | On hold per Auxiliary Services | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3460 | 3460 |  | FALSE | BAS | A-I Restroom Replacement - Reconfig | Provide Schematic Design and Design Development drawings for the complete replacement of the restrooms in all four resident hall wings. Existing restroom fixtures and finishes are largely original to the building and long past their service life, causing serious leaks between floors. New restrooms will be reconfigured to meet current accessibility code. Documents to be assembled for phased construction, one wing per summer, with the first building (D-Wing) to be constructed in Summer 2019. | ABER INVER |  | NTP and Start of Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 16 |  |  | FALSE | 2782000 |  | 2018-07-19 | Construction | 2019-07-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
3467 | 3467 |  | FALSE | BAS | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | Issuance of PSA | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 18 |  |  | FALSE | 50000 |  | 2018-07-31 | Site Inspections | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3466 | 3466 |  | FALSE | BAS | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Review of the assessment report to determine project plan. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 19 |  |  | FALSE | 0 |  | 2018-07-31 | Design Review | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3382 | 3382 |  | FALSE | BAS | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 20 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2021 | [11 empty] | PD&C | FALSE | 2017 | 2019-08-01
2868 | 2868 |  | FALSE | BAS | West Lothian Elevator Renovation |  |  |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 21 |  |  | FALSE | 365000 |  | 2015-04-08 | Complete Construction | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
3392 | 3392 |  | FALSE | BAS | Bicycle Master Plan Study | Bicycle Master Plan Study. This CPMS project is for the funding and creation of a Bicycle Master Plan Study for the UCR Campus. It is not for a specific capital project. |  |  | Pre-Programming | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Melissa Garrety | 22 |  |  | FALSE | 115000 |  | 2017-11-13 | Funding | [11 empty] | PD&C | FALSE | 2017 | 2019-08-01
3472 | 3472 |  | FALSE | BAS | Lot 20 Trash Enclosure Relocation | Construct a new CMU trash enclosure with water and power in a different location of Lot 21 to replace the existing enclosure that will be demolished to make way for the Dundee Residence Hall construction. Include hose bib for cleaning and power for future compactor installation. New enclosure needs to be on line BEFORE site construction can start on Dundee-Glasgow in January 2019. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 23 |  |  | FALSE | 0 |  | 2018-08-15 | Bidding | 2019-09-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
3397 | 3397 |  | FALSE | BAS | Dundee Residence Hall and Glasgow Dining | (Lot 22/Dundee-Glasgow) A newly proposed student housing development, including a single phase 760-bed residence hall and an 830-seat dining facility located on the existing Parking Lot 22 site south of Linden Street. The project is anticipated to be completed by Fall/Winter 2020. Funding for predevelopment activities including CEQA and staff augmentation to be determined. | ABER INVER |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Raoul Amescua | 24 |  |  | FALSE | 1120000 |  | 2017-11-21 | Complete Construction | 2019-01-01 | 2020-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3203 | 3203 |  | FALSE | BAS | Plaza Structural Seismic Study | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. |  |  | Site Inspection of C, E & F and conceptual planning review | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 25 |  |  | FALSE |  |  | 2016-10-10 | Design development | [11 empty] | PD&C | FALSE | 2016 | 2019-08-01
3490 | 3490 |  | FALSE | BAS | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Dave Bomba | 28 |  |  | FALSE | 1696000 |  | 2018-12-06 | Selection of Design Build Team | 2019-12-01 | 2021-02-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
3503 | 3503 |  | FALSE | BAS | Falkirk Stair/Front Porch Repair | Repair or replace four sets of entry stairs and landings that are long past their service life and are a life safety concern. Consider replacing these wood structures with steel to ease future maintenance. Apartments affected are #3RS, #11MN, #15A and #16FG. |  |  | In Bidding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 29 |  |  | FALSE |  |  | 2019-02-01 | Complete Construction | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-01
3411 | 3411 |  | FALSE | BAS | MRB Café Buildout & MS&E Loading Dock Mods | MRB1 CAFE and SERVICE YARD INTERIOR FIT-OUT: provide design and construction services to build out the interior of the MRB1 Café shell and modify the MS&E Service Yard to accommodate the café deliveries and trash movement. This CPMS Request is to combine and replace previously approved CPMS #3378 and #3398 into one project as requested by A&E. Please note that the IRT Job walk has already been completed. Intent is to design in FY'17/18 and construct in FY '18/19. Opening to coincide with the MRB1 facility turnover. Food service equipment will be Owner Furnished on a separate UCR Purchase Order. Note that the MRB1 Café shell construction is provided by the separately funded MRB1 project, construction drawings for this shell space are attached in CPMS. | MAT SCI ENGR |  | In Close-out | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Mihai Gavan | 30 |  |  | FALSE | 793000 |  | 2018-02-05 | Complete Close-out | 2018-11-19 | 2019-05-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
2508 | 2508 |  | FALSE | BAS | Barn Expansion | Project 950493 Barn has completed the DPP process and we are now adding this to CPMS to capture expenses related to the Program Process which occurred in FY11-12 and FY12-13. Please move all expenditures from A01233-70003-76 Cost Center to JR142 to a plant account. |  |  | In construction | Gerry Bomotti | Georgianne Carlson | Susan Marshburn |  | D.Hecht/J.Franklin | 33 |  |  | FALSE | 28929771.28 |  | 2013-07-05 | Complete Construction | 2018-06-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2013 | 2019-08-01
3519 | 3519 |  | FALSE | BAS | CBTL Permit Inspections | CBTL PERMIT INSPECTIONS - The Coffee Bean & Tea Leaf restaurant is being leased by a CBTL franchisee (currently this is operated by UCR). They have submitted drawings to do a light remodel of the space. Permit and inspection services are needed to support their remodel. |  |  | Project Number 110114 assigned | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 34 |  |  | FALSE |  |  | 2019-04-04 | Complete Construction | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3421 | 3421 |  | FALSE | BAS | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 35 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3426 | 3426 |  | FALSE | BAS | Lothian Boiler Replacement | The boiler equipment at Lothian is original to the building and past its useful life. Design, procure and install a replacement boiler that incorporates the latest energy saving and management technology that can be cost-effectively installed as a direct replacement to the existing unit. | LOTHIAN HALL |  | On hold | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 36 |  |  | FALSE | 0 |  | 2018-03-19 | On hold | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3533 | 3533 |  | FALSE | BAS | Solar Rooftop Initiative | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. |  |  | Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 39 |  |  | FALSE |  |  | 2019-06-03 | Design | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
19P000207 |  | 19P000207 | FALSE | CHASS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | IN PROGRESS | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-08-23 | [6 empty] | 7/15/19, DL; Floor covering will be installed next week. Floor covering is the last item for this project……..7/1/19, DL; This project is 95% complete except floor covering. Floor covering will be installed within 2- weeks……6/17/19, DL; This project is making good progress. We should be complete near July 1st…….5/31/19, DL; This project started this week and should be complete by June 28th…….3/18/19, DL; Working on plans and we will submit our plans and permit application this week….. | 2018-09-20 | Enrico Baez | 9/20/18 EB-Conducted site visit. Request to remove window in hall and install door. Interior space walls not to be removed. Secure doors, blank off and cover with sound soak. Replace carpet with Vinyl Plank, patch and paint. ---9/19/18 EB-Site visit scheduled for 9/20/18.---9/13/18 EB emailed Toya Adams to schedule site visit. | YES |  | FS | FALSE | 2018 | 2019-08-01
18P000321 |  | 18P000321 | FALSE | BCOE | SL5 STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST |  | STUDENT SERV | 1228 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Enrico Baez |  |  |  | FALSE |  |  | 2018-02-22 | [6 empty] | DL, 4/29/18; Enrico is cordinationg this. The permits are approved……. DL, 7/11/18; Just received confirmation the door is ready for delivery and installed. I need to check in with Paul about the paint and prep of the door. I also need to check in with Jason on lock hardware......Dl, 7/25/18; Door is painted and ready for install. Called Dugmore to schedule the install. This should be compolete within the next two weeks......DL, 8/8/18; This Project is 100% Complete |  | Enrico Baez | DL, 4/29/18; Enrico is cordinationg this. The permits are approved. EB. 5/11/18- waiting for PO to be issued to Vendor. Customer provided PO numbers, waiting to schedule install with vendor, 5 week lead time. | YES | 2018-08-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000343 |  | 18P000343 | FALSE | CHASS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER |  | THTR WKSH | 0400A | IN PROGRESS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 2018-03-16 | [6 empty] | 07/11/19 O-ANS: Dan and Chris P will walk the space. 05/21/19 O-ANS: Changed to In Progress per meeting with Dan L. Chris P is the PM for further updates. DL and CP will visit after commencement. 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez | Scope of work has been reviewed; determining how to complete project with trades. 5/11/18 EB-Conducted site visit on 3/21/18. Work based on Safety report written in October. Work consists of replacing door latches to orchestra pit. Adding loading dock rail, Paint frame guard, signage, gate/fall restraints, ladder modifications. | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000419 |  | 19P000419 | FALSE | CHASS | SL5 CHASS INT SOUTH 2117-CARD ACCESS |  | CHASS INT SOUTH | 2117 | Project Intake | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 2018-12-18 | [7 empty] | 2019-03-21 | Enrico Baez | 7/1/2019 E. Baez- Met with HCI on 6/28/2019, conducted job walk. Waiting for proposal. 4/18/19 E. Baez-Emailed Paul, Monty and Chris P. The project is requested in conjunction with Project 19P000400 ( moving walls and creating separate entry into 2117A). Both projects will need to be considered one project as work is requested for same area. 4/2/19 E. Baez- conducted job walk with HCI for proposal. Waiting for proposal. ***per Paul Richardson remove 2117G, 2117H and 2117J from request*** 3/19/19 E. Baez Scheduled site visit with Paul for 3/21/19 @ 11:00 ***3/19/19: O-ANS: Customer SOFT PRIORITIZED as priority 102.* | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000337 |  | 19P000337 | FALSE | CHASS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | Remove whiteboard (in front of room), mount LED mount, add double duplex and electrical power behind LED, patch and paint wall | PSYCHOLOGY1 | 3210 | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 1 | 101 | FALSE |  |  | 2018-10-11 | [6 empty] | 7/15/19, DL; I will walk the project in the near future and schedule the work if permits are not required…… | 2019-01-15 | Enrico Baez | 1/15/2019 E Baez please Scope completed 1/15/2019 see Shared drive file for more information. | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000415 |  | 19P000415 | FALSE | CHASS | SL5 PSYCHOLOGY -PSY BLDG- MINOR RENOVATION | Doorway with side window connecting 2124C to 2124B, as well as another doorway to connect 2124C to 2124D. | PSYCHOLOGY1 | 2124A,B,C,D | QUEUE TO START | Milagros Pena | Cindy Williams | Jay Melashenko |  | Dan Lerman |  | 3 | 2 | FALSE |  |  | 2018-12-17 | [7 empty] | 2019-01-09 | Dan Lerman | 12/14/18 E.Baez-Met with Jay Melashenko. Suggested the possibility of cutting wall open in 2124D and 2124B both leading to 2124C. No doors to be installed. Only finish opening. Install a low rise threshold at new opening, new carpet recently installed. Need to move outlets. Customer to pay for work. | YES |  | FS | FALSE | 2018 | 2019-08-01
18P000472 |  | 18P000472 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALL |  | CHUNG HALL | 458 | COMPLETE | Christopher Lynch | Maggie Souder | JANNA LE BLANC |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000454 |  | 18P000454 | FALSE | BCOE | SL5 BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS |  | BOURNS | A0346 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  |  | 9 | FALSE |  |  | 2018-05-29 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000350 |  | 19P000350 | FALSE | CHASS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | MISC WORK IN ROOMS 3121 AND 1133 Patch and paint-relocate white boards, hang pictures. | PSYCHOLOGY1 | 3121, 1133 | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 4 | 3 | TRUE |  |  | 2018-10-17 | [6 empty] | 7/15/19, DL; Appears not plans and permits will be required for the work. I will verify and schedule the work in the near future if no plans or permits are required….. | 2019-04-15 | Enrico Baez | 4/11/19 E.Baez emailed Toya Adams to schedule site visit | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000421 |  | 19P000421 | FALSE | CHASS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | Install door to access hallway directly | OLMSTED | 2139I | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 5 | 110 | TRUE |  |  | 2018-12-19 | [7 empty] | 2019-02-05 | Enrico Baez |  | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000413 |  | 19P000413 | FALSE | CNAS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | Batchelor 3111-Refresh BSL2 lab to accomodate Biosafety Cabinet. The Biosafety. Cabinet will be procured by BPSC. | BATCHELOR | 3111 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH | PATTY SPRINGER | Dan Lerman |  | R1 | 107 | FALSE |  |  | 2018-12-17 | [7 empty] | 2019-06-12 | Ron Veloz | 07/02/19 O-RVL: Met with Monty. RV will prepare estimate and call Patty to explain the estimate costs and inclusions based on EH&S requirements and also share concerns about the building infrastructure capabilities questioned by PD&C to meet the BSL2 lab requirements. Explain that the Batchelor Building reno will not increase the building's capacity and the BSL 2 requirement may not be met if the building single pass exhaust and HVAC systems cannot deliver the proper air exchanges etc.. Costs will not include additional work and or building systems modifications if required by PD&C. END~ 07/01/19 O-RVL: Pending estimate completion, hold per Monty on 06/28/19 to discuss/review estimate. END~ 06/24/19 O-RVL: Preparing Estimate. Received costs from Jess H for abatement and to replace flooring. Paul D will providean estimate for patch and paint. END~ 04/15/19 O-RVL: RV to scope project at the new room location 3111. End~ 03/19/19 O-RVL: Updating notes. PENDING Site visit with PM at rm 3111. Date TBD. END~ 06/17/19 O-RVL: Walked site with Patty Springer on 06/12/19. Reviewed SOW and noted work to make the necessary repairs per EH&S survey/correction list. RV will prepare a ROM estimate with project ranges. END~ 03/07/19 O-RVL: RV noticed this project was not on the Minor renovation list and brought up to Monty via email. END~ 03/18/19 O-RVL: RV changed room from 2203 to 3111. END ~ 03/04/19 O-RVL: Changed from O-RVL to O-UA1. END ~ 03/01/19 O-RVL: Received confirmation from Patty that room 3111 will be the permanent location for lab. RV changed the title from SL5-"Install Bio-safety Cabinet and Sink In Batchelor 2203" to SL5 "Renovate Batchelor Hall BSL-2 Lab Room 3111". RV will visit site for initial intake upon prioritization by the Dean's office. END~ 02/19/19 O-RV: Patty "HI Deborah, There is much uncertainty about the Batchelor Hall renovation and the timing of installation of an equipment room in 2163. Given that, I am considering 3111 the permanent location for the biosafety cabinet (replacing room 2203). 3111 will remain a dedicated BSL2 -use room" END ~ 02/14/19 O-RV: Patty Springer decided to try to use 3111 in lieu of 2203. END ~ 02/13/19 O-RVL: Received email from Tiffany Kwok, she wrote, " Hi Dr. Springer, It was great meeting with you this morning. For Batchelor 3111, there are a few items that need to be addressed before it can support BSL-2 work. Floors should be patched to provide a smooth and easily cleanable surface. Base coves along the wall should be replaced or repaired to provide a smooth and easily cleanable surface. Base coves under the cabinets on the corners should be provided. Provide a layer of sealant over the cabinets to ensure that the cabinets are moisture resistant and easily cleanable. Seal, repair or replace the wooden rack on the wall to provide a moisture resistant and easily cleanable surface. Ensure the door is self-closing. END ~ Since this is not a new facility and the space is not undergoing major renovations, it is not required to provide negative airflow into the space. However, it is still important that the air from the laboratory is not recirculated into clean spaces. Please let me know if you have any additional questions. Thanks, Tiffany Kwok". END ~ 02/08/19 O-RVL: On Feb 8, 2019, at 11:54 AM, Bpschair wrote: Hi all, I don’t think we want to do this - it is too much work, disruption, and expense. Deborah Mc Williams requested Dan L to place the current project on "Hold" pending further direction from Patty. This way it will remain in queue". END ~ 01/29/19 O-RVL: Adding SOW for BSL2 Lab: Install: One base cabinet with sink, chemical resistant top, install D.I. water, replace the door with a solid door, keypad entry lockset, Waterproof and patch the south concrete wall, Patch and Paint all walls with epoxy paint, replace damaged/rusted T-bar ceiling grid as needed, replace all existing 2x4 ceiling tiles with Armstrong washable/clean room ceiling tile or | YES |  | FS | FALSE | 2018 | 2019-08-01 |  | 1
19P000589 |  | 19P000589 | FALSE | CHASS | SL5 HMSS OFFICE 3405 RENOVATIONS | Construct partion, pending CBO approval, in room 3405. | HUM & SOC SC | 3405 | QUEUE TO START | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2019-04-23 | [7 empty] | 2019-06-27 | Enrico Baez |  | YES |  | FS | FALSE | 2019 | 2019-08-01
19P000540 |  | 19P000540 | FALSE | CHASS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | Remove metal roll up window, replace carpet, remove round column cover-reframe square. | HUM & SOC SC | 1202 | QUEUE TO START | Milagros Pena | Cindy Williams | JENNIFER MORGAN |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2019-03-20 | [7 empty] | 2019-07-25 | Enrico Baez | Ref: CP3514; Notes on project request in FAMIS and Shared drive. | YES |  | FS | FALSE | 2019 | 2019-08-01
19P000639 |  | 19P000639 | FALSE | CNAS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK |  | CHEMICAL SCI | 0435 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-17 | [8 empty] | Ron Veloz | 07/19/19 O-RVL: Updated notes from work request screen. "07/17/19 O-RVL: Met with Tim, Dan L, Nick and Tran(EH&S) will revise intake and scope for new location. Pending approvals from EH&S for the newly proposed location for Biosafety cabinet in room 441. Receieved request from Tim Su on 07/19 "bench and cabinet removal, would it be possible to have them delivered to Chemical Sciences Room 108 after they are taken out?" Pending final revisions from Tim Su. " END~ 07/01/19 O-RVL: Pending intake/site visit to confirm SOW. END~ CR Routing 6/19/19: Summer ’19 Renovation Project Priority 1; For Faculty Hire YES. (Stephen C) |  |  | FS | FALSE | 2019 | 2019-08-01
19P000445 |  | 19P000445 | FALSE | BCOE | SL5 BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT |  | BOURNS HALL | B0328D | CANCELED BY FS | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  |  |  | 0 |  | FALSE |  |  | 2019-01-11 | [8 empty] | Ron Veloz | 02/27/19 O-RVL: RV sent a project cancellation request to Deborah H and cc'd Alan S., Linda B., Loretta V. & Monty. RV reassigned from O-RVL to O-UA1. END--- 02/22/19 O-RVL: RV Received information from the last team meeting that is project will be cancelled and resubmitted at a later date. RV spoke with Maggie about the cancellation on Wednesday 2/20 and informed her a I would send a letter to follow up from our conversation. Maggie understood the scope creep from the previous project and will resubmit the request at a future date. END--- 02/15/19 O-RVL: Ron V will contact Maggie and explain this request would exceed our proejct allowance and place FS out of compliance with UC requirements. RV will present options to the customer. Possibility to utilize black out curtains and or BKM style furniture as an immediate altenative (Cost absorbed by the departments). The customer will be able to resubmit the request at a later date. END--- 2/7/19: Alan S. Customer Relations Team to follow-up with customer re: change in scope of work. END--- 1/11/19 SPOKE TO DAN LERMAN-THIS PROJECT MAGGIE SOUDER NEEDS IT DONE ASAP - PLEASE SEE DAN LERMAN FOR MORE INFO...DEBORAH email to Monty for Maggie's request. | N/A | 2019-02-27 | FS | FALSE | 2019 | 2019-08-01
19P000619 |  | 19P000619 | FALSE | BCOE | SL5 BOURNS, RM A0311- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0311 | IN PROGRESS | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-05-14 | [6 empty] | 06/28/19 O-ANS: Paint phase complete and awaitin flooring install. | [5 empty] | FS | FALSE | 2019 | 2019-08-01
19P000027 |  | 19P000027 | FALSE | ATHLETICS | SL5 ATHLETICS PATCH & PAINT ROOM | 9/19/18 | ATH DANCE | 0120C | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | DL, 9/19/18; This Project is 100% Complete……. |  | Paul Ditty | N/A | N/A | 2018-09-19 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000328 |  | 18P000328 | FALSE | ATHLETICS | SL5 HINDERAKER BASEMENT OFFICE REPAIR |  | HINDERAKER |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-01 | [6 empty] | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with Paul. Paul will complete as in the near future. Carpet will be installed shortly after......5/21/18, Painters started paint. Should be complete with paint by the end of the week....DL, 5/24/18; Painters are complete. Jess will schedule the carpet install.....DL, 6/12/18; Project is 98% Complete. Carpenters need to under cut two doors to accomodate the carpet.....DL, 7/11/18; This Project 100% Complete..... |  | Dan Lerman | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with PAul. Paul will complete as in the near future. Carpet will be installed shortly after...... | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000453 |  | 19P000453 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT |  | CHUNG HALL | 447 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-17 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000621 |  | 19P000621 | FALSE | BCOE | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0308 | QUEUE TO START | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000059 |  | 19P000059 | FALSE | BCOE | SL5 CHUNG HALL 201 SECURITY SYSTEM INSTALL | ITS to install cameras, no work by FS Required. | CHUNG HALL | 201 | CANCELED BY FS | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 10 | 7 | FALSE |  |  | 2018-07-17 | [6 empty] | DND 7/30/18 Project #19P000059 to replace REF CPMS # 9054 Ron to speak with ITS to complete installation. |  | Ron Veloz | 10/29/18 RV: Last meeting it was discussed that FS does not install Security Camera systems. Ron V spoke with Maggie on 10/26 to inform her that the project will be removed from the FS Minor Ren. List and she will need to contact ITS to request the Security Camers. 08/27/18 RV: Updated notes. Moved to "Que to Start". 09/19/18 RV, Install Security Cameras at points of entry. Install DVR locally in closet at an adjacent room. 08/23/18-RV Met with D.L. and Jason W. and verified F.S. will perform cabling installation and mount cameras. Equipment cost is not included in the SLA. R.V. will communcate informantion to Maggie. 08/22/18 O-RVL: Met with M. Souder to determine security camera needs and approximate location. | YES | 2018-07-30 | FS | FALSE | 2018 | 2019-08-01
19P000029 |  | 19P000029 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | Canceled; duplicate request to be completed with 19P000059 | CHUNG HALL | 205 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-16 | [6 empty] | Canceled; duplicate request to be completed with 19P000059 |  | Ron Veloz | to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | NO | 2018-09-18 | FS | FALSE | 2018 | 2019-08-01
19P000477 |  | 19P000477 | FALSE | BCOE | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT |  | CHUNG HALL | 457 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-01-30 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
18P000346 |  | 18P000346 | FALSE | ATHLETICS | SL5 ATHLETICS INSTALL WALL VOLLEYBALL OFFICES |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-18 | [6 empty] | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. DL, 5/24/18; We will start working on plans in the near future.... DL, 6/16/18; Need to submit plans asap.......DL, 7/11/18; The plans were approved today. This project is scheduled to start on 7/14/18. We will will be complete will all items related to this project on 8/27/18. Note, The door and sidelite are special order items and this item will probalby have a 6-8 week lead time. Steve T is going to order the door soon.. Customer is aware of the delay for the door and is not concerned......DL, 7/25/18; Passed framing and Electrical inspection. We will be finished with the project next week except for the door and window that is ordered but has a 6-8 week lead time. DL, 8/10/18; This Project is Complete except for special order door and window.......DL, 8/22/18; Door and Glass still not on site., Will check in with Steve T on delivery date......Will also schedule final inspection for Certificate of occupancy......9/6/18; The Glass window is installed but we are waiting on the door. this projects is 98% complete.......DL, 9/19/18; The door will be shipped on 9/24/18. We will schedule the door install when the door is on site......DL, 11/7/18; This Project is 100% Complete.... |  | Dan Lerman | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. Will start working on plans.... | YES | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000487 |  | 19P000487 | FALSE | BCOE | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES |  | BOURNS | A219, A211, A241 | COMPLETE | Christopher Lynch | Maggie Souder | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-02-05 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | FS | FALSE | 2019 | 2019-08-01 | FY 19-20
19P000442 |  | 19P000442 | FALSE | BCOE | SL5 WINSTON CHUNG- PATCH/PAINT ROOM 319 |  | CHUNG HALL | 319 | COMPLETE | Christopher Lynch | Maggie Souder | BILL BINGHAM |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-09 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000046 |  | 19P000046 | FALSE | BCOE | SL5 PATCH AND PAINT PLUS REPLACE BLINDS |  | BOURNS | A0131 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000252 |  | 19P000252 | FALSE | ATHLETICS | SL5 ATH DANCE SHOWER DOORS |  | ATH DANCE | 0050K | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-10 | [6 empty] | 5/31/19, DL; This project is 100% Complete……..5/15/19, DL; This work will be 100% complete this Friday…….4/15/19, DL; This project should stat is 2-weeks. We have a signed po# for the shower doors. Walked the needed tile repairs with the contractor today……..3/18/19, DL; Woring on quotes for the repairs. We will scheudle the work to be completed in the next 45- days…… |  | Enrico Baez | 10/3/2018 EB Replace aluminum and glass shower doors. Will need to contract work. Replace all rusty fixtures in showering space, repair/replace tile as needed. ---9/24/18 EB Site visit scheduled with John Jensen for 9/27 | YES | 2019-05-31 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000459 |  | 18P000459 | FALSE | BAS | SL5 BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 |  | THE BARN |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | Dan Lerman |  |  | 6 | FALSE |  |  | 2018-05-31 | [8 empty] | Enrico Baez | 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 6 | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000175 |  | 19P000175 | FALSE | BCOE | SL5 PAINTING |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT CHAVARRIA-VIVAR |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000312 |  | 19P000312 | FALSE | BCOE | SL5 VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP |  | STUDENT SERV | 1227 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000597 |  | 19P000597 | FALSE | BCOE | SL5 PATCH AND PAINT WALLS |  | CHUNG HALL | 355, 356, 351, & 353 | COMPLETE | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-05-03 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-01 | FY 19-20
19P000625 |  | 19P000625 | FALSE | BCOE | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM |  | BOURNS | A0108 | QUEUE TO START | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-15 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
18P000282 |  | 18P000282 | FALSE | BAS | SL5 EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 |  | POLICE BLDG |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | LISA MARTIN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-25 | [6 empty] | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work…..DL, 5/9/18; We need to submit plans……DL, 7/11/18; This still needs to be scheduled......DL, 8/8/18; Enrico Confirmed this project is 100% Complete.... |  | Enrico Baez | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work….. | YES | 2018-08-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000322 |  | 19P000322 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-05 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000250 |  | 19P000250 | FALSE | BCOE | SL5 BOURNS A303-PAINT AND PATCH WALL |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | JUANA GUERRERO |  | Paul Ditty |  | 5 |  | TRUE |  |  | 2018-09-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000558 |  | 19P000558 | FALSE | BCOE | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT |  | BOURNS | A0265 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-04-03 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | FS | FALSE | 2019 | 2019-08-01 | FY 19-20
19P000424 |  | 19P000424 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET |  | CHUNG HALL | 445 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-12-20 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000526 |  | 19P000526 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT |  | CHUNG HALL | 0202 & 0203 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-03-12 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000622 |  | 19P000622 | FALSE | CNAS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK |  | FAWCETT LAB | 204 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-15 | [8 empty] | Ron Veloz | 07/01/19 O-RVL: Pending intake/site visit to confirm SOW. |  |  | FS | FALSE | 2019 | 2019-08-01
19P000565 |  | 19P000565 | FALSE | BCOE | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS |  | BOURNS | A0133 | QUEUE TO START | Christopher Lynch | Maggie Souder | NANCY FORD |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-04-08 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000236 |  | 19P000236 | FALSE | BAS | SL5 EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION |  | ABER INVER | A0100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 10 |  | FALSE |  |  | 2018-09-04 | [6 empty] | JP 04/04/19 2/8/19 This project is complete. JP Estimated completion end of February | 2018-11-01 | Enrico Baez | 11/27/18 EB-Entered scope of work. Transferred work order to John Peraino in FAMIS. Estmate to be provided prior to work start. Aberdeen Inverness Lobby across from RSO. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Pentland Hills 1st floor of I/J, K/L, M/N, O/P • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Pentland Hills Alcove between E&F building. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exterior wall adjacent to B-101 • Remove existing dual fountain. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exercise Room H-101 • Install HS where pluming repairs were made in East wall. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch all walls and Paint as needed. Glen Mor K-206 Fitness Room • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Glen Mor Pool area • Remove existing double water fountains and HS. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. • Repair any brick work as needed Lothian Hallway near Dining Hall cashier stand adjacent to fire extinguisher cabinet • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Sample sheet. https://www.restroomdirect.com/halsey-taylor-drinking-fountains-and-water-coolers.aspx 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Waiting for Lisa L. to schedule site visit. Total number of station and needs not completed. 11/1/18 EB Conducted site visit with Lisa and Bob. AI Replace Hydration Station (HS) in Lobby near RSO Pentland Hills Replace fountains with HS first floor I/J, K/L, M/N, O/P. Also remove fountains and install HS near B-101, Alcove between E&F, H-104. Glen Mor Remove fountain at pool & K-206 fitness room, replace with HS. Lothian Replace existing HS near cashier to Dining Hal | YES | 2019-04-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000588 |  | 19P000588 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - PATCH & PAINT OFFICES |  | BOURNS | A127 Office, A129 Office, A131 Office, A133 Office, A135 Office, A137 Office, A139 Office, and A141 Office | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-04-22 | [6 empty] | 06/28/19 O-ANS: Paint phase complete. |  |  |  |  | 2019-06-28 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000227 |  | 19P000227 | FALSE | BAS | SL5 DINING STORAGE ROOM CONVERSION |  | BANNOCK J | J0100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | DARCI LOMBARD |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 05/16/19 O-ANS: Project complete per John P as of 05/16/19. 04/04/19, JP: This project has been placed on hold per Housing Edwin. 2/8/19: JP storage room slated to be completed simultaneously with break room as water supply connections will be done together with break room. Completion date for both is approximately three weeks. |  | Enrico Baez | 9/12/18 EB-Install Drywall, Patch & Paint, cap water line, install VCT & Cove Base, Verify HVAC operation, replace hydralic door closer, install LED lamps, Security light. Scope sent to Edwin Melgar for approval. | YES | 2019-05-16 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000620 |  | 19P000620 | FALSE | BCOE | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0304 | QUEUE TO START | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 9 |  | TRUE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000308 |  | 19P000308 | FALSE | BAS | SL5 ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK |  | ABER INVER |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | JP 04/04/19 Project Complete DL 10/4/18; Jess currently has this project scheduled for Winter break. |  | Enrico Baez | 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. |  | 2019-04-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000026 |  | 19P000026 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALLS | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000023. Canceled to be completed on 19P000035 | N/A | 2018-09-18 | FS | FALSE | 2018 | 2019-08-01
19P000023 |  | 19P000023 | FALSE | BCOE | SL5 PAINT ACCENT WALL | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-13 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000026. Canceled to be completed on 19P000035 | N/A | 2018-09-18 | FS | FALSE | 2018 | 2019-08-01
18P000438 |  | 18P000438 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING |  | CHUNG HALL | 415 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 10 | FALSE |  |  | 2018-05-14 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000439 |  | 18P000439 | FALSE | BCOE | SL5 CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING |  | CHUNG HALL | 315 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 11 | FALSE |  |  | 2018-05-15 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
3224 | 3224 |  | FALSE | BCOE | Bourns - Door Access Control | Replace outdated failing, and unsupported Identicard card reader system with campus approved Hirsch system at all existing locations in Bourns Hall B-wing at a minimum; inclusion of card readers in Bourns A-wing is also desired if possible. Immediate work is optimal since the building is currently under construction and many walls, ceilings, wiring, etc are currently exposed. Work to be done via surplus funds from BCOE 950534. AVC is putting together the costs and scope via meetings with Maggie/ Pat/ and John C. | BOURNS |  | On Hold | Christopher Lynch | Maggie Souder | Margaret Souder |  | Fernando Nunez | 1 |  |  | FALSE |  |  | 2016-11-14 | FS Direction | [11 empty] | PD&C | FALSE | 2016 | 2019-08-01
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Construction | Christopher Lynch | Maggie Souder | Margaret Souder |  | Dave Bomba | 2 |  |  | FALSE | 700000 |  | 2018-04-04 | Complete Construction | 2019-07-01 | 2019-09-18 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
3300 | 3300 |  | FALSE | BCOE | R'Garden - Solar Installation | Electrician to do the following wiring of our solar panels and inverters out at the R’Garden at UCR. The H model cyboinverter to be used powers the lower heating element of the water heater. The thermostat of the lower heating element must then be set to be higher than the upper heating element. The two output lines are to be connected to an AC switch or switchable AC outlet and the lower element water heater. |  |  | Work to be inspected by A&E. | Christopher Lynch | Maggie Souder | Arvin Tam |  | Scott Donnell | 3 |  |  | FALSE | 0 |  | 2017-05-03 | Relocation | [11 empty] | PD&C | FALSE | 2017 | 2019-08-01
18P000122 |  | 18P000122 | FALSE | CAMPUS | SL5 MS&E HYDRATION STATION - MS&E HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | Reviewing campus standards for these project requests. DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus….3/4/19: Single trade renovation project to be performed by FS but not captured as a minor renovation. | NO | 2018-04-02 | FS | FALSE | 2017 | 2019-08-01
19P000212 |  | 19P000212 | FALSE | CAMPUS | SL5 REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500A | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  | 1/11/19 Canceled per instruction from Ron Rector on 1/11/19; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting (Stephen C) |  | 2018-12-13 | FS | FALSE | 2018 | 2019-08-01
18P000121 |  | 18P000121 | FALSE | CAMPUS | SL5 PHYSICS HYDRATION STATION - PHYSICS HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | 5/1/19, DL; Per Chris, we will not be compelting this project. There is currently a Water dispenser on the drinking fountain. 3/28/19, DL; We will look into installing a bottle filler on this fountain verse a complete change out…..12/6/18, DL; This project is currently on hold…… DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | Reviewing campus standards for these project requests. 3/4/19 DND Removed from FS hold per Ron Rector. DND 7/14: hold per hydration station update for campus….4/2/18; Notes are current….DL, 2/26/18, Still need to review scope….. DL, 1/5/18; Still need to review scope | NO | 2019-05-01 | FS | FALSE | 2017 | 2019-08-01
19P000307 |  | 19P000307 | FALSE | BAS | SL5 LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 5 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… | 2018-10-03 | Enrico Baez | 1/8/19 EB Job Completed by Jess H. 12/22/18 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. | N/A | 2019-01-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000211 |  | 19P000211 | FALSE | CAMPUS | SL5 LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | Reviewing campus standards for these project requests. | LIFE SCIENCE | 2545 | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | FS | FALSE | 2018 | 2019-08-01
19P000215 |  | 19P000215 | FALSE | BAS | SL5 SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 |  | HUB | 346 | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | John Peraino |  | 9 |  | FALSE |  |  | 2018-08-24 | [6 empty] | 12/12/18 DND Project complete; electrical was installed and all kitchen equipment was hooked up as requested. |  | Enrico Baez | 9/13/18 EB emailed Gustavo Plascncia to schedule site visit. 9/18/18 EB. Conducted site visit. Connect water, drain and gas lines to kitchen equioment. Double oven need hardwired electrical. HUB staff will attach al shelving to walls. Day crew to move and deliver equipment. | YES | 2018-12-12 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000188 |  | 19P000188 | FALSE | CAMPUS | SL5 PAINT - HALLWAY DOORS & INSIDE RESTROOMS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500 | CANCELED BY FS |  |  | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-16 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | FS | FALSE | 2018 | 2019-08-01
19P000284 |  | 19P000284 | FALSE | CAMPUS | SL5 GEOLOGY ACCOMMODATION DOCK DOORS |  | GEOLOGY |  | COMPLETE |  |  | DEBORAH TERAO |  | Chris Pillen |  | Canceled | Canceled | FALSE |  |  | 2018-08-07 | [8 empty] | Ron Veloz | 01/10/19 O-RVL: CLOSE OUT-WORK COMPLETED. All work for this project is completed. Email sent to Monty & team on Jan 04, 2019 confirmating all work is completed. 12/14/18 O-RVL: Loading dock Post and Chain fabrication, is in progress, Auto door operators are on Order/Contract in progress, Loading dock signage is in progress by sign shop, information was confirmed by Chris Pillen as of 12/13/18. All other request related to this project have been completed. RV sent updates to Monty on 12/13/18. 11/14/18 RV: Walked Capitol door on 10/31 for pricing. pending quote for auto door operators. 10/30/18 RV: Walke Paradise Door -Automatic Door operator vendor to site. Met with Jason to discuss door access hardware & function of locksets . Pending quote. 10/03/18 RV: Notes from FAMIS: Lock Shop - Chris working with Jason to purchase and install two sets of automatic door openers with plain face plates - to be installed in the back receivin area. | YES | 2019-01-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
3536 | 3536 |  | FALSE | CAP.PROG. | HUB Monument Sign Path of Travel | The proposed project will create an accessible path of travel to the UCR monument sign next to the HUB. The sign experiences heavy pedestrian traffic and is constantly being utilized as background for photo-ops. It is currently not offering equal access to persons with disabilities. The project involves demolition of approximately 175 sq ft of concrete, grading in front of existing sign, and the installation of approximately 300 sq ft of concrete and ramp with required handrails, and lighting. |  |  | New | Jacqueline Norman | Sharyl Murdock | Gerald Caraig |  | Gerald Caraig |  |  |  | FALSE | 30000 |  | 2019-06-19 | New | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
18P000315 |  | 18P000315 | FALSE | BCOE | SL5 BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB |  | BOURNS | B0235 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  | HOLD | TRUE |  |  | 2018-02-16 | [6 empty] | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction to scope, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... Need to walk project with Ron and schedule the work....DL, 5/24/18; Conducted site visit with Ron V. Ron will order material and schedule the work once material is on site.....DL, 6/16/18; Need to verify delivery date for material.......DL. 7/11/18; Plumbing is disconnected. Corey is tentatively scheduled to disconnect the Fume hood. Once the Fume hood is disconnected, we will schedule the removeal of the fume hood and start the framing of the wall. Target complete date is 8/8/18....DL, 7/25/18; Fume hood is disconnected. Need to move Fume hood and start framing target date is delayed to creep scope but should be complete near 8/16/18.....DL, 8/10/18; Carp[enters will install the wall this week. Corey has parts orders. Corey will complete the install when the material arrives.......DL, 8/22/18; This Project is Complete |  | Dan Lerman | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... DND 7/14 Hold per customer on prioritization | YES | 2018-08-23 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
3233 | 3233 |  | FALSE | CAP.PROG. | Mobility HUB Central Campus Linkages | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Gerald Caraig | 1 |  |  | FALSE | 16011000 |  | 2016-12-16 | Leadership Direction | [11 empty] | PD&C | FALSE | 2016 | 2019-08-01
2916 | 2916 |  | FALSE | CAP.PROG. | Solar Greenhouse | Construction of a solar powered greenhouse. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Matt Barth |  | Scott Donnell | 2 |  |  | FALSE | 194000 |  | 2015-08-04 | Complete Construction | 2019-07-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
3234 | 3234 |  | FALSE | CAP.PROG. | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Close-out | Jacqueline Norman | Sharyl Murdock | John White |  | Fernando Nunez | 3 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete Punchlist & Close Out | 2018-11-05 | 2019-03-29 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3120 | 3120 |  | FALSE | CAP.PROG. | Arts Walk Sculpture (Ext Campus Art Project) | Sculpture design concept - hiring a consultant to revise an artist design concept for a proposed outdoor art piece to be placed between the Arts building and the CHASS Interdisciplinary buildings. |  |  | Site visit to review concrete work, slight delays due to finishes. | Jacqueline Norman | Sharyl Murdock | Uma Ramasubramanian |  | Jason Espinoza | 5 |  |  | FALSE | 1096000 |  | 2016-05-26 | Complete Construction | 2019-02-01 | 2019-07-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3119 | 3119 |  | FALSE | CAP.PROG. | Plant Growth Environment Facility | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. |  |  | Clearing of site has been completed; DPR will begin excavation and preparation of building pad | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 6 |  |  | FALSE | 25000000 |  | 2016-05-25 | Completion of building pad | 2019-04-01 | 2020-08-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3293 | 3293 |  | FALSE | CAP.PROG. | USDA Head House - Public Restroom | Provide an accessible public restroom facility in or adjacent to the USDA Head House Building in Ag Ops. Restroom will serve individuals and groups touring the UCR and USDA Citrus Facilities. Three options have been proposed, and need to be considered and evaluated to recommend a feasible solution for USDA. The work would be managed and paid by USDA, including the design, bidding and construction. UCR staff needs to review the proposed plans and specifications per the agreement with USDA, and provide the review, inspection and approvals. The USDA representative is Marylou Polek. | GERMPLASM |  | Pending Lease | Jacqueline Norman | Sharyl Murdock | Mary Lou Polek |  | Scott Donnell | 11 |  |  | FALSE | 0 |  | 2017-05-22 | USDA Scope & Design | [11 empty] | PD&C | FALSE | 2017 | 2019-08-01
3319 | 3319 |  | FALSE | CAP.PROG. | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Design Build competition | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Mihai Gavan | 13 |  |  | FALSE | 3607000 |  | 2017-06-01 | Award Contract | 2019-12-01 | 2021-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3005 | 3005 |  | FALSE | CAP.PROG. | Batchelor Hall Interior Improvements | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | BATCHELOR |  | Completed best value evaluations for the CM at Risk bidding process. | Jacqueline Norman | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 14 |  |  | FALSE | 8837000 |  | 2016-02-02 | CM at Risk Selection | 2019-09-01 | 2021-11-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3393 | 3393 |  | FALSE | CAP.PROG. | South Neighborhood Dist. Study | South Neighborhood District Study per discussions with the Provost/VCPB, July 2017. The South District Planning Study needs to provide guidance for future development in the South District that is inclusive of: **University aspirations to develop the South District to define the campus’ presence along the adjacent freeway (CA-60/215). **Development capacity, optimal building heights and conceptual massing presented both in metrics and a three dimensional format. **Broad parking strategy to meet the needs of the district in alignment with the campus’ overall parking management strategy and alternative transportation solutions. **High level understanding of infrastructure needs (electrical, domestic, fire and storm water, sanitary sewer, building heating and cooling) to meet the needs of the campus’ desired development capacity for district. **Pedestrian and vehicular connectivity. **East and South Campus Drive improvements |  |  | In Close-out | Jacqueline Norman | Sharyl Murdock | Uma Ramasubramanian |  | Fernando Nunez | 15 |  |  | FALSE | 309000 |  | 2017-11-15 | Follow Up on Study Reports | [11 empty] | PD&C | FALSE | 2017 | 2019-08-01
3452 | 3452 |  | FALSE | CAP.PROG. | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 15 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Programming | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3366 | 3366 |  | FALSE | CAP.PROG. | Genomics Ramps | Genomics Accessibility Improvements - The proposed project will create an accessible sidewalk connection from the Genomics Building to the University Lab and University Office Building. Currently, there is no accessible north sidewalk linkage east of the Genomics Building. The project will demolish and replace approximately 300 square feet of asphalt to bring it up to grade. Two ADA ramps will be added to sidewalk extensions of approximately 300 square feet that connect across a driveway. Existing landscaping and irrigation will be removed and replaced. No trees will be impacted by this work. |  |  | In Funding | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Gerald Caraig | 16 |  |  | FALSE | 0 |  | 2017-11-16 | Secure Funding | [11 empty] | PD&C | FALSE | 2017 | 2019-08-01
2970 | 2970 |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan - Phase 2 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 17 |  |  | FALSE | 2842000 |  | 2015-12-02 | Award package 1 & 3 | 2018-09-26 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
3401 | 3401 |  | FALSE | CAP.PROG. | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | Completing project budget and working on project approvals. | Jacqueline Norman | Sharyl Murdock | Mihai Gavan |  | Mihai Gavan | 18 |  |  | FALSE | 1530020 |  | 2017-12-03 | Budget and project approval | 2019-11-01 | 2020-09-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
2952 | 2952 |  | FALSE | CAP.PROG. | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jon Harvey |  | Dave Bomba | 19 |  |  | FALSE | 23547000 |  | 2015-09-11 | Completion of phase one 3/15/20 | 2019-01-02 | 2021-06-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
3395 | 3395 |  | FALSE | CAP.PROG. | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | Third party cost estimator needed. | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 20 |  |  | FALSE | 0 |  | 2017-12-03 | On Hold | [11 empty] | PD&C | FALSE | 2017 | 2019-08-01
3458 | 3458 |  | FALSE | CAP.PROG. | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | PM to update schedule | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 20 |  |  | FALSE | 0 |  | 2018-07-16 | PM to update schedule | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3438 | 3438 |  | FALSE | CAP.PROG. | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | City to determine schedule | Jacqueline Norman | Sharyl Murdock | Dave Bomba |  | Dave Bomba | 21 |  |  | FALSE | 0 |  | 2018-08-22 | City to determine schedule | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3175 | 3175 |  | FALSE | CAP.PROG. | DM16-Chilled Water Coils Multiple Buildings | Replace multiple leaking/degraded cooling coils across campus to prevent complete shutdown of building air handlers during the hot summer months. Buildings include: Student Services, Chemical Sciences, Genomics, Psychology, Entomology and MSE. |  |  | Owner-requested changed orders | Jacqueline Norman | Sharyl Murdock | Melissa Garrety |  | Scott Donnell | 99 |  |  | FALSE | 1294648 |  | 2016-10-11 | Complete Construction | 2019-01-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
18P000209 |  | 18P000209 | FALSE | CHANCELLOR | SL5 VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 |  | STUDENT SERV | 0 | CANCELED BY CLIENT | Kim Wilcox | Karim Zahedi | ANGIE GRAY |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2017-11-30 | [6 empty] | 5/16/19, DL Angie Grey canceled project on 5/15/19 via email….. 5/1/19, DL; Sent Angie an email this morning. Waiting to hear back from Angie to see if project will be canceled or sent to PD&C…..3/28/19, DL; Provided Angie with an estimate and waiting for her response. The esimate was for 65,000. this work will be redirected to PD&C if she wants to proceed…….2/14/19, DL; Ron V. to follow up with Doug from Capitol Door for alternate pricing .1/15/19, DL; Ron V is still working with Angie on verifying a vendor and product…………..12/14/18, DL; Ron V. is currently working to find a more affortable turnstyle system. When a sytem is approved, we will schedule the work…. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope and conduct site visit……DL, 7/11/18; This work will require plans and permits. Will schedule meeting with Scott to verify if the project request will be approved. If this is approved, we will plan the target complete date to be mid October…..The Request is to reverese Emergency Exit Doors and install Prox card access……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..DL, 8/22/18; Confirmed with Scott that we can reverse the door swing. We will work on plans for review process. This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 9/19/18; I mis understood this for a project at Health Services. I have a meeting with Angie this week. This project is to install turn styles for access to the building. I will need to discuss the equipment to be purchased by Angie verify the specs. We will start on the plans in the early Fall……DL, 11/7/18; Conducted site visit with Vendor. Informed Angie the cost of the project will be at $45K for the project. Angie is checking to verify if funds are availabe for the equipment. |  | Ron Veloz | 03/19/19 O-RVL: RV updated notes as a follow up to Alan's meeting minute action items received on 03/07/19. Updating notes, RV spoke with Angie Grey on 03/18/19, Angie and Dan L met with the vendor (03/19) and is expecting pricing. Status to remain on "HOLD" pending quote and department approval. Update input on Access, FAMIS and sent to Alan on 03/19 Notes on FAMIS and Access have been updated. END--- 02/28/19 O-RVL: RV received confirmation from Doug at Capital Door that they are unable to provide a quote at this time due to deign changes with the product. END--- 02/21/19 O-RVL: RV has contacted Capitol Door with a RFQ. Pending follow up by 02/22/19 per Doug @ Capitol. END---02/21/19 O-RVL: RV Updated notes, RVhas contacted Capitol Door with a RFQ. Pending follow up by 02/22/19 per Doug @ Capitol. END--- DL, 5/5/18; FAMIS work order, New ADA operator, power supply for operator and card swipe…. 2/6/18 E. Baez conducted site visit. Power and Data not located near desired installation site. Width of opening is 118" Flooring is combination of brick and vinyl. 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 1 and for faculty hire "NO"---- 5/5/18; FAMIS work order, New ADA operator, power supply for operator and card swipe….2/6/18 EB- conducted site visit. Request for automated access control system. Annotated on FAMIS…. 2/2/18 EB site visit scheduled for 2/5/18 with Angie Gray. THIS REQUEST IS FOR QUOTES. THE SYSTEM REQUIRES AN FAU TO BE PROVIDED IN ORDER TO SUBMIT REQUEST. ACTUAL WORK WILL MOST LIKELY BE CHARGED TO A DIFFERENT FAU. THEREFORE, PLEADO NOT CHARGE FAU WITHOUT APPROVAL. Original request SR # 17S001552/WO # 17W001873 was submitted on 8/12/16 to Facility Services. A recommendation has come from UCPD for an automatic swing door to be installed on the first floor of the Student Services Building. The door would need to include a switch, button, and card reader functionality (SSB already operates on a keycard system). Please provide us with all options and pricing. The door would be similar to the ones installed in the SRC. I have attached a copy of the recommendation that contains a rendition. Please let me know if you have any questions. Thank you. Angie Primary Contact: Angie Gray. angeladi@ucr.edu. (951) 827-2589. Secondary Contact: Sean Cason. SEANC@ucr.edu. (951) 827-4020. 20 year(s) in use. ==CUST FAU# A01401 19900 68 AXSSB | YES | 2019-05-16 | FS | FALSE | 2017 | 2019-08-01
18P000421 |  | 18P000421 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 2120 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-04-30 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000410 |  | 18P000410 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 3148B | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-25 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000028 |  | 19P000028 | FALSE | BCOE | SL5 BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS |  | BOURNS | A0169 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | 5/1/19, DL; This project is 100% Complete…..3/28/19, DL; Monitor mounts were removed, Patch and paint will be completed in the near future……2/28/19, DL; Will schedule the project to be complete the first week in April…… | 2018-11-14 | Ron Veloz | 11/14/18 RV: Moved to Que to Start….10/29/18 RV: Scoping is completed. Carpenters to Remove Ceiling Mounted TV supports from the lobby ceiling. Work may require Carpenters to open the hard ceiling and remove the TV bracket posts if they cannot be unscrewed from the mounting brkt at the deck above. Work ay also require drywall patch back, tape, sand and paint the lobby ceiling. | YES | 2019-05-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | HOLD - FACILITIES SERVICES | Kim Wilcox | Karim Zahedi | ALEXIS RAMBAUD |  |  |  | 0 |  | FALSE |  |  | 2018-12-11 | [7 empty] | 2018-12-20 | Ron Veloz | 07/01/19 O-RVL: HOLD PER SUSAN. 04/15/19 O-RVL: On Hold per Susan Marshburn, Pending follow up Gerry Bomotti as of 04/15. FAMIS & Acess notes are updated. END~ 03/15/19 O-RVL: RV reviewed FAMIS. All notes we located on the "Service Request" screen. RV copied onto the project screen and Access data base. RV will cancel this request on Access and send out an email to Deborah H and team to cancel the request on FAMIS. END--- 03/06/19 O-RVL: RV received email from Monty requesting information the project not in Access or FAMIS. END--- 01/18/19 O-RVL: RV emailed Karim to inform him of the project covered under the SLA. END--- 01/17/19 O-RVL: RV emailed Karim to inform him of the project covered under the SLA. 01/15/19 O-RVL: Met with Monty on 1/15, Monty informed RV the work will be covered under the SLA agreement in support of Business operations. No estimate is required. RV to contact Karim with this information on 01/16/19. 01/14/19: O-RVL: Met with Dan L. onsite to review the project scope. RV & Dan also spoke with Louis about the process. RV will work on the estimate and submit to Karim & Louis by CBD 01/18/19. RV Has informed Dan L. the project is on the "Non Prioritized List". 01/11/19: O-RVL: Emailed Karim and informed him that he will receive an estimate later the following week. 01/07/19: O-RVL: Monty asked Enrico to look into the this project. I (RV) told Monty that I'm already involved and will complete the estimate. Monty agreed and asked RV to follow up with Karim. 12/21/18 O-RVL: Received a response from Bob W., stating "the area is suitable to be an office space understanding understanding that we must conduct a more in-depth review and approval process..." 12/20/18 O-RVL: Emailed Bob Williams with the existing and proposed floor plan asking if it would be suitable to create an office and requested a budget estimate to add a wall with a door. 12/20/18 O-RVL: Ron V. Visited site and spoke with Karim and viewed the proposed location for the new office. 12/18/19 O-RVL: Received email from D. Hughes on 12/18/18 to look into this request for estimate. | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000375 |  | 19P000375 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT HOLES |  | SKYE HALL | 365 | COMPLETE | Kim Wilcox | Karim Zahedi | FELECIA GARRETT |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-07 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000414 |  | 18P000414 | FALSE | CHANCELLOR | SL5 CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL |  | STUDENT SERV | 0 | COMPLETE | Kim Wilcox | Karim Zahedi | DANIELLE GARCIA |  | Paul Ditty |  | 1 | 2 | FALSE |  |  | 2018-04-26 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000487 |  | 18P000487 | FALSE | CHANCELLOR | SL5 SKYE HALL PATCH HOLES AND PAINT |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | Karim Zahedi | SONIA ZAMORA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000420 |  | 19P000420 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT WALL |  | SKYE HALL | 325 | COMPLETE | Kim Wilcox | Karim Zahedi | REYNA ALARCON |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-19 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000122 |  | 19P000122 | FALSE | CHANCELLOR | SL5 REMOVE, PATCH & PAINT AND HANG |  | STUDENT SERV | 2222 | COMPLETE | Kim Wilcox | Karim Zahedi | CHRISTINE SMITH |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000349 |  | 18P000349 | FALSE | BCOE | SL5 PHYSICS INSTALL PARTITION WALL FOR LAB ROOM |  | PHYSICS | 1037 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 5/24/18; Ron V. has detailed scope and he is ordering material. Once material arives, we will schedule the work…. DL, 6/16/18; Materila is ordered, When door/frame arrives, we will prep, paint and start the work…….DL, 7/11/18; This Project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; This is a small partition wall with sound proofing to minimize noise from the compressor that is disruptive to the Helium Ion Microscope…….DL, 4/16/18; We will schedule this work to be complete by the end of the Spring quarter. DL, 5/19/18; Walked project with Ron. FAMIS work order producd and material is being ordered.... | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000294 |  | 18P000294 | FALSE | CHASS | SL5 HMSS REMOVE DOOR, INSTALL WALL |  | HUM & SOC SC | 3610 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2018-02-01 | [8 empty] | Enrico Baez | Canceled per customer on 7/16/18 via email with Enrico. 5/23/18 EB sent email request for site visit DND 7/14 Hold per customer on prioritization | YES | 2018-07-16 | FS | FALSE | 2018 | 2019-08-01
3535 | 3535 |  | FALSE | CHASS | Watkins 1311 Renovation | This request is for a new faculty hire. -Remove north countertop and sink. Install stainless counter and two sinks. -Install eye wash station -Install laminate flooring, remove existing. (Abatement) -Paint space to campus interior standard. -Remove east counter and replace with stainless. -Remove fume hood, discard. -Install new fume hood. |  | 1311 | New | Milagros Pena | Cindy Williams | Paul Richardson |  | Jason Espinoza |  |  |  | FALSE |  |  | 2019-07-10 | New | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
18W001170 |  | 18W001170 | FALSE | CHASS | SL5 ARTS: PAINT CLASSROOMS |  | ARTS | 407 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 27 | FALSE |  |  | 2017-07-25 | [8 empty] | Enrico Baez | DD 10/6: Enrico scoped; requested during break - coordinating with client to complete on a Saturday | YES | 2018-09-24 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
18P000300 |  | 18P000300 | FALSE | CHASS | SL5 ARTS PATCH AND PAINT - DANCE HALLWAYS |  | ARTS |  | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 24 | FALSE |  |  | 2018-02-02 | [6 empty] | centered. |  | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000426 |  | 18P000426 | FALSE | BCOE | SL5 BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER |  | BOURNS | A0375 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; A-375: Bhargav Rallabandi arrives on or about August 1….. DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/1/18.....DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000394 |  | 18P000394 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK |  | BOURNS | A0159A | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 2 | TRUE |  |  | 2018-04-12 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………….1/15/19, DL; Sound Soak is ordered and should arrive within two weeks……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; Need to review and scheudle…….DL, 7/11/18; Still need to review and scheudle…..DL, 8/22/18; This Project is complete but Maggie wants to see if the Faculty are happy with the results. We may install Sound Soak as a final option…… DL 9/6/18; Sent Maggie an email to see if she is satified with the work performed in regards to the sound proofing. I will have an update by the next Excel update….. DL, 9/19/18; The PI is out of town. Maggie will confirm the PI is satisiofd with the work when they return……on 9/18/18…DL, 10/8/18; Customer not satisfied with first round of sound proofing. We will proceed with Sound Soak material….. |  | Enrico Baez | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. EB 6/1 site visit- 3 door between 4 offices require sound proofing. Doors measure 36" x 106". Photos in FAMMIS. O-RVL: Uploaded sound soak panel data on FAMIS and is available on the Project Server File. 10/18/18 O-RVL: Per FS team meeting, we now have a clarified process that sound soak is not included in the SLA due to the fact this is not part of the work we perform at FS. Because we already committed to do further follow up with the sound soak, we will not charge this time but moving forward sound soak will be a recharge service as the team does not have the skillset to do the work and therefore outside the SLA. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000429 |  | 18P000429 | FALSE | BCOE | SL5 INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 |  | BOURNS | B0262 B0256 | COMPLETE | Christopher Lynch | Maggie Souder | KEVIN SCHULTE |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment…..DL, 5/9/18; We are working on plans to submitt to A&E soon....DL, 5/24/18; Plans were submitted on 5/24/18.......DL, 6/12/18; Plans were approved. Cabinets are ordered. Materila is 6-8 Weeks out.....DL, 7/11/18; We have confirmation for delivery of material for mid August. Target Complete date is 9/7/18......DL, 8/10/18; Project has started. We will be complete with in two weeks......DL, 8/22/18; Work is 90% Complete..Project should be complete by 8/31/18........ DL 9/6/1/8; This project is 99% complete. The parts arrived today. I will be sending out an email to schedule the installation time for next week.......DL, 9/19/18; This project is 100% Complete........ |  | Dan Lerman | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment….. | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000364 |  | 19P000364 | FALSE | CHASS | SL5 PATCH AND PAINT |  | CHASS INT S | 3106 | COMPLETE | Milagros Pena | Cindy Williams | FRANCESCA MOREIRA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-30 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2019-03-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000391 |  | 18P000391 | FALSE | BCOE | SL5 PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN |  | CHUNG HALL | 446 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 5/5/18; Conducted scope visit with Paul and Maggie. This project is target date is August 30th. As of now, we have 10 business days to complete the work……. Dean's Office….DL, 6/16/18;Walked project with Jess and Paul. This will be a project will now incluclude flooring is 7- additional offices due to additional trip hazzards identified in 3 of 7 offices during the carpet scope. Maggie will pay four four of the office since they are still in good condition. We are still on schedule with the work.......Dan, 7/11/18; This project is still on schedule. Complete Date is 8/18/18 and scheduled to be complete on 8/31/18.....DL, 8/10/18; The project is on schedule and we will start on Monday.......Ahead of schedule, project will be complete on 8/29/18......DL, 9/6/18; This project is 100% complete. Note, Maggie did request Jess to come back and remove some glue and he has this scheduled..... |  | Dan Lerman |  | YES | 2018-09-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000353 |  | 18P000353 | FALSE | CHASS | SL5 PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT |  | PSYCHOLOGY1 | 1111A | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 26 | FALSE |  |  | 2018-03-20 | [6 empty] | DL; 7/4/18;This project is scoped. We will only paint one out of the two offices. Working on PO# to install frosted glass with Sun Down Window coverings……DL, 7/25/18; PO# is produced and material is ordered. Target date mid August…….DL, 8/22/18; This project is complete.... |  | Paul Ditty |  | N/A | 2018-08-23 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000367 |  | 18P000367 | FALSE | CHASS | SL5 CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE |  | CHASS INT N | 3033 | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 23 | FALSE |  |  | 2018-03-27 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18W016588 |  | 18W016588 | FALSE | CHASS | PATCH AND PAINT FOR FACULTY |  | SPROUL | 4105 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | N/A | TRUE |  |  | 2018-06-19 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000425 |  | 18P000425 | FALSE | BCOE | SL5 BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - |  | BOURNS | A0379 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; Luat Vuong arrives on or about August 15…... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected..…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/15/18........DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000427 |  | 18P000427 | FALSE | BCOE | SL5 BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER |  | BOURNS | A0373 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie email; This is our new Dean’s faculty office. Dean Lynch is already on site getting up to speed one-two days a week. This office is an ASAP...... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected.....DL, 7/11/18; This project is 100% complete...... |  | Paul Ditty | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000469 |  | 18P000469 | FALSE | CHASS | SL5 WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS |  | WATKINS | 1317 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | 2018-07-25 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000267 |  | 18P000267 | FALSE | BCOE | SL5 CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-01-16 | [6 empty] | DL, 5/19/18; High table mounted on West wall to be relocated to South wall by light "Centered". Relocate white board from East Wall to West walll wher high table was removed. Paint and new flooring. Need to schedule work with Paul and Jess. BKM furniture is scheduled 4-6 weeks. DL, 6/16/18; Lower electrical outlets on North wall, repair blinds, paint and new flooring. The space is vacant as of June 16th. I will scheudle the workl.....BKM delivery is currently scheduled for July 23rd.......This project is 100% complete. There were two items added to the scope and they will be complete by 7/20/18..... |  | Enrico Baez | 4/3/2018 Met with Maggie. She is working with BKM. Floor to go down first. BKM furniture on top. Annotated in Famis. | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000445 |  | 18P000445 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 |  | ARTS | 225 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 11 | TRUE |  |  | 2018-05-21 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000278 |  | 19P000278 | FALSE | BCOE | SL5 REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR |  | BOURNS | A0165 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Dan Lerman |  | 1 |  | TRUE |  |  | 2018-08-03 | [6 empty] | DL, 10/4/18; This Project is 100% Complete…….. |  | Ron Veloz | Completed SOW, met withJess and informed of work and color. | YES | 2018-10-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000420 |  | 18P000420 | FALSE | CHASS | SL5 COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | Canceled by Customer on prioritization 7/2/18 | WATKINS | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  |  |  |  | Cancel | TRUE |  |  | 2018-04-27 | [10 empty] | YES | 2018-07-02 | FS | FALSE | 2018 | 2019-08-01
18P000383 |  | 18P000383 | FALSE | CHASS | SL5 HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT |  | HUM & SOC SC | 1302 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  | 4 | TRUE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000418 |  | 18P000418 | FALSE | CHASS | SL5 HMSS OFFICE PAINTING |  | HUM & SOC SC | 2002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 15 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty | 5/23/18 EB- Sent email to Jill requesting site visit. 5/23/ 18 EB- Scoped. Mount & TV on site. TV bottom edge to be mouted 48" from floor centered on West wall. Needs electrcal cut out and data. Entered in FAMIS. | N/A | 2018-07-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000417 |  | 18P000417 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTIONAL OFFICE PAINTING |  | HUM & SOC SC | 2106 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000416 |  | 18P000416 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTOR OFFICE PAINTING |  | HUM & SOC SC | 3002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000415 |  | 18P000415 | FALSE | CHASS | SL5 PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | Door and frame have been painted; construction to commence upon availability of the teams. | OLMSTED | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | RYAN LIPINSKI |  | Dan Lerman |  |  | 10 | TRUE |  |  | 2018-05-08 | [6 empty] | 12/14/18, DL; Angel cancelled this project as it is no longer needed at this time……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 7/11/18; This project was scoped and part of the IRT. Plans and permits are approved. We will schedule the work and we will plan to have this project complet by 9/21/18…..8/10/18; WE have approved plans, this project is scheduled to start late August and will be complete early October……DL, 10/4/18; The door and frame is scheduled for delivery in 3-5 weeks, We will start the project when the doors and frame are on site……..DL, 11/7/18; Door and frame and painted. We will start the contruction in the near future…… |  | Dan Lerman |  | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-01
18P000468 |  | 18P000468 | FALSE | CHASS | SL5 WATKINS 1222/1223 PATCH/PAINT |  | WATKINS | 1222 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 13 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000316 |  | 19P000316 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL |  | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…Anticipated completion 11/9/18. | 2018-10-03 | Ron Veloz |  | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000389 |  | 18P000389 | FALSE | CHASS | SL5 PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A |  | PSYCHOLOGY1 | 2122 | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 5 | TRUE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000387 |  | 18P000387 | FALSE | CHASS | SL5 HMSS PATCH/PAINT |  | HUM & SOC SC | 3600 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 28 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000111 |  | 18P000111 | FALSE | CHASS | SL5 KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 |  | CHASS INT S |  | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Jason Williams |  |  |  | FALSE |  |  | 2017-09-15 | [6 empty] | EB 1/31/18 Work was assigned to lock shop 12/7/17…. DND 5/11: Spoke with Jason, all work complete to be completed as trade is available. Only work remaining is on 3150 A; Jason short staffed to finish project but it's on his radar. 07/13/18 H-FMS: Troubleshoot programming and settings for this controller. Clear all data from panel and reset, perform required downloads, re-test and verify both doors working correctly. |  | Enrico Baez | EB 1/31/18 Work was assigned to lock shop 12/7/17 | YES | 2018-07-13 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000313 |  | 19P000313 | FALSE | CHASS | SL5 HUMANITIIES SOCSCI - PATCH HOLES & PAINT - |  | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000396 |  | 18P000396 | FALSE | CHASS | SL5 WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D |  | WATKINS | 2122 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | 6 | TRUE |  |  | 2018-04-13 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000575 |  | 19P000575 | FALSE | CHASS | SL5 WATKINS HALL PAINT/FLOORING |  | WATKINS | 1309A | QUEUE TO START | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-17 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000205 |  | 19P000205 | FALSE | BCOE | SL5 LABORATORY RENOVATION FOR NEW FACULTY |  | BOURNS | A0328 | COMPLETE | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  | Dan Lerman |  | 4 |  | TRUE |  |  | 2018-08-23 | [6 empty] | 2/28/19, DL; This Project is 100% Complete…….2/1/19, DL; This project is 99.9% Complete………..1/15/19, DL; This project is 90% complete. WE still need to finish snorkels and ceiling tiles. We should be 100% complete by 2/1/19……12/14/18, DL; This project is on schedule..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/4/18; This is a large scale project, we will walk with the trade supervisors next week. We will also work on the plans and schedule the work. Target Date is 1/1/19…..DL, 11/7/18; work is scheduled. We are working on the electrostatic paint contract. We are in plan check review process. There are questions about the fire sprinklers from Scott J. Sent Scott J. an email requesting a site visit to better determine if any work will be required on the sprinkler system….. |  | Ron Veloz | 10/03/18: RV spoke with Dan. He had previously met with Maggie and had scoped this project. | YES | 2019-02-18 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000226 |  | 18P000226 | FALSE | BCOE | SL5 BOURNS FUME HOOD INSTALLATION |  | BOURNS | B0235A | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  | 8 | HOLD | TRUE |  |  | 2017-12-11 | [6 empty] | 2/14/19, DL; This project is Complete…..2/1/19, DL; The Fume hood is complete. The vendor will be back in two weeks to comissison the clean room…..…1/15/9, DL; This project is 95% complete and should be complete on or near 2/1/19…………12/14/18, DL; This Project is 90% Complete. Fume hood is scheduled for install next week. We will finish balance of project after Fume hood is installed…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. WE are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans…..DL, 5/9/18; planning to submit plans on 5/11/18 for plan check review….. DL, 5/24/18; Plans were submitted to Bob W. on 5/24/18……DL, 6/12/18; Project is on Hold until Shane can provide plans/specs for the clean room……DL, 7/11/18; Still no change to the status……DL, 7/25/18, Maggie confirmed this project is on the books. I need to discuss the status with the team because the priority list is on Hold…….DL, 8/22/18; This project is no longer on hold. We will per shane we will submit what we have from the clena room suupplier for review from FM and BO……DL, 9/6/18; WE are almost complete with Plans and will submit the plans next week………DL, 9/19/18; Submitted plans to PD&C on 9/14/18…..DL, 10/4/18; Plans were approved thais week. WE will scheudle the project around the delivery date for the Clean room……..DL, 11/7/18; This is in progress. We will complete the install of the utilities so the clean room can be installed. WE will finish the balance of the project once the Clean room install is complete. The clen room is being install by an outside vendor….. |  | Dan Lerman | 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. We are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans..... DND 7/14 Hold per customer on prioritizatio | YES | 2019-02-14 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000361 |  | 19P000361 | FALSE | CHASS | SL5 OLMSTED-PATCH & PAINT/REPLACE CARPET |  | OLMSTED |  | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 05/29/19 O-ANS: Project completed 05/09/19 per Paul Ditty. |  | Paul Ditty | N/A | N/A | 2019-05-09 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000481 |  | 18P000481 | FALSE | CHASS | SL5 CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 |  | CHASS INT S | 3104 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000606 |  | 19P000606 | FALSE | CHASS | SL5 PAINT ROOM |  | WATKINS | 1213 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 06/14/19 O-ANS: Stephen spoke with customer Becky Campbell via phone who confirmed that project was going to be canceled due to re-allocation of space by another dept. |  |  | Canceled by client 6/14/19 |  | 2019-06-14 | FS | FALSE | 2019 | 2019-08-01
19P000378 |  | 19P000378 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 |  | HUM & SOC SC | 1613 | COMPLETE | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-11-13 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000400 |  | 19P000400 | FALSE | CHASS | SL5 CREATE DOOR INTO HALLWAY | Create a door between the hallway and CHASS INTS 2117A. The door should be placed at the south end of 2117A. | CHASS INT SOUTH | 2117A | CANCELED BY FS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 103 |  | FALSE |  |  | 2018-12-06 | [6 empty] | 05/21/19 O-ANS: Canceled by FS per conversation with Paul Richardson and combined with Project 19P000419. | 2019-04-15 | Enrico Baez | 4/18/19 E. Baez-Emailed Paul, Monty and Chris P. The project is requested in conjunction with Project 19P000419 (keyless entry in various offices within 2117). Both projects will need to be considered one project as work is requested for same area. Waiting for HCI to submit proposal. 4/15/19 E. Baez- Conducted site visit with Paul Richardson. Request is for separate entrance from hall to 2117A. Offered two possibilities and forwarded to Paul. Waiting for response. Will need detailed scope. | YES | 2019-05-21 | FS | FALSE | 2018 | 2019-08-01
19P000306 |  | 19P000306 | FALSE | CHASS | SL5 HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 |  | CHASS INT N | 4017 | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-01 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19W002930 |  | 19W002930 | FALSE | CHASS | HOLD - SL5 PATCH HOLES & PAINT - HUMANITIIES SOCSCI |  | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-08-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000585 |  | 19P000585 | FALSE | CHASS | SL5 HUMANITIES SS, RM 3604- PATCH/PAINT WEST WALL |  | HUM & SOC SC | 3604 | COMPLETE | Milagros Pena | Cindy Williams | DARA CERDA |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-04-19 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000355 |  | 19P000355 | FALSE | CHASS | SL5 HYDRATION STATION FOR THE SECOND FLOOR WATKINS | Hydration station installed where the water fountain is. | WATKINS | 2122D | CANCELED BY FS | Milagros Pena | Cindy Williams | CYNTHIA REDFIELD |  | Dan Lerman |  | 112 |  | FALSE |  |  | 2018-10-22 | [8 empty] | Enrico Baez | 4/24/19 LB: Per Ron Rector, hydration stations in common areas will be scheduled by FS. Project canceled. ~ 10/22/18 SC: Called Cynthia to clarify that this would be a project. Also asked if she wanted the water fountain checked out in the meantime since it seems to be stinking. She will put in a separate WO for this issue. |  | 2019-04-24 | FS | FALSE | 2018 | 2019-08-01
19P000603 |  | 19P000603 | FALSE | CHASS | SL5 CHASS INT N, RM 3046- PATCH AND PAINT - NEW FACULTY OFFICE |  | CHASS INT N | 3046 | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  | 12 |  | TRUE |  |  | 2019-05-10 | [6 empty] | 06/18/19 O-ANS: Project complete per updates. 06/15/19 D-MMN: Painted remaining finish. Pulled masking and plastic. Replaced plates and vacuumed. |  |  |  |  | 2019-06-18 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000195 |  | 19P000195 | FALSE | CHASS | SL5 HUM & SOC SC-ROOM PAINTING |  | HUM & SOC SC | 2003 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000216 |  | 19P000216 | FALSE | CHASS | SL5 HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT |  | HUM & SOC SC | 1214 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-08-27 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000640 |  | 19P000640 | FALSE | CHASS | SL5 NEW FACULTY - PATCH & PAINT SPROUL 3108 |  | SPROUL | 3108 | COMPLETE | Milagros Pena | Cindy Williams | MELISA VICARIO |  | Paul Ditty |  | 13 |  | TRUE |  |  | 2019-05-20 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000643 |  | 19P000643 | FALSE | CHASS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH |  | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2019-05-21 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-01 | FY 19-20
19P000221 |  | 19P000221 | FALSE | CHASS | SL5 PATCH, PAINTING, AND REGULAR CLEANING OF A126A |  | OLMSTED | A0126A | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000196 |  | 19P000196 | FALSE | CHASS | SL5 PAINT OFFICE AT UNIVERSITY THEATER |  | THTR WKSH |  | COMPLETE | Milagros Pena | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000171 |  | 19P000171 | FALSE | CHASS | SL5 HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST |  | HUM & SOC SC | 1614 | COMPLETE | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 16 |  | FALSE |  |  | 2018-08-09 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18W016621 |  | 18W016621 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2018-06-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000201 |  | 19P000201 | FALSE | CHASS | SL5 PATCH AND PAINT THE WALLS |  | CHASS INT S | 3111A | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 18 |  | FALSE |  |  | 2018-08-22 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000129 |  | 19P000129 | FALSE | BCOE | SL5 HANG MONITORS AND BOARDS |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | RICHARD BAIN |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2018-08-06 | [6 empty] | 12/14/18, DL; This Project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Dry errase boards and Monitor mounts are installed. Still need to install monitors, corner guards and monitors….. |  | Ron Veloz | 10/03/18 O-RVL: Install one 32" monitor asouth wall center of table, Install 55" TV at west wall(need power & data), install white bd at east wall 8' from north corner, install chalk bd at east wall 2'-6" from corner at 8" above small table. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000607 |  | 19P000607 | FALSE | CHASS | SL5 PAINT FACULTY OFFICE |  | WATKINS | 1312 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2019-05-10 | [6 empty] | 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-01
19P000362 |  | 19P000362 | FALSE | CHASS | SL5 PATCH & PAINT/REPLACE CARPET (HALLWAY) |  | OLMSTED |  | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000035 |  | 19P000035 | FALSE | BCOE | SL5 WCH--INSTALL NEW LED DISPLAY IN OFFICE |  | CHUNG HALL | 354 | COMPLETE | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This Porject is 100% Complet…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Install scheduled for this Friday. | 2018-10-03 | Ron Veloz | 10/03/18 RV Walked site with Dan L. SOW Install TV Bracket at south wall center of room. Requires Power (no Data)installation of mounting bracket. TV and brk is located in Sarah Galloways office. Scope is completed. Dinh 9/18 19P000023/19P000026 requests for paint to be included in project scope for room. | YES | 2018-11-19 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18W008762 |  | 18W008762 | FALSE | CHASS | SL5 HUMANITIES: PATCH & PAINT |  | HUM & SOC SC | 2415 | COMPLETE | Milagros Pena | Cindy Williams | ANDREW ALONSO |  | Paul Ditty |  | 20 | 22 | FALSE |  |  | 2018-01-02 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000435 |  | 18P000435 | FALSE | CAMPUS | SL5 HMSS HYDRATION STATION REQUEST |  | HUM & SOC SC | 3600 | COMPLETE |  |  | NELDA THOMAS |  | Dan Lerman |  |  | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 4/15/19, DL; This project is 100% Complete…..3/28/19, DL; Fountain is in. working on power and paint….. |  |  | 3/4/19 DND Removed from FS Hold Per Ron Rector | NO | 2019-04-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000296 |  | 19P000296 | FALSE | CAMPUS | SL5 MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB |  | MAT SCI ENGR |  | COMPLETE |  |  | MILLY PAREDEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-09-25 | [6 empty] | 2/28/19, DL; Project is 100% Complete…….2/14/19, DL; This project is 90% Complete and should be complete by the end of the month………….2/1/19, DL; Permits are approved, we will schedule the project in the next 2- weeks and hope to be complete by the end of February….12/14/18, DL; Rendering has been given to Ron R. Ron will present to Gerry for review and approval. Once approved, we will proceed with plans and permits……DL, 11/7/18; Need to find out where this project stands in regards to the priioroity….. Site vist was conducted and scope of work is verified. Plans and permits will be required for the work….. |  | Ron Veloz | 10/19/18 O-RVL: Walked the proposed location with Dr. Barsukov to review needs and location for nitrogen tanks in the hall. DL suggested to construct a wall with double doors approx 2' below the ceiling height. 09/27/18 O-RVL: Walked site with Chris P, Dan L., Deborah Mc Williams & Mayela C to review SOW. | YES | 2019-02-28 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000173 |  | 19P000173 | FALSE | CHASS | SL5 PAINT/PATCH UNIVERSITY THEATER LOBBY |  | THTR WKSH | 0400A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000574 |  | 19P000574 | FALSE | CHASS | SL5 FACULTY OFFICE PAINTING |  | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | QUEUE TO START | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-04-12 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000396 |  | 19P000396 | FALSE | CAP.PROG. | SL5 TRAILER #14 - CAMPUS INITIATED - STRUCTURE |  | T14 |  | COMPLETE | Jacqueline Norman | Sharyl Murdock | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-31 | [6 empty] | 2/28/19, DL; This Project is 100% Complete…..Trailers were demolished. We need to install the utilities. Once the Grow Pod is on site, we will connect the utilities to the structure…… |  | Enrico Baez |  |  | 2019-02-28 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000356 |  | 19P000356 | FALSE | CHASS | SL5 PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT |  | HUM & SOC SC | 4401 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-24 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000063 |  | 19P000063 | FALSE | CHASS | SL5 NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS |  | PSYCHOLOGY1 | 2124 | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-07-31 | [8 empty] | Paul Ditty | 9/13/18 EB this is a request for patch, paint and new carpet | NO | 2018-09-26 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000371 |  | 19P000371 | FALSE | CHASS | SL5 URGENT PATCH AND PAINT IN CHAIR'S OFFICE |  | HUM & SOC SC | 1213 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-11-05 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000609 |  | 19P000609 | FALSE | CHASS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR |  | WATKINS | 1229 | IN PROGRESS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 07/03/19 O-ANS: Paint phase complete and awaiting flooring change. 06/21/19 O-ANS: Customer requested to remove lighting change from project and only complete paint and carpeting via email to Paul Ditty (copied email below). Will create separate work order for lighting. Re-assigned to Paul Ditty to complete. "From: Becky L Campbell <becky.campbell@ucr.edu> Sent: Friday, June 21, 2019 10:51 AM In regards of the work order: 19P000609 - SL5 - PAINT FACULTY OFFICE – please cancel the connecting Work Order 19W015231 – REPLACING THE LIGHTING IN WATKINS 1229. Please do paint and replace flooring.For the lighting, please create new work order to be done at a later time." |  | Paul Ditty | Awaiting installation of new flooring |  |  | FS | FALSE | 2019 | 2019-08-01
19P000011 |  | 19P000011 | FALSE | CHASS | SL5 PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED |  | PSYCHOLOGY1 | 2111A | COMPLETE | Milagros Pena | Cindy Williams | LORENA QUINTANA |  | Paul Ditty |  | 4 |  | TRUE |  |  | 2018-07-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000605 |  | 19P000605 | FALSE | CHASS | SL5 PAINT NEW MAILROOM |  | WATKINS | 1320E | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-01
18P000329 |  | 18P000329 | FALSE | CHANCELLOR | SL5 SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST |  | SKYE HALL | 170 | COMPLETE | Kim Wilcox | Karim Zahedi | DA LAN DINH |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18…..DL, 5/24/18; Plans were approved. Demo work has started......DL, 6/12/18; MArshal and Kate are working on Carpet order......DL, 7/11/18; Carpet is ordered. We have a challenge with Title 24. I am working on the title 24 documents. We are still planning to have this project complete on 8/17/18......DL, 8/10/18; We now have the Title 24 plans. The are being reviewed by Bob and Scott.....Title 24 plans approved. Robert is working on PO#. Most parts are on site and Electricans are working on project. All other Trades to follow once Lights are in...... Hard Date of 9/7/18............9/6/18 As of today, Carpet is scheduled for install tomorrow morning and furniture is scheduled for delivery this Monday......WE will more than likely have electrical punch items and touch up paint but this propject should be 100% complete in regards to FS the end of next week next week......100% PROJECT COMPLETE... GREAT WORK DAN! |  | Dan Lerman | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18….. | YES | 2018-09-18 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000604 |  | 19P000604 | FALSE | CHASS | SL5 HUMANITIES SS, RM 7704- PAINT OFFICE BY JULY 1, 2019 |  | HUM & SOC SC | 7704 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000357 |  | 19P000357 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS, TIME SENSITIVE |  | HUM & SOC SC | 1302 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-10-25 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000419 |  | 18P000419 | FALSE | CHASS | SL5 COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | FS to coordinate with client to scope the work. | WATKINS | 1320C&E | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 5 | 8 | TRUE |  |  | 2018-04-27 | [6 empty] | 2/14/19,DL; This project was canceled by Paul R. 2/1/19, DL; We will custom make Sound panels and will start the installation in the next 6-8 Weeks……….. |  | Enrico Baez | 7/6/18 EB emailed Paul Richardson to schedule site visit 7/17/18 EB Scheduling site visit with Paul R. 8/7/18 EB-Job was part of an IRT. Dan said he will scope 8/20/18 EB emailed Lilia to schedule site visit. 8/24/18 EB scheduled site visit for 8/28/18 at 11:00AM 8/28/18 E.Baez- Met with Paul Richardson, Lilia Vega and Becky Campbell. Instead of tearing down walls and building new ones, they wanted to see if installing sound soak on three walls were possible, it is. They will then need to have their Dean approve the sound soak. Clients were sent an email with drawing indicating desired location of sound soak. | NO | 2019-02-14 | FS | FALSE | 2018 | 2019-08-01
18P000297 |  | 18P000297 | FALSE | CHANCELLOR | SL5 SKYE HALL CHECK LOCATION FOR TV INSTALL |  | SKYE HALL | 390 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Dan Lerman |  | 4 | 3 | FALSE |  |  | 2018-02-02 | [6 empty] | 2/1/19, DL; This Project is 100% Complete………1/18/19, DL; This Project is scheduled to be complete next week.….. DL, 5/24/18; Need to verify scope with Enrico…..DL, 7/11/18; Work orders are produced and need to be issued. Target complete date is 9/3/18…. |  | Enrico Baez | EB-scoped on 1/30. Mount TV above table. Advised an articulated mount be purchased. Drawing on FAMMIS WO. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000314 |  | 19P000314 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000642 |  | 19P000642 | FALSE | CHASS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM |  | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-05-21 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-01 | FY 19-20
18P000444 |  | 18P000444 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 |  | ARTS | 242 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-05-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-09-21 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000314 |  | 18P000314 | FALSE | CHASS | SL5 CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR |  | CA MUS PHOTO | 1000 | COMPLETE | Milagros Pena | Cindy Williams | EMILY PAPAVERO |  | Dan Lerman |  |  | 17 | FALSE |  |  | 2018-02-16 | [6 empty] | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date.......DL, 7/25/18; This project is 100% Complete..... |  | Enrico Baez | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date....... | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000552 |  | 19P000552 | FALSE | CHASS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS |  | HUM & SOC SC | 1001 B, C, and D | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-03-27 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | FS | FALSE | 2019 | 2019-08-01 | FY 19-20
19P000300 |  | 19P000300 | FALSE | CHASS | SL5 HUM & SOC SC--URGENT: PAINT AND PATCH WALLS |  | HUM & SOC SC | 4403 | COMPLETE | Milagros Pena | Cindy Williams | ANDREA HERAZ |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000318 |  | 18P000318 | FALSE | CHASS | SL5 CHASS INT S FLAT SCREEN INSTALLATION |  | CHASS INT S |  | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Dan Lerman |  |  | 20 | FALSE |  |  | 2018-02-21 | [6 empty] | 4/15/19, DL; This is 100% Complete….3/28/19, DL; Monitor is installed. Need to finishe power and data next week……2/28/19, DL; Scheduled to complete the install mid March…..2/1/19, DL; Francesca contacted me and informed me this project is now back on the books. She needs to gather more information and order the monitor. When the monitor arrives, we will schedule the installation…….1/29/19, DL; Francesca confirmed this project is not needed and requested this project to be cencelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; we have the brackets. Will scheule the work after the project is approved…..DL, 7/11/18; Work order are not produced. Need to assign and schedule the work…. Target complete date is 8/3/18……DL; 7/25/18; Need to change target date.. |  | Enrico Baez | 5/24/18 Conducted site visit. Met with Ryan Amriano. Electrical near buy. No data connection needed. Awaiting for dept. approval. They first wanted to know if this was possible. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000286 |  | 19P000286 | FALSE | CHASS | SL5 FACULTY OFFICES: TOUCH UP PAINT |  | HUM & SOC SC | 2005 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-09-17 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000194 |  | 19P000194 | FALSE | CHASS | SL5 PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 |  | HUM & SOC SC | 3304 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000448 |  | 19P000448 | FALSE | CHASS | SL5 ARTS 333- PATCH AND PAINT |  | ARTS | 333 | QUEUE TO START | Milagros Pena | Cindy Williams | SONJA SEKELY-ROWLAND |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-01-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000253 |  | 19P000253 | FALSE | CHASS | SL5 ARTS RENOVATION |  | ARTS | 157 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 16 | FALSE |  |  | 2018-04-17 | [6 empty] | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access……DL, 7/11/18; This project needs to be complete before Fall 2018. Space is vacant and ready go. Need to walk and confirm Schdule with Paul D. Tony's Flooring is ready to go after paint is complete.... Target complete date is 9/21/18......DL, 8/22/18; Walked with PAul, Paul will scheudle the work. Jess still need to cordinate with Tony's Flooring .....DL, 9/19/18; The paint and flooring is complete. The seams need to be welded and this will be complete. this will be complete by 9/21/18......9/19/21; This Project is 100% Complete....... |  | Dan Lerman | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000061 |  | 19P000061 | FALSE | CHASS | SL5 PSYCHOLOGY 1111H-PATCH HOLES IN WALL |  | PSYCHOLOGY1 | 1111H | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000429 |  | 19P000429 | FALSE | CHASS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | Patch & Paint | COLL BLDG SO | 103 | IN PROGRESS | Milagros Pena | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-01-03 | [6 empty] | 06/06/19 O-ANS: Project scheduled to be completed. | [5 empty] | FS | FALSE | 2019 | 2019-08-01
19P000608 |  | 19P000608 | FALSE | CHASS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE |  | WATKINS | 1345 | QUEUE TO START | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-05-10 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000226 |  | 19P000226 | FALSE | CHASS | SL5 PAINT OFFICE HMNSS 3304 |  | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-08-28 | [8 empty] | Paul Ditty | Duplicate request; project to be completed on 19P000194 |  | 2018-10-01 | FS | FALSE | 2018 | 2019-08-01
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On-hold/Funding | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [11 empty] | PD&C | FALSE | 2017 | 2019-08-01
3060 | 3060 |  | FALSE | CHASS | CHASS Intl N. - Paint 3rd Floor | Paint and patch the following CHASS INTN rooms to existing color: 3036 3038 3042 3046 3050 3049 3047 3033 3033B 3025 3021 3019 3015 3013 3011 3002 3008 3012 3014 3016 3018 3020 3022 Hallway outside of 3033 Hallway to main entrance to floor Hallway outside 3005 | CHASS INT N |  | Project on Hold | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2016-05-20 | On Hold | [11 empty] | PD&C | FALSE | 2016 | 2019-08-01
3469 | 3469 |  | FALSE | CHASS | Carillon Repair & Maintenance | Design, fabrication and replacement of bell beams for bells 24, 26, 28, 30 and 32. Design, fabrication and installation of bracing to brace the 5 other bells beams that are cracking, and corrective maintenance on the clappers & head pieces-this would include complete removal, cleaning, reaming, bushing and lubricating before re-installing and clean and lubricate the transmission system as much as possible without complete disassembly to make the instrument easier to play. | BELLTOWER |  | In design | Milagros Pena | Cindy Williams | Reasey Heang |  | Daneca Stevens | 4 |  |  | FALSE | 10000 |  | 2018-08-16 | Secure Funding | 2019-09-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
3441 | 3441 |  | FALSE | CHASS | INTS 1121 Convert Classroom to Dance Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use |  |  | In Funding | Milagros Pena | Cindy Williams | Anna Finn |  | Daneca Stevens | 14 |  |  | FALSE | 0 |  | 2018-06-22 | Design | 2020-01-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
18P000344 |  | 18P000344 | FALSE | CHASS | SL5 CHASS INTS PAINT MULTIPLE ROOMS - FACULTY |  | CHASS INT S | 2117E | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 1 | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 7/11/18; This was transferd in to my quque in the past week. I need to scope this project. I belive this is part of project # 18P000205 and 18P000295. If this is part of the other project. We will try to have the paint completed by 8/17/18…......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/10/18; Work has started. We passed rough electrical and framing inspection. The work should be complete in about three weeks......DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18.......DL, 9/6/18; This Project is 100% Complete....... |  | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000377 |  | 19P000377 | FALSE | CNAS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | Replace the gates on the Schneider House driveway, which secure the property, with the taller iron gates that used to be installed at the Gardens entrance. This will require new fence posts and hinges as well. The taller gates are stored along the side of the garage at Schneider House, and Facilities staff can come see them anytime. Please note this is a safety and security project. | SCHNEIDER |  | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | R2 | 117 | FALSE |  |  | 2018-11-08 | [7 empty] | 2019-04-05 | Ron Veloz | 04/15/19 O-RVL: RV updates, Measured gate with Enrico on 4/5. Contacted Cory on 04/15 to schedule a visit on 04/16 to view and estimate Gates. RV will contact Monty with Estimate 06/12/19 O-RVL: RV received costs from Sheetmetal and Carpentry, pending estimate from Paint-P. Ditty. | YES |  | FS | FALSE | 2018 | 2019-08-01 |  | 1
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION |  | SPIETH HALL | 1363 | Project Intake | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | DAN LERMAN |  | R3 |  | TRUE |  |  | 2019-03-26 | [8 empty] | Ron Veloz |  |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
19P000555 |  | 19P000555 | FALSE | CNAS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK |  | SAT CHIL PL | 0 | Project Intake | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | DAN LERMAN |  | R4 |  | FALSE |  |  | 2019-04-03 | [8 empty] | Ron Veloz |  |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
18P000295 |  | 18P000295 | FALSE | CHASS | SL5 CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL |  | CHASS INT S | 2117J | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-02-01 | [6 empty] | DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18……..DL, 5/24/18; Plans were approved. We need to scheudle the work….DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets.......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date.....DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18...........DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware..... |  | Enrico Baez | 4/25 EB Scoped site. Remove counter and Cage. Drywal closed with electrical. Patch Paint. Cut in two doors in 2117G&H……..DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18…….. | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000398 |  | 18P000398 | FALSE | CHASS | SL5 WATKINS ESTIMATE FOR SEALING OF ADJOINING DOORS |  | WATKINS | 2204 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-04-16 | [6 empty] | DL, 7/11/18; Need to walk project and verify scope and target complete date…..DL, 7/25/18; Verified scope. We need to order a new door and floor covering and need to schedule the abatnent, we will plan to start this project in 3- 4 weeks. Target complete date is late August.....DL, 8/8/18; Jess conducted the visit with the abatment contractor. Still need to verify abatment date. Carpenter shop is aware of the scope and they are ordering material. Note, one of the doors will have a lead time of 4- 6 weeks. .....DL, 8/22/18; Abatment is taking place this week. We will schedule the paint and carpet over the next week. This projcet all items for this project will be complete by 9/21/18. DL, 9/19/18; the Door was stained today and will be installed asap. The cove base is back ordered and will be installed when it is on site..target date is complete early next week...... DL, 10/4/18; This Project is 100% Complete....... |  | Enrico Baez | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. | YES | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION |  | GREENHOUSE #8 | 881 | Project Intake | Kathryn Uhrich | Deborah McWilliams | NANCY FERGUSON |  | DAN LERMAN |  | R5 |  | FALSE |  |  | 2019-01-29 | [8 empty] | Ron Veloz |  |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB |  | SPIETH HALL | 2349 | Project Intake | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | DAN LERMAN |  | R6 |  | FALSE |  |  | 2019-02-20 | [8 empty] | Ron Veloz |  |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
19P000056 |  | 19P000056 | FALSE | CHASS | SL5 HMSS CAPABILITY OF MOUNTING A TV |  | HUM & SOC SC | 1212 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  |  | 18 | FALSE |  |  | 2017-10-03 | [6 empty] | 12/14/18, DL; Monitor is complete. Still need to work on electrical……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope with Enrico and schedule the work…. Work orders are not produced. Need to assign and schedule the work DND 7/30/18: Closed work order #18W004822; created project #19P000056……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | EB 3/26-Project scoped on 10/23/17. Attached 5 photos and made annotations to FAMIS. | YES | 2018-12-14 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
18P000205 |  | 18P000205 | FALSE | CHASS | SL5 CHASS INT S CREATE DOOR |  | CHASS INT S | 2117H | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-11-27 | [6 empty] | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18……DL, 5/24/18; Plans were approved. WE need to schedule the work…..DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18...........DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... .. DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date..........DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18............DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware.....DL, 9/19/18; This Project is 100% Complete...... |  | Enrico Baez | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18…… | YES | 2018-09-21 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL |  | SKYE | 0268 | Project Intake | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | DAN LERMAN |  | R7 |  | FALSE |  |  | 2019-02-27 | [8 empty] | Enrico Baez |  |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
19P000543 |  | 19P000543 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION |  | CHEMICAL SCIENCES | 342 | Project Intake | Kathryn Uhrich | Deborah McWilliams | JEFFERY MATUTE |  | DAN LERMAN |  | R8 |  | FALSE |  |  | 2019-03-21 | [8 empty] | Ron Veloz |  |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
19P000594 |  | 19P000594 | FALSE | CNAS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS |  | ENTOMOLOGY BLDG | 171 | Project Intake | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | DAN LERMAN |  | R9 |  | FALSE |  |  | 2019-04-26 | [8 empty] | Ron Veloz |  |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
18P000201 |  | 18P000201 | FALSE | CHASS | SL5 ARTS REMOVE COUNTERTOP/SHELVES |  | ARTS | 0106A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 3 | TRUE |  |  | 2017-11-21 | [6 empty] | DL, 6/16/18; Ned to walk, scope and submit plans ASAP…..Sent Paul an email requesting information on Status of Faculty hire status……DL, 7/11/18; Paul is on Jury Duty and he said he should return back to work next week. Current Targe complete date is mid September......DL, 7/25/18; Carpentery and Electrical is complete. Patch and paint has started. Target complete date is 8/3/18......DL, 8/8/18; Space is VAcant and ready for paint. The paint department is working on several other projects that require their attention. The paint department will complete the work in the near future......DL, 8/22/18; This Project is 100% Complete....... |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS……DL, 4/29/18; Pasted from wo;remove the existing countertop and shelves that are built into the room. Follow with patch and paint of entire space. | YES | 2018-08-23 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000220 |  | 19P000220 | FALSE | CHASS | SL5 ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT |  | ARTS | 333 | COMPLETE | Milagros Pena | Cindy Williams | SONJA SEKELY-ROWLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 12/14/18, DL; This project is 100% Complete….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/8/18; Screeen is scheduled to be removed this Friday. We will schedule the installation and the patch / Paint repairs once we receive the repaired screen back from the vendor…….DL, 11/7/18; This project should already be complete. However, The vnedor did not deliver the correct screen. The correct screen is currently scheduled for this Friday..... |  | Enrico Baez | 8/27/18 EB-Remove 12' wide screen from finished ceiling. Need electricians to diconnect power, carpenters to remove drywall and lower screen. Repared screen to be re-hung by carpenters and drywall repaired. Electricians to reconnect power. Painters to patch and paint. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK |  | PHYSICS | 1132 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-03-19 | [8 empty] | Ron Veloz | 07/01/19 O-RVL: Pending Intake walk. |  |  | FS | FALSE | 2019 | 2019-08-01
19P000508 |  | 19P000508 | FALSE | CNAS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE |  | BOYCE | 3410 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-02-21 | [8 empty] | Ron Veloz | 07/01/19 O-RVL: Pending intake |  |  | FS | FALSE | 2019 | 2019-08-01
18P000385 |  | 18P000385 | FALSE | CHASS | SL5 HMSS INSTALL TV IN CONFERENCE ROOM |  | HUM & SOC SC | 1001E | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Dan Lerman |  | 19 | 19 | FALSE |  |  | 2018-03-06 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..12/14/18; Monitor is Complete, we still need to install power. The space is vacant…DL, 6/16/18; Pasted notes from FAMIS; University Writing program wants to install a 65 inch TV in the conference room at HMNSS 1001E. 1. Request to install the TV mount/ bracket on the wall; 2. Request to remove the old projector screen but leave two wood blocks on the wall; 3. Request to add a new double power outlet around the TV bracket area. If you have any questions, please contact Shanshan Liao at (shanshan.liao@ucr.edu or X27753)……DL, 7/25/18; Work orders are not produced. Need to assign and schedule the work…..……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | 6/11/18 Install TV above wainscot. Notes in FAMMIS. Need electrical and date cut ins. | YES | 2019-03-18 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | [6 empty] | 6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Ron Veloz | 04/15/19 O-RVL: Previously informed Dan L & Jason W of the approved Estimate and it was in que ready to go. RV followed up with email to Dan L & Jason W. on 04/15/19 to confirm. FAMIS & Access notes were updated. END~ 04/05/19 O-RVL: Changed Priority on FAMIS from SL9-Estimate back to SL5-Project and change assignment from O-RVL to J-DLN (Dan Lerman. Linda changed project title on Access from Room 2221 to 4231. END~ 04/04/19 O-RVL: Estimate is complete and accepted by the customer. The requester has accepted the revised estimate #2 to install one access card reader at room #4231. RV has updated FAMIS Access notes. RV informed Dan L. at team meeting that estimate is complete and will move the project from Customer Hold to Que to start. END~ 03/27/19 O-RVL: Pending Customer review, Received acceptance of the estimate from Aimee G. and modified the Rev.2 estimate and returned to her as requested. Pending final approval. END~ 03/19/19 O-RVL: RV spoke with Aimee, Department will proceed with one card reader and expecting a FAU within a week or two. RV will keep project on Hold. ACCESS & FAMIS Notes updated. END--- 03/13/19 Sent Aimee a revised estimate for one door as requested - for room # 4231. Pending response. END--- 03/08/19 O-RVL: Placed on Customer Hold. Contacted Chris Rogers at HCI (Access Control Vendor) Chris will send the revised proposal on 03/11/19. END--- 03/07/19 O-RVL: Received an email from Aimee Gonzales. Revised request to " provide us with an updated quote to install the FOB reader to Genomics 4231 only instead of all three rooms". END--- 02/22/19 O-RVL: Followed up with a phone call to Aimee to confirm receipt of the estimate. Aimee will respond within 30 days with the department's decision. END--- 02/21/19 O-RVL: RV received request for status of estimate from Aimee G. RV replied to send Estimate by CBD today. Estimate sent. Changed priority from SL5 to project to SL9-Estimate. END---02/15/19 O-RVL: RV-preparing estimate to deliver to the customer on the week of 02/17/19. END--- 01/31/19 O-RVL: Pending proposal revisions with equipment itemized with make and model no. from the Access control vendor. Revised proposal due soon per vendor. END--- 01/15/19 O-RVL: Forwarded access controls quote and SOW to Jason and Chris Rodriguez to review and qualify the HCI quote. Pending response. --- 01/10/19 O-RVL: RV received quote and will send a formal Estimate to Aimee by EBD Fri. 01/18 and ask if they would like to proceed. 12/14/18 O-RVL: REQUEST FOR ESTIMATE ONLY. Send Estimated costs to Aimee Gonzales for review and approval. Pending access controls and auto door operator quotes. Moved to Queue to start. ---11/08/18 O-RVL: Scope is complete. Assisting the lock shop with pricing to provide the requestor an estimate prior to start of construction. Walked a 2nd vendor, pending quote for access control card reader. ---11/05 RV called vendor for quote, no reply. ---10/29/18 RV: Conducted jobwalk with vendor last week. Pending quote from Vendor. Will follow up. --- 08/23/18 O-RVL: Ron V. input update from the requestor per M. Anderson (email 08/23), "We would like to review the estimated costs and timeline prior to the FOB system being installed, and from there we will determine if we would like to proceed with the installation." ---Please provide the total cost estimate to Aimee Gonzales before initiating any work(R.V). Contact: Aimee Gonzales 951-827-6254. | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000283 |  | 19P000283 | FALSE | CNAS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 20 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 7/1/19, DL; Barricades are complete. Signage needs to be installed. Signage to be installed in the next 3- weeks………….6/17/19, DL; Yello Caution tape is installed. Still need to install barricades and signage. Target complete date in mid to late July…...5/31/19, DL; The contractor has the PO#. We will start the work and complete the work in the next 30- days……5/15/19, DL; We are waiting on the quote, once we have the quote, we will proceed with the work……4/15/19, DL; We are trying to locate a roofing contractor that will complete the installation. This is a specialty product that requires a professional installation…….3/28/19, DL; We will install the yellow caution tape on the roof which is our most viable option. I will schedule a site visist / job walk with a contractor in the near future…… | 2018-09-19 | Ron Veloz | 10/17/18 RV: All construction information is on the server folder. Pending Saftey MOP's from Beiwei. Left message with her on Monday 10/15 for status. ---10/03/18 RV: SOW, Install safety guard railing and apply yellow markings (leading edge 6'from perimeter) on the Winston Chung Roof. --- 09/19/18-Scope is complete, received safety requirements prepared by EH&S/Beiwei. RV to upload onto FAMIS. | YES |  | FS | FALSE | 2018 | 2019-08-01
3228 | 3228 |  | FALSE | CNAS | Retrofit Screenhouse to Greenhouse | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. Location can be discussed with Greg Greer | RUBIDOUX SCR |  | In Design - Augmentation required | Kathryn Uhrich | Deborah McWilliams | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 1080000 |  | 2016-12-06 | Bidding | 2019-11-01 | 2020-03-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3218 | 3218 |  | FALSE | CNAS | Ag Ops - Demo Structures | Demolition of 15 structures, including hazardous materials cleanup, electrical reconnection of services as needed, UST removal as needed, relocation of ATT riser. |  |  | In construction Additional funding is not expected. | Kathryn Uhrich | Deborah McWilliams | Deborah McWilliams |  | Scott Donnell | 99 |  |  | FALSE | 316739 |  | 2016-10-19 | Complete Construction | 2015-11-01 | 2019-07-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3367 | 3367 |  | FALSE | CNAS | Field 16 Greenhouse Demo & Replacement | Replace GH1 and GH2 with a greenhouse from the Greenhouse Megastore. Conduct geotechnical investigation, prepare drawings and conduct asbestos and lead sampling. |  |  | In Construction | Kathryn Uhrich | Deborah McWilliams | Sue Lee, D. McWilliams |  | Dave Bomba | 2 |  |  | FALSE | 359000 |  | 2017-09-15 | Complete Construction | 2019-01-30 | 2019-07-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
2353 | 2353 |  | FALSE | CNAS | Natural Reserves-Sweeney Granite Mountain | This project will add structurally independent facilities for an administration building and researcher housing to provide meeting/office space and short term sleeping quarters. Additionally, the existing laboratory building and staff residence will be extensively renovated. High priority is focused on high insulation values, high wind resistance, rodent proofing, and pursue as much passive cooling and heating as possible with an eye toward low maintenance and high durability. Both new construction and renovation projects are to be sealed to prevent rodent intrusion. The new structures must withstand the harsh environment of extreme temperatures and very high winds. All site improvements shall be done with minimal disturbance to the desert environment. The overarching goal of the project is to provide a sustainable structure that respects its environment and is low maintenance while using best practice design standards. |  |  | In construction | Kathryn Uhrich | Deborah McWilliams | Jim Andre, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2545500 |  | 2015-11-23 | Complete Construction | 2019-01-14 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | FS to coordinate with client to scope the work. | DELFINO HHSE |  | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | [6 empty] | 5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000523 |  | 19P000523 | FALSE | CNAS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | Placed on HOLD by customer until next Quarter (Fall 2019) | SPIETH | 3366 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-03-12 | [9 empty] | 06/27/19 O-ANS: Paul Ditty met with customer to discuss scope and customer requested to place on HOLD until future semester since they were not prepared to move furniture in preparation for renovation. |  |  | FS | FALSE | 2019 | 2019-08-01
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | Funding/Project Approval | Kathryn Uhrich | Deborah McWilliams | Tracey Kahn, D. McWilliams |  | Scott Donnell | 3 |  |  | FALSE | 340000 |  | 2018-01-08 | Bidding | 2019-11-01 | 2020-01-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
1990b | 1990b |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon-Road | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | Finalized construction drawings are being reviewed | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE |  |  | 2018-06-22 | Finalize Design | 2019-10-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
18P000388 |  | 18P000388 | FALSE | CNAS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 2018-04-10 | [6 empty] | 7/15/19, DL, Work is in progress. Goal is to be complete with our scope near the first week in August……6/17/19, DL; This will be scheduled in July…….5/31/19, DL; Demo and removal of the dishwasher is. We will work on the installation and elctrical / power connections over the next three weeks. Note. Steam shut down is taking priority and the installation may be delayed….. 5/15/19, DL; We will schedule the work……..DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but there is no hard date as this is vacant space and we will access the space as time permits…… DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter….DL, DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans….7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved….. |  | Enrico Baez | 6/21/18 EB Remove old glass washer and install washer 400XLS. Disconnect steam, air, water, electrical, vent hood. Install new washer, electrical, step up x-former 208v to 480. Dept. to purchase x-former $5000 ill to dept. Elect. To provide specs. | YES |  | FS | FALSE | 2018 | 2019-08-01
18P000486 |  | 18P000486 | FALSE | CNAS | SL5 PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 2018-06-28 | [6 empty] | 6/17/19, DL; This project is making good progreess and will be complete near mid- July…..5/31/19, DL; This project is making good progress and we are hopeful to be complete on or before July 1st……5/1/19, DL: This project is in grogress and moving forward. Target complete date is 6- weeks… 4/15/19, DL; Started Demolition phase….2/28/19, DL; We will work on the plans in the next 30-days.12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman | Dan L. scoped this project as part of an IRT…. 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. If possible paint to match existing green accent wall, if not white is fine. Mount monitor bracket to wall centered side to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000390 |  | 19P000390 | FALSE | CNAS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 0 |  | TRUE |  |  | 2018-11-29 | [6 empty] | 7/1/19, DL; This project is 100% Complete…………6/17/19, DL; material is ordered. This project should be complete by July 1st…..5/31/19, DL; Plans were apprvied this week we will work on the contract and hopefully have the notice to proceed in the next two weeks. It is our goal to have the work complete on or before July 1st……5/15/19, DL; Need to order the special order door and frame…. | 2019-02-07 | Ron Veloz | 02/12/19 O-RVL: Scoping is complete. Revised door layout and emailed April photos of the proposed storefront door system received from D.L. on 2/11. April Meinzer approved storefornt door system on 2/12. RV reveised floor plan utilizing the existing cased opening as discussed with D.L. on 02/11. RV provided D.L. a copy of the revised Intake Formw/ layout. Form w/ layout. Unable to update project notes on FAMIS -Project is not available. END--- 02/07/19 O-RVL: Monty asked RV to follow up on this request. Ron V scheduled meeting with April Meinzer on 2/7 at 1:30pm to review intake information for the proposed project at room 5494. FAMIS Updated END--- | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-08-01 | FY 19-20
18P000434 |  | 18P000434 | FALSE | CNAS | SL5 BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY |  | BOYCE | 4478 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Paul Ditty |  |  | 3 | TRUE |  |  | 2018-05-09 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000247 |  | 18P000247 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 |  | PHYSICS | 3023 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  |  | 15 | FALSE |  |  | 2017-12-20 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000287 |  | 19P000287 | FALSE | CNAS | SL5 URGENT: PAINT SHOP TO PATCH AND PAINT |  | MAT SCI ENGR | 229 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | HONG XU |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-19 | [8 empty] | Paul Ditty |  |  | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000292 |  | 18P000292 | FALSE | CNAS | SL5 SKYE HALL PAINT MULTIPLE FACULTY OFFICES |  | SKYE HALL | 228 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul D. will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000293 |  | 18P000293 | FALSE | CNAS | SL5 SKYE HALL COPIER ROOM PATCH AND PAINT |  | SKYE HALL | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 32 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000288 |  | 18P000288 | FALSE | CNAS | SL5 SKYE HALL OFFICE SUITE PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18W011692 |  | 18W011692 | FALSE | CNAS | SL5 ENTOMOLOGY; PAINT/PATCH LAB |  | ENTOM MUSEUM | 211 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-03-08 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000356 |  | 18P000356 | FALSE | CNAS | SL5 ENTOMOLOGY PATCH AND PATCH |  | ENTOMOLOGY | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 10 | TRUE |  |  | 2018-03-20 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18W011672 |  | 18W011672 | FALSE | CNAS | SL5 ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY |  | ENTOMOLOGY | 268 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-03-08 | [6 empty] | Relocate white board from East wall onto the West wall, where high table was removed, 24" away from North end of wall. |  | Paul Ditty |  | N/A | 2018-07-25 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000185 |  | 19P000185 | FALSE | CNAS | SL5 NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE |  | PIERCE | 206 (originially identified as Room 204) | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 6 | TRUE |  |  | 2018-06-18 | [6 empty] | 12/14/18, DL; This project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Pending glove box relocation to rm 319 and minor vent reconfiguration. Both tasks will be performed afet the glove boxes relocate to rm. 319. 10/29/18 All project related work is completed. |  | Ron Veloz | 07/05/18 RonV. Input: I observed multiple WO's for this project and spoke with Zee for clarification. I will investogate the site on 07/06 to determine the actual SOW. 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/22/18 O-RVL: Revised WO to Project no. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". =10/03/18: RV, Work in progress. Plumber are working on new gas lines. Will coordinate glove box move after work in rm 319 is completed. 10/29/18 RV: All glove boxes, Solvent mixing equipment and Chemical cabinet are removed. Remaining work is to replace the existing PVC vent with stainless duct when materials arrive per Cory. Update from Matt L-Plumbing department is working on the gas lines and will continue work this week. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000058 |  | 19P000058 | FALSE | CNAS | SL5 Assess Feasiblity of Removing/Replacing Growth Chambers |  | GH HH | 18 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-28 | [6 empty] | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing...DL, 5/9/18; Project is scoped. Need to schedule the work.....Plumbers and HVAC are working on this. Still need to have electrical removed. I am working wiht Patty on who can do the demo and removal.....DL, 7/11/18; I need to check in with Ken to see if refrigerant is recovered. will isue work order to disconnect electrical..... I checked in with our campus surplus and do not have any contacts to dis,matel the very large growth Chambers. I need to inform Patty and suggest that she have Burges demo and move the Growth Chambers......We will be complete with our portion of this project before 8/1/18.......DL, 8/10/18; All work is done except the disconnect for electrical. I need to check and see if the electrical. Per FAMIS complete on 8/22/18 |  |  | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000392 |  | 18P000392 | FALSE | CNAS | SL5 BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 |  | BATCHELOR | 0 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  |  | 8 | TRUE |  |  | 2018-04-12 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000186 |  | 19P000186 | FALSE | CNAS | SL5 NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION |  | PIERCE | 319 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-06-18 | [6 empty] | Pending gas line installation scheduled for the week of 09/24 per Steve Burleson. Move glove boxes from 206 to Rm 319 after gas line are installed. All work is complete |  | Ron Veloz | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". 10/03/18 RV: Work in progress, Plumbers are installing gas lines. Glove boxes from 206 can be moved after gas lines are installed. 10/08/148 RV: Plumbers to complete the installation of new gas lines in 319. Glove boxes to be brought to rm 319 after gas lines are installed. 10/17/18 RV: Update, Gas lines are installe approx 90% complete per Plumbing Tech, misc parts on order. 10/29/18 RV: All project related work is completeand confirmed with trades and PI. | YES | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000287 |  | 18P000287 | FALSE | CNAS | SL5 SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 33 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19/18; This project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000256 |  | 18P000256 | FALSE | CNAS | SL5 BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES |  | BOYCE | 3451 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave at Webber is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place.......DL, 5/9/18; Autoclave is destroyed. Pictures were sent to Cheryl. We are now waiting for the equipment to arrive. Steve B is working on Steam connection at Boyce......DL, 5/24/18; Autoclaves arrived. Day crew is scheduled to deliver the unit on 5/30/18. we will schule the plumbers and electricians shortly there after......DL, 6/16/18; Webber Autoclave is almost complete. This portion should be complete next week. WE will run the Webbber autoclave for two weeks before we start the Boyce Autoclave. The weldolet for the BOyce unit will be installed during the steam shutdown...... DL, 7/11/18; Webber Auto clave will be complete on 7/12/18. We will start the demo of the Boyce Auto clave next soon. Target date for this project is 8/10/18...... DL, 7/25/18; We had a delay with the Webber autoclave which will implact the Boyce Auto clave. New target complete date is 8/22/18.....DL, Plumbing is almost complete, need to schedule final elctrical and Commission equipment. Target date 8/31/18...... DL, 9/6/18; This project should be complete but we still need to schedule the electrical connections ASAP.........DL, 9/19/18; This project is 100% Complete. |  | Dan Lerman | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place | YES | 2018-09-21 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
18P000296 |  | 18P000296 | FALSE | CNAS | SL5 SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES |  | SKYE HALL | 266 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 31 | FALSE |  |  | 2018-02-02 | [6 empty] | 01/17/19, DL; This project was completed last summer……..DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19 18; I neeed to check on this work order. I thought it was part of the 2nd floor Hallway project but it was not…… |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2019-01-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000227 |  | 18P000227 | FALSE | CNAS | SL5 BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL |  | BATCHELOR | 4128 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-12-12 | [6 empty] | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM.......DL, 5/24/18; Need to work on plans and permits. Project needs to be complete before Fall academic 2018.....DL, 6/16/18; Walked project with Jess. and he will schedule the abatment. We will not need plans for this project. We are not removing the exhasut hood which was the original purpose foor the plans......Carpenters started the demo. Still need to remove TSI. Once TSI is removed, we can schedule the plumbing work. Target Complete Date is 9/21/18....DL, 8/10/18; Abatement is scheduled for this weekend, we will start work soon.....DL, 8/22/18; Abatement and most demo complete. Still on track for 9/21/18.....DL, 9/19/18; Scope change. This project should be complete on 9/28/18.......DL, 10/4/18; Floor to be installed this Friday. Pianters will finalized the stain on the cabinets. Thsi project should be complete near 10/19/18.......Dl, 11/7/18; This project is 100% complete.... |  | Dan Lerman | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM....... | YES | 2018-11-08 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
18P000341 |  | 18P000341 | FALSE | CNAS | SL5 PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL |  | PHYSICS | 1132 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-14 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process…DL, 6/16/18; Jess tested the matreial flooring and paint is hot. Jess will abate before we proceed with the project….Still need to scheudle the work. This project target complete date is late Fall……DL, 7/25/18; Jess sent out the 14-day notification to the AQMD last week. We will start the balance of the project after the ACM and Lead is abated or encapsulated…..8/10/18; Abatement is complete. We will work on the other items as time permits. This space is vacant with no occupancy date |  | Dan Lerman | DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process… | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000346 |  | 19P000346 | FALSE | CNAS | SL5 I&Q--PAINTING ROOMS IN THE I&Q |  | EAST I&Q FAC |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | IMAD BAYOUN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2019-01-09 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18W011161 |  | 18W011161 | FALSE | CNAS | SL5 REPLACE CARPET |  | SCIENCE LAB1 | 301 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-23 | [6 empty] | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project……DL, 5/21/18; Floor covering is selected. Work will be scheudled for Mid June….DL, 5/24/18; The install is scheduled for June 18th & 19th……DL, 7/11/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project…… | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000118 |  | 18P000118 | FALSE | CNAS | SL5 OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT |  | OLMSTED | 1337 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2017-09-20 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space.......DL, 6/16/18. New staff member schedule to start mid july. BKM is also scheduled for mid july. This project will require cabinets to be removed, new carpet, paint and blank out electrical outlets that will no longer be used.. new signage too.....DL, 7/11/18;This project is in progress. Complete date is 7/20/18......DL, 7/25/18; This project is 100% Complete....... |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space. | YES | 2018-07-25 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000505 |  | 19P000505 | FALSE | CNAS | SL5 CHAPMAN HALL PAINT OFFICE WALL WHERE BOOK CASE WAS REMOVED |  | CHAPMAN | 10B | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-02-25 | [6 empty] | 05/10/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-05-10 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
18W000455 |  | 18W000455 | FALSE | CNAS | SL5 CHAPMAN CLEAN WINDOWS |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  | 37 | FALSE |  |  | 2017-07-11 | [6 empty] | Dl, 7/4/18; All Windows in Chapman were cleaned by Ductch Touch. This Project is 100% Complete |  | Ron Veloz |  | YES | 2018-07-11 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
18P000310 |  | 18P000310 | FALSE | CNAS | SL5 ADD INTERCOM/BUZZ IN SYSTEM |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-12 | [6 empty] | Dl, 7/4/18; This project is scoped. This will be a new ADA operator, door bell / Intercom and buzzer button to unlock door. Walked work with Contractor, need to work on producing contract with PD&C. Once Contract is confirmed, we will schedule the work..... DL, 7/11/18; We have the proposal. Need to execute the agreement and schedule the work. The target complete date is before 10/1/18.....Dl 8/10/18; Jason will try and complete the work with in the next three weeks......DL, 8/22/18; Jason order parts, parts have 6-8 week lead time. Work will be scheduled when material arrives.....DL, 10/4/18; This Project is 100% Complete....... |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000027 |  | 18P000027 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT LAB |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-05 | [6 empty] | 2/1/19, DL; This project is 100% Complete……………DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again…… DL, 4/2/18; This space is still on schedule for 7/1/18 completion date…..FAMIS work orders have been produced…..DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th….. |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again...... DL, 4/2/18; This space is still on schedule for 7/1/18 completion date.....FAMIS work orders have been produced..... | YES | 2018-07-12 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000028 |  | 18P000028 | FALSE | CNAS | SL5 CHAPMAN PATCH AND PAINT |  | CHAPMAN | 0010A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced .......DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced ...... | YES | 2018-07-12 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000449 |  | 19P000449 | FALSE | CNAS | SL5 PAINT OFFICE AREA OF 229A FOR RELOCATION |  | FAWCETT LAB | 229A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-01-14 | [6 empty] | 04/05/19 O-ANS: Project complete per Paul Ditty and closed in FAMIS. |  |  |  |  | 2019-04-05 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
18P000473 |  | 18P000473 | FALSE | CNAS | SL5 PIERCE NEW CARPET & PAINT FACULTY OFFICE |  | PIERCE | 202 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 1 | 5 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | 2018-09-26 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000117 |  | 18P000117 | FALSE | CNAS | SL5 PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION |  | WEBBER | 1303 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-21 | [6 empty] | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work....DL, 5/9/18; Produced work order for JEss to test for lead paint and ACM....Von wall is hot, everything else is good to go. I will schedule the work soon. The space is vacant......DL, 7/11/18; This project is in progress. Target Complete Date is 8/10/18....DL, 7/25/18; Vinyl plank and bullitin boards the balance of the task for this project. Still on target for complete on 8/10/18.....DL; 8/10/18; We were schedule to install the fllor and identified Asbestos,. Jess is working on the propsal and schedule for the abatment. This will require a 14- dat notification to the AQMD. This space is vacant with no scheduled move in date......DL, 8/22/18; Abatment is scheduled for this Tursday and Friday. We will scheule the carpet in dry errase boards for next week.Target complete date will be 8/31/18.....DL, 9/6/18; This project is 100% Complete...... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work.... | YES | 2018-09-10 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000299 |  | 19P000299 | FALSE | CNAS | SL5 SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 |  | SPIETH | 3378 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000347 |  | 19P000347 | FALSE | CNAS | SL5 SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT |  | SPIETH | 3320 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-10-16 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000244 |  | 19P000244 | FALSE | CNAS | SL5 PATCH & PAINT GEOLOGY |  | GEOLOGY | 2258A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2018-09-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000367 |  | 19P000367 | FALSE | CNAS | SL5 SCILAB 1 0211- PATCH & PAINT |  | SCIENCE LAB1 | 211 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-31 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000030 |  | 18P000030 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT FROM WATER DAMAGE |  | CHAPMAN | 100 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced....... | YES | 2018-11-08 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000137 |  | 19P000137 | FALSE | CNAS | SL5 LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM |  | LIFE SCIENCE | 2545 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000029 |  | 18P000029 | FALSE | CNAS | SL5 CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS |  | CHAPMAN | 1 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain......DL, 5/24/18; This work is scheduled to be complete on or before 7/1/18.....DL, 6/16/18; Blinds are delayed to mid July but window clenaning is still on schedule......DL, 7/11/18; This Project is 100% Complete |  | Dan Lerman | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain...... | YES | 2018-07-11 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000440 |  | 19P000440 | FALSE | CNAS | SL5 GH#21--INSTALLATION OF GROW POD BEHIND GREENHOUSE #21 |  | GH21 |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER | PATRICIA SPRINGER | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-08 | [6 empty] | 5/31/19, DL; This project is 100% complete :)……5/15/19, DL; Project is complete except for chain link fence. Fence will be installed some time early next week…….5/1/19, DL; Grow Pod is installed with power and water. Still need to install fence and door lock….. 4/15/19, DL; Grow Pod is scheduled for delivery this Thursay. Once on site, we will connect all utilities and this project will be complete. 2/28/19, DL; Demo is complete. We need to veify utilitiy point of connections. Once utilities are verified, we will install the water and power……. |  | Dan Lerman |  |  | 2019-05-31 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000298 |  | 19P000298 | FALSE | CNAS | SL5 SPIETH - PREP LAB FOR FACULTY SEARCH |  | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 5/15/19, DL; This Project is 100% Complete… 5/1/19, Dl; This project will be complete next week…..4/15/19, DL; We are making good progress on this project and we should be complete the first week in May……..3/28/19, DL; This project is in progress and should be complete by or near May 1st….2/14/19, DL; Need to schedule trades and obtain quotes to refinish countertops…… |  | Ron Veloz | 04/22/19 O-RVL: Update- RV reviewed incoming work request 19P000546 and spoke with Dan L on 04/19 regarding Spieth Hall 19P000546 to add 1)Fabrication of a stainless steel hood like the one in Spieth Hall 2218 (picture attached), to fit the space in Spieth 1363 on east corner wall where walk-in chamber was removed. 2)Hook up of the new hood into the current fume hood vent and spanning ~75% of the distance between the working fume hood and the wall. 3)Removal of the shelving above the lab bench (may need some minor abatement). 4)Installation of 3 tombstone electrical outlets on the lab bench to match the other bench. RV spoke with Dan L. Dan, some of the added work is in progress and the remainder of work will be included on projet # 19P000298. Sheet metal hood will be completed on a SL6 sheet metal per DL. END~ 01/15/19 O-RVL: RV to scope once priority is established. RV updated notes with information provided from Deborah Mc Williams. Spieth 1363 – Wet Lab Space Note by D McWilliams.: "There is evidence in the ceiling and along one wall of a water intrusion issue, i.e. peeling paint, leaking and rusted pipes, etc. The cause of this damage needs to be investigated and repairs confirmed, including painting the wall and ceiling where damage is visible". Patch/paint Re-finish, re-surface – existing cabinets Re-finish and/or replace bench-tops If both sinks cannot be significantly cleaned, they should be replaced, replace faucets at both sink locations. Clean existing Chemical fume hood Repair or replace self-closing chemical / flammables storage cabinet On one bench remove overhead shelving unit and relocate electrical outlets to the ends of bench to accommodate large desktop equipment. Cap off remaining utilities for potential use/re-connection in the future. Remove shelves on west wall to accommodate siting of large floor-standing equipment before patch and painting. Also, add 120/240 electrical outlets (raceway) along this wall. Replace flooring -- this depends on what we decide about removing the walk-in fume hood listed below Add GFCI outlets near water sources. Requires a connection to a DI water system Other utilities are required in this room and at what locations, e.g. air, oxygen, gas, vacuum, etc.? Remove existing walk-in Fume Hood (if cost for this issue does not trigger project over $50k) – Please assess/cost out and advise prior to project. Spieth 1364 – Lab Support Space work: Patch/paint –Re-finish, re-surface – existing cabinets (non-porous surface), Re-finish and/or replace benchtops, if sink cannot be significantly cleaned, they should be replaced Replace faucets at sink location. Add GFCI outlets near water sources Requires a connection to a DI water system" | N/A | 2019-05-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000358 |  | 19P000358 | FALSE | CNAS | SL5 GEOLOGY - ACCOMMODATION REQUEST |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-10-26 | [6 empty] | 4/15/19, DL; This Project is 100% Complete……. 3/28/19, DL; Plans are approved. We will start the work on 4/1/19……3/18/19, DL; Waiting for approved plans from building official……2/28/19, DL; Plans were submitted to building official for review. Once plans are approved, we will schedule the work………..2/14/19, DL; Plans are in process and we will apply for building permit next week………….. | 2019-02-07 | Ron Veloz | 02/07/19 O-RVL: RV changed title from "Geology" to "Physics". SOW is completed and on the server. Emailed a copy of SOW to FS team on 2/7. Received email from Ron Rector requesting Dan L. to provide Ronda Inzuna status update. END--- 01/31/19 O-RVL: Intake in progress. --- 01/15/19 O-RVL: Updated notes, the following SOW was from the requestor. --- 12/14/18 O-RVL: RV walked the site with Deborah Mc Williams on Mon 12/10. RV to create SOW. Returned request back to O-UA1 and will work from O-UA1 until the project is prioritized. "Potential scope of work for accommodation request: 1. Pour 10x10 cement pad for reserved electric transportation vehicle. 2. Electric charge station 3. appropriate signage" --- Deborah McWilliams is the main contact 951-218-3720 --- 11/14/18 RV: RV & Monty Received an "FYI" email from Deborah Mc Williams on 11/09/18 with information related to the approval of the charging station --- location currently undergoing review by the CBO. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000223 |  | 18P000223 | FALSE | CNAS | SL5 Provide requisite utility infrastructure to support 4 add'l chambers (on order). |  | FAWCETT LAB |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 11 | 21 | FALSE |  |  | 2017-12-11 | [6 empty] | 2/1/19, DL; This Project is 100% Complete……..01/15/19, DL; Plans are approved, Chambers are on site. Electrical is complete. Plumbing work is in progress. Our portion of the project should be complete by 2/1/19…………..12/14/18, DL; All Pre work is complete. The Chambers are scheduled to arrive on site within the next 30-days. We will finish this project when material on site……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans……..DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet….DL, 4/29/18; Still need to conduct site visit with the team….DL, 5/24/18; Per Patty, equipment is ordered but 5- months out…..DL, 9/6/18; We will submit plans to Bob W. tomorrow for review and approval……..DL, 9/19/18; Plans are approved. The equipment will be here in about 4- months. WE will start the work for this project in the Fall to ensure we are ready when the equipment arrives……DL, 9/19/18; Plans are currently being review by BO & FM……DL, 11/7/18; Plans are approved. WE are requesting to change the placement confirguration of the growth chamber and awaitng Bob's review and approval. WE are on track to have this work complete befoire the end of the new year….. |  | Dan Lerman | DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans........DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet....DL, 4/29/18; Still need to conduct site visit with the team… | YES | 2019-02-01 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000214 |  | 19P000214 | FALSE | CNAS | SL5 PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT |  | PHYSICS | 3005 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-08-24 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000341 |  | 19P000341 | FALSE | CNAS | SL5 PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL |  | PIERCE |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000340 |  | 19P000340 | FALSE | CNAS | SL5 PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE |  | SKYE HALL | 349 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | VICTORIA AVALOS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000045 |  | 19P000045 | FALSE | CNAS | SL5 PREPARE LOCATION AND UTILITIES FOR INSTALL |  | BOYCE | 2407 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 14 |  | FALSE |  |  | 2018-07-23 | [8 empty] | Ron Veloz | Scope is complete. Walked site with Steve Burelson. DI water is available behined wall in 2407 at interstictal space. Vendor will install Milpore unit, FS to provide DI water and back board.Power is available at the sink counter. Electrical has verified GFI. | YES | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000106 |  | 19P000106 | FALSE | CNAS | SL5 PHYICS 1134 - UTILITIES REQUEST |  | PHYSICS | 1134 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 15 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 6/15/19, DL; This Project is 100% Complete…...5/1/19, DL; Project should be complete this week or early next week…..3/28/19, DL; Power is complete. Need to finish chilled water…… 2/1/19, DL; Review scope with Customer. Still need to review with Brian from the Electic shop…………….12/14/18, DL; No update…. | 2018-11-07 | Ron Veloz | 01/31/19 O-RVL: Walked site with Dan L on 01/31 to review SOW. END--- 01/23/19 O-RVL: Received email from Ward B.in response to Brian Hambleton's request to use 208v. response is" ... 208 volt power 3-phase is fine for the compressor. Also having emergency power is not needed". END--- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela. END --- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela.-END 01/23/19 RV received Dr. Beyermann's comments and made corrections to the SOW, rev2. END--- 01/22/19 O-RVL: RV updates, Received a request from Mayela to meet on site with team. Sent team a copy of the Statement of Work for their review. Scope of Work: Install: Chilled new water supply & return drop, Electrical Power for the Compressor to be 3- phase 40Amp 220/230VAC hardwired from the equipment the disconnect for the Compressor. Power for the QD Pump and Controller to be single phase 200-230VAC, 20amp circuit. Patch and paint as needed, test for lead paint and TSI Asbestos abatement, equipment anchoring. Note: Job walk conducted on 11/07/18, 9:45-10:00am. Met in 1134 to determine Equipment and Utility Service location. In addition, on 11/03/18 the customer requested a single phase 200-230VAC, 20amp circuit (received info via email). END --- 01/11/19 O-RVL: Received an email from Mayella requesting status. END --- 11/08/18 O-RVL: Received email from Dr Beyerman today for added electrical. "I just realized that I also need a single phase 200-230VAC, 20 amp circuit in 1134 for the pump and controller, which is that unit next to the dewar. This can be down by the floor, in the vicinity of the 3 phase box. I will be meeting with the electrician today around 11am, and I will mention it to him". RV asked Dr Beyermann to contact me with the location for the pump receptacle. Will update floor plan upon receipt. 11/07/18 RV Walked site with Mayela and Dr Beyerman. Request to provide Chilled water loop, and two locations for Electrical power. Identified locations to install new utilities. END --- 11/07/18 O-RVL: Walked site on 11/07 with Dr Beyermann & Mayela, identified scope. Update FAMIS to J-DLN, MinRenlist and move to que to start. END --- 11/06/18 O-RVL: Jobwalk scheduled on 11/07 at 10:00am in Rm 1134 with Mayela, Ward Beyermann, Darren M HVAC, Brian H-Elect. Hold | YES | 2019-06-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000170 |  | 19P000170 | FALSE | CNAS | SL5 INSTALL NEW IRRADIATOR INSTRUMENT |  | MAT SCI ENGR | 51 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 16 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 2/14/19, DL; This project is 100% Complete………2/1/19, DL; Power is complete. Chilled water will be complete next week…………..1/15/19, DL; Electric is commplete, Water will be complete with in two weeks. Equipment should be on site soon…12/14/18, DL; This project is currently on hold per RED…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; The unit is schedukled for delivery in the next three weeks. | 2018-09-19 | Ron Veloz | 01/30/19 O-RVL: Spoke with Dan, equipment arrived staging into building. END---…..9/10: D. Dinh Project is shared between CNAS & BCOE, captured only on the CNAS College Count. 09/19/18 RV, Scope is complete. RV to Upload into FAMIS. Install chilled water and dedicated power for the irradiator instrument at the west wall in rm 051. 10/17/18 RV: SOW provide Chilled water loop and one(1ea) dedicated 208v 1ph 40a circuit to the Irradiator. Floor plan and specs are on the server folder. | YES | 2019-02-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000292 |  | 19P000292 | FALSE | CNAS | SL5 GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 18 |  | FALSE |  |  | 2018-08-10 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…….2/14/19, DL; The Concrete and Power is Complete. We still need to install the chain link which will be installed in about 3-4 weeks………..2/1/19, DL Electrical is complete. WE will pour Concrete next week. We will schedule the fence install 28- days after concrete is poured………; Th1/15/19, DL; Plans are approved, we will start the work in the next two weeks……12/14/18, DL; Plans are almost complete. We will schedule the work after plans are approved……DL, 11/7/18; Conducted site visit with Chris P. We need to confirm a feasable site location before we move forward with the work…. |  | Ron Veloz | 10/30/18 RV: Chris Pillen and D. McWilliams aggreed to leave the building in place and place a concrete pad with a chain link fence adjacent to the existing structure. 10/17/18 RV: SOW, demolish walls and roof. Verify and cap existing underground utilities. Remove overhead electrical from power pole to the building. The concrete pad to remain and install a 6'H fence with gate around the pad. Bring Power below grade to pad location. Met with C.Pillen and Dan to discuss alternate options. Photos and equipment info is on the server file. | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000099 |  | 18P000099 | FALSE | CNAS | SL5 EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 26 | 23 | FALSE |  |  | 2017-09-08 | [6 empty] | 4/19/19, DL; This Project is 100% Complete :)…………….12/6/18, DL; This project is a priority #23 and may be completed in the next 12 - months…..DL 1/3: Chris to verify with customer on electrical requirements for completion……DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress…..DL, 7/11/18; Still need to work on plans…. Target date is 9/30/18….. |  | Dan Lerman | DL 1/3: Chris to verify with customer on electrical requirements for completion…...Dl, 4/29/18; Will work on plans/permits. The display cases will be in a corridor and they may pose an obstruction for Emergency Exit egress.....DL, 4/2/18; This is electrical outlets for 4 display cabinets…..…NO FAMIS work orders yet…. | YES | 2019-04-19 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
17W012504 |  | 17W012504 | FALSE | CNAS | PAINT Business OFFICE AND CONF. ROOM |  | ENTOMOLOGY | 170 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 27 | 26 | FALSE |  |  | 2017-05-04 | [6 empty] | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. |  | Dan Lerman | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. | YES | 2018-10-22 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
18P000257 |  | 18P000257 | FALSE | CNAS | SL5 SKYE HALL MOUNT 55 |  | SKYE HALL | 209 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 28 | 28 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete…….1/15/19, DL, Site visit is scheduled with James M. this Thursday. We will schedule the work shortly after the site visit…….12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | 2019-02-01 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
18P000284 |  | 18P000284 | FALSE | CNAS | SL5 SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT |  | SKYE HALL | 277 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  | 29 | 23 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000258 |  | 18P000258 | FALSE | CNAS | SL5 SKYE HALL HALLWAY MOUNT |  | SKYE HALL | 212 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 29 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete……1/15/19, DL, Site visit is scheduled with James M. this Thursday…………12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | 2019-02-01 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000006 |  | 19P000006 | FALSE | CNAS | SL5 MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 |  | MAT SCI ENGR | 310 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..2/14/19, DL; This project is 90% Complete. ………2/1/19, DL; This Project started to day. We are scheduled to be complete by the end of February………..1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. | 2018-09-28 | Ron Veloz | 10/30/18 RV: Spoke with Deborah McWilliams, today. Project to remain as prioritized(#3) for new Faculty. 10/17/18 RV: Floor plan is on the server folder. RV: 10/03/18: Install metal stud wall at center of the room. Remove one door blank and install one lockset.Requires, Framing, drywall, tape, sand, paint, t-bar modifications and rubber base. PM to verify with user if power and Data will be required in the new wall. 09/28/18 O-RVL: Completed SOW: Add Wall in the center of room. Include a new Metal Stud Wall with rubber base to match existing. Remove metal cover at ceiling. Remove door lock blank and install new lockset at left door. RV completed SOW & placed on FS server. Updated FAMIS and Minor Reno List. 09/27/18 O-RVL: Site walk with Chris P, Dan L. Mayela and Deborah McW. FS to re-install the metal stud wall to original place dividing the room equally. Scoping completed. 09/26/18 O-RVL: 19P000006-Scheduled a site walk scheduled with Dan. Will contact Deborah and Mayela for their participation. | YES | 2019-03-18 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000347 |  | 18P000347 | FALSE | CNAS | SL5 GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) |  | GEOLOGY | 0 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 31 | Deferred to Fall Quarter - summer priority 27 | FALSE |  |  | 2018-03-18 | [6 empty] | 4/15/19, DL; Thios Project is 100% Complete….3/28/19, DL; Monitor is installed, need to finish power and data………………...2/14/19, DL: The monitor is on site. We need to schedule the installation. 2/1/19, DL; Conducted site visit with Amber. Amber will order the monitor. We will schedule the installation when the monitor is on site………….DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/1 EB Site visit. TV to be mounted on wall above water fountain across from Geo 2306. Center of mount 84" high and centered between wall corner and bulletin board. Will need electrical and data. Computer connection cutout will be in mail room. See W.O. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000301 |  | 19P000301 | FALSE | CNAS | SL5 SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH |  | SCIENCE LAB1 | 214 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-09-27 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000055 |  | 19P000055 | FALSE | CNAS | SL5 CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM |  | COLL BLDG SO | 207 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Dan Lerman |  | 32 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2018-05-18 | [6 empty] | 4/15/19, DL; This project is 100% Complete…….3/28/19, DL; Need to order material and schedule the work…… Work order is assigned. 12/14/18, Dl; This project is prioritized at 32 and will not be scheduled in the near futurer…….DL, 7/11/18; Correction, I did not scope this yet, I thought we were talking agout the door bell and ADA operator. I will check in with Ronda and verify the scope…… DND 7/30/18: Created project to replace WO #18015182; project #19P000055 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. | 2018-11-29 | Ron Veloz | 11/29/18: RV Visited site and identifed the toilet room on the 2nd floor. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000174 |  | 19P000174 | FALSE | CNAS | SL5 BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT |  | BATCHELOR | 2112 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMY RICKS |  | Dan Lerman |  | 37 |  | FALSE |  |  | 2018-07-24 | [6 empty] | 5/1/19, Dl; This project is 100% Complete….. 4/15/19, DL; This project should be complete in 2-weeks…… 12/14/18, DL; This project is priortized at 37 and will not be scheudled until further notice…… | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scoping narrative is available and located on the BZM Fall Folder. Patch & Paint, replace supply grilles, reverse door swing, remove door closers, install metal plate over door opening. | YES | 2019-05-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18W013160 |  | 18W013160 | FALSE | CNAS | BEES- PATCH & PAINT 2460D & 2460F |  | GEOLOGY | 2460 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 33 | 29 | FALSE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000191 |  | 19P000191 | FALSE | CNAS | SL5 PATCH AND PAINT HINDERAKER BASEMENT |  | HINDERAKER |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 34 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000464 |  | 18P000464 | FALSE | CNAS | SL5 PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 35 |  | FALSE |  |  | 2018-08-16 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000436 |  | 18P000436 | FALSE | CNAS | SL5 COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS |  | COLL BLDG SO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 36 | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000031 |  | 19P000031 | FALSE | CNAS | SL5 BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) |  | BIOLOGICAL SCI | 3101 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 40 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 6/15/19, DL; This Project is 100% Complete…...5/1/19, Dl; This project will be complete on 5/5/19…..3/28/19, DL; Need to schedule a site visit with Estella. Left voice mail message on 3/28/19 to schedule site visit……..12/14/18, DL; This is prioritized at #40 and will not be scheduled in the near future….. |  | Enrico Baez | 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. Install 2 duplex outlets | YES | 2019-06-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000042 |  | 19P000042 | FALSE | CNAS | SL5 COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL |  | COLL BLDG SO | 200 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Paul Ditty |  | 38 |  | FALSE |  |  | 2018-07-20 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000049 |  | 19P000049 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT |  | PHYSICS | 3036 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | 39 |  | FALSE |  |  | 2018-07-25 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000318 |  | 19P000318 | FALSE | CNAS | SL5 GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE |  | GEOLOGY | 420 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-04 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000184 |  | 19P000184 | FALSE | CNAS | SL5 REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES |  | GEOLOGY | 1270 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 45 |  | FALSE |  |  | 2018-08-14 | [6 empty] | 4/15/19, DL; This Project is 100% Complete…….. 3/28/19, DL; The project is 90% complete. Need to schedule floor installation…….. 2/14/19, DL; We will schedule the work soon. The space is vacant and ready…………….2/1/19, DL; This project has started. We would like to have the work complete by mid March…………..12/14/18, DL; This project is prioritized at 45 and will not be shceudled until further notice…… |  | Enrico Baez | 11/19/18 EB-Met with Laurie Graham at site. 11/08/18 RV: Enrico is assisting RV and has scheduled a job walk with Laurie Graham. Will follow up, pending confirmation. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000062 |  | 19P000062 | FALSE | CNAS | SL5 MSE 169-MINOR RENOVATION - NEW FACULTY |  | MAT SCI ENGR | 169 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 5 | 19 | TRUE |  |  | 2018-07-30 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………..1/15/19, DL; This project is 99% complete pending one water heater. Water heater is not here yet……12/14/18, DL; This project is 95% complete. The water heater is scheduled for delivery shortly after the new year. We will complete the install when the heater arrives…… 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 9/6/18; We will have the power and cabinets removed by 9/19/18. We are in the process of producing plans for this project. Once the plans are approved, we will proceed with the project. Note, we still need to obtain important information and some specifications regarding the procured base cabinets and counter tops, bio safety cabinet, diswasher, and freezer. ……DL, 7/7/18; The work is 90% complete. We are waiting on parts which have a 4-6 week lead time. We will finsh the balance of the project when the parts arrive….. | 2018-08-22 | Ron Veloz | 10/17/18 RV: Work is in Progress. END--- 08/27/18 RV: Updated notes. Moved to "Que to Start". Lab upgrades, Install utilities for new lab equipment, including DI water, electrical, modify existing cabinet to accommodate new flask washer, install owner furnished lab workstations. END ---...DND 8/12/18 replaced 3 projects for Summer quarter completion. Ron V. has scope on project. END --- 08/22/18 O-RVL: completed S.O.W, sent to Mayela Castillo for sign off. 08/23/18-RV: Ron V. Resubmitted S,O.W. rev.1 and received Final sign off from Mayela. Met with Dan to provide information and hand off the project. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000126 |  | 19P000126 | FALSE | CNAS | SL5 CHEMICAL SCIENCE - MINOR RENOVATIONS |  | CHEMICAL SCI | 455 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Dan Lerman |  | 6 |  | TRUE |  |  | 2018-08-03 | [6 empty] | 12/14/18, DL; This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL,11/7/18; Paint is complete, Plumbing shop is planning to schedule the work in the near future…… |  | Ron Veloz | Work in progress, install nitrogen lines and valves(valves by PI). Patch and paint. 10/30/18 RV: Spoke with Kevin, pending nitrogen line installation | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000102 |  | 19P000102 | FALSE | CNAS | SL5 PATCH & PAINT FRONT CORNER OF OFFICE |  | LIFE SCIENCE | 2930 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 42 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000133 |  | 19P000133 | FALSE | CNAS | SL5 PATCH HOLES AND PAINT |  | BATCHELOR | 2203 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 43 |  | FALSE |  |  | 2018-08-07 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000291 |  | 19P000291 | FALSE | CNAS | SL5 MSE HELIUM RECOVERY SYSTEM |  | MAT SCI ENGR | 205 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 9 | HOLD | FALSE |  |  | 2017-07-24 | [6 empty] | 12/14/18, DL; This project is 100% Complete……DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB - spoke with Mayela who is determining status within her dept…. DL, 11/7/18; This project is complete but I need to conduct a final site visit….. |  | Ron Veloz | DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB-Spoke with Mayela-she is researching where the project stalled within her department. 7/2/18 DND Please verify if work is still required for completion 8/7/18 EB-sent Mayela email requesting update on 9/20/18 EB-emailed Mayela to determine status of project. 9/24/18 EB-Project not cancelled. Passed on to Ron Veloz. 10/03/18: RV, Walke job with Mayela, Chris P, Dan L & Deb McWilliams. PI to provide Dan layout and equipment specs. | YES | 2018-12-14 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000246 |  | 19P000246 | FALSE | CNAS | SL5 PHYSICS - PATCH AND PAINT |  | PHYSICS | 3007N | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 46 |  | FALSE |  |  | 2018-09-07 | [6 empty] | n/a |  | Paul Ditty | Duplicate request; project to be completed on 19P000234 | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000242 |  | 19P000242 | FALSE | CNAS | SL5 PAINT OFFICE |  | COLLEGE BLDG NO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 47 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000231 |  | 19P000231 | FALSE | CNAS | SL5 OLMH 1428 PATCH AND PAINT |  | OLMSTED | 1428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ANDREW CABRERO |  | Paul Ditty |  | 48 |  | FALSE |  |  | 2018-08-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000243 |  | 19P000243 | FALSE | CNAS | SL5 GENOMICS 1206 - PATCH AND PAINT WALLS |  | GENOMICS | 1206 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Paul Ditty |  | 49 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000285 |  | 19P000285 | FALSE | CNAS | SL5 PAINT AND PATCH PI OFFICE |  | ENTOMOLOGY | 269 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-09-17 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000313 |  | 18P000313 | FALSE | GSOE | SL5 SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-15 | [6 empty] | 18W011689 Work order was cancelled because it has the same scope and is a duplicate………DL, 6/16/18; Contract is being awarded this week. Weill are scheduled to have this work completed by fiscal closing……DL, 7/25/18; This Project is 100% Complete…..9/13: Zee - Customer noted paint peeling; updated to status to back in progress for work to be addressed.......DL, 9/19/18; The contractor is on site repairing the walls and painting. The work should be complete this week.......dl, 10/4/18; tHIS PROJECT IS 100% Complete..... |  | Paul Ditty |  | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000221 |  | 18P000221 | FALSE | CNAS | SL5 Provide add'l HVAC capacity to maintain lower temp |  | BOYCE | 4414 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 9 | 16 | FALSE |  |  | 2017-12-11 | [6 empty] | 12/14/18, DL; This project is 100% Complete……….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob. DL, 5/9/18; We will work on plans and submit for review.....DL, 6/16/18. Had meeting with Bob W. to verify what is needed on plans. I will work with Gunther on plans for submittal and review......DL, 7/11/18; Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall.....DL, 11/7/18; Material is on site and will will schedule the work with in the next 30- days..... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob | YES | 2018-12-14 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000176 |  | 19P000176 | FALSE | CNAS | SL5 PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY |  | PHYSICS | 1112 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 50 |  | FALSE |  |  | 2018-08-10 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | 2019-01-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000360 |  | 19P000360 | FALSE | CNAS | SL5 GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING |  | GEOLOGY | 1444 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000230 |  | 19P000230 | FALSE | CNAS | SL5 NEW FACULTY OFFICE FOR PATCHWORK/PAINT |  | GEOLOGY | 1242A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-08-30 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000251 |  | 19P000251 | FALSE | CNAS | SL5 CHEM SCI 428-PATCH DRY WALL HOLES |  | CHEMICAL SCI | 428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000369 |  | 19P000369 | FALSE | CNAS | SL5 PIERCE - PAINT IS PEELING OFF WALLS |  | PIERCE | 3341 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000482 |  | 19P000482 | FALSE | CNAS | SL5 PIERCE HALL- PAINT/PATCH HOLES IN 1219C AND 1220D |  | PIERCE | 1219C | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JACQUELINE HAMILTON |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-02-01 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
18P000274 |  | 18P000274 | FALSE | GSOE | SL5 SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 |  | EADY CENTER |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES | BRANDON BARBOSA | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-18 | [6 empty] | 2/14/19, DL; This project is Complete………….2/1/19, DL; This project is 99.9% Complete. We still need to conduct Final inspection with Building inspector……1/15/19, DL; The door and automatic opener is scheduled to be installed on 1/22/19……..12/14/18, DL; This project is 95% complete. The contract for the door and ADA operator was awarded today. We will schedule the work shortly after the new year…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Conducted site visit with Gilbert. We need to have a meeting to determin if this work is part of the SLA…… DL, 6/16/18; We still need direction, SLA or Recharge?.......DL, 7/11/18; This Project will require Plans and Permits. We will start on the Plans next Week. We will also issue work orders for work we will complete with in house staff. The Concrete work and Entry Door will need to be contracted out. Target Complete date is 10/1/18……..DL, 7/25/18; Work orders are produced. Planing to walk the project with Chris, Steve B and Robert C. thisw week or next week. We will submit plans to Bob Williams for the contracted work next week……DL, 8/8/18; Completed site visit with Robert C. Steve B, Steve T. and Chris; the Plumbers are complete. The carpenters and electricians will work on their items over the next three weeks. The Plans will be ready to submit on 8/9/18. Once plans are approved, we will proceed to go out to bid for the Concrete and the ADA operator. Target complete date is 9/21/18…….DL, 8/22/18; Plans were apprroved, Concrete Contract is being executed. Still working on Door and ADA operator……..DL, 9/6/18; NTP for Concrete will be issued on Monday. I will schedule the work. I need to follow up on the door order and the ADA operator…….DL, 9/19/18; Concrete walkway scheduled to start on 9/20/18. The new door and Frame will arrieve in 3-5 weeks. We will schedule the install when the new door and frame are on site…….DL, 10/4/18; Concrete work is complete. Still need handrail, signage, door and ADA operator. Target date is Early November….DL, 11/7/18; Project is 95% complete. Contract is being processed to install the new Door, Door Fram and ADA operator. Goal is to have the work complete befor the winter break…… |  | Enrico Baez | Duplicate of 18W011999 project scoped and note entered to make facility ADA compliant. | YES | 2019-02-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000237 |  | 19P000237 | FALSE | GSOE | SL5 PATCH AND PAINT OFFICE - SPROUL 1206 |  | SPROUL | 1206 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 4/15/19, DL; Project is 100% Complete….. 2/1/19, DL; This project will start on 3.1.19. We will need to abate ACM before we can start. Jess will isuue the 14- day notification to the AQMD. Once we have confirmation, we will schedule the work…….. | 2018-10-05 | Enrico Baez | 0/5/18 E. Baez- conducted site visit. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000288 |  | 19P000288 | FALSE | CNAS | SL5 COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS |  | COLLEGE BLDG NO | 202 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-19 | [6 empty] | 05/10/19 O-ANS: Project was canceled by FS in March 2019 because customer will have to submit separate work orders for each room since customer has requested to schedule and complete them separately in sequence (not all at once). 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19W007474 |  | 19W007474 | FALSE | CNAS | SL5 BG - RAILROAD TIE WALLS | Repair Railroad Ties at Botanic Gardens | BOTANIC GARDENS |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV | [5 empty] | FALSE |  |  | 2018-11-07 | [7 empty] | 2018-12-10 | Ron Veloz | 03/11/19 O-RVL: Update, RV emailed Deborah H and Team to cancel this request. Message: "Facilities Services has reviewed the “Request for Estimate” under project number 19P000348. We (FS) have reviewed the request and have determined the costs exceed that allowed to Facilities Services within the UC guidelines and would also require structural engineering services which is beyond the services we are able to provide. ACCESS (WO) and FAMIS notes are updated and the customer was emailed with the Cancellation of the request. Updates completed by Ron V on 03/11/19. Please cancel Project - 19P000348 and Work Request #: 19W007474. END--- 03/11/19 O-RVL: Received information from Dan L and authorization from Team to CANCEL this work request for estimate. Cost would exceed 50k and will require engineering. RV emailed the team to cancel the request by "FS". END--- 03/01/19 O-RVL: RV will walk with Chad C to determine if FS is cabable of repair/reinstall railroad ties true & plumb. Walked site with Chad C. on 03/01 afternoon. Chad will meet with C.P. to determine capabilitiy and staff to perform work. RV will follow up. END--- 02/15/19 O-RVL: Udated SOW, RV will schedule a site visit with the Carpentry Supervisor to detemine the construction feasability and estimated costs. END --- 01/09/19 O-RVL: REQUEST FOR ESTIMATE, Not a Project. RV To schedule a site visit with C. Pillen and Chad Chambers to evaluate if repairs are possible. END--- 12/10/18 O-RVL: REQUEST FOR ESTIMATE. Ron V walked with D. McWilliams & Jodie and identified the railroad tie retaining wall area requiring repairs. Jodie would like an estimate to repair the leaning railroad ties at specified areas. RV to meet with Chris P. and or Chad Chambers to determine if FS can perform work and or provide an estimated cost to perform work. END--- 11/07/18 O-RVL: Received an email form Deborah Mc. to discuss the wall at Thursday during our 1-1 meeting. | YES | 2019-03-11 | FS | FALSE | 2018 | 2019-08-01
18P000312 |  | 18P000312 | FALSE | CNAS | SL5 URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 |  | CAMP LOC NOT IN BLDG |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  |  | 38 | FALSE |  |  | 2018-02-13 | [8 empty] | Enrico Baez | Canceled per customer 9/12/18/ EB, 5/29, conducted site visit 5/25. Structure is a double wide modular building/trailer. Space needs to be cleared of equipment, desks, tools. Disconnect electrical, plumbing. Needs professional removal. University Asset see Susan Marshburn for direction. EB, 9/12/18 Per Deborah McWilliams email.Project is cancelled due to lack of funding. | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-08-01
19P000390 |  | 19P000390 | FALSE | CNAS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 0 |  | TRUE |  |  | 2018-11-29 | [7 empty] | 2019-02-07 | Ron Veloz | 02/12/19 O-RVL: Scoping is complete. Revised door layout and emailed April photos of the proposed storefront door system received from D.L. on 2/11. April Meinzer approved storefornt door system on 2/12. RV reveised floor plan utilizing the existing cased opening as discussed with D.L. on 02/11. RV provided D.L. a copy of the revised Intake Formw/ layout. Form w/ layout. Unable to update project notes on FAMIS -Project is not available. END--- 02/07/19 O-RVL: Monty asked RV to follow up on this request. Ron V scheduled meeting with April Meinzer on 2/7 at 1:30pm to review intake information for the proposed project at room 5494. FAMIS Updated END--- | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-08-01 | FY 19-20
19P000210 |  | 19P000210 | FALSE | CNAS | SL5 CHEMICAL SCI Install Door In Doorway |  | CHEMICAL SCI | 0225A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  | 25 |  | FALSE |  |  | 2018-08-24 | [6 empty] | 7/1/19, DL; This project is 100% complete…..6/17/19, DL; Po is cut. Target complete date is before 7/1/19……Permit was approved this week. We are now working on the contract with the vendor. Our goal is start the work with in the next 30- days. 5/15/19, DL; Plans were approved. I am in the process of working with PD&C for the contract. We will order material and schedule the wrok once we have a signed contract……..3/28/19, DL; Plans were submitted last week… 3/18/19, DL; Conducted site visit last week. We are working on plans now we will try and submit plans for permit review next week…… | 2018-09-19 | Ron Veloz | 10/03/18 RV: Install non rated door into an existing cased opening-for privacy & noise reduction. Will require carpentry-framing, patch, paint, and minor flooring/base repair.---09/19/18-RV, Scope of work is complete. RV to upload docs to FAMIS. | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-08-01 | FY 19-20
18P000273 |  | 18P000273 | FALSE | LIBR | SL5 RIVERA LIB -RESTROOM REFRESH PROJECT |  | RIVERA LIBRARY |  | TO BE PERFORMED BY PD&C | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2018-01-18 | [6 empty] | DND 12/13/18: Customer advised maintenance requests related to project request has been addressed. Renovation work to be performed by PD&C and customer submitted a CPMS request. DL, 6/16/18; Need to schedule site visit with Dave and Chris P…….DL, 7/11/18; Chris and I will walk this poroject next week…..Wlaked projects with Chris. We need to review in more detail to better determin the process for this project…..DL, 9/6/18. WE need to discuss what we are going to do with this project.... We walked the project but we now need Direction from Facilities leadership… |  | Dan Lerman | .Scope of work has been reviewed; determining how to complete project with trades. DL, 4/29/18; Chris said he is aware of project scope. I need to review with Chris and schedule the work;…..Dl, 5/3/18; Dand to walk project with Chris and Dave to confirm scope. We will sub out tile work. This is paint tile, lighting and plumbing fixture upgrade…. | YES | 2018-12-13 | FS | FALSE | 2018 | 2019-08-01
19P000414 |  | 19P000414 | FALSE | PLANNING & BUDGET | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM |  | POLICE BLDG | 100 | QUEUE TO START | Gerry Bomotti | Sharyl Murdock | KELLY DUNCAN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-12-17 | [8 empty] | Enrico Baez | 7/8/2019 E.Baez-Spoke with Dan. Work has alread been scoped and will be scheduled by Dan. 7/1/2019 E. Baez-Voice mail to Dan to determine project needs to be scoped. |  |  | FS | FALSE | 2018 | 2019-08-01
19P000245 |  | 19P000245 | FALSE | SOM | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY |  | SOM RSCH |  | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-09-07 | [6 empty] | 7/1/19, DL; This project is 100% Complete…..6/171/19, DL; Material is on site. Project should be complete in the next two weeks……..5/31/19, DL; Contracts is working on the contract. We should have a notice to proceed in the next two weeks. The project will be complete with in 30- from when we receive the notice to proceed……5/15/19, DL;, Plans were approved. I am working with PD&C on the contract. Once the contract is complete, we will schedule the work……3/28/19, DL; Plans were submitted and pending review and approval….. | 2018-10-29 | Ron Veloz | 02/15/19 O-RVL: RV updated notes added SOW & moved to "Que to Start". END--- 01/31/19 O-RVL: Chris at Lockshop reviewed the vendor quote and requested detailed equipment list. Pending revisions from vendor due this week. END--- 01/15/19 O-RVL: Delivered Access control quote to Jason & Chris R for review. They will respond with comments. Upon receipt and confirmation, RV will complete docs on server folder and update FAMIS & Access DB. --- 01/11/19 O-RVL: Qualifying quote to verify proper components from door operator vendor expecting reply soon. --- 12/14/18 O-RVL: Received Quotes for Auto door operator and Access controls this week. RV to provide update & quotes to Dan Lerman. Moving status to "Que to Start" on Minor Ren List & updating Project Folder. --- 11/07/18 O-RVL: Walked site with Access Control vendor --- 10/31/18 O-RVL: Walked site with Door Op vendor --- 10/29/18 O-RVL: Scope was Completed. RV to schedule job walks with Vendors. --- 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-08-01 | FY 19-20
19P000687 |  | 19P000687 | FALSE | BAS | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | PROJECT INTAKE | Gerry Bomotti | Georgianne Carlson | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-06-26 | [8 empty] | Dan Lerman | 7/1/19 E. Baez-Per Dan Lerman's request, received estiamte from Controlled Key, forwarded to Brendan O'Brien. |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
19P000324 |  | 19P000324 | FALSE | CNAS | SL6 SPIETH HALL ASSESS AIR VENT OR PURIFIER FOR LAB | Provide the single pass exhaust, air changes (6-12 ACH) and the negative air requirements for PI to perform surgeries in the room. | SPIETH | 1312 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 106 |  | FALSE |  |  | 2018-10-05 | [7 empty] | 2018-10-10 | Ron Veloz | 04/04/19 O-RVL: RV emailed Deborah Hughes requesting cancellation of this project on 04/04 and copied the FS CR team. END~ 04/04/19 O-ANS: Canceled per Minor Reno meeting. 03/25/19 O-RVL: Ron V Contacted Estella via email 01/10/19 to provide the status for lab/surgical room 1312 and informed her of the collaborative results between efforts between Facilities Services and EH & S. Ron V stated "After further investigation of the building mechanical systems and review by EH&S; Facilities Services has confirmed the existing building mechanical systems is unable to provide the single pass exhaust, air changes (6-12 ACH) and the negative air requirements resulting in the cancellation of this request. Please feel free to contact me if you have any questions or need additional information". END~ O-RVL: Updated this project and copyied information from FAMIS. Not sure who requested this request to be a project. RV may need to rescope the project after Winter prioritizing. 01/10//19 RV copied notes from FAMIS and input the following notes: "10/10/18 O-RVL: Received email from Deborah Hughes to determine if this request is a SL5 or SL6. RV visited the site on 10-10 and saw filter media covering the supply air diffusers. RV sent photos to D.H. and informed her this was a SL6 for BM to remove filter media from the supply air diffusers. 12-21-18. R-DMU. W/O is waiting on filter to be removed. Will need to calculate air changes. Make repairs as needed. Room needs to be set (Negative). This may be the solution to their air deficiency. 11/21/18 R-DMU: Spieth hall. Rm 1312. Walk this job with BeiWei. 10-11-18. R-DMU. Will need tech to pull 3 ply media filter from supply register and verify proper air changes, and Exhaust flow with Flow Hood". | N/A | 2019-04-04 | FS | FALSE | 2018 | 2019-08-01
19P000560 |  | 19P000560 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION |  | UV BLDG B | 0240B | PROJECT INTAKE | Susan Marshburn | Da Lan Dinh | LESLIE ROSE |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-04-04 | [8 empty] | Dan Lerman | 4/4/19-JENNIFER- PER ENRICO BAEZ, THIS IS THE WORK ORDER TO GET STARTED ON THE JOB. PLEASE REFER TO WORK ORDER #19W013241 |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS |  | COMPUTING | 161 | PLAN DEVELOPMENT/CHECK | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 2019-01-07 | [6 empty] | 07/22/19 O-ANS: Notes from WO 18W007453 which was canceled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
19P000438 |  | 19P000438 | FALSE | CNAS | SL5 BOTANIC GARDENS RAILROAD TIE WALLS | Request for review and cost estimate for the repair of two railroad tie walls in the Botanic Gardens. 1) Retaining wall located below the Iris Garden (across from the Greenhouse). 2) Low wall located along the pathway just below the Garage Office. | BOTAN INFO C |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 118 |  | FALSE |  |  | 2019-01-08 | [8 empty] | Ron Veloz |  |  | 2019-03-05 | FS | FALSE | 2019 | 2019-08-01
18P000354 |  | 18P000354 | FALSE | CNAS | SL5 GH16-25 COOLING SYSTEM REPAIR |  | GH 16 25 |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | MARK TANKERSLEY |  | Dan Lerman |  | 13 | 17 | FALSE |  |  | 2018-03-20 | [6 empty] | DL, 7/25/18; Reviewed Ron V. noted. I will check in with Chris on this to better determin the method complete this project. |  | Dan Lerman | DL, 5/5/18; This is a repair, No alterations taking place. Pasted from FAMIS work order...THE COOLING SYSTEM ON GH 16-25 IS FALLING APART SHEET METAL TRAYS HAVE TONS OF HOLES, WOOD ROTTING ETC. PLEASE REPAIR….. RV, 07/06/18: Dan, Chis Pillen and I have walked this project months ago and have a quote from Ralph Cox/KIRA Construction to repair the head house damages. See Chris for the status of subletting this work. | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-08-01
18P000480 |  | 18P000480 | FALSE | CNAS | SL5 BG - LOWER RESTROOMS-PAINTING-FLOORS | Canceled by Facilities Services; Work is not within the SLA and is not needed. | BOTGDN RSTRM |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-09-01 | FS | FALSE | 2018 | 2019-08-01
19P000614 |  | 19P000614 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 202- PAINT |  | COLL BLDG NO | 0202 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-01
19W003012 |  | 19W003012 | FALSE | CNAS | SL5 FIX RESTROOMS (PAINT AND FLOORS) | FS to coordinate with client to schedule work for completion. | CHAPMAN | 5 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 51 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | N/A | N/A | 2018-12-13 | FS | FALSE | 2018 | 2019-08-01
19P000616 |  | 19P000616 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 208- PAINT |  | COLL BLDG NO | 208 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-01
19P000234 |  | 19P000234 | FALSE | CNAS | SL5 PHYSICS 3005-WALL HOLES PATCH |  | PHYSICS | 3005N | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-09-04 | [6 empty] | **9/19/18 DUPLICATE REQUEST SENT IN SEE 19P000246 |  | Paul Ditty | Duplicate work request. | N/A | 2018-09-19 | FS | FALSE | 2018 | 2019-08-01
19P000428 |  | 19P000428 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES AVC OFFICE PREPARATION |  | STUDENT SERV | 3102 | CANCELED BY CLIENT | LaRae Lundgren | TBD | ANGIE GRAY |  |  |  | 0 |  | FALSE |  |  | 2019-01-03 | [8 empty] | Ron Veloz | 03/18/19 O-RVL: RV received a phone call from Angie Grey on 03/18 to verify if this project was cancelled based on a cancellation request in Jan 2019. RV informed Angie that the project was cancelled. 02/06/19 O-RVL: Updating notes. "Cancelled by Angie Grey on 1/22/19". 02/11/19 O-RVL: Dan L asked RV to confirm with Angie Grey that the project is cancelled. RV called and left a voice message with Angie(2/11). RV will follow up. END--- | N/A | 2019-01-22 | FS | FALSE | 2019 | 2019-08-01
19P000370 |  | 19P000370 | FALSE | ENROLLMENT SERVICES | SL5 PATCH AND PAINT CAMPUS TOURS |  | STUDENT SERV | 1137 | COMPLETE | LaRae Lundgren | TBD | ELIZABETH TATUM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000384 |  | 19P000384 | FALSE | ENROLLMENT SERVICES | SL5 PATCH HOLES IN WALL AND PAINT |  | STUDENT SERV | 2234 | COMPLETE | LaRae Lundgren | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | HOLD - FACILITIES SERVICES | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-22 | [8 empty] | Dan Lerman |  |  |  | FS | FALSE | 2019 | 2019-08-01
19P000467 |  | 19P000467 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | WATKINS | 2101 | HOLD - FACILITIES SERVICES | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-01-22 | [8 empty] | Dan Lerman |  |  |  | FS | FALSE | 2019 | 2019-08-01
19P000535 |  | 19P000535 | FALSE | PLANNING & BUDGET - AUXILIARY | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV |  | BANNOCKBURN VILLAGE BLDG H | H0108 | Project Intake |  |  | EDWIN MELGAR-MEJIA |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 2019-03-14 | [8 empty] | Enrico Baez |  |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
19P000417 |  | 19P000417 | FALSE | VC-UNIV.ADV. | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY |  | UNIVERSITY VILLAGE OFFICE LEASE | 201 | Project Intake | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 2018-12-18 | [8 empty] | Enrico Baez |  |  |  | FS | FALSE | 2018 | 2019-08-01 |  | 1
3498 | 3498 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY18) Manhole C6 Modification | Construct new sanitary sewer lines, New manhole, pipe connections, demo existing manhole. |  |  | In Bidding | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Gerald Caraig | 2 |  |  | FALSE | 220200 |  | 2019-02-25 | Award Contract | 2019-08-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-01
3527 | 3527 |  | FALSE | FAC-PLNG-DESIGN-CONST | Central Utility Plant Fire Alarm | Replace aging and non-replaceable fire alarm system, and conduit. Conduit is damaged and only 10% of wiring is usable. ( fire alarm system and devices are failing and they are not supported by manufacture ) -Run new conduit from propane tanks to fire alarm system -Install new terminal box at propane tanks. -Pull twenty two, 14 awg THHN wires in new conduit and terminate in junction box. -Replace 25 year old fire alarm panel, parts are not available to maintain system. -Add ada compliant horn/strobes thru out structure. -Add code compliant indicating devices thru out structure. -Replace 8 flame detectors -Replace all fire sprinkler devices on riser. -Flow switch. -Pressure switches. -Tamper switches. -Replace high capacity sounder at propane tanks. -Engineering, and drawings to be submitted to fire marshal for approval. |  |  | In Programming | Susan Marshburn | Da Lan Dinh | Ben Kochevar |  | Scott Donnell | 4 |  |  | FALSE |  |  | 2019-05-08 | Close-out | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3528 | 3528 |  | FALSE | FAC-PLNG-DESIGN-CONST | Entomology Museum Fire Alarm | Deferred Maintenance Project. Fire alarm system and devices are failing and they are not supported by manufacture. -Replace fire alarm system and all existing fire alarm peripheral devices. -Engineering, and drawings to be submitted to fire marshal for approval. |  |  | In Programming | Susan Marshburn | Da Lan Dinh | Ben Kochevar |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2019-05-14 | Close-out | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | Physics 2000 Renewal | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. |  |  | Contract Awarded-Start Construction | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 6 |  |  | FALSE |  |  | 2019-05-15 | Start Construction | 2019-08-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-01
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Reviewing final reports | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 7 |  |  | FALSE | 1250000 | 0 | 2018-10-17 | Complete Final Report | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3035b | 3035b |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY15) Roofing - Olmstead Hall | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. 112010 project budget is $456,163.00. Estimated construction cost is $425,680.00. Bidding 8/8/2017. |  |  | In design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 383112 |  | 2016-02-25 | Re-bid | 2019-10-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY15) Roofing - Spieth Hall/LSP | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. |  |  | In design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 432510 |  | 2016-02-25 | Re-bid | 2019-10-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3275 | 3275 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Fiber Optic Infrastructure Upgrade | Repair, replace and upgrade the fiber optic infrastructure network that includes 50+ buildings across campus. Also includes work to main hubs, sub hubs and make available spare fiber for future utilization. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | ----- |  | Daneca Stevens | 8 |  |  | FALSE | 643750 |  | 2017-04-12 | Award Contract | 2019-09-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3270 | 3270 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Chapman Hall - Replace HVAC System | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | CHAPMAN |  | In Construction | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Scott Donnell | 8 |  |  | FALSE | 595819 |  | 2017-03-07 | Complete Construction | 2019-07-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3271 | 3271 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Life Sci/Spieth Hall Elevator Renewal | Scope of work includes the number 3 and 4 elevators of Spieth Hall. Project budget is $344,898.00. Estimated construction cost is $250,400.00. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 9 |  |  | FALSE | 345000 |  | 2017-03-07 | Award Contract | 2019-08-01 | 2020-07-31 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3437 | 3437 |  | FALSE | FAC-PLNG-DESIGN-CONST | UCPD Generator Replacement | Replace unsupported 125kw generator with new - Critical Facility |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Fernando Nunez | 9 |  |  | FALSE | 300000 |  | 2018-10-08 | Complete Construction | 2019-07-01 | 2019-12-27 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
3272 | 3272 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Athletic/Dance Elevator Renewal | Project budget is $219,371.00. Estimated construction cost is $169,020.00. | ATH DANCE |  | Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 220000 |  | 2017-03-07 | Award Contract | 2019-07-01 | 2020-07-31 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3064 | 3064 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Botanic Gardens Basin Silt Removal | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | BOTAN INFO C |  | Bidding | Susan Marshburn | Da Lan Dinh | Toshio Ishida |  | Dave Bomba | 44 |  |  | FALSE | 110000 |  | 2016-04-20 | CEQA approval | 2019-09-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Rivera Library Arches/Arcade Repair | Paint and replace roof. |  |  | Bids received, award on hold due to DM funding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Jason Espinoza | 99 |  |  | FALSE | 240000 |  | 2016-05-06 | Funding | [11 empty] | PD&C | FALSE | 2016 | 2019-08-01
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Design | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 99 |  |  | FALSE | 600000 |  | 2019-06-18 | Receive revised 90% CD's | 2019-11-04 | 2020-02-28 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-01
2671 | 2671 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Elevator Mods-Various Bldgs | Provide Vertical Transportation Consulting, Mechanical, Electrical, Fire Alarm and Architectural/Structural Construction document design and specifications for the modernization of two (2) elevators at Webber and Watkins buildings which is included in the base design and one (1) elevator at the Entomology Museum is included as an add alternate. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 99 |  |  | FALSE | 596011 |  | 2016-01-05 | Advertise Project | 2019-08-05 | 2020-07-31 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
2805 | 2805 |  | FALSE | FAC-PLNG-DESIGN-CONST | West Campus Water Well | Drill a water well on AGOPS property. This will be funded out of Energy Savings and Minor Cap Approval has been signed. |  |  | Re-activated | Susan Marshburn | Da Lan Dinh | Ken Muelleer |  | Scott Donnell | 99 |  |  | FALSE | 250000 |  |  | Prepare RFQ for Civl Engineering | [11 empty] | PD&C | FALSE | 1900 | 2019-08-01
19P000411 |  | 19P000411 | FALSE | GRAD.DIV | SL5 PAINT, CARPET AND BLINDS |  | UNIV OFC BLD | 150 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-14 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000399 |  | 19P000399 | FALSE | GRAD.DIV | SL5 NEW CARPET + WALL PAINT |  | UNIV OFC BLD | 100 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-06 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000572 |  | 19P000572 | FALSE | GRADUATE DIVISION | SL5 PATCH, PAINT, AND CARPET UOB 152 |  | UNIV OFC BLD | 152 | IN PROGRESS |  |  | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-11 | [6 empty] | 06/28/19 O-ANS: Paint phase complete and awaiting carpet change. | [5 empty] | FS | FALSE | 2019 | 2019-08-01
19P000217 |  | 19P000217 | FALSE | GSOE | SL5 PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 |  | SPROUL | 1359 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-27 | [6 empty] | 4/15/19, DL; This project is 100% Complete…..2/1/19, DL; This proect will start on 3/1/18 and should be complete by 4/1/19…… | 2018-09-18 | Enrico Baez | 9/18/18 E. Baez Conducted site visit. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000229 |  | 19P000229 | FALSE | GSOE | SL5 RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-08-29 | [6 empty] | 6/15/19, DL; This Project is 100% Complete….. |  | Enrico Baez | 11/13/2018 E. Baez-Met with Ron Rector to discuss system placement. WEPA system is to be placed on second floor near vending machines on North side. See note in shared drive. Will need power and data connections. ---9/20/18 EB-conducted site visit 9/18. Request for tile and plumbing removal, patch and paint. To facilitate placement of printer system. E-mail sent to Monty on 9/14 asking for direction on renovating hallway space. Awaiting Susan's response per Monty. Entered scope on shared drive. Will need Fire Marshal approval to determine which of three possible locations will allow placing of WEPA system. | YES | 2019-06-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000054 |  | 19P000054 | FALSE | GSOE | SL5 PATCH & PAINT OFFICE |  | SPROUL | 2131 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-26 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000628 |  | 19P000628 | FALSE | GSOE | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2129 | QUEUE TO START | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-05-15 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000627 |  | 19P000627 | FALSE | GSOE | SL5 SPROUL HALL, RM 2120 - PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2120 | QUEUE TO START | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-05-15 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
18P000471 |  | 18P000471 | FALSE | ITS | SL5 WCH INSTALL SECURITY FENCE |  | CHUNG HALL | 134 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  |  | 5 | FALSE |  |  | 2018-06-12 | [6 empty] | DL, 7/4/18; Walked this project with Angel, This request is to install security fence with Sliding gate and welded webs to increase security. Space is vacant and ready to schedule work. Need to walk with Corey to see if this is a project they can do or sub out to De ANza fence......DL 7/25/18; Still need to walk project with Corey. Dl, 8/10/18; Site walk complete, we are waiting on estimates. WE will try and schedule the work with in the next 30- days....DL, 8/22/18; Work is scheduled for August 27th. Still need to order hardware.....DL, 9/6/18; The fence is installed and Angel is very Happy, but I need to check the project to verify we are good to go....DL, 9/19/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000373 |  | 19P000373 | FALSE | ITS | SL5 URGENT-INSTALL RECPTACLE, ENCLOSURE & MOUNT BRACKET |  | GERMPLASM | 881 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-07 | [6 empty] | <div>mount a bracket to the Network Pole at AgOps. This will include mounting a bracket, an enclosure and a 20 Amp electrical receptacle.</div> |  | Ron Veloz | 2/26/19-LB: Per Ron Veloz, this project is complete. |  | 2019-02-26 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000382 |  | 18P000382 | FALSE | ITS | SL5 ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | PHYLLIS FRANCO |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL, This project is Complete……12/14/18, DL; This project is scheduled to be complete shortly after the winter break…….This project was scoped previously with the IR Team. We may need plans or a permit because we are installing a Dutch door…..DL, 7/11/18; Need to produce work orders and schedule the work….. DL, 7/25/18; Still need to produce work orders and schedule the work. Target date is 10/1/18 | 2018-07-06 | Ron Veloz | 06/29/18 Ron V: SOW, Remove the existing non rated solid core door & grille and replace with a new maple veneerd Dutch door with prefinished clear coat without grille. Door to be prepped on the hinge side with one continoues hinge. Confirm/field verify is a double bevel on door is requird. Do not prep the strike/lockset side.. Cylinder to be bored onsite by Lock shop. The top of the lower door to have a small shelf + - 6-8 inches wide, confirm size with Duffy prior to ordering the door. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | 2019-01-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000474 |  | 18P000474 | FALSE | ITS | SL5 MS&E ELECTRICAL MODIFICATIONS FOR ITS |  | MAT SCI ENGR | 119 | COMPLETE | Danna Gianforte | Shelley Gupta | MICHAEL CAPRIOTTI |  | Robert Corey |  |  | 1 | FALSE |  |  | 2018-06-13 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…….2/28/19, DL; Work is scheduled with Darrenn F. for Spring Break…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. |  | Enrico Baez | 7/17/18 EB-Scheduling site visit with Michael Capriotti 8/7/18 EB- Met with Robert Corey to discuss scope of work. He will coordinate work. | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000381 |  | 18P000381 | FALSE | ITS | SL5 ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 3 | 4 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL; This project is complete. Note, Duffy only wanted the dutch door completed……..12/14/18, DL; This project is in progress and should be complete shortly after the new year……`DL, 7/11/18; Need to walk the project and schedule the work…… | 2018-07-06 | Ron Veloz | 06/26/18 Ron V. visited site & met with Duffy. Scope of work for rm's 2103 & 2103 A requires: Painting of walls and conduit locted on the walls, replace damaged ceiling tiles, replace one damaged prismatic 2x4 light fixture lense, remove one tack board and shampoo carpet. Existing wall tiles to remain and receive paint. No work required in 2103 B per Duffy. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | 2019-01-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19W002419 |  | 19W002419 | FALSE | ITS | SL5 ITS CENTER - INSTALL CARD READER ACCESS |  | ITS CENTER | 161 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-08-09 | [9 empty] | 1/8/19: O-ANS: Converted to a project 19000433 and canceled in FAMIS. |  | 2019-01-08 | FS | FALSE | 2018 | 2019-08-01
19P000293 |  | 19P000293 | FALSE | ITS | SL5 PAINT ESTIMATE REQUEST |  | TELEPHONE |  | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-21 | [6 empty] | n/a |  | Paul Ditty | Canceled by Customer 10/24/18 | N/A | 2018-10-24 | FS | FALSE | 2018 | 2019-08-01
18W007453 |  | 18W007453 | FALSE | ITS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-11-30 | [6 empty] | 07/22/19 O-ANS: Work Order converted to project # 19P000433. For further updates, see 19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  |  | WO converted to project #19P000433. |  | 2019-07-22 | FS | FALSE | 2017 | 2019-08-01
19P000021 |  | 19P000021 | FALSE | ITS | SL5 ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS |  | ITS CENTER |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-07-12 | [6 empty] | 4/15/19, DL; This project is 100% Complete…… 3/28/19, DL; Monitors are done. Nee to finish the install of data and power…….12/14/18, DL; Still need to review scope….. |  | Enrico Baez | Met with IT staff. T.V. to be mounted in 4 locations. Will need electrical and painting in some locations. Waitng for updated scope from Joe Sepulveda | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000252 |  | 18P000252 | FALSE | ITS | SL5 CHASS INT S REPLACE ELECTRICAL SCREENS |  | CHASS INT S | 2130 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | JORGE MACIAS |  | Dan Lerman |  | 1 | 2 | FALSE |  |  | 2017-12-21 | [7 empty] | 2018-06-21 | Ron Veloz | 01/23/19 O-RVL: RV received confirmation (Telcon) with Jorge Macias to cancell the request. He will resubmit upon recipt of screens at a later date. RV instructed the Front desk(FS) to close out the request & "cc" Monty, Alan, Enrico & Linda & Loretta. END--- 01/23/19 O-RVL: RV emailed Jorge to verify status of the request/materials order. Pending response. END--- 01/09/19 O-RVL: RV spoke with Jorge on 1/09. Jorge expect screens to be ordered within two weeks and will cancel this request if the screens are not ordered by his department. Jorge asked to contact him in two weeks (01/23/19). END---6/21/18 RV HOLD, Walked site w/ Enrico & Jorge. Surveyed site and Enrico updated FAMIS & Project folder. Now pending - confirmation of party to purchase projection screens. S.O.W.: Remove two non functional motorized video screens. Replaced with new larger screen. Patch and repaint all walls and entry door. END--- 07/06/18 Ron V Input notes: Received email from Enrico on 07/03 confirming Facilities Services doe not purchase Audio Visual equipment in General Assigment class rooms. On 07/06 RV contacted Jorge Macias with this info and Jorge said he would get back to RV with follow up reply from his supervisor. Confirmed with E.B. that proj info/ photos are updated on the project folder and FAMMIS. END--- 8/22/18 O-RVL: Will follow up with Jorge to confirm status on the screen purchase and if Media will purchase the screens. END--- 08/23/18-RV emailed Jorge, Pending response. END--- 08/24/18-RV, Enrico followed up with Jorge, projection screens approved but not purchased yet). END--- 10/17/18: RV spoke with Jorge today and he said screens are on order. Jorge will follow up with updates to RV and Enrico. | YES | 2019-01-24 | FS | FALSE | 2017 | 2019-08-01
19P000386 |  | 19P000386 | FALSE | PROVOST/EVC | SL5 ROOM CHANGES |  | STUDENT SERV | 3106A | COMPLETE | Cynthia Larive | Luisa Levario | STEPHANIE ARCINIEGA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 4/15/19, DL; This Project is 100% Complete…… 2/28/19, DL; Conducted site visit. We need to schedule the work in the next 2-3 weeks This is for room 3109 C&D ……….. | 2019-02-07 | Ron Veloz | 02/07/19 O-RVL: RV completed Intake & Moved to "Que to Start". END--- 02/06/19 O-RVL: RV updates, Scope of work is to remove shelving from room, patch and Paint. Dan requested info on room availability. RV contacted Danielle for follow up from 02/05 call. RV will visit site, take pics, and follow up with Dan L.erman. Danielle reported that room 310C is vacant and available. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000053 |  | 19P000053 | FALSE | SoB | SL5 ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S |  | ANDERSON 1 |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-04-13 | [6 empty] | DL 8/22/18; two out of four monitors are complete. WE still need to install powree at four locations…….DL, 9/6/18; Still need Electrical installed……. Planing to have complete by 9/21/18……. This is aqctually 4- monitors in four locations. We should ensure each monitor is treated as an indidual project.......DL, 9/19/18; All monitors are installed. Robert will schedule the electricans this week or early next week...DL, 10/4/18; This project is 100% Complete..... |  | Enrico Baez | DND 7/25/18: Emailed R. Veloz advising work order is closed; upon completion of the scope review, Ron to work with Zee for a Project Number to be created. | YES | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000482 |  | 18P000482 | FALSE | SoB | SL5 CARD ACCESS SYSTEM ANDERSON SOUTH |  | ANDERSON |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-26 | [6 empty] | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with JasonDL, 7/11/18; Need to check in with Jason on status for his side of the project.....DL, 7/25/18; JAson's team is ready to install but the Anderson IT department does not have the necesary software. We will start the work when the software is up and running...... 8/12/18 DND FAMIS Status noted completion on 8/2/18. |  | Dan Lerman | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with Jason | YES | 2018-08-02 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000194 |  | 18P000194 | FALSE | ITS | SL5 TELEPHONE WINDOW REPLACEMENT |  | TELEPHONE | 101 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 5 | 6 | FALSE |  |  | 2017-11-20 | [6 empty] | 07/23/19 O-ANS: Canceled by customer per notes in FAMIS. |  | Enrico Baez | EB-1/31/18 Conducted site visit. Request to replace all exterior Plexiglas with glass. Will call glass vendor to provide estimate. 7/12/18 EB-Quote provided by Hour Glass. Emailed Tami, she is waiting for budget approval to proceed with project. Should have by end of July. 10/22/18 Customer Canceled; will resubmit when ready to proceed. | YES | 2018-10-19 | FS | FALSE | 2017 | 2019-08-01
19P000311 |  | 19P000311 | FALSE | ATHLETICS | SL5 ATHLETICS 150-KEYLESS ENTRY |  | ATHLETICS AND DANCE BUILDING | 0150 | Project Intake | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | DAN LERMAN |  | R2 |  | FALSE |  |  | 2018-10-02 | [7 empty] | 2018-09-27 | Enrico Baez | 1/31/19 EB emailed Joe Erbland inquiring if funding for project has been secured or to cancel request. 11/20/18 EB intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. From work order-looking to have two doors turned into key less entry for security of the practice center. |  |  | FS | FALSE | 2018 | 2019-08-01 |  | 1
3396 | 3396 |  | FALSE | ITS | C&C Rear Patio Tables/Shade | Installation of new exterior concrete slab and patio cover at the Computing and Communications Modular Buildings. The existing site will be cleared of all landscape to provide clear area to install concrete slab and address any grade/drainage issues. The addition of a proposed permanent patio cover is to be installed with full electrical options (lights, outlets, ceiling fans) to provide shade for future events and exterior lunch area. Shrubs along the street at the East side of the area are to be removed to provide a vendor/service ramp for events with the inclusion of lighted concrete seating within the space. | ITS CENTER |  | In Programming | Danna Gianforte | Shelley Gupta | Sheila Mabee |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2017-11-16 | Complete Project Study | [11 empty] | PD&C | FALSE | 2017 | 2019-08-01
18P000198 |  | 18P000198 | FALSE | VC-STU.AFF. | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 |  | HUB | 0 | QUEUE TO START | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 1 | 5 | FALSE |  |  | 2017-11-21 | [6 empty] | 6/17/19, DL; I will walk this work in the next two weeks and work on plan to submit to our campus architech and building official for review…..DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…… | 2018-01-23 | Enrico Baez | Plans will be developed and will be submitted for review and approval. 4/2 MN: Enrico to obtain an FAU….. 1/23/2018 E.Baez conducted job site walk. Request is for lighting installations above entries to store front and kitchen on East side of building and additional lighting above outside locker on loading dock. Manny has lights that can be re-used. Want estimate only. Need to include Campus Architect too…… 1/23/18 EB-site walk, scope enter in FAMMIS. | YES |  | FS | FALSE | 2017 | 2019-08-01
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. |  |  | Client approval/funding | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 2018-11-27 | Client approval/funding | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3413 | 3413 |  | FALSE | LIBR | Rivera Libr Gender Incl Restroom | Convert existing non-ADA multi-stall women's restroom to compliant ADA gender inclusive restroom. The project also involves the conversion of an existing non-ADA men's restroom to women's compliant ADA restroom. | RIVERA LIB |  | Secure Funding | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Dave Bomba | 3 |  |  | FALSE | 0 |  | 2018-03-26 | Secure Funding | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3104 | 3104 |  | FALSE | PALM DESERT GRAD CTR | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Programming | Tamara Hedges | Zelda Glenn | Zelda Glenn |  | Scott Donnell | 1 |  |  | FALSE | 22000 |  | 2016-05-12 | Design | [11 empty] | PD&C | FALSE | 2016 | 2019-08-01
2747 | 2747 |  | FALSE | PALM DESERT GRAD CTR | Heckmann Ctr-Landscaping (Donor Orchard) | UCR Palm Desert would like to replace the current turf grass with water-wise, sustainable landscaping. In return for the opportunity to use a “living laboratory” classroom for training, UC Cooperative Extension Master Gardener program has agreed to collaborate with UCR to revise and sustain the landscaping. The first phase will be to create an orchard to highlight UCR’s contributions to agricultural research in the Coachella Valley. The orchard will be located at the entrance to the Heckmann building, north of the walkway. UCR Physical Plant/Grounds to provide estimate for: • Project oversight • Project plan and drawings • Organic material to add to soil • Irrigation materials and installation • Edging for path • Weed cloth • Decomposed granite with stabilizer for ground cover • Decomposed granite with stabilizer for pathway • Concrete pad for art including bolting apparatus • Arbor for grapes • Flow system-fertigation • All other labor and materials other than kiosk, plant signage, turf and tree removal (current landscape maintenance vendor can remove) and plant materials and plant installation | HECKMAN ICEM |  | In Programming | Tamara Hedges | Zelda Glenn | Mike Lawrence |  | Scott Donnell | 2 |  |  | FALSE | 13800 |  | 2014-08-18 | Design | [11 empty] | PD&C | FALSE | 2014 | 2019-08-01
18P000390 |  | 18P000390 | FALSE | PLANNING & BUDGET | SL5 UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD |  | UV BLDG B | 0240B | COMPLETE | Gerry Bomotti | Sharyl Murdock | LESLIE ROSE |  | Paul Ditty |  |  | 1 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000324 |  | 18P000324 | FALSE | PLANNING & BUDGET | SL5 HINDERAKER PATCH AND PAINT |  | HINDERAKER | 4118 | COMPLETE | Gerry Bomotti | Sharyl Murdock | MILLY PAREDEZ |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-02-26 | [8 empty] | Paul Ditty |  | N/A | 2018-07-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000017 |  | 19P000017 | FALSE | SoB | SL5 ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD |  | ANDERSON 1 | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | DL, 9/6/18; Monitors are installed. Need to schedule the electrical. Target date is 9/21/18…… |  | Enrico Baez | 9/4/18 EB-This Project has been started. Monitors in place. Just need to run electrical. Dan aware. Refer to WO 19P000053. It asks for the same thing. Will request to close this and let Angela know. | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
17P000254 |  | 17P000254 | FALSE | PLANNING & BUDGET | SL5 FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS |  | CORP PP WHSE | 0106B | CANCELED BY CLIENT | Gerry Bomotti | Sharyl Murdock | DALAN DINH |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-06-07 | [6 empty] | 05/08/19 O-ANS: Canceled by customer per email from Deborah McWilliams. .2/1/19, DL; Material is ordered with a 4-6 week lead time.11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DD 10/6: On hold pending discussion on space…..DL, 7/11/18; I understand there is movement on this project but I need to check in with John P. or Chris P. for a status update. |  | Enrico Baez | 3/7/19 O-ANS: Project no longer moving forward per Ron Rector. ~ 12/14/18 O-RVL: F & LS shop space/Shop Location TBD. | NO | 2019-04-05 | FS | FALSE | 2017 | 2019-08-01
19P000241 |  | 19P000241 | FALSE | PLANNING & BUDGET | SL5 PATCH/PAINT IN OFFICE 2122 HINDERAKER |  | HINDERAKER | 2122 | CANCELED BY CLIENT | Gerry Bomotti | Sharyl Murdock | MILLY PAREDEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-06 | [8 empty] | Paul Ditty | Canceled per customer call on 9/13/18 | N/A | 2018-09-13 | FS | FALSE | 2018 | 2019-08-01
19P000401 |  | 19P000401 | FALSE | PLANNING & BUDGET | SL5 PATCH HOLES IN WALL AND PAINT |  | HINDERAKER | 4148E | COMPLETE | Gerry Bomotti | Sharyl Murdock | SHANNON TIMMONS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000261 |  | 18P000261 | FALSE | SOM | SL5 WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR |  | WEBBER | 1143 | COMPLETE | Deborah Deas | Brandon Barbosa | LOURDES ESCAMILLA |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 7/11/18; Work orders are produced. Need to assign the work order and order material. I will review with Steve and verify target complete date….DL, 7/25/18; Still need to walk the project with Steve……DL, 8/10/18; Material is ordered. We will complete the install when the materila arrives.....DL, 8/22/18; Material should be on site with in 4- weeks. Will schedule install when material is on site. Target date is 9/20/18.......DL, 9/6/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 4/29/18; Pasted from work order;I"nstall a glass window 28x9 on office door in WEBBER, Room 1143. | YES | 2018-09-10 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000425 |  | 19P000425 | FALSE | PLANNING & BUDGET | SL5 PAINT VIDEO PRODUCTION SUITE & HANG ITEMS |  | HINDERAKER | 1159A | COMPLETE | Gerry Bomotti | Sharyl Murdock | LISA CUSICK |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-20 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000599 |  | 19P000599 | FALSE | PLANNING & BUDGET | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | Sharyl Murdock | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 2019-05-09 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | FS | FALSE | 2019 | 2019-08-01 | FY 19-20 | 1
19P000573 |  | 19P000573 | FALSE | PLANNING & BUDGET | SL5 UNIVERSITY VILLAGE PAINT /REMOVE NAILS |  | UV BLDG B | 0208L | CANCELED BY CLIENT | Gerry Bomotti | Sharyl Murdock | JUDITH ABBEY |  | Paul Ditty |  | R2 |  | FALSE |  |  | 2019-04-11 | [6 empty] | 06/14/19 O-ANS: Canceled by Customer via email from Georgianne Carlson "Project 19P000573, UV Room 208L. Human Resources Department has withdrawn the request for this patch and paint project. Not a priority, at this time." |  |  | Canceled by client 6/14/19 |  | 2019-06-14 | FS | FALSE | 2019 | 2019-08-01 |  | 1
3518 | 3518 |  | FALSE | PLANNING & BUDGET | Chancellor House Kitchen Countertops | Replacement of kitchen countertops at Chancellor Residence |  |  | Construction | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 1 |  |  | FALSE | 24800 |  | 2019-04-02 | Complete Construction | 2019-07-01 | 2019-07-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-01
3516 | 3516 |  | FALSE | PLANNING & BUDGET | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Consultant Selection for Programming and Basis of Design | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Gerald Caraig | 2 |  |  | FALSE | 33980000 |  | 2019-03-04 | Program'g & Basis of Design Docs | 2021-01-04 | 2022-06-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-01
3520 | 3520 |  | FALSE | PLANNING & BUDGET | College Building South Seismic Improvements | Full building seismic retrofit to College Building South. |  |  | On-hold pending UCOP decision | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Jason Espinoza | 3 |  |  | FALSE |  |  | 2019-04-02 | On-hold pending UCOP decision | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3515 | 3515 |  | FALSE | PLANNING & BUDGET | DM(FY18) Elec Substation & Infra. Renewal |  |  |  | In Programming | Gerry Bomotti | Sharyl Murdock | Ron Rector |  | J.Franklin/G.Caraig | 3 |  |  | FALSE | 3750000 |  | 2019-03-08 | Field Data Gathering | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3521 | 3521 |  | FALSE | PLANNING & BUDGET | Life Sci Unit 2 Seismic Improvements | Full building seismic retrofit of Life Sciences Unit 2. |  |  | On-hold pending UCOP decision | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Jason Espinoza | 4 |  |  | FALSE |  |  | 2019-04-02 | On-hold pending UCOP decision | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3523 | 3523 |  | FALSE | PLANNING & BUDGET | 1907 Mt Rubidoux Facility Study | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. |  |  | Study in Progress | Gerry Bomotti | Sharyl Murdock | Melissa Garrety |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2019-04-22 | Complete Study | 2019-06-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-01
3504 | 3504 |  | FALSE | PLANNING & BUDGET | Silver Oaks Womens Health TI Fees | UCR Health will be acquiring new off-campus leased space by expanding into an adjacent medical office suite located at 19330 Jesse Ln #160, Riverside, CA 92508. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. |  |  | SOM to manage project | Gerry Bomotti | Sharyl Murdock | Brandon Barbosa |  | Brandon Barbosa | 6 |  |  | FALSE |  |  | 2019-02-14 | SOM to manage project | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3510 | 3510 |  | FALSE | PLANNING & BUDGET | SOMED Data Center Study | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. |  |  | Programming | Gerry Bomotti | Sharyl Murdock | Daneca Stevens |  | Daneca Stevens | 7 |  |  | FALSE | 55000 |  | 2019-03-04 | Study | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3501 | 3501 |  | FALSE | PLANNING & BUDGET | DMFI(17-19) Watkins 1000 Lecture Hall Reno | Renovation of Watkins 1000 lecture hall, to include lighting, HVAC, flooring, paint, and seating upgrades. This requests appears as projects Q-T on the approved 2017-2019 DMFI Program list. |  |  | In Bidding | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 8 |  |  | FALSE | 638000 |  | 2019-03-04 | Award Contract | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3508 | 3508 |  | FALSE | PLANNING & BUDGET | SOM New Academic Facility | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | Programming | Gerry Bomotti | Sharyl Murdock | Melissa Garrety |  | Mihai Gavan | 9 |  |  | FALSE |  |  | 2019-03-04 | Complete Programming | 2021-01-01 | 2022-12-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-01
3507 | 3507 |  | FALSE | PLANNING & BUDGET | Undergrad Class Labs & Studios |  |  |  | Pre-programming | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Blythe Wilson | 10 |  |  | FALSE |  |  | 2019-03-04 | Programming | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3492 | 3492 |  | FALSE | PLANNING & BUDGET | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Study in process | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 11 |  |  | FALSE | 65000 |  | 2019-03-04 | Complete Study | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3499 | 3499 |  | FALSE | PLANNING & BUDGET | Creekside Terrace Analysis | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Design | Gerry Bomotti | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 12 |  |  | FALSE |  |  | 2019-02-14 | CEQA | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3505 | 3505 |  | FALSE | PLANNING & BUDGET | Orange County Psychiatry | UCR Health will be acquiring new off-campus leased space by moving into an adjacent medical office suite located at The Airport Tower, 18881 Von Karman Ave #1227, Irvine, CA 92612. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. |  |  | SOM to manage project | Gerry Bomotti | Sharyl Murdock | Brandon Barbosa |  | Brandon Barbosa | 13 |  |  | FALSE |  |  | 2019-02-19 | SOM to manage project | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3474 | 3474 |  | FALSE | PLANNING & BUDGET | RUSD STEM High School |  |  |  | Real Estate project | Gerry Bomotti | Sharyl Murdock | ----- |  | Raoul Amescua | 16 |  |  | FALSE | 0 |  | 2018-10-31 | Regents Approval of Ground Lease | 2020-07-01 | 2022-06-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
2900 | 2900 |  | FALSE | PLANNING & BUDGET | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | BATCHELOR |  | Preconstruction - CMAR review of construction documents and site conditions | Gerry Bomotti | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 17 |  |  | FALSE | 18179000 |  | 2015-12-15 | Contractor Review of Building | 2019-09-01 | 2021-11-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
3484 | 3484 |  | FALSE | PLANNING & BUDGET | 266 Frost Ct Main House Demolition | Develop project budget and timeline, obtain funding from VCPB. Coordinate disconnection of all utilities: Electrical, Gas, and Water. Disconnect and cap sewer Coordinate HAZ Mat testing and report for asbestos and lead Hire abatement contractor (if necessary) to remove haz materials. Hire demolition contractor to demolish and dispose of existing house, garage and out buildings. Foundations to remain – but make safe and remove potential hazards (rebar, bolts, etc.) protruding from foundation. Paving, pavers and other “patio” slabs to remain – make safe by removing tripping hazards. Identify any hazards (I.E.; unstable retaining walls, debris piles, etc.) and make safe and secure or remove if more cost effective. |  |  | Close-out | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Daneca Stevens | 18 |  |  | FALSE | 72000 |  | 2018-11-15 | Complete Project close-out | 2019-05-01 | 2019-06-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
2839 | 2839 |  | FALSE | PLANNING & BUDGET | Multidisciplinary Research Building | External financing provided for this project. Total approved budget is $150,000,000. Confirmed per CPMX and BEA#978864 Xfer Tax Exemp Comm Paper. Funding received 7/25/2016. |  |  | Coordinating 2nd Phase Move-in & Related TI's | Gerry Bomotti | Sharyl Murdock | Jon Harvey |  | Mihai Gavan | 19 |  |  | FALSE | 156405000 |  | 2015-04-01 | 2nd Phse Move/TI | 2016-07-01 | 2018-09-28 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
2899 | 2899 |  | FALSE | PLANNING & BUDGET | Pierce Hall Improvements | Replacement of Mechanical, Plumbing and Electrical Infrastructure | PIERCE |  | In Construction | Gerry Bomotti | Sharyl Murdock | Jon Harvey |  | Dave Bomba | 21 |  |  | FALSE | 38560000 |  | 2015-08-06 | Fire Sprinkler Installation | 2019-01-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
2368 | 2368 |  | FALSE | PLANNING & BUDGET | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | Construction 7/15/19 | Gerry Bomotti | Sharyl Murdock | Katie Sanchez |  | Gerald Caraig | 22 |  |  | FALSE | 2600000 |  | 2016-05-19 | Complete Construction | 2019-07-15 | 2019-09-27 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3470 | 3470 |  | FALSE | PLANNING & BUDGET | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | New Study | Gerry Bomotti | Sharyl Murdock | Drew Hecht |  | Drew Hecht | 23 |  |  | FALSE |  |  | 2018-11-06 | Complete Review | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3110 | 3110 |  | FALSE | PLANNING & BUDGET | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded/never routed to the Dispatcher. 90% CD's completed. | Gerry Bomotti | Sharyl Murdock | Marianne Valenti |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | License Agreement Final Review | 2019-08-01 | 2020-06-01 | [9 empty] | PD&C | FALSE | 1900 | 2019-08-01
2774 | 2774 |  | FALSE | PLANNING & BUDGET | Highlander Hall Demolition | Demolition of the Highlander Hall Building |  |  | Complete Ciose-out | Gerry Bomotti | Sharyl Murdock | Blythe Wilson |  | Scott Donnell | 99 |  |  | FALSE | 2127000 |  | 2015-01-22 | Complete Ciose-out | 2018-08-01 | 2019-07-01 | [8 empty] | 2017-08-15 | PD&C | FALSE | 2015 | 2019-08-01
3195 | 3195 |  | FALSE | PLANNING & BUDGET | North District Development, Phase-1 | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Gerry Bomotti | Sharyl Murdock | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 3886110.55 |  | 2016-10-26 | Complete Construction | 2019-07-01 | 2021-08-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
19P000189 |  | 19P000189 | FALSE | CNAS | SL5 PHYSICS- WALL HOLES PATCH | Duplicate work order to 19P000049. Work to be completed on other project. | PHYSICS | 3036 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-16 | [10 empty] | NO | 2018-10-18 | FS | FALSE | 2018 | 2019-08-01
18W006022 |  | 18W006022 | FALSE | SOM | INSTALL CURTAIN ROD IN RESEARCH SPACE |  | SOM RSCH | 336 | COMPLETE | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-10-27 | [6 empty] | DL, 5/24/18; Need to review scope with Enrico….DL, 7/11/18; Enrico produced work orders for sheet metal shop. This is a singel trade project. |  | Enrico Baez | Blackout curtain needs to have a better way of being secured. Talked to Cory about fabricating a new curtain rod. 7/6/2018EB assigned to sheetmetal shop F-LNH | YES | 2018-07-11 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000473 |  | 19P000473 | FALSE | PROVOST/EVC | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 |  | HINDERAKER | 1100 | QUEUE TO START | Cynthia Larive | Luisa Levario | THERESA WAGNER | TORRI MCGARITY | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-29 | [8 empty] | Paul Ditty |  |  |  | FS | FALSE | 2019 | 2019-08-01
19P000434 |  | 19P000434 | FALSE | PROVOST/EVC | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | Please patch 50 plus holes on the wall and repaint that wall in Skye hall 136 due to the BKM removing the furniture attached to the wall. Please call Anita Ortiz if you have any questions at x2-5229. Shanshan's extension x7753 has not been moved to her new location yet. | SKYE HALL | 136 | COMPLETE | Cynthia Larive | Luisa Levario | THERESA WAGNER | SHANSHAN | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-07 | [6 empty] | 07/20/19 O-ANS: Work Complete per Paul Ditty. |  | Paul Ditty |  |  | 2019-07-22 | FS | FALSE | 2019 | 2019-08-01 | FY 19-20
19P000032 |  | 19P000032 | FALSE | SOM | SL5 Reconfigure recepetion desk to fit two FTEs. |  | SOM EDUC | 2608 | COMPLETE | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | 5 | 1 | FALSE |  |  | 2018-07-17 | [6 empty] | 5/1/19, DL; This project is 100% Complete….. 3/28/19, DL; Cabinet workl is complete. We need to finish the carpet and final laminate material…….2/28/19, DL; Conducted site visit with Chad. We will complete the work in the next two weeks…….2/1/19, DL; I Walked this project this week. We will try and schedule the work in the next 30- days…….12/14/18, DL, Still need to conduct site visit and schedule the work… | 2018-10-17 | Ron Veloz | 01/31/19 O-RVL: Met with Dan L onsite to review SOW with the requester. END---10/17/18 O-RVL: Remove one lower cabinet, Install a new corbel below to support the counter, install new carpet square or create an accent border if carpet tile is obsolete. Install new rubber base | YES | 2019-05-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000470 |  | 18P000470 | FALSE | SPP | SL5 Student Check-in Lobby |  | CHASS INT S | 4133 Corridor | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-11 | [6 empty] | DL, 6/16/18; I walked this project with Luis and Mark this week. They want this work completed by July 9th. Paint, data, electrical, chair rail and signage is requested. I need to review project with Paul and Robert C. DL, 7/11/18; Robert C. Ordered material and we will complete the install first part of next week We will scheudle the paint after Robert is Complete. Target Complete Date is 7/2018......DL, 7/25/18; WE have the electrical materila, plans were submitted. Once plans are reviewed and approved, we will proceed with the work. Target date is two weeks after plans are approved......DL, 8/10/18; Eletrical is complete. Pending paint. Paint will be scheduled in the near future. DL, 8/22/18; This project will be Complet on Saturday.....DL, 9/6/18. I miossed the chair rail request on this project. I will order the chair rail in the near future. The chair rail is the only item needed to complete this project. Aprroximately 20 lineal feet......DL, 9/19/18; Chair rail is ordered. We will schedule the install when the material arrives....... |  | Dan Lerman | Added by customer on prioritization; timeline and scope tbd. 4/25 EB emailed Christina to schedule site visit. No work order Luis to submit Google doc. To A&E sevral trades invlved. DND 6/13 Project rescoped and priorities adjusted per meeting between Dan and Luis Alvarez. | YES | 2018-08-23 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000351 |  | 18P000351 | FALSE | SoB | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 | 21 | HOLD - FACILITIES SERVICES | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2018-03-19 | [6 empty] | 7/15/19, DL; Work has started and should be complete on 7/16/19…….. 4/4/19 O-ANS: Moved to Queue to Start to complete during Summer 2019. DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week……8/8/18. The trades are ready to go after they finish current projects…..DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18………. DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date……..9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space……Note. The space is usable and everything works….. |  | Enrico Baez | 4/24/18 EB-scoped. Move screen, correct non-compliant electrical issues, remove&discard overhead projector bracket, relocate heat det. Add switched outles. Plans are needed because we are relocating a heat detector | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000033 |  | 19P000033 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT | Duplicate request to 19P000030; Canceling project to be completed on other request. | OLMSTED | 2301 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | Duplicate to project 19P000030. Canceling project. |  | Paul Ditty | Duplicate to project 19P000030. Canceling project. | N/A | 2018-10-01 | FS | FALSE | 2018 | 2019-08-01
18P000463 |  | 18P000463 | FALSE | SoB | SL5 ANDERSON HALL PATCH/PAINT-102C |  | ANDERSON 1 | 0102C | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-06-04 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000018 |  | 19P000018 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER |  | ANDERSON 1 | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000458 |  | 19P000458 | FALSE | SPP | SL5 CHASS INTS-BUILD PERM DRYWALL DIVIDER OR APPROVE BKM AIRWALL |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ | LUISA LEVARIO | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-19 | [6 empty] | 6/17/19, DL; This project is 100% Complete…..5/31/19, DL; This prject is making good progress and we are scheduled to be complete on or before June 19th…….5/15/19, DL; This project is in progress and schedule for complete near 6/15/19…. 5/1/19; We started this project last week and we are planning to be complete in 4 - 6 Weeks….4/15/19, DL; Material is ordered, we will start the demolition this week. We hope to be complete in 8-weeks or less……2/28/19, DL; Plans are complete and were submitted to for review and approval from campus building official and fire marshal. Once plans are approved, we will shcedule the work….. | 2019-01-28 | Enrico Baez |  | YES | 2019-06-17 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
18P000428 |  | 18P000428 | FALSE | SoB | SL5 OLMSTED RM 2352 PATCH/PAINT |  | OLMSTED | 2352 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-05-02 | [8 empty] | Paul Ditty |  | N/A | 2018-08-17 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000451 |  | 19P000451 | FALSE | SOB | SL5 ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 |  | ANDERSON 1 (N) | 58 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-15 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  |  |  |  | 2019-02-01 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000521 |  | 19P000521 | FALSE | SoB | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT |  | ANDERSON HAL NO | 138 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-03-08 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | FS | FALSE | 2019 | 2019-08-01 | FY 19-20
19P000030 |  | 19P000030 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT |  | OLMSTED | 2301 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000280 |  | 19P000280 | FALSE | SoB | SL5 ANDERSON HALL PAINT ONLY |  | ANDERSON 2 | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-13 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000353 |  | 19P000353 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT-2348 |  | OLMSTED | 2340 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-19 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Selection of DPP team | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Jason Espinoza | 1 |  |  | FALSE | 350000 |  | 2016-12-15 | Selection of Design Team | 2021-01-01 | 2022-10-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3415 | 3415 |  | FALSE | SoB | Anderson South Renovation | Per the sketched drawings that Dave Bomba was provided, please provide a proposal of what it would take to renovate Anderson South as follows: **1. Remove 1st Fl South side of Corridor wall and doors between 102 suite entrance and 106 suite entrance as well as adjoining walls within 102C. **2. Create a closet/wall, ideally, behind the existing door of the 102 Entrance running to the wall shared by 102A to include the best location for a door. Essentially, enclosing the window of 102, if possible. **3. Creating a closet under the stairwell between 1st floor and basement level, having entrance door flush with the bottom step of the stairwell. **4. Remove the West wall and door framing of room 001A, leaving an open look and no corridor in suite 001. | ANDERSON 2 |  | Bidding | Yunzeng Wang | Angela Chang | Laurie Gustafson |  | Dave Bomba | 2 |  |  | FALSE | 24700 |  | 2018-02-26 | Department funding | 2019-08-01 | 2019-09-30 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
3237 | 3237 |  | FALSE | SoB | Anderson Hall N. Access Imp. | ADA handrails installation at walkway and ramp on the East sidewalk by the bench of Anderson north, down the steep ramp leading to Anderson South. We have been working with Shelly Frohrip from HR and Mary-Alice Avila of A&E on this so they will have some information regarding the purpose. 11/15/17 The handicapped parking and POT are now included. Project approved, waiting for funding. | ANDERSON 1 |  | In Bidding | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 3 |  |  | FALSE | 150000 |  | 2016-12-19 | Re-bid | 2019-09-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
3345 | 3345 |  | FALSE | SoB | Anderson N & S - Landscaping | DESIGN SVC & LANDSCAPE Construction request as follows for updated CURB APPEAL of Anderson North/South: 1. Roses Garden in middle of Stair landing/court to be removed and replaced with Grass 2. Add Large Planters (Metal or Cement) with Citrus Trees (either Kumquat/Lemon/Orange/Etc) on ledges that are at top section of front steps to deter skateboarders from jumping off of these ledges. 3. Remove dead trees on North and south ends of front lawn 4. Remove plants around granite sign in front lawn and replace with grass 5. Remove flowers and grass at both corners of front lawn around Citrus Trees and replace with DG and low growing flowering plants. 6. Pull all Ivy and crown vetch and add Pavers to East/Back side of Anderson Hall within landscaped/planter areas where ADA walkway runs and replace with nice picnic tables to include umbrellas and/or lounge seating around Anderson North for students. 7. Add DG in all areas where space is open/available surrounding outdoor seating area in back of building. 7. Remove all hedges surrounding alcove/arched areas along buildings. |  |  | On hold until ADA path of travel is completed | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 4 |  |  | FALSE | 0 |  | 2017-07-18 | Completion of 3237 | 2019-10-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
18P000478 |  | 18P000478 | FALSE | UNDERGRAD ED | SL5 CARPET, PAINT, & AIR HANDLING MODIFICATION |  | HINDERAKER | 1120H | COMPLETE | Jennifer Brown | Tracey Scholtemeyer | TRACEY SCHOLTEMEYER |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-16 | [6 empty] | DL, 7/4/18; This project is scoped; Need to remove Switch gear storage rack components, remove electrical conduits, plywood backer board from walls, paint and floor covering. We will schedule this work to be complete by Fall 2018 academic year....DL, 7/11/18; Need to produce work orders and schedule the work. Target Complete date is 9/14/18... Space is vacant....DL, 8/10/18; Work has started and we are on schedule...... DL, 8/22/18; Demo is almost complete. This target date is 9/21/18......9/19/18; All trades are complete. New carpet to be installed on 9/21/18. .....DL, 9/19/18; This project is scheduled to be complete this week....... |  | Dan Lerman | 7/9 EB-Spoke with Dan, he has already scoped this. | YES | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000400 |  | 18P000400 | FALSE | SOM | SL5 Covert suite 1116 and suite 1126 to office space | Provost has placed a hold on converting lab spaces into office spaces. | WEBBER | 1116 & 1126 | CANCELED BY FS | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-14 | [6 empty] | DL, 6/16/18; Waiting for update on Provost approval….DL, 7/11/18; Per email from Enrico on 7/10/18. The Provost put a hold on converting any lab space into officess…… |  | Enrico Baez | 3/7/19 O-ANS: Project no longer moving forward per Ron Rector. 5/1 EB Convert two wet labs into offices. Same as Webber 2278. Abate floor, demo all cabinets, remove plumbing, patch & paint. Carpet tile. Equipment comes out. Awating Provost, Sheryl Murdoch and Bob Williams approval….. 7/11/18 EB-Per Brandon Barbosa project will be cancelled | YES | 2018-07-10 | FS | FALSE | 2018 | 2019-08-01
19S000833 |  | 19S000833 | FALSE | SOM | Add access control to entry doors |  | HECKMAN ICEM | Entry Doors | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-07-17 | [8 empty] | Ron Veloz | Canceled request per conversation with client; customer to coordinate for a contractor to complete project. ~ Will Meet with Chris Pillen on 08/23/18 to review notes by C.P. on FAMIS. 08/23/18-RV: Followed up with Chris P for update on the work request notes. Recommended to contact Brandon to procure a local vendor. 08/24/18-RV spoke with Brandon Barbosa to determine a plan to complete the request and will pursue pricing and oversee the installation. 08/27/18 RV: Update: Brandon will PM the project on his own. 09/19/18: UPDATE-CANCELLED BY Brandon. See notes above. | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-08-01
18P000380 |  | 18P000380 | FALSE | SOM | SL5 SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 | SOM RSCH | 330 | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-05 | [6 empty] | Canceled per customer on 8/22/18. |  | Enrico Baez | DD 7/17: Requested Enrico verify complete customer did not prioritize and noted work was done. 8/7/18-Conducted site visit-do not recommend location for TV due to potential damage from barn door type window screen. 8/15/18 emailed Tara Bathol that desired location for TV not recommended. Requested alternate location. 08/22/18 Ron V. Spoke with Tara. Tara confirmed the requestor cancelled the TV mounting bracket request after conversation with Enrico | NO | 2018-08-22 | FS | FALSE | 2018 | 2019-08-01
18P000215 |  | 18P000215 | FALSE | VC-STU.AFF. | SL5 STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA HAGGINS |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2017-12-08 | [6 empty] | 6/17/19, DL; This project is 100% complete. This project was the wall removal at the check in entrance…...5/31/19, DL; Contracts is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks4/15/19; All work is comleted except the floor covering and elcetronic card readers for the doors…..2/28/19, DL; This project has started and is on schedule…….2/14/19, DL; This project is scheduled to start on 2/19/19…………2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………1/15/19, DL, Material is ordered, material should arrive on site in the next 3- 5 weeks……12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 5/24/18; Need to review scope and site visti with Enrico. Plans and permits will be required for this project….DL, 7/11/18; Planning to walk work with Gloria and her team next week. Will be able to project complete date after site visit is conducted……DL; 7/25/18; We walked this project with the team. This will require plans and permits. We will schedule this work for Fall…………DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-45 Days…… |  | Enrico Baez | 01/15/19, DL; Plans are approved and material is ordered for the Phlebotomy room. We are securing the double doors. We are not conducting any work with countertop or window work. DL, 5/5/18; Pasted from wo: Noted changes to original request. Add counter windows onto end of the current SHS front desk main counter (2 windows/stations).2. Close exam room that is open to hallway with a wall (behind room 210).3. Covert 100A to phlebotomy room with a hallway access doorway.4. Open wall to reconfigure to allow space for lab manager…… EB 3/20 scoped project and annotated on FAMIS. | YES | 2019-06-17 | FS | FALSE | 2017 | 2019-08-01 | FY 18-19
19P000009 |  | 19P000009 | FALSE | SOM | SL5 SOME -- PAINT, SPACKLE AND CLEANING NEEDED |  | SOM EDUC | 2615 | COMPLETE | Deborah Deas | Brandon Barbosa | BEVERLEY HERBERT |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000354 |  | 19P000354 | FALSE | SOM | SL5 WEBBER 2130A-PAINT CHERI'S NEW OFFICE |  | WEBBER | 2130A | COMPLETE | Deborah Deas | Brandon Barbosa | DOMINIC SALAZAR |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-19 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000408 |  | 19P000408 | FALSE | SOM | SL5 PATCH & PAINT - 2605 SOM ED |  | SOM EDUC | 2605 | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000248 |  | 19P000248 | FALSE | SOM | SL5 SOME--SOME INSTALL ELECTRICAL 1682 |  | SOM EDUC | 1682 | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 2 |  | FALSE |  |  | 2018-09-10 | [6 empty] | 2/14/19, DL; This project is complete…… |  | Ron Veloz | 10/29/18 O-RVL: Scoping is completed. END--- 10/17/18: RV: Drawings are on server folder. END---10/08/18 RV: Spoke with Brandon B. Brandon will submitt BKM drawings via permit request through PD&C. 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon. Walked project with Brandon. SOW to install two each dedicated 120v/20a cicuits for new modular furniture one whip at each end of the office down the wall and one to two data drops overhead down wall. | YES | 2019-02-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000410 |  | 19P000410 | FALSE | SOM | SL5 PAINT OFFICES AT UC PATH |  | INTELLICTR |  | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-14 | [6 empty] | 06/06/19 O-ANS: Canceled per customer request. Paul spoke with customer who will outsource work. |  |  |  |  | 2019-06-06 | FS | FALSE | 2018 | 2019-08-01
19P000249 |  | 19P000249 | FALSE | SOM | SL5 SOME-INSTALL LOCKERS | Lockers on order by customer; upon arrival to be installed. | SOM EDUC |  | CANCELED BY FS | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-07 | [6 empty] | DL, 11/7/18; It is my understanding the lockers are ordered, but we donot have a confirmed delivery date. Once the material is on site, we will schedule the installation…… |  | Ron Veloz | 01/31/19 O-RVL: Contacted Domonic and confirmed lockers will not be avialable to install and agreed to cancel the request orginated on 09/07/18 and will resubmit a new request upon delivery of the new lockers. RV emailed Customer Relations staff to cancle the project request via emails and cc Monty, Deborah H., Alan, Loretta on the communication. 01/10/19 O-RVL: Emailed Dominic Salazar on locker delivery ststus. Pending follow up call from customer to inform FS on delivery of lockers. 11/08/18 RV: Visited site existing lockers in place and in use. Will follow up with the requestor for locker delivery status to schedule. RV Spoke with Brandon Barbosa. Deparment will purchase lockers. 11/08/18 RV: Received email from Domonic Salazar on 10/25 Lockers are expected to arrive. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01
18P000337 |  | 18P000337 | FALSE | VC-STU.AFF. | SL5 MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET |  | HEALTH SERV | 414 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-12 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18….Need to work on plans and permits….DL, 7/11/18; Gunther is working on plans. Target complete date is 9/14/18….DL, 7/25/18; Planning to submit plans for review next week. We will schedule the work once we have approved plans…….DL, 8/8/18; This is a structual wall and needs to be engineered. We are meeting with the Structual engineer on 8/9/18 to determine if project is possible.....DL, 8/22/18; Working on EDPA for Structual engineer; project timeline is late Fall. 9/19/18; The Agreement / Cointract for the structual engineer is processed for this project. We should have plans from the structual engineer to submitt to the Building Official and fire marshal with in 4- weeks......dl, 10/4/18; Plans are almost complete and we will submit them for review by the end of the week.....DL, 11/7/18; Plans are approved. WE are schedule to start this Project on Tuesday 11/13/18. Target complete date is by the end of the winter break..... |  | Enrico Baez | Cut wall between rooms 414 and 401, Case and trim opening, install carpet in- DL, 5/10/18; Gloria Vera is the contact; 827-5532 | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000281 |  | 18P000281 | FALSE | VC-UNIV.ADV. | SL5 ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS |  | ALUM VISITOR | 2202 | COMPLETE | Peter Hayashida | Naysia Caldwell | TRUDY COHEN |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-01-24 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…..2/28/19, DL; This work is scheduled…….DL, 5/24/18; Need to verify scope of work with EnricoDL, 7/11/18; Still need to visit the site and schedule the work…..DL, 11/8/18; This project was transferred to John. The target date was 1/2/19….. |  | Enrico Baez | 5/10/18 EB-Customer needs additional outlets in space to accommodate 4 new cubicles. Bob Williams wants additional information with plans. 9/13/18 EB-Met with Dan, Jorge, Rita and Kim. Scope to include patch and painting walls, removing art work, moving thermostat. Cubicles will need whip connections. | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000485 |  | 18P000485 | FALSE | SOM | SL5 SOMR PATCHING AND PAINTING |  | SOM RSCH |  | COMPLETE | Deborah Deas | Brandon Barbosa | DANA ABOU ABBAS |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000012 |  | 19P000012 | FALSE | SOM | SL5 SOME--PATCH & PAINT |  | SOM EDUC | 2638 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-07-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000014 |  | 19P000014 | FALSE | SOM | SL5 SOME - PATCH & PAINT |  | SOM EDUC | 2609 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-07-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
2359 | 2359 |  | FALSE | SOM | SOM - Research Bldg. BSL-3 | Reconfiguration and reconstruction of the existing BSL-3 suite on the 3rd floor. |  |  | Finalizing commissioning & air balance | Deborah Deas | Brandon Barbosa | Rebeccah Goldware |  | Mihai Gavan | 1 |  |  | FALSE | 2740000 |  | 2013-07-03 | Notice of Completion | 2016-10-01 | 2017-11-01 | [9 empty] | PD&C | FALSE | 2013 | 2019-08-01
3052 | 3052 |  | FALSE | SOM | SOM Trailer Expansion | Replace the (2) modular units with one 96' x 60' building and provide access from the SOM-ED building via concrete ramp; Re-vamp the entire site for accessibility. Signed Major Cap Approval for $150k augmentation received 10/25/17 - total project $2,250,000. |  |  | Completing Change Orders | Deborah Deas | Brandon Barbosa | Sharyl Murdock |  | Dave Bomba | 99 |  |  | FALSE | 2250000 |  | 2016-03-07 | Complete Change Orders | 2017-08-01 | 2018-02-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-01
2974 | 2974 |  | FALSE | SOM | SOM Research Building - 1st Floor Fit-Out | Buildout the 1st Floor of School of Medicine Research Building, a space of approximately 17,600 square feet. The construction includes wet laboratories, laboratory support spaces, offices and related support space. Work consists of, but not limited to the following: demolition of existing improvements, addition/alterations of walls, installation of new fume hoods, sinks, safety showers and eyewash stations, alterations/additions to the mechanical, electrical, plumbing, fire life safety, fire suppression, telecommunication and audio/video systems, as specified in the Construction Documents. |  |  | Completing Close-out. | Deborah Deas | Brandon Barbosa | Blythe Wilson |  | Mihai Gavan | 99 |  |  | FALSE | 9600000 |  | 2015-10-30 | Final Completion / NOC | 2017-10-01 | 2018-10-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
19P000645 |  | 19P000645 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT |  | BOTANIC GARDENS |  | Project Intake | Susan Marshburn | Da Lan Dinh | RONALD ANDERSON |  | DAN LERMAN |  | R2 |  | FALSE |  |  | 2019-05-22 | [8 empty] | Ron Veloz |  |  |  | FS | FALSE | 2019 | 2019-08-01 |  | 1
19P000213 |  | 19P000213 | FALSE | CNAS | SL5 NEEDS FOR NEW WALL DISPLAY (MONITOR) | Duplicate request to 19P000031; Work to be completed on other project. | BIOLOGICAL SCI | 3101 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [11 empty] | 2018-10-01 | FS | FALSE | 2018 | 2019-08-01
19P000255 |  | 19P000255 | FALSE | SPP | SL5 CHASS INT N REMODEL - 4022 PATCH AND PAINT |  | CHASS INT N | 4022 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000263 |  | 19P000263 | FALSE | SPP | SL5 CHASS NORTH REMODEL - 4009 PATCH AND PAINT |  | CHASS INT N | 4009 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-09-11 | [8 empty] | Paul Ditty |  |  | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000256 |  | 19P000256 | FALSE | SPP | SL5 CHASS REMODEL - 4146 PATCH AND PAINT |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  |  |  | 3 |  | TRUE |  |  | 2018-09-10 | [7 empty] | 2018-10-09 | Enrico Baez | 10/9/18 EB Sent Luis email, copied Mont too. Project will bw $25k-$30K. Asked Luis if we are to proceed. 10/15/18 E.Baez conducted site visit, Client requested cost estimate to construct 2-3 "huddle" Spaces with sound proof walls. Requires alterations to HVAC ducting, full height walls with doors, fire sprinkler additions, smoke detection additions, lighting changes. emailed Luis estimated cost of $25,000. 12/20/18 D. DINH: Spoke with customer, Luis Alvarez, and the project request has been modified to patch & paint and replacement of one ceiling tile. Customer to work with BKM to fulfill the wall partition request portion of the project. | YES | 2019-01-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000270 |  | 18P000270 | FALSE | SPP | SL5 CHASS INT S- EVALUATION FOR REMODEL |  | CHASS INT S | 4133 | CANCELED BY CLIENT | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Dan Lerman |  | 4 | 2 | TRUE |  |  | 2018-01-16 | [6 empty] | 4/24/18 EB- Per Christina Wong, no loner needed……DL, 5/5/18; Project is cancesled per notes DND 7/27; Please follow up with customer on the status and need for the work; customer advised to me that Dan has the scope of work for completion. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. |  | Enrico Baez | 4/24/18 EB- Per Christina Wong, no longer needed……DL, 5/5/18; Project is canceled per notes. DND 6/13; Project reopened and not canceled per conversation with customer. Complete scope review and speak with Luis Alvarez. DND 8/20/18: submitted Google form for Project to be reviewed by IRT. 8/19/18 Met with Louis Alvarez. Asked for measured plans from BKM for wall layout and dimensions. Emailed again on 9/6 asking for draws. Still waiting for BKM to provide drawings. 9/21/18 Dinh - placed on hold until customer provides BKM drawings. Enrico please manage follow up. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. On shared drive can be found in file. 10/30/18 EB-Cancelled by Customer | YES | 2018-04-24 | FS | FALSE | 2018 | 2019-08-01
19P000319 |  | 19P000319 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB |  | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-04 | FS | FALSE | 2018 | 2019-08-01
18W015691 |  | 18W015691 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER AND DRYER |  | BOYCE | 6444 | COMPLETE | Michael Pazzani | Laura Manor | DIERK BIGGS |  |  |  |  | 1 | FALSE |  |  | 2018-05-30 | [6 empty] | DL, 7/11/18; This project is in progress and almost complete. Target complete date is 7/20/18….. |  | Dan Lerman |  | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000476 |  | 18P000476 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER & DRYER | Canceled project, work completed on 18W015691 in July. | BOYCE | 6444 | CANCELED BY CLIENT | Michael Pazzani | Laura Manor | DIERK BIGGS |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-14 | [6 empty] | Duplicate to 18W015691; complete |  |  | Duplicate to 18W015691 | NO | 2018-07-11 | FS | FALSE | 2018 | 2019-08-01
18P000442 |  | 18P000442 | FALSE | VC-RED | SL5 FAWCETT LAB 203 PATCH & PAINT |  | FAWCETT LAB | 203 | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 3 | FALSE |  |  | 2018-05-18 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000379 |  | 18P000379 | FALSE | VC-RED | SL5 UOB PATCH AND PAINT |  | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-05 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18W013973 |  | 18W013973 | FALSE | VC-RED | SL5 BSL3 FACILITY- ASSEMBLE AND INSTALL |  | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2018-04-19 | [6 empty] | FAMIS NOTES 8/22: Plumbing filter system was installed and ice maker installed. Request for microscope and incubator moved into containment by customer. Complete 9/24/18 |  | Enrico Baez | 5/16/18 EB conducted site visit. 5/22/18 EB appliances dented, vaccum pump not on site. 6/19/18 emialed Chrystal to see if appliance have been replaced. 7/16/18 emailed Chrystal Jimenez asking for update. 8/7/18 EB Replacement appliances | YES | 2018-09-24 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000044 |  | 19P000044 | FALSE | VC-RED | SL5 PATCH AND PAINT |  | SPIETH | 345 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000439 |  | 19P000439 | FALSE | VC-RED | SL5 SPIETH PATCH AND PAINT ROOM 335 |  | SPIETH | 335 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-08 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2019 | 2019-08-01 | FY 18-19
19P000553 |  | 19P000553 | FALSE | VC-RED | SL5 SPIETH HALL PATCH AND PAINT |  | SPIETH | 341 | QUEUE TO START | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-01 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19W003050 |  | 19W003050 | FALSE | VC-RED | SL5 SPEITH HALL - PATCH & PAINT HOLE IN WALL |  | SPIETH | 0359A | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000495 |  | 19P000495 | FALSE | VC-RED | SL5 UOB RM 209- PATCH & PAINT |  | UNIV OFC BLD | 209 | QUEUE TO START | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-02-08 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [7 empty] | 2018-09-27 | Enrico Baez | 03/12/19 O-RVL: RV spoke with Enrico. He is already working on this proejct and will follow up to obtain the letter. END--- 3/08/19 O-RVL: RV Updated Notes on Access and copied to FAMIS. RV phoned Crystal Jimenez and followed up with an email to Crystal Jimenez with the request for authorization letter from the Land lord, cc'd Enrico, Dan L, Alan & Monty. END---03/07/19 O-RVL: During the minor renovation meeting, Susan asked RV to contact the requester and ask them to contact the landlord to provide a letter of approval in order to move forward with project. END---10/15/18 EB-sent Aaron Seitz approx. cost of project. 9/29/18 EB- install keyless entry system on two doors.--- 9/19/18 EB-Scheduled site visit for 9/20.--- 9/13/18 EB-emailed crystal Jimenez to schedule site visit. Awaiting response to determine funding. | YES |  | FS | FALSE | 2018 | 2019-08-01
19P000181 |  | 19P000181 | FALSE | VC-RED | SL5 PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS |  | UNIV OFC BLD | 249 | COMPLETE | Michael Pazzani | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-14 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-19 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | Funding | Michael Pazzani | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Daneca Stevens | 3 |  |  | FALSE | 45000 |  | 2017-06-13 | Secure Funding | 2020-03-01 | 2020-04-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
18P000269 |  | 18P000269 | FALSE | CNAS | SL5 BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED |  | BATCHELOR | 1123 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 12 | 18 | FALSE |  |  | 2018-01-16 | [6 empty] | 3/18/19, DL; went to schedule the work and the customer stated the power is no longer needed and confirmed this work order can be canceled. |  | Enrico Baez | 5/23/18 EB - Sent email to April requesting site visit. 6/11/18 EB conducted site visit request if for additional outlet only. Single trade only asked Deborah to change to SL6. FS to coordinate with client to scope the work. Customer contacted to schedule a site visit. | YES | 2019-03-18 | FS | FALSE | 2018 | 2019-08-01
18P000456 |  | 18P000456 | FALSE | VC-STU.AFF. | SL5 HUB--UTILITY METERS | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. | HUB |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-05-30 | [8 empty] | Enrico Baez | 1/24/19 EB Contacted Jonathan Bianchet of Design West for results of site evaluation. Will have report by middle of following week. 11/29/18 EB Met with Design West and HUB staff. Conducted site visit. Waiting for recommendations from Design West. 7/6/18 EB-emailed Brendan to schedule site visit. 7/11/18 EB- Site visit schduled for 7/12/18 7/16/18 Conducted site. Customer wants to have SEP metered for all food vendors. Requested electical power plans from Gunther 8/7/18 Contacted Design West for proposal of feasibility stud 8/15/18 Advised Brendan Obrien to submit request to CPMS as this work will not be self performed. Sent Brendan copy of proposal for sight assessment. | YES | 2019-01-24 | FS | FALSE | 2018 | 2019-08-01
19P000043 |  | 19P000043 | FALSE | CNAS | SL5 SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | Customer called and canceled the work on 10/23/18. | SCIENCE LAB1 | 309 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 19 |  | FALSE |  |  | 2018-07-20 | [7 empty] | 2018-10-22 | Ron Veloz | Customer called and canceled the work on 10/23/18. 10/20/18: O-RVL: Site visit on 10/20 with Amber 10:30am. 10/22/18 O-RVL: Walked site with Vendor/Controlled key sys. The PI requested pricing to change the locking function from room to room as "Storage use " and rekey the entry door with the same function. Matt will send pricing on the week of 10/22. 10/23/18 O-RVL: This request will not require access controls, but will require the entry door and side door lock-sets function to be changed to a storage function and rekeyed per Dave(PI). Received info from PI that there was a theft in his dept. Request is urgent. RV requested key count from Dave 8/23/18 and is pending a response from the department. 10/23/18 >> Canceling at the request of the customer - Loretta | YES | 2018-10-23 | FS | FALSE | 2018 | 2019-08-01
18P000214 |  | 18P000214 | FALSE | VC-STU.AFF. | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 |  | HEALTH SERV |  | HOLD - FACILITIES SERVICES | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-12-08 | [6 empty] | 7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for Doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once materila arrrives, we will schedule the installation. Floor covering is on hold untile we receive the process from EH&S…….5/31/19, DL; Contracts is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is comleted except the floor covering and elcetronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez | 01/15/19, DL; The plans are approved and Material is ordered. Once material arrives, we will schedule the work with Gloria… Dl, 5/3/18; Dan, Chris, Ron and Gloria will meet and re-scope the work……1/31/18 EB-Scoped site with Chris P. on 10/30/2017. Spoke with Gloria who thought still CPMS. Scope includes removing doors, adding teller counters, moving corridor wall…. | YES |  | FS | FALSE | 2017 | 2019-08-01
19P000455 |  | 19P000455 | FALSE | VC-STU.AFF. | SL5 FILL AND PAINT OVER HOLES ON WALL |  | HEALTH SERV | 100 | QUEUE TO START | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-17 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
18W011691 |  | 18W011691 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | FS to coordinate with client to schedule work for completion. | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 4 | 11 | TRUE |  |  | 2018-03-08 | [6 empty] | 12/17/18 DND: Canceled by client on 12/17/18. |  | Paul Ditty |  | N/A | 2018-12-17 | FS | FALSE | 2018 | 2019-08-01
19P000380 |  | 19P000380 | FALSE | VC-STU.AFF. | SL5 PATCH AND PAITN- WALL PAINT IS PEELING |  | HEALTH SERV | 404 | COMPLETE | Brian Haynes | Cathy Eckman | SAMANTHA HARRIS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-19 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000431 |  | 19P000431 | FALSE | VC-STU.AFF. | SL5 STUDENT SERVICES REMOVE NAILS AND PATCH WALL |  | STUDENT SERV | 2128 | QUEUE TO START | Brian Haynes | Cathy Eckman | VALERIE SANCHEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-04 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000405 |  | 19P000405 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED |  | HEALTH SERV | 0100D | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-11 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
18P000348 |  | 18P000348 | FALSE | VC-STU.AFF. | SL5 HUB ADD 3RD FLOOR WALLS |  | HUB | 0353E | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 2 | 6 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/1/19, DL; Per Chris P. This is a PD&C project………..DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Need to walk the project with Manny. Target date is late Fall…….. |  | Enrico Baez | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. EB 5/23/18. Conducted site visit. Request is for adding walls to interior spaces 353F, 381 and 377. Will impact A/C and fire protection. Still waiting for a firm plan from customer. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-01
19P000534 |  | 19P000534 | FALSE | VC-STU.AFF. | SL5 PATCH WALLS AND PAINT |  | HEALTH SERV | 334 | QUEUE TO START | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-03-15 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000037 |  | 19P000037 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE BLDG--PATCH WORK AND PAINTING |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-07-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000483 |  | 19P000483 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED |  | HEALTH SERV | 404, 407, 412, 405 & 411 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-02-01 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000124 |  | 19P000124 | FALSE | VC-STU.AFF. | SL5 PAINT ROOMS 115 AND 116 |  | COSTO HALL | 125 | COMPLETE | Brian Haynes | Cathy Eckman | LINDA KELLEY |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000172 |  | 19P000172 | FALSE | VC-STU.AFF. | SL5 HEALTH SERV- PAINT RESTROOM IN LABORATORY |  | HEALTH SERV | 0113A | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
3524 | 3524 |  | FALSE | VC-STU.AFF. | Stdnt Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. |  |  | Pre-Programming | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE |  |  | 2019-04-16 | Design | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3534 | 3534 |  | FALSE | VC-STU.AFF. | SRC N Cooling Towers Replcmt | Replacement of the 2 Cooling towers in the Student Recreation Center North. The towers are 25 plus years old and in needed of replacement to keep the HVAC system running efficiently. |  |  | New | Brian Haynes | Cathy Eckman | Michael Eason |  | John Franklin | 1 |  |  | FALSE |  |  | 2019-06-06 | New | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3471 | 3471 |  | FALSE | VC-STU.AFF. | HUB Electrical Sub-Meter Study | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Circuit Tracing of the designated spaces | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Gerald Caraig | 3 |  |  | FALSE | 50000 |  | 2018-08-20 | Circuit Tracing | 2019-12-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-01
3486 | 3486 |  | FALSE | VC-STU.AFF. | HUB 353/381, Costo 111 Add'l Wall/Doorway | Please evaluate additional wall/door way requests for HUB 353/381 and Costo Hall 111. | HUB |  | Client Approval/Funding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 4 |  |  | FALSE | 0 |  | 2018-11-26 | Secure Funding | [11 empty] | PD&C | FALSE | 2018 | 2019-08-01
3385 | 3385 |  | FALSE | VC-STU.AFF. | SRC North Gym Replace Interior Lights | Replace old technology sodium vapor light fixtures in SRC North Gymnasium with new technology LED light fixtures. Some flexibility available in the schedule. Selected vendor will need to phase work to minimize the effect on SRC operations and programming. | SRC NORTH |  | In Construction | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Fernando Nunez | 5 |  |  | FALSE | 396000 |  | 2017-10-31 | Start Construction 6/24/19 | 2019-06-24 | 2019-08-30 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-01
3512 | 3512 |  | FALSE | VC-STU.AFF. | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) |  | 2108ACDEF | Funding | Brian Haynes | Cathy Eckman | Christina Wong |  | Daneca Stevens | 6 |  |  | FALSE | 30000 |  | 2019-03-19 | Secure Funding | 2020-07-01 | 2020-10-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-01
2829 | 2829 |  | FALSE | VC-STU.AFF. | SRC South - New Storage Building | New storage building immediately south of SRC South Pool Building; approximately 20' x 40'; one roll up door and one standard door; electrical power required - number of outlets to be defined in design; concrete walkway and door pads required; non-potable water may be required if quick couplers are not available in nearby landscaping; please see attachment for location: approximately at gridlines T and 9.4 - dotted outline of building is labeled "FUTURE STORAGE" - located immediately south of the SRC POOL EQUIPMENT BUILDING. | SRC SOUTH |  | Coordinate with MRB & Mobility Hub Logistics | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Mihai Gavan | 7 |  |  | FALSE | 0 |  | 2015-01-23 | Coordinate with MRB Logistics | [11 empty] | PD&C | FALSE | 2015 | 2019-08-01
19P000238 |  | 19P000238 | FALSE | VC-UNIV.ADV. | SL5 PATCH & PAINT HINDERAKER 1136 |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000564 |  | 19P000564 | FALSE | VC-UNIV.ADV. | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | 1156C (AVC Johnny Cruz) – Patch molly holes, touch-up paint. 1156A (Jules Bernstein) – Remove (2) black & white photos from wall. Patch molly holes, touch-up paint. 1156B – Install picture frame (UCR campus map) onto wall. Suite 1159 – Patch holes. Remove film reels. Paint one accent wall “UCR Blue”. 1159B (Christy Zwicke) - Patch molly holes, touch-up paint. | HINDERAKER | 1156 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | Lisa Cusick | Christy Zwicke | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-08 | [12 empty] | FS | FALSE | 2019 | 2019-08-01
19P000326 |  | 19P000326 | FALSE | VC-UNIV.ADV. | SL5 HINDERAKER - PATCH & PAINT |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-08 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-01 | FY 18-19
19P000197 |  | 19P000197 | FALSE | CNAS | SL5 PATCH AND PAINT OFFICE, LOBBY AND HALL |  | COLLEGE BLDG NO | 0203B | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 44 |  | FALSE |  |  | 2018-08-21 | [6 empty] | 05/07/19 O-ANS: Canceled per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-01
19P000127 |  | 19P000127 | FALSE | CNAS | SL5 PIERCE PATCH & PAINT | Duplicate request to be combined with 19P000239 | PIERCE | 2301 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | MICHELLE KING |  | N/A |  | Canceled |  | FALSE |  |  | 2018-08-03 | [6 empty] | Paul Ditty |  | Paul Ditty | Paul Ditty |  | 2018-09-21 | FS | FALSE | 2018 | 2019-08-01
2245 | 2245 |  | FALSE | VC-UNIV.ADV. | Campus Directory & Blade Signs | Remove and replace campus directories at strategic locations throughout the campus. |  |  | Pending funding source approval | Peter Hayashida | Naysia Caldwell | Margene Mastin-Schepps |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2014-03-27 | Project Approval & Funding | [11 empty] | PD&C | FALSE | 2014 | 2019-08-01
19P000665 |  | 19P000665 | FALSE | PLANNING & BUDGET | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | Existing telephone-communications building on University Ave requires repairs and renovation in preparation for new use as fire safety offices. | TELEPHONE |  | PLAN DEVELOPMENT/CHECK | Gerry Bomotti | Sharyl Murdock | Carmen Long | Melissa Garrety | Dan Lerman |  | 2 |  | FALSE |  |  | 43649 | [8 empty] | Enrico Baez |  |  |  | FS | FALSE | 2019 | 2019-08-01
2970d | 2970d |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan-Phase 4 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Dave Bomba |  |  |  | FALSE | 2842000 |  | 42340 | Award package 1 & 3 | 43709 | 43800 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
2970c | 2970c |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan-Phase 3 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Dave Bomba |  |  |  | FALSE | 2842000 |  | 42340 | Award package 1 & 3 | 43344 | 43800 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
3540 | 3540 |  | FALSE | CAP.PROG. | BCOE Advising Move | Relocation expenses for BCOE advising including: $75k furniture, $10k moving expenses, $3k misc. Renovations were also approved and were completed by Facilities under SLA. Also includes relocation of VCBAS from Skye to Student Services at $1,010 and move expenses for Student Disability from Costo to Student Services at $25k. |  |  | New | Jacqueline Norman | Sharyl Murdock | Sharyl Murdock |  | Sharyl Murdock |  |  |  | FALSE | 111010 |  | 43671 | New | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
3537 | 3537 |  | FALSE | CAP.PROG. | Student Services Bldg Cubicles | Purchase and installation of up to 8 new cubicles on the 2nd and 3rd floors of Student Services building (up to 16 total) to increase occupant capacity. This has been initiated by VC Bomotti. There may also be associated telecom expenses. |  | 3rd Flr | New | Jacqueline Norman | Sharyl Murdock | Sharyl Murdock |  | Sharyl Murdock |  |  |  | FALSE | 90000 |  | 43671 | New | [11 empty] | PD&C | FALSE | 2019 | 2019-08-01
2970a | 2970a |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan-Phase 1 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Dave Bomba |  |  |  | FALSE | 2842000 |  | 42340 | Award package 1 & 3 | 43344 | 43800 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-01
2245 | 2245 |  | FALSE | VC-UNIV.ADV. | Campus Directory & Blade Signs | Remove and replace campus directories at strategic locations throughout the campus. |  |  | Pending funding source approval | Peter Hayashida | Naysia Caldwell | Margene Mastin-Schepps |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2014-03-27 | Project Approval & Funding | [11 empty] | PD&C | FALSE | 2014 | 2019-08-16
2353 | 2353 |  | FALSE | CNAS | Natural Reserves-Sweeney Granite Mountain | This project will add structurally independent facilities for an administration building and researcher housing to provide meeting/office space and short term sleeping quarters. Additionally, the existing laboratory building and staff residence will be extensively renovated. High priority is focused on high insulation values, high wind resistance, rodent proofing, and pursue as much passive cooling and heating as possible with an eye toward low maintenance and high durability. Both new construction and renovation projects are to be sealed to prevent rodent intrusion. The new structures must withstand the harsh environment of extreme temperatures and very high winds. All site improvements shall be done with minimal disturbance to the desert environment. The overarching goal of the project is to provide a sustainable structure that respects its environment and is low maintenance while using best practice design standards. |  |  | In construction | Kathryn Uhrich | Deborah McWilliams | Jim Andre, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2545500 |  | 2015-11-23 | Complete Construction | 2019-01-14 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
2368 | 2368 |  | FALSE | PLANNING & BUDGET | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | Construction 7/15/19 | Gerry Bomotti | Sharyl Murdock | Katie Sanchez |  | Gerald Caraig | 22 |  |  | FALSE | 2600000 |  | 2016-05-19 | Complete Construction | 2019-07-15 | 2019-09-27 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
2508 | 2508 |  | FALSE | BAS | Barn Expansion | Project 950493 Barn has completed the DPP process and we are now adding this to CPMS to capture expenses related to the Program Process which occurred in FY11-12 and FY12-13. Please move all expenditures from A01233-70003-76 Cost Center to JR142 to a plant account. |  |  | In construction | Gerry Bomotti | Georgianne Carlson | Susan Marshburn |  | D.Hecht/J.Franklin | 29 |  |  | FALSE | 28929771.28 |  | 2013-07-05 | Complete Construction | 2018-06-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2013 | 2019-08-16
2671 | 2671 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Elevator Mods-Various Bldgs | Provide Vertical Transportation Consulting, Mechanical, Electrical, Fire Alarm and Architectural/Structural Construction document design and specifications for the modernization of two (2) elevators at Webber and Watkins buildings which is included in the base design and one (1) elevator at the Entomology Museum is included as an add alternate. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 99 |  |  | FALSE | 596011 |  | 2016-01-05 | Award Contract | 2019-09-02 | 2020-08-28 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Rivera Library Arches/Arcade Repair | Paint and replace roof. |  |  | Bids received, award on hold due to DM funding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Jason Espinoza | 99 |  |  | FALSE | 240000 |  | 2016-05-06 | Funding | [11 empty] | PD&C | FALSE | 2016 | 2019-08-16
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Design | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 7 |  |  | FALSE | 600000 |  | 2019-06-18 | Receive revised 100% CD's | 2019-12-02 | 2020-05-29 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. |  |  | In coordination with Mobility Hub | Tamica Smith Jones | Joseph Erbland | Joe Erbland |  | Gerald Caraig | 3 |  |  | FALSE | 0 |  | 2014-04-10 | To be coord. with Rec Mall work | [11 empty] | PD&C | FALSE | 2014 | 2019-08-16
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | In negotiations with selected Architect | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Jason Espinoza | 1 |  |  | FALSE | 350000 |  | 2016-12-15 | Award of the project | 2021-01-01 | 2022-10-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
2747 | 2747 |  | FALSE | PALM DESERT GRAD CTR | Heckmann Ctr-Landscaping (Donor Orchard) | UCR Palm Desert would like to replace the current turf grass with water-wise, sustainable landscaping. In return for the opportunity to use a “living laboratory” classroom for training, UC Cooperative Extension Master Gardener program has agreed to collaborate with UCR to revise and sustain the landscaping. The first phase will be to create an orchard to highlight UCR’s contributions to agricultural research in the Coachella Valley. The orchard will be located at the entrance to the Heckmann building, north of the walkway. UCR Physical Plant/Grounds to provide estimate for: • Project oversight • Project plan and drawings • Organic material to add to soil • Irrigation materials and installation • Edging for path • Weed cloth • Decomposed granite with stabilizer for ground cover • Decomposed granite with stabilizer for pathway • Concrete pad for art including bolting apparatus • Arbor for grapes • Flow system-fertigation • All other labor and materials other than kiosk, plant signage, turf and tree removal (current landscape maintenance vendor can remove) and plant materials and plant installation | HECKMAN ICEM |  | In Programming | Tamara Hedges | Zelda Glenn | Mike Lawrence |  | Scott Donnell | 2 |  |  | FALSE | 13800 |  | 2014-08-18 | Design | [11 empty] | PD&C | FALSE | 2014 | 2019-08-16
2774 | 2774 |  | FALSE | PLANNING & BUDGET | Highlander Hall Demolition | Demolition of the Highlander Hall Building |  |  | Complete Construction | Gerry Bomotti | Sharyl Murdock | Blythe Wilson |  | Scott Donnell | 99 |  |  | FALSE | 2127000 |  | 2015-01-22 | Complete Construction | 2018-08-01 | 2019-09-01 | [8 empty] | 2017-08-15 | PD&C | FALSE | 2015 | 2019-08-16
2805 | 2805 |  | FALSE | FAC-PLNG-DESIGN-CONST | West Campus Water Well | Drill a water well on AGOPS property. This will be funded out of Energy Savings and Minor Cap Approval has been signed. |  |  | In Programming | Susan Marshburn | Da Lan Dinh | Ken Muelleer |  | Scott Donnell | 99 |  |  | FALSE | 250000 |  |  | CEQA | 2020-09-01 | 2020-11-01 | [9 empty] | PD&C | FALSE | 1900 | 2019-08-16
2829 | 2829 |  | FALSE | VC-STU.AFF. | SRC South - New Storage Building | New storage building immediately south of SRC South Pool Building; approximately 20' x 40'; one roll up door and one standard door; electrical power required - number of outlets to be defined in design; concrete walkway and door pads required; non-potable water may be required if quick couplers are not available in nearby landscaping; please see attachment for location: approximately at gridlines T and 9.4 - dotted outline of building is labeled "FUTURE STORAGE" - located immediately south of the SRC POOL EQUIPMENT BUILDING. | SRC SOUTH |  | Coordinate with MRB & Mobility Hub Logistics | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Mihai Gavan | 5 |  |  | FALSE | 0 |  | 2015-01-23 | Coordinate with MRB Logistics | [11 empty] | PD&C | FALSE | 2015 | 2019-08-16
2839 | 2839 |  | FALSE | PLANNING & BUDGET | Multidisciplinary Research Building | External financing provided for this project. Total approved budget is $150,000,000. Confirmed per CPMX and BEA#978864 Xfer Tax Exemp Comm Paper. Funding received 7/25/2016. |  |  | Coordinating 2nd Phase Move-in & Related TI's | Gerry Bomotti | Sharyl Murdock | Jon Harvey |  | Mihai Gavan | 19 |  |  | FALSE | 156405000 |  | 2015-04-01 | 2nd Phse Move/TI | 2016-07-01 | 2018-09-28 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
2868 | 2868 |  | FALSE | BAS | West Lothian Elevator Renovation |  |  |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 18 |  |  | FALSE | 365000 |  | 2015-04-08 | Complete Construction | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
2899 | 2899 |  | FALSE | PLANNING & BUDGET | Pierce Hall Improvements | Replacement of Mechanical, Plumbing and Electrical Infrastructure | PIERCE |  | In Construction | Gerry Bomotti | Sharyl Murdock | Jon Harvey |  | Dave Bomba | 21 |  |  | FALSE | 38560000 |  | 2015-08-06 | Fire Sprinkler Installation | 2019-01-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
2900 | 2900 |  | FALSE | PLANNING & BUDGET | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | BATCHELOR |  | In Design | Gerry Bomotti | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 17 |  |  | FALSE | 18179000 |  | 2015-12-15 | Contractor Review of Building | 2020-01-01 | 2021-11-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
2916 | 2916 |  | FALSE | CAP.PROG. | Solar Greenhouse | Construction of a solar powered greenhouse. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Matt Barth |  | Scott Donnell | 4 |  |  | FALSE | 194000 |  | 2015-08-04 | Complete Construction | 2019-07-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
2952 | 2952 |  | FALSE | CAP.PROG. | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jon Harvey |  | Dave Bomba | 22 |  |  | FALSE | 23547000 |  | 2015-09-11 | Completion of phase one 3/15/20 | 2019-01-02 | 2021-06-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
2974 | 2974 |  | FALSE | SOM | SOM Research Building - 1st Floor Fit-Out | Buildout the 1st Floor of School of Medicine Research Building, a space of approximately 17,600 square feet. The construction includes wet laboratories, laboratory support spaces, offices and related support space. Work consists of, but not limited to the following: demolition of existing improvements, addition/alterations of walls, installation of new fume hoods, sinks, safety showers and eyewash stations, alterations/additions to the mechanical, electrical, plumbing, fire life safety, fire suppression, telecommunication and audio/video systems, as specified in the Construction Documents. |  |  | Completing Close-out. | Deborah Deas | Brandon Barbosa | Blythe Wilson |  | Mihai Gavan | 99 |  |  | FALSE | 9600000 |  | 2015-10-30 | Final Completion / NOC | 2017-10-01 | 2018-10-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
3005 | 3005 |  | FALSE | CAP.PROG. | Batchelor Hall Interior Improvements | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | BATCHELOR |  | In Design | Jacqueline Norman | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 17 |  |  | FALSE | 8837000 |  | 2016-02-02 | CM at Risk Selection | 2020-01-01 | 2021-11-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
3052 | 3052 |  | FALSE | SOM | SOM Trailer Expansion | Replace the (2) modular units with one 96' x 60' building and provide access from the SOM-ED building via concrete ramp; Re-vamp the entire site for accessibility. Signed Major Cap Approval for $150k augmentation received 10/25/17 - total project $2,250,000. |  |  | Completing Change Orders | Deborah Deas | Brandon Barbosa | Sharyl Murdock |  | Dave Bomba | 99 |  |  | FALSE | 2250000 |  | 2016-03-07 | Complete Change Orders | 2017-08-01 | 2018-02-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
3060 | 3060 |  | FALSE | CHASS | CHASS Intl N. - Paint 3rd Floor | Paint and patch the following CHASS INTN rooms to existing color: 3036 3038 3042 3046 3050 3049 3047 3033 3033B 3025 3021 3019 3015 3013 3011 3002 3008 3012 3014 3016 3018 3020 3022 Hallway outside of 3033 Hallway to main entrance to floor Hallway outside 3005 | CHASS INT N |  | Project on Hold | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 4 |  |  | FALSE | 0 |  | 2016-05-20 | On Hold | [11 empty] | PD&C | FALSE | 2016 | 2019-08-16
3064 | 3064 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Botanic Gardens Basin Silt Removal | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | BOTAN INFO C |  | On hold | Susan Marshburn | Da Lan Dinh | Toshio Ishida |  | Dave Bomba | 43 |  |  | FALSE | 110000 |  | 2016-04-20 | Funding | [11 empty] | PD&C | FALSE | 2016 | 2019-08-16
3104 | 3104 |  | FALSE | PALM DESERT GRAD CTR | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Programming | Tamara Hedges | Zelda Glenn | Zelda Glenn |  | Scott Donnell | 1 |  |  | FALSE | 22000 |  | 2016-05-12 | Funding | [11 empty] | PD&C | FALSE | 2016 | 2019-08-16
3110 | 3110 |  | FALSE | PLANNING & BUDGET | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded/never routed to the Dispatcher. 90% CD's completed. | Gerry Bomotti | Sharyl Murdock | Marianne Valenti |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | License Agreement Final Review | 2019-09-01 | 2020-07-01 | [9 empty] | PD&C | FALSE | 1900 | 2019-08-16
3119 | 3119 |  | FALSE | CAP.PROG. | Plant Growth Environment Facility | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 9 |  |  | FALSE | 25000000 |  | 2016-05-25 | Site utilities & ret. Wall | 2019-04-01 | 2020-08-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
3120 | 3120 |  | FALSE | CAP.PROG. | Arts Walk Sculpture (Ext Campus Art Project) | Sculpture design concept - hiring a consultant to revise an artist design concept for a proposed outdoor art piece to be placed between the Arts building and the CHASS Interdisciplinary buildings. |  |  | Corretive action response due to defective finishes. | Jacqueline Norman | Sharyl Murdock | Uma Ramasubramanian |  | Jason Espinoza | 8 |  |  | FALSE | 1096000 |  | 2016-05-26 | Complete Construction | 2019-02-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
3175 | 3175 |  | FALSE | CAP.PROG. | DM16-Chilled Water Coils Multiple Buildings | Replace multiple leaking/degraded cooling coils across campus to prevent complete shutdown of building air handlers during the hot summer months. Buildings include: Student Services, Chemical Sciences, Genomics, Psychology, Entomology and MSE. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Melissa Garrety |  | Scott Donnell | 99 |  |  | FALSE | 1294648 |  | 2016-10-11 | Complete Construction | 2019-01-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
3195 | 3195 |  | FALSE | PLANNING & BUDGET | North District Development, Phase-1 | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Gerry Bomotti | Sharyl Murdock | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 3886110.55 |  | 2016-10-26 | Complete Construction | 2019-07-01 | 2021-08-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
3203 | 3203 |  | FALSE | BAS | Plaza Structural Seismic Study | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. |  |  | Site Inspection of C, E & F and conceptual planning review | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 22 |  |  | FALSE |  |  | 2016-10-10 | Design development | [11 empty] | PD&C | FALSE | 2016 | 2019-08-16
3218 | 3218 |  | FALSE | CNAS | Ag Ops - Demo Structures | Demolition of 15 structures, including hazardous materials cleanup, electrical reconnection of services as needed, UST removal as needed, relocation of ATT riser. |  |  | In Close-out | Kathryn Uhrich | Deborah McWilliams | Deborah McWilliams |  | Scott Donnell | 99 |  |  | FALSE | 316739 |  | 2016-10-19 | Complete Close-out | 2015-11-01 | 2019-07-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
3228 | 3228 |  | FALSE | CNAS | Retrofit Screenhouse to Greenhouse | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. Location can be discussed with Greg Greer | RUBIDOUX SCR |  | In Design | Kathryn Uhrich | Deborah McWilliams | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 1080000 |  | 2016-12-06 | Bidding | 2019-12-01 | 2020-03-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
3233 | 3233 |  | FALSE | CAP.PROG. | Mobility HUB Central Campus Linkages | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Gerald Caraig | 3 |  |  | FALSE | 16011000 |  | 2016-12-16 | Leadership Direction | [11 empty] | PD&C | FALSE | 2016 | 2019-08-16
3234 | 3234 |  | FALSE | CAP.PROG. | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Close-out | Jacqueline Norman | Sharyl Murdock | John White |  | Fernando Nunez | 6 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete Punchlist & Close Out | 2018-11-05 | 2019-03-29 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
3237 | 3237 |  | FALSE | SoB | Anderson Hall N. Access Imp. | ADA handrails installation at walkway and ramp on the East sidewalk by the bench of Anderson north, down the steep ramp leading to Anderson South. We have been working with Shelly Frohrip from HR and Mary-Alice Avila of A&E on this so they will have some information regarding the purpose. 11/15/17 The handicapped parking and POT are now included. Project approved, waiting for funding. | ANDERSON 1 (N) |  | In design | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 3 |  |  | FALSE | 150000 |  | 2016-12-19 | Re-bid | 2019-10-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
3270 | 3270 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Chapman Hall - Replace HVAC System | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | CHAPMAN |  | In Funding | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Scott Donnell | 11 |  |  | FALSE | 595819 |  | 2017-03-07 | Bidding | 2019-10-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3271 | 3271 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Life Sci/Spieth Hall Elevator Renewal | Scope of work includes the number 3 and 4 elevators of Spieth Hall. Project budget is $344,898.00. Estimated construction cost is $250,400.00. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 12 |  |  | FALSE | 345000 |  | 2017-03-07 | Award Contract | 2019-09-02 | 2020-08-28 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3272 | 3272 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Athletic/Dance Elevator Renewal | Project budget is $219,371.00. Estimated construction cost is $169,020.00. | ATH DANCE |  | Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 13 |  |  | FALSE | 220000 |  | 2017-03-07 | Award Contract | 2019-09-02 | 2020-08-28 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3275 | 3275 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Fiber Optic Infrastructure Upgrade | Repair, replace and upgrade the fiber optic infrastructure network that includes 50+ buildings across campus. Also includes work to main hubs, sub hubs and make available spare fiber for future utilization. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | ----- |  | Daneca Stevens | 9 |  |  | FALSE | 643750 |  | 2017-04-12 | Award Contract | 2019-11-01 | 2020-04-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On-hold/Funding | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [11 empty] | PD&C | FALSE | 2017 | 2019-08-16
3286 | 3286 |  | FALSE | BAS | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | Awarded contract | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 36 |  |  | FALSE | 2985000 |  | 2017-03-29 | Construction | 2019-07-01 | 2019-11-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3293 | 3293 |  | FALSE | CAP.PROG. | USDA Head House - Public Restroom | Provide an accessible public restroom facility in or adjacent to the USDA Head House Building in Ag Ops. Restroom will serve individuals and groups touring the UCR and USDA Citrus Facilities. Three options have been proposed, and need to be considered and evaluated to recommend a feasible solution for USDA. The work would be managed and paid by USDA, including the design, bidding and construction. UCR staff needs to review the proposed plans and specifications per the agreement with USDA, and provide the review, inspection and approvals. The USDA representative is Marylou Polek. | GERMPLASM |  | Pending Lease | Jacqueline Norman | Sharyl Murdock | Mary Lou Polek |  | Scott Donnell | 14 |  |  | FALSE | 0 |  | 2017-05-22 | USDA Scope & Design | [11 empty] | PD&C | FALSE | 2017 | 2019-08-16
3300 | 3300 |  | FALSE | BCOE | R'Garden - Solar Installation | Electrician to do the following wiring of our solar panels and inverters out at the R’Garden at UCR. The H model cyboinverter to be used powers the lower heating element of the water heater. The thermostat of the lower heating element must then be set to be higher than the upper heating element. The two output lines are to be connected to an AC switch or switchable AC outlet and the lower element water heater. |  |  | Work to be inspected by A&E. | Christopher Lynch | Maggie Souder | Arvin Tam |  | Scott Donnell | 3 |  |  | FALSE | 0 |  | 2017-05-03 | Relocation | [11 empty] | PD&C | FALSE | 2017 | 2019-08-16
3319 | 3319 |  | FALSE | CAP.PROG. | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Design Build competition | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Mihai Gavan | 16 |  |  | FALSE | 3607000 |  | 2017-06-01 | Execute Contract | 2019-12-01 | 2021-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | Funding | Michael Pazzani | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Daneca Stevens | 1 |  |  | FALSE | 45000 |  | 2017-06-13 | Secure Funding | 2020-03-01 | 2020-04-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3345 | 3345 |  | FALSE | SoB | Anderson N & S - Landscaping | DESIGN SVC & LANDSCAPE Construction request as follows for updated CURB APPEAL of Anderson North/South: 1. Roses Garden in middle of Stair landing/court to be removed and replaced with Grass 2. Add Large Planters (Metal or Cement) with Citrus Trees (either Kumquat/Lemon/Orange/Etc) on ledges that are at top section of front steps to deter skateboarders from jumping off of these ledges. 3. Remove dead trees on North and south ends of front lawn 4. Remove plants around granite sign in front lawn and replace with grass 5. Remove flowers and grass at both corners of front lawn around Citrus Trees and replace with DG and low growing flowering plants. 6. Pull all Ivy and crown vetch and add Pavers to East/Back side of Anderson Hall within landscaped/planter areas where ADA walkway runs and replace with nice picnic tables to include umbrellas and/or lounge seating around Anderson North for students. 7. Add DG in all areas where space is open/available surrounding outdoor seating area in back of building. 7. Remove all hedges surrounding alcove/arched areas along buildings. |  |  | On hold until ADA path of travel is completed | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 4 |  |  | FALSE | 0 |  | 2017-07-18 | Completion of 3237 | [11 empty] | PD&C | FALSE | 2017 | 2019-08-16
3354 | 3354 |  | FALSE | BAS | Lot 4/Barn Area ADA Improvements | Lot 4/Barn Area ADA Improvements - The proposed project will relocate an existing crosswalk that is not ADA compliant and provide path of travel improvements and additional ADA parking capacity in Parking Lot 4. The existing crosswalk located at West Campus Drive and Parking Lot 4 (north) was identified in the Draft ADA Transition Plan to be out of compliance. A Pedestrian Safety Study by Fehr & Peers completed in June 2008 identified the relocation of this crosswalk to approximately 100 feet east to provide a more visible, safe, pedestrian crossing. To increase pedestrian safety further, the crosswalk will be designed as a speed table. Additionally, Transportation and Parking Services proposes to create additional ADA parking spaces in Parking Lot 4 that exceed the required number, with hardscape and path of travel improvements that will connect to the new crosswalk. The improved crosswalk will correct required path of travel deficiencies from a parking lot that provides access to numerous publicly accessible buildings, as well as allow the Barn Expansion project to obtain Division of State Architect (DSA) approval once construction is completed. The funds to complete the crosswalk replacement will be requested from Campus ADA funds. Parking Lot 4 improvements will come from will come from TAPS. Although this project supports the Barn Renovation, its conception and need is not tied to the Barn project. The crosswalk improvements and additional ADA parking is needed to meet our ADA parking requirements and serve the growing demand on campus. This project is desired regardless of the Barn Renovation project. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | John Franklin | 5 |  |  | FALSE | 50000 |  | 2017-08-15 | Bidding | 2019-09-01 | 2019-11-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3366 | 3366 |  | FALSE | CAP.PROG. | Genomics Ramps | Genomics Accessibility Improvements - The proposed project will create an accessible sidewalk connection from the Genomics Building to the University Lab and University Office Building. Currently, there is no accessible north sidewalk linkage east of the Genomics Building. The project will demolish and replace approximately 300 square feet of asphalt to bring it up to grade. Two ADA ramps will be added to sidewalk extensions of approximately 300 square feet that connect across a driveway. Existing landscaping and irrigation will be removed and replaced. No trees will be impacted by this work. |  |  | In Funding | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Gerald Caraig | 19 |  |  | FALSE | 42000 |  | 2017-11-16 | Secure Funding | [11 empty] | PD&C | FALSE | 2017 | 2019-08-16
3367 | 3367 |  | FALSE | CNAS | Field 16 Greenhouse Demo & Replacement | Replace GH1 and GH2 with a greenhouse from the Greenhouse Megastore. Conduct geotechnical investigation, prepare drawings and conduct asbestos and lead sampling. |  |  | In Construction | Kathryn Uhrich | Deborah McWilliams | Sue Lee, D. McWilliams |  | Dave Bomba | 1 |  |  | FALSE | 359000 |  | 2017-09-15 | Complete Close-out | 2019-01-30 | 2019-07-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3376 | 3376 |  | FALSE | BAS | West Lothian Roof Replacement Design | Provide Schematic Design, Design Development and professional cost estimate to replace the existing single-ply membrane roof system on the Lothian West residence hall wings plus Common Area applications. Existing roofing is past its useful life and starting to experience multiple leaks that are damaging living spaces below. Design effort should select the most appropriate roof material for this roof plan. The intent is to design this year (alongside the Lothian East design) and construct immediately following the Lothian East roof replacement. | LOTHIAN HALL |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 7 |  |  | FALSE | 0 |  | 2017-09-28 | Complete Construction | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3382 | 3382 |  | FALSE | BAS | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 17 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2021 | [11 empty] | PD&C | FALSE | 2017 | 2019-08-16
3383 | 3383 |  | FALSE | BAS | W Lothian Air Handler Replacemt | Existing air handler equipment in West Lothian is original to the building and past its service life. Provide HVAC professional services to develop options for Air Handler replacement that meet UC Carbon Neutral 2025 goal. Each option analysis should include pros and cons for energy consumption, reliability, serviceability and system installation cost projections. At least one option should explore potential conversion to individual package units as practical. | LOTHIAN HALL |  | Complete Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 8 |  |  | FALSE | 883000 |  | 2017-10-03 | Complete Construction | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3385 | 3385 |  | FALSE | VC-STU.AFF. | SRC North Gym Replace Interior Lights | Replace old technology sodium vapor light fixtures in SRC North Gymnasium with new technology LED light fixtures. Some flexibility available in the schedule. Selected vendor will need to phase work to minimize the effect on SRC operations and programming. | SRC NORTH |  | In Construction | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Fernando Nunez | 3 |  |  | FALSE | 396000 |  | 2017-10-31 | Complete Construction | 2019-06-24 | 2019-08-30 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Design | Kathryn Uhrich | Deborah McWilliams | Tracey Kahn, D. McWilliams |  | Scott Donnell | 2 |  |  | FALSE | 340000 |  | 2018-01-08 | Bidding | 2019-12-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3392 | 3392 |  | FALSE | BAS | Bicycle Master Plan Study | Bicycle Master Plan Study. This CPMS project is for the funding and creation of a Bicycle Master Plan Study for the UCR Campus. It is not for a specific capital project. |  |  | Pre-Programming | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Melissa Garrety | 19 |  |  | FALSE | 115000 |  | 2017-11-13 | Funding | [11 empty] | PD&C | FALSE | 2017 | 2019-08-16
3393 | 3393 |  | FALSE | CAP.PROG. | South Neighborhood Dist. Study | South Neighborhood District Study per discussions with the Provost/VCPB, July 2017. The South District Planning Study needs to provide guidance for future development in the South District that is inclusive of: **University aspirations to develop the South District to define the campus’ presence along the adjacent freeway (CA-60/215). **Development capacity, optimal building heights and conceptual massing presented both in metrics and a three dimensional format. **Broad parking strategy to meet the needs of the district in alignment with the campus’ overall parking management strategy and alternative transportation solutions. **High level understanding of infrastructure needs (electrical, domestic, fire and storm water, sanitary sewer, building heating and cooling) to meet the needs of the campus’ desired development capacity for district. **Pedestrian and vehicular connectivity. **East and South Campus Drive improvements |  |  | In Close-out | Jacqueline Norman | Sharyl Murdock | Uma Ramasubramanian |  | Fernando Nunez | 18 |  |  | FALSE | 309000 |  | 2017-11-15 | Follow Up on Study Reports | [11 empty] | PD&C | FALSE | 2017 | 2019-08-16
3395 | 3395 |  | FALSE | CAP.PROG. | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | Third party cost estimator needed | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 23 |  |  | FALSE | 0 |  | 2017-12-03 | On Hold | [11 empty] | PD&C | FALSE | 2017 | 2019-08-16
3396 | 3396 |  | FALSE | ITS | C&C Rear Patio Tables/Shade | Installation of new exterior concrete slab and patio cover at the Computing and Communications Modular Buildings. The existing site will be cleared of all landscape to provide clear area to install concrete slab and address any grade/drainage issues. The addition of a proposed permanent patio cover is to be installed with full electrical options (lights, outlets, ceiling fans) to provide shade for future events and exterior lunch area. Shrubs along the street at the East side of the area are to be removed to provide a vendor/service ramp for events with the inclusion of lighted concrete seating within the space. | ITS CENTER |  | In Programming | Danna Gianforte | Shelley Gupta | Sheila Mabee |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2017-11-16 | Complete Project Study | [11 empty] | PD&C | FALSE | 2017 | 2019-08-16
3397 | 3397 |  | FALSE | BAS | Dundee Residence Hall and Glasgow Dining | (Lot 22/Dundee-Glasgow) A newly proposed student housing development, including a single phase 760-bed residence hall and an 830-seat dining facility located on the existing Parking Lot 22 site south of Linden Street. The project is anticipated to be completed by Fall/Winter 2020. Funding for predevelopment activities including CEQA and staff augmentation to be determined. | ABER INVER |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Thomas Toepfer | 21 |  |  | FALSE | 1120000 |  | 2017-11-21 | Complete Construction | 2019-01-01 | 2020-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3401 | 3401 |  | FALSE | CAP.PROG. | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | Completing project budget and working on project approvals. | Jacqueline Norman | Sharyl Murdock | Mihai Gavan |  | Mihai Gavan | 21 |  |  | FALSE | 1530020 |  | 2017-12-03 | Budget and project approval | 2019-11-01 | 2020-09-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-08-16
3403 | 3403 |  | FALSE | BAS | Parking Lot 23 Addition | Parking Lot 23 Expansion - The goal of the project is to add additional parking capacity to Parking Lot 23 to serve that area of the campus. Current parking capacity in this area will be impacted by the closures of Lot 22 and Crest Housing parking area. Additional capacity will be need for employee parking. |  |  | On Hold | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Daneca Stevens | 3 |  |  | FALSE | 92000 |  | 2018-05-17 | Funding | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | In Programming | Tamica Smith Jones | Joseph Erbland | Johnathan Jensen |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2018-08-23 | Create SOW | 2020-03-02 | 2020-06-26 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3408 | 3408 |  | FALSE | ATHLETICS | Harrison Field Netting | Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | SOFTBALL STG |  | Per department: Project is on hold until further notice. | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2018-01-23 | OnHold by Cust Til Furthr Notice | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3411 | 3411 |  | FALSE | BAS | MRB Café Buildout & MS&E Loading Dock Mods | MRB1 CAFE and SERVICE YARD INTERIOR FIT-OUT: provide design and construction services to build out the interior of the MRB1 Café shell and modify the MS&E Service Yard to accommodate the café deliveries and trash movement. This CPMS Request is to combine and replace previously approved CPMS #3378 and #3398 into one project as requested by A&E. Please note that the IRT Job walk has already been completed. Intent is to design in FY'17/18 and construct in FY '18/19. Opening to coincide with the MRB1 facility turnover. Food service equipment will be Owner Furnished on a separate UCR Purchase Order. Note that the MRB1 Café shell construction is provided by the separately funded MRB1 project, construction drawings for this shell space are attached in CPMS. | MAT SCI ENGR |  | In Close-out | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Mihai Gavan | 26 |  |  | FALSE | 793000 |  | 2018-02-05 | Complete Close-out | 2018-11-19 | 2019-05-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3413 | 3413 |  | FALSE | LIBR | Rivera Libr Gender Incl Restroom | Convert existing non-ADA multi-stall women's restroom to compliant ADA gender inclusive restroom. The project also involves the conversion of an existing non-ADA men's restroom to women's compliant ADA restroom. | RIVERA LIB |  | In Design | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Dave Bomba | 3 |  |  | FALSE | 0 |  | 2018-03-26 | Design Proposal | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3415 | 3415 |  | FALSE | SoB | Anderson South Renovation | Per the sketched drawings that Dave Bomba was provided, please provide a proposal of what it would take to renovate Anderson South as follows: **1. Remove 1st Fl South side of Corridor wall and doors between 102 suite entrance and 106 suite entrance as well as adjoining walls within 102C. **2. Create a closet/wall, ideally, behind the existing door of the 102 Entrance running to the wall shared by 102A to include the best location for a door. Essentially, enclosing the window of 102, if possible. **3. Creating a closet under the stairwell between 1st floor and basement level, having entrance door flush with the bottom step of the stairwell. **4. Remove the West wall and door framing of room 001A, leaving an open look and no corridor in suite 001. | ANDERSON 2 (S) |  | Funding | Yunzeng Wang | Angela Chang | Laurie Gustafson |  | Dave Bomba | 2 |  |  | FALSE | 24700 |  | 2018-02-26 | Department funding | 2019-08-01 | 2019-10-30 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3421 | 3421 |  | FALSE | BAS | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 31 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3426 | 3426 |  | FALSE | BAS | Lothian Boiler Replacement | The boiler equipment at Lothian is original to the building and past its useful life. Design, procure and install a replacement boiler that incorporates the latest energy saving and management technology that can be cost-effectively installed as a direct replacement to the existing unit. | LOTHIAN HALL |  | On hold | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 32 |  |  | FALSE | 0 |  | 2018-03-19 | On hold | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Construction | Christopher Lynch | Maggie Souder | Margaret Souder |  | Dave Bomba | 2 |  |  | FALSE | 700000 |  | 2018-04-04 | Complete Construction | 2019-07-01 | 2019-09-18 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3430 | 3430 |  | FALSE | BAS | TAPS Cust Svc Lobby Upgrades | Upgrades to Customer Service Lobby – Need to complete Tenant Improvement project upgrade customer service counter in Parking Services Building. Want to replace current counter to allow for; modern computer equipment, dividers between customers’ transaction spaces, under counter space for filing cabinets and check writing space. Please coordinate with Auxiliaries’ primary PM John Franklin. | PARKING SERV |  | On hold until Summer 2019 | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Dave Bomba | 4 |  |  | FALSE | 0 |  | 2018-05-17 | Customer Approval | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3437 | 3437 |  | FALSE | FAC-PLNG-DESIGN-CONST | UCPD Generator Replacement | Replace unsupported 125kw generator with new - Critical Facility |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Fernando Nunez | 10 |  |  | FALSE | 300000 |  | 2018-10-08 | Complete Construction | 2019-07-01 | 2019-12-27 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3438 | 3438 |  | FALSE | CAP.PROG. | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | City to determine schedule | Jacqueline Norman | Sharyl Murdock | Dave Bomba |  | Dave Bomba | 24 |  |  | FALSE | 0 |  | 2018-08-22 | City to determine schedule | 2020-01-01 | 2020-09-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3441 | 3441 |  | FALSE | CHASS | INTS 1121 Convert Classroom to Dance Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use |  |  | In Funding | Milagros Pena | Cindy Williams | Anna Finn |  | Daneca Stevens | 14 |  |  | FALSE | 0 |  | 2018-06-22 | Design | 2020-01-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3452 | 3452 |  | FALSE | CAP.PROG. | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 15 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Programming | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3453 | 3453 |  | FALSE | BAS | ECS N&S Playground Shade & Turf | Provide Schematic Design, Design Development and Professional Cost Estimate for the alteration of existing shade structures, provision for additional shade structures, refinish interior metal fencing, and the replacement of existing grass with synthetic turf at the Early Childhood Services north and south playground areas. Prepare drawings so that they can be bid and constructed as separate projects. |  |  | Dept approval/funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 10 |  |  | FALSE | 0 |  | 2018-07-03 | Dept approval/funding | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3458 | 3458 |  | FALSE | CAP.PROG. | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | PM to update schedule | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 20 |  |  | FALSE | 0 |  | 2018-07-16 | PM to update schedule | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3459 | 3459 |  | FALSE | BAS | A-I Hardscape Landscape Design-Study | Provide Schematic Design and Design Development drawings for a selective renovation of all hardscape and landscape around the perimeter of the Aberdeen-Inverness housing complex. Scope to include (but not limited to) widening of South Walk and replace its asphalt with concrete pavers, upgrade hardscape and landscape at Horseshoe, replace selected lawn areas with hardscape, seating and solar umbrellas at east and west lawns of Building E, consider new bike storage along South Walk, consider modifying slopped lawn between Building A and Linden St., generally reduce lawn areas and replace with sustainable planting, prune or replace unkempt trees, replace selected light fixtures to match Dundee fixtures, and generally freshen the landscaping so that it is harmonious with the new Dundee development. Design to be packaged in phases, with the South Walk and Dundee-facing landscape to be ready in Phase 1 for construction timing alongside Dundee-Glasgow landscaping in Spring of 2020. | ABER INVER |  | Architect design meetings scheduled. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 11 |  |  | FALSE | 160000 |  | 2018-07-16 | Complete Design | 2020-02-01 | 2020-09-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3460 | 3460 |  | FALSE | BAS | A-I Restroom Replacement - Reconfig | Provide Schematic Design and Design Development drawings for the complete replacement of the restrooms in all four resident hall wings. Existing restroom fixtures and finishes are largely original to the building and long past their service life, causing serious leaks between floors. New restrooms will be reconfigured to meet current accessibility code. Documents to be assembled for phased construction, one wing per summer, with the first building (D-Wing) to be constructed in Summer 2019. | ABER INVER |  | Project on hold until summer 2020 | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 14 |  |  | FALSE | 2782000 |  | 2018-07-19 | Bidding | 2020-06-01 | 2020-08-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3462 | 3462 |  | FALSE | BAS | A-I Restaurant & Lobby Reconfiguration | Provide Schematic Design and Design Development drawings for the complete reconfiguration of Building C including kitchen, dining space, and common areas. The restaurant and kitchen areas are largely original to the building and well past their useful life. The new, replacement, Glasgow restaurant coming on-line in Fall 2020 will allow a needed reprogramming and modernization of this space. Preliminary Program for this space includes a smaller Catering Kitchen, Meeting Rooms, new KUCR studio as well as a modernization and upgrade of the Lobby and other Common Areas. Documents to be assembled for a Fall 2020 construction start. | ABER INVER |  | Project currently on hold pending approval | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 12 |  |  | FALSE | 545000 |  | 2018-07-17 | Complete Design | 2020-06-01 | 2021-06-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3463 | 3463 |  | FALSE | BAS | Landscape Strategic Plan for Housing Services | Provide a comprehensive study of existing landscape areas within Auxiliary Services and provide specific and actionable recommendations for their conversion to sustainable landscaping by location. Study to include all Resident Hall and Apartment properties and include conceptual cost estimates, by location, for proposed landscape conversions. |  |  | Project on-hold | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 13 |  |  | FALSE | 0 |  | 2018-07-17 | On hold per Auxiliary Services | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3466 | 3466 |  | FALSE | BAS | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Assessment draft report submitted, finalizing details for complete report. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 16 |  |  | FALSE | 0 |  | 2018-07-31 | Design Review | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3467 | 3467 |  | FALSE | BAS | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | PSA issued, coordinating site inspections. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 15 |  |  | FALSE | 50000 |  | 2018-07-31 | Site Inspections | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3469 | 3469 |  | FALSE | CHASS | Carillon Repair & Maintenance | Design, fabrication and replacement of bell beams for bells 24, 26, 28, 30 and 32. Design, fabrication and installation of bracing to brace the 5 other bells beams that are cracking, and corrective maintenance on the clappers & head pieces-this would include complete removal, cleaning, reaming, bushing and lubricating before re-installing and clean and lubricate the transmission system as much as possible without complete disassembly to make the instrument easier to play. | BELLTOWER |  | Need to secure funding | Milagros Pena | Cindy Williams | Reasey Heang |  | Daneca Stevens | 5 |  |  | FALSE | 10000 |  | 2018-08-16 | Secure Funding | 2019-09-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3470 | 3470 |  | FALSE | PLANNING & BUDGET | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | New Study | Gerry Bomotti | Sharyl Murdock | Drew Hecht |  | Drew Hecht | 23 |  |  | FALSE |  |  | 2018-11-06 | Complete Review | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3471 | 3471 |  | FALSE | VC-STU.AFF. | HUB Electrical Sub-Meter Study | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Circuit Tracing of the designated spaces | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Gerald Caraig | 1 |  |  | FALSE | 50000 |  | 2018-08-20 | Circuit Tracing | 2019-12-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3472 | 3472 |  | FALSE | BAS | Lot 20 Trash Enclosure Relocation | Construct a new CMU trash enclosure with water and power in a different location of Lot 21 to replace the existing enclosure that will be demolished to make way for the Dundee Residence Hall construction. Include hose bib for cleaning and power for future compactor installation. New enclosure needs to be on line BEFORE site construction can start on Dundee-Glasgow in January 2019. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 20 |  |  | FALSE | 0 |  | 2018-08-15 | Award Contract | 2019-09-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3474 | 3474 |  | FALSE | PLANNING & BUDGET | RUSD STEM High School |  |  |  | Real Estate project | Gerry Bomotti | Sharyl Murdock | ----- |  | Thomas Toepfer | 16 |  |  | FALSE | 0 |  | 2018-10-31 | Regents Approval of Ground Lease | 2020-07-01 | 2022-06-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 8 |  |  | FALSE | 1250000 | 0 | 2018-10-17 | FS Direction | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. |  |  | Client approval/funding | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 2018-11-27 | Client approval/funding | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3484 | 3484 |  | FALSE | PLANNING & BUDGET | 266 Frost Ct Main House Demolition | Develop project budget and timeline, obtain funding from VCPB. Coordinate disconnection of all utilities: Electrical, Gas, and Water. Disconnect and cap sewer Coordinate HAZ Mat testing and report for asbestos and lead Hire abatement contractor (if necessary) to remove haz materials. Hire demolition contractor to demolish and dispose of existing house, garage and out buildings. Foundations to remain – but make safe and remove potential hazards (rebar, bolts, etc.) protruding from foundation. Paving, pavers and other “patio” slabs to remain – make safe by removing tripping hazards. Identify any hazards (I.E.; unstable retaining walls, debris piles, etc.) and make safe and secure or remove if more cost effective. |  |  | Close-out | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Daneca Stevens | 18 |  |  | FALSE | 72000 |  | 2018-11-15 | Complete Project close-out | 2019-05-01 | 2019-06-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3486 | 3486 |  | FALSE | VC-STU.AFF. | HUB 353/381, Costo 111 Add'l Wall/Doorway | Please evaluate additional wall/door way requests for HUB 353/381 and Costo Hall 111. | HUB |  | Client Approval/Funding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 2 |  |  | FALSE | 0 |  | 2018-11-26 | Secure Funding | [11 empty] | PD&C | FALSE | 2018 | 2019-08-16
3490 | 3490 |  | FALSE | BAS | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Dave Bomba | 24 |  |  | FALSE | 1696000 |  | 2018-12-06 | Selection of Design Build Team | 2019-12-01 | 2021-02-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
3492 | 3492 |  | FALSE | PLANNING & BUDGET | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Study in process | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 11 |  |  | FALSE | 65000 |  | 2019-03-04 | Complete Study | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3498 | 3498 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY18) Manhole C6 Modification | Construct new sanitary sewer lines, New manhole, pipe connections, demo existing manhole. |  |  | In Bidding | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Gerald Caraig | 2 |  |  | FALSE | 220200 |  | 2019-02-25 | Award Contract | 2019-08-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3499 | 3499 |  | FALSE | PLANNING & BUDGET | Creekside Terrace Analysis | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Design | Gerry Bomotti | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 12 |  |  | FALSE |  |  | 2019-02-14 | CEQA | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3501 | 3501 |  | FALSE | PLANNING & BUDGET | DMFI(17-19) Watkins 1000 Lecture Hall Reno | Renovation of Watkins 1000 lecture hall, to include lighting, HVAC, flooring, paint, and seating upgrades. This requests appears as projects Q-T on the approved 2017-2019 DMFI Program list. |  |  | In Bidding | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 8 |  |  | FALSE | 638000 |  | 2019-03-04 | Award Contract | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3503 | 3503 |  | FALSE | BAS | Falkirk Stair/Front Porch Repair | Repair or replace four sets of entry stairs and landings that are long past their service life and are a life safety concern. Consider replacing these wood structures with steel to ease future maintenance. Apartments affected are #3RS, #11MN, #15A and #16FG. |  |  | In Bidding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 25 |  |  | FALSE | 165000 |  | 2019-02-01 | Complete Construction | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3504 | 3504 |  | FALSE | PLANNING & BUDGET | Silver Oaks Womens Health TI Fees | UCR Health will be acquiring new off-campus leased space by expanding into an adjacent medical office suite located at 19330 Jesse Ln #160, Riverside, CA 92508. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. |  |  | SOM to manage project | Gerry Bomotti | Sharyl Murdock | Brandon Barbosa |  | Brandon Barbosa | 6 |  |  | FALSE |  |  | 2019-02-14 | SOM to manage project | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3505 | 3505 |  | FALSE | PLANNING & BUDGET | Orange County Psychiatry | UCR Health will be acquiring new off-campus leased space by moving into an adjacent medical office suite located at The Airport Tower, 18881 Von Karman Ave #1227, Irvine, CA 92612. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. |  |  | SOM to manage project | Gerry Bomotti | Sharyl Murdock | Brandon Barbosa |  | Brandon Barbosa | 13 |  |  | FALSE |  |  | 2019-02-19 | SOM to manage project | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3507 | 3507 |  | FALSE | PLANNING & BUDGET | Undergrad Class Labs & Studios Teaching Facility |  |  |  | Pre-programming | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Blythe Wilson | 10 |  |  | FALSE |  |  | 2019-03-04 | Programming | 2021-03-01 | 2023-01-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3508 | 3508 |  | FALSE | PLANNING & BUDGET | SOM New Academic Facility | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | Programming | Gerry Bomotti | Sharyl Murdock | Melissa Garrety |  | Mihai Gavan | 9 |  |  | FALSE |  |  | 2019-03-04 | Begin Programming | 2021-01-01 | 2022-12-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3510 | 3510 |  | FALSE | PLANNING & BUDGET | SOMED Data Center Study | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. |  |  | Programming | Gerry Bomotti | Sharyl Murdock | Daneca Stevens |  | Daneca Stevens | 7 |  |  | FALSE | 55000 |  | 2019-03-04 | Study | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3512 | 3512 |  | FALSE | VC-STU.AFF. | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) |  | 2108ACDEF | Funding | Brian Haynes | Cathy Eckman | Christina Wong |  | Daneca Stevens | 4 |  |  | FALSE | 130000 |  | 2019-03-19 | Secure Funding | 2020-07-01 | 2020-10-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3515 | 3515 |  | FALSE | PLANNING & BUDGET | DM(FY18) Elec Substation & Infra. Renewal |  |  |  | In Programming | Gerry Bomotti | Sharyl Murdock | Ron Rector |  | J.Franklin/G.Caraig | 3 |  |  | FALSE | 3750000 |  | 2019-03-08 | Field Data Gathering | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3516 | 3516 |  | FALSE | PLANNING & BUDGET | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Consultant Selection for Programming and Basis of Design | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Gerald Caraig | 1 |  |  | FALSE | 33980000 |  | 2019-03-04 | Program'g & Basis of Design Docs | 2021-01-04 | 2022-06-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3518 | 3518 |  | FALSE | PLANNING & BUDGET | Chancellor House Kitchen Countertops | Replacement of kitchen countertops at Chancellor Residence |  |  | Construction | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 24 |  |  | FALSE | 24800 |  | 2019-04-02 | Complete Construction | 2019-08-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3519 | 3519 |  | FALSE | BAS | CBTL Permit Inspections | CBTL PERMIT INSPECTIONS - The Coffee Bean & Tea Leaf restaurant is being leased by a CBTL franchisee (currently this is operated by UCR). They have submitted drawings to do a light remodel of the space. Permit and inspection services are needed to support their remodel. |  |  | In Close-out | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 30 |  |  | FALSE |  |  | 2019-04-04 | Complete Close-out | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3520 | 3520 |  | FALSE | PLANNING & BUDGET | College Building South Seismic Improvements | Full building seismic retrofit to College Building South. |  |  | On-hold pending UCOP decision | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Jason Espinoza | 2 |  |  | FALSE |  |  | 2019-04-02 | On-hold pending UCOP decision | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3521 | 3521 |  | FALSE | PLANNING & BUDGET | Life Sci Unit 2 Seismic Improvements | Full building seismic retrofit of Life Sciences Unit 2. |  |  | On-hold pending UCOP decision | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Jason Espinoza | 3 |  |  | FALSE |  |  | 2019-04-02 | On-hold pending UCOP decision | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3523 | 3523 |  | FALSE | PLANNING & BUDGET | 1907 Mt Rubidoux Facility Study | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. |  |  | Study in Progress | Gerry Bomotti | Sharyl Murdock | Melissa Garrety |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2019-04-22 | Complete Study | 2019-06-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3524 | 3524 |  | FALSE | VC-STU.AFF. | Stdnt Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. |  |  | Need to secure funding | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 8 |  |  | FALSE |  |  | 2019-04-16 | Secure Funding | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3527 | 3527 |  | FALSE | FAC-PLNG-DESIGN-CONST | Central Utility Plant Fire Alarm | Replace aging and non-replaceable fire alarm system, and conduit. Conduit is damaged and only 10% of wiring is usable. ( fire alarm system and devices are failing and they are not supported by manufacture ) -Run new conduit from propane tanks to fire alarm system -Install new terminal box at propane tanks. -Pull twenty two, 14 awg THHN wires in new conduit and terminate in junction box. -Replace 25 year old fire alarm panel, parts are not available to maintain system. -Add ada compliant horn/strobes thru out structure. -Add code compliant indicating devices thru out structure. -Replace 8 flame detectors -Replace all fire sprinkler devices on riser. -Flow switch. -Pressure switches. -Tamper switches. -Replace high capacity sounder at propane tanks. -Engineering, and drawings to be submitted to fire marshal for approval. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Ben Kochevar |  | Scott Donnell | 4 |  |  | FALSE |  |  | 2019-05-08 | Close-out | 2019-07-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3528 | 3528 |  | FALSE | FAC-PLNG-DESIGN-CONST | Entomology Museum Fire Alarm | Deferred Maintenance Project. Fire alarm system and devices are failing and they are not supported by manufacture. -Replace fire alarm system and all existing fire alarm peripheral devices. -Engineering, and drawings to be submitted to fire marshal for approval. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Ben Kochevar |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2019-05-14 | Close-out | 2019-07-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | (DMFI) Physics 2000 Renewal | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 6 |  |  | FALSE |  |  | 2019-05-15 | Complete Construction | 2019-07-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3533 | 3533 |  | FALSE | BAS | Solar Rooftop Initiative | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. |  |  | Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 35 |  |  | FALSE |  |  | 2019-06-03 | Design | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3534 | 3534 |  | FALSE | VC-STU.AFF. | SRC North Cooling Towers Replcmt | Replacement of the 2 Cooling towers in the Student Recreation Center North. The towers are 25 plus years old and in needed of replacement to keep the HVAC system running efficiently. |  |  | In Design | Brian Haynes | Cathy Eckman | Michael Eason |  | John Franklin | 7 |  |  | FALSE |  |  | 2019-06-06 | Bidding | 2019-12-01 | 2020-01-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-08-16
3535 | 3535 |  | FALSE | CHASS | Watkins 1311 Renovation | This request is for a new faculty hire. -Remove north countertop and sink. Install stainless counter and two sinks. -Install eye wash station -Install laminate flooring, remove existing. (Abatement) -Paint space to campus interior standard. -Remove east counter and replace with stainless. -Remove fume hood, discard. -Install new fume hood. |  | 1311 | Dept. in planning for next steps, report issued to assist in decision-making. | Milagros Pena | Cindy Williams | Paul Richardson |  | Jason Espinoza | 3 |  |  | FALSE |  |  | 2019-07-10 | Funding | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3537 | 3537 |  | FALSE | CAP.PROG. | Student Services Bldg Cubicles | Purchase and installation of up to 8 new cubicles on the 2nd and 3rd floors of Student Services building (up to 16 total) to increase occupant capacity. This has been initiated by VC Bomotti. There may also be associated telecom expenses. |  | 3rd Flr | New | Jacqueline Norman | Sharyl Murdock | Sharyl Murdock |  | Sharyl Murdock | 1 |  |  | FALSE | 96000 |  | 2019-07-25 | New | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3540 | 3540 |  | FALSE | CAP.PROG. | BCOE Advising Move | Relocation expenses for BCOE advising including: $75k furniture, $10k moving expenses, $3k misc. Renovations were also approved and were completed by Facilities under SLA. Also includes relocation of VCBAS from Skye to Student Services at $1,010 and move expenses for Student Disability from Costo to Student Services at $25k. |  |  | New | Jacqueline Norman | Sharyl Murdock | Sharyl Murdock |  | Sharyl Murdock | 2 |  |  | FALSE | 111010 |  | 2019-07-25 | New | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
3542 | 3542 |  | FALSE | CNAS | Chapman Rm 9 Fume Hood Install | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. |  | 9 | New | Kathryn Uhrich | Deborah McWilliams | Rick Redak |  | Scott Donnell | 3 |  |  | FALSE |  |  | 2019-08-01 | New | [11 empty] | PD&C | FALSE | 2019 | 2019-08-16
17P000254 |  | 17P000254 | FALSE | PLANNING & BUDGET | SL5 FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS |  | CORP PP WHSE | 0106B | CANCELED BY CLIENT | Gerry Bomotti | Sharyl Murdock | DALAN DINH |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-06-07 | [6 empty] | 05/08/19 O-ANS: Canceled by customer per email from Deborah McWilliams. .2/1/19, DL; Material is ordered with a 4-6 week lead time.11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DD 10/6: On hold pending discussion on space…..DL, 7/11/18; I understand there is movement on this project but I need to check in with John P. or Chris P. for a status update. |  | Enrico Baez | 3/7/19 O-ANS: Project no longer moving forward per Ron Rector. ~ 12/14/18 O-RVL: F & LS shop space/Shop Location TBD. | NO | 2019-04-05 | FS | FALSE | 2017 | 2019-08-16
17W012504 |  | 17W012504 | FALSE | CNAS | PAINT Business OFFICE AND CONF. ROOM |  | ENTOMOLOGY | 170 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 27 | 26 | FALSE |  |  | 2017-05-04 | [6 empty] | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. |  | Dan Lerman | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. | YES | 2018-10-22 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000027 |  | 18P000027 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT LAB |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-05 | [6 empty] | 2/1/19, DL; This project is 100% Complete……………DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again…… DL, 4/2/18; This space is still on schedule for 7/1/18 completion date…..FAMIS work orders have been produced…..DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th….. |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again...... DL, 4/2/18; This space is still on schedule for 7/1/18 completion date.....FAMIS work orders have been produced..... | YES | 2018-07-12 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000028 |  | 18P000028 | FALSE | CNAS | SL5 CHAPMAN PATCH AND PAINT |  | CHAPMAN | 0010A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced .......DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced ...... | YES | 2018-07-12 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000029 |  | 18P000029 | FALSE | CNAS | SL5 CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS |  | CHAPMAN | 1 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain......DL, 5/24/18; This work is scheduled to be complete on or before 7/1/18.....DL, 6/16/18; Blinds are delayed to mid July but window clenaning is still on schedule......DL, 7/11/18; This Project is 100% Complete |  | Dan Lerman | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain...... | YES | 2018-07-11 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000030 |  | 18P000030 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT FROM WATER DAMAGE |  | CHAPMAN | 100 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced....... | YES | 2018-11-08 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000094 |  | 18P000094 | FALSE | BAS | SL5 OBAN LAUNDRY ROOM RENOVATION |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2017-09-08 | [6 empty] | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on bid. 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/12 EB- rec'd approval to contract with Design West to consult on electrical panel upgrade. |  | Enrico Baez | Scope of work has changed and project to be routed to Google IRT/CPMS for completion. 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold. MN 3/20: pending approval from customer on 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/11/18 EB-requested drawings from Gunter per Desgn Wests request. 7/11/18EB-waiting for Desgn West to complete site survey. 8/7/18 EB-Met with Robert Brumbaugh. Scope has changed with additional requirements. Improve HVAC, replace VCT, bathroom remodle. Advised to submit CPMS for A&E. | YES | 2019-01-19 | FS | FALSE | 2017 | 2019-08-16
18P000095 |  | 18P000095 | FALSE | BAS | SL5 THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS |  | THE PLAZA | A0013 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  | C | HOLD | FALSE |  |  | 2017-09-08 | [6 empty] | 4/11/EB-On Hold per Robert Brumbaugh. 6/8 EB-emailed R. Brumbaugh for status update. |  | Enrico Baez | Canceled per customer on priortization list. 4/11/EB-On Hold per Robert Brumbaugh. DND 7/14 Hold per customer on prioritization | YES | 2018-06-08 | FS | FALSE | 2017 | 2019-08-16
18P000099 |  | 18P000099 | FALSE | CNAS | SL5 EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 26 | 23 | FALSE |  |  | 2017-09-08 | [6 empty] | 4/19/19, DL; This Project is 100% Complete :)…………….12/6/18, DL; This project is a priority #23 and may be completed in the next 12 - months…..DL 1/3: Chris to verify with customer on electrical requirements for completion……DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress…..DL, 7/11/18; Still need to work on plans…. Target date is 9/30/18….. |  | Dan Lerman | DL 1/3: Chris to verify with customer on electrical requirements for completion…...Dl, 4/29/18; Will work on plans/permits. The display cases will be in a corridor and they may pose an obstruction for Emergency Exit egress.....DL, 4/2/18; This is electrical outlets for 4 display cabinets…..…NO FAMIS work orders yet…. | YES | 2019-04-19 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000106 |  | 18P000106 | FALSE | BAS | SL5 HOUSING PROJECT - OBAN REC ROOM REMODEL |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 3 | FALSE |  |  | 2017-09-14 | [6 empty] | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. DL, 7/11/18; Per Susan this project is back on track. Project is scoped. Gunther will start working on the plans and permits. Once we have the approved permit. still need to check in with Susan on a few items.....Target complet date will be mid- fall...... |  | Enrico Baez | Scope of work has changed and project to be routed to Google IRT/CPMS for completion. EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. 8/22/18 Met with BoB Brumbaugh, Scope of work has changed with additional items. Fire alarm panel relocation, possible building HVAC upgrade. Ask he route project through CPMS and make laundry room and Rec. room one project. | YES | 2019-01-19 | FS | FALSE | 2017 | 2019-08-16
18P000111 |  | 18P000111 | FALSE | CHASS | SL5 KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 |  | CHASS INT S |  | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Jason Williams |  |  |  | FALSE |  |  | 2017-09-15 | [6 empty] | EB 1/31/18 Work was assigned to lock shop 12/7/17…. DND 5/11: Spoke with Jason, all work complete to be completed as trade is available. Only work remaining is on 3150 A; Jason short staffed to finish project but it's on his radar. 07/13/18 H-FMS: Troubleshoot programming and settings for this controller. Clear all data from panel and reset, perform required downloads, re-test and verify both doors working correctly. |  | Enrico Baez | EB 1/31/18 Work was assigned to lock shop 12/7/17 | YES | 2018-07-13 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000117 |  | 18P000117 | FALSE | CNAS | SL5 PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION |  | WEBBER | 1303 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-21 | [6 empty] | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work....DL, 5/9/18; Produced work order for JEss to test for lead paint and ACM....Von wall is hot, everything else is good to go. I will schedule the work soon. The space is vacant......DL, 7/11/18; This project is in progress. Target Complete Date is 8/10/18....DL, 7/25/18; Vinyl plank and bullitin boards the balance of the task for this project. Still on target for complete on 8/10/18.....DL; 8/10/18; We were schedule to install the fllor and identified Asbestos,. Jess is working on the propsal and schedule for the abatment. This will require a 14- dat notification to the AQMD. This space is vacant with no scheduled move in date......DL, 8/22/18; Abatment is scheduled for this Tursday and Friday. We will scheule the carpet in dry errase boards for next week.Target complete date will be 8/31/18.....DL, 9/6/18; This project is 100% Complete...... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work.... | YES | 2018-09-10 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000118 |  | 18P000118 | FALSE | CNAS | SL5 OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT |  | OLMSTED | 1337 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2017-09-20 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space.......DL, 6/16/18. New staff member schedule to start mid july. BKM is also scheduled for mid july. This project will require cabinets to be removed, new carpet, paint and blank out electrical outlets that will no longer be used.. new signage too.....DL, 7/11/18;This project is in progress. Complete date is 7/20/18......DL, 7/25/18; This project is 100% Complete....... |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space. | YES | 2018-07-25 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000121 |  | 18P000121 | FALSE | CAMPUS | SL5 PHYSICS HYDRATION STATION - PHYSICS HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | 5/1/19, DL; Per Chris, we will not be compelting this project. There is currently a Water dispenser on the drinking fountain. 3/28/19, DL; We will look into installing a bottle filler on this fountain verse a complete change out…..12/6/18, DL; This project is currently on hold…… DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | Reviewing campus standards for these project requests. 3/4/19 DND Removed from FS hold per Ron Rector. DND 7/14: hold per hydration station update for campus….4/2/18; Notes are current….DL, 2/26/18, Still need to review scope….. DL, 1/5/18; Still need to review scope | NO | 2019-05-01 | FS | FALSE | 2017 | 2019-08-16
18P000122 |  | 18P000122 | FALSE | CAMPUS | SL5 MS&E HYDRATION STATION - MS&E HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | Reviewing campus standards for these project requests. DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus….3/4/19: Single trade renovation project to be performed by FS but not captured as a minor renovation. | NO | 2018-04-02 | FS | FALSE | 2017 | 2019-08-16
18P000126 |  | 18P000126 | FALSE | CHASS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS |  | HUM & SOC SC | 3611 | COMPLETE | Milagros Pena | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 2017-09-28 | [6 empty] | 7/1/19,DL; This project is 100% Complete…..5/15/19, DL; Work is scheduled to start on 6/19/19…….5/1/19, DL; Plans are approved. Need to order material and schedule the work…..3/18/19, DL; Plans submitted to PD&C today…..02/2819, DL; Gunther will work on plans over the next three weeks to submit for a building permit. We will schedule the work if and after the plans are approved. If approved the door and window will more than likely have a 3- month lead time…………….12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS. Remove double doors and install single door.Remove small West wall. Relocate t-stat. Ceiling work. Replace carpeting. | YES | 2019-07-01 | FS | FALSE | 2017 | 2019-08-16 | FY 19-20
18P000194 |  | 18P000194 | FALSE | ITS | SL5 TELEPHONE WINDOW REPLACEMENT |  | TELEPHONE | 101 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 5 | 6 | FALSE |  |  | 2017-11-20 | [6 empty] | 07/23/19 O-ANS: Canceled by customer per notes in FAMIS. |  | Enrico Baez | EB-1/31/18 Conducted site visit. Request to replace all exterior Plexiglas with glass. Will call glass vendor to provide estimate. 7/12/18 EB-Quote provided by Hour Glass. Emailed Tami, she is waiting for budget approval to proceed with project. Should have by end of July. 10/22/18 Customer Canceled; will resubmit when ready to proceed. | YES | 2018-10-19 | FS | FALSE | 2017 | 2019-08-16
18P000198 |  | 18P000198 | FALSE | VC-STU.AFF. | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Install new Wall lights | HUB | 0 | PLAN DEVELOPMENT/CHECK | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 1 | 5 | FALSE |  |  | 2017-11-21 | [6 empty] | 8/14/19, DL; This project is now on Gunther's bench. Gunter will start the process in about 2- weeks and we should have plans top submitt with in the next 30- days….6/17/19, DL; I will walk this work in the next two weeks and work on plan to submit to our campus architech and building official for review…..DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…… | 2018-01-23 | Enrico Baez | Plans will be developed and will be submitted for review and approval. 4/2 MN: Enrico to obtain an FAU….. 1/23/2018 E.Baez conducted job site walk. Request is for lighting installations above entries to store front and kitchen on East side of building and additional lighting above outside locker on loading dock. Manny has lights that can be re-used. Want estimate only. Need to include Campus Architect too…… 1/23/18 EB-site walk, scope enter in FAMMIS. | YES |  | FS | FALSE | 2017 | 2019-08-16
18P000201 |  | 18P000201 | FALSE | CHASS | SL5 ARTS REMOVE COUNTERTOP/SHELVES |  | ARTS | 0106A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 3 | TRUE |  |  | 2017-11-21 | [6 empty] | DL, 6/16/18; Ned to walk, scope and submit plans ASAP…..Sent Paul an email requesting information on Status of Faculty hire status……DL, 7/11/18; Paul is on Jury Duty and he said he should return back to work next week. Current Targe complete date is mid September......DL, 7/25/18; Carpentery and Electrical is complete. Patch and paint has started. Target complete date is 8/3/18......DL, 8/8/18; Space is VAcant and ready for paint. The paint department is working on several other projects that require their attention. The paint department will complete the work in the near future......DL, 8/22/18; This Project is 100% Complete....... |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS……DL, 4/29/18; Pasted from wo;remove the existing countertop and shelves that are built into the room. Follow with patch and paint of entire space. | YES | 2018-08-23 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000205 |  | 18P000205 | FALSE | CHASS | SL5 CHASS INT S CREATE DOOR |  | CHASS INT S | 2117H | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-11-27 | [6 empty] | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18……DL, 5/24/18; Plans were approved. WE need to schedule the work…..DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18...........DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... .. DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date..........DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18............DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware.....DL, 9/19/18; This Project is 100% Complete...... |  | Enrico Baez | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18…… | YES | 2018-09-21 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000209 |  | 18P000209 | FALSE | CHANCELLOR | SL5 VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 |  | STUDENT SERV | 0 | CANCELED BY CLIENT | Kim Wilcox | Karim Zahedi | ANGIE GRAY |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2017-11-30 | [6 empty] | 5/16/19, DL Angie Grey canceled project on 5/15/19 via email….. 5/1/19, DL; Sent Angie an email this morning. Waiting to hear back from Angie to see if project will be canceled or sent to PD&C…..3/28/19, DL; Provided Angie with an estimate and waiting for her response. The esimate was for 65,000. this work will be redirected to PD&C if she wants to proceed…….2/14/19, DL; Ron V. to follow up with Doug from Capitol Door for alternate pricing .1/15/19, DL; Ron V is still working with Angie on verifying a vendor and product…………..12/14/18, DL; Ron V. is currently working to find a more affortable turnstyle system. When a sytem is approved, we will schedule the work…. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope and conduct site visit……DL, 7/11/18; This work will require plans and permits. Will schedule meeting with Scott to verify if the project request will be approved. If this is approved, we will plan the target complete date to be mid October…..The Request is to reverese Emergency Exit Doors and install Prox card access……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..DL, 8/22/18; Confirmed with Scott that we can reverse the door swing. We will work on plans for review process. This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 9/19/18; I mis understood this for a project at Health Services. I have a meeting with Angie this week. This project is to install turn styles for access to the building. I will need to discuss the equipment to be purchased by Angie verify the specs. We will start on the plans in the early Fall……DL, 11/7/18; Conducted site visit with Vendor. Informed Angie the cost of the project will be at $45K for the project. Angie is checking to verify if funds are availabe for the equipment. |  | Ron Veloz | 03/19/19 O-RVL: RV updated notes as a follow up to Alan's meeting minute action items received on 03/07/19. Updating notes, RV spoke with Angie Grey on 03/18/19, Angie and Dan L met with the vendor (03/19) and is expecting pricing. Status to remain on "HOLD" pending quote and department approval. Update input on Access, FAMIS and sent to Alan on 03/19 Notes on FAMIS and Access have been updated. END--- 02/28/19 O-RVL: RV received confirmation from Doug at Capital Door that they are unable to provide a quote at this time due to deign changes with the product. END--- 02/21/19 O-RVL: RV has contacted Capitol Door with a RFQ. Pending follow up by 02/22/19 per Doug @ Capitol. END---02/21/19 O-RVL: RV Updated notes, RVhas contacted Capitol Door with a RFQ. Pending follow up by 02/22/19 per Doug @ Capitol. END--- DL, 5/5/18; FAMIS work order, New ADA operator, power supply for operator and card swipe…. 2/6/18 E. Baez conducted site visit. Power and Data not located near desired installation site. Width of opening is 118" Flooring is combination of brick and vinyl. 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 1 and for faculty hire "NO"---- 5/5/18; FAMIS work order, New ADA operator, power supply for operator and card swipe….2/6/18 EB- conducted site visit. Request for automated access control system. Annotated on FAMIS…. 2/2/18 EB site visit scheduled for 2/5/18 with Angie Gray. THIS REQUEST IS FOR QUOTES. THE SYSTEM REQUIRES AN FAU TO BE PROVIDED IN ORDER TO SUBMIT REQUEST. ACTUAL WORK WILL MOST LIKELY BE CHARGED TO A DIFFERENT FAU. THEREFORE, PLEADO NOT CHARGE FAU WITHOUT APPROVAL. Original request SR # 17S001552/WO # 17W001873 was submitted on 8/12/16 to Facility Services. A recommendation has come from UCPD for an automatic swing door to be installed on the first floor of the Student Services Building. The door would need to include a switch, button, and card reader functionality (SSB already operates on a keycard system). Please provide us with all options and pricing. The door would be similar to the ones installed in the SRC. I have attached a copy of the recommendation that contains a rendition. Please let me know if you have any questions. Thank you. Angie Primary Contact: Angie Gray. angeladi@ucr.edu. (951) 827-2589. Secondary Contact: Sean Cason. SEANC@ucr.edu. (951) 827-4020. 20 year(s) in use. ==CUST FAU# A01401 19900 68 AXSSB | YES | 2019-05-16 | FS | FALSE | 2017 | 2019-08-16
18P000214 |  | 18P000214 | FALSE | VC-STU.AFF. | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 |  | HEALTH SERV |  | HOLD - FACILITIES SERVICES | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-12-08 | [6 empty] | 7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for Doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once materila arrrives, we will schedule the installation. Floor covering is on hold untile we receive the process from EH&S…….5/31/19, DL; Contracts is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is comleted except the floor covering and elcetronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez | 01/15/19, DL; The plans are approved and Material is ordered. Once material arrives, we will schedule the work with Gloria… Dl, 5/3/18; Dan, Chris, Ron and Gloria will meet and re-scope the work……1/31/18 EB-Scoped site with Chris P. on 10/30/2017. Spoke with Gloria who thought still CPMS. Scope includes removing doors, adding teller counters, moving corridor wall…. | YES |  | FS | FALSE | 2017 | 2019-08-16
18P000215 |  | 18P000215 | FALSE | VC-STU.AFF. | SL5 STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA HAGGINS |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2017-12-08 | [6 empty] | 6/17/19, DL; This project is 100% complete. This project was the wall removal at the check in entrance…...5/31/19, DL; Contracts is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks4/15/19; All work is comleted except the floor covering and elcetronic card readers for the doors…..2/28/19, DL; This project has started and is on schedule…….2/14/19, DL; This project is scheduled to start on 2/19/19…………2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………1/15/19, DL, Material is ordered, material should arrive on site in the next 3- 5 weeks……12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 5/24/18; Need to review scope and site visti with Enrico. Plans and permits will be required for this project….DL, 7/11/18; Planning to walk work with Gloria and her team next week. Will be able to project complete date after site visit is conducted……DL; 7/25/18; We walked this project with the team. This will require plans and permits. We will schedule this work for Fall…………DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-45 Days…… |  | Enrico Baez | 01/15/19, DL; Plans are approved and material is ordered for the Phlebotomy room. We are securing the double doors. We are not conducting any work with countertop or window work. DL, 5/5/18; Pasted from wo: Noted changes to original request. Add counter windows onto end of the current SHS front desk main counter (2 windows/stations).2. Close exam room that is open to hallway with a wall (behind room 210).3. Covert 100A to phlebotomy room with a hallway access doorway.4. Open wall to reconfigure to allow space for lab manager…… EB 3/20 scoped project and annotated on FAMIS. | YES | 2019-06-17 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000221 |  | 18P000221 | FALSE | CNAS | SL5 Provide add'l HVAC capacity to maintain lower temp |  | BOYCE | 4414 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 9 | 16 | FALSE |  |  | 2017-12-11 | [6 empty] | 12/14/18, DL; This project is 100% Complete……….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob. DL, 5/9/18; We will work on plans and submit for review.....DL, 6/16/18. Had meeting with Bob W. to verify what is needed on plans. I will work with Gunther on plans for submittal and review......DL, 7/11/18; Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall.....DL, 11/7/18; Material is on site and will will schedule the work with in the next 30- days..... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob | YES | 2018-12-14 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000223 |  | 18P000223 | FALSE | CNAS | SL5 Provide requisite utility infrastructure to support 4 add'l chambers (on order). |  | FAWCETT LAB |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 11 | 21 | FALSE |  |  | 2017-12-11 | [6 empty] | 2/1/19, DL; This Project is 100% Complete……..01/15/19, DL; Plans are approved, Chambers are on site. Electrical is complete. Plumbing work is in progress. Our portion of the project should be complete by 2/1/19…………..12/14/18, DL; All Pre work is complete. The Chambers are scheduled to arrive on site within the next 30-days. We will finish this project when material on site……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans……..DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet….DL, 4/29/18; Still need to conduct site visit with the team….DL, 5/24/18; Per Patty, equipment is ordered but 5- months out…..DL, 9/6/18; We will submit plans to Bob W. tomorrow for review and approval……..DL, 9/19/18; Plans are approved. The equipment will be here in about 4- months. WE will start the work for this project in the Fall to ensure we are ready when the equipment arrives……DL, 9/19/18; Plans are currently being review by BO & FM……DL, 11/7/18; Plans are approved. WE are requesting to change the placement confirguration of the growth chamber and awaitng Bob's review and approval. WE are on track to have this work complete befoire the end of the new year….. |  | Dan Lerman | DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans........DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet....DL, 4/29/18; Still need to conduct site visit with the team… | YES | 2019-02-01 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000226 |  | 18P000226 | FALSE | BCOE | SL5 BOURNS FUME HOOD INSTALLATION |  | BOURNS | B0235A | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  | 8 | HOLD | TRUE |  |  | 2017-12-11 | [6 empty] | 2/14/19, DL; This project is Complete…..2/1/19, DL; The Fume hood is complete. The vendor will be back in two weeks to comissison the clean room…..…1/15/9, DL; This project is 95% complete and should be complete on or near 2/1/19…………12/14/18, DL; This Project is 90% Complete. Fume hood is scheduled for install next week. We will finish balance of project after Fume hood is installed…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. WE are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans…..DL, 5/9/18; planning to submit plans on 5/11/18 for plan check review….. DL, 5/24/18; Plans were submitted to Bob W. on 5/24/18……DL, 6/12/18; Project is on Hold until Shane can provide plans/specs for the clean room……DL, 7/11/18; Still no change to the status……DL, 7/25/18, Maggie confirmed this project is on the books. I need to discuss the status with the team because the priority list is on Hold…….DL, 8/22/18; This project is no longer on hold. We will per shane we will submit what we have from the clena room suupplier for review from FM and BO……DL, 9/6/18; WE are almost complete with Plans and will submit the plans next week………DL, 9/19/18; Submitted plans to PD&C on 9/14/18…..DL, 10/4/18; Plans were approved thais week. WE will scheudle the project around the delivery date for the Clean room……..DL, 11/7/18; This is in progress. We will complete the install of the utilities so the clean room can be installed. WE will finish the balance of the project once the Clean room install is complete. The clen room is being install by an outside vendor….. |  | Dan Lerman | 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. We are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans..... DND 7/14 Hold per customer on prioritizatio | YES | 2019-02-14 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000227 |  | 18P000227 | FALSE | CNAS | SL5 BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL |  | BATCHELOR | 4128 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-12-12 | [6 empty] | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM.......DL, 5/24/18; Need to work on plans and permits. Project needs to be complete before Fall academic 2018.....DL, 6/16/18; Walked project with Jess. and he will schedule the abatment. We will not need plans for this project. We are not removing the exhasut hood which was the original purpose foor the plans......Carpenters started the demo. Still need to remove TSI. Once TSI is removed, we can schedule the plumbing work. Target Complete Date is 9/21/18....DL, 8/10/18; Abatement is scheduled for this weekend, we will start work soon.....DL, 8/22/18; Abatement and most demo complete. Still on track for 9/21/18.....DL, 9/19/18; Scope change. This project should be complete on 9/28/18.......DL, 10/4/18; Floor to be installed this Friday. Pianters will finalized the stain on the cabinets. Thsi project should be complete near 10/19/18.......Dl, 11/7/18; This project is 100% complete.... |  | Dan Lerman | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM....... | YES | 2018-11-08 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000247 |  | 18P000247 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 |  | PHYSICS | 3023 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  |  | 15 | FALSE |  |  | 2017-12-20 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000252 |  | 18P000252 | FALSE | ITS | SL5 CHASS INT S REPLACE ELECTRICAL SCREENS |  | CHASS INT S | 2130 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | JORGE MACIAS |  | Dan Lerman |  | 1 | 2 | FALSE |  |  | 2017-12-21 | [7 empty] | 2018-06-21 | Ron Veloz | 01/23/19 O-RVL: RV received confirmation (Telcon) with Jorge Macias to cancell the request. He will resubmit upon recipt of screens at a later date. RV instructed the Front desk(FS) to close out the request & "cc" Monty, Alan, Enrico & Linda & Loretta. END--- 01/23/19 O-RVL: RV emailed Jorge to verify status of the request/materials order. Pending response. END--- 01/09/19 O-RVL: RV spoke with Jorge on 1/09. Jorge expect screens to be ordered within two weeks and will cancel this request if the screens are not ordered by his department. Jorge asked to contact him in two weeks (01/23/19). END---6/21/18 RV HOLD, Walked site w/ Enrico & Jorge. Surveyed site and Enrico updated FAMIS & Project folder. Now pending - confirmation of party to purchase projection screens. S.O.W.: Remove two non functional motorized video screens. Replaced with new larger screen. Patch and repaint all walls and entry door. END--- 07/06/18 Ron V Input notes: Received email from Enrico on 07/03 confirming Facilities Services doe not purchase Audio Visual equipment in General Assigment class rooms. On 07/06 RV contacted Jorge Macias with this info and Jorge said he would get back to RV with follow up reply from his supervisor. Confirmed with E.B. that proj info/ photos are updated on the project folder and FAMMIS. END--- 8/22/18 O-RVL: Will follow up with Jorge to confirm status on the screen purchase and if Media will purchase the screens. END--- 08/23/18-RV emailed Jorge, Pending response. END--- 08/24/18-RV, Enrico followed up with Jorge, projection screens approved but not purchased yet). END--- 10/17/18: RV spoke with Jorge today and he said screens are on order. Jorge will follow up with updates to RV and Enrico. | YES | 2019-01-24 | FS | FALSE | 2017 | 2019-08-16
18P000256 |  | 18P000256 | FALSE | CNAS | SL5 BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES |  | BOYCE | 3451 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave at Webber is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place.......DL, 5/9/18; Autoclave is destroyed. Pictures were sent to Cheryl. We are now waiting for the equipment to arrive. Steve B is working on Steam connection at Boyce......DL, 5/24/18; Autoclaves arrived. Day crew is scheduled to deliver the unit on 5/30/18. we will schule the plumbers and electricians shortly there after......DL, 6/16/18; Webber Autoclave is almost complete. This portion should be complete next week. WE will run the Webbber autoclave for two weeks before we start the Boyce Autoclave. The weldolet for the BOyce unit will be installed during the steam shutdown...... DL, 7/11/18; Webber Auto clave will be complete on 7/12/18. We will start the demo of the Boyce Auto clave next soon. Target date for this project is 8/10/18...... DL, 7/25/18; We had a delay with the Webber autoclave which will implact the Boyce Auto clave. New target complete date is 8/22/18.....DL, Plumbing is almost complete, need to schedule final elctrical and Commission equipment. Target date 8/31/18...... DL, 9/6/18; This project should be complete but we still need to schedule the electrical connections ASAP.........DL, 9/19/18; This project is 100% Complete. |  | Dan Lerman | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place | YES | 2018-09-21 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000257 |  | 18P000257 | FALSE | CNAS | SL5 SKYE HALL MOUNT 55 |  | SKYE HALL | 209 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 28 | 28 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete…….1/15/19, DL, Site visit is scheduled with James M. this Thursday. We will schedule the work shortly after the site visit…….12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | 2019-02-01 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000258 |  | 18P000258 | FALSE | CNAS | SL5 SKYE HALL HALLWAY MOUNT |  | SKYE HALL | 212 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 29 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete……1/15/19, DL, Site visit is scheduled with James M. this Thursday…………12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | 2019-02-01 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000261 |  | 18P000261 | FALSE | SOM | SL5 WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR |  | WEBBER | 1143 | COMPLETE | Deborah Deas | Brandon Barbosa | LOURDES ESCAMILLA |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 7/11/18; Work orders are produced. Need to assign the work order and order material. I will review with Steve and verify target complete date….DL, 7/25/18; Still need to walk the project with Steve……DL, 8/10/18; Material is ordered. We will complete the install when the materila arrives.....DL, 8/22/18; Material should be on site with in 4- weeks. Will schedule install when material is on site. Target date is 9/20/18.......DL, 9/6/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 4/29/18; Pasted from work order;I"nstall a glass window 28x9 on office door in WEBBER, Room 1143. | YES | 2018-09-10 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18P000267 |  | 18P000267 | FALSE | BCOE | SL5 CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-01-16 | [6 empty] | DL, 5/19/18; High table mounted on West wall to be relocated to South wall by light "Centered". Relocate white board from East Wall to West walll wher high table was removed. Paint and new flooring. Need to schedule work with Paul and Jess. BKM furniture is scheduled 4-6 weeks. DL, 6/16/18; Lower electrical outlets on North wall, repair blinds, paint and new flooring. The space is vacant as of June 16th. I will scheudle the workl.....BKM delivery is currently scheduled for July 23rd.......This project is 100% complete. There were two items added to the scope and they will be complete by 7/20/18..... |  | Enrico Baez | 4/3/2018 Met with Maggie. She is working with BKM. Floor to go down first. BKM furniture on top. Annotated in Famis. | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000269 |  | 18P000269 | FALSE | CNAS | SL5 BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED |  | BATCHELOR | 1123 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 12 | 18 | FALSE |  |  | 2018-01-16 | [6 empty] | 3/18/19, DL; went to schedule the work and the customer stated the power is no longer needed and confirmed this work order can be canceled. |  | Enrico Baez | 5/23/18 EB - Sent email to April requesting site visit. 6/11/18 EB conducted site visit request if for additional outlet only. Single trade only asked Deborah to change to SL6. FS to coordinate with client to scope the work. Customer contacted to schedule a site visit. | YES | 2019-03-18 | FS | FALSE | 2018 | 2019-08-16
18P000270 |  | 18P000270 | FALSE | SPP | SL5 CHASS INT S- EVALUATION FOR REMODEL |  | CHASS INT S | 4133 | CANCELED BY CLIENT | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Dan Lerman |  | 4 | 2 | TRUE |  |  | 2018-01-16 | [6 empty] | 4/24/18 EB- Per Christina Wong, no loner needed……DL, 5/5/18; Project is cancesled per notes DND 7/27; Please follow up with customer on the status and need for the work; customer advised to me that Dan has the scope of work for completion. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. |  | Enrico Baez | 4/24/18 EB- Per Christina Wong, no longer needed……DL, 5/5/18; Project is canceled per notes. DND 6/13; Project reopened and not canceled per conversation with customer. Complete scope review and speak with Luis Alvarez. DND 8/20/18: submitted Google form for Project to be reviewed by IRT. 8/19/18 Met with Louis Alvarez. Asked for measured plans from BKM for wall layout and dimensions. Emailed again on 9/6 asking for draws. Still waiting for BKM to provide drawings. 9/21/18 Dinh - placed on hold until customer provides BKM drawings. Enrico please manage follow up. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. On shared drive can be found in file. 10/30/18 EB-Cancelled by Customer | YES | 2018-04-24 | FS | FALSE | 2018 | 2019-08-16
18P000273 |  | 18P000273 | FALSE | LIBR | SL5 RIVERA LIB -RESTROOM REFRESH PROJECT |  | RIVERA LIB |  | TO BE PERFORMED BY PD&C | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2018-01-18 | [6 empty] | DND 12/13/18: Customer advised maintenance requests related to project request has been addressed. Renovation work to be performed by PD&C and customer submitted a CPMS request. DL, 6/16/18; Need to schedule site visit with Dave and Chris P…….DL, 7/11/18; Chris and I will walk this poroject next week…..Wlaked projects with Chris. We need to review in more detail to better determin the process for this project…..DL, 9/6/18. WE need to discuss what we are going to do with this project.... We walked the project but we now need Direction from Facilities leadership… |  | Dan Lerman | .Scope of work has been reviewed; determining how to complete project with trades. DL, 4/29/18; Chris said he is aware of project scope. I need to review with Chris and schedule the work;…..Dl, 5/3/18; Dand to walk project with Chris and Dave to confirm scope. We will sub out tile work. This is paint tile, lighting and plumbing fixture upgrade…. | YES | 2018-12-13 | FS | FALSE | 2018 | 2019-08-16
18P000274 |  | 18P000274 | FALSE | GSOE | SL5 SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 |  | EADY CENTER |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES | BRANDON BARBOSA | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-18 | [6 empty] | 2/14/19, DL; This project is Complete………….2/1/19, DL; This project is 99.9% Complete. We still need to conduct Final inspection with Building inspector……1/15/19, DL; The door and automatic opener is scheduled to be installed on 1/22/19……..12/14/18, DL; This project is 95% complete. The contract for the door and ADA operator was awarded today. We will schedule the work shortly after the new year…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Conducted site visit with Gilbert. We need to have a meeting to determin if this work is part of the SLA…… DL, 6/16/18; We still need direction, SLA or Recharge?.......DL, 7/11/18; This Project will require Plans and Permits. We will start on the Plans next Week. We will also issue work orders for work we will complete with in house staff. The Concrete work and Entry Door will need to be contracted out. Target Complete date is 10/1/18……..DL, 7/25/18; Work orders are produced. Planing to walk the project with Chris, Steve B and Robert C. thisw week or next week. We will submit plans to Bob Williams for the contracted work next week……DL, 8/8/18; Completed site visit with Robert C. Steve B, Steve T. and Chris; the Plumbers are complete. The carpenters and electricians will work on their items over the next three weeks. The Plans will be ready to submit on 8/9/18. Once plans are approved, we will proceed to go out to bid for the Concrete and the ADA operator. Target complete date is 9/21/18…….DL, 8/22/18; Plans were apprroved, Concrete Contract is being executed. Still working on Door and ADA operator……..DL, 9/6/18; NTP for Concrete will be issued on Monday. I will schedule the work. I need to follow up on the door order and the ADA operator…….DL, 9/19/18; Concrete walkway scheduled to start on 9/20/18. The new door and Frame will arrieve in 3-5 weeks. We will schedule the install when the new door and frame are on site…….DL, 10/4/18; Concrete work is complete. Still need handrail, signage, door and ADA operator. Target date is Early November….DL, 11/7/18; Project is 95% complete. Contract is being processed to install the new Door, Door Fram and ADA operator. Goal is to have the work complete befor the winter break…… |  | Enrico Baez | Duplicate of 18W011999 project scoped and note entered to make facility ADA compliant. | YES | 2019-02-14 | FS | FALSE | 2018 | 2019-08-16
18P000281 |  | 18P000281 | FALSE | VC-UNIV.ADV. | SL5 ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS |  | ALUM VISITOR | 2202 | COMPLETE | Peter Hayashida | Naysia Caldwell | TRUDY COHEN |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-01-24 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…..2/28/19, DL; This work is scheduled…….DL, 5/24/18; Need to verify scope of work with EnricoDL, 7/11/18; Still need to visit the site and schedule the work…..DL, 11/8/18; This project was transferred to John. The target date was 1/2/19….. |  | Enrico Baez | 5/10/18 EB-Customer needs additional outlets in space to accommodate 4 new cubicles. Bob Williams wants additional information with plans. 9/13/18 EB-Met with Dan, Jorge, Rita and Kim. Scope to include patch and painting walls, removing art work, moving thermostat. Cubicles will need whip connections. | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000282 |  | 18P000282 | FALSE | BAS | SL5 EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 |  | POLICE BLDG |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | LISA MARTIN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-25 | [6 empty] | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work…..DL, 5/9/18; We need to submit plans……DL, 7/11/18; This still needs to be scheduled......DL, 8/8/18; Enrico Confirmed this project is 100% Complete.... |  | Enrico Baez | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work….. | YES | 2018-08-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000284 |  | 18P000284 | FALSE | CNAS | SL5 SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT |  | SKYE HALL | 277 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  | 29 | 23 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000287 |  | 18P000287 | FALSE | CNAS | SL5 SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 33 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19/18; This project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000288 |  | 18P000288 | FALSE | CNAS | SL5 SKYE HALL OFFICE SUITE PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000292 |  | 18P000292 | FALSE | CNAS | SL5 SKYE HALL PAINT MULTIPLE FACULTY OFFICES |  | SKYE HALL | 228 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul D. will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000293 |  | 18P000293 | FALSE | CNAS | SL5 SKYE HALL COPIER ROOM PATCH AND PAINT |  | SKYE HALL | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 32 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000294 |  | 18P000294 | FALSE | CHASS | SL5 HMSS REMOVE DOOR, INSTALL WALL |  | HUM & SOC SC | 3610 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2018-02-01 | [8 empty] | Enrico Baez | Canceled per customer on 7/16/18 via email with Enrico. 5/23/18 EB sent email request for site visit DND 7/14 Hold per customer on prioritization | YES | 2018-07-16 | FS | FALSE | 2018 | 2019-08-16
18P000295 |  | 18P000295 | FALSE | CHASS | SL5 CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL |  | CHASS INT S | 2117J | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-02-01 | [6 empty] | DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18……..DL, 5/24/18; Plans were approved. We need to scheudle the work….DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets.......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date.....DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18...........DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware..... |  | Enrico Baez | 4/25 EB Scoped site. Remove counter and Cage. Drywal closed with electrical. Patch Paint. Cut in two doors in 2117G&H……..DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18…….. | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000296 |  | 18P000296 | FALSE | CNAS | SL5 SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES |  | SKYE HALL | 266 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 31 | FALSE |  |  | 2018-02-02 | [6 empty] | 01/17/19, DL; This project was completed last summer……..DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19 18; I neeed to check on this work order. I thought it was part of the 2nd floor Hallway project but it was not…… |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2019-01-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000297 |  | 18P000297 | FALSE | CHANCELLOR | SL5 SKYE HALL CHECK LOCATION FOR TV INSTALL |  | SKYE HALL | 390 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Dan Lerman |  | 4 | 3 | FALSE |  |  | 2018-02-02 | [6 empty] | 2/1/19, DL; This Project is 100% Complete………1/18/19, DL; This Project is scheduled to be complete next week.….. DL, 5/24/18; Need to verify scope with Enrico…..DL, 7/11/18; Work orders are produced and need to be issued. Target complete date is 9/3/18…. |  | Enrico Baez | EB-scoped on 1/30. Mount TV above table. Advised an articulated mount be purchased. Drawing on FAMMIS WO. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000300 |  | 18P000300 | FALSE | CHASS | SL5 ARTS PATCH AND PAINT - DANCE HALLWAYS |  | ARTS |  | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 24 | FALSE |  |  | 2018-02-02 | [6 empty] | centered. |  | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000310 |  | 18P000310 | FALSE | CNAS | SL5 ADD INTERCOM/BUZZ IN SYSTEM |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-12 | [6 empty] | Dl, 7/4/18; This project is scoped. This will be a new ADA operator, door bell / Intercom and buzzer button to unlock door. Walked work with Contractor, need to work on producing contract with PD&C. Once Contract is confirmed, we will schedule the work..... DL, 7/11/18; We have the proposal. Need to execute the agreement and schedule the work. The target complete date is before 10/1/18.....Dl 8/10/18; Jason will try and complete the work with in the next three weeks......DL, 8/22/18; Jason order parts, parts have 6-8 week lead time. Work will be scheduled when material arrives.....DL, 10/4/18; This Project is 100% Complete....... |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000312 |  | 18P000312 | FALSE | CNAS | SL5 URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 |  | CAMP LOC NOT IN BLDG |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  |  | 38 | FALSE |  |  | 2018-02-13 | [8 empty] | Enrico Baez | Canceled per customer 9/12/18/ EB, 5/29, conducted site visit 5/25. Structure is a double wide modular building/trailer. Space needs to be cleared of equipment, desks, tools. Disconnect electrical, plumbing. Needs professional removal. University Asset see Susan Marshburn for direction. EB, 9/12/18 Per Deborah McWilliams email.Project is cancelled due to lack of funding. | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-08-16
18P000313 |  | 18P000313 | FALSE | GSOE | SL5 SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-15 | [6 empty] | 18W011689 Work order was cancelled because it has the same scope and is a duplicate………DL, 6/16/18; Contract is being awarded this week. Weill are scheduled to have this work completed by fiscal closing……DL, 7/25/18; This Project is 100% Complete…..9/13: Zee - Customer noted paint peeling; updated to status to back in progress for work to be addressed.......DL, 9/19/18; The contractor is on site repairing the walls and painting. The work should be complete this week.......dl, 10/4/18; tHIS PROJECT IS 100% Complete..... |  | Paul Ditty |  | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000314 |  | 18P000314 | FALSE | CHASS | SL5 CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR |  | CA MUS PHOTO | 1000 | COMPLETE | Milagros Pena | Cindy Williams | EMILY PAPAVERO |  | Dan Lerman |  |  | 17 | FALSE |  |  | 2018-02-16 | [6 empty] | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date.......DL, 7/25/18; This project is 100% Complete..... |  | Enrico Baez | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date....... | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000315 |  | 18P000315 | FALSE | BCOE | SL5 BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB |  | BOURNS | B0235 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  | HOLD | TRUE |  |  | 2018-02-16 | [6 empty] | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction to scope, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... Need to walk project with Ron and schedule the work....DL, 5/24/18; Conducted site visit with Ron V. Ron will order material and schedule the work once material is on site.....DL, 6/16/18; Need to verify delivery date for material.......DL. 7/11/18; Plumbing is disconnected. Corey is tentatively scheduled to disconnect the Fume hood. Once the Fume hood is disconnected, we will schedule the removeal of the fume hood and start the framing of the wall. Target complete date is 8/8/18....DL, 7/25/18; Fume hood is disconnected. Need to move Fume hood and start framing target date is delayed to creep scope but should be complete near 8/16/18.....DL, 8/10/18; Carp[enters will install the wall this week. Corey has parts orders. Corey will complete the install when the material arrives.......DL, 8/22/18; This Project is Complete |  | Dan Lerman | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... DND 7/14 Hold per customer on prioritization | YES | 2018-08-23 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000318 |  | 18P000318 | FALSE | CHASS | SL5 CHASS INT S FLAT SCREEN INSTALLATION |  | CHASS INT S |  | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Dan Lerman |  |  | 20 | FALSE |  |  | 2018-02-21 | [6 empty] | 4/15/19, DL; This is 100% Complete….3/28/19, DL; Monitor is installed. Need to finishe power and data next week……2/28/19, DL; Scheduled to complete the install mid March…..2/1/19, DL; Francesca contacted me and informed me this project is now back on the books. She needs to gather more information and order the monitor. When the monitor arrives, we will schedule the installation…….1/29/19, DL; Francesca confirmed this project is not needed and requested this project to be cencelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; we have the brackets. Will scheule the work after the project is approved…..DL, 7/11/18; Work order are not produced. Need to assign and schedule the work…. Target complete date is 8/3/18……DL; 7/25/18; Need to change target date.. |  | Enrico Baez | 5/24/18 Conducted site visit. Met with Ryan Amriano. Electrical near buy. No data connection needed. Awaiting for dept. approval. They first wanted to know if this was possible. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000321 |  | 18P000321 | FALSE | BCOE | SL5 STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST |  | STUDENT SERV | 1228 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Enrico Baez |  |  |  | FALSE |  |  | 2018-02-22 | [6 empty] | DL, 4/29/18; Enrico is cordinationg this. The permits are approved……. DL, 7/11/18; Just received confirmation the door is ready for delivery and installed. I need to check in with Paul about the paint and prep of the door. I also need to check in with Jason on lock hardware......Dl, 7/25/18; Door is painted and ready for install. Called Dugmore to schedule the install. This should be compolete within the next two weeks......DL, 8/8/18; This Project is 100% Complete |  | Enrico Baez | DL, 4/29/18; Enrico is cordinationg this. The permits are approved. EB. 5/11/18- waiting for PO to be issued to Vendor. Customer provided PO numbers, waiting to schedule install with vendor, 5 week lead time. | YES | 2018-08-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000324 |  | 18P000324 | FALSE | PLANNING & BUDGET | SL5 HINDERAKER PATCH AND PAINT |  | HINDERAKER | 4118 | COMPLETE | Gerry Bomotti | Sharyl Murdock | MILLY PAREDEZ |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-02-26 | [8 empty] | Paul Ditty |  | N/A | 2018-07-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000328 |  | 18P000328 | FALSE | ATHLETICS | SL5 HINDERAKER BASEMENT OFFICE REPAIR |  | HINDERAKER |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-01 | [6 empty] | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with Paul. Paul will complete as in the near future. Carpet will be installed shortly after......5/21/18, Painters started paint. Should be complete with paint by the end of the week....DL, 5/24/18; Painters are complete. Jess will schedule the carpet install.....DL, 6/12/18; Project is 98% Complete. Carpenters need to under cut two doors to accomodate the carpet.....DL, 7/11/18; This Project 100% Complete..... |  | Dan Lerman | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with PAul. Paul will complete as in the near future. Carpet will be installed shortly after...... | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000329 |  | 18P000329 | FALSE | CHANCELLOR | SL5 SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST |  | SKYE HALL | 170 | COMPLETE | Kim Wilcox | Karim Zahedi | DA LAN DINH |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18…..DL, 5/24/18; Plans were approved. Demo work has started......DL, 6/12/18; MArshal and Kate are working on Carpet order......DL, 7/11/18; Carpet is ordered. We have a challenge with Title 24. I am working on the title 24 documents. We are still planning to have this project complete on 8/17/18......DL, 8/10/18; We now have the Title 24 plans. The are being reviewed by Bob and Scott.....Title 24 plans approved. Robert is working on PO#. Most parts are on site and Electricans are working on project. All other Trades to follow once Lights are in...... Hard Date of 9/7/18............9/6/18 As of today, Carpet is scheduled for install tomorrow morning and furniture is scheduled for delivery this Monday......WE will more than likely have electrical punch items and touch up paint but this propject should be 100% complete in regards to FS the end of next week next week......100% PROJECT COMPLETE... GREAT WORK DAN! |  | Dan Lerman | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18….. | YES | 2018-09-18 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000337 |  | 18P000337 | FALSE | VC-STU.AFF. | SL5 MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET |  | HEALTH SERV | 414 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-12 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18….Need to work on plans and permits….DL, 7/11/18; Gunther is working on plans. Target complete date is 9/14/18….DL, 7/25/18; Planning to submit plans for review next week. We will schedule the work once we have approved plans…….DL, 8/8/18; This is a structual wall and needs to be engineered. We are meeting with the Structual engineer on 8/9/18 to determine if project is possible.....DL, 8/22/18; Working on EDPA for Structual engineer; project timeline is late Fall. 9/19/18; The Agreement / Cointract for the structual engineer is processed for this project. We should have plans from the structual engineer to submitt to the Building Official and fire marshal with in 4- weeks......dl, 10/4/18; Plans are almost complete and we will submit them for review by the end of the week.....DL, 11/7/18; Plans are approved. WE are schedule to start this Project on Tuesday 11/13/18. Target complete date is by the end of the winter break..... |  | Enrico Baez | Cut wall between rooms 414 and 401, Case and trim opening, install carpet in- DL, 5/10/18; Gloria Vera is the contact; 827-5532 | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000341 |  | 18P000341 | FALSE | CNAS | SL5 PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL |  | PHYSICS | 1132 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-14 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process…DL, 6/16/18; Jess tested the matreial flooring and paint is hot. Jess will abate before we proceed with the project….Still need to scheudle the work. This project target complete date is late Fall……DL, 7/25/18; Jess sent out the 14-day notification to the AQMD last week. We will start the balance of the project after the ACM and Lead is abated or encapsulated…..8/10/18; Abatement is complete. We will work on the other items as time permits. This space is vacant with no occupancy date |  | Dan Lerman | DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process… | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000343 |  | 18P000343 | FALSE | CHASS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER |  | THTR WKSH | 0400A | IN PROGRESS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 2018-03-16 | [6 empty] | 07/11/19 O-ANS: Dan and Chris P will walk the space. 05/21/19 O-ANS: Changed to In Progress per meeting with Dan L. Chris P is the PM for further updates. DL and CP will visit after commencement. 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez | Scope of work has been reviewed; determining how to complete project with trades. 5/11/18 EB-Conducted site visit on 3/21/18. Work based on Safety report written in October. Work consists of replacing door latches to orchestra pit. Adding loading dock rail, Paint frame guard, signage, gate/fall restraints, ladder modifications. | YES |  | FS | FALSE | 2018 | 2019-08-16
18P000344 |  | 18P000344 | FALSE | CHASS | SL5 CHASS INTS PAINT MULTIPLE ROOMS - FACULTY |  | CHASS INT S | 2117E | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 1 | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 7/11/18; This was transferd in to my quque in the past week. I need to scope this project. I belive this is part of project # 18P000205 and 18P000295. If this is part of the other project. We will try to have the paint completed by 8/17/18…......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/10/18; Work has started. We passed rough electrical and framing inspection. The work should be complete in about three weeks......DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18.......DL, 9/6/18; This Project is 100% Complete....... |  | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000346 |  | 18P000346 | FALSE | ATHLETICS | SL5 ATHLETICS INSTALL WALL VOLLEYBALL OFFICES |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-18 | [6 empty] | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. DL, 5/24/18; We will start working on plans in the near future.... DL, 6/16/18; Need to submit plans asap.......DL, 7/11/18; The plans were approved today. This project is scheduled to start on 7/14/18. We will will be complete will all items related to this project on 8/27/18. Note, The door and sidelite are special order items and this item will probalby have a 6-8 week lead time. Steve T is going to order the door soon.. Customer is aware of the delay for the door and is not concerned......DL, 7/25/18; Passed framing and Electrical inspection. We will be finished with the project next week except for the door and window that is ordered but has a 6-8 week lead time. DL, 8/10/18; This Project is Complete except for special order door and window.......DL, 8/22/18; Door and Glass still not on site., Will check in with Steve T on delivery date......Will also schedule final inspection for Certificate of occupancy......9/6/18; The Glass window is installed but we are waiting on the door. this projects is 98% complete.......DL, 9/19/18; The door will be shipped on 9/24/18. We will schedule the door install when the door is on site......DL, 11/7/18; This Project is 100% Complete.... |  | Dan Lerman | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. Will start working on plans.... | YES | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16
18P000347 |  | 18P000347 | FALSE | CNAS | SL5 GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) |  | GEOLOGY | 0 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 31 | Deferred to Fall Quarter - summer priority 27 | FALSE |  |  | 2018-03-18 | [6 empty] | 4/15/19, DL; Thios Project is 100% Complete….3/28/19, DL; Monitor is installed, need to finish power and data………………...2/14/19, DL: The monitor is on site. We need to schedule the installation. 2/1/19, DL; Conducted site visit with Amber. Amber will order the monitor. We will schedule the installation when the monitor is on site………….DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/1 EB Site visit. TV to be mounted on wall above water fountain across from Geo 2306. Center of mount 84" high and centered between wall corner and bulletin board. Will need electrical and data. Computer connection cutout will be in mail room. See W.O. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000348 |  | 18P000348 | FALSE | VC-STU.AFF. | SL5 HUB ADD 3RD FLOOR WALLS |  | HUB | 0353E | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 2 | 6 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/1/19, DL; Per Chris P. This is a PD&C project………..DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Need to walk the project with Manny. Target date is late Fall…….. |  | Enrico Baez | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. EB 5/23/18. Conducted site visit. Request is for adding walls to interior spaces 353F, 381 and 377. Will impact A/C and fire protection. Still waiting for a firm plan from customer. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16
18P000349 |  | 18P000349 | FALSE | BCOE | SL5 PHYSICS INSTALL PARTITION WALL FOR LAB ROOM |  | PHYSICS | 1037 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 5/24/18; Ron V. has detailed scope and he is ordering material. Once material arives, we will schedule the work…. DL, 6/16/18; Materila is ordered, When door/frame arrives, we will prep, paint and start the work…….DL, 7/11/18; This Project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; This is a small partition wall with sound proofing to minimize noise from the compressor that is disruptive to the Helium Ion Microscope…….DL, 4/16/18; We will schedule this work to be complete by the end of the Spring quarter. DL, 5/19/18; Walked project with Ron. FAMIS work order producd and material is being ordered.... | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000351 |  | 18P000351 | FALSE | SoB | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 (S) | 21 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2018-03-19 | [6 empty] | 8/1/19, DL; This project is 100% Complete……7/15/19, DL; Work has started and should be complete on 7/16/19…….. 4/4/19 O-ANS: Moved to Queue to Start to complete during Summer 2019. DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week……8/8/18. The trades are ready to go after they finish current projects…..DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18………. DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date……..9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space……Note. The space is usable and everything works….. |  | Enrico Baez | 4/24/18 EB-scoped. Move screen, correct non-compliant electrical issues, remove&discard overhead projector bracket, relocate heat det. Add switched outles. Plans are needed because we are relocating a heat detector | YES |  | FS | FALSE | 2018 | 2019-08-16
18P000353 |  | 18P000353 | FALSE | CHASS | SL5 PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT |  | PSYCHOLOGY1 | 1111A | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 26 | FALSE |  |  | 2018-03-20 | [6 empty] | DL; 7/4/18;This project is scoped. We will only paint one out of the two offices. Working on PO# to install frosted glass with Sun Down Window coverings……DL, 7/25/18; PO# is produced and material is ordered. Target date mid August…….DL, 8/22/18; This project is complete.... |  | Paul Ditty |  | N/A | 2018-08-23 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000354 |  | 18P000354 | FALSE | CNAS | SL5 GH16-25 COOLING SYSTEM REPAIR |  | GH 16 25 |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | MARK TANKERSLEY |  | Dan Lerman |  | 13 | 17 | FALSE |  |  | 2018-03-20 | [6 empty] | DL, 7/25/18; Reviewed Ron V. noted. I will check in with Chris on this to better determin the method complete this project. |  | Dan Lerman | DL, 5/5/18; This is a repair, No alterations taking place. Pasted from FAMIS work order...THE COOLING SYSTEM ON GH 16-25 IS FALLING APART SHEET METAL TRAYS HAVE TONS OF HOLES, WOOD ROTTING ETC. PLEASE REPAIR….. RV, 07/06/18: Dan, Chis Pillen and I have walked this project months ago and have a quote from Ralph Cox/KIRA Construction to repair the head house damages. See Chris for the status of subletting this work. | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-08-16
18P000356 |  | 18P000356 | FALSE | CNAS | SL5 ENTOMOLOGY PATCH AND PATCH |  | ENTOMOLOGY | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 10 | TRUE |  |  | 2018-03-20 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000363 |  | 18P000363 | FALSE | BAS | SL5 PAINT STOREHOUSE ADMINISTRATIVE OFFICE |  | CORP B |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | ERICA HENDERSON |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-03-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000367 |  | 18P000367 | FALSE | CHASS | SL5 CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE |  | CHASS INT N | 3033 | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 23 | FALSE |  |  | 2018-03-27 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000369 |  | 18P000369 | FALSE | BAS | SL5 BOYCE X-RAY IRRADIATOR PROJECT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 1407 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | KAREN JANIGA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-27 | [6 empty] | 12/14/18, DL; This project was cancelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……DL, 5/9/18; Need to work on plans/permits…..DL, 6/16/18; Meeting with Bob and confirmed what is needed. I will work with Gunther on plans. Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall…..DL, 11/7/18; Material is on site. We will schedule the work soon…… |  | Ron Veloz | DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……Need to work on plans….10/17/18 RV: This project was previously scoped and in Plan development. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-16
18P000373 |  | 18P000373 | FALSE | BAS | SL5 POLICE BLDG PAINTING IN DISPATCH AREA |  | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  |  | 8 | FALSE |  |  | 2018-04-02 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000379 |  | 18P000379 | FALSE | VC-RED | SL5 UOB PATCH AND PAINT |  | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-05 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000380 |  | 18P000380 | FALSE | SOM | SL5 SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 | SOM RSCH | 330 | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-05 | [6 empty] | Canceled per customer on 8/22/18. |  | Enrico Baez | DD 7/17: Requested Enrico verify complete customer did not prioritize and noted work was done. 8/7/18-Conducted site visit-do not recommend location for TV due to potential damage from barn door type window screen. 8/15/18 emailed Tara Bathol that desired location for TV not recommended. Requested alternate location. 08/22/18 Ron V. Spoke with Tara. Tara confirmed the requestor cancelled the TV mounting bracket request after conversation with Enrico | NO | 2018-08-22 | FS | FALSE | 2018 | 2019-08-16
18P000381 |  | 18P000381 | FALSE | ITS | SL5 ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 3 | 4 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL; This project is complete. Note, Duffy only wanted the dutch door completed……..12/14/18, DL; This project is in progress and should be complete shortly after the new year……`DL, 7/11/18; Need to walk the project and schedule the work…… | 2018-07-06 | Ron Veloz | 06/26/18 Ron V. visited site & met with Duffy. Scope of work for rm's 2103 & 2103 A requires: Painting of walls and conduit locted on the walls, replace damaged ceiling tiles, replace one damaged prismatic 2x4 light fixture lense, remove one tack board and shampoo carpet. Existing wall tiles to remain and receive paint. No work required in 2103 B per Duffy. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | 2019-01-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000382 |  | 18P000382 | FALSE | ITS | SL5 ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | PHYLLIS FRANCO |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL, This project is Complete……12/14/18, DL; This project is scheduled to be complete shortly after the winter break…….This project was scoped previously with the IR Team. We may need plans or a permit because we are installing a Dutch door…..DL, 7/11/18; Need to produce work orders and schedule the work….. DL, 7/25/18; Still need to produce work orders and schedule the work. Target date is 10/1/18 | 2018-07-06 | Ron Veloz | 06/29/18 Ron V: SOW, Remove the existing non rated solid core door & grille and replace with a new maple veneerd Dutch door with prefinished clear coat without grille. Door to be prepped on the hinge side with one continoues hinge. Confirm/field verify is a double bevel on door is requird. Do not prep the strike/lockset side.. Cylinder to be bored onsite by Lock shop. The top of the lower door to have a small shelf + - 6-8 inches wide, confirm size with Duffy prior to ordering the door. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | 2019-01-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000383 |  | 18P000383 | FALSE | CHASS | SL5 HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT |  | HUM & SOC SC | 1302 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  | 4 | TRUE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000385 |  | 18P000385 | FALSE | CHASS | SL5 HMSS INSTALL TV IN CONFERENCE ROOM |  | HUM & SOC SC | 1001E | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Dan Lerman |  | 19 | 19 | FALSE |  |  | 2018-03-06 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..12/14/18; Monitor is Complete, we still need to install power. The space is vacant…DL, 6/16/18; Pasted notes from FAMIS; University Writing program wants to install a 65 inch TV in the conference room at HMNSS 1001E. 1. Request to install the TV mount/ bracket on the wall; 2. Request to remove the old projector screen but leave two wood blocks on the wall; 3. Request to add a new double power outlet around the TV bracket area. If you have any questions, please contact Shanshan Liao at (shanshan.liao@ucr.edu or X27753)……DL, 7/25/18; Work orders are not produced. Need to assign and schedule the work…..……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | 6/11/18 Install TV above wainscot. Notes in FAMMIS. Need electrical and date cut ins. | YES | 2019-03-18 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000387 |  | 18P000387 | FALSE | CHASS | SL5 HMSS PATCH/PAINT |  | HUM & SOC SC | 3600 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 28 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000388 |  | 18P000388 | FALSE | CNAS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 2018-04-10 | [6 empty] | 8/14/19, DL; This project is 100% Complete………8/1/19, DL; This project work from Facilities Services should be complete in about 2- weeks…..7/15/19, DL, Work is in progress. Goal is to be complete with our scope near the first week in August……6/17/19, DL; This will be scheduled in July…….5/31/19, DL; Demo and removal of the dishwasher is. We will work on the installation and elctrical / power connections over the next three weeks. Note. Steam shut down is taking priority and the installation may be delayed….. 5/15/19, DL; We will schedule the work……..DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but there is no hard date as this is vacant space and we will access the space as time permits…… DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter….DL, DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans….7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved….. |  | Enrico Baez | 6/21/18 EB Remove old glass washer and install washer 400XLS. Disconnect steam, air, water, electrical, vent hood. Install new washer, electrical, step up x-former 208v to 480. Dept. to purchase x-former $5000 ill to dept. Elect. To provide specs. | YES |  | FS | FALSE | 2018 | 2019-08-16
18P000389 |  | 18P000389 | FALSE | CHASS | SL5 PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A |  | PSYCHOLOGY1 | 2122 | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 5 | TRUE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000390 |  | 18P000390 | FALSE | PLANNING & BUDGET | SL5 UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD |  | UV BLDG B | 0240B | COMPLETE | Gerry Bomotti | Sharyl Murdock | LESLIE ROSE |  | Paul Ditty |  |  | 1 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000391 |  | 18P000391 | FALSE | BCOE | SL5 PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN |  | CHUNG HALL | 446 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 5/5/18; Conducted scope visit with Paul and Maggie. This project is target date is August 30th. As of now, we have 10 business days to complete the work……. Dean's Office….DL, 6/16/18;Walked project with Jess and Paul. This will be a project will now incluclude flooring is 7- additional offices due to additional trip hazzards identified in 3 of 7 offices during the carpet scope. Maggie will pay four four of the office since they are still in good condition. We are still on schedule with the work.......Dan, 7/11/18; This project is still on schedule. Complete Date is 8/18/18 and scheduled to be complete on 8/31/18.....DL, 8/10/18; The project is on schedule and we will start on Monday.......Ahead of schedule, project will be complete on 8/29/18......DL, 9/6/18; This project is 100% complete. Note, Maggie did request Jess to come back and remove some glue and he has this scheduled..... |  | Dan Lerman |  | YES | 2018-09-10 | FS | FALSE | 2018 | 2019-08-16
18P000392 |  | 18P000392 | FALSE | CNAS | SL5 BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 |  | BATCHELOR | 0 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  |  | 8 | TRUE |  |  | 2018-04-12 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000394 |  | 18P000394 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK |  | BOURNS | A0159A | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 2 | TRUE |  |  | 2018-04-12 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………….1/15/19, DL; Sound Soak is ordered and should arrive within two weeks……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; Need to review and scheudle…….DL, 7/11/18; Still need to review and scheudle…..DL, 8/22/18; This Project is complete but Maggie wants to see if the Faculty are happy with the results. We may install Sound Soak as a final option…… DL 9/6/18; Sent Maggie an email to see if she is satified with the work performed in regards to the sound proofing. I will have an update by the next Excel update….. DL, 9/19/18; The PI is out of town. Maggie will confirm the PI is satisiofd with the work when they return……on 9/18/18…DL, 10/8/18; Customer not satisfied with first round of sound proofing. We will proceed with Sound Soak material….. |  | Enrico Baez | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. EB 6/1 site visit- 3 door between 4 offices require sound proofing. Doors measure 36" x 106". Photos in FAMMIS. O-RVL: Uploaded sound soak panel data on FAMIS and is available on the Project Server File. 10/18/18 O-RVL: Per FS team meeting, we now have a clarified process that sound soak is not included in the SLA due to the fact this is not part of the work we perform at FS. Because we already committed to do further follow up with the sound soak, we will not charge this time but moving forward sound soak will be a recharge service as the team does not have the skillset to do the work and therefore outside the SLA. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000396 |  | 18P000396 | FALSE | CHASS | SL5 WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | Please patch and paint these two Political Science Staff Offices in the Watkins Hall 2122 "suite". 2122A belongs to Tanya Wine, FAO; 2122D belongs to Cindy Redfield, Principal Analyst. | WATKINS | 2122 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS | CINDY REDFIELD | Paul Ditty |  |  |  | TRUE |  |  | 2018-04-13 | [6 empty] | 08/10/18 D-MMN: Completed painting the finish. Pulled our masking and plastic wiped down the furniture. Replaced fixture covers. vacuumed the carpets and moved furniture back.08/07/18 D-MMN: Removed anchors, related boards. Filled holes with spackle and topped with joint compound. used one 4x4 wall patch. Returned and applied second coat of joint compound. 08/09/18 D-MMN: Completed applying primer, and then began applying Suprema. 08/08/18 D-MMN: Removed steel case and file cabinets from walls. Pulled anchors and filled with smooth se 20 and 2 coats of joint compound. Also finished any other patching. Taped the base and fixtures and covered furniture with plastic. Used a fan to dry patching. Sanded patches and began primer. Vacuumed debris. |  | Paul Ditty | Complete as of 8/24/18 **7/30/18 ROUTED TO D-PDY FOR SUMMER QUARTER MINOR RENO EXECUTION; PRIORITY 6 AND FOR FACULTY HIRE "YES" (Stephen C) | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000400 |  | 18P000400 | FALSE | SOM | SL5 Covert suite 1116 and suite 1126 to office space | Provost has placed a hold on converting lab spaces into office spaces. | WEBBER | 1116 & 1126 | CANCELED BY FS | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-14 | [6 empty] | DL, 6/16/18; Waiting for update on Provost approval….DL, 7/11/18; Per email from Enrico on 7/10/18. The Provost put a hold on converting any lab space into officess…… |  | Enrico Baez | 3/7/19 O-ANS: Project no longer moving forward per Ron Rector. 5/1 EB Convert two wet labs into offices. Same as Webber 2278. Abate floor, demo all cabinets, remove plumbing, patch & paint. Carpet tile. Equipment comes out. Awating Provost, Sheryl Murdoch and Bob Williams approval….. 7/11/18 EB-Per Brandon Barbosa project will be cancelled | YES | 2018-07-10 | FS | FALSE | 2018 | 2019-08-16
18P000410 |  | 18P000410 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 3148B | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-25 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000414 |  | 18P000414 | FALSE | CHANCELLOR | SL5 CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL |  | STUDENT SERV | 0 | COMPLETE | Kim Wilcox | Karim Zahedi | DANIELLE GARCIA |  | Paul Ditty |  | 1 | 2 | FALSE |  |  | 2018-04-26 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000415 |  | 18P000415 | FALSE | CHASS | SL5 PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | Door and frame have been painted; construction to commence upon availability of the teams. | OLMSTED | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | RYAN LIPINSKI |  | Dan Lerman |  |  | 10 | TRUE |  |  | 2018-05-08 | [6 empty] | 12/14/18, DL; Angel cancelled this project as it is no longer needed at this time……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 7/11/18; This project was scoped and part of the IRT. Plans and permits are approved. We will schedule the work and we will plan to have this project complet by 9/21/18…..8/10/18; WE have approved plans, this project is scheduled to start late August and will be complete early October……DL, 10/4/18; The door and frame is scheduled for delivery in 3-5 weeks, We will start the project when the doors and frame are on site……..DL, 11/7/18; Door and frame and painted. We will start the contruction in the near future…… |  | Dan Lerman |  | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-16
18P000416 |  | 18P000416 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTOR OFFICE PAINTING |  | HUM & SOC SC | 3002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000417 |  | 18P000417 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTIONAL OFFICE PAINTING |  | HUM & SOC SC | 2106 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000418 |  | 18P000418 | FALSE | CHASS | SL5 HMSS OFFICE PAINTING |  | HUM & SOC SC | 2002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 15 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty | 5/23/18 EB- Sent email to Jill requesting site visit. 5/23/ 18 EB- Scoped. Mount & TV on site. TV bottom edge to be mouted 48" from floor centered on West wall. Needs electrcal cut out and data. Entered in FAMIS. | N/A | 2018-07-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000419 |  | 18P000419 | FALSE | CHASS | SL5 COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | FS to coordinate with client to scope the work. | WATKINS | 1320C&E | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 5 | 8 | TRUE |  |  | 2018-04-27 | [6 empty] | 2/14/19,DL; This project was canceled by Paul R. 2/1/19, DL; We will custom make Sound panels and will start the installation in the next 6-8 Weeks……….. |  | Enrico Baez | 7/6/18 EB emailed Paul Richardson to schedule site visit 7/17/18 EB Scheduling site visit with Paul R. 8/7/18 EB-Job was part of an IRT. Dan said he will scope 8/20/18 EB emailed Lilia to schedule site visit. 8/24/18 EB scheduled site visit for 8/28/18 at 11:00AM 8/28/18 E.Baez- Met with Paul Richardson, Lilia Vega and Becky Campbell. Instead of tearing down walls and building new ones, they wanted to see if installing sound soak on three walls were possible, it is. They will then need to have their Dean approve the sound soak. Clients were sent an email with drawing indicating desired location of sound soak. | NO | 2019-02-14 | FS | FALSE | 2018 | 2019-08-16
18P000420 |  | 18P000420 | FALSE | CHASS | SL5 COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | Canceled by Customer on prioritization 7/2/18 | WATKINS | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  |  |  |  | Cancel | TRUE |  |  | 2018-04-27 | [10 empty] | YES | 2018-07-02 | FS | FALSE | 2018 | 2019-08-16
18P000421 |  | 18P000421 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 2120 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-04-30 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000425 |  | 18P000425 | FALSE | BCOE | SL5 BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - |  | BOURNS | A0379 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; Luat Vuong arrives on or about August 15…... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected..…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/15/18........DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000426 |  | 18P000426 | FALSE | BCOE | SL5 BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER |  | BOURNS | A0375 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; A-375: Bhargav Rallabandi arrives on or about August 1….. DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/1/18.....DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-08-16
18P000427 |  | 18P000427 | FALSE | BCOE | SL5 BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER |  | BOURNS | A0373 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie email; This is our new Dean’s faculty office. Dean Lynch is already on site getting up to speed one-two days a week. This office is an ASAP...... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected.....DL, 7/11/18; This project is 100% complete...... |  | Paul Ditty | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000428 |  | 18P000428 | FALSE | SoB | SL5 OLMSTED RM 2352 PATCH/PAINT |  | OLMSTED | 2352 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-05-02 | [8 empty] | Paul Ditty |  | N/A | 2018-08-17 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000429 |  | 18P000429 | FALSE | BCOE | SL5 INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 |  | BOURNS | B0262 B0256 | COMPLETE | Christopher Lynch | Maggie Souder | KEVIN SCHULTE |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment…..DL, 5/9/18; We are working on plans to submitt to A&E soon....DL, 5/24/18; Plans were submitted on 5/24/18.......DL, 6/12/18; Plans were approved. Cabinets are ordered. Materila is 6-8 Weeks out.....DL, 7/11/18; We have confirmation for delivery of material for mid August. Target Complete date is 9/7/18......DL, 8/10/18; Project has started. We will be complete with in two weeks......DL, 8/22/18; Work is 90% Complete..Project should be complete by 8/31/18........ DL 9/6/1/8; This project is 99% complete. The parts arrived today. I will be sending out an email to schedule the installation time for next week.......DL, 9/19/18; This project is 100% Complete........ |  | Dan Lerman | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment….. | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000432 |  | 18P000432 | FALSE | BAS | SL5 BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 |  | BANNOCK H | H0101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-05-04 | [8 empty] | Paul Ditty |  | N/A | 2018-07-13 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000434 |  | 18P000434 | FALSE | CNAS | SL5 BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY |  | BOYCE | 4478 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Paul Ditty |  |  | 3 | TRUE |  |  | 2018-05-09 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000435 |  | 18P000435 | FALSE | CAMPUS | SL5 HMSS HYDRATION STATION REQUEST |  | HUM & SOC SC | 3600 | COMPLETE |  |  | NELDA THOMAS |  | Dan Lerman |  |  | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 4/15/19, DL; This project is 100% Complete…..3/28/19, DL; Fountain is in. working on power and paint….. |  |  | 3/4/19 DND Removed from FS Hold Per Ron Rector | NO | 2019-04-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000436 |  | 18P000436 | FALSE | CNAS | SL5 COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS |  | COLL BLDG SO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 36 | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000438 |  | 18P000438 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING |  | CHUNG HALL | 415 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 10 | FALSE |  |  | 2018-05-14 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000439 |  | 18P000439 | FALSE | BCOE | SL5 CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING |  | CHUNG HALL | 315 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 11 | FALSE |  |  | 2018-05-15 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000442 |  | 18P000442 | FALSE | VC-RED | SL5 FAWCETT LAB 203 PATCH & PAINT |  | FAWCETT LAB | 203 | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 3 | FALSE |  |  | 2018-05-18 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000444 |  | 18P000444 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 |  | ARTS | 242 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-05-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-09-21 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000445 |  | 18P000445 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 |  | ARTS | 225 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 11 | TRUE |  |  | 2018-05-21 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | FS to coordinate with client to scope the work. | DELFINO HHSE |  | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | [6 empty] | 5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Scope completed per DL. | YES |  | FS | FALSE | 2018 | 2019-08-16
18P000454 |  | 18P000454 | FALSE | BCOE | SL5 BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS |  | BOURNS | A0346 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  |  | 9 | FALSE |  |  | 2018-05-29 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000456 |  | 18P000456 | FALSE | VC-STU.AFF. | SL5 HUB--UTILITY METERS | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. | HUB |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-05-30 | [8 empty] | Enrico Baez | 1/24/19 EB Contacted Jonathan Bianchet of Design West for results of site evaluation. Will have report by middle of following week. 11/29/18 EB Met with Design West and HUB staff. Conducted site visit. Waiting for recommendations from Design West. 7/6/18 EB-emailed Brendan to schedule site visit. 7/11/18 EB- Site visit schduled for 7/12/18 7/16/18 Conducted site. Customer wants to have SEP metered for all food vendors. Requested electical power plans from Gunther 8/7/18 Contacted Design West for proposal of feasibility stud 8/15/18 Advised Brendan Obrien to submit request to CPMS as this work will not be self performed. Sent Brendan copy of proposal for sight assessment. | YES | 2019-01-24 | FS | FALSE | 2018 | 2019-08-16
18P000459 |  | 18P000459 | FALSE | BAS | SL5 BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 |  | THE BARN |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | Dan Lerman |  |  | 6 | FALSE |  |  | 2018-05-31 | [8 empty] | Enrico Baez | 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 6 | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000463 |  | 18P000463 | FALSE | SoB | SL5 ANDERSON HALL PATCH/PAINT-102C |  | ANDERSON 1 (N) | 0102C | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-06-04 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000464 |  | 18P000464 | FALSE | CNAS | SL5 PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 35 |  | FALSE |  |  | 2018-08-16 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000468 |  | 18P000468 | FALSE | CHASS | SL5 WATKINS 1222/1223 PATCH/PAINT |  | WATKINS | 1222 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 13 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000469 |  | 18P000469 | FALSE | CHASS | SL5 WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS |  | WATKINS | 1317 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | 2018-07-25 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000470 |  | 18P000470 | FALSE | SPP | SL5 Student Check-in Lobby |  | CHASS INT S | 4133 Corridor | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-11 | [6 empty] | DL, 6/16/18; I walked this project with Luis and Mark this week. They want this work completed by July 9th. Paint, data, electrical, chair rail and signage is requested. I need to review project with Paul and Robert C. DL, 7/11/18; Robert C. Ordered material and we will complete the install first part of next week We will scheudle the paint after Robert is Complete. Target Complete Date is 7/2018......DL, 7/25/18; WE have the electrical materila, plans were submitted. Once plans are reviewed and approved, we will proceed with the work. Target date is two weeks after plans are approved......DL, 8/10/18; Eletrical is complete. Pending paint. Paint will be scheduled in the near future. DL, 8/22/18; This project will be Complet on Saturday.....DL, 9/6/18. I miossed the chair rail request on this project. I will order the chair rail in the near future. The chair rail is the only item needed to complete this project. Aprroximately 20 lineal feet......DL, 9/19/18; Chair rail is ordered. We will schedule the install when the material arrives....... |  | Dan Lerman | Added by customer on prioritization; timeline and scope tbd. 4/25 EB emailed Christina to schedule site visit. No work order Luis to submit Google doc. To A&E sevral trades invlved. DND 6/13 Project rescoped and priorities adjusted per meeting between Dan and Luis Alvarez. | YES | 2018-08-23 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000471 |  | 18P000471 | FALSE | ITS | SL5 WCH INSTALL SECURITY FENCE |  | CHUNG HALL | 134 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  |  | 5 | FALSE |  |  | 2018-06-12 | [6 empty] | DL, 7/4/18; Walked this project with Angel, This request is to install security fence with Sliding gate and welded webs to increase security. Space is vacant and ready to schedule work. Need to walk with Corey to see if this is a project they can do or sub out to De ANza fence......DL 7/25/18; Still need to walk project with Corey. Dl, 8/10/18; Site walk complete, we are waiting on estimates. WE will try and schedule the work with in the next 30- days....DL, 8/22/18; Work is scheduled for August 27th. Still need to order hardware.....DL, 9/6/18; The fence is installed and Angel is very Happy, but I need to check the project to verify we are good to go....DL, 9/19/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000472 |  | 18P000472 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALL |  | CHUNG HALL | 458 | COMPLETE | Christopher Lynch | Maggie Souder | JANNA LE BLANC |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000473 |  | 18P000473 | FALSE | CNAS | SL5 PIERCE NEW CARPET & PAINT FACULTY OFFICE |  | PIERCE | 202 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 1 | 5 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | 2018-09-26 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000474 |  | 18P000474 | FALSE | ITS | SL5 MS&E ELECTRICAL MODIFICATIONS FOR ITS |  | MAT SCI ENGR | 119 | COMPLETE | Danna Gianforte | Shelley Gupta | MICHAEL CAPRIOTTI |  | Robert Corey |  |  | 1 | FALSE |  |  | 2018-06-13 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…….2/28/19, DL; Work is scheduled with Darrenn F. for Spring Break…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. |  | Enrico Baez | 7/17/18 EB-Scheduling site visit with Michael Capriotti 8/7/18 EB- Met with Robert Corey to discuss scope of work. He will coordinate work. | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000476 |  | 18P000476 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER & DRYER | Canceled project, work completed on 18W015691 in July. | BOYCE | 6444 | CANCELED BY CLIENT | Michael Pazzani | Laura Manor | DIERK BIGGS |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-14 | [6 empty] | Duplicate to 18W015691; complete |  |  | Duplicate to 18W015691 | NO | 2018-07-11 | FS | FALSE | 2018 | 2019-08-16
18P000478 |  | 18P000478 | FALSE | UNDERGRAD ED | SL5 CARPET, PAINT, & AIR HANDLING MODIFICATION |  | HINDERAKER | 1120H | COMPLETE | Jennifer Brown | Tracey Scholtemeyer | TRACEY SCHOLTEMEYER |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-16 | [6 empty] | DL, 7/4/18; This project is scoped; Need to remove Switch gear storage rack components, remove electrical conduits, plywood backer board from walls, paint and floor covering. We will schedule this work to be complete by Fall 2018 academic year....DL, 7/11/18; Need to produce work orders and schedule the work. Target Complete date is 9/14/18... Space is vacant....DL, 8/10/18; Work has started and we are on schedule...... DL, 8/22/18; Demo is almost complete. This target date is 9/21/18......9/19/18; All trades are complete. New carpet to be installed on 9/21/18. .....DL, 9/19/18; This project is scheduled to be complete this week....... |  | Dan Lerman | 7/9 EB-Spoke with Dan, he has already scoped this. | YES | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000480 |  | 18P000480 | FALSE | CNAS | SL5 BG - LOWER RESTROOMS-PAINTING-FLOORS | Canceled by Facilities Services; Work is not within the SLA and is not needed. | BOTGDN RSTRM |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-09-01 | FS | FALSE | 2018 | 2019-08-16
18P000481 |  | 18P000481 | FALSE | CHASS | SL5 CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 |  | CHASS INT S | 3104 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000482 |  | 18P000482 | FALSE | SoB | SL5 CARD ACCESS SYSTEM ANDERSON SOUTH |  | ANDERSON 2 (S) |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-26 | [6 empty] | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with JasonDL, 7/11/18; Need to check in with Jason on status for his side of the project.....DL, 7/25/18; JAson's team is ready to install but the Anderson IT department does not have the necesary software. We will start the work when the software is up and running...... 8/12/18 DND FAMIS Status noted completion on 8/2/18. |  | Dan Lerman | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with Jason | YES | 2018-08-02 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000483 |  | 18P000483 | FALSE | BAS | SL5 INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | FS to coordinate with customer to scope the work. | P1 |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | AMANDA GREY |  | Enrico Baez |  | 7 |  | FALSE |  |  | 2018-06-26 | [6 empty] | Waiting for Amanda Grey to verify ownership of chain link fence. Once confirmed will contract with De Anza to install 36" wide gate. | 2018-08-29 | Enrico Baez | 12/3/18 EB-Cancelled request per email from Amanda Gray. Will resubmit request when funding is available. 10/1/18 EB-Contract De Anza Fence to have a gate installed at chain link fence leading to storm culvert in parking lot 1. | YES | 2018-12-03 | FS | FALSE | 2018 | 2019-08-16
18P000484 |  | 18P000484 | FALSE | ATHLETICS | SL5 INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | Project will be managed by A&E for completion. | SOFTBALL STG |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-26 | [6 empty] | 2/1/19, DL; This is a PD&C Project due to IRT walk. Project will exceed $50,000……….. |  | Enrico Baez | 12/6/18 EB Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | NO | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16
18P000485 |  | 18P000485 | FALSE | SOM | SL5 SOMR PATCHING AND PAINTING |  | SOM RSCH |  | COMPLETE | Deborah Deas | Brandon Barbosa | DANA ABOU ABBAS |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18P000486 |  | 18P000486 | FALSE | CNAS | SL5 PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 2018-06-28 | [6 empty] | 8/1/19, DL; This project is 100% Complete…… 6/17/19, DL; This project is making good progreess and will be complete near mid- July…..5/31/19, DL; This project is making good progress and we are hopeful to be complete on or before July 1st……5/1/19, DL: This project is in grogress and moving forward. Target complete date is 6- weeks… 4/15/19, DL; Started Demolition phase….2/28/19, DL; We will work on the plans in the next 30-days.12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman | Dan L. scoped this project as part of an IRT…. 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. If possible paint to match existing green accent wall, if not white is fine. Mount monitor bracket to wall centered side to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | YES |  | FS | FALSE | 2018 | 2019-08-16
18P000487 |  | 18P000487 | FALSE | CHANCELLOR | SL5 SKYE HALL PATCH HOLES AND PAINT |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | Karim Zahedi | SONIA ZAMORA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18W000455 |  | 18W000455 | FALSE | CNAS | SL5 CHAPMAN CLEAN WINDOWS |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  | 37 | FALSE |  |  | 2017-07-11 | [6 empty] | Dl, 7/4/18; All Windows in Chapman were cleaned by Ductch Touch. This Project is 100% Complete |  | Ron Veloz |  | YES | 2018-07-11 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18W001170 |  | 18W001170 | FALSE | CHASS | SL5 ARTS: PAINT CLASSROOMS |  | ARTS | 407 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 27 | FALSE |  |  | 2017-07-25 | [8 empty] | Enrico Baez | DD 10/6: Enrico scoped; requested during break - coordinating with client to complete on a Saturday | YES | 2018-09-24 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18W006022 |  | 18W006022 | FALSE | SOM | INSTALL CURTAIN ROD IN RESEARCH SPACE |  | SOM RSCH | 336 | COMPLETE | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-10-27 | [6 empty] | DL, 5/24/18; Need to review scope with Enrico….DL, 7/11/18; Enrico produced work orders for sheet metal shop. This is a singel trade project. |  | Enrico Baez | Blackout curtain needs to have a better way of being secured. Talked to Cory about fabricating a new curtain rod. 7/6/2018EB assigned to sheetmetal shop F-LNH | YES | 2018-07-11 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
18W007453 |  | 18W007453 | FALSE | ITS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-11-30 | [6 empty] | 07/22/19 O-ANS: Work Order converted to project # 19P000433. For further updates, see 19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  |  | WO converted to project #19P000433. |  | 2019-07-22 | FS | FALSE | 2017 | 2019-08-16
18W008762 |  | 18W008762 | FALSE | CHASS | SL5 HUMANITIES: PATCH & PAINT |  | HUM & SOC SC | 2415 | COMPLETE | Milagros Pena | Cindy Williams | ANDREW ALONSO |  | Paul Ditty |  | 20 | 22 | FALSE |  |  | 2018-01-02 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18W009630 |  | 18W009630 | FALSE | BAS | SL5 BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. | PHYS PL STOR | 100 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | JUDY HODGE |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-22 | [6 empty] | 3/28/19, DL; This project is cancelled per Judy Hodge….DL, 6/16/18; Project includes demo wall/door install new wall, dry wall, paint, door, eletrical outlets, lighting, smoke relocation, lighting motion, new t-bar, relocate heat pump, andn install new carpet…...DL, 7/11/18; Need to work on plans….. Target complete date is late Fall..... |  | Enrico Baez | See work order 18W012349 scoped and annotated in FAMMIS. 6/11/18 EB- Add wall to current space and eliminate exisiting wall. Relocate exisiting A/C on wall. Minor electrical DND 7/14 Hold per customer on prioritization; per Corp Yard Space Planning | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-08-16
18W011161 |  | 18W011161 | FALSE | CNAS | SL5 REPLACE CARPET |  | SCIENCE LAB1 | 301 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-23 | [6 empty] | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project……DL, 5/21/18; Floor covering is selected. Work will be scheudled for Mid June….DL, 5/24/18; The install is scheduled for June 18th & 19th……DL, 7/11/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project…… | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18W011672 |  | 18W011672 | FALSE | CNAS | SL5 ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY |  | ENTOMOLOGY | 268 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-03-08 | [6 empty] | Relocate white board from East wall onto the West wall, where high table was removed, 24" away from North end of wall. |  | Paul Ditty |  | N/A | 2018-07-25 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18W011691 |  | 18W011691 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | FS to coordinate with client to schedule work for completion. | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 4 | 11 | TRUE |  |  | 2018-03-08 | [6 empty] | 12/17/18 DND: Canceled by client on 12/17/18. |  | Paul Ditty |  | N/A | 2018-12-17 | FS | FALSE | 2018 | 2019-08-16
18W011692 |  | 18W011692 | FALSE | CNAS | SL5 ENTOMOLOGY; PAINT/PATCH LAB |  | ENTOM MUSEUM | 211 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-03-08 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18W011772 |  | 18W011772 | FALSE | BAS | SL5 PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | Canceled per customer on priority list 7/3/18 | PRINT MOD |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Dan Lerman |  |  | Canceled | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/29/18; Pasted from WO; install an outside electrical outlet based on the attached amazon specs. also estimate for removing and sealing the outside vent from the copier. fyi_the copier will be moving within the next few months…..DL, 7/11/18; Need to verfy scope and schedule the work...... |  | Enrico Baez | fyi_the copier will be moving within the next few months | YES | 2018-07-03 | FS | FALSE | 2018 | 2019-08-16
18W013160 |  | 18W013160 | FALSE | CNAS | BEES- PATCH & PAINT 2460D & 2460F |  | GEOLOGY | 2460 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 33 | 29 | FALSE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18W013973 |  | 18W013973 | FALSE | VC-RED | SL5 BSL3 FACILITY- ASSEMBLE AND INSTALL |  | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2018-04-19 | [6 empty] | FAMIS NOTES 8/22: Plumbing filter system was installed and ice maker installed. Request for microscope and incubator moved into containment by customer. Complete 9/24/18 |  | Enrico Baez | 5/16/18 EB conducted site visit. 5/22/18 EB appliances dented, vaccum pump not on site. 6/19/18 emialed Chrystal to see if appliance have been replaced. 7/16/18 emailed Chrystal Jimenez asking for update. 8/7/18 EB Replacement appliances | YES | 2018-09-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18W015691 |  | 18W015691 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER AND DRYER |  | BOYCE | 6444 | COMPLETE | Michael Pazzani | Laura Manor | DIERK BIGGS |  |  |  |  | 1 | FALSE |  |  | 2018-05-30 | [6 empty] | DL, 7/11/18; This project is in progress and almost complete. Target complete date is 7/20/18….. |  | Dan Lerman |  | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18W016588 |  | 18W016588 | FALSE | CHASS | PATCH AND PAINT FOR FACULTY |  | SPROUL | 4105 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | N/A | TRUE |  |  | 2018-06-19 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
18W016621 |  | 18W016621 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2018-06-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
1990a | 1990a |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | Under construction | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2193000 |  | 2015-10-09 | Complete Construction | 2019-05-01 | 2019-11-16 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
1990b | 1990b |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon-Road | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | In Design | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE |  |  | 2018-06-22 | Finalize Design | 2019-11-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-08-16
19P000006 |  | 19P000006 | FALSE | CNAS | SL5 MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 |  | MAT SCI ENGR | 310 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..2/14/19, DL; This project is 90% Complete. ………2/1/19, DL; This Project started to day. We are scheduled to be complete by the end of February………..1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. | 2018-09-28 | Ron Veloz | 10/30/18 RV: Spoke with Deborah McWilliams, today. Project to remain as prioritized(#3) for new Faculty. 10/17/18 RV: Floor plan is on the server folder. RV: 10/03/18: Install metal stud wall at center of the room. Remove one door blank and install one lockset.Requires, Framing, drywall, tape, sand, paint, t-bar modifications and rubber base. PM to verify with user if power and Data will be required in the new wall. 09/28/18 O-RVL: Completed SOW: Add Wall in the center of room. Include a new Metal Stud Wall with rubber base to match existing. Remove metal cover at ceiling. Remove door lock blank and install new lockset at left door. RV completed SOW & placed on FS server. Updated FAMIS and Minor Reno List. 09/27/18 O-RVL: Site walk with Chris P, Dan L. Mayela and Deborah McW. FS to re-install the metal stud wall to original place dividing the room equally. Scoping completed. 09/26/18 O-RVL: 19P000006-Scheduled a site walk scheduled with Dan. Will contact Deborah and Mayela for their participation. | YES | 2019-03-18 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000009 |  | 19P000009 | FALSE | SOM | SL5 SOME -- PAINT, SPACKLE AND CLEANING NEEDED |  | SOM EDUC | 2615 | COMPLETE | Deborah Deas | Brandon Barbosa | BEVERLEY HERBERT |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000011 |  | 19P000011 | FALSE | CHASS | SL5 PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED |  | PSYCHOLOGY1 | 2111A | COMPLETE | Milagros Pena | Cindy Williams | LORENA QUINTANA |  | Paul Ditty |  | 4 |  | TRUE |  |  | 2018-07-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000012 |  | 19P000012 | FALSE | SOM | SL5 SOME--PATCH & PAINT |  | SOM EDUC | 2638 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-07-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000014 |  | 19P000014 | FALSE | SOM | SL5 SOME - PATCH & PAINT |  | SOM EDUC | 2609 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-07-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000015 |  | 19P000015 | FALSE | BAS | SL5 POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING |  | POLICE TRLR | 1 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-07-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000017 |  | 19P000017 | FALSE | SoB | SL5 ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD |  | ANDERSON 1 (N) | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | DL, 9/6/18; Monitors are installed. Need to schedule the electrical. Target date is 9/21/18…… |  | Enrico Baez | 9/4/18 EB-This Project has been started. Monitors in place. Just need to run electrical. Dan aware. Refer to WO 19P000053. It asks for the same thing. Will request to close this and let Angela know. | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000018 |  | 19P000018 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER |  | ANDERSON 1 (N) | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000021 |  | 19P000021 | FALSE | ITS | SL5 ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS |  | ITS CENTER |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-07-12 | [6 empty] | 4/15/19, DL; This project is 100% Complete…… 3/28/19, DL; Monitors are done. Nee to finish the install of data and power…….12/14/18, DL; Still need to review scope….. |  | Enrico Baez | Met with IT staff. T.V. to be mounted in 4 locations. Will need electrical and painting in some locations. Waitng for updated scope from Joe Sepulveda | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000022 |  | 19P000022 | FALSE | BAS | SL5 HUB--PAINT TWO WALL AS SCOTTY'S HUB |  | HUB | 101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | DIANE THOMAS |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-07-12 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-09-17 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000023 |  | 19P000023 | FALSE | BCOE | SL5 PAINT ACCENT WALL | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-13 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000026. Canceled to be completed on 19P000035 | N/A | 2018-09-18 | FS | FALSE | 2018 | 2019-08-16
19P000026 |  | 19P000026 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALLS | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000023. Canceled to be completed on 19P000035 | N/A | 2018-09-18 | FS | FALSE | 2018 | 2019-08-16
19P000027 |  | 19P000027 | FALSE | ATHLETICS | SL5 ATHLETICS PATCH & PAINT ROOM | 9/19/18 | ATH DANCE | 0120C | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | DL, 9/19/18; This Project is 100% Complete……. |  | Paul Ditty | N/A | N/A | 2018-09-19 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000028 |  | 19P000028 | FALSE | BCOE | SL5 BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS |  | BOURNS | A0169 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | 5/1/19, DL; This project is 100% Complete…..3/28/19, DL; Monitor mounts were removed, Patch and paint will be completed in the near future……2/28/19, DL; Will schedule the project to be complete the first week in April…… | 2018-11-14 | Ron Veloz | 11/14/18 RV: Moved to Que to Start….10/29/18 RV: Scoping is completed. Carpenters to Remove Ceiling Mounted TV supports from the lobby ceiling. Work may require Carpenters to open the hard ceiling and remove the TV bracket posts if they cannot be unscrewed from the mounting brkt at the deck above. Work ay also require drywall patch back, tape, sand and paint the lobby ceiling. | YES | 2019-05-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000029 |  | 19P000029 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | Canceled; duplicate request to be completed with 19P000059 | CHUNG HALL | 205 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-16 | [6 empty] | Canceled; duplicate request to be completed with 19P000059 |  | Ron Veloz | to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | NO | 2018-09-18 | FS | FALSE | 2018 | 2019-08-16
19P000030 |  | 19P000030 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT |  | OLMSTED | 2301 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000031 |  | 19P000031 | FALSE | CNAS | SL5 BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) |  | BIOLOGICAL SCI | 3101 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 40 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 6/15/19, DL; This Project is 100% Complete…...5/1/19, Dl; This project will be complete on 5/5/19…..3/28/19, DL; Need to schedule a site visit with Estella. Left voice mail message on 3/28/19 to schedule site visit……..12/14/18, DL; This is prioritized at #40 and will not be scheduled in the near future….. |  | Enrico Baez | 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. Install 2 duplex outlets | YES | 2019-06-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000032 |  | 19P000032 | FALSE | SOM | SL5 Reconfigure recepetion desk to fit two FTEs. |  | SOM EDUC | 2608 | COMPLETE | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | 5 | 1 | FALSE |  |  | 2018-07-17 | [6 empty] | 5/1/19, DL; This project is 100% Complete….. 3/28/19, DL; Cabinet workl is complete. We need to finish the carpet and final laminate material…….2/28/19, DL; Conducted site visit with Chad. We will complete the work in the next two weeks…….2/1/19, DL; I Walked this project this week. We will try and schedule the work in the next 30- days…….12/14/18, DL, Still need to conduct site visit and schedule the work… | 2018-10-17 | Ron Veloz | 01/31/19 O-RVL: Met with Dan L onsite to review SOW with the requester. END---10/17/18 O-RVL: Remove one lower cabinet, Install a new corbel below to support the counter, install new carpet square or create an accent border if carpet tile is obsolete. Install new rubber base | YES | 2019-05-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000033 |  | 19P000033 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT | Duplicate request to 19P000030; Canceling project to be completed on other request. | OLMSTED | 2301 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | Duplicate to project 19P000030. Canceling project. |  | Paul Ditty | Duplicate to project 19P000030. Canceling project. | N/A | 2018-10-01 | FS | FALSE | 2018 | 2019-08-16
19P000035 |  | 19P000035 | FALSE | BCOE | SL5 WCH--INSTALL NEW LED DISPLAY IN OFFICE |  | CHUNG HALL | 354 | COMPLETE | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This Porject is 100% Complet…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Install scheduled for this Friday. | 2018-10-03 | Ron Veloz | 10/03/18 RV Walked site with Dan L. SOW Install TV Bracket at south wall center of room. Requires Power (no Data)installation of mounting bracket. TV and brk is located in Sarah Galloways office. Scope is completed. Dinh 9/18 19P000023/19P000026 requests for paint to be included in project scope for room. | YES | 2018-11-19 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000037 |  | 19P000037 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE BLDG--PATCH WORK AND PAINTING |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-07-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000042 |  | 19P000042 | FALSE | CNAS | SL5 COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL |  | COLL BLDG SO | 200 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Paul Ditty |  | 38 |  | FALSE |  |  | 2018-07-20 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000043 |  | 19P000043 | FALSE | CNAS | SL5 SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | Customer called and canceled the work on 10/23/18. | SCIENCE LAB1 | 309 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 19 |  | FALSE |  |  | 2018-07-20 | [7 empty] | 2018-10-22 | Ron Veloz | Customer called and canceled the work on 10/23/18. 10/20/18: O-RVL: Site visit on 10/20 with Amber 10:30am. 10/22/18 O-RVL: Walked site with Vendor/Controlled key sys. The PI requested pricing to change the locking function from room to room as "Storage use " and rekey the entry door with the same function. Matt will send pricing on the week of 10/22. 10/23/18 O-RVL: This request will not require access controls, but will require the entry door and side door lock-sets function to be changed to a storage function and rekeyed per Dave(PI). Received info from PI that there was a theft in his dept. Request is urgent. RV requested key count from Dave 8/23/18 and is pending a response from the department. 10/23/18 >> Canceling at the request of the customer - Loretta | YES | 2018-10-23 | FS | FALSE | 2018 | 2019-08-16
19P000044 |  | 19P000044 | FALSE | VC-RED | SL5 PATCH AND PAINT |  | SPIETH | 345 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000045 |  | 19P000045 | FALSE | CNAS | SL5 PREPARE LOCATION AND UTILITIES FOR INSTALL |  | BOYCE | 2407 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 14 |  | FALSE |  |  | 2018-07-23 | [8 empty] | Ron Veloz | Scope is complete. Walked site with Steve Burelson. DI water is available behined wall in 2407 at interstictal space. Vendor will install Milpore unit, FS to provide DI water and back board.Power is available at the sink counter. Electrical has verified GFI. | YES | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000046 |  | 19P000046 | FALSE | BCOE | SL5 PATCH AND PAINT PLUS REPLACE BLINDS |  | BOURNS | A0131 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000049 |  | 19P000049 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT |  | PHYSICS | 3036 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | 39 |  | FALSE |  |  | 2018-07-25 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000053 |  | 19P000053 | FALSE | SoB | SL5 ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S |  | ANDERSON 1 (N) |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-04-13 | [6 empty] | DL 8/22/18; two out of four monitors are complete. WE still need to install powree at four locations…….DL, 9/6/18; Still need Electrical installed……. Planing to have complete by 9/21/18……. This is aqctually 4- monitors in four locations. We should ensure each monitor is treated as an indidual project.......DL, 9/19/18; All monitors are installed. Robert will schedule the electricans this week or early next week...DL, 10/4/18; This project is 100% Complete..... |  | Enrico Baez | DND 7/25/18: Emailed R. Veloz advising work order is closed; upon completion of the scope review, Ron to work with Zee for a Project Number to be created. | YES | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000054 |  | 19P000054 | FALSE | GSOE | SL5 PATCH & PAINT OFFICE |  | SPROUL | 2131 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-26 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000055 |  | 19P000055 | FALSE | CNAS | SL5 CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM |  | COLL BLDG SO | 207 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Dan Lerman |  | 32 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2018-05-18 | [6 empty] | 4/15/19, DL; This project is 100% Complete…….3/28/19, DL; Need to order material and schedule the work…… Work order is assigned. 12/14/18, Dl; This project is prioritized at 32 and will not be scheduled in the near futurer…….DL, 7/11/18; Correction, I did not scope this yet, I thought we were talking agout the door bell and ADA operator. I will check in with Ronda and verify the scope…… DND 7/30/18: Created project to replace WO #18015182; project #19P000055 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. | 2018-11-29 | Ron Veloz | 11/29/18: RV Visited site and identifed the toilet room on the 2nd floor. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000056 |  | 19P000056 | FALSE | CHASS | SL5 HMSS CAPABILITY OF MOUNTING A TV |  | HUM & SOC SC | 1212 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  |  | 18 | FALSE |  |  | 2017-10-03 | [6 empty] | 12/14/18, DL; Monitor is complete. Still need to work on electrical……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope with Enrico and schedule the work…. Work orders are not produced. Need to assign and schedule the work DND 7/30/18: Closed work order #18W004822; created project #19P000056……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | EB 3/26-Project scoped on 10/23/17. Attached 5 photos and made annotations to FAMIS. | YES | 2018-12-14 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
19P000058 |  | 19P000058 | FALSE | CNAS | SL5 Assess Feasiblity of Removing/Replacing Growth Chambers |  | GH HH | 18 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-28 | [6 empty] | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing...DL, 5/9/18; Project is scoped. Need to schedule the work.....Plumbers and HVAC are working on this. Still need to have electrical removed. I am working wiht Patty on who can do the demo and removal.....DL, 7/11/18; I need to check in with Ken to see if refrigerant is recovered. will isue work order to disconnect electrical..... I checked in with our campus surplus and do not have any contacts to dis,matel the very large growth Chambers. I need to inform Patty and suggest that she have Burges demo and move the Growth Chambers......We will be complete with our portion of this project before 8/1/18.......DL, 8/10/18; All work is done except the disconnect for electrical. I need to check and see if the electrical. Per FAMIS complete on 8/22/18 |  |  | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000059 |  | 19P000059 | FALSE | BCOE | SL5 CHUNG HALL 201 SECURITY SYSTEM INSTALL | ITS to install cameras, no work by FS Required. | CHUNG HALL | 201 | CANCELED BY FS | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 10 | 7 | FALSE |  |  | 2018-07-17 | [6 empty] | DND 7/30/18 Project #19P000059 to replace REF CPMS # 9054 Ron to speak with ITS to complete installation. |  | Ron Veloz | 10/29/18 RV: Last meeting it was discussed that FS does not install Security Camera systems. Ron V spoke with Maggie on 10/26 to inform her that the project will be removed from the FS Minor Ren. List and she will need to contact ITS to request the Security Camers. 08/27/18 RV: Updated notes. Moved to "Que to Start". 09/19/18 RV, Install Security Cameras at points of entry. Install DVR locally in closet at an adjacent room. 08/23/18-RV Met with D.L. and Jason W. and verified F.S. will perform cabling installation and mount cameras. Equipment cost is not included in the SLA. R.V. will communcate informantion to Maggie. 08/22/18 O-RVL: Met with M. Souder to determine security camera needs and approximate location. | YES | 2018-07-30 | FS | FALSE | 2018 | 2019-08-16
19P000060 |  | 19P000060 | FALSE | BCOE | SL5 CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | CHUNG HALL | 223 & 224 | TO BE PERFORMED BY PD&C | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 6 | 4 | FALSE |  |  | 2018-05-15 | [6 empty] | 2/1/19, DL; Thios is a PD&C project. Maggie S. is aware this project may be a $130,00. project……DL, 7/25/18; This project is complicated and plans/permits will be required. This project will also require Air Hanlers to be shut down so Vibration dampners can be instlled. We will work on the plans in the next 45 days. This project should be scheduled during the Winter. We may also need to rent a large portable air handler to ensure the Large server room can maintain temp……. Project #19P000060 to replace REF CPMS # 9043. DL, 11/7/18; Sent Maggie an email on 11/7/18 informing her this project is well beyond our scope and $50K threshold. |  | Dan Lerman | DD 7/17: IRT Scoped with Dan present. Attached to FS Project. REF CMPS 9043 | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16
19P000061 |  | 19P000061 | FALSE | CHASS | SL5 PSYCHOLOGY 1111H-PATCH HOLES IN WALL |  | PSYCHOLOGY1 | 1111H | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000062 |  | 19P000062 | FALSE | CNAS | SL5 MSE 169-MINOR RENOVATION - NEW FACULTY |  | MAT SCI ENGR | 169 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 5 | 19 | TRUE |  |  | 2018-07-30 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………..1/15/19, DL; This project is 99% complete pending one water heater. Water heater is not here yet……12/14/18, DL; This project is 95% complete. The water heater is scheduled for delivery shortly after the new year. We will complete the install when the heater arrives…… 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 9/6/18; We will have the power and cabinets removed by 9/19/18. We are in the process of producing plans for this project. Once the plans are approved, we will proceed with the project. Note, we still need to obtain important information and some specifications regarding the procured base cabinets and counter tops, bio safety cabinet, diswasher, and freezer. ……DL, 7/7/18; The work is 90% complete. We are waiting on parts which have a 4-6 week lead time. We will finsh the balance of the project when the parts arrive….. | 2018-08-22 | Ron Veloz | 10/17/18 RV: Work is in Progress. END--- 08/27/18 RV: Updated notes. Moved to "Que to Start". Lab upgrades, Install utilities for new lab equipment, including DI water, electrical, modify existing cabinet to accommodate new flask washer, install owner furnished lab workstations. END ---...DND 8/12/18 replaced 3 projects for Summer quarter completion. Ron V. has scope on project. END --- 08/22/18 O-RVL: completed S.O.W, sent to Mayela Castillo for sign off. 08/23/18-RV: Ron V. Resubmitted S,O.W. rev.1 and received Final sign off from Mayela. Met with Dan to provide information and hand off the project. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000063 |  | 19P000063 | FALSE | CHASS | SL5 NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS |  | PSYCHOLOGY1 | 2124 | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-07-31 | [8 empty] | Paul Ditty | 9/13/18 EB this is a request for patch, paint and new carpet | NO | 2018-09-26 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000102 |  | 19P000102 | FALSE | CNAS | SL5 PATCH & PAINT FRONT CORNER OF OFFICE |  | LIFE SCIENCE | 2930 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 42 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000106 |  | 19P000106 | FALSE | CNAS | SL5 PHYICS 1134 - UTILITIES REQUEST |  | PHYSICS | 1134 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 15 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 6/15/19, DL; This Project is 100% Complete…...5/1/19, DL; Project should be complete this week or early next week…..3/28/19, DL; Power is complete. Need to finish chilled water…… 2/1/19, DL; Review scope with Customer. Still need to review with Brian from the Electic shop…………….12/14/18, DL; No update…. | 2018-11-07 | Ron Veloz | 01/31/19 O-RVL: Walked site with Dan L on 01/31 to review SOW. END--- 01/23/19 O-RVL: Received email from Ward B.in response to Brian Hambleton's request to use 208v. response is" ... 208 volt power 3-phase is fine for the compressor. Also having emergency power is not needed". END--- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela. END --- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela.-END 01/23/19 RV received Dr. Beyermann's comments and made corrections to the SOW, rev2. END--- 01/22/19 O-RVL: RV updates, Received a request from Mayela to meet on site with team. Sent team a copy of the Statement of Work for their review. Scope of Work: Install: Chilled new water supply & return drop, Electrical Power for the Compressor to be 3- phase 40Amp 220/230VAC hardwired from the equipment the disconnect for the Compressor. Power for the QD Pump and Controller to be single phase 200-230VAC, 20amp circuit. Patch and paint as needed, test for lead paint and TSI Asbestos abatement, equipment anchoring. Note: Job walk conducted on 11/07/18, 9:45-10:00am. Met in 1134 to determine Equipment and Utility Service location. In addition, on 11/03/18 the customer requested a single phase 200-230VAC, 20amp circuit (received info via email). END --- 01/11/19 O-RVL: Received an email from Mayella requesting status. END --- 11/08/18 O-RVL: Received email from Dr Beyerman today for added electrical. "I just realized that I also need a single phase 200-230VAC, 20 amp circuit in 1134 for the pump and controller, which is that unit next to the dewar. This can be down by the floor, in the vicinity of the 3 phase box. I will be meeting with the electrician today around 11am, and I will mention it to him". RV asked Dr Beyermann to contact me with the location for the pump receptacle. Will update floor plan upon receipt. 11/07/18 RV Walked site with Mayela and Dr Beyerman. Request to provide Chilled water loop, and two locations for Electrical power. Identified locations to install new utilities. END --- 11/07/18 O-RVL: Walked site on 11/07 with Dr Beyermann & Mayela, identified scope. Update FAMIS to J-DLN, MinRenlist and move to que to start. END --- 11/06/18 O-RVL: Jobwalk scheduled on 11/07 at 10:00am in Rm 1134 with Mayela, Ward Beyermann, Darren M HVAC, Brian H-Elect. Hold | YES | 2019-06-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000122 |  | 19P000122 | FALSE | CHANCELLOR | SL5 REMOVE, PATCH & PAINT AND HANG |  | STUDENT SERV | 2222 | COMPLETE | Kim Wilcox | Karim Zahedi | CHRISTINE SMITH |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000124 |  | 19P000124 | FALSE | VC-STU.AFF. | SL5 PAINT ROOMS 115 AND 116 |  | COSTO HALL | 125 | COMPLETE | Brian Haynes | Cathy Eckman | LINDA KELLEY |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000126 |  | 19P000126 | FALSE | CNAS | SL5 CHEMICAL SCIENCE - MINOR RENOVATIONS |  | CHEMICAL SCI | 455 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Dan Lerman |  | 6 |  | TRUE |  |  | 2018-08-03 | [6 empty] | 12/14/18, DL; This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL,11/7/18; Paint is complete, Plumbing shop is planning to schedule the work in the near future…… |  | Ron Veloz | Work in progress, install nitrogen lines and valves(valves by PI). Patch and paint. 10/30/18 RV: Spoke with Kevin, pending nitrogen line installation | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000127 |  | 19P000127 | FALSE | CNAS | SL5 PIERCE PATCH & PAINT | Duplicate request to be combined with 19P000239 | PIERCE | 2301 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | MICHELLE KING |  | N/A |  | Canceled |  | FALSE |  |  | 2018-08-03 | [6 empty] | Paul Ditty |  | Paul Ditty | Paul Ditty |  | 2018-09-21 | FS | FALSE | 2018 | 2019-08-16
19P000129 |  | 19P000129 | FALSE | BCOE | SL5 HANG MONITORS AND BOARDS |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | RICHARD BAIN |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2018-08-06 | [6 empty] | 12/14/18, DL; This Project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Dry errase boards and Monitor mounts are installed. Still need to install monitors, corner guards and monitors….. |  | Ron Veloz | 10/03/18 O-RVL: Install one 32" monitor asouth wall center of table, Install 55" TV at west wall(need power & data), install white bd at east wall 8' from north corner, install chalk bd at east wall 2'-6" from corner at 8" above small table. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000133 |  | 19P000133 | FALSE | CNAS | SL5 PATCH HOLES AND PAINT |  | BATCHELOR | 2203 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 43 |  | FALSE |  |  | 2018-08-07 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000137 |  | 19P000137 | FALSE | CNAS | SL5 LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM |  | LIFE SCIENCE | 2545 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000170 |  | 19P000170 | FALSE | CNAS | SL5 INSTALL NEW IRRADIATOR INSTRUMENT |  | MAT SCI ENGR | 51 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 16 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 2/14/19, DL; This project is 100% Complete………2/1/19, DL; Power is complete. Chilled water will be complete next week…………..1/15/19, DL; Electric is commplete, Water will be complete with in two weeks. Equipment should be on site soon…12/14/18, DL; This project is currently on hold per RED…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; The unit is schedukled for delivery in the next three weeks. | 2018-09-19 | Ron Veloz | 01/30/19 O-RVL: Spoke with Dan, equipment arrived staging into building. END---…..9/10: D. Dinh Project is shared between CNAS & BCOE, captured only on the CNAS College Count. 09/19/18 RV, Scope is complete. RV to Upload into FAMIS. Install chilled water and dedicated power for the irradiator instrument at the west wall in rm 051. 10/17/18 RV: SOW provide Chilled water loop and one(1ea) dedicated 208v 1ph 40a circuit to the Irradiator. Floor plan and specs are on the server folder. | YES | 2019-02-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000171 |  | 19P000171 | FALSE | CHASS | SL5 HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST |  | HUM & SOC SC | 1614 | COMPLETE | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 16 |  | FALSE |  |  | 2018-08-09 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000172 |  | 19P000172 | FALSE | VC-STU.AFF. | SL5 HEALTH SERV- PAINT RESTROOM IN LABORATORY |  | HEALTH SERV | 0113A | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000173 |  | 19P000173 | FALSE | CHASS | SL5 PAINT/PATCH UNIVERSITY THEATER LOBBY |  | THTR WKSH | 0400A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000174 |  | 19P000174 | FALSE | CNAS | SL5 BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT |  | BATCHELOR | 2112 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMY RICKS |  | Dan Lerman |  | 37 |  | FALSE |  |  | 2018-07-24 | [6 empty] | 5/1/19, Dl; This project is 100% Complete….. 4/15/19, DL; This project should be complete in 2-weeks…… 12/14/18, DL; This project is priortized at 37 and will not be scheudled until further notice…… | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scoping narrative is available and located on the BZM Fall Folder. Patch & Paint, replace supply grilles, reverse door swing, remove door closers, install metal plate over door opening. | YES | 2019-05-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000175 |  | 19P000175 | FALSE | BCOE | SL5 PAINTING |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT CHAVARRIA-VIVAR |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000176 |  | 19P000176 | FALSE | CNAS | SL5 PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY |  | PHYSICS | 1112 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 50 |  | FALSE |  |  | 2018-08-10 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | 2019-01-15 | FS | FALSE | 2018 | 2019-08-16
19P000181 |  | 19P000181 | FALSE | VC-RED | SL5 PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS |  | UNIV OFC BLD | 249 | COMPLETE | Michael Pazzani | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-14 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-19 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000184 |  | 19P000184 | FALSE | CNAS | SL5 REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES |  | GEOLOGY | 1270 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 45 |  | FALSE |  |  | 2018-08-14 | [6 empty] | 4/15/19, DL; This Project is 100% Complete…….. 3/28/19, DL; The project is 90% complete. Need to schedule floor installation…….. 2/14/19, DL; We will schedule the work soon. The space is vacant and ready…………….2/1/19, DL; This project has started. We would like to have the work complete by mid March…………..12/14/18, DL; This project is prioritized at 45 and will not be shceudled until further notice…… |  | Enrico Baez | 11/19/18 EB-Met with Laurie Graham at site. 11/08/18 RV: Enrico is assisting RV and has scheduled a job walk with Laurie Graham. Will follow up, pending confirmation. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000185 |  | 19P000185 | FALSE | CNAS | SL5 NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE |  | PIERCE | 206 (originially identified as Room 204) | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 6 | TRUE |  |  | 2018-06-18 | [6 empty] | 12/14/18, DL; This project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Pending glove box relocation to rm 319 and minor vent reconfiguration. Both tasks will be performed afet the glove boxes relocate to rm. 319. 10/29/18 All project related work is completed. |  | Ron Veloz | 07/05/18 RonV. Input: I observed multiple WO's for this project and spoke with Zee for clarification. I will investogate the site on 07/06 to determine the actual SOW. 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/22/18 O-RVL: Revised WO to Project no. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". =10/03/18: RV, Work in progress. Plumber are working on new gas lines. Will coordinate glove box move after work in rm 319 is completed. 10/29/18 RV: All glove boxes, Solvent mixing equipment and Chemical cabinet are removed. Remaining work is to replace the existing PVC vent with stainless duct when materials arrive per Cory. Update from Matt L-Plumbing department is working on the gas lines and will continue work this week. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000186 |  | 19P000186 | FALSE | CNAS | SL5 NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION |  | PIERCE | 319 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-06-18 | [6 empty] | Pending gas line installation scheduled for the week of 09/24 per Steve Burleson. Move glove boxes from 206 to Rm 319 after gas line are installed. All work is complete |  | Ron Veloz | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". 10/03/18 RV: Work in progress, Plumbers are installing gas lines. Glove boxes from 206 can be moved after gas lines are installed. 10/08/148 RV: Plumbers to complete the installation of new gas lines in 319. Glove boxes to be brought to rm 319 after gas lines are installed. 10/17/18 RV: Update, Gas lines are installe approx 90% complete per Plumbing Tech, misc parts on order. 10/29/18 RV: All project related work is completeand confirmed with trades and PI. | YES | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000188 |  | 19P000188 | FALSE | CAMPUS | SL5 PAINT - HALLWAY DOORS & INSIDE RESTROOMS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500 | CANCELED BY FS |  |  | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-16 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | FS | FALSE | 2018 | 2019-08-16
19P000189 |  | 19P000189 | FALSE | CNAS | SL5 PHYSICS- WALL HOLES PATCH | Duplicate work order to 19P000049. Work to be completed on other project. | PHYSICS | 3036 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-16 | [10 empty] | NO | 2018-10-18 | FS | FALSE | 2018 | 2019-08-16
19P000191 |  | 19P000191 | FALSE | CNAS | SL5 PATCH AND PAINT HINDERAKER BASEMENT |  | HINDERAKER |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 34 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000192 |  | 19P000192 | FALSE | BAS | SL5 MAIL-PAINTING |  | MAIL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | [6 empty] | 8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Ron Veloz | 04/15/19 O-RVL: Previously informed Dan L & Jason W of the approved Estimate and it was in que ready to go. RV followed up with email to Dan L & Jason W. on 04/15/19 to confirm. FAMIS & Access notes were updated. END~ 04/05/19 O-RVL: Changed Priority on FAMIS from SL9-Estimate back to SL5-Project and change assignment from O-RVL to J-DLN (Dan Lerman. Linda changed project title on Access from Room 2221 to 4231. END~ 04/04/19 O-RVL: Estimate is complete and accepted by the customer. The requester has accepted the revised estimate #2 to install one access card reader at room #4231. RV has updated FAMIS Access notes. RV informed Dan L. at team meeting that estimate is complete and will move the project from Customer Hold to Que to start. END~ 03/27/19 O-RVL: Pending Customer review, Received acceptance of the estimate from Aimee G. and modified the Rev.2 estimate and returned to her as requested. Pending final approval. END~ 03/19/19 O-RVL: RV spoke with Aimee, Department will proceed with one card reader and expecting a FAU within a week or two. RV will keep project on Hold. ACCESS & FAMIS Notes updated. END--- 03/13/19 Sent Aimee a revised estimate for one door as requested - for room # 4231. Pending response. END--- 03/08/19 O-RVL: Placed on Customer Hold. Contacted Chris Rogers at HCI (Access Control Vendor) Chris will send the revised proposal on 03/11/19. END--- 03/07/19 O-RVL: Received an email from Aimee Gonzales. Revised request to " provide us with an updated quote to install the FOB reader to Genomics 4231 only instead of all three rooms". END--- 02/22/19 O-RVL: Followed up with a phone call to Aimee to confirm receipt of the estimate. Aimee will respond within 30 days with the department's decision. END--- 02/21/19 O-RVL: RV received request for status of estimate from Aimee G. RV replied to send Estimate by CBD today. Estimate sent. Changed priority from SL5 to project to SL9-Estimate. END---02/15/19 O-RVL: RV-preparing estimate to deliver to the customer on the week of 02/17/19. END--- 01/31/19 O-RVL: Pending proposal revisions with equipment itemized with make and model no. from the Access control vendor. Revised proposal due soon per vendor. END--- 01/15/19 O-RVL: Forwarded access controls quote and SOW to Jason and Chris Rodriguez to review and qualify the HCI quote. Pending response. --- 01/10/19 O-RVL: RV received quote and will send a formal Estimate to Aimee by EBD Fri. 01/18 and ask if they would like to proceed. 12/14/18 O-RVL: REQUEST FOR ESTIMATE ONLY. Send Estimated costs to Aimee Gonzales for review and approval. Pending access controls and auto door operator quotes. Moved to Queue to start. ---11/08/18 O-RVL: Scope is complete. Assisting the lock shop with pricing to provide the requestor an estimate prior to start of construction. Walked a 2nd vendor, pending quote for access control card reader. ---11/05 RV called vendor for quote, no reply. ---10/29/18 RV: Conducted jobwalk with vendor last week. Pending quote from Vendor. Will follow up. --- 08/23/18 O-RVL: Ron V. input update from the requestor per M. Anderson (email 08/23), "We would like to review the estimated costs and timeline prior to the FOB system being installed, and from there we will determine if we would like to proceed with the installation." ---Please provide the total cost estimate to Aimee Gonzales before initiating any work(R.V). Contact: Aimee Gonzales 951-827-6254. | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000194 |  | 19P000194 | FALSE | CHASS | SL5 PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 |  | HUM & SOC SC | 3304 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000195 |  | 19P000195 | FALSE | CHASS | SL5 HUM & SOC SC-ROOM PAINTING |  | HUM & SOC SC | 2003 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000196 |  | 19P000196 | FALSE | CHASS | SL5 PAINT OFFICE AT UNIVERSITY THEATER |  | THTR WKSH |  | COMPLETE | Milagros Pena | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000197 |  | 19P000197 | FALSE | CNAS | SL5 PATCH AND PAINT OFFICE, LOBBY AND HALL |  | COLL BLDG NO | 0203B | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 44 |  | FALSE |  |  | 2018-08-21 | [6 empty] | 05/07/19 O-ANS: Canceled per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16
19P000201 |  | 19P000201 | FALSE | CHASS | SL5 PATCH AND PAINT THE WALLS |  | CHASS INT S | 3111A | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 18 |  | FALSE |  |  | 2018-08-22 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000205 |  | 19P000205 | FALSE | BCOE | SL5 LABORATORY RENOVATION FOR NEW FACULTY |  | BOURNS | A0328 | COMPLETE | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  | Dan Lerman |  | 4 |  | TRUE |  |  | 2018-08-23 | [6 empty] | 2/28/19, DL; This Project is 100% Complete…….2/1/19, DL; This project is 99.9% Complete………..1/15/19, DL; This project is 90% complete. WE still need to finish snorkels and ceiling tiles. We should be 100% complete by 2/1/19……12/14/18, DL; This project is on schedule..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/4/18; This is a large scale project, we will walk with the trade supervisors next week. We will also work on the plans and schedule the work. Target Date is 1/1/19…..DL, 11/7/18; work is scheduled. We are working on the electrostatic paint contract. We are in plan check review process. There are questions about the fire sprinklers from Scott J. Sent Scott J. an email requesting a site visit to better determine if any work will be required on the sprinkler system….. |  | Ron Veloz | 10/03/18: RV spoke with Dan. He had previously met with Maggie and had scoped this project. | YES | 2019-02-18 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000207 |  | 19P000207 | FALSE | CHASS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-08-23 | [6 empty] | 8/1/19, DL: This project is 100% Complete……7/15/19, DL; Floor covering will be installed next week. Floor covering is the last item for this project……..7/1/19, DL; This project is 95% complete except floor covering. Floor covering will be installed within 2- weeks……6/17/19, DL; This project is making good progress. We should be complete near July 1st…….5/31/19, DL; This project started this week and should be complete by June 28th…….3/18/19, DL; Working on plans and we will submit our plans and permit application this week….. | 2018-09-20 | Enrico Baez | 9/20/18 EB-Conducted site visit. Request to remove window in hall and install door. Interior space walls not to be removed. Secure doors, blank off and cover with sound soak. Replace carpet with Vinyl Plank, patch and paint. ---9/19/18 EB-Site visit scheduled for 9/20/18.---9/13/18 EB emailed Toya Adams to schedule site visit. | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000208 |  | 19P000208 | FALSE | BAS | SL5 PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | Canceled per customer on priority list 9/17/18 | THE PLAZA |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | CARLA CHAPPLE |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-14 | [8 empty] | Enrico Baez |  | NO | 2018-09-17 | FS | FALSE | 2018 | 2019-08-16
19P000209 |  | 19P000209 | FALSE | PLANNING & BUDGET | SL5 OLD EH&S SITE- FS ANNEX A REMODEL |  | ENV H AND S | 100 | COMPLETE | Gerry Bomotti | Sharyl Murdock | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 2018-08-24 | [6 empty] | 7/1/19, DL; This project is 100% Complte….6/17/19, DL; This project is almost complete. Target complete date is 6/26………….5/31/19, DL; This project is in progress. Our goal is to have the projected completed by June 28th……. 5/15/19, DL; We are schedule to start the demo tomorrow. Project timeline is 3-4 weeks….3/28/19, DL; Gunther is working on plans……3/18/19, DL; Conducted site visit with Chris, Hassan and Francis last week. We will work on plans and permits…….9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen | Chris walked the project with Craig Kasten on 9/6/18. | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-08-16 | FY 19-20
19P000210 |  | 19P000210 | FALSE | CNAS | SL5 CHEMICAL SCI Install Door In Doorway |  | CHEMICAL SCI | 0225A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  | 25 |  | FALSE |  |  | 2018-08-24 | [6 empty] | 7/1/19, DL; This project is 100% complete…..6/17/19, DL; Po is cut. Target complete date is before 7/1/19……Permit was approved this week. We are now working on the contract with the vendor. Our goal is start the work with in the next 30- days. 5/15/19, DL; Plans were approved. I am in the process of working with PD&C for the contract. We will order material and schedule the wrok once we have a signed contract……..3/28/19, DL; Plans were submitted last week… 3/18/19, DL; Conducted site visit last week. We are working on plans now we will try and submit plans for permit review next week…… | 2018-09-19 | Ron Veloz | 10/03/18 RV: Install non rated door into an existing cased opening-for privacy & noise reduction. Will require carpentry-framing, patch, paint, and minor flooring/base repair.---09/19/18-RV, Scope of work is complete. RV to upload docs to FAMIS. | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-08-16 | FY 19-20
19P000211 |  | 19P000211 | FALSE | CAMPUS | SL5 LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | Reviewing campus standards for these project requests. | LIFE SCIENCE | 2545 | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | FS | FALSE | 2018 | 2019-08-16
19P000212 |  | 19P000212 | FALSE | CAMPUS | SL5 REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500A | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  | 1/11/19 Canceled per instruction from Ron Rector on 1/11/19; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting (Stephen C) |  | 2018-12-13 | FS | FALSE | 2018 | 2019-08-16
19P000213 |  | 19P000213 | FALSE | CNAS | SL5 NEEDS FOR NEW WALL DISPLAY (MONITOR) | Duplicate request to 19P000031; Work to be completed on other project. | BIOLOGICAL SCI | 3101 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [11 empty] | 2018-10-01 | FS | FALSE | 2018 | 2019-08-16
19P000214 |  | 19P000214 | FALSE | CNAS | SL5 PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT |  | PHYSICS | 3005 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-08-24 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000215 |  | 19P000215 | FALSE | BAS | SL5 SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 |  | HUB | 346 | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | John Peraino |  | 9 |  | FALSE |  |  | 2018-08-24 | [6 empty] | 12/12/18 DND Project complete; electrical was installed and all kitchen equipment was hooked up as requested. |  | Enrico Baez | 9/13/18 EB emailed Gustavo Plascncia to schedule site visit. 9/18/18 EB. Conducted site visit. Connect water, drain and gas lines to kitchen equioment. Double oven need hardwired electrical. HUB staff will attach al shelving to walls. Day crew to move and deliver equipment. | YES | 2018-12-12 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000216 |  | 19P000216 | FALSE | CHASS | SL5 HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT |  | HUM & SOC SC | 1214 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-08-27 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000217 |  | 19P000217 | FALSE | GSOE | SL5 PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 |  | SPROUL | 1359 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-27 | [6 empty] | 4/15/19, DL; This project is 100% Complete…..2/1/19, DL; This proect will start on 3/1/18 and should be complete by 4/1/19…… | 2018-09-18 | Enrico Baez | 9/18/18 E. Baez Conducted site visit. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000220 |  | 19P000220 | FALSE | CHASS | SL5 ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT |  | ARTS | 333 | COMPLETE | Milagros Pena | Cindy Williams | SONJA SEKELY-ROWLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 12/14/18, DL; This project is 100% Complete….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/8/18; Screeen is scheduled to be removed this Friday. We will schedule the installation and the patch / Paint repairs once we receive the repaired screen back from the vendor…….DL, 11/7/18; This project should already be complete. However, The vnedor did not deliver the correct screen. The correct screen is currently scheduled for this Friday..... |  | Enrico Baez | 8/27/18 EB-Remove 12' wide screen from finished ceiling. Need electricians to diconnect power, carpenters to remove drywall and lower screen. Repared screen to be re-hung by carpenters and drywall repaired. Electricians to reconnect power. Painters to patch and paint. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000221 |  | 19P000221 | FALSE | CHASS | SL5 PATCH, PAINTING, AND REGULAR CLEANING OF A126A |  | OLMSTED | A0126A | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000222 |  | 19P000222 | FALSE | BAS | SL5 PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000224 |  | 19P000224 | FALSE | BAS | SL5 PAINT EXTERIOR RAMP AT HUB MODULAR |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | MIKE CLEMONS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [7 empty] | 2018-09-27 | Enrico Baez | 03/12/19 O-RVL: RV spoke with Enrico. He is already working on this proejct and will follow up to obtain the letter. END--- 3/08/19 O-RVL: RV Updated Notes on Access and copied to FAMIS. RV phoned Crystal Jimenez and followed up with an email to Crystal Jimenez with the request for authorization letter from the Land lord, cc'd Enrico, Dan L, Alan & Monty. END---03/07/19 O-RVL: During the minor renovation meeting, Susan asked RV to contact the requester and ask them to contact the landlord to provide a letter of approval in order to move forward with project. END---10/15/18 EB-sent Aaron Seitz approx. cost of project. 9/29/18 EB- install keyless entry system on two doors.--- 9/19/18 EB-Scheduled site visit for 9/20.--- 9/13/18 EB-emailed crystal Jimenez to schedule site visit. Awaiting response to determine funding. | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000226 |  | 19P000226 | FALSE | CHASS | SL5 PAINT OFFICE HMNSS 3304 |  | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-08-28 | [8 empty] | Paul Ditty | Duplicate request; project to be completed on 19P000194 |  | 2018-10-01 | FS | FALSE | 2018 | 2019-08-16
19P000227 |  | 19P000227 | FALSE | BAS | SL5 DINING STORAGE ROOM CONVERSION |  | BANNOCK J | J0100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | DARCI LOMBARD |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 05/16/19 O-ANS: Project complete per John P as of 05/16/19. 04/04/19, JP: This project has been placed on hold per Housing Edwin. 2/8/19: JP storage room slated to be completed simultaneously with break room as water supply connections will be done together with break room. Completion date for both is approximately three weeks. |  | Enrico Baez | 9/12/18 EB-Install Drywall, Patch & Paint, cap water line, install VCT & Cove Base, Verify HVAC operation, replace hydralic door closer, install LED lamps, Security light. Scope sent to Edwin Melgar for approval. | YES | 2019-05-16 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000229 |  | 19P000229 | FALSE | GSOE | SL5 RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-08-29 | [6 empty] | 6/15/19, DL; This Project is 100% Complete….. |  | Enrico Baez | 11/13/2018 E. Baez-Met with Ron Rector to discuss system placement. WEPA system is to be placed on second floor near vending machines on North side. See note in shared drive. Will need power and data connections. ---9/20/18 EB-conducted site visit 9/18. Request for tile and plumbing removal, patch and paint. To facilitate placement of printer system. E-mail sent to Monty on 9/14 asking for direction on renovating hallway space. Awaiting Susan's response per Monty. Entered scope on shared drive. Will need Fire Marshal approval to determine which of three possible locations will allow placing of WEPA system. | YES | 2019-06-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000230 |  | 19P000230 | FALSE | CNAS | SL5 NEW FACULTY OFFICE FOR PATCHWORK/PAINT |  | GEOLOGY | 1242A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-08-30 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000231 |  | 19P000231 | FALSE | CNAS | SL5 OLMH 1428 PATCH AND PAINT |  | OLMSTED | 1428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ANDREW CABRERO |  | Paul Ditty |  | 48 |  | FALSE |  |  | 2018-08-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000232 |  | 19P000232 | FALSE | BAS | SL5 BANNOCKBURN J-104 BREAK ROOM UPGRADE | Scheduled work with trades anticipated 60% completion by Jun 15th. | BANNOCK I | I0105 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | John Peraino |  | 6 |  | FALSE |  |  | 2018-09-04 | [6 empty] | 6/14/19, JP; Project on schedule to be completed June 30th 2019. 05/16/19 O-ANS: Project to be 60% completed by June 15th per John P. 04/04/19 JP: This project placed on hold per Housing/Edwin. Finishing up the cabinet and lighting order, will be submitting to purchasing today. Scheduling installation of VCT flooring pending per Tony’s Flooring, will have date this week. New ceiling tiles have been delivered and will be installed when relocating of electrical components are complete. Awaiting confirmation and clearance from Jess to proceed with cutting into walls to facilitate electrical modifications |  | Enrico Baez | 9/19/18 EB-conducted site visit. Entered Scop in FAMMIS and in BZM projects on shared drive. Requires pluming for sink and disposal, electrical, lighting upgrade. | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000233 |  | 19P000233 | FALSE | BAS | SL5 PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | FS to coordinate with customer to scope the work. | MAIL | 884 | CANCELED BY FS | Gerry Bomotti | Georgianne Carlson | AMY EVERETT |  |  |  | 12 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Enrico Baez | Per Enrico, creating two individual WO's for Tile repair (19W004955) and door painting (19W004956). | YES | 2018-09-24 | FS | FALSE | 2018 | 2019-08-16
19P000234 |  | 19P000234 | FALSE | CNAS | SL5 PHYSICS 3005-WALL HOLES PATCH |  | PHYSICS | 3005N | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-09-04 | [6 empty] | **9/19/18 DUPLICATE REQUEST SENT IN SEE 19P000246 |  | Paul Ditty | Duplicate work request. | N/A | 2018-09-19 | FS | FALSE | 2018 | 2019-08-16
19P000235 |  | 19P000235 | FALSE | BAS | SL5 RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | Customer to determine scope of work. | ABER INVER | A0100 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 11 |  | FALSE |  |  | 2018-09-04 | [6 empty] | JP 04/04/19 Project cancelled per Housing/Lisa | 2018-11-01 | Enrico Baez | 11/26/18EB-Tranfered FAMIS work order to John Peraino's bench. Estimate to customer needed, prior to moving forward with project. 11/26/18 EB-SCOPE entered Aberdeen Inverness • Paint acoustic panels. Customer to provide color specification. • Remove carpet and replace with customer specified vinyl plank flooring. Replace base board • Cut door to accept 16” x 7” glass lite. Frame as needed. • Paint door • Replace surface mounted light fixture with LED surface mounted fixture. Customer to approve design. • Clean, paint or replace A/C vents. • Remove louvered vent in wall for abandoned water cooler. Install sheet metal cover, paint to match new wall color. Pentland Hills -Rooms 105 and 107 • Install full height acoustic panels on three walls. • 4th wall on East side of each room gets mirror. Height of mirror to be flush with top edge of door casing. Mirror width to be between inside corner of wall and switch plate cover. Provide cut out in mirror for thermostat installation. • Replace all ceiling tiles. • Replace 2’ x 2’ ceiling light with 2’ x 4’ LED fixture-customer to approve design. Pentland Hills -Rooms 105 and 107 • Remove carpet and replace with vinyl plank flooring, replace base board • Fire rated doors to be replaced with fire rated doors with small lite, approx. dimensions 16’ x 7”. • Paint as needed. Lothian • Install full height acoustic panels on three walls. • 4th wall gets mirror height to be even with door casing height. Customer to determine location. • Replace all ceiling tiles. • Replace ceiling lights with LED fixtures. • Remove all carpet in rooms and replace with vinyl plank and new base board-customer to specify style and color. • Replace door wire reinforced glass with clear, non-reinforced fire rated glass. • Paint as needed. Suggested Vendor for sound absorbing paneling. Riverside Acoustics Contact: Keith Atkins 951-682-6123 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 Met with Bob and Lisa, no firm plans or ideas in place. Lisa will schedule site walk once they have determined what they want. 11/1/18 Conducted site visit with Bob and Lisa. | YES | 2019-04-04 | FS | FALSE | 2018 | 2019-08-16
19P000236 |  | 19P000236 | FALSE | BAS | SL5 EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION |  | ABER INVER | A0100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 10 |  | FALSE |  |  | 2018-09-04 | [6 empty] | JP 04/04/19 2/8/19 This project is complete. JP Estimated completion end of February | 2018-11-01 | Enrico Baez | 11/27/18 EB-Entered scope of work. Transferred work order to John Peraino in FAMIS. Estmate to be provided prior to work start. Aberdeen Inverness Lobby across from RSO. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Pentland Hills 1st floor of I/J, K/L, M/N, O/P • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Pentland Hills Alcove between E&F building. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exterior wall adjacent to B-101 • Remove existing dual fountain. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exercise Room H-101 • Install HS where pluming repairs were made in East wall. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch all walls and Paint as needed. Glen Mor K-206 Fitness Room • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Glen Mor Pool area • Remove existing double water fountains and HS. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. • Repair any brick work as needed Lothian Hallway near Dining Hall cashier stand adjacent to fire extinguisher cabinet • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Sample sheet. https://www.restroomdirect.com/halsey-taylor-drinking-fountains-and-water-coolers.aspx 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Waiting for Lisa L. to schedule site visit. Total number of station and needs not completed. 11/1/18 EB Conducted site visit with Lisa and Bob. AI Replace Hydration Station (HS) in Lobby near RSO Pentland Hills Replace fountains with HS first floor I/J, K/L, M/N, O/P. Also remove fountains and install HS near B-101, Alcove between E&F, H-104. Glen Mor Remove fountain at pool & K-206 fitness room, replace with HS. Lothian Replace existing HS near cashier to Dining Hal | YES | 2019-04-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000237 |  | 19P000237 | FALSE | GSOE | SL5 PATCH AND PAINT OFFICE - SPROUL 1206 |  | SPROUL | 1206 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 4/15/19, DL; Project is 100% Complete….. 2/1/19, DL; This project will start on 3.1.19. We will need to abate ACM before we can start. Jess will isuue the 14- day notification to the AQMD. Once we have confirmation, we will schedule the work…….. | 2018-10-05 | Enrico Baez | 0/5/18 E. Baez- conducted site visit. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000238 |  | 19P000238 | FALSE | VC-UNIV.ADV. | SL5 PATCH & PAINT HINDERAKER 1136 |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000241 |  | 19P000241 | FALSE | PLANNING & BUDGET | SL5 PATCH/PAINT IN OFFICE 2122 HINDERAKER |  | HINDERAKER | 2122 | CANCELED BY CLIENT | Gerry Bomotti | Sharyl Murdock | MILLY PAREDEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-06 | [8 empty] | Paul Ditty | Canceled per customer call on 9/13/18 | N/A | 2018-09-13 | FS | FALSE | 2018 | 2019-08-16
19P000242 |  | 19P000242 | FALSE | CNAS | SL5 PAINT OFFICE |  | COLL BLDG NO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 47 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000243 |  | 19P000243 | FALSE | CNAS | SL5 GENOMICS 1206 - PATCH AND PAINT WALLS |  | GENOMICS | 1206 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Paul Ditty |  | 49 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000244 |  | 19P000244 | FALSE | CNAS | SL5 PATCH & PAINT GEOLOGY |  | GEOLOGY | 2258A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2018-09-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000245 |  | 19P000245 | FALSE | SOM | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY |  | SOM RSCH |  | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-09-07 | [6 empty] | 7/1/19, DL; This project is 100% Complete…..6/171/19, DL; Material is on site. Project should be complete in the next two weeks……..5/31/19, DL; Contracts is working on the contract. We should have a notice to proceed in the next two weeks. The project will be complete with in 30- from when we receive the notice to proceed……5/15/19, DL;, Plans were approved. I am working with PD&C on the contract. Once the contract is complete, we will schedule the work……3/28/19, DL; Plans were submitted and pending review and approval….. | 2018-10-29 | Ron Veloz | 02/15/19 O-RVL: RV updated notes added SOW & moved to "Que to Start". END--- 01/31/19 O-RVL: Chris at Lockshop reviewed the vendor quote and requested detailed equipment list. Pending revisions from vendor due this week. END--- 01/15/19 O-RVL: Delivered Access control quote to Jason & Chris R for review. They will respond with comments. Upon receipt and confirmation, RV will complete docs on server folder and update FAMIS & Access DB. --- 01/11/19 O-RVL: Qualifying quote to verify proper components from door operator vendor expecting reply soon. --- 12/14/18 O-RVL: Received Quotes for Auto door operator and Access controls this week. RV to provide update & quotes to Dan Lerman. Moving status to "Que to Start" on Minor Ren List & updating Project Folder. --- 11/07/18 O-RVL: Walked site with Access Control vendor --- 10/31/18 O-RVL: Walked site with Door Op vendor --- 10/29/18 O-RVL: Scope was Completed. RV to schedule job walks with Vendors. --- 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-08-16
19P000246 |  | 19P000246 | FALSE | CNAS | SL5 PHYSICS - PATCH AND PAINT |  | PHYSICS | 3007N | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 46 |  | FALSE |  |  | 2018-09-07 | [6 empty] | n/a |  | Paul Ditty | Duplicate request; project to be completed on 19P000234 | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000247 |  | 19P000247 | FALSE | BAS | SL5 LOTHIAN FIRST FLOOR COMMON AREA FLOORING |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Jess Hernandez |  |  |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez |  |  | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000248 |  | 19P000248 | FALSE | SOM | SL5 SOME--SOME INSTALL ELECTRICAL 1682 |  | SOM EDUC | 1682 | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 2 |  | FALSE |  |  | 2018-09-10 | [6 empty] | 2/14/19, DL; This project is complete…… |  | Ron Veloz | 10/29/18 O-RVL: Scoping is completed. END--- 10/17/18: RV: Drawings are on server folder. END---10/08/18 RV: Spoke with Brandon B. Brandon will submitt BKM drawings via permit request through PD&C. 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon. Walked project with Brandon. SOW to install two each dedicated 120v/20a cicuits for new modular furniture one whip at each end of the office down the wall and one to two data drops overhead down wall. | YES | 2019-02-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000249 |  | 19P000249 | FALSE | SOM | SL5 SOME-INSTALL LOCKERS | Lockers on order by customer; upon arrival to be installed. | SOM EDUC |  | CANCELED BY FS | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-07 | [6 empty] | DL, 11/7/18; It is my understanding the lockers are ordered, but we donot have a confirmed delivery date. Once the material is on site, we will schedule the installation…… |  | Ron Veloz | 01/31/19 O-RVL: Contacted Domonic and confirmed lockers will not be avialable to install and agreed to cancel the request orginated on 09/07/18 and will resubmit a new request upon delivery of the new lockers. RV emailed Customer Relations staff to cancle the project request via emails and cc Monty, Deborah H., Alan, Loretta on the communication. 01/10/19 O-RVL: Emailed Dominic Salazar on locker delivery ststus. Pending follow up call from customer to inform FS on delivery of lockers. 11/08/18 RV: Visited site existing lockers in place and in use. Will follow up with the requestor for locker delivery status to schedule. RV Spoke with Brandon Barbosa. Deparment will purchase lockers. 11/08/18 RV: Received email from Domonic Salazar on 10/25 Lockers are expected to arrive. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16
19P000250 |  | 19P000250 | FALSE | BCOE | SL5 BOURNS A303-PAINT AND PATCH WALL |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | JUANA GUERRERO |  | Paul Ditty |  | 5 |  | TRUE |  |  | 2018-09-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000251 |  | 19P000251 | FALSE | CNAS | SL5 CHEM SCI 428-PATCH DRY WALL HOLES |  | CHEMICAL SCI | 428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000252 |  | 19P000252 | FALSE | ATHLETICS | SL5 ATH DANCE SHOWER DOORS |  | ATH DANCE | 0050K | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-10 | [6 empty] | 5/31/19, DL; This project is 100% Complete……..5/15/19, DL; This work will be 100% complete this Friday…….4/15/19, DL; This project should stat is 2-weeks. We have a signed po# for the shower doors. Walked the needed tile repairs with the contractor today……..3/18/19, DL; Woring on quotes for the repairs. We will scheudle the work to be completed in the next 45- days…… |  | Enrico Baez | 10/3/2018 EB Replace aluminum and glass shower doors. Will need to contract work. Replace all rusty fixtures in showering space, repair/replace tile as needed. ---9/24/18 EB Site visit scheduled with John Jensen for 9/27 | YES | 2019-05-31 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000253 |  | 19P000253 | FALSE | CHASS | SL5 ARTS RENOVATION |  | ARTS | 157 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 16 | FALSE |  |  | 2018-04-17 | [6 empty] | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access……DL, 7/11/18; This project needs to be complete before Fall 2018. Space is vacant and ready go. Need to walk and confirm Schdule with Paul D. Tony's Flooring is ready to go after paint is complete.... Target complete date is 9/21/18......DL, 8/22/18; Walked with PAul, Paul will scheudle the work. Jess still need to cordinate with Tony's Flooring .....DL, 9/19/18; The paint and flooring is complete. The seams need to be welded and this will be complete. this will be complete by 9/21/18......9/19/21; This Project is 100% Complete....... |  | Dan Lerman | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000255 |  | 19P000255 | FALSE | SPP | SL5 CHASS INT N REMODEL - 4022 PATCH AND PAINT |  | CHASS INT N | 4022 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000256 |  | 19P000256 | FALSE | SPP | SL5 CHASS REMODEL - 4146 PATCH AND PAINT |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  |  |  | 3 |  | TRUE |  |  | 2018-09-10 | [7 empty] | 2018-10-09 | Enrico Baez | 10/9/18 EB Sent Luis email, copied Mont too. Project will bw $25k-$30K. Asked Luis if we are to proceed. 10/15/18 E.Baez conducted site visit, Client requested cost estimate to construct 2-3 "huddle" Spaces with sound proof walls. Requires alterations to HVAC ducting, full height walls with doors, fire sprinkler additions, smoke detection additions, lighting changes. emailed Luis estimated cost of $25,000. 12/20/18 D. DINH: Spoke with customer, Luis Alvarez, and the project request has been modified to patch & paint and replacement of one ceiling tile. Customer to work with BKM to fulfill the wall partition request portion of the project. | YES | 2019-01-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000263 |  | 19P000263 | FALSE | SPP | SL5 CHASS NORTH REMODEL - 4009 PATCH AND PAINT |  | CHASS INT N | 4009 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-09-11 | [8 empty] | Paul Ditty |  |  | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000265 |  | 19P000265 | FALSE | ATHLETICS | SL5 ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000266 |  | 19P000266 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | n/a | N/A | 2018-12-13 | FS | FALSE | 2018 | 2019-08-16
19P000268 |  | 19P000268 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT 20C |  | ATH DANCE | 20C | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000269 |  | 19P000269 | FALSE | ATHLETICS | SL5 ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | Project is not within the purview for completion; condition is fair and usable. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 5 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18…..This is a cooman area. Is this recharge work……. | 2018-09-27 | Enrico Baez | 2/5/19 E. Baez. Common spaces are managed by Facilities Services. Any work done in corridors, stairwells and open spaces will be assessed by FS. 11/20/18 E. Baez-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB-Request for installing vinyl flooring. Remove and replace existing Terrazo and ceramic floor tile in 1st floor lobby and stairs to basement. | YES | 2018-10-04 | FS | FALSE | 2018 | 2019-08-16
19P000270 |  | 19P000270 | FALSE | ATHLETICS | SL5 ATH DANCE-WEIGHT ROOM DROP DOWN CEILING |  | ATH DANCE | 78 | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 14 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project is 100% Complete….. |  | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB remove all t-bar ceiling components. Will need relocation of supply and return registers, lighting Alarms, Etc. |  | 2019-02-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000271 |  | 19P000271 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 |  | ATH DANCE | 3 | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000272 |  | 19P000272 | FALSE | ATHLETICS | SL5 NEED URINAL DIVIDERS | FS to coordinate with customer to scope the work. | ATH DANCE | 50E | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 13 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 3/7/19 O-ANS: Project no longer moving forward per Ron Rector and placed on DM list. 1/15/19 E Baez. Per "Monty" project cancelled to be placed on Deferred Maint. List. Emailed Chris P. to provide renovation cost and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Install dividers for urinals. Wall is tile. |  | 2019-01-24 | FS | FALSE | 2018 | 2019-08-16
19P000273 |  | 19P000273 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000274 |  | 19P000274 | FALSE | ATHLETICS | SL5 RIV SPORTS CPX - REPLACE URINALS | FS to coordinate with customer to scope the work. | RIV SPORTS CPX |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 15 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-10-15 | Enrico Baez | 1/14/19 E Baez. Per "Monty" this project to go on deferred maint. list. emailed Chris Pillen to provide coast and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27. 10/3/18 EB not time to visit on 9/27. will schedule follow up meeting. 10/15/18 EB conducted site visit, 11 urinals to be replaced. | YES | 2019-01-24 | FS | FALSE | 2018 | 2019-08-16
19P000275 |  | 19P000275 | FALSE | ATHLETICS | SL5 SOFTBALL STG PRESS BOX AC ADDITION | FS to coordinate with customer to scope the work. | SOFTBALL STG |  | CANCELED BY CLIENT | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 6 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project was canceled by Johnathan J. as there is not funding at this time…………DL, 10/4/18; I checked on this recently and this is not a building, it is stoarge and should be recharge work…. | 2018-09-27 | Enrico Baez | 2/5/2019 E Baez Client wants a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. Client will need to fund this project as this is not a core building 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Client want a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. |  | 2019-02-14 | FS | FALSE | 2018 | 2019-08-16
19P000276 |  | 19P000276 | FALSE | ATHLETICS | SL5 TRACK BLEACH-PUBLIC RESTROOMS UPGRADE |  | TRACK BLEACH |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 16 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 11/20/18 EB Project cancelled, will be addressed by PD&C. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB conducted site visit, Client wants additional toilet in mens room, changing table and lighting improvements. ADA Issues. Also spoke with Scott Donnell he has project . | YES | 2018-11-20 | FS | FALSE | 2018 | 2019-08-16
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  | 10 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 4/18/19, DL; Per Enrico, we are waiting for a proposal from HCI and approved funding from Athletics. We should have the proposal in 2- weeks…. | 2018-09-27 | Enrico Baez | 1/14/19 E Baez. Per "Monty" Athletics are to pay for this project. Joe Erbland emailed to determine if funding has been approved. Waiting on response. ---11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. --- 10/3/2018 EB Install keyless entry system for building exterior. ---9/24/18 EB Site visit scheduled with John Jensen for 9/27 | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000278 |  | 19P000278 | FALSE | BCOE | SL5 REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR |  | BOURNS | A0165 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Dan Lerman |  | 1 |  | TRUE |  |  | 2018-08-03 | [6 empty] | DL, 10/4/18; This Project is 100% Complete…….. |  | Ron Veloz | Completed SOW, met withJess and informed of work and color. | YES | 2018-10-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000280 |  | 19P000280 | FALSE | SoB | SL5 ANDERSON HALL PAINT ONLY |  | ANDERSON 2 (S) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-13 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000283 |  | 19P000283 | FALSE | CNAS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 20 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 8/1/19, DL; This Project is 100% Complete……7/1/19, DL; Barricades are complete. Signage needs to be installed. Signage to be installed in the next 3- weeks………….6/17/19, DL; Yello Caution tape is installed. Still need to install barricades and signage. Target complete date in mid to late July……5/31/19, DL; The contractor has the PO#. We will start the work and complete the work in the next 30- days……5/15/19, DL; We are waiting on the quote, once we have the quote, we will proceed with the work……4/15/19, DL; We are trying to locate a roofing contractor that will complete the installation. This is a specialty product that requires a professional installation…….3/28/19, DL; We will install the yellow caution tape on the roof which is our most viable option. I will schedule a site visist / job walk with a contractor in the near future…… | 2018-09-19 | Ron Veloz | 10/17/18 RV: All construction information is on the server folder. Pending Saftey MOP's from Beiwei. Left message with her on Monday 10/15 for status. ---10/03/18 RV: SOW, Install safety guard railing and apply yellow markings (leading edge 6'from perimeter) on the Winston Chung Roof. --- 09/19/18-Scope is complete, received safety requirements prepared by EH&S/Beiwei. RV to upload onto FAMIS. | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000284 |  | 19P000284 | FALSE | CAMPUS | SL5 GEOLOGY ACCOMMODATION DOCK DOORS |  | GEOLOGY |  | COMPLETE |  |  | DEBORAH TERAO |  | Chris Pillen |  | Canceled | Canceled | FALSE |  |  | 2018-08-07 | [8 empty] | Ron Veloz | 01/10/19 O-RVL: CLOSE OUT-WORK COMPLETED. All work for this project is completed. Email sent to Monty & team on Jan 04, 2019 confirmating all work is completed. 12/14/18 O-RVL: Loading dock Post and Chain fabrication, is in progress, Auto door operators are on Order/Contract in progress, Loading dock signage is in progress by sign shop, information was confirmed by Chris Pillen as of 12/13/18. All other request related to this project have been completed. RV sent updates to Monty on 12/13/18. 11/14/18 RV: Walked Capitol door on 10/31 for pricing. pending quote for auto door operators. 10/30/18 RV: Walke Paradise Door -Automatic Door operator vendor to site. Met with Jason to discuss door access hardware & function of locksets . Pending quote. 10/03/18 RV: Notes from FAMIS: Lock Shop - Chris working with Jason to purchase and install two sets of automatic door openers with plain face plates - to be installed in the back receivin area. | YES | 2019-01-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000285 |  | 19P000285 | FALSE | CNAS | SL5 PAINT AND PATCH PI OFFICE |  | ENTOMOLOGY | 269 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-09-17 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000286 |  | 19P000286 | FALSE | CHASS | SL5 FACULTY OFFICES: TOUCH UP PAINT |  | HUM & SOC SC | 2005 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-09-17 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000287 |  | 19P000287 | FALSE | CNAS | SL5 URGENT: PAINT SHOP TO PATCH AND PAINT |  | MAT SCI ENGR | 229 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | HONG XU |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-19 | [8 empty] | Paul Ditty |  |  | 2018-10-22 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000288 |  | 19P000288 | FALSE | CNAS | SL5 COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS |  | COLL BLDG NO | 202 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-19 | [6 empty] | 05/10/19 O-ANS: Project was canceled by FS in March 2019 because customer will have to submit separate work orders for each room since customer has requested to schedule and complete them separately in sequence (not all at once). 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000291 |  | 19P000291 | FALSE | CNAS | SL5 MSE HELIUM RECOVERY SYSTEM |  | MAT SCI ENGR | 205 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 9 | HOLD | FALSE |  |  | 2017-07-24 | [6 empty] | 12/14/18, DL; This project is 100% Complete……DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB - spoke with Mayela who is determining status within her dept…. DL, 11/7/18; This project is complete but I need to conduct a final site visit….. |  | Ron Veloz | DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB-Spoke with Mayela-she is researching where the project stalled within her department. 7/2/18 DND Please verify if work is still required for completion 8/7/18 EB-sent Mayela email requesting update on 9/20/18 EB-emailed Mayela to determine status of project. 9/24/18 EB-Project not cancelled. Passed on to Ron Veloz. 10/03/18: RV, Walke job with Mayela, Chris P, Dan L & Deb McWilliams. PI to provide Dan layout and equipment specs. | YES | 2018-12-14 | FS | FALSE | 2017 | 2019-08-16 | FY 18-19
19P000292 |  | 19P000292 | FALSE | CNAS | SL5 GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 18 |  | FALSE |  |  | 2018-08-10 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…….2/14/19, DL; The Concrete and Power is Complete. We still need to install the chain link which will be installed in about 3-4 weeks………..2/1/19, DL Electrical is complete. WE will pour Concrete next week. We will schedule the fence install 28- days after concrete is poured………; Th1/15/19, DL; Plans are approved, we will start the work in the next two weeks……12/14/18, DL; Plans are almost complete. We will schedule the work after plans are approved……DL, 11/7/18; Conducted site visit with Chris P. We need to confirm a feasable site location before we move forward with the work…. |  | Ron Veloz | 10/30/18 RV: Chris Pillen and D. McWilliams aggreed to leave the building in place and place a concrete pad with a chain link fence adjacent to the existing structure. 10/17/18 RV: SOW, demolish walls and roof. Verify and cap existing underground utilities. Remove overhead electrical from power pole to the building. The concrete pad to remain and install a 6'H fence with gate around the pad. Bring Power below grade to pad location. Met with C.Pillen and Dan to discuss alternate options. Photos and equipment info is on the server file. | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-08-16
19P000293 |  | 19P000293 | FALSE | ITS | SL5 PAINT ESTIMATE REQUEST |  | TELEPHONE |  | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-21 | [6 empty] | n/a |  | Paul Ditty | Canceled by Customer 10/24/18 | N/A | 2018-10-24 | FS | FALSE | 2018 | 2019-08-16
19P000295 |  | 19P000295 | FALSE | ATHLETICS | SL5 PATCH & PAINT |  | ATH DANCE | 50B | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 12 | 18 - 19 | FALSE |  |  | 2018-09-12 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000296 |  | 19P000296 | FALSE | CAMPUS | SL5 MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB |  | MAT SCI ENGR |  | COMPLETE |  |  | MILLY PAREDEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-09-25 | [6 empty] | 2/28/19, DL; Project is 100% Complete…….2/14/19, DL; This project is 90% Complete and should be complete by the end of the month………….2/1/19, DL; Permits are approved, we will schedule the project in the next 2- weeks and hope to be complete by the end of February….12/14/18, DL; Rendering has been given to Ron R. Ron will present to Gerry for review and approval. Once approved, we will proceed with plans and permits……DL, 11/7/18; Need to find out where this project stands in regards to the priioroity….. Site vist was conducted and scope of work is verified. Plans and permits will be required for the work….. |  | Ron Veloz | 10/19/18 O-RVL: Walked the proposed location with Dr. Barsukov to review needs and location for nitrogen tanks in the hall. DL suggested to construct a wall with double doors approx 2' below the ceiling height. 09/27/18 O-RVL: Walked site with Chris P, Dan L., Deborah Mc Williams & Mayela C to review SOW. | YES | 2019-02-28 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000298 |  | 19P000298 | FALSE | CNAS | SL5 SPIETH - PREP LAB FOR FACULTY SEARCH |  | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 5/15/19, DL; This Project is 100% Complete… 5/1/19, Dl; This project will be complete next week…..4/15/19, DL; We are making good progress on this project and we should be complete the first week in May……..3/28/19, DL; This project is in progress and should be complete by or near May 1st….2/14/19, DL; Need to schedule trades and obtain quotes to refinish countertops…… |  | Ron Veloz | 04/22/19 O-RVL: Update- RV reviewed incoming work request 19P000546 and spoke with Dan L on 04/19 regarding Spieth Hall 19P000546 to add 1)Fabrication of a stainless steel hood like the one in Spieth Hall 2218 (picture attached), to fit the space in Spieth 1363 on east corner wall where walk-in chamber was removed. 2)Hook up of the new hood into the current fume hood vent and spanning ~75% of the distance between the working fume hood and the wall. 3)Removal of the shelving above the lab bench (may need some minor abatement). 4)Installation of 3 tombstone electrical outlets on the lab bench to match the other bench. RV spoke with Dan L. Dan, some of the added work is in progress and the remainder of work will be included on projet # 19P000298. Sheet metal hood will be completed on a SL6 sheet metal per DL. END~ 01/15/19 O-RVL: RV to scope once priority is established. RV updated notes with information provided from Deborah Mc Williams. Spieth 1363 – Wet Lab Space Note by D McWilliams.: "There is evidence in the ceiling and along one wall of a water intrusion issue, i.e. peeling paint, leaking and rusted pipes, etc. The cause of this damage needs to be investigated and repairs confirmed, including painting the wall and ceiling where damage is visible". Patch/paint Re-finish, re-surface – existing cabinets Re-finish and/or replace bench-tops If both sinks cannot be significantly cleaned, they should be replaced, replace faucets at both sink locations. Clean existing Chemical fume hood Repair or replace self-closing chemical / flammables storage cabinet On one bench remove overhead shelving unit and relocate electrical outlets to the ends of bench to accommodate large desktop equipment. Cap off remaining utilities for potential use/re-connection in the future. Remove shelves on west wall to accommodate siting of large floor-standing equipment before patch and painting. Also, add 120/240 electrical outlets (raceway) along this wall. Replace flooring -- this depends on what we decide about removing the walk-in fume hood listed below Add GFCI outlets near water sources. Requires a connection to a DI water system Other utilities are required in this room and at what locations, e.g. air, oxygen, gas, vacuum, etc.? Remove existing walk-in Fume Hood (if cost for this issue does not trigger project over $50k) – Please assess/cost out and advise prior to project. Spieth 1364 – Lab Support Space work: Patch/paint –Re-finish, re-surface – existing cabinets (non-porous surface), Re-finish and/or replace benchtops, if sink cannot be significantly cleaned, they should be replaced Replace faucets at sink location. Add GFCI outlets near water sources Requires a connection to a DI water system" | N/A | 2019-05-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000299 |  | 19P000299 | FALSE | CNAS | SL5 SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 |  | SPIETH | 3378 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000300 |  | 19P000300 | FALSE | CHASS | SL5 HUM & SOC SC--URGENT: PAINT AND PATCH WALLS |  | HUM & SOC SC | 4403 | COMPLETE | Milagros Pena | Cindy Williams | ANDREA HERAZ |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000301 |  | 19P000301 | FALSE | CNAS | SL5 SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH |  | SCIENCE LAB1 | 214 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-09-27 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000306 |  | 19P000306 | FALSE | CHASS | SL5 HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 |  | CHASS INT N | 4017 | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-01 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000307 |  | 19P000307 | FALSE | BAS | SL5 LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 5 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… | 2018-10-03 | Enrico Baez | 1/8/19 EB Job Completed by Jess H. 12/22/18 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. | N/A | 2019-01-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000308 |  | 19P000308 | FALSE | BAS | SL5 ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK |  | ABER INVER |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | JP 04/04/19 Project Complete DL 10/4/18; Jess currently has this project scheduled for Winter break. |  | Enrico Baez | 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. |  | 2019-04-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | IN PROGRESS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 3/28/19, Doors are in the process of being …. DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez | 10/3/2018 EB approx. 16-20 doors need repair. Sand, patch, repair as needed. Re-varnish. ---9/24/18 EB Site visit scheduled with John Jensen for 9/27 | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000311 |  | 19P000311 | FALSE | ATHLETICS | SL5 ATHLETICS 150-KEYLESS ENTRY | Keyless entry system | ATH DANCE | 0150 | Project Intake | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | DAN LERMAN |  | R2 |  | FALSE |  |  | 2018-10-02 | [7 empty] | 2018-09-27 | Enrico Baez | 1/31/19 EB emailed Joe Erbland inquiring if funding for project has been secured or to cancel request. 11/20/18 EB intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. From work order-looking to have two doors turned into key less entry for security of the practice center. 1/31/19 EB emailed Joe Erbland inquiring if funding for project has been secured or to cancel request. 3/28/19 E. Baez- Consulted with lock shop, approximate cost would be $10,000 4/2/2019 E. Baez- Conducted site walk with HCI Systems Chris and John for proposal. 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to EBZ. 7/26/19 E. Follow up email to Chris Rogers from HCI. | YES |  | FS | FALSE | 2018 | 2019-08-16 |  | 1
19P000312 |  | 19P000312 | FALSE | BCOE | SL5 VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP |  | STUDENT SERV | 1227 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000313 |  | 19P000313 | FALSE | CHASS | SL5 HUMANITIIES SOCSCI - PATCH HOLES & PAINT - |  | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000314 |  | 19P000314 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000316 |  | 19P000316 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL |  | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…Anticipated completion 11/9/18. | 2018-10-03 | Ron Veloz |  | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000317 |  | 19P000317 | FALSE | BAS | SL5 HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 | conversation with Susan Marshburn and Bob Brumbaugh. | PENTLAND A |  | CANCELED BY FS | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER | [5 empty] | FALSE |  |  | 2018-10-03 | [9 empty] | D. Dinh : Project canceled; customer collaborating with John Peraino using a TMA work order per |  | 2019-01-14 | FS | FALSE | 2018 | 2019-08-16
19P000318 |  | 19P000318 | FALSE | CNAS | SL5 GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE |  | GEOLOGY | 420 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-04 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000319 |  | 19P000319 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB |  | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-04 | FS | FALSE | 2018 | 2019-08-16
19P000322 |  | 19P000322 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-05 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000324 |  | 19P000324 | FALSE | CNAS | SL6 SPIETH HALL ASSESS AIR VENT OR PURIFIER FOR LAB | Provide the single pass exhaust, air changes (6-12 ACH) and the negative air requirements for PI to perform surgeries in the room. | SPIETH | 1312 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 106 |  | FALSE |  |  | 2018-10-05 | [7 empty] | 2018-10-10 | Ron Veloz | 04/04/19 O-RVL: RV emailed Deborah Hughes requesting cancellation of this project on 04/04 and copied the FS CR team. END~ 04/04/19 O-ANS: Canceled per Minor Reno meeting. 03/25/19 O-RVL: Ron V Contacted Estella via email 01/10/19 to provide the status for lab/surgical room 1312 and informed her of the collaborative results between efforts between Facilities Services and EH & S. Ron V stated "After further investigation of the building mechanical systems and review by EH&S; Facilities Services has confirmed the existing building mechanical systems is unable to provide the single pass exhaust, air changes (6-12 ACH) and the negative air requirements resulting in the cancellation of this request. Please feel free to contact me if you have any questions or need additional information". END~ O-RVL: Updated this project and copyied information from FAMIS. Not sure who requested this request to be a project. RV may need to rescope the project after Winter prioritizing. 01/10//19 RV copied notes from FAMIS and input the following notes: "10/10/18 O-RVL: Received email from Deborah Hughes to determine if this request is a SL5 or SL6. RV visited the site on 10-10 and saw filter media covering the supply air diffusers. RV sent photos to D.H. and informed her this was a SL6 for BM to remove filter media from the supply air diffusers. 12-21-18. R-DMU. W/O is waiting on filter to be removed. Will need to calculate air changes. Make repairs as needed. Room needs to be set (Negative). This may be the solution to their air deficiency. 11/21/18 R-DMU: Spieth hall. Rm 1312. Walk this job with BeiWei. 10-11-18. R-DMU. Will need tech to pull 3 ply media filter from supply register and verify proper air changes, and Exhaust flow with Flow Hood". | N/A | 2019-04-04 | FS | FALSE | 2018 | 2019-08-16
19P000326 |  | 19P000326 | FALSE | VC-UNIV.ADV. | SL5 HINDERAKER - PATCH & PAINT |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-08 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000337 |  | 19P000337 | FALSE | CHASS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | Remove whiteboard (in front of room), mount LED mount, add double duplex and electrical power behind LED, patch and paint wall | PSYCHOLOGY1 | 3210 | PLAN DEVELOPMENT/CHECK | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 1 | 101 | FALSE |  |  | 2018-10-11 | [6 empty] | 8/14/19, DL; Conducted site visit with Trades. We will schedule the space to be blocked out and start the work mid September….8/1/19, DL; Planning to start this project in two weeks……7/15/19, DL; I will walk the project in the near future and schedule the work if permits are not required…… | 2019-01-15 | Enrico Baez | 1/15/2019 E Baez please Scope completed 1/15/2019 see Shared drive file for more information. | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000340 |  | 19P000340 | FALSE | CNAS | SL5 PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE |  | SKYE HALL | 349 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | VICTORIA AVALOS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000341 |  | 19P000341 | FALSE | CNAS | SL5 PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL |  | PIERCE |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000346 |  | 19P000346 | FALSE | CNAS | SL5 I&Q--PAINTING ROOMS IN THE I&Q |  | EAST I&Q FAC |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | IMAD BAYOUN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2019-01-09 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000347 |  | 19P000347 | FALSE | CNAS | SL5 SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT |  | SPIETH | 3320 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-10-16 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000350 |  | 19P000350 | FALSE | CHASS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | MISC WORK IN ROOMS 3121 AND 1133 Patch and paint-relocate white boards, hang pictures. | PSYCHOLOGY1 | 3121, 1133 | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 4 | 3 | TRUE |  |  | 2018-10-17 | [6 empty] | 8/15/19, DL; This Project is 100% Complete…….. 8/1/19, DL; We will start this project this Friday…… 7/15/19, DL; Appears not plans and permits will be required for the work. I will verify and schedule the work in the near future if no plans or permits are required….. | 2019-04-15 | Enrico Baez | 4/11/19 E.Baez emailed Toya Adams to schedule site visit | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000353 |  | 19P000353 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT-2348 |  | OLMSTED | 2340 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-19 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000354 |  | 19P000354 | FALSE | SOM | SL5 WEBBER 2130A-PAINT CHERI'S NEW OFFICE |  | WEBBER | 2130A | COMPLETE | Deborah Deas | Brandon Barbosa | DOMINIC SALAZAR |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-19 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000355 |  | 19P000355 | FALSE | CHASS | SL5 HYDRATION STATION FOR THE SECOND FLOOR WATKINS | Hydration station installed where the water fountain is. | WATKINS | 2122D | CANCELED BY FS | Milagros Pena | Cindy Williams | CYNTHIA REDFIELD |  | Dan Lerman |  | 112 |  | FALSE |  |  | 2018-10-22 | [8 empty] | Enrico Baez | 4/24/19 LB: Per Ron Rector, hydration stations in common areas will be scheduled by FS. Project canceled. ~ 10/22/18 SC: Called Cynthia to clarify that this would be a project. Also asked if she wanted the water fountain checked out in the meantime since it seems to be stinking. She will put in a separate WO for this issue. |  | 2019-04-24 | FS | FALSE | 2018 | 2019-08-16
19P000356 |  | 19P000356 | FALSE | CHASS | SL5 PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT |  | HUM & SOC SC | 4401 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-24 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000357 |  | 19P000357 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS, TIME SENSITIVE |  | HUM & SOC SC | 1302 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-10-25 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000358 |  | 19P000358 | FALSE | CNAS | SL5 GEOLOGY - ACCOMMODATION REQUEST |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-10-26 | [6 empty] | 4/15/19, DL; This Project is 100% Complete……. 3/28/19, DL; Plans are approved. We will start the work on 4/1/19……3/18/19, DL; Waiting for approved plans from building official……2/28/19, DL; Plans were submitted to building official for review. Once plans are approved, we will schedule the work………..2/14/19, DL; Plans are in process and we will apply for building permit next week………….. | 2019-02-07 | Ron Veloz | 02/07/19 O-RVL: RV changed title from "Geology" to "Physics". SOW is completed and on the server. Emailed a copy of SOW to FS team on 2/7. Received email from Ron Rector requesting Dan L. to provide Ronda Inzuna status update. END--- 01/31/19 O-RVL: Intake in progress. --- 01/15/19 O-RVL: Updated notes, the following SOW was from the requestor. --- 12/14/18 O-RVL: RV walked the site with Deborah Mc Williams on Mon 12/10. RV to create SOW. Returned request back to O-UA1 and will work from O-UA1 until the project is prioritized. "Potential scope of work for accommodation request: 1. Pour 10x10 cement pad for reserved electric transportation vehicle. 2. Electric charge station 3. appropriate signage" --- Deborah McWilliams is the main contact 951-218-3720 --- 11/14/18 RV: RV & Monty Received an "FYI" email from Deborah Mc Williams on 11/09/18 with information related to the approval of the charging station --- location currently undergoing review by the CBO. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000360 |  | 19P000360 | FALSE | CNAS | SL5 GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING |  | GEOLOGY | 1444 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000361 |  | 19P000361 | FALSE | CHASS | SL5 OLMSTED-PATCH & PAINT/REPLACE CARPET |  | OLMSTED |  | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 05/29/19 O-ANS: Project completed 05/09/19 per Paul Ditty. |  | Paul Ditty | N/A | N/A | 2019-05-09 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000362 |  | 19P000362 | FALSE | CHASS | SL5 PATCH & PAINT/REPLACE CARPET (HALLWAY) |  | OLMSTED |  | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000364 |  | 19P000364 | FALSE | CHASS | SL5 PATCH AND PAINT |  | CHASS INT S | 3106 | COMPLETE | Milagros Pena | Cindy Williams | FRANCESCA MOREIRA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-30 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2019-03-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000367 |  | 19P000367 | FALSE | CNAS | SL5 SCILAB 1 0211- PATCH & PAINT |  | SCIENCE LAB1 | 211 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-31 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000369 |  | 19P000369 | FALSE | CNAS | SL5 PIERCE - PAINT IS PEELING OFF WALLS |  | PIERCE | 3341 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000370 |  | 19P000370 | FALSE | ENROLLMENT SERVICES | SL5 PATCH AND PAINT CAMPUS TOURS |  | STUDENT SERV | 1137 | COMPLETE | LaRae Lundgren | TBD | ELIZABETH TATUM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000371 |  | 19P000371 | FALSE | CHASS | SL5 URGENT PATCH AND PAINT IN CHAIR'S OFFICE |  | HUM & SOC SC | 1213 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-11-05 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000373 |  | 19P000373 | FALSE | ITS | SL5 URGENT-INSTALL RECPTACLE, ENCLOSURE & MOUNT BRACKET |  | GERMPLASM | 881 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-07 | [6 empty] | <div>mount a bracket to the Network Pole at AgOps. This will include mounting a bracket, an enclosure and a 20 Amp electrical receptacle.</div> |  | Ron Veloz | 2/26/19-LB: Per Ron Veloz, this project is complete. |  | 2019-02-26 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000375 |  | 19P000375 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT HOLES |  | SKYE HALL | 365 | COMPLETE | Kim Wilcox | Karim Zahedi | FELECIA GARRETT |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-07 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000377 |  | 19P000377 | FALSE | CNAS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | Replace the gates on the Schneider House driveway, which secure the property, with the taller iron gates that used to be installed at the Gardens entrance. This will require new fence posts and hinges as well. The taller gates are stored along the side of the garage at Schneider House, and Facilities staff can come see them anytime. Please note this is a safety and security project. | SCHNEIDER |  | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | R2 | 117 | FALSE |  |  | 2018-11-08 | [7 empty] | 2019-04-05 | Ron Veloz | 08/08/19 O-RVL: Estimate on Hold. Cannot ust previous costs from FS trades and require vendor quotes. RV will contact a vendor to price the gate modifications and installation (gates by department). RV will need to 08/02/19 O-RVL: Estimate in progress with FS Pricing. END~ 06/12/19 O-RVL: RV received costs from Sheetmetal and Carpentry, pending estimate from Paint-P. Ditty. 04/15/19 O-RVL: RV updates, Measured gate with Enrico on 4/5. Contacted Cory on 04/15 to schedule a visit on 04/16 to view and estimate Gates. RV will contact Monty with Estimate | YES |  | FS | FALSE | 2018 | 2019-08-16 |  | 1
19P000378 |  | 19P000378 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 |  | HUM & SOC SC | 1613 | COMPLETE | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-11-13 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000380 |  | 19P000380 | FALSE | VC-STU.AFF. | SL5 PATCH AND PAITN- WALL PAINT IS PEELING |  | HEALTH SERV | 404 | COMPLETE | Brian Haynes | Cathy Eckman | SAMANTHA HARRIS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-19 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000384 |  | 19P000384 | FALSE | ENROLLMENT SERVICES | SL5 PATCH HOLES IN WALL AND PAINT |  | STUDENT SERV | 2234 | COMPLETE | LaRae Lundgren | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000386 |  | 19P000386 | FALSE | PROVOST/EVC | SL5 ROOM CHANGES |  | STUDENT SERV | 3106A | COMPLETE | Cynthia Larive | Luisa Levario | STEPHANIE ARCINIEGA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 4/15/19, DL; This Project is 100% Complete…… 2/28/19, DL; Conducted site visit. We need to schedule the work in the next 2-3 weeks This is for room 3109 C&D ……….. | 2019-02-07 | Ron Veloz | 02/07/19 O-RVL: RV completed Intake & Moved to "Que to Start". END--- 02/06/19 O-RVL: RV updates, Scope of work is to remove shelving from room, patch and Paint. Dan requested info on room availability. RV contacted Danielle for follow up from 02/05 call. RV will visit site, take pics, and follow up with Dan L.erman. Danielle reported that room 310C is vacant and available. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000388 |  | 19P000388 | FALSE | BCOE | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | BCOE Advising is being reassigned to space on the 3rd floor of Skye (at the recommendation of the University Space Committee). | SKYE HALL | 308 | COMPLETE | Christopher Lynch | Maggie Souder | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-26 | [6 empty] | 7/15/19, DL; This project is 100% Complete………..7/1/19, DL; This project ois 95% Complete. Floor covering install will start this Wednesday…………6/17/19, DL; This project is almost complete. Target complete date is July 1st….…..5/31/19, DL; We are making good progress on this project. we are on tract to be copmplete with this project on or before July 1st……5/15/19, DL; Work is in progress and we are on schedule for th3 6/28/19 complete date…….5/1/19, DL; We will start this project this week. 4/15/19, DL; Plans were approved today. We will work on material and schedule the work. We will start this project shortly after May 1st…….3/18/19, DL; We are working on plans and plan to apply for building permit an plan review process next week | 2019-02-13 | Ron Veloz | 03/04/19 O-RVL: Updating notes on FAMIS & Access DB. Scoping is completed. After discussing the project with Monty and Dan, this project does not require an estimate and will be covered under Core since it is required for student advising and department operations. RV has communicated this to Sharyl Murdock on 03/04/19. RV Reassigning from O-RVL to O-UA1. Intake was completed on 02/13/19. ~ 02/22/19 O-RVL: RV walked the site with Enrico to survey carpet. Enrico suggested a deep extraction. RV contacted Custodial to sample a section to determine if cleaning the carpet could enhance the appearance. Pending response for Gena L. ~ 02/21/19 O-RVL Spoke with Monty about carpet conditions. Will walk with Enrico for second opinion. ~ 02/13/19 O-RVL: Completed intake. 01/28/19 O-RVL: Jobwalk scheduled with Hour Glass Co 1/28/19 11:30am ~ 01/25/19 O-RVL: Met Maggie & Sharyl M at Skye to review the SOW for new walls, sliding glass door and interior viewing window. RV will contact a glazing vendor the week of 01/27 to request a quote to install new storefront windows and sliding glass door within a storefront frame or Western Integrated Frame ~ 01/23/19 O-RVL: RV emailed Sharyl for meeting date and time. Pending response. Received response on ~ 01/23 from Sharyl. She will schedule the meeting/site visit. Pending invitation. ~ 1/22/19 O-RVL: Acknowledged request. Will schedule a site visit with Sharyl Murdock. Left voice message and emailed Sharyl (01/22) to schedule a site visit. Proj # is not in the Data base, unable update notes. ~ 01/22/19 RV spoke with Sharyl and will receive an email with updates. ~ 01/22/19 RV received email with updates from Sharyl and added to the project folder. ~ MA 1/7/19: Assigning to Ron Veloz for Estimation process with BCOE partners. | YES | 2019-07-15 | FS | FALSE | 2018 | 2019-08-16 | FY 19-20
19P000390 |  | 19P000390 | FALSE | CNAS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 0 |  | TRUE |  |  | 2018-11-29 | [6 empty] | 7/1/19, DL; This project is 100% Complete…………6/17/19, DL; material is ordered. This project should be complete by July 1st…..5/31/19, DL; Plans were apprvied this week we will work on the contract and hopefully have the notice to proceed in the next two weeks. It is our goal to have the work complete on or before July 1st……5/15/19, DL; Need to order the special order door and frame…. | 2019-02-07 | Ron Veloz | 02/12/19 O-RVL: Scoping is complete. Revised door layout and emailed April photos of the proposed storefront door system received from D.L. on 2/11. April Meinzer approved storefornt door system on 2/12. RV reveised floor plan utilizing the existing cased opening as discussed with D.L. on 02/11. RV provided D.L. a copy of the revised Intake Formw/ layout. Form w/ layout. Unable to update project notes on FAMIS -Project is not available. END--- 02/07/19 O-RVL: Monty asked RV to follow up on this request. Ron V scheduled meeting with April Meinzer on 2/7 at 1:30pm to review intake information for the proposed project at room 5494. FAMIS Updated END--- | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-08-16 | FY 19-20
19P000396 |  | 19P000396 | FALSE | CAP.PROG. | SL5 TRAILER #14 - CAMPUS INITIATED - STRUCTURE |  | T14 |  | COMPLETE | Jacqueline Norman | Sharyl Murdock | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-31 | [6 empty] | 2/28/19, DL; This Project is 100% Complete…..Trailers were demolished. We need to install the utilities. Once the Grow Pod is on site, we will connect the utilities to the structure…… |  | Enrico Baez |  |  | 2019-02-28 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000399 |  | 19P000399 | FALSE | GRAD.DIV | SL5 NEW CARPET + WALL PAINT |  | UNIV OFC BLD | 100 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-06 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000400 |  | 19P000400 | FALSE | CHASS | SL5 CREATE DOOR INTO HALLWAY | Create a door between the hallway and CHASS INTS 2117A. The door should be placed at the south end of 2117A. | CHASS INT S | 2117A | CANCELED BY FS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 103 |  | FALSE |  |  | 2018-12-06 | [6 empty] | 05/21/19 O-ANS: Canceled by FS per conversation with Paul Richardson and combined with Project 19P000419. | 2019-04-15 | Enrico Baez | 4/18/19 E. Baez-Emailed Paul, Monty and Chris P. The project is requested in conjunction with Project 19P000419 (keyless entry in various offices within 2117). Both projects will need to be considered one project as work is requested for same area. Waiting for HCI to submit proposal. 4/15/19 E. Baez- Conducted site visit with Paul Richardson. Request is for separate entrance from hall to 2117A. Offered two possibilities and forwarded to Paul. Waiting for response. Will need detailed scope. | YES | 2019-05-21 | FS | FALSE | 2018 | 2019-08-16
19P000401 |  | 19P000401 | FALSE | PLANNING & BUDGET | SL5 PATCH HOLES IN WALL AND PAINT |  | HINDERAKER | 4148E | COMPLETE | Gerry Bomotti | Sharyl Murdock | SHANNON TIMMONS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000405 |  | 19P000405 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED |  | HEALTH SERV | 0100D | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-11 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | HOLD - FACILITIES SERVICES | Kim Wilcox | Karim Zahedi | ALEXIS RAMBAUD |  |  |  | 1 | 0 | FALSE |  |  | 2018-12-11 | [7 empty] | 2018-12-20 | Ron Veloz | 07/01/19 O-RVL: HOLD PER SUSAN. 04/15/19 O-RVL: On Hold per Susan Marshburn, Pending follow up Gerry Bomotti as of 04/15. FAMIS & Acess notes are updated. END~ 03/15/19 O-RVL: RV reviewed FAMIS. All notes we located on the "Service Request" screen. RV copied onto the project screen and Access data base. RV will cancel this request on Access and send out an email to Deborah H and team to cancel the request on FAMIS. END--- 03/06/19 O-RVL: RV received email from Monty requesting information the project not in Access or FAMIS. END--- 01/18/19 O-RVL: RV emailed Karim to inform him of the project covered under the SLA. END--- 01/17/19 O-RVL: RV emailed Karim to inform him of the project covered under the SLA. 01/15/19 O-RVL: Met with Monty on 1/15, Monty informed RV the work will be covered under the SLA agreement in support of Business operations. No estimate is required. RV to contact Karim with this information on 01/16/19. 01/14/19: O-RVL: Met with Dan L. onsite to review the project scope. RV & Dan also spoke with Louis about the process. RV will work on the estimate and submit to Karim & Louis by CBD 01/18/19. RV Has informed Dan L. the project is on the "Non Prioritized List". 01/11/19: O-RVL: Emailed Karim and informed him that he will receive an estimate later the following week. 01/07/19: O-RVL: Monty asked Enrico to look into the this project. I (RV) told Monty that I'm already involved and will complete the estimate. Monty agreed and asked RV to follow up with Karim. 12/21/18 O-RVL: Received a response from Bob W., stating "the area is suitable to be an office space understanding understanding that we must conduct a more in-depth review and approval process..." 12/20/18 O-RVL: Emailed Bob Williams with the existing and proposed floor plan asking if it would be suitable to create an office and requested a budget estimate to add a wall with a door. 12/20/18 O-RVL: Ron V. Visited site and spoke with Karim and viewed the proposed location for the new office. 12/18/19 O-RVL: Received email from D. Hughes on 12/18/18 to look into this request for estimate. | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000408 |  | 19P000408 | FALSE | SOM | SL5 PATCH & PAINT - 2605 SOM ED |  | SOM EDUC | 2605 | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000410 |  | 19P000410 | FALSE | SOM | SL5 PAINT OFFICES AT UC PATH |  | INTELLICTR |  | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-14 | [6 empty] | 06/06/19 O-ANS: Canceled per customer request. Paul spoke with customer who will outsource work. |  |  |  |  | 2019-06-06 | FS | FALSE | 2018 | 2019-08-16
19P000411 |  | 19P000411 | FALSE | GRAD.DIV | SL5 PAINT, CARPET AND BLINDS |  | UNIV OFC BLD | 150 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-14 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000413 |  | 19P000413 | FALSE | CNAS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | Batchelor 3111-Refresh BSL2 lab to accomodate Biosafety Cabinet. The Biosafety. Cabinet will be procured by BPSC. | BATCHELOR | 3111 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH | PATTY SPRINGER | Dan Lerman |  | R1 | 107 | FALSE |  |  | 2018-12-17 | [7 empty] | 2019-06-12 | Ron Veloz | 08/08/19 O-RVL: Emailed Patty S for status on the departments decision with the project/estimate. Pending response. END~ 07/19/19-RVL: Status on Hold-Pending the customer's acceptance of cost ROM estimate. END~ 07/03/19 O-RVL: Prepared estimate and will review with Monty before contacting Patty Springer or emailing the estimate. RV sent Estimate to Patty on 07/03. END~ 07/02/19 O-RVL: Met with Monty. RV will prepare estimate and call Patty to explain the estimate costs and inclusions based on EH&S requirements and also share concerns about the building infrastructure capabilities questioned by PD&C to meet the BSL2 lab requirements. Explain that the Batchelor Building reno will not increase the building's capacity and the BSL 2 requirement may not be met if the building single pass exhaust and HVAC systems cannot deliver the proper air exchanges etc.. Costs will not include additional work and or building systems modifications if required by PD&C. END~ 07/01/19 O-RVL: Pending estimate completion, hold per Monty on 06/28/19 to discuss/review estimate. END~ 06/24/19 O-RVL: Preparing Estimate. Received costs from Jess H for abatement and to replace flooring. Paul D will providean estimate for patch and paint. END~ 04/15/19 O-RVL: RV to scope project at the new room location 3111. End~ 03/19/19 O-RVL: Updating notes. PENDING Site visit with PM at rm 3111. Date TBD. END~ 06/17/19 O-RVL: Walked site with Patty Springer on 06/12/19. Reviewed SOW and noted work to make the necessary repairs per EH&S survey/correction list. RV will prepare a ROM estimate with project ranges. END~ 03/07/19 O-RVL: RV noticed this project was not on the Minor renovation list and brought up to Monty via email. END~ 03/18/19 O-RVL: RV changed room from 2203 to 3111. END ~ 03/04/19 O-RVL: Changed from O-RVL to O-UA1. END ~ 03/01/19 O-RVL: Received confirmation from Patty that room 3111 will be the permanent location for lab. RV changed the title from SL5-"Install Bio-safety Cabinet and Sink In Batchelor 2203" to SL5 "Renovate Batchelor Hall BSL-2 Lab Room 3111". RV will visit site for initial intake upon prioritization by the Dean's office. END~ 02/19/19 O-RV: Patty "HI Deborah, There is much uncertainty about the Batchelor Hall renovation and the timing of installation of an equipment room in 2163. Given that, I am considering 3111 the permanent location for the biosafety cabinet (replacing room 2203). 3111 will remain a dedicated BSL2 -use room" END ~ 02/14/19 O-RV: Patty Springer decided to try to use 3111 in lieu of 2203. END ~ 02/13/19 O-RVL: Received email from Tiffany Kwok, she wrote, " Hi Dr. Springer, It was great meeting with you this morning. For Batchelor 3111, there are a few items that need to be addressed before it can support BSL-2 work. Floors should be patched to provide a smooth and easily cleanable surface. Base coves along the wall should be replaced or repaired to provide a smooth and easily cleanable surface. Base coves under the cabinets on the corners should be provided. Provide a layer of sealant over the cabinets to ensure that the cabinets are moisture resistant and easily cleanable. Seal, repair or replace the wooden rack on the wall to provide a moisture resistant and easily cleanable surface. Ensure the door is self-closing. END ~ Since this is not a new facility and the space is not undergoing major renovations, it is not required to provide negative airflow into the space. However, it is still important that the air from the laboratory is not recirculated into clean spaces. Please let me know if you have any additional questions. Thanks, Tiffany Kwok". END ~ 02/08/19 O-RVL: On Feb 8, 2019, at 11:54 AM, Bpschair wrote: Hi all, I don’t think we want to do this - it is too much work, disruption, and expense. Deborah Mc Williams requested Dan L to place the current project on "Hold" pending further direction from Patty. This way it will remain in queue". END ~ 01/29/19 O-RVL: Adding SOW for BSL2 Lab | YES |  | FS | FALSE | 2018 | 2019-08-16 |  | 1
19P000415 |  | 19P000415 | FALSE | CHASS | SL5 PSYCHOLOGY -PSY BLDG- MINOR RENOVATION | Doorway with side window connecting 2124C to 2124B, as well as another doorway to connect 2124C to 2124D. | PSYCHOLOGY1 | 2124A,B,C,D | IN PROGRESS | Milagros Pena | Cindy Williams | Jay Melashenko |  | Dan Lerman |  | 3 | 2 | FALSE |  |  | 2018-12-17 | [6 empty] | 8/15/19, DL; This project is in progress and schedule for complete in the next 4- weeks…….8/1/19, DL; Gunter is working on Plans. Plan to submit plans for building permit in two weeks. Once plans are approved, we will schedule the work….. | 2019-01-09 | Dan Lerman | 12/14/18 E.Baez-Met with Jay Melashenko. Suggested the possibility of cutting wall open in 2124D and 2124B both leading to 2124C. No doors to be installed. Only finish opening. Install a low rise threshold at new opening, new carpet recently installed. Need to move outlets. Customer to pay for work. | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000417 |  | 19P000417 | FALSE | VC-UNIV.ADV. | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY |  | UV BLDG A | 201 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 2018-12-18 | [8 empty] | Enrico Baez | 8/6/19 LB: Canceled by client |  |  | FS | FALSE | 2018 | 2019-08-16 |  | 1
19P000419 |  | 19P000419 | FALSE | CHASS | SL5 CHASS INT SOUTH 2117-CARD ACCESS | Remove Door and wall leading to 2117 Media Library and reconfigure to allow enterance into 2117 A & J without having to go through 2117C. | CHASS INT S | 2117 | IN PROGRESS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 8/1/19, DL; Gunther is working on plans. Once permit is approved, we will scheudle the work…. | 2019-03-21 | Enrico Baez | 7/1/2019 E. Baez- Met with HCI on 6/28/2019, conducted job walk. Waiting for proposal. 4/18/19 E. Baez-Emailed Paul, Monty and Chris P. The project is requested in conjunction with Project 19P000400 ( moving walls and creating separate entry into 2117A). Both projects will need to be considered one project as work is requested for same area. 4/2/19 E. Baez- conducted job walk with HCI for proposal. Waiting for proposal. ***per Paul Richardson remove 2117G, 2117H and 2117J from request*** 3/19/19 E. Baez Scheduled site visit with Paul for 3/21/19 @ 11:00 ***3/19/19: O-ANS: Customer SOFT PRIORITIZED as priority 102.* | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000420 |  | 19P000420 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT WALL |  | SKYE HALL | 325 | COMPLETE | Kim Wilcox | Karim Zahedi | REYNA ALARCON |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-19 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000421 |  | 19P000421 | FALSE | CHASS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | Install door to access hallway directly | OLMSTED | 2139I | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 5 | 110 | TRUE |  |  | 2018-12-19 | [7 empty] | 2019-02-05 | Enrico Baez |  | YES |  | FS | FALSE | 2018 | 2019-08-16
19P000424 |  | 19P000424 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET |  | CHUNG HALL | 445 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-12-20 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16
19P000425 |  | 19P000425 | FALSE | PLANNING & BUDGET | SL5 PAINT VIDEO PRODUCTION SUITE & HANG ITEMS |  | HINDERAKER | 1159A | COMPLETE | Gerry Bomotti | Sharyl Murdock | LISA CUSICK |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-20 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19P000428 |  | 19P000428 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES AVC OFFICE PREPARATION |  | STUDENT SERV | 3102 | CANCELED BY CLIENT | LaRae Lundgren | TBD | ANGIE GRAY |  |  |  | 0 |  | FALSE |  |  | 2019-01-03 | [8 empty] | Ron Veloz | 03/18/19 O-RVL: RV received a phone call from Angie Grey on 03/18 to verify if this project was cancelled based on a cancellation request in Jan 2019. RV informed Angie that the project was cancelled. 02/06/19 O-RVL: Updating notes. "Cancelled by Angie Grey on 1/22/19". 02/11/19 O-RVL: Dan L asked RV to confirm with Angie Grey that the project is cancelled. RV called and left a voice message with Angie(2/11). RV will follow up. END--- | N/A | 2019-01-22 | FS | FALSE | 2019 | 2019-08-16
19P000429 |  | 19P000429 | FALSE | CHASS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | Patch & Paint | COLL BLDG SO | 103 | COMPLETE | Milagros Pena | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-01-03 | [6 empty] | 07/26/19 O-ANS: Project complete per Paul Ditty. 06/06/19 O-ANS: Project scheduled to be completed. |  |  |  |  | 2019-07-26 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20
19P000431 |  | 19P000431 | FALSE | VC-STU.AFF. | SL5 STUDENT SERVICES REMOVE NAILS AND PATCH WALL |  | STUDENT SERV | 2128 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | VALERIE SANCHEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-04 | [6 empty] | 6/24/19 O-ANS: CANCEL WO/PROJECT PER DONNA POWELL EMAIL. |  |  |  |  | 2019-06-24 | FS | FALSE | 2019 | 2019-08-16
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | COMPUTING | 161 | PLAN DEVELOPMENT/CHECK | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 2019-01-07 | [6 empty] | 8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, Once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was canceled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez | 7/26/2019 E. Baez Re-assigned RECHARGE project to DLN and added to Access by Linda. |  |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000434 |  | 19P000434 | FALSE | PROVOST/EVC | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | Please patch 50 plus holes on the wall and repaint that wall in Skye hall 136 due to the BKM removing the furniture attached to the wall. Please call Anita Ortiz if you have any questions at x2-5229. Shanshan's extension x7753 has not been moved to her new location yet. | SKYE HALL | 136 | COMPLETE | Cynthia Larive | Luisa Levario | THERESA WAGNER | SHANSHAN | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-07 | [6 empty] | 07/20/19 O-ANS: Work Complete per Paul Ditty. |  | Paul Ditty |  |  | 2019-07-22 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20
19P000438 |  | 19P000438 | FALSE | CNAS | SL5 BOTANIC GARDENS RAILROAD TIE WALLS | Request for review and cost estimate for the repair of two railroad tie walls in the Botanic Gardens. 1) Retaining wall located below the Iris Garden (across from the Greenhouse). 2) Low wall located along the pathway just below the Garage Office. | BOTAN INFO C |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 118 |  | FALSE |  |  | 2019-01-08 | [8 empty] | Ron Veloz |  |  | 2019-03-05 | FS | FALSE | 2019 | 2019-08-16
19P000439 |  | 19P000439 | FALSE | VC-RED | SL5 SPIETH PATCH AND PAINT ROOM 335 |  | SPIETH | 335 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-08 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000440 |  | 19P000440 | FALSE | CNAS | SL5 GH#21--INSTALLATION OF GROW POD BEHIND GREENHOUSE #21 |  | GH21 |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER | PATRICIA SPRINGER | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-08 | [6 empty] | 5/31/19, DL; This project is 100% complete :)……5/15/19, DL; Project is complete except for chain link fence. Fence will be installed some time early next week…….5/1/19, DL; Grow Pod is installed with power and water. Still need to install fence and door lock….. 4/15/19, DL; Grow Pod is scheduled for delivery this Thursay. Once on site, we will connect all utilities and this project will be complete. 2/28/19, DL; Demo is complete. We need to veify utilitiy point of connections. Once utilities are verified, we will install the water and power……. |  | Dan Lerman |  |  | 2019-05-31 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000442 |  | 19P000442 | FALSE | BCOE | SL5 WINSTON CHUNG- PATCH/PAINT ROOM 319 |  | CHUNG HALL | 319 | COMPLETE | Christopher Lynch | Maggie Souder | BILL BINGHAM |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-09 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000445 |  | 19P000445 | FALSE | BCOE | SL5 BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT |  | BOURNS | B0328D | CANCELED BY FS | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  |  |  | 0 |  | FALSE |  |  | 2019-01-11 | [8 empty] | Ron Veloz | 02/27/19 O-RVL: RV sent a project cancellation request to Deborah H and cc'd Alan S., Linda B., Loretta V. & Monty. RV reassigned from O-RVL to O-UA1. END--- 02/22/19 O-RVL: RV Received information from the last team meeting that is project will be cancelled and resubmitted at a later date. RV spoke with Maggie about the cancellation on Wednesday 2/20 and informed her a I would send a letter to follow up from our conversation. Maggie understood the scope creep from the previous project and will resubmit the request at a future date. END--- 02/15/19 O-RVL: Ron V will contact Maggie and explain this request would exceed our proejct allowance and place FS out of compliance with UC requirements. RV will present options to the customer. Possibility to utilize black out curtains and or BKM style furniture as an immediate altenative (Cost absorbed by the departments). The customer will be able to resubmit the request at a later date. END--- 2/7/19: Alan S. Customer Relations Team to follow-up with customer re: change in scope of work. END--- 1/11/19 SPOKE TO DAN LERMAN-THIS PROJECT MAGGIE SOUDER NEEDS IT DONE ASAP - PLEASE SEE DAN LERMAN FOR MORE INFO...DEBORAH email to Monty for Maggie's request. | N/A | 2019-02-27 | FS | FALSE | 2019 | 2019-08-16
19P000448 |  | 19P000448 | FALSE | CHASS | SL5 ARTS 333- PATCH AND PAINT |  | ARTS | 333 | QUEUE TO START | Milagros Pena | Cindy Williams | SONJA SEKELY-ROWLAND |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-01-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000449 |  | 19P000449 | FALSE | CNAS | SL5 PAINT OFFICE AREA OF 229A FOR RELOCATION |  | FAWCETT LAB | 229A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-01-14 | [6 empty] | 04/05/19 O-ANS: Project complete per Paul Ditty and closed in FAMIS. |  |  |  |  | 2019-04-05 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000451 |  | 19P000451 | FALSE | SOB | SL5 ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 |  | ANDERSON 1 (N) | 58 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-15 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  |  |  |  | 2019-02-01 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000453 |  | 19P000453 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT |  | CHUNG HALL | 447 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-17 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000455 |  | 19P000455 | FALSE | VC-STU.AFF. | SL5 FILL AND PAINT OVER HOLES ON WALL |  | HEALTH SERV | 100 | QUEUE TO START | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-17 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000458 |  | 19P000458 | FALSE | SPP | SL5 CHASS INTS-BUILD PERM DRYWALL DIVIDER OR APPROVE BKM AIRWALL |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ | LUISA LEVARIO | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-19 | [6 empty] | 6/17/19, DL; This project is 100% Complete…..5/31/19, DL; This prject is making good progress and we are scheduled to be complete on or before June 19th…….5/15/19, DL; This project is in progress and schedule for complete near 6/15/19…. 5/1/19; We started this project last week and we are planning to be complete in 4 - 6 Weeks….4/15/19, DL; Material is ordered, we will start the demolition this week. We hope to be complete in 8-weeks or less……2/28/19, DL; Plans are complete and were submitted to for review and approval from campus building official and fire marshal. Once plans are approved, we will shcedule the work….. | 2019-01-28 | Enrico Baez |  | YES | 2019-06-17 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | HOLD - FACILITIES SERVICES | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-22 | [8 empty] | Dan Lerman |  |  |  | FS | FALSE | 2019 | 2019-08-16
19P000467 |  | 19P000467 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | WATKINS | 2101 | HOLD - FACILITIES SERVICES | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  |  |  | FALSE |  |  | 2019-01-22 | [8 empty] | Dan Lerman |  |  |  | FS | FALSE | 2019 | 2019-08-16
19P000473 |  | 19P000473 | FALSE | PROVOST/EVC | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 |  | HINDERAKER | 1100 | QUEUE TO START | Cynthia Larive | Luisa Levario | THERESA WAGNER | TORRI MCGARITY | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-29 | [8 empty] | Paul Ditty |  |  |  | FS | FALSE | 2019 | 2019-08-16
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GREENHOUSE #8 | 881 | Project Intake | Kathryn Uhrich | Deborah McWilliams | NANCY FERGUSON |  | DAN LERMAN |  | R5 |  | FALSE |  |  | 2019-01-29 | [8 empty] | Ron Veloz | 08/08/19 O-RVL: R5-Contact Vendors for quotes to prepare estimate. END~ 08/02/19 O-RVL: Acknowledged request and will prepare the estimate. END~ 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to RVL. END~ 03/21/19 O-RVL Updated FAMIS by adding info for 02/26. END~ 02/26/19 O-RVL: RV emailed Monty on 02/26 with information: "I visited head house 8 and spoke with Ken Grombacher yesterday. He is familiar with the need for HCAV at HH #8 and just needs a couple of weeks to order the 3Ton roof top unit (with a heat pump) and will move forward when he is requested to do so by the PM. (SOW) The following trades will be required: Electrical-dedicated circuit, Carpentry -roof cut open and roof patching and BM/Sheet Metal-Duct fabrication/installation. Please let the team know if this becomes a bubble up. RV will complete the intake process". END- 02/25/19 O-RVL: This request was reviewed on 2/25 with team. Monty asked Ron V to look into emails and scope due to weather changes and for bubble up. RV visited the stite & is preparing intake per meeting with Monty & team. Spoke with Building Mechanical-Ken Grombaucher and received info on building trades needed to complete the HVAC 3ton roof top ackaged unit w/ heat pump. (SOW) "Need HVAC/Sheetmetal, Electrical & Carpentry(roof cutting and *roof repair(*Outsourced). Intake in progress. UPDATED on Project bench in FAMIS. Project is not on Access data base as of Feb 25 pm. Intake is in progress. | NO |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000477 |  | 19P000477 | FALSE | BCOE | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT |  | CHUNG HALL | 457 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-01-30 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000482 |  | 19P000482 | FALSE | CNAS | SL5 PIERCE HALL- PAINT/PATCH HOLES IN 1219C AND 1220D |  | PIERCE | 1219C | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JACQUELINE HAMILTON |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-02-01 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000483 |  | 19P000483 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED |  | HEALTH SERV | 404, 407, 412, 405 & 411 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-02-01 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000487 |  | 19P000487 | FALSE | BCOE | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES |  | BOURNS | A219, A211, A241 | COMPLETE | Christopher Lynch | Maggie Souder | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-02-05 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20
19P000495 |  | 19P000495 | FALSE | VC-RED | SL5 UOB RM 209- PATCH & PAINT |  | UNIV OFC BLD | 209 | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-02-08 | [6 empty] | 07/30/19 O-ANS: Project closed per Paul Ditty. 07/30/19 D-MMN: Moved furniture and filled holes. Taped base and fixtures. Primed and painted one half of office. Pulled tape replaced plates and moved furniture to other side. Removed plates taped base and fixtures. Primed and painted other half. Used spray texture on patch under window. Pulled masking. Replaced plates. Moved furniture back. Vacuumed carpet during and after total process. | [5 empty] | FS | FALSE | 2019 | 2019-08-16
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB | SPIETH | 2349 | Project Intake | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | DAN LERMAN |  | R6 |  | FALSE |  |  | 2019-02-20 | [8 empty] | Ron Veloz | 08/02/19 O-RVL: Acknowledged request and will schedule site visit with outside vendors to request quotes. END~ 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to RVL. |  |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000505 |  | 19P000505 | FALSE | CNAS | SL5 CHAPMAN HALL PAINT OFFICE WALL WHERE BOOK CASE WAS REMOVED |  | CHAPMAN | 10B | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-02-25 | [6 empty] | 05/10/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-05-10 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000508 |  | 19P000508 | FALSE | CNAS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | BOYCE | 3410 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-02-21 | [8 empty] | Ron Veloz | 08/07/19 O-RVL: Will schedule site visit soon. 07/01/19 O-RVL: Pending intake | NO |  | FS | FALSE | 2019 | 2019-08-16
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | DAN LERMAN |  | R7 |  | FALSE |  |  | 2019-02-27 | [7 empty] | 2018-10-19 | Enrico Baez | 8/9/19 E. Baez-Departemnt is paying for this project rather than having count against their allotment | YES |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000521 |  | 19P000521 | FALSE | SoB | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT |  | ANDERSON 1 (N) | 138 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-03-08 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20
19P000523 |  | 19P000523 | FALSE | CNAS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | Placed on HOLD by customer until next Quarter (Fall 2019) | SPIETH | 3366 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-03-12 | [9 empty] | 06/27/19 O-ANS: Paul Ditty met with customer to discuss scope and customer requested to place on HOLD until future semester since they were not prepared to move furniture in preparation for renovation. |  |  | FS | FALSE | 2019 | 2019-08-16
19P000526 |  | 19P000526 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT |  | CHUNG HALL | 0202 & 0203 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-03-12 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000534 |  | 19P000534 | FALSE | VC-STU.AFF. | SL5 PATCH WALLS AND PAINT |  | HEALTH SERV | 334 | QUEUE TO START | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-03-15 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000535 |  | 19P000535 | FALSE | PLANNING & BUDGET - AUXILIARY | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV | Install TV Mount and additional electrical | BANNOCK H | H0108 | COMPLETE |  |  | EDWIN MELGAR-MEJIA |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 2019-03-14 | [7 empty] | 2019-07-08 | Enrico Baez | Met with Trent Mabee, he was coordinating abatment work with Jess H. Trent's Crew to install electrical | YES | 2019-07-26 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20 | 1
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install utilities for new equipment | PHYSICS | 1132 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-03-19 | [8 empty] | Ron Veloz | 08/-8/19 O-RVL: Received equipment informaion/specifications from Mayela on 08/08. RV will prpeare intake with PI, PM and Davide Neff. END~ 08/07/19 O-RVL: RV emailed David Neff request for status & cc'd D.Lerman. Pending equipment specs from PI to determine heat loads & affect to the current Bld infrastructure and to determine new electrical load requirements. RV placed on Hold until equipment specs/ information is received. END~ 07/01/19 O-RVL: Pending Intake walk. END~ CR Routing 6/19/19: Summer ’19 Renovation Project Priority 3; For Faculty Hire NO. (Stephen C) END~ 04/22/19 O-RVL: Update - RV emailed Mayela on 04/18 on the same day her inquiry was received on " to confirm if equipment specifications and pertinent information have been reviewed to discuss the project." RV responded "we have not received the equipment specs and will no longer be engaged with projects before they have been reviewed and prioritized by the Dean's office for the upcoming quarter". RV cc'd Deans off, Monty, Dan L., C. Pillen, PI and R. Rector. END~ 03/20/19 O-RVL: Emailed Marcelina (in Mayela's absence) requesting equipment specs. Pending response. END~ 03/19/19 O-RVL: Received email from Mayela, Work request was submitted. END~ 03/18/19 O-RVL: RV received an email from Dan to Mayela on 03/13. RV contacted spoke with Dan requesting info. RV contacted Mayela and asked her to submit a work request for the additional work. | NO |  | FS | FALSE | 2019 | 2019-08-16
19P000540 |  | 19P000540 | FALSE | CHASS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | Remove metal roll up window, replace carpet, remove round column cover-reframe square. | HUM & SOC SC | 1202 | PLAN DEVELOPMENT/CHECK | Milagros Pena | Cindy Williams | JENNIFER MORGAN |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2019-03-20 | [6 empty] | 8/15/19, DL; Gunter has the project on his list. We will try and be ready for plan check review in the next two weeks…….. | 2019-07-25 | Enrico Baez | Ref: CP3514; Notes on project request in FAMIS and Shared drive. | YES |  | FS | FALSE | 2019 | 2019-08-16
19P000543 |  | 19P000543 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION | TV Bracket &Power/Network box. | CHEMICAL SCI | 342 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | JEFFERY MATUTE |  | DAN LERMAN |  | R8 |  | FALSE |  |  | 2019-03-21 | [8 empty] | Ron Veloz | 08/02/19 O-RVL: Estimate required, RV to schedule walk with vendors for quotes. 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to RVL. | NO |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | Project Intake | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | DAN LERMAN |  | R3 |  | TRUE |  |  | 2019-03-26 | [8 empty] | Ron Veloz | 08/07/19 O-RVL: RV met with Dan L on 08/07 to compose a final estimate & is in progress (pending vent hood & vac pump pricing). END ~ 08/02/19 O-RVL: SOW is complete, sent Dan L Intake on 08/02 & rev Intake on 08/05. Estimate in progress. End~ 07/08/19 O-RVL: Met with Customer and Dan L on 07/02/19. Customer requested the to keep the shelving and gases on the West table. Requested vacuum pump and lies. Plumbing supervisor investigated and confirmed the building does not have vacuum infrastructure. RV to revise the SOW and send to PM Dan L for review. Dan L will determine the type of "off the shelf" hood to install. Revised SOW is in progress. END~ 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to RVL. | YES |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000552 |  | 19P000552 | FALSE | CHASS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS |  | HUM & SOC SC | 1001 B, C, and D | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-03-27 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20
19P000553 |  | 19P000553 | FALSE | VC-RED | SL5 SPIETH HALL PATCH AND PAINT |  | SPIETH | 341 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-01 | [6 empty] | 07/26/19 O-ANS: Project Complete per Paul Ditty. |  |  |  |  | 2019-07-26 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20
19P000555 |  | 19P000555 | FALSE | CNAS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK | INSTALL OF FENCE FOR RAIN COLLECTOR AT TES TANK | SAT CHIL PL | 0 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | DAN LERMAN |  | R4 |  | FALSE |  |  | 2019-04-03 | [6 empty] | 8/15/19, DL; Plans are approved. We ware waiting for a estimate from our contractor. Once we have the quote, we will forward the quoted to Deborah for review and approval. Note, this is a recharge project…….8/1/19, DL; Plans are complete pending approval from building official…. |  | Ron Veloz | 08/08/19 O-RVL: Not aware of plans progress. RV will talk with Dan if additional I fo & support is needed. |  |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000558 |  | 19P000558 | FALSE | BCOE | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT |  | BOURNS | A0265 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-04-03 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20
19P000560 |  | 19P000560 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION |  | UV BLDG B | 0240B | IN PROGRESS | Susan Marshburn | Da Lan Dinh | LESLIE ROSE |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-04-04 | [6 empty] | 8/15/19, DL; This Project is 90% Complete and will be complete by the end of the week. Please note. ITS still needs to connect the data lines. Our portion of the work is complete………8/1/19, DL; Plans are approved. Material is ordered. We will schedule the work when the material is on site…. |  | Dan Lerman | 4/4/19-JENNIFER- PER ENRICO BAEZ, THIS IS THE WORK ORDER TO GET STARTED ON THE JOB. PLEASE REFER TO WORK ORDER #19W013241 |  |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000564 |  | 19P000564 | FALSE | VC-UNIV.ADV. | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | 1156C (AVC Johnny Cruz) – Patch molly holes, touch-up paint. 1156A (Jules Bernstein) – Remove (2) black & white photos from wall. Patch molly holes, touch-up paint. 1156B – Install picture frame (UCR campus map) onto wall. Suite 1159 – Patch holes. Remove film reels. Paint one accent wall “UCR Blue”. 1159B (Christy Zwicke) - Patch molly holes, touch-up paint. | HINDERAKER | 1156 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | Lisa Cusick | Christy Zwicke | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-08 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000565 |  | 19P000565 | FALSE | BCOE | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS |  | BOURNS | A0133 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | NANCY FORD |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-04-08 | [6 empty] | 07/30/19 O-ANS: Per Paul Ditty, Customer Maggie Souder canceled project. |  |  |  |  | 2019-07-30 | FS | FALSE | 2019 | 2019-08-16
19P000571 |  | 19P000571 | FALSE | CNAS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 |  | SCIENCE LAB1 | 215 & 322 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2019-04-10 | [6 empty] | 07/30/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-07-30 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20
19P000572 |  | 19P000572 | FALSE | GRADUATE DIVISION | SL5 PATCH, PAINT, AND CARPET UOB 152 |  | UNIV OFC BLD | 152 | IN PROGRESS |  |  | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-11 | [6 empty] | 06/28/19 O-ANS: Paint phase complete and awaiting carpet change. | [5 empty] | FS | FALSE | 2019 | 2019-08-16
19P000573 |  | 19P000573 | FALSE | PLANNING & BUDGET | SL5 UNIVERSITY VILLAGE PAINT /REMOVE NAILS |  | UV BLDG B | 0208L | CANCELED BY CLIENT | Gerry Bomotti | Sharyl Murdock | JUDITH ABBEY |  | Paul Ditty |  | R2 |  | FALSE |  |  | 2019-04-11 | [6 empty] | 06/14/19 O-ANS: Canceled by Customer via email from Georgianne Carlson "Project 19P000573, UV Room 208L. Human Resources Department has withdrawn the request for this patch and paint project. Not a priority, at this time." |  |  | Canceled by client 6/14/19 |  | 2019-06-14 | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000574 |  | 19P000574 | FALSE | CHASS | SL5 FACULTY OFFICE PAINTING |  | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | QUEUE TO START | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-04-12 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000575 |  | 19P000575 | FALSE | CHASS | SL5 WATKINS HALL PAINT/FLOORING |  | WATKINS | 1309A | QUEUE TO START | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-17 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000585 |  | 19P000585 | FALSE | CHASS | SL5 HUMANITIES SS, RM 3604- PATCH/PAINT WEST WALL |  | HUM & SOC SC | 3604 | COMPLETE | Milagros Pena | Cindy Williams | DARA CERDA |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-04-19 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000588 |  | 19P000588 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - PATCH & PAINT OFFICES |  | BOURNS | A127 Office, A129 Office, A131 Office, A133 Office, A135 Office, A137 Office, A139 Office, and A141 Office | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-04-22 | [6 empty] | 06/28/19 O-ANS: Paint phase complete. |  |  |  |  | 2019-06-28 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000589 |  | 19P000589 | FALSE | CHASS | SL5 HMSS OFFICE 3405 RENOVATIONS | Construct partion, pending CBO approval, in room 3405. | HUM & SOC SC | 3405 | IN PROGRESS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2019-04-23 | [6 empty] | 8/15/19, DL; Plans are approved but the PI is not. We will probably start the project the 2nd week in September…… | 2019-06-27 | Enrico Baez |  | YES |  | FS | FALSE | 2019 | 2019-08-16
19P000594 |  | 19P000594 | FALSE | CNAS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS | Take down a dividing wall in this office and move the desks to their old location and rehang the overhead desk bins back into their old locations with inserts still in the walls. | ENTOMOLOGY | 171 | Project Intake | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | DAN LERMAN |  | R9 |  | FALSE |  |  | 2019-04-26 | [8 empty] | Ron Veloz | 08/08/19 O-RVL: Estimate required, RV to schedule walk with vendors for quotes. 08/02/19 O-RVL: Acknowledged request and will schedule site visit. 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to RVL. | NO |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000597 |  | 19P000597 | FALSE | BCOE | SL5 PATCH AND PAINT WALLS |  | CHUNG HALL | 355, 356, 351, & 353 | COMPLETE | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-05-03 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-16
19P000599 |  | 19P000599 | FALSE | PLANNING & BUDGET | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | Sharyl Murdock | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 2019-05-09 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20 | 1
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | PLAN DEVELOPMENT/CHECK | Christopher Lynch | Maggie Souder | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-09 | [6 empty] | 8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Ron Veloz | 08/08/19 O-RVL updating notes. 07/02/19 O-RVL: Jobwalk with PI and Dan l. END~ 07/01/19 O-RVL: Pending intake/walk. | YES |  | FS | FALSE | 2019 | 2019-08-16
19P000601 |  | 19P000601 | FALSE | BCOE | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY | Renopvate lab space, Patch/paint, Re-finish, re-surface – existing cabinets/casework. Re-finish, bench-tops. Clean existing Chemical fume hood. Repair or replace self-closing chemical/flammables storage cabinet. Repair or replace bench shelves as needed. Clean and wax floors. | BOURNS | B0328E | QUEUE TO START | Christopher Lynch | Maggie Souder | KATHALENA COCKER |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-05-09 | [6 empty] | Scope is copmplete, waiting on estimates from vendors. We will need to work up a contract which will add time to the project timeline… | 2019-08-06 | Ron Veloz | 08/08/19 O-RVL: Received final revisions from Maggie via email today. Dan L was copied on email. END~ 08/07/19 O-RVL: Pending final review fof SOW from PI/Maggie. END~ 07/24/19 O-RVL: RV scheduled site visit for Dan, Maggie and Luat to confirm the SOW. RV was unable to attend. 07/19/19 O-RVL: RV scheduled a site visit with Dan L, Luat to verify SOW. 07/10/19 O-RVL: RV Met 1-1 with PI Luat Vuong, meet and discuss process and SOW . 07/07/01/19 O-RVL: Pending intake / site visit | YES |  | FS | FALSE | 2019 | 2019-08-16
19P000603 |  | 19P000603 | FALSE | CHASS | SL5 CHASS INT N, RM 3046- PATCH AND PAINT - NEW FACULTY OFFICE |  | CHASS INT N | 3046 | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  | 12 |  | TRUE |  |  | 2019-05-10 | [6 empty] | 06/18/19 O-ANS: Project complete per updates. 06/15/19 D-MMN: Painted remaining finish. Pulled masking and plastic. Replaced plates and vacuumed. |  |  |  |  | 2019-06-18 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000604 |  | 19P000604 | FALSE | CHASS | SL5 HUMANITIES SS, RM 7704- PAINT OFFICE BY JULY 1, 2019 |  | HUM & SOC SC | 7704 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000605 |  | 19P000605 | FALSE | CHASS | SL5 PAINT NEW MAILROOM |  | WATKINS | 1320E | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-16
19P000606 |  | 19P000606 | FALSE | CHASS | SL5 PAINT ROOM |  | WATKINS | 1213 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 06/14/19 O-ANS: Stephen spoke with customer Becky Campbell via phone who confirmed that project was going to be canceled due to re-allocation of space by another dept. |  |  | Canceled by client 6/14/19 |  | 2019-06-14 | FS | FALSE | 2019 | 2019-08-16
19P000607 |  | 19P000607 | FALSE | CHASS | SL5 PAINT FACULTY OFFICE |  | WATKINS | 1312 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2019-05-10 | [6 empty] | 08/13/19 O-ANS: Customer scope of work includes more than just PAINT so project added to Fall 2019 list for prioritization by organization. 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-16
19P000608 |  | 19P000608 | FALSE | CHASS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE |  | WATKINS | 1345 | QUEUE TO START | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-05-10 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000609 |  | 19P000609 | FALSE | CHASS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR |  | WATKINS | 1229 | IN PROGRESS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 07/03/19 O-ANS: Paint phase complete and awaiting flooring change. 06/21/19 O-ANS: Customer requested to remove lighting change from project and only complete paint and carpeting via email to Paul Ditty (copied email below). Will create separate work order for lighting. Re-assigned to Paul Ditty to complete. "From: Becky L Campbell <becky.campbell@ucr.edu> Sent: Friday, June 21, 2019 10:51 AM In regards of the work order: 19P000609 - SL5 - PAINT FACULTY OFFICE – please cancel the connecting Work Order 19W015231 – REPLACING THE LIGHTING IN WATKINS 1229. Please do paint and replace flooring.For the lighting, please create new work order to be done at a later time." |  | Paul Ditty | Awaiting installation of new flooring |  |  | FS | FALSE | 2019 | 2019-08-16
19P000613 |  | 19P000613 | FALSE | CNAS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT |  | COLL BLDG NO | 0203B | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000614 |  | 19P000614 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 202- PAINT |  | COLL BLDG NO | 0202 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-16
19P000615 |  | 19P000615 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT |  | COLL BLDG NO | 203 AND 204 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000616 |  | 19P000616 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 208- PAINT |  | COLL BLDG NO | 208 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-16
19P000617 |  | 19P000617 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 212- PAINT |  | COLL BLDG NO | 212 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-16
19P000618 |  | 19P000618 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 205 AND 205A- PAINT |  | COLL BLDG NO | 205 AND 205A | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 06/11/19 O-ANS: Per Paul, conference room was in decent condition and does not need to be repainted. He will speak with customer to explain. |  |  |  |  | 2019-06-11 | FS | FALSE | 2019 | 2019-08-16
19P000619 |  | 19P000619 | FALSE | BCOE | SL5 BOURNS, RM A0311- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0311 | IN PROGRESS | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-05-14 | [6 empty] | 06/28/19 O-ANS: Paint phase complete and awaitin flooring install. | [5 empty] | FS | FALSE | 2019 | 2019-08-16
19P000620 |  | 19P000620 | FALSE | BCOE | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0304 | QUEUE TO START | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 9 |  | TRUE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000621 |  | 19P000621 | FALSE | BCOE | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0308 | QUEUE TO START | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000622 |  | 19P000622 | FALSE | CNAS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK | Replace doors & frame | FAWCETT LAB | 204 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-15 | [6 empty] | 8/15/19, DL; PO# will be provided this week to order the doors and frame, lead time is 4- weeks for the doors/ frame. We will scheudule the install once the door / frame is on site……..8/1/19, DL ; Pending estimate from vendor. Once we have everything needed, we will schedule the work…. | 2019-07-15 | Ron Veloz | 07/18/19 O-RVL: RV complete Intake and placed on the project folder on the FS Server on 07/17. END~07/15/19 O-RVL: Received email on 07/15 regarding door project. Spoke with Dan L and forwarded the floor plan to him. Explained the SOW is to replace the door frame and door and hardware as recommended by Jason Williams to provide the proper door functions for the department. Dan requested a site plan and will outsource to a door vendor and not further scoping is required for this project. END~ 07/12/19 O-RVL: Walked site. END~ 07/01/19 O-RVL: Pending intake/site visit to confirm SOW. END~ CR Routing 6/19/19: Summer ’19 Renovation Project Priority 2; For Faculty Hire NO. (Stephen C) | YES |  | FS | FALSE | 2019 | 2019-08-16
19P000625 |  | 19P000625 | FALSE | BCOE | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM |  | BOURNS | A0108 | QUEUE TO START | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-15 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000627 |  | 19P000627 | FALSE | GSOE | SL5 SPROUL HALL, RM 2120 - PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2120 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-05-15 | [6 empty] | 08/13/19 O-ANS: Customer requested that project be moved to Fall 2019 list for prioritization. | [5 empty] | FS | FALSE | 2019 | 2019-08-16
19P000628 |  | 19P000628 | FALSE | GSOE | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2129 | QUEUE TO START | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-05-15 | [12 empty] | FS | FALSE | 2019 | 2019-08-16
19P000638 |  | 19P000638 | FALSE | BCOE | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM | renovate lab | BOURNS | B207 | IN PROGRESS | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-16 | [6 empty] | 8/15/19, DL; Plans were approved this week. We will order the material and schedule the work……..Plans are 90% complete and we will probably submit plans for plan check review this Monday | 2019-07-19 | Ron Veloz | 07/10/19 O-RVL: Visited Luat V with Dan L on site on 07/10 at 10:00am-11:30 to review SOW. Additional changes were made. Luat will prepare a revised layout and send to Ron V & Dan L. Thereafter, RV will incorporate all SOW and note on the intake form and send to Luat & Dan to verify the SOW and floor plan. ~END~ 07/24/19 O-RVL: Met with Dan, Luat and Gilbert(PD&C) for final SOW review and code requirements. 07-01-19 O-RVL: RV visited with Luat Voung on 06-25 to review scope. PI was uncertain of renovation and requested additional time to revise SOW. PI will contat RV when ready with new list. 07/01/19 O-RVL: Pending intake/site visit to confirm SOW. | YES |  | FS | FALSE | 2019 | 2019-08-16
19P000639 |  | 19P000639 | FALSE | CNAS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK | Make modifications to accommodate new PI | CHEMICAL SCI | 0435 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-17 | [7 empty] | 2019-07-19 | Ron Veloz | 07/19/19 O-RVL: Updated notes from work request screen. "07/17/19 O-RVL: Met with Tim, Dan L, Nick and Tran(EH&S) will revise intake and scope for new location. Pending approvals from EH&S for the newly proposed location for Biosafety cabinet in room 441. Receieved request from Tim Su on 07/19 "bench and cabinet removal, would it be possible to have them delivered to Chemical Sciences Room 108 after they are taken out?" Pending final revisions from Tim Su. " END~ 07/01/19 O-RVL: Pending intake/site visit to confirm SOW. END~ CR Routing 6/19/19: Summer ’19 Renovation Project Priority 1; For Faculty Hire YES. (Stephen C) | YES |  | FS | FALSE | 2019 | 2019-08-16
19P000640 |  | 19P000640 | FALSE | CHASS | SL5 NEW FACULTY - PATCH & PAINT SPROUL 3108 |  | SPROUL | 3108 | COMPLETE | Milagros Pena | Cindy Williams | MELISA VICARIO |  | Paul Ditty |  | 13 |  | TRUE |  |  | 2019-05-20 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | FS | FALSE | 2019 | 2019-08-16 | FY 18-19
19P000642 |  | 19P000642 | FALSE | CHASS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM |  | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-05-21 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20
19P000643 |  | 19P000643 | FALSE | CHASS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH |  | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2019-05-21 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-08-16 | FY 19-20
19P000645 |  | 19P000645 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT |  | BOTANIC GARDENS |  | PROJECT INTAKE | Susan Marshburn | Da Lan Dinh | RONALD ANDERSON |  | DAN LERMAN |  | R2 |  | FALSE |  |  | 2019-05-22 | [8 empty] | Ron Veloz |  |  |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19P000646 |  | 19P000646 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING |  | ATH DANCE | 20R, 20S | IN PROGRESS | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-23 | [6 empty] | 8/15/19, DL; This project is in progress and slated for complete by the end of september…..8/1/19, DL; Project is in progress with a complete date of 3-4 weeks. |  | Dan Lerman |  |  |  | FS | FALSE | 2019 | 2019-08-16
19P000647 |  | 19P000647 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- LOCKER ROOM REFRESH |  | ATH DANCE | Men's & Women's Locker Rooms | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-23 | [6 empty] | 6/19/19 O-ANS: Combined with project 19P000646 since work in the same area. Dan Lerman to perform scope. |  | Dan Lerman |  |  | 2019-06-19 | FS | FALSE | 2019 | 2019-08-16
19P000665 |  | 19P000665 | FALSE | PLANNING & BUDGET | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | Existing telephone-communications building on University Ave requires repairs and renovation in preparation for new use as fire safety offices. | TELEPHONE |  | PLAN DEVELOPMENT/CHECK | Gerry Bomotti | Sharyl Murdock | Carmen Long | Melissa Garrety | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-03 | [6 empty] | 8/15/19, DL Plans were approved this week. Abatement is still needed and the 14- day notification to AQMD is complete. We are on track to complete the work by mid November……. |  | Enrico Baez |  |  |  | FS | FALSE | 2019 | 2019-08-16
19P000687 |  | 19P000687 | FALSE | BAS | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | PLAN DEVELOPMENT/CHECK | Gerry Bomotti | Georgianne Carlson | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-06-26 | [6 empty] | 8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | 7/1/19 E. Baez-Per Dan Lerman's request, received estiamte from Controlled Key, forwarded to Brendan O'Brien. |  |  | FS | FALSE | 2019 | 2019-08-16 |  | 1
19S000833 |  | 19S000833 | FALSE | SOM | Add access control to entry doors |  | HECKMAN ICEM | Entry Doors | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-07-17 | [8 empty] | Ron Veloz | Canceled request per conversation with client; customer to coordinate for a contractor to complete project. ~ Will Meet with Chris Pillen on 08/23/18 to review notes by C.P. on FAMIS. 08/23/18-RV: Followed up with Chris P for update on the work request notes. Recommended to contact Brandon to procure a local vendor. 08/24/18-RV spoke with Brandon Barbosa to determine a plan to complete the request and will pursue pricing and oversee the installation. 08/27/18 RV: Update: Brandon will PM the project on his own. 09/19/18: UPDATE-CANCELLED BY Brandon. See notes above. | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-08-16
19W002419 |  | 19W002419 | FALSE | ITS | SL5 ITS CENTER - INSTALL CARD READER ACCESS |  | ITS CENTER | 161 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-08-09 | [9 empty] | 1/8/19: O-ANS: Converted to a project 19000433 and canceled in FAMIS. |  | 2019-01-08 | FS | FALSE | 2018 | 2019-08-16
19W002930 |  | 19W002930 | FALSE | CHASS | HOLD - SL5 PATCH HOLES & PAINT - HUMANITIIES SOCSCI |  | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-08-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19W003012 |  | 19W003012 | FALSE | CNAS | SL5 FIX RESTROOMS (PAINT AND FLOORS) | FS to coordinate with client to schedule work for completion. | CHAPMAN | 5 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 51 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | N/A | N/A | 2018-12-13 | FS | FALSE | 2018 | 2019-08-16
19W003050 |  | 19W003050 | FALSE | VC-RED | SL5 SPEITH HALL - PATCH & PAINT HOLE IN WALL |  | SPIETH | 0359A | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-08-16 | FY 18-19
19W007474 |  | 19W007474 | FALSE | CNAS | SL5 BG - RAILROAD TIE WALLS | Repair Railroad Ties at Botanic Gardens | BOTANIC GARDENS |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV | [5 empty] | FALSE |  |  | 2018-11-07 | [7 empty] | 2018-12-10 | Ron Veloz | 03/11/19 O-RVL: Update, RV emailed Deborah H and Team to cancel this request. Message: "Facilities Services has reviewed the “Request for Estimate” under project number 19P000348. We (FS) have reviewed the request and have determined the costs exceed that allowed to Facilities Services within the UC guidelines and would also require structural engineering services which is beyond the services we are able to provide. ACCESS (WO) and FAMIS notes are updated and the customer was emailed with the Cancellation of the request. Updates completed by Ron V on 03/11/19. Please cancel Project - 19P000348 and Work Request #: 19W007474. END--- 03/11/19 O-RVL: Received information from Dan L and authorization from Team to CANCEL this work request for estimate. Cost would exceed 50k and will require engineering. RV emailed the team to cancel the request by "FS". END--- 03/01/19 O-RVL: RV will walk with Chad C to determine if FS is cabable of repair/reinstall railroad ties true & plumb. Walked site with Chad C. on 03/01 afternoon. Chad will meet with C.P. to determine capabilitiy and staff to perform work. RV will follow up. END--- 02/15/19 O-RVL: Udated SOW, RV will schedule a site visit with the Carpentry Supervisor to detemine the construction feasability and estimated costs. END --- 01/09/19 O-RVL: REQUEST FOR ESTIMATE, Not a Project. RV To schedule a site visit with C. Pillen and Chad Chambers to evaluate if repairs are possible. END--- 12/10/18 O-RVL: REQUEST FOR ESTIMATE. Ron V walked with D. McWilliams & Jodie and identified the railroad tie retaining wall area requiring repairs. Jodie would like an estimate to repair the leaning railroad ties at specified areas. RV to meet with Chris P. and or Chad Chambers to determine if FS can perform work and or provide an estimated cost to perform work. END--- 11/07/18 O-RVL: Received an email form Deborah Mc. to discuss the wall at Thursday during our 1-1 meeting. | YES | 2019-03-11 | FS | FALSE | 2018 | 2019-08-16
2970a | 2970a |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan-Phase 1 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 20 |  |  | FALSE | 2842000 |  | 2015-12-02 | Award package 1 & 3 | 2018-09-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
2970c | 2970c |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan-Phase 3 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 20 |  |  | FALSE | 2842000 |  | 2015-12-02 | Award package 1 & 3 | 2018-09-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
2970d | 2970d |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan-Phase 4 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 20 |  |  | FALSE | 2842000 |  | 2015-12-02 | Award package 1 & 3 | 2019-09-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-08-16
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY15) Roofing - Spieth Hall/LSP | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. |  |  | In design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 10 |  |  | FALSE | 432510 |  | 2016-02-25 | Bidding | 2019-12-01 | 2020-01-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-08-16
19P000414 |  | 19P000414 | FALSE | PLANNING & BUDGET | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | QUEUE TO START | Gerry Bomotti | Sharyl Murdock | KELLY DUNCAN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-12-17 | [8 empty] | Enrico Baez | 7/8/2019 E.Baez-Spoke with Dan. Work has alread been scoped and will be scheduled by Dan. 7/1/2019 E. Baez-Voice mail to Dan to determine project needs to be scoped. |  |  | FS | FALSE | 2018 | 2019-08-16
18P000346 |  | 18P000346 | FALSE | ATHLETICS | SL5 ATHLETICS INSTALL WALL VOLLEYBALL OFFICES |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-18 | [6 empty] | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. DL, 5/24/18; We will start working on plans in the near future.... DL, 6/16/18; Need to submit plans asap.......DL, 7/11/18; The plans were approved today. This project is scheduled to start on 7/14/18. We will will be complete will all items related to this project on 8/27/18. Note, The door and sidelite are special order items and this item will probalby have a 6-8 week lead time. Steve T is going to order the door soon.. Customer is aware of the delay for the door and is not concerned......DL, 7/25/18; Passed framing and Electrical inspection. We will be finished with the project next week except for the door and window that is ordered but has a 6-8 week lead time. DL, 8/10/18; This Project is Complete except for special order door and window.......DL, 8/22/18; Door and Glass still not on site., Will check in with Steve T on delivery date......Will also schedule final inspection for Certificate of occupancy......9/6/18; The Glass window is installed but we are waiting on the door. this projects is 98% complete.......DL, 9/19/18; The door will be shipped on 9/24/18. We will schedule the door install when the door is on site......DL, 11/7/18; This Project is 100% Complete.... |  | Dan Lerman | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. Will start working on plans.... | YES | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000484 |  | 18P000484 | FALSE | ATHLETICS | SL5 INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | Project will be managed by A&E for completion. | SOFTBALL STG |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-26 | [6 empty] | 2/1/19, DL; This is a PD&C Project due to IRT walk. Project will exceed $50,000……….. |  | Enrico Baez | 12/6/18 EB Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | NO | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01
18P000328 |  | 18P000328 | FALSE | ATHLETICS | SL5 HINDERAKER BASEMENT OFFICE REPAIR |  | HINDERAKER |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-01 | [6 empty] | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with Paul. Paul will complete as in the near future. Carpet will be installed shortly after......5/21/18, Painters started paint. Should be complete with paint by the end of the week....DL, 5/24/18; Painters are complete. Jess will schedule the carpet install.....DL, 6/12/18; Project is 98% Complete. Carpenters need to under cut two doors to accomodate the carpet.....DL, 7/11/18; This Project 100% Complete..... |  | Dan Lerman | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with PAul. Paul will complete as in the near future. Carpet will be installed shortly after...... | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000027 |  | 19P000027 | FALSE | ATHLETICS | SL5 ATHLETICS PATCH & PAINT ROOM | 9/19/18 | ATH DANCE | 0120C | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | DL, 9/19/18; This Project is 100% Complete……. |  | Paul Ditty | N/A | N/A | 2018-09-19 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000265 |  | 19P000265 | FALSE | ATHLETICS | SL5 ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000646 |  | 19P000646 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING |  | ATH DANCE | 20R, 20S | IN PROGRESS | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-23 | [6 empty] | 9/3/19, DL; Project is 80% Complete. Floor covering is scheduled for this Friday. Target complete date is 9/13/19……8/15/19, DL; This project is in progress and slated for complete by the end of september…..8/1/19, DL; Project is in progress with a complete date of 3-4 weeks. |  | Dan Lerman |  |  |  | FS | FALSE | 2019 | 2019-09-01
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  | 10 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 4/18/19, DL; Per Enrico, we are waiting for a proposal from HCI and approved funding from Athletics. We should have the proposal in 2- weeks…. | 2018-09-27 | Enrico Baez | 1/14/19 E Baez. Per "Monty" Athletics are to pay for this project. Joe Erbland emailed to determine if funding has been approved. Waiting on response. ---11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. --- 10/3/2018 EB Install keyless entry system for building exterior. ---9/24/18 EB Site visit scheduled with John Jensen for 9/27 | YES |  | FS | FALSE | 2018 | 2019-09-01
19P000271 |  | 19P000271 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 |  | ATH DANCE | 3 | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000295 |  | 19P000295 | FALSE | ATHLETICS | SL5 PATCH & PAINT |  | ATH DANCE | 50B | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 12 | 18 - 19 | FALSE |  |  | 2018-09-12 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000272 |  | 19P000272 | FALSE | ATHLETICS | SL5 NEED URINAL DIVIDERS | FS to coordinate with customer to scope the work. | ATH DANCE | 50E | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 13 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 3/7/19 O-ANS: Project no longer moving forward per Ron Rector and placed on DM list. 1/15/19 E Baez. Per "Monty" project cancelled to be placed on Deferred Maint. List. Emailed Chris P. to provide renovation cost and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Install dividers for urinals. Wall is tile. |  | 2019-01-24 | FS | FALSE | 2018 | 2019-09-01
19P000270 |  | 19P000270 | FALSE | ATHLETICS | SL5 ATH DANCE-WEIGHT ROOM DROP DOWN CEILING |  | ATH DANCE | 78 | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 14 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project is 100% Complete….. |  | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB remove all t-bar ceiling components. Will need relocation of supply and return registers, lighting Alarms, Etc. |  | 2019-02-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000274 |  | 19P000274 | FALSE | ATHLETICS | SL5 RIV SPORTS CPX - REPLACE URINALS | FS to coordinate with customer to scope the work. | RIV SPORTS CPX |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 15 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-10-15 | Enrico Baez | 1/14/19 E Baez. Per "Monty" this project to go on deferred maint. list. emailed Chris Pillen to provide coast and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27. 10/3/18 EB not time to visit on 9/27. will schedule follow up meeting. 10/15/18 EB conducted site visit, 11 urinals to be replaced. | YES | 2019-01-24 | FS | FALSE | 2018 | 2019-09-01
19P000276 |  | 19P000276 | FALSE | ATHLETICS | SL5 TRACK BLEACH-PUBLIC RESTROOMS UPGRADE |  | TRACK BLEACH |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 16 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 11/20/18 EB Project cancelled, will be addressed by PD&C. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB conducted site visit, Client wants additional toilet in mens room, changing table and lighting improvements. ADA Issues. Also spoke with Scott Donnell he has project . | YES | 2018-11-20 | FS | FALSE | 2018 | 2019-09-01
19P000266 |  | 19P000266 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | n/a | N/A | 2018-12-13 | FS | FALSE | 2018 | 2019-09-01
19P000647 |  | 19P000647 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- LOCKER ROOM REFRESH |  | ATH DANCE | Men's & Women's Locker Rooms | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-23 | [6 empty] | 6/19/19 O-ANS: Combined with project 19P000646 since work in the same area. Dan Lerman to perform scope. |  | Dan Lerman |  |  | 2019-06-19 | FS | FALSE | 2019 | 2019-09-01
19P000252 |  | 19P000252 | FALSE | ATHLETICS | SL5 ATH DANCE SHOWER DOORS |  | ATH DANCE | 0050K | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-10 | [6 empty] | 5/31/19, DL; This project is 100% Complete……..5/15/19, DL; This work will be 100% complete this Friday…….4/15/19, DL; This project should stat is 2-weeks. We have a signed po# for the shower doors. Walked the needed tile repairs with the contractor today……..3/18/19, DL; Woring on quotes for the repairs. We will scheudle the work to be completed in the next 45- days…… |  | Enrico Baez | 10/3/2018 EB Replace aluminum and glass shower doors. Will need to contract work. Replace all rusty fixtures in showering space, repair/replace tile as needed. ---9/24/18 EB Site visit scheduled with John Jensen for 9/27 | YES | 2019-05-31 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000268 |  | 19P000268 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT 20C |  | ATH DANCE | 20C | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000269 |  | 19P000269 | FALSE | ATHLETICS | SL5 ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | Project is not within the purview for completion; condition is fair and usable. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 5 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18…..This is a cooman area. Is this recharge work……. | 2018-09-27 | Enrico Baez | 2/5/19 E. Baez. Common spaces are managed by Facilities Services. Any work done in corridors, stairwells and open spaces will be assessed by FS. 11/20/18 E. Baez-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB-Request for installing vinyl flooring. Remove and replace existing Terrazo and ceramic floor tile in 1st floor lobby and stairs to basement. | YES | 2018-10-04 | FS | FALSE | 2018 | 2019-09-01
19P000275 |  | 19P000275 | FALSE | ATHLETICS | SL5 SOFTBALL STG PRESS BOX AC ADDITION | FS to coordinate with customer to scope the work. | SOFTBALL STG |  | CANCELED BY CLIENT | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 6 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project was canceled by Johnathan J. as there is not funding at this time…………DL, 10/4/18; I checked on this recently and this is not a building, it is stoarge and should be recharge work…. | 2018-09-27 | Enrico Baez | 2/5/2019 E Baez Client wants a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. Client will need to fund this project as this is not a core building 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Client want a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. |  | 2019-02-14 | FS | FALSE | 2018 | 2019-09-01
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | IN PROGRESS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 3/28/19, Doors are in the process of being …. DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez | 10/3/2018 EB approx. 16-20 doors need repair. Sand, patch, repair as needed. Re-varnish. ---9/24/18 EB Site visit scheduled with John Jensen for 9/27 | YES |  | FS | FALSE | 2018 | 2019-09-01
19P000273 |  | 19P000273 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000311 |  | 19P000311 | FALSE | ATHLETICS | SL5 ATHLETICS 150-KEYLESS ENTRY | Keyless entry system | ATH DANCE | 0150 | Project Intake | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | DAN LERMAN |  | R2 |  | FALSE |  |  | 2018-10-02 | [7 empty] | 2018-09-27 | Enrico Baez | 1/31/19 EB emailed Joe Erbland inquiring if funding for project has been secured or to cancel request. 11/20/18 EB intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. From work order-looking to have two doors turned into key less entry for security of the practice center. 1/31/19 EB emailed Joe Erbland inquiring if funding for project has been secured or to cancel request. 3/28/19 E. Baez- Consulted with lock shop, approximate cost would be $10,000 4/2/2019 E. Baez- Conducted site walk with HCI Systems Chris and John for proposal. 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to EBZ. 7/26/19 E. Follow up email to Chris Rogers from HCI. | YES |  | FS | FALSE | 2018 | 2019-09-01 |  | 1
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | In Programming | Tamica Smith Jones | Joseph Erbland | Johnathan Jensen |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2018-08-23 | Create SOW | 2020-03-02 | 2020-06-26 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. |  |  | In coordination with Mobility Hub | Tamica Smith Jones | Joseph Erbland | Joe Erbland |  | Gerald Caraig | 3 |  |  | FALSE | 0 |  | 2014-04-10 | To be coord. with Rec Mall work | [11 empty] | PD&C | FALSE | 2014 | 2019-09-01
3408 | 3408 |  | FALSE | ATHLETICS | Harrison Field Netting | Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | SOFTBALL STG |  | Per department: Project is on hold until further notice. | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2018-01-23 | OnHold by Cust Til Furthr Notice | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
18W009630 |  | 18W009630 | FALSE | BAS | SL5 BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. | PHYS PL STOR | 100 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | JUDY HODGE |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-22 | [6 empty] | 3/28/19, DL; This project is cancelled per Judy Hodge….DL, 6/16/18; Project includes demo wall/door install new wall, dry wall, paint, door, eletrical outlets, lighting, smoke relocation, lighting motion, new t-bar, relocate heat pump, andn install new carpet…...DL, 7/11/18; Need to work on plans….. Target complete date is late Fall..... |  | Enrico Baez | See work order 18W012349 scoped and annotated in FAMMIS. 6/11/18 EB- Add wall to current space and eliminate exisiting wall. Relocate exisiting A/C on wall. Minor electrical DND 7/14 Hold per customer on prioritization; per Corp Yard Space Planning | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-09-01
18P000094 |  | 18P000094 | FALSE | BAS | SL5 OBAN LAUNDRY ROOM RENOVATION |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2017-09-08 | [6 empty] | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on bid. 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/12 EB- rec'd approval to contract with Design West to consult on electrical panel upgrade. |  | Enrico Baez | Scope of work has changed and project to be routed to Google IRT/CPMS for completion. 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold. MN 3/20: pending approval from customer on 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/11/18 EB-requested drawings from Gunter per Desgn Wests request. 7/11/18EB-waiting for Desgn West to complete site survey. 8/7/18 EB-Met with Robert Brumbaugh. Scope has changed with additional requirements. Improve HVAC, replace VCT, bathroom remodle. Advised to submit CPMS for A&E. | YES | 2019-01-19 | FS | FALSE | 2017 | 2019-09-01
18P000369 |  | 18P000369 | FALSE | BAS | SL5 BOYCE X-RAY IRRADIATOR PROJECT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 1407 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | KAREN JANIGA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-27 | [6 empty] | 12/14/18, DL; This project was cancelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……DL, 5/9/18; Need to work on plans/permits…..DL, 6/16/18; Meeting with Bob and confirmed what is needed. I will work with Gunther on plans. Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall…..DL, 11/7/18; Material is on site. We will schedule the work soon…… |  | Ron Veloz | DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……Need to work on plans….10/17/18 RV: This project was previously scoped and in Plan development. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-09-01
18P000282 |  | 18P000282 | FALSE | BAS | SL5 EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 |  | POLICE BLDG |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | LISA MARTIN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-25 | [6 empty] | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work…..DL, 5/9/18; We need to submit plans……DL, 7/11/18; This still needs to be scheduled......DL, 8/8/18; Enrico Confirmed this project is 100% Complete.... |  | Enrico Baez | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work….. | YES | 2018-08-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18W011772 |  | 18W011772 | FALSE | BAS | SL5 PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | Canceled per customer on priority list 7/3/18 | PRINT MOD |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Dan Lerman |  |  | Canceled | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/29/18; Pasted from WO; install an outside electrical outlet based on the attached amazon specs. also estimate for removing and sealing the outside vent from the copier. fyi_the copier will be moving within the next few months…..DL, 7/11/18; Need to verfy scope and schedule the work...... |  | Enrico Baez | fyi_the copier will be moving within the next few months | YES | 2018-07-03 | FS | FALSE | 2018 | 2019-09-01
18P000373 |  | 18P000373 | FALSE | BAS | SL5 POLICE BLDG PAINTING IN DISPATCH AREA |  | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  |  | 8 | FALSE |  |  | 2018-04-02 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000459 |  | 18P000459 | FALSE | BAS | SL5 BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 |  | THE BARN |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | Dan Lerman |  |  | 6 | FALSE |  |  | 2018-05-31 | [8 empty] | Enrico Baez | 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 6 | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000432 |  | 18P000432 | FALSE | BAS | SL5 BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 |  | BANNOCK H | H0101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-05-04 | [8 empty] | Paul Ditty |  | N/A | 2018-07-13 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000208 |  | 19P000208 | FALSE | BAS | SL5 PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | Canceled per customer on priority list 9/17/18 | THE PLAZA |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | CARLA CHAPPLE |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-14 | [8 empty] | Enrico Baez |  | NO | 2018-09-17 | FS | FALSE | 2018 | 2019-09-01
19P000247 |  | 19P000247 | FALSE | BAS | SL5 LOTHIAN FIRST FLOOR COMMON AREA FLOORING |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Jess Hernandez |  |  |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez |  |  | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000222 |  | 19P000222 | FALSE | BAS | SL5 PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000317 |  | 19P000317 | FALSE | BAS | SL5 HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 | conversation with Susan Marshburn and Bob Brumbaugh. | PENTLAND A |  | CANCELED BY FS | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER | [5 empty] | FALSE |  |  | 2018-10-03 | [9 empty] | D. Dinh : Project canceled; customer collaborating with John Peraino using a TMA work order per |  | 2019-01-14 | FS | FALSE | 2018 | 2019-09-01
18P000106 |  | 18P000106 | FALSE | BAS | SL5 HOUSING PROJECT - OBAN REC ROOM REMODEL |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 3 | FALSE |  |  | 2017-09-14 | [6 empty] | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. DL, 7/11/18; Per Susan this project is back on track. Project is scoped. Gunther will start working on the plans and permits. Once we have the approved permit. still need to check in with Susan on a few items.....Target complet date will be mid- fall...... |  | Enrico Baez | Scope of work has changed and project to be routed to Google IRT/CPMS for completion. EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. 8/22/18 Met with BoB Brumbaugh, Scope of work has changed with additional items. Fire alarm panel relocation, possible building HVAC upgrade. Ask he route project through CPMS and make laundry room and Rec. room one project. | YES | 2019-01-19 | FS | FALSE | 2017 | 2019-09-01
19P000192 |  | 19P000192 | FALSE | BAS | SL5 MAIL-PAINTING |  | MAIL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000236 |  | 19P000236 | FALSE | BAS | SL5 EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION |  | ABER INVER | A0100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 10 |  | FALSE |  |  | 2018-09-04 | [6 empty] | JP 04/04/19 2/8/19 This project is complete. JP Estimated completion end of February | 2018-11-01 | Enrico Baez | 11/27/18 EB-Entered scope of work. Transferred work order to John Peraino in FAMIS. Estmate to be provided prior to work start. Aberdeen Inverness Lobby across from RSO. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Pentland Hills 1st floor of I/J, K/L, M/N, O/P • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Pentland Hills Alcove between E&F building. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exterior wall adjacent to B-101 • Remove existing dual fountain. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exercise Room H-101 • Install HS where pluming repairs were made in East wall. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch all walls and Paint as needed. Glen Mor K-206 Fitness Room • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Glen Mor Pool area • Remove existing double water fountains and HS. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. • Repair any brick work as needed Lothian Hallway near Dining Hall cashier stand adjacent to fire extinguisher cabinet • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Sample sheet. https://www.restroomdirect.com/halsey-taylor-drinking-fountains-and-water-coolers.aspx 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Waiting for Lisa L. to schedule site visit. Total number of station and needs not completed. 11/1/18 EB Conducted site visit with Lisa and Bob. AI Replace Hydration Station (HS) in Lobby near RSO Pentland Hills Replace fountains with HS first floor I/J, K/L, M/N, O/P. Also remove fountains and install HS near B-101, Alcove between E&F, H-104. Glen Mor Remove fountain at pool & K-206 fitness room, replace with HS. Lothian Replace existing HS near cashier to Dining Hal | YES | 2019-04-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000235 |  | 19P000235 | FALSE | BAS | SL5 RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | Customer to determine scope of work. | ABER INVER | A0100 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 11 |  | FALSE |  |  | 2018-09-04 | [6 empty] | JP 04/04/19 Project cancelled per Housing/Lisa | 2018-11-01 | Enrico Baez | 11/26/18EB-Tranfered FAMIS work order to John Peraino's bench. Estimate to customer needed, prior to moving forward with project. 11/26/18 EB-SCOPE entered Aberdeen Inverness • Paint acoustic panels. Customer to provide color specification. • Remove carpet and replace with customer specified vinyl plank flooring. Replace base board • Cut door to accept 16” x 7” glass lite. Frame as needed. • Paint door • Replace surface mounted light fixture with LED surface mounted fixture. Customer to approve design. • Clean, paint or replace A/C vents. • Remove louvered vent in wall for abandoned water cooler. Install sheet metal cover, paint to match new wall color. Pentland Hills -Rooms 105 and 107 • Install full height acoustic panels on three walls. • 4th wall on East side of each room gets mirror. Height of mirror to be flush with top edge of door casing. Mirror width to be between inside corner of wall and switch plate cover. Provide cut out in mirror for thermostat installation. • Replace all ceiling tiles. • Replace 2’ x 2’ ceiling light with 2’ x 4’ LED fixture-customer to approve design. Pentland Hills -Rooms 105 and 107 • Remove carpet and replace with vinyl plank flooring, replace base board • Fire rated doors to be replaced with fire rated doors with small lite, approx. dimensions 16’ x 7”. • Paint as needed. Lothian • Install full height acoustic panels on three walls. • 4th wall gets mirror height to be even with door casing height. Customer to determine location. • Replace all ceiling tiles. • Replace ceiling lights with LED fixtures. • Remove all carpet in rooms and replace with vinyl plank and new base board-customer to specify style and color. • Replace door wire reinforced glass with clear, non-reinforced fire rated glass. • Paint as needed. Suggested Vendor for sound absorbing paneling. Riverside Acoustics Contact: Keith Atkins 951-682-6123 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 Met with Bob and Lisa, no firm plans or ideas in place. Lisa will schedule site walk once they have determined what they want. 11/1/18 Conducted site visit with Bob and Lisa. | YES | 2019-04-04 | FS | FALSE | 2018 | 2019-09-01
19P000015 |  | 19P000015 | FALSE | BAS | SL5 POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING |  | POLICE TRLR | 1 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-07-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000233 |  | 19P000233 | FALSE | BAS | SL5 PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | FS to coordinate with customer to scope the work. | MAIL | 884 | CANCELED BY FS | Gerry Bomotti | Georgianne Carlson | AMY EVERETT |  |  |  | 12 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Enrico Baez | Per Enrico, creating two individual WO's for Tile repair (19W004955) and door painting (19W004956). | YES | 2018-09-24 | FS | FALSE | 2018 | 2019-09-01
18P000363 |  | 18P000363 | FALSE | BAS | SL5 PAINT STOREHOUSE ADMINISTRATIVE OFFICE |  | CORP B |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | ERICA HENDERSON |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-03-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000227 |  | 19P000227 | FALSE | BAS | SL5 DINING STORAGE ROOM CONVERSION |  | BANNOCK J | J0100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | DARCI LOMBARD |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 05/16/19 O-ANS: Project complete per John P as of 05/16/19. 04/04/19, JP: This project has been placed on hold per Housing Edwin. 2/8/19: JP storage room slated to be completed simultaneously with break room as water supply connections will be done together with break room. Completion date for both is approximately three weeks. |  | Enrico Baez | 9/12/18 EB-Install Drywall, Patch & Paint, cap water line, install VCT & Cove Base, Verify HVAC operation, replace hydralic door closer, install LED lamps, Security light. Scope sent to Edwin Melgar for approval. | YES | 2019-05-16 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000224 |  | 19P000224 | FALSE | BAS | SL5 PAINT EXTERIOR RAMP AT HUB MODULAR |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | MIKE CLEMONS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000308 |  | 19P000308 | FALSE | BAS | SL5 ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK |  | ABER INVER |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | JP 04/04/19 Project Complete DL 10/4/18; Jess currently has this project scheduled for Winter break. |  | Enrico Baez | 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. |  | 2019-04-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000307 |  | 19P000307 | FALSE | BAS | SL5 LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 5 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… | 2018-10-03 | Enrico Baez | 1/8/19 EB Job Completed by Jess H. 12/22/18 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. | N/A | 2019-01-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000232 |  | 19P000232 | FALSE | BAS | SL5 BANNOCKBURN J-104 BREAK ROOM UPGRADE | Scheduled work with trades anticipated 60% completion by Jun 15th. | BANNOCK I | I0105 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | John Peraino |  | 6 |  | FALSE |  |  | 2018-09-04 | [6 empty] | 6/14/19, JP; Project on schedule to be completed June 30th 2019. 05/16/19 O-ANS: Project to be 60% completed by June 15th per John P. 04/04/19 JP: This project placed on hold per Housing/Edwin. Finishing up the cabinet and lighting order, will be submitting to purchasing today. Scheduling installation of VCT flooring pending per Tony’s Flooring, will have date this week. New ceiling tiles have been delivered and will be installed when relocating of electrical components are complete. Awaiting confirmation and clearance from Jess to proceed with cutting into walls to facilitate electrical modifications |  | Enrico Baez | 9/19/18 EB-conducted site visit. Entered Scop in FAMMIS and in BZM projects on shared drive. Requires pluming for sink and disposal, electrical, lighting upgrade. | YES |  | FS | FALSE | 2018 | 2019-09-01
18P000483 |  | 18P000483 | FALSE | BAS | SL5 INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | FS to coordinate with customer to scope the work. | P1 |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | AMANDA GREY |  | Enrico Baez |  | 7 |  | FALSE |  |  | 2018-06-26 | [6 empty] | Waiting for Amanda Grey to verify ownership of chain link fence. Once confirmed will contract with De Anza to install 36" wide gate. | 2018-08-29 | Enrico Baez | 12/3/18 EB-Cancelled request per email from Amanda Gray. Will resubmit request when funding is available. 10/1/18 EB-Contract De Anza Fence to have a gate installed at chain link fence leading to storm culvert in parking lot 1. | YES | 2018-12-03 | FS | FALSE | 2018 | 2019-09-01
19P000022 |  | 19P000022 | FALSE | BAS | SL5 HUB--PAINT TWO WALL AS SCOTTY'S HUB |  | HUB | 101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | DIANE THOMAS |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-07-12 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-09-17 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000215 |  | 19P000215 | FALSE | BAS | SL5 SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 |  | HUB | 346 | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | John Peraino |  | 9 |  | FALSE |  |  | 2018-08-24 | [6 empty] | 12/12/18 DND Project complete; electrical was installed and all kitchen equipment was hooked up as requested. |  | Enrico Baez | 9/13/18 EB emailed Gustavo Plascncia to schedule site visit. 9/18/18 EB. Conducted site visit. Connect water, drain and gas lines to kitchen equioment. Double oven need hardwired electrical. HUB staff will attach al shelving to walls. Day crew to move and deliver equipment. | YES | 2018-12-12 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000095 |  | 18P000095 | FALSE | BAS | SL5 THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS |  | THE PLAZA | A0013 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  | C | HOLD | FALSE |  |  | 2017-09-08 | [6 empty] | 4/11/EB-On Hold per Robert Brumbaugh. 6/8 EB-emailed R. Brumbaugh for status update. |  | Enrico Baez | Canceled per customer on priortization list. 4/11/EB-On Hold per Robert Brumbaugh. DND 7/14 Hold per customer on prioritization | YES | 2018-06-08 | FS | FALSE | 2017 | 2019-09-01
19P000687 |  | 19P000687 | FALSE | BAS | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | PLAN DEVELOPMENT/CHECK | Gerry Bomotti | Georgianne Carlson | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-06-26 | [6 empty] | 8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | 7/1/19 E. Baez-Per Dan Lerman's request, received estiamte from Controlled Key, forwarded to Brendan O'Brien. |  |  | FS | FALSE | 2019 | 2019-09-01 |  | 1
3430 | 3430 |  | FALSE | BAS | TAPS Cust Svc Lobby Upgrades | Upgrades to Customer Service Lobby – Need to complete Tenant Improvement project upgrade customer service counter in Parking Services Building. Want to replace current counter to allow for; modern computer equipment, dividers between customers’ transaction spaces, under counter space for filing cabinets and check writing space. Please coordinate with Auxiliaries’ primary PM John Franklin. | PARKING SERV |  | On hold | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Dave Bomba | 2 |  |  | FALSE | 0 |  | 2018-05-17 | Customer Approval & Funding | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3354 | 3354 |  | FALSE | BAS | Lot 4/Barn Area ADA Improvements | Lot 4/Barn Area ADA Improvements - The proposed project will relocate an existing crosswalk that is not ADA compliant and provide path of travel improvements and additional ADA parking capacity in Parking Lot 4. The existing crosswalk located at West Campus Drive and Parking Lot 4 (north) was identified in the Draft ADA Transition Plan to be out of compliance. A Pedestrian Safety Study by Fehr & Peers completed in June 2008 identified the relocation of this crosswalk to approximately 100 feet east to provide a more visible, safe, pedestrian crossing. To increase pedestrian safety further, the crosswalk will be designed as a speed table. Additionally, Transportation and Parking Services proposes to create additional ADA parking spaces in Parking Lot 4 that exceed the required number, with hardscape and path of travel improvements that will connect to the new crosswalk. The improved crosswalk will correct required path of travel deficiencies from a parking lot that provides access to numerous publicly accessible buildings, as well as allow the Barn Expansion project to obtain Division of State Architect (DSA) approval once construction is completed. The funds to complete the crosswalk replacement will be requested from Campus ADA funds. Parking Lot 4 improvements will come from will come from TAPS. Although this project supports the Barn Renovation, its conception and need is not tied to the Barn project. The crosswalk improvements and additional ADA parking is needed to meet our ADA parking requirements and serve the growing demand on campus. This project is desired regardless of the Barn Renovation project. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | John Franklin | 3 |  |  | FALSE | 50000 |  | 2017-08-15 | Bidding | 2019-09-01 | 2019-11-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3376 | 3376 |  | FALSE | BAS | West Lothian Roof Replacement Design | Provide Schematic Design, Design Development and professional cost estimate to replace the existing single-ply membrane roof system on the Lothian West residence hall wings plus Common Area applications. Existing roofing is past its useful life and starting to experience multiple leaks that are damaging living spaces below. Design effort should select the most appropriate roof material for this roof plan. The intent is to design this year (alongside the Lothian East design) and construct immediately following the Lothian East roof replacement. | LOTHIAN HALL |  | In Close-out | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 4 |  |  | FALSE | 0 |  | 2017-09-28 | Complete Close-out | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3383 | 3383 |  | FALSE | BAS | W Lothian Air Handler Replacemt | Existing air handler equipment in West Lothian is original to the building and past its service life. Provide HVAC professional services to develop options for Air Handler replacement that meet UC Carbon Neutral 2025 goal. Each option analysis should include pros and cons for energy consumption, reliability, serviceability and system installation cost projections. At least one option should explore potential conversion to individual package units as practical. | LOTHIAN HALL |  | In Close-out | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 5 |  |  | FALSE | 883000 |  | 2017-10-03 | Complete Close-out | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3453 | 3453 |  | FALSE | BAS | ECS N&S Playground Shade & Turf | Provide Schematic Design, Design Development and Professional Cost Estimate for the alteration of existing shade structures, provision for additional shade structures, refinish interior metal fencing, and the replacement of existing grass with synthetic turf at the Early Childhood Services north and south playground areas. Prepare drawings so that they can be bid and constructed as separate projects. |  |  | Dept approval/funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 7 |  |  | FALSE | 0 |  | 2018-07-03 | Dept approval/funding | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3459 | 3459 |  | FALSE | BAS | A-I Hardscape Landscape Design-Study | Provide Schematic Design and Design Development drawings for a selective renovation of all hardscape and landscape around the perimeter of the Aberdeen-Inverness housing complex. Scope to include (but not limited to) widening of South Walk and replace its asphalt with concrete pavers, upgrade hardscape and landscape at Horseshoe, replace selected lawn areas with hardscape, seating and solar umbrellas at east and west lawns of Building E, consider new bike storage along South Walk, consider modifying slopped lawn between Building A and Linden St., generally reduce lawn areas and replace with sustainable planting, prune or replace unkempt trees, replace selected light fixtures to match Dundee fixtures, and generally freshen the landscaping so that it is harmonious with the new Dundee development. Design to be packaged in phases, with the South Walk and Dundee-facing landscape to be ready in Phase 1 for construction timing alongside Dundee-Glasgow landscaping in Spring of 2020. | ABER INVER |  | Architect design meetings scheduled. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 8 |  |  | FALSE | 160000 |  | 2018-07-16 | Complete Design | 2020-05-01 | 2020-09-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3462 | 3462 |  | FALSE | BAS | A-I Restaurant & Lobby Reconfiguration | Provide Schematic Design and Design Development drawings for the complete reconfiguration of Building C including kitchen, dining space, and common areas. The restaurant and kitchen areas are largely original to the building and well past their useful life. The new, replacement, Glasgow restaurant coming on-line in Fall 2020 will allow a needed reprogramming and modernization of this space. Preliminary Program for this space includes a smaller Catering Kitchen, Meeting Rooms, new KUCR studio as well as a modernization and upgrade of the Lobby and other Common Areas. Documents to be assembled for a Fall 2020 construction start. | ABER INVER |  | Project currently on hold pending approval | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 9 |  |  | FALSE | 545000 |  | 2018-07-17 | Approval & Funding | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3463 | 3463 |  | FALSE | BAS | Landscape Strategic Plan for Housing Services | Provide a comprehensive study of existing landscape areas within Auxiliary Services and provide specific and actionable recommendations for their conversion to sustainable landscaping by location. Study to include all Resident Hall and Apartment properties and include conceptual cost estimates, by location, for proposed landscape conversions. |  |  | Project on-hold | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 11 |  |  | FALSE | 0 |  | 2018-07-17 | On hold per Auxiliary Services | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3460 | 3460 |  | FALSE | BAS | A-I Restroom Replacement - Reconfig | Provide Schematic Design and Design Development drawings for the complete replacement of the restrooms in all four resident hall wings. Existing restroom fixtures and finishes are largely original to the building and long past their service life, causing serious leaks between floors. New restrooms will be reconfigured to meet current accessibility code. Documents to be assembled for phased construction, one wing per summer, with the first building (D-Wing) to be constructed in Summer 2019. | ABER INVER |  | On-hold | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 12 |  |  | FALSE | 2782000 |  | 2018-07-19 | Bidding in Late-Nov. | 2020-03-01 | 2020-09-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3467 | 3467 |  | FALSE | BAS | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | PSA issued, coordinating site inspections. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 13 |  |  | FALSE | 50000 |  | 2018-07-31 | Site Inspections | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3466 | 3466 |  | FALSE | BAS | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Final Report Review | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 14 |  |  | FALSE | 0 |  | 2018-07-31 | Project Planning with Aux. Svcs. | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3382 | 3382 |  | FALSE | BAS | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 15 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2021 | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
2868 | 2868 |  | FALSE | BAS | West Lothian Elevator Renovation |  |  |  | In Close-out | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 16 |  |  | FALSE | 365000 |  | 2015-04-08 | Complete Close-out | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
3392 | 3392 |  | FALSE | BAS | Bicycle Master Plan Study | Bicycle Master Plan Study. This CPMS project is for the funding and creation of a Bicycle Master Plan Study for the UCR Campus. It is not for a specific capital project. |  |  | Pre-Programming | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Melissa Garrety | 17 |  |  | FALSE | 115000 |  | 2017-11-13 | Funding | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
3472 | 3472 |  | FALSE | BAS | Lot 20 Trash Enclosure Relocation | Construct a new CMU trash enclosure with water and power in a different location of Lot 21 to replace the existing enclosure that will be demolished to make way for the Dundee Residence Hall construction. Include hose bib for cleaning and power for future compactor installation. New enclosure needs to be on line BEFORE site construction can start on Dundee-Glasgow in January 2019. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 18 |  |  | FALSE | 0 |  | 2018-08-15 | Award Contract | 2019-09-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3397 | 3397 |  | FALSE | BAS | Dundee Residence Hall and Glasgow Dining | (Lot 22/Dundee-Glasgow) A newly proposed student housing development, including a single phase 760-bed residence hall and an 830-seat dining facility located on the existing Parking Lot 22 site south of Linden Street. The project is anticipated to be completed by Fall/Winter 2020. Funding for predevelopment activities including CEQA and staff augmentation to be determined. | ABER INVER |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Thomas Toepfer | 20 |  |  | FALSE | 1120000 |  | 2017-11-21 | Complete Construction | 2019-01-01 | 2020-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3203 | 3203 |  | FALSE | BAS | Plaza Structural Seismic Study | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. |  |  | Design Development for Bldgs. C, E & F | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 21 |  |  | FALSE |  |  | 2016-10-10 | Design development | [11 empty] | PD&C | FALSE | 2016 | 2019-09-01
3490 | 3490 |  | FALSE | BAS | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Daneca Stevens | 23 |  |  | FALSE | 1696000 |  | 2018-12-06 | Selection of Design Build Team | 2019-12-01 | 2021-02-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3503 | 3503 |  | FALSE | BAS | Falkirk Stair/Front Porch Repair | Repair or replace four sets of entry stairs and landings that are long past their service life and are a life safety concern. Consider replacing these wood structures with steel to ease future maintenance. Apartments affected are #3RS, #11MN, #15A and #16FG. |  |  | In Bidding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 24 |  |  | FALSE | 165000 |  | 2019-02-01 | Complete Close-out | 2019-06-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
2508 | 2508 |  | FALSE | BAS | Barn Expansion | Project 950493 Barn has completed the DPP process and we are now adding this to CPMS to capture expenses related to the Program Process which occurred in FY11-12 and FY12-13. Please move all expenditures from A01233-70003-76 Cost Center to JR142 to a plant account. |  |  | In construction | Gerry Bomotti | Georgianne Carlson | Susan Marshburn |  | D.Hecht/J.Franklin | 28 |  |  | FALSE | 28929771.28 |  | 2013-07-05 | Complete Construction | 2018-06-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2013 | 2019-09-01
3519 | 3519 |  | FALSE | BAS | CBTL Permit Inspections | CBTL PERMIT INSPECTIONS - The Coffee Bean & Tea Leaf restaurant is being leased by a CBTL franchisee (currently this is operated by UCR). They have submitted drawings to do a light remodel of the space. Permit and inspection services are needed to support their remodel. |  |  | In Close-out | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 29 |  |  | FALSE |  |  | 2019-04-04 | Complete Close-out | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3421 | 3421 |  | FALSE | BAS | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 30 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3426 | 3426 |  | FALSE | BAS | Lothian Boiler Replacement | The boiler equipment at Lothian is original to the building and past its useful life. Design, procure and install a replacement boiler that incorporates the latest energy saving and management technology that can be cost-effectively installed as a direct replacement to the existing unit. | LOTHIAN HALL |  | On hold | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 32 |  |  | FALSE | 0 |  | 2018-03-19 | On hold | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3533 | 3533 |  | FALSE | BAS | Solar Rooftop Initiative | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. |  |  | Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 35 |  |  | FALSE |  |  | 2019-06-03 | Design | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3286 | 3286 |  | FALSE | BAS | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 36 |  |  | FALSE | 2985000 |  | 2017-03-29 | Complete Construction | 2019-08-01 | 2019-11-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
19P000028 |  | 19P000028 | FALSE | BCOE | SL5 BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS |  | BOURNS | A0169 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | 5/1/19, DL; This project is 100% Complete…..3/28/19, DL; Monitor mounts were removed, Patch and paint will be completed in the near future……2/28/19, DL; Will schedule the project to be complete the first week in April…… | 2018-11-14 | Ron Veloz | 11/14/18 RV: Moved to Que to Start….10/29/18 RV: Scoping is completed. Carpenters to Remove Ceiling Mounted TV supports from the lobby ceiling. Work may require Carpenters to open the hard ceiling and remove the TV bracket posts if they cannot be unscrewed from the mounting brkt at the deck above. Work ay also require drywall patch back, tape, sand and paint the lobby ceiling. | YES | 2019-05-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000349 |  | 18P000349 | FALSE | BCOE | SL5 PHYSICS INSTALL PARTITION WALL FOR LAB ROOM |  | PHYSICS | 1037 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 5/24/18; Ron V. has detailed scope and he is ordering material. Once material arives, we will schedule the work…. DL, 6/16/18; Materila is ordered, When door/frame arrives, we will prep, paint and start the work…….DL, 7/11/18; This Project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; This is a small partition wall with sound proofing to minimize noise from the compressor that is disruptive to the Helium Ion Microscope…….DL, 4/16/18; We will schedule this work to be complete by the end of the Spring quarter. DL, 5/19/18; Walked project with Ron. FAMIS work order producd and material is being ordered.... | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000321 |  | 18P000321 | FALSE | BCOE | SL5 STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST |  | STUDENT SERV | 1228 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Enrico Baez |  |  |  | FALSE |  |  | 2018-02-22 | [6 empty] | DL, 4/29/18; Enrico is cordinationg this. The permits are approved……. DL, 7/11/18; Just received confirmation the door is ready for delivery and installed. I need to check in with Paul about the paint and prep of the door. I also need to check in with Jason on lock hardware......Dl, 7/25/18; Door is painted and ready for install. Called Dugmore to schedule the install. This should be compolete within the next two weeks......DL, 8/8/18; This Project is 100% Complete |  | Enrico Baez | DL, 4/29/18; Enrico is cordinationg this. The permits are approved. EB. 5/11/18- waiting for PO to be issued to Vendor. Customer provided PO numbers, waiting to schedule install with vendor, 5 week lead time. | YES | 2018-08-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000315 |  | 18P000315 | FALSE | BCOE | SL5 BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB |  | BOURNS | B0235 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  | HOLD | TRUE |  |  | 2018-02-16 | [6 empty] | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction to scope, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... Need to walk project with Ron and schedule the work....DL, 5/24/18; Conducted site visit with Ron V. Ron will order material and schedule the work once material is on site.....DL, 6/16/18; Need to verify delivery date for material.......DL. 7/11/18; Plumbing is disconnected. Corey is tentatively scheduled to disconnect the Fume hood. Once the Fume hood is disconnected, we will schedule the removeal of the fume hood and start the framing of the wall. Target complete date is 8/8/18....DL, 7/25/18; Fume hood is disconnected. Need to move Fume hood and start framing target date is delayed to creep scope but should be complete near 8/16/18.....DL, 8/10/18; Carp[enters will install the wall this week. Corey has parts orders. Corey will complete the install when the material arrives.......DL, 8/22/18; This Project is Complete |  | Dan Lerman | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... DND 7/14 Hold per customer on prioritization | YES | 2018-08-23 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000472 |  | 18P000472 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALL |  | CHUNG HALL | 458 | COMPLETE | Christopher Lynch | Maggie Souder | JANNA LE BLANC |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000427 |  | 18P000427 | FALSE | BCOE | SL5 BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER |  | BOURNS | A0373 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie email; This is our new Dean’s faculty office. Dean Lynch is already on site getting up to speed one-two days a week. This office is an ASAP...... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected.....DL, 7/11/18; This project is 100% complete...... |  | Paul Ditty | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000454 |  | 18P000454 | FALSE | BCOE | SL5 BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS |  | BOURNS | A0346 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  |  | 9 | FALSE |  |  | 2018-05-29 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000394 |  | 18P000394 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK |  | BOURNS | A0159A | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 2 | TRUE |  |  | 2018-04-12 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………….1/15/19, DL; Sound Soak is ordered and should arrive within two weeks……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; Need to review and scheudle…….DL, 7/11/18; Still need to review and scheudle…..DL, 8/22/18; This Project is complete but Maggie wants to see if the Faculty are happy with the results. We may install Sound Soak as a final option…… DL 9/6/18; Sent Maggie an email to see if she is satified with the work performed in regards to the sound proofing. I will have an update by the next Excel update….. DL, 9/19/18; The PI is out of town. Maggie will confirm the PI is satisiofd with the work when they return……on 9/18/18…DL, 10/8/18; Customer not satisfied with first round of sound proofing. We will proceed with Sound Soak material….. |  | Enrico Baez | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. EB 6/1 site visit- 3 door between 4 offices require sound proofing. Doors measure 36" x 106". Photos in FAMMIS. O-RVL: Uploaded sound soak panel data on FAMIS and is available on the Project Server File. 10/18/18 O-RVL: Per FS team meeting, we now have a clarified process that sound soak is not included in the SLA due to the fact this is not part of the work we perform at FS. Because we already committed to do further follow up with the sound soak, we will not charge this time but moving forward sound soak will be a recharge service as the team does not have the skillset to do the work and therefore outside the SLA. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000425 |  | 18P000425 | FALSE | BCOE | SL5 BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - |  | BOURNS | A0379 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; Luat Vuong arrives on or about August 15…... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected..…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/15/18........DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000429 |  | 18P000429 | FALSE | BCOE | SL5 INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 |  | BOURNS | B0262 B0256 | COMPLETE | Christopher Lynch | Maggie Souder | KEVIN SCHULTE |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment…..DL, 5/9/18; We are working on plans to submitt to A&E soon....DL, 5/24/18; Plans were submitted on 5/24/18.......DL, 6/12/18; Plans were approved. Cabinets are ordered. Materila is 6-8 Weeks out.....DL, 7/11/18; We have confirmation for delivery of material for mid August. Target Complete date is 9/7/18......DL, 8/10/18; Project has started. We will be complete with in two weeks......DL, 8/22/18; Work is 90% Complete..Project should be complete by 8/31/18........ DL 9/6/1/8; This project is 99% complete. The parts arrived today. I will be sending out an email to schedule the installation time for next week.......DL, 9/19/18; This project is 100% Complete........ |  | Dan Lerman | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment….. | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000426 |  | 18P000426 | FALSE | BCOE | SL5 BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER |  | BOURNS | A0375 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; A-375: Bhargav Rallabandi arrives on or about August 1….. DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/1/18.....DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000267 |  | 18P000267 | FALSE | BCOE | SL5 CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-01-16 | [6 empty] | DL, 5/19/18; High table mounted on West wall to be relocated to South wall by light "Centered". Relocate white board from East Wall to West walll wher high table was removed. Paint and new flooring. Need to schedule work with Paul and Jess. BKM furniture is scheduled 4-6 weeks. DL, 6/16/18; Lower electrical outlets on North wall, repair blinds, paint and new flooring. The space is vacant as of June 16th. I will scheudle the workl.....BKM delivery is currently scheduled for July 23rd.......This project is 100% complete. There were two items added to the scope and they will be complete by 7/20/18..... |  | Enrico Baez | 4/3/2018 Met with Maggie. She is working with BKM. Floor to go down first. BKM furniture on top. Annotated in Famis. | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000391 |  | 18P000391 | FALSE | BCOE | SL5 PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN |  | CHUNG HALL | 446 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 5/5/18; Conducted scope visit with Paul and Maggie. This project is target date is August 30th. As of now, we have 10 business days to complete the work……. Dean's Office….DL, 6/16/18;Walked project with Jess and Paul. This will be a project will now incluclude flooring is 7- additional offices due to additional trip hazzards identified in 3 of 7 offices during the carpet scope. Maggie will pay four four of the office since they are still in good condition. We are still on schedule with the work.......Dan, 7/11/18; This project is still on schedule. Complete Date is 8/18/18 and scheduled to be complete on 8/31/18.....DL, 8/10/18; The project is on schedule and we will start on Monday.......Ahead of schedule, project will be complete on 8/29/18......DL, 9/6/18; This project is 100% complete. Note, Maggie did request Jess to come back and remove some glue and he has this scheduled..... |  | Dan Lerman |  | YES | 2018-09-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000388 |  | 19P000388 | FALSE | BCOE | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | BCOE Advising is being reassigned to space on the 3rd floor of Skye (at the recommendation of the University Space Committee). | SKYE HALL | 308 | COMPLETE | Christopher Lynch | Maggie Souder | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-26 | [6 empty] | 7/15/19, DL; This project is 100% Complete………..7/1/19, DL; This project ois 95% Complete. Floor covering install will start this Wednesday…………6/17/19, DL; This project is almost complete. Target complete date is July 1st….…..5/31/19, DL; We are making good progress on this project. we are on tract to be copmplete with this project on or before July 1st……5/15/19, DL; Work is in progress and we are on schedule for th3 6/28/19 complete date…….5/1/19, DL; We will start this project this week. 4/15/19, DL; Plans were approved today. We will work on material and schedule the work. We will start this project shortly after May 1st…….3/18/19, DL; We are working on plans and plan to apply for building permit an plan review process next week | 2019-02-13 | Ron Veloz | 03/04/19 O-RVL: Updating notes on FAMIS & Access DB. Scoping is completed. After discussing the project with Monty and Dan, this project does not require an estimate and will be covered under Core since it is required for student advising and department operations. RV has communicated this to Sharyl Murdock on 03/04/19. RV Reassigning from O-RVL to O-UA1. Intake was completed on 02/13/19. ~ 02/22/19 O-RVL: RV walked the site with Enrico to survey carpet. Enrico suggested a deep extraction. RV contacted Custodial to sample a section to determine if cleaning the carpet could enhance the appearance. Pending response for Gena L. ~ 02/21/19 O-RVL Spoke with Monty about carpet conditions. Will walk with Enrico for second opinion. ~ 02/13/19 O-RVL: Completed intake. 01/28/19 O-RVL: Jobwalk scheduled with Hour Glass Co 1/28/19 11:30am ~ 01/25/19 O-RVL: Met Maggie & Sharyl M at Skye to review the SOW for new walls, sliding glass door and interior viewing window. RV will contact a glazing vendor the week of 01/27 to request a quote to install new storefront windows and sliding glass door within a storefront frame or Western Integrated Frame ~ 01/23/19 O-RVL: RV emailed Sharyl for meeting date and time. Pending response. Received response on ~ 01/23 from Sharyl. She will schedule the meeting/site visit. Pending invitation. ~ 1/22/19 O-RVL: Acknowledged request. Will schedule a site visit with Sharyl Murdock. Left voice message and emailed Sharyl (01/22) to schedule a site visit. Proj # is not in the Data base, unable update notes. ~ 01/22/19 RV spoke with Sharyl and will receive an email with updates. ~ 01/22/19 RV received email with updates from Sharyl and added to the project folder. ~ MA 1/7/19: Assigning to Ron Veloz for Estimation process with BCOE partners. | YES | 2019-07-15 | FS | FALSE | 2018 | 2019-09-01 | FY 19-20
19P000445 |  | 19P000445 | FALSE | BCOE | SL5 BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT |  | BOURNS | B0328D | CANCELED BY FS | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  |  |  | 0 |  | FALSE |  |  | 2019-01-11 | [8 empty] | Ron Veloz | 02/27/19 O-RVL: RV sent a project cancellation request to Deborah H and cc'd Alan S., Linda B., Loretta V. & Monty. RV reassigned from O-RVL to O-UA1. END--- 02/22/19 O-RVL: RV Received information from the last team meeting that is project will be cancelled and resubmitted at a later date. RV spoke with Maggie about the cancellation on Wednesday 2/20 and informed her a I would send a letter to follow up from our conversation. Maggie understood the scope creep from the previous project and will resubmit the request at a future date. END--- 02/15/19 O-RVL: Ron V will contact Maggie and explain this request would exceed our proejct allowance and place FS out of compliance with UC requirements. RV will present options to the customer. Possibility to utilize black out curtains and or BKM style furniture as an immediate altenative (Cost absorbed by the departments). The customer will be able to resubmit the request at a later date. END--- 2/7/19: Alan S. Customer Relations Team to follow-up with customer re: change in scope of work. END--- 1/11/19 SPOKE TO DAN LERMAN-THIS PROJECT MAGGIE SOUDER NEEDS IT DONE ASAP - PLEASE SEE DAN LERMAN FOR MORE INFO...DEBORAH email to Monty for Maggie's request. | N/A | 2019-02-27 | FS | FALSE | 2019 | 2019-09-01
19P000278 |  | 19P000278 | FALSE | BCOE | SL5 REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR |  | BOURNS | A0165 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Dan Lerman |  | 1 |  | TRUE |  |  | 2018-08-03 | [6 empty] | DL, 10/4/18; This Project is 100% Complete…….. |  | Ron Veloz | Completed SOW, met withJess and informed of work and color. | YES | 2018-10-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000638 |  | 19P000638 | FALSE | BCOE | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM | renovate lab | BOURNS | B207 | IN PROGRESS | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-16 | [6 empty] | 9/3/19, DL; Project is in progress and 75% complete. 8/15/19, DL; Plans were approved this week. We will order the material and schedule the work……..Plans are 90% complete and we will probably submit plans for plan check review this Monday | 2019-07-19 | Ron Veloz | 07/10/19 O-RVL: Visited Luat V with Dan L on site on 07/10 at 10:00am-11:30 to review SOW. Additional changes were made. Luat will prepare a revised layout and send to Ron V & Dan L. Thereafter, RV will incorporate all SOW and note on the intake form and send to Luat & Dan to verify the SOW and floor plan. ~END~ 07/24/19 O-RVL: Met with Dan, Luat and Gilbert(PD&C) for final SOW review and code requirements. 07-01-19 O-RVL: RV visited with Luat Voung on 06-25 to review scope. PI was uncertain of renovation and requested additional time to revise SOW. PI will contat RV when ready with new list. 07/01/19 O-RVL: Pending intake/site visit to confirm SOW. | YES |  | FS | FALSE | 2019 | 2019-09-01
19P000619 |  | 19P000619 | FALSE | BCOE | SL5 BOURNS, RM A0311- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0311 | IN PROGRESS | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-05-14 | [6 empty] | 06/28/19 O-ANS: Paint phase complete and awaitin flooring install. | [5 empty] | FS | FALSE | 2019 | 2019-09-01
19P000453 |  | 19P000453 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT |  | CHUNG HALL | 447 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-17 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000059 |  | 19P000059 | FALSE | BCOE | SL5 CHUNG HALL 201 SECURITY SYSTEM INSTALL | ITS to install cameras, no work by FS Required. | CHUNG HALL | 201 | CANCELED BY FS | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 10 | 7 | FALSE |  |  | 2018-07-17 | [6 empty] | DND 7/30/18 Project #19P000059 to replace REF CPMS # 9054 Ron to speak with ITS to complete installation. |  | Ron Veloz | 10/29/18 RV: Last meeting it was discussed that FS does not install Security Camera systems. Ron V spoke with Maggie on 10/26 to inform her that the project will be removed from the FS Minor Ren. List and she will need to contact ITS to request the Security Camers. 08/27/18 RV: Updated notes. Moved to "Que to Start". 09/19/18 RV, Install Security Cameras at points of entry. Install DVR locally in closet at an adjacent room. 08/23/18-RV Met with D.L. and Jason W. and verified F.S. will perform cabling installation and mount cameras. Equipment cost is not included in the SLA. R.V. will communcate informantion to Maggie. 08/22/18 O-RVL: Met with M. Souder to determine security camera needs and approximate location. | YES | 2018-07-30 | FS | FALSE | 2018 | 2019-09-01
19P000621 |  | 19P000621 | FALSE | BCOE | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0308 | QUEUE TO START | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000477 |  | 19P000477 | FALSE | BCOE | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT |  | CHUNG HALL | 457 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-01-30 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000029 |  | 19P000029 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | Canceled; duplicate request to be completed with 19P000059 | CHUNG HALL | 205 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-16 | [6 empty] | Canceled; duplicate request to be completed with 19P000059 |  | Ron Veloz | to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | NO | 2018-09-18 | FS | FALSE | 2018 | 2019-09-01
19P000316 |  | 19P000316 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL |  | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…Anticipated completion 11/9/18. | 2018-10-03 | Ron Veloz |  | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000046 |  | 19P000046 | FALSE | BCOE | SL5 PATCH AND PAINT PLUS REPLACE BLINDS |  | BOURNS | A0131 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000442 |  | 19P000442 | FALSE | BCOE | SL5 WINSTON CHUNG- PATCH/PAINT ROOM 319 |  | CHUNG HALL | 319 | COMPLETE | Christopher Lynch | Maggie Souder | BILL BINGHAM |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-09 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000487 |  | 19P000487 | FALSE | BCOE | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES |  | BOURNS | A219, A211, A241 | COMPLETE | Christopher Lynch | Maggie Souder | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-02-05 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | PLAN DEVELOPMENT/CHECK | Christopher Lynch | Maggie Souder | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-09 | [6 empty] | 9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Ron Veloz | 08/08/19 O-RVL updating notes. 07/02/19 O-RVL: Jobwalk with PI and Dan l. END~ 07/01/19 O-RVL: Pending intake/walk. | YES |  | FS | FALSE | 2019 | 2019-09-01
19P000175 |  | 19P000175 | FALSE | BCOE | SL5 PAINTING |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT CHAVARRIA-VIVAR |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000312 |  | 19P000312 | FALSE | BCOE | SL5 VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP |  | STUDENT SERV | 1227 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000601 |  | 19P000601 | FALSE | BCOE | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY | Renopvate lab space, Patch/paint, Re-finish, re-surface – existing cabinets/casework. Re-finish, bench-tops. Clean existing Chemical fume hood. Repair or replace self-closing chemical/flammables storage cabinet. Repair or replace bench shelves as needed. Clean and wax floors. | BOURNS | B0328E | PLAN DEVELOPMENT/CHECK | Christopher Lynch | Maggie Souder | KATHALENA COCKER |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-05-09 | [6 empty] | Scope is copmplete, waiting on estimates from vendors. We will need to work up a contract which will add time to the project timeline… | 2019-08-06 | Ron Veloz | 08/08/19 O-RVL: Received final revisions from Maggie via email today. Dan L was copied on email. END~ 08/07/19 O-RVL: Pending final review fof SOW from PI/Maggie. END~ 07/24/19 O-RVL: RV scheduled site visit for Dan, Maggie and Luat to confirm the SOW. RV was unable to attend. 07/19/19 O-RVL: RV scheduled a site visit with Dan L, Luat to verify SOW. 07/10/19 O-RVL: RV Met 1-1 with PI Luat Vuong, meet and discuss process and SOW . 07/07/01/19 O-RVL: Pending intake / site visit | YES |  | FS | FALSE | 2019 | 2019-09-01
19P000597 |  | 19P000597 | FALSE | BCOE | SL5 PATCH AND PAINT WALLS |  | CHUNG HALL | 355, 356, 351, & 353 | COMPLETE | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-05-03 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
19P000625 |  | 19P000625 | FALSE | BCOE | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM |  | BOURNS | A0108 | QUEUE TO START | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-15 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000322 |  | 19P000322 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-05 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000205 |  | 19P000205 | FALSE | BCOE | SL5 LABORATORY RENOVATION FOR NEW FACULTY |  | BOURNS | A0328 | COMPLETE | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  | Dan Lerman |  | 4 |  | TRUE |  |  | 2018-08-23 | [6 empty] | 2/28/19, DL; This Project is 100% Complete…….2/1/19, DL; This project is 99.9% Complete………..1/15/19, DL; This project is 90% complete. WE still need to finish snorkels and ceiling tiles. We should be 100% complete by 2/1/19……12/14/18, DL; This project is on schedule..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/4/18; This is a large scale project, we will walk with the trade supervisors next week. We will also work on the plans and schedule the work. Target Date is 1/1/19…..DL, 11/7/18; work is scheduled. We are working on the electrostatic paint contract. We are in plan check review process. There are questions about the fire sprinklers from Scott J. Sent Scott J. an email requesting a site visit to better determine if any work will be required on the sprinkler system….. |  | Ron Veloz | 10/03/18: RV spoke with Dan. He had previously met with Maggie and had scoped this project. | YES | 2019-02-18 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000250 |  | 19P000250 | FALSE | BCOE | SL5 BOURNS A303-PAINT AND PATCH WALL |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | JUANA GUERRERO |  | Paul Ditty |  | 5 |  | TRUE |  |  | 2018-09-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000558 |  | 19P000558 | FALSE | BCOE | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT |  | BOURNS | A0265 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-04-03 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
19P000424 |  | 19P000424 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET |  | CHUNG HALL | 445 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-12-20 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000526 |  | 19P000526 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT |  | CHUNG HALL | 0202 & 0203 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-03-12 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000060 |  | 19P000060 | FALSE | BCOE | SL5 CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | CHUNG HALL | 223 & 224 | TO BE PERFORMED BY PD&C | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 6 | 4 | FALSE |  |  | 2018-05-15 | [6 empty] | 2/1/19, DL; Thios is a PD&C project. Maggie S. is aware this project may be a $130,00. project……DL, 7/25/18; This project is complicated and plans/permits will be required. This project will also require Air Hanlers to be shut down so Vibration dampners can be instlled. We will work on the plans in the next 45 days. This project should be scheduled during the Winter. We may also need to rent a large portable air handler to ensure the Large server room can maintain temp……. Project #19P000060 to replace REF CPMS # 9043. DL, 11/7/18; Sent Maggie an email on 11/7/18 informing her this project is well beyond our scope and $50K threshold. |  | Dan Lerman | DD 7/17: IRT Scoped with Dan present. Attached to FS Project. REF CMPS 9043 | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01
19P000565 |  | 19P000565 | FALSE | BCOE | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS |  | BOURNS | A0133 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | NANCY FORD |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-04-08 | [6 empty] | 07/30/19 O-ANS: Per Paul Ditty, Customer Maggie Souder canceled project. |  |  |  |  | 2019-07-30 | FS | FALSE | 2019 | 2019-09-01
19P000129 |  | 19P000129 | FALSE | BCOE | SL5 HANG MONITORS AND BOARDS |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | RICHARD BAIN |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2018-08-06 | [6 empty] | 12/14/18, DL; This Project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Dry errase boards and Monitor mounts are installed. Still need to install monitors, corner guards and monitors….. |  | Ron Veloz | 10/03/18 O-RVL: Install one 32" monitor asouth wall center of table, Install 55" TV at west wall(need power & data), install white bd at east wall 8' from north corner, install chalk bd at east wall 2'-6" from corner at 8" above small table. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000226 |  | 18P000226 | FALSE | BCOE | SL5 BOURNS FUME HOOD INSTALLATION |  | BOURNS | B0235A | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  | 8 | HOLD | TRUE |  |  | 2017-12-11 | [6 empty] | 2/14/19, DL; This project is Complete…..2/1/19, DL; The Fume hood is complete. The vendor will be back in two weeks to comissison the clean room…..…1/15/9, DL; This project is 95% complete and should be complete on or near 2/1/19…………12/14/18, DL; This Project is 90% Complete. Fume hood is scheduled for install next week. We will finish balance of project after Fume hood is installed…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. WE are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans…..DL, 5/9/18; planning to submit plans on 5/11/18 for plan check review….. DL, 5/24/18; Plans were submitted to Bob W. on 5/24/18……DL, 6/12/18; Project is on Hold until Shane can provide plans/specs for the clean room……DL, 7/11/18; Still no change to the status……DL, 7/25/18, Maggie confirmed this project is on the books. I need to discuss the status with the team because the priority list is on Hold…….DL, 8/22/18; This project is no longer on hold. We will per shane we will submit what we have from the clena room suupplier for review from FM and BO……DL, 9/6/18; WE are almost complete with Plans and will submit the plans next week………DL, 9/19/18; Submitted plans to PD&C on 9/14/18…..DL, 10/4/18; Plans were approved thais week. WE will scheudle the project around the delivery date for the Clean room……..DL, 11/7/18; This is in progress. We will complete the install of the utilities so the clean room can be installed. WE will finish the balance of the project once the Clean room install is complete. The clen room is being install by an outside vendor….. |  | Dan Lerman | 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. We are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans..... DND 7/14 Hold per customer on prioritizatio | YES | 2019-02-14 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
19P000588 |  | 19P000588 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - PATCH & PAINT OFFICES |  | BOURNS | A127 Office, A129 Office, A131 Office, A133 Office, A135 Office, A137 Office, A139 Office, and A141 Office | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-04-22 | [6 empty] | 06/28/19 O-ANS: Paint phase complete. |  |  |  |  | 2019-06-28 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000620 |  | 19P000620 | FALSE | BCOE | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0304 | QUEUE TO START | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Paul Ditty |  | 9 |  | TRUE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000035 |  | 19P000035 | FALSE | BCOE | SL5 WCH--INSTALL NEW LED DISPLAY IN OFFICE |  | CHUNG HALL | 354 | COMPLETE | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This Porject is 100% Complet…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Install scheduled for this Friday. | 2018-10-03 | Ron Veloz | 10/03/18 RV Walked site with Dan L. SOW Install TV Bracket at south wall center of room. Requires Power (no Data)installation of mounting bracket. TV and brk is located in Sarah Galloways office. Scope is completed. Dinh 9/18 19P000023/19P000026 requests for paint to be included in project scope for room. | YES | 2018-11-19 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000023 |  | 19P000023 | FALSE | BCOE | SL5 PAINT ACCENT WALL | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-13 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000026. Canceled to be completed on 19P000035 | N/A | 2018-09-18 | FS | FALSE | 2018 | 2019-09-01
19P000026 |  | 19P000026 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALLS | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000023. Canceled to be completed on 19P000035 | N/A | 2018-09-18 | FS | FALSE | 2018 | 2019-09-01
18P000439 |  | 18P000439 | FALSE | BCOE | SL5 CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING |  | CHUNG HALL | 315 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 11 | FALSE |  |  | 2018-05-15 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000438 |  | 18P000438 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING |  | CHUNG HALL | 415 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 10 | FALSE |  |  | 2018-05-14 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | Award Contract - September | Christopher Lynch | Maggie Souder | Margaret Souder |  | Scott Donnell | 1 |  |  | FALSE | 700000 |  | 2018-04-04 | Award Contract | 2019-11-01 | 2020-01-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3300 | 3300 |  | FALSE | BCOE | R'Garden - Solar Installation | Electrician to do the following wiring of our solar panels and inverters out at the R’Garden at UCR. The H model cyboinverter to be used powers the lower heating element of the water heater. The thermostat of the lower heating element must then be set to be higher than the upper heating element. The two output lines are to be connected to an AC switch or switchable AC outlet and the lower element water heater. |  |  | Work to be inspected by A&E. | Christopher Lynch | Maggie Souder | Arvin Tam |  | Scott Donnell | 2 |  |  | FALSE | 0 |  | 2017-05-03 | Relocation | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
19P000296 |  | 19P000296 | FALSE | CAMPUS | SL5 MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB |  | MAT SCI ENGR |  | COMPLETE |  |  | MILLY PAREDEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-09-25 | [6 empty] | 2/28/19, DL; Project is 100% Complete…….2/14/19, DL; This project is 90% Complete and should be complete by the end of the month………….2/1/19, DL; Permits are approved, we will schedule the project in the next 2- weeks and hope to be complete by the end of February….12/14/18, DL; Rendering has been given to Ron R. Ron will present to Gerry for review and approval. Once approved, we will proceed with plans and permits……DL, 11/7/18; Need to find out where this project stands in regards to the priioroity….. Site vist was conducted and scope of work is verified. Plans and permits will be required for the work….. |  | Ron Veloz | 10/19/18 O-RVL: Walked the proposed location with Dr. Barsukov to review needs and location for nitrogen tanks in the hall. DL suggested to construct a wall with double doors approx 2' below the ceiling height. 09/27/18 O-RVL: Walked site with Chris P, Dan L., Deborah Mc Williams & Mayela C to review SOW. | YES | 2019-02-28 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000188 |  | 19P000188 | FALSE | CAMPUS | SL5 PAINT - HALLWAY DOORS & INSIDE RESTROOMS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500 | CANCELED BY FS |  |  | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-16 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | FS | FALSE | 2018 | 2019-09-01
19P000212 |  | 19P000212 | FALSE | CAMPUS | SL5 REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500A | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  | 1/11/19 Canceled per instruction from Ron Rector on 1/11/19; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting (Stephen C) |  | 2018-12-13 | FS | FALSE | 2018 | 2019-09-01
19P000211 |  | 19P000211 | FALSE | CAMPUS | SL5 LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | Reviewing campus standards for these project requests. | LIFE SCIENCE | 2545 | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | FS | FALSE | 2018 | 2019-09-01
18P000121 |  | 18P000121 | FALSE | CAMPUS | SL5 PHYSICS HYDRATION STATION - PHYSICS HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | 5/1/19, DL; Per Chris, we will not be compelting this project. There is currently a Water dispenser on the drinking fountain. 3/28/19, DL; We will look into installing a bottle filler on this fountain verse a complete change out…..12/6/18, DL; This project is currently on hold…… DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | Reviewing campus standards for these project requests. 3/4/19 DND Removed from FS hold per Ron Rector. DND 7/14: hold per hydration station update for campus….4/2/18; Notes are current….DL, 2/26/18, Still need to review scope….. DL, 1/5/18; Still need to review scope | NO | 2019-05-01 | FS | FALSE | 2017 | 2019-09-01
18P000435 |  | 18P000435 | FALSE | CAMPUS | SL5 HMSS HYDRATION STATION REQUEST |  | HUM & SOC SC | 3600 | COMPLETE |  |  | NELDA THOMAS |  | Dan Lerman |  |  | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 4/15/19, DL; This project is 100% Complete…..3/28/19, DL; Fountain is in. working on power and paint….. |  |  | 3/4/19 DND Removed from FS Hold Per Ron Rector | NO | 2019-04-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000122 |  | 18P000122 | FALSE | CAMPUS | SL5 MS&E HYDRATION STATION - MS&E HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | Reviewing campus standards for these project requests. DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus….3/4/19: Single trade renovation project to be performed by FS but not captured as a minor renovation. | NO | 2018-04-02 | FS | FALSE | 2017 | 2019-09-01
19P000284 |  | 19P000284 | FALSE | CAMPUS | SL5 GEOLOGY ACCOMMODATION DOCK DOORS |  | GEOLOGY |  | COMPLETE |  |  | DEBORAH TERAO |  | Chris Pillen |  | Canceled | Canceled | FALSE |  |  | 2018-08-07 | [8 empty] | Ron Veloz | 01/10/19 O-RVL: CLOSE OUT-WORK COMPLETED. All work for this project is completed. Email sent to Monty & team on Jan 04, 2019 confirmating all work is completed. 12/14/18 O-RVL: Loading dock Post and Chain fabrication, is in progress, Auto door operators are on Order/Contract in progress, Loading dock signage is in progress by sign shop, information was confirmed by Chris Pillen as of 12/13/18. All other request related to this project have been completed. RV sent updates to Monty on 12/13/18. 11/14/18 RV: Walked Capitol door on 10/31 for pricing. pending quote for auto door operators. 10/30/18 RV: Walke Paradise Door -Automatic Door operator vendor to site. Met with Jason to discuss door access hardware & function of locksets . Pending quote. 10/03/18 RV: Notes from FAMIS: Lock Shop - Chris working with Jason to purchase and install two sets of automatic door openers with plain face plates - to be installed in the back receivin area. | YES | 2019-01-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000396 |  | 19P000396 | FALSE | CAP.PROG. | SL5 TRAILER #14 - CAMPUS INITIATED - STRUCTURE |  | T14 |  | COMPLETE | Jacqueline Norman | Sharyl Murdock | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-31 | [6 empty] | 2/28/19, DL; This Project is 100% Complete…..Trailers were demolished. We need to install the utilities. Once the Grow Pod is on site, we will connect the utilities to the structure…… |  | Enrico Baez |  |  | 2019-02-28 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
3540 | 3540 |  | FALSE | CAP.PROG. | BCOE Advising Move | Relocation expenses for BCOE advising including: $75k furniture, $10k moving expenses, $3k misc. Renovations were also approved and were completed by Facilities under SLA. Also includes relocation of VCBAS from Skye to Student Services at $1,010 and move expenses for Student Disability from Costo to Student Services at $25k. |  |  | New | Jacqueline Norman | Sharyl Murdock | Sharyl Murdock |  | Sharyl Murdock | 2 |  |  | FALSE | 111010 |  | 2019-07-25 | Furniture Delivery | 2019-09-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
3233 | 3233 |  | FALSE | CAP.PROG. | Mobility HUB Central Campus Linkages | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Gerald Caraig | 3 |  |  | FALSE | 16011000 |  | 2016-12-16 | Leadership Direction | [11 empty] | PD&C | FALSE | 2016 | 2019-09-01
2916 | 2916 |  | FALSE | CAP.PROG. | Solar Greenhouse | Construction of a solar powered greenhouse. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Matt Barth |  | Scott Donnell | 4 |  |  | FALSE | 194000 |  | 2015-08-04 | Complete Construction | 2019-09-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
3234 | 3234 |  | FALSE | CAP.PROG. | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Close-out | Jacqueline Norman | Sharyl Murdock | John White |  | Fernando Nunez | 6 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete Punchlist & Close Out | 2018-11-05 | 2019-03-29 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
3120 | 3120 |  | FALSE | CAP.PROG. | Arts Walk Sculpture (Ext Campus Art Project) | Sculpture design concept - hiring a consultant to revise an artist design concept for a proposed outdoor art piece to be placed between the Arts building and the CHASS Interdisciplinary buildings. |  |  | Contractor removing rejected concrete | Jacqueline Norman | Sharyl Murdock | Uma Ramasubramanian |  | Jason Espinoza | 8 |  |  | FALSE | 1096000 |  | 2016-05-26 | Complete Construction | 2019-02-01 | 2019-11-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
3119 | 3119 |  | FALSE | CAP.PROG. | Plant Growth Environment Facility | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 9 |  |  | FALSE | 25000000 |  | 2016-05-25 | Site utilities & ret. Wall | 2019-04-01 | 2020-08-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
3293 | 3293 |  | FALSE | CAP.PROG. | USDA Head House - Public Restroom | Provide an accessible public restroom facility in or adjacent to the USDA Head House Building in Ag Ops. Restroom will serve individuals and groups touring the UCR and USDA Citrus Facilities. Three options have been proposed, and need to be considered and evaluated to recommend a feasible solution for USDA. The work would be managed and paid by USDA, including the design, bidding and construction. UCR staff needs to review the proposed plans and specifications per the agreement with USDA, and provide the review, inspection and approvals. The USDA representative is Marylou Polek. | GERMPLASM |  | Pending Lease | Jacqueline Norman | Sharyl Murdock | Mary Lou Polek |  | Scott Donnell | 14 |  |  | FALSE | 0 |  | 2017-05-22 | USDA Scope & Design | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
3319 | 3319 |  | FALSE | CAP.PROG. | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Design Development | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Mihai Gavan | 16 |  |  | FALSE | 3607000 |  | 2017-06-01 | Start Construction | 2019-11-01 | 2021-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3452 | 3452 |  | FALSE | CAP.PROG. | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 16 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Programming | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3005 | 3005 |  | FALSE | CAP.PROG. | Batchelor Hall Interior Improvements | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | BATCHELOR |  | In Design | Jacqueline Norman | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 17 |  |  | FALSE | 8837000 |  | 2016-02-02 | CM at Risk Selection | 2020-01-01 | 2021-11-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
3393 | 3393 |  | FALSE | CAP.PROG. | South Neighborhood Dist. Study | South Neighborhood District Study per discussions with the Provost/VCPB, July 2017. The South District Planning Study needs to provide guidance for future development in the South District that is inclusive of: **University aspirations to develop the South District to define the campus’ presence along the adjacent freeway (CA-60/215). **Development capacity, optimal building heights and conceptual massing presented both in metrics and a three dimensional format. **Broad parking strategy to meet the needs of the district in alignment with the campus’ overall parking management strategy and alternative transportation solutions. **High level understanding of infrastructure needs (electrical, domestic, fire and storm water, sanitary sewer, building heating and cooling) to meet the needs of the campus’ desired development capacity for district. **Pedestrian and vehicular connectivity. **East and South Campus Drive improvements |  |  | In Close-out | Jacqueline Norman | Sharyl Murdock | Uma Ramasubramanian |  | Fernando Nunez | 18 |  |  | FALSE | 309000 |  | 2017-11-15 | Follow Up on Study Reports | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
3366 | 3366 |  | FALSE | CAP.PROG. | Genomics Ramps | Genomics Accessibility Improvements - The proposed project will create an accessible sidewalk connection from the Genomics Building to the University Lab and University Office Building. Currently, there is no accessible north sidewalk linkage east of the Genomics Building. The project will demolish and replace approximately 300 square feet of asphalt to bring it up to grade. Two ADA ramps will be added to sidewalk extensions of approximately 300 square feet that connect across a driveway. Existing landscaping and irrigation will be removed and replaced. No trees will be impacted by this work. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Gerald Caraig | 19 |  |  | FALSE | 42000 |  | 2017-11-16 | Bidding | 2019-11-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3458 | 3458 |  | FALSE | CAP.PROG. | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | PM to update schedule | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 20 |  |  | FALSE | 0 |  | 2018-07-16 | PM to update schedule | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
2970d | 2970d |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan-Phase 4 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Programming | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Scott Donnell | 20 |  |  | FALSE | 2842000 |  | 2015-12-02 | Award package 1 & 3 | 2019-11-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
2970a | 2970a |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan-Phase 1 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | Bidding | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Scott Donnell | 20 |  |  | FALSE | 2842000 |  | 2015-12-02 | Award package 1 & 3 | 2018-09-01 | 2020-01-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
2970c | 2970c |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan-Phase 3 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Programming | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Scott Donnell | 20 |  |  | FALSE | 2842000 |  | 2015-12-02 | Award package 1 & 3 | 2019-11-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
3401 | 3401 |  | FALSE | CAP.PROG. | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | Working on Construction Docs | Jacqueline Norman | Sharyl Murdock | Mihai Gavan |  | Mihai Gavan | 21 |  |  | FALSE | 1530020 |  | 2017-12-03 | Project approval & bidding | 2019-12-01 | 2020-09-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
2952 | 2952 |  | FALSE | CAP.PROG. | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jon Harvey |  | Dave Bomba | 22 |  |  | FALSE | 23547000 |  | 2015-09-11 | Completion of phase one 3/15/20 | 2019-01-02 | 2021-06-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
3395 | 3395 |  | FALSE | CAP.PROG. | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | Third party cost estimator needed | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 23 |  |  | FALSE | 0 |  | 2017-12-03 | On Hold | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
3438 | 3438 |  | FALSE | CAP.PROG. | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | City to determine schedule | Jacqueline Norman | Sharyl Murdock | Dave Bomba |  | Dave Bomba | 24 |  |  | FALSE | 0 |  | 2018-08-22 | City to determine schedule | 2020-01-01 | 2020-09-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3175 | 3175 |  | FALSE | CAP.PROG. | DM16-Chilled Water Coils Multiple Buildings | Replace multiple leaking/degraded cooling coils across campus to prevent complete shutdown of building air handlers during the hot summer months. Buildings include: Student Services, Chemical Sciences, Genomics, Psychology, Entomology and MSE. |  |  | In Close-out | Jacqueline Norman | Sharyl Murdock | Melissa Garrety |  | Scott Donnell | 99 |  |  | FALSE | 1294648 |  | 2016-10-11 | Complete Close-out | 2019-01-01 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
18P000421 |  | 18P000421 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 2120 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-04-30 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000329 |  | 18P000329 | FALSE | CHANCELLOR | SL5 SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST |  | SKYE HALL | 170 | COMPLETE | Kim Wilcox | Karim Zahedi | DA LAN DINH |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18…..DL, 5/24/18; Plans were approved. Demo work has started......DL, 6/12/18; MArshal and Kate are working on Carpet order......DL, 7/11/18; Carpet is ordered. We have a challenge with Title 24. I am working on the title 24 documents. We are still planning to have this project complete on 8/17/18......DL, 8/10/18; We now have the Title 24 plans. The are being reviewed by Bob and Scott.....Title 24 plans approved. Robert is working on PO#. Most parts are on site and Electricans are working on project. All other Trades to follow once Lights are in...... Hard Date of 9/7/18............9/6/18 As of today, Carpet is scheduled for install tomorrow morning and furniture is scheduled for delivery this Monday......WE will more than likely have electrical punch items and touch up paint but this propject should be 100% complete in regards to FS the end of next week next week......100% PROJECT COMPLETE... GREAT WORK DAN! |  | Dan Lerman | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18….. | YES | 2018-09-18 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000209 |  | 18P000209 | FALSE | CHANCELLOR | SL5 VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 |  | STUDENT SERV | 0 | CANCELED BY CLIENT | Kim Wilcox | Karim Zahedi | ANGIE GRAY |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2017-11-30 | [6 empty] | 5/16/19, DL Angie Grey canceled project on 5/15/19 via email….. 5/1/19, DL; Sent Angie an email this morning. Waiting to hear back from Angie to see if project will be canceled or sent to PD&C…..3/28/19, DL; Provided Angie with an estimate and waiting for her response. The esimate was for 65,000. this work will be redirected to PD&C if she wants to proceed…….2/14/19, DL; Ron V. to follow up with Doug from Capitol Door for alternate pricing .1/15/19, DL; Ron V is still working with Angie on verifying a vendor and product…………..12/14/18, DL; Ron V. is currently working to find a more affortable turnstyle system. When a sytem is approved, we will schedule the work…. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope and conduct site visit……DL, 7/11/18; This work will require plans and permits. Will schedule meeting with Scott to verify if the project request will be approved. If this is approved, we will plan the target complete date to be mid October…..The Request is to reverese Emergency Exit Doors and install Prox card access……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..DL, 8/22/18; Confirmed with Scott that we can reverse the door swing. We will work on plans for review process. This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 9/19/18; I mis understood this for a project at Health Services. I have a meeting with Angie this week. This project is to install turn styles for access to the building. I will need to discuss the equipment to be purchased by Angie verify the specs. We will start on the plans in the early Fall……DL, 11/7/18; Conducted site visit with Vendor. Informed Angie the cost of the project will be at $45K for the project. Angie is checking to verify if funds are availabe for the equipment. |  | Ron Veloz | 03/19/19 O-RVL: RV updated notes as a follow up to Alan's meeting minute action items received on 03/07/19. Updating notes, RV spoke with Angie Grey on 03/18/19, Angie and Dan L met with the vendor (03/19) and is expecting pricing. Status to remain on "HOLD" pending quote and department approval. Update input on Access, FAMIS and sent to Alan on 03/19 Notes on FAMIS and Access have been updated. END--- 02/28/19 O-RVL: RV received confirmation from Doug at Capital Door that they are unable to provide a quote at this time due to deign changes with the product. END--- 02/21/19 O-RVL: RV has contacted Capitol Door with a RFQ. Pending follow up by 02/22/19 per Doug @ Capitol. END---02/21/19 O-RVL: RV Updated notes, RVhas contacted Capitol Door with a RFQ. Pending follow up by 02/22/19 per Doug @ Capitol. END--- DL, 5/5/18; FAMIS work order, New ADA operator, power supply for operator and card swipe…. 2/6/18 E. Baez conducted site visit. Power and Data not located near desired installation site. Width of opening is 118" Flooring is combination of brick and vinyl. 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 1 and for faculty hire "NO"---- 5/5/18; FAMIS work order, New ADA operator, power supply for operator and card swipe….2/6/18 EB- conducted site visit. Request for automated access control system. Annotated on FAMIS…. 2/2/18 EB site visit scheduled for 2/5/18 with Angie Gray. THIS REQUEST IS FOR QUOTES. THE SYSTEM REQUIRES AN FAU TO BE PROVIDED IN ORDER TO SUBMIT REQUEST. ACTUAL WORK WILL MOST LIKELY BE CHARGED TO A DIFFERENT FAU. THEREFORE, PLEADO NOT CHARGE FAU WITHOUT APPROVAL. Original request SR # 17S001552/WO # 17W001873 was submitted on 8/12/16 to Facility Services. A recommendation has come from UCPD for an automatic swing door to be installed on the first floor of the Student Services Building. The door would need to include a switch, button, and card reader functionality (SSB already operates on a keycard system). Please provide us with all options and pricing. The door would be similar to the ones installed in the SRC. I have attached a copy of the recommendation that contains a rendition. Please let me know if you have any questions. Thank you. Angie Primary Contact: Angie Gray. angeladi@ucr.edu. (951) 827-2589. Secondary Contact: Sean Cason. SEANC@ucr.edu. (951) 827-4020. 20 year(s) in use. ==CUST FAU# A01401 19900 68 AXSSB | YES | 2019-05-16 | FS | FALSE | 2017 | 2019-09-01
18P000410 |  | 18P000410 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 3148B | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-25 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | HOLD - FACILITIES SERVICES | Kim Wilcox | Karim Zahedi | ALEXIS RAMBAUD |  |  |  | 1 | 0 | FALSE |  |  | 2018-12-11 | [7 empty] | 2018-12-20 | Ron Veloz | 07/01/19 O-RVL: HOLD PER SUSAN. 04/15/19 O-RVL: On Hold per Susan Marshburn, Pending follow up Gerry Bomotti as of 04/15. FAMIS & Acess notes are updated. END~ 03/15/19 O-RVL: RV reviewed FAMIS. All notes we located on the "Service Request" screen. RV copied onto the project screen and Access data base. RV will cancel this request on Access and send out an email to Deborah H and team to cancel the request on FAMIS. END--- 03/06/19 O-RVL: RV received email from Monty requesting information the project not in Access or FAMIS. END--- 01/18/19 O-RVL: RV emailed Karim to inform him of the project covered under the SLA. END--- 01/17/19 O-RVL: RV emailed Karim to inform him of the project covered under the SLA. 01/15/19 O-RVL: Met with Monty on 1/15, Monty informed RV the work will be covered under the SLA agreement in support of Business operations. No estimate is required. RV to contact Karim with this information on 01/16/19. 01/14/19: O-RVL: Met with Dan L. onsite to review the project scope. RV & Dan also spoke with Louis about the process. RV will work on the estimate and submit to Karim & Louis by CBD 01/18/19. RV Has informed Dan L. the project is on the "Non Prioritized List". 01/11/19: O-RVL: Emailed Karim and informed him that he will receive an estimate later the following week. 01/07/19: O-RVL: Monty asked Enrico to look into the this project. I (RV) told Monty that I'm already involved and will complete the estimate. Monty agreed and asked RV to follow up with Karim. 12/21/18 O-RVL: Received a response from Bob W., stating "the area is suitable to be an office space understanding understanding that we must conduct a more in-depth review and approval process..." 12/20/18 O-RVL: Emailed Bob Williams with the existing and proposed floor plan asking if it would be suitable to create an office and requested a budget estimate to add a wall with a door. 12/20/18 O-RVL: Ron V. Visited site and spoke with Karim and viewed the proposed location for the new office. 12/18/19 O-RVL: Received email from D. Hughes on 12/18/18 to look into this request for estimate. | YES |  | FS | FALSE | 2018 | 2019-09-01
18P000414 |  | 18P000414 | FALSE | CHANCELLOR | SL5 CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL |  | STUDENT SERV | 0 | COMPLETE | Kim Wilcox | Karim Zahedi | DANIELLE GARCIA |  | Paul Ditty |  | 1 | 2 | FALSE |  |  | 2018-04-26 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000375 |  | 19P000375 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT HOLES |  | SKYE HALL | 365 | COMPLETE | Kim Wilcox | Karim Zahedi | FELECIA GARRETT |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-07 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000487 |  | 18P000487 | FALSE | CHANCELLOR | SL5 SKYE HALL PATCH HOLES AND PAINT |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | Karim Zahedi | SONIA ZAMORA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000420 |  | 19P000420 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT WALL |  | SKYE HALL | 325 | COMPLETE | Kim Wilcox | Karim Zahedi | REYNA ALARCON |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-19 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000122 |  | 19P000122 | FALSE | CHANCELLOR | SL5 REMOVE, PATCH & PAINT AND HANG |  | STUDENT SERV | 2222 | COMPLETE | Kim Wilcox | Karim Zahedi | CHRISTINE SMITH |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000297 |  | 18P000297 | FALSE | CHANCELLOR | SL5 SKYE HALL CHECK LOCATION FOR TV INSTALL |  | SKYE HALL | 390 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Dan Lerman |  | 4 | 3 | FALSE |  |  | 2018-02-02 | [6 empty] | 2/1/19, DL; This Project is 100% Complete………1/18/19, DL; This Project is scheduled to be complete next week.….. DL, 5/24/18; Need to verify scope with Enrico…..DL, 7/11/18; Work orders are produced and need to be issued. Target complete date is 9/3/18…. |  | Enrico Baez | EB-scoped on 1/30. Mount TV above table. Advised an articulated mount be purchased. Drawing on FAMMIS WO. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000389 |  | 18P000389 | FALSE | CHASS | SL5 PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A |  | PSYCHOLOGY1 | 2122 | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 5 | TRUE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000416 |  | 18P000416 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTOR OFFICE PAINTING |  | HUM & SOC SC | 3002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000415 |  | 18P000415 | FALSE | CHASS | SL5 PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | Door and frame have been painted; construction to commence upon availability of the teams. | OLMSTED | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | RYAN LIPINSKI |  | Dan Lerman |  |  | 10 | TRUE |  |  | 2018-05-08 | [6 empty] | 12/14/18, DL; Angel cancelled this project as it is no longer needed at this time……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 7/11/18; This project was scoped and part of the IRT. Plans and permits are approved. We will schedule the work and we will plan to have this project complet by 9/21/18…..8/10/18; WE have approved plans, this project is scheduled to start late August and will be complete early October……DL, 10/4/18; The door and frame is scheduled for delivery in 3-5 weeks, We will start the project when the doors and frame are on site……..DL, 11/7/18; Door and frame and painted. We will start the contruction in the near future…… |  | Dan Lerman |  | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-09-01
18P000445 |  | 18P000445 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 |  | ARTS | 225 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 11 | TRUE |  |  | 2018-05-21 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000367 |  | 18P000367 | FALSE | CHASS | SL5 CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE |  | CHASS INT N | 3033 | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 23 | FALSE |  |  | 2018-03-27 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000353 |  | 18P000353 | FALSE | CHASS | SL5 PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT |  | PSYCHOLOGY1 | 1111A | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 26 | FALSE |  |  | 2018-03-20 | [6 empty] | DL; 7/4/18;This project is scoped. We will only paint one out of the two offices. Working on PO# to install frosted glass with Sun Down Window coverings……DL, 7/25/18; PO# is produced and material is ordered. Target date mid August…….DL, 8/22/18; This project is complete.... |  | Paul Ditty |  | N/A | 2018-08-23 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000313 |  | 19P000313 | FALSE | CHASS | SL5 HUMANITIIES SOCSCI - PATCH HOLES & PAINT - |  | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000314 |  | 18P000314 | FALSE | CHASS | SL5 CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR |  | CA MUS PHOTO | 1000 | COMPLETE | Milagros Pena | Cindy Williams | EMILY PAPAVERO |  | Dan Lerman |  |  | 17 | FALSE |  |  | 2018-02-16 | [6 empty] | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date.......DL, 7/25/18; This project is 100% Complete..... |  | Enrico Baez | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date....... | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000344 |  | 18P000344 | FALSE | CHASS | SL5 CHASS INTS PAINT MULTIPLE ROOMS - FACULTY |  | CHASS INT S | 2117E | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 1 | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 7/11/18; This was transferd in to my quque in the past week. I need to scope this project. I belive this is part of project # 18P000205 and 18P000295. If this is part of the other project. We will try to have the paint completed by 8/17/18…......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/10/18; Work has started. We passed rough electrical and framing inspection. The work should be complete in about three weeks......DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18.......DL, 9/6/18; This Project is 100% Complete....... |  | Paul Ditty |  | N/A | 2018-09-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000294 |  | 18P000294 | FALSE | CHASS | SL5 HMSS REMOVE DOOR, INSTALL WALL |  | HUM & SOC SC | 3610 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2018-02-01 | [8 empty] | Enrico Baez | Canceled per customer on 7/16/18 via email with Enrico. 5/23/18 EB sent email request for site visit DND 7/14 Hold per customer on prioritization | YES | 2018-07-16 | FS | FALSE | 2018 | 2019-09-01
19P000056 |  | 19P000056 | FALSE | CHASS | SL5 HMSS CAPABILITY OF MOUNTING A TV |  | HUM & SOC SC | 1212 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  |  | 18 | FALSE |  |  | 2017-10-03 | [6 empty] | 12/14/18, DL; Monitor is complete. Still need to work on electrical……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope with Enrico and schedule the work…. Work orders are not produced. Need to assign and schedule the work DND 7/30/18: Closed work order #18W004822; created project #19P000056……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | EB 3/26-Project scoped on 10/23/17. Attached 5 photos and made annotations to FAMIS. | YES | 2018-12-14 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18W016588 |  | 18W016588 | FALSE | CHASS | PATCH AND PAINT FOR FACULTY |  | SPROUL | 4105 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | N/A | TRUE |  |  | 2018-06-19 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000318 |  | 18P000318 | FALSE | CHASS | SL5 CHASS INT S FLAT SCREEN INSTALLATION |  | CHASS INT S |  | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Dan Lerman |  |  | 20 | FALSE |  |  | 2018-02-21 | [6 empty] | 4/15/19, DL; This is 100% Complete….3/28/19, DL; Monitor is installed. Need to finishe power and data next week……2/28/19, DL; Scheduled to complete the install mid March…..2/1/19, DL; Francesca contacted me and informed me this project is now back on the books. She needs to gather more information and order the monitor. When the monitor arrives, we will schedule the installation…….1/29/19, DL; Francesca confirmed this project is not needed and requested this project to be cencelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; we have the brackets. Will scheule the work after the project is approved…..DL, 7/11/18; Work order are not produced. Need to assign and schedule the work…. Target complete date is 8/3/18……DL; 7/25/18; Need to change target date.. |  | Enrico Baez | 5/24/18 Conducted site visit. Met with Ryan Amriano. Electrical near buy. No data connection needed. Awaiting for dept. approval. They first wanted to know if this was possible. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000417 |  | 18P000417 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTIONAL OFFICE PAINTING |  | HUM & SOC SC | 2106 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000364 |  | 19P000364 | FALSE | CHASS | SL5 PATCH AND PAINT |  | CHASS INT S | 3106 | COMPLETE | Milagros Pena | Cindy Williams | FRANCESCA MOREIRA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-30 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2019-03-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000387 |  | 18P000387 | FALSE | CHASS | SL5 HMSS PATCH/PAINT |  | HUM & SOC SC | 3600 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 28 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000300 |  | 18P000300 | FALSE | CHASS | SL5 ARTS PATCH AND PAINT - DANCE HALLWAYS |  | ARTS |  | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 24 | FALSE |  |  | 2018-02-02 | [6 empty] | centered. |  | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000295 |  | 18P000295 | FALSE | CHASS | SL5 CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL |  | CHASS INT S | 2117J | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-02-01 | [6 empty] | DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18……..DL, 5/24/18; Plans were approved. We need to scheudle the work….DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets.......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date.....DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18...........DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware..... |  | Enrico Baez | 4/25 EB Scoped site. Remove counter and Cage. Drywal closed with electrical. Patch Paint. Cut in two doors in 2117G&H……..DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18…….. | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18W001170 |  | 18W001170 | FALSE | CHASS | SL5 ARTS: PAINT CLASSROOMS |  | ARTS | 407 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 27 | FALSE |  |  | 2017-07-25 | [8 empty] | Enrico Baez | DD 10/6: Enrico scoped; requested during break - coordinating with client to complete on a Saturday | YES | 2018-09-24 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000205 |  | 18P000205 | FALSE | CHASS | SL5 CHASS INT S CREATE DOOR |  | CHASS INT S | 2117H | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-11-27 | [6 empty] | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18……DL, 5/24/18; Plans were approved. WE need to schedule the work…..DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18...........DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... .. DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date..........DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18............DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware.....DL, 9/19/18; This Project is 100% Complete...... |  | Enrico Baez | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18…… | YES | 2018-09-21 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
19P000253 |  | 19P000253 | FALSE | CHASS | SL5 ARTS RENOVATION |  | ARTS | 157 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 16 | FALSE |  |  | 2018-04-17 | [6 empty] | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access……DL, 7/11/18; This project needs to be complete before Fall 2018. Space is vacant and ready go. Need to walk and confirm Schdule with Paul D. Tony's Flooring is ready to go after paint is complete.... Target complete date is 9/21/18......DL, 8/22/18; Walked with PAul, Paul will scheudle the work. Jess still need to cordinate with Tony's Flooring .....DL, 9/19/18; The paint and flooring is complete. The seams need to be welded and this will be complete. this will be complete by 9/21/18......9/19/21; This Project is 100% Complete....... |  | Dan Lerman | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000396 |  | 18P000396 | FALSE | CHASS | SL5 WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | Please patch and paint these two Political Science Staff Offices in the Watkins Hall 2122 "suite". 2122A belongs to Tanya Wine, FAO; 2122D belongs to Cindy Redfield, Principal Analyst. | WATKINS | 2122 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS | CINDY REDFIELD | Paul Ditty |  |  |  | TRUE |  |  | 2018-04-13 | [6 empty] | 08/10/18 D-MMN: Completed painting the finish. Pulled our masking and plastic wiped down the furniture. Replaced fixture covers. vacuumed the carpets and moved furniture back.08/07/18 D-MMN: Removed anchors, related boards. Filled holes with spackle and topped with joint compound. used one 4x4 wall patch. Returned and applied second coat of joint compound. 08/09/18 D-MMN: Completed applying primer, and then began applying Suprema. 08/08/18 D-MMN: Removed steel case and file cabinets from walls. Pulled anchors and filled with smooth se 20 and 2 coats of joint compound. Also finished any other patching. Taped the base and fixtures and covered furniture with plastic. Used a fan to dry patching. Sanded patches and began primer. Vacuumed debris. |  | Paul Ditty | Complete as of 8/24/18 **7/30/18 ROUTED TO D-PDY FOR SUMMER QUARTER MINOR RENO EXECUTION; PRIORITY 6 AND FOR FACULTY HIRE "YES" (Stephen C) | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000111 |  | 18P000111 | FALSE | CHASS | SL5 KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 |  | CHASS INT S |  | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Jason Williams |  |  |  | FALSE |  |  | 2017-09-15 | [6 empty] | EB 1/31/18 Work was assigned to lock shop 12/7/17…. DND 5/11: Spoke with Jason, all work complete to be completed as trade is available. Only work remaining is on 3150 A; Jason short staffed to finish project but it's on his radar. 07/13/18 H-FMS: Troubleshoot programming and settings for this controller. Clear all data from panel and reset, perform required downloads, re-test and verify both doors working correctly. |  | Enrico Baez | EB 1/31/18 Work was assigned to lock shop 12/7/17 | YES | 2018-07-13 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000383 |  | 18P000383 | FALSE | CHASS | SL5 HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT |  | HUM & SOC SC | 1302 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  | 4 | TRUE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000420 |  | 18P000420 | FALSE | CHASS | SL5 COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | Canceled by Customer on prioritization 7/2/18 | WATKINS | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  |  |  |  | Cancel | TRUE |  |  | 2018-04-27 | [10 empty] | YES | 2018-07-02 | FS | FALSE | 2018 | 2019-09-01
18P000201 |  | 18P000201 | FALSE | CHASS | SL5 ARTS REMOVE COUNTERTOP/SHELVES |  | ARTS | 0106A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 3 | TRUE |  |  | 2017-11-21 | [6 empty] | DL, 6/16/18; Ned to walk, scope and submit plans ASAP…..Sent Paul an email requesting information on Status of Faculty hire status……DL, 7/11/18; Paul is on Jury Duty and he said he should return back to work next week. Current Targe complete date is mid September......DL, 7/25/18; Carpentery and Electrical is complete. Patch and paint has started. Target complete date is 8/3/18......DL, 8/8/18; Space is VAcant and ready for paint. The paint department is working on several other projects that require their attention. The paint department will complete the work in the near future......DL, 8/22/18; This Project is 100% Complete....... |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS……DL, 4/29/18; Pasted from wo;remove the existing countertop and shelves that are built into the room. Follow with patch and paint of entire space. | YES | 2018-08-23 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000468 |  | 18P000468 | FALSE | CHASS | SL5 WATKINS 1222/1223 PATCH/PAINT |  | WATKINS | 1222 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 13 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000469 |  | 18P000469 | FALSE | CHASS | SL5 WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS |  | WATKINS | 1317 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | 2018-07-25 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000418 |  | 18P000418 | FALSE | CHASS | SL5 HMSS OFFICE PAINTING |  | HUM & SOC SC | 2002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 15 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty | 5/23/18 EB- Sent email to Jill requesting site visit. 5/23/ 18 EB- Scoped. Mount & TV on site. TV bottom edge to be mouted 48" from floor centered on West wall. Needs electrcal cut out and data. Entered in FAMIS. | N/A | 2018-07-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000220 |  | 19P000220 | FALSE | CHASS | SL5 ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT |  | ARTS | 333 | COMPLETE | Milagros Pena | Cindy Williams | SONJA SEKELY-ROWLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 12/14/18, DL; This project is 100% Complete….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/8/18; Screeen is scheduled to be removed this Friday. We will schedule the installation and the patch / Paint repairs once we receive the repaired screen back from the vendor…….DL, 11/7/18; This project should already be complete. However, The vnedor did not deliver the correct screen. The correct screen is currently scheduled for this Friday..... |  | Enrico Baez | 8/27/18 EB-Remove 12' wide screen from finished ceiling. Need electricians to diconnect power, carpenters to remove drywall and lower screen. Repared screen to be re-hung by carpenters and drywall repaired. Electricians to reconnect power. Painters to patch and paint. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000361 |  | 19P000361 | FALSE | CHASS | SL5 OLMSTED-PATCH & PAINT/REPLACE CARPET |  | OLMSTED |  | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 05/29/19 O-ANS: Project completed 05/09/19 per Paul Ditty. |  | Paul Ditty | N/A | N/A | 2019-05-09 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000575 |  | 19P000575 | FALSE | CHASS | SL5 WATKINS HALL PAINT/FLOORING |  | WATKINS | 1309A | QUEUE TO START | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-17 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000337 |  | 19P000337 | FALSE | CHASS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | Remove whiteboard (in front of room), mount LED mount, add double duplex and electrical power behind LED, patch and paint wall | PSYCHOLOGY1 | 3210 | IN PROGRESS | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 1 | 101 | FALSE |  |  | 2018-10-11 | [6 empty] | 9/3/19, DL; Space is blocked and schedculed to be completed by 9/27/19…..8/14/19, DL; Conducted site visit with Trades. We will schedule the space to be blocked out and start the work mid September….8/1/19, DL; Planning to start this project in two weeks……7/15/19, DL; I will walk the project in the near future and schedule the work if permits are not required…… | 2019-01-15 | Enrico Baez | 1/15/2019 E Baez please Scope completed 1/15/2019 see Shared drive file for more information. | YES |  | FS | FALSE | 2018 | 2019-09-01
18P000481 |  | 18P000481 | FALSE | CHASS | SL5 CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 |  | CHASS INT S | 3104 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000606 |  | 19P000606 | FALSE | CHASS | SL5 PAINT ROOM |  | WATKINS | 1213 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 06/14/19 O-ANS: Stephen spoke with customer Becky Campbell via phone who confirmed that project was going to be canceled due to re-allocation of space by another dept. |  |  | Canceled by client 6/14/19 |  | 2019-06-14 | FS | FALSE | 2019 | 2019-09-01
19P000378 |  | 19P000378 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 |  | HUM & SOC SC | 1613 | COMPLETE | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-11-13 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000400 |  | 19P000400 | FALSE | CHASS | SL5 CREATE DOOR INTO HALLWAY | Create a door between the hallway and CHASS INTS 2117A. The door should be placed at the south end of 2117A. | CHASS INT S | 2117A | CANCELED BY FS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 103 |  | FALSE |  |  | 2018-12-06 | [6 empty] | 05/21/19 O-ANS: Canceled by FS per conversation with Paul Richardson and combined with Project 19P000419. | 2019-04-15 | Enrico Baez | 4/18/19 E. Baez-Emailed Paul, Monty and Chris P. The project is requested in conjunction with Project 19P000419 (keyless entry in various offices within 2117). Both projects will need to be considered one project as work is requested for same area. Waiting for HCI to submit proposal. 4/15/19 E. Baez- Conducted site visit with Paul Richardson. Request is for separate entrance from hall to 2117A. Offered two possibilities and forwarded to Paul. Waiting for response. Will need detailed scope. | YES | 2019-05-21 | FS | FALSE | 2018 | 2019-09-01
19P000306 |  | 19P000306 | FALSE | CHASS | SL5 HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 |  | CHASS INT N | 4017 | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-01 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19W002930 |  | 19W002930 | FALSE | CHASS | HOLD - SL5 PATCH HOLES & PAINT - HUMANITIIES SOCSCI |  | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-08-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000585 |  | 19P000585 | FALSE | CHASS | SL5 HUMANITIES SS, RM 3604- PATCH/PAINT WEST WALL |  | HUM & SOC SC | 3604 | COMPLETE | Milagros Pena | Cindy Williams | DARA CERDA |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-04-19 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000355 |  | 19P000355 | FALSE | CHASS | SL5 HYDRATION STATION FOR THE SECOND FLOOR WATKINS | Hydration station installed where the water fountain is. | WATKINS | 2122D | CANCELED BY FS | Milagros Pena | Cindy Williams | CYNTHIA REDFIELD |  | Dan Lerman |  | 112 |  | FALSE |  |  | 2018-10-22 | [8 empty] | Enrico Baez | 4/24/19 LB: Per Ron Rector, hydration stations in common areas will be scheduled by FS. Project canceled. ~ 10/22/18 SC: Called Cynthia to clarify that this would be a project. Also asked if she wanted the water fountain checked out in the meantime since it seems to be stinking. She will put in a separate WO for this issue. |  | 2019-04-24 | FS | FALSE | 2018 | 2019-09-01
19P000603 |  | 19P000603 | FALSE | CHASS | SL5 CHASS INT N, RM 3046- PATCH AND PAINT - NEW FACULTY OFFICE |  | CHASS INT N | 3046 | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  | 12 |  | TRUE |  |  | 2019-05-10 | [6 empty] | 06/18/19 O-ANS: Project complete per updates. 06/15/19 D-MMN: Painted remaining finish. Pulled masking and plastic. Replaced plates and vacuumed. |  |  |  |  | 2019-06-18 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000195 |  | 19P000195 | FALSE | CHASS | SL5 HUM & SOC SC-ROOM PAINTING |  | HUM & SOC SC | 2003 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000640 |  | 19P000640 | FALSE | CHASS | SL5 NEW FACULTY - PATCH & PAINT SPROUL 3108 |  | SPROUL | 3108 | COMPLETE | Milagros Pena | Cindy Williams | MELISA VICARIO |  | Paul Ditty |  | 13 |  | TRUE |  |  | 2019-05-20 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000216 |  | 19P000216 | FALSE | CHASS | SL5 HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT |  | HUM & SOC SC | 1214 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-08-27 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000221 |  | 19P000221 | FALSE | CHASS | SL5 PATCH, PAINTING, AND REGULAR CLEANING OF A126A |  | OLMSTED | A0126A | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000643 |  | 19P000643 | FALSE | CHASS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH |  | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2019-05-21 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
19P000196 |  | 19P000196 | FALSE | CHASS | SL5 PAINT OFFICE AT UNIVERSITY THEATER |  | THTR WKSH |  | COMPLETE | Milagros Pena | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000171 |  | 19P000171 | FALSE | CHASS | SL5 HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST |  | HUM & SOC SC | 1614 | COMPLETE | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 16 |  | FALSE |  |  | 2018-08-09 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18W016621 |  | 18W016621 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2018-06-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000201 |  | 19P000201 | FALSE | CHASS | SL5 PATCH AND PAINT THE WALLS |  | CHASS INT S | 3111A | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 18 |  | FALSE |  |  | 2018-08-22 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000385 |  | 18P000385 | FALSE | CHASS | SL5 HMSS INSTALL TV IN CONFERENCE ROOM |  | HUM & SOC SC | 1001E | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Dan Lerman |  | 19 | 19 | FALSE |  |  | 2018-03-06 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..12/14/18; Monitor is Complete, we still need to install power. The space is vacant…DL, 6/16/18; Pasted notes from FAMIS; University Writing program wants to install a 65 inch TV in the conference room at HMNSS 1001E. 1. Request to install the TV mount/ bracket on the wall; 2. Request to remove the old projector screen but leave two wood blocks on the wall; 3. Request to add a new double power outlet around the TV bracket area. If you have any questions, please contact Shanshan Liao at (shanshan.liao@ucr.edu or X27753)……DL, 7/25/18; Work orders are not produced. Need to assign and schedule the work…..……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | 6/11/18 Install TV above wainscot. Notes in FAMMIS. Need electrical and date cut ins. | YES | 2019-03-18 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000607 |  | 19P000607 | FALSE | CHASS | SL5 PAINT FACULTY OFFICE |  | WATKINS | 1312 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2019-05-10 | [6 empty] | 08/26/19: Canceled by customer because duplicate of project 20P000044. 08/13/19 O-ANS: Customer scope of work includes more than just PAINT so project added to Fall 2019 list for prioritization by organization. 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-09-01
19P000362 |  | 19P000362 | FALSE | CHASS | SL5 PATCH & PAINT/REPLACE CARPET (HALLWAY) |  | OLMSTED |  | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000419 |  | 19P000419 | FALSE | CHASS | SL5 CHASS INT SOUTH 2117-CARD ACCESS | Remove Door and wall leading to 2117 Media Library and reconfigure to allow enterance into 2117 A & J without having to go through 2117C. | CHASS INT S | 2117 | IN PROGRESS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 9/3/19, DL; We started this project today. We are planning to be 90% complete by 9/27/19. Note, we have special order doors that have a 4-6 week lead time and that is the reason why we will be only 90% complete on 9/27/19. Paul Richardson is aware of the schedule…….8/15/19, DL; The plans were approved this week, we will order the needed material and start the work very soon…….This is a two part project. We will complete the construction process now. The four doors that need key card access still require a request for proposal and a contract. This portion of the project will take 3- months due to contracts administartion, lead time on material and contractor scheduling…….8/1/19, DL; Gunther is working on plans. Once permit is approved, we will scheudle the work…. | 2019-03-21 | Enrico Baez | 7/1/2019 E. Baez- Met with HCI on 6/28/2019, conducted job walk. Waiting for proposal. 4/18/19 E. Baez-Emailed Paul, Monty and Chris P. The project is requested in conjunction with Project 19P000400 ( moving walls and creating separate entry into 2117A). Both projects will need to be considered one project as work is requested for same area. 4/2/19 E. Baez- conducted job walk with HCI for proposal. Waiting for proposal. ***per Paul Richardson remove 2117G, 2117H and 2117J from request*** 3/19/19 E. Baez Scheduled site visit with Paul for 3/21/19 @ 11:00 ***3/19/19: O-ANS: Customer SOFT PRIORITIZED as priority 102.* | YES |  | FS | FALSE | 2018 | 2019-09-01
18W008762 |  | 18W008762 | FALSE | CHASS | SL5 HUMANITIES: PATCH & PAINT |  | HUM & SOC SC | 2415 | COMPLETE | Milagros Pena | Cindy Williams | ANDREW ALONSO |  | Paul Ditty |  | 20 | 22 | FALSE |  |  | 2018-01-02 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000126 |  | 18P000126 | FALSE | CHASS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS |  | HUM & SOC SC | 3611 | COMPLETE | Milagros Pena | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 2017-09-28 | [6 empty] | 7/1/19,DL; This project is 100% Complete…..5/15/19, DL; Work is scheduled to start on 6/19/19…….5/1/19, DL; Plans are approved. Need to order material and schedule the work…..3/18/19, DL; Plans submitted to PD&C today…..02/2819, DL; Gunther will work on plans over the next three weeks to submit for a building permit. We will schedule the work if and after the plans are approved. If approved the door and window will more than likely have a 3- month lead time…………….12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS. Remove double doors and install single door.Remove small West wall. Relocate t-stat. Ceiling work. Replace carpeting. | YES | 2019-07-01 | FS | FALSE | 2017 | 2019-09-01 | FY 19-20
18P000343 |  | 18P000343 | FALSE | CHASS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER |  | THTR WKSH | 0400A | IN PROGRESS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 2018-03-16 | [6 empty] | 07/11/19 O-ANS: Dan and Chris P will walk the space. 05/21/19 O-ANS: Changed to In Progress per meeting with Dan L. Chris P is the PM for further updates. DL and CP will visit after commencement. 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez | Scope of work has been reviewed; determining how to complete project with trades. 5/11/18 EB-Conducted site visit on 3/21/18. Work based on Safety report written in October. Work consists of replacing door latches to orchestra pit. Adding loading dock rail, Paint frame guard, signage, gate/fall restraints, ladder modifications. | YES |  | FS | FALSE | 2018 | 2019-09-01
19P000173 |  | 19P000173 | FALSE | CHASS | SL5 PAINT/PATCH UNIVERSITY THEATER LOBBY |  | THTR WKSH | 0400A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000356 |  | 19P000356 | FALSE | CHASS | SL5 PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT |  | HUM & SOC SC | 4401 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-24 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000063 |  | 19P000063 | FALSE | CHASS | SL5 NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS |  | PSYCHOLOGY1 | 2124 | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-07-31 | [8 empty] | Paul Ditty | 9/13/18 EB this is a request for patch, paint and new carpet | NO | 2018-09-26 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000574 |  | 19P000574 | FALSE | CHASS | SL5 FACULTY OFFICE PAINTING |  | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | QUEUE TO START | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-04-12 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000415 |  | 19P000415 | FALSE | CHASS | SL5 PSYCHOLOGY -PSY BLDG- MINOR RENOVATION | Doorway with side window connecting 2124C to 2124B, as well as another doorway to connect 2124C to 2124D. | PSYCHOLOGY1 | 2124A,B,C,D | IN PROGRESS | Milagros Pena | Cindy Williams | Jay Melashenko |  | Dan Lerman |  | 3 | 2 | FALSE |  |  | 2018-12-17 | [6 empty] | 9/3/19, DL; The project is 90% Complete. We will be 100% Complete by mid September…….8/15/19, DL; This project is in progress and schedule for complete in the next 4- weeks…….8/1/19, DL; Gunter is working on Plans. Plan to submit plans for building permit in two weeks. Once plans are approved, we will schedule the work….. | 2019-01-09 | Dan Lerman | 12/14/18 E.Baez-Met with Jay Melashenko. Suggested the possibility of cutting wall open in 2124D and 2124B both leading to 2124C. No doors to be installed. Only finish opening. Install a low rise threshold at new opening, new carpet recently installed. Need to move outlets. Customer to pay for work. | YES |  | FS | FALSE | 2018 | 2019-09-01
19P000605 |  | 19P000605 | FALSE | CHASS | SL5 PAINT NEW MAILROOM |  | WATKINS | 1320E | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-09-01
19P000350 |  | 19P000350 | FALSE | CHASS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | MISC WORK IN ROOMS 3121 AND 1133 Patch and paint-relocate white boards, hang pictures. | PSYCHOLOGY1 | 3121, 1133 | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 4 | 3 | TRUE |  |  | 2018-10-17 | [6 empty] | 8/15/19, DL; This Project is 100% Complete…….. 8/1/19, DL; We will start this project this Friday…… 7/15/19, DL; Appears not plans and permits will be required for the work. I will verify and schedule the work in the near future if no plans or permits are required….. | 2019-04-15 | Enrico Baez | 4/11/19 E.Baez emailed Toya Adams to schedule site visit | YES |  | FS | FALSE | 2018 | 2019-09-01
19P000609 |  | 19P000609 | FALSE | CHASS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR |  | WATKINS | 1229 | IN PROGRESS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 07/03/19 O-ANS: Paint phase complete and awaiting flooring change. 06/21/19 O-ANS: Customer requested to remove lighting change from project and only complete paint and carpeting via email to Paul Ditty (copied email below). Will create separate work order for lighting. Re-assigned to Paul Ditty to complete. "From: Becky L Campbell <becky.campbell@ucr.edu> Sent: Friday, June 21, 2019 10:51 AM In regards of the work order: 19P000609 - SL5 - PAINT FACULTY OFFICE – please cancel the connecting Work Order 19W015231 – REPLACING THE LIGHTING IN WATKINS 1229. Please do paint and replace flooring.For the lighting, please create new work order to be done at a later time." |  | Paul Ditty | Awaiting installation of new flooring |  |  | FS | FALSE | 2019 | 2019-09-01
19P000371 |  | 19P000371 | FALSE | CHASS | SL5 URGENT PATCH AND PAINT IN CHAIR'S OFFICE |  | HUM & SOC SC | 1213 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-11-05 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000011 |  | 19P000011 | FALSE | CHASS | SL5 PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED |  | PSYCHOLOGY1 | 2111A | COMPLETE | Milagros Pena | Cindy Williams | LORENA QUINTANA |  | Paul Ditty |  | 4 |  | TRUE |  |  | 2018-07-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000604 |  | 19P000604 | FALSE | CHASS | SL5 HUMANITIES SS, RM 7704- PAINT OFFICE BY JULY 1, 2019 |  | HUM & SOC SC | 7704 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
18P000419 |  | 18P000419 | FALSE | CHASS | SL5 COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | FS to coordinate with client to scope the work. | WATKINS | 1320C&E | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 5 | 8 | TRUE |  |  | 2018-04-27 | [6 empty] | 2/14/19,DL; This project was canceled by Paul R. 2/1/19, DL; We will custom make Sound panels and will start the installation in the next 6-8 Weeks……….. |  | Enrico Baez | 7/6/18 EB emailed Paul Richardson to schedule site visit 7/17/18 EB Scheduling site visit with Paul R. 8/7/18 EB-Job was part of an IRT. Dan said he will scope 8/20/18 EB emailed Lilia to schedule site visit. 8/24/18 EB scheduled site visit for 8/28/18 at 11:00AM 8/28/18 E.Baez- Met with Paul Richardson, Lilia Vega and Becky Campbell. Instead of tearing down walls and building new ones, they wanted to see if installing sound soak on three walls were possible, it is. They will then need to have their Dean approve the sound soak. Clients were sent an email with drawing indicating desired location of sound soak. | NO | 2019-02-14 | FS | FALSE | 2018 | 2019-09-01
19P000357 |  | 19P000357 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS, TIME SENSITIVE |  | HUM & SOC SC | 1302 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-10-25 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000421 |  | 19P000421 | FALSE | CHASS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | Install door to access hallway directly | OLMSTED | 2139I | PLAN DEVELOPMENT/CHECK | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 5 | 110 | TRUE |  |  | 2018-12-19 | [6 empty] | 9/3/19, DL; Plans are at 50%, We will try and have plans to submit for review within the next two weeks…… | 2019-02-05 | Enrico Baez |  | YES |  | FS | FALSE | 2018 | 2019-09-01
19P000642 |  | 19P000642 | FALSE | CHASS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM |  | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-05-21 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
18P000444 |  | 18P000444 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 |  | ARTS | 242 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-05-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-09-21 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000314 |  | 19P000314 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000207 |  | 19P000207 | FALSE | CHASS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-08-23 | [6 empty] | 8/1/19, DL: This project is 100% Complete……7/15/19, DL; Floor covering will be installed next week. Floor covering is the last item for this project……..7/1/19, DL; This project is 95% complete except floor covering. Floor covering will be installed within 2- weeks……6/17/19, DL; This project is making good progress. We should be complete near July 1st…….5/31/19, DL; This project started this week and should be complete by June 28th…….3/18/19, DL; Working on plans and we will submit our plans and permit application this week….. | 2018-09-20 | Enrico Baez | 9/20/18 EB-Conducted site visit. Request to remove window in hall and install door. Interior space walls not to be removed. Secure doors, blank off and cover with sound soak. Replace carpet with Vinyl Plank, patch and paint. ---9/19/18 EB-Site visit scheduled for 9/20/18.---9/13/18 EB emailed Toya Adams to schedule site visit. | YES |  | FS | FALSE | 2018 | 2019-09-01
19P000552 |  | 19P000552 | FALSE | CHASS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS |  | HUM & SOC SC | 1001 B, C, and D | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-03-27 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
19P000300 |  | 19P000300 | FALSE | CHASS | SL5 HUM & SOC SC--URGENT: PAINT AND PATCH WALLS |  | HUM & SOC SC | 4403 | COMPLETE | Milagros Pena | Cindy Williams | ANDREA HERAZ |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000589 |  | 19P000589 | FALSE | CHASS | SL5 HMSS OFFICE 3405 RENOVATIONS | Construct partion, pending CBO approval, in room 3405. | HUM & SOC SC | 3405 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2019-04-23 | [6 empty] | 9/3/19, DL; We are ready to start the work. The PI returned to work this week. I sent Paul R. an email letting him know we are available to start once we have confirmed dates from him…..8/15/19, DL; Plans are approved but the PI is not. We will probably start the project the 2nd week in September…… | 2019-06-27 | Enrico Baez |  | YES |  | FS | FALSE | 2019 | 2019-09-01
19P000448 |  | 19P000448 | FALSE | CHASS | SL5 ARTS 333- PATCH AND PAINT |  | ARTS | 333 | QUEUE TO START | Milagros Pena | Cindy Williams | SONJA SEKELY-ROWLAND |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-01-14 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000286 |  | 19P000286 | FALSE | CHASS | SL5 FACULTY OFFICES: TOUCH UP PAINT |  | HUM & SOC SC | 2005 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-09-17 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000194 |  | 19P000194 | FALSE | CHASS | SL5 PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 |  | HUM & SOC SC | 3304 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000061 |  | 19P000061 | FALSE | CHASS | SL5 PSYCHOLOGY 1111H-PATCH HOLES IN WALL |  | PSYCHOLOGY1 | 1111H | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000540 |  | 19P000540 | FALSE | CHASS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | Remove metal roll up window, replace carpet, remove round column cover-reframe square. | HUM & SOC SC | 1202 | PLAN DEVELOPMENT/CHECK | Milagros Pena | Cindy Williams | JENNIFER MORGAN |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2019-03-20 | [6 empty] | 8/15/19, DL; Gunter has the project on his list. We will try and be ready for plan check review in the next two weeks…….. | 2019-07-25 | Enrico Baez | Ref: CP3514; Notes on project request in FAMIS and Shared drive. | YES |  | FS | FALSE | 2019 | 2019-09-01
19P000608 |  | 19P000608 | FALSE | CHASS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE |  | WATKINS | 1345 | QUEUE TO START | Milagros Pena | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-05-10 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000429 |  | 19P000429 | FALSE | CHASS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | Patch & Paint | COLL BLDG SO | 103 | COMPLETE | Milagros Pena | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-01-03 | [6 empty] | 07/26/19 O-ANS: Project complete per Paul Ditty. 06/06/19 O-ANS: Project scheduled to be completed. |  |  |  |  | 2019-07-26 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
19P000226 |  | 19P000226 | FALSE | CHASS | SL5 PAINT OFFICE HMNSS 3304 |  | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-08-28 | [8 empty] | Paul Ditty | Duplicate request; project to be completed on 19P000194 |  | 2018-10-01 | FS | FALSE | 2018 | 2019-09-01
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On-hold/Funding | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
3535 | 3535 |  | FALSE | CHASS | Watkins 1311 Renovation | This request is for a new faculty hire. -Remove north countertop and sink. Install stainless counter and two sinks. -Install eye wash station -Install laminate flooring, remove existing. (Abatement) -Paint space to campus interior standard. -Remove east counter and replace with stainless. -Remove fume hood, discard. -Install new fume hood. |  | 1311 | New location LS-452 determined, fume hood installation | Milagros Pena | Cindy Williams | Paul Richardson |  | Jason Espinoza | 3 |  |  | FALSE |  |  | 2019-07-10 | Bidding | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3060 | 3060 |  | FALSE | CHASS | CHASS Intl N. - Paint 3rd Floor | Paint and patch the following CHASS INTN rooms to existing color: 3036 3038 3042 3046 3050 3049 3047 3033 3033B 3025 3021 3019 3015 3013 3011 3002 3008 3012 3014 3016 3018 3020 3022 Hallway outside of 3033 Hallway to main entrance to floor Hallway outside 3005 | CHASS INT N |  | Project on Hold | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 4 |  |  | FALSE | 0 |  | 2016-05-20 | On Hold | [11 empty] | PD&C | FALSE | 2016 | 2019-09-01
3469 | 3469 |  | FALSE | CHASS | Carillon Repair & Maintenance | Design, fabrication and replacement of bell beams for bells 24, 26, 28, 30 and 32. Design, fabrication and installation of bracing to brace the 5 other bells beams that are cracking, and corrective maintenance on the clappers & head pieces-this would include complete removal, cleaning, reaming, bushing and lubricating before re-installing and clean and lubricate the transmission system as much as possible without complete disassembly to make the instrument easier to play. | BELLTOWER |  | Need to secure funding | Milagros Pena | Cindy Williams | Reasey Heang |  | Daneca Stevens | 5 |  |  | FALSE | 10000 |  | 2018-08-16 | Secure Funding | 2019-09-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use |  |  | In Funding | Milagros Pena | Cindy Williams | Anna Finn |  | Daneca Stevens | 15 |  |  | FALSE | 0 |  | 2018-06-22 | Design | 2020-01-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
18P000118 |  | 18P000118 | FALSE | CNAS | SL5 OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT |  | OLMSTED | 1337 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2017-09-20 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space.......DL, 6/16/18. New staff member schedule to start mid july. BKM is also scheduled for mid july. This project will require cabinets to be removed, new carpet, paint and blank out electrical outlets that will no longer be used.. new signage too.....DL, 7/11/18;This project is in progress. Complete date is 7/20/18......DL, 7/25/18; This project is 100% Complete....... |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space. | YES | 2018-07-25 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
19P000213 |  | 19P000213 | FALSE | CNAS | SL5 NEEDS FOR NEW WALL DISPLAY (MONITOR) | Duplicate request to 19P000031; Work to be completed on other project. | BIOLOGICAL SCI | 3101 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [11 empty] | 2018-10-01 | FS | FALSE | 2018 | 2019-09-01
18W000455 |  | 18W000455 | FALSE | CNAS | SL5 CHAPMAN CLEAN WINDOWS |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  | 37 | FALSE |  |  | 2017-07-11 | [6 empty] | Dl, 7/4/18; All Windows in Chapman were cleaned by Ductch Touch. This Project is 100% Complete |  | Ron Veloz |  | YES | 2018-07-11 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000256 |  | 18P000256 | FALSE | CNAS | SL5 BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES |  | BOYCE | 3451 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave at Webber is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place.......DL, 5/9/18; Autoclave is destroyed. Pictures were sent to Cheryl. We are now waiting for the equipment to arrive. Steve B is working on Steam connection at Boyce......DL, 5/24/18; Autoclaves arrived. Day crew is scheduled to deliver the unit on 5/30/18. we will schule the plumbers and electricians shortly there after......DL, 6/16/18; Webber Autoclave is almost complete. This portion should be complete next week. WE will run the Webbber autoclave for two weeks before we start the Boyce Autoclave. The weldolet for the BOyce unit will be installed during the steam shutdown...... DL, 7/11/18; Webber Auto clave will be complete on 7/12/18. We will start the demo of the Boyce Auto clave next soon. Target date for this project is 8/10/18...... DL, 7/25/18; We had a delay with the Webber autoclave which will implact the Boyce Auto clave. New target complete date is 8/22/18.....DL, Plumbing is almost complete, need to schedule final elctrical and Commission equipment. Target date 8/31/18...... DL, 9/6/18; This project should be complete but we still need to schedule the electrical connections ASAP.........DL, 9/19/18; This project is 100% Complete. |  | Dan Lerman | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place | YES | 2018-09-21 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000247 |  | 18P000247 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 |  | PHYSICS | 3023 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  |  | 15 | FALSE |  |  | 2017-12-20 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18W011161 |  | 18W011161 | FALSE | CNAS | SL5 REPLACE CARPET |  | SCIENCE LAB1 | 301 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-23 | [6 empty] | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project……DL, 5/21/18; Floor covering is selected. Work will be scheudled for Mid June….DL, 5/24/18; The install is scheduled for June 18th & 19th……DL, 7/11/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project…… | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000227 |  | 18P000227 | FALSE | CNAS | SL5 BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL |  | BATCHELOR | 4128 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-12-12 | [6 empty] | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM.......DL, 5/24/18; Need to work on plans and permits. Project needs to be complete before Fall academic 2018.....DL, 6/16/18; Walked project with Jess. and he will schedule the abatment. We will not need plans for this project. We are not removing the exhasut hood which was the original purpose foor the plans......Carpenters started the demo. Still need to remove TSI. Once TSI is removed, we can schedule the plumbing work. Target Complete Date is 9/21/18....DL, 8/10/18; Abatement is scheduled for this weekend, we will start work soon.....DL, 8/22/18; Abatement and most demo complete. Still on track for 9/21/18.....DL, 9/19/18; Scope change. This project should be complete on 9/28/18.......DL, 10/4/18; Floor to be installed this Friday. Pianters will finalized the stain on the cabinets. Thsi project should be complete near 10/19/18.......Dl, 11/7/18; This project is 100% complete.... |  | Dan Lerman | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM....... | YES | 2018-11-08 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18W011672 |  | 18W011672 | FALSE | CNAS | SL5 ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY |  | ENTOMOLOGY | 268 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-03-08 | [6 empty] | Relocate white board from East wall onto the West wall, where high table was removed, 24" away from North end of wall. |  | Paul Ditty |  | N/A | 2018-07-25 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000392 |  | 18P000392 | FALSE | CNAS | SL5 BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 |  | BATCHELOR | 0 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  |  | 8 | TRUE |  |  | 2018-04-12 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000434 |  | 18P000434 | FALSE | CNAS | SL5 BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY |  | BOYCE | 4478 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Paul Ditty |  |  | 3 | TRUE |  |  | 2018-05-09 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000027 |  | 18P000027 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT LAB |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-05 | [6 empty] | 2/1/19, DL; This project is 100% Complete……………DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again…… DL, 4/2/18; This space is still on schedule for 7/1/18 completion date…..FAMIS work orders have been produced…..DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th….. |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again...... DL, 4/2/18; This space is still on schedule for 7/1/18 completion date.....FAMIS work orders have been produced..... | YES | 2018-07-12 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000346 |  | 19P000346 | FALSE | CNAS | SL5 I&Q--PAINTING ROOMS IN THE I&Q |  | EAST I&Q FAC |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | IMAD BAYOUN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2019-01-09 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000117 |  | 18P000117 | FALSE | CNAS | SL5 PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION |  | WEBBER | 1303 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-21 | [6 empty] | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work....DL, 5/9/18; Produced work order for JEss to test for lead paint and ACM....Von wall is hot, everything else is good to go. I will schedule the work soon. The space is vacant......DL, 7/11/18; This project is in progress. Target Complete Date is 8/10/18....DL, 7/25/18; Vinyl plank and bullitin boards the balance of the task for this project. Still on target for complete on 8/10/18.....DL; 8/10/18; We were schedule to install the fllor and identified Asbestos,. Jess is working on the propsal and schedule for the abatment. This will require a 14- dat notification to the AQMD. This space is vacant with no scheduled move in date......DL, 8/22/18; Abatment is scheduled for this Tursday and Friday. We will scheule the carpet in dry errase boards for next week.Target complete date will be 8/31/18.....DL, 9/6/18; This project is 100% Complete...... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work.... | YES | 2018-09-10 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
19W007474 |  | 19W007474 | FALSE | CNAS | SL5 BG - RAILROAD TIE WALLS | Repair Railroad Ties at Botanic Gardens | BOTANIC GARDENS |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV | [5 empty] | FALSE |  |  | 2018-11-07 | [7 empty] | 2018-12-10 | Ron Veloz | 03/11/19 O-RVL: Update, RV emailed Deborah H and Team to cancel this request. Message: "Facilities Services has reviewed the “Request for Estimate” under project number 19P000348. We (FS) have reviewed the request and have determined the costs exceed that allowed to Facilities Services within the UC guidelines and would also require structural engineering services which is beyond the services we are able to provide. ACCESS (WO) and FAMIS notes are updated and the customer was emailed with the Cancellation of the request. Updates completed by Ron V on 03/11/19. Please cancel Project - 19P000348 and Work Request #: 19W007474. END--- 03/11/19 O-RVL: Received information from Dan L and authorization from Team to CANCEL this work request for estimate. Cost would exceed 50k and will require engineering. RV emailed the team to cancel the request by "FS". END--- 03/01/19 O-RVL: RV will walk with Chad C to determine if FS is cabable of repair/reinstall railroad ties true & plumb. Walked site with Chad C. on 03/01 afternoon. Chad will meet with C.P. to determine capabilitiy and staff to perform work. RV will follow up. END--- 02/15/19 O-RVL: Udated SOW, RV will schedule a site visit with the Carpentry Supervisor to detemine the construction feasability and estimated costs. END --- 01/09/19 O-RVL: REQUEST FOR ESTIMATE, Not a Project. RV To schedule a site visit with C. Pillen and Chad Chambers to evaluate if repairs are possible. END--- 12/10/18 O-RVL: REQUEST FOR ESTIMATE. Ron V walked with D. McWilliams & Jodie and identified the railroad tie retaining wall area requiring repairs. Jodie would like an estimate to repair the leaning railroad ties at specified areas. RV to meet with Chris P. and or Chad Chambers to determine if FS can perform work and or provide an estimated cost to perform work. END--- 11/07/18 O-RVL: Received an email form Deborah Mc. to discuss the wall at Thursday during our 1-1 meeting. | YES | 2019-03-11 | FS | FALSE | 2018 | 2019-09-01
19P000319 |  | 19P000319 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB |  | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-04 | FS | FALSE | 2018 | 2019-09-01
19P000058 |  | 19P000058 | FALSE | CNAS | SL5 Assess Feasiblity of Removing/Replacing Growth Chambers |  | GH HH | 18 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-28 | [6 empty] | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing...DL, 5/9/18; Project is scoped. Need to schedule the work.....Plumbers and HVAC are working on this. Still need to have electrical removed. I am working wiht Patty on who can do the demo and removal.....DL, 7/11/18; I need to check in with Ken to see if refrigerant is recovered. will isue work order to disconnect electrical..... I checked in with our campus surplus and do not have any contacts to dis,matel the very large growth Chambers. I need to inform Patty and suggest that she have Burges demo and move the Growth Chambers......We will be complete with our portion of this project before 8/1/18.......DL, 8/10/18; All work is done except the disconnect for electrical. I need to check and see if the electrical. Per FAMIS complete on 8/22/18 |  |  | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000030 |  | 18P000030 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT FROM WATER DAMAGE |  | CHAPMAN | 100 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced....... | YES | 2018-11-08 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000029 |  | 18P000029 | FALSE | CNAS | SL5 CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS |  | CHAPMAN | 1 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain......DL, 5/24/18; This work is scheduled to be complete on or before 7/1/18.....DL, 6/16/18; Blinds are delayed to mid July but window clenaning is still on schedule......DL, 7/11/18; This Project is 100% Complete |  | Dan Lerman | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain...... | YES | 2018-07-11 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000028 |  | 18P000028 | FALSE | CNAS | SL5 CHAPMAN PATCH AND PAINT |  | CHAPMAN | 0010A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced .......DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced ...... | YES | 2018-07-12 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
19P000185 |  | 19P000185 | FALSE | CNAS | SL5 NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE |  | PIERCE | 206 (originially identified as Room 204) | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 6 | TRUE |  |  | 2018-06-18 | [6 empty] | 12/14/18, DL; This project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Pending glove box relocation to rm 319 and minor vent reconfiguration. Both tasks will be performed afet the glove boxes relocate to rm. 319. 10/29/18 All project related work is completed. |  | Ron Veloz | 07/05/18 RonV. Input: I observed multiple WO's for this project and spoke with Zee for clarification. I will investigate the site on 07/06 to determine the actual SOW. 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/22/18 O-RVL: Revised WO to Project no. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". =10/03/18: RV, Work in progress. Plumber are working on new gas lines. Will coordinate glove box move after work in rm 319 is completed. 10/29/18 RV: All glove boxes, Solvent mixing equipment and Chemical cabinet are removed. Remaining work is to replace the existing PVC vent with stainless duct when materials arrive per Cory. Update from Matt L-Plumbing department is working on the gas lines and will continue work this week. | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000186 |  | 19P000186 | FALSE | CNAS | SL5 NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION |  | PIERCE | 319 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-06-18 | [6 empty] | Pending gas line installation scheduled for the week of 09/24 per Steve Burleson. Move glove boxes from 206 to Rm 319 after gas line are installed. All work is complete |  | Ron Veloz | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". 10/03/18 RV: Work in progress, Plumbers are installing gas lines. Glove boxes from 206 can be moved after gas lines are installed. 10/08/148 RV: Plumbers to complete the installation of new gas lines in 319. Glove boxes to be brought to rm 319 after gas lines are installed. 10/17/18 RV: Update, Gas lines are installe approx 90% complete per Plumbing Tech, misc parts on order. 10/29/18 RV: All project related work is completeand confirmed with trades and PI. | YES | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000189 |  | 19P000189 | FALSE | CNAS | SL5 PHYSICS- WALL HOLES PATCH | Duplicate work order to 19P000049. Work to be completed on other project. | PHYSICS | 3036 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-16 | [10 empty] | NO | 2018-10-18 | FS | FALSE | 2018 | 2019-09-01
18W011692 |  | 18W011692 | FALSE | CNAS | SL5 ENTOMOLOGY; PAINT/PATCH LAB |  | ENTOM MUSEUM | 211 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-03-08 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000288 |  | 18P000288 | FALSE | CNAS | SL5 SKYE HALL OFFICE SUITE PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000312 |  | 18P000312 | FALSE | CNAS | SL5 URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 |  | CAMP LOC NOT IN BLDG |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  |  | 38 | FALSE |  |  | 2018-02-13 | [8 empty] | Enrico Baez | Canceled per customer 9/12/18/ EB, 5/29, conducted site visit 5/25. Structure is a double wide modular building/trailer. Space needs to be cleared of equipment, desks, tools. Disconnect electrical, plumbing. Needs professional removal. University Asset see Susan Marshburn for direction. EB, 9/12/18 Per Deborah McWilliams email.Project is cancelled due to lack of funding. | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-09-01
18P000310 |  | 18P000310 | FALSE | CNAS | SL5 ADD INTERCOM/BUZZ IN SYSTEM |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-12 | [6 empty] | Dl, 7/4/18; This project is scoped. This will be a new ADA operator, door bell / Intercom and buzzer button to unlock door. Walked work with Contractor, need to work on producing contract with PD&C. Once Contract is confirmed, we will schedule the work..... DL, 7/11/18; We have the proposal. Need to execute the agreement and schedule the work. The target complete date is before 10/1/18.....Dl 8/10/18; Jason will try and complete the work with in the next three weeks......DL, 8/22/18; Jason order parts, parts have 6-8 week lead time. Work will be scheduled when material arrives.....DL, 10/4/18; This Project is 100% Complete....... |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000341 |  | 18P000341 | FALSE | CNAS | SL5 PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL |  | PHYSICS | 1132 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-14 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process…DL, 6/16/18; Jess tested the matreial flooring and paint is hot. Jess will abate before we proceed with the project….Still need to scheudle the work. This project target complete date is late Fall……DL, 7/25/18; Jess sent out the 14-day notification to the AQMD last week. We will start the balance of the project after the ACM and Lead is abated or encapsulated…..8/10/18; Abatement is complete. We will work on the other items as time permits. This space is vacant with no occupancy date |  | Dan Lerman | DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process… | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000356 |  | 18P000356 | FALSE | CNAS | SL5 ENTOMOLOGY PATCH AND PATCH |  | ENTOMOLOGY | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 10 | TRUE |  |  | 2018-03-20 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000296 |  | 18P000296 | FALSE | CNAS | SL5 SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES |  | SKYE HALL | 266 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 31 | FALSE |  |  | 2018-02-02 | [6 empty] | 01/17/19, DL; This project was completed last summer……..DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19 18; I neeed to check on this work order. I thought it was part of the 2nd floor Hallway project but it was not…… |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2019-01-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000293 |  | 18P000293 | FALSE | CNAS | SL5 SKYE HALL COPIER ROOM PATCH AND PAINT |  | SKYE HALL | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 32 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000287 |  | 18P000287 | FALSE | CNAS | SL5 SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 33 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19/18; This project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000287 |  | 19P000287 | FALSE | CNAS | SL5 URGENT: PAINT SHOP TO PATCH AND PAINT |  | MAT SCI ENGR | 229 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | HONG XU |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-19 | [8 empty] | Paul Ditty |  |  | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000292 |  | 18P000292 | FALSE | CNAS | SL5 SKYE HALL PAINT MULTIPLE FACULTY OFFICES |  | SKYE HALL | 228 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul D. will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000390 |  | 19P000390 | FALSE | CNAS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 0 |  | TRUE |  |  | 2018-11-29 | [6 empty] | 7/1/19, DL; This project is 100% Complete…………6/17/19, DL; material is ordered. This project should be complete by July 1st…..5/31/19, DL; Plans were apprvied this week we will work on the contract and hopefully have the notice to proceed in the next two weeks. It is our goal to have the work complete on or before July 1st……5/15/19, DL; Need to order the special order door and frame…. | 2019-02-07 | Ron Veloz | 02/12/19 O-RVL: Scoping is complete. Revised door layout and emailed April photos of the proposed storefront door system received from D.L. on 2/11. April Meinzer approved storefornt door system on 2/12. RV reveised floor plan utilizing the existing cased opening as discussed with D.L. on 02/11. RV provided D.L. a copy of the revised Intake Formw/ layout. Form w/ layout. Unable to update project notes on FAMIS -Project is not available. END--- 02/07/19 O-RVL: Monty asked RV to follow up on this request. Ron V scheduled meeting with April Meinzer on 2/7 at 1:30pm to review intake information for the proposed project at room 5494. FAMIS Updated END--- | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-09-01 | FY 19-20
19P000358 |  | 19P000358 | FALSE | CNAS | SL5 GEOLOGY - ACCOMMODATION REQUEST |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-10-26 | [6 empty] | 4/15/19, DL; This Project is 100% Complete……. 3/28/19, DL; Plans are approved. We will start the work on 4/1/19……3/18/19, DL; Waiting for approved plans from building official……2/28/19, DL; Plans were submitted to building official for review. Once plans are approved, we will schedule the work………..2/14/19, DL; Plans are in process and we will apply for building permit next week………….. | 2019-02-07 | Ron Veloz | 02/07/19 O-RVL: RV changed title from "Geology" to "Physics". SOW is completed and on the server. Emailed a copy of SOW to FS team on 2/7. Received email from Ron Rector requesting Dan L. to provide Ronda Inzuna status update. END--- 01/31/19 O-RVL: Intake in progress. --- 01/15/19 O-RVL: Updated notes, the following SOW was from the requestor. --- 12/14/18 O-RVL: RV walked the site with Deborah Mc Williams on Mon 12/10. RV to create SOW. Returned request back to O-UA1 and will work from O-UA1 until the project is prioritized. "Potential scope of work for accommodation request: 1. Pour 10x10 cement pad for reserved electric transportation vehicle. 2. Electric charge station 3. appropriate signage" --- Deborah McWilliams is the main contact 951-218-3720 --- 11/14/18 RV: RV & Monty Received an "FYI" email from Deborah Mc Williams on 11/09/18 with information related to the approval of the charging station --- location currently undergoing review by the CBO. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000298 |  | 19P000298 | FALSE | CNAS | SL5 SPIETH - PREP LAB FOR FACULTY SEARCH |  | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 5/15/19, DL; This Project is 100% Complete… 5/1/19, Dl; This project will be complete next week…..4/15/19, DL; We are making good progress on this project and we should be complete the first week in May……..3/28/19, DL; This project is in progress and should be complete by or near May 1st….2/14/19, DL; Need to schedule trades and obtain quotes to refinish countertops…… |  | Ron Veloz | 04/22/19 O-RVL: Update- RV reviewed incoming work request 19P000546 and spoke with Dan L on 04/19 regarding Spieth Hall 19P000546 to add 1)Fabrication of a stainless steel hood like the one in Spieth Hall 2218 (picture attached), to fit the space in Spieth 1363 on east corner wall where walk-in chamber was removed. 2)Hook up of the new hood into the current fume hood vent and spanning ~75% of the distance between the working fume hood and the wall. 3)Removal of the shelving above the lab bench (may need some minor abatement). 4)Installation of 3 tombstone electrical outlets on the lab bench to match the other bench. RV spoke with Dan L. Dan, some of the added work is in progress and the remainder of work will be included on projet # 19P000298. Sheet metal hood will be completed on a SL6 sheet metal per DL. END~ 01/15/19 O-RVL: RV to scope once priority is established. RV updated notes with information provided from Deborah Mc Williams. Spieth 1363 – Wet Lab Space Note by D McWilliams.: "There is evidence in the ceiling and along one wall of a water intrusion issue, i.e. peeling paint, leaking and rusted pipes, etc. The cause of this damage needs to be investigated and repairs confirmed, including painting the wall and ceiling where damage is visible". Patch/paint Re-finish, re-surface – existing cabinets Re-finish and/or replace bench-tops If both sinks cannot be significantly cleaned, they should be replaced, replace faucets at both sink locations. Clean existing Chemical fume hood Repair or replace self-closing chemical / flammables storage cabinet On one bench remove overhead shelving unit and relocate electrical outlets to the ends of bench to accommodate large desktop equipment. Cap off remaining utilities for potential use/re-connection in the future. Remove shelves on west wall to accommodate siting of large floor-standing equipment before patch and painting. Also, add 120/240 electrical outlets (raceway) along this wall. Replace flooring -- this depends on what we decide about removing the walk-in fume hood listed below Add GFCI outlets near water sources. Requires a connection to a DI water system Other utilities are required in this room and at what locations, e.g. air, oxygen, gas, vacuum, etc.? Remove existing walk-in Fume Hood (if cost for this issue does not trigger project over $50k) – Please assess/cost out and advise prior to project. Spieth 1364 – Lab Support Space work: Patch/paint –Re-finish, re-surface – existing cabinets (non-porous surface), Re-finish and/or replace benchtops, if sink cannot be significantly cleaned, they should be replaced Replace faucets at sink location. Add GFCI outlets near water sources Requires a connection to a DI water system" | N/A | 2019-05-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000449 |  | 19P000449 | FALSE | CNAS | SL5 PAINT OFFICE AREA OF 229A FOR RELOCATION |  | FAWCETT LAB | 229A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-01-14 | [6 empty] | 04/05/19 O-ANS: Project complete per Paul Ditty and closed in FAMIS. |  |  |  |  | 2019-04-05 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000505 |  | 19P000505 | FALSE | CNAS | SL5 CHAPMAN HALL PAINT OFFICE WALL WHERE BOOK CASE WAS REMOVED |  | CHAPMAN | 10B | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-02-25 | [6 empty] | 05/10/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-05-10 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000440 |  | 19P000440 | FALSE | CNAS | SL5 GH#21--INSTALLATION OF GROW POD BEHIND GREENHOUSE #21 |  | GH21 |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER | PATRICIA SPRINGER | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-08 | [6 empty] | 5/31/19, DL; This project is 100% complete :)……5/15/19, DL; Project is complete except for chain link fence. Fence will be installed some time early next week…….5/1/19, DL; Grow Pod is installed with power and water. Still need to install fence and door lock….. 4/15/19, DL; Grow Pod is scheduled for delivery this Thursay. Once on site, we will connect all utilities and this project will be complete. 2/28/19, DL; Demo is complete. We need to veify utilitiy point of connections. Once utilities are verified, we will install the water and power……. |  | Dan Lerman |  |  | 2019-05-31 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000299 |  | 19P000299 | FALSE | CNAS | SL5 SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 |  | SPIETH | 3378 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000639 |  | 19P000639 | FALSE | CNAS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK | Make modifications to accommodate new PI | CHEMICAL SCI | 0435 | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-17 | [6 empty] | 9/3/19, DL; Need to verify scope with Ron and start working on plans. Will start plans in the next two- three weeks…… | 2019-07-19 | Ron Veloz | 07/19/19 O-RVL: Updated notes from work request screen. "07/17/19 O-RVL: Met with Tim, Dan L, Nick and Tran(EH&S) will revise intake and scope for new location. Pending approvals from EH&S for the newly proposed location for Biosafety cabinet in room 441. Receieved request from Tim Su on 07/19 "bench and cabinet removal, would it be possible to have them delivered to Chemical Sciences Room 108 after they are taken out?" Pending final revisions from Tim Su. " END~ 07/01/19 O-RVL: Pending intake/site visit to confirm SOW. END~ CR Routing 6/19/19: Summer ’19 Renovation Project Priority 1; For Faculty Hire YES. (Stephen C) | YES |  | FS | FALSE | 2019 | 2019-09-01
18P000473 |  | 18P000473 | FALSE | CNAS | SL5 PIERCE NEW CARPET & PAINT FACULTY OFFICE |  | PIERCE | 202 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 1 | 5 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | 2018-09-26 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000347 |  | 19P000347 | FALSE | CNAS | SL5 SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT |  | SPIETH | 3320 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-10-16 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000571 |  | 19P000571 | FALSE | CNAS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 |  | SCIENCE LAB1 | 215 & 322 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2019-04-10 | [6 empty] | 07/30/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-07-30 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
19P000244 |  | 19P000244 | FALSE | CNAS | SL5 PATCH & PAINT GEOLOGY |  | GEOLOGY | 2258A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2018-09-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000324 |  | 19P000324 | FALSE | CNAS | SL6 SPIETH HALL ASSESS AIR VENT OR PURIFIER FOR LAB | Provide the single pass exhaust, air changes (6-12 ACH) and the negative air requirements for PI to perform surgeries in the room. | SPIETH | 1312 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 106 |  | FALSE |  |  | 2018-10-05 | [7 empty] | 2018-10-10 | Ron Veloz | 04/04/19 O-RVL: RV emailed Deborah Hughes requesting cancellation of this project on 04/04 and copied the FS CR team. END~ 04/04/19 O-ANS: Canceled per Minor Reno meeting. 03/25/19 O-RVL: Ron V Contacted Estella via email 01/10/19 to provide the status for lab/surgical room 1312 and informed her of the collaborative results between efforts between Facilities Services and EH & S. Ron V stated "After further investigation of the building mechanical systems and review by EH&S; Facilities Services has confirmed the existing building mechanical systems is unable to provide the single pass exhaust, air changes (6-12 ACH) and the negative air requirements resulting in the cancellation of this request. Please feel free to contact me if you have any questions or need additional information". END~ O-RVL: Updated this project and copyied information from FAMIS. Not sure who requested this request to be a project. RV may need to rescope the project after Winter prioritizing. 01/10//19 RV copied notes from FAMIS and input the following notes: "10/10/18 O-RVL: Received email from Deborah Hughes to determine if this request is a SL5 or SL6. RV visited the site on 10-10 and saw filter media covering the supply air diffusers. RV sent photos to D.H. and informed her this was a SL6 for BM to remove filter media from the supply air diffusers. 12-21-18. R-DMU. W/O is waiting on filter to be removed. Will need to calculate air changes. Make repairs as needed. Room needs to be set (Negative). This may be the solution to their air deficiency. 11/21/18 R-DMU: Spieth hall. Rm 1312. Walk this job with BeiWei. 10-11-18. R-DMU. Will need tech to pull 3 ply media filter from supply register and verify proper air changes, and Exhaust flow with Flow Hood". | N/A | 2019-04-04 | FS | FALSE | 2018 | 2019-09-01
19P000367 |  | 19P000367 | FALSE | CNAS | SL5 SCILAB 1 0211- PATCH & PAINT |  | SCIENCE LAB1 | 211 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-31 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000223 |  | 18P000223 | FALSE | CNAS | SL5 Provide requisite utility infrastructure to support 4 add'l chambers (on order). |  | FAWCETT LAB |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 11 | 21 | FALSE |  |  | 2017-12-11 | [6 empty] | 2/1/19, DL; This Project is 100% Complete……..01/15/19, DL; Plans are approved, Chambers are on site. Electrical is complete. Plumbing work is in progress. Our portion of the project should be complete by 2/1/19…………..12/14/18, DL; All Pre work is complete. The Chambers are scheduled to arrive on site within the next 30-days. We will finish this project when material on site……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans……..DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet….DL, 4/29/18; Still need to conduct site visit with the team….DL, 5/24/18; Per Patty, equipment is ordered but 5- months out…..DL, 9/6/18; We will submit plans to Bob W. tomorrow for review and approval……..DL, 9/19/18; Plans are approved. The equipment will be here in about 4- months. WE will start the work for this project in the Fall to ensure we are ready when the equipment arrives……DL, 9/19/18; Plans are currently being review by BO & FM……DL, 11/7/18; Plans are approved. WE are requesting to change the placement confirguration of the growth chamber and awaitng Bob's review and approval. WE are on track to have this work complete befoire the end of the new year….. |  | Dan Lerman | DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans........DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet....DL, 4/29/18; Still need to conduct site visit with the team… | YES | 2019-02-01 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
19P000438 |  | 19P000438 | FALSE | CNAS | SL5 BOTANIC GARDENS RAILROAD TIE WALLS | Request for review and cost estimate for the repair of two railroad tie walls in the Botanic Gardens. 1) Retaining wall located below the Iris Garden (across from the Greenhouse). 2) Low wall located along the pathway just below the Garage Office. | BOTAN INFO C |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 118 |  | FALSE |  |  | 2019-01-08 | [8 empty] | Ron Veloz |  |  | 2019-03-05 | FS | FALSE | 2019 | 2019-09-01
18P000269 |  | 18P000269 | FALSE | CNAS | SL5 BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED |  | BATCHELOR | 1123 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 12 | 18 | FALSE |  |  | 2018-01-16 | [6 empty] | 3/18/19, DL; went to schedule the work and the customer stated the power is no longer needed and confirmed this work order can be canceled. |  | Enrico Baez | 5/23/18 EB - Sent email to April requesting site visit. 6/11/18 EB conducted site visit request if for additional outlet only. Single trade only asked Deborah to change to SL6. FS to coordinate with client to scope the work. Customer contacted to schedule a site visit. | YES | 2019-03-18 | FS | FALSE | 2018 | 2019-09-01
19P000137 |  | 19P000137 | FALSE | CNAS | SL5 LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM |  | LIFE SCIENCE | 2545 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000354 |  | 18P000354 | FALSE | CNAS | SL5 GH16-25 COOLING SYSTEM REPAIR |  | GH 16 25 |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | MARK TANKERSLEY |  | Dan Lerman |  | 13 | 17 | FALSE |  |  | 2018-03-20 | [6 empty] | DL, 7/25/18; Reviewed Ron V. noted. I will check in with Chris on this to better determin the method complete this project. |  | Dan Lerman | DL, 5/5/18; This is a repair, No alterations taking place. Pasted from FAMIS work order...THE COOLING SYSTEM ON GH 16-25 IS FALLING APART SHEET METAL TRAYS HAVE TONS OF HOLES, WOOD ROTTING ETC. PLEASE REPAIR….. RV, 07/06/18: Dan, Chis Pillen and I have walked this project months ago and have a quote from Ralph Cox/KIRA Construction to repair the head house damages. See Chris for the status of subletting this work. | YES | 2018-07-25 | FS | FALSE | 2018 | 2019-09-01
19P000045 |  | 19P000045 | FALSE | CNAS | SL5 PREPARE LOCATION AND UTILITIES FOR INSTALL |  | BOYCE | 2407 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 14 |  | FALSE |  |  | 2018-07-23 | [8 empty] | Ron Veloz | Scope is complete. Walked site with Steve Burelson. DI water is available behined wall in 2407 at interstictal space. Vendor will install Milpore unit, FS to provide DI water and back board.Power is available at the sink counter. Electrical has verified GFI. | YES | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000106 |  | 19P000106 | FALSE | CNAS | SL5 PHYICS 1134 - UTILITIES REQUEST |  | PHYSICS | 1134 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 15 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 6/15/19, DL; This Project is 100% Complete…...5/1/19, DL; Project should be complete this week or early next week…..3/28/19, DL; Power is complete. Need to finish chilled water…… 2/1/19, DL; Review scope with Customer. Still need to review with Brian from the Electic shop…………….12/14/18, DL; No update…. | 2018-11-07 | Ron Veloz | 01/31/19 O-RVL: Walked site with Dan L on 01/31 to review SOW. END--- 01/23/19 O-RVL: Received email from Ward B.in response to Brian Hambleton's request to use 208v. response is" ... 208 volt power 3-phase is fine for the compressor. Also having emergency power is not needed". END--- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela. END --- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela.-END 01/23/19 RV received Dr. Beyermann's comments and made corrections to the SOW, rev2. END--- 01/22/19 O-RVL: RV updates, Received a request from Mayela to meet on site with team. Sent team a copy of the Statement of Work for their review. Scope of Work: Install: Chilled new water supply & return drop, Electrical Power for the Compressor to be 3- phase 40Amp 220/230VAC hardwired from the equipment the disconnect for the Compressor. Power for the QD Pump and Controller to be single phase 200-230VAC, 20amp circuit. Patch and paint as needed, test for lead paint and TSI Asbestos abatement, equipment anchoring. Note: Job walk conducted on 11/07/18, 9:45-10:00am. Met in 1134 to determine Equipment and Utility Service location. In addition, on 11/03/18 the customer requested a single phase 200-230VAC, 20amp circuit (received info via email). END --- 01/11/19 O-RVL: Received an email from Mayella requesting status. END --- 11/08/18 O-RVL: Received email from Dr Beyerman today for added electrical. "I just realized that I also need a single phase 200-230VAC, 20 amp circuit in 1134 for the pump and controller, which is that unit next to the dewar. This can be down by the floor, in the vicinity of the 3 phase box. I will be meeting with the electrician today around 11am, and I will mention it to him". RV asked Dr Beyermann to contact me with the location for the pump receptacle. Will update floor plan upon receipt. 11/07/18 RV Walked site with Mayela and Dr Beyerman. Request to provide Chilled water loop, and two locations for Electrical power. Identified locations to install new utilities. END --- 11/07/18 O-RVL: Walked site on 11/07 with Dr Beyermann & Mayela, identified scope. Update FAMIS to J-DLN, MinRenlist and move to que to start. END --- 11/06/18 O-RVL: Jobwalk scheduled on 11/07 at 10:00am in Rm 1134 with Mayela, Ward Beyermann, Darren M HVAC, Brian H-Elect. Hold | YES | 2019-06-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000170 |  | 19P000170 | FALSE | CNAS | SL5 INSTALL NEW IRRADIATOR INSTRUMENT |  | MAT SCI ENGR | 51 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 16 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 2/14/19, DL; This project is 100% Complete………2/1/19, DL; Power is complete. Chilled water will be complete next week…………..1/15/19, DL; Electric is commplete, Water will be complete with in two weeks. Equipment should be on site soon…12/14/18, DL; This project is currently on hold per RED…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; The unit is schedukled for delivery in the next three weeks. | 2018-09-19 | Ron Veloz | 01/30/19 O-RVL: Spoke with Dan, equipment arrived staging into building. END---…..9/10: D. Dinh Project is shared between CNAS & BCOE, captured only on the CNAS College Count. 09/19/18 RV, Scope is complete. RV to Upload into FAMIS. Install chilled water and dedicated power for the irradiator instrument at the west wall in rm 051. 10/17/18 RV: SOW provide Chilled water loop and one(1ea) dedicated 208v 1ph 40a circuit to the Irradiator. Floor plan and specs are on the server folder. | YES | 2019-02-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | FS to coordinate with client to scope the work. | DELFINO HHSE |  | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | [6 empty] | 5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Scope completed per DL. | YES |  | FS | FALSE | 2018 | 2019-09-01
19P000292 |  | 19P000292 | FALSE | CNAS | SL5 GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 18 |  | FALSE |  |  | 2018-08-10 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…….2/14/19, DL; The Concrete and Power is Complete. We still need to install the chain link which will be installed in about 3-4 weeks………..2/1/19, DL Electrical is complete. WE will pour Concrete next week. We will schedule the fence install 28- days after concrete is poured………; Th1/15/19, DL; Plans are approved, we will start the work in the next two weeks……12/14/18, DL; Plans are almost complete. We will schedule the work after plans are approved……DL, 11/7/18; Conducted site visit with Chris P. We need to confirm a feasable site location before we move forward with the work…. |  | Ron Veloz | 10/30/18 RV: Chris Pillen and D. McWilliams aggreed to leave the building in place and place a concrete pad with a chain link fence adjacent to the existing structure. 10/17/18 RV: SOW, demolish walls and roof. Verify and cap existing underground utilities. Remove overhead electrical from power pole to the building. The concrete pad to remain and install a 6'H fence with gate around the pad. Bring Power below grade to pad location. Met with C.Pillen and Dan to discuss alternate options. Photos and equipment info is on the server file. | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000043 |  | 19P000043 | FALSE | CNAS | SL5 SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | Customer called and canceled the work on 10/23/18. | SCIENCE LAB1 | 309 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 19 |  | FALSE |  |  | 2018-07-20 | [7 empty] | 2018-10-22 | Ron Veloz | Customer called and canceled the work on 10/23/18. 10/20/18: O-RVL: Site visit on 10/20 with Amber 10:30am. 10/22/18 O-RVL: Walked site with Vendor/Controlled key sys. The PI requested pricing to change the locking function from room to room as "Storage use " and rekey the entry door with the same function. Matt will send pricing on the week of 10/22. 10/23/18 O-RVL: This request will not require access controls, but will require the entry door and side door lock-sets function to be changed to a storage function and rekeyed per Dave(PI). Received info from PI that there was a theft in his dept. Request is urgent. RV requested key count from Dave 8/23/18 and is pending a response from the department. 10/23/18 >> Canceling at the request of the customer - Loretta | YES | 2018-10-23 | FS | FALSE | 2018 | 2019-09-01
19P000340 |  | 19P000340 | FALSE | CNAS | SL5 PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE |  | SKYE HALL | 349 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | VICTORIA AVALOS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000618 |  | 19P000618 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 205 AND 205A- PAINT |  | COLL BLDG NO | 205 AND 205A | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 06/11/19 O-ANS: Per Paul, conference room was in decent condition and does not need to be repainted. He will speak with customer to explain. |  |  |  |  | 2019-06-11 | FS | FALSE | 2019 | 2019-09-01
19P000341 |  | 19P000341 | FALSE | CNAS | SL5 PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL |  | PIERCE |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000622 |  | 19P000622 | FALSE | CNAS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK | Replace doors & frame | FAWCETT LAB | 204 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-15 | [6 empty] | 9/3/19, DL; Contractor has PO# for the doors. I need to verify lead time on material and schedule the installation…….8/15/19, DL; PO# will be provided this week to order the doors and frame, lead time is 4- weeks for the doors/ frame. We will scheudule the install once the door / frame is on site……..8/1/19, DL ; Pending estimate from vendor. Once we have everything needed, we will schedule the work…. | 2019-07-15 | Ron Veloz | 07/18/19 O-RVL: RV complete Intake and placed on the project folder on the FS Server on 07/17. END~07/15/19 O-RVL: Received email on 07/15 regarding door project. Spoke with Dan L and forwarded the floor plan to him. Explained the SOW is to replace the door frame and door and hardware as recommended by Jason Williams to provide the proper door functions for the department. Dan requested a site plan and will outsource to a door vendor and not further scoping is required for this project. END~ 07/12/19 O-RVL: Walked site. END~ 07/01/19 O-RVL: Pending intake/site visit to confirm SOW. END~ CR Routing 6/19/19: Summer ’19 Renovation Project Priority 2; For Faculty Hire NO. (Stephen C) | YES |  | FS | FALSE | 2019 | 2019-09-01
19P000214 |  | 19P000214 | FALSE | CNAS | SL5 PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT |  | PHYSICS | 3005 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-08-24 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000283 |  | 19P000283 | FALSE | CNAS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 20 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 8/1/19, DL; This Project is 100% Complete……7/1/19, DL; Barricades are complete. Signage needs to be installed. Signage to be installed in the next 3- weeks………….6/17/19, DL; Yello Caution tape is installed. Still need to install barricades and signage. Target complete date in mid to late July……5/31/19, DL; The contractor has the PO#. We will start the work and complete the work in the next 30- days……5/15/19, DL; We are waiting on the quote, once we have the quote, we will proceed with the work……4/15/19, DL; We are trying to locate a roofing contractor that will complete the installation. This is a specialty product that requires a professional installation…….3/28/19, DL; We will install the yellow caution tape on the roof which is our most viable option. I will schedule a site visist / job walk with a contractor in the near future…… | 2018-09-19 | Ron Veloz | 10/17/18 RV: All construction information is on the server folder. Pending Saftey MOP's from Beiwei. Left message with her on Monday 10/15 for status. ---10/03/18 RV: SOW, Install safety guard railing and apply yellow markings (leading edge 6'from perimeter) on the Winston Chung Roof. --- 09/19/18-Scope is complete, received safety requirements prepared by EH&S/Beiwei. RV to upload onto FAMIS. | YES |  | FS | FALSE | 2018 | 2019-09-01
18P000388 |  | 18P000388 | FALSE | CNAS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 2018-04-10 | [6 empty] | 8/14/19, DL; This project is 100% Complete………8/1/19, DL; This project work from Facilities Services should be complete in about 2- weeks…..7/15/19, DL, Work is in progress. Goal is to be complete with our scope near the first week in August……6/17/19, DL; This will be scheduled in July…….5/31/19, DL; Demo and removal of the dishwasher is. We will work on the installation and elctrical / power connections over the next three weeks. Note. Steam shut down is taking priority and the installation may be delayed….. 5/15/19, DL; We will schedule the work……..DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but there is no hard date as this is vacant space and we will access the space as time permits…… DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter….DL, DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans….7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved….. |  | Enrico Baez | 6/21/18 EB Remove old glass washer and install washer 400XLS. Disconnect steam, air, water, electrical, vent hood. Install new washer, electrical, step up x-former 208v to 480. Dept. to purchase x-former $5000 ill to dept. Elect. To provide specs. | YES | 2019-08-14 | FS | FALSE | 2018 | 2019-09-01 | FY 19-20
18P000480 |  | 18P000480 | FALSE | CNAS | SL5 BG - LOWER RESTROOMS-PAINTING-FLOORS | Canceled by Facilities Services; Work is not within the SLA and is not needed. | BOTGDN RSTRM |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-09-01 | FS | FALSE | 2018 | 2019-09-01
18P000486 |  | 18P000486 | FALSE | CNAS | SL5 PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 2018-06-28 | [6 empty] | 8/1/19, DL; This project is 100% Complete…… 6/17/19, DL; This project is making good progreess and will be complete near mid- July…..5/31/19, DL; This project is making good progress and we are hopeful to be complete on or before July 1st……5/1/19, DL: This project is in grogress and moving forward. Target complete date is 6- weeks… 4/15/19, DL; Started Demolition phase….2/28/19, DL; We will work on the plans in the next 30-days.12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman | Dan L. scoped this project as part of an IRT…. 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. If possible paint to match existing green accent wall, if not white is fine. Mount monitor bracket to wall centered side to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | YES | 2019-08-01 | FS | FALSE | 2018 | 2019-09-01 | FY 19-20
19P000210 |  | 19P000210 | FALSE | CNAS | SL5 CHEMICAL SCI Install Door In Doorway |  | CHEMICAL SCI | 0225A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  | 25 |  | FALSE |  |  | 2018-08-24 | [6 empty] | 7/1/19, DL; This project is 100% complete…..6/17/19, DL; Po is cut. Target complete date is before 7/1/19……Permit was approved this week. We are now working on the contract with the vendor. Our goal is start the work with in the next 30- days. 5/15/19, DL; Plans were approved. I am in the process of working with PD&C for the contract. We will order material and schedule the wrok once we have a signed contract……..3/28/19, DL; Plans were submitted last week… 3/18/19, DL; Conducted site visit last week. We are working on plans now we will try and submit plans for permit review next week…… | 2018-09-19 | Ron Veloz | 10/03/18 RV: Install non rated door into an existing cased opening-for privacy & noise reduction. Will require carpentry-framing, patch, paint, and minor flooring/base repair.---09/19/18-RV, Scope of work is complete. RV to upload docs to FAMIS. | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-09-01 | FY 19-20
18P000099 |  | 18P000099 | FALSE | CNAS | SL5 EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 26 | 23 | FALSE |  |  | 2017-09-08 | [6 empty] | 4/19/19, DL; This Project is 100% Complete :)…………….12/6/18, DL; This project is a priority #23 and may be completed in the next 12 - months…..DL 1/3: Chris to verify with customer on electrical requirements for completion……DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress…..DL, 7/11/18; Still need to work on plans…. Target date is 9/30/18….. |  | Dan Lerman | DL 1/3: Chris to verify with customer on electrical requirements for completion…...Dl, 4/29/18; Will work on plans/permits. The display cases will be in a corridor and they may pose an obstruction for Emergency Exit egress.....DL, 4/2/18; This is electrical outlets for 4 display cabinets…..…NO FAMIS work orders yet…. | YES | 2019-04-19 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
17W012504 |  | 17W012504 | FALSE | CNAS | PAINT Business OFFICE AND CONF. ROOM |  | ENTOMOLOGY | 170 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 27 | 26 | FALSE |  |  | 2017-05-04 | [6 empty] | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. |  | Dan Lerman | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. | YES | 2018-10-22 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000257 |  | 18P000257 | FALSE | CNAS | SL5 SKYE HALL MOUNT 55 |  | SKYE HALL | 209 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 28 | 28 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete…….1/15/19, DL, Site visit is scheduled with James M. this Thursday. We will schedule the work shortly after the site visit…….12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | 2019-02-01 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000284 |  | 18P000284 | FALSE | CNAS | SL5 SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT |  | SKYE HALL | 277 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  | 29 | 23 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | 2018-09-21 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000258 |  | 18P000258 | FALSE | CNAS | SL5 SKYE HALL HALLWAY MOUNT |  | SKYE HALL | 212 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 29 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete……1/15/19, DL, Site visit is scheduled with James M. this Thursday…………12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | 2019-02-01 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
19P000006 |  | 19P000006 | FALSE | CNAS | SL5 MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 |  | MAT SCI ENGR | 310 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..2/14/19, DL; This project is 90% Complete. ………2/1/19, DL; This Project started to day. We are scheduled to be complete by the end of February………..1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. | 2018-09-28 | Ron Veloz | 10/30/18 RV: Spoke with Deborah McWilliams, today. Project to remain as prioritized(#3) for new Faculty. 10/17/18 RV: Floor plan is on the server folder. RV: 10/03/18: Install metal stud wall at center of the room. Remove one door blank and install one lockset.Requires, Framing, drywall, tape, sand, paint, t-bar modifications and rubber base. PM to verify with user if power and Data will be required in the new wall. 09/28/18 O-RVL: Completed SOW: Add Wall in the center of room. Include a new Metal Stud Wall with rubber base to match existing. Remove metal cover at ceiling. Remove door lock blank and install new lockset at left door. RV completed SOW & placed on FS server. Updated FAMIS and Minor Reno List. 09/27/18 O-RVL: Site walk with Chris P, Dan L. Mayela and Deborah McW. FS to re-install the metal stud wall to original place dividing the room equally. Scoping completed. 09/26/18 O-RVL: 19P000006-Scheduled a site walk scheduled with Dan. Will contact Deborah and Mayela for their participation. | YES | 2019-03-18 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install utilities for new equipment | PHYSICS | 1132 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-03-19 | [8 empty] | Ron Veloz | 08/-8/19 O-RVL: Received equipment informaion/specifications from Mayela on 08/08. RV will prepeare intake with PI, PM and Davide Neff. END~ 08/07/19 O-RVL: RV emailed David Neff request for status & cc'd D.Lerman. Pending equipment specs from PI to determine heat loads & affect to the current Bld infrastructure and to determine new electrical load requirements. RV placed on Hold until equipment specs/ information is received. END~ 07/01/19 O-RVL: Pending Intake walk. END~ CR Routing 6/19/19: Summer ’19 Renovation Project Priority 3; For Faculty Hire NO. (Stephen C) END~ 04/22/19 O-RVL: Update - RV emailed Mayela on 04/18 on the same day her inquiry was received on " to confirm if equipment specifications and pertinent information have been reviewed to discuss the project." RV responded "we have not received the equipment specs and will no longer be engaged with projects before they have been reviewed and prioritized by the Dean's office for the upcoming quarter". RV cc'd Deans off, Monty, Dan L., C. Pillen, PI and R. Rector. END~ 03/20/19 O-RVL: Emailed Marcelina (in Mayela's absence) requesting equipment specs. Pending response. END~ 03/19/19 O-RVL: Received email from Mayela, Work request was submitted. END~ 03/18/19 O-RVL: RV received an email from Dan to Mayela on 03/13. RV contacted spoke with Dan requesting info. RV contacted Mayela and asked her to submit a work request for the additional work. | NO |  | FS | FALSE | 2019 | 2019-09-01
19P000613 |  | 19P000613 | FALSE | CNAS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT |  | COLL BLDG NO | 0203B | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000301 |  | 19P000301 | FALSE | CNAS | SL5 SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH |  | SCIENCE LAB1 | 214 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-09-27 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000347 |  | 18P000347 | FALSE | CNAS | SL5 GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) |  | GEOLOGY | 0 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 31 | Deferred to Fall Quarter - summer priority 27 | FALSE |  |  | 2018-03-18 | [6 empty] | 4/15/19, DL; Thios Project is 100% Complete….3/28/19, DL; Monitor is installed, need to finish power and data………………...2/14/19, DL: The monitor is on site. We need to schedule the installation. 2/1/19, DL; Conducted site visit with Amber. Amber will order the monitor. We will schedule the installation when the monitor is on site………….DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/1 EB Site visit. TV to be mounted on wall above water fountain across from Geo 2306. Center of mount 84" high and centered between wall corner and bulletin board. Will need electrical and data. Computer connection cutout will be in mail room. See W.O. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000055 |  | 19P000055 | FALSE | CNAS | SL5 CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM |  | COLL BLDG SO | 207 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Dan Lerman |  | 32 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2018-05-18 | [6 empty] | 4/15/19, DL; This project is 100% Complete…….3/28/19, DL; Need to order material and schedule the work…… Work order is assigned. 12/14/18, Dl; This project is prioritized at 32 and will not be scheduled in the near futurer…….DL, 7/11/18; Correction, I did not scope this yet, I thought we were talking agout the door bell and ADA operator. I will check in with Ronda and verify the scope…… DND 7/30/18: Created project to replace WO #18015182; project #19P000055 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. | 2018-11-29 | Ron Veloz | 11/29/18: RV Visited site and identifed the toilet room on the 2nd floor. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18W013160 |  | 18W013160 | FALSE | CNAS | BEES- PATCH & PAINT 2460D & 2460F |  | GEOLOGY | 2460 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 33 | 29 | FALSE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000191 |  | 19P000191 | FALSE | CNAS | SL5 PATCH AND PAINT HINDERAKER BASEMENT |  | HINDERAKER |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 34 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000464 |  | 18P000464 | FALSE | CNAS | SL5 PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 35 |  | FALSE |  |  | 2018-08-16 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000436 |  | 18P000436 | FALSE | CNAS | SL5 COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS |  | COLL BLDG SO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 36 | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000174 |  | 19P000174 | FALSE | CNAS | SL5 BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT |  | BATCHELOR | 2112 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMY RICKS |  | Dan Lerman |  | 37 |  | FALSE |  |  | 2018-07-24 | [6 empty] | 5/1/19, Dl; This project is 100% Complete….. 4/15/19, DL; This project should be complete in 2-weeks…… 12/14/18, DL; This project is priortized at 37 and will not be scheudled until further notice…… | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scoping narrative is available and located on the BZM Fall Folder. Patch & Paint, replace supply grilles, reverse door swing, remove door closers, install metal plate over door opening. | YES | 2019-05-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000042 |  | 19P000042 | FALSE | CNAS | SL5 COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL |  | COLL BLDG SO | 200 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Paul Ditty |  | 38 |  | FALSE |  |  | 2018-07-20 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000049 |  | 19P000049 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT |  | PHYSICS | 3036 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | 39 |  | FALSE |  |  | 2018-07-25 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000508 |  | 19P000508 | FALSE | CNAS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | BOYCE | 3410 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-02-21 | [8 empty] | Ron Veloz | 08/07/19 O-RVL: Will schedule site visit soon. 07/01/19 O-RVL: Pending intake | NO |  | FS | FALSE | 2019 | 2019-09-01
18W011691 |  | 18W011691 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | FS to coordinate with client to schedule work for completion. | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 4 | 11 | TRUE |  |  | 2018-03-08 | [6 empty] | 12/17/18 DND: Canceled by client on 12/17/18. |  | Paul Ditty |  | N/A | 2018-12-17 | FS | FALSE | 2018 | 2019-09-01
19P000614 |  | 19P000614 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 202- PAINT |  | COLL BLDG NO | 0202 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-09-01
19P000318 |  | 19P000318 | FALSE | CNAS | SL5 GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE |  | GEOLOGY | 420 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-04 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000031 |  | 19P000031 | FALSE | CNAS | SL5 BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) |  | BIOLOGICAL SCI | 3101 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 40 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 6/15/19, DL; This Project is 100% Complete…...5/1/19, Dl; This project will be complete on 5/5/19…..3/28/19, DL; Need to schedule a site visit with Estella. Left voice mail message on 3/28/19 to schedule site visit……..12/14/18, DL; This is prioritized at #40 and will not be scheduled in the near future….. |  | Enrico Baez | 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. Install 2 duplex outlets | YES | 2019-06-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | [6 empty] | 9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Ron Veloz | 04/15/19 O-RVL: Previously informed Dan L & Jason W of the approved Estimate and it was in que ready to go. RV followed up with email to Dan L & Jason W. on 04/15/19 to confirm. FAMIS & Access notes were updated. END~ 04/05/19 O-RVL: Changed Priority on FAMIS from SL9-Estimate back to SL5-Project and change assignment from O-RVL to J-DLN (Dan Lerman. Linda changed project title on Access from Room 2221 to 4231. END~ 04/04/19 O-RVL: Estimate is complete and accepted by the customer. The requester has accepted the revised estimate #2 to install one access card reader at room #4231. RV has updated FAMIS Access notes. RV informed Dan L. at team meeting that estimate is complete and will move the project from Customer Hold to Que to start. END~ 03/27/19 O-RVL: Pending Customer review, Received acceptance of the estimate from Aimee G. and modified the Rev.2 estimate and returned to her as requested. Pending final approval. END~ 03/19/19 O-RVL: RV spoke with Aimee, Department will proceed with one card reader and expecting a FAU within a week or two. RV will keep project on Hold. ACCESS & FAMIS Notes updated. END--- 03/13/19 Sent Aimee a revised estimate for one door as requested - for room # 4231. Pending response. END--- 03/08/19 O-RVL: Placed on Customer Hold. Contacted Chris Rogers at HCI (Access Control Vendor) Chris will send the revised proposal on 03/11/19. END--- 03/07/19 O-RVL: Received an email from Aimee Gonzales. Revised request to " provide us with an updated quote to install the FOB reader to Genomics 4231 only instead of all three rooms". END--- 02/22/19 O-RVL: Followed up with a phone call to Aimee to confirm receipt of the estimate. Aimee will respond within 30 days with the department's decision. END--- 02/21/19 O-RVL: RV received request for status of estimate from Aimee G. RV replied to send Estimate by CBD today. Estimate sent. Changed priority from SL5 to project to SL9-Estimate. END---02/15/19 O-RVL: RV-preparing estimate to deliver to the customer on the week of 02/17/19. END--- 01/31/19 O-RVL: Pending proposal revisions with equipment itemized with make and model no. from the Access control vendor. Revised proposal due soon per vendor. END--- 01/15/19 O-RVL: Forwarded access controls quote and SOW to Jason and Chris Rodriguez to review and qualify the HCI quote. Pending response. --- 01/10/19 O-RVL: RV received quote and will send a formal Estimate to Aimee by EBD Fri. 01/18 and ask if they would like to proceed. 12/14/18 O-RVL: REQUEST FOR ESTIMATE ONLY. Send Estimated costs to Aimee Gonzales for review and approval. Pending access controls and auto door operator quotes. Moved to Queue to start. ---11/08/18 O-RVL: Scope is complete. Assisting the lock shop with pricing to provide the requestor an estimate prior to start of construction. Walked a 2nd vendor, pending quote for access control card reader. ---11/05 RV called vendor for quote, no reply. ---10/29/18 RV: Conducted jobwalk with vendor last week. Pending quote from Vendor. Will follow up. --- 08/23/18 O-RVL: Ron V. input update from the requestor per M. Anderson (email 08/23), "We would like to review the estimated costs and timeline prior to the FOB system being installed, and from there we will determine if we would like to proceed with the installation." ---Please provide the total cost estimate to Aimee Gonzales before initiating any work(R.V). Contact: Aimee Gonzales 951-827-6254. | YES |  | FS | FALSE | 2018 | 2019-09-01
19P000102 |  | 19P000102 | FALSE | CNAS | SL5 PATCH & PAINT FRONT CORNER OF OFFICE |  | LIFE SCIENCE | 2930 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 42 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000133 |  | 19P000133 | FALSE | CNAS | SL5 PATCH HOLES AND PAINT |  | BATCHELOR | 2203 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 43 |  | FALSE |  |  | 2018-08-07 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000197 |  | 19P000197 | FALSE | CNAS | SL5 PATCH AND PAINT OFFICE, LOBBY AND HALL |  | COLL BLDG NO | 0203B | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 44 |  | FALSE |  |  | 2018-08-21 | [6 empty] | 05/07/19 O-ANS: Canceled per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01
19P000184 |  | 19P000184 | FALSE | CNAS | SL5 REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES |  | GEOLOGY | 1270 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 45 |  | FALSE |  |  | 2018-08-14 | [6 empty] | 4/15/19, DL; This Project is 100% Complete…….. 3/28/19, DL; The project is 90% complete. Need to schedule floor installation…….. 2/14/19, DL; We will schedule the work soon. The space is vacant and ready…………….2/1/19, DL; This project has started. We would like to have the work complete by mid March…………..12/14/18, DL; This project is prioritized at 45 and will not be shceudled until further notice…… |  | Enrico Baez | 11/19/18 EB-Met with Laurie Graham at site. 11/08/18 RV: Enrico is assisting RV and has scheduled a job walk with Laurie Graham. Will follow up, pending confirmation. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000246 |  | 19P000246 | FALSE | CNAS | SL5 PHYSICS - PATCH AND PAINT |  | PHYSICS | 3007N | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 46 |  | FALSE |  |  | 2018-09-07 | [6 empty] | n/a |  | Paul Ditty | Duplicate request; project to be completed on 19P000234 | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000242 |  | 19P000242 | FALSE | CNAS | SL5 PAINT OFFICE |  | COLL BLDG NO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 47 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000231 |  | 19P000231 | FALSE | CNAS | SL5 OLMH 1428 PATCH AND PAINT |  | OLMSTED | 1428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ANDREW CABRERO |  | Paul Ditty |  | 48 |  | FALSE |  |  | 2018-08-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000243 |  | 19P000243 | FALSE | CNAS | SL5 GENOMICS 1206 - PATCH AND PAINT WALLS |  | GENOMICS | 1206 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Paul Ditty |  | 49 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | n/a | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000285 |  | 19P000285 | FALSE | CNAS | SL5 PAINT AND PATCH PI OFFICE |  | ENTOMOLOGY | 269 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-09-17 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000615 |  | 19P000615 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT |  | COLL BLDG NO | 203 AND 204 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-05-14 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000062 |  | 19P000062 | FALSE | CNAS | SL5 MSE 169-MINOR RENOVATION - NEW FACULTY |  | MAT SCI ENGR | 169 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 5 | 19 | TRUE |  |  | 2018-07-30 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………..1/15/19, DL; This project is 99% complete pending one water heater. Water heater is not here yet……12/14/18, DL; This project is 95% complete. The water heater is scheduled for delivery shortly after the new year. We will complete the install when the heater arrives…… 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 9/6/18; We will have the power and cabinets removed by 9/19/18. We are in the process of producing plans for this project. Once the plans are approved, we will proceed with the project. Note, we still need to obtain important information and some specifications regarding the procured base cabinets and counter tops, bio safety cabinet, diswasher, and freezer. ……DL, 7/7/18; The work is 90% complete. We are waiting on parts which have a 4-6 week lead time. We will finsh the balance of the project when the parts arrive….. | 2018-08-22 | Ron Veloz | 10/17/18 RV: Work is in Progress. END--- 08/27/18 RV: Updated notes. Moved to "Que to Start". Lab upgrades, Install utilities for new lab equipment, including DI water, electrical, modify existing cabinet to accommodate new flask washer, install owner furnished lab workstations. END ---...DND 8/12/18 replaced 3 projects for Summer quarter completion. Ron V. has scope on project. END --- 08/22/18 O-RVL: completed S.O.W, sent to Mayela Castillo for sign off. 08/23/18-RV: Ron V. Resubmitted S,O.W. rev.1 and received Final sign off from Mayela. Met with Dan to provide information and hand off the project. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000176 |  | 19P000176 | FALSE | CNAS | SL5 PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY |  | PHYSICS | 1112 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 50 |  | FALSE |  |  | 2018-08-10 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | 2019-01-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19W003012 |  | 19W003012 | FALSE | CNAS | SL5 FIX RESTROOMS (PAINT AND FLOORS) | FS to coordinate with client to schedule work for completion. | CHAPMAN | 5 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 51 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | N/A | N/A | 2018-12-13 | FS | FALSE | 2018 | 2019-09-01
19P000126 |  | 19P000126 | FALSE | CNAS | SL5 CHEMICAL SCIENCE - MINOR RENOVATIONS |  | CHEMICAL SCI | 455 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Dan Lerman |  | 6 |  | TRUE |  |  | 2018-08-03 | [6 empty] | 12/14/18, DL; This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL,11/7/18; Paint is complete, Plumbing shop is planning to schedule the work in the near future…… |  | Ron Veloz | Work in progress, install nitrogen lines and valves(valves by PI). Patch and paint. 10/30/18 RV: Spoke with Kevin, pending nitrogen line installation | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000616 |  | 19P000616 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 208- PAINT |  | COLL BLDG NO | 208 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-09-01
19P000230 |  | 19P000230 | FALSE | CNAS | SL5 NEW FACULTY OFFICE FOR PATCHWORK/PAINT |  | GEOLOGY | 1242A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-08-30 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000360 |  | 19P000360 | FALSE | CNAS | SL5 GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING |  | GEOLOGY | 1444 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000617 |  | 19P000617 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 212- PAINT |  | COLL BLDG NO | 212 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | FS | FALSE | 2019 | 2019-09-01
19P000251 |  | 19P000251 | FALSE | CNAS | SL5 CHEM SCI 428-PATCH DRY WALL HOLES |  | CHEMICAL SCI | 428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000369 |  | 19P000369 | FALSE | CNAS | SL5 PIERCE - PAINT IS PEELING OFF WALLS |  | PIERCE | 3341 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000482 |  | 19P000482 | FALSE | CNAS | SL5 PIERCE HALL- PAINT/PATCH HOLES IN 1219C AND 1220D |  | PIERCE | 1219C | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JACQUELINE HAMILTON |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-02-01 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000291 |  | 19P000291 | FALSE | CNAS | SL5 MSE HELIUM RECOVERY SYSTEM |  | MAT SCI ENGR | 205 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 9 | HOLD | FALSE |  |  | 2017-07-24 | [6 empty] | 12/14/18, DL; This project is 100% Complete……DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB - spoke with Mayela who is determining status within her dept…. DL, 11/7/18; This project is complete but I need to conduct a final site visit….. |  | Ron Veloz | DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB-Spoke with Mayela-she is researching where the project stalled within her department. 7/2/18 DND Please verify if work is still required for completion 8/7/18 EB-sent Mayela email requesting update on 9/20/18 EB-emailed Mayela to determine status of project. 9/24/18 EB-Project not cancelled. Passed on to Ron Veloz. 10/03/18: RV, Walke job with Mayela, Chris P, Dan L & Deb McWilliams. PI to provide Dan layout and equipment specs. | YES | 2018-12-14 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
19P000288 |  | 19P000288 | FALSE | CNAS | SL5 COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS |  | COLL BLDG NO | 202 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-19 | [6 empty] | 05/10/19 O-ANS: Project was canceled by FS in March 2019 because customer will have to submit separate work orders for each room since customer has requested to schedule and complete them separately in sequence (not all at once). 3/4/19 DND Complete per PD |  | Paul Ditty | N/A | N/A | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000523 |  | 19P000523 | FALSE | CNAS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | Placed on HOLD by customer until next Quarter (Fall 2019) | SPIETH | 3366 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-03-12 | [9 empty] | 06/27/19 O-ANS: Paul Ditty met with customer to discuss scope and customer requested to place on HOLD until future semester since they were not prepared to move furniture in preparation for renovation. |  |  | FS | FALSE | 2019 | 2019-09-01
18P000221 |  | 18P000221 | FALSE | CNAS | SL5 Provide add'l HVAC capacity to maintain lower temp |  | BOYCE | 4414 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 9 | 16 | FALSE |  |  | 2017-12-11 | [6 empty] | 12/14/18, DL; This project is 100% Complete……….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob. DL, 5/9/18; We will work on plans and submit for review.....DL, 6/16/18. Had meeting with Bob W. to verify what is needed on plans. I will work with Gunther on plans for submittal and review......DL, 7/11/18; Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall.....DL, 11/7/18; Material is on site and will will schedule the work with in the next 30- days..... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob | YES | 2018-12-14 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
19P000234 |  | 19P000234 | FALSE | CNAS | SL5 PHYSICS 3005-WALL HOLES PATCH |  | PHYSICS | 3005N | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-09-04 | [6 empty] | **9/19/18 DUPLICATE REQUEST SENT IN SEE 19P000246 |  | Paul Ditty | Duplicate work request. | N/A | 2018-09-19 | FS | FALSE | 2018 | 2019-09-01
19P000127 |  | 19P000127 | FALSE | CNAS | SL5 PIERCE PATCH & PAINT | Duplicate request to be combined with 19P000239 | PIERCE | 2301 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | MICHELLE KING |  | N/A |  | Canceled |  | FALSE |  |  | 2018-08-03 | [6 empty] | Paul Ditty |  | Paul Ditty | Paul Ditty |  | 2018-09-21 | FS | FALSE | 2018 | 2019-09-01
19P000413 |  | 19P000413 | FALSE | CNAS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | Batchelor 3111-Refresh BSL2 lab to accomodate Biosafety Cabinet. The Biosafety. Cabinet will be procured by BPSC. | BATCHELOR | 3111 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH | PATTY SPRINGER | Dan Lerman |  | R1 | 107 | FALSE |  |  | 2018-12-17 | [7 empty] | 2019-06-12 | Ron Veloz | 08/26/19 O-RVL: Received email from Deborah Mc Williams to place this request on HOLD "19P000413 – Renovate BH, Room 3111, to BSL-2 will decide in early Spring whether or not to give it an Org allocation or cancel it outright". END~ 08/26/19 O-RVL: RV received the following message from Patty Springer on 08/12/19 " HI Ron, Sorry for the delay in getting back to you. At this time, we don’t have the funds for this project. To be honest, the estimated cost seems very high to me - I especially wonder about $6700 for patch and paint - it is a small room. So, no for now. Thanks, Patty". RV Change Stautus from Hold to Canceled by Client. END~ 08/08/19 O-RVL: Emailed Patty S for status on the departments decision with the project/estimate. Pending response. END~ 07/19/19-RVL: Status on Hold-Pending the customer's acceptance of cost ROM estimate. END~ 07/03/19 O-RVL: Prepared estimate and will review with Monty before contacting Patty Springer or emailing the estimate. RV sent Estimate to Patty on 07/03. END~ 07/02/19 O-RVL: Met with Monty. RV will prepare estimate and call Patty to explain the estimate costs and inclusions based on EH&S requirements and also share concerns about the building infrastructure capabilities questioned by PD&C to meet the BSL2 lab requirements. Explain that the Batchelor Building reno will not increase the building's capacity and the BSL 2 requirement may not be met if the building single pass exhaust and HVAC systems cannot deliver the proper air exchanges etc.. Costs will not include additional work and or building systems modifications if required by PD&C. END~ 07/01/19 O-RVL: Pending estimate completion, hold per Monty on 06/28/19 to discuss/review estimate. END~ 06/24/19 O-RVL: Preparing Estimate. Received costs from Jess H for abatement and to replace flooring. Paul D will providean estimate for patch and paint. END~ 04/15/19 O-RVL: RV to scope project at the new room location 3111. End~ 03/19/19 O-RVL: Updating notes. PENDING Site visit with PM at rm 3111. Date TBD. END~ 06/17/19 O-RVL: Walked site with Patty Springer on 06/12/19. Reviewed SOW and noted work to make the necessary repairs per EH&S survey/correction list. RV will prepare a ROM estimate with project ranges. END~ 03/07/19 O-RVL: RV noticed this project was not on the Minor renovation list and brought up to Monty via email. END~ 03/18/19 O-RVL: RV changed room from 2203 to 3111. END ~ 03/04/19 O-RVL: Changed from O-RVL to O-UA1. END ~ 03/01/19 O-RVL: Received confirmation from Patty that room 3111 will be the permanent location for lab. RV changed the title from SL5-"Install Bio-safety Cabinet and Sink In Batchelor 2203" to SL5 "Renovate Batchelor Hall BSL-2 Lab Room 3111". RV will visit site for initial intake upon prioritization by the Dean's office. END~ 02/19/19 O-RV: Patty "HI Deborah, There is much uncertainty about the Batchelor Hall renovation and the timing of installation of an equipment room in 2163. Given that, I am considering 3111 the permanent location for the biosafety cabinet (replacing room 2203). 3111 will remain a dedicated BSL2 -use room" END ~ 02/14/19 O-RV: Patty Springer decided to try to use 3111 in lieu of 2203. END ~ 02/13/19 O-RVL: Received email from Tiffany Kwok, she wrote, " Hi Dr. Springer, It was great meeting with you this morning. For Batchelor 3111, there are a few items that need to be addressed before it can support BSL-2 work. Floors should be patched to provide a smooth and easily cleanable surface. Base coves along the wall should be replaced or repaired to provide a smooth and easily cleanable surface. Base coves under the cabinets on the corners should be provided. Provide a layer of sealant over the cabinets to ensure that the cabinets are moisture resistant and easily cleanable. Seal, repair or replace the wooden rack on the wall to provide a moisture resistant and easily cleanable surface. Ensure the door is self-closing. END ~ Since this is not a new fac | YES |  | FS | FALSE | 2018 | 2019-09-01 |  | 1
19P000377 |  | 19P000377 | FALSE | CNAS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | Replace the gates on the Schneider House driveway, which secure the property, with the taller iron gates that used to be installed at the Gardens entrance. This will require new fence posts and hinges as well. The taller gates are stored along the side of the garage at Schneider House, and Facilities staff can come see them anytime. Please note this is a safety and security project. | SCHNEIDER |  | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | R2 | 117 | FALSE |  |  | 2018-11-08 | [7 empty] | 2019-04-05 | Ron Veloz | 08/08/19 O-RVL: Estimate on Hold. Cannot ust previous costs from FS trades and require vendor quotes. RV will contact a vendor to price the gate modifications and installation (gates by department). RV will need to 08/02/19 O-RVL: Estimate in progress with FS Pricing. END~ 06/12/19 O-RVL: RV received costs from Sheetmetal and Carpentry, pending estimate from Paint-P. Ditty. 04/15/19 O-RVL: RV updates, Measured gate with Enrico on 4/5. Contacted Cory on 04/15 to schedule a visit on 04/16 to view and estimate Gates. RV will contact Monty with Estimate | YES |  | FS | FALSE | 2018 | 2019-09-01 |  | 1
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | Project Intake | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | DAN LERMAN |  | R3 |  | TRUE |  |  | 2019-03-26 | [8 empty] | Ron Veloz | 08/07/19 O-RVL: RV met with Dan L on 08/07 to compose a final estimate & is in progress (pending vent hood & vac pump pricing). END ~ 08/02/19 O-RVL: SOW is complete, sent Dan L Intake on 08/02 & rev Intake on 08/05. Estimate in progress. End~ 07/08/19 O-RVL: Met with Customer and Dan L on 07/02/19. Customer requested the to keep the shelving and gases on the West table. Requested vacuum pump and lies. Plumbing supervisor investigated and confirmed the building does not have vacuum infrastructure. RV to revise the SOW and send to PM Dan L for review. Dan L will determine the type of "off the shelf" hood to install. Revised SOW is in progress. END~ 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to RVL. | YES |  | FS | FALSE | 2019 | 2019-09-01 |  | 1
19P000555 |  | 19P000555 | FALSE | CNAS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK | INSTALL OF FENCE FOR RAIN COLLECTOR AT TES TANK | SAT CHIL PL | 0 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | DAN LERMAN |  | R4 |  | FALSE |  |  | 2019-04-03 | [6 empty] | 9/3/19, DL; Plans and estimate are complete. Enrico will provide Deborah with a formal estimate and let us know if we will proceed with the work…..8/15/19, DL; Plans are approved. We ware waiting for a estimate from our contractor. Once we have the quote, we will forward the quoted to Deborah for review and approval. Note, this is a recharge project…….8/1/19, DL; Plans are complete pending approval from building official…. |  | Ron Veloz | 08/08/19 O-RVL: Not aware of plans progress. RV will talk with Dan if additional I fo & support is needed. |  |  | FS | FALSE | 2019 | 2019-09-01 |  | 1
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GREENHOUSE #8 | 881 | Project Intake | Kathryn Uhrich | Deborah McWilliams | NANCY FERGUSON |  | DAN LERMAN |  | R5 |  | FALSE |  |  | 2019-01-29 | [8 empty] | Ron Veloz | 08/08/19 O-RVL: R5-Contact Vendors for quotes to prepare estimate. END~ 08/02/19 O-RVL: Acknowledged request and will prepare the estimate. END~ 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to RVL. END~ 03/21/19 O-RVL Updated FAMIS by adding info for 02/26. END~ 02/26/19 O-RVL: RV emailed Monty on 02/26 with information: "I visited head house 8 and spoke with Ken Grombacher yesterday. He is familiar with the need for HCAV at HH #8 and just needs a couple of weeks to order the 3Ton roof top unit (with a heat pump) and will move forward when he is requested to do so by the PM. (SOW) The following trades will be required: Electrical-dedicated circuit, Carpentry -roof cut open and roof patching and BM/Sheet Metal-Duct fabrication/installation. Please let the team know if this becomes a bubble up. RV will complete the intake process". END- 02/25/19 O-RVL: This request was reviewed on 2/25 with team. Monty asked Ron V to look into emails and scope due to weather changes and for bubble up. RV visited the stite & is preparing intake per meeting with Monty & team. Spoke with Building Mechanical-Ken Grombaucher and received info on building trades needed to complete the HVAC 3ton roof top ackaged unit w/ heat pump. (SOW) "Need HVAC/Sheetmetal, Electrical & Carpentry(roof cutting and *roof repair(*Outsourced). Intake in progress. UPDATED on Project bench in FAMIS. Project is not on Access data base as of Feb 25 pm. Intake is in progress. | NO |  | FS | FALSE | 2019 | 2019-09-01 |  | 1
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB | SPIETH | 2349 | Project Intake | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | DAN LERMAN |  | R6 |  | FALSE |  |  | 2019-02-20 | [8 empty] | Ron Veloz | 08/02/19 O-RVL: Acknowledged request and will schedule site visit with outside vendors to request quotes. END~ 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to RVL. |  |  | FS | FALSE | 2019 | 2019-09-01 |  | 1
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | DAN LERMAN |  | R7 |  | FALSE |  |  | 2019-02-27 | [7 empty] | 2018-10-19 | Enrico Baez | 8/9/19 E. Baez-Departemnt is paying for this project rather than having count against their allotment | YES |  | FS | FALSE | 2019 | 2019-09-01 |  | 1
19P000543 |  | 19P000543 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION | TV Bracket &Power/Network box. | CHEMICAL SCI | 342 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | JEFFERY MATUTE |  | DAN LERMAN |  | R8 |  | FALSE |  |  | 2019-03-21 | [8 empty] | Ron Veloz | 08/02/19 O-RVL: Estimate required, RV to schedule walk with vendors for quotes. 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to RVL. | NO |  | FS | FALSE | 2019 | 2019-09-01 |  | 1
19P000594 |  | 19P000594 | FALSE | CNAS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS | Take down a dividing wall in this office and move the desks to their old location and rehang the overhead desk bins back into their old locations with inserts still in the walls. | ENTOMOLOGY | 171 | Project Intake | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | DAN LERMAN |  | R9 |  | FALSE |  |  | 2019-04-26 | [8 empty] | Ron Veloz | 08/08/19 O-RVL: Estimate required, RV to schedule walk with vendors for quotes. 08/02/19 O-RVL: Acknowledged request and will schedule site visit. 06/26/19 O-ANS: Created ESTIMATE phase I and assigned to RVL. | NO |  | FS | FALSE | 2019 | 2019-09-01 |  | 1
3228 | 3228 |  | FALSE | CNAS | Retrofit Screenhouse to Greenhouse | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. Location can be discussed with Greg Greer | RUBIDOUX SCR |  | In Design | Kathryn Uhrich | Deborah McWilliams | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 1080000 |  | 2016-12-06 | Bidding | 2019-12-01 | 2020-03-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
3367 | 3367 |  | FALSE | CNAS | Field 16 Greenhouse Demo & Replacement | Replace GH1 and GH2 with a greenhouse from the Greenhouse Megastore. Conduct geotechnical investigation, prepare drawings and conduct asbestos and lead sampling. |  |  | In Construction | Kathryn Uhrich | Deborah McWilliams | Sue Lee, D. McWilliams |  | Dave Bomba | 1 |  |  | FALSE | 359000 |  | 2017-09-15 | Complete Close-out | 2019-01-30 | 2019-08-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Design | Kathryn Uhrich | Deborah McWilliams | Tracey Kahn, D. McWilliams |  | Scott Donnell | 2 |  |  | FALSE | 340000 |  | 2018-01-08 | Bidding | 2019-12-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3542 | 3542 |  | FALSE | CNAS | Chapman Rm 9 Fume Hood Install | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. |  | 9 | Funding | Kathryn Uhrich | Deborah McWilliams | Rick Redak |  | Scott Donnell | 3 |  |  | FALSE |  |  | 2019-08-01 | Procurement | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3547 | 3547 |  | FALSE | CNAS | USDA Germplsm Apprvls, Permits | The request is to accomplish the necessary UCR-based permit and planning applications, reviews, and approvals, as well as to coordinate requisite utility connections (such as sewer and irrigation) for a Federally-funded renovation project at the USDA Germplasm Facility located on West Campus. |  | First Flr | Plan check & inspection | Kathryn Uhrich | Deborah McWilliams | MaryLou Polek |  | Scott Donnell | 4 |  |  | FALSE |  |  | 2019-05-16 | Plan check & inspection | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
1990a | 1990a |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | Under construction | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2193000 |  | 2015-10-09 | Complete Construction | 2019-05-01 | 2019-11-16 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
2353 | 2353 |  | FALSE | CNAS | Natural Reserves-Sweeney Granite Mountain | This project will add structurally independent facilities for an administration building and researcher housing to provide meeting/office space and short term sleeping quarters. Additionally, the existing laboratory building and staff residence will be extensively renovated. High priority is focused on high insulation values, high wind resistance, rodent proofing, and pursue as much passive cooling and heating as possible with an eye toward low maintenance and high durability. Both new construction and renovation projects are to be sealed to prevent rodent intrusion. The new structures must withstand the harsh environment of extreme temperatures and very high winds. All site improvements shall be done with minimal disturbance to the desert environment. The overarching goal of the project is to provide a sustainable structure that respects its environment and is low maintenance while using best practice design standards. |  |  | In construction | Kathryn Uhrich | Deborah McWilliams | Jim Andre, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2545500 |  | 2015-11-23 | Complete Construction | 2019-01-14 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
1990b | 1990b |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon-Road | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | On Hold | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE |  |  | 2018-06-22 | Bidding | 2019-11-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
19P000428 |  | 19P000428 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES AVC OFFICE PREPARATION |  | STUDENT SERV | 3102 | CANCELED BY CLIENT | LaRae Lundgren | TBD | ANGIE GRAY |  |  |  | 0 |  | FALSE |  |  | 2019-01-03 | [8 empty] | Ron Veloz | 03/18/19 O-RVL: RV received a phone call from Angie Grey on 03/18 to verify if this project was cancelled based on a cancellation request in Jan 2019. RV informed Angie that the project was cancelled. 02/06/19 O-RVL: Updating notes. "Cancelled by Angie Grey on 1/22/19". 02/11/19 O-RVL: Dan L asked RV to confirm with Angie Grey that the project is cancelled. RV called and left a voice message with Angie(2/11). RV will follow up. END--- | N/A | 2019-01-22 | FS | FALSE | 2019 | 2019-09-01
19P000370 |  | 19P000370 | FALSE | ENROLLMENT SERVICES | SL5 PATCH AND PAINT CAMPUS TOURS |  | STUDENT SERV | 1137 | COMPLETE | LaRae Lundgren | TBD | ELIZABETH TATUM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000384 |  | 19P000384 | FALSE | ENROLLMENT SERVICES | SL5 PATCH HOLES IN WALL AND PAINT |  | STUDENT SERV | 2234 | COMPLETE | LaRae Lundgren | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000467 |  | 19P000467 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | WATKINS | 2101 | HOLD - FACILITIES SERVICES | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-22 | [6 empty] | 09/03/19 O-ANS: Updated Priority to #1 for Fall 2019 per Susan request. 9/3/19, We are scheduled to complete the work before winter break begins….. |  | Dan Lerman |  |  |  | FS | FALSE | 2019 | 2019-09-01
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | HOLD - FACILITIES SERVICES | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-22 | [8 empty] | Dan Lerman |  |  |  | FS | FALSE | 2019 | 2019-09-01
19P000560 |  | 19P000560 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION |  | UV BLDG B | 0240B | COMPLETE | Susan Marshburn | Da Lan Dinh | LESLIE ROSE |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-04-04 | [6 empty] | 9/3/19, DL; This project is 100% complete. We still need to conduct training but the work is complete and training is scheduled…..8/15/19, DL; This Project is 90% Complete and will be complete by the end of the week. Please note. ITS still needs to connect the data lines. Our portion of the work is complete………8/1/19, DL; Plans are approved. Material is ordered. We will schedule the work when the material is on site…. |  | Dan Lerman | 4/4/19-JENNIFER- PER ENRICO BAEZ, THIS IS THE WORK ORDER TO GET STARTED ON THE JOB. PLEASE REFER TO WORK ORDER #19W013241 |  |  | FS | FALSE | 2019 | 2019-09-01 |  | 1
19P000645 |  | 19P000645 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT | Termite Treatment/Cover Gate House and repair roughtd woos as necessary | BOTANIC GARDENS |  | CANCELED BY FS | Susan Marshburn | Da Lan Dinh | RONALD ANDERSON |  | DAN LERMAN |  | R2 |  | FALSE |  |  | 2019-05-22 | [8 empty] | Ron Veloz | There will be no additional supporting documentation mailed or faxed. *BOTANIC GARDEN GATE HOUSE (AND OTHER STRUCTURES) REQUIRES EXTERMINATION OF TERMITES- WITH INSPECTION RESULTS RECEIVED BY ERS *PROJECT TO INCLUDE FOLLOWING NEEDS *SECURE PROPER EXTERMINATION FROM OUTSIDE VENDOR- TENTED AND CONDUCTED OVER A WEEKEND (CONFIRMATION FROM BOTANIC GARDENS LEADERSHIP) *POTENTIAL PHASE TO CARPENTRY BASED ON POST EXTERMINATION REVIEW AND ASSESSMENT *POTENTIAL PHASE TO PAINT CREW BASED ON POST EXTERMINATION REVIEW AND ASSESSMENT *FUNDING AND OWNERSHIP OF PROJECT TBD AT TIME OF CREATION. - FS LEADERSHIP TO DISCUSS 08/29/19 O-JSY: PER RON VELOZ (directed by Monty)PROCESS WORK ORDER AND DIRECT TO PEST CONTROL Project # 19P000645/WR# 19W016944 was canceled and new work request 20W003693 created and assigned to Pest control by Jen Seeley. 08/02/19: RV forwarded the extermination report and quote to Hassan on 07/23/19. Not sure what FS involvement is for pest control. RV will place on Hold and speak with Monty on the next step. 07/11/19 O-ANS: Re-assigned RECHARGE project to DLN and added to Access by Linda. 07/02/19 O-ANS: Project awaiting prioritization for Summer 2019 by Dean’s Delegate. Status PENDING. 07/02/19 O-ANS: Project prioritized as RECHARGE "R2" per Summer 2019 Prioritization. Estimate phase I created and assigned to BZM. |  | 2019-08-29 | FS | FALSE | 2019 | 2019-09-01 |  | 1
3498 | 3498 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY18) Manhole C6 Modification | Construct new sanitary sewer lines, New manhole, pipe connections, demo existing manhole. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Gerald Caraig | 2 |  |  | FALSE | 220200 |  | 2019-02-25 | Complete Construction | 2019-08-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
3527 | 3527 |  | FALSE | FAC-PLNG-DESIGN-CONST | Central Utility Plant Fire Alarm | Replace aging and non-replaceable fire alarm system, and conduit. Conduit is damaged and only 10% of wiring is usable. ( fire alarm system and devices are failing and they are not supported by manufacture ) -Run new conduit from propane tanks to fire alarm system -Install new terminal box at propane tanks. -Pull twenty two, 14 awg THHN wires in new conduit and terminate in junction box. -Replace 25 year old fire alarm panel, parts are not available to maintain system. -Add ada compliant horn/strobes thru out structure. -Add code compliant indicating devices thru out structure. -Replace 8 flame detectors -Replace all fire sprinkler devices on riser. -Flow switch. -Pressure switches. -Tamper switches. -Replace high capacity sounder at propane tanks. -Engineering, and drawings to be submitted to fire marshal for approval. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Ben Kochevar |  | Scott Donnell | 4 |  |  | FALSE |  |  | 2019-05-08 | Complete Project | 2019-07-01 | 2020-03-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
3528 | 3528 |  | FALSE | FAC-PLNG-DESIGN-CONST | Entomology Museum Fire Alarm | Deferred Maintenance Project. Fire alarm system and devices are failing and they are not supported by manufacture. -Replace fire alarm system and all existing fire alarm peripheral devices. -Engineering, and drawings to be submitted to fire marshal for approval. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Ben Kochevar |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2019-05-14 | Complete Project | 2019-07-01 | 2019-12-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | (DMFI) Physics 2000 Renewal | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 6 |  |  | FALSE |  |  | 2019-05-15 | Complete Construction | 2019-07-01 | 2019-09-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Design | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 7 |  |  | FALSE | 600000 |  | 2019-06-18 | Receive revised 100% Specs | 2019-12-02 | 2020-05-29 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 8 |  |  | FALSE | 1250000 | 0 | 2018-10-17 | FS Direction | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3275 | 3275 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Fiber Optic Infrastructure Upgrade | Repair, replace and upgrade the fiber optic infrastructure network that includes 50+ buildings across campus. Also includes work to main hubs, sub hubs and make available spare fiber for future utilization. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | ----- |  | Daneca Stevens | 9 |  |  | FALSE | 643750 |  | 2017-04-12 | Award Contract | 2019-11-01 | 2020-04-01 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3437 | 3437 |  | FALSE | FAC-PLNG-DESIGN-CONST | UCPD Generator Replacement | Replace unsupported 125kw generator with new - Critical Facility |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Fernando Nunez | 10 |  |  | FALSE | 300000 |  | 2018-10-08 | Complete Construction | 2019-07-01 | 2019-12-27 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY15) Roofing - Spieth Hall/LSP | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. |  |  | In design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 10 |  |  | FALSE | 432510 |  | 2016-02-25 | Bidding | 2019-12-01 | 2020-01-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
3270 | 3270 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Chapman Hall - Replace HVAC System | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | CHAPMAN |  | In Close-out | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Scott Donnell | 11 |  |  | FALSE | 595819 |  | 2017-03-07 | Complete Close-out | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
3271 | 3271 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Life Sci/Spieth Hall Elevator Renewal | Scope of work includes the number 3 and 4 elevators of Spieth Hall. Project budget is $344,898.00. Estimated construction cost is $250,400.00. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 12 |  |  | FALSE | 345000 |  | 2017-03-07 | Award Contract | 2019-10-21 | 2020-08-28 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3272 | 3272 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Athletic/Dance Elevator Renewal | Project budget is $219,371.00. Estimated construction cost is $169,020.00. | ATH DANCE |  | Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 13 |  |  | FALSE | 220000 |  | 2017-03-07 | Award Contract | 2019-10-21 | 2020-08-28 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3064 | 3064 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Botanic Gardens Basin Silt Removal | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | BOTAN INFO C |  | On hold | Susan Marshburn | Da Lan Dinh | Toshio Ishida |  | Scott Donnell | 41 |  |  | FALSE | 110000 |  | 2016-04-20 | Funding | [11 empty] | PD&C | FALSE | 2016 | 2019-09-01
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Rivera Library Arches/Arcade Repair | Paint and replace roof. |  |  | Bids received, award on hold due to DM funding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Jason Espinoza | 99 |  |  | FALSE | 240000 |  | 2016-05-06 | Funding | [11 empty] | PD&C | FALSE | 2016 | 2019-09-01
2671 | 2671 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Elevator Mods-Various Bldgs | Provide Vertical Transportation Consulting, Mechanical, Electrical, Fire Alarm and Architectural/Structural Construction document design and specifications for the modernization of two (2) elevators at Webber and Watkins buildings which is included in the base design and one (1) elevator at the Entomology Museum is included as an add alternate. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 99 |  |  | FALSE | 596011 |  | 2016-01-05 | Award Contract | 2019-10-21 | 2020-08-28 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
2805 | 2805 |  | FALSE | FAC-PLNG-DESIGN-CONST | West Campus Water Well | Drill a water well on AGOPS property. This will be funded out of Energy Savings and Minor Cap Approval has been signed. |  |  | On Hold | Susan Marshburn | Da Lan Dinh | Ken Muelleer |  | Scott Donnell | 99 |  |  | FALSE | 250000 |  |  | CEQA | [11 empty] | PD&C | FALSE | 1900 | 2019-09-01
19P000411 |  | 19P000411 | FALSE | GRAD.DIV | SL5 PAINT, CARPET AND BLINDS |  | UNIV OFC BLD | 150 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-14 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000399 |  | 19P000399 | FALSE | GRAD.DIV | SL5 NEW CARPET + WALL PAINT |  | UNIV OFC BLD | 100 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-06 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000572 |  | 19P000572 | FALSE | GRADUATE DIVISION | SL5 PATCH, PAINT, AND CARPET UOB 152 |  | UNIV OFC BLD | 152 | IN PROGRESS |  |  | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-11 | [6 empty] | 06/28/19 O-ANS: Paint phase complete and awaiting carpet change. | [5 empty] | FS | FALSE | 2019 | 2019-09-01
18P000313 |  | 18P000313 | FALSE | GSOE | SL5 SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-15 | [6 empty] | 18W011689 Work order was cancelled because it has the same scope and is a duplicate………DL, 6/16/18; Contract is being awarded this week. Weill are scheduled to have this work completed by fiscal closing……DL, 7/25/18; This Project is 100% Complete…..9/13: Zee - Customer noted paint peeling; updated to status to back in progress for work to be addressed.......DL, 9/19/18; The contractor is on site repairing the walls and painting. The work should be complete this week.......dl, 10/4/18; tHIS PROJECT IS 100% Complete..... |  | Paul Ditty |  | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000274 |  | 18P000274 | FALSE | GSOE | SL5 SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 |  | EADY CENTER |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES | BRANDON BARBOSA | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-18 | [6 empty] | 2/14/19, DL; This project is Complete………….2/1/19, DL; This project is 99.9% Complete. We still need to conduct Final inspection with Building inspector……1/15/19, DL; The door and automatic opener is scheduled to be installed on 1/22/19……..12/14/18, DL; This project is 95% complete. The contract for the door and ADA operator was awarded today. We will schedule the work shortly after the new year…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Conducted site visit with Gilbert. We need to have a meeting to determin if this work is part of the SLA…… DL, 6/16/18; We still need direction, SLA or Recharge?.......DL, 7/11/18; This Project will require Plans and Permits. We will start on the Plans next Week. We will also issue work orders for work we will complete with in house staff. The Concrete work and Entry Door will need to be contracted out. Target Complete date is 10/1/18……..DL, 7/25/18; Work orders are produced. Planing to walk the project with Chris, Steve B and Robert C. thisw week or next week. We will submit plans to Bob Williams for the contracted work next week……DL, 8/8/18; Completed site visit with Robert C. Steve B, Steve T. and Chris; the Plumbers are complete. The carpenters and electricians will work on their items over the next three weeks. The Plans will be ready to submit on 8/9/18. Once plans are approved, we will proceed to go out to bid for the Concrete and the ADA operator. Target complete date is 9/21/18…….DL, 8/22/18; Plans were apprroved, Concrete Contract is being executed. Still working on Door and ADA operator……..DL, 9/6/18; NTP for Concrete will be issued on Monday. I will schedule the work. I need to follow up on the door order and the ADA operator…….DL, 9/19/18; Concrete walkway scheduled to start on 9/20/18. The new door and Frame will arrieve in 3-5 weeks. We will schedule the install when the new door and frame are on site…….DL, 10/4/18; Concrete work is complete. Still need handrail, signage, door and ADA operator. Target date is Early November….DL, 11/7/18; Project is 95% complete. Contract is being processed to install the new Door, Door Fram and ADA operator. Goal is to have the work complete befor the winter break…… |  | Enrico Baez | Duplicate of 18W011999 project scoped and note entered to make facility ADA compliant. | YES | 2019-02-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000054 |  | 19P000054 | FALSE | GSOE | SL5 PATCH & PAINT OFFICE |  | SPROUL | 2131 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-26 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000628 |  | 19P000628 | FALSE | GSOE | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2129 | QUEUE TO START | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-05-15 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000237 |  | 19P000237 | FALSE | GSOE | SL5 PATCH AND PAINT OFFICE - SPROUL 1206 |  | SPROUL | 1206 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 4/15/19, DL; Project is 100% Complete….. 2/1/19, DL; This project will start on 3.1.19. We will need to abate ACM before we can start. Jess will isuue the 14- day notification to the AQMD. Once we have confirmation, we will schedule the work…….. | 2018-10-05 | Enrico Baez | 0/5/18 E. Baez- conducted site visit. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000627 |  | 19P000627 | FALSE | GSOE | SL5 SPROUL HALL, RM 2120 - PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2120 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-05-15 | [6 empty] | 08/13/19 O-ANS: Customer requested that project be moved to Fall 2019 list for prioritization. | [5 empty] | FS | FALSE | 2019 | 2019-09-01
19P000217 |  | 19P000217 | FALSE | GSOE | SL5 PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 |  | SPROUL | 1359 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-27 | [6 empty] | 4/15/19, DL; This project is 100% Complete…..2/1/19, DL; This proect will start on 3/1/18 and should be complete by 4/1/19…… | 2018-09-18 | Enrico Baez | 9/18/18 E. Baez Conducted site visit. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000229 |  | 19P000229 | FALSE | GSOE | SL5 RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-08-29 | [6 empty] | 6/15/19, DL; This Project is 100% Complete….. |  | Enrico Baez | 11/13/2018 E. Baez-Met with Ron Rector to discuss system placement. WEPA system is to be placed on second floor near vending machines on North side. See note in shared drive. Will need power and data connections. ---9/20/18 EB-conducted site visit 9/18. Request for tile and plumbing removal, patch and paint. To facilitate placement of printer system. E-mail sent to Monty on 9/14 asking for direction on renovating hallway space. Awaiting Susan's response per Monty. Entered scope on shared drive. Will need Fire Marshal approval to determine which of three possible locations will allow placing of WEPA system. | YES | 2019-06-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18W007453 |  | 18W007453 | FALSE | ITS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-11-30 | [6 empty] | 07/22/19 O-ANS: Work Order converted to project # 19P000433. For further updates, see 19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  |  | WO converted to project #19P000433. |  | 2019-07-22 | FS | FALSE | 2017 | 2019-09-01
19P000293 |  | 19P000293 | FALSE | ITS | SL5 PAINT ESTIMATE REQUEST |  | TELEPHONE |  | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-21 | [6 empty] | n/a |  | Paul Ditty | Canceled by Customer 10/24/18 | N/A | 2018-10-24 | FS | FALSE | 2018 | 2019-09-01
18P000474 |  | 18P000474 | FALSE | ITS | SL5 MS&E ELECTRICAL MODIFICATIONS FOR ITS |  | MAT SCI ENGR | 119 | COMPLETE | Danna Gianforte | Shelley Gupta | MICHAEL CAPRIOTTI |  | Robert Corey |  |  | 1 | FALSE |  |  | 2018-06-13 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…….2/28/19, DL; Work is scheduled with Darrenn F. for Spring Break…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. |  | Enrico Baez | 7/17/18 EB-Scheduling site visit with Michael Capriotti 8/7/18 EB- Met with Robert Corey to discuss scope of work. He will coordinate work. | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19W002419 |  | 19W002419 | FALSE | ITS | SL5 ITS CENTER - INSTALL CARD READER ACCESS |  | ITS CENTER | 161 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-08-09 | [9 empty] | 1/8/19: O-ANS: Converted to a project 19000433 and canceled in FAMIS. |  | 2019-01-08 | FS | FALSE | 2018 | 2019-09-01
18P000471 |  | 18P000471 | FALSE | ITS | SL5 WCH INSTALL SECURITY FENCE |  | CHUNG HALL | 134 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  |  | 5 | FALSE |  |  | 2018-06-12 | [6 empty] | DL, 7/4/18; Walked this project with Angel, This request is to install security fence with Sliding gate and welded webs to increase security. Space is vacant and ready to schedule work. Need to walk with Corey to see if this is a project they can do or sub out to De ANza fence......DL 7/25/18; Still need to walk project with Corey. Dl, 8/10/18; Site walk complete, we are waiting on estimates. WE will try and schedule the work with in the next 30- days....DL, 8/22/18; Work is scheduled for August 27th. Still need to order hardware.....DL, 9/6/18; The fence is installed and Angel is very Happy, but I need to check the project to verify we are good to go....DL, 9/19/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000373 |  | 19P000373 | FALSE | ITS | SL5 URGENT-INSTALL RECPTACLE, ENCLOSURE & MOUNT BRACKET |  | GERMPLASM | 881 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-07 | [6 empty] | <div>mount a bracket to the Network Pole at AgOps. This will include mounting a bracket, an enclosure and a 20 Amp electrical receptacle.</div> |  | Ron Veloz | 2/26/19-LB: Per Ron Veloz, this project is complete. |  | 2019-02-26 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000252 |  | 18P000252 | FALSE | ITS | SL5 CHASS INT S REPLACE ELECTRICAL SCREENS |  | CHASS INT S | 2130 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | JORGE MACIAS |  | Dan Lerman |  | 1 | 2 | FALSE |  |  | 2017-12-21 | [7 empty] | 2018-06-21 | Ron Veloz | 01/23/19 O-RVL: RV received confirmation (Telcon) with Jorge Macias to cancell the request. He will resubmit upon recipt of screens at a later date. RV instructed the Front desk(FS) to close out the request & "cc" Monty, Alan, Enrico & Linda & Loretta. END--- 01/23/19 O-RVL: RV emailed Jorge to verify status of the request/materials order. Pending response. END--- 01/09/19 O-RVL: RV spoke with Jorge on 1/09. Jorge expect screens to be ordered within two weeks and will cancel this request if the screens are not ordered by his department. Jorge asked to contact him in two weeks (01/23/19). END---6/21/18 RV HOLD, Walked site w/ Enrico & Jorge. Surveyed site and Enrico updated FAMIS & Project folder. Now pending - confirmation of party to purchase projection screens. S.O.W.: Remove two non functional motorized video screens. Replaced with new larger screen. Patch and repaint all walls and entry door. END--- 07/06/18 Ron V Input notes: Received email from Enrico on 07/03 confirming Facilities Services doe not purchase Audio Visual equipment in General Assigment class rooms. On 07/06 RV contacted Jorge Macias with this info and Jorge said he would get back to RV with follow up reply from his supervisor. Confirmed with E.B. that proj info/ photos are updated on the project folder and FAMMIS. END--- 8/22/18 O-RVL: Will follow up with Jorge to confirm status on the screen purchase and if Media will purchase the screens. END--- 08/23/18-RV emailed Jorge, Pending response. END--- 08/24/18-RV, Enrico followed up with Jorge, projection screens approved but not purchased yet). END--- 10/17/18: RV spoke with Jorge today and he said screens are on order. Jorge will follow up with updates to RV and Enrico. | YES | 2019-01-24 | FS | FALSE | 2017 | 2019-09-01
18P000382 |  | 18P000382 | FALSE | ITS | SL5 ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | PHYLLIS FRANCO |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL, This project is Complete……12/14/18, DL; This project is scheduled to be complete shortly after the winter break…….This project was scoped previously with the IR Team. We may need plans or a permit because we are installing a Dutch door…..DL, 7/11/18; Need to produce work orders and schedule the work….. DL, 7/25/18; Still need to produce work orders and schedule the work. Target date is 10/1/18 | 2018-07-06 | Ron Veloz | 06/29/18 Ron V: SOW, Remove the existing non rated solid core door & grille and replace with a new maple veneerd Dutch door with prefinished clear coat without grille. Door to be prepped on the hinge side with one continoues hinge. Confirm/field verify is a double bevel on door is requird. Do not prep the strike/lockset side.. Cylinder to be bored onsite by Lock shop. The top of the lower door to have a small shelf + - 6-8 inches wide, confirm size with Duffy prior to ordering the door. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | 2019-01-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000381 |  | 18P000381 | FALSE | ITS | SL5 ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 3 | 4 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL; This project is complete. Note, Duffy only wanted the dutch door completed……..12/14/18, DL; This project is in progress and should be complete shortly after the new year……`DL, 7/11/18; Need to walk the project and schedule the work…… | 2018-07-06 | Ron Veloz | 06/26/18 Ron V. visited site & met with Duffy. Scope of work for rm's 2103 & 2103 A requires: Painting of walls and conduit locted on the walls, replace damaged ceiling tiles, replace one damaged prismatic 2x4 light fixture lense, remove one tack board and shampoo carpet. Existing wall tiles to remain and receive paint. No work required in 2103 B per Duffy. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | 2019-01-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000021 |  | 19P000021 | FALSE | ITS | SL5 ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS |  | ITS CENTER |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-07-12 | [6 empty] | 4/15/19, DL; This project is 100% Complete…… 3/28/19, DL; Monitors are done. Nee to finish the install of data and power…….12/14/18, DL; Still need to review scope….. |  | Enrico Baez | Met with IT staff. T.V. to be mounted in 4 locations. Will need electrical and painting in some locations. Waitng for updated scope from Joe Sepulveda | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000194 |  | 18P000194 | FALSE | ITS | SL5 TELEPHONE WINDOW REPLACEMENT |  | TELEPHONE | 101 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 5 | 6 | FALSE |  |  | 2017-11-20 | [6 empty] | 07/23/19 O-ANS: Canceled by customer per notes in FAMIS. |  | Enrico Baez | EB-1/31/18 Conducted site visit. Request to replace all exterior Plexiglas with glass. Will call glass vendor to provide estimate. 7/12/18 EB-Quote provided by Hour Glass. Emailed Tami, she is waiting for budget approval to proceed with project. Should have by end of July. 10/22/18 Customer Canceled; will resubmit when ready to proceed. | YES | 2018-10-19 | FS | FALSE | 2017 | 2019-09-01
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | COMPUTING | 161 | PLAN DEVELOPMENT/CHECK | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 2019-01-07 | [6 empty] | 8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, Once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was canceled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez | 7/26/2019 E. Baez Re-assigned RECHARGE project to DLN and added to Access by Linda. |  |  | FS | FALSE | 2019 | 2019-09-01 |  | 1
3396 | 3396 |  | FALSE | ITS | C&C Rear Patio Tables/Shade | Installation of new exterior concrete slab and patio cover at the Computing and Communications Modular Buildings. The existing site will be cleared of all landscape to provide clear area to install concrete slab and address any grade/drainage issues. The addition of a proposed permanent patio cover is to be installed with full electrical options (lights, outlets, ceiling fans) to provide shade for future events and exterior lunch area. Shrubs along the street at the East side of the area are to be removed to provide a vendor/service ramp for events with the inclusion of lighted concrete seating within the space. | ITS CENTER |  | In Programming | Danna Gianforte | Shelley Gupta | Sheila Mabee |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2017-11-16 | Complete Project Study | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
18P000273 |  | 18P000273 | FALSE | LIBR | SL5 RIVERA LIB -RESTROOM REFRESH PROJECT |  | RIVERA LIB |  | TO BE PERFORMED BY PD&C | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2018-01-18 | [6 empty] | DND 12/13/18: Customer advised maintenance requests related to project request has been addressed. Renovation work to be performed by PD&C and customer submitted a CPMS request. DL, 6/16/18; Need to schedule site visit with Dave and Chris P…….DL, 7/11/18; Chris and I will walk this poroject next week…..Wlaked projects with Chris. We need to review in more detail to better determin the process for this project…..DL, 9/6/18. WE need to discuss what we are going to do with this project.... We walked the project but we now need Direction from Facilities leadership… |  | Dan Lerman | .Scope of work has been reviewed; determining how to complete project with trades. DL, 4/29/18; Chris said he is aware of project scope. I need to review with Chris and schedule the work;…..Dl, 5/3/18; Dand to walk project with Chris and Dave to confirm scope. We will sub out tile work. This is paint tile, lighting and plumbing fixture upgrade…. | YES | 2018-12-13 | FS | FALSE | 2018 | 2019-09-01
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. |  |  | Client approval/funding | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 2018-11-27 | Client approval/funding | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3413 | 3413 |  | FALSE | LIBR | Rivera Libr Gender Incl Restroom | Convert existing non-ADA multi-stall women's restroom to compliant ADA gender inclusive restroom. The project also involves the conversion of an existing non-ADA men's restroom to women's compliant ADA restroom. | RIVERA LIB |  | On Hold | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Dave Bomba | 3 |  |  | FALSE | 0 |  | 2018-03-26 | Funding Design | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3104 | 3104 |  | FALSE | PALM DESERT GRAD CTR | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Programming | Tamara Hedges | Zelda Glenn | Zelda Glenn |  | Scott Donnell | 1 |  |  | FALSE | 22000 |  | 2016-05-12 | Funding | [11 empty] | PD&C | FALSE | 2016 | 2019-09-01
2747 | 2747 |  | FALSE | PALM DESERT GRAD CTR | Heckmann Ctr-Landscaping (Donor Orchard) | UCR Palm Desert would like to replace the current turf grass with water-wise, sustainable landscaping. In return for the opportunity to use a “living laboratory” classroom for training, UC Cooperative Extension Master Gardener program has agreed to collaborate with UCR to revise and sustain the landscaping. The first phase will be to create an orchard to highlight UCR’s contributions to agricultural research in the Coachella Valley. The orchard will be located at the entrance to the Heckmann building, north of the walkway. UCR Physical Plant/Grounds to provide estimate for: • Project oversight • Project plan and drawings • Organic material to add to soil • Irrigation materials and installation • Edging for path • Weed cloth • Decomposed granite with stabilizer for ground cover • Decomposed granite with stabilizer for pathway • Concrete pad for art including bolting apparatus • Arbor for grapes • Flow system-fertigation • All other labor and materials other than kiosk, plant signage, turf and tree removal (current landscape maintenance vendor can remove) and plant materials and plant installation | HECKMAN ICEM |  | In Programming | Tamara Hedges | Zelda Glenn | Mike Lawrence |  | Scott Donnell | 2 |  |  | FALSE | 13800 |  | 2014-08-18 | Design | [11 empty] | PD&C | FALSE | 2014 | 2019-09-01
18P000390 |  | 18P000390 | FALSE | PLANNING & BUDGET | SL5 UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD |  | UV BLDG B | 0240B | COMPLETE | Gerry Bomotti | Sharyl Murdock | LESLIE ROSE |  | Paul Ditty |  |  | 1 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
17P000254 |  | 17P000254 | FALSE | PLANNING & BUDGET | SL5 FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS |  | CORP PP WHSE | 0106B | CANCELED BY CLIENT | Gerry Bomotti | Sharyl Murdock | DALAN DINH |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-06-07 | [6 empty] | 05/08/19 O-ANS: Canceled by customer per email from Deborah McWilliams. .2/1/19, DL; Material is ordered with a 4-6 week lead time.11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DD 10/6: On hold pending discussion on space…..DL, 7/11/18; I understand there is movement on this project but I need to check in with John P. or Chris P. for a status update. |  | Enrico Baez | 3/7/19 O-ANS: Project no longer moving forward per Ron Rector. ~ 12/14/18 O-RVL: F & LS shop space/Shop Location TBD. | NO | 2019-04-05 | FS | FALSE | 2017 | 2019-09-01
19P000209 |  | 19P000209 | FALSE | PLANNING & BUDGET | SL5 OLD EH&S SITE- FS ANNEX A REMODEL |  | ENV H AND S | 100 | COMPLETE | Gerry Bomotti | Sharyl Murdock | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 2018-08-24 | [6 empty] | 7/1/19, DL; This project is 100% Complte….6/17/19, DL; This project is almost complete. Target complete date is 6/26………….5/31/19, DL; This project is in progress. Our goal is to have the projected completed by June 28th……. 5/15/19, DL; We are schedule to start the demo tomorrow. Project timeline is 3-4 weeks….3/28/19, DL; Gunther is working on plans……3/18/19, DL; Conducted site visit with Chris, Hassan and Francis last week. We will work on plans and permits…….9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen | Chris walked the project with Craig Kasten on 9/6/18. | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-09-01 | FY 19-20
18P000324 |  | 18P000324 | FALSE | PLANNING & BUDGET | SL5 HINDERAKER PATCH AND PAINT |  | HINDERAKER | 4118 | COMPLETE | Gerry Bomotti | Sharyl Murdock | MILLY PAREDEZ |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-02-26 | [8 empty] | Paul Ditty |  | N/A | 2018-07-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000241 |  | 19P000241 | FALSE | PLANNING & BUDGET | SL5 PATCH/PAINT IN OFFICE 2122 HINDERAKER |  | HINDERAKER | 2122 | CANCELED BY CLIENT | Gerry Bomotti | Sharyl Murdock | MILLY PAREDEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-06 | [8 empty] | Paul Ditty | Canceled per customer call on 9/13/18 | N/A | 2018-09-13 | FS | FALSE | 2018 | 2019-09-01
19P000401 |  | 19P000401 | FALSE | PLANNING & BUDGET | SL5 PATCH HOLES IN WALL AND PAINT |  | HINDERAKER | 4148E | COMPLETE | Gerry Bomotti | Sharyl Murdock | SHANNON TIMMONS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000414 |  | 19P000414 | FALSE | PLANNING & BUDGET | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | PLAN DEVELOPMENT/CHECK | Gerry Bomotti | Sharyl Murdock | KELLY DUNCAN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-12-17 | [6 empty] | 9/3/19, DL; This is The Quequ for plans, we will start the plans in the next two weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez | 7/8/2019 E.Baez-Spoke with Dan. Work has alread been scoped and will be scheduled by Dan. 7/1/2019 E. Baez-Voice mail to Dan to determine project needs to be scoped. |  |  | FS | FALSE | 2018 | 2019-09-01
19P000665 |  | 19P000665 | FALSE | PLANNING & BUDGET | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | Existing telephone-communications building on University Ave requires repairs and renovation in preparation for new use as fire safety offices. | TELEPHONE |  | IN PROGRESS | Gerry Bomotti | Sharyl Murdock | Carmen Long | Melissa Garrety | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-03 | [6 empty] | 9/3/19, DL; Abatement was complete this weekend. Trades are schedule and we are on track for 11/15/19 complete date…..8/15/19, DL Plans were approved this week. Abatement is still needed and the 14- day notification to AQMD is complete. We are on track to complete the work by mid November……. |  | Enrico Baez |  |  |  | FS | FALSE | 2019 | 2019-09-01
19P000425 |  | 19P000425 | FALSE | PLANNING & BUDGET | SL5 PAINT VIDEO PRODUCTION SUITE & HANG ITEMS |  | HINDERAKER | 1159A | COMPLETE | Gerry Bomotti | Sharyl Murdock | LISA CUSICK |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-20 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000599 |  | 19P000599 | FALSE | PLANNING & BUDGET | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | Sharyl Murdock | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 2019-05-09 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20 | 1
19P000573 |  | 19P000573 | FALSE | PLANNING & BUDGET | SL5 UNIVERSITY VILLAGE PAINT /REMOVE NAILS |  | UV BLDG B | 0208L | CANCELED BY CLIENT | Gerry Bomotti | Sharyl Murdock | JUDITH ABBEY |  | Paul Ditty |  | R2 |  | FALSE |  |  | 2019-04-11 | [6 empty] | 06/14/19 O-ANS: Canceled by Customer via email from Georgianne Carlson "Project 19P000573, UV Room 208L. Human Resources Department has withdrawn the request for this patch and paint project. Not a priority, at this time." |  |  | Canceled by client 6/14/19 |  | 2019-06-14 | FS | FALSE | 2019 | 2019-09-01 |  | 1
3516 | 3516 |  | FALSE | PLANNING & BUDGET | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | In Programming | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Gerald Caraig | 1 |  |  | FALSE | 33980000 |  | 2019-03-04 | Workgroups | 2021-01-04 | 2022-06-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
3520 | 3520 |  | FALSE | PLANNING & BUDGET | College Building South Seismic Improvements | Full building seismic retrofit to College Building South. |  |  | On-hold pending UCOP decision | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Jason Espinoza | 2 |  |  | FALSE |  |  | 2019-04-02 | On-hold pending UCOP decision | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3515 | 3515 |  | FALSE | PLANNING & BUDGET | DM(FY18) Elec Substation & Infra. Renewal |  |  |  | In Programming | Gerry Bomotti | Sharyl Murdock | Ron Rector |  | J.Franklin/G.Caraig | 3 |  |  | FALSE | 5610000 |  | 2019-03-08 | Field Data Gathering | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3521 | 3521 |  | FALSE | PLANNING & BUDGET | Life Sci Unit 2 Seismic Improvements | Full building seismic retrofit of Life Sciences Unit 2. |  |  | On-hold pending UCOP decision | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Jason Espinoza | 3 |  |  | FALSE |  |  | 2019-04-02 | On-hold pending UCOP decision | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3523 | 3523 |  | FALSE | PLANNING & BUDGET | 1907 Mt Rubidoux Facility Study | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. |  |  | Study in Progress | Gerry Bomotti | Sharyl Murdock | Melissa Garrety |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2019-04-22 | Complete Study | 2019-06-01 | 2019-10-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
3504 | 3504 |  | FALSE | PLANNING & BUDGET | Silver Oaks Womens Health TI Fees | UCR Health will be acquiring new off-campus leased space by expanding into an adjacent medical office suite located at 19330 Jesse Ln #160, Riverside, CA 92508. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. |  |  | SOM to manage project | Gerry Bomotti | Sharyl Murdock | Brandon Barbosa |  | Brandon Barbosa | 7 |  |  | FALSE |  |  | 2019-02-14 | SOM to manage project | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3510 | 3510 |  | FALSE | PLANNING & BUDGET | SOMED Data Center Study | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. |  |  | Programming | Gerry Bomotti | Sharyl Murdock | Daneca Stevens |  | Daneca Stevens | 8 |  |  | FALSE | 55000 |  | 2019-03-04 | Complete Study | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3501 | 3501 |  | FALSE | PLANNING & BUDGET | DMFI(17-19) Watkins 1000 Lecture Hall Reno | Renovation of Watkins 1000 lecture hall, to include lighting, HVAC, flooring, paint, and seating upgrades. This requests appears as projects Q-T on the approved 2017-2019 DMFI Program list. |  |  | In Bidding | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 9 |  |  | FALSE | 638000 |  | 2019-03-04 | Award Contract | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3508 | 3508 |  | FALSE | PLANNING & BUDGET | SOM New Academic Facility | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | Programming | Gerry Bomotti | Sharyl Murdock | Melissa Garrety |  | Mihai Gavan | 10 |  |  | FALSE |  |  | 2019-03-04 | Bidding | 2021-03-01 | 2023-02-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
3507 | 3507 |  | FALSE | PLANNING & BUDGET | Undergrad Class Labs & Studios Teaching Facility |  |  |  | Pre-programming | Gerry Bomotti | Sharyl Murdock | Michelle Baniqued |  | Blythe Wilson | 11 |  |  | FALSE |  |  | 2019-03-04 | Programming | 2021-03-01 | 2023-01-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
3492 | 3492 |  | FALSE | PLANNING & BUDGET | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Study in process | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 12 |  |  | FALSE | 65000 |  | 2019-03-04 | Complete Study | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3499 | 3499 |  | FALSE | PLANNING & BUDGET | Creekside Terrace Analysis | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Design | Gerry Bomotti | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 13 |  |  | FALSE |  |  | 2019-02-14 | CEQA | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3505 | 3505 |  | FALSE | PLANNING & BUDGET | Orange County Psychiatry | UCR Health will be acquiring new off-campus leased space by moving into an adjacent medical office suite located at The Airport Tower, 18881 Von Karman Ave #1227, Irvine, CA 92612. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. |  |  | SOM to manage project | Gerry Bomotti | Sharyl Murdock | Brandon Barbosa |  | Brandon Barbosa | 14 |  |  | FALSE |  |  | 2019-02-19 | SOM to manage project | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
3474 | 3474 |  | FALSE | PLANNING & BUDGET | RUSD STEM High School |  |  |  | Real Estate project | Gerry Bomotti | Sharyl Murdock | ----- |  | Thomas Toepfer | 17 |  |  | FALSE | 0 |  | 2018-10-31 | Regents Approval of Ground Lease | 2020-07-01 | 2022-06-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
2900 | 2900 |  | FALSE | PLANNING & BUDGET | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | BATCHELOR |  | In Design | Gerry Bomotti | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 18 |  |  | FALSE | 18179000 |  | 2015-12-15 | Contractor Review of Building | 2020-01-01 | 2021-11-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
2839 | 2839 |  | FALSE | PLANNING & BUDGET | Multidisciplinary Research Building | External financing provided for this project. Total approved budget is $150,000,000. Confirmed per CPMX and BEA#978864 Xfer Tax Exemp Comm Paper. Funding received 7/25/2016. |  |  | Coordinating 2nd Phase Move-in & Related TI's | Gerry Bomotti | Sharyl Murdock | Jon Harvey |  | Mihai Gavan | 19 |  |  | FALSE | 156405000 |  | 2015-04-01 | 2nd Phse Move/TI | 2016-07-01 | 2018-09-28 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
2899 | 2899 |  | FALSE | PLANNING & BUDGET | Pierce Hall Improvements | Replacement of Mechanical, Plumbing and Electrical Infrastructure | PIERCE |  | In Construction | Gerry Bomotti | Sharyl Murdock | Jon Harvey |  | Dave Bomba | 21 |  |  | FALSE | 38560000 |  | 2015-08-06 | Phase I Completion | 2019-01-01 | 2020-02-01 | [9 empty] | PD&C | FALSE | 2015 | 2019-09-01
2368 | 2368 |  | FALSE | PLANNING & BUDGET | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Programming | Gerry Bomotti | Sharyl Murdock | Katie Sanchez |  | Gerald Caraig | 22 |  |  | FALSE | 2600000 |  | 2016-05-19 | Design | [11 empty] | PD&C | FALSE | 2016 | 2019-09-01
3470 | 3470 |  | FALSE | PLANNING & BUDGET | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | New Study | Gerry Bomotti | Sharyl Murdock | Drew Hecht |  | Drew Hecht | 23 |  |  | FALSE |  |  | 2018-11-06 | Complete Review | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3110 | 3110 |  | FALSE | PLANNING & BUDGET | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded/never routed to the Dispatcher. 90% CD's completed. | Gerry Bomotti | Sharyl Murdock | Marianne Valenti |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | License Agreement Final Review | 2019-09-01 | 2020-07-01 | [9 empty] | PD&C | FALSE | 1900 | 2019-09-01
2774 | 2774 |  | FALSE | PLANNING & BUDGET | Highlander Hall Demolition | Demolition of the Highlander Hall Building |  |  | Complete Construction | Gerry Bomotti | Sharyl Murdock | Blythe Wilson |  | Scott Donnell | 99 |  |  | FALSE | 2127000 |  | 2015-01-22 | Complete Construction | 2018-08-01 | 2019-09-01 | [8 empty] | 2017-08-15 | PD&C | FALSE | 2015 | 2019-09-01
3195 | 3195 |  | FALSE | PLANNING & BUDGET | North District Pre-Development Study | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Gerry Bomotti | Sharyl Murdock | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 3886110.55 |  | 2016-10-26 | Complete Construction | 2019-07-01 | 2021-08-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
19P000535 |  | 19P000535 | FALSE | PLANNING & BUDGET - AUXILIARY | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV | Install TV Mount and additional electrical | BANNOCK H | H0108 | COMPLETE |  |  | EDWIN MELGAR-MEJIA |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 2019-03-14 | [7 empty] | 2019-07-08 | Enrico Baez | Met with Trent Mabee, he was coordinating abatment work with Jess H. Trent's Crew to install electrical | YES | 2019-07-26 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20 | 1
19P000386 |  | 19P000386 | FALSE | PROVOST/EVC | SL5 ROOM CHANGES |  | STUDENT SERV | 3106A | COMPLETE | Cynthia Larive | Luisa Levario | STEPHANIE ARCINIEGA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 4/15/19, DL; This Project is 100% Complete…… 2/28/19, DL; Conducted site visit. We need to schedule the work in the next 2-3 weeks This is for room 3109 C&D ……….. | 2019-02-07 | Ron Veloz | 02/07/19 O-RVL: RV completed Intake & Moved to "Que to Start". END--- 02/06/19 O-RVL: RV updates, Scope of work is to remove shelving from room, patch and Paint. Dan requested info on room availability. RV contacted Danielle for follow up from 02/05 call. RV will visit site, take pics, and follow up with Dan L.erman. Danielle reported that room 310C is vacant and available. | YES | 2019-04-15 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000473 |  | 19P000473 | FALSE | PROVOST/EVC | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 |  | HINDERAKER | 1100 | QUEUE TO START | Cynthia Larive | Luisa Levario | THERESA WAGNER | TORRI MCGARITY | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-29 | [8 empty] | Paul Ditty |  |  |  | FS | FALSE | 2019 | 2019-09-01
19P000434 |  | 19P000434 | FALSE | PROVOST/EVC | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | Please patch 50 plus holes on the wall and repaint that wall in Skye hall 136 due to the BKM removing the furniture attached to the wall. Please call Anita Ortiz if you have any questions at x2-5229. Shanshan's extension x7753 has not been moved to her new location yet. | SKYE HALL | 136 | COMPLETE | Cynthia Larive | Luisa Levario | THERESA WAGNER | SHANSHAN | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-07 | [6 empty] | 07/20/19 O-ANS: Work Complete per Paul Ditty. |  | Paul Ditty |  |  | 2019-07-22 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
19P000017 |  | 19P000017 | FALSE | SoB | SL5 ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD |  | ANDERSON 1 (N) | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | DL, 9/6/18; Monitors are installed. Need to schedule the electrical. Target date is 9/21/18…… |  | Enrico Baez | 9/4/18 EB-This Project has been started. Monitors in place. Just need to run electrical. Dan aware. Refer to WO 19P000053. It asks for the same thing. Will request to close this and let Angela know. | YES | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000482 |  | 18P000482 | FALSE | SoB | SL5 CARD ACCESS SYSTEM ANDERSON SOUTH |  | ANDERSON 2 (S) |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-26 | [6 empty] | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with JasonDL, 7/11/18; Need to check in with Jason on status for his side of the project.....DL, 7/25/18; JAson's team is ready to install but the Anderson IT department does not have the necesary software. We will start the work when the software is up and running...... 8/12/18 DND FAMIS Status noted completion on 8/2/18. |  | Dan Lerman | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with Jason | YES | 2018-08-02 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000053 |  | 19P000053 | FALSE | SoB | SL5 ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S |  | ANDERSON 1 (N) |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-04-13 | [6 empty] | DL 8/22/18; two out of four monitors are complete. WE still need to install powree at four locations…….DL, 9/6/18; Still need Electrical installed……. Planing to have complete by 9/21/18……. This is aqctually 4- monitors in four locations. We should ensure each monitor is treated as an indidual project.......DL, 9/19/18; All monitors are installed. Robert will schedule the electricans this week or early next week...DL, 10/4/18; This project is 100% Complete..... |  | Enrico Baez | DND 7/25/18: Emailed R. Veloz advising work order is closed; upon completion of the scope review, Ron to work with Zee for a Project Number to be created. | YES | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000428 |  | 18P000428 | FALSE | SoB | SL5 OLMSTED RM 2352 PATCH/PAINT |  | OLMSTED | 2352 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-05-02 | [8 empty] | Paul Ditty |  | N/A | 2018-08-17 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000351 |  | 18P000351 | FALSE | SoB | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 (S) | 21 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2018-03-19 | [6 empty] | 8/1/19, DL; This project is 100% Complete……7/15/19, DL; Work has started and should be complete on 7/16/19…….. 4/4/19 O-ANS: Moved to Queue to Start to complete during Summer 2019. DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week……8/8/18. The trades are ready to go after they finish current projects…..DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18………. DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date……..9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space……Note. The space is usable and everything works….. |  | Enrico Baez | 4/24/18 EB-scoped. Move screen, correct non-compliant electrical issues, remove&discard overhead projector bracket, relocate heat det. Add switched outles. Plans are needed because we are relocating a heat detector | YES | 2019-08-01 | FS | FALSE | 2018 | 2019-09-01 | FY 19-20
19P000033 |  | 19P000033 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT | Duplicate request to 19P000030; Canceling project to be completed on other request. | OLMSTED | 2301 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | Duplicate to project 19P000030. Canceling project. |  | Paul Ditty | Duplicate to project 19P000030. Canceling project. | N/A | 2018-10-01 | FS | FALSE | 2018 | 2019-09-01
19P000018 |  | 19P000018 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER |  | ANDERSON 1 (N) | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000463 |  | 18P000463 | FALSE | SoB | SL5 ANDERSON HALL PATCH/PAINT-102C |  | ANDERSON 1 (N) | 0102C | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-06-04 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000521 |  | 19P000521 | FALSE | SoB | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT |  | ANDERSON 1 (N) | 138 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-03-08 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
19P000030 |  | 19P000030 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT |  | OLMSTED | 2301 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000451 |  | 19P000451 | FALSE | SOB | SL5 ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 |  | ANDERSON 1 (N) | 58 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-15 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  |  |  |  | 2019-02-01 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000280 |  | 19P000280 | FALSE | SoB | SL5 ANDERSON HALL PAINT ONLY |  | ANDERSON 2 (S) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-13 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000353 |  | 19P000353 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT-2348 |  | OLMSTED | 2340 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-19 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Basis of technical design | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Jason Espinoza | 1 |  |  | FALSE | 350000 |  | 2016-12-15 | Design Development | 2021-01-01 | 2022-10-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
3415 | 3415 |  | FALSE | SoB | Anderson South Renovation | Per the sketched drawings that Dave Bomba was provided, please provide a proposal of what it would take to renovate Anderson South as follows: **1. Remove 1st Fl South side of Corridor wall and doors between 102 suite entrance and 106 suite entrance as well as adjoining walls within 102C. **2. Create a closet/wall, ideally, behind the existing door of the 102 Entrance running to the wall shared by 102A to include the best location for a door. Essentially, enclosing the window of 102, if possible. **3. Creating a closet under the stairwell between 1st floor and basement level, having entrance door flush with the bottom step of the stairwell. **4. Remove the West wall and door framing of room 001A, leaving an open look and no corridor in suite 001. | ANDERSON 2 (S) |  | Funding | Yunzeng Wang | Angela Chang | Laurie Gustafson |  | Dave Bomba | 2 |  |  | FALSE | 24700 |  | 2018-02-26 | Department funding | 2019-10-01 | 2019-10-30 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3237 | 3237 |  | FALSE | SoB | Anderson Hall N. Access Imp. | ADA handrails installation at walkway and ramp on the East sidewalk by the bench of Anderson north, down the steep ramp leading to Anderson South. We have been working with Shelly Frohrip from HR and Mary-Alice Avila of A&E on this so they will have some information regarding the purpose. 11/15/17 The handicapped parking and POT are now included. Project approved, waiting for funding. | ANDERSON 1 (N) |  | In design | Yunzeng Wang | Angela Chang | Angela Chang |  | Scott Donnell | 3 |  |  | FALSE | 150000 |  | 2016-12-19 | Re-bid | 2020-01-01 | 2020-01-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
3345 | 3345 |  | FALSE | SoB | Anderson N & S - Landscaping | DESIGN SVC & LANDSCAPE Construction request as follows for updated CURB APPEAL of Anderson North/South: 1. Roses Garden in middle of Stair landing/court to be removed and replaced with Grass 2. Add Large Planters (Metal or Cement) with Citrus Trees (either Kumquat/Lemon/Orange/Etc) on ledges that are at top section of front steps to deter skateboarders from jumping off of these ledges. 3. Remove dead trees on North and south ends of front lawn 4. Remove plants around granite sign in front lawn and replace with grass 5. Remove flowers and grass at both corners of front lawn around Citrus Trees and replace with DG and low growing flowering plants. 6. Pull all Ivy and crown vetch and add Pavers to East/Back side of Anderson Hall within landscaped/planter areas where ADA walkway runs and replace with nice picnic tables to include umbrellas and/or lounge seating around Anderson North for students. 7. Add DG in all areas where space is open/available surrounding outdoor seating area in back of building. 7. Remove all hedges surrounding alcove/arched areas along buildings. |  |  | On hold until ADA path of travel is completed | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 4 |  |  | FALSE | 0 |  | 2017-07-18 | Completion of 3237 | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
18W006022 |  | 18W006022 | FALSE | SOM | INSTALL CURTAIN ROD IN RESEARCH SPACE |  | SOM RSCH | 336 | COMPLETE | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-10-27 | [6 empty] | DL, 5/24/18; Need to review scope with Enrico….DL, 7/11/18; Enrico produced work orders for sheet metal shop. This is a singel trade project. |  | Enrico Baez | Blackout curtain needs to have a better way of being secured. Talked to Cory about fabricating a new curtain rod. 7/6/2018EB assigned to sheetmetal shop F-LNH | YES | 2018-07-11 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000380 |  | 18P000380 | FALSE | SOM | SL5 SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 | SOM RSCH | 330 | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-05 | [6 empty] | Canceled per customer on 8/22/18. |  | Enrico Baez | DD 7/17: Requested Enrico verify complete customer did not prioritize and noted work was done. 8/7/18-Conducted site visit-do not recommend location for TV due to potential damage from barn door type window screen. 8/15/18 emailed Tara Bathol that desired location for TV not recommended. Requested alternate location. 08/22/18 Ron V. Spoke with Tara. Tara confirmed the requestor cancelled the TV mounting bracket request after conversation with Enrico | NO | 2018-08-22 | FS | FALSE | 2018 | 2019-09-01
18P000261 |  | 18P000261 | FALSE | SOM | SL5 WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR |  | WEBBER | 1143 | COMPLETE | Deborah Deas | Brandon Barbosa | LOURDES ESCAMILLA |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 7/11/18; Work orders are produced. Need to assign the work order and order material. I will review with Steve and verify target complete date….DL, 7/25/18; Still need to walk the project with Steve……DL, 8/10/18; Material is ordered. We will complete the install when the materila arrives.....DL, 8/22/18; Material should be on site with in 4- weeks. Will schedule install when material is on site. Target date is 9/20/18.......DL, 9/6/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 4/29/18; Pasted from work order;I"nstall a glass window 28x9 on office door in WEBBER, Room 1143. | YES | 2018-09-10 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
19S000833 |  | 19S000833 | FALSE | SOM | Add access control to entry doors |  | HECKMAN ICEM | Entry Doors | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-07-17 | [8 empty] | Ron Veloz | Canceled request per conversation with client; customer to coordinate for a contractor to complete project. ~ Will Meet with Chris Pillen on 08/23/18 to review notes by C.P. on FAMIS. 08/23/18-RV: Followed up with Chris P for update on the work request notes. Recommended to contact Brandon to procure a local vendor. 08/24/18-RV spoke with Brandon Barbosa to determine a plan to complete the request and will pursue pricing and oversee the installation. 08/27/18 RV: Update: Brandon will PM the project on his own. 09/19/18: UPDATE-CANCELLED BY Brandon. See notes above. | YES | 2018-09-19 | FS | FALSE | 2018 | 2019-09-01
18P000400 |  | 18P000400 | FALSE | SOM | SL5 Covert suite 1116 and suite 1126 to office space | Provost has placed a hold on converting lab spaces into office spaces. | WEBBER | 1116 & 1126 | CANCELED BY FS | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-14 | [6 empty] | DL, 6/16/18; Waiting for update on Provost approval….DL, 7/11/18; Per email from Enrico on 7/10/18. The Provost put a hold on converting any lab space into officess…… |  | Enrico Baez | 3/7/19 O-ANS: Project no longer moving forward per Ron Rector. 5/1 EB Convert two wet labs into offices. Same as Webber 2278. Abate floor, demo all cabinets, remove plumbing, patch & paint. Carpet tile. Equipment comes out. Awating Provost, Sheryl Murdoch and Bob Williams approval….. 7/11/18 EB-Per Brandon Barbosa project will be cancelled | YES | 2018-07-10 | FS | FALSE | 2018 | 2019-09-01
19P000009 |  | 19P000009 | FALSE | SOM | SL5 SOME -- PAINT, SPACKLE AND CLEANING NEEDED |  | SOM EDUC | 2615 | COMPLETE | Deborah Deas | Brandon Barbosa | BEVERLEY HERBERT |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000354 |  | 19P000354 | FALSE | SOM | SL5 WEBBER 2130A-PAINT CHERI'S NEW OFFICE |  | WEBBER | 2130A | COMPLETE | Deborah Deas | Brandon Barbosa | DOMINIC SALAZAR |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-19 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty | N/A | N/A | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000408 |  | 19P000408 | FALSE | SOM | SL5 PATCH & PAINT - 2605 SOM ED |  | SOM EDUC | 2605 | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000410 |  | 19P000410 | FALSE | SOM | SL5 PAINT OFFICES AT UC PATH |  | INTELLICTR |  | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-14 | [6 empty] | 06/06/19 O-ANS: Canceled per customer request. Paul spoke with customer who will outsource work. |  |  |  |  | 2019-06-06 | FS | FALSE | 2018 | 2019-09-01
19P000248 |  | 19P000248 | FALSE | SOM | SL5 SOME--SOME INSTALL ELECTRICAL 1682 |  | SOM EDUC | 1682 | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 2 |  | FALSE |  |  | 2018-09-10 | [6 empty] | 2/14/19, DL; This project is complete…… |  | Ron Veloz | 10/29/18 O-RVL: Scoping is completed. END--- 10/17/18: RV: Drawings are on server folder. END---10/08/18 RV: Spoke with Brandon B. Brandon will submitt BKM drawings via permit request through PD&C. 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon. Walked project with Brandon. SOW to install two each dedicated 120v/20a cicuits for new modular furniture one whip at each end of the office down the wall and one to two data drops overhead down wall. | YES | 2019-02-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000249 |  | 19P000249 | FALSE | SOM | SL5 SOME-INSTALL LOCKERS | Lockers on order by customer; upon arrival to be installed. | SOM EDUC |  | CANCELED BY FS | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-07 | [6 empty] | DL, 11/7/18; It is my understanding the lockers are ordered, but we donot have a confirmed delivery date. Once the material is on site, we will schedule the installation…… |  | Ron Veloz | 01/31/19 O-RVL: Contacted Domonic and confirmed lockers will not be avialable to install and agreed to cancel the request orginated on 09/07/18 and will resubmit a new request upon delivery of the new lockers. RV emailed Customer Relations staff to cancle the project request via emails and cc Monty, Deborah H., Alan, Loretta on the communication. 01/10/19 O-RVL: Emailed Dominic Salazar on locker delivery ststus. Pending follow up call from customer to inform FS on delivery of lockers. 11/08/18 RV: Visited site existing lockers in place and in use. Will follow up with the requestor for locker delivery status to schedule. RV Spoke with Brandon Barbosa. Deparment will purchase lockers. 11/08/18 RV: Received email from Domonic Salazar on 10/25 Lockers are expected to arrive. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01
19P000245 |  | 19P000245 | FALSE | SOM | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY |  | SOM RSCH |  | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-09-07 | [6 empty] | 7/1/19, DL; This project is 100% Complete…..6/171/19, DL; Material is on site. Project should be complete in the next two weeks……..5/31/19, DL; Contracts is working on the contract. We should have a notice to proceed in the next two weeks. The project will be complete with in 30- from when we receive the notice to proceed……5/15/19, DL;, Plans were approved. I am working with PD&C on the contract. Once the contract is complete, we will schedule the work……3/28/19, DL; Plans were submitted and pending review and approval….. | 2018-10-29 | Ron Veloz | 02/15/19 O-RVL: RV updated notes added SOW & moved to "Que to Start". END--- 01/31/19 O-RVL: Chris at Lockshop reviewed the vendor quote and requested detailed equipment list. Pending revisions from vendor due this week. END--- 01/15/19 O-RVL: Delivered Access control quote to Jason & Chris R for review. They will respond with comments. Upon receipt and confirmation, RV will complete docs on server folder and update FAMIS & Access DB. --- 01/11/19 O-RVL: Qualifying quote to verify proper components from door operator vendor expecting reply soon. --- 12/14/18 O-RVL: Received Quotes for Auto door operator and Access controls this week. RV to provide update & quotes to Dan Lerman. Moving status to "Que to Start" on Minor Ren List & updating Project Folder. --- 11/07/18 O-RVL: Walked site with Access Control vendor --- 10/31/18 O-RVL: Walked site with Door Op vendor --- 10/29/18 O-RVL: Scope was Completed. RV to schedule job walks with Vendors. --- 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon | YES | 2019-07-01 | FS | FALSE | 2018 | 2019-09-01 | FY 19-20
19P000032 |  | 19P000032 | FALSE | SOM | SL5 Reconfigure recepetion desk to fit two FTEs. |  | SOM EDUC | 2608 | COMPLETE | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | 5 | 1 | FALSE |  |  | 2018-07-17 | [6 empty] | 5/1/19, DL; This project is 100% Complete….. 3/28/19, DL; Cabinet workl is complete. We need to finish the carpet and final laminate material…….2/28/19, DL; Conducted site visit with Chad. We will complete the work in the next two weeks…….2/1/19, DL; I Walked this project this week. We will try and schedule the work in the next 30- days…….12/14/18, DL, Still need to conduct site visit and schedule the work… | 2018-10-17 | Ron Veloz | 01/31/19 O-RVL: Met with Dan L onsite to review SOW with the requester. END---10/17/18 O-RVL: Remove one lower cabinet, Install a new corbel below to support the counter, install new carpet square or create an accent border if carpet tile is obsolete. Install new rubber base | YES | 2019-05-01 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000485 |  | 18P000485 | FALSE | SOM | SL5 SOMR PATCHING AND PAINTING |  | SOM RSCH |  | COMPLETE | Deborah Deas | Brandon Barbosa | DANA ABOU ABBAS |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000012 |  | 19P000012 | FALSE | SOM | SL5 SOME--PATCH & PAINT |  | SOM EDUC | 2638 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-07-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000014 |  | 19P000014 | FALSE | SOM | SL5 SOME - PATCH & PAINT |  | SOM EDUC | 2609 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-07-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
3052 | 3052 |  | FALSE | SOM | SOM Trailer Expansion | Replace the (2) modular units with one 96' x 60' building and provide access from the SOM-ED building via concrete ramp; Re-vamp the entire site for accessibility. Signed Major Cap Approval for $150k augmentation received 10/25/17 - total project $2,250,000. |  |  | Completing Change Orders | Deborah Deas | Brandon Barbosa | Sharyl Murdock |  | Scott Donnell | 99 |  |  | FALSE | 2250000 |  | 2016-03-07 | Complete Change Orders | 2017-08-01 | 2018-02-01 | [9 empty] | PD&C | FALSE | 2016 | 2019-09-01
18P000470 |  | 18P000470 | FALSE | SPP | SL5 Student Check-in Lobby |  | CHASS INT S | 4133 Corridor | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-11 | [6 empty] | DL, 6/16/18; I walked this project with Luis and Mark this week. They want this work completed by July 9th. Paint, data, electrical, chair rail and signage is requested. I need to review project with Paul and Robert C. DL, 7/11/18; Robert C. Ordered material and we will complete the install first part of next week We will scheudle the paint after Robert is Complete. Target Complete Date is 7/2018......DL, 7/25/18; WE have the electrical materila, plans were submitted. Once plans are reviewed and approved, we will proceed with the work. Target date is two weeks after plans are approved......DL, 8/10/18; Eletrical is complete. Pending paint. Paint will be scheduled in the near future. DL, 8/22/18; This project will be Complet on Saturday.....DL, 9/6/18. I miossed the chair rail request on this project. I will order the chair rail in the near future. The chair rail is the only item needed to complete this project. Aprroximately 20 lineal feet......DL, 9/19/18; Chair rail is ordered. We will schedule the install when the material arrives....... |  | Dan Lerman | Added by customer on prioritization; timeline and scope tbd. 4/25 EB emailed Christina to schedule site visit. No work order Luis to submit Google doc. To A&E sevral trades invlved. DND 6/13 Project rescoped and priorities adjusted per meeting between Dan and Luis Alvarez. | YES | 2018-08-23 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000458 |  | 19P000458 | FALSE | SPP | SL5 CHASS INTS-BUILD PERM DRYWALL DIVIDER OR APPROVE BKM AIRWALL |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ | LUISA LEVARIO | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-19 | [6 empty] | 6/17/19, DL; This project is 100% Complete…..5/31/19, DL; This prject is making good progress and we are scheduled to be complete on or before June 19th…….5/15/19, DL; This project is in progress and schedule for complete near 6/15/19…. 5/1/19; We started this project last week and we are planning to be complete in 4 - 6 Weeks….4/15/19, DL; Material is ordered, we will start the demolition this week. We hope to be complete in 8-weeks or less……2/28/19, DL; Plans are complete and were submitted to for review and approval from campus building official and fire marshal. Once plans are approved, we will shcedule the work….. | 2019-01-28 | Enrico Baez |  | YES | 2019-06-17 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000255 |  | 19P000255 | FALSE | SPP | SL5 CHASS INT N REMODEL - 4022 PATCH AND PAINT |  | CHASS INT N | 4022 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000263 |  | 19P000263 | FALSE | SPP | SL5 CHASS NORTH REMODEL - 4009 PATCH AND PAINT |  | CHASS INT N | 4009 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-09-11 | [8 empty] | Paul Ditty |  |  | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000256 |  | 19P000256 | FALSE | SPP | SL5 CHASS REMODEL - 4146 PATCH AND PAINT |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  |  |  | 3 |  | TRUE |  |  | 2018-09-10 | [7 empty] | 2018-10-09 | Enrico Baez | 10/9/18 EB Sent Luis email, copied Mont too. Project will bw $25k-$30K. Asked Luis if we are to proceed. 10/15/18 E.Baez conducted site visit, Client requested cost estimate to construct 2-3 "huddle" Spaces with sound proof walls. Requires alterations to HVAC ducting, full height walls with doors, fire sprinkler additions, smoke detection additions, lighting changes. emailed Luis estimated cost of $25,000. 12/20/18 D. DINH: Spoke with customer, Luis Alvarez, and the project request has been modified to patch & paint and replacement of one ceiling tile. Customer to work with BKM to fulfill the wall partition request portion of the project. | YES | 2019-01-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000270 |  | 18P000270 | FALSE | SPP | SL5 CHASS INT S- EVALUATION FOR REMODEL |  | CHASS INT S | 4133 | CANCELED BY CLIENT | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Dan Lerman |  | 4 | 2 | TRUE |  |  | 2018-01-16 | [6 empty] | 4/24/18 EB- Per Christina Wong, no loner needed……DL, 5/5/18; Project is cancesled per notes DND 7/27; Please follow up with customer on the status and need for the work; customer advised to me that Dan has the scope of work for completion. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. |  | Enrico Baez | 4/24/18 EB- Per Christina Wong, no longer needed……DL, 5/5/18; Project is canceled per notes. DND 6/13; Project reopened and not canceled per conversation with customer. Complete scope review and speak with Luis Alvarez. DND 8/20/18: submitted Google form for Project to be reviewed by IRT. 8/19/18 Met with Louis Alvarez. Asked for measured plans from BKM for wall layout and dimensions. Emailed again on 9/6 asking for draws. Still waiting for BKM to provide drawings. 9/21/18 Dinh - placed on hold until customer provides BKM drawings. Enrico please manage follow up. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. On shared drive can be found in file. 10/30/18 EB-Cancelled by Customer | YES | 2018-04-24 | FS | FALSE | 2018 | 2019-09-01
18P000478 |  | 18P000478 | FALSE | UNDERGRAD ED | SL5 CARPET, PAINT, & AIR HANDLING MODIFICATION |  | HINDERAKER | 1120H | COMPLETE | Jennifer Brown | Tracey Scholtemeyer | TRACEY SCHOLTEMEYER |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-16 | [6 empty] | DL, 7/4/18; This project is scoped; Need to remove Switch gear storage rack components, remove electrical conduits, plywood backer board from walls, paint and floor covering. We will schedule this work to be complete by Fall 2018 academic year....DL, 7/11/18; Need to produce work orders and schedule the work. Target Complete date is 9/14/18... Space is vacant....DL, 8/10/18; Work has started and we are on schedule...... DL, 8/22/18; Demo is almost complete. This target date is 9/21/18......9/19/18; All trades are complete. New carpet to be installed on 9/21/18. .....DL, 9/19/18; This project is scheduled to be complete this week....... |  | Dan Lerman | 7/9 EB-Spoke with Dan, he has already scoped this. | YES | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000442 |  | 18P000442 | FALSE | VC-RED | SL5 FAWCETT LAB 203 PATCH & PAINT |  | FAWCETT LAB | 203 | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 3 | FALSE |  |  | 2018-05-18 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18W015691 |  | 18W015691 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER AND DRYER |  | BOYCE | 6444 | COMPLETE | Michael Pazzani | Laura Manor | DIERK BIGGS |  |  |  |  | 1 | FALSE |  |  | 2018-05-30 | [6 empty] | DL, 7/11/18; This project is in progress and almost complete. Target complete date is 7/20/18….. |  | Dan Lerman |  | YES | 2018-07-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000476 |  | 18P000476 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER & DRYER | Canceled project, work completed on 18W015691 in July. | BOYCE | 6444 | CANCELED BY CLIENT | Michael Pazzani | Laura Manor | DIERK BIGGS |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-14 | [6 empty] | Duplicate to 18W015691; complete |  |  | Duplicate to 18W015691 | NO | 2018-07-11 | FS | FALSE | 2018 | 2019-09-01
18W013973 |  | 18W013973 | FALSE | VC-RED | SL5 BSL3 FACILITY- ASSEMBLE AND INSTALL |  | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2018-04-19 | [6 empty] | FAMIS NOTES 8/22: Plumbing filter system was installed and ice maker installed. Request for microscope and incubator moved into containment by customer. Complete 9/24/18 |  | Enrico Baez | 5/16/18 EB conducted site visit. 5/22/18 EB appliances dented, vaccum pump not on site. 6/19/18 emialed Chrystal to see if appliance have been replaced. 7/16/18 emailed Chrystal Jimenez asking for update. 8/7/18 EB Replacement appliances | YES | 2018-09-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000379 |  | 18P000379 | FALSE | VC-RED | SL5 UOB PATCH AND PAINT |  | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-05 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000553 |  | 19P000553 | FALSE | VC-RED | SL5 SPIETH HALL PATCH AND PAINT |  | SPIETH | 341 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-01 | [6 empty] | 07/26/19 O-ANS: Project Complete per Paul Ditty. |  |  |  |  | 2019-07-26 | FS | FALSE | 2019 | 2019-09-01 | FY 19-20
19P000439 |  | 19P000439 | FALSE | VC-RED | SL5 SPIETH PATCH AND PAINT ROOM 335 |  | SPIETH | 335 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-08 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2019 | 2019-09-01 | FY 18-19
19P000044 |  | 19P000044 | FALSE | VC-RED | SL5 PATCH AND PAINT |  | SPIETH | 345 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000495 |  | 19P000495 | FALSE | VC-RED | SL5 UOB RM 209- PATCH & PAINT |  | UNIV OFC BLD | 209 | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-02-08 | [6 empty] | 07/30/19 O-ANS: Project closed per Paul Ditty. 07/30/19 D-MMN: Moved furniture and filled holes. Taped base and fixtures. Primed and painted one half of office. Pulled tape replaced plates and moved furniture to other side. Removed plates taped base and fixtures. Primed and painted other half. Used spray texture on patch under window. Pulled masking. Replaced plates. Moved furniture back. Vacuumed carpet during and after total process. | [5 empty] | FS | FALSE | 2019 | 2019-09-01
19W003050 |  | 19W003050 | FALSE | VC-RED | SL5 SPEITH HALL - PATCH & PAINT HOLE IN WALL |  | SPIETH | 0359A | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-10 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [7 empty] | 2018-09-27 | Enrico Baez | 03/12/19 O-RVL: RV spoke with Enrico. He is already working on this proejct and will follow up to obtain the letter. END--- 3/08/19 O-RVL: RV Updated Notes on Access and copied to FAMIS. RV phoned Crystal Jimenez and followed up with an email to Crystal Jimenez with the request for authorization letter from the Land lord, cc'd Enrico, Dan L, Alan & Monty. END---03/07/19 O-RVL: During the minor renovation meeting, Susan asked RV to contact the requester and ask them to contact the landlord to provide a letter of approval in order to move forward with project. END---10/15/18 EB-sent Aaron Seitz approx. cost of project. 9/29/18 EB- install keyless entry system on two doors.--- 9/19/18 EB-Scheduled site visit for 9/20.--- 9/13/18 EB-emailed crystal Jimenez to schedule site visit. Awaiting response to determine funding. | YES |  | FS | FALSE | 2018 | 2019-09-01
19P000181 |  | 19P000181 | FALSE | VC-RED | SL5 PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS |  | UNIV OFC BLD | 249 | COMPLETE | Michael Pazzani | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-14 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-19 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | On-hold | Michael Pazzani | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Daneca Stevens | 1 |  |  | FALSE | 45000 |  | 2017-06-13 | Secure Funding | [11 empty] | PD&C | FALSE | 2017 | 2019-09-01
18P000215 |  | 18P000215 | FALSE | VC-STU.AFF. | SL5 STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA HAGGINS |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2017-12-08 | [6 empty] | 6/17/19, DL; This project is 100% complete. This project was the wall removal at the check in entrance…...5/31/19, DL; Contracts is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks4/15/19; All work is comleted except the floor covering and elcetronic card readers for the doors…..2/28/19, DL; This project has started and is on schedule…….2/14/19, DL; This project is scheduled to start on 2/19/19…………2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………1/15/19, DL, Material is ordered, material should arrive on site in the next 3- 5 weeks……12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 5/24/18; Need to review scope and site visti with Enrico. Plans and permits will be required for this project….DL, 7/11/18; Planning to walk work with Gloria and her team next week. Will be able to project complete date after site visit is conducted……DL; 7/25/18; We walked this project with the team. This will require plans and permits. We will schedule this work for Fall…………DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-45 Days…… |  | Enrico Baez | 01/15/19, DL; Plans are approved and material is ordered for the Phlebotomy room. We are securing the double doors. We are not conducting any work with countertop or window work. DL, 5/5/18; Pasted from wo: Noted changes to original request. Add counter windows onto end of the current SHS front desk main counter (2 windows/stations).2. Close exam room that is open to hallway with a wall (behind room 210).3. Covert 100A to phlebotomy room with a hallway access doorway.4. Open wall to reconfigure to allow space for lab manager…… EB 3/20 scoped project and annotated on FAMIS. | YES | 2019-06-17 | FS | FALSE | 2017 | 2019-09-01 | FY 18-19
18P000214 |  | 18P000214 | FALSE | VC-STU.AFF. | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 |  | HEALTH SERV |  | HOLD - FACILITIES SERVICES | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-12-08 | [6 empty] | 7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for Doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once materila arrrives, we will schedule the installation. Floor covering is on hold untile we receive the process from EH&S…….5/31/19, DL; Contracts is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is comleted except the floor covering and elcetronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez | 01/15/19, DL; The plans are approved and Material is ordered. Once material arrives, we will schedule the work with Gloria… Dl, 5/3/18; Dan, Chris, Ron and Gloria will meet and re-scope the work……1/31/18 EB-Scoped site with Chris P. on 10/30/2017. Spoke with Gloria who thought still CPMS. Scope includes removing doors, adding teller counters, moving corridor wall…. | YES |  | FS | FALSE | 2017 | 2019-09-01
18P000456 |  | 18P000456 | FALSE | VC-STU.AFF. | SL5 HUB--UTILITY METERS | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. | HUB |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-05-30 | [8 empty] | Enrico Baez | 1/24/19 EB Contacted Jonathan Bianchet of Design West for results of site evaluation. Will have report by middle of following week. 11/29/18 EB Met with Design West and HUB staff. Conducted site visit. Waiting for recommendations from Design West. 7/6/18 EB-emailed Brendan to schedule site visit. 7/11/18 EB- Site visit schduled for 7/12/18 7/16/18 Conducted site. Customer wants to have SEP metered for all food vendors. Requested electical power plans from Gunther 8/7/18 Contacted Design West for proposal of feasibility stud 8/15/18 Advised Brendan Obrien to submit request to CPMS as this work will not be self performed. Sent Brendan copy of proposal for sight assessment. | YES | 2019-01-24 | FS | FALSE | 2018 | 2019-09-01
18P000337 |  | 18P000337 | FALSE | VC-STU.AFF. | SL5 MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET |  | HEALTH SERV | 414 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-12 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18….Need to work on plans and permits….DL, 7/11/18; Gunther is working on plans. Target complete date is 9/14/18….DL, 7/25/18; Planning to submit plans for review next week. We will schedule the work once we have approved plans…….DL, 8/8/18; This is a structual wall and needs to be engineered. We are meeting with the Structual engineer on 8/9/18 to determine if project is possible.....DL, 8/22/18; Working on EDPA for Structual engineer; project timeline is late Fall. 9/19/18; The Agreement / Cointract for the structual engineer is processed for this project. We should have plans from the structual engineer to submitt to the Building Official and fire marshal with in 4- weeks......dl, 10/4/18; Plans are almost complete and we will submit them for review by the end of the week.....DL, 11/7/18; Plans are approved. WE are schedule to start this Project on Tuesday 11/13/18. Target complete date is by the end of the winter break..... |  | Enrico Baez | Cut wall between rooms 414 and 401, Case and trim opening, install carpet in- DL, 5/10/18; Gloria Vera is the contact; 827-5532 | YES | 2018-12-14 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000431 |  | 19P000431 | FALSE | VC-STU.AFF. | SL5 STUDENT SERVICES REMOVE NAILS AND PATCH WALL |  | STUDENT SERV | 2128 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | VALERIE SANCHEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-04 | [6 empty] | 6/24/19 O-ANS: CANCEL WO/PROJECT PER DONNA POWELL EMAIL. |  |  |  |  | 2019-06-24 | FS | FALSE | 2019 | 2019-09-01
19P000380 |  | 19P000380 | FALSE | VC-STU.AFF. | SL5 PATCH AND PAITN- WALL PAINT IS PEELING |  | HEALTH SERV | 404 | COMPLETE | Brian Haynes | Cathy Eckman | SAMANTHA HARRIS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-19 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
18P000198 |  | 18P000198 | FALSE | VC-STU.AFF. | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Install new Wall lights | HUB | 0 | PLAN DEVELOPMENT/CHECK | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 1 | 5 | FALSE |  |  | 2017-11-21 | [6 empty] | 9/3/19, DL; Gunter has plans at 60%, We will try and submitt with in the next two weeks. 8/14/19, DL;This project is now on Gunther's bench. Gunter will start the process in about 2- weeks and we should have plans top submitt with in the next 30- days….6/17/19, DL; I will walk this work in the next two weeks and work on plan to submit to our campus architech and building official for review…..DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…… | 2018-01-23 | Enrico Baez | Plans will be developed and will be submitted for review and approval. 4/2 MN: Enrico to obtain an FAU….. 1/23/2018 E.Baez conducted job site walk. Request is for lighting installations above entries to store front and kitchen on East side of building and additional lighting above outside locker on loading dock. Manny has lights that can be re-used. Want estimate only. Need to include Campus Architect too…… 1/23/18 EB-site walk, scope enter in FAMMIS. | YES |  | FS | FALSE | 2017 | 2019-09-01
19P000455 |  | 19P000455 | FALSE | VC-STU.AFF. | SL5 FILL AND PAINT OVER HOLES ON WALL |  | HEALTH SERV | 100 | QUEUE TO START | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-17 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000405 |  | 19P000405 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED |  | HEALTH SERV | 0100D | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-11 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000534 |  | 19P000534 | FALSE | VC-STU.AFF. | SL5 PATCH WALLS AND PAINT |  | HEALTH SERV | 334 | QUEUE TO START | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-03-15 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
18P000348 |  | 18P000348 | FALSE | VC-STU.AFF. | SL5 HUB ADD 3RD FLOOR WALLS |  | HUB | 0353E | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 2 | 6 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/1/19, DL; Per Chris P. This is a PD&C project………..DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Need to walk the project with Manny. Target date is late Fall…….. |  | Enrico Baez | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. EB 5/23/18. Conducted site visit. Request is for adding walls to interior spaces 353F, 381 and 377. Will impact A/C and fire protection. Still waiting for a firm plan from customer. | YES | 2019-02-01 | FS | FALSE | 2018 | 2019-09-01
19P000037 |  | 19P000037 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE BLDG--PATCH WORK AND PAINTING |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-07-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000483 |  | 19P000483 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED |  | HEALTH SERV | 404, 407, 412, 405 & 411 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-02-01 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
19P000124 |  | 19P000124 | FALSE | VC-STU.AFF. | SL5 PAINT ROOMS 115 AND 116 |  | COSTO HALL | 125 | COMPLETE | Brian Haynes | Cathy Eckman | LINDA KELLEY |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-10-22 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000172 |  | 19P000172 | FALSE | VC-STU.AFF. | SL5 HEALTH SERV- PAINT RESTROOM IN LABORATORY |  | HEALTH SERV | 0113A | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | 2018-11-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
3471 | 3471 |  | FALSE | VC-STU.AFF. | HUB Electrical Sub-Meter Study | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Circuit Tracing of the designated spaces | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | J.Espinoza/G.Caraig | 1 |  |  | FALSE | 50000 |  | 2018-08-20 | Design | 2020-01-01 | 2020-04-01 | [9 empty] | PD&C | FALSE | 2018 | 2019-09-01
3486 | 3486 |  | FALSE | VC-STU.AFF. | HUB 353/381, Costo 111 Add'l Wall/Doorway | Please evaluate additional wall/door way requests for HUB 353/381 and Costo Hall 111. | HUB |  | On-hold | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 2 |  |  | FALSE | 0 |  | 2018-11-26 | Approval/Funding | [11 empty] | PD&C | FALSE | 2018 | 2019-09-01
3385 | 3385 |  | FALSE | VC-STU.AFF. | SRC North Gym Replace Interior Lights | Replace old technology sodium vapor light fixtures in SRC North Gymnasium with new technology LED light fixtures. Some flexibility available in the schedule. Selected vendor will need to phase work to minimize the effect on SRC operations and programming. | SRC NORTH |  | In Construction | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Fernando Nunez | 3 |  |  | FALSE | 396000 |  | 2017-10-31 | Complete Construction | 2019-06-24 | 2019-08-30 | [9 empty] | PD&C | FALSE | 2017 | 2019-09-01
3512 | 3512 |  | FALSE | VC-STU.AFF. | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) |  | 2108ACDEF | Programming | Brian Haynes | Cathy Eckman | Christina Wong |  | Daneca Stevens | 5 |  |  | FALSE | 130000 |  | 2019-03-19 | Design | 2020-07-01 | 2020-10-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
2829 | 2829 |  | FALSE | VC-STU.AFF. | SRC South - New Storage Building | New storage building immediately south of SRC South Pool Building; approximately 20' x 40'; one roll up door and one standard door; electrical power required - number of outlets to be defined in design; concrete walkway and door pads required; non-potable water may be required if quick couplers are not available in nearby landscaping; please see attachment for location: approximately at gridlines T and 9.4 - dotted outline of building is labeled "FUTURE STORAGE" - located immediately south of the SRC POOL EQUIPMENT BUILDING. | SRC SOUTH |  | Coordinate with MRB Logistics | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Mihai Gavan | 6 |  |  | FALSE | 0 |  | 2015-01-23 | Coordinate with MRB Logistics | [11 empty] | PD&C | FALSE | 2015 | 2019-09-01
3534 | 3534 |  | FALSE | VC-STU.AFF. | SRC North Cooling Towers Replcmt | Replacement of the 2 Cooling towers in the Student Recreation Center North. The towers are 25 plus years old and in needed of replacement to keep the HVAC system running efficiently. |  |  | In funding | Brian Haynes | Cathy Eckman | Michael Eason |  | John Franklin | 8 |  |  | FALSE | 680000 |  | 2019-06-06 | Secure Funding | 2019-12-01 | 2020-01-01 | [9 empty] | PD&C | FALSE | 2019 | 2019-09-01
3524 | 3524 |  | FALSE | VC-STU.AFF. | Stdnt Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. |  |  | Programming | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 9 |  |  | FALSE |  |  | 2019-04-16 | Design | [11 empty] | PD&C | FALSE | 2019 | 2019-09-01
19P000238 |  | 19P000238 | FALSE | VC-UNIV.ADV. | SL5 PATCH & PAINT HINDERAKER 1136 |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | 2019-01-11 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000564 |  | 19P000564 | FALSE | VC-UNIV.ADV. | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | 1156C (AVC Johnny Cruz) – Patch molly holes, touch-up paint. 1156A (Jules Bernstein) – Remove (2) black & white photos from wall. Patch molly holes, touch-up paint. 1156B – Install picture frame (UCR campus map) onto wall. Suite 1159 – Patch holes. Remove film reels. Paint one accent wall “UCR Blue”. 1159B (Christy Zwicke) - Patch molly holes, touch-up paint. | HINDERAKER | 1156 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | Lisa Cusick | Christy Zwicke | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-08 | [12 empty] | FS | FALSE | 2019 | 2019-09-01
18P000281 |  | 18P000281 | FALSE | VC-UNIV.ADV. | SL5 ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS |  | ALUM VISITOR | 2202 | COMPLETE | Peter Hayashida | Naysia Caldwell | TRUDY COHEN |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-01-24 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…..2/28/19, DL; This work is scheduled…….DL, 5/24/18; Need to verify scope of work with EnricoDL, 7/11/18; Still need to visit the site and schedule the work…..DL, 11/8/18; This project was transferred to John. The target date was 1/2/19….. |  | Enrico Baez | 5/10/18 EB-Customer needs additional outlets in space to accommodate 4 new cubicles. Bob Williams wants additional information with plans. 9/13/18 EB-Met with Dan, Jorge, Rita and Kim. Scope to include patch and painting walls, removing art work, moving thermostat. Cubicles will need whip connections. | YES | 2019-03-28 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000326 |  | 19P000326 | FALSE | VC-UNIV.ADV. | SL5 HINDERAKER - PATCH & PAINT |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-08 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | 2019-02-08 | FS | FALSE | 2018 | 2019-09-01 | FY 18-19
19P000417 |  | 19P000417 | FALSE | VC-UNIV.ADV. | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY |  | UV BLDG A | 201 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 2018-12-18 | [8 empty] | Enrico Baez | 8/6/19 LB: Canceled by client |  |  | FS | FALSE | 2018 | 2019-09-01 |  | 1
2245 | 2245 |  | FALSE | VC-UNIV.ADV. | Campus Directory & Blade Signs | Remove and replace campus directories at strategic locations throughout the campus. |  |  | Pending funding source approval | Peter Hayashida | Naysia Caldwell | Margene Mastin-Schepps |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2014-03-27 | Project Approval & Funding | [11 empty] | PD&C | FALSE | 2014 | 2019-09-01

## Legend
Legend and Contacts
FS | Facilities Services
PD&C | Planning, Design & Construction (formerly A&E - Architects & Engineers)
FS Current Statuses | Definitions
Project Intake | Building Zone Manager (BZM) to meet with customer to understand and define scope of work.
Queue to Start | Initial scope of work has been identified by BZM; project in queue for FS Project Manager to develop drawings and coordinate trades for execution.
Plan Development / Check | Project Manager is coordinating plan development and review by Building Official and/or Fire Marshal.
In Progress | Project is in progress which includes but not limited to plan development, scheduling and coordination of trades for work execution.
Hold - Customer Equipment/Schedule | Project is on hold pending customer provided equipment or scheduling availability.
Hold - Facilities Services | Project is on hold pending FS; determining ability to complete project within FS purview or parts ordered by FS for completion.
Quality Check of Work | Project is being reviewed to ensure work is completed to customer and FS standards.
Canceled by Client | Project is canceled at the request of the customer or duplicative project request.
Canceled by FS | Project is canceled by FS administration or duplicative project request.
IRT Review | Project is to be reviewed by PD&C/FS or to be completed by PD&C with a project submittal by customer within CPMS.
Complete | Project is complete to customer and FS standards.
TO BE PERFORMED BY PD&C | Project is no longer an FS project and will be managed and completed by PD&C.
PD&C Current Statuses | Definitions
"Open Field" | PD&C project managers will input most recent update in this field.
| FS | PD&C
Org | Org Delegate/Contact | CPMS Department Approver
ATHLETICS | Joseph Erbland | Joseph Erbland
BAS | Georgianne Carlson | Andy Plumley
BCOE | Maggie Souder | Susana Aparicio
CAMPUS | TBD
CAP.PROG. | Sharyl Murdock | John White
CHANCELLOR | Karim Zahedi
CHASS | Cindy Williams | Cindy Williams KatriceCalloway
CNAS | Deborah McWilliams | Beverly McNeil Kimberly Hammond
ENROLLMENT SERVICES | TBD
FAC-PLNG-DESIGN-CONST | Da Lan Dinh | Susan Marshburn
GRAD.DIV | Kennett Lai
GSOE | Sally Tavizon
ITS | Shelley Gupta | Shelley Gupta
LIBR | Jackie Bates | Jacqueline Bates
PALM DESERT |  | Tamara Hedges
PLANNING & BUDGET | TBD | Jeff Kaplan
PROVOST/EVC | Luisa Levario
SoB | Angela Chang | Laurie Gustafson
SOM | Brandon Barbosa | Laura Manor
SPP | Luis Alvarez
UNDERGRAD ED | Tracey Scholtemeyer
VC-RED | Laura Manor | Laura Manor
VC-STU.AFF. | Cathy Eckman | Karen McComb Lindy Fenex Cathy Eckman
VC-UNIV.ADV. | Naysia Caldwell | Margene Mastin-Schepps