## Active Project Summary
ACTIVE Project Status Report
[6 empty] | Total Active PD&C Projects |  | 93
[6 empty] | Total Active FS Projects |  | 50
Last Updated | 2021-03-16 | Project Summary |  |  |  | Project Status |  |  |  |  | Project Details | [6 empty] | Internal Use Only
Organization | Project Ref No. | Project Service Unit | Project Title | Building | Room | Request Date | Current Status | Next Steps | START Date | COMPLETE Date | Project Description | PD&C Org Priority No. | FS Org Priority No. | For New Faculty Hire? | FS Org Prior. Quarter & Year | Contact / Requestor | Proj Manager | Chronology
ATHLETICS | 2696 | PD&C | Soccer Stadium Fencing (E Side) | SOCCER FIELD AND AREA |  | 2014-04-10 | On Hold | Need direction by PM Director |  |  | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | 2 |  |  |  | Joe Erbland | Gerald Caraig
ATHLETICS | 2989 | PD&C | Dance - Locker Room Remodel |  |  | 2015-11-19 | On Hold (COVID-19) | On Hold (COVID-19) |  |  | We are requesting to utilize Base Architecture, Planning, & Engineering, Inc. to provide pro bono work on planning for locker room renovations in the Athletics & Dance Building. Rob Gayle is aware of our desire to utilize this company for services. | 99 |  |  |  | Joseph Erbland | Tameesha Hayes
ATHLETICS | 3407 | PD&C | Athletics Media Room | S LCKRM/CONC |  | 2018-08-23 | On Hold | Department approval to move fwd |  |  | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | 1 |  |  |  | Johnathan Jensen | Fernando Nunez
ATHLETICS | 3622 | PD&C | Baseball Outfield Wall Repairs |  |  | 2021-02-10 | In Design | Permitting |  |  | Contractor to replace damaged panels and baseboards on outfield fence at Riverside Sports Complex. This is to be done with pressure treated wood. Metal rail at top to be reattached and secured. Entire wall to be painted to specific UCR Athletics colors attached. Damaged boards on scoreboard catwalk and camera scaffolding to be replaced. | 3 |  |  |  | Eugene Hutchinson | Tameesha Hayes
BCOE | 3428 | PD&C | MS&E Cleanroom Expansion | MAT SCI ENGR |  | 2018-04-04 | In Funding | Secure Funding |  |  | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | 2 |  |  |  | Margaret Souder | Scott Donnell
BCOE | 3617 | PD&C | WCH 108 Server Rm HVAC Upgrade |  |  | 2021-01-22 | In Pre-programming | Design |  |  | Winston Chung 108. Upgrade the HVAC system to provide cooling as needed for the server room. | 3 |  |  |  | Michael Ambriz | Tameesha Hayes
BCOE | 3624 | PD&C | CE-CERT Circuit Upgrade |  |  | 2021-03-03 | New (3/3) | Need PM Assignment |  |  | We have an existing 208 VAC 100 Amp circuit. We would like to upgrade to a 200 Amp service. The existing service is located in the electrical room at 1084 Columbia. |  |  |  |  | Todd Ambriz | Tameesha Hayes
BCOE | 20P000212 | FS | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | MARLAN & ROSEMARY BOURNS HALL | B0328E | 2019-11-05 | QUEUE TO START |  |  |  | Repair the damaged exhaust duct at Fume hood in BCOE 328E |  | R1 |  | Winter 2021 | MARGARET SOUDER | Enrico Baez | 14
BCOE | 20P000253 | FS | SL5 BOURNS HALL LAB B156 - EXHAUST SYSTEM | MARLAN & ROSEMARY BOURNS HALL | B0156 | 2019-12-11 | IN PROGRESS | Demolish cabinets and schedule paint and flooring | 2021-03-01 | 2021-05-07 | EXHAUST SYSTEM |  | 1 |  | Winter 2021 | LOUIS SANDOVAL | DAN LERMAN | 14
BCOE | 20P000310 | FS | SL5 BOURNS A-WING A129 - PATCH & PAINT | MARLAN & ROSEMARY BOURNS HALL | A0129 | 2020-01-10 | QUEUE TO START |  |  |  | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. |  | X | YES | Winter 2021 | ROBERT LOPEZ-A | PAUL DITTY | 14
BCOE | 20P000363 | FS | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | WINSTON CHUNG HALL | 433 | 2020-02-13 | QUEUE TO START |  |  |  | Paint Only |  | X | YES | Winter 2021 | MANGLAI ZHOU | PAUL DITTY | 14
BCOE | 21P000019 | FS | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | MARLAN & ROSEMARY BOURNS HALL | A305 | 2020-07-20 | PROJECT INTAKE | Complete priority 2 projects |  |  | Bourns Office A305 - Install Plank Floor |  | 3 | YES | Winter 2021 | ROBERT LOPEZ-A | Dan Lerman | 14
BCOE | 21P000049 | FS | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MATERIALS SCIENCE & ENGINEERING | 71 | 2020-08-06 | PLAN DEVELOPMENT/CHECK | Start working on CAD drawings and building permit |  |  | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS |  | 2 |  | Winter 2021 | XI CHEN | DAN LERMAN | 14
CAP PROG | 2952 | PD&C | Pierce Hall Interiors | PIERCE |  | 2015-09-11 | In Construction | Phase I Completion | 2019-01-02 | 2021-05-01 | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | 13 |  |  |  | Jon Harvey | Gerald Caraig
CAP PROG | 3119 | PD&C | Plant Growth Environment Facility |  |  | 2016-05-25 | Furniture/Equipment | Equipment and Furnishing | 2019-06-01 | 2021-02-26 | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. | 6 |  |  |  | Michelle Baniqued | Rowan Reid
CAP PROG | 3233 | PD&C | South Recreation Mall |  |  | 2016-12-16 | In Design | Bidding | 2021-05-01 | 2021-11-01 | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. | 99 |  |  |  | Jaime Enghbrecht | Daneca Stevens
CAP PROG | 3234 | PD&C | UC Intellicenter 2nd Floor TI |  |  | 2016-12-21 | In Construction | Complete Construction | 2021-01-01 | 2021-05-01 | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. | 4 |  |  |  | John White | Fernando Nunez
CAP PROG | 3319 | PD&C | Student Success Center |  |  | 2017-06-01 | In Construction | Complete Construction | 2019-11-01 | 2021-08-01 | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. | 9 |  |  |  | Michelle Baniqued | Mihai Gavan
CAP PROG | 3395 | PD&C | Recreation Fields Replacement |  |  | 2017-12-03 | On Hold | On Hold |  |  | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. | 14 |  |  |  | Tameesha Hayes | Daneca Stevens
CAP PROG | 3401 | PD&C | SOM Clinical Skills & Simulation Suite | ORBACH LIB |  | 2017-12-03 | Substantial Completion 2/5/21 | Complete Furniture & Equipment | 2020-05-01 | 2021-02-01 | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | 12 |  |  |  | Mihai Gavan | Fernando Canon
CAP PROG | 3438 | PD&C | Iowa Street Widening |  |  | 2018-08-22 | In Construction | City to determine schedule | 2020-07-01 |  | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. | 15 |  |  |  | Scott Donnell | Scott Donnell
CAP PROG | 3452 | PD&C | Long Range Dev Plan - 2018 |  |  | 2018-07-16 | In Programming (Study) | Complete Study |  |  | New Long Range Development Plan (LRDP), with all required technical studies | 12 |  |  |  | Jacqueline Norman | Uma R.
CAP PROG | 3458 | PD&C | KUCR Replacement Project |  |  | 2018-07-16 | On Hold | Coordinating with North District |  |  | Proposed replacement of KUCR radio station facility | 17 |  |  |  | Blythe Wilson | Blythe Wilson
CAP PROG | 3589 | PD&C | Various Bldgs LED Lighting Ph2 |  |  | 2020-03-11 | Bidding | 100% Cd stamped approval | 2021-04-01 | 2021-07-30 | LED Lighting Phase 2 - Package 1 - Replacing existing lamps to LED | 15 |  |  |  | David Palacios | Fernando Nunez
CAP PROG | 3612 | PD&C | Native American Landscape Garden |  | Ext | 2021-02-11 | New (2/11) | New (2/11) |  |  | Create a physical marker to commemorate the UCR Land Acknowledgement in the form of a Native American Landscape Garden (working name) at the proposed project location. | 16 |  |  |  | Uma R. | G.Caraig/V.Kern
CAP PROG | 3615 | PD&C | Student Success Center Buildout |  |  | 2021-03-09 | New (3/9/21) | New (3/9/21) |  |  | Buildout and furnishing of the SSC dining venue for temporary use as seating/study area and other as needed construction scope related to the overall building project that was not described in the Basis of Design. |  |  |  |  | Jaime Engbrecht | Mihai Gavan
CAP PROG | 3616 | PD&C | University Ave/Canyon Crest Dr Improvements |  |  | 2021-03-01 | New (3/1) | New (3/1) |  |  | $100,000 in Violent Acts Mitigation and Prevention funding have been awarded to study short and long-term safety improvements at the intersection at University Avenue and Canyon Crest Drive. Subsequent activities will involve the construction of identified improvements. | 17 |  |  |  | Jaime Engbrecht | Uma R.
CAP PROG | 2970c | PD&C | ADA Improvements/Transition Plan |  |  | 2015-12-02 | In Bidding (Phase 3) | Award Contract (Phase 3) | 2021-04-01 | 2021-06-01 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) | 11 |  |  |  | Blythe Wilson | Tameesha Hayes
CAP PROG | 2970d | PD&C | ADA Improvements/Transition Plan |  |  | 2015-12-02 | In Design (Phase 4) | Complete Design (Phase 4) |  |  | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) | 11 |  |  |  | Blythe Wilson | Tameesha Hayes
CHASS | 3280 | PD&C | Athletics Dance Bldg Repairs | ATH DANCE |  | 2017-05-31 | On Hold/Funding | Department Approval/Funding |  |  | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | 2 |  |  |  | Paul Richardson | Fernando Nunez
CHASS | 3441 | PD&C | CHASS INTS 1121 Exercise Room | CHASS INT S |  | 2018-06-22 | On Hold (COVID-19) | On Hold (COVID-19) |  |  | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | 11 |  |  |  | Anna Finn | Daneca Stevens
CHASS | 3557 | PD&C | Campus Sculpture Installation |  |  | 2019-11-27 | Construction | Complete Construction | 2020-10-01 | 2021-03-01 | We will bring 5 sculptures to campus that will go in public places that have already been identified by Uma Ramasubramanian and Jacqueline Norman . Please construct 5 concrete plinths at various locations around campus. Locations are on the attachment. | 3 |  |  |  | Emily Rankin | Tameesha Hayes
CHASS | 20P000231 | FS | SL5 ARTS 54 - CONVERT TO PIANO LAB | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 54 | 2019-11-19 | PROJECT INTAKE | start plans once priority 3 proj. are almost comp. |  |  | Convert Basement Library into Piano Lab |  | 4 |  | Winter 2021 | PAUL RICHARDSON | Dan Lerman | 14
CHASS | 20P000272 | FS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 245 | 2020-01-02 | PROJECT INTAKE | Plans and permit once we start priority 3 projects |  |  | LIGHTING UPGRADE/PROJECTOR INSTALLATION |  | 3 |  | Winter 2021 | ANDREA HIDALGO | DAN LERMAN | 14
CHASS | 20P000317 | FS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 150 | 2020-01-14 | PROJECT INTAKE | Electrical Engineer design |  |  | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel |  | 2 |  | Winter 2021 | PAUL RICHARDSON | DAN LERMAN | 14
CHASS | 20P000370 | FS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | GORDON S. WATKINS HALL | 1311 | 2020-02-19 | IN PROGRESS | 14 day notification to AQMD for Asbestos Abatement | 2021-03-19 | 2021-07-02 | SPACE RENOVATION PROJECT |  | 1 | YES | Winter 2021 | PAUL RICHARDSON | DAN LERMAN | 14
CHASS | 20P000403 | FS | SL5 OLMSTED 232 - PAINT OFFICE | JOHN W. OLMSTED HALL | 2321 | 2020-03-13 | QUEUE TO START |  |  |  | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). |  | X | YES | Winter 2021 | PAUL RICHARDSON | Paul Ditty | 14
CHASS | 20P000446 | FS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | CHASS INTERDISCIPLINARY NORTH | 4047 | 2020-06-04 | QUEUE TO START |  |  |  | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. |  | X | YES | Winter 2021 | PAUL RICHARDSON | PAUL DITTY | 14
CHASS | 20P000453 | FS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 142 | 2020-06-18 | QUEUE TO START |  |  |  | Paint Only - Please patch/paint to existing color office for faculty new hire. |  | X | YES | Winter 2021 | PAUL RICHARDSON | PAUL DITTY | 14
CHASS | 20P000462 | FS | SL5 HMSS 2001 - PAINT OFFICE / CLEAN FLOOR NEW FACULTY HIRE | HUMANITIES BUILDING | 2001 | 2020-06-18 | QUEUE TO START |  |  |  | Patch/paint to existing color for faculty new hire |  | X | YES | Winter 2021 | PAUL RICHARDSON | Paul Ditty | 14
CHASS | 20P000463 | FS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | HUMANITIES BUILDING | 2000 | 2020-06-18 | QUEUE TO START |  |  |  | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 |  | X | YES | Winter 2021 | PAUL RICHARDSON | PAUL DITTY | 14
CHASS | 20P000464 | FS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | HUMANITIES BUILDING | 3001 | 2020-06-18 | QUEUE TO START |  |  |  | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) |  | X | YES | Winter 2021 | PAUL RICHARDSON | PAUL DITTY | 14
CHASS | 20P000469 | FS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 222 | 2020-06-23 | QUEUE TO START |  |  |  | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. |  | X | YES | Winter 2021 | PAUL RICHARDSON | PAUL DITTY | 14
CHASS | 20P000470 | FS | SL5 HMSS 3210 - PATCH/PAINT | HUMANITIES BUILDING | 3210 | 2020-06-24 | QUEUE TO START |  |  |  | Paint Only |  | X | YES | Winter 2021 | PAUL RICHARDSON | PAUL DITTY | 14
CHASS | 21P000109 | FS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | GORDON S. WATKINS HALL | 1146 | 2020-11-18 | QUEUE TO START |  |  |  | Please patch, paint the room and install new flooring for new faculty member, Dr. Robert Clark. He started working July 1, 2020. |  | X | YES | Winter 2021 | BECKY CAMPBELL | Paul Ditty | 14
CHASS | 21P000110 | FS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | GORDON S. WATKINS HALL | 2146 | 2020-11-18 | QUEUE TO START |  |  |  | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. |  | X | YES | Winter 2021 | BECKY CAMPBELL | Paul Ditty | 14
CHASS | 21P000111 | FS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | GORDON S. WATKINS HALL | 2144 | 2020-11-18 | QUEUE TO START |  |  |  | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. |  | X | YES | Winter 2021 | BECKY CAMPBELL | Paul Ditty | 14
CNAS | 3390 | PD&C | Field 11C-D CVC Screenhouse |  |  | 2018-01-08 | In Construction | Complete Construction | 2021-02-01 | 2021-08-01 | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. | 12 |  |  |  | Tracey Kahn, D. McWilliams | Scott Donnell
CNAS | 3559 | PD&C | USDA Screen House Expansion | GERMPLASM |  | 2019-10-04 | In Design | Construction by USDA |  |  | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | 1 |  |  |  | MaryLou Polek | Scott Donnell
CNAS | 3593 | PD&C | R'Garden Walk-in Cooler Installation |  |  | 2020-05-08 | In Bidding | Award Contract | 2021-04-01 | 2021-05-01 | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. | 5 |  |  |  | Richard Zapien | Scott Donnell
CNAS | 3594 | PD&C | R'Garden Grow Pod Installation |  |  | 2020-05-21 | On Hold | Secure Funding |  |  | R'Garden Gro Pod Installation | 6 |  |  |  | Richard Zapien | Scott Donnell
CNAS | 3596 | PD&C | Rubidoux MPGU |  |  | 2020-09-11 | In Construction | Complete Construction | 2021-01-01 | 2021-05-01 | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. | 7 |  |  |  | Georgios Vidalakis | Scott Donnell
CNAS | 3599 | PD&C | MS&E 155 Pulsed Laser Deposition |  | 0155 | 2020-06-19 | In Design | Waiting for equipment from overseas |  |  | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. | 3 |  |  |  | Wendi Tapia | Tameesha Hayes
CNAS | 3602 | PD&C | GH 16 Retractable Shade Cloth |  |  | 2020-07-14 | In Bidding | Construction |  |  | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 | 4 |  |  |  | Mireya Botello Santoyo | Scott Donnell
CNAS | 3618 | PD&C | NRS James Reserve Upgrades |  |  | 2021-02-02 | New (2/2/21) | New (2/2/21) |  |  | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. | 11 |  |  |  | Heather Constable | Rowan Reid
CNAS | 3623 | PD&C | NRS Boyd Deep Canyon Repairs & Upgrades |  |  | 2021-02-02 | New (2/2/21) | New (2/2/21) |  |  | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ | 10 |  |  |  | Heather Constable | Rowan Reid
CNAS | 19P000485 | FS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | HOMER D. CHAPMAN HALL | 9 | 2019-01-29 | IN PROGRESS | Connect and install air flow monitor |  | 2021-03-12 | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. |  | 1 |  | Spring 2020 | WILLIAM SUTTON | Dan Lerman | 11
CNAS | 19P000539 | FS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | PHYSICS BUILDING | 1132 | 2019-03-19 | IN PROGRESS | Install final electrical, countertop and Sink |  | 2021-03-26 | Install electrical utilities for new equipment |  | 3 |  | Summer 2019 | MAYELA CASTILLO | Dan Lerman | 8
CNAS | 20P000046 | FS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | HOMER D. CHAPMAN HALL | 0001 | 2019-07-31 | PROJECT INTAKE |  |  |  | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS |  | R2 |  | Winter 2021 | WILLIAM SUTTON | Enrico Baez | 14
CNAS | 20P000144 | FS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | ALFRED M. BOYCE HALL | 3432, 3432A, 3446, 3446A | 2019-09-26 | IN PROGRESS | final paint, floor covering and final cabinets |  | 2021-04-02 | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A |  | 3 |  | Winter 2020 | MATTHEW ULRICH | Dan Lerman | 10
CNAS | 20P000174 | FS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | PHYSICS BUILDING | 3009 | 2019-10-11 | QUEUE TO START |  |  |  | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 |  | 1 | YES | Winter 2021 | MAYELA CASTILLO | PAUL DITTY | 14
CNAS | 20P000244 | FS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | SKYE HALL | 242 | 2019-11-25 | QUEUE TO START |  |  |  | Paint Only |  | X | YES | Winter 2021 | MELISSA GOMEZ | PAUL DITTY | 14
CNAS | 20P000248 | FS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT | HERBERT JOHN WEBBER HALL | 1223 + 1223-A | 2019-11-27 | PROJECT INTAKE | EH&S to sanitize space | 2021-03-02 | 2021-04-21 | Space Management has temporarily allocated Rooms 1223 and 1223-A in Webber Hall to CNAS. We need this lab cleaned and modified to accommodate relocating an existing (and active) lab. |  | 5 |  | Winter 2021 | SHARYL MURDOCK | Dan Lerman | 14
CNAS | 20P000320 | FS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | HERMAN T. SPIETH HALL | 1303 | 2019-11-20 | PROJECT INTAKE | Will start the work once we start priority 4 proj |  |  | ACTIVATE VACUUM LINES |  | 4 |  | Winter 2021 | ESTELLA DAVALOS | DAN LERMAN | 14
CNAS | 20P000333 | FS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | W. CONWAY PIERCE HALL | 2232A | 2020-01-22 | PROJECT INTAKE | will start when we start priority 9 projects |  |  | MINOR RENOVATIONS CASEWORK SINK UTL LINES |  | 9 |  | Winter 2021 | KEVIN SIMPSON | DAN LERMAN | 14
CNAS | 20P000366 | FS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | HERMAN T. SPIETH HALL | 2375 / 2375-A | 2020-02-19 | PROJECT INTAKE | Will start when we start priority 7 projects. |  |  | MINOR LAB RENOVATION |  | 7 | YES | Winter 2021 | SHERICE UNDERWOOD | DAN LERMAN | 14
CNAS | 20P000367 | FS | SL5 SCI LAB ROOM 315-PATCH & PAINT | SCIENCE LABORATORIES 1 | 315 | 2020-02-19 | HOLD - FACILITIES SERVICES | [5 empty] | 9 |  | Spring 2020 | DEBORAH TERAO | PAUL DITTY | 11
CNAS | 20P000368 | FS | SL5 SCI LAB ROOM 317 - PATCH & PAINT | SCIENCE LABORATORIES 1 | 317 | 2020-02-18 | HOLD - FACILITIES SERVICES | [5 empty] | 10 |  | Spring 2020 | DEBORAH TERAO | PAUL DITTY | 11
CNAS | 20P000397 | FS | SL5 ENTOMOLOGY 139 - PATCH AND PAINT OFFICE | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 0139 | 2020-03-05 | QUEUE TO START |  |  |  | Patch and paint room 139 for the new faculty member |  | X | YES | Winter 2021 | WILLIAM SUTTON | Paul Ditty | 14
CNAS | 20P000419 | FS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | HERMAN T. SPIETH HALL | 2312 | 2020-04-22 | QUEUE TO START |  |  |  | Paint Only |  | X | YES | Winter 2021 | ESTELLA DAVALOS | PAUL DITTY | 14
CNAS | 20P000445 | FS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 279 | 2020-06-03 | QUEUE TO START | schedule work inline with current proj. in progres |  |  | Add Air + Vacuum / Remove Sink + Cabinet |  | 3 | YES | Winter 2021 | WILLIAM SUTTON | DAN LERMAN | 14
CNAS | 21P000001 | FS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | HOWARD SAMUEL FAWCETT LABORATORY |  | 2020-06-08 | PLAN DEVELOPMENT/CHECK | Still pending plan check review. |  |  | NEW GROWTH CHAMBER PLACEMENT |  | 2 | YES | Winter 2021 | LINDA WALLING | DAN LERMAN | 14
CNAS | 21P000009 | FS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | CHEMICAL SCIENCES |  | 2020-07-08 | IN PROGRESS | We will start the demolition early next week. | 2021-03-08 | 2021-04-23 | GLOVEBOX SYSTEM |  | 1 | YES | Winter 2021 | NATASHA GONZALES | DAN LERMAN | 14
CNAS | 21P000083 | FS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS BUILDING |  | 2019-12-19 | PROJECT INTAKE |  |  |  | UPDATE KEYCARD SYSTEM FOR BUILDING |  | R1 |  | Winter 2021 | JOSE WUDKA | Enrico Baez | 14
CNAS | 3228b | PD&C | Rubidoux Screenhouse Conv |  |  | 2016-12-06 | In Design (Phase 2) | RPU plan review/design (Phase 2) | 2021-08-01 | 2021-10-01 | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. | 8 |  |  |  | Sabrina Schuster, D. McWilliams | Scott Donnell
ENROLLMENT SERVICES | 20P000336 | FS | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS | STUDENT SUPPORT SERVICES BUILDING | 2109B | 2020-01-22 | HOLD - FACILITIES SERVICES | [5 empty] | 1 |  | Spring 2020 | SELENA SANCHEZ | PAUL DITTY | 11
FAC-PLNG-DESIGN-CONST | 2368 | PD&C | Creekside Drainage Channel |  |  | 2016-05-19 | In Design | Funding & Approval |  |  | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. | 20 |  |  |  | Katie Sanchez | Gerald Caraig
FAC-PLNG-DESIGN-CONST | 2682 | PD&C | DM(FY14) Rivera Library Arches/Arcade Repair | RIVERA LIB |  | 2016-05-06 | Bids received, award on hold due to DM funding | Funding |  |  | Paint and replace roof. | 99 |  |  |  | Susan Marshburn | Scott Donnell
FAC-PLNG-DESIGN-CONST | 2687 | PD&C | DM(FY14) Bourns Fire Alarm Sys Replcmt | BOURNS |  | 2019-06-18 | In Construction | Complete Construction | 2020-12-01 | 2021-05-28 | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | 6 |  |  |  | ----- | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3110 | PD&C | Ag Ops Cell Tower - New |  |  |  | Project is not funded or approved | Approve in CPMS & fund |  |  | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. | 99 |  |  |  | Yvonne Lujan | Yvonne Lujan
FAC-PLNG-DESIGN-CONST | 3195 | PD&C | North District |  |  | 2016-10-26 | In Construction | Complete Construction | 2019-07-01 | 2021-08-01 | Development of UCR North District Development, located near the housing development north of Linden St. | 99 |  |  |  | Raoula Amescua | Drew Hecht
FAC-PLNG-DESIGN-CONST | 3476 | PD&C | DMFI(FY17-19) Tunnel System Plumbing |  |  | 2018-10-17 | Pre-Programming | FS Direction |  |  | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. | 16 |  |  |  | Mihai Gavan | Mihai Gavan
FAC-PLNG-DESIGN-CONST | 3499 | PD&C | Creekside Terrace Analysis (RE Proj) |  |  | 2019-02-14 | In Programming (Study) | Complete Study |  |  | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. | 13 |  |  |  | Blythe Wilson | Thomas Toepfer
FAC-PLNG-DESIGN-CONST | 3527 | PD&C | DMFI(FY17-19) Central Utility Plant Fire Alarm | CNTRL UTL PL |  | 2019-05-08 | In Construction | Complete Construction | 2021-03-01 | 2021-04-01 | Replace aging and non-replaceable fire alarm system, and conduit. Conduit is damaged and only 10% of wiring is usable. ( fire alarm system and devices are failing and they are not supported by manufacture ) | 4 |  |  |  | Ben Kochevar | Daneca Stevens
FAC-PLNG-DESIGN-CONST | 3529 | PD&C | DMFI(FY17-19) Physics 2000 Renewal - Handrail | PHYSICS |  | 2019-05-15 | In Bidding (Re-bid) | Award Contract | 2021-06-01 | 2021-09-01 | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | 3 |  |  |  | Scott Donnell | Scott Donnell
FAC-PLNG-DESIGN-CONST | 3548 | PD&C | DMFI(FY17-19) Fine Arts Performance Lab Ext | ARTS |  | 2019-09-05 | In Funding | Procure Funding |  |  | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | 9 |  |  |  | Scott Donnell | Tameesha Hayes
FAC-PLNG-DESIGN-CONST | 3549 | PD&C | DMFI(FY17-19) Fine Arts Decking | ARTS |  | 2019-09-05 | In Funding | Procure Funding |  |  | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | 8 |  |  |  | Scott Donnell | Tameesha Hayes
FAC-PLNG-DESIGN-CONST | 3550 | PD&C | DMFI(FY17-19) Skye Hall HVAC Replacement | SKYE HALL |  | 2019-09-05 | In Bidding | Award Contract | 2021-05-01 | 2021-08-01 | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | 7 |  |  |  | Scott Donnell | Tameesha Hayes
FAC-PLNG-DESIGN-CONST | 3564 | PD&C | DM(FY17-19) Rivera Library North Wing AHU Replacement | RIVERA LIB |  | 2019-11-06 | On Hold | On Hold |  |  | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | 10 |  |  |  | Scott Donnell | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3607 | PD&C | DM(FY20) Central Utility Plant Controls |  |  | 2020-09-17 | Pre-Programming | Begin RFQ Process |  |  | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) | 1 |  |  |  | David Palacios | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3035a | PD&C | DM(FY16) Spieth Hall Roof Replacement | SPIETH |  | 2016-02-25 | In Design | Bidding | 2021-03-01 | 2021-04-01 | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | 7 |  |  |  | John White | Scott Donnell
FAC-PLNG-DESIGN-CONST | 3590a | PD&C | DMFI(FY17-19) Multiple Projects |  |  | 2020-03-30 | Projects to be assigned | Projects to be assigned |  |  | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. | 4 |  |  |  | Susan McFadden | Scott Donnell
GRAD DIV | 20P000003 | FS | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | UNIVERSITY OFFICE BUILDING |  | 2019-07-02 | IN PROGRESS | schedule inspection by the building inspector | 2021-02-17 | 2021-04-20 | ADD POWER/DATA, PATCH/PAINT |  | 1 |  | FALL 2019 | CYNTHIA CARDENAS | Dan Lerman | 9
INACTIVE P&B | 3541 | PD&C | Olmsted Sidewk/Tunnel V16 Repair | WATKINS |  | 2019-07-30 | In Funding | Secure Funding | 2021-06-01 | 2021-07-01 | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | 2 |  |  |  | Gerald Caraig | Daneca Stevens
PALM DESERT GRAD CTR | 3104 | PD&C | Palm Desert Campus Access Evaluation | HECKMANN PH2 |  | 2016-05-12 | In Funding | Approval & Funding |  |  | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | 1 |  |  |  | Zelda Glenn | Scott Donnell
PB&A | 2900 | PD&C | Batchelor Hall Systems Renewal | BATCHELOR |  | 2015-12-15 | Sub-contractor bidding | Start Construction | 2021-04-01 | 2023-08-01 | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | 16 |  |  |  | Sharyl Murdock | Rowan Reid
PB&A | 3203 | PD&C | Plaza Seismic Structural Repairs | THE PLAZA |  | 2016-10-10 | In Programming | Design |  |  | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | 22 |  |  |  | Richard Geiger | Daneca Stevens
PB&A | 3286 | PD&C | Falkirk Apartments Seismic Improvements | FALKIRK 1 |  | 2017-03-29 | In Construction | Complete Construction | 2021-02-01 | 2021-05-01 | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | 10 |  |  |  | Sean Hatfield | John Franklin
PB&A | 3382 | PD&C | West Lothian Restroom & Common Area Design | LOTHIAN HALL |  | 2017-09-29 | Project pushed to 2021 | Project pushed to 2021 |  |  | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | 20 |  |  |  | Sean Hatfield | D.Hecht/J.Franklin
PB&A | 3421 | PD&C | A-I Boiler Replacement | ABER INVER |  | 2018-03-19 | On Hold-Funding | CIB Approval |  |  | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | 6 |  |  |  | Sean Hatfield | John Franklin
PB&A | 3466 | PD&C | Oban Porch and Stair Repair | OBAN APTS A |  | 2018-07-31 | Design | Bidding | 2021-06-01 | 2021-08-01 | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | 19 |  |  |  | Richard Geiger | Daneca Stevens
PB&A | 3467 | PD&C | Plaza Porch/Stair Structural Repairs | THE PLAZA |  | 2018-07-31 | Bidding - 3rd flr Walking Deck Only | Award Contract | 2021-05-01 | 2021-06-01 | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | 17 |  |  |  | Richard Geiger | Daneca Stevens
PB&A | 3470 | PD&C | 2018 Campus Seismic Audit |  |  | 2018-11-06 | Tier III evaluations pending | Complete Review |  |  | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. | 19 |  |  |  | Drew Hecht | Drew Hecht
PB&A | 3474 | PD&C | RUSD STEM High School |  |  | 2018-10-31 | In Programming (Study) | CEQA |  |  | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. | 14 |  |  |  | ----- | Thomas Toepfer
PB&A | 3490 | PD&C | Parking Structure 1 | Parking Lot 13 |  | 2018-12-06 | In Construction | Complete Construction | 2020-02-01 | 2021-05-01 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | 25 |  |  |  | Irma Henderson | D.Hecht/J.Franklin
PB&A | 3492 | PD&C | W.Campus Irrigation System Study |  |  | 2019-03-04 | Programming (Study) | Complete Study |  |  | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. | 10 |  |  |  | Scott Donnell | Scott Donnell
PB&A | 3501 | PD&C | DMFI(FY17-19) Watkins 1000 Lecture Hall Reno | WATKINS |  | 2019-03-04 | In Construction | Complete Construction | 2020-07-01 | 2021-03-01 | Renovation of Watkins 1000 lecture hall, to include lighting, HVAC, flooring, paint, and seating upgrades. This requests appears as projects Q-T on the approved 2017-2019 DMFI Program list. | 7 |  |  |  | Scott Donnell | Tameesha Hayes
PB&A | 3507 | PD&C | Undergraduate Teaching & Learning Facility |  |  | 2019-03-04 | In Programming | DB Competition |  |  | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. | 9 |  |  |  | Michelle Baniqued | Dexter Galang
PB&A | 3508 | PD&C | SOM Education Bldg 2 |  |  | 2019-03-04 | Design | Construction | 2021-07-01 | 2023-05-01 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. | 8 |  |  |  | Melissa Garrety | Mihai Gavan
PB&A | 3510 | PD&C | SOMED Data Center Upgrade | SOM EDUC |  | 2019-03-04 | In Bidding | Award Contract | 2021-05-01 | 2021-09-01 | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | 4 |  |  |  | Daneca Stevens | Tameesha Hayes
PB&A | 3516 | PD&C | Student Health & Counseling Center (SHCC) |  |  | 2019-03-04 | Bidding Competition | Select Design Builder | 2021-10-01 | 2023-04-01 | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. | 1 |  |  |  | Michelle Baniqued | Fernando Canon
PB&A | 3523 | PD&C | 1907 Mt Rubidoux Facility Study |  |  | 2019-04-22 | Programming (Study) | Complete Study |  |  | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. | 3 |  |  |  | Melissa Garrety | Scott Donnell
PB&A | 3533 | PD&C | Solar Rooftop Initiative | MULTIPLE BUILDINGS |  | 2019-06-03 | In Construction | Complete Construction | 2020-10-01 | 2021-05-01 | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. | 9 |  |  |  | Richard Geiger | John Franklin
PB&A | 3597 | PD&C | Plaza F Roof Replacement |  |  | 2020-06-17 | In Construction | Complete Construction | 2021-02-01 | 2021-04-01 | Plaza building F roof is well past its service life and is experiencing multiple leaks into the apartment spaces below. This scope of work is to replace the roof in total and repair damages observed to the apartments below as a result of roof leaks. REQUESTING JOHN FRANKLIN AS THE PROJECT MANAGER. | 18 |  |  |  | Sean Hatfield | John Franklin
PB&A | 3610 | PD&C | Hulen Place Homeless Medical Clinic |  |  | 2020-10-06 | In Construction | Complete Construction | 2021-03-01 | 2021-03-01 | SOM is acquiring additional space for a medical clinic to assist with the homeless population. | 5 |  |  |  | Diana Armenta | Daneca Stevens
PB&A | 9058 | PD&C | Lothian West Rooftop Solar |  |  | 2020-09-23 | In Design | Bidding | 2021-06-01 | 2021-09-01 |  | 99 |  |  |  | Sean Hatfield | John Franklin
PB&A | 9059 | PD&C | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches |  |  | 2020-09-22 | Design | Bidding | 2021-07-01 | 2021-10-01 | Replace ten gas filled - medium voltage switches | 99 |  |  |  | David Palacios | John Franklin
PB&A | 9060 | PD&C | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  | 2020-09-15 | In Bidding | Award Contract | 2021-04-01 | 2021-04-01 |  | 99 |  |  |  |  | Daneca Stevens
PB&A | 9061 | PD&C | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Design | Bidding |  |  |  | 99 |  |  |  |  | Tameesha Hayes
PB&A | 9062 | PD&C | DM(FY20) Life Sci Sewer line |  |  | 2020-09-15 | In Construction | Complete Construction | 2021-03-01 | 2021-03-01 |  | 99 |  |  |  |  | Daneca Stevens
PB&A | 20P000275 | FS | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE | MAIL BUILDING | 884 | 2019-12-04 | HOLD - FACILITIES SERVICES | [5 empty] | 1 |  | Spring 2020 | JENNIFER TENNEY STRATTON | PAUL DITTY | 11
PB&A | 21P000003 | FS | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | CC LIND 691 | ROOF | 2020-06-26 | PROJECT INTAKE |  |  |  | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. |  | R1 |  | Winter 2021 | SEAN HATFIELD | Enrico Baez | 14
PB&A | 3515b | PD&C | DM(FY18) Elec Substation & Infra. Renewal |  |  | 2019-03-08 | In Programming | Complete Report-Arc Flash |  |  | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. | 2 |  |  |  | Ron Rector | J.Franklin/G.Caraig
PB&A | 3515c | PD&C | DM(FY18) Elec Substation & Infra. Renewal |  |  | 2019-03-08 | In Construction | Complete Construction | 2020-12-01 | 2021-06-01 | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. | 2 |  |  |  | Ron Rector | J.Franklin/G.Caraig
PB&A | 3515d | PD&C | Multiple SF6 Primary Switches |  |  | 2021-03-01 | TBD | TBD |  |  | Sub-project of 950568 | 2 |  |  |  | John Franklin | J.Franklin/G.Caraig
PB&A | 3590b | PD&C | DMFI(FY17-20) Physics Elevator Modernization | PHYSICS |  | 2019-11-27 | In Bidding | Award Contract | 2021-04-05 | 2021-06-01 | Physics Elevator Modernization | 4 |  |  |  | Ben Kochevar | Fernando Nunez
SoB | 2725 | PD&C | School of Business Professional Schools Study |  |  | 2016-12-15 | Commencing Technical Criteria Phase | Completion of Basis of Design |  |  | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. | 1 |  |  |  | Leo Gonzalez | Rowan Reid
SOM | 3581 | PD&C | SOMR Interior Egress Doors |  |  | 2020-03-04 | In Funding | Procure Funding |  |  | All egress doors - Floors 1, 2, and 3 - need to be replaced with compliant structures. Please inspect, evaluate and provide quote. | 2 |  |  |  | Cynthia Carolina | Tameesha Hayes
SOM | 3603 | PD&C | Orbach Libr SOM CSSS AV Equipment |  |  | 2020-07-27 | In Construction | Complete Construction | 2020-12-01 | 2021-04-01 | AV for CSSS project - 954044 / re: Fernando Cortez. Please refer to MSRIV in the line reference field for the draw down. | 1 |  |  |  | Deborah Trujillo | Fernando Canon
SOM | 20P000467 | FS | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | HERBERT JOHN WEBBER HALL | 1247 | 2020-06-19 | QUEUE TO START |  |  |  | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. |  | X | YES | Winter 2021 | CYNTHIA CAROLINA | PAUL DITTY | 14
UNDERGRADUATE EDUCATION | 3626 | PD&C | Rivera Library Room Modifications |  | A101A | 2021-02-10 | New (2/10/21) | New (2/10/21) |  |  | Conduct room modifications to support new wall display on west wall Rivera A101A. Work needed: 1. West wall - ½” three-ply to support 12 x 55” displays over bookshelves. 2. West wall – drywall cover bookshelves any area not covered by the technology displays. 3. West wall – add electrical outlets as needed for new displays 4. North and south walls – add electrical for new motorized shades 5. Rivera A101A – add carpeting 6. Rivera A101A – paint room Notes: - Working with Chuck Forsyth in ITS and Bahram Mobasher from CNAS/Physics on project. - Israel and Chuck had a preliminary meeting with Enrico Baez from facilities to discuss project. - Point of contact: Israel Fletes and Charles Forsyth. Israel Fletes cellphone: 951-300-6693 | 1 |  |  |  | Israel Fletes | Vilma Kern
UNEX | 3574 | PD&C | UNEX Roof Repair/Solar | UCR EXTEN CT |  | 2019-12-10 | On Hold | Departmental Approval |  |  | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | 2 |  |  |  | Sandy Navarro | Tameesha Hayes
VC-RED | 3326 | PD&C | Genomics 1120A - Power & UPS | GENOMICS |  | 2017-06-13 | On Hold | On Hold |  |  | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | 1 |  |  |  | T.Girke, L.Manor, D.McWilliams | Daneca Stevens
VC-RED | 20P000218 | FS | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | HERMAN T. SPIETH HALL | 347 | 2019-05-17 | QUEUE TO START | We will start once priority 1 projects are complet |  |  | VIVARIUM UPDATE AIR COMPRESSOR |  | 2 |  | Winter 2021 | DIERK BIGGS | DAN LERMAN | 14
VC-RED | 20P000354 | FS | SL5 UOB 200 - PAINT & PATCH OFFICES | UNIVERSITY OFFICE BUILDING | 200 | 2020-02-07 | HOLD - FACILITIES SERVICES | [5 empty] | 1 |  | Spring 2020 | MARISELA MARTINEZ | PAUL DITTY | 11
VC-RED | 20P000468 | FS | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | HERMAN T. SPIETH HALL | 364 | 2020-06-23 | QUEUE TO START |  |  |  | Paint Only |  | X |  | Winter 2021 | JOHNNY PHAN | PAUL DITTY | 14
VC-RED | 21P000078 | FS | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MULTIDISCIPLINARY RESEARCH BUILDING |  | 2020-09-23 | IN PROGRESS | Start 2nd floor install |  |  | QTY 32 -80 FREEZERS CHILLED CONNECTIONS |  | 1 |  | Winter 2021 | TARA BARTHOL | DAN LERMAN | 14
VC-RED | 21P000079 | FS | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | PSYCHOLOGY BUILDING |  | 2020-09-25 | QUEUE TO START |  |  |  | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. |  | X |  | Winter 2021 | LESLIE KARPINSKI | PAUL DITTY | 14
VC-STU AFF | 3471 | PD&C | HUB Electrical Sub Meter Installation | HUB |  | 2018-08-20 | In Bidding | Award Contract | 2021-04-01 | 2021-05-01 | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | 4 |  |  |  | Brendan O'Brien | Tameesha Hayes
VC-STU AFF | 3512 | PD&C | Hinderaker VCSA Office | HINDERAKER | 2108ACDEF | 2019-03-19 | On Hold (COVID-19) | On hold (COVID-19) |  |  | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | 5 |  |  |  | Christina Wong | Tameesha Hayes
VC-STU AFF | 3524 | PD&C | Student Srvs Bldg 1st Floor Reno | STUDENT SERV |  | 2019-04-16 | Design | BKM Lead Time 10 Weeks | 2021-06-01 | 2021-07-01 | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | 1 |  |  |  | Laura Riley | Daneca Stevens
VC-STU AFF | 3608 | PD&C | HUB2 Roof Repair/Replacement |  |  | 2020-09-21 | In Bidding | Award Contract |  |  | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. | 3 |  |  |  | Brendan O'Brien | Tameesha Hayes
VC-STU AFF | 20P000196 | FS | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | JEANETTE AND RUPERT COSTO HALL |  | 2019-10-24 | PROJECT INTAKE |  |  |  | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. |  | R1 |  | Winter 2021 | BRENDAN O'BRIEN | Enrico Baez | 14
To view projects for a specific organization ONLY, click on the filter options HERE.

## Project Detail
Project Status Report | [5 empty] | Last Updated | 2021-03-16
FS
SL5 SKYE 2ND FLOOR - KEY CARD ACCESS ESTIMATE
Project Reference No. | 20P000086
FS
Financials
Project Manager | Dan Lerman | Organization | CNAS | Prioritization Designate | Jose Wudka | PD&C Approved Budget
Contact/ Requestor | JAMES MARBERRY | Building | SKYE HALL | Project Service Unit | FS | FS Recharge Actuals To Date
CPMS # |  | Room | 2ND FLOOR | PD&C Org Priority No. |  | Core / Non-Core | CORE
FS # | 20P000086 | Request Date | 2019-08-19 | FS Org Priority No. | R3
For Faculty Hire
Project Description
FS
Project Status
Project Status | CANCELED BY CLIENT |  |  |  | START Date
Next Steps |  |  |  |  | COMPLETION Date
IRT Status
FS
Campus Impact (i.e. excessive noise / limited access / utility shutdown)
Description
Impact Start
Impact End
FS
PM Notes |  | Project Manager | Dan Lerman | PM Email | daniel.lerman@ucr.edu | PM Phone | 951-827-6224
09/26/19 O-ANS: CANCELED BY CUSTOMER - Estimated cost to go keyless outside of budget.
FS
Scope |  | Reviewer | Enrico Baez | BZM Email | enrico.baez@ucr.edu | BZM Phone | 951-827-4214
Provide estimate for keyless entry.
Scope Completed
To view more detailed information for a specific project, type in the Project Reference No. or clear the field and then scroll through the dropdown list HERE.

## FS Closed Projects
CLOSED Facilities Services Summary Report | [7 empty] | **Closed FS Projects include projects that have been Completed, Canceled by FS, Canceled by Client and projects To Be Performed by PD&C.
Total Closed FS Projects |  | 244
Last Updated | 2021-03-16 | FS Project Summary
Organization | Project Ref No. | Project Service Unit | Project Title | Building | Room | Request Date | Current Status | Completed Date | Fiscal Year | FS Org Priority No. | For New Faculty Hire? | Contact | Proj Manager
CHASS | 18P000126 | FS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS | HUM & SOC SC | 3611 | 2017-09-28 | COMPLETE | 2019-07-01 | FY 19-20 | 21 |  | DARA CERDA | Dan Lerman
CNAS | 19P000390 | FS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE | BOYCE | 5494 | 2018-11-29 | COMPLETE | 2019-07-01 | FY 19-20 | 0 | YES | APRIL MEINZER | Dan Lerman
CNAS | 19P000210 | FS | SL5 CHEMICAL SCI Install Door In Doorway | CHEMICAL SCI | 0225A | 2018-08-24 | COMPLETE | 2019-07-01 | FY 19-20 | 25 |  | BARBARA OUTZEN | Dan Lerman
PB&A | 19P000209 | FS | SL5 OLD EH&S SITE- FS ANNEX A REMODEL | ENV HLTHSFTY | 100 | 2018-08-24 | COMPLETE | 2019-07-01 | FY 19-20 |  |  | FRANCES RAVE | Craig/Chris Pillen
SOM | 19P000245 | FS | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY | SOM RSCH |  | 2018-09-07 | COMPLETE | 2019-07-01 | FY 19-20 | 4 |  | DEBORAH TRUJILLO | Dan Lerman
CHASS | 19P000574 | FS | SL5 FACULTY OFFICE PAINTING | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | 2019-04-12 | COMPLETE | 2019-07-03 | FY 19-20 | 3 |  | JILL CANTONWINE | Paul Ditty
CHASS | 19P000609 | FS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR | WATKINS | 1229 | 2019-05-10 | COMPLETE | 2019-07-03 | FY 19-20 | 4 |  | PAUL RICHARDSON | Paul Ditty
BCOE | 19P000558 | FS | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT | BOURNS | A0265 | 2019-04-03 | COMPLETE | 2019-07-09 | FY 19-20 | 5 |  | ROBERT LOPEZ-A | Paul Ditty
CHASS | 19P000552 | FS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS | HUM & SOC SC | 1001 B, C, and D | 2019-03-27 | COMPLETE | 2019-07-09 | FY 19-20 | 7 |  | JILL CANTONWINE | Paul Ditty
SoB | 19P000521 | FS | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT | ANDERSON 1 (N) | 138 | 2019-03-08 | COMPLETE | 2019-07-09 | FY 19-20 | 1 |  | ANGELA CHANG | Paul Ditty
BCOE | 19P000388 | FS | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | SKYE HALL | 308 | 2018-11-26 | COMPLETE | 2019-07-15 | FY 19-20 | 0 |  | SHARYL MURDOCK | Dan Lerman
CHASS | 19P000607 | FS | SL5 PAINT FACULTY OFFICE | WATKINS | 1312 | 2019-05-10 | CANCELED BY CLIENT | 2019-07-16 | FY 19-20 | 2 | YES | BECKY CAMPBELL | Paul Ditty
CHASS | 19P000605 | FS | SL5 PAINT NEW MAILROOM | WATKINS | 1320E | 2019-05-10 | CANCELED BY CLIENT | 2019-07-16 | FY 19-20 | 4 |  | BECKY CAMPBELL | Paul Ditty
CNAS | 19P000614 | FS | SL5 COLLEGE BLDG NO, RM 202- PAINT | COLL BLDG NO | 0202 | 2019-05-14 | CANCELED BY FS | 2019-07-16 | FY 19-20 | 4 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000616 | FS | SL5 COLLEGE BLDG NO, RM 208- PAINT | COLL BLDG NO | 208 | 2019-05-14 | CANCELED BY FS | 2019-07-16 | FY 19-20 | 6 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000617 | FS | SL5 COLLEGE BLDG NO, RM 212- PAINT | COLL BLDG NO | 212 | 2019-05-14 | CANCELED BY FS | 2019-07-16 | FY 19-20 | 7 |  | RONDA INZUNZA | Paul Ditty
BCOE | 19P000597 | FS | SL5 PATCH AND PAINT WALLS | CHUNG HALL | 355, 356, 351, & 353 | 2019-05-03 | COMPLETE | 2019-07-16 | FY 19-20 | 3 |  | SARA GALLOWAY | Paul Ditty
CHASS | 19P000643 | FS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | 2019-05-21 | COMPLETE | 2019-07-16 | FY 19-20 | 14 |  | CHRISTY GRAY | Paul Ditty
CHASS | 19P000642 | FS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | 2019-05-21 | COMPLETE | 2019-07-16 | FY 19-20 | 6 |  | CHRISTY GRAY | Paul Ditty
ITS | 18W007453 | FS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. | ITS CENTER | 100 | 2017-11-30 | CANCELED BY FS | 2019-07-22 | FY 19-20 |  |  | SHEILA MABEE | Dan Lerman
BCOE | 19P000487 | FS | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES | BOURNS | A219, A211, A241 | 2019-02-05 | COMPLETE | 2019-07-22 | FY 19-20 | 2 |  | DEANNA VORHEES | Paul Ditty
PB&A | 19P000599 | FS | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS | CORP B | 126 | 2019-05-09 | COMPLETE | 2019-07-22 | FY 19-20 | R1 |  | HELMA AVILA | Paul Ditty
PROVOST/EVC | 19P000434 | FS | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | SKYE HALL | 136 | 2019-01-07 | COMPLETE | 2019-07-22 | FY 19-20 | 2 |  | THERESA WAGNER | Paul Ditty
CHASS | 19P000429 | FS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | COLL BLDG NO | 103 | 2019-01-03 | COMPLETE | 2019-07-26 | FY 19-20 | 9 |  | RENEE DEGUIRE | Paul Ditty
PB&A | 19P000535 | FS | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV | BANNOCK H | H0108 | 2019-03-14 | COMPLETE | 2019-07-26 | FY 19-20 | R1 |  | EDWIN MELGAR-MEJIA | Dan Lerman
VC-RED | 19P000553 | FS | SL5 SPIETH HALL PATCH AND PAINT | SPIETH | 341 | 2019-04-01 | COMPLETE | 2019-07-26 | FY 19-20 | 1 |  | JOHNNY PHAN | Paul Ditty
BCOE | 19P000565 | FS | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS | BOURNS | A0133 | 2019-04-08 | CANCELED BY CLIENT | 2019-07-30 | FY 19-20 | 7 |  | NANCY FORD | Paul Ditty
BCOE | 19P000477 | FS | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT | CHUNG HALL | 457 | 2019-01-30 | COMPLETE | 2019-07-30 | FY 19-20 | 11 |  | ROBERT LOPEZ-A | Paul Ditty
CNAS | 19P000571 | FS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 | SCIENCE LAB1 | 215 & 322 | 2019-04-10 | COMPLETE | 2019-07-30 | FY 19-20 | 10 |  | DEBORAH TERAO | Paul Ditty
VC-RED | 19P000495 | FS | SL5 UOB RM 209- PATCH & PAINT | UNIV OFC BLD | 209 | 2019-02-08 | COMPLETE | 2019-07-30 | FY 19-20 | 2 |  | CRYSTAL JIMENEZ | Paul Ditty
BCOE | 19P000625 | FS | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM | BOURNS | A0108 | 2019-05-15 | COMPLETE | 2019-08-01 | FY 19-20 | 4 |  | LOUIS SANDOVAL | Paul Ditty
CHASS | 19P000207 | FS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | OLMSTED |  | 2018-08-23 | COMPLETE | 2019-08-01 | FY 19-20 | 7 |  | TOYA ADAMS | Dan Lerman
CNAS | 19P000283 | FS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | CHUNG HALL | ROOF | 2018-09-05 | COMPLETE | 2019-08-01 | FY 19-20 | 20 |  | DEBORAH MCWILLIAMS | Dan Lerman
CNAS | 18P000486 | FS | SL5 PHYSICS 3027/3028 RENOVATION | PHYSICS | 3027 | 2018-06-28 | COMPLETE | 2019-08-01 | FY 19-20 | 24 |  | MAYELA CASTILLO | Dan Lerman
SoB | 18P000351 | FS | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | ANDERSON 1 (N) | 21 | 2018-03-19 | COMPLETE | 2019-08-01 | FY 19-20 |  |  | ANGELA CHANG | Dan Lerman
VC-UNIV ADV | 19P000417 | FS | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY | UV BLDG A | 201 | 2018-12-18 | CANCELED BY CLIENT | 2019-08-06 | FY 19-20 | R1 |  | NAYSIA CALDWELL | Dan Lerman
BCOE | 19P000526 | FS | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT | CHUNG HALL | 0202 & 0203 | 2019-03-12 | COMPLETE | 2019-08-08 | FY 19-20 | 6 |  | ROBERT LOPEZ-A | Paul Ditty
CNAS | 18P000388 | FS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | SPIETH | 0317A | 2018-04-10 | COMPLETE | 2019-08-14 | FY 19-20 | 22 |  | ESTELLA DAVALOS | Dan Lerman
CHASS | 19P000350 | FS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | PSYCHOLOGY1 | 3121, 1133 | 2018-10-17 | COMPLETE | 2019-08-15 | FY 19-20 | 4 | YES | TOYA ADAMS | Dan Lerman
CNAS | 19P000613 | FS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT | COLL BLDG NO | 0203B | 2019-05-14 | COMPLETE | 2019-08-21 | FY 19-20 | 3 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000615 | FS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT | COLL BLDG NO | 203 AND 204 | 2019-05-14 | COMPLETE | 2019-08-22 | FY 19-20 | 5 |  | RONDA INZUNZA | Paul Ditty
GSOE | 19P000628 | FS | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE | SPROUL | 2129 | 2019-05-15 | COMPLETE | 2019-08-22 | FY 19-20 | 1 |  | SALLY TAVIZON | Paul Ditty
CNAS | 19P000413 | FS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | BATCHELOR | 3111 | 2018-12-17 | CANCELED BY CLIENT | 2019-08-26 | FY 19-20 | R1 |  | MATTHEW ULRICH | Dan Lerman
CHASS | 19P000608 | FS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE | WATKINS | 1345 | 2019-05-10 | COMPLETE | 2019-08-27 | FY 19-20 | 9 |  | BECKY CAMPBELL | Paul Ditty
FAC-PLNG-DESIGN-CONST | 19P000645 | FS | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT | BOTAN INFO C |  | 2019-05-22 | CANCELED BY FS | 2019-08-29 | FY 19-20 | R2 |  | RONALD ANDERSON | Dan Lerman
PB&A | 20P000223 | FS | SL5 PENTLAND HILLS - SHOWER PAN REPLACEMENTS | PENTLAND A | A238, B245, B325, C215, F325 | 2019-11-15 | COMPLETE | 2019-09-01 | FY 19-20 | R3 |  | SEAN HATFIELD | John Peraino
FAC-PLNG-DESIGN-CONST | 19P000560 | FS | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION | UV BLDG B | 0240B | 2019-04-04 | COMPLETE | 2019-09-03 | FY 19-20 | R1 |  | LESLIE ROSE | Dan Lerman
CHASS | 19P000448 | FS | SL5 ARTS 333- PATCH AND PAINT | ARTS | 333 | 2019-01-14 | COMPLETE | 2019-09-04 | FY 19-20 | 8 |  | SONJA SEKELY-ROWLAND | Paul Ditty
CHASS | 19P000575 | FS | SL5 WATKINS HALL PAINT/FLOORING | WATKINS | 1309A | 2019-04-17 | COMPLETE | 2019-09-05 | FY 19-20 | 1 |  | PAUL RICHARDSON | Paul Ditty
SOM | 19P000670 | FS | SL5 SOME, RM 1670- RENOVATE FOR EXPANDED ENROLLMENT | SOM EDUC | 1670 | 2019-06-18 | TO BE PERFORMED BY PD&C | 2019-09-06 | FY 19-20 |  |  | DEBORAH TRUJILLO | Dan Lerman
VC-UNIV ADV | 19P000564 | FS | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | HINDERAKER | 1156 | 2019-04-08 | COMPLETE | 2019-09-07 | FY 19-20 | 1 |  | Lisa Cusick | Paul Ditty
ATHLETICS | 19P000646 | FS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING | ATH DANCE | 20R, 20S | 2019-05-23 | COMPLETE | 2019-09-16 | FY 19-20 | 1 |  | JOSEPH ERBLAND | Dan Lerman
BCOE | 19P000623 | FS | HOLD SL5 WINSTON CHUNG HALL, RM 348- MOUNT TV | CHUNG HALL | 0348 | 2019-05-15 | COMPLETE | 2019-09-16 | FY 19-20 |  |  | BILL BINGHAM | Paul Ditty
CNAS | 18P000465 | FS | SL 5 GEOLOGY 2258B AND 2258C - PATCH/PAINT | GEOLOGY | 2258B & 2258C | 2018-06-06 | COMPLETE | 2019-09-16 | FY 19-20 | COMPLETED |  | RONDA INZUNZA | Paul Ditty
FAC-PLNG-DESIGN-CONST | 20P000085 | FS | SL5 FACILITES ANNEX B - PAINT OFFICE SPACE | CUST AND GRD | 0001 | 2019-08-19 | COMPLETE | 2019-09-16 | FY 19-20 | COMPLETED |  | SANDRA MARTINEZ | Paul Ditty
BCOE | 20P000065 | FS | SL5 CHUNG HALL 2ND FLOOR CONFERENCE ROOM 205/206 - PATCH & PAINT | CHUNG HALL | 205 & 206 | 2019-08-08 | COMPLETE | 2019-09-17 | FY 19-20 | 5 |  | ROBERT LOPEZ-A | Paul Ditty
CHASS | 20P000004 | FS | SL5 NEW FACULTY HIRE - ROOM PAINTING - COURTNEY BAKER | HUM & SOC SC | 2204 | 2019-07-02 | COMPLETE | 2019-09-17 | FY 19-20 | 2 |  | CHRISTY GRAY | Paul Ditty
CHASS | 20P000005 | FS | SL5 NEW FACULTY HIRE - ROOM PAINTING - KIM FROST | HUM & SOC SC | 3215 | 2019-07-02 | COMPLETE | 2019-09-17 | FY 19-20 | 3 |  | CHRISTY GRAY | Paul Ditty
CNAS | 19P000594 | FS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS | ENTOMOLOGY | 171 | 2019-04-26 | CANCELED BY CLIENT | 2019-09-18 | FY 19-20 | R9 |  | WILLIAM SUTTON | Dan Lerman
CHASS | 20P000094 | FS | SL5 ARTS 0221 -PAINT OFFICE | ARTS | 221 | 2019-08-22 | COMPLETE | 2019-09-18 | FY 19-20 | 8 |  | SUSAN KOMURA | Paul Ditty
PB&A | 20P000114 | FS | SL5 PENTLAND HILLS - SHOWER DOOR, BASEBOARD, AND BRACKETS | PENTLAND A |  | 2019-09-05 | COMPLETE | 2019-09-18 | FY 19-20 | R1 |  | SEAN HATFIELD | John Peraino
PB&A | 20P000115 | FS | SL5 FALKIRK APARTMENTS 1 - BALCONY COSMETIC REPAIRS | FALKIRK 1 | 2nd Floor | 2019-09-05 | COMPLETE | 2019-09-18 | FY 19-20 | R2 |  | SEAN HATFIELD | John Peraino
PB&A | 20P000116 | FS | SL5 FALKIRK APARTMENTS 5 - BALCONY EMERGENCY REPAIRS | FALKIRK 1 | 2nd Floor | 2019-09-05 | COMPLETE | 2019-09-18 | FY 19-20 | R3 |  | SEAN HATFIELD | John Peraino
PB&A | 20P000117 | FS | SL5 PENTLAND HILLS A-H - LATTICE REBUILD | PENTLAND A | A-H | 2019-09-05 | COMPLETE | 2019-09-18 | FY 19-20 | R4 |  | SEAN HATFIELD | John Peraino
PB&A | 20P000118 | FS | SL5 FALKIRK 1, 2, & 12 - FIRST FLOOR PATIO FENCING | FALKIRK 1 | 1st Floor | 2019-09-05 | COMPLETE | 2019-09-18 | FY 19-20 | R5 |  | SEAN HATFIELD | John Peraino
CHASS | 19P000674 | FS | SL5 HMSS RM 2416 OFFICE ROOM PATCH AND PAINT | HUM & SOC SC | 2416 | 2019-06-19 | TO BE PERFORMED BY PD&C | 2019-09-23 | FY 19-20 | 6 |  | JENNIFER HAMILTON | Paul Ditty
CNAS | 20P000038 | FS | SL5 BATCHELOR HALL 1151- QUOTE FOR ADDING FOB ACCESS TO A DOOR | BATCHELOR | 1151 | 2019-07-24 | CANCELED BY CLIENT | 2019-09-24 | FY 19-20 | R1 |  | RACHEL BEHAR | Dan Lerman
CHASS | 19P000568 | FS | HOLD SL5 HMSS HANG WHITE BOARD, TV MOUNTING, PATCH AND PAINT | HUM & SOC SC | 1214 | 2019-04-09 | COMPLETE | 2019-09-24 | FY 19-20 | R1 |  | ALLISON ROGERS | Dan Lerman
PB&A | 20P000037 | FS | SL5 FAC ADMINISTRATION -PAINT WALLS | CORP B | 126 | 2019-07-23 | COMPLETE | 2019-09-24 | FY 19-20 | R1 |  | HELMA AVILA | Paul Ditty
CNAS | 20P000086 | FS | SL5 SKYE 2ND FLOOR - KEY CARD ACCESS ESTIMATE | SKYE HALL | 2ND FLOOR | 2019-08-19 | CANCELED BY CLIENT | 2019-09-26 | FY 19-20 | R3 |  | JAMES MARBERRY | Dan Lerman
BCOE | 20P000107 | FS | SL5 WINSTON CHUNG 322 - PATCH/PAINT NEW FACULTY FACULTY OFFICE | CHUNG HALL | 322 | 2019-08-29 | COMPLETE | 2019-09-26 | FY 19-20 | 1 |  | BILL BINGHAM | Paul Ditty
BCOE | 19P000657 | FS | SL5 WINSTON CHUNG HALL, RM 406- PATCH/PAINT OFFICE | CHUNG HALL | 406 | 2019-06-07 | COMPLETE | 2019-09-26 | FY 19-20 | 6 |  | BILL BINGHAM | Paul Ditty
CNAS | 20P000075 | FS | SL5 SPIETH 2372 - PATCH/PAINT FACULTY OFFICE | SPIETH | 2372 | 2019-08-13 | COMPLETE | 2019-09-27 | FY 19-20 | 1 |  | DEBORAH MCWILLIAMS | Paul Ditty
SOM | 20P000060 | FS | SL5 WEBBER HALL 1274- PATCH & PAINT OFFICE | WEBBER | 1274 | 2019-08-05 | COMPLETE | 2019-09-28 | FY 19-20 | 3 |  | TARA BARTHOL | Paul Ditty
SOM | 19P000661 | FS | SL5 SOM RB, CR0600- FY 19/20 PROJECT- PATCH & PAINT | SOM EDUC | CR0600 | 2019-06-11 | COMPLETE | 2019-09-30 | FY 19-20 | 2 |  | DEBORAH TRUJILLO | Paul Ditty
VC-RED | 20P000149 | FS | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 242 | UNIV OFC BLD | 242 | 2019-09-25 | COMPLETE | 2019-09-30 | FY 19-20 | - |  | GLORIA GALLEGO | Paul Ditty
CHANCELLOR | 20P000068 | FS | SL5 SKYE 349 - COVER HOLES ON WALL | SKYE HALL | 349 | 2019-08-09 | COMPLETE | 2019-10-01 | FY 19-20 | 1 |  | VICTORIA AVALOS | Paul Ditty
CHASS | 19P000337 | FS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | PSYCHOLOGY1 | 3210 | 2018-10-11 | COMPLETE | 2019-10-01 | FY 19-20 | 1 |  | TOYA ADAMS | Dan Lerman
SOB | 19P000673 | FS | SL5 ANDERSON HAL NO, RM 158- RECARPET 12 ROOMS / ELECTRICAL WORK | ANDERSON 1 (N) | 158 | 2019-06-18 | COMPLETE | 2019-10-01 | FY 19-20 | 1 |  | ANGELA CHANG | Dan Lerman
SOM | 20P000051 | FS | SL5 SOMED 2611 - PATCH & PAINT | SOM EDUC | 2611 | 2019-07-31 | COMPLETE | 2019-10-01 | FY 19-20 | 5 |  | DEBORAH TRUJILLO | Paul Ditty
CNAS | 20P000034 | FS | SL5 CHEMICAL SCIENCES 451- PATCH AND PAINT 2 SMALL WALL SECTIONS | CHEMICAL SCI | 451 | 2019-07-22 | COMPLETE | 2019-10-02 | FY 19-20 | 2 |  | KEVIN KOU | Paul Ditty
CHASS | 20P000143 | FS | SL5 HUMANITIES SOCSCI 6605 - PATCH AND PAINT IN FACULTY OFFICE | HUM & SOC SC | 6605 | 2019-09-26 | COMPLETE | 2019-10-03 | FY 19-20 | - |  | ALLISON ROGERS | Paul Ditty
GSOE | 20P000031 | FS | SL5 SPROUL HALL 1124B- PATCH/PAINT OFFICE | SPROUL | 1124B | 2019-07-22 | COMPLETE | 2019-10-03 | FY 19-20 | 1 |  | MARICELA ARCINIEGA | Paul Ditty
PROVOST/EVC | 19P000683 | FS | SL5 PATHC/PAINTING REPAIR | HUM & SOC SC | 1103A | 2019-06-25 | COMPLETE | 2019-10-03 | FY 19-20 | 1 |  | JILL CANTONWINE | Paul Ditty
SOM | 20P000152 | FS | SL5 SOME 2669 - PATCH & PAINT | SOM EDUC | 2669 | 2019-09-30 | COMPLETE | 2019-10-03 | FY 19-20 | - |  | DEBORAH TRUJILLO | Paul Ditty
CHASS | 20P000090 | FS | SL5 OLMSTED 3345 - PAINT WALL AND FILL HOLES | OLMSTED | 3345 | 2019-08-20 | COMPLETE | 2019-10-04 | FY 19-20 | 4 |  | EMILY LAM | Paul Ditty
CHASS | 19P000676 | FS | SL5 PATCH THE PAINT IN THIS OFFICE | HUM & SOC SC | 2501 | 2019-06-19 | COMPLETE | 2019-10-04 | FY 19-20 | 5 |  | EVAN ISMAIL | Paul Ditty
PB&A | 20P000008 | FS | SL5 EHS 1133 - PATCH / PAINT AND FIX HOLES IN WALLS | ENV HLTHSFTY | 1133 | 2019-07-08 | COMPLETE | 2019-10-07 | FY 19-20 | 1 |  | CESAR PLA | Paul Ditty
CHASS | 19P000664 | FS | SL5 WATKINS HALL, RM 1343/1343A- PAINT OFFICE AND LAB | WATKINS | 1343 & 1343A | 2019-06-12 | COMPLETE | 2019-10-08 | FY 19-20 | 1 |  | BECKY CAMPBELL | Paul Ditty
CHASS | 20P000140 | FS | SL5 HUMANITIES SOCSCI 4400 - PATCH AND PAINT IN FACULTY OFFICE | HUM & SOC SC | 4400 | 2019-09-25 | COMPLETE | 2019-10-09 | FY 19-20 | - |  | ALLISON ROGERS | Paul Ditty
CHASS | 20P000141 | FS | SL5 HUMANITIES SOCSCI 4401- PATCH AND PAINT IN FACULTY OFFICE | HUM & SOC SC | 4401 | 2019-09-26 | COMPLETE | 2019-10-10 | FY 19-20 | - |  | ALLISON ROGERS | Paul Ditty
PB&A | 20P000158 | FS | SL5 FS ADMIN OFFICE - TOUCH-UP PAINT AROUND BUILDING | CORP B |  | 2019-10-03 | COMPLETE | 2019-10-10 | FY 19-20 | - |  | DA LAN DINH | Paul Ditty
SOM | 19P000666 | FS | SL5 WEBBER, ROOM 1237- PATCH AND PAINT | WEBBER | 1237 | 2019-06-17 | COMPLETE | 2019-10-11 | FY 19-20 | 4 |  | DEBORAH TRUJILLO | Paul Ditty
PROVOST/EVC | 20P000162 | FS | SL5 HINDERAKER 1101B - PATCH HOLE IN WALL | HINDERAKER | 1101B | 2019-10-07 | CANCELED BY FS | 2019-10-14 | FY 19-20 | - |  | AMY GU | Paul Ditty
CHASS | 20P000142 | FS | SL5 HUMANITIES SOCSCI 5502 - PATCH AND PAINT FACULTY OFFICE | HUM & SOC SC | 5502 | 2019-09-26 | COMPLETE | 2019-10-14 | FY 19-20 | - |  | ALLISON ROGERS | Paul Ditty
PROVOST/EVC | 19P000473 | FS | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 | HINDERAKER | 1100 | 2019-01-29 | COMPLETE | 2019-10-28 | FY 19-20 | 1 |  | THERESA WAGNER | Paul Ditty
CNAS | 19P000555 | FS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK | SAT CHIL PL | 0 | 2019-04-03 | CANCELED BY CLIENT | 2019-10-30 | FY 19-20 | R4 |  | AMBER RHEMREV | Dan Lerman
VC-STU AFF | 18P000198 | FS | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | HUB | 0 | 2017-11-21 | CANCELED BY CLIENT | 2019-10-30 | FY 19-20 | R1 |  | BRENDAN OBRIEN | Dan Lerman
CNAS | 20P000185 | FS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR (OFF WHITE) | PHYSICS | 3004S | 2019-10-18 | CANCELED BY FS | 2019-11-01 | FY 19-20 | - |  | RONDA INZUNZA | Paul Ditty
CNAS | 20P000187 | FS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR | PHYSICS | 3004S | 2019-10-23 | COMPLETE | 2019-11-05 | FY 19-20 | - |  | RONDA INZUNZA | Paul Ditty
PB&A | 20P000169 | FS | SL5 LOTHIAN LO-G104-OFFICE - JOB WALK FOR REMODEL OF SCOTTY'S | LOTHIAN HALL | SCOTTY'S | 2019-10-09 | CANCELED BY CLIENT | 2019-11-06 | FY 19-20 | - |  | FRED OFFENEY | John Peraino
VC-STU AFF | 20P000206 | FS | SL5 COSTO HALL 111-HUB 353/381- RENOVATIONS - CP0003486 | COSTO HALL | Lower Level | 2019-11-01 | CANCELED BY CLIENT | 2019-11-06 | FY 19-20 | - |  | BRENDAN OBRIEN | Dan Lerman
CHASS | 20P000195 | FS | SL5 ARTS 0054 - PAINT PIANO LAB | ARTS | 54 | 2019-10-24 | COMPLETE | 2019-11-06 | FY 19-20 | - |  | PAUL RICHARDSON | Paul Ditty
BCOE | 19P000638 | FS | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM | BOURNS | B207 | 2019-05-16 | COMPLETE | 2019-11-11 | FY 19-20 | 1 |  | LOUIS SANDOVAL | Dan Lerman
CNAS | 19P000622 | FS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK | FAWCETT LAB | 204 | 2019-05-15 | COMPLETE | 2019-11-11 | FY 19-20 | 2 |  | MATTHEW ULRICH | Dan Lerman
VC-RED | 20P000045 | FS | SL5 MRB SOUND BOOTH | MRB | 2210 & 2204 | 2019-07-30 | COMPLETE | 2019-11-11 | FY 19-20 | 2 |  | DAN LERMAN | Dan Lerman
SoB | 20P000199 | FS | SL5 ANDERSON SO RM 0002 - KEYLESS ENTRY MINOR RENOVATION REQUEST | ANDERSON 2 (S) | 2 | 2019-10-25 | CANCELED BY CLIENT | 2019-11-14 | FY 19-20 | - |  | ANGELA CHANG | Dan Lerman
CHASS | 18P000343 | FS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER | HUM & SOC SC | 0400A | 2018-03-16 | COMPLETE | 2019-11-15 | FY 19-20 | 22 |  | PAUL RICHARDSON | Dan Lerman
CHASS | 19P000589 | FS | SL5 HMSS OFFICE 3405 RENOVATIONS | HUM & SOC SC | 3405 | 2019-04-23 | COMPLETE | 2019-11-19 | FY 19-20 | 8 |  | PAUL RICHARDSON | Dan Lerman
CNAS | 19P000523 | FS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | SPIETH | 3366 | 2019-03-12 | COMPLETE | 2019-11-20 | FY 19-20 | 5 |  | ESTELLA DAVALOS | Paul Ditty
CNAS | 20P000220 | FS | SL5 SPIETH-NEW CLOSING/SECURITY MECHANISM FOR LOADING DOCK DOORS | SPIETH |  | 2019-11-14 | CANCELED BY CLIENT | 2019-11-22 | FY 19-20 | - |  | ESTELLA DAVALOS | Dan Lerman
VC-STU AFF | 19P000483 | FS | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED | HEALTH SERV | 404, 407, 412, 405 & 411 | 2019-02-01 | COMPLETE | 2019-11-22 | FY 19-20 | 3 |  | GLORIA VERA | Paul Ditty
BCOE | 20P000163 | FS | SL5 BOURNS A0223 - PATCH/PAINT WALLS, DEEP CLEAN/REPLACE CARPET | BOURNS | A0223 | 2019-10-07 | COMPLETE | 2019-11-25 | FY 19-20 | - |  | SABRINA SCHUSTER | Paul Ditty
GSOE | 20P000077 | FS | SL5 SPROUL HALL 1223 - PATCH AND PAINT | SPROUL | 1223 | 2019-08-06 | COMPLETE | 2019-11-25 | FY 19-20 | 2 |  | KAREN NAPLES | Paul Ditty
ATHLETICS | 20P000093 | FS | SL5 ATHLETICS 0078 - TELEVISION MOUNT/ ELECTRICAL | ATH DANCE | 0078 | 2019-08-20 | CANCELED BY CLIENT | 2019-11-26 | FY 19-20 | R1 |  | JOSEPH ERBLAND | Dan Lerman
SOM | 20P000059 | FS | SL5 SOME 2626- PATCH & PAINT | SOM EDUC | 2626 | 2019-08-05 | CANCELED BY CLIENT | 2019-11-26 | FY 19-20 | 1 |  | DEBORAH TRUJILLO | Paul Ditty
CNAS | 19P000543 | FS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION | CHEMICAL SCI | 342 | 2019-03-21 | CANCELED BY FS | 2019-11-26 | FY 19-20 | R8 |  | JEFFERY MATUTE | Dan Lerman
SOM | 19P000662 | FS | SL5 FY19-20 PROJECT: DEANS CONF ROOM | SOM EDUC | 2652 | 2019-06-12 | CANCELED BY FS | 2019-11-26 | FY 19-20 | 3 |  | DEBORAH TRUJILLO | Dan Lerman
BCOE | 20P000028 | FS | SL5 BOURNS HALL 2ND FL A0219- PAINT FACULTY OFFICES | BOURNS | A0219 | 2019-07-19 | COMPLETE | 2019-11-26 | FY 19-20 | 2 |  | DEANNA VORHEES | Paul Ditty
CHASS | 20P000082 | FS | SL5 HUMANITIES THEATRE - PATCH & PAINT | THTR WKSH | 405 | 2019-08-15 | COMPLETE | 2019-11-26 | FY 19-20 | 7 |  | JULIE SALGADO | Paul Ditty
CNAS | 19P000377 | FS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | BOT GDN HSE |  | 2018-11-08 | COMPLETE | 2019-11-26 | FY 19-20 | R2 |  | AMBER RHEMREV | Dan Lerman
GRAD DIV | 19P000572 | FS | SL5 PATCH, PAINT, AND CARPET UOB 152 | UNIV OFC BLD | 152 | 2019-04-11 | COMPLETE | 2019-11-26 | FY 19-20 | 1 |  | CYNTHIA CARDENAS | Paul Ditty
VC-STU AFF | 19P000534 | FS | SL5 PATCH WALLS AND PAINT | HEALTH SERV | 334 | 2019-03-15 | CANCELED BY FS | 2019-12-06 | FY 19-20 | 2 |  | PAMELA BOCKSTADTER | Paul Ditty
BCOE | 20P000161 | FS | SL5 WCH 112 - MODIFY ROOM FOR NEW OCCUPANT | CHUNG HALL | 112 | 2019-10-04 | COMPLETE | 2019-12-11 | FY 19-20 | - |  | MARGARET SOUDER | Paul Ditty
BCOE | 20P000175 | FS | SL5 CHUNG HALL 1ST FLOOR ROOM 112 - PATCH & PAINT | CHUNG HALL | 112 | 2019-10-11 | COMPLETE | 2019-12-11 | FY 19-20 | - |  | ROBERT LOPEZ-A | Paul Ditty
VC-RED | 20P000150 | FS | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 207 | UNIV OFC BLD | 207 | 2019-09-25 | COMPLETE | 2019-12-11 | FY 19-20 | - |  | GLORIA GALLEGO | Paul Ditty
BCOE | 20P000029 | FS | SL5 BOURNS HALL 2ND FL A0211- PAINT FACULTY OFFICES | BOURNS | A0211 | 2019-07-19 | COMPLETE | 2019-12-12 | FY 19-20 | 3 |  | DEANNA VORHEES | Paul Ditty
VC-STU AFF | 20P000073 | FS | SL5 HUB - THE WELL -3RD FL RM 346 DOOR INSTALLATION CP00003544 | HUB | 346 | 2019-08-12 | CANCELED BY CLIENT | 2019-12-13 | FY 19-20 | PENDING |  | JONATHAN GODOY | Dan Lerman
CNAS | 20P000242 | FS | SL5 SKYE 366 - PATCH AND PAINT | SKYE HALL | 366 | 2019-11-25 | CANCELED BY FS | 2019-12-13 | FY 19-20 | 10 | YES | MELISSA GOMEZ | Paul Ditty
CNAS | 20P000238 | FS | SL5 SKYE 366 - PATCH AND PAINT | SKYE HALL | 366 | 2019-11-25 | CANCELED BY FS | 2019-12-13 | FY 19-20 | 14 | YES | MELISSA GOMEZ | Paul Ditty
CHASS | 20P000232 | FS | SL5 PSYCHOLOGY 3111B - WALL PATCH FOR SMALL HOLES IN THE WALL | PSYCHOLOGY1 | 3111B | 2019-11-20 | COMPLETE | 2019-12-13 | FY 19-20 | 9 |  | EMILY LAM | Paul Ditty
CNAS | 20P000113 | FS | SL5 GEOLOGY 2258 - PATCHPAINT RECEPTION WALL OVER BIN REMOVED | GEOLOGY | 2258 | 2019-09-04 | COMPLETE | 2019-12-13 | FY 19-20 | 7 |  | RONDA INZUNZA | Paul Ditty
CHASS | 19P000419 | FS | SL5 CHASS INT SOUTH 2117-CARD ACCESS | CHASS INT S | 2117 | 2018-12-18 | COMPLETE | 2019-12-16 | FY 19-20 | 2 |  | PAUL RICHARDSON | Dan Lerman
CNAS | 19P000639 | FS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK | CHEMICAL SCI | 0435 | 2019-05-17 | COMPLETE | 2019-12-16 | FY 19-20 | 1 |  | BARBARA OUTZEN | Dan Lerman
CNAS | 20P000235 | FS | SL5 SKYE 374 - PATCH AND PAINT | SKYE HALL | 374 | 2019-11-25 | COMPLETE | 2019-12-17 | FY 19-20 | 4 | YES | MELISSA GOMEZ | Paul Ditty
CNAS | 20P000236 | FS | SL5 SKYE 368 - PATCH AND PAINT | SKYE HALL | 368 | 2019-11-25 | COMPLETE | 2019-12-17 | FY 19-20 | 5 | YES | MELISSA GOMEZ | Paul Ditty
CNAS | 20P000023 | FS | SL5 PIERCE RM 1144 - PATCH AND PAINT DOOR WHERE WALL POCKET WAS | PIERCE | 1144 | 2019-07-18 | COMPLETE | 2019-12-18 | FY 19-20 | 6 |  | JACQUELINE | Paul Ditty
CNAS | 20P000121 | FS | SL5 SKYE 217 - PATCH AND PAINT | SKYE HALL | 217 | 2019-09-05 | COMPLETE | 2019-12-18 | FY 19-20 | 6 |  | JAMES MARBERRY | Paul Ditty
CHASS | 20P000204 | FS | SL5 ARTS 166 - PATCH AND PAINT IN LOBBY AND GREEN ROOM | ARTS | 166 | 2019-10-31 | COMPLETE | 2019-12-20 | FY 19-20 | 7 |  | ALBERT FETTER | Paul Ditty
VC-STU AFF | 19P000455 | FS | SL5 FILL AND PAINT OVER HOLES ON WALL | HEALTH SERV | 100 | 2019-01-17 | COMPLETE | 2019-12-27 | FY 19-20 | 1 |  | PAMELA BOCKSTADTER | Paul Ditty
PB&A | 20P000127 | FS | SL5 FALKIRK APARTMENTS EMERGENCY EGRESS | FALKIRK 1 | 10E | 2019-09-13 | COMPLETE | 2020-01-01 | FY 19-20 | R1 |  | SEAN HATFIELD | John Peraino
PB&A | 20P000205 | FS | SL5 THE PLAZA 12 & 14 - EMERGENCY DECK REPAIR | THE PLAZA | A0012 | 2019-11-01 | COMPLETE | 2020-01-01 | FY 19-20 | R2 |  | SEAN HATFIELD | John Peraino
SoB | 20P000193 | FS | SL5 ANDERSON HALL SO - PATCH/PAINT | ANDERSON 2 (S) | 0001A | 2019-10-23 | COMPLETE | 2020-01-02 | FY 19-20 | 3 |  | ANGELA CHANG | Paul Ditty
CHASS | 20P000171 | FS | SL5 CHASS INTN 2107 - PATCH UP HOLES IN THE WALL | CHASS INT N | 2017 | 2019-10-10 | COMPLETE | 2020-01-03 | FY 19-20 | 6 |  | GENEVA AMADOR | Paul Ditty
BCOE | 20P000233 | FS | SL5 BOURNS A-WING 1ST FLOOR - A169 & A170 ENTRY AREA DAMAGED | BOURNS | A169 & A170 | 2019-11-22 | CANCELED BY FS | 2020-01-07 | FY 19-20 | 2 |  | ROBERT LOPEZ-A | Paul Ditty
SoB | 20P000192 | FS | SL5 ANDERSON HALL SO - PATCH/PAINT | ANDERSON 2 (S) | 1st Floor | 2019-10-23 | CANCELED BY FS | 2020-01-07 | FY 19-20 | 2 |  | ANGELA CHANG | Paul Ditty
CNAS | 20P000239 | FS | SL5 SKYE 382 - PATCH AND PAINT | SKYE HALL | 382 | 2019-11-25 | COMPLETE | 2020-01-07 | FY 19-20 | 11 |  | MELISSA GOMEZ | Paul Ditty
CNAS | 20P000240 | FS | SL5 SKYE 384 - PATCH AND PAINT | SKYE HALL | 384 | 2019-11-25 | COMPLETE | 2020-01-07 | FY 19-20 | 12 |  | MELISSA GOMEZ | Paul Ditty
CNAS | 20P000241 | FS | SL5 SKYE 386 - PATCH AND PAINT | SKYE HALL | 386 | 2019-11-25 | COMPLETE | 2020-01-07 | FY 19-20 | 13 |  | MELISSA GOMEZ | Paul Ditty
CHASS | 20P000145 | FS | SL5 PSYCHOLOGY 1111 - PATCH AND PAINT FRONT OFFICE WALL | PSYCHOLOGY1 | 1111 | 2019-09-25 | COMPLETE | 2020-01-08 | FY 19-20 | 2 |  | TOYA ADAMS | Paul Ditty
CNAS | 20P000036 | FS | SL5 ENTOMOLOGY 224 - PAINT OFFICE FOR NEW PI HANSEN | ENTOMOLOGY | 224 | 2019-07-23 | COMPLETE | 2020-01-08 | FY 19-20 | 1 | YES | WILLIAM SUTTON | Paul Ditty
CHASS | 20P000194 | FS | SL5 WATKINS 1224 - PAINT NEW FACULTY OFFICE ONLY | WATKINS | 1224 | 2019-10-17 | COMPLETE | 2020-01-09 | FY 19-20 | 1 | YES | BECKY CAMPBELL | Paul Ditty
CHASS | 20P000120 | FS | SL5 OLMSTED 2139 SUITE - PATCH AND PAINT | OLMSTED | 2139 | 2019-09-05 | COMPLETE | 2020-01-14 | FY 19-20 | 3 | YES | TOYA ADAMS | Paul Ditty
CNAS | 20P000081 | FS | SL5 CHEM SCI 0441- INSTALL FUME HOODS | CHEMICAL SCI | 441 | 2019-08-15 | COMPLETE | 2020-01-14 | FY 19-20 | 2 |  | TIMOTHY SU | Dan Lerman
CNAS | 19P000688 | FS | SL5 PHYSICS- RENOVATION OF THREE PHYSICS ROOMS | PHYSICS | 2128 | 2019-06-28 | COMPLETE | 2020-01-14 | FY 19-20 | 4 |  | DAVID NEFF | Dan Lerman
FAC-PLNG-DESIGN-CONST | 19P000467 | FS | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | WATKINS | 2101 | 2019-01-22 | COMPLETE | 2020-01-14 | FY 19-20 | 1 |  | Monty Anderson | Dan Lerman
PB&A | 20P000083 | FS | SL5 STUDENT SERVICES - INSTALL 8 CUBICLES - CP00003537 | STUDENT SERV | 3rd Floor | 2019-06-25 | COMPLETE | 2020-01-14 | FY 19-20 | 1 |  | SHARYL MURDOCK | Dan Lerman
CHASS | 20P000112 | FS | SL5 PSYCHOLOGY 2123 - PATCH AND PAINT JOB | PSYCHOLOGY1 | 2123 | 2019-09-04 | COMPLETE | 2020-01-15 | FY 19-20 | 4 |  | EMILY LAM | Paul Ditty
CHASS | 20P000172 | FS | SL5 PYSCHOLOGY 2136B & 2136C - PAINT & PATCH | PSYCHOLOGY1 | 2136B & 2136C | 2019-10-10 | COMPLETE | 2020-01-15 | FY 19-20 | 5 |  | ANNIKA KIRMAN | Paul Ditty
VC-UNIV ADV | 20P000225 | FS | SL5 HINDERAKER 0137 - BASEMENT RESTROOM SINK INSTALL | HINDERAKER | B137 | 2019-11-15 | CANCELED BY CLIENT | 2020-01-22 | FY 19-20 | 1 |  | NAYSIA CALDWELL | Dan Lerman
BCOE | 20P000129 | FS | SL5 BOURNS HALL B0360C - PATCH & PAINT | BOURNS | B0360C | 2019-09-12 | COMPLETE | 2020-01-22 | FY 19-20 | 1 | YES | DEANNA VORHEES | Paul Ditty
ATHLETICS | 19P000277 | FS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | ATH DANCE |  | 2018-09-12 | CANCELED BY CLIENT | 2020-01-24 | FY 19-20 | 10 |  | JOHNATHAN JENSEN | Dan Lerman
CNAS | 20P000189 | FS | SL5 SPIETH 3352 - ESTIMATE FOR PATCH AND PAINT | SPIETH | 3352 | 2019-10-23 | COMPLETE | 2020-01-28 | FY 19-20 | 2 |  | NATALIE HOLT | Paul Ditty
CNAS | 20P000017 | FS | SL5 COLLEGE BLDG CR200 - PAINT PROJECT | COLL BLDG NO | CR0200 | 2019-07-15 | CANCELED BY CLIENT | 2020-01-30 | FY 19-20 | R4 |  | RONDA INZUNZA | Dan Lerman
CHASS | 20P000002 | FS | SL5 HMNSS, RM 1212- REMOVAL OF ROLL UP WINDOW | HUM & SOC SC | 1212 | 2019-07-01 | COMPLETE | 2020-01-30 | FY 19-20 | 2 |  | ALLISON ROGERS | Dan Lerman
CNAS | 19P000508 | FS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | BOYCE | 3410 | 2019-02-21 | COMPLETE | 2020-01-30 | FY 19-20 | 4 |  | Sabrina Schuster | Dan Lerman
CNAS | 20P000155 | FS | SL5 BOYCE 3407 - PAINT OFFICE FOR NEW FACULTY | BOYCE | 3407 | 2019-10-01 | COMPLETE | 2020-01-30 | FY 19-20 | 8 | YES | MATTHEW ULRICH | Paul Ditty
VC-STU AFF | 20P000157 | FS | SL5 HEALTH SERVICE BUILDING - HOLES NEED PATCH AND PAINT | HEALTH SERV | 325 | 2019-10-02 | COMPLETE | 2020-01-31 | FY 19-20 | 1 |  | CHRISTINA FARIA | Paul Ditty
CHASS | 20P000226 | FS | SL5 HUMANITIES SOCSCI 3401 - OFFICE PATCH AND PAINT | HUM & SOC SC | 3401 | 2019-11-18 | COMPLETE | 2020-02-03 | FY 19-20 | 8 | YES | JENNIFER HAMILTON | Paul Ditty
CNAS | 20P000207 | FS | SL5 PHYSICS 3033 - PAINT & PATCH STAFF OFFICE | PHYSICS | 3033 | 2019-11-04 | COMPLETE | 2020-02-04 | FY 19-20 | 3 |  | MAYELA CASTILLO | Paul Ditty
ATHLETICS | 19P000309 | FS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | ATH DANCE |  | 2018-09-12 | COMPLETE | 2020-02-05 | FY 19-20 | 7 |  | JOHNATHAN JENSEN | Dan Lerman
CNAS | 20P000200 | FS | SL5 COLLEGE BLDG NO 306 - PATCH AND PAINT ONE WALL ONLY | COLL BLDG NO | 306 | 2019-10-29 | COMPLETE | 2020-02-06 | FY 19-20 | 15 |  | RONDA INZUNZA | Paul Ditty
CNAS | 20P000105 | FS | SL5 PHYSICS 2029 - PATCH AND PAINT | PHYSICS | 2029A | 2019-08-28 | COMPLETE | 2020-02-06 | FY 19-20 | 17 |  | DAVID NEFF | Paul Ditty
ATHLETICS | 19P000311 | FS | SL5 ATHLETICS 150-KEYLESS ENTRY | ATH DANCE | 0150 | 2018-10-02 | CANCELED BY CLIENT | 2020-02-07 | FY 19-20 | R2 |  | JOHNATHAN JENSEN | Dan Lerman
VC-STU AFF | 20P000184 | FS | SL5 HUB 261 - CONSTRUCT WALL FOR MEETING/CONFERENCE RM | HUB | 261 | 2019-10-17 | CANCELED BY CLIENT | 2020-02-07 | FY 19-20 | R1 |  | Manny Sanchez | Dan Lerman
SoB | 20P000151 | FS | SL5 ANDERSON HALL NO 113 - PATCH/PAINT HOLES | ANDERSON 1 (N) | 113 | 2019-09-30 | COMPLETE | 2020-02-07 | FY 19-20 | 1 |  | ANGELA CHANG | Paul Ditty
VC-STU AFF | 20P000337 | FS | SL5 HEATLH SERVICE 382 - NEED OFFICE PAINTED | HEALTH SERV | 382 | 2020-01-23 | COMPLETE | 2020-02-11 | FY 19-20 | 1 |  | GLORIA VERA | PAUL DITTY
CHASS | 20P000237 | FS | SL5 HMNSS 1202A - PATCH AND PAINT SERVICE | HUM & SOC SC | 1202A | 2019-11-22 | COMPLETE | 2020-02-14 | FY 19-20 | 1 |  | CHRISTIAN BACK | PAUL DITTY
CHASS | 19P000540 | FS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | HUM & SOC SC | 1202 | 2019-03-20 | COMPLETE | 2020-02-18 | FY 19-20 | 9 |  | MICHAEL MOLINAR | Dan Lerman
CHASS | 20P000044 | FS | SL5 WATKINS 1312 - NEW HIRE RENOVATION - ELIZABETH BERGER | WATKINS | 1312 | 2019-07-30 | COMPLETE | 2020-02-19 | FY 19-20 | 1 |  | PAUL RICHARDSON | Dan Lerman
PB&A | 19P000665 | FS | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | TELEPHONE |  | 2019-07-03 | COMPLETE | 2020-02-19 | FY 19-20 | 2 |  | Carmen Long | Dan Lerman
BCOE | 20P000070 | FS | SL5 BOURNS B342D - PREPARE LAB FOR NEW FACULTY | BOURNS | B0342D | 2019-08-09 | COMPLETE | 2020-02-28 | FY 19-20 | 1 |  | SABRINA SCHUSTER | Dan Lerman
BCOE | 19P000601 | FS | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY | BOURNS | B0328E | 2019-05-09 | COMPLETE | 2020-02-28 | FY 19-20 | 3 |  | KATHALENA COCKER | Dan Lerman
CHASS | 19P000421 | FS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | OLMSTED | 2139I | 2018-12-19 | COMPLETE | 2020-02-28 | FY 19-20 | 5 | YES | TOYA ADAMS | Dan Lerman
CNAS | 20P000266 | FS | SL5 GEOLOGY 2460B - PATCH & PAINT | GEOLOGY | 2460B | 2019-12-19 | COMPLETE | 2020-03-03 | FY 19-20 | 3 |  | DEBORAH TERAO | PAUL DITTY
CNAS | 20P000268 | FS | SL5 GEOLOGY 2460D - PATCH & PAINT | GEOLOGY | 2460D | 2019-12-19 | COMPLETE | 2020-03-03 | FY 19-20 | 5 |  | DEBORAH TERAO | PAUL DITTY
CNAS | 20P000270 | FS | SL5 GEOLOGY 2460F - PATCH & PAINT | GEOLOGY | 2460F | 2019-12-19 | COMPLETE | 2020-03-03 | FY 19-20 | 7 |  | DEBORAH TERAO | PAUL DITTY
CNAS | 20P000267 | FS | SL5 GEOLOGY 2460C - PATCH & PAINT | GEOLOGY | 2460C | 2019-12-19 | COMPLETE | 2020-03-04 | FY 19-20 | 4 |  | DEBORAH TERAO | PAUL DITTY
SOM | 19P000658 | FS | SL5 SOM RB- PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 230 | 2019-06-11 | CANCELED BY CLIENT | 2020-03-05 | FY 19-20 | 4 |  | BRANDON BARBOSA | Dan Lerman
CNAS | 20P000269 | FS | SL5 GEOLOGY 2460E - PATCH & PAINT | GEOLOGY | 2460E | 2019-12-19 | COMPLETE | 2020-03-05 | FY 19-20 | 6 |  | DEBORAH TERAO | PAUL DITTY
CNAS | 20P000271 | FS | SL5 GEOLOGY 2460G - PATCH & PAINT | GEOLOGY | 2460G | 2019-12-19 | COMPLETE | 2020-03-06 | FY 19-20 | 8 |  | DEBORAH TERAO | PAUL DITTY
BCOE | 20P000245 | FS | SL5 WCH RM 0325 - PATCH AND PAINT DAMAGE FROM WHITE BOARD | CHUNG HALL | 325 | 2019-11-25 | COMPLETE | 2020-03-13 | FY 19-20 | 1 |  | SARA GALLOWAY | PAUL DITTY
CNAS | 20P000355 | FS | SL5 GEOL 454A- PATCH & PAINT | GEOLOGY | 0454A | 2020-02-09 | COMPLETE | 2020-03-13 | FY 19-20 | 2 |  | DEBORAH TERAO | PAUL DITTY
BCOE | 19P000602 | FS | SL5 BOURNS B328F- PREPARE LAB FOR NEW PI OCCUPANCY | BOURNS | B0328F | 2019-05-09 | COMPLETE | 2020-03-25 | FY 19-20 | 2 |  | KATHALENA COCKER | Dan Lerman
CNAS | 20P000024 | FS | SL5 PHYSICS 1003- RENOVATION | PHYSICS | 1003 | 2019-07-18 | COMPLETE | 2020-03-25 | FY 19-20 | 3 |  | DAVID NEFF | Dan Lerman
CNAS | 20P000019 | FS | SL5 PHYSICS 2029A- NEW EYEWASH STATION | PHYSICS | 2029A | 2019-07-16 | COMPLETE | 2020-03-25 | FY 19-20 | 5 |  | DAVID NEFF | Dan Lerman
CNAS | 20P000061 | FS | SL5 PHYSICS 1028 - MOVE UTILITIES FOR GLASS SHOP | PHYSICS | 1028 | 2019-08-06 | COMPLETE | 2020-04-23 | FY 19-20 | 1 |  | CHRISTOPHER BARDEEN | Dan Lerman
CNAS | 20P000335 | FS | SL5 ENTOMOLOGY BLDG 239-246 - PAINT AND PATCH OFFICE AND LAB | ENTOMOLOGY | 239 | 2020-01-22 | CANCELED BY CLIENT | 2020-05-22 | FY 19-20 | 1 |  | WILLIAM SUTTON | PAUL DITTY
BCOE | 19P000621 | FS | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY | BOURNS | A0308 | 2019-05-14 | CANCELED BY FS | 2020-05-22 | FY 19-20 | 10 | YES | LOUIS SANDOVAL | Paul Ditty
BCOE | 19P000620 | FS | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY | BOURNS | A0304 | 2019-05-14 | CANCELED BY FS | 2020-05-22 | FY 19-20 | 9 | YES | LOUIS SANDOVAL | Paul Ditty
PB&A | 20P000243 | FS | SL5 ALUMNI CENTER - HYDRATION STATION INSTALL | ALUM VISITOR | FIRST FLOOR | 2019-11-16 | COMPLETE | 2020-06-01 | FY 19-20 | R4 |  | LESLIE ANN GERRETSE | John Peraino
SOM | 19P000659 | FS | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 230 | 2019-06-11 | CANCELED BY CLIENT | 2020-08-05 | FY 20-21 | 5 |  | CYNTHIA CAROLINA | Dan Lerman
BCOE | 19P000600 | FS | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | BOURNS | B0316 | 2019-05-09 | COMPLETE | 2020-08-05 | FY 20-21 | 2 |  | KATHALENA COCKER | Dan Lerman
CHANCELLOR | 19P000407 | FS | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | HINDERAKER | 1101 | 2018-12-11 | COMPLETE | 2020-08-05 | FY 20-21 | 1 |  | ALEXIS RAMBAUD | Dan Lerman
CHASS | 20P000213 | FS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS | CHASS INT S | 2117A, 2117C, 2117D, 2117E | 2019-11-08 | COMPLETE | 2020-08-05 | FY 20-21 | R1 |  | PAUL RICHARDSON | Dan Lerman
CNAS | 19P000193 | FS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | GENOMICS | 4231 | 2018-08-20 | COMPLETE | 2020-08-05 | FY 20-21 | 41 |  | AIMEE GONZALES | Dan Lerman
CNAS | 19P000547 | FS | SL5 SPIETH HALL 1363-RENOVATION | SPIETH | 1363 | 2019-03-26 | COMPLETE | 2020-08-05 | FY 20-21 | R3 | YES | ESTELLA DAVALOS | Dan Lerman
FAC-PLNG-DESIGN-CONST | 19P000466 | FS | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | SPROUL | 2225 | 2019-01-22 | COMPLETE | 2020-08-05 | FY 20-21 | 1 |  | Monty Anderson | Dan Lerman
ITS | 19P000433 | FS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | C&C CARPORT | 161 | 2019-01-07 | COMPLETE | 2020-08-05 | FY 20-21 | R1 |  | SHELLEY GUPTA | Dan Lerman
PB&A | 19P000414 | FS | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | POLICE BLDG | 100 | 2018-12-17 | COMPLETE | 2020-08-05 | FY 20-21 | 1 |  | Seth Morrison | Dan Lerman
PB&A | 19P000687 | FS | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | HUB | Various | 2019-06-26 | COMPLETE | 2020-08-05 | FY 20-21 | R1 |  | MANNY SANCHEZ | Dan Lerman
BCOE | 20P000135 | FS | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MAT SCI ENGR | 75 | 2019-09-19 | COMPLETE | 2020-09-30 | FY 20-21 | 1 |  | MARK HEIDEN | Dan Lerman
CHASS | 20P000214 | FS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | PSYCHOLOGY1 | 2nd Floor | 2019-11-07 | COMPLETE | 2020-09-30 | FY 20-21 | 2 |  | JAY MELASHENKO | Dan Lerman
CNAS | 20P000202 | FS | SL5 SKYE HALL 361 RENOVATION PROJECT | SKYE HALL | 361 | 2019-10-30 | COMPLETE | 2020-09-30 | FY 20-21 | 1 |  | JAMES MARBERRY | Dan Lerman
SOM | 19P000660 | FS | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | 2019-06-11 | COMPLETE | 2020-09-30 | FY 20-21 | 1 |  | BRANDON BARBOSA | Dan Lerman
SOM | 20P000054 | FS | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | 2019-07-31 | COMPLETE | 2020-09-30 | FY 20-21 | 2 |  | CYNTHIA CAROLINA | Dan Lerman
BCOE | 20P000449 | FS | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | CHUNG HALL | 461 | 2020-06-11 | COMPLETE | 2020-11-09 | FY 20-21 | X | YES | ROBERT LOPEZ-A | PAUL DITTY
BCOE | 20P000210 | FS | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | CHUNG HALL | 224 | 2019-11-05 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 2 |  | MARGARET SOUDER | Dan Lerman
BCOE | 19P000624 | FS | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | BOURNS | A0346 | 2019-05-15 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 3 |  | LOUIS SANDOVAL | Dan Lerman
BCOE | 20P000039 | FS | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE | BOURNS | A0318 | 2019-05-13 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 4 |  | LOUIS SANDOVAL | Dan Lerman
BCOE | 19P000427 | FS | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | CHUNG HALL | 453 | 2019-01-03 | CANCELED BY FS | 2020-11-19 | FY 20-21 | R2 |  | ROBERT LOPEZ-A | Dan Lerman
BCOE | 19P000502 | FS | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | CHUNG HALL | 444 | 2019-02-19 | CANCELED BY FS | 2020-11-19 | FY 20-21 | R3 |  | RICHARD BAIN | Dan Lerman
CHASS | 20P000183 | FS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | HUM & SOC SC | 1202 | 2019-10-18 | CANCELED BY FS | 2020-11-19 | FY 20-21 | R2 |  | PAUL RICHARDSON | Dan Lerman
CNAS | 19P000514 | FS | SL5 SKYE 268-PROJECTOR INSTALL | SKYE HALL | 0268 | 2019-02-27 | CANCELED BY FS | 2020-11-19 | FY 20-21 | R7 |  | JAMES MARBERRY | Dan Lerman
LIBR | 20P000188 | FS | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 | ORBACH LIB | 204 | 2019-10-23 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 1 |  | DAVID SCHUSTER | Dan Lerman
VC-RED | 20P000197 | FS | SL5 UOB 210 - SOUND PROOF INSTALLATION | UNIV OFC BLD | 210 | 2019-10-24 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 2 |  | CRYSTAL JIMENEZ | Dan Lerman
VC-RED | 20P000047 | FS | SL5 ADVANCED NEUROIMAGING | ADV NEURO |  | 2019-07-31 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 3 |  | CHELSEA EVELYN | Dan Lerman
VC-RED | 19P000225 | FS | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | UV BLDG A | 0204A | 2018-08-28 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 3 |  | CRYSTAL JIMENEZ | Dan Lerman
VC-RED | 20P000230 | FS | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | BOURNS | B116C & B116D | 2019-11-18 | COMPLETE | 2020-11-19 | FY 20-21 | 1 |  | KRASSIMIR BOZHILOV | Dan Lerman
BCOE | 20P000067 | FS | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS | B-Wing | 2016-11-14 | TO BE PERFORMED BY PD&C | 2020-11-19 | FY 20-21 | R1 |  | MARGARET SOUDER | Dan Lerman
CNAS | 19P000504 | FS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH | 2349 | 2019-02-20 | TO BE PERFORMED BY PD&C | 2020-11-19 | FY 20-21 | 5 |  | ESTELLA DAVALOS | Dan Lerman
BCOE | 21P000037 | FS | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | CHUNG HALL | 427 | 2020-07-31 | COMPLETE | 2020-11-30 | FY 20-21 | X | YES | ROBERT LOPEZ-A | PAUL DITTY
CNAS | 18P000453 | FS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | DELFINO HHSE |  | 2018-05-25 | TO BE PERFORMED BY PD&C | 2020-12-07 | FY 20-21 | 17 |  | MATTHEW ULRICH | Dan Lerman
VC-RED | 21P000102 | FS | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | SPIETH | 348, 352 & 363 | 2020-10-29 | COMPLETE | 2020-12-08 | FY 20-21 | TBD |  | DIERK BIGGS | Paul Ditty
VC-UNIV ADV | 20P000309 | FS | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES | 1955 CHICAGO | 200 | 2020-01-10 | CANCELED BY FS | 2020-12-16 | FY 20-21 | 1 |  | SARAH KARSON | PAUL DITTY
CHASS | 20P000211 | FS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | ARTS | 54 | 2019-11-07 | CANCELED BY CLIENT | 2021-01-19 | FY 20-21 | R1 |  | PAUL RICHARDSON | Dan Lerman
BCOE | 20P000221 | FS | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | 2019-11-15 | COMPLETE | 2021-01-19 | FY 20-21 | 3 |  | HONG XU | Dan Lerman
CHASS | 20P000215 | FS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | PSYCHOLOGY1 | 3rd Floor | 2019-11-07 | COMPLETE | 2021-01-19 | FY 20-21 | 3 |  | JAY MELASHENKO | Dan Lerman
CNAS | 20P000247 | FS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | SPIETH | 2110 + 2118 | 2019-11-27 | COMPLETE | 2021-01-19 | FY 20-21 | 6 | YES | ESTELLA DAVALOS | Dan Lerman
CNAS | 19P000474 | FS | SL5 HEADHOUSE 8-AC INSTALLATION | GH08 | 881 | 2019-01-29 | COMPLETE | 2021-01-19 | FY 20-21 | 7 |  | NANCY FERGUSON | Dan Lerman
ENROLLMENT SERVICES | 19P000517 | FS | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | 2019-03-07 | COMPLETE | 2021-01-19 | FY 20-21 | 1 |  | DANIELLE GARCIA | Dan Lerman
VC-RED | 20P000026 | FS | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | LIFE SCIENCE | Basement Level | 2019-07-19 | COMPLETE | 2021-01-19 | FY 20-21 | 1 |  | DIERK BIGGS | Dan Lerman
VC-STU AFF | 18P000214 | FS | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | HEALTH SERV |  | 2017-12-08 | COMPLETE | 2021-01-19 | FY 20-21 | 2 |  | GLORIA VERA | Dan Lerman
ATHLETICS | 20P000208 | FS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | ATH DANCE | 50 | 2019-11-04 | COMPLETE | 2021-01-28 | FY 20-21 | 1 |  | JOSEPH ERBLAND | Dan Lerman

## q_Report_Integrated (hidden)
Proj_Ref_No | CPMS_No | Work_Order_No | IRT | Org | Project_Title | Project_Description | Building | Room | Current_Status | Org_Leadership | Org_Contact (Prioritization Designate) | Contact | Contact_2 | Proj_Mgr | Org_Priority | FS_Priority | FS_Priority_Last | For_Faculty_Hire | Approved_Budget | FS_Recharge_Costs | Project_Initiated | Next_Major_Milestone | Const_Start | Construction_Completion | Impact_Description | Impact_Date_Start | Impact_Date_End | PM_Notes | Scope_Date | Scope_Reviewer | Scope_Notes | Scope_Complete | Completed Date | Quarter Submitted | Owner | IRT? | Requested Year | Data Pulled On | FY | Recharge?
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | Bidding | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 6950000 |  | 43528 | Award Contract | 44348 | 45047 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Bidding Competition | Gerry Bomotti | TBD | Michelle Baniqued |  | Fernando Canon | 1 |  |  | FALSE | 33980000 |  | 43528 | Select Design Builder | 44470 | 45017 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Rivera Library Arches/Arcade Repair | Paint and replace roof. | RIVERA LIB |  | Bids received, award on hold due to DM funding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Scott Donnell | 99 |  |  | FALSE | 240000 |  | 42496 | Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-01-01
3438 | 3438 |  | FALSE | CAP PROG | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | City to determine schedule | Jacqueline Norman | Sharyl Murdock | Dave Bomba |  | Scott Donnell | 17 |  |  | FALSE | 88500 |  | 43334 | City to determine schedule | 44013 | 44166 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-01
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Commencing Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Rowan Reid | 1 |  |  | FALSE | 1150000 |  | 42719 | Completion of Basis of Design | [12 empty] | PD&C | FALSE | 2016 | 2021-01-01
18P000126 |  | 18P000126 | FALSE | CHASS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS |  | HUM & SOC SC | 3611 | COMPLETE | Juliet McMullin | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 43006 | [6 empty] | 7/1/19,DL; This project is 100% Complete…..5/15/19, DL; Work is scheduled to start on 6/19/19…….5/1/19, DL; Plans are approved. Need to order material and schedule the work…..3/18/19, DL; Plans submitted to PD&C today…..02/2819, DL; Gunther will work on plans over the next three weeks to submit for a building permit. We will schedule the work if and after the plans are approved. If approved the door and window will more than likely have a 3- month lead time…………….12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez |  | YES | 2019-07-01 | Winter 2018 | FS | FALSE | 2017 | 2021-01-01 | FY 19-20
19P000209 |  | 19P000209 | FALSE | PB&A | SL5 OLD EH&S SITE- FS ANNEX A REMODEL |  | ENV HLTHSFTY | 100 | COMPLETE | Gerry Bomotti | TBD | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 43336 | [6 empty] | 7/1/19, DL; This project is 100% Complte….6/17/19, DL; This project is almost complete. Target complete date is 6/26………….5/31/19, DL; This project is in progress. Our goal is to have the projected completed by June 28th……. 5/15/19, DL; We are schedule to start the demo tomorrow. Project timeline is 3-4 weeks….3/28/19, DL; Gunther is working on plans……3/18/19, DL; Conducted site visit with Chris, Hassan and Francis last week. We will work on plans and permits…….9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000210 |  | 19P000210 | FALSE | CNAS | SL5 CHEMICAL SCI Install Door In Doorway |  | CHEMICAL SCI | 0225A | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  | 25 |  | FALSE |  |  | 43336 | [6 empty] | 7/1/19, DL; This project is 100% complete…..6/17/19, DL; Po is cut. Target complete date is before 7/1/19……Permit was approved this week. We are now working on the contract with the vendor. Our goal is start the work with in the next 30- days. 5/15/19, DL; Plans were approved. I am in the process of working with PD&C for the contract. We will order material and schedule the wrok once we have a signed contract……..3/28/19, DL; Plans were submitted last week… 3/18/19, DL; Conducted site visit last week. We are working on plans now we will try and submit plans for permit review next week…… | 2018-09-19 | Ron Veloz |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000245 |  | 19P000245 | FALSE | SOM | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY |  | SOM RSCH |  | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43350 | [6 empty] | 7/1/19, DL; This project is 100% Complete…..6/171/19, DL; Material is on site. Project should be complete in the next two weeks……..5/31/19, DL; Contracts is working on the contract. We should have a notice to proceed in the next two weeks. The project will be complete with in 30- from when we receive the notice to proceed……5/15/19, DL;, Plans were approved. I am working with PD&C on the contract. Once the contract is complete, we will schedule the work……3/28/19, DL; Plans were submitted and pending review and approval….. | 2018-10-29 | Ron Veloz | Install ADA complian auto door operator, push plates and electrified panic hardware. Auto operator will be outsourced through Capitol door. FS lock shop will perform acess control wiring. Electrical shop to provide a dedicated circuit for the auto door operator. | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000390 |  | 19P000390 | FALSE | CNAS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  | 0 |  | TRUE |  |  | 43433 | [6 empty] | 7/1/19, DL; This project is 100% Complete…………6/17/19, DL; material is ordered. This project should be complete by July 1st…..5/31/19, DL; Plans were apprvied this week we will work on the contract and hopefully have the notice to proceed in the next two weeks. It is our goal to have the work complete on or before July 1st……5/15/19, DL; Need to order the special order door and frame…. | 2019-02-07 | Ron Veloz | Install new aluminum storefront door, frame and side lite(requested by Dan L.), patch & paint door opening and west interior wall. | YES | 2019-07-01 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000574 |  | 19P000574 | FALSE | CHASS | SL5 FACULTY OFFICE PAINTING |  | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43567 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000609 |  | 19P000609 | FALSE | CHASS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR |  | WATKINS | 1229 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43595 | [6 empty] | 07/03/19 O-ANS: Paint phase complete and awaiting flooring change. 06/21/19 O-ANS: Customer requested to remove lighting change from project and only complete paint and carpeting via email to Paul Ditty (copied email below). Will create separate work order for lighting. Re-assigned to Paul Ditty to complete. "From: Becky L Campbell <becky.campbell@ucr.edu> Sent: Friday, June 21, 2019 10:51 AM In regards of the work order: 19P000609 - SL5 - PAINT FACULTY OFFICE – please cancel the connecting Work Order 19W015231 – REPLACING THE LIGHTING IN WATKINS 1229. Please do paint and replace flooring.For the lighting, please create new work order to be done at a later time." |  | Paul Ditty |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000521 |  | 19P000521 | FALSE | SoB | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT |  | ANDERSON 1 (N) | 138 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43532 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000552 |  | 19P000552 | FALSE | CHASS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS |  | HUM & SOC SC | 1001 B, C, and D | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43551 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000558 |  | 19P000558 | FALSE | BCOE | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT |  | BOURNS | A0265 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43558 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000388 |  | 19P000388 | FALSE | BCOE | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | BCOE Advising is being reassigned to space on the 3rd floor of Skye (at the recommendation of the University Space Committee). | SKYE HALL | 308 | COMPLETE | Christopher Lynch | TBD | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 43430 | [6 empty] | 7/15/19, DL; This project is 100% Complete………..7/1/19, DL; This project ois 95% Complete. Floor covering install will start this Wednesday…………6/17/19, DL; This project is almost complete. Target complete date is July 1st….…..5/31/19, DL; We are making good progress on this project. we are on tract to be copmplete with this project on or before July 1st……5/15/19, DL; Work is in progress and we are on schedule for th3 6/28/19 complete date…….5/1/19, DL; We will start this project this week. 4/15/19, DL; Plans were approved today. We will work on material and schedule the work. We will start this project shortly after May 1st…….3/18/19, DL; We are working on plans and plan to apply for building permit an plan review process next week | 2019-02-13 | Ron Veloz | Customer Request: Frame new walls in rm. 0310B & 0326. Widen door opening, install sliding glass door rm. 0310 Work Covered: Install metal stud framed partition walls in room 0310B and 0326 and install electrical and voice data outlets as required for new furniture layout. Widen the existing door opening in room 0310 and install one new 6-0x7-0 sliding glass door. Install a viewing window (approximately 9-0x4-0 overall width) made with two pieces of glass within a storefront frame. Relocate utilities and one wall *cabinet (*location TBD) as needed. Inclusions: Demolition: Remove the side door and frame in room 0310 and widen the opening to accept a 6-0x7-0 sliding door. Room 0310 east wall, cut in opening (approx. 9-0x4-0) at 36”-48” A.F.F.(field verify). Carpentry: Framing & Drywall: Rooms 0310B & 0326; Construct metal stud partition walls and new cased openings, and install drywall with finished edge metal (room 0310). Intersect new walls into the window mullions with a finished edge or metal with neoprene expansion tape installed between the wall and million. Room 0310; Frame a new cased opening to accept a 6-0x7-0 sliding door and frame a new cased opening at the east wall opening (approx. 9-0x4-0, at 36”-48” A.F.F. field verify) to accept a new viewing window. Floorcovering: Install new 4” rubber base in rooms 0310B and 0326, base to match existing. Acoustical Ceilings: Modify the T-bar ceiling grid and cut ceiling tiles to accommodate the new partition walls in rooms 0310B and 0326. Painting: Tape, sand and paint the new partition walls, door/cased openings. Patch and paint other walls in the Advising room 0310 as needed. Glazing: Room 0310; Install a 6-0x7-0 sliding glass commercial door (outsourced to Hour Glass). Quote is on file. Electrical: Room 0310; Relocate light switch and or wall mounted devices at room 0310/corridor wall and possibly may need to relocate conduit in the east wall where the new window opening is created. Rooms 0310B & 0326; reconfigure/separate lighting circuits and switching. Note: “Installation of electrical and voice data outlets may be required in the new partition walls at rooms 0310B & 0326 depending the furniture configuration”. Fire Alarm: Investigate at rooms 0310B & 0326. Fire Sprinklers: Investigate at rooms 0310B & 0326. Exclusions: Replacement of the existing carpet floorcovering. Repaint all walls at rooms 0310B and 0326 (paint new and adjacent walls only). Installation of new mixing boxes and T-stats in rooms 0310B and 0326. | YES | 2019-07-15 | Spring 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000605 |  | 19P000605 | FALSE | CHASS | SL5 PAINT NEW MAILROOM |  | WATKINS | 1320E | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43595 | [6 empty] | 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000607 |  | 19P000607 | FALSE | CHASS | SL5 PAINT FACULTY OFFICE |  | WATKINS | 1312 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 2 |  | TRUE |  |  | 43595 | [6 empty] | 08/26/19: Canceled by customer because duplicate of project 20P000044. 08/13/19 O-ANS: Customer scope of work includes more than just PAINT so project added to Fall 2019 list for prioritization by organization. 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000614 |  | 19P000614 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 202- PAINT |  | COLL BLDG NO | 0202 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000616 |  | 19P000616 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 208- PAINT |  | COLL BLDG NO | 208 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000617 |  | 19P000617 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 212- PAINT |  | COLL BLDG NO | 212 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000597 |  | 19P000597 | FALSE | BCOE | SL5 PATCH AND PAINT WALLS |  | CHUNG HALL | 355, 356, 351, & 353 | COMPLETE | Christopher Lynch | TBD | SARA GALLOWAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43588 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000642 |  | 19P000642 | FALSE | CHASS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM |  | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43606 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000643 |  | 19P000643 | FALSE | CHASS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH |  | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 14 |  | FALSE |  |  | 43606 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
18W007453 |  | 18W007453 | FALSE | ITS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  |  |  | FALSE |  |  | 43069 | [6 empty] | 07/22/19 O-ANS: Work Order converted to project # 19P000433. For further updates, see 19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  |  |  |  | 2019-07-22 | Winter 2019 | FS | FALSE | 2017 | 2021-01-01 | FY 19-20
19P000434 |  | 19P000434 | FALSE | PROVOST/EVC | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | Please patch 50 plus holes on the wall and repaint that wall in Skye hall 136 due to the BKM removing the furniture attached to the wall. Please call Anita Ortiz if you have any questions at x2-5229. Shanshan's extension x7753 has not been moved to her new location yet. | SKYE HALL | 136 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | SHANSHAN | Paul Ditty |  | 2 |  | FALSE |  |  | 43472 | [6 empty] | 07/20/19 O-ANS: Work Complete per Paul Ditty. |  | Paul Ditty |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000487 |  | 19P000487 | FALSE | BCOE | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES |  | BOURNS | A219, A211, A241 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43501 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000599 |  | 19P000599 | FALSE | PB&A | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 43594 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000429 |  | 19P000429 | FALSE | CHASS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | Patch & Paint | COLL BLDG NO | 103 | COMPLETE | Juliet McMullin | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43468 | [6 empty] | 07/26/19 O-ANS: Project complete per Paul Ditty. 06/06/19 O-ANS: Project scheduled to be completed. |  |  |  |  | 2019-07-26 | SPRING 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000535 |  | 19P000535 | FALSE | PB&A | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV | Install TV Mount and additional electrical | BANNOCK H | H0108 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43538 | [7 empty] | 2019-07-08 | Enrico Baez | Install TV Mount and additional electrical | YES | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000553 |  | 19P000553 | FALSE | VC-RED | SL5 SPIETH HALL PATCH AND PAINT |  | SPIETH | 341 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43556 | [6 empty] | 07/26/19 O-ANS: Project Complete per Paul Ditty. |  |  |  |  | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000565 |  | 19P000565 | FALSE | BCOE | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS |  | BOURNS | A0133 | CANCELED BY CLIENT | Christopher Lynch | TBD | NANCY FORD |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43563 | [6 empty] | 07/30/19 O-ANS: Per Paul Ditty, Customer Maggie Souder canceled project. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000477 |  | 19P000477 | FALSE | BCOE | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT |  | CHUNG HALL | 457 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 11 |  | FALSE |  |  | 43495 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000495 |  | 19P000495 | FALSE | VC-RED | SL5 UOB RM 209- PATCH & PAINT |  | UNIV OFC BLD | 209 | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43504 | [6 empty] | 07/30/19 O-ANS: Project closed per Paul Ditty. 07/30/19 D-MMN: Moved furniture and filled holes. Taped base and fixtures. Primed and painted one half of office. Pulled tape replaced plates and moved furniture to other side. Removed plates taped base and fixtures. Primed and painted other half. Used spray texture on patch under window. Pulled masking. Replaced plates. Moved furniture back. Vacuumed carpet during and after total process. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000571 |  | 19P000571 | FALSE | CNAS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 |  | SCIENCE LAB1 | 215 & 322 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO |  | Paul Ditty |  | 10 |  | FALSE |  |  | 43565 | [6 empty] | 07/30/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
18P000351 |  | 18P000351 | FALSE | SoB | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 (S) | 21 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 43178 | [6 empty] | 8/1/19, DL; This project is 100% Complete……7/15/19, DL; Work has started and should be complete on 7/16/19…….. 4/4/19 O-ANS: Moved to Queue to Start to complete during Summer 2019. DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week……8/8/18. The trades are ready to go after they finish current projects…..DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18………. DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date……..9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space……Note. The space is usable and everything works….. |  | Enrico Baez |  | YES | 2019-08-01 | Spring 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
18P000486 |  | 18P000486 | FALSE | CNAS | SL5 PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 43279 | [6 empty] | 8/1/19, DL; This project is 100% Complete…… 6/17/19, DL; This project is making good progreess and will be complete near mid- July…..5/31/19, DL; This project is making good progress and we are hopeful to be complete on or before July 1st……5/1/19, DL: This project is in grogress and moving forward. Target complete date is 6- weeks… 4/15/19, DL; Started Demolition phase….2/28/19, DL; We will work on the plans in the next 30-days.12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000207 |  | 19P000207 | FALSE | CHASS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43335 | [6 empty] | 8/1/19, DL: This project is 100% Complete……7/15/19, DL; Floor covering will be installed next week. Floor covering is the last item for this project……..7/1/19, DL; This project is 95% complete except floor covering. Floor covering will be installed within 2- weeks……6/17/19, DL; This project is making good progress. We should be complete near July 1st…….5/31/19, DL; This project started this week and should be complete by June 28th…….3/18/19, DL; Working on plans and we will submit our plans and permit application this week….. | 2018-09-20 | Enrico Baez |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000283 |  | 19P000283 | FALSE | CNAS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | COMPLETE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 20 |  | FALSE |  |  | 43348 | [6 empty] | 8/1/19, DL; This Project is 100% Complete……7/1/19, DL; Barricades are complete. Signage needs to be installed. Signage to be installed in the next 3- weeks………….6/17/19, DL; Yello Caution tape is installed. Still need to install barricades and signage. Target complete date in mid to late July……5/31/19, DL; The contractor has the PO#. We will start the work and complete the work in the next 30- days……5/15/19, DL; We are waiting on the quote, once we have the quote, we will proceed with the work……4/15/19, DL; We are trying to locate a roofing contractor that will complete the installation. This is a specialty product that requires a professional installation…….3/28/19, DL; We will install the yellow caution tape on the roof which is our most viable option. I will schedule a site visist / job walk with a contractor in the near future…… | 2018-09-19 | Ron Veloz | Install hand railing and marking for a leading edge as direcetd by EH&S. | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000625 |  | 19P000625 | FALSE | BCOE | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM |  | BOURNS | A0108 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43600 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-01 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000417 |  | 19P000417 | FALSE | VC-UNIV ADV | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY |  | UV BLDG A | 201 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43452 | [8 empty] | Enrico Baez |  |  | 2019-08-06 | Summer 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20 | 1
19P000526 |  | 19P000526 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT |  | CHUNG HALL | 0202 & 0203 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43536 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-08 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
18P000388 |  | 18P000388 | FALSE | CNAS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 43200 | [6 empty] | 8/14/19, DL; This project is 100% Complete………8/1/19, DL; This project work from Facilities Services should be complete in about 2- weeks…..7/15/19, DL, Work is in progress. Goal is to be complete with our scope near the first week in August……6/17/19, DL; This will be scheduled in July…….5/31/19, DL; Demo and removal of the dishwasher is. We will work on the installation and elctrical / power connections over the next three weeks. Note. Steam shut down is taking priority and the installation may be delayed….. 5/15/19, DL; We will schedule the work……..DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but there is no hard date as this is vacant space and we will access the space as time permits…… DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter….DL, DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans….7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved….. |  | Enrico Baez |  | YES | 2019-08-14 | Summer 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000350 |  | 19P000350 | FALSE | CHASS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | MISC WORK IN ROOMS 3121 AND 1133 Patch and paint-relocate white boards, hang pictures. | PSYCHOLOGY1 | 3121, 1133 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 4 | 3 | TRUE |  |  | 43390 | [6 empty] | 8/15/19, DL; This Project is 100% Complete…….. 8/1/19, DL; We will start this project this Friday…… 7/15/19, DL; Appears not plans and permits will be required for the work. I will verify and schedule the work in the near future if no plans or permits are required….. | 2019-04-15 | Enrico Baez | Carpentry: 1. Needs to occur after October 26 2. Remove the whiteboard in 3121, patch and paint 3. Remove Glass board in 1133 and relocate to 3121 (in the same way and place as it was in 1133) 3. Mount pictures on the wall in 3121 4. Secure shelving units in 1133 and 3121 5. There is a ceiling tile in 1133 that is stained and needs to be replaced Painters: 1. Room 3121 Patch and Paint walls | YES | 2019-08-15 | Summer 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000613 |  | 19P000613 | FALSE | CNAS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT |  | COLL BLDG NO | 0203B | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43599 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-21 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000615 |  | 19P000615 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT |  | COLL BLDG NO | 203 AND 204 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43599 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000628 |  | 19P000628 | FALSE | GSOE | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2129 | COMPLETE | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43600 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000413 |  | 19P000413 | FALSE | CNAS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | Batchelor 3111-Refresh BSL2 lab to accomodate Biosafety Cabinet. The Biosafety. Cabinet will be procured by BPSC. | BATCHELOR | 3111 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | MATTHEW ULRICH | PATTY SPRINGER | Dan Lerman |  | R1 | 107 | FALSE |  |  | 43451 | [6 empty] | 11/22/19 O-ANS: Project canceled per email from Deborah McWilliams. "The need for an appropriate space to accommodate use of a biosafety cabinet will be addressed in BH 2163 via the campus Batchelor Hall MEP-Tenant Improvement Project managed by PD&C." | 2019-06-12 | Ron Veloz | Preliminary assessment provided by Tiffany Kwok on 2/13/19 email. "For Batchelor 3111, there are a few items that need to be addressed before it can support BSL-2 work. • Floors should be patched to provide a smooth and easily cleanable surface. • Base coves along the wall should be replaced or repaired to provide a smooth and easily cleanable surface. • Base coves under the cabinets on the corners should be provided. • Provide a layer of sealant over the cabinets to ensure that the cabinets are moisture resistant and easily cleanable. • Seal, repair or replace the wooden rack on the wall to provide a moisture resistant and easily cleanable surface. • Ensure the door is self-closing. Since this is not a new facility and the space is not undergoing major renovations, it is not required to provide negative airflow into the space. However, it is still important that the air from the laboratory is not recirculated into clean spaces". | YES | 2019-08-26 | Winter 2020 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20 | 1
19P000608 |  | 19P000608 | FALSE | CHASS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE |  | WATKINS | 1345 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43595 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-27 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000645 |  | 19P000645 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT | Termite Treatment/Cover Gate House and repair roughtd woos as necessary | BOTAN INFO C |  | CANCELED BY FS | Susan Marshburn | Da Lan Dinh | RONALD ANDERSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43607 | [8 empty] | Ron Veloz | BOTANIC GARDEN GATE HOUSE (AND OTHER STRUCTURES) REQUIRES EXTERMINATION OF TERMITES- WITH INSPECTION RESULTS RECEIVED BY ERS |  | 2019-08-29 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000223 |  | 20P000223 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER PAN REPLACEMENTS | Shower Pan replacement | PENTLAND A | A238, B245, B325, C215, F325 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R3 |  | FALSE |  |  | 43784 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Sep 2019. |  | John Peraino |  |  | 2019-09-01 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000560 |  | 19P000560 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION |  | UV BLDG B | 0240B | COMPLETE | Susan Marshburn | Da Lan Dinh | LESLIE ROSE |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43559 | [6 empty] | 9/3/19, DL; This project is 100% complete. We still need to conduct training but the work is complete and training is scheduled…..8/15/19, DL; This Project is 90% Complete and will be complete by the end of the week. Please note. ITS still needs to connect the data lines. Our portion of the work is complete………8/1/19, DL; Plans are approved. Material is ordered. We will schedule the work when the material is on site…. |  | Dan Lerman |  |  | 2019-09-03 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000448 |  | 19P000448 | FALSE | CHASS | SL5 ARTS 333- PATCH AND PAINT |  | ARTS | 333 | COMPLETE | Juliet McMullin | Cindy Williams | SONJA SEKELY-ROWLAND |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43479 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-04 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000575 |  | 19P000575 | FALSE | CHASS | SL5 WATKINS HALL PAINT/FLOORING |  | WATKINS | 1309A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43572 | [6 empty] | 11/26/2019 O-ANS: Paint phase completed per Paul Ditty. Awaiting completion of flooring. |  |  | 01/31/20 O-ANS: Completed per notes as of 09/05/19. |  | 2019-09-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000670 |  | 19P000670 | FALSE | SOM | SL5 SOME, RM 1670- RENOVATE FOR EXPANDED ENROLLMENT |  | SOM EDUC | 1670 | TO BE PERFORMED BY PD&C | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 43634 | [8 empty] | Ron Veloz |  |  | 2019-09-06 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000564 |  | 19P000564 | FALSE | VC-UNIV ADV | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | 1156C (AVC Johnny Cruz) – Patch molly holes, touch-up paint. 1156A (Jules Bernstein) – Remove (2) black & white photos from wall. Patch molly holes, touch-up paint. 1156B – Install picture frame (UCR campus map) onto wall. Suite 1159 – Patch holes. Remove film reels. Paint one accent wall “UCR Blue”. 1159B (Christy Zwicke) - Patch molly holes, touch-up paint. | HINDERAKER | 1156 | COMPLETE | Peter Hayashida | Naysia Caldwell | Lisa Cusick | Christy Zwicke | Paul Ditty |  | 1 |  | FALSE |  |  | 43563 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-07 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
18P000465 |  | 18P000465 | FALSE | CNAS | SL 5 GEOLOGY 2258B AND 2258C - PATCH/PAINT |  | GEOLOGY | 2258B & 2258C | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 43257 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000623 |  | 19P000623 | FALSE | BCOE | HOLD SL5 WINSTON CHUNG HALL, RM 348- MOUNT TV |  | CHUNG HALL | 0348 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  |  |  | FALSE |  |  | 43600 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000646 |  | 19P000646 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING |  | ATH DANCE | 20R, 20S | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43608 | [6 empty] | 9/16/19, DL; This project is Complete…….9/3/19, DL; Project is 80% Complete. Floor covering is scheduled for this Friday. Target complete date is 9/13/19……8/15/19, DL; This project is in progress and slated for complete by the end of september…..8/1/19, DL; Project is in progress with a complete date of 3-4 weeks. |  | Dan Lerman | 06/19/19 O-ANS: Project 19P000647 was combined with this project. |  | 2019-09-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000085 |  | 20P000085 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 FACILITES ANNEX B - PAINT OFFICE SPACE |  | FS ANNEX B | 0001 | COMPLETE | Susan Marshburn | Da Lan Dinh | SANDRA MARTINEZ |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 43696 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000004 |  | 20P000004 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - COURTNEY BAKER |  | HUM & SOC SC | 2204 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43648 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000005 |  | 20P000005 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - KIM FROST |  | HUM & SOC SC | 3215 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43648 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000065 |  | 20P000065 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR CONFERENCE ROOM 205/206 - PATCH & PAINT |  | CHUNG HALL | 205 & 206 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43685 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000594 |  | 19P000594 | FALSE | CNAS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS | Take down a dividing wall in this office and move the desks to their old location and rehang the overhead desk bins back into their old locations with inserts still in the walls. | ENTOMOLOGY | 171 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  | R9 |  | FALSE |  |  | 43581 | [8 empty] | Ron Veloz | TBD | NO | 2019-09-18 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000094 |  | 20P000094 | FALSE | CHASS | SL5 ARTS 0221 -PAINT OFFICE |  | ARTS | 221 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43699 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000114 |  | 20P000114 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER DOOR, BASEBOARD, AND BRACKETS |  | PENTLAND A |  | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000115 |  | 20P000115 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 1 - BALCONY COSMETIC REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R2 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000116 |  | 20P000116 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 5 - BALCONY EMERGENCY REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R3 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000117 |  | 20P000117 | FALSE | PB&A | SL5 PENTLAND HILLS A-H - LATTICE REBUILD |  | PENTLAND A | A-H | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R4 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000118 |  | 20P000118 | FALSE | PB&A | SL5 FALKIRK 1, 2, & 12 - FIRST FLOOR PATIO FENCING |  | FALKIRK 1 | 1st Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R5 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000674 |  | 19P000674 | FALSE | CHASS | SL5 HMSS RM 2416 OFFICE ROOM PATCH AND PAINT |  | HUM & SOC SC | 2416 | TO BE PERFORMED BY PD&C | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43635 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-23 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000038 |  | 20P000038 | FALSE | CNAS | SL5 BATCHELOR HALL 1151- QUOTE FOR ADDING FOB ACCESS TO A DOOR |  | BATCHELOR | 1151 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | RACHEL BEHAR |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43670 | [6 empty] | 09/24/19 O-ANS: PROJECT CANCELD BY CLIENT PER EMAIL FROM DEBORAH MCWILLIAMS. |  | Ron Veloz |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000568 |  | 19P000568 | FALSE | CHASS | HOLD SL5 HMSS HANG WHITE BOARD, TV MOUNTING, PATCH AND PAINT | Remove Glass White Board, mount TV, patch and paint | HUM & SOC SC | 1214 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43564 | [8 empty] | Enrico Baez | No scope |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000037 |  | 20P000037 | FALSE | PB&A | SL5 FAC ADMINISTRATION -PAINT WALLS |  | FS ADMIN | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 43669 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000086 |  | 20P000086 | FALSE | CNAS | SL5 SKYE 2ND FLOOR - KEY CARD ACCESS ESTIMATE |  | SKYE HALL | 2ND FLOOR | CANCELED BY CLIENT | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | R3 |  | FALSE |  |  | 43696 | [6 empty] | 09/26/19 O-ANS: CANCELED BY CUSTOMER - Estimated cost to go keyless outside of budget. | 2019-09-10 | Enrico Baez | Provide estimate for keyless entry. | YES | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000657 |  | 19P000657 | FALSE | BCOE | SL5 WINSTON CHUNG HALL, RM 406- PATCH/PAINT OFFICE |  | CHUNG HALL | 406 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43623 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000107 |  | 20P000107 | FALSE | BCOE | SL5 WINSTON CHUNG 322 - PATCH/PAINT NEW FACULTY FACULTY OFFICE |  | CHUNG HALL | 322 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43706 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000075 |  | 20P000075 | FALSE | CNAS | SL5 SPIETH 2372 - PATCH/PAINT FACULTY OFFICE |  | SPIETH | 2372 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43690 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-27 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000060 |  | 20P000060 | FALSE | SOM | SL5 WEBBER HALL 1274- PATCH & PAINT OFFICE |  | WEBBER | 1274 | COMPLETE | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43682 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-28 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000661 |  | 19P000661 | FALSE | SOM | SL5 SOM RB, CR0600- FY 19/20 PROJECT- PATCH & PAINT |  | SOM EDUC | CR0600 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43627 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000149 |  | 20P000149 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 242 |  | UNIV OFC BLD | 242 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000337 |  | 19P000337 | FALSE | CHASS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | Remove whiteboard (in front of room), mount LED mount, add double duplex and electrical power behind LED, patch and paint wall | PSYCHOLOGY1 | 3210 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 1 | 101 | FALSE |  |  | 43384 | [6 empty] | 10/1/19, DL; This Project is Complete……………..9/3/19, DL; Space is blocked and schedculed to be completed by 9/27/19…..8/14/19, DL; Conducted site visit with Trades. We will schedule the space to be blocked out and start the work mid September….8/1/19, DL; Planning to start this project in two weeks……7/15/19, DL; I will walk the project in the near future and schedule the work if permits are not required…… | 2019-01-15 | Enrico Baez | Electricians 1. Install behind TV. Provide two duplex outlets and power. Also provide single gang box and conduit for data. Data lines have been run to T-bar in Hallway. 2. Secure loose Extron plate and cover next to TV. Painters 1. Patch and paint wall where TV is mounted | YES | 2019-10-01 | Summer 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000673 |  | 19P000673 | FALSE | SOB | SL5 ANDERSON HAL NO, RM 158- RECARPET 12 ROOMS / ELECTRICAL WORK |  | ANDERSON 1 (N) | 158 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43634 | [6 empty] | 10/1/19, DL; This proect is complete… |  | Enrico Baez |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000051 |  | 20P000051 | FALSE | SOM | SL5 SOMED 2611 - PATCH & PAINT |  | SOM EDUC | 2611 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43677 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000068 |  | 20P000068 | FALSE | CHANCELLOR | SL5 SKYE 349 - COVER HOLES ON WALL |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | TBD | VICTORIA AVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43686 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000034 |  | 20P000034 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 451- PATCH AND PAINT 2 SMALL WALL SECTIONS |  | CHEMICAL SCI | 451 | COMPLETE | Kathryn Uhrich | TBD | KEVIN KOU |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43668 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-02 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000683 |  | 19P000683 | FALSE | PROVOST/EVC | SL5 PATHC/PAINTING REPAIR |  | HUM & SOC SC | 1103A | COMPLETE | Thomas Smith | Luisa Levario | JILL CANTONWINE |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43641 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000031 |  | 20P000031 | FALSE | GSOE | SL5 SPROUL HALL 1124B- PATCH/PAINT OFFICE |  | SPROUL | 1124B | COMPLETE | Thomas Smith | Sally Tavizon | MARICELA ARCINIEGA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43668 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000143 |  | 20P000143 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 6605 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 6605 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000152 |  | 20P000152 | FALSE | SOM | SL5 SOME 2669 - PATCH & PAINT |  | SOM EDUC | 2669 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | TRACEY TRETTIN | Paul Ditty |  | - |  | FALSE |  |  | 43738 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000676 |  | 19P000676 | FALSE | CHASS | SL5 PATCH THE PAINT IN THIS OFFICE |  | HUM & SOC SC | 2501 | COMPLETE | Juliet McMullin | Cindy Williams | EVAN ISMAIL |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43635 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000090 |  | 20P000090 | FALSE | CHASS | SL5 OLMSTED 3345 - PAINT WALL AND FILL HOLES |  | OLMSTED | 3345 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43697 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000008 |  | 20P000008 | FALSE | PB&A | SL5 EHS 1133 - PATCH / PAINT AND FIX HOLES IN WALLS |  | ENV HLTHSFTY | 1133 | COMPLETE | Gerry Bomotti | TBD | CESAR PLA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43654 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-07 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000664 |  | 19P000664 | FALSE | CHASS | SL5 WATKINS HALL, RM 1343/1343A- PAINT OFFICE AND LAB |  | WATKINS | 1343 & 1343A | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43628 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-08 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000140 |  | 20P000140 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4400 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4400 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-10-09 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000141 |  | 20P000141 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4401- PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4401 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000158 |  | 20P000158 | FALSE | PB&A | SL5 FS ADMIN OFFICE - TOUCH-UP PAINT AROUND BUILDING |  | FS ADMIN |  | COMPLETE | Gerry Bomotti | TBD | DA LAN DINH |  | Paul Ditty |  | - |  | FALSE |  |  | 43741 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000666 |  | 19P000666 | FALSE | SOM | SL5 WEBBER, ROOM 1237- PATCH AND PAINT | TBD - SOM RM 107, 111 & 330- PROJECT: NEW PI, EQUIPMENT INSTALL | WEBBER | 1237 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43633 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-11 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000162 |  | 20P000162 | FALSE | PROVOST/EVC | SL5 HINDERAKER 1101B - PATCH HOLE IN WALL |  | HINDERAKER | 1101B | CANCELED BY FS | Thomas Smith | Luisa Levario | AMY GU |  | Paul Ditty |  | - |  | FALSE |  |  | 43745 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000142 |  | 20P000142 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 5502 - PATCH AND PAINT FACULTY OFFICE |  | HUM & SOC SC | 5502 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000473 |  | 19P000473 | FALSE | PROVOST/EVC | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 |  | HINDERAKER | 1100 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | TORRI MCGARITY | Paul Ditty |  | 1 |  | FALSE |  |  | 43494 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-28 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
18P000198 |  | 18P000198 | FALSE | VC-STU AFF | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Install new Wall lights | HUB | 0 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | R1 | 5 | FALSE |  |  | 43060 | [6 empty] | 10/30/19, DL: This project is on Hold and may be canceled as funding is not availabel at this time. Plans are approved……10/16/19, DL; Plans were submitted for plan check review last week. I also notified Brendan that this will be a recharge project . The ball park estimate I provided to Brendan was $7,000 - $9,000. Brendan needs to confirm if funds are available. If funds are available, I will have a contractor bid on the project……… 10/16/19: O-ANS - Not a CORE location so project changed to Recharge. 10/1/19, DL; Plans will be submitted a building permit and plan check review this week…….9/3/19, DL; Gunter has plans at 60%, We will try and submitt with in the next two weeks. 8/14/19, DL;This project is now on Gunther's bench. Gunter will start the process in about 2- weeks and we should have plans top submitt with in the next 30- days….6/17/19, DL; I will walk this work in the next two weeks and work on plan to submit to our campus architech and building official for review…..DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…… | 2018-01-23 | Enrico Baez |  | YES | 2019-10-30 | Winter 2018 | FS | FALSE | 2017 | 2021-01-01 | FY 19-20 | 1
19P000555 |  | 19P000555 | FALSE | CNAS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK | INSTALL OF FENCE FOR RAIN COLLECTOR AT TES TANK | SAT CHIL PL | 0 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | R4 |  | FALSE |  |  | 43558 | [6 empty] | 10/30/19 O-RVL: RV sent Andrew a message to ask if a decision was made to proceed with this project or if it will be cancelled?" Pending response. END~ 10/16/19, DL; I placed this project on hold as we have not heard back from the customer. We notified the customer of the cost but have not heard back from them. If the project is approved, we will schedule the work………...10/1/19, DL; Ron provide Deborah the propsal and we are waiting for her response to proceed or cancel the project……...9/16/19, DL; Ron submitted the estimate to Debora and the Faculty member last week. If project is approved, we will schedule the work……9/3/19, DL; Plans and estimate are complete. Ron will provide Deborah with a formal estimate and let us know if we will proceed with the work…..8/15/19, DL; Plans are approved. We ware waiting for a estimate from our contractor. Once we have the quote, we will forward the quoted to Deborah for review and approval. Note, this is a recharge project…….8/1/19, DL; Plans are complete pending approval from building official…. |  | Ron Veloz | Install Chain Link fence with gate. Includes grading, gravel and fence posts set in concrete. |  | 2019-10-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000185 |  | 20P000185 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR (OFF WHITE) |  | PHYSICS | 3004S | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 43756 | [6 empty] | 11/01/19 O-ANS: Canceling bc duplicate of 20P000187. Paul Ditty to speak with customer re: room. |  | Paul Ditty |  |  | 2019-11-01 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000187 |  | 20P000187 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR |  | PHYSICS | 3004S | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 43761 | [8 empty] | Paul Ditty |  |  | 2019-11-05 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000169 |  | 20P000169 | FALSE | PB&A | SL5 LOTHIAN LO-G104-OFFICE - JOB WALK FOR REMODEL OF SCOTTY'S |  | LOTHIAN HALL | SCOTTY'S | CANCELED BY CLIENT | Gerry Bomotti | TBD | FRED OFFENEY |  | John Peraino |  | - |  | FALSE |  |  | 43747 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000206 |  | 20P000206 | FALSE | VC-STU AFF | SL5 COSTO HALL 111-HUB 353/381- RENOVATIONS - CP0003486 |  | COSTO HALL | Lower Level | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | - |  | FALSE |  |  | 43770 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000195 |  | 20P000195 | FALSE | CHASS | SL5 ARTS 0054 - PAINT PIANO LAB |  | ARTS | 54 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | - |  | FALSE |  |  | 43762 | [8 empty] | Paul Ditty |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000622 |  | 19P000622 | FALSE | CNAS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK | Replace doors & frame | FAWCETT LAB | 204 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43600 | [6 empty] | 11/11/19, DL: This project is complete……10/30/19,DL: The doors are scheduled to be installed this Friday…………10/16/19, DL; Doors shuld be here with in the next week. Once the doors arrive, we will prep and paint the first coat and schedule the install. Target complete date is 3-4 weeks depending on when the doors arrive…….9/16/19, DL The doors are ordered. Once the doors arrive, we will schedule them to be painted and installed……..9/3/19, DL; Contractor has PO# for the doors. I need to verify lead time on material and schedule the installation…….8/15/19, DL; PO# will be provided this week to order the doors and frame, lead time is 4- weeks for the doors/ frame. We will scheudule the install once the door / frame is on site……..8/1/19, DL ; Pending estimate from vendor. Once we have everything needed, we will schedule the work…. | 2019-07-15 | Ron Veloz | Replace existing dual egress doors with ne doors and frames. | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000638 |  | 19P000638 | FALSE | BCOE | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM | renovate lab | BOURNS | B207 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43601 | [6 empty] | 11/11/19, DL: This project is Complete……10/30/19, DL: This Project is 95% complete and we should be complete next week………..10/16/19, DL; This project is 99% complete. We need to insulate ducting and deep clean the lab………9/16/19, DL; Project is 95% complete. We are planning to be complete in the next 30 days……9/3/19, DL; Project is in progress and 75% complete. 8/15/19, DL; Plans were approved this week. We will order the material and schedule the work……..Plans are 90% complete and we will probably submit plans for plan check review this Monday | 2019-07-19 | Ron Veloz | 07-01-19 O-RVL: RV Received email from Luat on 06-28 with revised SOW. RV Uploaded the referenced sketch into FAMIS. Revisions read: "In efforts to be helpful, I've color coded comments related to the simple attached sketch. 1) Unchanged: HVAC ductwork needs to be insulated so that we cannot hear it— the vibrations from the noise affect precision optical measurements. 2) Revised to be more specific: only the first row of overhead lights should be on the main switch (dark green). The other lights should be lowered and have pull-down chains, like this but with a longer a longer chain: https://www.grainger.com/product/19YX62 3) Removed: it would be nice if cabinets are nicer and not broken, but we'll turn them into open shelves if there are no funds for this. 4) Removed: (unless fire marshalls object and request sprinklers be lowered) 5) 3) Revised: for air venting machined fumes and soldering, a flexible fume vent should be installed, something like this: https://www.grainger.com/product/EXTRACT-ALL-Extractor-Arm-2DBX4 I'm flexible about where this is hung... what are the options? 6) 4) Revised: the utility rack in the center of the room should be moved to be in line with the other, and centered with the whiteboard on the wall. (Pink) 5) Added: chilled water (blue) and compressed air (light green) should be piped over so it's available to the 10'x3' optical table. 6) Added: Black plywood would be installed at the height of the current 8 1/2" frame like Kevin's in 2 spaces: a) around the 10x3' marked optical table b) around the 6x3' overhead rack close to the doors. Luat T. Vuong" | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000045 |  | 20P000045 | FALSE | VC-RED | SL5 MRB SOUND BOOTH |  | MRB | 2210 & 2204 | COMPLETE | Rodolfo Torres | Laura Manor | DAN LERMAN |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43676 | [6 empty] | 11/11/19, DL: This project is complete…….10/30/19, DL: This project is complete but we need to conduct the final inspection with the building official………..10/16/19, DL: The plans are approved and the work is complete. I need to field verify and schedule the inspection. |  | Ron Veloz | Contact PM for SOW. | NO | 2019-11-11 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000199 |  | 20P000199 | FALSE | SoB | SL5 ANDERSON SO RM 0002 - KEYLESS ENTRY MINOR RENOVATION REQUEST |  | ANDERSON 2 (S) | 2 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG | KENNETT LAI | Dan Lerman |  | - |  | FALSE |  |  | 43763 | [8 empty] | Enrico Baez |  |  | 2019-11-14 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
18P000343 |  | 18P000343 | FALSE | CHASS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER |  | THTR WKSH | 0400A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 43175 | [6 empty] | 11/15/19, DL: This project is complete…..10/30/19, DL: Sheet metal shop fabricated the hand rails. The paint shop will prime and paint the hand rails and the curb. Once the rails are painted, the sheet metal shop will complete the installation…….10/16/19, DL; Cory from the sheet metal shop is aware of the scope of work and they will schedule the work in the near future……..10/1/19, DL; Dan to show Cory from sheet metal the area where a hand rail will be installed for painting backdrops……..07/11/19 O-ANS: Dan and Chris P will walk the space. 05/21/19 O-ANS: Changed to In Progress per meeting with Dan L. Chris P is the PM for further updates. DL and CP will visit after commencement. 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez |  | YES | 2019-11-15 | Spring 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000589 |  | 19P000589 | FALSE | CHASS | SL5 HMSS OFFICE 3405 RENOVATIONS | Construct partion, pending CBO approval, in room 3405. | HUM & SOC SC | 3405 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 8 |  | FALSE |  |  | 43578 | [6 empty] | 11/19/19 DH: Emailed Status Report to customer…..11/19/19 DL: This project is complete….11/11/19, DL: The carpet is delayed and scheduled to be instlled on Friday, 11/15/19. The project will be complete once the carpet is installed……10/30/19, DL: This project is 90% Complete. We are planning to install carpet next week………..10/16/19, DL; This project is 80% complete. Target complete date is 3- weeks…..10/3/19 O-ANS: Updated status per minor reno meeting…. 10/1/19, DL; This project is in progress. We will call for rough electrical inspection….. 9/16/19, DL; We are ready to schedule the work. We are currently waiting for the space to be vacated. Once the space is vacant, we will start the project……9/3/19, DL; We are ready to start the work. The PI returned to work this week. I sent Paul R. an email letting him know we are available to start once we have confirmed dates from him…..8/15/19, DL; Plans are approved but the PI is not. We will probably start the project the 2nd week in September…… | 2019-06-27 | Enrico Baez | CARPENTERS: 1. Construct partition above T-bar ceiling, full height not required. Drywall 5/8" tape and finish. 2. Remove and store three book cases. 3. Cut in opening for 36" (stain grade to match) door in general area of were bookcases were in South wall leading to corridor. Painters: 1. Patch and paint as needed Electricians: 1. Isolate existing switches to control to operate lights in West half of partitioned space. 2. Install two additional switches in East partition. 3. Install additional single gang outlets one on each side of new partition. Telecom: 1. Install additional Voice and data connection in Western side of partitioned space. Flooring: 1. Remove carpet and base. 2. Install new customer selected base and flooring. HVAC: 1. Separate existing duct work from one to two zones controlled by separate stats in each office. | YES | 2019-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000523 |  | 19P000523 | FALSE | CNAS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | PATCH & PAINT GRAD STUDENT OFFICE | SPIETH | 3366 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 5 | 9 | FALSE |  |  | 43536 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-20 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000220 |  | 20P000220 | FALSE | CNAS | SL5 SPIETH-NEW CLOSING/SECURITY MECHANISM FOR LOADING DOCK DOORS |  | SPIETH |  | CANCELED BY CLIENT | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | - |  | FALSE |  |  | 43783 | [8 empty] | Ron Veloz |  |  | 2019-11-22 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000483 |  | 19P000483 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED |  | HEALTH SERV | 404, 407, 412, 405 & 411 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43497 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-11-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000077 |  | 20P000077 | FALSE | GSOE | SL5 SPROUL HALL 1223 - PATCH AND PAINT |  | SPROUL | 1223 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43683 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-25 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000163 |  | 20P000163 | FALSE | BCOE | SL5 BOURNS A0223 - PATCH/PAINT WALLS, DEEP CLEAN/REPLACE CARPET |  | BOURNS | A0223 | COMPLETE | Christopher Lynch | TBD | SABRINA SCHUSTER | DEANNA VORHEES | Paul Ditty |  | - |  | FALSE |  |  | 43745 | [8 empty] | Paul Ditty |  |  | 2019-11-25 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000059 |  | 20P000059 | FALSE | SOM | SL5 SOME 2626- PATCH & PAINT |  | SOM EDUC | 2626 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43682 | [6 empty] | 11/26/2019 O-ANS: Project canceled per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000093 |  | 20P000093 | FALSE | ATHLETICS | SL5 ATHLETICS 0078 - TELEVISION MOUNT/ ELECTRICAL |  | ATH DANCE | 0078 | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43697 | [6 empty] | 11/26/19 O-ANS: Project canceled per communication with Enrico. | 2019-10-04 | Enrico Baez | Install TV bracket on wall near weight room. Provide recessed/flush single gang outlet near bracket. | YES | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000543 |  | 19P000543 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION | TV Bracket &Power/Network box. | CHEMICAL SCI | 342 | CANCELED BY FS | Kathryn Uhrich | TBD | JEFFERY MATUTE |  | Dan Lerman |  | R8 |  | FALSE |  |  | 43545 | [7 empty] | 2019-10-01 | Ron Veloz | "The Chemistry Department is purchasing a 75" TV to mount in CS 342. The wall that will hold the TV needs to be inspected before any action of mounting the TV is done. The wall that we are hoping to place is the Brown-ish wall, where the projector screen is, opposite to the single whiteboard (Upon entry of CS 342, the leftmost wall). We would like a electrical outlet behind the TV, if possible". RV-Cut back sound proofing (sound soak) to accommodate TV brkt & electrical. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000662 |  | 19P000662 | FALSE | SOM | SL5 FY19-20 PROJECT: DEANS CONF ROOM | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | SOM EDUC | 2652 | CANCELED BY FS | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43628 | [8 empty] | Ron Veloz | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | NO | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000377 |  | 19P000377 | FALSE | CNAS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | Replace the gates on the Schneider House driveway, which secure the property, with the taller iron gates that used to be installed at the Gardens entrance. This will require new fence posts and hinges as well. The taller gates are stored along the side of the garage at Schneider House, and Facilities staff can come see them anytime. Please note this is a safety and security project. | BOT GDN HSE |  | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | R2 | 117 | FALSE |  |  | 43412 | [6 empty] | 11/26/19, D: This Project is 100% Complete……………11/19/19 DH: Emailed Status Report to customer….11/15/19, DL: We should have A PO this week. Once we have the PO#, we will schedule the work……10/30/19, DL: Project was approved by customer with an FAU #. I will work on providing a PO# as this is maintenance and schedule the work. | 2019-04-05 | Ron Veloz | Replace Gates with new refurbished & modified gates furnished by BG. Install new steel posts and strip and repaint gates. Gate style revised by customer to purchase vendor fabricated light gauge meta gates without spike, per Jodie Holt 10/09/19. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20 | 1
19P000572 |  | 19P000572 | FALSE | GRAD DIV | SL5 PATCH, PAINT, AND CARPET UOB 152 |  | UNIV OFC BLD | 152 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43566 | [6 empty] | 06/28/19 O-ANS: Paint phase complete and awaiting carpet change. |  |  |  |  | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000028 |  | 20P000028 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0219- PAINT FACULTY OFFICES |  | BOURNS | A0219 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43665 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000082 |  | 20P000082 | FALSE | CHASS | SL5 HUMANITIES THEATRE - PATCH & PAINT |  | THTR WKSH | 405 | COMPLETE | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43692 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000534 |  | 19P000534 | FALSE | VC-STU AFF | SL5 PATCH WALLS AND PAINT |  | HEALTH SERV | 334 | CANCELED BY FS | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43539 | [6 empty] | 12/06/19 O-ANS: Canceled by FS because unable to identify room location even after inspecting rooms with staff support. Original requester has since retired. |  |  |  |  | 2019-12-06 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000150 |  | 20P000150 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 207 |  | UNIV OFC BLD | 207 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000161 |  | 20P000161 | FALSE | BCOE | SL5 WCH 112 - MODIFY ROOM FOR NEW OCCUPANT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | TBD | MARGARET SOUDER |  | Paul Ditty |  | - |  | FALSE |  |  | 43742 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000175 |  | 20P000175 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 112 - PATCH & PAINT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | - |  | FALSE |  |  | 43749 | [8 empty] | Ron Veloz | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with metal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000029 |  | 20P000029 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0211- PAINT FACULTY OFFICES |  | BOURNS | A0211 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43665 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/12/19 |  | Paul Ditty |  |  | 2019-12-12 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000073 |  | 20P000073 | FALSE | VC-STU AFF | SL5 HUB - THE WELL -3RD FL RM 346 DOOR INSTALLATION CP00003544 | DOOR INSTALLATION | HUB | 346 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | JONATHAN GODOY |  | Dan Lerman |  | PENDING |  | FALSE |  |  | 43689 | [6 empty] | 12/13/19 O-ANS: Project canceled by client Brendan O-Brien. | 2019-10-02 | Enrico Baez | 1.) Remove Aluminum accordian door from opening. Customer to determine how to discard. 2.) Frame opening with metal 2"x4" stud and sheet with 3/4" drywall. Allow for oppening to accommodate 36"x 80" door. 3.) Install metal door jamb and casing to match exisiting openings. Door to match exisiting. Campus Fire Marshall to determine if door to be fire rated. Swing to be approved by Campus Building official and/or Campus Fire Marshall. 4.) Relocate single gang outlet on North side of opening , if needed. 5.) Finish drywall, prime and paint walls. Texture to match exisiting. Customer to approve final paint color. | YES | 2019-12-13 | FALL 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000238 |  | 20P000238 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 14 |  | TRUE |  |  | 43794 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000242 |  | 20P000242 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 10 |  | TRUE |  |  | 43794 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000113 |  | 20P000113 | FALSE | CNAS | SL5 GEOLOGY 2258 - PATCHPAINT RECEPTION WALL OVER BIN REMOVED |  | GEOLOGY | 2258 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43712 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000232 |  | 20P000232 | FALSE | CHASS | SL5 PSYCHOLOGY 3111B - WALL PATCH FOR SMALL HOLES IN THE WALL |  | PSYCHOLOGY1 | 3111B | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43789 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000419 |  | 19P000419 | FALSE | CHASS | SL5 CHASS INT SOUTH 2117-CARD ACCESS | Remove Door and wall leading to 2117 Media Library and reconfigure to allow enterance into 2117 A & J without having to go through 2117C. | CHASS INT S | 2117 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43452 | [6 empty] | 12/16/19, DL: This project is now complete…….11/19/19 DH: Emailed Status Report to customer…..11/11/19, The work is 98% Complete. We have one door that we had to send back to the vendor to have it prepared for door hardware. We should have the door back on site with in the next two weeks………..10/30/19, DL: Doors and Frame are on site. The paint team will prime and paint the doors and frame. Once the doors and frame are painted, we will schedule the work……………10/1/19, DL; This Project is 90% Complete. We are waiting on the doors to arrive. Once the doors arrive, we will schedule them to be painted and installed…………..9/3/19, DL; We started this project today. We are planning to be 90% complete by 9/27/19. Note, we have special order doors that have a 4-6 week lead time and that is the reason why we will be only 90% complete on 9/27/19. Paul Richardson is aware of the schedule…….8/15/19, DL; The plans were approved this week, we will order the needed material and start the work very soon…….This is a two part project. We will complete the construction process now. The four doors that need key card access still require a request for proposal and a contract. This portion of the project will take 3- months due to contracts administration, lead time on material and contractor scheduling…….8/1/19, DL; Gunther is working on plans. Once permit is approved, we will schedule the work…. | 2019-03-21 | Enrico Baez | Install 8 position control panel, keyless entry for 2117, 2117A, 2117D and 2117E. ***per Paul Richardson remove 2117G, 2117H and 2117J from request*** !!!!Project to reconfigure wall space, 19P000400 has been combined with 19P000419. !!! | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000639 |  | 19P000639 | FALSE | CNAS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK | Make modifications to accommodate new PI | CHEMICAL SCI | 0435 | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43602 | [6 empty] | 12/16/19, DL: This project is complete…11/19/19 Emailed Status to customer….11/11/19, DL: This project is 90% Complete. We should be complete with the balance of the work in the next two weeks…………10/30/19, DL: This project is in progress and should be complete in 3- weeks……..10/16/19, DL; We will start the work in the next two weeks. 9/16/19, DL; We will start working on the plans in the next 3- weeks and submit them for plan check review. Once approved, we will schedule the work……..9/3/19, DL; Need to verify scope with Ron and start working on plans. Will start plans in the next two- three weeks…… | 2019-07-19 | Ron Veloz | For new Faculty Hire, Dr. Timothy Su we need the following done to CS 435: Original SOW: (1) Add a door between 435 and 439 (swinging outside of 435 into 439). (2) Exhaust connection for a biosafety cabinet (3) Vacuum line hook up (4) Gas cylinder rack Revised SOW 07/30/19: Room 435: (A) Remove mounted wooden cabinets (B) Remove standing wooden cabinet (C) Move flammable cabinet to Room 439 (D) Move flammable refrigerator to Room 447 Room 439: (A) Remove cabinets under sink Room 441: (A) Remove cabinets under sink (B) Remove top and bottom cabinets and bench, then deliver both items to Chemical Sciences Rm 108 (C) De-activate airflow in chemical fume hood #005855 if it does not disrupt air flow in the other chemical fume hoods. Can facilities check whether it is possible to turn valve off for this fume hood without disrupting others? (D) Move biosafety cabinet and incubator from Rm 458 to Rm 441, then hook up biosafety cabinet to house vacuum plumbing (E) Move flammable cabinet to Rm 439 | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000235 |  | 20P000235 | FALSE | CNAS | SL5 SKYE 374 - PATCH AND PAINT |  | SKYE HALL | 374 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 4 |  | TRUE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000236 |  | 20P000236 | FALSE | CNAS | SL5 SKYE 368 - PATCH AND PAINT |  | SKYE HALL | 368 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 5 |  | TRUE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000023 |  | 20P000023 | FALSE | CNAS | SL5 PIERCE RM 1144 - PATCH AND PAINT DOOR WHERE WALL POCKET WAS |  | PIERCE | 1144 | COMPLETE | Kathryn Uhrich | TBD | JACQUELINE |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43664 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000121 |  | 20P000121 | FALSE | CNAS | SL5 SKYE 217 - PATCH AND PAINT |  | SKYE HALL | 217 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43713 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000204 |  | 20P000204 | FALSE | CHASS | SL5 ARTS 166 - PATCH AND PAINT IN LOBBY AND GREEN ROOM |  | ARTS | 166 | COMPLETE | Juliet McMullin | Cindy Williams | ALBERT FETTER |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43769 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/20/19 |  | Paul Ditty |  |  | 2019-12-20 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000455 |  | 19P000455 | FALSE | VC-STU AFF | SL5 FILL AND PAINT OVER HOLES ON WALL |  | HEALTH SERV | 100 | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43482 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/27/19 |  |  |  |  | 2019-12-27 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000127 |  | 20P000127 | FALSE | PB&A | SL5 FALKIRK APARTMENTS EMERGENCY EGRESS |  | FALKIRK 1 | 10E | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 43721 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000205 |  | 20P000205 | FALSE | PB&A | SL5 THE PLAZA 12 & 14 - EMERGENCY DECK REPAIR | Deck repair | THE PLAZA | A0012 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R2 |  | FALSE |  |  | 43770 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000193 |  | 20P000193 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 0001A | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43761 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/02/20 |  | Paul Ditty |  |  | 2020-01-02 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000171 |  | 20P000171 | FALSE | CHASS | SL5 CHASS INTN 2107 - PATCH UP HOLES IN THE WALL |  | CHASS INT N | 2017 | COMPLETE | Juliet McMullin | Cindy Williams | GENEVA AMADOR |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43748 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/03/20 |  | Paul Ditty |  |  | 2020-01-03 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000192 |  | 20P000192 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 1st Floor | CANCELED BY FS | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43761 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000233 |  | 20P000233 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - A169 & A170 ENTRY AREA DAMAGED |  | BOURNS | A169 & A170 | CANCELED BY FS | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43791 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000239 |  | 20P000239 | FALSE | CNAS | SL5 SKYE 382 - PATCH AND PAINT |  | SKYE HALL | 382 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 11 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000240 |  | 20P000240 | FALSE | CNAS | SL5 SKYE 384 - PATCH AND PAINT |  | SKYE HALL | 384 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 12 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000241 |  | 20P000241 | FALSE | CNAS | SL5 SKYE 386 - PATCH AND PAINT |  | SKYE HALL | 386 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 13 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000036 |  | 20P000036 | FALSE | CNAS | SL5 ENTOMOLOGY 224 - PAINT OFFICE FOR NEW PI HANSEN |  | ENTOMOLOGY | 224 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43669 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20. 09/19/19 O-ANS: Project placed on HOLD for WINTER 2020 prioritization per customer request. |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000145 |  | 20P000145 | FALSE | CHASS | SL5 PSYCHOLOGY 1111 - PATCH AND PAINT FRONT OFFICE WALL |  | PSYCHOLOGY1 | 1111 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43733 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20 |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000194 |  | 20P000194 | FALSE | CHASS | SL5 WATKINS 1224 - PAINT NEW FACULTY OFFICE ONLY |  | WATKINS | 1224 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43755 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/09/20 |  | Paul Ditty |  |  | 2020-01-09 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000467 |  | 19P000467 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | WATKINS | 2101 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 43487 | [6 empty] | 1/14/20, DL: This project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Project is 99.9% complete. We should be complete with the work by this Friday. Furniture is scheduled to be install this Friday morning……..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL; The project is still on schedule to be completed on 12/12/19…………….10/30/19, DL: This Project is on Schedule to be completed on or before 12/17/19….10/16/19, DL; This project is in progress with a completion date of 12/15/19…….10/1/19, DL; We will schedule the work. Our portion of the project will be completed mid December……….9/16/19, DL; We will work on the plans soon. This project will be complete by 12/21/19….. 09/03/19 O-ANS: Updated Priority to #1 for Fall 2019 per Susan request. 9/3/19, We are scheduled to complete the work before winter break begins….. |  | Enrico Baez |  |  | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000688 |  | 19P000688 | FALSE | CNAS | SL5 PHYSICS- RENOVATION OF THREE PHYSICS ROOMS | Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 2128 | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43644 | [6 empty] | 1/14/20, DL: This Project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 99% Complete. Custodial will be there this week to complete the final clean. The space will be ready for occupancy starting 1/6/19…..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: The project is on track to be complete on 12/13/19. Once the abatement is complete, we will start the wall repair as the walls are severely damaged from the previous use of the space……10/30/19, DL: WE are working on this project. Our target date for completion is 12/17/19………… | 2019-10-16 | Ron Veloz | Test for ACM and or other hazardous materials in the room. RM 2124, 2128 & 2132: Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2128 Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2132: Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000081 |  | 20P000081 | FALSE | CNAS | SL5 CHEM SCI 0441- INSTALL FUME HOODS | Install vacuum to new fume hood | CHEMICAL SCI | 441 | COMPLETE | Kathryn Uhrich | TBD | TIMOTHY SU |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43692 | [6 empty] | 1/14/20, DL This Project is 100% Complete…….12/17/19 O-DHN: Emailed Status report to customer…..12/16/19, DL: This Project is almost Complete except for connecting the glove box. Cory will try and connect the glove box before the new year……...11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: This project should be complete with in the next two weeks……….10/30/19, DL: This project is in progress and we should be complete in 2- 3 weeks…………10/16/19, DL: We will start this project with in the next two weeks…. |  | Ron Veloz | Install eight (8ea) electrical swithced outlets behind cabinets for new vac pumps, remove doors and install sliding lower pump shelves. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000083 |  | 20P000083 | FALSE | PB&A | SL5 STUDENT SERVICES - INSTALL 8 CUBICLES - CP00003537 | Installation of BKM Cubicles with electric and Data | STUDENT SERV | 3rd Floor | COMPLETE | Gerry Bomotti | TBD | SHARYL MURDOCK |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43641 | [6 empty] | 1/14/20, DL: This project is 100% Complete………..11/18/19 DH: Emailed Status Report to customer…..10/30/19, DL: The plans were approved and we are scheduled to do the work in December…………10/16/19, DL: Plans were submitted this week…….. |  | Enrico Baez | Scope completed by Dan Lerman | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000120 |  | 20P000120 | FALSE | CHASS | SL5 OLMSTED 2139 SUITE - PATCH AND PAINT |  | OLMSTED | 2139 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 43713 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/14/20 |  | Paul Ditty |  |  | 2020-01-14 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000112 |  | 20P000112 | FALSE | CHASS | SL5 PSYCHOLOGY 2123 - PATCH AND PAINT JOB |  | PSYCHOLOGY1 | 2123 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43712 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000172 |  | 20P000172 | FALSE | CHASS | SL5 PYSCHOLOGY 2136B & 2136C - PAINT & PATCH |  | PSYCHOLOGY1 | 2136B & 2136C | COMPLETE | Juliet McMullin | Cindy Williams | ANNIKA KIRMAN | YERAM CHEONG | Paul Ditty |  | 5 |  | FALSE |  |  | 43748 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000225 |  | 20P000225 | FALSE | VC-UNIV ADV | SL5 HINDERAKER 0137 - BASEMENT RESTROOM SINK INSTALL | Install Kitchen Sink in entry room of Restroom 0137 | HINDERAKER | B137 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL | KIM MCDADE | Dan Lerman |  | 1 |  | FALSE |  |  | 43784 | [6 empty] | 1/22/20 O-ANS: Canceled per customer request. | 2020-01-22 | Enrico Baez |  | YES | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000129 |  | 20P000129 | FALSE | BCOE | SL5 BOURNS HALL B0360C - PATCH & PAINT |  | BOURNS | B0360C | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES | KATHY COCKER | Paul Ditty |  | 1 |  | TRUE |  |  | 43720 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/22/20 |  | Paul Ditty |  |  | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | 10 |  | FALSE |  |  | 43355 | [6 empty] | 1/24/2020 E. Baez- Cancelled per Joe Erbland. 4/18/19, DL; Per Enrico, we are waiting for a proposal from HCI and approved funding from Athletics. We should have the proposal in 2- weeks…. | 2018-09-27 | Enrico Baez |  | YES | 2020-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
20P000189 |  | 20P000189 | FALSE | CNAS | SL5 SPIETH 3352 - ESTIMATE FOR PATCH AND PAINT |  | SPIETH | 3352 | COMPLETE | Kathryn Uhrich | TBD | NATALIE HOLT | SILVANA | Paul Ditty |  | 2 |  | FALSE |  |  | 43761 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/28/20 |  | Paul Ditty |  |  | 2020-01-28 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000017 |  | 20P000017 | FALSE | CNAS | SL5 COLLEGE BLDG CR200 - PAINT PROJECT |  | COLL BLDG NO | CR0200 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Dan Lerman |  | R4 |  | FALSE |  |  | 43661 | [6 empty] | 1/30/20, DL: This Project was Canceled per Rohnda via email on 1/29/20……….11/26/19, DL; Provided Ronda with updated quote on 11/25/19: She will present the quote to her team and provide us with an update in the near future if they would like to proceed………11/20/19 O-ANS: Re-assigned to Dan Lerman. Project was originally a paint project but will be outsourced as Recharge project paid for by the customer's department. |  | Dan Lerman |  |  | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000508 |  | 19P000508 | FALSE | CNAS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | BOYCE | 3410 | COMPLETE | Kathryn Uhrich | TBD | CHERYL GERRY |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43517 | [6 empty] | 1/30/20, DL: Project is now cxomplete. The electrical panel cover was installed this morning…………. 11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: We are not complete. We still need to complete the following items; Light bulbs, electrical panel cover, replace ACM ceiling tiles and deep clean the space…..10/30/19, DL: Progress is in progress. We should be done within two weeks…….10/16/19, DL; Paint is in progress and additional work to follow. Target date for complete is 11/19/19…..10/1/19, DL; Jess to survey space for ACM, Lead paint, etc… We will schedule work once we have confirmation from Jess….. | 2019-09-30 | Ron Veloz | ……….Remove lower base cabinets and upper cabinet in room 3410B. Repair delaminated flooring between room 3410 & 3426, Patch and Paint entire rooms 3410, 3410B & 3426 up to 8'H(no paint in in 3410 A&C). Repair damaged floor tiles in room 3410 A&B. Repace all burned out lamps w/ LED throughout labs and office. Strip & wax all floors in labs space. Remove cylinder racks in room 3410B. Fabricate a hinged metal door to cover the electrical panel in roon 3426 (panel is near door). | YES | 2020-01-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000002 |  | 20P000002 | FALSE | CHASS | SL5 HMNSS, RM 1212- REMOVAL OF ROLL UP WINDOW |  | HUM & SOC SC | 1212 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43647 | [6 empty] | 1/30/20, DL: This project is Complete. We will istall the monitor after IT services installls the Data lines. Michael or Aliosn will notify us when IT is complete and we will schedule th emonitor installation…………1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: This project is in progress and will be complete with in two weeks……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project was delayed. The material is currently ordered. We are planning to start the week of 1/6/20……. 11/19/19 DH: Emailed Status Report to customer….10/30/19, DL; We will plan on scheduling the work shortly after Thanksgiving……….10/16/19, DL: Plans are approved, we will order the material and schedule the work once material is on site. Projected start date is mid November………..9/16/19, DL; Plans will be submitted this week for building permit and plan check review….. | 2019-10-01 | Dan Lerman | Remove Roll up partition. Install outlet and data port, patch and paint walls. | YES | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000155 |  | 20P000155 | FALSE | CNAS | SL5 BOYCE 3407 - PAINT OFFICE FOR NEW FACULTY |  | BOYCE | 3407 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | TRUE |  |  | 43739 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/30/20 |  | Paul Ditty |  |  | 2020-01-30 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000157 |  | 20P000157 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BUILDING - HOLES NEED PATCH AND PAINT |  | HEALTH SERV | 325 | COMPLETE | Brian Haynes | Cathy Eckman | CHRISTINA FARIA | WENDY ALEXIS | Paul Ditty |  | 1 |  | FALSE |  |  | 43740 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 01/31/20. |  | Paul Ditty |  |  | 2020-01-31 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000226 |  | 20P000226 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 3401 - OFFICE PATCH AND PAINT |  | HUM & SOC SC | 3401 | COMPLETE | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON | TRACY AVERY | Paul Ditty |  | 8 |  | TRUE |  |  | 43787 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/03/20. |  | Paul Ditty |  |  | 2020-02-03 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000207 |  | 20P000207 | FALSE | CNAS | SL5 PHYSICS 3033 - PAINT & PATCH STAFF OFFICE |  | PHYSICS | 3033 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO | DAVID NEFF | Paul Ditty |  | 3 |  | FALSE |  |  | 43773 | [6 empty] | 03/02/20 O-ANS: Completed per Paul Ditty as of 02/04/20. |  | Paul Ditty |  |  | 2020-02-04 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43355 | [6 empty] | 2/5/20, DL: This Project is 100% Complete………….3/28/19, Doors are in the process of being …. DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez |  | YES | 2020-02-05 | Fall 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
20P000105 |  | 20P000105 | FALSE | CNAS | SL5 PHYSICS 2029 - PATCH AND PAINT |  | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Paul Ditty |  | 17 |  | FALSE |  |  | 43705 | [8 empty] | Paul Ditty | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/06/20. |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000200 |  | 20P000200 | FALSE | CNAS | SL5 COLLEGE BLDG NO 306 - PATCH AND PAINT ONE WALL ONLY |  | COLL BLDG NO | 306 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 15 |  | FALSE |  |  | 43767 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/06/20. |  | Paul Ditty |  |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000311 |  | 19P000311 | FALSE | ATHLETICS | SL5 ATHLETICS 150-KEYLESS ENTRY | Keyless entry system | ATH DANCE | 0150 | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43375 | [6 empty] | 02/07/2020 O-ANS: Canceled by customer Joe Erbland due to lack of funding per email to EBZ. | 2018-09-27 | Enrico Baez | Install keyless entry system, part of larger project throughout the athletics building | YES | 2020-02-07 | Summer 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20 | 1
20P000184 |  | 20P000184 | FALSE | VC-STU AFF | SL5 HUB 261 - CONSTRUCT WALL FOR MEETING/CONFERENCE RM | In HUB 261 the administration is requesting a wall be constructed to create a meeting/conference room. We need a building zone manager to walk the area give estimate as well as reaching out to the fire marshals inspector for recommendations. | HUB | 261 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | Manny Sanchez |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43755 | [6 empty] | 02/07/2020 O-ANS: Canceled due to client request. | 2019-11-05 | Enrico Baez | 11/5/19 E.Baez conducted site visit. **********SCOPE********* 1. Construct, full height, partition wall with door in HUB 261. 2. Provide/install ADA compliant door in new partition wall. 3. Add and relocate fire sprinkler. 4. Re-position lighting in ceiling, add lighting control. 5. Patch and paint. 6. Install base board. 7. Add strobe and smoke detectors. 8. T-bar ceiling re-work. | YES | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
20P000151 |  | 20P000151 | FALSE | SoB | SL5 ANDERSON HALL NO 113 - PATCH/PAINT HOLES |  | ANDERSON 1 (N) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43738 | [6 empty] | 03/02/20 O-ANS: Project complete per Paul Ditty as of 02/07/20. |  | Paul Ditty |  |  | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000337 |  | 20P000337 | FALSE | VC-STU AFF | SL5 HEATLH SERVICE 382 - NEED OFFICE PAINTED |  | HEALTH SERV | 382 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43853 | [6 empty] | 08/06/20 O-ANS: Complete per D-BFA on 02/11/20. |  | PAUL DITTY |  |  | 2020-02-11 | Spring 2020 | FS | FALSE | 2020 | 2021-01-01 | FY 19-20
20P000237 |  | 20P000237 | FALSE | CHASS | SL5 HMNSS 1202A - PATCH AND PAINT SERVICE |  | HUM & SOC SC | 1202A | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTIAN BACK |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43791 | [8 empty] | PAUL DITTY | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/14/20. |  | 2020-02-14 | Spring 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000540 |  | 19P000540 | FALSE | CHASS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | Remove metal roll up window, replace carpet, remove round column cover-reframe square. | HUM & SOC SC | 1202 | COMPLETE | Juliet McMullin | Cindy Williams | MICHAEL MOLINAR |  | Dan Lerman |  | 9 |  | FALSE |  |  | 43544 | [6 empty] | 2/18/20, DL: Thois project is 100% Complete…….1/31/20 O-DHN: Emailed Status Report to customer…..1/30/20, DL; Project is 95% complete. We will install carpet this weekend………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is in progress and should be complete within 3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project was delayed. Material is ordered. We are currently scheduled to start shortly after 1/6/20………..11/19/19 DH: Emailed Status Report to customer…..10/30/19, DL: We will plan on scheduling the project shortly after Thanksgiving……….. 10/16/19, DL; Plans were approved, we will work on ordering material and schedule the work. Anticipated start date is mid-November…….10/1/19, DL; Plans were submitted last week. Once plans are approved, we will schedule the work…………9/16/19, DL; Plans are 90% Complete. We will submit plans for plan check review in the next two weeks……. 8/15/19, DL; Gunter has the project on his list. We will try and be ready for plan check review in the next two weeks…….. | 2019-07-25 | Enrico Baez | 7/1/2019 E. Baez Carpenters: 1. Remove roll up partition and stainless steel counter top. 2. Frame opening, hang drywall, tape and finish 3. Remove round decorative column from support pillar. 4. Frame over column for square foot print. Keep as narrow as possible. 5. Hang drywall, tape and finish. Painters: 1. Paint all new construction Flooring: 1. Remove carpet and base in 1202, lobby area of 1220 and hallway. Refer to drawing. 2. Replace customer selected carpet and base. | YES | 2020-02-18 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000665 |  | 19P000665 | FALSE | PB&A | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | Existing telephone-communications building on University Ave requires repairs and renovation in preparation for new use as fire safety offices. | TELEPHONE |  | COMPLETE | Gerry Bomotti | TBD | Carmen Long | Melissa Garrety | Dan Lerman |  | 2 |  | FALSE |  |  | 43649 | [6 empty] | 2/19/20; This project is complete. We still need to paint the door black but this was not part of the original scope. The paint shop will paint the door in the next two weeks………… 1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL:. This project is 99.9% complete with a few minor punch list items…..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project is on track to finish before the new year with a punch items to be addressed after the new year. IT services still needs to install data and phone. Landscape services is working on the landscape but the landscape was not part of the original scope. Sharyl in is the process of coordinating keys, alarm code and setting up the delivery of the furniture for her team. Overall, we are all in good shape.…….11/19/19 DH: Emailed Status Report to customer…..11/11/19,DL: This project is still on schedule to be complete before the new year……….10/30/19, DL: This project is in progress and on track to be complete before the new year…………….10/16/19, DL: Drain, waste, vent and concrete is complete. We started framing this week. We will start rough electrical and rough plumbing next week……..9/3/19, DL; Abatement was complete this weekend. Trades are scheduled and we are on track for 11/15/19 completion date…..8/15/19, DL Plans were approved this week. Abatement is still needed and the 14- day notification to AQMD is complete. We are on track to complete the work by mid November……. |  | Enrico Baez |  |  | 2020-02-19 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000044 |  | 20P000044 | FALSE | CHASS | SL5 WATKINS 1312 - NEW HIRE RENOVATION - ELIZABETH BERGER | Install drywall over out dated would paneling | WATKINS | 1312 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43676 | [6 empty] | 2/19/20, DL: This project is Complete…………..1/14/20, DL: We started this project today and should be complete with in 3-4 weeks………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will plan on starting the project the 2nd week in January but will not confirm until we have confirmation from the carpenter shop…………11/18/19 DH: Emailed Status Report to customer……11/11/19, DL: The Material is ordered. The carpenters may start the work the week of 11/18/19………10/30/19, DL: I received confirmation the space is vacant we will schedule the work in the next 6- 8 weeks……10/16/19, DL; The plans are approved and the work is complete. I need to schedule final inspection………. | 2019-09-23 | Enrico Baez | ABATEMENT NEEDED----remove mastic from walls at base on wood paneled wall CARPENTERS 1.) Remove chalk board 2.) Install 1/2" plywood over wood paneled walls. Including over plywood partition separating wall. Do not drywall over trim. 3.) Finish drywall. ELECTRICIANS 1.) Bring out electrical for new drywall and secure when drywall has been installed. PAINTERS 1.) Patch, paint and finish all walls. CUSTODIAL 1.) Clean space after construction. | YES | 2020-02-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000421 |  | 19P000421 | FALSE | CHASS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | Install door to access hallway directly | OLMSTED | 2139I | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 5 | 110 | TRUE |  |  | 43453 | [6 empty] | 2/28/20, DL: This Project is Complete….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This Project is 95% complete. We should be complete within the next week…………..1/31/20 O-DHN: Emailed Status Report to customer……1/30/20,DL; Project is in progress and should be complete with in 2- weeks………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will work on the construction schedule and material shortly after the new year. 11/21/19 DH: Emailed Status Report to customer…..10/30/19, DL: Plans are approved. Need to find out the status of the door. We will plan on scheduling the project shortly after Thanksgiving…………10/1/19, DL; Plans are approved. We need to order the door / Frame. Once door is on site, we will schedule the work……..9/16/19, DL; Plans are submitted for the permit review process……9/3/19, DL; Plans are at 50%. We will try and have plans to submit for review within the next two weeks…… | 2019-02-05 | Enrico Baez | *****This work is being performed to accommodate new faculty scheduled to arrive July 1, 2019***** Core work falls under SLA Carpenters • Open wall between corridor and 2139I. • Install metal frame and solid core door similar to 2139. Smoke and draft gasket. • Install carpet patch at threshold of new door. Carpet should match or complement existing carpet. • Remove bulletin board in hallway to facilitate doorway construction and relocate on same wall. See photos in shared drive.. • Replace base boards as needed. Painters • Prime, Patch and Paint walls, doors and trim. • Paint to match existing wall colors. Lock Shop • Furnish and install 1 each, ADA compliant handle sets, match existing hardware. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 19-20
19P000601 |  | 19P000601 | FALSE | BCOE | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY | Renopvate lab space, Patch/paint, Re-finish, re-surface – existing cabinets/casework. Re-finish, bench-tops. Clean existing Chemical fume hood. Repair or replace self-closing chemical/flammables storage cabinet. Repair or replace bench shelves as needed. Clean and wax floors. | BOURNS | B0328E | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43594 | [6 empty] | 2/28/20, DL: This project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL; This Project should be complete in the next 2-3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were approved. We will order material and schedule the work once the material is on site. The material should arrive around the 21st of January…….11/25/19, DL; Floor covering will be complete today. This project is complete except for the Snorkel vents. We are still waiting for plans check approval on the snorkels………11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Floor covering is delayed. We will schedule the floor covering installation when the material is on site. We submitted the plans for the snorkels last week. Once the plans are approved, we will order the phoenix valves and schedule the work………. 10/30/19, DL: This Project is 85% Complete. We will install new floor covering in the next two weeks. All work will be completed except the two snorkels. We still need to submit plans for the snorkels……..10/16/19, DL; This project is 80% complete. 9/16/19, DL; Project is in progress. We still need to submit plans for the snorkel for the power and snorkel. We will submit the plans for review within the next week. Once plans are approved, we will schedule the work……..Scope is complete, waiting on estimates from vendors. We will need to work up a contract which will add time to the project timeline… | 2019-08-06 | Ron Veloz | Provide two new 4” exhaust duct drops. One at the south wall above mobile table & one at the east wall above counter. Refinish two wood work station counter tops with chemical resistant coating (approx. 64lf) including one mobile table wood top. Install four(4) 208v / 30a Electrical receptacles and data drops at gutter racks above two work benches Provide drawer and door maintenance and or repairs at all metal cabinets and metal shelving. Powder coat all lower metal cabinets, shelving, fume hood doors and drawers. Replace damaged sheet vinyl flooring as needed. Move surplus items to materials management as identified by the PI. Install MilQ equipment at the east wall near sink. Relocated cylinder rack as necessary to accommodate “L” shaped work station. Provide and install two new cylinder racks at the south end of two work benches. Furnish and install two new metal cylinder racks. Replace damaged and/or stained 2x4 acoustical ceiling tiles. Relocate “L” shaped front cabinets. Relamp light fixtures and needed. Infill wall between rm 328E & D Patch and paint walls. Strip and wax floor. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000070 |  | 20P000070 | FALSE | BCOE | SL5 BOURNS B342D - PREPARE LAB FOR NEW FACULTY | PREPARE LAB FOR NEW FACULTY | BOURNS | B0342D | COMPLETE | Christopher Lynch | TBD | SABRINA SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43686 | [6 empty] | 2/28/20, DL This Project is Complete……….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is 95% Complete, we need to install 3 power outlets. This project will be 100% complete within two weeks……..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is on schedule to be complete before the 2/3/20 complete date…….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19,DL: We conducted a site visit with the PI> We will do what we can to have the project complete before 2/3/20………… | 2019-11-06 | Ron Veloz | Paint all walls to match existing colors, paint the back of wood cabinets located at the east side of the room, replace stained or damaged ceiling tiles, replace and or replace all HVAC supply & return grilles, relamp as needed, Cal Labs to clean SS sinks, disconnect and dispose of the dishwasher, Plumbing and electrical to disconnect, Cal Labs to refurbish counter tops (light sand & seal), clean strip and wax sheet vinyl floor, repair and refurbish cabinets (white Rm 316, Blue Rm 328), customer to remove all chemical and sanitize fume hoods. | YES | 2020-02-28 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000266 |  | 20P000266 | FALSE | CNAS | SL5 GEOLOGY 2460B - PATCH & PAINT |  | GEOLOGY | 2460B | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 3 |  | FALSE |  |  | 43818 | [8 empty] | PAUL DITTY | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000268 |  | 20P000268 | FALSE | CNAS | SL5 GEOLOGY 2460D - PATCH & PAINT |  | GEOLOGY | 2460D | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 5 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | PAUL DITTY |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000270 |  | 20P000270 | FALSE | CNAS | SL5 GEOLOGY 2460F - PATCH & PAINT |  | GEOLOGY | 2460F | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 7 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | PAUL DITTY |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000267 |  | 20P000267 | FALSE | CNAS | SL5 GEOLOGY 2460C - PATCH & PAINT |  | GEOLOGY | 2460C | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 4 |  | FALSE |  |  | 43818 | [8 empty] | PAUL DITTY | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/04/20. |  | 2020-03-04 | Spring 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000658 |  | 19P000658 | FALSE | SOM | SL5 SOM RB- PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD - PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43627 | [6 empty] | 03/05/20 O-ANS: Canceled by client per Cynthia Carolina. |  | Ron Veloz | TBD | NO | 2020-03-05 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000269 |  | 20P000269 | FALSE | CNAS | SL5 GEOLOGY 2460E - PATCH & PAINT |  | GEOLOGY | 2460E | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 6 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/05/20. |  | PAUL DITTY |  |  | 2020-03-05 | Spring 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000271 |  | 20P000271 | FALSE | CNAS | SL5 GEOLOGY 2460G - PATCH & PAINT |  | GEOLOGY | 2460G | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 8 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/06/20. |  | PAUL DITTY |  |  | 2020-03-06 | Spring 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000245 |  | 20P000245 | FALSE | BCOE | SL5 WCH RM 0325 - PATCH AND PAINT DAMAGE FROM WHITE BOARD |  | CHUNG HALL | 325 | COMPLETE | Christopher Lynch | TBD | SARA GALLOWAY |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43794 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/13/20 |  | PAUL DITTY |  |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000355 |  | 20P000355 | FALSE | CNAS | SL5 GEOL 454A- PATCH & PAINT |  | GEOLOGY | 0454A | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | LAURIE GRAHAM | PAUL DITTY |  | 2 |  | FALSE |  |  | 43870 | [8 empty] | PAUL DITTY | 08/06/20 O-ANS: Closed per Paul Ditty as of 03/13/20. |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2020 | 2021-01-01 | FY 19-20
19P000602 |  | 19P000602 | FALSE | BCOE | SL5 BOURNS B328F- PREPARE LAB FOR NEW PI OCCUPANCY |  | BOURNS | B0328F | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43594 | [6 empty] | 3/25/20, DL: this Project is Complete………...2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is almost complete and should be complete in the next 2-3 weeks………..10/30/19, DL: Plans and permits will be required for the work. We will work on the plans shortly after Thanksgiving……….. | 2019-09-27 | Ron Veloz | Construct metal stud wall framing and bracing above ceiling to infill the opening. Remove and reinstallation wall mounted cabinets located near the cased opening to access and join to the existing wall to new drywall. Install sound insulation. Install drywall, tape, sand, prime and paint wall. Install install rubber base to match existing. Modify T-bar ceiling to accept the wall framing Provide dust containment (Zip Walls) at both rooms near construction area. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000019 |  | 20P000019 | FALSE | CNAS | SL5 PHYSICS 2029A- NEW EYEWASH STATION | PHYSICS 2029A- INSTALL A NEW EYEWASH STATION | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43662 | [6 empty] | 2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL; Permit was approved, we need to order material and schedule the work………. | 2019-11-27 | Ron Veloz | Install new eyewashing station | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000024 |  | 20P000024 | FALSE | CNAS | SL5 PHYSICS 1003- RENOVATION | New Faculty-Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 1003 | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43664 | [6 empty] | 3/25/20, DL: This project is complete……2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: The paint is complete and the floor covering should be delivered this week. Once the floor covering is on site, we will schedule the installation……………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We started this project and should be complete in the next 6- weeks……….11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: David who is responsible for clearing out the space is in the process. Once the space is empty we will schedule the work. We will probably start the physical project shortly after Thanksgiving…….10/30/19, DL; We are planning to start this project within the next 6-8 weeks……. | 2019-10-16 | Ron Veloz | Test for ACM and or other hazardous materials in the room. Replace all existing flooring, remove power pole and miscellaneous wall mounted items shelving/racks, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks) and repair/replace top & bottom flush bolts, install new door closer(s), relamp with LED as needed. Replace faucet, clean sink/counter and infill pit. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000061 |  | 20P000061 | FALSE | CNAS | SL5 PHYSICS 1028 - MOVE UTILITIES FOR GLASS SHOP | Install utilities in Physics for the Glass shop equipment relocated from Pierce. | PHYSICS | 1028 | COMPLETE | Kathryn Uhrich | TBD | CHRISTOPHER BARDEEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43683 | [6 empty] | 04/23/20 O-ANS: Complete per Dan Lerman. Separate work order to install gas line created - 20W026489 …. 1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is 90% complete and should be 100% complete 1/24/20………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 95% complete. They are moving the equipment over. Once the equipment is delivered and setup, we will connect all of the power and plumbing……11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL; We are still working on plans for this project. 10/30/19, DL: We're planning to complete the project by 12/7/19. We are working on the plans and are planning to submit the plans for plan check review tomorrow. | 2019-10-16 | Ron Veloz | Electrical: Relocate existing power for the welder & other equipment. Install new power and safety switch for relocated equipment. Relocate power for welder and other equipment to the machine shop side of the north wall. Plumbing: Lab air and Natural Gas - relocate and install new POC's. Install water supply lines to Wet sander and diamond wet saw. Cap and or extend the existing Lab air and natural gas as necessary. Install drain lines for new equipment. Modify water supply and existing sink and faucet. Carpentry: Demo selected upper and lower cabinets at the West wall. | YES | 2020-04-23 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000335 |  | 20P000335 | FALSE | CNAS | SL5 ENTOMOLOGY BLDG 239-246 - PAINT AND PATCH OFFICE AND LAB |  | ENTOMOLOGY | 239 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43852 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY | 05/22/20 O-ANS: Project canceled per customer request (Bill Sutton). |  | 2020-05-22 | Spring 2020 | FS | FALSE | 2020 | 2021-01-01 | FY 19-20
19P000620 |  | 19P000620 | FALSE | BCOE | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0304 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 9 |  | TRUE |  |  | 43599 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
19P000621 |  | 19P000621 | FALSE | BCOE | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0308 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 10 |  | TRUE |  |  | 43599 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20
20P000243 |  | 20P000243 | FALSE | PB&A | SL5 ALUMNI CENTER - HYDRATION STATION INSTALL | Install hydration station | ALUM VISITOR | FIRST FLOOR | COMPLETE | Gerry Bomotti | TBD | LESLIE ANN GERRETSE |  | John Peraino |  | R4 |  | FALSE |  |  | 43785 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by June 2020. |  | John Peraino |  |  | 2020-06-01 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 19-20 | 1
19P000659 |  | 19P000659 | FALSE | SOM | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43627 | [6 empty] | 08/05/20 O-ANS: Canceled by client (Cynthia Carolina) via email with Ron Veloz. 8/5/20, DL: Dan to follow -up with customer…………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "remove 330 from work order / update project details / Update: Furniture on order 3.30.2020 - delivery tbd" |  | Ron Veloz | TBD | NO | 2020-08-05 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | COMPLETE | Kathryn Uhrich | TBD | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 43332 | [6 empty] | 8/5/20, DL: This project is complete……………..06/17/20, DL: This project should be complete with in the next two weeks……..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within two weeks. Once we have a contract, we will schedule the work……….1/15/20 O-DH: Emailed Status Report to customer……1/14/20, DL: Contracts is currently working on the contract. Once the contract is complete, we will order the material and schedule the work…………11/26/19, DL: Plans were approved. We will work on the construction contract. Once we have the notice to proceed, we will schedule the work……….10/15/19, DL: Sent PD&C and follow-up email on 11/11/19. We should have approved plans in the near future……10/30/19, DL: Sent PD&C an email asking for a status update on 10.30.19…… 10/16/19, DL; Plans are still in plan check. I sent the building official an email asking if any additional information is needed. This work will be completed by a contractor which means we need to allow time for the bid and contract process……… …………9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Ron Veloz | Request for Estimate to install three new FOB readers with electrified locksets. Work covered: Install one AC Fob Reader at door 2221 and one AC Fob reader at each Door 4231 & 4235. Connect card readers to the existing Hirsh ACP located in the IDF closet at each floor. 03/07/19: Scope revised to eliminate two FOB readers. Install one FOB reader at Genomics door 4231 only instead of all three rooms. | YES | 2020-08-05 | Fall 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 20-21
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | COMPLETE | Kim Wilcox | TBD | ALEXIS RAMBAUD |  | Dan Lerman |  | 1 | 0 | FALSE |  |  | 43445 | [6 empty] | 8/5/20, DL: This project is complete…………3/25/20,DL: Doors are scheduled to arrive the second week in April……2/19/20 O-DHN: Emailed Status Report to customer……2/18/20, DL: Work is complete except for Door and final deep cleaned I do have final stain samples from the vendor. I need to verify color……… We will complete the project when the doors arrive……….1/14/20, DL: Plans are approved, PO# is cut for the ordering of the custom doors, we are currently scheduled to start the work on or shortly after 1/21/20,. Karim understands that we will start and finish the project but we will not be able to install the door until the door arrives on site. There is a minimum of 6-8 week lead time on the door delivery………….12/16/19, DL: Plans are still in plan check review. I sent the building department an email asking for a startus update today…….10/16/19, DL; Plans were submitted to our building official this week for plan check review and a permit……9/16/19, DL; Guther will work on plans in the next three weeks. Once plans are complete, we will proceed with the permit process… | 2018-12-20 | Ron Veloz | SOW: Wall: Construct a metal stud framed wall with drywall up to hard ceiling (ceiling has 12x12 glue up ceiling tiles). Hardware: Install new lockset & keys are required.***** French Door: Install new stain grade birch door with full lite. Door and finish to match the existing office doors.***** Hard Ceiling: * Ceiling is 8’-0” A.F.F. + - with 12x12 glue up ceiling tiles. Work may require a new access panel if access to space above is needed. The 12x12 glue up ceiling tiles may need to be removed where the new wall is constructed.***** Flooring: The existing flooring will remain. Install rubber base to match existing.***** Painting, Taping & Sanding: Taping sanding and painting is required at the new wall and connecting walls.***** HVAC: May require modifications to split the existing supply air to accommodate the open office space.***** Electrical: Provide light switch at new office, power(new or relocate); add and or relocate electrical and voice/data outlets required for a standard office.***** Lighting: Provide a new light switch/circuit near office entrance. The existing 2x4 fixture is on main lighting circuit and will require lighting circuit modifications. Verify if the existing lighting is sufficient for the proposed office. Field verify if additional lighting is required.***** Fire Alarm: Provide a new Smoke/chime detector at new office area, confirm requirements. | YES | 2020-08-05 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 20-21
19P000414 |  | 19P000414 | FALSE | PB&A | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | Seth Morrison |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43451 | [6 empty] | 8/5/20, DL: This Project is Complete………….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: We have the motor on site, we are working on the permit for the crane. Once we have the crane lift permit, we will schedule the install…………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: We are working on the new motor platform. It is our goal to install the new motor in late January. Once the motor is installed, we will be able to identify if additional work is needed…….11/19/19 DH: Emailed Status Report to customer…..11/15/19, DL: Material has not arrived……..10/30/19, DL: The new exhaust fan is ordered with a 2- 4 lead time. Once the exhaust fan arrives, we will schedule the install……….10/16/19, DL; We are in the process of the work. At this current time, we are not modifying the building to where permits may not be required…….10/1/19, DL; This is in the queue for plans, we will start the plans in the next 3-4 weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2018 | 2021-01-01 | FY 20-21
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | C&C CARPORT | 161 | COMPLETE | Danna Gianforte | Shelley Gupta | SHELLEY GUPTA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43472 | [6 empty] | 8/5/20, DL: This Project is complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have the contract, we will schedule the work……………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Project was approved by Shelley. We will work on the contract. Once we have the notice to proceed from contracts, we will order the material and schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Sent Shelley another follow-up email today and she has not verified if she would like to move forward with the project………10/30/19, DL: Sent Shelley the updated quote last week and she has not responded. I sent Shelley a followup email today asking her to let me know if she would like to proceed with the work……..10/16/19, DL; Had a meeting with Shelley, we modified the scope of work and software for the project. We are now revising the quote with our vendor. We should have an updated quote within the next two weeks. If Shelley approves the work and scope, we will proceed….10/1/19, DL; I have a meeting with Shelley this afternoon to review proposal. If she approves the project we will submit plans for a building permit……8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was cancelled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; We have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28/19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21 | 1
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43487 | [6 empty] | 8/5/20, DL: This Project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer…..2/18/20, DL: We are making great progress and still on schedule to be complete before Spring Break begins. We pass drywall inspection on 2/18/20………..1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: Plans are approved. All items have been removed from the space. Abatement is schedule to take place within two weeks…..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were submitted for plan check review. Fire marshal stamped the plans, we are waiting on the final stamp from our building official. Once plans are approved we will order material and schedule the work……..10/30/19, DL: Gunter is working on plans. We are planning to complete the work before Spring Quarter begins. |  | Dan Lerman |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | R3 |  | TRUE |  |  | 43550 | [6 empty] | 8/5/20, DL: This Project is COMPLETE…….3/25/20, DL: The material is here and we are 95% complete with the work. We will complete the work when we return from the campus closure…………1/31/20 O-DHN: Emailed Status Report to customer…….1/30/20,DL: The pump is now on site but we are still waiting for the fittings. In the mean time, our plumber is putting everything together and is working on the installation. Once the fittings arrive, we will make the connections and the system should be good to go………….1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: The pump is scheduled to arrive on or before 1/31/20. We will schedule the work once we have the pump and material on site…..11/26/19, DL; Emailed Natalie and Sherice the quote for the vacuum pump. We will order the material and schedule the work once we have approval and the pump on site……11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: I sent the vendor a 2nd email requesting an update on the proposal. I also included Natalie on the email so she is aware of where we stand with the proposal……10/30/19, DL: We had a followup meeting with the vendor last week. The vendor is now working on a pump that will best meet our needs……….10/16/19, DL; We are working with a vendor on a quote for a new lab vacuum pump. We are hoping to have a quote in the next week or two…..9/16/19, DL; Estimate was provided to customer last week. If the project is approved, we will work on the plans and permits. Once approved, we will schedule the work…… |  | Ron Veloz | Old SOW Revised SOWInstall exhaust hood, electical receptacle, vacuum pump, vac lines and valves (six valves total) and hood location. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21 | 1
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43594 | [6 empty] | 8/5/20, DL: This Project is Complete…….3/25/20, DL: Project is 95% complete. We will install the fire sprinkler and exhaust duct to the gas cabinet when we return from the campus closure………..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Plans were approved and material is ordered. We are hopeful the material will arrive the 2nd or 3rd week in January. Once material is on site we will schedule the work…… 11/19/19 DH: Emailed Status Report to customer……10/16/19, DL: This project is 90% Complete. We are working on plans and permits for the two snorkels……….10/1/19, DL: This project is almost complete. We will be complete in the next 4- weeks except the Snorkel……….. 9/13/19, DL; The paint of the cabinets is scheduled for this week along with the power. We will submit the plans for the snorkel this with in the next two weeks…….9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Ron Veloz | SOW, Patch& Paint Walls, replace plexi glass on shelving, powder coat metal shelving & cabinets, clean & polish or replace chem sinks, polish counter tops, Validate all gas, water, drains, DI water & utilities. Replace damaged and dirty ceiling tiles, relamp as needed. Strip & wax floor. Dan L is requesting vendor pricing to restore finishes. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
19P000687 |  | 19P000687 | FALSE | PB&A | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | COMPLETE | Gerry Bomotti | TBD | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 43642 | [6 empty] | 8/5/20, DL This Project is Complete……………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Contracts is processing the contract. Once the contract is complete, we will schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Plans were approved. I sent Brendan an email 11/11/19 requesting an FAU # as this is Recharge work. Once we have the FAU #, we will work on the contract agreement with the contractor………10/30/19, DL; Sent Lezlie and email asking if she has an update on the resubmitted plans on 10/30/19………..10/16/19, DL; The plans were resubmitted for plan check review this week. We are hopeful the plans will be approved this week. Once approved we will work on contract and scheduling the work…10/7/19 LB: This is a test. The timestamp will be reset when the test is done. 10/1/19, DL: We are working on plan check review. We should have approved plans in the next two weeks…..8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | Provide estimate to install key card access control |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21 | 1
20P000213 |  | 20P000213 | FALSE | CHASS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS |  | CHASS INT S | 2117A, 2117C, 2117D, 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43777 | [6 empty] | 8/5/20, DL: This Project is Complete……………..2819/20 O-DHN: Emailed Status Report to customer…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have a contract, we will order the material and schedule the work………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Plans are complete and submitted for building permit. We are also working on the contract. Once the plans are approved and the contract is complete, we will schedule the work………. |  | Enrico Baez |  |  | 2020-08-05 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21 | 1
19P000660 |  | 19P000660 | FALSE | SOM | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SL5 SOME RB, RM 330- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43627 | [6 empty] | 9/30/20, DL: This Project is Complete………..8/5/20, DL: Dan to follow-up with customer…………..03/05/20 O-ANS: Removed room 330 per client request. Only updates to 107 & 111. |  | Ron Veloz | TBD | NO | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000054 |  | 20P000054 | FALSE | SOM | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOMED-SOME G0600, G0621 & 1682B- ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43677 | [6 empty] | 9/30/20, DL: This Project is Complete…………..8/5/20, DL, Dan to follow-up with customer………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "Remove status Hold / Update project detail to include information on 1682B -ADD ELECTRICAL, PAINT/PATCH, AND RELOCATE WHITE BOARD." |  | Ron Veloz | Room G0600 Install Power behind and below the TV, install one TV Bracket, install one cut-in back box below the TV for data(data cabling by ITS), Paint the entire East wall to match existing. Room G0621 Insatll three(3) new double duplex receptacles and three(3) data back boxes only(no data cabling) in room G0621. Install SS tubing for Co2 from room G0621 to room G0623. Include Valves at both ends of P.O.C., Install one uni-strut siesmic cylinder support at the south wall. Steve Burleson has walked the site and has knowledge of the SOW. Loading Dock Install Pole & chains at Loading dock. |  | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000135 |  | 20P000135 | FALSE | BCOE | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MS&E Rm 0075 - 3 Ph208 Power CHW S&R WATER PPMS TOOL, Install Chilled water loop & power in clean room 075. | MAT SCI ENGR | 75 | COMPLETE | Christopher Lynch | TBD | MARK HEIDEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43727 | [6 empty] | 9/30/20, DL: This project is complete……..8/5/20, DL: This is in progress…….3/25/20, DL: We will work on plans and permits when we return back from the campus closure……. | 2020-02-18 | Ron Veloz | Intake/SOW: Install 208V 3ph power & disconnect/safety switch and one 3/4" Chilled water loop (Supply and Return) in the MSE southeast corner of clean room 0075. Create a 4" diameter pass-thru hole from this corner of room 0075 into the adjacent room 0071. FS to provide power and cooling to a compressor which will connect through the wall to the PPMS system with cryogenic helium lines. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000202 |  | 20P000202 | FALSE | CNAS | SL5 SKYE HALL 361 RENOVATION PROJECT | Renovete space for class room. | SKYE HALL | 361 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY | MELISSA GOMEX | Dan Lerman |  | 1 |  | FALSE |  |  | 43768 | [6 empty] | 9/30/20, DL: This Project is Complete……….8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Permits were approved. Demolition is complete…..1/15/20 O-DHN: Emailed Status Report to customer……..1/14/20, DL: Plans have been submitted for a building permit. Once plans are approved, it is our goal to complete the work by the beginning of spring quarter….. |  | Ron Veloz | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000214 |  | 20P000214 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | Remove walls and doors in spaces 2139 A,B and C. | PSYCHOLOGY1 | 2nd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43776 | [6 empty] | 9/30/20, DL: This Project is Complete…………8/5/20, DL: we will submiot plans this week.…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Plans were submitted for a permit on 2/12/20. Once plans are approved, we will order the material and schedule the work……… | 2020-01-10 | Enrico Baez | **************************************SCOPE********************************** 1.) Remove doors, and jambs 2139A, 2139B, 2139C. 2.) Remove drop ceiling in 2139A, 2139B, 2139C and repair as needed. 3.) Remove cabinets in 2139A, 2139B, 2139C. 4.) Remove walls between 2139A & B, and remove walls between 2139B & C. 5.) Change light fixture to match existing. 6.) Repair walls as needed. 7.) Patch and paint as needed. 8.) Replace carpet and base in 2139A, 2139B, 2139C and 2139 common area. 9.) HVAC duct work in individual spaces can be removed and simplified. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43340 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice. | 2018-09-27 | Enrico Baez |  | YES | 2020-11-19 | Fall 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 20-21
19P000427 |  | 19P000427 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | Install Power and TV bracket, move white board | CHUNG HALL | 453 | CANCELED BY FS | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43468 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold……… | 2019-09-18 | Ron Veloz | Install Power and TV bracket, remove white board and relocate , patch and paint wall prior to installing | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21 | 1
19P000502 |  | 19P000502 | FALSE | BCOE | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | Install Electrical power & TV bracket.for a 75" TV to mount in CS 342. | CHUNG HALL | 444 | CANCELED BY FS | Christopher Lynch | TBD | RICHARD BAIN |  | Dan Lerman |  | R3 |  | FALSE |  |  | 43515 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This project is on hold……………3/25/20, DL: Work orders are produced. I will work on scheduling the work when we return back to work…….. | 2019-09-17 | Ron Veloz | Install Electrical power & TV bracket. Excludes network/data back box and stub up to ceiling. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21 | 1
3275 | 3275 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Fiber Optic Infrastructure Upgrade | Repair, replace and upgrade the fiber optic infrastructure network that includes 50+ buildings across campus. Also includes work to main hubs, sub hubs and make available spare fiber for future utilization. |  |  | Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Daneca Stevens | 12 |  |  | FALSE | 703750 |  | 42837 | Complete Construction | 44013 | 44166 | [10 empty] | PD&C | FALSE | 2017 | 2021-01-01
3535 | 3535 |  | FALSE | CHASS | Life Sciences 452 Renovation | This request is for a new faculty hire. -Remove north countertop and sink. Install stainless counter and two sinks. -Install eye wash station -Install laminate flooring, remove existing. (Abatement) -Paint space to campus interior standard. -Remove east counter and replace with stainless. -Remove fume hood, discard. -Install new fume hood. | LIFE SCIENCE | 452 | Construction | Juliet McMullin | Cindy Williams | Paul Richardson |  | Tameesha Hayes | 1 |  |  | FALSE | 133500 |  | 43656 | Complete Construction | 44105 | 44197 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3557 | 3557 |  | FALSE | CHASS | Campus Sculpture Installation | We will bring 5 sculptures to campus that will go in public places that have already been identified by Uma Ramasubramanian and Jacqueline Norman . Please construct 5 concrete plinths at various locations around campus. Locations are on the attachment. |  |  | Construction | Juliet McMullin | Cindy Williams | Emily Rankin |  | Tameesha Hayes | 3 |  |  | FALSE | 82000 |  | 43796 | Complete Construction | 44075 | 44166 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 20 |  |  | FALSE | 315000 |  | 43312 | Bidding | 44287 | 44348 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-01
3471 | 3471 |  | FALSE | VC-STU AFF | HUB Electrical Sub Meter Installation | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Design | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 200000 |  | 43332 | Bidding | [12 empty] | PD&C | FALSE | 2018 | 2021-01-01
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | Design | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 43528 | Bidding | 44256 | 44378 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3524 | 3524 |  | FALSE | VC-STU AFF | Student Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | STUDENT SERV |  | Design | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE | 450000 |  | 43571 | BKM Lead Time 10 Weeks | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 44096 | Bidding | 44287 | 44378 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-01
9062 | 9062 |  | FALSE | PB&A | DM(FY20) Life Sci Sewer line |  |  |  | Design | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 116000 |  | 44089 | Bidding | 44228 | 44228 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-01
3467 | 3467 |  | FALSE | PB&A | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | Design - 3rd flr Walking Deck Only | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 18 |  |  | FALSE | 235000 |  | 43312 | Bidding | 44197 | 44287 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-01
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 43803 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2019 | 2021-01-01
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SERV | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | TBD | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 43852 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-01-01
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES |  | UNIV OFC BLD | 200 | HOLD - FACILITIES SERVICES | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43868 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-01-01
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LAB1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 43880 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-01-01
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT |  | SCIENCE LAB1 | 317 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 10 |  | FALSE |  |  | 43879 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-01-01
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Bidding | Jacqueline Norman | Sharyl Murdock | John White |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 42725 | Re-bid Lighting Project | 44228 | 44317 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-01
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Bidding | Kathryn Uhrich | TBD | Tracey Kahn, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 1575000 |  | 43108 | Procurement | 44197 | 44287 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-01
3550 | 3550 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Skye Hall HVAC Replacement | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | SKYE HALL |  | In Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 1177000 |  | 43713 | Award Contract | 44197 | 44317 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3597 | 3597 |  | FALSE | PB&A | Plaza F Roof Replacement | Plaza building F roof is well past its service life and is experiencing multiple leaks into the apartment spaces below. This scope of work is to replace the roof in total and repair damages observed to the apartments below as a result of roof leaks. REQUESTING JOHN FRANKLIN AS THE PROJECT MANAGER. |  |  | In Bidding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 19 |  |  | FALSE | 250000 |  | 43999 | Award Contract | 44197 | 44228 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-01
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | In Bidding | Kathryn Uhrich | TBD | Mireya Botello Santoyo |  | Scott Donnell | 5 |  |  | FALSE | 32871.65 |  | 44026 | Construction | 44136 | 44166 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-01
2970c | 2970c |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Bidding | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 13 |  |  | FALSE |  |  | 42340 | Award Contract | 44197 | 44256 | [10 empty] | PD&C | FALSE | 2015 | 2021-01-01
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | In Bidding (prequalification) | Gerry Bomotti | TBD | Sharyl Murdock |  | Rowan Reid | 16 |  |  | FALSE | 18179000 |  | 42353 | Award Contract | 44197 | 45139 | [10 empty] | PD&C | FALSE | 2015 | 2021-01-01
3005 | 3005 |  | FALSE | CAP PROG | Batchelor Hall Interior Improvements | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: - Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality - Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | In Bidding (prequalification) | Jacqueline Norman | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 12 |  |  | FALSE | 8837000 |  | 42402 | Award Contract | 44197 | 45139 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-01
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 7 |  |  | FALSE | 600000 |  | 43634 | Receive Submittals | 44166 | 44344 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
2952 | 2952 |  | FALSE | CAP PROG | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jon Harvey |  | Gerald Caraig | 15 |  |  | FALSE | 23895000 |  | 42258 | Phase I Completion | 43467 | 44317 | [10 empty] | PD&C | FALSE | 2015 | 2021-01-01
3195 | 3195 |  | FALSE | FAC-PLNG-DESIGN-CONST | North District | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 4146146.55 |  | 42669 | Complete Construction | 43647 | 44409 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-01
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Mihai Gavan | 11 |  |  | FALSE | 57950000 |  | 42887 | Complete Construction | 43770 | 44409 | [10 empty] | PD&C | FALSE | 2017 | 2021-01-01
3401 | 3401 |  | FALSE | CAP PROG | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | In Construction | Jacqueline Norman | Sharyl Murdock | Mihai Gavan |  | Fernando Canon | 14 |  |  | FALSE | 8754623.11 |  | 43072 | Complete Construction | 43952 | 44197 | [10 empty] | PD&C | FALSE | 2017 | 2021-01-01
3490 | 3490 |  | FALSE | PB&A | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | Parking Lot 13 |  | In Construction | Gerry Bomotti | TBD | Irma Henderson |  | D.Hecht/J.Franklin | 1 |  |  | FALSE | 31844000 |  | 43440 | Complete Construction | 43862 | 44256 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-01
3501 | 3501 |  | FALSE | PB&A | DMFI(FY17-19) Watkins 1000 Lecture Hall Reno | Renovation of Watkins 1000 lecture hall, to include lighting, HVAC, flooring, paint, and seating upgrades. This requests appears as projects Q-T on the approved 2017-2019 DMFI Program list. | WATKINS |  | In Construction | Gerry Bomotti | TBD | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 750000 |  | 43528 | Complete Construction | 44013 | 44166 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3533 | 3533 |  | FALSE | PB&A | Solar Rooftop Initiative | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. | MULTIPLE BUILDINGS |  | In Construction | Gerry Bomotti | TBD | Richard Geiger |  | John Franklin | 11 |  |  | FALSE | 2165000 |  | 43619 | Complete Construction | 44105 | 44228 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3603 | 3603 |  | FALSE | SOM | Orbach Libr SOM CSSS AV Equipment | AV for CSSS project - 954044 / re: Fernando Cortez. Please refer to MSRIV in the line reference field for the draw down. |  |  | In Construction | Deborah Deas | Deborah Trujillo | Deborah Trujillo |  | Fernando Canon | 1 |  |  | FALSE | 1652000 |  | 44039 | Complete Construction | 44166 | 44256 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-01
3515c | 3515c |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Construction | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 43532 | Complete Construction | 44166 | 44348 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Construction (delayed by water event) | Christopher Lynch | TBD | Margaret Souder |  | Scott Donnell | 4 |  |  | FALSE | 700000 |  | 43194 | Project Completion | 43770 | 44197 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-01
3560 | 3560 |  | FALSE | CNAS | USDA Modular Bldg Installation | B19-284: Provide and install one (1) 1400 square foot double-wide modular office building with five (5) offices, one (1) being ADA compliant, one (1) ADA compliant unisex restroom, one (1) multi-purpose room with sink. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In construction by USDA | Kathryn Uhrich | TBD | MaryLou Polek |  | Scott Donnell | 3 |  |  | FALSE | 2500 |  | 43742 | Complete Construction (by USDA) | 44166 | 44317 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | Katie Sanchez |  | Gerald Caraig | 20 |  |  | FALSE | 2600000 |  | 42509 | Funding & Approval | [12 empty] | PD&C | FALSE | 2016 | 2021-01-01
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 15690389.32 |  | 42720 | Bidding | 44287 | 44470 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-01
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Design | Kathryn Uhrich | TBD | MaryLou Polek |  | Scott Donnell | 2 |  |  | FALSE | 2500 |  | 43742 | Construction by USDA | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3589 | 3589 |  | FALSE | CAP PROG | Various Bldgs LED Lighting Ph2 | LED Lighting Phase 2 - Package 1 - Replacing existing lamps to LED |  |  | In Design | Jacqueline Norman | Sharyl Murdock | David Palacios |  | Fernando Nunez | 19 |  |  | FALSE | 780545 |  | 43901 | Receive 100% CD's | 44256 | 44317 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-01
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | TBD | Wendi Tapia |  | Tameesha Hayes | 4 |  |  | FALSE |  |  | 44001 | Bidding | [12 empty] | PD&C | FALSE | 2020 | 2021-01-01
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 44097 | Bidding | 44228 | 44348 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-01
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Design | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 44089 | Bidding | 44256 | 44256 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-01
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 13 |  |  | FALSE |  |  | 42340 | Complete Design | [12 empty] | PD&C | FALSE | 2015 | 2021-01-01
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 8 |  |  | FALSE | 432510 |  | 42425 | Bidding | 44256 | 44287 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-01
3590b | 3590b |  | FALSE | PB&A | Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Design | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 43796 | Receive 100% CD's for Review | 44256 | 44348 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Design (Phase 2) | Kathryn Uhrich | TBD | Cheryl Gerry, D. McWilliams |  | Scott Donnell |  |  |  | FALSE |  |  | 42710 | RPU plan review/design (Phase 2) | 44348 | 44409 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-01
3064 | 3064 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Botanic Gardens Basin Silt Removal | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | BOTAN INFO C |  | In Funding | Susan Marshburn | Da Lan Dinh | Toshio Ishida |  | Scott Donnell | 30 |  |  | FALSE | 110000 |  | 42480 | Decision Memo | [12 empty] | PD&C | FALSE | 2016 | 2021-01-01
3104 | 3104 |  | FALSE | PALM DESERT GRAD CTR | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Funding | Tamara Hedges | Zelda Glenn | Zelda Glenn |  | Scott Donnell | 2 |  |  | FALSE | 22000 |  | 42502 | Approval & Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-01-01
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Funding | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 25 |  |  | FALSE |  |  | 42653 | Secure Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-01-01
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | In Funding | Gerry Bomotti | Sharyl Murdock | Gerald Caraig |  | Daneca Stevens | 2 |  |  | FALSE | 50000 |  | 43676 | Secure Funding | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3581 | 3581 |  | FALSE | SOM | SOMR Interior Egress Doors | All egress doors - Floors 1, 2, and 3 - need to be replaced with compliant structures. Please inspect, evaluate and provide quote. |  |  | In Pre-Programming | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 43894 | Design | [12 empty] | PD&C | FALSE | 2020 | 2021-01-01
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | Michelle Baniqued |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 43528 | DB Competition | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Programming | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 10 |  |  | FALSE | 500000 |  | 43713 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | In Programming | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 9 |  |  | FALSE | 600000 |  | 43713 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Programming | Kathryn Uhrich | TBD | Richard Zapien |  | Scott Donnell | 6 |  |  | FALSE |  |  | 43959 | Design | [12 empty] | PD&C | FALSE | 2020 | 2021-01-01
3610 | 3610 |  | FALSE | PB&A | Hulen Place Homeless Medical Clinic | SOM is acquiring additional space for a medical clinic to assist with the homeless population. |  |  | In Programming | Gerry Bomotti | TBD | Diana Armenta |  | Daneca Stevens |  |  |  | FALSE |  |  | 44110 | Design | 44256 | 44256 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-01
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 43532 | Complete Report-Arc Flash | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 43297 | Complete Study | [12 empty] | PD&C | FALSE | 2018 | 2021-01-01
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 43404 | CEQA | [12 empty] | PD&C | FALSE | 2018 | 2021-01-01
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 43510 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Programming (Study) | Kathryn Uhrich | TBD | Georgios Vidalakis |  | Scott Donnell | 8 |  |  | FALSE | 15000 |  | 44085 | Contracting | 44197 | 44228 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-01
18P000214 |  | 18P000214 | FALSE | VC-STU AFF | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Install Card readers | HEALTH SERV |  | IN PROGRESS | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  | 2 | 2 | FALSE |  |  | 43077 | [6 empty] | 9/30/20, DL: Vendor should have the balance of the material in the next 30- days…….8/5/20, DL: This project is complete except the card reader portion of the project…………6/17/20, DL: The floor covering was completed two weeks ago. The card reader portion of this project is 95% complete but additional parts were needed and they are on order. Once they arrive, we will schedule the installation and this project will be 100% Complete………1/15/20 Emailed Status Report to customer…..1/14/20, DL: We were recently approved to proceed with the work. I have reached out to the vendor for the doors and card access. We are still waiting to hear back from them so we can order the material and schedule the work. I communicated with Nicole on the floor covering replacement. Nicole needs to verify what areas we will replace as we were going to complete several offices and a hallway as part of the scope but this will displace many team members for at least a week. We will work on scheduling the work once Nicole gets back to me……..12/17/19 - O-DHN: Emailed Status Report to Customer……12/19/19, DL; We are working with our contractor to order the material and schedule the work. Once we have confirmation on the material, we will be able to schedule the work. It Is our goal to start this project in late January……11/26/19, DL: This project was taken off of on hold and we can now proceed. I contacted the contractor last week and I am awaiting their response on when they can schedule the work. I also left a message with them this morning………..7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once material arrives, we will schedule the installation.….5/31/19, DL; Contract is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is completed except the floor covering and electronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being prepped for paint. We have a pre-construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, material is ordered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct site visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez |  | YES |  | Winter 2018 | FS | FALSE | 2017 | 2021-01-01
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GH08 | 881 | IN PROGRESS | Kathryn Uhrich | TBD | NANCY FERGUSON |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43494 | [6 empty] | 8/5/20, DL: This project is in Progress and should be complete in the next 8-12 weeks…………….3/25/20, DL: Work orders are produced. Once we are back to work, we will schedule the work……...12/11/19 O-ANS: Re-assigned as project allotment - priority #7 for Winter 2020. 11/27/19 O-ANS: Hold by client for re-prioritization for Winter 2020. | 2020-03-04 | Ron Veloz | Install new 3 ton Packaged unit with heat pump and dedicated electrical service on the roof top. Provide 1ea return plenum, 2ea supply drops in the work space. | YES |  | Winter 2020 | FS | FALSE | 2019 | 2021-01-01
19P000485 |  | 19P000485 | FALSE | CNAS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | CHAPMAN | 9 | IN PROGRESS | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43494 | [6 empty] | 9/30/20, DL: Fume Hood demolition and abatement will be completed on 10/2/20. Fume hood install should be coplete in mid Novemeber……8/5/20, DL: We will submit plans this week. Once plans are approved, we will schedule the work……………Work orders are produced. We need to work on plans and permits once we return.. | 2020-02-10 | Ron Veloz | Disconnect, cap and safe off the existing utility services. Provide the necessary abatement services to properly remove the fume hood from the site and deliver to the campus surplus yard. Install one new department furnished fume hood. Abatement Services: Provide the necessary abatement services to perform all utilities disconnections and floor repair. Floorcovering: Patch and or repair as necessary to match or provide a close match. Install rubber base. Access Control: Survey and adjust the entry door closer to increase latch pull to allow the door to closer completely. Patching and painting: Patch and paint wall at the old fume hood location. Mechanical: Disconnect metal duct, cap/safe off, reconnect/reconfigure new duct to accommodate the new fume hood. Electrical: Provide electrical disconnections and safe off. Reconnect/reconfigure power to the new fume hood. Plumbing: Disconnect Air, Gas, Vacuum, Cold water, and Drain, cap and safe off and reconnect/reconfigure service to the new fume hood. Resource Management: Properly remove the fume hood from the site and deliver to the campus surplus yard. | YES |  | Spring 2020 | FS | FALSE | 2019 | 2021-01-01
20P000026 |  | 20P000026 | FALSE | VC-RED | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | Install T-bar ceiling, Provide HVAC and Fire sprinklers drops. Install new 2x4 LED light fixtures | LIFE SCIENCE | Basement Level | IN PROGRESS | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43665 | [6 empty] | 9/30/20, DL: The plans were submitted two weeks ago. We should receive the plan check review comments in the near future…………….8/5/20, DL: This Project will exceed $50,000. Monty A. will inform customer this is a project that will need to be managerd through PD&C……………3/25/20, DL: We will work on plans when we return back from the campus closure. | 2020-01-31 | Ron Veloz | Install T-bar ceiling with wipable(coated) ceiling tile. Provide HVAC and new Fire sprinklers drops to new ceiling. Install new 2x4 LED light fixtures. Verify Fire alarm systems work. | YES |  | Fall 2019 | FS | FALSE | 2019 | 2021-01-01
20P000144 |  | 20P000144 | FALSE | CNAS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A | BOYCE | 3432, 3432A, 3446, 3446A | IN PROGRESS | Kathryn Uhrich | TBD | MATTHEW ULRICH | CHERYL GERRY | Dan Lerman |  | 3 |  | FALSE |  |  | 43734 | [6 empty] | 9/30/20, DL: WE have started a few items but we are waiting on Matt U. and the PI to remove their items so we can have access to the space. Once the space is cleared out, we will proceed with the work…………8/5/20, DL: We will start the work in the next 4-6 weeks. | 2020-02-18 | Ron Veloz | Boyce 3432, 3446, 3436 and 3436A . Patch and paint 3432, 3432A, 3436, 3436A, 3446, 3446A. Reface/replace water damaged cabinets near sink (3446). Install GCFI outlets near sink (replace existing) (3446). Install panel cover for electrical panel box. Replace many burnt out bulbs in ceiling lamps. Replace broken chemical plexi-glass on bench shelves. | YES |  | Winter 2020 | FS | FALSE | 2019 | 2021-01-01
20P000208 |  | 20P000208 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | Men's locker room refresh | ATH DANCE | 50 | IN PROGRESS | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND | EUGENE HUTCHINSON | Dan Lerman |  | 1 |  | FALSE |  |  | 43773 | [6 empty] | 9/30/20, DL: The work is complete except for the paint……………..8/5/20, DL: The work is almost complete.……. |  | Dan Lerman |  |  |  | Winter 2020 | FS | FALSE | 2019 | 2021-01-01
20P000215 |  | 20P000215 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | Remove Vaughan wall seperating Olmsted 3349/3351.Add 4 single gang outlets and 2, 2gang outlets. | PSYCHOLOGY1 | 3rd Floor | IN PROGRESS | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43776 | [6 empty] | 9/30/20, DL: Plans were approved, we had the Vaughn Wall tested for Asbestos containing material. Once we have the results, we will schedule the work………….8/5/20, DL: We will submit plans by this Friday for a building permit | 2020-02-24 | Enrico Baez | 2/24/2020 E. Baez - 1.Remove Vaughan wall and electrical circuit in wall. 2. Add 4 Single Gan outlets and 2, 2gang outlets. 3. Patch vinyl plank flooring from removed wall and safe. 4. Remove panel in 2249 with wall paper on it next to window. 5. Remove handle set to 3351, install blank, render door inoperable. 6. Repair T-Bar ceiling as needed. 7. Patch and paint walls. 8. Coordinate with ITS for data line for 8 computers. | YES |  | Winter 2020 | FS | FALSE | 2019 | 2021-01-01
20P000221 |  | 20P000221 | FALSE | BCOE | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | IN PROGRESS | Christopher Lynch | TBD | HONG XU | KEVIN FREEDMAN | Dan Lerman |  | 3 |  | FALSE |  |  | 43784 | [6 empty] | 9/30/20, DL: We are in the process of finishing up a few other projects. Once they are complete, we will schedule the work….8/5/20, DL: Plans are approved and we will start the work in the next 2-6 weeks…….. | 2020-02-25 | Ron Veloz | Install Plywood and supports. Paint Plywood black. | YES |  | Winter 2020 | FS | FALSE | 2019 | 2021-01-01
20P000230 |  | 20P000230 | FALSE | VC-RED | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | Install Ceilings, Widen Door & Extend Utilities | BOURNS | B116C & B116D | IN PROGRESS | Rodolfo Torres | Laura Manor | KRASSIMIR BOZHILOV | LAURA MANOR | Dan Lerman |  | 1 |  | FALSE |  |  | 43787 | [6 empty] | 9/30/20, DL: This project is in progress and 50% complete. We should be complete with in the next 4-6 weeks…………...8/5/20, DL: We will submit plans in the next week………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We will start working on the plans and apply for a building permit in the next 2-3 weeks. | 2020-01-23 | Ron Veloz | Install new T-bar ceilings, lighting/switches, verify electrical service/disconnect. Relocate the existing eye washer, widen the exiting door opening and *reverse swing(*if approved by F.M). Install one customer furnished transformer. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000247 |  | 20P000247 | FALSE | CNAS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | Refresh Lab: Patch paint, strip & clean floor, repair broken ceiling and floor (VCT) tiles at room 2110 & 2118. Install Electrical power & Co2 cylinder racks at each end of workbench/tables | SPIETH | 2110 + 2118 | IN PROGRESS | Kathryn Uhrich | TBD | ESTELLA DAVALOS | SHERICE UNDERWOOD | Dan Lerman |  | 6 |  | TRUE |  |  | 43796 | [6 empty] | 9/30/20, DL: This project is in progress and will be compete in the next 6- 8 weeks……………8/5/20, DL: We will start on this project in the next 6-8 weeks….. | 2020-04-17 | Ron Veloz | Spieth 2110: Carpentry: Seismic anchoring for “New” tables and equipment. Replace damaged ceiling tiles. Install misc. wall mounted items. Sheet Metal: Remove “existing” steel cage. Fabricate & install metal cylinder rack w/ restrains/seismic anchoring to floor. Plumbing: Install Co2 POC for gas cylinders at four (4ea) new free-standing work benches (see configuration on this document). Electrical: Install dedicated *120v power drop & connect to the existing power strips built-in the four (4ea) new workstation tables (see configuration on this document). *VERIFY/CONFIRM VOLTAGE W/ D. MCW. Relamp fixtures as needed. Spieth 2118 & 2110: Sheetmetal: Clean and or replace air distribution grilles. Flooring: Repair/patch broken floor tile and Replace broken ceiling tiles (abate floor tiles if required). Painting: Paint and patch all walls, verify recondition doors @ room side. Plumbing: Assess sinks to be fully operational & clean. *Replace sink in Rm 2118 for glassware, confirm with Faculty/Estella. Replace sink in room 2118 (Sink type TBD by Faculty). HVAC: Check lab air pressure is operational & proper pressure. Custodial: Strip and Wax floor, clean interior windows, wipe down doors and windowsills. EXCLUSIONS: Furnish, assemble, and install new workstations, tables or lab equipment. Removal of existing lab furniture or equipment. Natural gas or air output taps not required (per Faculty). | YES |  | Winter 2020 | FS | FALSE | 2019 | 2021-01-01
3604 | 3604 |  | FALSE | PB&A | Madison Farm Acquisition | Purchase of a 21.14 acre property with 42 shares of gage canal water for Agricultural Operations. Property is located at 2350 & 2450 Madison Ave., Riverside (between Victoria & Cleveland, approximately 7 miles SW of UCR campus). |  |  | New (12/15/20) | Gerry Bomotti | TBD | Tom Toepfer |  | Thomas Toepfer |  |  |  | FALSE | 1875000 |  | 44180 | New (12/15/20) | [12 empty] | PD&C | FALSE | 2020 | 2021-01-01
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | SOCCER FIELD AND AREA |  | On Hold | Tamica Smith Jones | Eugene Hutchinson | Joe Erbland |  | Gerald Caraig | 3 |  |  | FALSE | 0 |  | 41739 | Need direction by PM Director | [12 empty] | PD&C | FALSE | 2014 | 2021-01-01
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | On Hold | Rodolfo Torres | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Daneca Stevens | 1 |  |  | FALSE | 45000 |  | 42899 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-01-01
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 16 |  |  | FALSE | 0 |  | 43072 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-01-01
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Eugene Hutchinson | Johnathan Jensen |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 43335 | Department approval to move fwd | [12 empty] | PD&C | FALSE | 2018 | 2021-01-01
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 17 |  |  | FALSE | 0 |  | 43297 | Coordinating with North District | [12 empty] | PD&C | FALSE | 2018 | 2021-01-01
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. | RIVERA LIB |  | On Hold | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 43431 | Client approval/funding | [12 empty] | PD&C | FALSE | 2018 | 2021-01-01
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 11 |  |  | FALSE | 1500000 |  | 43775 | On Hold | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 43809 | Departmental Approval | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3594 | 3594 |  | FALSE | CNAS | R'Garden Grow Pod Installation | R'Garden Gro Pod Installation |  |  | On Hold | Kathryn Uhrich | TBD | Richard Zapien |  | Scott Donnell | 7 |  |  | FALSE |  |  | 43972 | Secure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-01-01
2989 | 2989 |  | FALSE | ATHLETICS | Dance - Locker Room Remodel | We are requesting to utilize Base Architecture, Planning, & Engineering, Inc. to provide pro bono work on planning for locker room renovations in the Athletics & Dance Building. Rob Gayle is aware of our desire to utilize this company for services. |  |  | On Hold (COVID-19) | Tamica Smith Jones | Eugene Hutchinson | Joseph Erbland |  | Tameesha Hayes | 99 |  |  | FALSE | 28395 |  | 42327 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2015 | 2021-01-01
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | On Hold (COVID-19) | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 43273 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2018 | 2021-01-01
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | On Hold (COVID-19) | Brian Haynes | Cathy Eckman | Christina Wong |  | Tameesha Hayes | 2 |  |  | FALSE | 130000 |  | 43543 | On hold (COVID-19) | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 42886 | Department Approval/Funding | [12 empty] | PD&C | FALSE | 2017 | 2021-01-01
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Richard Geiger |  | John Franklin | 7 |  |  | FALSE | 0 |  | 43178 | CIB Approval | [12 empty] | PD&C | FALSE | 2018 | 2021-01-01
3286 | 3286 |  | FALSE | PB&A | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | Phase 2 Design | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 12 |  |  | FALSE | 3375000 |  | 42823 | Phase 2 Bidding | 44197 | 44287 | [10 empty] | PD&C | FALSE | 2017 | 2021-01-01
2899 | 2899 |  | FALSE | PB&A | Pierce Hall Improvements | Replacement of Mechanical, Plumbing and Electrical Infrastructure | PIERCE |  | Phase I in Construction | Gerry Bomotti | TBD | Jon Harvey |  | Gerald Caraig | 18 |  |  | FALSE | 38560000 |  | 42222 | Phase I Completion | 43466 | 44197 | [10 empty] | PD&C | FALSE | 2015 | 2021-01-01
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install electrical utilities for new equipment | PHYSICS | 1132 | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43543 | [6 empty] | 9/30/20, DL: Plans were submitted for Plan Check review last week and we should have an update on the plan check review process soon………..8/5/20, DL: Need to meet with Kirk to verify electrical load. Once confirmed, we will work on plans for a permit | 2019-10-15 | Ron Veloz | Install utilities for new equipment | YES |  | Summer 2019 | FS | FALSE | 2019 | 2021-01-01
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 20 |  |  | FALSE | 1250000 | 0 | 43390 | FS Direction | [12 empty] | PD&C | FALSE | 2018 | 2021-01-01
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 44091 | Begin RFQ Process | [12 empty] | PD&C | FALSE | 2020 | 2021-01-01
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair/Replacement | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | Pre-Programming | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 8 |  |  | FALSE |  |  | 44095 | Design | [12 empty] | PD&C | FALSE | 2020 | 2021-01-01
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns Hall A Interior Finishes |  |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Programming | [12 empty] | PD&C | FALSE | 1900 | 2021-01-01
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Scott Donnell | 10 |  |  | FALSE | 65000 |  | 43528 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3523 | 3523 |  | FALSE | PB&A | 1907 Mt Rubidoux Facility Study | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. |  |  | Programming (Study) | Gerry Bomotti | TBD | Melissa Garrety |  | Scott Donnell | 3 |  |  | FALSE |  |  | 43577 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
19P000517 |  | 19P000517 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | PROJECT INTAKE | LaRae Lundgren | TBD | DANIELLE GARCIA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43531 | [6 empty] | 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced, We will schedule the work when we return from the campus closure…………11/11/19, DL: I will work on scheduling this project… | 2019-06-17 | Enrico Baez | 6/17/19 E. Baez Conducted site visit with Sean. Will need carpenters to mount TV and electricians to add outlet to North wall. Data not needed. Might need painters depending on how carpenters install TV mount. | YES |  | FALL 2019 | FS | FALSE | 2019 | 2021-01-01
20P000003 |  | 20P000003 | FALSE | GRAD DIV | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | ADD POWER/DATA, PATCH/PAINT | UNIV OFC BLD |  | PROJECT INTAKE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS | CHERYL GERRY | Dan Lerman |  | 1 |  | FALSE |  |  | 43648 | [6 empty] | 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Permit is approved. We need to verify floor covering. Once floor covering is confirmed and ordered, we will schedule the work………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We will need plans as we are installing a new hydration station and a Counter top that needs to be ADA compliant…………We started the plans and will submit them for a permit and plan check review within 2- weeks……….10/30/19, DL: No Plans will be needed. We will plan on scheduling the work shortly after Thanksgiving……. | 2019-06-13 | Enrico Baez | 9/24/2019 E. Baez--SCOPE-- 1. Removal and disposal of one bulletin board and two director cases. 2. Removal and disposal of abandoned telephone mounting bracket. 3. Remove and dispose of abandoned alarm box in wall. 4. Patch and paint walls in lobby and public restroom area. 5. Provide electrical connection for wall mounted monitor. 6. Cut access for data boxes. 7. Install monitor mount on wall. 8. Construct 7" x 18" laminate counter top and install in Lobby. | YES |  | FALL 2019 | FS | FALSE | 2019 | 2021-01-01
20P000046 |  | 20P000046 | FALSE | CNAS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN | 0001 | PROJECT INTAKE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43677 | [6 empty] | 11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Install wireless access controls systems at front and rear entry doors. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01 |  | 1
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | COSTO HALL |  | PROJECT INTAKE | Brian Haynes | Cathy Eckman | Manny Sanchez |  | Dan Lerman |  | R1 | R2 | FALSE |  |  | 43762 | [6 empty] | 11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01 |  | 1
20P000211 |  | 20P000211 | FALSE | CHASS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | Install keyless entry system for door to Arts Building RM 54 | ARTS | 54 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 | R3 | FALSE |  |  | 43776 | [6 empty] | 11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment installation. 8/5/20, DL: This Project is on hold until further notice……. | 2020-01-20 | Enrico Baez | Provide new panel, power supply and door hardware for 2 doors. Prox reader only. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01 |  | 1
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | BOURNS | B0328E | PROJECT INTAKE | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | R1 | R1 | FALSE |  |  | 43774 | [6 empty] | 11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01 |  | 1
20P000218 |  | 20P000218 | FALSE | VC-RED | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | VIVARIUM UPDATE AIR COMPRESSOR | SPIETH | 347 | PROJECT INTAKE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | DAN LERMAN |  | 2 | R2 | FALSE |  |  | 43602 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Cinvert Basement Library into Piano Lab | ARTS | 54 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 43788 | [6 empty] | 11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks……….. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01
20P000248 |  | 20P000248 | FALSE | CNAS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT |  | WEBBER | 1223 + 1223-A | PROJECT INTAKE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS | SHARYL MURDOCK | Dan Lerman |  | 5 | 4 | FALSE |  |  | 43796 | [6 empty] | 11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….02/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Survey space for hazardous material. Once survey is complete, we will schedule abatement and the work. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01
20P000253 |  | 20P000253 | FALSE | BCOE | SL5 BOURNS HALL LAB B256 - EXHAUST SYSTEM | EXHAUST SYSTEM | BOURNS | B0156 | PROJECT INTAKE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 43810 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS | 245 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | ANDREA HIDALGO |  | DAN LERMAN |  | 3 |  | FALSE |  |  | 43832 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB | ARTS | 150 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 43844 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000320 |  | 20P000320 | FALSE | CNAS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | ACTIVATE VACUUM LINES | SPIETH | 1303 | PROJECT INTAKE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | DAN LERMAN |  | 4 |  | FALSE |  |  | 43789 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | PIERCE | 2232A | PROJECT INTAKE | Kathryn Uhrich | TBD | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 43852 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000366 |  | 20P000366 | FALSE | CNAS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | MINOR LAB RENOVATION | SPIETH | 2375 / 2375-A | PROJECT INTAKE | Kathryn Uhrich | TBD | SHERICE UNDERWOOD |  | DAN LERMAN |  | 7 |  | TRUE |  |  | 43880 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000370 |  | 20P000370 | FALSE | CHASS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | SPACE RENOVATION PROJECT | WATKINS | 1311 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 43880 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000445 |  | 20P000445 | FALSE | CNAS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY | 279 | PROJECT INTAKE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | DAN LERMAN |  | 2 |  | TRUE |  |  | 43985 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20S027621 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | PROJECT INTAKE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Dan Lerman |  | R1 |  | FALSE |  |  | 44008 | [8 empty] | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01 |  | 1
21P000001 |  | 21P000001 | FALSE | CNAS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | NEW GROWTH CHAMBER PLACEMENT | FAWCETT LAB |  | PROJECT INTAKE | Kathryn Uhrich | TBD | LINDA WALLING |  | DAN LERMAN |  | 3 |  | TRUE |  |  | 43990 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
21P000009 |  | 21P000009 | FALSE | CNAS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | GLOVEBOX SYSTEM | CHEM SCI |  | PROJECT INTAKE | Kathryn Uhrich | TBD | NATASHA GONZALES |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 44020 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MAT SCI ENGR | 71 | PROJECT INTAKE | Christopher Lynch | TBD | XI CHEN |  | DAN LERMAN |  | 3 |  | FALSE |  |  | 44049 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
21P000078 |  | 21P000078 | FALSE | VC-RED | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MRB |  | PROJECT INTAKE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 44097 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS |  | PROJECT INTAKE | Kathryn Uhrich | TBD | JOSE WUDKA |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 43818 | [8 empty] | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01 |  | 1
21S000997 |  | 21P000019 | FALSE | BCOE | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | Bourns Office A305 - Install Plank Floor Please remove old damaged carpet and install new plank floor. Match with that of the ME suite (same floor). Thank you. Note: Current PI has not moved out. We will contact Facilities once date is known and all items have been removed from the room. Questions: ME Department Manager (Interim) - William Bingham - bill@ece.ucr.edu , or Robert Lopez lopezra@engr.ucr.edu | BOURNS | A305 | PROJECT INTAKE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | 2 |  | TRUE |  |  | 44032 | [8 empty] | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | 44197 | 44317 | [10 empty] | PD&C | FALSE | 1900 | 2021-01-01
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | TBD | Richard Geiger |  | D.Hecht/J.Franklin | 21 |  |  | FALSE | 0 |  | 43007 | Project pushed to 2021 | [12 empty] | PD&C | FALSE | 2017 | 2021-01-01
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 43920 | Projects to be assigned | [12 empty] | PD&C | FALSE | 2020 | 2021-01-01
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT REMOVE DOOR | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. Request removal of interior access door and drywall to remove access to office 3011. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS | 3009 | Queue to Start | Kathryn Uhrich | TBD | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 43749 | [6 empty] | 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure. | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | Queue to Start | Kathryn Uhrich | TBD | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 43794 | [6 empty] | 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-01
20P000310 |  | 20P000310 | FALSE | BCOE | SL5 BOURNS A-WING A129 - PATCH & PAINT | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. | BOURNS | A0129 | Queue to Start | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43840 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000363 |  | 20P000363 | FALSE | BCOE | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | Paint Only | CHUNG HALL | 433 | Queue to Start | Christopher Lynch | TBD | MANGLAI ZHOU | FARIBORZ KARGAR | PAUL DITTY |  | X |  | TRUE |  |  | 43874 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000419 |  | 20P000419 | FALSE | CNAS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | Paint Only | SPIETH | 2312 | Queue to Start | Kathryn Uhrich | TBD | ESTELLA DAVALOS | SHERICE UNDERWOOD | PAUL DITTY |  | X |  | TRUE |  |  | 43943 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000446 |  | 20P000446 | FALSE | CHASS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. | CHASS INT N | 4047 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 43986 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000449 |  | 20P000449 | FALSE | BCOE | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | Paint Only - Chung Hall, Fourth Floor, Room 461 Patch & Paint: At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. Follow up with fresh paint. Thank you. | CHUNG HALL | 461 | Queue to Start | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43993 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000453 |  | 20P000453 | FALSE | CHASS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | Paint Only - Please patch/paint to existing color office for faculty new hire. | ARTS | 142 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000463 |  | 20P000463 | FALSE | CHASS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 | HUM & SOC SC | 2000 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000464 |  | 20P000464 | FALSE | CHASS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) | HUM & SOC SC | 3001 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000467 |  | 20P000467 | FALSE | SOM | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. | WEBBER | 1247 | Queue to Start | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | CYNTHIA CAROLINA | PAUL DITTY |  | X |  | TRUE |  |  | 44001 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000468 |  | 20P000468 | FALSE | VC-RED | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | Paint Only | SPIETH | 364 | Queue to Start | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 44005 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000469 |  | 20P000469 | FALSE | CHASS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. | ARTS | 222 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | SUSAN KOMURA | PAUL DITTY |  | X |  | TRUE |  |  | 44005 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUM & SOC SC | 3210 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44006 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
20S023644 |  | 20P000403 | FALSE | CHASS | SL5 OLMSTED 232 - PAINT OFFICE | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). | OLMSTED | 2321 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | MELISA VICARIO | Paul Ditty |  | TBD |  | TRUE |  |  | 43903 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
21P000037 |  | 21P000037 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | Paint Only | CHUNG HALL | 427 | Queue to Start | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44043 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
21P000079 |  | 21P000079 | FALSE | VC-RED | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. | PSYCHOLOGY1 |  | Queue to Start | Rodolfo Torres | Laura Manor | LESLIE KARPINSKI |  | PAUL DITTY |  | X |  | FALSE |  |  | 44099 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
21S008231 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Dr. Robert Clark. He started working July 1, 2020. | WATKINS | 1146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | TBD |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
21s008232 |  | 21P000110 | FALSE | CHASS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. | WATKINS | 2146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | TBD |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
21S008233 |  | 21P000111 | FALSE | CHASS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. | WATKINS | 2144 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | TBD |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-01
3119 | 3119 |  | FALSE | CAP PROG | Plant Growth Environment Facility | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. |  |  | Relocation/Move-in | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 6 |  |  | FALSE | 27425000 |  | 42515 | Commisioning | 43617 | 44157 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-01
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | Re-scope | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 3 |  |  | FALSE | 1340000 |  | 43600 | Re-scope/Re-bid | 44287 | 44440 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-01
3505 | 3505 |  | FALSE | FAC-PLNG-DESIGN-CONST | Orange County Psychiatry | UCR Health will be acquiring new off-campus leased space by moving into an adjacent medical office suite located at The Airport Tower, 18881 Von Karman Ave #1227, Irvine, CA 92612. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. | 18881 VONKAR |  | SOM to manage project | Susan Marshburn | Da Lan Dinh | Brandon Barbosa |  | ---- | 15 |  |  | FALSE |  |  | 43515 | SOM to manage project-need PM | [12 empty] | PD&C | FALSE | 2019 | 2021-01-01
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 19 |  |  | FALSE | 916581 |  | 43410 | Complete Review | [12 empty] | PD&C | FALSE | 2018 | 2021-01-01
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | CANCELED BY FS | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | R7 |  | FALSE |  |  | 43523 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced. We will schedule the work when we return from campus closure………11/11/19, DL: Project is in the queue to start but we do not have an FAU# as this is a recharge project. I sent Enrico and James an email requesting the FAU#. Once we have an FAU #, I will work on scheudling the work…..10/1/19, DL; Enrico is wtill working on estimate. | 2018-10-19 | Enrico Baez | E. Baez 1. Provide power in ceiling for projector. 2. Install projector center in room between two 4ft light fixtures. 3. Install 2 duplex outlets in 4S box on South West corner of room 4. Remove existing screen. 5. Install new screen centered on South wall. Extend power from existing screen to new screen location. 6. Use existing screen power switch to control new screen. | YES | 2020-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21 | 1
19P000624 |  | 19P000624 | FALSE | BCOE | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | Refurbish Room-Student Space, | BOURNS | A0346 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43600 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Susanna is working on a cubicle layout. Once we have the information from her. We will schedule the work………… | 2019-11-07 | Ron Veloz | Remove all lower cabinets in room A0346 and all lower cabinets and mail boxes in Rm A0304 | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000039 |  | 20P000039 | FALSE | BCOE | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE |  | BOURNS | A0318 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43598 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……..09/19/19 O-ANS: HOLD FOR WINTER 2020 PER CUSTOMER (LOUIS SANDOVAL) REQUEST. EMAILED PAUL DITTY TO CONFIRM. PAUL STATED THIS IS NON-PAINT PROJECT B/C SCOPE OF WORK INCLUDES CARPENTERS AND ELECTRIC SHOPS. |  | Paul Ditty |  |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000047 |  | 20P000047 | FALSE | VC-RED | SL5 ADVANCED NEUROIMAGING | NEEDING TO TAKE DOWN OVERHEAD CABINETRY AND REPLACE WITH SOME KIND OF SHELVING TO OPTIMIZE SPACE. LOOKING FOR AN ESTIMATE AND A PLAN. | ADV NEURO |  | CANCELED BY FS | Rodolfo Torres | Laura Manor | CHELSEA EVELYN |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43677 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice…….3/23/20, DL: Shelves are ordered. We will schedule the work when we return from the campus closure……….1/15/20 O-DHN: Emailed Status Report to customer…...1/14/20, DL: We waiting for a revised quote from the vendor as there quote was not complete. We will process the quote for a PO# when we receive the correct quote……. 11/11/19, DL: Need to review scope with Ron as the shelving system is a special order item with a 3- month lead time….. | 2019-09-24 | Ron Veloz | Remove 5'-0" x3'-0" upper cabinet, and soffits. Patch and paint walls to match the existing grey . Install customer furnished adjustable shelf. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000183 |  | 20P000183 | FALSE | CHASS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | Install side walk | HUM & SOC SC | 1202 | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43756 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Also Existing door is compliant and there are other accessible exits to the building… 8/5/20, DL: This Project is on hold until further notice……. | 2019-11-13 | Enrico Baez | Construct Side walk. ADA compliance not required. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21 | 1
20P000188 |  | 20P000188 | FALSE | LIBR | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 |  | ORBACH LIB | 204 | CANCELED BY FS | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43761 | [6 empty] | 11/19/20 O-ANS: Declined to move forward by FS Admin but may revisit in future prioritization period. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: We are working on floor covering samples that will work for the space. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000197 |  | 20P000197 | FALSE | VC-RED | SL5 UOB 210 - SOUND PROOF INSTALLATION |  | UNIV OFC BLD | 210 | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43762 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000210 |  | 20P000210 | FALSE | BCOE | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | Reduce noise. Replace doors with solid core doors and install an Acoustic Door Seal Kit. | CHUNG HALL | 224 | CANCELED BY FS | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43774 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……. | 2020-02-11 | Ron Veloz | Removal of the existing double doors and door hardware, install new solid core double doors with continuous hinges, install new acoustical jamb seals, threshold seal and a surface mounted Automatic Door Bottom utilizing a flat spring mechanism, which activates when closing the door, lowering a neoprene seal insert against the floor or threshold to create a sound seal. Install acoustic double door astragals with seal. Reinstall all existing door locksets, and door closers. Quote received from Brad Aduddell-American Door to perform this work. Quote & Specs are available in the project folder. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB. Patch Paint walls, replace flooring, refinish wood cabinets and sinks. | SPIETH | 2349 | TO BE PERFORMED BY PD&C | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43516 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold……….12/11/19: O-ANS: Reassigned as project allotment - priority #5 for Winter 2020. 11/27/19 O-ANS: Placed on Hold for re-prioritization by client for Winter 2020. | 2020-02-27 | Ron Veloz | Patch and paint and extra work to upgrade an old lab that we are now inhabiting. In addition to painting, we need to have floors re-surfaced, cabinets re-stained, and counter tops re-surfaced, if possible. There is also a metal sink that could be polished. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-01 | FY 20-21
20P000067 |  | 20P000067 | FALSE | BCOE | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM | BOURNS | B-Wing | TO BE PERFORMED BY PD&C | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | R1 |  | FALSE |  |  | 42688 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold until further notice……. |  | Ron Veloz | Replace access controls at BCOE WCH & Bourns bldgs. |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2016 | 2021-01-01 | FY 20-21 | 1
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | Modify the existing room in Soil House 1 (attached to the Delphino Lab at the Rubidoux Facilities) to expand CCPP quarantine services to include USDA/CDFA compliance for installation of new Economic Development Administration (EDA) citrus growth chambers. | DELFINO HHSE |  | TO BE PERFORMED BY PD&C | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 43245 | [6 empty] | 12/7/20, DL: This project will be managed by PD&C…..9/30/20, DL: Project is still on Hold until Furhther notice………...8/5/20, DL: WE will work on plans in the next 30- 45 days……………6/17/20, DL: This project is under review and is on hold until further notice………10/3/19 O-ANS: Plan Development per Minor Reno Meeting. 10/1/19,DL; We are getting ready to start the plans as we are currently conducting resarch on products that will meet the needs of the space……………..5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman |  | YES | 2020-12-07 | Summer 2018 | FS | FALSE | 2018 | 2021-01-01 | FY 20-21
21S007221 |  | 21P000102 | FALSE | VC-RED | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | AAALAC Certification updates to rooms 348, 352 & 363 | SPIETH | 348, 352 & 363 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS | YURIDIA REYNOSO | Paul Ditty |  | TBD |  | FALSE |  |  | 44133 | [6 empty] | 12/08/20 O-ANS: Customer Dierk Biggs confirmed via email that these room updates are complete. |  | Paul Ditty |  |  | 2020-12-08 | Winter 2021 | FS | FALSE | 2020 | 2021-01-01 | FY 20-21
20P000309 |  | 20P000309 | FALSE | VC-UNIV ADV | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES |  | 1955 CHICAGO | 200 | CANCELED BY FS | Peter Hayashida | Naysia Caldwell | SARAH KARSON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43840 | [6 empty] | 12/16/20 O-ANS: Canceled by FS - Project location not serviced as FS CORE location and reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Please retain project # as reference. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  | 2020-12-16 | Spring 2020 | FS | FALSE | 2020 | 2021-01-01 | FY 20-21
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | Katie Sanchez |  | Gerald Caraig | 20 |  |  | FALSE | 2600000 |  | 42509 | Funding & Approval | [12 empty] | PD&C | FALSE | 2016 | 2021-01-16
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Rivera Library Arches/Arcade Repair | Paint and replace roof. | RIVERA LIB |  | Bids received, award on hold due to DM funding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Scott Donnell | 99 |  |  | FALSE | 240000 |  | 42496 | Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-01-16
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 6 |  |  | FALSE | 600000 |  | 43634 | Complete Construction | 44166 | 44344 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | SOCCER FIELD AND AREA |  | On Hold | Tamica Smith Jones | Eugene Hutchinson | Joe Erbland |  | Gerald Caraig | 3 |  |  | FALSE | 0 |  | 41739 | Need direction by PM Director | [12 empty] | PD&C | FALSE | 2014 | 2021-01-16
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Commencing Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Rowan Reid | 1 |  |  | FALSE | 1150000 |  | 42719 | Completion of Basis of Design | [12 empty] | PD&C | FALSE | 2016 | 2021-01-16
2899 | 2899 |  | FALSE | PB&A | Pierce Hall Improvements | Replacement of Mechanical, Plumbing and Electrical Infrastructure | PIERCE |  | Phase I in Construction | Gerry Bomotti | TBD | Jon Harvey |  | Gerald Caraig | 18 |  |  | FALSE | 38560000 |  | 42222 | Phase I Completion | 43466 | 44197 | [10 empty] | PD&C | FALSE | 2015 | 2021-01-16
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | In Bidding (prequalification) | Gerry Bomotti | TBD | Sharyl Murdock |  | Rowan Reid | 16 |  |  | FALSE | 26329342.06 |  | 42353 | Start Construction | 44197 | 45139 | [10 empty] | PD&C | FALSE | 2015 | 2021-01-16
2952 | 2952 |  | FALSE | CAP PROG | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jon Harvey |  | Gerald Caraig | 13 |  |  | FALSE | 23895000 |  | 42258 | Phase I Completion | 43467 | 44317 | [10 empty] | PD&C | FALSE | 2015 | 2021-01-16
2989 | 2989 |  | FALSE | ATHLETICS | Dance - Locker Room Remodel | We are requesting to utilize Base Architecture, Planning, & Engineering, Inc. to provide pro bono work on planning for locker room renovations in the Athletics & Dance Building. Rob Gayle is aware of our desire to utilize this company for services. |  |  | On Hold (COVID-19) | Tamica Smith Jones | Eugene Hutchinson | Joseph Erbland |  | Tameesha Hayes | 99 |  |  | FALSE | 28395 |  | 42327 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2015 | 2021-01-16
3064 | 3064 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Botanic Gardens Basin Silt Removal | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | BOTAN INFO C |  | In Funding | Susan Marshburn | Da Lan Dinh | Toshio Ishida |  | Scott Donnell | 29 |  |  | FALSE | 110000 |  | 42480 | Decision Memo | [12 empty] | PD&C | FALSE | 2016 | 2021-01-16
3104 | 3104 |  | FALSE | PALM DESERT GRAD CTR | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Funding | Tamara Hedges | Zelda Glenn | Zelda Glenn |  | Scott Donnell | 2 |  |  | FALSE | 22000 |  | 42502 | Approval & Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-01-16
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | 44197 | 44317 | [10 empty] | PD&C | FALSE | 1900 | 2021-01-16
3119 | 3119 |  | FALSE | CAP PROG | Plant Growth Environment Facility | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 6 |  |  | FALSE | 27425000 |  | 42515 | Commisioning | 43617 | 44197 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-16
3195 | 3195 |  | FALSE | FAC-PLNG-DESIGN-CONST | North District | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 4146146.55 |  | 42669 | Complete Construction | 43647 | 44409 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-16
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Programming | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 22 |  |  | FALSE |  |  | 42653 | Design | [12 empty] | PD&C | FALSE | 2016 | 2021-01-16
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 15690389.32 |  | 42720 | Bidding | 44287 | 44470 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-16
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Bidding | Jacqueline Norman | Sharyl Murdock | John White |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 42725 | Award Contract | 44228 | 44317 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-16
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 42886 | Department Approval/Funding | [12 empty] | PD&C | FALSE | 2017 | 2021-01-16
3286 | 3286 |  | FALSE | PB&A | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | Bidding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 10 |  |  | FALSE | 3375000 |  | 42823 | Award Contract | 44228 | 44287 | [10 empty] | PD&C | FALSE | 2017 | 2021-01-16
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Mihai Gavan | 9 |  |  | FALSE | 57950000 |  | 42887 | Complete Construction | 43770 | 44409 | [10 empty] | PD&C | FALSE | 2017 | 2021-01-16
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | On Hold | Rodolfo Torres | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Daneca Stevens | 1 |  |  | FALSE | 45000 |  | 42899 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-01-16
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | TBD | Richard Geiger |  | D.Hecht/J.Franklin | 20 |  |  | FALSE | 0 |  | 43007 | Project pushed to 2021 | [12 empty] | PD&C | FALSE | 2017 | 2021-01-16
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Construction | Kathryn Uhrich | TBD | Tracey Kahn, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 1575000 |  | 43108 | Complete Construction | 44197 | 44287 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-16
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 14 |  |  | FALSE | 0 |  | 43072 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-01-16
3401 | 3401 |  | FALSE | CAP PROG | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | In Construction | Jacqueline Norman | Sharyl Murdock | Mihai Gavan |  | Fernando Canon | 12 |  |  | FALSE | 8754623.11 |  | 43072 | Complete Construction | 43952 | 44228 | [10 empty] | PD&C | FALSE | 2017 | 2021-01-16
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Eugene Hutchinson | Johnathan Jensen |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 43335 | Department approval to move fwd | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Richard Geiger |  | John Franklin | 6 |  |  | FALSE | 0 |  | 43178 | CIB Approval | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Funding | Christopher Lynch | TBD | Margaret Souder |  | Scott Donnell | 4 |  |  | FALSE | 700000 |  | 43194 | Secure Funding | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3438 | 3438 |  | FALSE | CAP PROG | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | City to determine schedule | Jacqueline Norman | Sharyl Murdock | Dave Bomba |  | Scott Donnell | 15 |  |  | FALSE | 88500 |  | 43334 | City to determine schedule | 44013 | 44287 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-16
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | On Hold (COVID-19) | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 43273 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 43297 | Complete Study | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 17 |  |  | FALSE | 0 |  | 43297 | Coordinating with North District | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 19 |  |  | FALSE | 315000 |  | 43312 | Bidding | 44317 | 44378 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-16
3467 | 3467 |  | FALSE | PB&A | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | Design - 3rd flr Walking Deck Only | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 17 |  |  | FALSE | 235000 |  | 43312 | Bidding | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-16
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 19 |  |  | FALSE | 916581 |  | 43410 | Complete Review | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3471 | 3471 |  | FALSE | VC-STU AFF | HUB Electrical Sub Meter Installation | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Design | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 200000 |  | 43332 | Bidding | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 43404 | CEQA | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 16 |  |  | FALSE | 1250000 | 0 | 43390 | FS Direction | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. | RIVERA LIB |  | On Hold | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 43431 | Client approval/funding | [12 empty] | PD&C | FALSE | 2018 | 2021-01-16
3490 | 3490 |  | FALSE | PB&A | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | Parking Lot 13 |  | In Construction | Gerry Bomotti | TBD | Irma Henderson |  | D.Hecht/J.Franklin | 25 |  |  | FALSE | 31844000 |  | 43440 | Complete Construction | 43862 | 44256 | [10 empty] | PD&C | FALSE | 2018 | 2021-01-16
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Scott Donnell | 10 |  |  | FALSE | 65000 |  | 43528 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 43510 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3501 | 3501 |  | FALSE | PB&A | DMFI(FY17-19) Watkins 1000 Lecture Hall Reno | Renovation of Watkins 1000 lecture hall, to include lighting, HVAC, flooring, paint, and seating upgrades. This requests appears as projects Q-T on the approved 2017-2019 DMFI Program list. | WATKINS |  | In Construction | Gerry Bomotti | TBD | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 750000 |  | 43528 | Complete Construction | 44013 | 44197 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3505 | 3505 |  | FALSE | FAC-PLNG-DESIGN-CONST | Orange County Psychiatry | UCR Health will be acquiring new off-campus leased space by moving into an adjacent medical office suite located at The Airport Tower, 18881 Von Karman Ave #1227, Irvine, CA 92612. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. | 18881 VONKAR |  | SOM to manage project | Susan Marshburn | Da Lan Dinh | Brandon Barbosa |  | ---- | 15 |  |  | FALSE |  |  | 43515 | SOM to manage project-need PM | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | Michelle Baniqued |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 43528 | DB Competition | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | Bidding | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 6950000 |  | 43528 | Award Contract | 44348 | 45047 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | Design | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 43528 | Bidding | 44287 | 44409 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | On Hold (COVID-19) | Brian Haynes | Cathy Eckman | Christina Wong |  | Tameesha Hayes | 2 |  |  | FALSE | 130000 |  | 43543 | On hold (COVID-19) | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Bidding Competition | Gerry Bomotti | TBD | Michelle Baniqued |  | Fernando Canon | 1 |  |  | FALSE | 33980000 |  | 43528 | Select Design Builder | 44470 | 45017 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3523 | 3523 |  | FALSE | PB&A | 1907 Mt Rubidoux Facility Study | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. |  |  | Programming (Study) | Gerry Bomotti | TBD | Melissa Garrety |  | Scott Donnell | 3 |  |  | FALSE |  |  | 43577 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3524 | 3524 |  | FALSE | VC-STU AFF | Student Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | STUDENT SERV |  | Design | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE | 450000 |  | 43571 | BKM Lead Time 10 Weeks | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | Re-design/Re-bid | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 3 |  |  | FALSE | 1340000 |  | 43600 | Re-scope/Re-bid | 44256 | 44440 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3533 | 3533 |  | FALSE | PB&A | Solar Rooftop Initiative | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. | MULTIPLE BUILDINGS |  | In Construction | Gerry Bomotti | TBD | Richard Geiger |  | John Franklin | 9 |  |  | FALSE | 2165000 |  | 43619 | Complete Construction | 44105 | 44256 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3535 | 3535 |  | FALSE | CHASS | Life Sciences 452 Renovation | This request is for a new faculty hire. -Remove north countertop and sink. Install stainless counter and two sinks. -Install eye wash station -Install laminate flooring, remove existing. (Abatement) -Paint space to campus interior standard. -Remove east counter and replace with stainless. -Remove fume hood, discard. -Install new fume hood. | LIFE SCIENCE | 452 | Construction | Juliet McMullin | Cindy Williams | Paul Richardson |  | Tameesha Hayes | 1 |  |  | FALSE | 133500 |  | 43656 | Complete Construction | 44105 | 44197 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | In Funding | Gerry Bomotti | Sharyl Murdock | Gerald Caraig |  | Daneca Stevens | 2 |  |  | FALSE | 50000 |  | 43676 | Secure Funding | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Programming | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 9 |  |  | FALSE | 500000 |  | 43713 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | In Programming | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 600000 |  | 43713 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3550 | 3550 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Skye Hall HVAC Replacement | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | SKYE HALL |  | In Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 1177000 |  | 43713 | Award Contract | 44256 | 44348 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3557 | 3557 |  | FALSE | CHASS | Campus Sculpture Installation | We will bring 5 sculptures to campus that will go in public places that have already been identified by Uma Ramasubramanian and Jacqueline Norman . Please construct 5 concrete plinths at various locations around campus. Locations are on the attachment. |  |  | Construction | Juliet McMullin | Cindy Williams | Emily Rankin |  | Tameesha Hayes | 3 |  |  | FALSE | 82000 |  | 43796 | Complete Construction | 44105 | 44228 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Design | Kathryn Uhrich | TBD | MaryLou Polek |  | Scott Donnell | 2 |  |  | FALSE | 2500 |  | 43742 | Construction by USDA | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3560 | 3560 |  | FALSE | CNAS | USDA Modular Bldg Installation | B19-284: Provide and install one (1) 1400 square foot double-wide modular office building with five (5) offices, one (1) being ADA compliant, one (1) ADA compliant unisex restroom, one (1) multi-purpose room with sink. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In construction by USDA | Kathryn Uhrich | TBD | MaryLou Polek |  | Scott Donnell | 3 |  |  | FALSE | 2500 |  | 43742 | Complete Construction (by USDA) | 44166 | 44197 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 1500000 |  | 43775 | On Hold | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 43809 | Departmental Approval | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3581 | 3581 |  | FALSE | SOM | SOMR Interior Egress Doors | All egress doors - Floors 1, 2, and 3 - need to be replaced with compliant structures. Please inspect, evaluate and provide quote. |  |  | In Pre-Programming | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 43894 | Design | [12 empty] | PD&C | FALSE | 2020 | 2021-01-16
3589 | 3589 |  | FALSE | CAP PROG | Various Bldgs LED Lighting Ph2 | LED Lighting Phase 2 - Package 1 - Replacing existing lamps to LED |  |  | In Design | Jacqueline Norman | Sharyl Murdock | David Palacios |  | Fernando Nunez | 15 |  |  | FALSE | 780545 |  | 43901 | Receive 100% CD's | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-16
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Programming | Kathryn Uhrich | TBD | Richard Zapien |  | Scott Donnell | 6 |  |  | FALSE |  |  | 43959 | Design | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-16
3594 | 3594 |  | FALSE | CNAS | R'Garden Grow Pod Installation | R'Garden Gro Pod Installation |  |  | On Hold | Kathryn Uhrich | TBD | Richard Zapien |  | Scott Donnell | 7 |  |  | FALSE |  |  | 43972 | Secure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-01-16
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Construction | Kathryn Uhrich | TBD | Georgios Vidalakis |  | Scott Donnell | 8 |  |  | FALSE | 15000 |  | 44085 | Complete Construction | 44197 | 44317 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-16
3597 | 3597 |  | FALSE | PB&A | Plaza F Roof Replacement | Plaza building F roof is well past its service life and is experiencing multiple leaks into the apartment spaces below. This scope of work is to replace the roof in total and repair damages observed to the apartments below as a result of roof leaks. REQUESTING JOHN FRANKLIN AS THE PROJECT MANAGER. |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 18 |  |  | FALSE | 250000 |  | 43999 | Complete Construction | 44197 | 44256 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-16
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | TBD | Wendi Tapia |  | Tameesha Hayes | 4 |  |  | FALSE |  |  | 44001 | Bidding | [12 empty] | PD&C | FALSE | 2020 | 2021-01-16
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | In Bidding | Kathryn Uhrich | TBD | Mireya Botello Santoyo |  | Scott Donnell | 5 |  |  | FALSE | 32871.65 |  | 44026 | Construction | [12 empty] | PD&C | FALSE | 2020 | 2021-01-16
3603 | 3603 |  | FALSE | SOM | Orbach Libr SOM CSSS AV Equipment | AV for CSSS project - 954044 / re: Fernando Cortez. Please refer to MSRIV in the line reference field for the draw down. |  |  | In Construction | Deborah Deas | Deborah Trujillo | Deborah Trujillo |  | Fernando Canon | 1 |  |  | FALSE | 1652000 |  | 44039 | Complete Construction | 44166 | 44256 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-16
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 44091 | Begin RFQ Process | [12 empty] | PD&C | FALSE | 2020 | 2021-01-16
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair/Replacement | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | Funding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 8 |  |  | FALSE |  |  | 44095 | Secure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-01-16
3610 | 3610 |  | FALSE | PB&A | Hulen Place Homeless Medical Clinic | SOM is acquiring additional space for a medical clinic to assist with the homeless population. |  |  | In Programming | Gerry Bomotti | TBD | Diana Armenta |  | Daneca Stevens | 5 |  |  | FALSE |  |  | 44110 | Design | 44256 | 44256 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-16
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 44097 | Bidding | 44256 | 44317 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-16
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 44096 | Bidding | 44287 | 44378 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-16
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Design | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 44089 | Bidding | 44287 | 44287 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-16
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns Hall A Interior Finishes |  |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Programming | [12 empty] | PD&C | FALSE | 1900 | 2021-01-16
9062 | 9062 |  | FALSE | PB&A | DM(FY20) Life Sci Sewer line |  |  |  | Bidding | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 116000 |  | 44089 | Award Contract | 44228 | 44228 | [10 empty] | PD&C | FALSE | 2020 | 2021-01-16
17P000254 |  | 17P000254 | FALSE | PB&A | SL5 FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS | Emergency Egress | CORP PP WHSE | 0106B | CANCELED BY CLIENT | Gerry Bomotti | TBD | DALAN DINH |  | Dan Lerman |  |  | 2 | FALSE |  |  | 42893 | [6 empty] | 05/08/19 O-ANS: Canceled by customer per email from Deborah McWilliams. .2/1/19, DL; Material is ordered with a 4-6 week lead time.11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DD 10/6: On hold pending discussion on space…..DL, 7/11/18; I understand there is movement on this project but I need to check in with John P. or Chris P. for a status update. |  | John Peraino |  | NO | 2019-04-05 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
17W012504 |  | 17W012504 | FALSE | CNAS | PAINT Business OFFICE AND CONF. ROOM |  | ENTOMOLOGY | 170 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 27 | 26 | FALSE |  |  | 42859 | [6 empty] | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. |  | Dan Lerman |  | YES | 2018-10-22 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
18P000027 |  | 18P000027 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT LAB |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 43164 | [6 empty] | 2/1/19, DL; This project is 100% Complete……………DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again…… DL, 4/2/18; This space is still on schedule for 7/1/18 completion date…..FAMIS work orders have been produced…..DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th…..TEST TEST |  | Dan Lerman |  | YES | 2018-07-12 | Fall 2017 | FS | FALSE | 2018 | 2021-01-16
18P000028 |  | 18P000028 | FALSE | CNAS | SL5 CHAPMAN PATCH AND PAINT |  | CHAPMAN | 0010A | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 42927 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced .......DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th.....Test test |  | Dan Lerman |  | YES | 2018-07-12 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
18P000029 |  | 18P000029 | FALSE | CNAS | SL5 CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS |  | CHAPMAN | 1 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 42927 | [6 empty] | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain......DL, 5/24/18; This work is scheduled to be complete on or before 7/1/18.....DL, 6/16/18; Blinds are delayed to mid July but window clenaning is still on schedule......DL, 7/11/18; This Project is 100% Complete |  | Dan Lerman |  | YES | 2018-07-11 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
18P000030 |  | 18P000030 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT FROM WATER DAMAGE |  | CHAPMAN | 100 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 42927 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete..... |  | Dan Lerman |  | YES | 2018-11-08 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
18P000094 |  | 18P000094 | FALSE | PB&A | SL5 OBAN LAUNDRY ROOM RENOVATION |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 2 | FALSE |  |  | 42986 | [6 empty] | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on bid. 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/12 EB- rec'd approval to contract with Design West to consult on electrical panel upgrade. |  | Enrico Baez |  | YES | 2019-01-19 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
18P000095 |  | 18P000095 | FALSE | PB&A | SL5 THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS |  | THE PLAZA | A0013 | CANCELED BY CLIENT | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Enrico Baez |  | C | HOLD | FALSE |  |  | 42986 | [6 empty] | 4/11/EB-On Hold per Robert Brumbaugh. 6/8 EB-emailed R. Brumbaugh for status update. |  | Enrico Baez |  | YES | 2018-06-08 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
18P000099 |  | 18P000099 | FALSE | CNAS | SL5 EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | TBD | LAURIE GRAHAM |  | Dan Lerman |  | 26 | 23 | FALSE |  |  | 42986 | [6 empty] | 4/19/19, DL; This Project is 100% Complete :)…………….12/6/18, DL; This project is a priority #23 and may be completed in the next 12 - months…..DL 1/3: Chris to verify with customer on electrical requirements for completion……DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress…..DL, 7/11/18; Still need to work on plans…. Target date is 9/30/18….. |  | Dan Lerman | Install power to 4- cabinets in hallway | YES | 2019-04-19 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
18P000106 |  | 18P000106 | FALSE | PB&A | SL5 HOUSING PROJECT - OBAN REC ROOM REMODEL |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 3 | FALSE |  |  | 42992 | [6 empty] | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. DL, 7/11/18; Per Susan this project is back on track. Project is scoped. Gunther will start working on the plans and permits. Once we have the approved permit. still need to check in with Susan on a few items.....Target complet date will be mid- fall...... |  | Enrico Baez |  | YES | 2019-01-19 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
18P000111 |  | 18P000111 | FALSE | CHASS | SL5 KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 |  | CHASS INT S |  | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Jason Williams |  |  |  | FALSE |  |  | 42993 | [6 empty] | EB 1/31/18 Work was assigned to lock shop 12/7/17…. DND 5/11: Spoke with Jason, all work complete to be completed as trade is available. Only work remaining is on 3150 A; Jason short staffed to finish project but it's on his radar. 07/13/18 H-FMS: Troubleshoot programming and settings for this controller. Clear all data from panel and reset, perform required downloads, re-test and verify both doors working correctly. |  | Enrico Baez |  | YES | 2018-07-13 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
18P000117 |  | 18P000117 | FALSE | CNAS | SL5 PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION |  | WEBBER | 1303 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 43090 | [6 empty] | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work....DL, 5/9/18; Produced work order for JEss to test for lead paint and ACM....Von wall is hot, everything else is good to go. I will schedule the work soon. The space is vacant......DL, 7/11/18; This project is in progress. Target Complete Date is 8/10/18....DL, 7/25/18; Vinyl plank and bullitin boards the balance of the task for this project. Still on target for complete on 8/10/18.....DL; 8/10/18; We were schedule to install the fllor and identified Asbestos,. Jess is working on the propsal and schedule for the abatment. This will require a 14- dat notification to the AQMD. This space is vacant with no scheduled move in date......DL, 8/22/18; Abatment is scheduled for this Tursday and Friday. We will scheule the carpet in dry errase boards for next week.Target complete date will be 8/31/18.....DL, 9/6/18; This project is 100% Complete...... |  | Dan Lerman |  | YES | 2018-09-10 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000118 |  | 18P000118 | FALSE | CNAS | SL5 OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT |  | OLMSTED | 1337 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ |  | Dan Lerman |  |  | 4 | FALSE |  |  | 42998 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space.......DL, 6/16/18. New staff member schedule to start mid july. BKM is also scheduled for mid july. This project will require cabinets to be removed, new carpet, paint and blank out electrical outlets that will no longer be used.. new signage too.....DL, 7/11/18;This project is in progress. Complete date is 7/20/18......DL, 7/25/18; This project is 100% Complete....... |  | Dan Lerman |  | YES | 2018-07-25 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000121 |  | 18P000121 | FALSE | CAMPUS | SL5 PHYSICS HYDRATION STATION - PHYSICS HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 42999 | [6 empty] | 5/1/19, DL; Per Chris, we will not be compelting this project. There is currently a Water dispenser on the drinking fountain. 3/28/19, DL; We will look into installing a bottle filler on this fountain verse a complete change out…..12/6/18, DL; This project is currently on hold…… DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman |  | NO | 2019-05-01 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000122 |  | 18P000122 | FALSE | CAMPUS | SL5 MS&E HYDRATION STATION - MS&E HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 42999 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman |  | NO | 2018-04-02 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000126 |  | 18P000126 | FALSE | CHASS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS |  | HUM & SOC SC | 3611 | COMPLETE | Juliet McMullin | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 43006 | [6 empty] | 7/1/19,DL; This project is 100% Complete…..5/15/19, DL; Work is scheduled to start on 6/19/19…….5/1/19, DL; Plans are approved. Need to order material and schedule the work…..3/18/19, DL; Plans submitted to PD&C today…..02/2819, DL; Gunther will work on plans over the next three weeks to submit for a building permit. We will schedule the work if and after the plans are approved. If approved the door and window will more than likely have a 3- month lead time…………….12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez |  | YES | 2019-07-01 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16 | FY 19-20
18P000194 |  | 18P000194 | FALSE | ITS | SL5 TELEPHONE WINDOW REPLACEMENT |  | TELEPHONE | 101 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 5 | 6 | FALSE |  |  | 43059 | [6 empty] | 07/23/19 O-ANS: Canceled by customer per notes in FAMIS. |  | Enrico Baez |  | YES | 2018-10-19 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000198 |  | 18P000198 | FALSE | VC-STU AFF | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Install new Wall lights | HUB | 0 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | R1 | 5 | FALSE |  |  | 43060 | [6 empty] | 10/30/19, DL: This project is on Hold and may be canceled as funding is not availabel at this time. Plans are approved……10/16/19, DL; Plans were submitted for plan check review last week. I also notified Brendan that this will be a recharge project . The ball park estimate I provided to Brendan was $7,000 - $9,000. Brendan needs to confirm if funds are available. If funds are available, I will have a contractor bid on the project……… 10/16/19: O-ANS - Not a CORE location so project changed to Recharge. 10/1/19, DL; Plans will be submitted a building permit and plan check review this week…….9/3/19, DL; Gunter has plans at 60%, We will try and submitt with in the next two weeks. 8/14/19, DL;This project is now on Gunther's bench. Gunter will start the process in about 2- weeks and we should have plans top submitt with in the next 30- days….6/17/19, DL; I will walk this work in the next two weeks and work on plan to submit to our campus architech and building official for review…..DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…… | 2018-01-23 | Enrico Baez |  | YES | 2019-10-30 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16 | FY 19-20 | 1
18P000201 |  | 18P000201 | FALSE | CHASS | SL5 ARTS REMOVE COUNTERTOP/SHELVES |  | ARTS | 0106A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 3 | TRUE |  |  | 43060 | [6 empty] | DL, 6/16/18; Ned to walk, scope and submit plans ASAP…..Sent Paul an email requesting information on Status of Faculty hire status……DL, 7/11/18; Paul is on Jury Duty and he said he should return back to work next week. Current Targe complete date is mid September......DL, 7/25/18; Carpentery and Electrical is complete. Patch and paint has started. Target complete date is 8/3/18......DL, 8/8/18; Space is VAcant and ready for paint. The paint department is working on several other projects that require their attention. The paint department will complete the work in the near future......DL, 8/22/18; This Project is 100% Complete....... |  | Enrico Baez |  | YES | 2018-08-23 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000205 |  | 18P000205 | FALSE | CHASS | SL5 CHASS INT S CREATE DOOR |  | CHASS INT S | 2117H | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 43066 | [6 empty] | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18……DL, 5/24/18; Plans were approved. WE need to schedule the work…..DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18...........DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... .. DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date..........DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18............DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware.....DL, 9/19/18; This Project is 100% Complete...... |  | Enrico Baez |  | YES | 2018-09-21 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000209 |  | 18P000209 | FALSE | CHANCELLOR | SL5 VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 |  | STUDENT SERV | 0 | CANCELED BY CLIENT | Kim Wilcox | TBD | ANGIE GRAY |  | Dan Lerman |  |  | 1 | FALSE |  |  | 43069 | [6 empty] | 5/16/19, DL Angie Grey canceled project on 5/15/19 via email….. 5/1/19, DL; Sent Angie an email this morning. Waiting to hear back from Angie to see if project will be canceled or sent to PD&C…..3/28/19, DL; Provided Angie with an estimate and waiting for her response. The esimate was for 65,000. this work will be redirected to PD&C if she wants to proceed…….2/14/19, DL; Ron V. to follow up with Doug from Capitol Door for alternate pricing .1/15/19, DL; Ron V is still working with Angie on verifying a vendor and product…………..12/14/18, DL; Ron V. is currently working to find a more affortable turnstyle system. When a sytem is approved, we will schedule the work…. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope and conduct site visit……DL, 7/11/18; This work will require plans and permits. Will schedule meeting with Scott to verify if the project request will be approved. If this is approved, we will plan the target complete date to be mid October…..The Request is to reverese Emergency Exit Doors and install Prox card access……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..DL, 8/22/18; Confirmed with Scott that we can reverse the door swing. We will work on plans for review process. This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 9/19/18; I mis understood this for a project at Health Services. I have a meeting with Angie this week. This project is to install turn styles for access to the building. I will need to discuss the equipment to be purchased by Angie verify the specs. We will start on the plans in the early Fall……DL, 11/7/18; Conducted site visit with Vendor. Informed Angie the cost of the project will be at $45K for the project. Angie is checking to verify if funds are availabe for the equipment. |  | Ron Veloz | Install automatic swing gates at the student services lobby. Include Access controls relay cabling | YES | 2019-05-16 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000214 |  | 18P000214 | FALSE | VC-STU AFF | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Install Card readers | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  | 2 | 2 | FALSE |  |  | 43077 | [6 empty] | 1/19/21, DL: This project is 100% Complete…….9/30/20, DL: Vendor should have the balance of the material in the next 30- days…….8/5/20, DL: This project is complete except the card reader portion of the project…………6/17/20, DL: The floor covering was completed two weeks ago. The card reader portion of this project is 95% complete but additional parts were needed and they are on order. Once they arrive, we will schedule the installation and this project will be 100% Complete………1/15/20 Emailed Status Report to customer…..1/14/20, DL: We were recently approved to proceed with the work. I have reached out to the vendor for the doors and card access. We are still waiting to hear back from them so we can order the material and schedule the work. I communicated with Nicole on the floor covering replacement. Nicole needs to verify what areas we will replace as we were going to complete several offices and a hallway as part of the scope but this will displace many team members for at least a week. We will work on scheduling the work once Nicole gets back to me……..12/17/19 - O-DHN: Emailed Status Report to Customer……12/19/19, DL; We are working with our contractor to order the material and schedule the work. Once we have confirmation on the material, we will be able to schedule the work. It Is our goal to start this project in late January……11/26/19, DL: This project was taken off of on hold and we can now proceed. I contacted the contractor last week and I am awaiting their response on when they can schedule the work. I also left a message with them this morning………..7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once material arrives, we will schedule the installation.….5/31/19, DL; Contract is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is completed except the floor covering and electronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being prepped for paint. We have a pre-construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, material is ordered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct site visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez |  | YES | 2021-01-19 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16 | FY 20-21
18P000215 |  | 18P000215 | FALSE | VC-STU AFF | SL5 STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA HAGGINS |  | Dan Lerman |  |  | 3 | FALSE |  |  | 43077 | [6 empty] | 6/17/19, DL; This project is 100% complete. This project was the wall removal at the check in entrance…...5/31/19, DL; Contracts is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks4/15/19; All work is comleted except the floor covering and elcetronic card readers for the doors…..2/28/19, DL; This project has started and is on schedule…….2/14/19, DL; This project is scheduled to start on 2/19/19…………2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………1/15/19, DL, Material is ordered, material should arrive on site in the next 3- 5 weeks……12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 5/24/18; Need to review scope and site visti with Enrico. Plans and permits will be required for this project….DL, 7/11/18; Planning to walk work with Gloria and her team next week. Will be able to project complete date after site visit is conducted……DL; 7/25/18; We walked this project with the team. This will require plans and permits. We will schedule this work for Fall…………DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-45 Days…… |  | Enrico Baez |  | YES | 2019-06-17 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000221 |  | 18P000221 | FALSE | CNAS | SL5 Provide add'l HVAC capacity to maintain lower temp |  | BOYCE | 4414 | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  | 9 | 16 | FALSE |  |  | 43080 | [6 empty] | 12/14/18, DL; This project is 100% Complete……….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob. DL, 5/9/18; We will work on plans and submit for review.....DL, 6/16/18. Had meeting with Bob W. to verify what is needed on plans. I will work with Gunther on plans for submittal and review......DL, 7/11/18; Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall.....DL, 11/7/18; Material is on site and will will schedule the work with in the next 30- days..... |  | Dan Lerman |  | YES | 2018-12-14 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000223 |  | 18P000223 | FALSE | CNAS | SL5 Provide requisite utility infrastructure to support 4 add'l chambers (on order). |  | FAWCETT LAB |  | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  | 11 | 21 | FALSE |  |  | 43080 | [6 empty] | 2/1/19, DL; This Project is 100% Complete……..01/15/19, DL; Plans are approved, Chambers are on site. Electrical is complete. Plumbing work is in progress. Our portion of the project should be complete by 2/1/19…………..12/14/18, DL; All Pre work is complete. The Chambers are scheduled to arrive on site within the next 30-days. We will finish this project when material on site……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans……..DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet….DL, 4/29/18; Still need to conduct site visit with the team….DL, 5/24/18; Per Patty, equipment is ordered but 5- months out…..DL, 9/6/18; We will submit plans to Bob W. tomorrow for review and approval……..DL, 9/19/18; Plans are approved. The equipment will be here in about 4- months. WE will start the work for this project in the Fall to ensure we are ready when the equipment arrives……DL, 9/19/18; Plans are currently being review by BO & FM……DL, 11/7/18; Plans are approved. WE are requesting to change the placement confirguration of the growth chamber and awaitng Bob's review and approval. WE are on track to have this work complete befoire the end of the new year….. |  | Dan Lerman |  | YES | 2019-02-01 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000226 |  | 18P000226 | FALSE | BCOE | SL5 BOURNS FUME HOOD INSTALLATION |  | BOURNS | B0235A | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 8 | HOLD | TRUE |  |  | 43080 | [6 empty] | 2/14/19, DL; This project is Complete…..2/1/19, DL; The Fume hood is complete. The vendor will be back in two weeks to comissison the clean room…..…1/15/9, DL; This project is 95% complete and should be complete on or near 2/1/19…………12/14/18, DL; This Project is 90% Complete. Fume hood is scheduled for install next week. We will finish balance of project after Fume hood is installed…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. WE are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans…..DL, 5/9/18; planning to submit plans on 5/11/18 for plan check review….. DL, 5/24/18; Plans were submitted to Bob W. on 5/24/18……DL, 6/12/18; Project is on Hold until Shane can provide plans/specs for the clean room……DL, 7/11/18; Still no change to the status……DL, 7/25/18, Maggie confirmed this project is on the books. I need to discuss the status with the team because the priority list is on Hold…….DL, 8/22/18; This project is no longer on hold. We will per shane we will submit what we have from the clena room suupplier for review from FM and BO……DL, 9/6/18; WE are almost complete with Plans and will submit the plans next week………DL, 9/19/18; Submitted plans to PD&C on 9/14/18…..DL, 10/4/18; Plans were approved thais week. WE will scheudle the project around the delivery date for the Clean room……..DL, 11/7/18; This is in progress. We will complete the install of the utilities so the clean room can be installed. WE will finish the balance of the project once the Clean room install is complete. The clen room is being install by an outside vendor….. |  | Dan Lerman |  | YES | 2019-02-14 | Spring 2018 | FS | FALSE | 2017 | 2021-01-16
18P000227 |  | 18P000227 | FALSE | CNAS | SL5 BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL |  | BATCHELOR | 4128 | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  |  |  | TRUE |  |  | 43081 | [6 empty] | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM.......DL, 5/24/18; Need to work on plans and permits. Project needs to be complete before Fall academic 2018.....DL, 6/16/18; Walked project with Jess. and he will schedule the abatment. We will not need plans for this project. We are not removing the exhasut hood which was the original purpose foor the plans......Carpenters started the demo. Still need to remove TSI. Once TSI is removed, we can schedule the plumbing work. Target Complete Date is 9/21/18....DL, 8/10/18; Abatement is scheduled for this weekend, we will start work soon.....DL, 8/22/18; Abatement and most demo complete. Still on track for 9/21/18.....DL, 9/19/18; Scope change. This project should be complete on 9/28/18.......DL, 10/4/18; Floor to be installed this Friday. Pianters will finalized the stain on the cabinets. Thsi project should be complete near 10/19/18.......Dl, 11/7/18; This project is 100% complete.... |  | Dan Lerman |  | YES | 2018-11-08 | Winter 2018 | FS | FALSE | 2017 | 2021-01-16
18P000247 |  | 18P000247 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 |  | PHYSICS | 3023 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Paul Ditty |  |  | 15 | FALSE |  |  | 43089 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Spring 2018 | FS | FALSE | 2017 | 2021-01-16
18P000252 |  | 18P000252 | FALSE | ITS | SL5 CHASS INT S REPLACE ELECTRICAL SCREENS |  | CHASS INT S | 2130 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | JORGE MACIAS |  | Dan Lerman |  | 1 | 2 | FALSE |  |  | 43090 | [7 empty] | 2018-06-21 | Ron Veloz |  | YES | 2019-01-24 | Summer 2018 | FS | FALSE | 2017 | 2021-01-16
18P000256 |  | 18P000256 | FALSE | CNAS | SL5 BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES |  | BOYCE | 3451 | COMPLETE | Kathryn Uhrich | TBD | CHERYL GERRY |  | Dan Lerman |  |  |  | FALSE |  |  | 43091 | [6 empty] | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave at Webber is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place.......DL, 5/9/18; Autoclave is destroyed. Pictures were sent to Cheryl. We are now waiting for the equipment to arrive. Steve B is working on Steam connection at Boyce......DL, 5/24/18; Autoclaves arrived. Day crew is scheduled to deliver the unit on 5/30/18. we will schule the plumbers and electricians shortly there after......DL, 6/16/18; Webber Autoclave is almost complete. This portion should be complete next week. WE will run the Webbber autoclave for two weeks before we start the Boyce Autoclave. The weldolet for the BOyce unit will be installed during the steam shutdown...... DL, 7/11/18; Webber Auto clave will be complete on 7/12/18. We will start the demo of the Boyce Auto clave next soon. Target date for this project is 8/10/18...... DL, 7/25/18; We had a delay with the Webber autoclave which will implact the Boyce Auto clave. New target complete date is 8/22/18.....DL, Plumbing is almost complete, need to schedule final elctrical and Commission equipment. Target date 8/31/18...... DL, 9/6/18; This project should be complete but we still need to schedule the electrical connections ASAP.........DL, 9/19/18; This project is 100% Complete. |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2017 | 2021-01-16
18P000257 |  | 18P000257 | FALSE | CNAS | SL5 SKYE HALL MOUNT 55 |  | SKYE HALL | 209 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | 28 | 28 | FALSE |  |  | 43091 | [6 empty] | 2/1/19; This Project is 100% Complete…….1/15/19, DL, Site visit is scheduled with James M. this Thursday. We will schedule the work shortly after the site visit…….12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2017 | 2021-01-16
18P000258 |  | 18P000258 | FALSE | CNAS | SL5 SKYE HALL HALLWAY MOUNT |  | SKYE HALL | 212 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | 29 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 43091 | [6 empty] | 2/1/19; This Project is 100% Complete……1/15/19, DL, Site visit is scheduled with James M. this Thursday…………12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2017 | 2021-01-16
18P000261 |  | 18P000261 | FALSE | SOM | SL5 WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR |  | WEBBER | 1143 | COMPLETE | Deborah Deas | Deborah Trujillo | LOURDES ESCAMILLA |  | Dan Lerman |  |  |  | FALSE |  |  | 43091 | [6 empty] | DL, 7/11/18; Work orders are produced. Need to assign the work order and order material. I will review with Steve and verify target complete date….DL, 7/25/18; Still need to walk the project with Steve……DL, 8/10/18; Material is ordered. We will complete the install when the materila arrives.....DL, 8/22/18; Material should be on site with in 4- weeks. Will schedule install when material is on site. Target date is 9/20/18.......DL, 9/6/18; This Project is 100% Complete...... |  | Dan Lerman |  | YES | 2018-09-10 | Spring 2018 | FS | FALSE | 2017 | 2021-01-16
18P000267 |  | 18P000267 | FALSE | BCOE | SL5 CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 4 | FALSE |  |  | 43116 | [6 empty] | DL, 5/19/18; High table mounted on West wall to be relocated to South wall by light "Centered". Relocate white board from East Wall to West walll wher high table was removed. Paint and new flooring. Need to schedule work with Paul and Jess. BKM furniture is scheduled 4-6 weeks. DL, 6/16/18; Lower electrical outlets on North wall, repair blinds, paint and new flooring. The space is vacant as of June 16th. I will scheudle the workl.....BKM delivery is currently scheduled for July 23rd.......This project is 100% complete. There were two items added to the scope and they will be complete by 7/20/18..... |  | Enrico Baez |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000269 |  | 18P000269 | FALSE | CNAS | SL5 BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED |  | BATCHELOR | 1123 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  | 12 | 18 | FALSE |  |  | 43116 | [6 empty] | 3/18/19, DL; went to schedule the work and the customer stated the power is no longer needed and confirmed this work order can be canceled. |  | Enrico Baez |  | YES | 2019-03-18 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000270 |  | 18P000270 | FALSE | SPP | SL5 CHASS INT S- EVALUATION FOR REMODEL |  | CHASS INT S | 4133 | CANCELED BY CLIENT | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Dan Lerman |  | 4 | 2 | TRUE |  |  | 43116 | [6 empty] | 4/24/18 EB- Per Christina Wong, no loner needed……DL, 5/5/18; Project is cancesled per notes DND 7/27; Please follow up with customer on the status and need for the work; customer advised to me that Dan has the scope of work for completion. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. |  | Enrico Baez |  | YES | 2018-04-24 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000273 |  | 18P000273 | FALSE | LIBR | SL5 RIVERA LIB -RESTROOM REFRESH PROJECT |  | RIVERA LIB |  | TO BE PERFORMED BY PD&C | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 43118 | [6 empty] | DND 12/13/18: Customer advised maintenance requests related to project request has been addressed. Renovation work to be performed by PD&C and customer submitted a CPMS request. DL, 6/16/18; Need to schedule site visit with Dave and Chris P…….DL, 7/11/18; Chris and I will walk this poroject next week…..Wlaked projects with Chris. We need to review in more detail to better determin the process for this project…..DL, 9/6/18. WE need to discuss what we are going to do with this project.... We walked the project but we now need Direction from Facilities leadership… |  | Dan Lerman |  | YES | 2018-12-13 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000274 |  | 18P000274 | FALSE | GSOE | SL5 SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 |  | CHILD DEV N |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES | BRANDON BARBOSA | Dan Lerman |  |  |  | FALSE |  |  | 43118 | [6 empty] | 2/14/19, DL; This project is Complete………….2/1/19, DL; This project is 99.9% Complete. We still need to conduct Final inspection with Building inspector……1/15/19, DL; The door and automatic opener is scheduled to be installed on 1/22/19……..12/14/18, DL; This project is 95% complete. The contract for the door and ADA operator was awarded today. We will schedule the work shortly after the new year…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Conducted site visit with Gilbert. We need to have a meeting to determin if this work is part of the SLA…… DL, 6/16/18; We still need direction, SLA or Recharge?.......DL, 7/11/18; This Project will require Plans and Permits. We will start on the Plans next Week. We will also issue work orders for work we will complete with in house staff. The Concrete work and Entry Door will need to be contracted out. Target Complete date is 10/1/18……..DL, 7/25/18; Work orders are produced. Planing to walk the project with Chris, Steve B and Robert C. thisw week or next week. We will submit plans to Bob Williams for the contracted work next week……DL, 8/8/18; Completed site visit with Robert C. Steve B, Steve T. and Chris; the Plumbers are complete. The carpenters and electricians will work on their items over the next three weeks. The Plans will be ready to submit on 8/9/18. Once plans are approved, we will proceed to go out to bid for the Concrete and the ADA operator. Target complete date is 9/21/18…….DL, 8/22/18; Plans were apprroved, Concrete Contract is being executed. Still working on Door and ADA operator……..DL, 9/6/18; NTP for Concrete will be issued on Monday. I will schedule the work. I need to follow up on the door order and the ADA operator…….DL, 9/19/18; Concrete walkway scheduled to start on 9/20/18. The new door and Frame will arrieve in 3-5 weeks. We will schedule the install when the new door and frame are on site…….DL, 10/4/18; Concrete work is complete. Still need handrail, signage, door and ADA operator. Target date is Early November….DL, 11/7/18; Project is 95% complete. Contract is being processed to install the new Door, Door Fram and ADA operator. Goal is to have the work complete befor the winter break…… |  | Enrico Baez |  | YES | 2019-02-14 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000281 |  | 18P000281 | FALSE | VC-UNIV ADV | SL5 ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS |  | ALUM VISITOR | 2202 | COMPLETE | Peter Hayashida | Naysia Caldwell | TRUDY COHEN |  | John Peraino |  | 2 |  | FALSE |  |  | 43124 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…..2/28/19, DL; This work is scheduled…….DL, 5/24/18; Need to verify scope of work with EnricoDL, 7/11/18; Still need to visit the site and schedule the work…..DL, 11/8/18; This project was transferred to John. The target date was 1/2/19….. |  | Enrico Baez |  | YES | 2019-03-28 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000282 |  | 18P000282 | FALSE | PB&A | SL5 EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 |  | POLICE BLDG |  | COMPLETE | Gerry Bomotti | TBD | LISA MARTIN |  | Dan Lerman |  |  |  | FALSE |  |  | 43125 | [6 empty] | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work…..DL, 5/9/18; We need to submit plans……DL, 7/11/18; This still needs to be scheduled......DL, 8/8/18; Enrico Confirmed this project is 100% Complete.... |  | Enrico Baez |  | YES | 2018-08-10 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000284 |  | 18P000284 | FALSE | CNAS | SL5 SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT |  | SKYE HALL | 277 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  | 29 | 23 | FALSE |  |  | 43131 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000287 |  | 18P000287 | FALSE | CNAS | SL5 SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  |  | 33 | FALSE |  |  | 43131 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19/18; This project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000288 |  | 18P000288 | FALSE | CNAS | SL5 SKYE HALL OFFICE SUITE PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  |  | 14 | TRUE |  |  | 43131 | [8 empty] | Dan Lerman |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000292 |  | 18P000292 | FALSE | CNAS | SL5 SKYE HALL PAINT MULTIPLE FACULTY OFFICES |  | SKYE HALL | 228 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  |  | 1 | TRUE |  |  | 43131 | [8 empty] | Dan Lerman |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000293 |  | 18P000293 | FALSE | CNAS | SL5 SKYE HALL COPIER ROOM PATCH AND PAINT |  | SKYE HALL | 278 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  |  | 32 | FALSE |  |  | 43131 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000294 |  | 18P000294 | FALSE | CHASS | SL5 HMSS REMOVE DOOR, INSTALL WALL |  | HUM & SOC SC | 3610 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 43132 | [8 empty] | Enrico Baez |  | YES | 2018-07-16 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000295 |  | 18P000295 | FALSE | CHASS | SL5 CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL |  | CHASS INT S | 2117J | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 43132 | [6 empty] | DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18……..DL, 5/24/18; Plans were approved. We need to scheudle the work….DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets.......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date.....DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18...........DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware..... |  | Enrico Baez |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000296 |  | 18P000296 | FALSE | CNAS | SL5 SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES |  | SKYE HALL | 266 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  |  | 31 | FALSE |  |  | 43133 | [6 empty] | 01/17/19, DL; This project was completed last summer……..DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19 18; I neeed to check on this work order. I thought it was part of the 2nd floor Hallway project but it was not…… |  | Dan Lerman |  | YES | 2019-01-01 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000297 |  | 18P000297 | FALSE | CHANCELLOR | SL5 SKYE HALL CHECK LOCATION FOR TV INSTALL |  | SKYE HALL | 390 | COMPLETE | Kim Wilcox | TBD | CANDICE GOMEZ |  | Dan Lerman |  | 4 | 3 | FALSE |  |  | 43133 | [6 empty] | 2/1/19, DL; This Project is 100% Complete………1/18/19, DL; This Project is scheduled to be complete next week.….. DL, 5/24/18; Need to verify scope with Enrico…..DL, 7/11/18; Work orders are produced and need to be issued. Target complete date is 9/3/18…. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000300 |  | 18P000300 | FALSE | CHASS | SL5 ARTS PATCH AND PAINT - DANCE HALLWAYS |  | ARTS |  | COMPLETE | Juliet McMullin | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 24 | FALSE |  |  | 43133 | [6 empty] | centered. |  | Paul Ditty |  | N/A | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000310 |  | 18P000310 | FALSE | CNAS | SL5 ADD INTERCOM/BUZZ IN SYSTEM |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Dan Lerman |  |  |  | FALSE |  |  | 43143 | [6 empty] | Dl, 7/4/18; This project is scoped. This will be a new ADA operator, door bell / Intercom and buzzer button to unlock door. Walked work with Contractor, need to work on producing contract with PD&C. Once Contract is confirmed, we will schedule the work..... DL, 7/11/18; We have the proposal. Need to execute the agreement and schedule the work. The target complete date is before 10/1/18.....Dl 8/10/18; Jason will try and complete the work with in the next three weeks......DL, 8/22/18; Jason order parts, parts have 6-8 week lead time. Work will be scheduled when material arrives.....DL, 10/4/18; This Project is 100% Complete....... |  | Dan Lerman |  | YES | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000312 |  | 18P000312 | FALSE | CNAS | SL5 URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 |  | PARKING LOT P 42 |  | CANCELED BY FS | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  |  | 38 | FALSE |  |  | 43144 | [8 empty] | Enrico Baez |  | YES | 2018-09-19 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000313 |  | 18P000313 | FALSE | GSOE | SL5 SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  |  |  | FALSE |  |  | 43146 | [6 empty] | 18W011689 Work order was cancelled because it has the same scope and is a duplicate………DL, 6/16/18; Contract is being awarded this week. Weill are scheduled to have this work completed by fiscal closing……DL, 7/25/18; This Project is 100% Complete…..9/13: Zee - Customer noted paint peeling; updated to status to back in progress for work to be addressed.......DL, 9/19/18; The contractor is on site repairing the walls and painting. The work should be complete this week.......dl, 10/4/18; tHIS PROJECT IS 100% Complete..... |  | Paul Ditty |  | N/A | 2018-10-22 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000314 |  | 18P000314 | FALSE | CHASS | SL5 CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR |  | CA MUS PHOTO | 1000 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY PAPAVERO |  | Dan Lerman |  |  | 17 | FALSE |  |  | 43147 | [6 empty] | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date.......DL, 7/25/18; This project is 100% Complete..... |  | Enrico Baez |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000315 |  | 18P000315 | FALSE | BCOE | SL5 BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB |  | BOURNS | B0235 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  |  | HOLD | TRUE |  |  | 43147 | [6 empty] | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction to scope, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... Need to walk project with Ron and schedule the work....DL, 5/24/18; Conducted site visit with Ron V. Ron will order material and schedule the work once material is on site.....DL, 6/16/18; Need to verify delivery date for material.......DL. 7/11/18; Plumbing is disconnected. Corey is tentatively scheduled to disconnect the Fume hood. Once the Fume hood is disconnected, we will schedule the removeal of the fume hood and start the framing of the wall. Target complete date is 8/8/18....DL, 7/25/18; Fume hood is disconnected. Need to move Fume hood and start framing target date is delayed to creep scope but should be complete near 8/16/18.....DL, 8/10/18; Carp[enters will install the wall this week. Corey has parts orders. Corey will complete the install when the material arrives.......DL, 8/22/18; This Project is Complete |  | Dan Lerman |  | YES | 2018-08-23 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000318 |  | 18P000318 | FALSE | CHASS | SL5 CHASS INT S FLAT SCREEN INSTALLATION |  | CHASS INT S |  | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Dan Lerman |  |  | 20 | FALSE |  |  | 43152 | [6 empty] | 4/15/19, DL; This is 100% Complete….3/28/19, DL; Monitor is installed. Need to finishe power and data next week……2/28/19, DL; Scheduled to complete the install mid March…..2/1/19, DL; Francesca contacted me and informed me this project is now back on the books. She needs to gather more information and order the monitor. When the monitor arrives, we will schedule the installation…….1/29/19, DL; Francesca confirmed this project is not needed and requested this project to be cencelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; we have the brackets. Will scheule the work after the project is approved…..DL, 7/11/18; Work order are not produced. Need to assign and schedule the work…. Target complete date is 8/3/18……DL; 7/25/18; Need to change target date.. |  | Enrico Baez |  | YES | 2019-04-15 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000321 |  | 18P000321 | FALSE | BCOE | SL5 STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST |  | STUDENT SERV | 1228 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Enrico Baez |  |  |  | FALSE |  |  | 43153 | [6 empty] | DL, 4/29/18; Enrico is cordinationg this. The permits are approved……. DL, 7/11/18; Just received confirmation the door is ready for delivery and installed. I need to check in with Paul about the paint and prep of the door. I also need to check in with Jason on lock hardware......Dl, 7/25/18; Door is painted and ready for install. Called Dugmore to schedule the install. This should be compolete within the next two weeks......DL, 8/8/18; This Project is 100% Complete |  | Enrico Baez |  | YES | 2018-08-10 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000324 |  | 18P000324 | FALSE | PB&A | SL5 HINDERAKER PATCH AND PAINT |  | HINDERAKER | 4118 | COMPLETE | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  |  |  | FALSE |  |  | 43157 | [8 empty] | Paul Ditty |  | N/A | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000328 |  | 18P000328 | FALSE | ATHLETICS | SL5 HINDERAKER BASEMENT OFFICE REPAIR |  | HINDERAKER |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 43160 | [6 empty] | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with Paul. Paul will complete as in the near future. Carpet will be installed shortly after......5/21/18, Painters started paint. Should be complete with paint by the end of the week....DL, 5/24/18; Painters are complete. Jess will schedule the carpet install.....DL, 6/12/18; Project is 98% Complete. Carpenters need to under cut two doors to accomodate the carpet.....DL, 7/11/18; This Project 100% Complete..... |  | Dan Lerman |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000329 |  | 18P000329 | FALSE | CHANCELLOR | SL5 SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST |  | SKYE HALL | 170 | COMPLETE | Kim Wilcox | TBD | DA LAN DINH |  | Dan Lerman |  |  |  | FALSE |  |  | 43171 | [6 empty] | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18…..DL, 5/24/18; Plans were approved. Demo work has started......DL, 6/12/18; MArshal and Kate are working on Carpet order......DL, 7/11/18; Carpet is ordered. We have a challenge with Title 24. I am working on the title 24 documents. We are still planning to have this project complete on 8/17/18......DL, 8/10/18; We now have the Title 24 plans. The are being reviewed by Bob and Scott.....Title 24 plans approved. Robert is working on PO#. Most parts are on site and Electricans are working on project. All other Trades to follow once Lights are in...... Hard Date of 9/7/18............9/6/18 As of today, Carpet is scheduled for install tomorrow morning and furniture is scheduled for delivery this Monday......WE will more than likely have electrical punch items and touch up paint but this propject should be 100% complete in regards to FS the end of next week next week......100% PROJECT COMPLETE... GREAT WORK DAN! |  | Dan Lerman |  | YES | 2018-09-18 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000337 |  | 18P000337 | FALSE | VC-STU AFF | SL5 MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET |  | HEALTH SERV | 414 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 43171 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18….Need to work on plans and permits….DL, 7/11/18; Gunther is working on plans. Target complete date is 9/14/18….DL, 7/25/18; Planning to submit plans for review next week. We will schedule the work once we have approved plans…….DL, 8/8/18; This is a structual wall and needs to be engineered. We are meeting with the Structual engineer on 8/9/18 to determine if project is possible.....DL, 8/22/18; Working on EDPA for Structual engineer; project timeline is late Fall. 9/19/18; The Agreement / Cointract for the structual engineer is processed for this project. We should have plans from the structual engineer to submitt to the Building Official and fire marshal with in 4- weeks......dl, 10/4/18; Plans are almost complete and we will submit them for review by the end of the week.....DL, 11/7/18; Plans are approved. WE are schedule to start this Project on Tuesday 11/13/18. Target complete date is by the end of the winter break..... |  | Enrico Baez |  | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000341 |  | 18P000341 | FALSE | CNAS | SL5 PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL |  | PHYSICS | 1132 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 43173 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process…DL, 6/16/18; Jess tested the matreial flooring and paint is hot. Jess will abate before we proceed with the project….Still need to scheudle the work. This project target complete date is late Fall……DL, 7/25/18; Jess sent out the 14-day notification to the AQMD last week. We will start the balance of the project after the ACM and Lead is abated or encapsulated…..8/10/18; Abatement is complete. We will work on the other items as time permits. This space is vacant with no occupancy date |  | Dan Lerman |  | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000343 |  | 18P000343 | FALSE | CHASS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER |  | THTR WKSH | 0400A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 43175 | [6 empty] | 11/15/19, DL: This project is complete…..10/30/19, DL: Sheet metal shop fabricated the hand rails. The paint shop will prime and paint the hand rails and the curb. Once the rails are painted, the sheet metal shop will complete the installation…….10/16/19, DL; Cory from the sheet metal shop is aware of the scope of work and they will schedule the work in the near future……..10/1/19, DL; Dan to show Cory from sheet metal the area where a hand rail will be installed for painting backdrops……..07/11/19 O-ANS: Dan and Chris P will walk the space. 05/21/19 O-ANS: Changed to In Progress per meeting with Dan L. Chris P is the PM for further updates. DL and CP will visit after commencement. 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez |  | YES | 2019-11-15 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
18P000344 |  | 18P000344 | FALSE | CHASS | SL5 CHASS INTS PAINT MULTIPLE ROOMS - FACULTY |  | CHASS INT S | 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 1 | TRUE |  |  | 43177 | [6 empty] | DL, 7/11/18; This was transferd in to my quque in the past week. I need to scope this project. I belive this is part of project # 18P000205 and 18P000295. If this is part of the other project. We will try to have the paint completed by 8/17/18…......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/10/18; Work has started. We passed rough electrical and framing inspection. The work should be complete in about three weeks......DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18.......DL, 9/6/18; This Project is 100% Complete....... |  | Paul Ditty |  | N/A | 2018-09-10 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000346 |  | 18P000346 | FALSE | ATHLETICS | SL5 ATHLETICS INSTALL WALL VOLLEYBALL OFFICES |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 43177 | [6 empty] | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. DL, 5/24/18; We will start working on plans in the near future.... DL, 6/16/18; Need to submit plans asap.......DL, 7/11/18; The plans were approved today. This project is scheduled to start on 7/14/18. We will will be complete will all items related to this project on 8/27/18. Note, The door and sidelite are special order items and this item will probalby have a 6-8 week lead time. Steve T is going to order the door soon.. Customer is aware of the delay for the door and is not concerned......DL, 7/25/18; Passed framing and Electrical inspection. We will be finished with the project next week except for the door and window that is ordered but has a 6-8 week lead time. DL, 8/10/18; This Project is Complete except for special order door and window.......DL, 8/22/18; Door and Glass still not on site., Will check in with Steve T on delivery date......Will also schedule final inspection for Certificate of occupancy......9/6/18; The Glass window is installed but we are waiting on the door. this projects is 98% complete.......DL, 9/19/18; The door will be shipped on 9/24/18. We will schedule the door install when the door is on site......DL, 11/7/18; This Project is 100% Complete.... |  | Dan Lerman |  | YES | 2018-11-08 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000347 |  | 18P000347 | FALSE | CNAS | SL5 GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) |  | GEOLOGY | 0 | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | 31 | Deferred to Fall Quarter - summer priority 27 | FALSE |  |  | 43177 | [6 empty] | 4/15/19, DL; Thios Project is 100% Complete….3/28/19, DL; Monitor is installed, need to finish power and data………………...2/14/19, DL: The monitor is on site. We need to schedule the installation. 2/1/19, DL; Conducted site visit with Amber. Amber will order the monitor. We will schedule the installation when the monitor is on site………….DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez |  | YES | 2019-04-15 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000348 |  | 18P000348 | FALSE | VC-STU AFF | SL5 HUB ADD 3RD FLOOR WALLS |  | HUB | 0353E | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 2 | 6 | FALSE |  |  | 43177 | [6 empty] | 2/1/19, DL; Per Chris P. This is a PD&C project………..DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Need to walk the project with Manny. Target date is late Fall…….. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000349 |  | 18P000349 | FALSE | BCOE | SL5 PHYSICS INSTALL PARTITION WALL FOR LAB ROOM |  | PHYSICS | 1037 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 43177 | [6 empty] | DL, 5/24/18; Ron V. has detailed scope and he is ordering material. Once material arives, we will schedule the work…. DL, 6/16/18; Materila is ordered, When door/frame arrives, we will prep, paint and start the work…….DL, 7/11/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000351 |  | 18P000351 | FALSE | SoB | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 (S) | 21 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 43178 | [6 empty] | 8/1/19, DL; This project is 100% Complete……7/15/19, DL; Work has started and should be complete on 7/16/19…….. 4/4/19 O-ANS: Moved to Queue to Start to complete during Summer 2019. DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week……8/8/18. The trades are ready to go after they finish current projects…..DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18………. DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date……..9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space……Note. The space is usable and everything works….. |  | Enrico Baez |  | YES | 2019-08-01 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
18P000353 |  | 18P000353 | FALSE | CHASS | SL5 PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT |  | PSYCHOLOGY1 | 1111A | COMPLETE | Juliet McMullin | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 26 | FALSE |  |  | 43179 | [6 empty] | DL; 7/4/18;This project is scoped. We will only paint one out of the two offices. Working on PO# to install frosted glass with Sun Down Window coverings……DL, 7/25/18; PO# is produced and material is ordered. Target date mid August…….DL, 8/22/18; This project is complete.... |  | Paul Ditty |  | N/A | 2018-08-23 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000354 |  | 18P000354 | FALSE | CNAS | SL5 GH16-25 COOLING SYSTEM REPAIR |  | GH 16 25 |  | CANCELED BY FS | Kathryn Uhrich | TBD | MARK TANKERSLEY |  | Dan Lerman |  | 13 | 17 | FALSE |  |  | 43179 | [6 empty] | DL, 7/25/18; Reviewed Ron V. noted. I will check in with Chris on this to better determin the method complete this project. |  | Dan Lerman |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000356 |  | 18P000356 | FALSE | CNAS | SL5 ENTOMOLOGY PATCH AND PATCH |  | ENTOMOLOGY | 278 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  |  | 10 | TRUE |  |  | 43179 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000363 |  | 18P000363 | FALSE | PB&A | SL5 PAINT STOREHOUSE ADMINISTRATIVE OFFICE |  | CORP B |  | COMPLETE | Gerry Bomotti | TBD | ERICA HENDERSON |  | Paul Ditty |  | 13 |  | FALSE |  |  | 43185 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
18P000367 |  | 18P000367 | FALSE | CHASS | SL5 CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE |  | CHASS INT N | 3033 | COMPLETE | Juliet McMullin | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 23 | FALSE |  |  | 43186 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000369 |  | 18P000369 | FALSE | PB&A | SL5 BOYCE X-RAY IRRADIATOR PROJECT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 1407 | CANCELED BY CLIENT | Gerry Bomotti | TBD | KAREN JANIGA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 43186 | [6 empty] | 12/14/18, DL; This project was cancelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……DL, 5/9/18; Need to work on plans/permits…..DL, 6/16/18; Meeting with Bob and confirmed what is needed. I will work with Gunther on plans. Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall…..DL, 11/7/18; Material is on site. We will schedule the work soon…… |  | Ron Veloz |  | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000373 |  | 18P000373 | FALSE | PB&A | SL5 POLICE BLDG PAINTING IN DISPATCH AREA |  | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | KELLY DUNCAN |  | Paul Ditty |  |  | 8 | FALSE |  |  | 43192 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000379 |  | 18P000379 | FALSE | VC-RED | SL5 UOB PATCH AND PAINT |  | UNIV OFC BLD |  | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 43195 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000380 |  | 18P000380 | FALSE | SOM | SL5 SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 | SOM RSCH | 330 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 43195 | [6 empty] | Canceled per customer on 8/22/18. |  | Enrico Baez |  | NO | 2018-08-22 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000381 |  | 18P000381 | FALSE | ITS | SL5 ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 3 | 4 | FALSE |  |  | 43195 | [6 empty] | 1/15/19, DL; This project is complete. Note, Duffy only wanted the dutch door completed……..12/14/18, DL; This project is in progress and should be complete shortly after the new year……`DL, 7/11/18; Need to walk the project and schedule the work…… | 2018-07-06 | Ron Veloz |  | YES | 2019-01-15 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000382 |  | 18P000382 | FALSE | ITS | SL5 ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | PHYLLIS FRANCO |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 43195 | [6 empty] | 1/15/19, DL, This project is Complete……12/14/18, DL; This project is scheduled to be complete shortly after the winter break…….This project was scoped previously with the IR Team. We may need plans or a permit because we are installing a Dutch door…..DL, 7/11/18; Need to produce work orders and schedule the work….. DL, 7/25/18; Still need to produce work orders and schedule the work. Target date is 10/1/18 | 2018-07-06 | Ron Veloz |  | YES | 2019-01-15 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000383 |  | 18P000383 | FALSE | CHASS | SL5 HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT |  | HUM & SOC SC | 1302 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  | 4 | TRUE |  |  | 43196 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000385 |  | 18P000385 | FALSE | CHASS | SL5 HMSS INSTALL TV IN CONFERENCE ROOM |  | HUM & SOC SC | 1001E | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Dan Lerman |  | 19 | 19 | FALSE |  |  | 43165 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..12/14/18; Monitor is Complete, we still need to install power. The space is vacant…DL, 6/16/18; Pasted notes from FAMIS; University Writing program wants to install a 65 inch TV in the conference room at HMNSS 1001E. 1. Request to install the TV mount/ bracket on the wall; 2. Request to remove the old projector screen but leave two wood blocks on the wall; 3. Request to add a new double power outlet around the TV bracket area. If you have any questions, please contact Shanshan Liao at (shanshan.liao@ucr.edu or X27753)……DL, 7/25/18; Work orders are not produced. Need to assign and schedule the work…..……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez |  | YES | 2019-03-18 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000387 |  | 18P000387 | FALSE | CHASS | SL5 HMSS PATCH/PAINT |  | HUM & SOC SC | 3600 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 28 | FALSE |  |  | 43200 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000388 |  | 18P000388 | FALSE | CNAS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 43200 | [6 empty] | 8/14/19, DL; This project is 100% Complete………8/1/19, DL; This project work from Facilities Services should be complete in about 2- weeks…..7/15/19, DL, Work is in progress. Goal is to be complete with our scope near the first week in August……6/17/19, DL; This will be scheduled in July…….5/31/19, DL; Demo and removal of the dishwasher is. We will work on the installation and elctrical / power connections over the next three weeks. Note. Steam shut down is taking priority and the installation may be delayed….. 5/15/19, DL; We will schedule the work……..DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but there is no hard date as this is vacant space and we will access the space as time permits…… DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter….DL, DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans….7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved….. |  | Enrico Baez |  | YES | 2019-08-14 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
18P000389 |  | 18P000389 | FALSE | CHASS | SL5 PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A |  | PSYCHOLOGY1 | 2122 | COMPLETE | Juliet McMullin | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 5 | TRUE |  |  | 43200 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000390 |  | 18P000390 | FALSE | PB&A | SL5 UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD |  | UV BLDG B | 0240B | COMPLETE | Gerry Bomotti | TBD | LESLIE ROSE |  | Paul Ditty |  |  | 1 | FALSE |  |  | 43200 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000391 |  | 18P000391 | FALSE | BCOE | SL5 PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN |  | CHUNG HALL | 446 449 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | TRUE |  |  | 43200 | [6 empty] | DL, 5/5/18; Conducted scope visit with Paul and Maggie. This project is target date is August 30th. As of now, we have 10 business days to complete the work……. Dean's Office….DL, 6/16/18;Walked project with Jess and Paul. This will be a project will now incluclude flooring is 7- additional offices due to additional trip hazzards identified in 3 of 7 offices during the carpet scope. Maggie will pay four four of the office since they are still in good condition. We are still on schedule with the work.......Dan, 7/11/18; This project is still on schedule. Complete Date is 8/18/18 and scheduled to be complete on 8/31/18.....DL, 8/10/18; The project is on schedule and we will start on Monday.......Ahead of schedule, project will be complete on 8/29/18......DL, 9/6/18; This project is 100% complete. Note, Maggie did request Jess to come back and remove some glue and he has this scheduled..... |  | Dan Lerman |  | YES | 2018-09-10 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000392 |  | 18P000392 | FALSE | CNAS | SL5 BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 |  | BATCHELOR | 0 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Paul Ditty |  |  | 8 | TRUE |  |  | 43202 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000394 |  | 18P000394 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK |  | BOURNS | A0159A | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 2 | TRUE |  |  | 43202 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………….1/15/19, DL; Sound Soak is ordered and should arrive within two weeks……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; Need to review and scheudle…….DL, 7/11/18; Still need to review and scheudle…..DL, 8/22/18; This Project is complete but Maggie wants to see if the Faculty are happy with the results. We may install Sound Soak as a final option…… DL 9/6/18; Sent Maggie an email to see if she is satified with the work performed in regards to the sound proofing. I will have an update by the next Excel update….. DL, 9/19/18; The PI is out of town. Maggie will confirm the PI is satisiofd with the work when they return……on 9/18/18…DL, 10/8/18; Customer not satisfied with first round of sound proofing. We will proceed with Sound Soak material….. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000396 |  | 18P000396 | FALSE | CHASS | SL5 WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | Please patch and paint these two Political Science Staff Offices in the Watkins Hall 2122 "suite". 2122A belongs to Tanya Wine, FAO; 2122D belongs to Cindy Redfield, Principal Analyst. | WATKINS | 2122 | COMPLETE | Juliet McMullin | Cindy Williams | DAMARIS CARLOS | CINDY REDFIELD | Paul Ditty |  |  |  | TRUE |  |  | 43203 | [6 empty] | 08/10/18 D-MMN: Completed painting the finish. Pulled our masking and plastic wiped down the furniture. Replaced fixture covers. vacuumed the carpets and moved furniture back.08/07/18 D-MMN: Removed anchors, related boards. Filled holes with spackle and topped with joint compound. used one 4x4 wall patch. Returned and applied second coat of joint compound. 08/09/18 D-MMN: Completed applying primer, and then began applying Suprema. 08/08/18 D-MMN: Removed steel case and file cabinets from walls. Pulled anchors and filled with smooth se 20 and 2 coats of joint compound. Also finished any other patching. Taped the base and fixtures and covered furniture with plastic. Used a fan to dry patching. Sanded patches and began primer. Vacuumed debris. |  | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000400 |  | 18P000400 | FALSE | SOM | SL5 Covert suite 1116 and suite 1126 to office space | Provost has placed a hold on converting lab spaces into office spaces. | WEBBER | 1116 & 1126 | CANCELED BY FS | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  |  |  | FALSE |  |  | 43204 | [6 empty] | DL, 6/16/18; Waiting for update on Provost approval….DL, 7/11/18; Per email from Enrico on 7/10/18. The Provost put a hold on converting any lab space into officess…… |  | Enrico Baez |  | YES | 2018-07-10 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000410 |  | 18P000410 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 3148B | COMPLETE | Kim Wilcox | TBD | CANDICE GOMEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 43215 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000414 |  | 18P000414 | FALSE | CHANCELLOR | SL5 CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL |  | STUDENT SERV | 0 | COMPLETE | Kim Wilcox | TBD | DANIELLE GARCIA |  | Paul Ditty |  | 1 | 2 | FALSE |  |  | 43216 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000415 |  | 18P000415 | FALSE | CHASS | SL5 PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | Door and frame have been painted; construction to commence upon availability of the teams. | OLMSTED | 0 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | RYAN LIPINSKI |  | Dan Lerman |  |  | 10 | TRUE |  |  | 43228 | [6 empty] | 12/14/18, DL; Angel cancelled this project as it is no longer needed at this time……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 7/11/18; This project was scoped and part of the IRT. Plans and permits are approved. We will schedule the work and we will plan to have this project complet by 9/21/18…..8/10/18; WE have approved plans, this project is scheduled to start late August and will be complete early October……DL, 10/4/18; The door and frame is scheduled for delivery in 3-5 weeks, We will start the project when the doors and frame are on site……..DL, 11/7/18; Door and frame and painted. We will start the contruction in the near future…… |  | Dan Lerman |  | YES | 2018-12-14 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000416 |  | 18P000416 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTOR OFFICE PAINTING |  | HUM & SOC SC | 3002 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 9 | TRUE |  |  | 43217 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000417 |  | 18P000417 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTIONAL OFFICE PAINTING |  | HUM & SOC SC | 2106 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 14 | TRUE |  |  | 43217 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000418 |  | 18P000418 | FALSE | CHASS | SL5 HMSS OFFICE PAINTING |  | HUM & SOC SC | 2002 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 15 | TRUE |  |  | 43217 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000419 |  | 18P000419 | FALSE | CHASS | SL5 COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | FS to coordinate with client to scope the work. | WATKINS | 1320C&E | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 5 | 8 | TRUE |  |  | 43217 | [6 empty] | 2/14/19,DL; This project was canceled by Paul R. 2/1/19, DL; We will custom make Sound panels and will start the installation in the next 6-8 Weeks……….. |  | Enrico Baez |  | NO | 2019-02-14 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000420 |  | 18P000420 | FALSE | CHASS | SL5 COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | Canceled by Customer on prioritization 7/2/18 | WATKINS | 0 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  |  |  |  | Cancel | TRUE |  |  | 43217 | [10 empty] | YES | 2018-07-02 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000421 |  | 18P000421 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 2120 | COMPLETE | Kim Wilcox | TBD | CANDICE GOMEZ |  | Paul Ditty |  |  | 5 | FALSE |  |  | 43220 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000425 |  | 18P000425 | FALSE | BCOE | SL5 BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - |  | BOURNS | A0379 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 43221 | [6 empty] | DL, 6/7/18; Per Maggie; Luat Vuong arrives on or about August 15…... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected..…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/15/18........DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000426 |  | 18P000426 | FALSE | BCOE | SL5 BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER |  | BOURNS | A0375 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 43221 | [6 empty] | DL, 6/7/18; Per Maggie; A-375: Bhargav Rallabandi arrives on or about August 1….. DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/1/18.....DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000427 |  | 18P000427 | FALSE | BCOE | SL5 BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER |  | BOURNS | A0373 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 43221 | [6 empty] | DL, 6/7/18; Per Maggie email; This is our new Dean’s faculty office. Dean Lynch is already on site getting up to speed one-two days a week. This office is an ASAP...... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected.....DL, 7/11/18; This project is 100% complete...... |  | Paul Ditty |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000428 |  | 18P000428 | FALSE | SoB | SL5 OLMSTED RM 2352 PATCH/PAINT |  | OLMSTED | 2352 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 5 | FALSE |  |  | 43222 | [8 empty] | Paul Ditty |  | N/A | 2018-08-17 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000429 |  | 18P000429 | FALSE | BCOE | SL5 INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 |  | BOURNS | B0262 B0256 | COMPLETE | Christopher Lynch | TBD | KEVIN SCHULTE |  | Dan Lerman |  |  |  | TRUE |  |  | 43200 | [6 empty] | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment…..DL, 5/9/18; We are working on plans to submitt to A&E soon....DL, 5/24/18; Plans were submitted on 5/24/18.......DL, 6/12/18; Plans were approved. Cabinets are ordered. Materila is 6-8 Weeks out.....DL, 7/11/18; We have confirmation for delivery of material for mid August. Target Complete date is 9/7/18......DL, 8/10/18; Project has started. We will be complete with in two weeks......DL, 8/22/18; Work is 90% Complete..Project should be complete by 8/31/18........ DL 9/6/1/8; This project is 99% complete. The parts arrived today. I will be sending out an email to schedule the installation time for next week.......DL, 9/19/18; This project is 100% Complete........ |  | Dan Lerman |  | YES | 2018-09-19 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000432 |  | 18P000432 | FALSE | PB&A | SL5 BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 |  | BANNOCK H | H0101 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Paul Ditty |  |  |  | FALSE |  |  | 43224 | [8 empty] | Paul Ditty |  | N/A | 2018-07-13 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000434 |  | 18P000434 | FALSE | CNAS | SL5 BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY |  | BOYCE | 4478 | COMPLETE | Kathryn Uhrich | TBD | CHERYL GERRY |  | Paul Ditty |  |  | 3 | TRUE |  |  | 43229 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000435 |  | 18P000435 | FALSE | CAMPUS | SL5 HMSS HYDRATION STATION REQUEST |  | HUM & SOC SC | 3600 | COMPLETE |  |  | NELDA THOMAS |  | Dan Lerman |  |  | 30 | FALSE |  |  | 43230 | [6 empty] | 4/15/19, DL; This project is 100% Complete…..3/28/19, DL; Fountain is in. working on power and paint….. |  |  |  | NO | 2019-04-15 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000436 |  | 18P000436 | FALSE | CNAS | SL5 COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS |  | COLL BLDG NO | 210 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 36 | 30 | FALSE |  |  | 43230 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000438 |  | 18P000438 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING |  | CHUNG HALL | 415 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 10 | FALSE |  |  | 43234 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000439 |  | 18P000439 | FALSE | BCOE | SL5 CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING |  | CHUNG HALL | 315 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 11 | FALSE |  |  | 43235 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000442 |  | 18P000442 | FALSE | VC-RED | SL5 FAWCETT LAB 203 PATCH & PAINT |  | FAWCETT LAB | 203 | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 3 | FALSE |  |  | 43238 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000444 |  | 18P000444 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 |  | ARTS | 242 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 6 |  | TRUE |  |  | 43241 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-21 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
18P000445 |  | 18P000445 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 |  | ARTS | 225 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 11 | TRUE |  |  | 43241 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | Modify the existing room in Soil House 1 (attached to the Delphino Lab at the Rubidoux Facilities) to expand CCPP quarantine services to include USDA/CDFA compliance for installation of new Economic Development Administration (EDA) citrus growth chambers. | DELFINO HHSE |  | TO BE PERFORMED BY PD&C | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 43245 | [6 empty] | 12/7/20, DL: This project will be managed by PD&C…..9/30/20, DL: Project is still on Hold until Furhther notice………...8/5/20, DL: WE will work on plans in the next 30- 45 days……………6/17/20, DL: This project is under review and is on hold until further notice………10/3/19 O-ANS: Plan Development per Minor Reno Meeting. 10/1/19,DL; We are getting ready to start the plans as we are currently conducting resarch on products that will meet the needs of the space……………..5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman |  | YES | 2020-12-07 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 20-21
18P000454 |  | 18P000454 | FALSE | BCOE | SL5 BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS |  | BOURNS | A0346 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  |  | 9 | FALSE |  |  | 43249 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000456 |  | 18P000456 | FALSE | VC-STU AFF | SL5 HUB--UTILITY METERS | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. | HUB |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  |  | 1 | FALSE |  |  | 43250 | [8 empty] | Enrico Baez |  | YES | 2019-01-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000459 |  | 18P000459 | FALSE | PB&A | SL5 BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 |  | BARN |  | COMPLETE | Gerry Bomotti | TBD | GUSTAVO PLASCENCIA |  | Dan Lerman |  |  | 6 | FALSE |  |  | 43251 | [8 empty] | Enrico Baez |  | YES | 2018-09-21 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000463 |  | 18P000463 | FALSE | SoB | SL5 ANDERSON HALL PATCH/PAINT-102C |  | ANDERSON 1 (N) | 0102C | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 4 | FALSE |  |  | 43255 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000464 |  | 18P000464 | FALSE | CNAS | SL5 PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 35 |  | FALSE |  |  | 43328 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
18P000465 |  | 18P000465 | FALSE | CNAS | SL 5 GEOLOGY 2258B AND 2258C - PATCH/PAINT |  | GEOLOGY | 2258B & 2258C | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 43257 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
18P000468 |  | 18P000468 | FALSE | CHASS | SL5 WATKINS 1222/1223 PATCH/PAINT |  | WATKINS | 1222 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 13 | TRUE |  |  | 43262 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000469 |  | 18P000469 | FALSE | CHASS | SL5 WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS |  | WATKINS | 1317 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 43262 | [8 empty] | Paul Ditty |  | N/A | 2018-07-25 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000470 |  | 18P000470 | FALSE | SPP | SL5 Student Check-in Lobby |  | CHASS INT S | 4133 Corridor | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ |  | Dan Lerman |  |  | 1 | FALSE |  |  | 43262 | [6 empty] | DL, 6/16/18; I walked this project with Luis and Mark this week. They want this work completed by July 9th. Paint, data, electrical, chair rail and signage is requested. I need to review project with Paul and Robert C. DL, 7/11/18; Robert C. Ordered material and we will complete the install first part of next week We will scheudle the paint after Robert is Complete. Target Complete Date is 7/2018......DL, 7/25/18; WE have the electrical materila, plans were submitted. Once plans are reviewed and approved, we will proceed with the work. Target date is two weeks after plans are approved......DL, 8/10/18; Eletrical is complete. Pending paint. Paint will be scheduled in the near future. DL, 8/22/18; This project will be Complet on Saturday.....DL, 9/6/18. I miossed the chair rail request on this project. I will order the chair rail in the near future. The chair rail is the only item needed to complete this project. Aprroximately 20 lineal feet......DL, 9/19/18; Chair rail is ordered. We will schedule the install when the material arrives....... |  | Dan Lerman |  | YES | 2018-08-23 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18P000471 |  | 18P000471 | FALSE | ITS | SL5 WCH INSTALL SECURITY FENCE |  | CHUNG HALL | 134 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  |  | 5 | FALSE |  |  | 43263 | [6 empty] | DL, 7/4/18; Walked this project with Angel, This request is to install security fence with Sliding gate and welded webs to increase security. Space is vacant and ready to schedule work. Need to walk with Corey to see if this is a project they can do or sub out to De ANza fence......DL 7/25/18; Still need to walk project with Corey. Dl, 8/10/18; Site walk complete, we are waiting on estimates. WE will try and schedule the work with in the next 30- days....DL, 8/22/18; Work is scheduled for August 27th. Still need to order hardware.....DL, 9/6/18; The fence is installed and Angel is very Happy, but I need to check the project to verify we are good to go....DL, 9/19/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-09-19 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000472 |  | 18P000472 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALL |  | CHUNG HALL | 458 | COMPLETE | Christopher Lynch | TBD | JANNA LE BLANC |  | Paul Ditty |  |  | 1 | TRUE |  |  | 43263 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000473 |  | 18P000473 | FALSE | CNAS | SL5 PIERCE NEW CARPET & PAINT FACULTY OFFICE |  | PIERCE | 202 | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Paul Ditty |  | 1 | 5 | TRUE |  |  | 43263 | [8 empty] | Paul Ditty |  | N/A | 2018-09-26 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000474 |  | 18P000474 | FALSE | ITS | SL5 MS&E ELECTRICAL MODIFICATIONS FOR ITS |  | MAT SCI ENGR | 119 | COMPLETE | Danna Gianforte | Shelley Gupta | MICHAEL CAPRIOTTI |  | Robert Corey |  |  | 1 | FALSE |  |  | 43264 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…….2/28/19, DL; Work is scheduled with Darrenn F. for Spring Break…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. |  | Enrico Baez |  | YES | 2019-03-28 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000476 |  | 18P000476 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER & DRYER | Canceled project, work completed on 18W015691 in July. | BOYCE | 6444 | CANCELED BY CLIENT | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  |  |  | FALSE |  |  | 43265 | [6 empty] | Duplicate to 18W015691; complete |  |  |  | NO | 2018-07-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
18P000478 |  | 18P000478 | FALSE | UNDERGRAD ED | SL5 CARPET, PAINT, & AIR HANDLING MODIFICATION |  | HINDERAKER | 1120H | COMPLETE |  |  | TRACEY SCHOLTEMEYER |  | Dan Lerman |  |  | 1 | FALSE |  |  | 43267 | [6 empty] | DL, 7/4/18; This project is scoped; Need to remove Switch gear storage rack components, remove electrical conduits, plywood backer board from walls, paint and floor covering. We will schedule this work to be complete by Fall 2018 academic year....DL, 7/11/18; Need to produce work orders and schedule the work. Target Complete date is 9/14/18... Space is vacant....DL, 8/10/18; Work has started and we are on schedule...... DL, 8/22/18; Demo is almost complete. This target date is 9/21/18......9/19/18; All trades are complete. New carpet to be installed on 9/21/18. .....DL, 9/19/18; This project is scheduled to be complete this week....... |  | Dan Lerman |  | YES | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000480 |  | 18P000480 | FALSE | CNAS | SL5 BG - LOWER RESTROOMS-PAINTING-FLOORS | Canceled by Facilities Services; Work is not within the SLA and is not needed. | BOTGDN RSTRM |  | CANCELED BY FS | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Paul Ditty |  | 23 |  | FALSE |  |  | 43276 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
18P000481 |  | 18P000481 | FALSE | CHASS | SL5 CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 |  | CHASS INT S | 3104 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 10 |  | FALSE |  |  | 43276 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
18P000482 |  | 18P000482 | FALSE | SoB | SL5 CARD ACCESS SYSTEM ANDERSON SOUTH |  | ANDERSON 2 (S) |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 1 | FALSE |  |  | 43277 | [6 empty] | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with JasonDL, 7/11/18; Need to check in with Jason on status for his side of the project.....DL, 7/25/18; JAson's team is ready to install but the Anderson IT department does not have the necesary software. We will start the work when the software is up and running...... 8/12/18 DND FAMIS Status noted completion on 8/2/18. |  | Dan Lerman |  | YES | 2018-08-02 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18P000483 |  | 18P000483 | FALSE | PB&A | SL5 INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | FS to coordinate with customer to scope the work. | PARKING LOT 1 |  | CANCELED BY CLIENT | Gerry Bomotti | TBD | AMANDA GREY |  | Enrico Baez |  | 7 |  | FALSE |  |  | 43277 | [6 empty] | Waiting for Amanda Grey to verify ownership of chain link fence. Once confirmed will contract with De Anza to install 36" wide gate. | 2018-08-29 | Enrico Baez |  | YES | 2018-12-03 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
18P000484 |  | 18P000484 | FALSE | ATHLETICS | SL5 INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | Project will be managed by A&E for completion. | SOFTBALL STG |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 43277 | [6 empty] | 2/1/19, DL; This is a PD&C Project due to IRT walk. Project will exceed $50,000……….. |  | Enrico Baez |  | NO | 2019-02-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
18P000485 |  | 18P000485 | FALSE | SOM | SL5 SOMR PATCHING AND PAINTING |  | SOM RSCH |  | COMPLETE | Deborah Deas | Deborah Trujillo | DANA ABOU ABBAS |  | Paul Ditty |  | 6 |  | TRUE |  |  | 43279 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
18P000486 |  | 18P000486 | FALSE | CNAS | SL5 PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 43279 | [6 empty] | 8/1/19, DL; This project is 100% Complete…… 6/17/19, DL; This project is making good progreess and will be complete near mid- July…..5/31/19, DL; This project is making good progress and we are hopeful to be complete on or before July 1st……5/1/19, DL: This project is in grogress and moving forward. Target complete date is 6- weeks… 4/15/19, DL; Started Demolition phase….2/28/19, DL; We will work on the plans in the next 30-days.12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
18P000487 |  | 18P000487 | FALSE | CHANCELLOR | SL5 SKYE HALL PATCH HOLES AND PAINT |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | TBD | SONIA ZAMORA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43279 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
18W000455 |  | 18W000455 | FALSE | CNAS | SL5 CHAPMAN CLEAN WINDOWS |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  |  | 37 | FALSE |  |  | 42927 | [6 empty] | Dl, 7/4/18; All Windows in Chapman were cleaned by Ductch Touch. This Project is 100% Complete |  | Ron Veloz |  | YES | 2018-07-11 | Summer 2018 | FS | FALSE | 2017 | 2021-01-16
18W001170 |  | 18W001170 | FALSE | CHASS | SL5 ARTS: PAINT CLASSROOMS |  | ARTS | 407 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 27 | FALSE |  |  | 42941 | [8 empty] | Enrico Baez |  | YES | 2018-09-24 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
18W006022 |  | 18W006022 | FALSE | SOM | INSTALL CURTAIN ROD IN RESEARCH SPACE |  | SOM RSCH | 336 | COMPLETE | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 43035 | [6 empty] | DL, 5/24/18; Need to review scope with Enrico….DL, 7/11/18; Enrico produced work orders for sheet metal shop. This is a singel trade project. |  | Enrico Baez |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2017 | 2021-01-16
18W007453 |  | 18W007453 | FALSE | ITS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  |  |  | FALSE |  |  | 43069 | [6 empty] | 07/22/19 O-ANS: Work Order converted to project # 19P000433. For further updates, see 19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  |  |  |  | 2019-07-22 | Winter 2019 | FS | FALSE | 2017 | 2021-01-16 | FY 19-20
18W008762 |  | 18W008762 | FALSE | CHASS | SL5 HUMANITIES: PATCH & PAINT |  | HUM & SOC SC | 2415 | COMPLETE | Juliet McMullin | Cindy Williams | ANDREW ALONSO |  | Paul Ditty |  | 20 | 22 | FALSE |  |  | 43102 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18W009630 |  | 18W009630 | FALSE | PB&A | SL5 BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. | PHYS PL STOR | 100 | CANCELED BY CLIENT | Gerry Bomotti | TBD | JUDY HODGE |  | Dan Lerman |  |  |  | FALSE |  |  | 43122 | [6 empty] | 3/28/19, DL; This project is cancelled per Judy Hodge….DL, 6/16/18; Project includes demo wall/door install new wall, dry wall, paint, door, eletrical outlets, lighting, smoke relocation, lighting motion, new t-bar, relocate heat pump, andn install new carpet…...DL, 7/11/18; Need to work on plans….. Target complete date is late Fall..... |  | Enrico Baez |  | YES | 2019-03-28 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18W011161 |  | 18W011161 | FALSE | CNAS | SL5 REPLACE CARPET |  | SCIENCE LAB1 | 301 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO |  | Dan Lerman |  |  |  | FALSE |  |  | 43154 | [6 empty] | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project……DL, 5/21/18; Floor covering is selected. Work will be scheudled for Mid June….DL, 5/24/18; The install is scheduled for June 18th & 19th……DL, 7/11/18; This Project is 100% Complete...... |  | Dan Lerman |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18W011672 |  | 18W011672 | FALSE | CNAS | SL5 ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY |  | ENTOMOLOGY | 268 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  |  | 9 | TRUE |  |  | 43167 | [6 empty] | Relocate white board from East wall onto the West wall, where high table was removed, 24" away from North end of wall. |  | Paul Ditty |  | N/A | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18W011691 |  | 18W011691 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | FS to coordinate with client to schedule work for completion. | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 4 | 11 | TRUE |  |  | 43167 | [6 empty] | 12/17/18 DND: Canceled by client on 12/17/18. |  | Paul Ditty |  | N/A | 2018-12-17 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18W011692 |  | 18W011692 | FALSE | CNAS | SL5 ENTOMOLOGY; PAINT/PATCH LAB |  | ENTOM MUSEUM | 211 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 43167 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18W011772 |  | 18W011772 | FALSE | PB&A | SL5 PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | Canceled per customer on priority list 7/3/18 | PRINT MOD |  | CANCELED BY CLIENT | Gerry Bomotti | TBD | PRISCILLA MARTIN |  | Dan Lerman |  |  | Canceled | FALSE |  |  | 43171 | [6 empty] | DL, 4/29/18; Pasted from WO; install an outside electrical outlet based on the attached amazon specs. also estimate for removing and sealing the outside vent from the copier. fyi_the copier will be moving within the next few months…..DL, 7/11/18; Need to verfy scope and schedule the work...... |  | Enrico Baez |  | YES | 2018-07-03 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
18W013160 |  | 18W013160 | FALSE | CNAS | BEES- PATCH & PAINT 2460D & 2460F |  | GEOLOGY | 2460 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO |  | Paul Ditty |  | 33 | 29 | FALSE |  |  | 43196 | [8 empty] | Paul Ditty |  | N/A | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18W013973 |  | 18W013973 | FALSE | VC-RED | SL5 BSL3 FACILITY- ASSEMBLE AND INSTALL |  | UNIV OFC BLD |  | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Enrico Baez |  |  | 2 | FALSE |  |  | 43209 | [6 empty] | FAMIS NOTES 8/22: Plumbing filter system was installed and ice maker installed. Request for microscope and incubator moved into containment by customer. Complete 9/24/18 |  | Enrico Baez |  | YES | 2018-09-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18W015691 |  | 18W015691 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER AND DRYER |  | BOYCE | 6444 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  |  |  |  | 1 | FALSE |  |  | 43250 | [6 empty] | DL, 7/11/18; This project is in progress and almost complete. Target complete date is 7/20/18….. |  | Dan Lerman |  | YES | 2018-07-11 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18W016588 |  | 18W016588 | FALSE | CHASS | PATCH AND PAINT FOR FACULTY |  | SPROUL | 4105 | COMPLETE | Juliet McMullin | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | N/A | TRUE |  |  | 43270 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
18W016621 |  | 18W016621 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Juliet McMullin | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 17 |  | FALSE |  |  | 43271 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000006 |  | 19P000006 | FALSE | CNAS | SL5 MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 |  | MAT SCI ENGR | 310 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 43283 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..2/14/19, DL; This project is 90% Complete. ………2/1/19, DL; This Project started to day. We are scheduled to be complete by the end of February………..1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. | 2018-09-28 | Ron Veloz |  | YES | 2019-03-18 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000009 |  | 19P000009 | FALSE | SOM | SL5 SOME -- PAINT, SPACKLE AND CLEANING NEEDED |  | SOM EDUC | 2615 | COMPLETE | Deborah Deas | Deborah Trujillo | BEVERLEY HERBERT |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43283 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000011 |  | 19P000011 | FALSE | CHASS | SL5 PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED |  | PSYCHOLOGY1 | 2111A | COMPLETE | Juliet McMullin | Cindy Williams | LORENA QUINTANA |  | Paul Ditty |  | 4 |  | TRUE |  |  | 43284 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000012 |  | 19P000012 | FALSE | SOM | SL5 SOME--PATCH & PAINT |  | SOM EDUC | 2638 | COMPLETE | Deborah Deas | Deborah Trujillo | MARISELA MARTINEZ |  | Paul Ditty |  | 7 |  | TRUE |  |  | 43287 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000014 |  | 19P000014 | FALSE | SOM | SL5 SOME - PATCH & PAINT |  | SOM EDUC | 2609 | COMPLETE | Deborah Deas | Deborah Trujillo | MARISELA MARTINEZ |  | Paul Ditty |  | 8 |  | TRUE |  |  | 43290 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000015 |  | 19P000015 | FALSE | PB&A | SL5 POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING |  | POLICE TRLR | 1 | COMPLETE | Gerry Bomotti | TBD | KELLY DUNCAN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 43291 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000017 |  | 19P000017 | FALSE | SoB | SL5 ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD |  | ANDERSON 1 (N) | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  |  | FALSE |  |  | 43292 | [6 empty] | DL, 9/6/18; Monitors are installed. Need to schedule the electrical. Target date is 9/21/18…… |  | Enrico Baez |  | YES | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000018 |  | 19P000018 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER |  | ANDERSON 1 (N) | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 43292 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000021 |  | 19P000021 | FALSE | ITS | SL5 ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS |  | ITS CENTER |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43293 | [6 empty] | 4/15/19, DL; This project is 100% Complete…… 3/28/19, DL; Monitors are done. Nee to finish the install of data and power…….12/14/18, DL; Still need to review scope….. |  | Enrico Baez | 1. Telecom Building - Conference Space Electricians Power Requirements: • Install double duplex(quad outlet), AC power on East wall at display location (4S Box) low profile • All electrical junction boxes, J-boxes, and conduit can be surface mounted. J-boxes to be located behind TV. Data Requirements: • Install single gang junction box on East wall behind display with Panduit running to specified location (for telecom network drops) o Single gang, low profile junction box o (conduit to be lead through masonry wall above T Bar ceiling in adjacent room. O (Low profile boxes for data ports) • Single gang box, mounted behind TV location, for data. • Note: Non-traditional wall – masonry Carpenters • Install mounting bracket for display on East wall • note: Non-traditional wall – masonry Painters • Paint junction boxes and conduit to match wall. 2. Intellicenter - First Floor Common Area Carpenters • Install mounting brackets on East Wall for each display (2 total) • (ITS to note the top of the bracket) 3. SOM-E - 1675A DataCenter Electricians Power Requirements: • Install double duplex(quad outlet), AC power on North wall at each display location (2 total) o Surface mounted J Boxes and Conduit Data Requirements: • Install single gang junction box on North wall at each display location with conduit/panduit running to specified location (for telecom network drops) (2 total) o (Wire mold boxes for both power and data) (2inch boxes – low profile boxes for data ports) o Data conduit to stub up and terminate through T-bar ceiling panels. • All conduit and J-boxes to run upward through T-bar ceiling Carpenter • Install mounting bracket for each display on North wall (2 total) • Install backing for mounts in adjacent data room in shelving. Painters • Patch and paint installation area as needed Location Notes • Non-traditional wall – drywall over carpentry 4. ITS Building - 174 Electricians • Install double duplex, AC power on East wall at each display location (2 total) • Install single gang junction box on East wall at each display location with conduit above ceiling (for telecom network drops) (2 total) o Terminate Data conduit above T-bar ceilings Carpenters: • Install mounting bracket (marked on the wall) for each display on East wall (2 total) Location Notes: • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 5. ITS Building - Main Lobby Electricians • Install double duplex, AC power on South wall at display location • Install single gang junction box on South wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on South wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 6. ITS Building – AVC / CIO’s Office (ITS 147) Electricians • Install double duplex, AC power on North wall at display location • Install single gang junction box on North wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on North wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 7. ITS Building Room 138 Electricians • Install double duplex, AC power on East wall at display location • Install single gang junction box on East wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on East wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000022 |  | 19P000022 | FALSE | PB&A | SL5 HUB--PAINT TWO WALL AS SCOTTY'S HUB |  | HUB | 101 | COMPLETE | Gerry Bomotti | TBD | DIANE THOMAS |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43293 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-17 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000023 |  | 19P000023 | FALSE | BCOE | SL5 PAINT ACCENT WALL | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | TBD | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43294 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-18 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000026 |  | 19P000026 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALLS | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | TBD | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43297 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-18 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000027 |  | 19P000027 | FALSE | ATHLETICS | SL5 ATHLETICS PATCH & PAINT ROOM | 9/19/18 | ATH DANCE | 0120C | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 43297 | [6 empty] | DL, 9/19/18; This Project is 100% Complete……. |  | Paul Ditty |  | N/A | 2018-09-19 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000028 |  | 19P000028 | FALSE | BCOE | SL5 BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS |  | BOURNS | A0169 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | FALSE |  |  | 43297 | [6 empty] | 5/1/19, DL; This project is 100% Complete…..3/28/19, DL; Monitor mounts were removed, Patch and paint will be completed in the near future……2/28/19, DL; Will schedule the project to be complete the first week in April…… | 2018-11-14 | Ron Veloz |  | YES | 2019-05-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000029 |  | 19P000029 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | Canceled; duplicate request to be completed with 19P000059 | CHUNG HALL | 205 | CANCELED BY CLIENT | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 43297 | [6 empty] | Canceled; duplicate request to be completed with 19P000059 |  | Ron Veloz |  | NO | 2018-09-18 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000030 |  | 19P000030 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT |  | OLMSTED | 2301 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43297 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000031 |  | 19P000031 | FALSE | CNAS | SL5 BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) |  | BIOLOGIC SCI | 3101 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 40 |  | FALSE |  |  | 43297 | [6 empty] | 6/15/19, DL; This Project is 100% Complete…...5/1/19, Dl; This project will be complete on 5/5/19…..3/28/19, DL; Need to schedule a site visit with Estella. Left voice mail message on 3/28/19 to schedule site visit……..12/14/18, DL; This is prioritized at #40 and will not be scheduled in the near future….. |  | Enrico Baez |  | YES | 2019-06-15 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000032 |  | 19P000032 | FALSE | SOM | SL5 Reconfigure recepetion desk to fit two FTEs. |  | SOM EDUC | 2608 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 5 | 1 | FALSE |  |  | 43298 | [6 empty] | 5/1/19, DL; This project is 100% Complete….. 3/28/19, DL; Cabinet workl is complete. We need to finish the carpet and final laminate material…….2/28/19, DL; Conducted site visit with Chad. We will complete the work in the next two weeks…….2/1/19, DL; I Walked this project this week. We will try and schedule the work in the next 30- days…….12/14/18, DL, Still need to conduct site visit and schedule the work… | 2018-10-17 | Ron Veloz | Remove lower the left lower cabinet to create an additional work station. SOW: Remove/demo cabinet, install a new corbel patch floor with similar carpet and install 4" rubber base as needed. | YES | 2019-05-01 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000033 |  | 19P000033 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT | Duplicate request to 19P000030; Canceling project to be completed on other request. | OLMSTED | 2301 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 43297 | [6 empty] | Duplicate to project 19P000030. Canceling project. |  | Paul Ditty |  | N/A | 2018-10-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000035 |  | 19P000035 | FALSE | BCOE | SL5 WCH--INSTALL NEW LED DISPLAY IN OFFICE |  | CHUNG HALL | 354 | COMPLETE | Christopher Lynch | TBD | SARA GALLOWAY |  | Dan Lerman |  | 9 |  | FALSE |  |  | 43297 | [6 empty] | 12/14/18, DL; This Porject is 100% Complet…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Install scheduled for this Friday. | 2018-10-03 | Ron Veloz |  | YES | 2018-11-19 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000037 |  | 19P000037 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BLDG--PATCH WORK AND PAINTING |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43298 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000042 |  | 19P000042 | FALSE | CNAS | SL5 COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL |  | COLL BLDG NO | 200 | COMPLETE | Kathryn Uhrich | TBD | LISA DUNMORE |  | Paul Ditty |  | 38 |  | FALSE |  |  | 43301 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000043 |  | 19P000043 | FALSE | CNAS | SL5 SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | Customer called and canceled the work on 10/23/18. | SCIENCE LAB1 | 309 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | 19 |  | FALSE |  |  | 43301 | [7 empty] | 2018-10-22 | Ron Veloz |  | YES | 2018-10-23 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000044 |  | 19P000044 | FALSE | VC-RED | SL5 PATCH AND PAINT |  | SPIETH | 345 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43304 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000045 |  | 19P000045 | FALSE | CNAS | SL5 PREPARE LOCATION AND UTILITIES FOR INSTALL |  | BOYCE | 2407 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Dan Lerman |  | 14 |  | FALSE |  |  | 43304 | [8 empty] | Ron Veloz |  | YES | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000046 |  | 19P000046 | FALSE | BCOE | SL5 PATCH AND PAINT PLUS REPLACE BLINDS |  | BOURNS | A0131 | COMPLETE | Christopher Lynch | TBD | NANCY FORD |  | Paul Ditty |  | 2 |  | TRUE |  |  | 43304 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000049 |  | 19P000049 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT |  | PHYSICS | 3036 | COMPLETE | Kathryn Uhrich | TBD | JAZMIN CHAVEZ |  | Paul Ditty |  | 39 |  | FALSE |  |  | 43306 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000053 |  | 19P000053 | FALSE | SoB | SL5 ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S |  | ANDERSON 1 (N) |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 2 | FALSE |  |  | 43203 | [6 empty] | DL 8/22/18; two out of four monitors are complete. WE still need to install powree at four locations…….DL, 9/6/18; Still need Electrical installed……. Planing to have complete by 9/21/18……. This is aqctually 4- monitors in four locations. We should ensure each monitor is treated as an indidual project.......DL, 9/19/18; All monitors are installed. Robert will schedule the electricans this week or early next week...DL, 10/4/18; This project is 100% Complete..... |  | Enrico Baez |  | YES | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000054 |  | 19P000054 | FALSE | GSOE | SL5 PATCH & PAINT OFFICE |  | SPROUL | 2131 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43307 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000055 |  | 19P000055 | FALSE | CNAS | SL5 CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM |  | COLL BLDG NO | 207 | COMPLETE | Kathryn Uhrich | TBD | LISA DUNMORE |  | Dan Lerman |  | 32 | 24 | FALSE |  |  | 43238 | [6 empty] | 4/15/19, DL; This project is 100% Complete…….3/28/19, DL; Need to order material and schedule the work…… Work order is assigned. 12/14/18, Dl; This project is prioritized at 32 and will not be scheduled in the near futurer…….DL, 7/11/18; Correction, I did not scope this yet, I thought we were talking agout the door bell and ADA operator. I will check in with Ronda and verify the scope…… DND 7/30/18: Created project to replace WO #18015182; project #19P000055 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. | 2018-11-29 | Ron Veloz | SOW is to install a new exhaust fan at the second floor toilet room. Roof access is available from the access panel in the closet located in the room 210 next door. There is roof is transite per Jess. Abatement is necessary for roof penetrations and possibly has lead paint on ceilings and walls. | YES | 2019-04-15 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000056 |  | 19P000056 | FALSE | CHASS | SL5 HMSS CAPABILITY OF MOUNTING A TV |  | HUM & SOC SC | 1212 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  |  | 18 | FALSE |  |  | 43011 | [6 empty] | 12/14/18, DL; Monitor is complete. Still need to work on electrical……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope with Enrico and schedule the work…. Work orders are not produced. Need to assign and schedule the work DND 7/30/18: Closed work order #18W004822; created project #19P000056……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | 3/04/19, DL; Allison Rodgers confirmed this project is 100% Complete…. | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2017 | 2021-01-16
19P000058 |  | 19P000058 | FALSE | CNAS | SL5 Assess Feasiblity of Removing/Replacing Growth Chambers |  | GH18 | 18 | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  |  |  | FALSE |  |  | 43187 | [6 empty] | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing...DL, 5/9/18; Project is scoped. Need to schedule the work.....Plumbers and HVAC are working on this. Still need to have electrical removed. I am working wiht Patty on who can do the demo and removal.....DL, 7/11/18; I need to check in with Ken to see if refrigerant is recovered. will isue work order to disconnect electrical..... I checked in with our campus surplus and do not have any contacts to dis,matel the very large growth Chambers. I need to inform Patty and suggest that she have Burges demo and move the Growth Chambers......We will be complete with our portion of this project before 8/1/18.......DL, 8/10/18; All work is done except the disconnect for electrical. I need to check and see if the electrical. Per FAMIS complete on 8/22/18 |  |  |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
19P000059 |  | 19P000059 | FALSE | BCOE | SL5 CHUNG HALL 201 SECURITY SYSTEM INSTALL | ITS to install cameras, no work by FS Required. | CHUNG HALL | 201 | CANCELED BY FS | Christopher Lynch | TBD | MAGARET SOUDER |  | Dan Lerman |  | 10 | 7 | FALSE |  |  | 43298 | [6 empty] | DND 7/30/18 Project #19P000059 to replace REF CPMS # 9054 Ron to speak with ITS to complete installation. |  | Ron Veloz |  | YES | 2018-07-30 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000060 |  | 19P000060 | FALSE | BCOE | SL5 CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | CHUNG HALL | 223 & 224 | TO BE PERFORMED BY PD&C | Christopher Lynch | TBD | MAGARET SOUDER |  | Dan Lerman |  | 6 | 4 | FALSE |  |  | 43235 | [6 empty] | 2/1/19, DL; Thios is a PD&C project. Maggie S. is aware this project may be a $130,00. project……DL, 7/25/18; This project is complicated and plans/permits will be required. This project will also require Air Hanlers to be shut down so Vibration dampners can be instlled. We will work on the plans in the next 45 days. This project should be scheduled during the Winter. We may also need to rent a large portable air handler to ensure the Large server room can maintain temp……. Project #19P000060 to replace REF CPMS # 9043. DL, 11/7/18; Sent Maggie an email on 11/7/18 informing her this project is well beyond our scope and $50K threshold. |  | Dan Lerman |  | YES | 2019-02-01 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000061 |  | 19P000061 | FALSE | CHASS | SL5 PSYCHOLOGY 1111H-PATCH HOLES IN WALL |  | PSYCHOLOGY1 | 1111H | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43311 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000062 |  | 19P000062 | FALSE | CNAS | SL5 MSE 169-MINOR RENOVATION - NEW FACULTY |  | MAT SCI ENGR | 169 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 5 | 19 | TRUE |  |  | 43311 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………..1/15/19, DL; This project is 99% complete pending one water heater. Water heater is not here yet……12/14/18, DL; This project is 95% complete. The water heater is scheduled for delivery shortly after the new year. We will complete the install when the heater arrives…… 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 9/6/18; We will have the power and cabinets removed by 9/19/18. We are in the process of producing plans for this project. Once the plans are approved, we will proceed with the project. Note, we still need to obtain important information and some specifications regarding the procured base cabinets and counter tops, bio safety cabinet, diswasher, and freezer. ……DL, 7/7/18; The work is 90% complete. We are waiting on parts which have a 4-6 week lead time. We will finsh the balance of the project when the parts arrive….. | 2018-08-22 | Ron Veloz |  | YES | 2019-02-01 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000063 |  | 19P000063 | FALSE | CHASS | SL5 NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS |  | PSYCHOLOGY1 | 2124 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 43312 | [8 empty] | Paul Ditty |  | NO | 2018-09-26 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000102 |  | 19P000102 | FALSE | CNAS | SL5 PATCH & PAINT FRONT CORNER OF OFFICE |  | LIFE SCIENCE | 2930 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 42 |  | FALSE |  |  | 43313 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000106 |  | 19P000106 | FALSE | CNAS | SL5 PHYICS 1134 - UTILITIES REQUEST |  | PHYSICS | 1134 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 15 |  | FALSE |  |  | 43313 | [6 empty] | 6/15/19, DL; This Project is 100% Complete…...5/1/19, DL; Project should be complete this week or early next week…..3/28/19, DL; Power is complete. Need to finish chilled water…… 2/1/19, DL; Review scope with Customer. Still need to review with Brian from the Electic shop…………….12/14/18, DL; No update…. | 2018-11-07 | Ron Veloz |  | YES | 2019-06-15 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000122 |  | 19P000122 | FALSE | CHANCELLOR | SL5 REMOVE, PATCH & PAINT AND HANG |  | STUDENT SERV | 2222 | COMPLETE | Kim Wilcox | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43314 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000124 |  | 19P000124 | FALSE | VC-STU AFF | SL5 PAINT ROOMS 115 AND 116 |  | COSTO HALL | 125 | COMPLETE | Brian Haynes | Cathy Eckman | LINDA KELLEY |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43314 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000126 |  | 19P000126 | FALSE | CNAS | SL5 CHEMICAL SCIENCE - MINOR RENOVATIONS |  | CHEMICAL SCI | 455 | COMPLETE | Kathryn Uhrich | TBD | KEVIN KOU |  | Dan Lerman |  | 6 |  | TRUE |  |  | 43315 | [6 empty] | 12/14/18, DL; This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL,11/7/18; Paint is complete, Plumbing shop is planning to schedule the work in the near future…… |  | Ron Veloz |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000127 |  | 19P000127 | FALSE | CNAS | SL5 PIERCE PATCH & PAINT | Duplicate request to be combined with 19P000239 | PIERCE | 2301 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | MICHELLE KING |  | N/A |  | Canceled |  | FALSE |  |  | 43315 | [6 empty] | Paul Ditty |  | Paul Ditty |  |  | 2018-09-21 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000129 |  | 19P000129 | FALSE | BCOE | SL5 HANG MONITORS AND BOARDS |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | TBD | RICHARD BAIN |  | Dan Lerman |  | 8 |  | FALSE |  |  | 43318 | [6 empty] | 12/14/18, DL; This Project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Dry errase boards and Monitor mounts are installed. Still need to install monitors, corner guards and monitors….. |  | Ron Veloz |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000133 |  | 19P000133 | FALSE | CNAS | SL5 PATCH HOLES AND PAINT |  | BATCHELOR | 2203 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Paul Ditty |  | 43 |  | FALSE |  |  | 43319 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000137 |  | 19P000137 | FALSE | CNAS | SL5 LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM |  | LIFE SCIENCE | 2545 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 12 |  | FALSE |  |  | 43320 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000170 |  | 19P000170 | FALSE | CNAS | SL5 INSTALL NEW IRRADIATOR INSTRUMENT |  | MAT SCI ENGR | 51 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 16 |  | FALSE |  |  | 43320 | [6 empty] | 2/14/19, DL; This project is 100% Complete………2/1/19, DL; Power is complete. Chilled water will be complete next week…………..1/15/19, DL; Electric is commplete, Water will be complete with in two weeks. Equipment should be on site soon…12/14/18, DL; This project is currently on hold per RED…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; The unit is schedukled for delivery in the next three weeks. | 2018-09-19 | Ron Veloz |  | YES | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000171 |  | 19P000171 | FALSE | CHASS | SL5 HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST |  | HUM & SOC SC | 1614 | COMPLETE | Juliet McMullin | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 16 |  | FALSE |  |  | 43321 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000172 |  | 19P000172 | FALSE | VC-STU AFF | SL5 HEALTH SERV- PAINT RESTROOM IN LABORATORY |  | HEALTH SERV | 0113A | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43321 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000173 |  | 19P000173 | FALSE | CHASS | SL5 PAINT/PATCH UNIVERSITY THEATER LOBBY |  | THTR WKSH | 0400A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 23 |  | FALSE |  |  | 43321 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000174 |  | 19P000174 | FALSE | CNAS | SL5 BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT |  | BATCHELOR | 2112 | COMPLETE | Kathryn Uhrich | TBD | AMY RICKS |  | Dan Lerman |  | 37 |  | FALSE |  |  | 43305 | [6 empty] | 5/1/19, Dl; This project is 100% Complete….. 4/15/19, DL; This project should be complete in 2-weeks…… 12/14/18, DL; This project is priortized at 37 and will not be scheudled until further notice…… | 2018-09-19 | Ron Veloz |  | YES | 2019-05-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000175 |  | 19P000175 | FALSE | BCOE | SL5 PAINTING |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | TBD | ROBERT CHAVARRIA-VIVAR |  | Paul Ditty |  | 3 |  | TRUE |  |  | 43321 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000176 |  | 19P000176 | FALSE | CNAS | SL5 PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY |  | PHYSICS | 1112 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Paul Ditty |  | 50 |  | FALSE |  |  | 43322 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2019-01-15 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000181 |  | 19P000181 | FALSE | VC-RED | SL5 PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS |  | UNIV OFC BLD | 249 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43326 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-19 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000184 |  | 19P000184 | FALSE | CNAS | SL5 REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES |  | GEOLOGY | 1270 | COMPLETE | Kathryn Uhrich | TBD | LAURIE GRAHAM |  | Dan Lerman |  | 45 |  | FALSE |  |  | 43326 | [6 empty] | 4/15/19, DL; This Project is 100% Complete…….. 3/28/19, DL; The project is 90% complete. Need to schedule floor installation…….. 2/14/19, DL; We will schedule the work soon. The space is vacant and ready…………….2/1/19, DL; This project has started. We would like to have the work complete by mid March…………..12/14/18, DL; This project is prioritized at 45 and will not be shceudled until further notice…… |  | Enrico Baez | SCOPE CARPENTERS-Remove all wall, base and center island cabinet work. Verify no ACM flooring under center island. PLUMBERS-Remove sinks in 1270 and 1270A. Terminate, at wall plumbing. Remove air/gas lines on wall in 1270 and 1270A. Remove lower chilled water, supply and return, lines on East wall. Remove air and gas line, flush with floor, from center island. FLOORING-Remove VCT in 1270 and 1270A, replace with customer selected VCT. Replace all cove base. ELECTRICIANS-Remove gray flexible conduit at raceway, terminate circuit. PAINTERS- Patch and paint walls in both spaces. | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000185 |  | 19P000185 | FALSE | CNAS | SL5 NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE |  | PIERCE | 206 (originially identified as Room 204) | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  |  | 6 | TRUE |  |  | 43269 | [6 empty] | 12/14/18, DL; This project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Pending glove box relocation to rm 319 and minor vent reconfiguration. Both tasks will be performed afet the glove boxes relocate to rm. 319. 10/29/18 All project related work is completed. |  | Ron Veloz |  | YES | 2018-12-14 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000186 |  | 19P000186 | FALSE | CNAS | SL5 NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION |  | PIERCE | 319 | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  |  | 7 | TRUE |  |  | 43269 | [6 empty] | Pending gas line installation scheduled for the week of 09/24 per Steve Burleson. Move glove boxes from 206 to Rm 319 after gas line are installed. All work is complete |  | Ron Veloz |  | YES | 2018-11-08 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19P000188 |  | 19P000188 | FALSE | CAMPUS | SL5 PAINT - HALLWAY DOORS & INSIDE RESTROOMS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500 | CANCELED BY FS |  |  | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 43328 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000189 |  | 19P000189 | FALSE | CNAS | SL5 PHYSICS- WALL HOLES PATCH | Duplicate work order to 19P000049. Work to be completed on other project. | PHYSICS | 3036 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | JAZMIN CHAVEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 43328 | [10 empty] | NO | 2018-10-18 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000191 |  | 19P000191 | FALSE | CNAS | SL5 PATCH AND PAINT HINDERAKER BASEMENT |  | HINDERAKER |  | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 34 |  | FALSE |  |  | 43332 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000192 |  | 19P000192 | FALSE | PB&A | SL5 MAIL-PAINTING |  | MAIL |  | COMPLETE | Gerry Bomotti | TBD | PRISCILLA MARTIN |  | Paul Ditty |  | 10 |  | FALSE |  |  | 43332 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | COMPLETE | Kathryn Uhrich | TBD | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 43332 | [6 empty] | 8/5/20, DL: This project is complete……………..06/17/20, DL: This project should be complete with in the next two weeks……..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within two weeks. Once we have a contract, we will schedule the work……….1/15/20 O-DH: Emailed Status Report to customer……1/14/20, DL: Contracts is currently working on the contract. Once the contract is complete, we will order the material and schedule the work…………11/26/19, DL: Plans were approved. We will work on the construction contract. Once we have the notice to proceed, we will schedule the work……….10/15/19, DL: Sent PD&C and follow-up email on 11/11/19. We should have approved plans in the near future……10/30/19, DL: Sent PD&C an email asking for a status update on 10.30.19…… 10/16/19, DL; Plans are still in plan check. I sent the building official an email asking if any additional information is needed. This work will be completed by a contractor which means we need to allow time for the bid and contract process……… …………9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Ron Veloz | Request for Estimate to install three new FOB readers with electrified locksets. Work covered: Install one AC Fob Reader at door 2221 and one AC Fob reader at each Door 4231 & 4235. Connect card readers to the existing Hirsh ACP located in the IDF closet at each floor. 03/07/19: Scope revised to eliminate two FOB readers. Install one FOB reader at Genomics door 4231 only instead of all three rooms. | YES | 2020-08-05 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 20-21
19P000194 |  | 19P000194 | FALSE | CHASS | SL5 PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 |  | HUM & SOC SC | 3304 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43332 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000195 |  | 19P000195 | FALSE | CHASS | SL5 HUM & SOC SC-ROOM PAINTING |  | HUM & SOC SC | 2003 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 12 |  | FALSE |  |  | 43333 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000196 |  | 19P000196 | FALSE | CHASS | SL5 PAINT OFFICE AT UNIVERSITY THEATER |  | THTR WKSH |  | COMPLETE | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 15 |  | FALSE |  |  | 43333 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000197 |  | 19P000197 | FALSE | CNAS | SL5 PATCH AND PAINT OFFICE, LOBBY AND HALL |  | COLL BLDG NO | 0203B | CANCELED BY CLIENT | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 44 |  | FALSE |  |  | 43333 | [6 empty] | 05/07/19 O-ANS: Canceled per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000201 |  | 19P000201 | FALSE | CHASS | SL5 PATCH AND PAINT THE WALLS |  | CHASS INT S | 3111A | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 18 |  | FALSE |  |  | 43334 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000205 |  | 19P000205 | FALSE | BCOE | SL5 LABORATORY RENOVATION FOR NEW FACULTY |  | BOURNS | A0328 | COMPLETE | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | 4 |  | TRUE |  |  | 43335 | [6 empty] | 2/28/19, DL; This Project is 100% Complete…….2/1/19, DL; This project is 99.9% Complete………..1/15/19, DL; This project is 90% complete. WE still need to finish snorkels and ceiling tiles. We should be 100% complete by 2/1/19……12/14/18, DL; This project is on schedule..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/4/18; This is a large scale project, we will walk with the trade supervisors next week. We will also work on the plans and schedule the work. Target Date is 1/1/19…..DL, 11/7/18; work is scheduled. We are working on the electrostatic paint contract. We are in plan check review process. There are questions about the fire sprinklers from Scott J. Sent Scott J. an email requesting a site visit to better determine if any work will be required on the sprinkler system….. |  | Ron Veloz |  | YES | 2019-02-18 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000207 |  | 19P000207 | FALSE | CHASS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43335 | [6 empty] | 8/1/19, DL: This project is 100% Complete……7/15/19, DL; Floor covering will be installed next week. Floor covering is the last item for this project……..7/1/19, DL; This project is 95% complete except floor covering. Floor covering will be installed within 2- weeks……6/17/19, DL; This project is making good progress. We should be complete near July 1st…….5/31/19, DL; This project started this week and should be complete by June 28th…….3/18/19, DL; Working on plans and we will submit our plans and permit application this week….. | 2018-09-20 | Enrico Baez |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000208 |  | 19P000208 | FALSE | PB&A | SL5 PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | Canceled per customer on priority list 9/17/18 | THE PLAZA |  | CANCELED BY CLIENT | Gerry Bomotti | TBD | CARLA CHAPPLE |  | Dan Lerman |  |  |  | FALSE |  |  | 43326 | [8 empty] | Enrico Baez |  | NO | 2018-09-17 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000209 |  | 19P000209 | FALSE | PB&A | SL5 OLD EH&S SITE- FS ANNEX A REMODEL |  | ENV HLTHSFTY | 100 | COMPLETE | Gerry Bomotti | TBD | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 43336 | [6 empty] | 7/1/19, DL; This project is 100% Complte….6/17/19, DL; This project is almost complete. Target complete date is 6/26………….5/31/19, DL; This project is in progress. Our goal is to have the projected completed by June 28th……. 5/15/19, DL; We are schedule to start the demo tomorrow. Project timeline is 3-4 weeks….3/28/19, DL; Gunther is working on plans……3/18/19, DL; Conducted site visit with Chris, Hassan and Francis last week. We will work on plans and permits…….9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000210 |  | 19P000210 | FALSE | CNAS | SL5 CHEMICAL SCI Install Door In Doorway |  | CHEMICAL SCI | 0225A | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  | 25 |  | FALSE |  |  | 43336 | [6 empty] | 7/1/19, DL; This project is 100% complete…..6/17/19, DL; Po is cut. Target complete date is before 7/1/19……Permit was approved this week. We are now working on the contract with the vendor. Our goal is start the work with in the next 30- days. 5/15/19, DL; Plans were approved. I am in the process of working with PD&C for the contract. We will order material and schedule the wrok once we have a signed contract……..3/28/19, DL; Plans were submitted last week… 3/18/19, DL; Conducted site visit last week. We are working on plans now we will try and submit plans for permit review next week…… | 2018-09-19 | Ron Veloz |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000211 |  | 19P000211 | FALSE | CAMPUS | SL5 LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | Reviewing campus standards for these project requests. | LIFE SCIENCE | 2545 | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 43336 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000212 |  | 19P000212 | FALSE | CAMPUS | SL5 REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500A | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 43336 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000213 |  | 19P000213 | FALSE | CNAS | SL5 NEEDS FOR NEW WALL DISPLAY (MONITOR) | Duplicate request to 19P000031; Work to be completed on other project. | BIOLOGIC SCI | 3101 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 43336 | [11 empty] | 2018-10-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000214 |  | 19P000214 | FALSE | CNAS | SL5 PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT |  | PHYSICS | 3005 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Paul Ditty |  | 2 |  | TRUE |  |  | 43336 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000215 |  | 19P000215 | FALSE | PB&A | SL5 SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 |  | HUB | 346 | COMPLETE | Gerry Bomotti | TBD | GUSTAVO PLASCENCIA |  | John Peraino |  | 9 |  | FALSE |  |  | 43336 | [6 empty] | 12/12/18 DND Project complete; electrical was installed and all kitchen equipment was hooked up as requested. |  | Enrico Baez |  | YES | 2018-12-12 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000216 |  | 19P000216 | FALSE | CHASS | SL5 HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT |  | HUM & SOC SC | 1214 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 13 |  | FALSE |  |  | 43339 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000217 |  | 19P000217 | FALSE | GSOE | SL5 PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 |  | SPROUL | 1359 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43339 | [6 empty] | 4/15/19, DL; This project is 100% Complete…..2/1/19, DL; This proect will start on 3/1/18 and should be complete by 4/1/19…… | 2018-09-18 | Enrico Baez | Scope of work Carpentry Remove 20 feet of built-in wood cabinets and counter top. Install TV mount on South wall. Remove and replace white board on North wall. Abatement Abate approximately 200 square feet of 9â€ x 9â€ VCT tile and base cove Flooring Install carpet similar to what is in room 1357 Replace base cove. Walls Patch and paint walls. Electrical Install duplex outlet for TV Replace fluorescent lamps with LED lamps TV Install data point and Internet connection to support video conferencing. Custodial Vacuum dust from ceiling tiles. 9/18/18 EB-Conducted site visit. Request to remove cabinet, abate VCT, install carpet, mount TV. Electrical and date lines needed. Install white board. Replace fluorescent tube with LED. 9/13/18 EB-emailed Karen Naples to schedule site visit. | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000220 |  | 19P000220 | FALSE | CHASS | SL5 ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT |  | ARTS | 333 | COMPLETE | Juliet McMullin | Cindy Williams | SONJA SEKELY-ROWLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43340 | [6 empty] | 12/14/18, DL; This project is 100% Complete….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/8/18; Screeen is scheduled to be removed this Friday. We will schedule the installation and the patch / Paint repairs once we receive the repaired screen back from the vendor…….DL, 11/7/18; This project should already be complete. However, The vnedor did not deliver the correct screen. The correct screen is currently scheduled for this Friday..... |  | Enrico Baez |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000221 |  | 19P000221 | FALSE | CHASS | SL5 PATCH, PAINTING, AND REGULAR CLEANING OF A126A |  | OLMSTED | A0126A | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 14 |  | FALSE |  |  | 43340 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000222 |  | 19P000222 | FALSE | PB&A | SL5 PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | TBD | RICHARD GEIGER |  | Paul Ditty |  |  |  | FALSE |  |  | 43375 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-01 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000224 |  | 19P000224 | FALSE | PB&A | SL5 PAINT EXTERIOR RAMP AT HUB MODULAR |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | TBD | MIKE CLEMONS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43340 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43340 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice. | 2018-09-27 | Enrico Baez |  | YES | 2020-11-19 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 20-21
19P000226 |  | 19P000226 | FALSE | CHASS | SL5 PAINT OFFICE HMNSS 3304 |  | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 43340 | [8 empty] | Paul Ditty |  |  | 2018-10-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000227 |  | 19P000227 | FALSE | PB&A | SL5 DINING STORAGE ROOM CONVERSION |  | BANNOCK J | J0100 | COMPLETE | Gerry Bomotti | TBD | DARCI LOMBARD |  | John Peraino |  | 2 |  | FALSE |  |  | 43329 | [6 empty] | 05/16/19 O-ANS: Project complete per John P as of 05/16/19. 04/04/19, JP: This project has been placed on hold per Housing Edwin. 2/8/19: JP storage room slated to be completed simultaneously with break room as water supply connections will be done together with break room. Completion date for both is approximately three weeks. |  | Enrico Baez |  | YES | 2019-05-16 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000229 |  | 19P000229 | FALSE | GSOE | SL5 RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43341 | [6 empty] | 6/15/19, DL; This Project is 100% Complete….. |  | Enrico Baez |  | YES | 2019-06-15 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000230 |  | 19P000230 | FALSE | CNAS | SL5 NEW FACULTY OFFICE FOR PATCHWORK/PAINT |  | GEOLOGY | 1242A | COMPLETE | Kathryn Uhrich | TBD | KAREN CATO |  | Paul Ditty |  | 7 |  | TRUE |  |  | 43342 | [6 empty] | n/a |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000231 |  | 19P000231 | FALSE | CNAS | SL5 OLMH 1428 PATCH AND PAINT |  | OLMSTED | 1428 | COMPLETE | Kathryn Uhrich | TBD | ANDREW CABRERO |  | Paul Ditty |  | 48 |  | FALSE |  |  | 43342 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000232 |  | 19P000232 | FALSE | PB&A | SL5 BANNOCKBURN J-104 BREAK ROOM UPGRADE | Scheduled work with trades anticipated 60% completion by Jun 15th. | BANNOCK I | I0105 | COMPLETE | Gerry Bomotti | TBD | RICHARD GEIGER |  | John Peraino |  | 6 |  | FALSE |  |  | 43347 | [6 empty] | 6/14/19, JP; Project on schedule to be completed June 30th 2019. 05/16/19 O-ANS: Project to be 60% completed by June 15th per John P. 04/04/19 JP: This project placed on hold per Housing/Edwin. Finishing up the cabinet and lighting order, will be submitting to purchasing today. Scheduling installation of VCT flooring pending per Tony’s Flooring, will have date this week. New ceiling tiles have been delivered and will be installed when relocating of electrical components are complete. Awaiting confirmation and clearance from Jess to proceed with cutting into walls to facilitate electrical modifications |  | Enrico Baez |  | YES | 2019-06-14 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000233 |  | 19P000233 | FALSE | PB&A | SL5 PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | FS to coordinate with customer to scope the work. | MAIL | 884 | CANCELED BY FS | Gerry Bomotti | TBD | AMY EVERETT |  |  |  | 12 |  | FALSE |  |  | 43347 | [8 empty] | Enrico Baez |  | YES | 2018-09-24 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000234 |  | 19P000234 | FALSE | CNAS | SL5 PHYSICS 3005-WALL HOLES PATCH |  | PHYSICS | 3005N | CANCELED BY FS | Kathryn Uhrich | TBD | JAZMIN CHAVEZ |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 43347 | [6 empty] | **9/19/18 DUPLICATE REQUEST SENT IN SEE 19P000246 |  | Paul Ditty |  | N/A | 2018-09-19 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000235 |  | 19P000235 | FALSE | PB&A | SL5 RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | Customer to determine scope of work. | ABER INVER | A0100 | CANCELED BY CLIENT | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 11 |  | FALSE |  |  | 43347 | [6 empty] | JP 04/04/19 Project cancelled per Housing/Lisa | 2018-11-01 | Enrico Baez |  | YES | 2019-04-04 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000236 |  | 19P000236 | FALSE | PB&A | SL5 EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION |  | ABER INVER | A0100 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 10 |  | FALSE |  |  | 43347 | [6 empty] | JP 04/04/19 2/8/19 This project is complete. JP Estimated completion end of February | 2018-11-01 | Enrico Baez |  | YES | 2019-04-04 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000237 |  | 19P000237 | FALSE | GSOE | SL5 PATCH AND PAINT OFFICE - SPROUL 1206 |  | SPROUL | 1206 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43348 | [6 empty] | 4/15/19, DL; Project is 100% Complete….. 2/1/19, DL; This project will start on 3.1.19. We will need to abate ACM before we can start. Jess will isuue the 14- day notification to the AQMD. Once we have confirmation, we will schedule the work…….. | 2018-10-05 | Enrico Baez | Carpenters: Removes sliding chalk boards in 1206 and 1206 and fill in with wall. Remove patched in panels on left of chalk board in 1206. Patch where " do not enter" signs were removed. Electricians: Disconnect power to two "do not enter" signs above doors. Abatement: Remove approx 300 sq.ft. of ACM VCT Flooring: replace flooring with either VCT of vinyl plank. Painters: Patch and paint, at least one wall accent wall. | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000238 |  | 19P000238 | FALSE | VC-UNIV ADV | SL5 PATCH & PAINT HINDERAKER 1136 |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43348 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000241 |  | 19P000241 | FALSE | PB&A | SL5 PATCH/PAINT IN OFFICE 2122 HINDERAKER |  | HINDERAKER | 2122 | CANCELED BY CLIENT | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43349 | [8 empty] | Paul Ditty |  | N/A | 2018-09-13 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000242 |  | 19P000242 | FALSE | CNAS | SL5 PAINT OFFICE |  | COLL BLDG NO | 210 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 47 |  | FALSE |  |  | 43349 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000243 |  | 19P000243 | FALSE | CNAS | SL5 GENOMICS 1206 - PATCH AND PAINT WALLS |  | GENOMICS | 1206 | COMPLETE | Kathryn Uhrich | TBD | AIMEE GONZALES |  | Paul Ditty |  | 49 |  | FALSE |  |  | 43349 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000244 |  | 19P000244 | FALSE | CNAS | SL5 PATCH & PAINT GEOLOGY |  | GEOLOGY | 2258A | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Paul Ditty |  | 10 |  | TRUE |  |  | 43349 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000245 |  | 19P000245 | FALSE | SOM | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY |  | SOM RSCH |  | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43350 | [6 empty] | 7/1/19, DL; This project is 100% Complete…..6/171/19, DL; Material is on site. Project should be complete in the next two weeks……..5/31/19, DL; Contracts is working on the contract. We should have a notice to proceed in the next two weeks. The project will be complete with in 30- from when we receive the notice to proceed……5/15/19, DL;, Plans were approved. I am working with PD&C on the contract. Once the contract is complete, we will schedule the work……3/28/19, DL; Plans were submitted and pending review and approval….. | 2018-10-29 | Ron Veloz | Install ADA complian auto door operator, push plates and electrified panic hardware. Auto operator will be outsourced through Capitol door. FS lock shop will perform acess control wiring. Electrical shop to provide a dedicated circuit for the auto door operator. | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000246 |  | 19P000246 | FALSE | CNAS | SL5 PHYSICS - PATCH AND PAINT |  | PHYSICS | 3007N | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Paul Ditty |  | 46 |  | FALSE |  |  | 43350 | [6 empty] | n/a |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000247 |  | 19P000247 | FALSE | PB&A | SL5 LOTHIAN FIRST FLOOR COMMON AREA FLOORING |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | TBD | RICHARD GEIGER |  | Jess Hernandez |  |  |  | FALSE |  |  | 43353 | [8 empty] | Enrico Baez |  |  | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000248 |  | 19P000248 | FALSE | SOM | SL5 SOME--SOME INSTALL ELECTRICAL 1682 |  | SOM EDUC | 1682 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  |  |  | 2 |  | FALSE |  |  | 43353 | [6 empty] | 2/14/19, DL; This project is complete…… |  | Ron Veloz |  | YES | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000249 |  | 19P000249 | FALSE | SOM | SL5 SOME-INSTALL LOCKERS | Lockers on order by customer; upon arrival to be installed. | SOM EDUC |  | CANCELED BY FS | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43350 | [6 empty] | DL, 11/7/18; It is my understanding the lockers are ordered, but we donot have a confirmed delivery date. Once the material is on site, we will schedule the installation…… |  | Ron Veloz |  | YES | 2019-02-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000250 |  | 19P000250 | FALSE | BCOE | SL5 BOURNS A303-PAINT AND PATCH WALL |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | TBD | JUANA GUERRERO |  | Paul Ditty |  | 5 |  | TRUE |  |  | 43353 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000251 |  | 19P000251 | FALSE | CNAS | SL5 CHEM SCI 428-PATCH DRY WALL HOLES |  | CHEMICAL SCI | 428 | COMPLETE | Kathryn Uhrich | TBD | KEVIN KOU |  | Paul Ditty |  | 8 |  | TRUE |  |  | 43353 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000252 |  | 19P000252 | FALSE | ATHLETICS | SL5 ATH DANCE SHOWER DOORS |  | ATH DANCE | 0050K | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43353 | [6 empty] | 5/31/19, DL; This project is 100% Complete……..5/15/19, DL; This work will be 100% complete this Friday…….4/15/19, DL; This project should stat is 2-weeks. We have a signed po# for the shower doors. Walked the needed tile repairs with the contractor today……..3/18/19, DL; Woring on quotes for the repairs. We will scheudle the work to be completed in the next 45- days…… |  | Enrico Baez |  | YES | 2019-05-31 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000253 |  | 19P000253 | FALSE | CHASS | SL5 ARTS RENOVATION |  | ARTS | 157 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 16 | FALSE |  |  | 43207 | [6 empty] | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access……DL, 7/11/18; This project needs to be complete before Fall 2018. Space is vacant and ready go. Need to walk and confirm Schdule with Paul D. Tony's Flooring is ready to go after paint is complete.... Target complete date is 9/21/18......DL, 8/22/18; Walked with PAul, Paul will scheudle the work. Jess still need to cordinate with Tony's Flooring .....DL, 9/19/18; The paint and flooring is complete. The seams need to be welded and this will be complete. this will be complete by 9/21/18......9/19/21; This Project is 100% Complete....... |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-01-16
19P000255 |  | 19P000255 | FALSE | SPP | SL5 CHASS INT N REMODEL - 4022 PATCH AND PAINT |  | CHASS INT N | 4022 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43353 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000256 |  | 19P000256 | FALSE | SPP | SL5 CHASS REMODEL - 4146 PATCH AND PAINT |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  |  |  | 3 |  | TRUE |  |  | 43353 | [7 empty] | 2018-10-09 | Enrico Baez |  | YES | 2019-01-04 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000263 |  | 19P000263 | FALSE | SPP | SL5 CHASS NORTH REMODEL - 4009 PATCH AND PAINT |  | CHASS INT N | 4009 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 2 |  | TRUE |  |  | 43354 | [8 empty] | Paul Ditty |  |  | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000265 |  | 19P000265 | FALSE | ATHLETICS | SL5 ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43354 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000266 |  | 19P000266 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43354 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty |  | N/A | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000268 |  | 19P000268 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT 20C |  | ATH DANCE | 20C | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43354 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000269 |  | 19P000269 | FALSE | ATHLETICS | SL5 ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | Project is not within the purview for completion; condition is fair and usable. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 5 |  | FALSE |  |  | 43355 | [6 empty] | DL, 10/4/18…..This is a cooman area. Is this recharge work……. | 2018-09-27 | Enrico Baez |  | YES | 2018-10-04 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000270 |  | 19P000270 | FALSE | ATHLETICS | SL5 ATH DANCE-WEIGHT ROOM DROP DOWN CEILING |  | ATH DANCE | 78 | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 14 |  | FALSE |  |  | 43355 | [6 empty] | 2/14/19, DL; This project is 100% Complete….. |  | Enrico Baez |  |  | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000271 |  | 19P000271 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 |  | ATH DANCE | 3 | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 43355 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000272 |  | 19P000272 | FALSE | ATHLETICS | SL5 NEED URINAL DIVIDERS | FS to coordinate with customer to scope the work. | ATH DANCE | 50E | CANCELED BY FS | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 13 |  | FALSE |  |  | 43355 | [7 empty] | 2018-09-27 | Enrico Baez |  |  | 2019-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000273 |  | 19P000273 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43355 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000274 |  | 19P000274 | FALSE | ATHLETICS | SL5 RIV SPORTS CPX - REPLACE URINALS | FS to coordinate with customer to scope the work. | W LCKRM/CONC |  | CANCELED BY FS | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 15 |  | FALSE |  |  | 43355 | [7 empty] | 2018-10-15 | Enrico Baez |  | YES | 2019-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000275 |  | 19P000275 | FALSE | ATHLETICS | SL5 SOFTBALL STG PRESS BOX AC ADDITION | FS to coordinate with customer to scope the work. | PRESS BOX |  | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 6 |  | FALSE |  |  | 43355 | [6 empty] | 2/14/19, DL; This project was canceled by Johnathan J. as there is not funding at this time…………DL, 10/4/18; I checked on this recently and this is not a building, it is stoarge and should be recharge work…. | 2018-09-27 | Enrico Baez |  |  | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000276 |  | 19P000276 | FALSE | ATHLETICS | SL5 TRACK BLEACH-PUBLIC RESTROOMS UPGRADE |  | TRACK BLEACH |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 16 |  | FALSE |  |  | 43355 | [7 empty] | 2018-09-27 | Enrico Baez |  | YES | 2018-11-20 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | 10 |  | FALSE |  |  | 43355 | [6 empty] | 1/24/2020 E. Baez- Cancelled per Joe Erbland. 4/18/19, DL; Per Enrico, we are waiting for a proposal from HCI and approved funding from Athletics. We should have the proposal in 2- weeks…. | 2018-09-27 | Enrico Baez |  | YES | 2020-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000278 |  | 19P000278 | FALSE | BCOE | SL5 REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR |  | BOURNS | A0165 | COMPLETE | Christopher Lynch | TBD | NANCY FORD |  | Dan Lerman |  | 1 |  | TRUE |  |  | 43315 | [6 empty] | DL, 10/4/18; This Project is 100% Complete…….. |  | Ron Veloz |  | YES | 2018-10-04 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000280 |  | 19P000280 | FALSE | SoB | SL5 ANDERSON HALL PAINT ONLY |  | ANDERSON 2 (S) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43356 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000283 |  | 19P000283 | FALSE | CNAS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | COMPLETE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 20 |  | FALSE |  |  | 43348 | [6 empty] | 8/1/19, DL; This Project is 100% Complete……7/1/19, DL; Barricades are complete. Signage needs to be installed. Signage to be installed in the next 3- weeks………….6/17/19, DL; Yello Caution tape is installed. Still need to install barricades and signage. Target complete date in mid to late July……5/31/19, DL; The contractor has the PO#. We will start the work and complete the work in the next 30- days……5/15/19, DL; We are waiting on the quote, once we have the quote, we will proceed with the work……4/15/19, DL; We are trying to locate a roofing contractor that will complete the installation. This is a specialty product that requires a professional installation…….3/28/19, DL; We will install the yellow caution tape on the roof which is our most viable option. I will schedule a site visist / job walk with a contractor in the near future…… | 2018-09-19 | Ron Veloz | Install hand railing and marking for a leading edge as direcetd by EH&S. | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000284 |  | 19P000284 | FALSE | CAMPUS | SL5 GEOLOGY ACCOMMODATION DOCK DOORS |  | GEOLOGY |  | COMPLETE |  |  | DEBORAH TERAO |  | Chris Pillen |  | Canceled | Canceled | FALSE |  |  | 43319 | [8 empty] | Ron Veloz |  | YES | 2019-01-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000285 |  | 19P000285 | FALSE | CNAS | SL5 PAINT AND PATCH PI OFFICE |  | ENTOMOLOGY | 269 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43360 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000286 |  | 19P000286 | FALSE | CHASS | SL5 FACULTY OFFICES: TOUCH UP PAINT |  | HUM & SOC SC | 2005 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43360 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000287 |  | 19P000287 | FALSE | CNAS | SL5 URGENT: PAINT SHOP TO PATCH AND PAINT |  | MAT SCI ENGR | 229 | COMPLETE | Kathryn Uhrich | TBD | HONG XU |  | Paul Ditty |  |  |  | FALSE |  |  | 43362 | [8 empty] | Paul Ditty |  |  | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000288 |  | 19P000288 | FALSE | CNAS | SL5 COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS |  | COLL BLDG NO | 202 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43362 | [6 empty] | 05/10/19 O-ANS: Project was canceled by FS in March 2019 because customer will have to submit separate work orders for each room since customer has requested to schedule and complete them separately in sequence (not all at once). 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000291 |  | 19P000291 | FALSE | CNAS | SL5 MSE HELIUM RECOVERY SYSTEM |  | MAT SCI ENGR | 205 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 9 | HOLD | FALSE |  |  | 42940 | [6 empty] | 12/14/18, DL; This project is 100% Complete……DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB - spoke with Mayela who is determining status within her dept…. DL, 11/7/18; This project is complete but I need to conduct a final site visit….. |  | Ron Veloz |  | YES | 2018-12-14 | Fall 2017 | FS | FALSE | 2017 | 2021-01-16
19P000292 |  | 19P000292 | FALSE | CNAS | SL5 GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | 18 |  | FALSE |  |  | 43322 | [6 empty] | 3/28/19, DL; This Project is 100% Complete…….2/14/19, DL; The Concrete and Power is Complete. We still need to install the chain link which will be installed in about 3-4 weeks………..2/1/19, DL Electrical is complete. WE will pour Concrete next week. We will schedule the fence install 28- days after concrete is poured………; Th1/15/19, DL; Plans are approved, we will start the work in the next two weeks……12/14/18, DL; Plans are almost complete. We will schedule the work after plans are approved……DL, 11/7/18; Conducted site visit with Chris P. We need to confirm a feasable site location before we move forward with the work…. |  | Ron Veloz |  | YES | 2019-03-28 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000293 |  | 19P000293 | FALSE | ITS | SL5 PAINT ESTIMATE REQUEST |  | TELEPHONE |  | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 43333 | [6 empty] | n/a |  | Paul Ditty |  | N/A | 2018-10-24 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000295 |  | 19P000295 | FALSE | ATHLETICS | SL5 PATCH & PAINT |  | ATH DANCE | 50B | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 12 | 18 - 19 | FALSE |  |  | 43355 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000296 |  | 19P000296 | FALSE | CAMPUS | SL5 MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB |  | MAT SCI ENGR |  | COMPLETE |  |  | MILLY PAREDEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 43368 | [6 empty] | 2/28/19, DL; Project is 100% Complete…….2/14/19, DL; This project is 90% Complete and should be complete by the end of the month………….2/1/19, DL; Permits are approved, we will schedule the project in the next 2- weeks and hope to be complete by the end of February….12/14/18, DL; Rendering has been given to Ron R. Ron will present to Gerry for review and approval. Once approved, we will proceed with plans and permits……DL, 11/7/18; Need to find out where this project stands in regards to the priioroity….. Site vist was conducted and scope of work is verified. Plans and permits will be required for the work….. |  | Ron Veloz |  | YES | 2019-02-28 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000298 |  | 19P000298 | FALSE | CNAS | SL5 SPIETH - PREP LAB FOR FACULTY SEARCH |  | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 0 |  | FALSE |  |  | 43369 | [6 empty] | 5/15/19, DL; This Project is 100% Complete… 5/1/19, Dl; This project will be complete next week…..4/15/19, DL; We are making good progress on this project and we should be complete the first week in May……..3/28/19, DL; This project is in progress and should be complete by or near May 1st….2/14/19, DL; Need to schedule trades and obtain quotes to refinish countertops…… |  | Ron Veloz | 12/13/18 O-RVL: Ron V was informed of this project by D. McWilliams on 12/12/18. RV reviewed the request and noticed it was assigned to Paint. RV changed to O-RVL for scoping for new faculty. RV added revised scope (12/13)of work provided by D.McWilliams email on 12/10. See below. REVISED SOW 1363 & 1364 Spieth 1363 Wet Lab Space Note: There is evidence in the ceiling and along one wall of a water intrusion issue, i.e. peeling paint, leaking and rusted pipes, etc. The cause of this damage needs to be investigated and repairs confirmed, including painting the wall and ceiling where damage is visible. Patch/paint Re-finish, re-surface the existing cabinets Re-finish and/or replace bench-tops If both sinks cannot be significantly cleaned, they should be replaced Replace faucets at both sink locations. Clean existing Chemical fume hood Repair or replace self-closing chemical / flammables storage cabinet On one bench remove overhead shelving unit and relocate electrical outlets to the ends of bench to accommodate large desktop equipment. Cap off remaining utilities for potential use/re-connection in the future. Remove shelves on west wall to accommodate siting of large floor-standing equipment before patch and painting. Also, add 120/240 electrical outlets (raceway) along this wall. Replace flooring -- this depends on what we decide about removing the walk-in fume hood listed below Add GFCI outlets near water sources Requires a connection to a DI water system Other utilities are required in this room and at what locations, e.g. air, oxygen, gas, vacuum, etc.? Remove existing walk-in Fume Hood (if cost for this issue does not trigger project over $50k)Please assess/cost out and advise prior to project. Spieth 1364 Lab Support Space Patch/paint, Re-finish, re-surface the existing cabinets (non-porous surface) Re-finish and/or replace bench-tops If sink cannot be significantly cleaned, they should be replaced Replace faucets at sink location. Add GFCI outlets near water sources Requires a connection to a DI water system | N/A | 2019-05-15 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000299 |  | 19P000299 | FALSE | CNAS | SL5 SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 |  | SPIETH | 3378 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43369 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000300 |  | 19P000300 | FALSE | CHASS | SL5 HUM & SOC SC--URGENT: PAINT AND PATCH WALLS |  | HUM & SOC SC | 4403 | COMPLETE | Juliet McMullin | Cindy Williams | ANDREA HERAZ |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43369 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000301 |  | 19P000301 | FALSE | CNAS | SL5 SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH |  | SCIENCE LAB1 | 214 | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43370 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000306 |  | 19P000306 | FALSE | CHASS | SL5 HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 |  | CHASS INT N | 4017 | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 43374 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000307 |  | 19P000307 | FALSE | PB&A | SL5 LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 5 |  | FALSE |  |  | 43354 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… | 2018-10-03 | Enrico Baez |  | N/A | 2019-01-01 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000308 |  | 19P000308 | FALSE | PB&A | SL5 ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK |  | ABER INVER |  | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 4 |  | FALSE |  |  | 43354 | [6 empty] | JP 04/04/19 Project Complete DL 10/4/18; Jess currently has this project scheduled for Winter break. |  | Enrico Baez |  |  | 2019-04-04 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43355 | [6 empty] | 2/5/20, DL: This Project is 100% Complete………….3/28/19, Doors are in the process of being …. DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez |  | YES | 2020-02-05 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000311 |  | 19P000311 | FALSE | ATHLETICS | SL5 ATHLETICS 150-KEYLESS ENTRY | Keyless entry system | ATH DANCE | 0150 | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43375 | [6 empty] | 02/07/2020 O-ANS: Canceled by customer Joe Erbland due to lack of funding per email to EBZ. | 2018-09-27 | Enrico Baez | Install keyless entry system, part of larger project throughout the athletics building | YES | 2020-02-07 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20 | 1
19P000312 |  | 19P000312 | FALSE | BCOE | SL5 VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP |  | STUDENT SERV | 1227 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43376 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000313 |  | 19P000313 | FALSE | CHASS | SL5 HUMANITIIES SOCSCI - PATCH HOLES & PAINT - |  | HUM & SOC SC | 1203 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  |  |  | FALSE |  |  | 43376 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-01 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000314 |  | 19P000314 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Juliet McMullin | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43376 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000316 |  | 19P000316 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL |  | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 43376 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…Anticipated completion 11/9/18. | 2018-10-03 | Ron Veloz |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000317 |  | 19P000317 | FALSE | PB&A | SL5 HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 | conversation with Susan Marshburn and Bob Brumbaugh. | PENTLAND A |  | CANCELED BY FS | Gerry Bomotti | TBD | RICHARD GEIGER | [5 empty] | FALSE |  |  | 43376 | [11 empty] | 2019-01-14 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000318 |  | 19P000318 | FALSE | CNAS | SL5 GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE |  | GEOLOGY | 420 | COMPLETE | Kathryn Uhrich | TBD | KAREN CATO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43377 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000319 |  | 19P000319 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB |  | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 43377 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000322 |  | 19P000322 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43378 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000324 |  | 19P000324 | FALSE | CNAS | SL6 SPIETH HALL ASSESS AIR VENT OR PURIFIER FOR LAB | Provide the single pass exhaust, air changes (6-12 ACH) and the negative air requirements for PI to perform surgeries in the room. | SPIETH | 1312 | CANCELED BY FS | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 106 |  | FALSE |  |  | 43378 | [7 empty] | 2018-10-10 | Ron Veloz | Upgrade infrastructure to accomodate surgical procedures in room 1312. | N/A | 2019-04-04 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16
19P000326 |  | 19P000326 | FALSE | VC-UNIV ADV | SL5 HINDERAKER - PATCH & PAINT |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43381 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000337 |  | 19P000337 | FALSE | CHASS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | Remove whiteboard (in front of room), mount LED mount, add double duplex and electrical power behind LED, patch and paint wall | PSYCHOLOGY1 | 3210 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 1 | 101 | FALSE |  |  | 43384 | [6 empty] | 10/1/19, DL; This Project is Complete……………..9/3/19, DL; Space is blocked and schedculed to be completed by 9/27/19…..8/14/19, DL; Conducted site visit with Trades. We will schedule the space to be blocked out and start the work mid September….8/1/19, DL; Planning to start this project in two weeks……7/15/19, DL; I will walk the project in the near future and schedule the work if permits are not required…… | 2019-01-15 | Enrico Baez | Electricians 1. Install behind TV. Provide two duplex outlets and power. Also provide single gang box and conduit for data. Data lines have been run to T-bar in Hallway. 2. Secure loose Extron plate and cover next to TV. Painters 1. Patch and paint wall where TV is mounted | YES | 2019-10-01 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000340 |  | 19P000340 | FALSE | CNAS | SL5 PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE |  | SKYE HALL | 349 | COMPLETE | Kathryn Uhrich | TBD | VICTORIA AVALOS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43385 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000341 |  | 19P000341 | FALSE | CNAS | SL5 PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL |  | PIERCE |  | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43385 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000346 |  | 19P000346 | FALSE | CNAS | SL5 I&Q--PAINTING ROOMS IN THE I&Q |  | EAST I&Q FAC |  | COMPLETE | Kathryn Uhrich | TBD | IMAD BAYOUN |  | Paul Ditty |  |  |  | FALSE |  |  | 43389 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2019-01-09 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000347 |  | 19P000347 | FALSE | CNAS | SL5 SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT |  | SPIETH | 3320 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 10 |  | FALSE |  |  | 43389 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000350 |  | 19P000350 | FALSE | CHASS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | MISC WORK IN ROOMS 3121 AND 1133 Patch and paint-relocate white boards, hang pictures. | PSYCHOLOGY1 | 3121, 1133 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 4 | 3 | TRUE |  |  | 43390 | [6 empty] | 8/15/19, DL; This Project is 100% Complete…….. 8/1/19, DL; We will start this project this Friday…… 7/15/19, DL; Appears not plans and permits will be required for the work. I will verify and schedule the work in the near future if no plans or permits are required….. | 2019-04-15 | Enrico Baez | Carpentry: 1. Needs to occur after October 26 2. Remove the whiteboard in 3121, patch and paint 3. Remove Glass board in 1133 and relocate to 3121 (in the same way and place as it was in 1133) 3. Mount pictures on the wall in 3121 4. Secure shelving units in 1133 and 3121 5. There is a ceiling tile in 1133 that is stained and needs to be replaced Painters: 1. Room 3121 Patch and Paint walls | YES | 2019-08-15 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000353 |  | 19P000353 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT-2348 |  | OLMSTED | 2340 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43392 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000354 |  | 19P000354 | FALSE | SOM | SL5 WEBBER 2130A-PAINT CHERI'S NEW OFFICE |  | WEBBER | 2130A | COMPLETE | Deborah Deas | Deborah Trujillo | DOMINIC SALAZAR |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43392 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000355 |  | 19P000355 | FALSE | CHASS | SL5 HYDRATION STATION FOR THE SECOND FLOOR WATKINS | Hydration station installed where the water fountain is. | WATKINS | 2122D | CANCELED BY FS | Juliet McMullin | Cindy Williams | CYNTHIA REDFIELD |  | Dan Lerman |  | 112 |  | FALSE |  |  | 43395 | [8 empty] | Enrico Baez |  |  | 2019-04-24 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16
19P000356 |  | 19P000356 | FALSE | CHASS | SL5 PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT |  | HUM & SOC SC | 4401 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43397 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000357 |  | 19P000357 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS, TIME SENSITIVE |  | HUM & SOC SC | 1302 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43398 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000358 |  | 19P000358 | FALSE | CNAS | SL5 GEOLOGY - ACCOMMODATION REQUEST |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 43399 | [6 empty] | 4/15/19, DL; This Project is 100% Complete……. 3/28/19, DL; Plans are approved. We will start the work on 4/1/19……3/18/19, DL; Waiting for approved plans from building official……2/28/19, DL; Plans were submitted to building official for review. Once plans are approved, we will schedule the work………..2/14/19, DL; Plans are in process and we will apply for building permit next week………….. | 2019-02-07 | Ron Veloz | SOW: Installation of Charging station Power Point of connection, concrete drive and charge station pad. Landscape: Clearing, cap and relocate irrigation lines and sprinklers. Replant vegetation as needed. Demolition: Concrete saw cutting curb Concrete: Excavation, form-work, place and finish concrete pad approx. 10'x10'. Signage: Provide the appropriate signage identifying parking designation, pavement markings-striping marked in front of the drive Electrical: Provide an Electrical POC and weather proof enclosure for the new cart charger. NOTES: Title changed to PHYSICS on 02/07/19, FORMERLY TITLED GEOLOGY BLD ACCOMMODATION REQUEST | YES | 2019-04-15 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000360 |  | 19P000360 | FALSE | CNAS | SL5 GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING |  | GEOLOGY | 1444 | COMPLETE | Kathryn Uhrich | TBD | KAREN CATO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43402 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000361 |  | 19P000361 | FALSE | CHASS | SL5 OLMSTED-PATCH & PAINT/REPLACE CARPET |  | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43402 | [6 empty] | 05/29/19 O-ANS: Project completed 05/09/19 per Paul Ditty. |  | Paul Ditty |  | N/A | 2019-05-09 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000362 |  | 19P000362 | FALSE | CHASS | SL5 PATCH & PAINT/REPLACE CARPET (HALLWAY) |  | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43402 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000364 |  | 19P000364 | FALSE | CHASS | SL5 PATCH AND PAINT |  | CHASS INT S | 3106 | COMPLETE | Juliet McMullin | Cindy Williams | FRANCESCA MOREIRA |  | Paul Ditty |  |  |  | FALSE |  |  | 43403 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2019-03-15 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000367 |  | 19P000367 | FALSE | CNAS | SL5 SCILAB 1 0211- PATCH & PAINT |  | SCIENCE LAB1 | 211 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 43404 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000369 |  | 19P000369 | FALSE | CNAS | SL5 PIERCE - PAINT IS PEELING OFF WALLS |  | PIERCE | 3341 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43405 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000370 |  | 19P000370 | FALSE | ENROLLMENT SERVICES | SL5 PATCH AND PAINT CAMPUS TOURS |  | STUDENT SERV | 1137 | COMPLETE | LaRae Lundgren | TBD | ELIZABETH TATUM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43405 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000371 |  | 19P000371 | FALSE | CHASS | SL5 URGENT PATCH AND PAINT IN CHAIR'S OFFICE |  | HUM & SOC SC | 1213 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43409 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000373 |  | 19P000373 | FALSE | ITS | SL5 URGENT-INSTALL RECPTACLE, ENCLOSURE & MOUNT BRACKET |  | GERMPLASM | 881 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 0 |  | FALSE |  |  | 43411 | [6 empty] | <div>mount a bracket to the Network Pole at AgOps. This will include mounting a bracket, an enclosure and a 20 Amp electrical receptacle.</div> |  | Ron Veloz |  |  | 2019-02-26 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000375 |  | 19P000375 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT HOLES |  | SKYE HALL | 365 | COMPLETE | Kim Wilcox | TBD | FELECIA GARRETT |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43411 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19P000377 |  | 19P000377 | FALSE | CNAS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | Replace the gates on the Schneider House driveway, which secure the property, with the taller iron gates that used to be installed at the Gardens entrance. This will require new fence posts and hinges as well. The taller gates are stored along the side of the garage at Schneider House, and Facilities staff can come see them anytime. Please note this is a safety and security project. | BOT GDN HSE |  | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | R2 | 117 | FALSE |  |  | 43412 | [6 empty] | 11/26/19, D: This Project is 100% Complete……………11/19/19 DH: Emailed Status Report to customer….11/15/19, DL: We should have A PO this week. Once we have the PO#, we will schedule the work……10/30/19, DL: Project was approved by customer with an FAU #. I will work on providing a PO# as this is maintenance and schedule the work. | 2019-04-05 | Ron Veloz | Replace Gates with new refurbished & modified gates furnished by BG. Install new steel posts and strip and repaint gates. Gate style revised by customer to purchase vendor fabricated light gauge meta gates without spike, per Jodie Holt 10/09/19. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20 | 1
19P000378 |  | 19P000378 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 |  | HUM & SOC SC | 1613 | COMPLETE | Juliet McMullin | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 10 |  | FALSE |  |  | 43417 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000380 |  | 19P000380 | FALSE | VC-STU AFF | SL5 PATCH AND PAITN- WALL PAINT IS PEELING |  | HEALTH SERV | 404 | COMPLETE | Brian Haynes | Cathy Eckman | SAMANTHA HARRIS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43423 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000384 |  | 19P000384 | FALSE | ENROLLMENT SERVICES | SL5 PATCH HOLES IN WALL AND PAINT |  | STUDENT SERV | 2234 | COMPLETE | LaRae Lundgren | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43424 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000386 |  | 19P000386 | FALSE | PROVOST/EVC | SL5 ROOM CHANGES |  | STUDENT SERV | 3106A | COMPLETE | Thomas Smith | Luisa Levario | STEPHANIE ARCINIEGA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 43424 | [6 empty] | 4/15/19, DL; This Project is 100% Complete…… 2/28/19, DL; Conducted site visit. We need to schedule the work in the next 2-3 weeks This is for room 3109 C&D ……….. | 2019-02-07 | Ron Veloz |  | YES | 2019-04-15 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000388 |  | 19P000388 | FALSE | BCOE | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | BCOE Advising is being reassigned to space on the 3rd floor of Skye (at the recommendation of the University Space Committee). | SKYE HALL | 308 | COMPLETE | Christopher Lynch | TBD | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 43430 | [6 empty] | 7/15/19, DL; This project is 100% Complete………..7/1/19, DL; This project ois 95% Complete. Floor covering install will start this Wednesday…………6/17/19, DL; This project is almost complete. Target complete date is July 1st….…..5/31/19, DL; We are making good progress on this project. we are on tract to be copmplete with this project on or before July 1st……5/15/19, DL; Work is in progress and we are on schedule for th3 6/28/19 complete date…….5/1/19, DL; We will start this project this week. 4/15/19, DL; Plans were approved today. We will work on material and schedule the work. We will start this project shortly after May 1st…….3/18/19, DL; We are working on plans and plan to apply for building permit an plan review process next week | 2019-02-13 | Ron Veloz | Customer Request: Frame new walls in rm. 0310B & 0326. Widen door opening, install sliding glass door rm. 0310 Work Covered: Install metal stud framed partition walls in room 0310B and 0326 and install electrical and voice data outlets as required for new furniture layout. Widen the existing door opening in room 0310 and install one new 6-0x7-0 sliding glass door. Install a viewing window (approximately 9-0x4-0 overall width) made with two pieces of glass within a storefront frame. Relocate utilities and one wall *cabinet (*location TBD) as needed. Inclusions: Demolition: Remove the side door and frame in room 0310 and widen the opening to accept a 6-0x7-0 sliding door. Room 0310 east wall, cut in opening (approx. 9-0x4-0) at 36”-48” A.F.F.(field verify). Carpentry: Framing & Drywall: Rooms 0310B & 0326; Construct metal stud partition walls and new cased openings, and install drywall with finished edge metal (room 0310). Intersect new walls into the window mullions with a finished edge or metal with neoprene expansion tape installed between the wall and million. Room 0310; Frame a new cased opening to accept a 6-0x7-0 sliding door and frame a new cased opening at the east wall opening (approx. 9-0x4-0, at 36”-48” A.F.F. field verify) to accept a new viewing window. Floorcovering: Install new 4” rubber base in rooms 0310B and 0326, base to match existing. Acoustical Ceilings: Modify the T-bar ceiling grid and cut ceiling tiles to accommodate the new partition walls in rooms 0310B and 0326. Painting: Tape, sand and paint the new partition walls, door/cased openings. Patch and paint other walls in the Advising room 0310 as needed. Glazing: Room 0310; Install a 6-0x7-0 sliding glass commercial door (outsourced to Hour Glass). Quote is on file. Electrical: Room 0310; Relocate light switch and or wall mounted devices at room 0310/corridor wall and possibly may need to relocate conduit in the east wall where the new window opening is created. Rooms 0310B & 0326; reconfigure/separate lighting circuits and switching. Note: “Installation of electrical and voice data outlets may be required in the new partition walls at rooms 0310B & 0326 depending the furniture configuration”. Fire Alarm: Investigate at rooms 0310B & 0326. Fire Sprinklers: Investigate at rooms 0310B & 0326. Exclusions: Replacement of the existing carpet floorcovering. Repaint all walls at rooms 0310B and 0326 (paint new and adjacent walls only). Installation of new mixing boxes and T-stats in rooms 0310B and 0326. | YES | 2019-07-15 | Spring 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000390 |  | 19P000390 | FALSE | CNAS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  | 0 |  | TRUE |  |  | 43433 | [6 empty] | 7/1/19, DL; This project is 100% Complete…………6/17/19, DL; material is ordered. This project should be complete by July 1st…..5/31/19, DL; Plans were apprvied this week we will work on the contract and hopefully have the notice to proceed in the next two weeks. It is our goal to have the work complete on or before July 1st……5/15/19, DL; Need to order the special order door and frame…. | 2019-02-07 | Ron Veloz | Install new aluminum storefront door, frame and side lite(requested by Dan L.), patch & paint door opening and west interior wall. | YES | 2019-07-01 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000396 |  | 19P000396 | FALSE | CAP PROG | SL5 TRAILER #14 - CAMPUS INITIATED - STRUCTURE |  | T14 |  | COMPLETE | Jacqueline Norman | Sharyl Murdock | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 43496 | [6 empty] | 2/28/19, DL; This Project is 100% Complete…..Trailers were demolished. We need to install the utilities. Once the Grow Pod is on site, we will connect the utilities to the structure…… |  | Enrico Baez |  |  | 2019-02-28 | Winter 2018 | FS | FALSE | 2019 | 2021-01-16
19P000399 |  | 19P000399 | FALSE | GRAD DIV | SL5 NEW CARPET + WALL PAINT |  | UNIV OFC BLD | 100 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43440 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000400 |  | 19P000400 | FALSE | CHASS | SL5 CREATE DOOR INTO HALLWAY | Create a door between the hallway and CHASS INTS 2117A. The door should be placed at the south end of 2117A. | CHASS INT S | 2117A | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 103 |  | FALSE |  |  | 43440 | [6 empty] | 05/21/19 O-ANS: Canceled by FS per conversation with Paul Richardson and combined with Project 19P000419. | 2019-04-15 | Enrico Baez | Add additional door into space 2117. Door in concrete wall was original location. Would require engineering. Suggest alternate location. | YES | 2019-05-21 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16
19P000401 |  | 19P000401 | FALSE | PB&A | SL5 PATCH HOLES IN WALL AND PAINT |  | HINDERAKER | 4148E | COMPLETE | Gerry Bomotti | TBD | SHANNON TIMMONS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43452 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000405 |  | 19P000405 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED |  | HEALTH SERV | 0100D | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43445 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | COMPLETE | Kim Wilcox | TBD | ALEXIS RAMBAUD |  | Dan Lerman |  | 1 | 0 | FALSE |  |  | 43445 | [6 empty] | 8/5/20, DL: This project is complete…………3/25/20,DL: Doors are scheduled to arrive the second week in April……2/19/20 O-DHN: Emailed Status Report to customer……2/18/20, DL: Work is complete except for Door and final deep cleaned I do have final stain samples from the vendor. I need to verify color……… We will complete the project when the doors arrive……….1/14/20, DL: Plans are approved, PO# is cut for the ordering of the custom doors, we are currently scheduled to start the work on or shortly after 1/21/20,. Karim understands that we will start and finish the project but we will not be able to install the door until the door arrives on site. There is a minimum of 6-8 week lead time on the door delivery………….12/16/19, DL: Plans are still in plan check review. I sent the building department an email asking for a startus update today…….10/16/19, DL; Plans were submitted to our building official this week for plan check review and a permit……9/16/19, DL; Guther will work on plans in the next three weeks. Once plans are complete, we will proceed with the permit process… | 2018-12-20 | Ron Veloz | SOW: Wall: Construct a metal stud framed wall with drywall up to hard ceiling (ceiling has 12x12 glue up ceiling tiles). Hardware: Install new lockset & keys are required.***** French Door: Install new stain grade birch door with full lite. Door and finish to match the existing office doors.***** Hard Ceiling: * Ceiling is 8’-0” A.F.F. + - with 12x12 glue up ceiling tiles. Work may require a new access panel if access to space above is needed. The 12x12 glue up ceiling tiles may need to be removed where the new wall is constructed.***** Flooring: The existing flooring will remain. Install rubber base to match existing.***** Painting, Taping & Sanding: Taping sanding and painting is required at the new wall and connecting walls.***** HVAC: May require modifications to split the existing supply air to accommodate the open office space.***** Electrical: Provide light switch at new office, power(new or relocate); add and or relocate electrical and voice/data outlets required for a standard office.***** Lighting: Provide a new light switch/circuit near office entrance. The existing 2x4 fixture is on main lighting circuit and will require lighting circuit modifications. Verify if the existing lighting is sufficient for the proposed office. Field verify if additional lighting is required.***** Fire Alarm: Provide a new Smoke/chime detector at new office area, confirm requirements. | YES | 2020-08-05 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 20-21
19P000408 |  | 19P000408 | FALSE | SOM | SL5 PATCH & PAINT - 2605 SOM ED |  | SOM EDUC | 2605 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43446 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000410 |  | 19P000410 | FALSE | SOM | SL5 PAINT OFFICES AT UC PATH |  | INTELLICTR |  | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43448 | [6 empty] | 06/06/19 O-ANS: Canceled per customer request. Paul spoke with customer who will outsource work. |  |  |  |  | 2019-06-06 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000411 |  | 19P000411 | FALSE | GRAD DIV | SL5 PAINT, CARPET AND BLINDS |  | UNIV OFC BLD | 150 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43448 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000413 |  | 19P000413 | FALSE | CNAS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | Batchelor 3111-Refresh BSL2 lab to accomodate Biosafety Cabinet. The Biosafety. Cabinet will be procured by BPSC. | BATCHELOR | 3111 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | MATTHEW ULRICH | PATTY SPRINGER | Dan Lerman |  | R1 | 107 | FALSE |  |  | 43451 | [6 empty] | 11/22/19 O-ANS: Project canceled per email from Deborah McWilliams. "The need for an appropriate space to accommodate use of a biosafety cabinet will be addressed in BH 2163 via the campus Batchelor Hall MEP-Tenant Improvement Project managed by PD&C." | 2019-06-12 | Ron Veloz | Preliminary assessment provided by Tiffany Kwok on 2/13/19 email. "For Batchelor 3111, there are a few items that need to be addressed before it can support BSL-2 work. • Floors should be patched to provide a smooth and easily cleanable surface. • Base coves along the wall should be replaced or repaired to provide a smooth and easily cleanable surface. • Base coves under the cabinets on the corners should be provided. • Provide a layer of sealant over the cabinets to ensure that the cabinets are moisture resistant and easily cleanable. • Seal, repair or replace the wooden rack on the wall to provide a moisture resistant and easily cleanable surface. • Ensure the door is self-closing. Since this is not a new facility and the space is not undergoing major renovations, it is not required to provide negative airflow into the space. However, it is still important that the air from the laboratory is not recirculated into clean spaces". | YES | 2019-08-26 | Winter 2020 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20 | 1
19P000414 |  | 19P000414 | FALSE | PB&A | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | Seth Morrison |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43451 | [6 empty] | 8/5/20, DL: This Project is Complete………….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: We have the motor on site, we are working on the permit for the crane. Once we have the crane lift permit, we will schedule the install…………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: We are working on the new motor platform. It is our goal to install the new motor in late January. Once the motor is installed, we will be able to identify if additional work is needed…….11/19/19 DH: Emailed Status Report to customer…..11/15/19, DL: Material has not arrived……..10/30/19, DL: The new exhaust fan is ordered with a 2- 4 lead time. Once the exhaust fan arrives, we will schedule the install……….10/16/19, DL; We are in the process of the work. At this current time, we are not modifying the building to where permits may not be required…….10/1/19, DL; This is in the queue for plans, we will start the plans in the next 3-4 weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 20-21
19P000417 |  | 19P000417 | FALSE | VC-UNIV ADV | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY |  | UV BLDG A | 201 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43452 | [8 empty] | Enrico Baez |  |  | 2019-08-06 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20 | 1
19P000419 |  | 19P000419 | FALSE | CHASS | SL5 CHASS INT SOUTH 2117-CARD ACCESS | Remove Door and wall leading to 2117 Media Library and reconfigure to allow enterance into 2117 A & J without having to go through 2117C. | CHASS INT S | 2117 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43452 | [6 empty] | 12/16/19, DL: This project is now complete…….11/19/19 DH: Emailed Status Report to customer…..11/11/19, The work is 98% Complete. We have one door that we had to send back to the vendor to have it prepared for door hardware. We should have the door back on site with in the next two weeks………..10/30/19, DL: Doors and Frame are on site. The paint team will prime and paint the doors and frame. Once the doors and frame are painted, we will schedule the work……………10/1/19, DL; This Project is 90% Complete. We are waiting on the doors to arrive. Once the doors arrive, we will schedule them to be painted and installed…………..9/3/19, DL; We started this project today. We are planning to be 90% complete by 9/27/19. Note, we have special order doors that have a 4-6 week lead time and that is the reason why we will be only 90% complete on 9/27/19. Paul Richardson is aware of the schedule…….8/15/19, DL; The plans were approved this week, we will order the needed material and start the work very soon…….This is a two part project. We will complete the construction process now. The four doors that need key card access still require a request for proposal and a contract. This portion of the project will take 3- months due to contracts administration, lead time on material and contractor scheduling…….8/1/19, DL; Gunther is working on plans. Once permit is approved, we will schedule the work…. | 2019-03-21 | Enrico Baez | Install 8 position control panel, keyless entry for 2117, 2117A, 2117D and 2117E. ***per Paul Richardson remove 2117G, 2117H and 2117J from request*** !!!!Project to reconfigure wall space, 19P000400 has been combined with 19P000419. !!! | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000420 |  | 19P000420 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT WALL |  | SKYE HALL | 325 | COMPLETE | Kim Wilcox | TBD | REYNA ALARCON |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43453 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000421 |  | 19P000421 | FALSE | CHASS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | Install door to access hallway directly | OLMSTED | 2139I | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 5 | 110 | TRUE |  |  | 43453 | [6 empty] | 2/28/20, DL: This Project is Complete….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This Project is 95% complete. We should be complete within the next week…………..1/31/20 O-DHN: Emailed Status Report to customer……1/30/20,DL; Project is in progress and should be complete with in 2- weeks………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will work on the construction schedule and material shortly after the new year. 11/21/19 DH: Emailed Status Report to customer…..10/30/19, DL: Plans are approved. Need to find out the status of the door. We will plan on scheduling the project shortly after Thanksgiving…………10/1/19, DL; Plans are approved. We need to order the door / Frame. Once door is on site, we will schedule the work……..9/16/19, DL; Plans are submitted for the permit review process……9/3/19, DL; Plans are at 50%. We will try and have plans to submit for review within the next two weeks…… | 2019-02-05 | Enrico Baez | *****This work is being performed to accommodate new faculty scheduled to arrive July 1, 2019***** Core work falls under SLA Carpenters • Open wall between corridor and 2139I. • Install metal frame and solid core door similar to 2139. Smoke and draft gasket. • Install carpet patch at threshold of new door. Carpet should match or complement existing carpet. • Remove bulletin board in hallway to facilitate doorway construction and relocate on same wall. See photos in shared drive.. • Replace base boards as needed. Painters • Prime, Patch and Paint walls, doors and trim. • Paint to match existing wall colors. Lock Shop • Furnish and install 1 each, ADA compliant handle sets, match existing hardware. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2018 | 2021-01-16 | FY 19-20
19P000424 |  | 19P000424 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET |  | CHUNG HALL | 445 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43454 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000425 |  | 19P000425 | FALSE | PB&A | SL5 PAINT VIDEO PRODUCTION SUITE & HANG ITEMS |  | HINDERAKER | 1159A | COMPLETE | Gerry Bomotti | TBD | LISA CUSICK |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43454 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-01-16
19P000427 |  | 19P000427 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | Install Power and TV bracket, move white board | CHUNG HALL | 453 | CANCELED BY FS | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43468 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold……… | 2019-09-18 | Ron Veloz | Install Power and TV bracket, remove white board and relocate , patch and paint wall prior to installing | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21 | 1
19P000428 |  | 19P000428 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES AVC OFFICE PREPARATION |  | STUDENT SERV | 3102 | CANCELED BY CLIENT | LaRae Lundgren | TBD | ANGIE GRAY |  |  |  | 0 |  | FALSE |  |  | 43468 | [8 empty] | Ron Veloz |  | N/A | 2019-01-22 | SPRING 2019 | FS | FALSE | 2019 | 2021-01-16
19P000429 |  | 19P000429 | FALSE | CHASS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | Patch & Paint | COLL BLDG NO | 103 | COMPLETE | Juliet McMullin | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43468 | [6 empty] | 07/26/19 O-ANS: Project complete per Paul Ditty. 06/06/19 O-ANS: Project scheduled to be completed. |  |  |  |  | 2019-07-26 | SPRING 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000431 |  | 19P000431 | FALSE | VC-STU AFF | SL5 STUDENT SERVICES REMOVE NAILS AND PATCH WALL |  | STUDENT SERV | 2128 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | VALERIE SANCHEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43469 | [6 empty] | 6/24/19 O-ANS: CANCEL WO/PROJECT PER DONNA POWELL EMAIL. |  |  |  |  | 2019-06-24 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | C&C CARPORT | 161 | COMPLETE | Danna Gianforte | Shelley Gupta | SHELLEY GUPTA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43472 | [6 empty] | 8/5/20, DL: This Project is complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have the contract, we will schedule the work……………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Project was approved by Shelley. We will work on the contract. Once we have the notice to proceed from contracts, we will order the material and schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Sent Shelley another follow-up email today and she has not verified if she would like to move forward with the project………10/30/19, DL: Sent Shelley the updated quote last week and she has not responded. I sent Shelley a followup email today asking her to let me know if she would like to proceed with the work……..10/16/19, DL; Had a meeting with Shelley, we modified the scope of work and software for the project. We are now revising the quote with our vendor. We should have an updated quote within the next two weeks. If Shelley approves the work and scope, we will proceed….10/1/19, DL; I have a meeting with Shelley this afternoon to review proposal. If she approves the project we will submit plans for a building permit……8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was cancelled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; We have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28/19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21 | 1
19P000434 |  | 19P000434 | FALSE | PROVOST/EVC | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | Please patch 50 plus holes on the wall and repaint that wall in Skye hall 136 due to the BKM removing the furniture attached to the wall. Please call Anita Ortiz if you have any questions at x2-5229. Shanshan's extension x7753 has not been moved to her new location yet. | SKYE HALL | 136 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | SHANSHAN | Paul Ditty |  | 2 |  | FALSE |  |  | 43472 | [6 empty] | 07/20/19 O-ANS: Work Complete per Paul Ditty. |  | Paul Ditty |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000435 |  | 19P000435 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR WEST HALLWAYS - FLOORING | FS to coordinate with client to scope work. | BOURNS | A0145 | CANCELED BY FS | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 43300 | [6 empty] | 2/14/19, DL; This project was a repair and not complete replacement | 2018-10-25 | Ron Veloz |  | YES | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19P000438 |  | 19P000438 | FALSE | CNAS | SL5 BOTANIC GARDENS RAILROAD TIE WALLS | Request for review and cost estimate for the repair of two railroad tie walls in the Botanic Gardens. 1) Retaining wall located below the Iris Garden (across from the Greenhouse). 2) Low wall located along the pathway just below the Garage Office. | BOTAN INFO C |  | CANCELED BY FS | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | 118 |  | FALSE |  |  | 43473 | [8 empty] | Ron Veloz | 03/05/19 O-RVL: RV noticed two requests on the O-UA1 bench and updated notes on this (19P000438) request with notes from 11/07/18 to 03/01/19. END ~ 03/01/19 O-RVL: RV will walk with Chad C to determine if FS is capable of repair/reinstall railroad ties true & plumb. Site walk is scheduled for 03/01 afternoon. END ~ 02/15/19 O-RVL: Updated SOW, RV will schedule a site visit with the Carpentry Supervisor to determine the construction feasibility and estimated costs. END ~ 01/09/19 O-RVL: REQUEST FOR ESTIMATE, Not a Project. RV To schedule a site visit with C. Pillen and Chad Chambers to evaluate if repairs are possible. ~ 12/10/18 O-RVL: REQUEST FOR ESTIMATE. Ron V walked with D. McWilliams & Jodie and identified the railroad tie retaining wall area requiring repairs. Jodie would like an estimate to repair the leaning railroad ties at specified areas. RV to meet with Chris P. and or Chad Chambers to determine if FS can perform work and or provide an estimated cost to perform work. ~ 11/07/18 O-RVL: Received an email form Deborah Mc. to discuss the wall at Thursday during our 1-1 meeting |  | 2019-03-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000439 |  | 19P000439 | FALSE | VC-RED | SL5 SPIETH PATCH AND PAINT ROOM 335 |  | SPIETH | 335 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43473 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2019 | 2021-01-16
19P000440 |  | 19P000440 | FALSE | CNAS | SL5 GH#21--INSTALLATION OF GROW POD BEHIND GREENHOUSE #21 |  | GH21 |  | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER | PATRICIA SPRINGER | Dan Lerman |  | 0 |  | FALSE |  |  | 43473 | [6 empty] | 5/31/19, DL; This project is 100% complete :)……5/15/19, DL; Project is complete except for chain link fence. Fence will be installed some time early next week…….5/1/19, DL; Grow Pod is installed with power and water. Still need to install fence and door lock….. 4/15/19, DL; Grow Pod is scheduled for delivery this Thursay. Once on site, we will connect all utilities and this project will be complete. 2/28/19, DL; Demo is complete. We need to veify utilitiy point of connections. Once utilities are verified, we will install the water and power……. |  | Dan Lerman |  |  | 2019-05-31 | Winter 2019 | FS | FALSE | 2019 | 2021-01-16
19P000442 |  | 19P000442 | FALSE | BCOE | SL5 WINSTON CHUNG- PATCH/PAINT ROOM 319 |  | CHUNG HALL | 319 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43474 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2019 | 2021-01-16
19P000445 |  | 19P000445 | FALSE | BCOE | SL5 BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT |  | BOURNS | B0328D | CANCELED BY FS | Christopher Lynch | TBD | MARGARET SOUDER |  |  |  | 0 |  | FALSE |  |  | 43476 | [8 empty] | Ron Veloz | Install new wall at room 0328 | N/A | 2019-02-27 | SPRING 2019 | FS | FALSE | 2019 | 2021-01-16
19P000448 |  | 19P000448 | FALSE | CHASS | SL5 ARTS 333- PATCH AND PAINT |  | ARTS | 333 | COMPLETE | Juliet McMullin | Cindy Williams | SONJA SEKELY-ROWLAND |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43479 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-04 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000449 |  | 19P000449 | FALSE | CNAS | SL5 PAINT OFFICE AREA OF 229A FOR RELOCATION |  | FAWCETT LAB | 229A | COMPLETE | Kathryn Uhrich | TBD | CHERYL GERRY |  | Paul Ditty |  | 0 |  | FALSE |  |  | 43479 | [6 empty] | 04/05/19 O-ANS: Project complete per Paul Ditty and closed in FAMIS. |  |  |  |  | 2019-04-05 | Winter 2019 | FS | FALSE | 2019 | 2021-01-16
19P000451 |  | 19P000451 | FALSE | SOB | SL5 ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 |  | ANDERSON 1 (N) | 58 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43480 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  |  |  |  | 2019-02-01 | SPRING 2019 | FS | FALSE | 2019 | 2021-01-16
19P000453 |  | 19P000453 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT |  | CHUNG HALL | 447 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43482 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2019 | 2021-01-16
19P000455 |  | 19P000455 | FALSE | VC-STU AFF | SL5 FILL AND PAINT OVER HOLES ON WALL |  | HEALTH SERV | 100 | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43482 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/27/19 |  |  |  |  | 2019-12-27 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000458 |  | 19P000458 | FALSE | SPP | SL5 CHASS INTS-BUILD PERM DRYWALL DIVIDER OR APPROVE BKM AIRWALL |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ | LUISA LEVARIO | Dan Lerman |  | 0 |  | FALSE |  |  | 43484 | [6 empty] | 6/17/19, DL; This project is 100% Complete…..5/31/19, DL; This prject is making good progress and we are scheduled to be complete on or before June 19th…….5/15/19, DL; This project is in progress and schedule for complete near 6/15/19…. 5/1/19; We started this project last week and we are planning to be complete in 4 - 6 Weeks….4/15/19, DL; Material is ordered, we will start the demolition this week. We hope to be complete in 8-weeks or less……2/28/19, DL; Plans are complete and were submitted to for review and approval from campus building official and fire marshal. Once plans are approved, we will shcedule the work….. | 2019-01-28 | Enrico Baez | 1/28/19 EB See Shared drive for additional information. Carpenters • Construct new approx. 4” metal stud walls with 5/8” drywall over 48” x 96”x1/2” sound insulating panels. See plans for location. • Remove T-bar drop ceiling under soffit in location of partitioned space, frame with metal stud, attach 5/8” drywall over sound insulating panels. • Extend soffit face flush to meet with new walls, frame under soffit, cover with sound insulating panels and 5/8” drywall. • Install 1 ADA compliant half lite, 36" wide, 3/4" thick, paint grade, entry door and trim in each space. • Finish and texture walls to match existing. • Install base cove to match. Electrical • No additional electrical outlets to be added. • Install switched recessed can lights, similar to existing, 4 in each new space. Fire Protection and Suppression • Relocate existing fire sprinklers to be compliant in each newly created space. • Relocate and add smoke detectors in each newly created space. Painters • Prime, Patch and Paint walls, ceiling, doors and trim. Lock Shop • Furnish and install 2 each, ADA compliant handle sets, match existing hardware HVAC • Relocate HVAC duct work in new extended soffit. Split 10” center duct or two new spaces with 6” Wye and registers. • Provide return air in ceiling. • No thermostat or zone controls will be installed. Customer informed. | YES | 2019-06-17 | Spring 2019 | FS | FALSE | 2019 | 2021-01-16
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43487 | [6 empty] | 8/5/20, DL: This Project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer…..2/18/20, DL: We are making great progress and still on schedule to be complete before Spring Break begins. We pass drywall inspection on 2/18/20………..1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: Plans are approved. All items have been removed from the space. Abatement is schedule to take place within two weeks…..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were submitted for plan check review. Fire marshal stamped the plans, we are waiting on the final stamp from our building official. Once plans are approved we will order material and schedule the work……..10/30/19, DL: Gunter is working on plans. We are planning to complete the work before Spring Quarter begins. |  | Dan Lerman |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
19P000467 |  | 19P000467 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | WATKINS | 2101 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 43487 | [6 empty] | 1/14/20, DL: This project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Project is 99.9% complete. We should be complete with the work by this Friday. Furniture is scheduled to be install this Friday morning……..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL; The project is still on schedule to be completed on 12/12/19…………….10/30/19, DL: This Project is on Schedule to be completed on or before 12/17/19….10/16/19, DL; This project is in progress with a completion date of 12/15/19…….10/1/19, DL; We will schedule the work. Our portion of the project will be completed mid December……….9/16/19, DL; We will work on the plans soon. This project will be complete by 12/21/19….. 09/03/19 O-ANS: Updated Priority to #1 for Fall 2019 per Susan request. 9/3/19, We are scheduled to complete the work before winter break begins….. |  | Enrico Baez |  |  | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000473 |  | 19P000473 | FALSE | PROVOST/EVC | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 |  | HINDERAKER | 1100 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | TORRI MCGARITY | Paul Ditty |  | 1 |  | FALSE |  |  | 43494 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-28 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GH08 | 881 | COMPLETE | Kathryn Uhrich | TBD | NANCY FERGUSON |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43494 | [6 empty] | 1/19/21, DL: This project is complete……………8/5/20, DL: This project is in Progress and should be complete in the next 8-12 weeks…………….3/25/20, DL: Work orders are produced. Once we are back to work, we will schedule the work………12/11/19 O-ANS: Re-assigned as project allotment - priority #7 for Winter 2020. 11/27/19 O-ANS: Hold by client for re-prioritization for Winter 2020. | 2020-03-04 | Ron Veloz | Install new 3 ton Packaged unit with heat pump and dedicated electrical service on the roof top. Provide 1ea return plenum, 2ea supply drops in the work space. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
19P000477 |  | 19P000477 | FALSE | BCOE | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT |  | CHUNG HALL | 457 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 11 |  | FALSE |  |  | 43495 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000482 |  | 19P000482 | FALSE | CNAS | SL5 PIERCE HALL- PAINT/PATCH HOLES IN 1219C AND 1220D |  | PIERCE | 1219C | COMPLETE | Kathryn Uhrich | TBD | JACQUELINE HAMILTON |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43497 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000483 |  | 19P000483 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED |  | HEALTH SERV | 404, 407, 412, 405 & 411 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43497 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-11-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000485 |  | 19P000485 | FALSE | CNAS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | CHAPMAN | 9 | IN PROGRESS | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43494 | [6 empty] | 1/10/21, DL: This project is almost complete. This project will be complete in the next 30- days………...9/30/20, DL: Fume Hood demolition and abatement will be completed on 10/2/20. Fume hood install should be coplete in mid Novemeber……8/5/20, DL: We will submit plans this week. Once plans are approved, we will schedule the work……………Work orders are produced. We need to work on plans and permits once we return.. | 2020-02-10 | Ron Veloz | Disconnect, cap and safe off the existing utility services. Provide the necessary abatement services to properly remove the fume hood from the site and deliver to the campus surplus yard. Install one new department furnished fume hood. Abatement Services: Provide the necessary abatement services to perform all utilities disconnections and floor repair. Floorcovering: Patch and or repair as necessary to match or provide a close match. Install rubber base. Access Control: Survey and adjust the entry door closer to increase latch pull to allow the door to closer completely. Patching and painting: Patch and paint wall at the old fume hood location. Mechanical: Disconnect metal duct, cap/safe off, reconnect/reconfigure new duct to accommodate the new fume hood. Electrical: Provide electrical disconnections and safe off. Reconnect/reconfigure power to the new fume hood. Plumbing: Disconnect Air, Gas, Vacuum, Cold water, and Drain, cap and safe off and reconnect/reconfigure service to the new fume hood. Resource Management: Properly remove the fume hood from the site and deliver to the campus surplus yard. | YES |  | Spring 2020 | FS | FALSE | 2019 | 2021-01-16
19P000487 |  | 19P000487 | FALSE | BCOE | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES |  | BOURNS | A219, A211, A241 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43501 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000495 |  | 19P000495 | FALSE | VC-RED | SL5 UOB RM 209- PATCH & PAINT |  | UNIV OFC BLD | 209 | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43504 | [6 empty] | 07/30/19 O-ANS: Project closed per Paul Ditty. 07/30/19 D-MMN: Moved furniture and filled holes. Taped base and fixtures. Primed and painted one half of office. Pulled tape replaced plates and moved furniture to other side. Removed plates taped base and fixtures. Primed and painted other half. Used spray texture on patch under window. Pulled masking. Replaced plates. Moved furniture back. Vacuumed carpet during and after total process. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000502 |  | 19P000502 | FALSE | BCOE | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | Install Electrical power & TV bracket.for a 75" TV to mount in CS 342. | CHUNG HALL | 444 | CANCELED BY FS | Christopher Lynch | TBD | RICHARD BAIN |  | Dan Lerman |  | R3 |  | FALSE |  |  | 43515 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This project is on hold……………3/25/20, DL: Work orders are produced. I will work on scheduling the work when we return back to work…….. | 2019-09-17 | Ron Veloz | Install Electrical power & TV bracket. Excludes network/data back box and stub up to ceiling. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21 | 1
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB. Patch Paint walls, replace flooring, refinish wood cabinets and sinks. | SPIETH | 2349 | TO BE PERFORMED BY PD&C | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43516 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold……….12/11/19: O-ANS: Reassigned as project allotment - priority #5 for Winter 2020. 11/27/19 O-ANS: Placed on Hold for re-prioritization by client for Winter 2020. | 2020-02-27 | Ron Veloz | Patch and paint and extra work to upgrade an old lab that we are now inhabiting. In addition to painting, we need to have floors re-surfaced, cabinets re-stained, and counter tops re-surfaced, if possible. There is also a metal sink that could be polished. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
19P000505 |  | 19P000505 | FALSE | CNAS | SL5 CHAPMAN HALL PAINT OFFICE WALL WHERE BOOK CASE WAS REMOVED |  | CHAPMAN | 10B | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 0 |  | FALSE |  |  | 43521 | [6 empty] | 05/10/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-05-10 | Winter 2019 | FS | FALSE | 2019 | 2021-01-16
19P000508 |  | 19P000508 | FALSE | CNAS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | BOYCE | 3410 | COMPLETE | Kathryn Uhrich | TBD | CHERYL GERRY |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43517 | [6 empty] | 1/30/20, DL: Project is now cxomplete. The electrical panel cover was installed this morning…………. 11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: We are not complete. We still need to complete the following items; Light bulbs, electrical panel cover, replace ACM ceiling tiles and deep clean the space…..10/30/19, DL: Progress is in progress. We should be done within two weeks…….10/16/19, DL; Paint is in progress and additional work to follow. Target date for complete is 11/19/19…..10/1/19, DL; Jess to survey space for ACM, Lead paint, etc… We will schedule work once we have confirmation from Jess….. | 2019-09-30 | Ron Veloz | ……….Remove lower base cabinets and upper cabinet in room 3410B. Repair delaminated flooring between room 3410 & 3426, Patch and Paint entire rooms 3410, 3410B & 3426 up to 8'H(no paint in in 3410 A&C). Repair damaged floor tiles in room 3410 A&B. Repace all burned out lamps w/ LED throughout labs and office. Strip & wax all floors in labs space. Remove cylinder racks in room 3410B. Fabricate a hinged metal door to cover the electrical panel in roon 3426 (panel is near door). | YES | 2020-01-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | CANCELED BY FS | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | R7 |  | FALSE |  |  | 43523 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced. We will schedule the work when we return from campus closure………11/11/19, DL: Project is in the queue to start but we do not have an FAU# as this is a recharge project. I sent Enrico and James an email requesting the FAU#. Once we have an FAU #, I will work on scheudling the work…..10/1/19, DL; Enrico is wtill working on estimate. | 2018-10-19 | Enrico Baez | E. Baez 1. Provide power in ceiling for projector. 2. Install projector center in room between two 4ft light fixtures. 3. Install 2 duplex outlets in 4S box on South West corner of room 4. Remove existing screen. 5. Install new screen centered on South wall. Extend power from existing screen to new screen location. 6. Use existing screen power switch to control new screen. | YES | 2020-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21 | 1
19P000517 |  | 19P000517 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | COMPLETE | LaRae Lundgren | TBD | DANIELLE GARCIA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43531 | [6 empty] | 1/19/21, DL: This project is complete…………..8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced, We will schedule the work when we return from the campus closure…………11/11/19, DL: I will work on scheduling this project… | 2019-06-17 | Enrico Baez | 6/17/19 E. Baez Conducted site visit with Sean. Will need carpenters to mount TV and electricians to add outlet to North wall. Data not needed. Might need painters depending on how carpenters install TV mount. | YES | 2021-01-19 | FALL 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
19P000521 |  | 19P000521 | FALSE | SoB | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT |  | ANDERSON 1 (N) | 138 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43532 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000523 |  | 19P000523 | FALSE | CNAS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | PATCH & PAINT GRAD STUDENT OFFICE | SPIETH | 3366 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 5 | 9 | FALSE |  |  | 43536 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-20 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000526 |  | 19P000526 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT |  | CHUNG HALL | 0202 & 0203 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43536 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-08 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000534 |  | 19P000534 | FALSE | VC-STU AFF | SL5 PATCH WALLS AND PAINT |  | HEALTH SERV | 334 | CANCELED BY FS | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43539 | [6 empty] | 12/06/19 O-ANS: Canceled by FS because unable to identify room location even after inspecting rooms with staff support. Original requester has since retired. |  |  |  |  | 2019-12-06 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000535 |  | 19P000535 | FALSE | PB&A | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV | Install TV Mount and additional electrical | BANNOCK H | H0108 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43538 | [7 empty] | 2019-07-08 | Enrico Baez | Install TV Mount and additional electrical | YES | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install electrical utilities for new equipment | PHYSICS | 1132 | IN PROGRESS | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43543 | [6 empty] | 1/19/21, DL: This project is in progress and will be complete with in 30- days………..9/30/20, DL: Plans were submitted for Plan Check review last week and we should have an update on the plan check review process soon………..8/5/20, DL: Need to meet with Kirk to verify electrical load. Once confirmed, we will work on plans for a permit | 2019-10-15 | Ron Veloz | Install utilities for new equipment | YES |  | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000540 |  | 19P000540 | FALSE | CHASS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | Remove metal roll up window, replace carpet, remove round column cover-reframe square. | HUM & SOC SC | 1202 | COMPLETE | Juliet McMullin | Cindy Williams | MICHAEL MOLINAR |  | Dan Lerman |  | 9 |  | FALSE |  |  | 43544 | [6 empty] | 2/18/20, DL: Thois project is 100% Complete…….1/31/20 O-DHN: Emailed Status Report to customer…..1/30/20, DL; Project is 95% complete. We will install carpet this weekend………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is in progress and should be complete within 3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project was delayed. Material is ordered. We are currently scheduled to start shortly after 1/6/20………..11/19/19 DH: Emailed Status Report to customer…..10/30/19, DL: We will plan on scheduling the project shortly after Thanksgiving……….. 10/16/19, DL; Plans were approved, we will work on ordering material and schedule the work. Anticipated start date is mid-November…….10/1/19, DL; Plans were submitted last week. Once plans are approved, we will schedule the work…………9/16/19, DL; Plans are 90% Complete. We will submit plans for plan check review in the next two weeks……. 8/15/19, DL; Gunter has the project on his list. We will try and be ready for plan check review in the next two weeks…….. | 2019-07-25 | Enrico Baez | 7/1/2019 E. Baez Carpenters: 1. Remove roll up partition and stainless steel counter top. 2. Frame opening, hang drywall, tape and finish 3. Remove round decorative column from support pillar. 4. Frame over column for square foot print. Keep as narrow as possible. 5. Hang drywall, tape and finish. Painters: 1. Paint all new construction Flooring: 1. Remove carpet and base in 1202, lobby area of 1220 and hallway. Refer to drawing. 2. Replace customer selected carpet and base. | YES | 2020-02-18 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000543 |  | 19P000543 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION | TV Bracket &Power/Network box. | CHEMICAL SCI | 342 | CANCELED BY FS | Kathryn Uhrich | TBD | JEFFERY MATUTE |  | Dan Lerman |  | R8 |  | FALSE |  |  | 43545 | [7 empty] | 2019-10-01 | Ron Veloz | "The Chemistry Department is purchasing a 75" TV to mount in CS 342. The wall that will hold the TV needs to be inspected before any action of mounting the TV is done. The wall that we are hoping to place is the Brown-ish wall, where the projector screen is, opposite to the single whiteboard (Upon entry of CS 342, the leftmost wall). We would like a electrical outlet behind the TV, if possible". RV-Cut back sound proofing (sound soak) to accommodate TV brkt & electrical. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | R3 |  | TRUE |  |  | 43550 | [6 empty] | 8/5/20, DL: This Project is COMPLETE…….3/25/20, DL: The material is here and we are 95% complete with the work. We will complete the work when we return from the campus closure…………1/31/20 O-DHN: Emailed Status Report to customer…….1/30/20,DL: The pump is now on site but we are still waiting for the fittings. In the mean time, our plumber is putting everything together and is working on the installation. Once the fittings arrive, we will make the connections and the system should be good to go………….1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: The pump is scheduled to arrive on or before 1/31/20. We will schedule the work once we have the pump and material on site…..11/26/19, DL; Emailed Natalie and Sherice the quote for the vacuum pump. We will order the material and schedule the work once we have approval and the pump on site……11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: I sent the vendor a 2nd email requesting an update on the proposal. I also included Natalie on the email so she is aware of where we stand with the proposal……10/30/19, DL: We had a followup meeting with the vendor last week. The vendor is now working on a pump that will best meet our needs……….10/16/19, DL; We are working with a vendor on a quote for a new lab vacuum pump. We are hoping to have a quote in the next week or two…..9/16/19, DL; Estimate was provided to customer last week. If the project is approved, we will work on the plans and permits. Once approved, we will schedule the work…… |  | Ron Veloz | Old SOW Revised SOWInstall exhaust hood, electical receptacle, vacuum pump, vac lines and valves (six valves total) and hood location. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21 | 1
19P000552 |  | 19P000552 | FALSE | CHASS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS |  | HUM & SOC SC | 1001 B, C, and D | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43551 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000553 |  | 19P000553 | FALSE | VC-RED | SL5 SPIETH HALL PATCH AND PAINT |  | SPIETH | 341 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43556 | [6 empty] | 07/26/19 O-ANS: Project Complete per Paul Ditty. |  |  |  |  | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000555 |  | 19P000555 | FALSE | CNAS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK | INSTALL OF FENCE FOR RAIN COLLECTOR AT TES TANK | SAT CHIL PL | 0 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | R4 |  | FALSE |  |  | 43558 | [6 empty] | 10/30/19 O-RVL: RV sent Andrew a message to ask if a decision was made to proceed with this project or if it will be cancelled?" Pending response. END~ 10/16/19, DL; I placed this project on hold as we have not heard back from the customer. We notified the customer of the cost but have not heard back from them. If the project is approved, we will schedule the work………...10/1/19, DL; Ron provide Deborah the propsal and we are waiting for her response to proceed or cancel the project……...9/16/19, DL; Ron submitted the estimate to Debora and the Faculty member last week. If project is approved, we will schedule the work……9/3/19, DL; Plans and estimate are complete. Ron will provide Deborah with a formal estimate and let us know if we will proceed with the work…..8/15/19, DL; Plans are approved. We ware waiting for a estimate from our contractor. Once we have the quote, we will forward the quoted to Deborah for review and approval. Note, this is a recharge project…….8/1/19, DL; Plans are complete pending approval from building official…. |  | Ron Veloz | Install Chain Link fence with gate. Includes grading, gravel and fence posts set in concrete. |  | 2019-10-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
19P000558 |  | 19P000558 | FALSE | BCOE | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT |  | BOURNS | A0265 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43558 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000560 |  | 19P000560 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION |  | UV BLDG B | 0240B | COMPLETE | Susan Marshburn | Da Lan Dinh | LESLIE ROSE |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43559 | [6 empty] | 9/3/19, DL; This project is 100% complete. We still need to conduct training but the work is complete and training is scheduled…..8/15/19, DL; This Project is 90% Complete and will be complete by the end of the week. Please note. ITS still needs to connect the data lines. Our portion of the work is complete………8/1/19, DL; Plans are approved. Material is ordered. We will schedule the work when the material is on site…. |  | Dan Lerman |  |  | 2019-09-03 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
19P000564 |  | 19P000564 | FALSE | VC-UNIV ADV | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | 1156C (AVC Johnny Cruz) – Patch molly holes, touch-up paint. 1156A (Jules Bernstein) – Remove (2) black & white photos from wall. Patch molly holes, touch-up paint. 1156B – Install picture frame (UCR campus map) onto wall. Suite 1159 – Patch holes. Remove film reels. Paint one accent wall “UCR Blue”. 1159B (Christy Zwicke) - Patch molly holes, touch-up paint. | HINDERAKER | 1156 | COMPLETE | Peter Hayashida | Naysia Caldwell | Lisa Cusick | Christy Zwicke | Paul Ditty |  | 1 |  | FALSE |  |  | 43563 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-07 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000565 |  | 19P000565 | FALSE | BCOE | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS |  | BOURNS | A0133 | CANCELED BY CLIENT | Christopher Lynch | TBD | NANCY FORD |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43563 | [6 empty] | 07/30/19 O-ANS: Per Paul Ditty, Customer Maggie Souder canceled project. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000568 |  | 19P000568 | FALSE | CHASS | HOLD SL5 HMSS HANG WHITE BOARD, TV MOUNTING, PATCH AND PAINT | Remove Glass White Board, mount TV, patch and paint | HUM & SOC SC | 1214 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43564 | [8 empty] | Enrico Baez | No scope |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
19P000571 |  | 19P000571 | FALSE | CNAS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 |  | SCIENCE LAB1 | 215 & 322 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO |  | Paul Ditty |  | 10 |  | FALSE |  |  | 43565 | [6 empty] | 07/30/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000572 |  | 19P000572 | FALSE | GRAD DIV | SL5 PATCH, PAINT, AND CARPET UOB 152 |  | UNIV OFC BLD | 152 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43566 | [6 empty] | 06/28/19 O-ANS: Paint phase complete and awaiting carpet change. |  |  |  |  | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000573 |  | 19P000573 | FALSE | PB&A | SL5 UNIVERSITY VILLAGE PAINT /REMOVE NAILS |  | UV BLDG B | 0208L | CANCELED BY CLIENT | Gerry Bomotti | TBD | JUDITH ABBEY |  | Paul Ditty |  | R2 |  | FALSE |  |  | 43566 | [6 empty] | 06/14/19 O-ANS: Canceled by Customer via email from Georgianne Carlson "Project 19P000573, UV Room 208L. Human Resources Department has withdrawn the request for this patch and paint project. Not a priority, at this time." |  |  |  |  | 2019-06-14 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 |  | 1
19P000574 |  | 19P000574 | FALSE | CHASS | SL5 FACULTY OFFICE PAINTING |  | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43567 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000575 |  | 19P000575 | FALSE | CHASS | SL5 WATKINS HALL PAINT/FLOORING |  | WATKINS | 1309A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43572 | [6 empty] | 11/26/2019 O-ANS: Paint phase completed per Paul Ditty. Awaiting completion of flooring. |  |  | 01/31/20 O-ANS: Completed per notes as of 09/05/19. |  | 2019-09-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000585 |  | 19P000585 | FALSE | CHASS | SL5 HUMANITIES SS, RM 3604- PATCH/PAINT WEST WALL |  | HUM & SOC SC | 3604 | COMPLETE | Juliet McMullin | Cindy Williams | DARA CERDA |  | Paul Ditty |  | 11 |  | FALSE |  |  | 43574 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000588 |  | 19P000588 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - PATCH & PAINT OFFICES |  | BOURNS | A127 Office, A129 Office, A131 Office, A133 Office, A135 Office, A137 Office, A139 Office, and A141 Office | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43577 | [6 empty] | 06/28/19 O-ANS: Paint phase complete. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000589 |  | 19P000589 | FALSE | CHASS | SL5 HMSS OFFICE 3405 RENOVATIONS | Construct partion, pending CBO approval, in room 3405. | HUM & SOC SC | 3405 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 8 |  | FALSE |  |  | 43578 | [6 empty] | 11/19/19 DH: Emailed Status Report to customer…..11/19/19 DL: This project is complete….11/11/19, DL: The carpet is delayed and scheduled to be instlled on Friday, 11/15/19. The project will be complete once the carpet is installed……10/30/19, DL: This project is 90% Complete. We are planning to install carpet next week………..10/16/19, DL; This project is 80% complete. Target complete date is 3- weeks…..10/3/19 O-ANS: Updated status per minor reno meeting…. 10/1/19, DL; This project is in progress. We will call for rough electrical inspection….. 9/16/19, DL; We are ready to schedule the work. We are currently waiting for the space to be vacated. Once the space is vacant, we will start the project……9/3/19, DL; We are ready to start the work. The PI returned to work this week. I sent Paul R. an email letting him know we are available to start once we have confirmed dates from him…..8/15/19, DL; Plans are approved but the PI is not. We will probably start the project the 2nd week in September…… | 2019-06-27 | Enrico Baez | CARPENTERS: 1. Construct partition above T-bar ceiling, full height not required. Drywall 5/8" tape and finish. 2. Remove and store three book cases. 3. Cut in opening for 36" (stain grade to match) door in general area of were bookcases were in South wall leading to corridor. Painters: 1. Patch and paint as needed Electricians: 1. Isolate existing switches to control to operate lights in West half of partitioned space. 2. Install two additional switches in East partition. 3. Install additional single gang outlets one on each side of new partition. Telecom: 1. Install additional Voice and data connection in Western side of partitioned space. Flooring: 1. Remove carpet and base. 2. Install new customer selected base and flooring. HVAC: 1. Separate existing duct work from one to two zones controlled by separate stats in each office. | YES | 2019-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000594 |  | 19P000594 | FALSE | CNAS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS | Take down a dividing wall in this office and move the desks to their old location and rehang the overhead desk bins back into their old locations with inserts still in the walls. | ENTOMOLOGY | 171 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  | R9 |  | FALSE |  |  | 43581 | [8 empty] | Ron Veloz | TBD | NO | 2019-09-18 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
19P000597 |  | 19P000597 | FALSE | BCOE | SL5 PATCH AND PAINT WALLS |  | CHUNG HALL | 355, 356, 351, & 353 | COMPLETE | Christopher Lynch | TBD | SARA GALLOWAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43588 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000599 |  | 19P000599 | FALSE | PB&A | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 43594 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43594 | [6 empty] | 8/5/20, DL: This Project is Complete…….3/25/20, DL: Project is 95% complete. We will install the fire sprinkler and exhaust duct to the gas cabinet when we return from the campus closure………..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Plans were approved and material is ordered. We are hopeful the material will arrive the 2nd or 3rd week in January. Once material is on site we will schedule the work…… 11/19/19 DH: Emailed Status Report to customer……10/16/19, DL: This project is 90% Complete. We are working on plans and permits for the two snorkels……….10/1/19, DL: This project is almost complete. We will be complete in the next 4- weeks except the Snorkel……….. 9/13/19, DL; The paint of the cabinets is scheduled for this week along with the power. We will submit the plans for the snorkel this with in the next two weeks…….9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Ron Veloz | SOW, Patch& Paint Walls, replace plexi glass on shelving, powder coat metal shelving & cabinets, clean & polish or replace chem sinks, polish counter tops, Validate all gas, water, drains, DI water & utilities. Replace damaged and dirty ceiling tiles, relamp as needed. Strip & wax floor. Dan L is requesting vendor pricing to restore finishes. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
19P000601 |  | 19P000601 | FALSE | BCOE | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY | Renopvate lab space, Patch/paint, Re-finish, re-surface – existing cabinets/casework. Re-finish, bench-tops. Clean existing Chemical fume hood. Repair or replace self-closing chemical/flammables storage cabinet. Repair or replace bench shelves as needed. Clean and wax floors. | BOURNS | B0328E | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43594 | [6 empty] | 2/28/20, DL: This project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL; This Project should be complete in the next 2-3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were approved. We will order material and schedule the work once the material is on site. The material should arrive around the 21st of January…….11/25/19, DL; Floor covering will be complete today. This project is complete except for the Snorkel vents. We are still waiting for plans check approval on the snorkels………11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Floor covering is delayed. We will schedule the floor covering installation when the material is on site. We submitted the plans for the snorkels last week. Once the plans are approved, we will order the phoenix valves and schedule the work………. 10/30/19, DL: This Project is 85% Complete. We will install new floor covering in the next two weeks. All work will be completed except the two snorkels. We still need to submit plans for the snorkels……..10/16/19, DL; This project is 80% complete. 9/16/19, DL; Project is in progress. We still need to submit plans for the snorkel for the power and snorkel. We will submit the plans for review within the next week. Once plans are approved, we will schedule the work……..Scope is complete, waiting on estimates from vendors. We will need to work up a contract which will add time to the project timeline… | 2019-08-06 | Ron Veloz | Provide two new 4” exhaust duct drops. One at the south wall above mobile table & one at the east wall above counter. Refinish two wood work station counter tops with chemical resistant coating (approx. 64lf) including one mobile table wood top. Install four(4) 208v / 30a Electrical receptacles and data drops at gutter racks above two work benches Provide drawer and door maintenance and or repairs at all metal cabinets and metal shelving. Powder coat all lower metal cabinets, shelving, fume hood doors and drawers. Replace damaged sheet vinyl flooring as needed. Move surplus items to materials management as identified by the PI. Install MilQ equipment at the east wall near sink. Relocated cylinder rack as necessary to accommodate “L” shaped work station. Provide and install two new cylinder racks at the south end of two work benches. Furnish and install two new metal cylinder racks. Replace damaged and/or stained 2x4 acoustical ceiling tiles. Relocate “L” shaped front cabinets. Relamp light fixtures and needed. Infill wall between rm 328E & D Patch and paint walls. Strip and wax floor. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000602 |  | 19P000602 | FALSE | BCOE | SL5 BOURNS B328F- PREPARE LAB FOR NEW PI OCCUPANCY |  | BOURNS | B0328F | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43594 | [6 empty] | 3/25/20, DL: this Project is Complete………...2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is almost complete and should be complete in the next 2-3 weeks………..10/30/19, DL: Plans and permits will be required for the work. We will work on the plans shortly after Thanksgiving……….. | 2019-09-27 | Ron Veloz | Construct metal stud wall framing and bracing above ceiling to infill the opening. Remove and reinstallation wall mounted cabinets located near the cased opening to access and join to the existing wall to new drywall. Install sound insulation. Install drywall, tape, sand, prime and paint wall. Install install rubber base to match existing. Modify T-bar ceiling to accept the wall framing Provide dust containment (Zip Walls) at both rooms near construction area. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000603 |  | 19P000603 | FALSE | CHASS | SL5 CHASS INT N, RM 3046- PATCH AND PAINT - NEW FACULTY OFFICE |  | CHASS INT N | 3046 | COMPLETE | Juliet McMullin | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  | 12 |  | TRUE |  |  | 43595 | [6 empty] | 06/18/19 O-ANS: Project complete per updates. 06/15/19 D-MMN: Painted remaining finish. Pulled masking and plastic. Replaced plates and vacuumed. |  |  |  |  | 2019-06-18 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000604 |  | 19P000604 | FALSE | CHASS | SL5 HUMANITIES SS, RM 7704- PAINT OFFICE BY JULY 1, 2019 |  | HUM & SOC SC | 7704 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43595 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000605 |  | 19P000605 | FALSE | CHASS | SL5 PAINT NEW MAILROOM |  | WATKINS | 1320E | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43595 | [6 empty] | 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000606 |  | 19P000606 | FALSE | CHASS | SL5 PAINT ROOM |  | WATKINS | 1213 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 10 |  | FALSE |  |  | 43595 | [6 empty] | 06/14/19 O-ANS: Stephen spoke with customer Becky Campbell via phone who confirmed that project was going to be canceled due to re-allocation of space by another dept. |  |  |  |  | 2019-06-14 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000607 |  | 19P000607 | FALSE | CHASS | SL5 PAINT FACULTY OFFICE |  | WATKINS | 1312 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 2 |  | TRUE |  |  | 43595 | [6 empty] | 08/26/19: Canceled by customer because duplicate of project 20P000044. 08/13/19 O-ANS: Customer scope of work includes more than just PAINT so project added to Fall 2019 list for prioritization by organization. 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000608 |  | 19P000608 | FALSE | CHASS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE |  | WATKINS | 1345 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43595 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-27 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000609 |  | 19P000609 | FALSE | CHASS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR |  | WATKINS | 1229 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43595 | [6 empty] | 07/03/19 O-ANS: Paint phase complete and awaiting flooring change. 06/21/19 O-ANS: Customer requested to remove lighting change from project and only complete paint and carpeting via email to Paul Ditty (copied email below). Will create separate work order for lighting. Re-assigned to Paul Ditty to complete. "From: Becky L Campbell <becky.campbell@ucr.edu> Sent: Friday, June 21, 2019 10:51 AM In regards of the work order: 19P000609 - SL5 - PAINT FACULTY OFFICE – please cancel the connecting Work Order 19W015231 – REPLACING THE LIGHTING IN WATKINS 1229. Please do paint and replace flooring.For the lighting, please create new work order to be done at a later time." |  | Paul Ditty |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000613 |  | 19P000613 | FALSE | CNAS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT |  | COLL BLDG NO | 0203B | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43599 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-21 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000614 |  | 19P000614 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 202- PAINT |  | COLL BLDG NO | 0202 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000615 |  | 19P000615 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT |  | COLL BLDG NO | 203 AND 204 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43599 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000616 |  | 19P000616 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 208- PAINT |  | COLL BLDG NO | 208 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000617 |  | 19P000617 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 212- PAINT |  | COLL BLDG NO | 212 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000618 |  | 19P000618 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 205 AND 205A- PAINT |  | COLL BLDG NO | 205 AND 205A | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43599 | [6 empty] | 06/11/19 O-ANS: Per Paul, conference room was in decent condition and does not need to be repainted. He will speak with customer to explain. |  |  |  |  | 2019-06-11 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000619 |  | 19P000619 | FALSE | BCOE | SL5 BOURNS, RM A0311- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0311 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43599 | [6 empty] | 06/28/19 O-ANS: Paint phase complete and awaitin flooring install. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000620 |  | 19P000620 | FALSE | BCOE | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0304 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 9 |  | TRUE |  |  | 43599 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000621 |  | 19P000621 | FALSE | BCOE | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0308 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 10 |  | TRUE |  |  | 43599 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000622 |  | 19P000622 | FALSE | CNAS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK | Replace doors & frame | FAWCETT LAB | 204 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43600 | [6 empty] | 11/11/19, DL: This project is complete……10/30/19,DL: The doors are scheduled to be installed this Friday…………10/16/19, DL; Doors shuld be here with in the next week. Once the doors arrive, we will prep and paint the first coat and schedule the install. Target complete date is 3-4 weeks depending on when the doors arrive…….9/16/19, DL The doors are ordered. Once the doors arrive, we will schedule them to be painted and installed……..9/3/19, DL; Contractor has PO# for the doors. I need to verify lead time on material and schedule the installation…….8/15/19, DL; PO# will be provided this week to order the doors and frame, lead time is 4- weeks for the doors/ frame. We will scheudule the install once the door / frame is on site……..8/1/19, DL ; Pending estimate from vendor. Once we have everything needed, we will schedule the work…. | 2019-07-15 | Ron Veloz | Replace existing dual egress doors with ne doors and frames. | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000623 |  | 19P000623 | FALSE | BCOE | HOLD SL5 WINSTON CHUNG HALL, RM 348- MOUNT TV |  | CHUNG HALL | 0348 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  |  |  | FALSE |  |  | 43600 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000624 |  | 19P000624 | FALSE | BCOE | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | Refurbish Room-Student Space, | BOURNS | A0346 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43600 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Susanna is working on a cubicle layout. Once we have the information from her. We will schedule the work………… | 2019-11-07 | Ron Veloz | Remove all lower cabinets in room A0346 and all lower cabinets and mail boxes in Rm A0304 | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
19P000625 |  | 19P000625 | FALSE | BCOE | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM |  | BOURNS | A0108 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43600 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-01 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000627 |  | 19P000627 | FALSE | GSOE | SL5 SPROUL HALL, RM 2120- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2120 | CANCELED BY CLIENT | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 | 2 | TRUE |  |  | 43600 | [6 empty] | 01/29/20 O-ANS: Canceled per email from customer Karen Naples: "I’ve checked with Sally and this request to paint the Sproul 2120 office can be cancelled. We will submit a new work order if we need to have the office painted at a later time." 08/13/19 O-ANS: Customer requested that project be moved to Fall 2019 list for prioritization. |  | Paul Ditty |  |  | 2019-01-29 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16
19P000628 |  | 19P000628 | FALSE | GSOE | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2129 | COMPLETE | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43600 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000638 |  | 19P000638 | FALSE | BCOE | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM | renovate lab | BOURNS | B207 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43601 | [6 empty] | 11/11/19, DL: This project is Complete……10/30/19, DL: This Project is 95% complete and we should be complete next week………..10/16/19, DL; This project is 99% complete. We need to insulate ducting and deep clean the lab………9/16/19, DL; Project is 95% complete. We are planning to be complete in the next 30 days……9/3/19, DL; Project is in progress and 75% complete. 8/15/19, DL; Plans were approved this week. We will order the material and schedule the work……..Plans are 90% complete and we will probably submit plans for plan check review this Monday | 2019-07-19 | Ron Veloz | 07-01-19 O-RVL: RV Received email from Luat on 06-28 with revised SOW. RV Uploaded the referenced sketch into FAMIS. Revisions read: "In efforts to be helpful, I've color coded comments related to the simple attached sketch. 1) Unchanged: HVAC ductwork needs to be insulated so that we cannot hear it— the vibrations from the noise affect precision optical measurements. 2) Revised to be more specific: only the first row of overhead lights should be on the main switch (dark green). The other lights should be lowered and have pull-down chains, like this but with a longer a longer chain: https://www.grainger.com/product/19YX62 3) Removed: it would be nice if cabinets are nicer and not broken, but we'll turn them into open shelves if there are no funds for this. 4) Removed: (unless fire marshalls object and request sprinklers be lowered) 5) 3) Revised: for air venting machined fumes and soldering, a flexible fume vent should be installed, something like this: https://www.grainger.com/product/EXTRACT-ALL-Extractor-Arm-2DBX4 I'm flexible about where this is hung... what are the options? 6) 4) Revised: the utility rack in the center of the room should be moved to be in line with the other, and centered with the whiteboard on the wall. (Pink) 5) Added: chilled water (blue) and compressed air (light green) should be piped over so it's available to the 10'x3' optical table. 6) Added: Black plywood would be installed at the height of the current 8 1/2" frame like Kevin's in 2 spaces: a) around the 10x3' marked optical table b) around the 6x3' overhead rack close to the doors. Luat T. Vuong" | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000639 |  | 19P000639 | FALSE | CNAS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK | Make modifications to accommodate new PI | CHEMICAL SCI | 0435 | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43602 | [6 empty] | 12/16/19, DL: This project is complete…11/19/19 Emailed Status to customer….11/11/19, DL: This project is 90% Complete. We should be complete with the balance of the work in the next two weeks…………10/30/19, DL: This project is in progress and should be complete in 3- weeks……..10/16/19, DL; We will start the work in the next two weeks. 9/16/19, DL; We will start working on the plans in the next 3- weeks and submit them for plan check review. Once approved, we will schedule the work……..9/3/19, DL; Need to verify scope with Ron and start working on plans. Will start plans in the next two- three weeks…… | 2019-07-19 | Ron Veloz | For new Faculty Hire, Dr. Timothy Su we need the following done to CS 435: Original SOW: (1) Add a door between 435 and 439 (swinging outside of 435 into 439). (2) Exhaust connection for a biosafety cabinet (3) Vacuum line hook up (4) Gas cylinder rack Revised SOW 07/30/19: Room 435: (A) Remove mounted wooden cabinets (B) Remove standing wooden cabinet (C) Move flammable cabinet to Room 439 (D) Move flammable refrigerator to Room 447 Room 439: (A) Remove cabinets under sink Room 441: (A) Remove cabinets under sink (B) Remove top and bottom cabinets and bench, then deliver both items to Chemical Sciences Rm 108 (C) De-activate airflow in chemical fume hood #005855 if it does not disrupt air flow in the other chemical fume hoods. Can facilities check whether it is possible to turn valve off for this fume hood without disrupting others? (D) Move biosafety cabinet and incubator from Rm 458 to Rm 441, then hook up biosafety cabinet to house vacuum plumbing (E) Move flammable cabinet to Rm 439 | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000640 |  | 19P000640 | FALSE | CHASS | SL5 NEW FACULTY - PATCH & PAINT SPROUL 3108 |  | SPROUL | 3108 | COMPLETE | Juliet McMullin | Cindy Williams | MELISA VICARIO |  | Paul Ditty |  | 13 |  | TRUE |  |  | 43605 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000642 |  | 19P000642 | FALSE | CHASS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM |  | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43606 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000643 |  | 19P000643 | FALSE | CHASS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH |  | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 14 |  | FALSE |  |  | 43606 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000645 |  | 19P000645 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT | Termite Treatment/Cover Gate House and repair roughtd woos as necessary | BOTAN INFO C |  | CANCELED BY FS | Susan Marshburn | Da Lan Dinh | RONALD ANDERSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43607 | [8 empty] | Ron Veloz | BOTANIC GARDEN GATE HOUSE (AND OTHER STRUCTURES) REQUIRES EXTERMINATION OF TERMITES- WITH INSPECTION RESULTS RECEIVED BY ERS |  | 2019-08-29 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
19P000646 |  | 19P000646 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING |  | ATH DANCE | 20R, 20S | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43608 | [6 empty] | 9/16/19, DL; This project is Complete…….9/3/19, DL; Project is 80% Complete. Floor covering is scheduled for this Friday. Target complete date is 9/13/19……8/15/19, DL; This project is in progress and slated for complete by the end of september…..8/1/19, DL; Project is in progress with a complete date of 3-4 weeks. |  | Dan Lerman | 06/19/19 O-ANS: Project 19P000647 was combined with this project. |  | 2019-09-16 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000647 |  | 19P000647 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- LOCKER ROOM REFRESH |  | ATH DANCE | Men's & Women's Locker Rooms | CANCELED BY FS | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43608 | [6 empty] | 6/19/19 O-ANS: Combined with project 19P000646 since work in the same area. Dan Lerman to perform scope. |  | Dan Lerman |  |  | 2019-06-19 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16
19P000657 |  | 19P000657 | FALSE | BCOE | SL5 WINSTON CHUNG HALL, RM 406- PATCH/PAINT OFFICE |  | CHUNG HALL | 406 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43623 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000658 |  | 19P000658 | FALSE | SOM | SL5 SOM RB- PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD - PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43627 | [6 empty] | 03/05/20 O-ANS: Canceled by client per Cynthia Carolina. |  | Ron Veloz | TBD | NO | 2020-03-05 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000659 |  | 19P000659 | FALSE | SOM | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43627 | [6 empty] | 08/05/20 O-ANS: Canceled by client (Cynthia Carolina) via email with Ron Veloz. 8/5/20, DL: Dan to follow -up with customer…………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "remove 330 from work order / update project details / Update: Furniture on order 3.30.2020 - delivery tbd" |  | Ron Veloz | TBD | NO | 2020-08-05 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
19P000660 |  | 19P000660 | FALSE | SOM | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SL5 SOME RB, RM 330- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43627 | [6 empty] | 9/30/20, DL: This Project is Complete………..8/5/20, DL: Dan to follow-up with customer…………..03/05/20 O-ANS: Removed room 330 per client request. Only updates to 107 & 111. |  | Ron Veloz | TBD | NO | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
19P000661 |  | 19P000661 | FALSE | SOM | SL5 SOM RB, CR0600- FY 19/20 PROJECT- PATCH & PAINT |  | SOM EDUC | CR0600 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43627 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000662 |  | 19P000662 | FALSE | SOM | SL5 FY19-20 PROJECT: DEANS CONF ROOM | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | SOM EDUC | 2652 | CANCELED BY FS | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43628 | [8 empty] | Ron Veloz | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | NO | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000664 |  | 19P000664 | FALSE | CHASS | SL5 WATKINS HALL, RM 1343/1343A- PAINT OFFICE AND LAB |  | WATKINS | 1343 & 1343A | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43628 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-08 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000665 |  | 19P000665 | FALSE | PB&A | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | Existing telephone-communications building on University Ave requires repairs and renovation in preparation for new use as fire safety offices. | TELEPHONE |  | COMPLETE | Gerry Bomotti | TBD | Carmen Long | Melissa Garrety | Dan Lerman |  | 2 |  | FALSE |  |  | 43649 | [6 empty] | 2/19/20; This project is complete. We still need to paint the door black but this was not part of the original scope. The paint shop will paint the door in the next two weeks………… 1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL:. This project is 99.9% complete with a few minor punch list items…..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project is on track to finish before the new year with a punch items to be addressed after the new year. IT services still needs to install data and phone. Landscape services is working on the landscape but the landscape was not part of the original scope. Sharyl in is the process of coordinating keys, alarm code and setting up the delivery of the furniture for her team. Overall, we are all in good shape.…….11/19/19 DH: Emailed Status Report to customer…..11/11/19,DL: This project is still on schedule to be complete before the new year……….10/30/19, DL: This project is in progress and on track to be complete before the new year…………….10/16/19, DL: Drain, waste, vent and concrete is complete. We started framing this week. We will start rough electrical and rough plumbing next week……..9/3/19, DL; Abatement was complete this weekend. Trades are scheduled and we are on track for 11/15/19 completion date…..8/15/19, DL Plans were approved this week. Abatement is still needed and the 14- day notification to AQMD is complete. We are on track to complete the work by mid November……. |  | Enrico Baez |  |  | 2020-02-19 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000666 |  | 19P000666 | FALSE | SOM | SL5 WEBBER, ROOM 1237- PATCH AND PAINT | TBD - SOM RM 107, 111 & 330- PROJECT: NEW PI, EQUIPMENT INSTALL | WEBBER | 1237 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43633 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-11 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000670 |  | 19P000670 | FALSE | SOM | SL5 SOME, RM 1670- RENOVATE FOR EXPANDED ENROLLMENT |  | SOM EDUC | 1670 | TO BE PERFORMED BY PD&C | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 43634 | [8 empty] | Ron Veloz |  |  | 2019-09-06 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000673 |  | 19P000673 | FALSE | SOB | SL5 ANDERSON HAL NO, RM 158- RECARPET 12 ROOMS / ELECTRICAL WORK |  | ANDERSON 1 (N) | 158 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43634 | [6 empty] | 10/1/19, DL; This proect is complete… |  | Enrico Baez |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000674 |  | 19P000674 | FALSE | CHASS | SL5 HMSS RM 2416 OFFICE ROOM PATCH AND PAINT |  | HUM & SOC SC | 2416 | TO BE PERFORMED BY PD&C | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43635 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-23 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000676 |  | 19P000676 | FALSE | CHASS | SL5 PATCH THE PAINT IN THIS OFFICE |  | HUM & SOC SC | 2501 | COMPLETE | Juliet McMullin | Cindy Williams | EVAN ISMAIL |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43635 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000683 |  | 19P000683 | FALSE | PROVOST/EVC | SL5 PATHC/PAINTING REPAIR |  | HUM & SOC SC | 1103A | COMPLETE | Thomas Smith | Luisa Levario | JILL CANTONWINE |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43641 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19P000687 |  | 19P000687 | FALSE | PB&A | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | COMPLETE | Gerry Bomotti | TBD | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 43642 | [6 empty] | 8/5/20, DL This Project is Complete……………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Contracts is processing the contract. Once the contract is complete, we will schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Plans were approved. I sent Brendan an email 11/11/19 requesting an FAU # as this is Recharge work. Once we have the FAU #, we will work on the contract agreement with the contractor………10/30/19, DL; Sent Lezlie and email asking if she has an update on the resubmitted plans on 10/30/19………..10/16/19, DL; The plans were resubmitted for plan check review this week. We are hopeful the plans will be approved this week. Once approved we will work on contract and scheduling the work…10/7/19 LB: This is a test. The timestamp will be reset when the test is done. 10/1/19, DL: We are working on plan check review. We should have approved plans in the next two weeks…..8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | Provide estimate to install key card access control |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21 | 1
19P000688 |  | 19P000688 | FALSE | CNAS | SL5 PHYSICS- RENOVATION OF THREE PHYSICS ROOMS | Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 2128 | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43644 | [6 empty] | 1/14/20, DL: This Project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 99% Complete. Custodial will be there this week to complete the final clean. The space will be ready for occupancy starting 1/6/19…..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: The project is on track to be complete on 12/13/19. Once the abatement is complete, we will start the wall repair as the walls are severely damaged from the previous use of the space……10/30/19, DL: WE are working on this project. Our target date for completion is 12/17/19………… | 2019-10-16 | Ron Veloz | Test for ACM and or other hazardous materials in the room. RM 2124, 2128 & 2132: Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2128 Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2132: Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
19S000833 |  | 19S000833 | FALSE | SOM | Add access control to entry doors |  | HECKMAN ICEM | Entry Doors | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 43298 | [8 empty] | Ron Veloz |  | YES | 2018-09-19 | Summer 2018 | FS | FALSE | 2018 | 2021-01-16
19W002419 |  | 19W002419 | FALSE | ITS | SL5 ITS CENTER - INSTALL CARD READER ACCESS |  | ITS CENTER | 161 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 43321 | [11 empty] | 2019-01-08 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
19W002930 |  | 19W002930 | FALSE | CHASS | HOLD - SL5 PATCH HOLES & PAINT - HUMANITIIES SOCSCI |  | HUM & SOC SC | 1203 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 11 |  | FALSE |  |  | 43329 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19W003012 |  | 19W003012 | FALSE | CNAS | SL5 FIX RESTROOMS (PAINT AND FLOORS) | FS to coordinate with client to schedule work for completion. | CHAPMAN | 5 | CANCELED BY FS | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 51 |  | FALSE |  |  | 43329 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty |  | N/A | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19W003050 |  | 19W003050 | FALSE | VC-RED | SL5 SPEITH HALL - PATCH & PAINT HOLE IN WALL |  | SPIETH | 0359A | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43333 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-01-16
19W007474 |  | 19W007474 | FALSE | CNAS | SL5 BG - RAILROAD TIE WALLS | Repair Railroad Ties at Botanic Gardens | BOTAN INFO C |  | CANCELED BY FS | Kathryn Uhrich | TBD | AMBER RHEMREV | [5 empty] | FALSE |  |  | 43411 | [7 empty] | 2018-12-10 | Ron Veloz | Request For "ESTIMATE" to repair the raillroad ties used as a retaining wall at botanic gardens. | YES | 2019-03-11 | Winter 2019 | FS | FALSE | 2018 | 2021-01-16
20P000002 |  | 20P000002 | FALSE | CHASS | SL5 HMNSS, RM 1212- REMOVAL OF ROLL UP WINDOW |  | HUM & SOC SC | 1212 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43647 | [6 empty] | 1/30/20, DL: This project is Complete. We will istall the monitor after IT services installls the Data lines. Michael or Aliosn will notify us when IT is complete and we will schedule th emonitor installation…………1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: This project is in progress and will be complete with in two weeks……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project was delayed. The material is currently ordered. We are planning to start the week of 1/6/20……. 11/19/19 DH: Emailed Status Report to customer….10/30/19, DL; We will plan on scheduling the work shortly after Thanksgiving……….10/16/19, DL: Plans are approved, we will order the material and schedule the work once material is on site. Projected start date is mid November………..9/16/19, DL; Plans will be submitted this week for building permit and plan check review….. | 2019-10-01 | Dan Lerman | Remove Roll up partition. Install outlet and data port, patch and paint walls. | YES | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000003 |  | 20P000003 | FALSE | GRAD DIV | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | ADD POWER/DATA, PATCH/PAINT | UNIV OFC BLD |  | PLAN DEVELOPMENT/CHECK | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS | CHERYL GERRY | Dan Lerman |  | 1 |  | FALSE |  |  | 43648 | [6 empty] | 1/19/21, DL: Plans were approved and we will schedule the work in the near future………. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Permit is approved. We need to verify floor covering. Once floor covering is confirmed and ordered, we will schedule the work………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We will need plans as we are installing a new hydration station and a Counter top that needs to be ADA compliant…………We started the plans and will submit them for a permit and plan check review within 2- weeks……….10/30/19, DL: No Plans will be needed. We will plan on scheduling the work shortly after Thanksgiving……. | 2019-06-13 | Enrico Baez | 9/24/2019 E. Baez--SCOPE-- 1. Removal and disposal of one bulletin board and two director cases. 2. Removal and disposal of abandoned telephone mounting bracket. 3. Remove and dispose of abandoned alarm box in wall. 4. Patch and paint walls in lobby and public restroom area. 5. Provide electrical connection for wall mounted monitor. 6. Cut access for data boxes. 7. Install monitor mount on wall. 8. Construct 7" x 18" laminate counter top and install in Lobby. | YES |  | FALL 2019 | FS | FALSE | 2019 | 2021-01-16
20P000004 |  | 20P000004 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - COURTNEY BAKER |  | HUM & SOC SC | 2204 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43648 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000005 |  | 20P000005 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - KIM FROST |  | HUM & SOC SC | 3215 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43648 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000008 |  | 20P000008 | FALSE | PB&A | SL5 EHS 1133 - PATCH / PAINT AND FIX HOLES IN WALLS |  | ENV HLTHSFTY | 1133 | COMPLETE | Gerry Bomotti | TBD | CESAR PLA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43654 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-07 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000017 |  | 20P000017 | FALSE | CNAS | SL5 COLLEGE BLDG CR200 - PAINT PROJECT |  | COLL BLDG NO | CR0200 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Dan Lerman |  | R4 |  | FALSE |  |  | 43661 | [6 empty] | 1/30/20, DL: This Project was Canceled per Rohnda via email on 1/29/20……….11/26/19, DL; Provided Ronda with updated quote on 11/25/19: She will present the quote to her team and provide us with an update in the near future if they would like to proceed………11/20/19 O-ANS: Re-assigned to Dan Lerman. Project was originally a paint project but will be outsourced as Recharge project paid for by the customer's department. |  | Dan Lerman |  |  | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000019 |  | 20P000019 | FALSE | CNAS | SL5 PHYSICS 2029A- NEW EYEWASH STATION | PHYSICS 2029A- INSTALL A NEW EYEWASH STATION | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43662 | [6 empty] | 2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL; Permit was approved, we need to order material and schedule the work………. | 2019-11-27 | Ron Veloz | Install new eyewashing station | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000023 |  | 20P000023 | FALSE | CNAS | SL5 PIERCE RM 1144 - PATCH AND PAINT DOOR WHERE WALL POCKET WAS |  | PIERCE | 1144 | COMPLETE | Kathryn Uhrich | TBD | JACQUELINE |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43664 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000024 |  | 20P000024 | FALSE | CNAS | SL5 PHYSICS 1003- RENOVATION | New Faculty-Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 1003 | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43664 | [6 empty] | 3/25/20, DL: This project is complete……2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: The paint is complete and the floor covering should be delivered this week. Once the floor covering is on site, we will schedule the installation……………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We started this project and should be complete in the next 6- weeks……….11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: David who is responsible for clearing out the space is in the process. Once the space is empty we will schedule the work. We will probably start the physical project shortly after Thanksgiving…….10/30/19, DL; We are planning to start this project within the next 6-8 weeks……. | 2019-10-16 | Ron Veloz | Test for ACM and or other hazardous materials in the room. Replace all existing flooring, remove power pole and miscellaneous wall mounted items shelving/racks, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks) and repair/replace top & bottom flush bolts, install new door closer(s), relamp with LED as needed. Replace faucet, clean sink/counter and infill pit. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000026 |  | 20P000026 | FALSE | VC-RED | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | Install T-bar ceiling, Provide HVAC and Fire sprinklers drops. Install new 2x4 LED light fixtures | LIFE SCIENCE | Basement Level | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43665 | [6 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: The plans were submitted two weeks ago. We should receive the plan check review comments in the near future…………….8/5/20, DL: This Project will exceed $50,000. Monty A. will inform customer this is a project that will need to be managerd through PD&C……………3/25/20, DL: We will work on plans when we return back from the campus closure. | 2020-01-31 | Ron Veloz | Install T-bar ceiling with wipable(coated) ceiling tile. Provide HVAC and new Fire sprinklers drops to new ceiling. Install new 2x4 LED light fixtures. Verify Fire alarm systems work. | YES | 2021-01-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000028 |  | 20P000028 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0219- PAINT FACULTY OFFICES |  | BOURNS | A0219 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43665 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000029 |  | 20P000029 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0211- PAINT FACULTY OFFICES |  | BOURNS | A0211 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43665 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/12/19 |  | Paul Ditty |  |  | 2019-12-12 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000031 |  | 20P000031 | FALSE | GSOE | SL5 SPROUL HALL 1124B- PATCH/PAINT OFFICE |  | SPROUL | 1124B | COMPLETE | Thomas Smith | Sally Tavizon | MARICELA ARCINIEGA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43668 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000034 |  | 20P000034 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 451- PATCH AND PAINT 2 SMALL WALL SECTIONS |  | CHEMICAL SCI | 451 | COMPLETE | Kathryn Uhrich | TBD | KEVIN KOU |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43668 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-02 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000036 |  | 20P000036 | FALSE | CNAS | SL5 ENTOMOLOGY 224 - PAINT OFFICE FOR NEW PI HANSEN |  | ENTOMOLOGY | 224 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43669 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20. 09/19/19 O-ANS: Project placed on HOLD for WINTER 2020 prioritization per customer request. |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000037 |  | 20P000037 | FALSE | PB&A | SL5 FAC ADMINISTRATION -PAINT WALLS |  | FS ADMIN | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 43669 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000038 |  | 20P000038 | FALSE | CNAS | SL5 BATCHELOR HALL 1151- QUOTE FOR ADDING FOB ACCESS TO A DOOR |  | BATCHELOR | 1151 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | RACHEL BEHAR |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43670 | [6 empty] | 09/24/19 O-ANS: PROJECT CANCELD BY CLIENT PER EMAIL FROM DEBORAH MCWILLIAMS. |  | Ron Veloz |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000039 |  | 20P000039 | FALSE | BCOE | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE |  | BOURNS | A0318 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43598 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……..09/19/19 O-ANS: HOLD FOR WINTER 2020 PER CUSTOMER (LOUIS SANDOVAL) REQUEST. EMAILED PAUL DITTY TO CONFIRM. PAUL STATED THIS IS NON-PAINT PROJECT B/C SCOPE OF WORK INCLUDES CARPENTERS AND ELECTRIC SHOPS. |  | Paul Ditty |  |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000044 |  | 20P000044 | FALSE | CHASS | SL5 WATKINS 1312 - NEW HIRE RENOVATION - ELIZABETH BERGER | Install drywall over out dated would paneling | WATKINS | 1312 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43676 | [6 empty] | 2/19/20, DL: This project is Complete…………..1/14/20, DL: We started this project today and should be complete with in 3-4 weeks………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will plan on starting the project the 2nd week in January but will not confirm until we have confirmation from the carpenter shop…………11/18/19 DH: Emailed Status Report to customer……11/11/19, DL: The Material is ordered. The carpenters may start the work the week of 11/18/19………10/30/19, DL: I received confirmation the space is vacant we will schedule the work in the next 6- 8 weeks……10/16/19, DL; The plans are approved and the work is complete. I need to schedule final inspection………. | 2019-09-23 | Enrico Baez | ABATEMENT NEEDED----remove mastic from walls at base on wood paneled wall CARPENTERS 1.) Remove chalk board 2.) Install 1/2" plywood over wood paneled walls. Including over plywood partition separating wall. Do not drywall over trim. 3.) Finish drywall. ELECTRICIANS 1.) Bring out electrical for new drywall and secure when drywall has been installed. PAINTERS 1.) Patch, paint and finish all walls. CUSTODIAL 1.) Clean space after construction. | YES | 2020-02-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000045 |  | 20P000045 | FALSE | VC-RED | SL5 MRB SOUND BOOTH |  | MRB | 2210 & 2204 | COMPLETE | Rodolfo Torres | Laura Manor | DAN LERMAN |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43676 | [6 empty] | 11/11/19, DL: This project is complete…….10/30/19, DL: This project is complete but we need to conduct the final inspection with the building official………..10/16/19, DL: The plans are approved and the work is complete. I need to field verify and schedule the inspection. |  | Ron Veloz | Contact PM for SOW. | NO | 2019-11-11 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000046 |  | 20P000046 | FALSE | CNAS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN | 0001 | PROJECT INTAKE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43677 | [6 empty] | 1/19/21, DL: Enrico B. will manage this priject………….11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Install wireless access controls systems at front and rear entry doors. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16 |  | 1
20P000047 |  | 20P000047 | FALSE | VC-RED | SL5 ADVANCED NEUROIMAGING | NEEDING TO TAKE DOWN OVERHEAD CABINETRY AND REPLACE WITH SOME KIND OF SHELVING TO OPTIMIZE SPACE. LOOKING FOR AN ESTIMATE AND A PLAN. | ADV NEURO |  | CANCELED BY FS | Rodolfo Torres | Laura Manor | CHELSEA EVELYN |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43677 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice…….3/23/20, DL: Shelves are ordered. We will schedule the work when we return from the campus closure……….1/15/20 O-DHN: Emailed Status Report to customer…...1/14/20, DL: We waiting for a revised quote from the vendor as there quote was not complete. We will process the quote for a PO# when we receive the correct quote……. 11/11/19, DL: Need to review scope with Ron as the shelving system is a special order item with a 3- month lead time….. | 2019-09-24 | Ron Veloz | Remove 5'-0" x3'-0" upper cabinet, and soffits. Patch and paint walls to match the existing grey . Install customer furnished adjustable shelf. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000051 |  | 20P000051 | FALSE | SOM | SL5 SOMED 2611 - PATCH & PAINT |  | SOM EDUC | 2611 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43677 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000054 |  | 20P000054 | FALSE | SOM | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOMED-SOME G0600, G0621 & 1682B- ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43677 | [6 empty] | 9/30/20, DL: This Project is Complete…………..8/5/20, DL, Dan to follow-up with customer………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "Remove status Hold / Update project detail to include information on 1682B -ADD ELECTRICAL, PAINT/PATCH, AND RELOCATE WHITE BOARD." |  | Ron Veloz | Room G0600 Install Power behind and below the TV, install one TV Bracket, install one cut-in back box below the TV for data(data cabling by ITS), Paint the entire East wall to match existing. Room G0621 Insatll three(3) new double duplex receptacles and three(3) data back boxes only(no data cabling) in room G0621. Install SS tubing for Co2 from room G0621 to room G0623. Include Valves at both ends of P.O.C., Install one uni-strut siesmic cylinder support at the south wall. Steve Burleson has walked the site and has knowledge of the SOW. Loading Dock Install Pole & chains at Loading dock. |  | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000059 |  | 20P000059 | FALSE | SOM | SL5 SOME 2626- PATCH & PAINT |  | SOM EDUC | 2626 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43682 | [6 empty] | 11/26/2019 O-ANS: Project canceled per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000060 |  | 20P000060 | FALSE | SOM | SL5 WEBBER HALL 1274- PATCH & PAINT OFFICE |  | WEBBER | 1274 | COMPLETE | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43682 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-28 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000061 |  | 20P000061 | FALSE | CNAS | SL5 PHYSICS 1028 - MOVE UTILITIES FOR GLASS SHOP | Install utilities in Physics for the Glass shop equipment relocated from Pierce. | PHYSICS | 1028 | COMPLETE | Kathryn Uhrich | TBD | CHRISTOPHER BARDEEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43683 | [6 empty] | 04/23/20 O-ANS: Complete per Dan Lerman. Separate work order to install gas line created - 20W026489 …. 1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is 90% complete and should be 100% complete 1/24/20………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 95% complete. They are moving the equipment over. Once the equipment is delivered and setup, we will connect all of the power and plumbing……11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL; We are still working on plans for this project. 10/30/19, DL: We're planning to complete the project by 12/7/19. We are working on the plans and are planning to submit the plans for plan check review tomorrow. | 2019-10-16 | Ron Veloz | Electrical: Relocate existing power for the welder & other equipment. Install new power and safety switch for relocated equipment. Relocate power for welder and other equipment to the machine shop side of the north wall. Plumbing: Lab air and Natural Gas - relocate and install new POC's. Install water supply lines to Wet sander and diamond wet saw. Cap and or extend the existing Lab air and natural gas as necessary. Install drain lines for new equipment. Modify water supply and existing sink and faucet. Carpentry: Demo selected upper and lower cabinets at the West wall. | YES | 2020-04-23 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000065 |  | 20P000065 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR CONFERENCE ROOM 205/206 - PATCH & PAINT |  | CHUNG HALL | 205 & 206 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43685 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000067 |  | 20P000067 | FALSE | BCOE | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM | BOURNS | B-Wing | TO BE PERFORMED BY PD&C | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | R1 |  | FALSE |  |  | 42688 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold until further notice……. |  | Ron Veloz | Replace access controls at BCOE WCH & Bourns bldgs. |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2016 | 2021-01-16 | FY 20-21 | 1
20P000068 |  | 20P000068 | FALSE | CHANCELLOR | SL5 SKYE 349 - COVER HOLES ON WALL |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | TBD | VICTORIA AVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43686 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000070 |  | 20P000070 | FALSE | BCOE | SL5 BOURNS B342D - PREPARE LAB FOR NEW FACULTY | PREPARE LAB FOR NEW FACULTY | BOURNS | B0342D | COMPLETE | Christopher Lynch | TBD | SABRINA SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43686 | [6 empty] | 2/28/20, DL This Project is Complete……….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is 95% Complete, we need to install 3 power outlets. This project will be 100% complete within two weeks……..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is on schedule to be complete before the 2/3/20 complete date…….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19,DL: We conducted a site visit with the PI> We will do what we can to have the project complete before 2/3/20………… | 2019-11-06 | Ron Veloz | Paint all walls to match existing colors, paint the back of wood cabinets located at the east side of the room, replace stained or damaged ceiling tiles, replace and or replace all HVAC supply & return grilles, relamp as needed, Cal Labs to clean SS sinks, disconnect and dispose of the dishwasher, Plumbing and electrical to disconnect, Cal Labs to refurbish counter tops (light sand & seal), clean strip and wax sheet vinyl floor, repair and refurbish cabinets (white Rm 316, Blue Rm 328), customer to remove all chemical and sanitize fume hoods. | YES | 2020-02-28 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000073 |  | 20P000073 | FALSE | VC-STU AFF | SL5 HUB - THE WELL -3RD FL RM 346 DOOR INSTALLATION CP00003544 | DOOR INSTALLATION | HUB | 346 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | JONATHAN GODOY |  | Dan Lerman |  | PENDING |  | FALSE |  |  | 43689 | [6 empty] | 12/13/19 O-ANS: Project canceled by client Brendan O-Brien. | 2019-10-02 | Enrico Baez | 1.) Remove Aluminum accordian door from opening. Customer to determine how to discard. 2.) Frame opening with metal 2"x4" stud and sheet with 3/4" drywall. Allow for oppening to accommodate 36"x 80" door. 3.) Install metal door jamb and casing to match exisiting openings. Door to match exisiting. Campus Fire Marshall to determine if door to be fire rated. Swing to be approved by Campus Building official and/or Campus Fire Marshall. 4.) Relocate single gang outlet on North side of opening , if needed. 5.) Finish drywall, prime and paint walls. Texture to match exisiting. Customer to approve final paint color. | YES | 2019-12-13 | FALL 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000075 |  | 20P000075 | FALSE | CNAS | SL5 SPIETH 2372 - PATCH/PAINT FACULTY OFFICE |  | SPIETH | 2372 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43690 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-27 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000077 |  | 20P000077 | FALSE | GSOE | SL5 SPROUL HALL 1223 - PATCH AND PAINT |  | SPROUL | 1223 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43683 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-25 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000081 |  | 20P000081 | FALSE | CNAS | SL5 CHEM SCI 0441- INSTALL FUME HOODS | Install vacuum to new fume hood | CHEMICAL SCI | 441 | COMPLETE | Kathryn Uhrich | TBD | TIMOTHY SU |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43692 | [6 empty] | 1/14/20, DL This Project is 100% Complete…….12/17/19 O-DHN: Emailed Status report to customer…..12/16/19, DL: This Project is almost Complete except for connecting the glove box. Cory will try and connect the glove box before the new year……...11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: This project should be complete with in the next two weeks……….10/30/19, DL: This project is in progress and we should be complete in 2- 3 weeks…………10/16/19, DL: We will start this project with in the next two weeks…. |  | Ron Veloz | Install eight (8ea) electrical swithced outlets behind cabinets for new vac pumps, remove doors and install sliding lower pump shelves. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000082 |  | 20P000082 | FALSE | CHASS | SL5 HUMANITIES THEATRE - PATCH & PAINT |  | THTR WKSH | 405 | COMPLETE | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43692 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000083 |  | 20P000083 | FALSE | PB&A | SL5 STUDENT SERVICES - INSTALL 8 CUBICLES - CP00003537 | Installation of BKM Cubicles with electric and Data | STUDENT SERV | 3rd Floor | COMPLETE | Gerry Bomotti | TBD | SHARYL MURDOCK |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43641 | [6 empty] | 1/14/20, DL: This project is 100% Complete………..11/18/19 DH: Emailed Status Report to customer…..10/30/19, DL: The plans were approved and we are scheduled to do the work in December…………10/16/19, DL: Plans were submitted this week…….. |  | Enrico Baez | Scope completed by Dan Lerman | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000085 |  | 20P000085 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 FACILITES ANNEX B - PAINT OFFICE SPACE |  | FS ANNEX B | 0001 | COMPLETE | Susan Marshburn | Da Lan Dinh | SANDRA MARTINEZ |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 43696 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000086 |  | 20P000086 | FALSE | CNAS | SL5 SKYE 2ND FLOOR - KEY CARD ACCESS ESTIMATE |  | SKYE HALL | 2ND FLOOR | CANCELED BY CLIENT | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | R3 |  | FALSE |  |  | 43696 | [6 empty] | 09/26/19 O-ANS: CANCELED BY CUSTOMER - Estimated cost to go keyless outside of budget. | 2019-09-10 | Enrico Baez | Provide estimate for keyless entry. | YES | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000090 |  | 20P000090 | FALSE | CHASS | SL5 OLMSTED 3345 - PAINT WALL AND FILL HOLES |  | OLMSTED | 3345 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43697 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000093 |  | 20P000093 | FALSE | ATHLETICS | SL5 ATHLETICS 0078 - TELEVISION MOUNT/ ELECTRICAL |  | ATH DANCE | 0078 | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43697 | [6 empty] | 11/26/19 O-ANS: Project canceled per communication with Enrico. | 2019-10-04 | Enrico Baez | Install TV bracket on wall near weight room. Provide recessed/flush single gang outlet near bracket. | YES | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000094 |  | 20P000094 | FALSE | CHASS | SL5 ARTS 0221 -PAINT OFFICE |  | ARTS | 221 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43699 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000105 |  | 20P000105 | FALSE | CNAS | SL5 PHYSICS 2029 - PATCH AND PAINT |  | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Paul Ditty |  | 17 |  | FALSE |  |  | 43705 | [8 empty] | Paul Ditty | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/06/20. |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000107 |  | 20P000107 | FALSE | BCOE | SL5 WINSTON CHUNG 322 - PATCH/PAINT NEW FACULTY FACULTY OFFICE |  | CHUNG HALL | 322 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43706 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000112 |  | 20P000112 | FALSE | CHASS | SL5 PSYCHOLOGY 2123 - PATCH AND PAINT JOB |  | PSYCHOLOGY1 | 2123 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43712 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000113 |  | 20P000113 | FALSE | CNAS | SL5 GEOLOGY 2258 - PATCHPAINT RECEPTION WALL OVER BIN REMOVED |  | GEOLOGY | 2258 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43712 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000114 |  | 20P000114 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER DOOR, BASEBOARD, AND BRACKETS |  | PENTLAND A |  | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000115 |  | 20P000115 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 1 - BALCONY COSMETIC REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R2 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000116 |  | 20P000116 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 5 - BALCONY EMERGENCY REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R3 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000117 |  | 20P000117 | FALSE | PB&A | SL5 PENTLAND HILLS A-H - LATTICE REBUILD |  | PENTLAND A | A-H | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R4 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000118 |  | 20P000118 | FALSE | PB&A | SL5 FALKIRK 1, 2, & 12 - FIRST FLOOR PATIO FENCING |  | FALKIRK 1 | 1st Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R5 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000120 |  | 20P000120 | FALSE | CHASS | SL5 OLMSTED 2139 SUITE - PATCH AND PAINT |  | OLMSTED | 2139 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 43713 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/14/20 |  | Paul Ditty |  |  | 2020-01-14 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000121 |  | 20P000121 | FALSE | CNAS | SL5 SKYE 217 - PATCH AND PAINT |  | SKYE HALL | 217 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43713 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000127 |  | 20P000127 | FALSE | PB&A | SL5 FALKIRK APARTMENTS EMERGENCY EGRESS |  | FALKIRK 1 | 10E | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 43721 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000129 |  | 20P000129 | FALSE | BCOE | SL5 BOURNS HALL B0360C - PATCH & PAINT |  | BOURNS | B0360C | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES | KATHY COCKER | Paul Ditty |  | 1 |  | TRUE |  |  | 43720 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/22/20 |  | Paul Ditty |  |  | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000135 |  | 20P000135 | FALSE | BCOE | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MS&E Rm 0075 - 3 Ph208 Power CHW S&R WATER PPMS TOOL, Install Chilled water loop & power in clean room 075. | MAT SCI ENGR | 75 | COMPLETE | Christopher Lynch | TBD | MARK HEIDEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43727 | [6 empty] | 9/30/20, DL: This project is complete……..8/5/20, DL: This is in progress…….3/25/20, DL: We will work on plans and permits when we return back from the campus closure……. | 2020-02-18 | Ron Veloz | Intake/SOW: Install 208V 3ph power & disconnect/safety switch and one 3/4" Chilled water loop (Supply and Return) in the MSE southeast corner of clean room 0075. Create a 4" diameter pass-thru hole from this corner of room 0075 into the adjacent room 0071. FS to provide power and cooling to a compressor which will connect through the wall to the PPMS system with cryogenic helium lines. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000140 |  | 20P000140 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4400 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4400 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-10-09 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000141 |  | 20P000141 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4401- PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4401 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000142 |  | 20P000142 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 5502 - PATCH AND PAINT FACULTY OFFICE |  | HUM & SOC SC | 5502 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000143 |  | 20P000143 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 6605 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 6605 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000144 |  | 20P000144 | FALSE | CNAS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A | BOYCE | 3432, 3432A, 3446, 3446A | IN PROGRESS | Kathryn Uhrich | TBD | MATTHEW ULRICH | CHERYL GERRY | Dan Lerman |  | 3 |  | FALSE |  |  | 43734 | [6 empty] | 1/19/20, DL: This project is in progress and will be complete in the next 30- days………….9/30/20, DL: WE have started a few items but we are waiting on Matt U. and the PI to remove their items so we can have access to the space. Once the space is cleared out, we will proceed with the work…………8/5/20, DL: We will start the work in the next 4-6 weeks. | 2020-02-18 | Ron Veloz | Boyce 3432, 3446, 3436 and 3436A . Patch and paint 3432, 3432A, 3436, 3436A, 3446, 3446A. Reface/replace water damaged cabinets near sink (3446). Install GCFI outlets near sink (replace existing) (3446). Install panel cover for electrical panel box. Replace many burnt out bulbs in ceiling lamps. Replace broken chemical plexi-glass on bench shelves. | YES |  | Winter 2020 | FS | FALSE | 2019 | 2021-01-16
20P000145 |  | 20P000145 | FALSE | CHASS | SL5 PSYCHOLOGY 1111 - PATCH AND PAINT FRONT OFFICE WALL |  | PSYCHOLOGY1 | 1111 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43733 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20 |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000149 |  | 20P000149 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 242 |  | UNIV OFC BLD | 242 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000150 |  | 20P000150 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 207 |  | UNIV OFC BLD | 207 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000151 |  | 20P000151 | FALSE | SoB | SL5 ANDERSON HALL NO 113 - PATCH/PAINT HOLES |  | ANDERSON 1 (N) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43738 | [6 empty] | 03/02/20 O-ANS: Project complete per Paul Ditty as of 02/07/20. |  | Paul Ditty |  |  | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000152 |  | 20P000152 | FALSE | SOM | SL5 SOME 2669 - PATCH & PAINT |  | SOM EDUC | 2669 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | TRACEY TRETTIN | Paul Ditty |  | - |  | FALSE |  |  | 43738 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000155 |  | 20P000155 | FALSE | CNAS | SL5 BOYCE 3407 - PAINT OFFICE FOR NEW FACULTY |  | BOYCE | 3407 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | TRUE |  |  | 43739 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/30/20 |  | Paul Ditty |  |  | 2020-01-30 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000157 |  | 20P000157 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BUILDING - HOLES NEED PATCH AND PAINT |  | HEALTH SERV | 325 | COMPLETE | Brian Haynes | Cathy Eckman | CHRISTINA FARIA | WENDY ALEXIS | Paul Ditty |  | 1 |  | FALSE |  |  | 43740 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 01/31/20. |  | Paul Ditty |  |  | 2020-01-31 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000158 |  | 20P000158 | FALSE | PB&A | SL5 FS ADMIN OFFICE - TOUCH-UP PAINT AROUND BUILDING |  | FS ADMIN |  | COMPLETE | Gerry Bomotti | TBD | DA LAN DINH |  | Paul Ditty |  | - |  | FALSE |  |  | 43741 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000161 |  | 20P000161 | FALSE | BCOE | SL5 WCH 112 - MODIFY ROOM FOR NEW OCCUPANT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | TBD | MARGARET SOUDER |  | Paul Ditty |  | - |  | FALSE |  |  | 43742 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000162 |  | 20P000162 | FALSE | PROVOST/EVC | SL5 HINDERAKER 1101B - PATCH HOLE IN WALL |  | HINDERAKER | 1101B | CANCELED BY FS | Thomas Smith | Luisa Levario | AMY GU |  | Paul Ditty |  | - |  | FALSE |  |  | 43745 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000163 |  | 20P000163 | FALSE | BCOE | SL5 BOURNS A0223 - PATCH/PAINT WALLS, DEEP CLEAN/REPLACE CARPET |  | BOURNS | A0223 | COMPLETE | Christopher Lynch | TBD | SABRINA SCHUSTER | DEANNA VORHEES | Paul Ditty |  | - |  | FALSE |  |  | 43745 | [8 empty] | Paul Ditty |  |  | 2019-11-25 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000169 |  | 20P000169 | FALSE | PB&A | SL5 LOTHIAN LO-G104-OFFICE - JOB WALK FOR REMODEL OF SCOTTY'S |  | LOTHIAN HALL | SCOTTY'S | CANCELED BY CLIENT | Gerry Bomotti | TBD | FRED OFFENEY |  | John Peraino |  | - |  | FALSE |  |  | 43747 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000171 |  | 20P000171 | FALSE | CHASS | SL5 CHASS INTN 2107 - PATCH UP HOLES IN THE WALL |  | CHASS INT N | 2017 | COMPLETE | Juliet McMullin | Cindy Williams | GENEVA AMADOR |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43748 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/03/20 |  | Paul Ditty |  |  | 2020-01-03 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000172 |  | 20P000172 | FALSE | CHASS | SL5 PYSCHOLOGY 2136B & 2136C - PAINT & PATCH |  | PSYCHOLOGY1 | 2136B & 2136C | COMPLETE | Juliet McMullin | Cindy Williams | ANNIKA KIRMAN | YERAM CHEONG | Paul Ditty |  | 5 |  | FALSE |  |  | 43748 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT REMOVE DOOR | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. Request removal of interior access door and drywall to remove access to office 3011. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS | 3009 | Queue to Start | Kathryn Uhrich | TBD | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 43749 | [6 empty] | 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure. | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16
20P000175 |  | 20P000175 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 112 - PATCH & PAINT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | - |  | FALSE |  |  | 43749 | [8 empty] | Ron Veloz | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with metal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000183 |  | 20P000183 | FALSE | CHASS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | Install side walk | HUM & SOC SC | 1202 | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43756 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Also Existing door is compliant and there are other accessible exits to the building… 8/5/20, DL: This Project is on hold until further notice……. | 2019-11-13 | Enrico Baez | Construct Side walk. ADA compliance not required. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21 | 1
20P000184 |  | 20P000184 | FALSE | VC-STU AFF | SL5 HUB 261 - CONSTRUCT WALL FOR MEETING/CONFERENCE RM | In HUB 261 the administration is requesting a wall be constructed to create a meeting/conference room. We need a building zone manager to walk the area give estimate as well as reaching out to the fire marshals inspector for recommendations. | HUB | 261 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | Manny Sanchez |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43755 | [6 empty] | 02/07/2020 O-ANS: Canceled due to client request. | 2019-11-05 | Enrico Baez | 11/5/19 E.Baez conducted site visit. **********SCOPE********* 1. Construct, full height, partition wall with door in HUB 261. 2. Provide/install ADA compliant door in new partition wall. 3. Add and relocate fire sprinkler. 4. Re-position lighting in ceiling, add lighting control. 5. Patch and paint. 6. Install base board. 7. Add strobe and smoke detectors. 8. T-bar ceiling re-work. | YES | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000185 |  | 20P000185 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR (OFF WHITE) |  | PHYSICS | 3004S | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 43756 | [6 empty] | 11/01/19 O-ANS: Canceling bc duplicate of 20P000187. Paul Ditty to speak with customer re: room. |  | Paul Ditty |  |  | 2019-11-01 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000187 |  | 20P000187 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR |  | PHYSICS | 3004S | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 43761 | [8 empty] | Paul Ditty |  |  | 2019-11-05 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000188 |  | 20P000188 | FALSE | LIBR | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 |  | ORBACH LIB | 204 | CANCELED BY FS | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43761 | [6 empty] | 11/19/20 O-ANS: Declined to move forward by FS Admin but may revisit in future prioritization period. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: We are working on floor covering samples that will work for the space. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000189 |  | 20P000189 | FALSE | CNAS | SL5 SPIETH 3352 - ESTIMATE FOR PATCH AND PAINT |  | SPIETH | 3352 | COMPLETE | Kathryn Uhrich | TBD | NATALIE HOLT | SILVANA | Paul Ditty |  | 2 |  | FALSE |  |  | 43761 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/28/20 |  | Paul Ditty |  |  | 2020-01-28 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000192 |  | 20P000192 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 1st Floor | CANCELED BY FS | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43761 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000193 |  | 20P000193 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 0001A | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43761 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/02/20 |  | Paul Ditty |  |  | 2020-01-02 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000194 |  | 20P000194 | FALSE | CHASS | SL5 WATKINS 1224 - PAINT NEW FACULTY OFFICE ONLY |  | WATKINS | 1224 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43755 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/09/20 |  | Paul Ditty |  |  | 2020-01-09 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000195 |  | 20P000195 | FALSE | CHASS | SL5 ARTS 0054 - PAINT PIANO LAB |  | ARTS | 54 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | - |  | FALSE |  |  | 43762 | [8 empty] | Paul Ditty |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | COSTO HALL |  | PROJECT INTAKE | Brian Haynes | Cathy Eckman | Manny Sanchez |  | Dan Lerman |  | R1 | R2 | FALSE |  |  | 43762 | [6 empty] | 1/19/21, DL: Enrico B. Will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16 |  | 1
20P000197 |  | 20P000197 | FALSE | VC-RED | SL5 UOB 210 - SOUND PROOF INSTALLATION |  | UNIV OFC BLD | 210 | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43762 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000199 |  | 20P000199 | FALSE | SoB | SL5 ANDERSON SO RM 0002 - KEYLESS ENTRY MINOR RENOVATION REQUEST |  | ANDERSON 2 (S) | 2 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG | KENNETT LAI | Dan Lerman |  | - |  | FALSE |  |  | 43763 | [8 empty] | Enrico Baez |  |  | 2019-11-14 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000200 |  | 20P000200 | FALSE | CNAS | SL5 COLLEGE BLDG NO 306 - PATCH AND PAINT ONE WALL ONLY |  | COLL BLDG NO | 306 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 15 |  | FALSE |  |  | 43767 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/06/20. |  | Paul Ditty |  |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000202 |  | 20P000202 | FALSE | CNAS | SL5 SKYE HALL 361 RENOVATION PROJECT | Renovete space for class room. | SKYE HALL | 361 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY | MELISSA GOMEX | Dan Lerman |  | 1 |  | FALSE |  |  | 43768 | [6 empty] | 9/30/20, DL: This Project is Complete……….8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Permits were approved. Demolition is complete…..1/15/20 O-DHN: Emailed Status Report to customer……..1/14/20, DL: Plans have been submitted for a building permit. Once plans are approved, it is our goal to complete the work by the beginning of spring quarter….. |  | Ron Veloz | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000204 |  | 20P000204 | FALSE | CHASS | SL5 ARTS 166 - PATCH AND PAINT IN LOBBY AND GREEN ROOM |  | ARTS | 166 | COMPLETE | Juliet McMullin | Cindy Williams | ALBERT FETTER |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43769 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/20/19 |  | Paul Ditty |  |  | 2019-12-20 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000205 |  | 20P000205 | FALSE | PB&A | SL5 THE PLAZA 12 & 14 - EMERGENCY DECK REPAIR | Deck repair | THE PLAZA | A0012 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R2 |  | FALSE |  |  | 43770 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000206 |  | 20P000206 | FALSE | VC-STU AFF | SL5 COSTO HALL 111-HUB 353/381- RENOVATIONS - CP0003486 |  | COSTO HALL | Lower Level | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | - |  | FALSE |  |  | 43770 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000207 |  | 20P000207 | FALSE | CNAS | SL5 PHYSICS 3033 - PAINT & PATCH STAFF OFFICE |  | PHYSICS | 3033 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO | DAVID NEFF | Paul Ditty |  | 3 |  | FALSE |  |  | 43773 | [6 empty] | 03/02/20 O-ANS: Completed per Paul Ditty as of 02/04/20. |  | Paul Ditty |  |  | 2020-02-04 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000208 |  | 20P000208 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | Men's locker room refresh | ATH DANCE | 50 | IN PROGRESS | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND | EUGENE HUTCHINSON | Dan Lerman |  | 1 |  | FALSE |  |  | 43773 | [6 empty] | 1/19/21, DL: We will schedule the balance of the paint before the students return back to campus………..9/30/20, DL: The work is complete except for the paint……………..8/5/20, DL: The work is almost complete.……. |  | Dan Lerman |  |  |  | Winter 2020 | FS | FALSE | 2019 | 2021-01-16
20P000210 |  | 20P000210 | FALSE | BCOE | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | Reduce noise. Replace doors with solid core doors and install an Acoustic Door Seal Kit. | CHUNG HALL | 224 | CANCELED BY FS | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43774 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……. | 2020-02-11 | Ron Veloz | Removal of the existing double doors and door hardware, install new solid core double doors with continuous hinges, install new acoustical jamb seals, threshold seal and a surface mounted Automatic Door Bottom utilizing a flat spring mechanism, which activates when closing the door, lowering a neoprene seal insert against the floor or threshold to create a sound seal. Install acoustic double door astragals with seal. Reinstall all existing door locksets, and door closers. Quote received from Brad Aduddell-American Door to perform this work. Quote & Specs are available in the project folder. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000211 |  | 20P000211 | FALSE | CHASS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | Install keyless entry system for door to Arts Building RM 54 | ARTS | 54 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 | R3 | FALSE |  |  | 43776 | [6 empty] | 1/19/21, DL: Enrico will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment installation. 8/5/20, DL: This Project is on hold until further notice……. | 2020-01-20 | Enrico Baez | 1/19/21, EB: Per Paul R., This project is canceled………….Provide new panel, power supply and door hardware for 2 doors. Prox reader only. | YES | 2021-01-19 | Winter 2021 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21 | 1
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | BOURNS | B0328E | QUEUE TO START | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | R1 | R1 | FALSE |  |  | 43774 | [6 empty] | 1/19/21, DL: Todd has the estimate. Sent follow up email to Todd requesting update or FAU number………………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16 |  | 1
20P000213 |  | 20P000213 | FALSE | CHASS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS |  | CHASS INT S | 2117A, 2117C, 2117D, 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43777 | [6 empty] | 8/5/20, DL: This Project is Complete……………..2819/20 O-DHN: Emailed Status Report to customer…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have a contract, we will order the material and schedule the work………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Plans are complete and submitted for building permit. We are also working on the contract. Once the plans are approved and the contract is complete, we will schedule the work………. |  | Enrico Baez |  |  | 2020-08-05 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21 | 1
20P000214 |  | 20P000214 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | Remove walls and doors in spaces 2139 A,B and C. | PSYCHOLOGY1 | 2nd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43776 | [6 empty] | 9/30/20, DL: This Project is Complete…………8/5/20, DL: we will submiot plans this week.…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Plans were submitted for a permit on 2/12/20. Once plans are approved, we will order the material and schedule the work……… | 2020-01-10 | Enrico Baez | **************************************SCOPE********************************** 1.) Remove doors, and jambs 2139A, 2139B, 2139C. 2.) Remove drop ceiling in 2139A, 2139B, 2139C and repair as needed. 3.) Remove cabinets in 2139A, 2139B, 2139C. 4.) Remove walls between 2139A & B, and remove walls between 2139B & C. 5.) Change light fixture to match existing. 6.) Repair walls as needed. 7.) Patch and paint as needed. 8.) Replace carpet and base in 2139A, 2139B, 2139C and 2139 common area. 9.) HVAC duct work in individual spaces can be removed and simplified. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000215 |  | 20P000215 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | Remove Vaughan wall seperating Olmsted 3349/3351.Add 4 single gang outlets and 2, 2gang outlets. | PSYCHOLOGY1 | 3rd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43776 | [6 empty] | 1/19/21, DL: This project is 100% complete…………9/30/20, DL: Plans were approved, we had the Vaughn Wall tested for Asbestos containing material. Once we have the results, we will schedule the work………….8/5/20, DL: We will submit plans by this Friday for a building permit | 2020-02-24 | Enrico Baez | 2/24/2020 E. Baez - 1.Remove Vaughan wall and electrical circuit in wall. 2. Add 4 Single Gan outlets and 2, 2gang outlets. 3. Patch vinyl plank flooring from removed wall and safe. 4. Remove panel in 2249 with wall paper on it next to window. 5. Remove handle set to 3351, install blank, render door inoperable. 6. Repair T-Bar ceiling as needed. 7. Patch and paint walls. 8. Coordinate with ITS for data line for 8 computers. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000218 |  | 20P000218 | FALSE | VC-RED | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | VIVARIUM UPDATE AIR COMPRESSOR | SPIETH | 347 | PROJECT INTAKE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | DAN LERMAN |  | 2 | R2 | FALSE |  |  | 43602 | [6 empty] | 1/19/21, DL: This project has been scoped. We will start the work when we are complete with all priority #1 projects…….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16
20P000220 |  | 20P000220 | FALSE | CNAS | SL5 SPIETH-NEW CLOSING/SECURITY MECHANISM FOR LOADING DOCK DOORS |  | SPIETH |  | CANCELED BY CLIENT | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | - |  | FALSE |  |  | 43783 | [8 empty] | Ron Veloz |  |  | 2019-11-22 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000221 |  | 20P000221 | FALSE | BCOE | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | COMPLETE | Christopher Lynch | TBD | HONG XU | KEVIN FREEDMAN | Dan Lerman |  | 3 |  | FALSE |  |  | 43784 | [6 empty] | 1/19/21, DL: This project is 100% Complete……..9/30/20, DL: We are in the process of finishing up a few other projects. Once they are complete, we will schedule the work….8/5/20, DL: Plans are approved and we will start the work in the next 2-6 weeks…….. | 2020-02-25 | Ron Veloz | Install Plywood and supports. Paint Plywood black. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000223 |  | 20P000223 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER PAN REPLACEMENTS | Shower Pan replacement | PENTLAND A | A238, B245, B325, C215, F325 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R3 |  | FALSE |  |  | 43784 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Sep 2019. |  | John Peraino |  |  | 2019-09-01 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000225 |  | 20P000225 | FALSE | VC-UNIV ADV | SL5 HINDERAKER 0137 - BASEMENT RESTROOM SINK INSTALL | Install Kitchen Sink in entry room of Restroom 0137 | HINDERAKER | B137 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL | KIM MCDADE | Dan Lerman |  | 1 |  | FALSE |  |  | 43784 | [6 empty] | 1/22/20 O-ANS: Canceled per customer request. | 2020-01-22 | Enrico Baez |  | YES | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000226 |  | 20P000226 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 3401 - OFFICE PATCH AND PAINT |  | HUM & SOC SC | 3401 | COMPLETE | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON | TRACY AVERY | Paul Ditty |  | 8 |  | TRUE |  |  | 43787 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/03/20. |  | Paul Ditty |  |  | 2020-02-03 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000230 |  | 20P000230 | FALSE | VC-RED | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | Install Ceilings, Widen Door & Extend Utilities | BOURNS | B116C & B116D | COMPLETE | Rodolfo Torres | Laura Manor | KRASSIMIR BOZHILOV | LAURA MANOR | Dan Lerman |  | 1 |  | FALSE |  |  | 43787 | [6 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: This project is in progress and 50% complete. We should be complete with in the next 4-6 weeks…………...8/5/20, DL: We will submit plans in the next week………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We will start working on the plans and apply for a building permit in the next 2-3 weeks. | 2020-01-23 | Ron Veloz | Install new T-bar ceilings, lighting/switches, verify electrical service/disconnect. Relocate the existing eye washer, widen the exiting door opening and *reverse swing(*if approved by F.M). Install one customer furnished transformer. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Cinvert Basement Library into Piano Lab | ARTS | 54 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 43788 | [6 empty] | 1/19/21, DL: We will Start the plans, permit and the work once all priority #3 projects…………...11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks……….. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16
20P000232 |  | 20P000232 | FALSE | CHASS | SL5 PSYCHOLOGY 3111B - WALL PATCH FOR SMALL HOLES IN THE WALL |  | PSYCHOLOGY1 | 3111B | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43789 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000233 |  | 20P000233 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - A169 & A170 ENTRY AREA DAMAGED |  | BOURNS | A169 & A170 | CANCELED BY FS | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43791 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000235 |  | 20P000235 | FALSE | CNAS | SL5 SKYE 374 - PATCH AND PAINT |  | SKYE HALL | 374 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 4 |  | TRUE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000236 |  | 20P000236 | FALSE | CNAS | SL5 SKYE 368 - PATCH AND PAINT |  | SKYE HALL | 368 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 5 |  | TRUE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000237 |  | 20P000237 | FALSE | CHASS | SL5 HMNSS 1202A - PATCH AND PAINT SERVICE |  | HUM & SOC SC | 1202A | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTIAN BACK |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43791 | [8 empty] | PAUL DITTY | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/14/20. |  | 2020-02-14 | Spring 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000238 |  | 20P000238 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 14 |  | TRUE |  |  | 43794 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000239 |  | 20P000239 | FALSE | CNAS | SL5 SKYE 382 - PATCH AND PAINT |  | SKYE HALL | 382 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 11 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000240 |  | 20P000240 | FALSE | CNAS | SL5 SKYE 384 - PATCH AND PAINT |  | SKYE HALL | 384 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 12 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000241 |  | 20P000241 | FALSE | CNAS | SL5 SKYE 386 - PATCH AND PAINT |  | SKYE HALL | 386 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 13 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000242 |  | 20P000242 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 10 |  | TRUE |  |  | 43794 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000243 |  | 20P000243 | FALSE | PB&A | SL5 ALUMNI CENTER - HYDRATION STATION INSTALL | Install hydration station | ALUM VISITOR | FIRST FLOOR | COMPLETE | Gerry Bomotti | TBD | LESLIE ANN GERRETSE |  | John Peraino |  | R4 |  | FALSE |  |  | 43785 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by June 2020. |  | John Peraino |  |  | 2020-06-01 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20 | 1
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | Queue to Start | Kathryn Uhrich | TBD | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 43794 | [6 empty] | 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16
20P000245 |  | 20P000245 | FALSE | BCOE | SL5 WCH RM 0325 - PATCH AND PAINT DAMAGE FROM WHITE BOARD |  | CHUNG HALL | 325 | COMPLETE | Christopher Lynch | TBD | SARA GALLOWAY |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43794 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/13/20 |  | PAUL DITTY |  |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000247 |  | 20P000247 | FALSE | CNAS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | Refresh Lab: Patch paint, strip & clean floor, repair broken ceiling and floor (VCT) tiles at room 2110 & 2118. Install Electrical power & Co2 cylinder racks at each end of workbench/tables | SPIETH | 2110 + 2118 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS | SHERICE UNDERWOOD | Dan Lerman |  | 6 |  | TRUE |  |  | 43796 | [6 empty] | 1/19/21, DL: This project is complete…………..9/30/20, DL: This project is in progress and will be compete in the next 6- 8 weeks……………8/5/20, DL: We will start on this project in the next 6-8 weeks….. | 2020-04-17 | Ron Veloz | Spieth 2110: Carpentry: Seismic anchoring for “New” tables and equipment. Replace damaged ceiling tiles. Install misc. wall mounted items. Sheet Metal: Remove “existing” steel cage. Fabricate & install metal cylinder rack w/ restrains/seismic anchoring to floor. Plumbing: Install Co2 POC for gas cylinders at four (4ea) new free-standing work benches (see configuration on this document). Electrical: Install dedicated *120v power drop & connect to the existing power strips built-in the four (4ea) new workstation tables (see configuration on this document). *VERIFY/CONFIRM VOLTAGE W/ D. MCW. Relamp fixtures as needed. Spieth 2118 & 2110: Sheetmetal: Clean and or replace air distribution grilles. Flooring: Repair/patch broken floor tile and Replace broken ceiling tiles (abate floor tiles if required). Painting: Paint and patch all walls, verify recondition doors @ room side. Plumbing: Assess sinks to be fully operational & clean. *Replace sink in Rm 2118 for glassware, confirm with Faculty/Estella. Replace sink in room 2118 (Sink type TBD by Faculty). HVAC: Check lab air pressure is operational & proper pressure. Custodial: Strip and Wax floor, clean interior windows, wipe down doors and windowsills. EXCLUSIONS: Furnish, assemble, and install new workstations, tables or lab equipment. Removal of existing lab furniture or equipment. Natural gas or air output taps not required (per Faculty). | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 20-21
20P000248 |  | 20P000248 | FALSE | CNAS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT |  | WEBBER | 1223 + 1223-A | PROJECT INTAKE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS | SHARYL MURDOCK | Dan Lerman |  | 5 | 4 | FALSE |  |  | 43796 | [6 empty] | 1/19/21, DL: This project is a priority #5. We will start this project when all priority #4 projects are complete…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….02/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Survey space for hazardous material. Once survey is complete, we will schedule abatement and the work. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16
20P000253 |  | 20P000253 | FALSE | BCOE | SL5 BOURNS HALL LAB B256 - EXHAUST SYSTEM | EXHAUST SYSTEM | BOURNS | B0156 | PLAN DEVELOPMENT/CHECK | Christopher Lynch | TBD | LOUIS SANDOVAL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 43810 | [6 empty] | 1/19/21, DL: We will start working on the plans for this project in the next two weeks. We will start this project once the permit is approved…… |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16
20P000266 |  | 20P000266 | FALSE | CNAS | SL5 GEOLOGY 2460B - PATCH & PAINT |  | GEOLOGY | 2460B | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 3 |  | FALSE |  |  | 43818 | [8 empty] | PAUL DITTY | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000267 |  | 20P000267 | FALSE | CNAS | SL5 GEOLOGY 2460C - PATCH & PAINT |  | GEOLOGY | 2460C | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 4 |  | FALSE |  |  | 43818 | [8 empty] | PAUL DITTY | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/04/20. |  | 2020-03-04 | Spring 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000268 |  | 20P000268 | FALSE | CNAS | SL5 GEOLOGY 2460D - PATCH & PAINT |  | GEOLOGY | 2460D | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 5 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | PAUL DITTY |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000269 |  | 20P000269 | FALSE | CNAS | SL5 GEOLOGY 2460E - PATCH & PAINT |  | GEOLOGY | 2460E | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 6 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/05/20. |  | PAUL DITTY |  |  | 2020-03-05 | Spring 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000270 |  | 20P000270 | FALSE | CNAS | SL5 GEOLOGY 2460F - PATCH & PAINT |  | GEOLOGY | 2460F | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 7 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | PAUL DITTY |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000271 |  | 20P000271 | FALSE | CNAS | SL5 GEOLOGY 2460G - PATCH & PAINT |  | GEOLOGY | 2460G | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 8 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/06/20. |  | PAUL DITTY |  |  | 2020-03-06 | Spring 2020 | FS | FALSE | 2019 | 2021-01-16 | FY 19-20
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS | 245 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | ANDREA HIDALGO |  | DAN LERMAN |  | 3 |  | FALSE |  |  | 43832 | [6 empty] | 1/19/21, DL: This is a priority 3 project. We will start the plans and permit for this project when all priortiy #2 projects are complete…….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 43803 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2019 | 2021-01-16
20P000309 |  | 20P000309 | FALSE | VC-UNIV ADV | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES |  | 1955 CHICAGO | 200 | CANCELED BY FS | Peter Hayashida | Naysia Caldwell | SARAH KARSON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43840 | [6 empty] | 12/16/20 O-ANS: Canceled by FS - Project location not serviced as FS CORE location and reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Please retain project # as reference. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  | 2020-12-16 | Spring 2020 | FS | FALSE | 2020 | 2021-01-16 | FY 20-21
20P000310 |  | 20P000310 | FALSE | BCOE | SL5 BOURNS A-WING A129 - PATCH & PAINT | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. | BOURNS | A0129 | Queue to Start | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43840 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB | ARTS | 150 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 43844 | [6 empty] | 1/19/21, DL: This project will require engineered plans. This is a priority 2 project. We will start the plans and permit process when all priority #1 projects are comple………… |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000320 |  | 20P000320 | FALSE | CNAS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | ACTIVATE VACUUM LINES | SPIETH | 1303 | PROJECT INTAKE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | DAN LERMAN |  | 4 |  | FALSE |  |  | 43789 | [6 empty] | 1/19/21, DL: This is a priority 4 project. We will start this project when all all priority 3 projects are complete……….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | PIERCE | 2232A | PROJECT INTAKE | Kathryn Uhrich | TBD | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 43852 | [6 empty] | 1/19/21, DL: This is a priority #9 project. We will start this project when all priority #8 projects are complete…………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000335 |  | 20P000335 | FALSE | CNAS | SL5 ENTOMOLOGY BLDG 239-246 - PAINT AND PATCH OFFICE AND LAB |  | ENTOMOLOGY | 239 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43852 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY | 05/22/20 O-ANS: Project canceled per customer request (Bill Sutton). |  | 2020-05-22 | Spring 2020 | FS | FALSE | 2020 | 2021-01-16 | FY 19-20
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SERV | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | TBD | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 43852 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-01-16
20P000337 |  | 20P000337 | FALSE | VC-STU AFF | SL5 HEATLH SERVICE 382 - NEED OFFICE PAINTED |  | HEALTH SERV | 382 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43853 | [6 empty] | 08/06/20 O-ANS: Complete per D-BFA on 02/11/20. |  | PAUL DITTY |  |  | 2020-02-11 | Spring 2020 | FS | FALSE | 2020 | 2021-01-16 | FY 19-20
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES |  | UNIV OFC BLD | 200 | HOLD - FACILITIES SERVICES | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43868 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-01-16
20P000355 |  | 20P000355 | FALSE | CNAS | SL5 GEOL 454A- PATCH & PAINT |  | GEOLOGY | 0454A | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | LAURIE GRAHAM | PAUL DITTY |  | 2 |  | FALSE |  |  | 43870 | [8 empty] | PAUL DITTY | 08/06/20 O-ANS: Closed per Paul Ditty as of 03/13/20. |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2020 | 2021-01-16 | FY 19-20
20P000363 |  | 20P000363 | FALSE | BCOE | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | Paint Only | CHUNG HALL | 433 | Queue to Start | Christopher Lynch | TBD | MANGLAI ZHOU | FARIBORZ KARGAR | PAUL DITTY |  | X |  | TRUE |  |  | 43874 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000366 |  | 20P000366 | FALSE | CNAS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | MINOR LAB RENOVATION | SPIETH | 2375 / 2375-A | PROJECT INTAKE | Kathryn Uhrich | TBD | SHERICE UNDERWOOD |  | DAN LERMAN |  | 7 |  | TRUE |  |  | 43880 | [6 empty] | 1/19/21, DL: This is a priority 7 project, we will start this project when all priority 6 projects are complete………….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LAB1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 43880 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-01-16
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT |  | SCIENCE LAB1 | 317 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 10 |  | FALSE |  |  | 43879 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-01-16
20P000370 |  | 20P000370 | FALSE | CHASS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | SPACE RENOVATION PROJECT | WATKINS | 1311 | PLAN DEVELOPMENT/CHECK | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 43880 | [6 empty] | 1/19/21, DL: We will start working on the plans for this project in the next two weeks. We should have plans to submit for plan check review in the next 5- weeks……….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000403 |  | 20P000403 | FALSE | CHASS | SL5 OLMSTED 232 - PAINT OFFICE | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). | OLMSTED | 2321 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | MELISA VICARIO | Paul Ditty |  | TBD |  | TRUE |  |  | 43903 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000419 |  | 20P000419 | FALSE | CNAS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | Paint Only | SPIETH | 2312 | Queue to Start | Kathryn Uhrich | TBD | ESTELLA DAVALOS | SHERICE UNDERWOOD | PAUL DITTY |  | X |  | TRUE |  |  | 43943 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000445 |  | 20P000445 | FALSE | CNAS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY | 279 | PROJECT INTAKE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | DAN LERMAN |  | 2 |  | TRUE |  |  | 43985 | [6 empty] | 1/19/21, DL: This is a priority 2 project. We will start the project when all priority 1 projects are complete…………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000446 |  | 20P000446 | FALSE | CHASS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. | CHASS INT N | 4047 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 43986 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000449 |  | 20P000449 | FALSE | BCOE | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | Paint Only - Chung Hall, Fourth Floor, Room 461 Patch & Paint: At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. Follow up with fresh paint. Thank you. | CHUNG HALL | 461 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43993 | [6 empty] | 01/19/21 O-ANS: Complete per technician updates and closed project. Completed by Wendy M. 11/09 -SC |  | Paul Ditty |  |  | 2020-11-09 | Winter 2021 | FS | FALSE | 2020 | 2021-01-16 | FY 20-21
20P000453 |  | 20P000453 | FALSE | CHASS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | Paint Only - Please patch/paint to existing color office for faculty new hire. | ARTS | 142 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000463 |  | 20P000463 | FALSE | CHASS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 | HUM & SOC SC | 2000 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000464 |  | 20P000464 | FALSE | CHASS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) | HUM & SOC SC | 3001 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000467 |  | 20P000467 | FALSE | SOM | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. | WEBBER | 1247 | Queue to Start | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | CYNTHIA CAROLINA | PAUL DITTY |  | X |  | TRUE |  |  | 44001 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000468 |  | 20P000468 | FALSE | VC-RED | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | Paint Only | SPIETH | 364 | Queue to Start | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 44005 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000469 |  | 20P000469 | FALSE | CHASS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. | ARTS | 222 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | SUSAN KOMURA | PAUL DITTY |  | X |  | TRUE |  |  | 44005 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUM & SOC SC | 3210 | Queue to Start | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44006 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
21P000001 |  | 21P000001 | FALSE | CNAS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | NEW GROWTH CHAMBER PLACEMENT | FAWCETT LAB |  | PROJECT INTAKE | Kathryn Uhrich | TBD | LINDA WALLING |  | DAN LERMAN |  | 3 |  | TRUE |  |  | 43990 | [6 empty] | 1/19/21, DL: This is a priorty 3 project. We will start this project when all priority 2 projects are complete……. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
21P000003 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | PROJECT INTAKE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Dan Lerman |  | R1 |  | FALSE |  |  | 44008 | [6 empty] | 1/19/21, DL: Enrico is managing this project………….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16 |  | 1
21P000009 |  | 21P000009 | FALSE | CNAS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | GLOVEBOX SYSTEM | CHEMICAL SCI |  | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | TBD | NATASHA GONZALES |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 44020 | [6 empty] | 1/19/21, DL: we will submit plans this week……………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
21P000019 |  | 21P000019 | FALSE | BCOE | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | Bourns Office A305 - Install Plank Floor Please remove old damaged carpet and install new plank floor. Match with that of the ME suite (same floor). Thank you. Note: Current PI has not moved out. We will contact Facilities once date is known and all items have been removed from the room. Questions: ME Department Manager (Interim) - William Bingham - bill@ece.ucr.edu , or Robert Lopez lopezra@engr.ucr.edu | BOURNS | A305 | PROJECT INTAKE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | 3 | 2 | TRUE |  |  | 44032 | [6 empty] | 1/19/21, DL: This a priority 3 project. We will start this project when all priority #2 projects are complete………..1/14/21 O-ANS: Updated prioritization to #3 (from #2) per org leadership request. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
21P000037 |  | 21P000037 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | Paint Only | CHUNG HALL | 427 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44043 | [6 empty] | 01/19/21 O-ANS: Paint complete per technician and closed project. 11/30/20 B-SBT: repatch & Paint north wall |  | Paul Ditty |  |  | 2020-11-30 | Winter 2021 | FS | FALSE | 2020 | 2021-01-16 | FY 20-21
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MAT SCI ENGR | 71 | PROJECT INTAKE | Christopher Lynch | TBD | XI CHEN |  | DAN LERMAN |  | 2 | 3 | FALSE |  |  | 44049 | [6 empty] | 1/19/21, DL: This is a priority #2 project. WE will start the plans and permit process for this project when all priority 1 projects are complete…………1/14/21 O-ANS: Updated prioritization to #2 (from #3) per org leadership request. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
21P000078 |  | 21P000078 | FALSE | VC-RED | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MRB |  | IN PROGRESS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 44097 | [6 empty] | 1/19/21, DL: the First floor work will be complete today, we will start the 2nd floor this week……………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
21P000079 |  | 21P000079 | FALSE | VC-RED | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. | PSYCHOLOGY1 |  | Queue to Start | Rodolfo Torres | Laura Manor | LESLIE KARPINSKI |  | PAUL DITTY |  | X |  | FALSE |  |  | 44099 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS |  | PROJECT INTAKE | Kathryn Uhrich | TBD | JOSE WUDKA |  | DAN LERMAN |  | R1 |  | FALSE |  |  | 43818 | [6 empty] | 1/19/21 DL: Enrico is managing this project. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-01-16 |  | 1
21P000102 |  | 21P000102 | FALSE | VC-RED | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | AAALAC Certification updates to rooms 348, 352 & 363 | SPIETH | 348, 352 & 363 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS | YURIDIA REYNOSO | Paul Ditty |  | TBD |  | FALSE |  |  | 44133 | [6 empty] | 12/08/20 O-ANS: Customer Dierk Biggs confirmed via email that these room updates are complete. |  | Paul Ditty |  |  | 2020-12-08 | Winter 2021 | FS | FALSE | 2020 | 2021-01-16 | FY 20-21
21P000109 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Dr. Robert Clark. He started working July 1, 2020. | WATKINS | 1146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | TBD |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
21P000110 |  | 21P000110 | FALSE | CHASS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. | WATKINS | 2146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | TBD |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
21P000111 |  | 21P000111 | FALSE | CHASS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. | WATKINS | 2144 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | TBD |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-01-16
2970c | 2970c |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 42340 | Complete Construction | 44197 | 44256 | [10 empty] | PD&C | FALSE | 2015 | 2021-01-16
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 42340 | Complete Design | [12 empty] | PD&C | FALSE | 2015 | 2021-01-16
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 432510 |  | 42425 | Bidding | 44256 | 44287 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-16
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Design (Phase 2) | Kathryn Uhrich | TBD | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 9 |  |  | FALSE |  |  | 42710 | RPU plan review/design (Phase 2) | 44348 | 44409 | [10 empty] | PD&C | FALSE | 2016 | 2021-01-16
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 43532 | Complete Report-Arc Flash | [12 empty] | PD&C | FALSE | 2019 | 2021-01-16
3515c | 3515c |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Construction | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 43532 | Complete Construction | 44166 | 44348 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 43920 | Projects to be assigned | [12 empty] | PD&C | FALSE | 2020 | 2021-01-16
3590b | 3590b |  | FALSE | PB&A | Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Bidding | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 43796 | Award Contract | 44256 | 44348 | [10 empty] | PD&C | FALSE | 2019 | 2021-01-16
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | COMPLETE | Kim Wilcox | TBD | ALEXIS RAMBAUD |  | Dan Lerman |  | 1 | 0 | FALSE |  |  | 2018-12-11 | schedule the work | 2019-01-21 | 2019-03-27 |  |  |  | 8/5/20, DL: This project is complete…………3/25/20,DL: Doors are scheduled to arrive the second week in April……2/19/20 O-DHN: Emailed Status Report to customer……2/18/20, DL: Work is complete except for Door and final deep cleaned I do have final stain samples from the vendor. I need to verify color……… We will complete the project when the doors arrive……….1/14/20, DL: Plans are approved, PO# is cut for the ordering of the custom doors, we are currently scheduled to start the work on or shortly after 1/21/20,. Karim understands that we will start and finish the project but we will not be able to install the door until the door arrives on site. There is a minimum of 6-8 week lead time on the door delivery………….12/16/19, DL: Plans are still in plan check review. I sent the building department an email asking for a startus update today…….10/16/19, DL; Plans were submitted to our building official this week for plan check review and a permit……9/16/19, DL; Guther will work on plans in the next three weeks. Once plans are complete, we will proceed with the permit process… | 2018-12-20 | Ron Veloz | SOW: Wall: Construct a metal stud framed wall with drywall up to hard ceiling (ceiling has 12x12 glue up ceiling tiles). Hardware: Install new lockset & keys are required.***** French Door: Install new stain grade birch door with full lite. Door and finish to match the existing office doors.***** Hard Ceiling: * Ceiling is 8’-0” A.F.F. + - with 12x12 glue up ceiling tiles. Work may require a new access panel if access to space above is needed. The 12x12 glue up ceiling tiles may need to be removed where the new wall is constructed.***** Flooring: The existing flooring will remain. Install rubber base to match existing.***** Painting, Taping & Sanding: Taping sanding and painting is required at the new wall and connecting walls.***** HVAC: May require modifications to split the existing supply air to accommodate the open office space.***** Electrical: Provide light switch at new office, power(new or relocate); add and or relocate electrical and voice/data outlets required for a standard office.***** Lighting: Provide a new light switch/circuit near office entrance. The existing 2x4 fixture is on main lighting circuit and will require lighting circuit modifications. Verify if the existing lighting is sufficient for the proposed office. Field verify if additional lighting is required.***** Fire Alarm: Provide a new Smoke/chime detector at new office area, confirm requirements. | YES | 2020-08-05 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 20-21
19P000673 |  | 19P000673 | FALSE | SOB | SL5 ANDERSON HAL NO, RM 158- RECARPET 12 ROOMS / ELECTRICAL WORK |  | ANDERSON 1 (N) | 158 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-06-18 | Construction | 2019-09-12 | 2019-09-23 |  |  |  | 9/16/19, DL; This project started last Thursday and will be completed early next week…… |  | Enrico Baez |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18P000328 |  | 18P000328 | FALSE | ATHLETICS | SL5 HINDERAKER BASEMENT OFFICE REPAIR |  | HINDERAKER |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-01 | [6 empty] | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with Paul. Paul will complete as in the near future. Carpet will be installed shortly after......5/21/18, Painters started paint. Should be complete with paint by the end of the week....DL, 5/24/18; Painters are complete. Jess will schedule the carpet install.....DL, 6/12/18; Project is 98% Complete. Carpenters need to under cut two doors to accomodate the carpet.....DL, 7/11/18; This Project 100% Complete..... |  | Dan Lerman |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000484 |  | 18P000484 | FALSE | ATHLETICS | SL5 INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | Project will be managed by A&E for completion. | SOFTBALL STG |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-26 | [6 empty] | 2/1/19, DL; This is a PD&C Project due to IRT walk. Project will exceed $50,000……….. |  | Enrico Baez |  | NO | 2019-02-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000346 |  | 18P000346 | FALSE | ATHLETICS | SL5 ATHLETICS INSTALL WALL VOLLEYBALL OFFICES |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-18 | [6 empty] | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. DL, 5/24/18; We will start working on plans in the near future.... DL, 6/16/18; Need to submit plans asap.......DL, 7/11/18; The plans were approved today. This project is scheduled to start on 7/14/18. We will will be complete will all items related to this project on 8/27/18. Note, The door and sidelite are special order items and this item will probalby have a 6-8 week lead time. Steve T is going to order the door soon.. Customer is aware of the delay for the door and is not concerned......DL, 7/25/18; Passed framing and Electrical inspection. We will be finished with the project next week except for the door and window that is ordered but has a 6-8 week lead time. DL, 8/10/18; This Project is Complete except for special order door and window.......DL, 8/22/18; Door and Glass still not on site., Will check in with Steve T on delivery date......Will also schedule final inspection for Certificate of occupancy......9/6/18; The Glass window is installed but we are waiting on the door. this projects is 98% complete.......DL, 9/19/18; The door will be shipped on 9/24/18. We will schedule the door install when the door is on site......DL, 11/7/18; This Project is 100% Complete.... |  | Dan Lerman |  | YES | 2018-11-08 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000027 |  | 19P000027 | FALSE | ATHLETICS | SL5 ATHLETICS PATCH & PAINT ROOM | 9/19/18 | ATH DANCE | 0120C | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | DL, 9/19/18; This Project is 100% Complete……. |  | Paul Ditty |  | N/A | 2018-09-19 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000265 |  | 19P000265 | FALSE | ATHLETICS | SL5 ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000646 |  | 19P000646 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING |  | ATH DANCE | 20R, 20S | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-23 | tile wash and shower doors | 2019-08-01 | 2019-09-27 |  |  |  | 9/16/19, DL; This project is Complete…….9/3/19, DL; Project is 80% Complete. Floor covering is scheduled for this Friday. Target complete date is 9/13/19……8/15/19, DL; This project is in progress and slated for complete by the end of september…..8/1/19, DL; Project is in progress with a complete date of 3-4 weeks. |  | Dan Lerman | 06/19/19 O-ANS: Project 19P000647 was combined with this project. |  | 2019-09-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000208 |  | 20P000208 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | Men's locker room refresh | ATH DANCE | 50 | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND | EUGENE HUTCHINSON | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-11-04 | [6 empty] | 1/28/21, DL: Project is complete. Paul will schedule the paint once he is back on projects……….1/19/21, DL: We will schedule the balance of the paint before the students return back to campus………..9/30/20, DL: The work is complete except for the paint……………..8/5/20, DL: The work is almost complete.……. |  | Dan Lerman |  |  | 2021-01-28 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | 10 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 1/24/2020 E. Baez- Cancelled per Joe Erbland. 4/18/19, DL; Per Enrico, we are waiting for a proposal from HCI and approved funding from Athletics. We should have the proposal in 2- weeks…. | 2018-09-27 | Enrico Baez |  | YES | 2020-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
19P000271 |  | 19P000271 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 |  | ATH DANCE | 3 | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000295 |  | 19P000295 | FALSE | ATHLETICS | SL5 PATCH & PAINT |  | ATH DANCE | 50B | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 12 | 18 - 19 | FALSE |  |  | 2018-09-12 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000272 |  | 19P000272 | FALSE | ATHLETICS | SL5 NEED URINAL DIVIDERS | FS to coordinate with customer to scope the work. | ATH DANCE | 50E | CANCELED BY FS | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 13 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez |  |  | 2019-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000270 |  | 19P000270 | FALSE | ATHLETICS | SL5 ATH DANCE-WEIGHT ROOM DROP DOWN CEILING |  | ATH DANCE | 78 | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 14 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project is 100% Complete….. |  | Enrico Baez |  |  | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000274 |  | 19P000274 | FALSE | ATHLETICS | SL5 RIV SPORTS CPX - REPLACE URINALS | FS to coordinate with customer to scope the work. | W LCKRM/CONC |  | CANCELED BY FS | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 15 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-10-15 | Enrico Baez |  | YES | 2019-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000276 |  | 19P000276 | FALSE | ATHLETICS | SL5 TRACK BLEACH-PUBLIC RESTROOMS UPGRADE |  | TRACK BLEACH |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 16 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez |  | YES | 2018-11-20 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000266 |  | 19P000266 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty |  | N/A | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000647 |  | 19P000647 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- LOCKER ROOM REFRESH |  | ATH DANCE | Men's & Women's Locker Rooms | CANCELED BY FS | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-23 | [6 empty] | 6/19/19 O-ANS: Combined with project 19P000646 since work in the same area. Dan Lerman to perform scope. |  | Dan Lerman |  |  | 2019-06-19 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
19P000252 |  | 19P000252 | FALSE | ATHLETICS | SL5 ATH DANCE SHOWER DOORS |  | ATH DANCE | 0050K | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-10 | schedule the work | 2019-04-01 | 2019-04-26 |  |  |  | 5/31/19, DL; This project is 100% Complete……..5/15/19, DL; This work will be 100% complete this Friday…….4/15/19, DL; This project should stat is 2-weeks. We have a signed po# for the shower doors. Walked the needed tile repairs with the contractor today……..3/18/19, DL; Woring on quotes for the repairs. We will scheudle the work to be completed in the next 45- days…… |  | Enrico Baez |  | YES | 2019-05-31 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000268 |  | 19P000268 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT 20C |  | ATH DANCE | 20C | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000269 |  | 19P000269 | FALSE | ATHLETICS | SL5 ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | Project is not within the purview for completion; condition is fair and usable. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 5 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18…..This is a cooman area. Is this recharge work……. | 2018-09-27 | Enrico Baez |  | YES | 2018-10-04 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000275 |  | 19P000275 | FALSE | ATHLETICS | SL5 SOFTBALL STG PRESS BOX AC ADDITION | FS to coordinate with customer to scope the work. | PRESS BOX |  | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  |  |  | 6 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project was canceled by Johnathan J. as there is not funding at this time…………DL, 10/4/18; I checked on this recently and this is not a building, it is stoarge and should be recharge work…. | 2018-09-27 | Enrico Baez |  |  | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/5/20, DL: This Project is 100% Complete………….3/28/19, Doors are in the process of being …. DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez |  | YES | 2020-02-05 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
19P000273 |  | 19P000273 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000093 |  | 20P000093 | FALSE | ATHLETICS | SL5 ATHLETICS 0078 - TELEVISION MOUNT/ ELECTRICAL |  | ATH DANCE | 0078 | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-08-20 | [6 empty] | 11/26/19 O-ANS: Project canceled per communication with Enrico. | 2019-10-04 | Enrico Baez | Install TV bracket on wall near weight room. Provide recessed/flush single gang outlet near bracket. | YES | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
19P000311 |  | 19P000311 | FALSE | ATHLETICS | SL5 ATHLETICS 150-KEYLESS ENTRY | Keyless entry system | ATH DANCE | 0150 | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2018-10-02 | [6 empty] | 02/07/2020 O-ANS: Canceled by customer Joe Erbland due to lack of funding per email to EBZ. | 2018-09-27 | Enrico Baez | Install keyless entry system, part of larger project throughout the athletics building | YES | 2020-02-07 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20 | 1
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Eugene Hutchinson | Johnathan Jensen |  | Fernando Nunez | 1 |  |  | FALSE | 0 |  | 2018-08-23 | Department approval to move fwd | [12 empty] | PD&C | FALSE | 2018 | 2021-02-01
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | SOCCER FIELD AND AREA |  | On Hold | Tamica Smith Jones | Eugene Hutchinson | Joe Erbland |  | Gerald Caraig | 2 |  |  | FALSE | 0 |  | 2014-04-10 | Need direction by PM Director | [12 empty] | PD&C | FALSE | 2014 | 2021-02-01
2989 | 2989 |  | FALSE | ATHLETICS | Dance - Locker Room Remodel | We are requesting to utilize Base Architecture, Planning, & Engineering, Inc. to provide pro bono work on planning for locker room renovations in the Athletics & Dance Building. Rob Gayle is aware of our desire to utilize this company for services. |  |  | On Hold (COVID-19) | Tamica Smith Jones | Eugene Hutchinson | Joseph Erbland |  | Tameesha Hayes | 99 |  |  | FALSE | 28395 |  | 2015-11-19 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2015 | 2021-02-01
18P000394 |  | 18P000394 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK |  | BOURNS | A0159A | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 2 | TRUE |  |  | 2018-04-12 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………….1/15/19, DL; Sound Soak is ordered and should arrive within two weeks……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; Need to review and scheudle…….DL, 7/11/18; Still need to review and scheudle…..DL, 8/22/18; This Project is complete but Maggie wants to see if the Faculty are happy with the results. We may install Sound Soak as a final option…… DL 9/6/18; Sent Maggie an email to see if she is satified with the work performed in regards to the sound proofing. I will have an update by the next Excel update….. DL, 9/19/18; The PI is out of town. Maggie will confirm the PI is satisiofd with the work when they return……on 9/18/18…DL, 10/8/18; Customer not satisfied with first round of sound proofing. We will proceed with Sound Soak material….. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000391 |  | 18P000391 | FALSE | BCOE | SL5 PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN |  | CHUNG HALL | 446 449 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 5/5/18; Conducted scope visit with Paul and Maggie. This project is target date is August 30th. As of now, we have 10 business days to complete the work……. Dean's Office….DL, 6/16/18;Walked project with Jess and Paul. This will be a project will now incluclude flooring is 7- additional offices due to additional trip hazzards identified in 3 of 7 offices during the carpet scope. Maggie will pay four four of the office since they are still in good condition. We are still on schedule with the work.......Dan, 7/11/18; This project is still on schedule. Complete Date is 8/18/18 and scheduled to be complete on 8/31/18.....DL, 8/10/18; The project is on schedule and we will start on Monday.......Ahead of schedule, project will be complete on 8/29/18......DL, 9/6/18; This project is 100% complete. Note, Maggie did request Jess to come back and remove some glue and he has this scheduled..... |  | Dan Lerman |  | YES | 2018-09-10 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000315 |  | 18P000315 | FALSE | BCOE | SL5 BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB |  | BOURNS | B0235 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  |  | HOLD | TRUE |  |  | 2018-02-16 | [6 empty] | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction to scope, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... Need to walk project with Ron and schedule the work....DL, 5/24/18; Conducted site visit with Ron V. Ron will order material and schedule the work once material is on site.....DL, 6/16/18; Need to verify delivery date for material.......DL. 7/11/18; Plumbing is disconnected. Corey is tentatively scheduled to disconnect the Fume hood. Once the Fume hood is disconnected, we will schedule the removeal of the fume hood and start the framing of the wall. Target complete date is 8/8/18....DL, 7/25/18; Fume hood is disconnected. Need to move Fume hood and start framing target date is delayed to creep scope but should be complete near 8/16/18.....DL, 8/10/18; Carp[enters will install the wall this week. Corey has parts orders. Corey will complete the install when the material arrives.......DL, 8/22/18; This Project is Complete |  | Dan Lerman |  | YES | 2018-08-23 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000267 |  | 18P000267 | FALSE | BCOE | SL5 CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-01-16 | [6 empty] | DL, 5/19/18; High table mounted on West wall to be relocated to South wall by light "Centered". Relocate white board from East Wall to West walll wher high table was removed. Paint and new flooring. Need to schedule work with Paul and Jess. BKM furniture is scheduled 4-6 weeks. DL, 6/16/18; Lower electrical outlets on North wall, repair blinds, paint and new flooring. The space is vacant as of June 16th. I will scheudle the workl.....BKM delivery is currently scheduled for July 23rd.......This project is 100% complete. There were two items added to the scope and they will be complete by 7/20/18..... |  | Enrico Baez |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000472 |  | 18P000472 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALL |  | CHUNG HALL | 458 | COMPLETE | Christopher Lynch | TBD | JANNA LE BLANC |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000321 |  | 18P000321 | FALSE | BCOE | SL5 STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST |  | STUDENT SERV | 1228 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Enrico Baez |  |  |  | FALSE |  |  | 2018-02-22 | [6 empty] | DL, 4/29/18; Enrico is cordinationg this. The permits are approved……. DL, 7/11/18; Just received confirmation the door is ready for delivery and installed. I need to check in with Paul about the paint and prep of the door. I also need to check in with Jason on lock hardware......Dl, 7/25/18; Door is painted and ready for install. Called Dugmore to schedule the install. This should be compolete within the next two weeks......DL, 8/8/18; This Project is 100% Complete |  | Enrico Baez |  | YES | 2018-08-10 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000623 |  | 19P000623 | FALSE | BCOE | HOLD SL5 WINSTON CHUNG HALL, RM 348- MOUNT TV |  | CHUNG HALL | 0348 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  |  |  | FALSE |  |  | 2019-05-15 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18P000349 |  | 18P000349 | FALSE | BCOE | SL5 PHYSICS INSTALL PARTITION WALL FOR LAB ROOM |  | PHYSICS | 1037 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 5/24/18; Ron V. has detailed scope and he is ordering material. Once material arives, we will schedule the work…. DL, 6/16/18; Materila is ordered, When door/frame arrives, we will prep, paint and start the work…….DL, 7/11/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000425 |  | 18P000425 | FALSE | BCOE | SL5 BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - |  | BOURNS | A0379 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; Luat Vuong arrives on or about August 15…... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected..…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/15/18........DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000426 |  | 18P000426 | FALSE | BCOE | SL5 BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER |  | BOURNS | A0375 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; A-375: Bhargav Rallabandi arrives on or about August 1….. DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/1/18.....DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000454 |  | 18P000454 | FALSE | BCOE | SL5 BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS |  | BOURNS | A0346 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  |  | 9 | FALSE |  |  | 2018-05-29 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000427 |  | 18P000427 | FALSE | BCOE | SL5 BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER |  | BOURNS | A0373 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie email; This is our new Dean’s faculty office. Dean Lynch is already on site getting up to speed one-two days a week. This office is an ASAP...... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected.....DL, 7/11/18; This project is 100% complete...... |  | Paul Ditty |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000028 |  | 19P000028 | FALSE | BCOE | SL5 BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS |  | BOURNS | A0169 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | Schedule the patch and paint | 2019-04-01 | 2019-05-01 |  |  |  | 5/1/19, DL; This project is 100% Complete…..3/28/19, DL; Monitor mounts were removed, Patch and paint will be completed in the near future……2/28/19, DL; Will schedule the project to be complete the first week in April…… | 2018-11-14 | Ron Veloz |  | YES | 2019-05-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000429 |  | 18P000429 | FALSE | BCOE | SL5 INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 |  | BOURNS | B0262 B0256 | COMPLETE | Christopher Lynch | TBD | KEVIN SCHULTE |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment…..DL, 5/9/18; We are working on plans to submitt to A&E soon....DL, 5/24/18; Plans were submitted on 5/24/18.......DL, 6/12/18; Plans were approved. Cabinets are ordered. Materila is 6-8 Weeks out.....DL, 7/11/18; We have confirmation for delivery of material for mid August. Target Complete date is 9/7/18......DL, 8/10/18; Project has started. We will be complete with in two weeks......DL, 8/22/18; Work is 90% Complete..Project should be complete by 8/31/18........ DL 9/6/1/8; This project is 99% complete. The parts arrived today. I will be sending out an email to schedule the installation time for next week.......DL, 9/19/18; This project is 100% Complete........ |  | Dan Lerman |  | YES | 2018-09-19 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
20P000175 |  | 20P000175 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 112 - PATCH & PAINT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-11 | [8 empty] | Ron Veloz | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with metal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000161 |  | 20P000161 | FALSE | BCOE | SL5 WCH 112 - MODIFY ROOM FOR NEW OCCUPANT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | TBD | MARGARET SOUDER |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-04 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000163 |  | 20P000163 | FALSE | BCOE | SL5 BOURNS A0223 - PATCH/PAINT WALLS, DEEP CLEAN/REPLACE CARPET |  | BOURNS | A0223 | COMPLETE | Christopher Lynch | TBD | SABRINA SCHUSTER | DEANNA VORHEES | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-07 | [8 empty] | Paul Ditty |  |  | 2019-11-25 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000445 |  | 19P000445 | FALSE | BCOE | SL5 BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT |  | BOURNS | B0328D | CANCELED BY FS | Christopher Lynch | TBD | MARGARET SOUDER |  |  |  | 0 |  | FALSE |  |  | 2019-01-11 | [8 empty] | Ron Veloz | Install new wall at room 0328 | N/A | 2019-02-27 | SPRING 2019 | FS | FALSE | 2019 | 2021-02-01
19P000388 |  | 19P000388 | FALSE | BCOE | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | BCOE Advising is being reassigned to space on the 3rd floor of Skye (at the recommendation of the University Space Committee). | SKYE HALL | 308 | COMPLETE | Christopher Lynch | TBD | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-26 | Order material and schedule work | 2019-05-01 | 2019-06-28 |  |  |  | 7/15/19, DL; This project is 100% Complete………..7/1/19, DL; This project ois 95% Complete. Floor covering install will start this Wednesday…………6/17/19, DL; This project is almost complete. Target complete date is July 1st….…..5/31/19, DL; We are making good progress on this project. we are on tract to be copmplete with this project on or before July 1st……5/15/19, DL; Work is in progress and we are on schedule for th3 6/28/19 complete date…….5/1/19, DL; We will start this project this week. 4/15/19, DL; Plans were approved today. We will work on material and schedule the work. We will start this project shortly after May 1st…….3/18/19, DL; We are working on plans and plan to apply for building permit an plan review process next week | 2019-02-13 | Ron Veloz | Customer Request: Frame new walls in rm. 0310B & 0326. Widen door opening, install sliding glass door rm. 0310 Work Covered: Install metal stud framed partition walls in room 0310B and 0326 and install electrical and voice data outlets as required for new furniture layout. Widen the existing door opening in room 0310 and install one new 6-0x7-0 sliding glass door. Install a viewing window (approximately 9-0x4-0 overall width) made with two pieces of glass within a storefront frame. Relocate utilities and one wall *cabinet (*location TBD) as needed. Inclusions: Demolition: Remove the side door and frame in room 0310 and widen the opening to accept a 6-0x7-0 sliding door. Room 0310 east wall, cut in opening (approx. 9-0x4-0) at 36”-48” A.F.F.(field verify). Carpentry: Framing & Drywall: Rooms 0310B & 0326; Construct metal stud partition walls and new cased openings, and install drywall with finished edge metal (room 0310). Intersect new walls into the window mullions with a finished edge or metal with neoprene expansion tape installed between the wall and million. Room 0310; Frame a new cased opening to accept a 6-0x7-0 sliding door and frame a new cased opening at the east wall opening (approx. 9-0x4-0, at 36”-48” A.F.F. field verify) to accept a new viewing window. Floorcovering: Install new 4” rubber base in rooms 0310B and 0326, base to match existing. Acoustical Ceilings: Modify the T-bar ceiling grid and cut ceiling tiles to accommodate the new partition walls in rooms 0310B and 0326. Painting: Tape, sand and paint the new partition walls, door/cased openings. Patch and paint other walls in the Advising room 0310 as needed. Glazing: Room 0310; Install a 6-0x7-0 sliding glass commercial door (outsourced to Hour Glass). Quote is on file. Electrical: Room 0310; Relocate light switch and or wall mounted devices at room 0310/corridor wall and possibly may need to relocate conduit in the east wall where the new window opening is created. Rooms 0310B & 0326; reconfigure/separate lighting circuits and switching. Note: “Installation of electrical and voice data outlets may be required in the new partition walls at rooms 0310B & 0326 depending the furniture configuration”. Fire Alarm: Investigate at rooms 0310B & 0326. Fire Sprinklers: Investigate at rooms 0310B & 0326. Exclusions: Replacement of the existing carpet floorcovering. Repaint all walls at rooms 0310B and 0326 (paint new and adjacent walls only). Installation of new mixing boxes and T-stats in rooms 0310B and 0326. | YES | 2019-07-15 | Spring 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
20P000129 |  | 20P000129 | FALSE | BCOE | SL5 BOURNS HALL B0360C - PATCH & PAINT |  | BOURNS | B0360C | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES | KATHY COCKER | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-09-12 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/22/20 |  | Paul Ditty |  |  | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000278 |  | 19P000278 | FALSE | BCOE | SL5 REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR |  | BOURNS | A0165 | COMPLETE | Christopher Lynch | TBD | NANCY FORD |  | Dan Lerman |  | 1 |  | TRUE |  |  | 2018-08-03 | [6 empty] | DL, 10/4/18; This Project is 100% Complete…….. |  | Ron Veloz |  | YES | 2018-10-04 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000245 |  | 20P000245 | FALSE | BCOE | SL5 WCH RM 0325 - PATCH AND PAINT DAMAGE FROM WHITE BOARD |  | CHUNG HALL | 325 | COMPLETE | Christopher Lynch | TBD | SARA GALLOWAY |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2019-11-25 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/13/20 |  | PAUL DITTY |  |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000107 |  | 20P000107 | FALSE | BCOE | SL5 WINSTON CHUNG 322 - PATCH/PAINT NEW FACULTY FACULTY OFFICE |  | CHUNG HALL | 322 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-08-29 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000135 |  | 20P000135 | FALSE | BCOE | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MS&E Rm 0075 - 3 Ph208 Power CHW S&R WATER PPMS TOOL, Install Chilled water loop & power in clean room 075. | MAT SCI ENGR | 75 | COMPLETE | Christopher Lynch | TBD | MARK HEIDEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-09-19 | Plans and permit | [5 empty] | 9/30/20, DL: This project is complete……..8/5/20, DL: This is in progress…….3/25/20, DL: We will work on plans and permits when we return back from the campus closure……. | 2020-02-18 | Ron Veloz | Intake/SOW: Install 208V 3ph power & disconnect/safety switch and one 3/4" Chilled water loop (Supply and Return) in the MSE southeast corner of clean room 0075. Create a 4" diameter pass-thru hole from this corner of room 0075 into the adjacent room 0071. FS to provide power and cooling to a compressor which will connect through the wall to the PPMS system with cryogenic helium lines. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
20P000253 |  | 20P000253 | FALSE | BCOE | SL5 BOURNS HALL LAB B156 - EXHAUST SYSTEM | EXHAUST SYSTEM | BOURNS | B0156 | PLAN DEVELOPMENT/CHECK | Christopher Lynch | TBD | LOUIS SANDOVAL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 2019-12-11 | fin. plans and apply for prmits | 2021-02-01 |  |  |  |  | 1/19/21, DL: We will start working on the plans for this project in the next two weeks. We will start this project once the permit is approved…… |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01
20P000070 |  | 20P000070 | FALSE | BCOE | SL5 BOURNS B342D - PREPARE LAB FOR NEW FACULTY | PREPARE LAB FOR NEW FACULTY | BOURNS | B0342D | COMPLETE | Christopher Lynch | TBD | SABRINA SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-08-09 | work on paint contract | 2020-01-13 | 2020-02-03 |  |  |  | 2/28/20, DL This Project is Complete……….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is 95% Complete, we need to install 3 power outlets. This project will be 100% complete within two weeks……..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is on schedule to be complete before the 2/3/20 complete date…….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19,DL: We conducted a site visit with the PI> We will do what we can to have the project complete before 2/3/20………… | 2019-11-06 | Ron Veloz | Paint all walls to match existing colors, paint the back of wood cabinets located at the east side of the room, replace stained or damaged ceiling tiles, replace and or replace all HVAC supply & return grilles, relamp as needed, Cal Labs to clean SS sinks, disconnect and dispose of the dishwasher, Plumbing and electrical to disconnect, Cal Labs to refurbish counter tops (light sand & seal), clean strip and wax sheet vinyl floor, repair and refurbish cabinets (white Rm 316, Blue Rm 328), customer to remove all chemical and sanitize fume hoods. | YES | 2020-02-28 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000638 |  | 19P000638 | FALSE | BCOE | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM | renovate lab | BOURNS | B207 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-16 | order material and schedule work | 2019-08-04 | 2019-10-04 |  |  |  | 11/11/19, DL: This project is Complete……10/30/19, DL: This Project is 95% complete and we should be complete next week………..10/16/19, DL; This project is 99% complete. We need to insulate ducting and deep clean the lab………9/16/19, DL; Project is 95% complete. We are planning to be complete in the next 30 days……9/3/19, DL; Project is in progress and 75% complete. 8/15/19, DL; Plans were approved this week. We will order the material and schedule the work……..Plans are 90% complete and we will probably submit plans for plan check review this Monday | 2019-07-19 | Ron Veloz | 07-01-19 O-RVL: RV Received email from Luat on 06-28 with revised SOW. RV Uploaded the referenced sketch into FAMIS. Revisions read: "In efforts to be helpful, I've color coded comments related to the simple attached sketch. 1) Unchanged: HVAC ductwork needs to be insulated so that we cannot hear it— the vibrations from the noise affect precision optical measurements. 2) Revised to be more specific: only the first row of overhead lights should be on the main switch (dark green). The other lights should be lowered and have pull-down chains, like this but with a longer a longer chain: https://www.grainger.com/product/19YX62 3) Removed: it would be nice if cabinets are nicer and not broken, but we'll turn them into open shelves if there are no funds for this. 4) Removed: (unless fire marshalls object and request sprinklers be lowered) 5) 3) Revised: for air venting machined fumes and soldering, a flexible fume vent should be installed, something like this: https://www.grainger.com/product/EXTRACT-ALL-Extractor-Arm-2DBX4 I'm flexible about where this is hung... what are the options? 6) 4) Revised: the utility rack in the center of the room should be moved to be in line with the other, and centered with the whiteboard on the wall. (Pink) 5) Added: chilled water (blue) and compressed air (light green) should be piped over so it's available to the 10'x3' optical table. 6) Added: Black plywood would be installed at the height of the current 8 1/2" frame like Kevin's in 2 spaces: a) around the 10x3' marked optical table b) around the 6x3' overhead rack close to the doors. Luat T. Vuong" | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000619 |  | 19P000619 | FALSE | BCOE | SL5 BOURNS, RM A0311- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0311 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-05-14 | Awaiting Flooring Install | [5 empty] | 06/28/19 O-ANS: Paint phase complete and awaitin flooring install. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
19P000453 |  | 19P000453 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT |  | CHUNG HALL | 447 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-17 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2019 | 2021-02-01
19P000621 |  | 19P000621 | FALSE | BCOE | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0308 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2019-05-14 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000059 |  | 19P000059 | FALSE | BCOE | SL5 CHUNG HALL 201 SECURITY SYSTEM INSTALL | ITS to install cameras, no work by FS Required. | CHUNG HALL | 201 | CANCELED BY FS | Christopher Lynch | TBD | MAGARET SOUDER |  | Dan Lerman |  | 10 | 7 | FALSE |  |  | 2018-07-17 | [6 empty] | DND 7/30/18 Project #19P000059 to replace REF CPMS # 9054 Ron to speak with ITS to complete installation. |  | Ron Veloz |  | YES | 2018-07-30 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000435 |  | 19P000435 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR WEST HALLWAYS - FLOORING | FS to coordinate with client to scope work. | BOURNS | A0145 | CANCELED BY FS | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-19 | [6 empty] | 2/14/19, DL; This project was a repair and not complete replacement | 2018-10-25 | Ron Veloz |  | YES | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000477 |  | 19P000477 | FALSE | BCOE | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT |  | CHUNG HALL | 457 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-01-30 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000029 |  | 19P000029 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | Canceled; duplicate request to be completed with 19P000059 | CHUNG HALL | 205 | CANCELED BY CLIENT | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-16 | [6 empty] | Canceled; duplicate request to be completed with 19P000059 |  | Ron Veloz |  | NO | 2018-09-18 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000316 |  | 19P000316 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL |  | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 2018-10-03 |  | 2018-08-30 | 2018-12-14 |  |  |  | 12/14/18, DL; This Project is 100% Complete…Anticipated completion 11/9/18. | 2018-10-03 | Ron Veloz |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000602 |  | 19P000602 | FALSE | BCOE | SL5 BOURNS B328F- PREPARE LAB FOR NEW PI OCCUPANCY |  | BOURNS | B0328F | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-09 | Finish the work… | 2020-02-10 | 2020-03-07 |  |  |  | 3/25/20, DL: this Project is Complete………...2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is almost complete and should be complete in the next 2-3 weeks………..10/30/19, DL: Plans and permits will be required for the work. We will work on the plans shortly after Thanksgiving……….. | 2019-09-27 | Ron Veloz | Construct metal stud wall framing and bracing above ceiling to infill the opening. Remove and reinstallation wall mounted cabinets located near the cased opening to access and join to the existing wall to new drywall. Install sound insulation. Install drywall, tape, sand, prime and paint wall. Install install rubber base to match existing. Modify T-bar ceiling to accept the wall framing Provide dust containment (Zip Walls) at both rooms near construction area. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000442 |  | 19P000442 | FALSE | BCOE | SL5 WINSTON CHUNG- PATCH/PAINT ROOM 319 |  | CHUNG HALL | 319 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-09 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2019 | 2021-02-01
20P000028 |  | 20P000028 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0219- PAINT FACULTY OFFICES |  | BOURNS | A0219 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-07-19 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MAT SCI ENGR | 71 | PROJECT INTAKE | Christopher Lynch | TBD | XI CHEN |  | DAN LERMAN |  | 2 | 3 | FALSE |  |  | 2020-08-06 | plans and permits | [5 empty] | 1/19/21, DL: This is a priority #2 project. WE will start the plans and permit process for this project when all priority 1 projects are complete…………1/14/21 O-ANS: Updated prioritization to #2 (from #3) per org leadership request. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
20P000210 |  | 20P000210 | FALSE | BCOE | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | Reduce noise. Replace doors with solid core doors and install an Acoustic Door Seal Kit. | CHUNG HALL | 224 | CANCELED BY FS | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-11-05 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……. | 2020-02-11 | Ron Veloz | Removal of the existing double doors and door hardware, install new solid core double doors with continuous hinges, install new acoustical jamb seals, threshold seal and a surface mounted Automatic Door Bottom utilizing a flat spring mechanism, which activates when closing the door, lowering a neoprene seal insert against the floor or threshold to create a sound seal. Install acoustic double door astragals with seal. Reinstall all existing door locksets, and door closers. Quote received from Brad Aduddell-American Door to perform this work. Quote & Specs are available in the project folder. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
20P000233 |  | 20P000233 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - A169 & A170 ENTRY AREA DAMAGED |  | BOURNS | A169 & A170 | CANCELED BY FS | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-11-22 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000046 |  | 19P000046 | FALSE | BCOE | SL5 PATCH AND PAINT PLUS REPLACE BLINDS |  | BOURNS | A0131 | COMPLETE | Christopher Lynch | TBD | NANCY FORD |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-09 | Finish Gas cabinet installation | 2019-09-23 | 2020-02-07 |  |  |  | 8/5/20, DL: This Project is Complete…….3/25/20, DL: Project is 95% complete. We will install the fire sprinkler and exhaust duct to the gas cabinet when we return from the campus closure………..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Plans were approved and material is ordered. We are hopeful the material will arrive the 2nd or 3rd week in January. Once material is on site we will schedule the work…… 11/19/19 DH: Emailed Status Report to customer……10/16/19, DL: This project is 90% Complete. We are working on plans and permits for the two snorkels……….10/1/19, DL: This project is almost complete. We will be complete in the next 4- weeks except the Snorkel……….. 9/13/19, DL; The paint of the cabinets is scheduled for this week along with the power. We will submit the plans for the snorkel this with in the next two weeks…….9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Ron Veloz | SOW, Patch& Paint Walls, replace plexi glass on shelving, powder coat metal shelving & cabinets, clean & polish or replace chem sinks, polish counter tops, Validate all gas, water, drains, DI water & utilities. Replace damaged and dirty ceiling tiles, relamp as needed. Strip & wax floor. Dan L is requesting vendor pricing to restore finishes. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000487 |  | 19P000487 | FALSE | BCOE | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES |  | BOURNS | A219, A211, A241 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-02-05 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000221 |  | 20P000221 | FALSE | BCOE | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | COMPLETE | Christopher Lynch | TBD | HONG XU | KEVIN FREEDMAN | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-11-15 | [6 empty] | 1/19/21, DL: This project is 100% Complete……..9/30/20, DL: We are in the process of finishing up a few other projects. Once they are complete, we will schedule the work….8/5/20, DL: Plans are approved and we will start the work in the next 2-6 weeks…….. | 2020-02-25 | Ron Veloz | Install Plywood and supports. Paint Plywood black. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000601 |  | 19P000601 | FALSE | BCOE | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY | Renopvate lab space, Patch/paint, Re-finish, re-surface – existing cabinets/casework. Re-finish, bench-tops. Clean existing Chemical fume hood. Repair or replace self-closing chemical/flammables storage cabinet. Repair or replace bench shelves as needed. Clean and wax floors. | BOURNS | B0328E | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-05-09 | Order material and scheudle work |  | 2020-02-07 |  |  |  | 2/28/20, DL: This project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL; This Project should be complete in the next 2-3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were approved. We will order material and schedule the work once the material is on site. The material should arrive around the 21st of January…….11/25/19, DL; Floor covering will be complete today. This project is complete except for the Snorkel vents. We are still waiting for plans check approval on the snorkels………11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Floor covering is delayed. We will schedule the floor covering installation when the material is on site. We submitted the plans for the snorkels last week. Once the plans are approved, we will order the phoenix valves and schedule the work………. 10/30/19, DL: This Project is 85% Complete. We will install new floor covering in the next two weeks. All work will be completed except the two snorkels. We still need to submit plans for the snorkels……..10/16/19, DL; This project is 80% complete. 9/16/19, DL; Project is in progress. We still need to submit plans for the snorkel for the power and snorkel. We will submit the plans for review within the next week. Once plans are approved, we will schedule the work……..Scope is complete, waiting on estimates from vendors. We will need to work up a contract which will add time to the project timeline… | 2019-08-06 | Ron Veloz | Provide two new 4” exhaust duct drops. One at the south wall above mobile table & one at the east wall above counter. Refinish two wood work station counter tops with chemical resistant coating (approx. 64lf) including one mobile table wood top. Install four(4) 208v / 30a Electrical receptacles and data drops at gutter racks above two work benches Provide drawer and door maintenance and or repairs at all metal cabinets and metal shelving. Powder coat all lower metal cabinets, shelving, fume hood doors and drawers. Replace damaged sheet vinyl flooring as needed. Move surplus items to materials management as identified by the PI. Install MilQ equipment at the east wall near sink. Relocated cylinder rack as necessary to accommodate “L” shaped work station. Provide and install two new cylinder racks at the south end of two work benches. Furnish and install two new metal cylinder racks. Replace damaged and/or stained 2x4 acoustical ceiling tiles. Relocate “L” shaped front cabinets. Relamp light fixtures and needed. Infill wall between rm 328E & D Patch and paint walls. Strip and wax floor. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
21P000019 |  | 21P000019 | FALSE | BCOE | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | Bourns Office A305 - Install Plank Floor Please remove old damaged carpet and install new plank floor. Match with that of the ME suite (same floor). Thank you. Note: Current PI has not moved out. We will contact Facilities once date is known and all items have been removed from the room. Questions: ME Department Manager (Interim) - William Bingham - bill@ece.ucr.edu , or Robert Lopez lopezra@engr.ucr.edu | BOURNS | A305 | PROJECT INTAKE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | 3 | 2 | TRUE |  |  | 2020-07-20 | complete priority 2 projects | [5 empty] | 1/19/21, DL: This a priority 3 project. We will start this project when all priority #2 projects are complete………..1/14/21 O-ANS: Updated prioritization to #3 (from #2) per org leadership request. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
19P000597 |  | 19P000597 | FALSE | BCOE | SL5 PATCH AND PAINT WALLS |  | CHUNG HALL | 355, 356, 351, & 353 | COMPLETE | Christopher Lynch | TBD | SARA GALLOWAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-05-03 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000175 |  | 19P000175 | FALSE | BCOE | SL5 PAINTING |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | TBD | ROBERT CHAVARRIA-VIVAR |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000312 |  | 19P000312 | FALSE | BCOE | SL5 VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP |  | STUDENT SERV | 1227 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000029 |  | 20P000029 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0211- PAINT FACULTY OFFICES |  | BOURNS | A0211 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-07-19 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/12/19 |  | Paul Ditty |  |  | 2019-12-12 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000624 |  | 19P000624 | FALSE | BCOE | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | Refurbish Room-Student Space, | BOURNS | A0346 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-05-15 | Pending information from Susanna | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Susanna is working on a cubicle layout. Once we have the information from her. We will schedule the work………… | 2019-11-07 | Ron Veloz | Remove all lower cabinets in room A0346 and all lower cabinets and mail boxes in Rm A0304 | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
20P000039 |  | 20P000039 | FALSE | BCOE | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE |  | BOURNS | A0318 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-05-13 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……..09/19/19 O-ANS: HOLD FOR WINTER 2020 PER CUSTOMER (LOUIS SANDOVAL) REQUEST. EMAILED PAUL DITTY TO CONFIRM. PAUL STATED THIS IS NON-PAINT PROJECT B/C SCOPE OF WORK INCLUDES CARPENTERS AND ELECTRIC SHOPS. |  | Paul Ditty |  |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000625 |  | 19P000625 | FALSE | BCOE | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM |  | BOURNS | A0108 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-15 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-01 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000205 |  | 19P000205 | FALSE | BCOE | SL5 LABORATORY RENOVATION FOR NEW FACULTY |  | BOURNS | A0328 | COMPLETE | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | 4 |  | TRUE |  |  | 2018-08-23 | electrostatic Paint | 2018-11-01 | 2019-01-14 |  |  |  | 2/28/19, DL; This Project is 100% Complete…….2/1/19, DL; This project is 99.9% Complete………..1/15/19, DL; This project is 90% complete. WE still need to finish snorkels and ceiling tiles. We should be 100% complete by 2/1/19……12/14/18, DL; This project is on schedule..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/4/18; This is a large scale project, we will walk with the trade supervisors next week. We will also work on the plans and schedule the work. Target Date is 1/1/19…..DL, 11/7/18; work is scheduled. We are working on the electrostatic paint contract. We are in plan check review process. There are questions about the fire sprinklers from Scott J. Sent Scott J. an email requesting a site visit to better determine if any work will be required on the sprinkler system….. |  | Ron Veloz |  | YES | 2019-02-18 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000322 |  | 19P000322 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-05 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000065 |  | 20P000065 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR CONFERENCE ROOM 205/206 - PATCH & PAINT |  | CHUNG HALL | 205 & 206 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-08-08 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000250 |  | 19P000250 | FALSE | BCOE | SL5 BOURNS A303-PAINT AND PATCH WALL |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | TBD | JUANA GUERRERO |  | Paul Ditty |  | 5 |  | TRUE |  |  | 2018-09-10 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000424 |  | 19P000424 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET |  | CHUNG HALL | 445 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-12-20 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
19P000558 |  | 19P000558 | FALSE | BCOE | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT |  | BOURNS | A0265 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-04-03 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000526 |  | 19P000526 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT |  | CHUNG HALL | 0202 & 0203 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-03-12 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-08 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000657 |  | 19P000657 | FALSE | BCOE | SL5 WINSTON CHUNG HALL, RM 406- PATCH/PAINT OFFICE |  | CHUNG HALL | 406 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-06-07 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000060 |  | 19P000060 | FALSE | BCOE | SL5 CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | CHUNG HALL | 223 & 224 | TO BE PERFORMED BY PD&C | Christopher Lynch | TBD | MAGARET SOUDER |  | Dan Lerman |  | 6 | 4 | FALSE |  |  | 2018-05-15 | [6 empty] | 2/1/19, DL; Thios is a PD&C project. Maggie S. is aware this project may be a $130,00. project……DL, 7/25/18; This project is complicated and plans/permits will be required. This project will also require Air Hanlers to be shut down so Vibration dampners can be instlled. We will work on the plans in the next 45 days. This project should be scheduled during the Winter. We may also need to rent a large portable air handler to ensure the Large server room can maintain temp……. Project #19P000060 to replace REF CPMS # 9043. DL, 11/7/18; Sent Maggie an email on 11/7/18 informing her this project is well beyond our scope and $50K threshold. |  | Dan Lerman |  | YES | 2019-02-01 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000565 |  | 19P000565 | FALSE | BCOE | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS |  | BOURNS | A0133 | CANCELED BY CLIENT | Christopher Lynch | TBD | NANCY FORD |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-04-08 | [6 empty] | 07/30/19 O-ANS: Per Paul Ditty, Customer Maggie Souder canceled project. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000588 |  | 19P000588 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - PATCH & PAINT OFFICES |  | BOURNS | A127 Office, A129 Office, A131 Office, A133 Office, A135 Office, A137 Office, A139 Office, and A141 Office | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-04-22 | [6 empty] | 06/28/19 O-ANS: Paint phase complete. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
18P000226 |  | 18P000226 | FALSE | BCOE | SL5 BOURNS FUME HOOD INSTALLATION |  | BOURNS | B0235A | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 8 | HOLD | TRUE |  |  | 2017-12-11 |  | 2018-11-26 | 2019-01-31 |  |  |  | 2/14/19, DL; This project is Complete…..2/1/19, DL; The Fume hood is complete. The vendor will be back in two weeks to comissison the clean room…..…1/15/9, DL; This project is 95% complete and should be complete on or near 2/1/19…………12/14/18, DL; This Project is 90% Complete. Fume hood is scheduled for install next week. We will finish balance of project after Fume hood is installed…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. WE are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans…..DL, 5/9/18; planning to submit plans on 5/11/18 for plan check review….. DL, 5/24/18; Plans were submitted to Bob W. on 5/24/18……DL, 6/12/18; Project is on Hold until Shane can provide plans/specs for the clean room……DL, 7/11/18; Still no change to the status……DL, 7/25/18, Maggie confirmed this project is on the books. I need to discuss the status with the team because the priority list is on Hold…….DL, 8/22/18; This project is no longer on hold. We will per shane we will submit what we have from the clena room suupplier for review from FM and BO……DL, 9/6/18; WE are almost complete with Plans and will submit the plans next week………DL, 9/19/18; Submitted plans to PD&C on 9/14/18…..DL, 10/4/18; Plans were approved thais week. WE will scheudle the project around the delivery date for the Clean room……..DL, 11/7/18; This is in progress. We will complete the install of the utilities so the clean room can be installed. WE will finish the balance of the project once the Clean room install is complete. The clen room is being install by an outside vendor….. |  | Dan Lerman |  | YES | 2019-02-14 | Spring 2018 | FS | FALSE | 2017 | 2021-02-01
19P000129 |  | 19P000129 | FALSE | BCOE | SL5 HANG MONITORS AND BOARDS |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | TBD | RICHARD BAIN |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2018-08-06 |  | 2018-11-05 | 2018-12-14 |  |  |  | 12/14/18, DL; This Project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Dry errase boards and Monitor mounts are installed. Still need to install monitors, corner guards and monitors….. |  | Ron Veloz |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000620 |  | 19P000620 | FALSE | BCOE | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0304 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 9 |  | TRUE |  |  | 2019-05-14 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000026 |  | 19P000026 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALLS | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | TBD | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-18 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000023 |  | 19P000023 | FALSE | BCOE | SL5 PAINT ACCENT WALL | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | TBD | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-13 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-18 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000035 |  | 19P000035 | FALSE | BCOE | SL5 WCH--INSTALL NEW LED DISPLAY IN OFFICE |  | CHUNG HALL | 354 | COMPLETE | Christopher Lynch | TBD | SARA GALLOWAY |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This Porject is 100% Complet…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Install scheduled for this Friday. | 2018-10-03 | Ron Veloz |  | YES | 2018-11-19 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000438 |  | 18P000438 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING |  | CHUNG HALL | 415 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 10 | FALSE |  |  | 2018-05-14 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000439 |  | 18P000439 | FALSE | BCOE | SL5 CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING |  | CHUNG HALL | 315 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 11 | FALSE |  |  | 2018-05-15 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | BOURNS | B0328E | QUEUE TO START | Christopher Lynch | TBD | MARGARET SOUDER |  | Enrico Baez |  | R1 | R1 | FALSE |  |  | 2019-11-05 | [6 empty] | 1/19/21, DL: Todd has the estimate. Sent follow up email to Todd requesting update or FAU number………………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01 |  | 1
20P000067 |  | 20P000067 | FALSE | BCOE | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM | BOURNS | B-Wing | TO BE PERFORMED BY PD&C | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2016-11-14 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold until further notice……. |  | Ron Veloz | Replace access controls at BCOE WCH & Bourns bldgs. |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2016 | 2021-02-01 | FY 20-21 | 1
19P000427 |  | 19P000427 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | Install Power and TV bracket, move white board | CHUNG HALL | 453 | CANCELED BY FS | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2019-01-03 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold……… | 2019-09-18 | Ron Veloz | Install Power and TV bracket, remove white board and relocate , patch and paint wall prior to installing | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21 | 1
19P000502 |  | 19P000502 | FALSE | BCOE | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | Install Electrical power & TV bracket.for a 75" TV to mount in CS 342. | CHUNG HALL | 444 | CANCELED BY FS | Christopher Lynch | TBD | RICHARD BAIN |  | Dan Lerman |  | R3 |  | FALSE |  |  | 2019-02-19 | Schedule the work. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This project is on hold……………3/25/20, DL: Work orders are produced. I will work on scheduling the work when we return back to work…….. | 2019-09-17 | Ron Veloz | Install Electrical power & TV bracket. Excludes network/data back box and stub up to ceiling. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21 | 1
20P000449 |  | 20P000449 | FALSE | BCOE | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | Paint Only - Chung Hall, Fourth Floor, Room 461 Patch & Paint: At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. Follow up with fresh paint. Thank you. | CHUNG HALL | 461 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-11 | [6 empty] | 01/19/21 O-ANS: Complete per technician updates and closed project. Completed by Wendy M. 11/09 -SC |  | Paul Ditty |  |  | 2020-11-09 | Winter 2021 | FS | FALSE | 2020 | 2021-02-01 | FY 20-21
20P000363 |  | 20P000363 | FALSE | BCOE | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | Paint Only | CHUNG HALL | 433 | QUEUE TO START | Christopher Lynch | TBD | MANGLAI ZHOU | FARIBORZ KARGAR | PAUL DITTY |  | X |  | TRUE |  |  | 2020-02-13 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
21P000037 |  | 21P000037 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | Paint Only | CHUNG HALL | 427 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-07-31 | [6 empty] | 01/19/21 O-ANS: Paint complete per technician and closed project. 11/30/20 B-SBT: repatch & Paint north wall |  | Paul Ditty |  |  | 2020-11-30 | Winter 2021 | FS | FALSE | 2020 | 2021-02-01 | FY 20-21
20P000310 |  | 20P000310 | FALSE | BCOE | SL5 BOURNS A-WING A129 - PATCH & PAINT | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. | BOURNS | A0129 | QUEUE TO START | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-01-10 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Funding | Christopher Lynch | TBD | Margaret Souder |  | Scott Donnell | 2 |  |  | FALSE | 700000 |  | 2018-04-04 | Secure Funding | [12 empty] | PD&C | FALSE | 2018 | 2021-02-01
3617 | 3617 |  | FALSE | BCOE | WCH 108 Server Rm HVAC Upgrade | Winston Chung 108. Upgrade the HVAC system to provide cooling as needed for the server room. |  |  | In Pre-programming | Christopher Lynch | TBD | Michael Ambriz |  | Tameesha Hayes | 3 |  |  | FALSE |  |  | 2021-01-22 | Design | [12 empty] | PD&C | FALSE | 2021 | 2021-02-01
19P000188 |  | 19P000188 | FALSE | CAMPUS | SL5 PAINT - HALLWAY DOORS & INSIDE RESTROOMS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500 | CANCELED BY FS |  |  | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-16 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000296 |  | 19P000296 | FALSE | CAMPUS | SL5 MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB |  | MAT SCI ENGR |  | COMPLETE |  |  | MILLY PAREDEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-09-25 |  | 2019-02-01 | 2019-02-28 |  |  |  | 2/28/19, DL; Project is 100% Complete…….2/14/19, DL; This project is 90% Complete and should be complete by the end of the month………….2/1/19, DL; Permits are approved, we will schedule the project in the next 2- weeks and hope to be complete by the end of February….12/14/18, DL; Rendering has been given to Ron R. Ron will present to Gerry for review and approval. Once approved, we will proceed with plans and permits……DL, 11/7/18; Need to find out where this project stands in regards to the priioroity….. Site vist was conducted and scope of work is verified. Plans and permits will be required for the work….. |  | Ron Veloz |  | YES | 2019-02-28 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000211 |  | 19P000211 | FALSE | CAMPUS | SL5 LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | Reviewing campus standards for these project requests. | LIFE SCIENCE | 2545 | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000122 |  | 18P000122 | FALSE | CAMPUS | SL5 MS&E HYDRATION STATION - MS&E HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman |  | NO | 2018-04-02 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
18P000121 |  | 18P000121 | FALSE | CAMPUS | SL5 PHYSICS HYDRATION STATION - PHYSICS HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | order parts | 2019-04-20 | 2019-05-31 |  |  |  | 5/1/19, DL; Per Chris, we will not be compelting this project. There is currently a Water dispenser on the drinking fountain. 3/28/19, DL; We will look into installing a bottle filler on this fountain verse a complete change out…..12/6/18, DL; This project is currently on hold…… DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman |  | NO | 2019-05-01 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
19P000212 |  | 19P000212 | FALSE | CAMPUS | SL5 REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500A | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000435 |  | 18P000435 | FALSE | CAMPUS | SL5 HMSS HYDRATION STATION REQUEST |  | HUM & SOC SC | 3600 | COMPLETE |  |  | NELDA THOMAS |  | Dan Lerman |  |  | 30 | FALSE |  |  | 2018-05-10 | schedule the work | 2019-03-28 | 2019-04-26 |  |  |  | 4/15/19, DL; This project is 100% Complete…..3/28/19, DL; Fountain is in. working on power and paint….. |  |  |  | NO | 2019-04-15 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000284 |  | 19P000284 | FALSE | CAMPUS | SL5 GEOLOGY ACCOMMODATION DOCK DOORS |  | GEOLOGY |  | COMPLETE |  |  | DEBORAH TERAO |  | Chris Pillen |  | Canceled | Canceled | FALSE |  |  | 2018-08-07 | [8 empty] | Ron Veloz |  | YES | 2019-01-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000396 |  | 19P000396 | FALSE | CAP PROG | SL5 TRAILER #14 - CAMPUS INITIATED - STRUCTURE |  | T14 |  | COMPLETE | Jacqueline Norman | Sharyl Murdock | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-31 | Install underground utilites | 2019-02-01 | 2019-05-01 |  |  |  | 2/28/19, DL; This Project is 100% Complete…..Trailers were demolished. We need to install the utilities. Once the Grow Pod is on site, we will connect the utilities to the structure…… |  | Enrico Baez |  |  | 2019-02-28 | Winter 2018 | FS | FALSE | 2019 | 2021-02-01
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | John White |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete Construction | 2021-01-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-01
3119 | 3119 |  | FALSE | CAP PROG | Plant Growth Environment Facility | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. |  |  | Furniture/Equipment | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 6 |  |  | FALSE | 27425000 |  | 2016-05-25 | Commisioning | 2019-06-01 | 2021-01-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-01
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Mihai Gavan | 9 |  |  | FALSE | 57950000 |  | 2017-06-01 | Complete Construction | 2019-11-01 | 2021-08-01 | [10 empty] | PD&C | FALSE | 2017 | 2021-02-01
2970c | 2970c |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | Re-bid | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 2015-12-02 | Award Contract | 2021-03-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2015 | 2021-02-01
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 2015-12-02 | Complete Design | [12 empty] | PD&C | FALSE | 2015 | 2021-02-01
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Study | [12 empty] | PD&C | FALSE | 2018 | 2021-02-01
3401 | 3401 |  | FALSE | CAP PROG | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | In Construction | Jacqueline Norman | Sharyl Murdock | Mihai Gavan |  | Fernando Canon | 12 |  |  | FALSE | 8754623.11 |  | 2017-12-03 | Complete Construction | 2020-05-01 | 2021-02-01 | [10 empty] | PD&C | FALSE | 2017 | 2021-02-01
2952 | 2952 |  | FALSE | CAP PROG | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jon Harvey |  | Gerald Caraig | 13 |  |  | FALSE | 23895000 |  | 2015-09-11 | Phase I Completion | 2019-01-02 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2015 | 2021-02-01
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 14 |  |  | FALSE | 0 |  | 2017-12-03 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-02-01
3438 | 3438 |  | FALSE | CAP PROG | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | City to determine schedule | Jacqueline Norman | Sharyl Murdock | Dave Bomba |  | Scott Donnell | 15 |  |  | FALSE | 88500 |  | 2018-08-22 | City to determine schedule | 2020-07-01 | [11 empty] | PD&C | FALSE | 2018 | 2021-02-01
3589 | 3589 |  | FALSE | CAP PROG | Various Bldgs LED Lighting Ph2 | LED Lighting Phase 2 - Package 1 - Replacing existing lamps to LED |  |  | Bidding | Jacqueline Norman | Sharyl Murdock | David Palacios |  | Fernando Nunez | 15 |  |  | FALSE | 780545 |  | 2020-03-11 | 100% Cd stamped approval | 2021-04-01 | 2021-07-30 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-01
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 17 |  |  | FALSE | 0 |  | 2018-07-16 | Coordinating with North District | [12 empty] | PD&C | FALSE | 2018 | 2021-02-01
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 15690389.32 |  | 2016-12-16 | Bidding | 2021-04-01 | 2021-10-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-01
18P000410 |  | 18P000410 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 3148B | COMPLETE | Kim Wilcox | TBD | CANDICE GOMEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-25 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000421 |  | 18P000421 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 2120 | COMPLETE | Kim Wilcox | TBD | CANDICE GOMEZ |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-04-30 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000329 |  | 18P000329 | FALSE | CHANCELLOR | SL5 SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST |  | SKYE HALL | 170 | COMPLETE | Kim Wilcox | TBD | DA LAN DINH |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18…..DL, 5/24/18; Plans were approved. Demo work has started......DL, 6/12/18; MArshal and Kate are working on Carpet order......DL, 7/11/18; Carpet is ordered. We have a challenge with Title 24. I am working on the title 24 documents. We are still planning to have this project complete on 8/17/18......DL, 8/10/18; We now have the Title 24 plans. The are being reviewed by Bob and Scott.....Title 24 plans approved. Robert is working on PO#. Most parts are on site and Electricans are working on project. All other Trades to follow once Lights are in...... Hard Date of 9/7/18............9/6/18 As of today, Carpet is scheduled for install tomorrow morning and furniture is scheduled for delivery this Monday......WE will more than likely have electrical punch items and touch up paint but this propject should be 100% complete in regards to FS the end of next week next week......100% PROJECT COMPLETE... GREAT WORK DAN! |  | Dan Lerman |  | YES | 2018-09-18 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000209 |  | 18P000209 | FALSE | CHANCELLOR | SL5 VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 |  | STUDENT SERV | 0 | CANCELED BY CLIENT | Kim Wilcox | TBD | ANGIE GRAY |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2017-11-30 | waiting to hear back from Angie | [5 empty] | 5/16/19, DL Angie Grey canceled project on 5/15/19 via email….. 5/1/19, DL; Sent Angie an email this morning. Waiting to hear back from Angie to see if project will be canceled or sent to PD&C…..3/28/19, DL; Provided Angie with an estimate and waiting for her response. The esimate was for 65,000. this work will be redirected to PD&C if she wants to proceed…….2/14/19, DL; Ron V. to follow up with Doug from Capitol Door for alternate pricing .1/15/19, DL; Ron V is still working with Angie on verifying a vendor and product…………..12/14/18, DL; Ron V. is currently working to find a more affortable turnstyle system. When a sytem is approved, we will schedule the work…. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope and conduct site visit……DL, 7/11/18; This work will require plans and permits. Will schedule meeting with Scott to verify if the project request will be approved. If this is approved, we will plan the target complete date to be mid October…..The Request is to reverese Emergency Exit Doors and install Prox card access……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..DL, 8/22/18; Confirmed with Scott that we can reverse the door swing. We will work on plans for review process. This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 9/19/18; I mis understood this for a project at Health Services. I have a meeting with Angie this week. This project is to install turn styles for access to the building. I will need to discuss the equipment to be purchased by Angie verify the specs. We will start on the plans in the early Fall……DL, 11/7/18; Conducted site visit with Vendor. Informed Angie the cost of the project will be at $45K for the project. Angie is checking to verify if funds are availabe for the equipment. |  | Ron Veloz | Install automatic swing gates at the student services lobby. Include Access controls relay cabling | YES | 2019-05-16 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
18P000414 |  | 18P000414 | FALSE | CHANCELLOR | SL5 CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL |  | STUDENT SERV | 0 | COMPLETE | Kim Wilcox | TBD | DANIELLE GARCIA |  | Paul Ditty |  | 1 | 2 | FALSE |  |  | 2018-04-26 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000375 |  | 19P000375 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT HOLES |  | SKYE HALL | 365 | COMPLETE | Kim Wilcox | TBD | FELECIA GARRETT |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-07 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000068 |  | 20P000068 | FALSE | CHANCELLOR | SL5 SKYE 349 - COVER HOLES ON WALL |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | TBD | VICTORIA AVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-08-09 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18P000487 |  | 18P000487 | FALSE | CHANCELLOR | SL5 SKYE HALL PATCH HOLES AND PAINT |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | TBD | SONIA ZAMORA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000420 |  | 19P000420 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT WALL |  | SKYE HALL | 325 | COMPLETE | Kim Wilcox | TBD | REYNA ALARCON |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-19 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
19P000122 |  | 19P000122 | FALSE | CHANCELLOR | SL5 REMOVE, PATCH & PAINT AND HANG |  | STUDENT SERV | 2222 | COMPLETE | Kim Wilcox | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000297 |  | 18P000297 | FALSE | CHANCELLOR | SL5 SKYE HALL CHECK LOCATION FOR TV INSTALL |  | SKYE HALL | 390 | COMPLETE | Kim Wilcox | TBD | CANDICE GOMEZ |  | Dan Lerman |  | 4 | 3 | FALSE |  |  | 2018-02-02 | [6 empty] | 2/1/19, DL; This Project is 100% Complete………1/18/19, DL; This Project is scheduled to be complete next week.….. DL, 5/24/18; Need to verify scope with Enrico…..DL, 7/11/18; Work orders are produced and need to be issued. Target complete date is 9/3/18…. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000387 |  | 18P000387 | FALSE | CHASS | SL5 HMSS PATCH/PAINT |  | HUM & SOC SC | 3600 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 28 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000344 |  | 18P000344 | FALSE | CHASS | SL5 CHASS INTS PAINT MULTIPLE ROOMS - FACULTY |  | CHASS INT S | 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 1 | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 7/11/18; This was transferd in to my quque in the past week. I need to scope this project. I belive this is part of project # 18P000205 and 18P000295. If this is part of the other project. We will try to have the paint completed by 8/17/18…......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/10/18; Work has started. We passed rough electrical and framing inspection. The work should be complete in about three weeks......DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18.......DL, 9/6/18; This Project is 100% Complete....... |  | Paul Ditty |  | N/A | 2018-09-10 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000353 |  | 18P000353 | FALSE | CHASS | SL5 PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT |  | PSYCHOLOGY1 | 1111A | COMPLETE | Juliet McMullin | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 26 | FALSE |  |  | 2018-03-20 | [6 empty] | DL; 7/4/18;This project is scoped. We will only paint one out of the two offices. Working on PO# to install frosted glass with Sun Down Window coverings……DL, 7/25/18; PO# is produced and material is ordered. Target date mid August…….DL, 8/22/18; This project is complete.... |  | Paul Ditty |  | N/A | 2018-08-23 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000253 |  | 19P000253 | FALSE | CHASS | SL5 ARTS RENOVATION |  | ARTS | 157 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 16 | FALSE |  |  | 2018-04-17 | [6 empty] | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access……DL, 7/11/18; This project needs to be complete before Fall 2018. Space is vacant and ready go. Need to walk and confirm Schdule with Paul D. Tony's Flooring is ready to go after paint is complete.... Target complete date is 9/21/18......DL, 8/22/18; Walked with PAul, Paul will scheudle the work. Jess still need to cordinate with Tony's Flooring .....DL, 9/19/18; The paint and flooring is complete. The seams need to be welded and this will be complete. this will be complete by 9/21/18......9/19/21; This Project is 100% Complete....... |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000383 |  | 18P000383 | FALSE | CHASS | SL5 HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT |  | HUM & SOC SC | 1302 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  | 4 | TRUE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000318 |  | 18P000318 | FALSE | CHASS | SL5 CHASS INT S FLAT SCREEN INSTALLATION |  | CHASS INT S |  | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Dan Lerman |  |  | 20 | FALSE |  |  | 2018-02-21 | schedule the work | 2019-03-14 | 2019-04-12 |  |  |  | 4/15/19, DL; This is 100% Complete….3/28/19, DL; Monitor is installed. Need to finishe power and data next week……2/28/19, DL; Scheduled to complete the install mid March…..2/1/19, DL; Francesca contacted me and informed me this project is now back on the books. She needs to gather more information and order the monitor. When the monitor arrives, we will schedule the installation…….1/29/19, DL; Francesca confirmed this project is not needed and requested this project to be cencelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; we have the brackets. Will scheule the work after the project is approved…..DL, 7/11/18; Work order are not produced. Need to assign and schedule the work…. Target complete date is 8/3/18……DL; 7/25/18; Need to change target date.. |  | Enrico Baez |  | YES | 2019-04-15 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000367 |  | 18P000367 | FALSE | CHASS | SL5 CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE |  | CHASS INT N | 3033 | COMPLETE | Juliet McMullin | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 23 | FALSE |  |  | 2018-03-27 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000056 |  | 19P000056 | FALSE | CHASS | SL5 HMSS CAPABILITY OF MOUNTING A TV |  | HUM & SOC SC | 1212 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  |  | 18 | FALSE |  |  | 2017-10-03 | Install power after winter break | 2018-12-07 | 2019-01-17 |  |  |  | 12/14/18, DL; Monitor is complete. Still need to work on electrical……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope with Enrico and schedule the work…. Work orders are not produced. Need to assign and schedule the work DND 7/30/18: Closed work order #18W004822; created project #19P000056……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | 3/04/19, DL; Allison Rodgers confirmed this project is 100% Complete…. | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2017 | 2021-02-01
18P000469 |  | 18P000469 | FALSE | CHASS | SL5 WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS |  | WATKINS | 1317 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | 2018-07-25 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000468 |  | 18P000468 | FALSE | CHASS | SL5 WATKINS 1222/1223 PATCH/PAINT |  | WATKINS | 1222 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 13 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000201 |  | 18P000201 | FALSE | CHASS | SL5 ARTS REMOVE COUNTERTOP/SHELVES |  | ARTS | 0106A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 3 | TRUE |  |  | 2017-11-21 | [6 empty] | DL, 6/16/18; Ned to walk, scope and submit plans ASAP…..Sent Paul an email requesting information on Status of Faculty hire status……DL, 7/11/18; Paul is on Jury Duty and he said he should return back to work next week. Current Targe complete date is mid September......DL, 7/25/18; Carpentery and Electrical is complete. Patch and paint has started. Target complete date is 8/3/18......DL, 8/8/18; Space is VAcant and ready for paint. The paint department is working on several other projects that require their attention. The paint department will complete the work in the near future......DL, 8/22/18; This Project is 100% Complete....... |  | Enrico Baez |  | YES | 2018-08-23 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
18P000205 |  | 18P000205 | FALSE | CHASS | SL5 CHASS INT S CREATE DOOR |  | CHASS INT S | 2117H | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-11-27 | [6 empty] | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18……DL, 5/24/18; Plans were approved. WE need to schedule the work…..DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18...........DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... .. DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date..........DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18............DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware.....DL, 9/19/18; This Project is 100% Complete...... |  | Enrico Baez |  | YES | 2018-09-21 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
18P000111 |  | 18P000111 | FALSE | CHASS | SL5 KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 |  | CHASS INT S |  | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Jason Williams |  |  |  | FALSE |  |  | 2017-09-15 | [6 empty] | EB 1/31/18 Work was assigned to lock shop 12/7/17…. DND 5/11: Spoke with Jason, all work complete to be completed as trade is available. Only work remaining is on 3150 A; Jason short staffed to finish project but it's on his radar. 07/13/18 H-FMS: Troubleshoot programming and settings for this controller. Clear all data from panel and reset, perform required downloads, re-test and verify both doors working correctly. |  | Enrico Baez |  | YES | 2018-07-13 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
18P000445 |  | 18P000445 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 |  | ARTS | 225 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 11 | TRUE |  |  | 2018-05-21 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18W001170 |  | 18W001170 | FALSE | CHASS | SL5 ARTS: PAINT CLASSROOMS |  | ARTS | 407 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 27 | FALSE |  |  | 2017-07-25 | [8 empty] | Enrico Baez |  | YES | 2018-09-24 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
19P000364 |  | 19P000364 | FALSE | CHASS | SL5 PATCH AND PAINT |  | CHASS INT S | 3106 | COMPLETE | Juliet McMullin | Cindy Williams | FRANCESCA MOREIRA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-30 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2019-03-15 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
18P000295 |  | 18P000295 | FALSE | CHASS | SL5 CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL |  | CHASS INT S | 2117J | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-02-01 | [6 empty] | DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18……..DL, 5/24/18; Plans were approved. We need to scheudle the work….DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets.......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date.....DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18...........DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware..... |  | Enrico Baez |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000420 |  | 18P000420 | FALSE | CHASS | SL5 COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | Canceled by Customer on prioritization 7/2/18 | WATKINS | 0 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  |  |  |  | Cancel | TRUE |  |  | 2018-04-27 | [10 empty] | YES | 2018-07-02 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000389 |  | 18P000389 | FALSE | CHASS | SL5 PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A |  | PSYCHOLOGY1 | 2122 | COMPLETE | Juliet McMullin | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 5 | TRUE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000396 |  | 18P000396 | FALSE | CHASS | SL5 WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | Please patch and paint these two Political Science Staff Offices in the Watkins Hall 2122 "suite". 2122A belongs to Tanya Wine, FAO; 2122D belongs to Cindy Redfield, Principal Analyst. | WATKINS | 2122 | COMPLETE | Juliet McMullin | Cindy Williams | DAMARIS CARLOS | CINDY REDFIELD | Paul Ditty |  |  |  | TRUE |  |  | 2018-04-13 | [6 empty] | 08/10/18 D-MMN: Completed painting the finish. Pulled our masking and plastic wiped down the furniture. Replaced fixture covers. vacuumed the carpets and moved furniture back.08/07/18 D-MMN: Removed anchors, related boards. Filled holes with spackle and topped with joint compound. used one 4x4 wall patch. Returned and applied second coat of joint compound. 08/09/18 D-MMN: Completed applying primer, and then began applying Suprema. 08/08/18 D-MMN: Removed steel case and file cabinets from walls. Pulled anchors and filled with smooth se 20 and 2 coats of joint compound. Also finished any other patching. Taped the base and fixtures and covered furniture with plastic. Used a fan to dry patching. Sanded patches and began primer. Vacuumed debris. |  | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000418 |  | 18P000418 | FALSE | CHASS | SL5 HMSS OFFICE PAINTING |  | HUM & SOC SC | 2002 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 15 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000417 |  | 18P000417 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTIONAL OFFICE PAINTING |  | HUM & SOC SC | 2106 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000416 |  | 18P000416 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTOR OFFICE PAINTING |  | HUM & SOC SC | 3002 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000415 |  | 18P000415 | FALSE | CHASS | SL5 PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | Door and frame have been painted; construction to commence upon availability of the teams. | OLMSTED | 0 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | RYAN LIPINSKI |  | Dan Lerman |  |  | 10 | TRUE |  |  | 2018-05-08 | [6 empty] | 12/14/18, DL; Angel cancelled this project as it is no longer needed at this time……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 7/11/18; This project was scoped and part of the IRT. Plans and permits are approved. We will schedule the work and we will plan to have this project complet by 9/21/18…..8/10/18; WE have approved plans, this project is scheduled to start late August and will be complete early October……DL, 10/4/18; The door and frame is scheduled for delivery in 3-5 weeks, We will start the project when the doors and frame are on site……..DL, 11/7/18; Door and frame and painted. We will start the contruction in the near future…… |  | Dan Lerman |  | YES | 2018-12-14 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000313 |  | 19P000313 | FALSE | CHASS | SL5 HUMANITIIES SOCSCI - PATCH HOLES & PAINT - |  | HUM & SOC SC | 1203 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-01 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
18P000294 |  | 18P000294 | FALSE | CHASS | SL5 HMSS REMOVE DOOR, INSTALL WALL |  | HUM & SOC SC | 3610 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2018-02-01 | [8 empty] | Enrico Baez |  | YES | 2018-07-16 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000300 |  | 18P000300 | FALSE | CHASS | SL5 ARTS PATCH AND PAINT - DANCE HALLWAYS |  | ARTS |  | COMPLETE | Juliet McMullin | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 24 | FALSE |  |  | 2018-02-02 | [6 empty] | centered. |  | Paul Ditty |  | N/A | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000314 |  | 18P000314 | FALSE | CHASS | SL5 CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR |  | CA MUS PHOTO | 1000 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY PAPAVERO |  | Dan Lerman |  |  | 17 | FALSE |  |  | 2018-02-16 | [6 empty] | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date.......DL, 7/25/18; This project is 100% Complete..... |  | Enrico Baez |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18W016588 |  | 18W016588 | FALSE | CHASS | PATCH AND PAINT FOR FACULTY |  | SPROUL | 4105 | COMPLETE | Juliet McMullin | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | N/A | TRUE |  |  | 2018-06-19 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
20P000142 |  | 20P000142 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 5502 - PATCH AND PAINT FACULTY OFFICE |  | HUM & SOC SC | 5502 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-26 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000141 |  | 20P000141 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4401- PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4401 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-26 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000195 |  | 20P000195 | FALSE | CHASS | SL5 ARTS 0054 - PAINT PIANO LAB |  | ARTS | 54 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-24 | [8 empty] | Paul Ditty |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000140 |  | 20P000140 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4400 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4400 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-25 | [8 empty] | Paul Ditty |  |  | 2019-10-09 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000143 |  | 20P000143 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 6605 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 6605 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-26 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000220 |  | 19P000220 | FALSE | CHASS | SL5 ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT |  | ARTS | 333 | COMPLETE | Juliet McMullin | Cindy Williams | SONJA SEKELY-ROWLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 12/14/18, DL; This project is 100% Complete….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/8/18; Screeen is scheduled to be removed this Friday. We will schedule the installation and the patch / Paint repairs once we receive the repaired screen back from the vendor…….DL, 11/7/18; This project should already be complete. However, The vnedor did not deliver the correct screen. The correct screen is currently scheduled for this Friday..... |  | Enrico Baez |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000237 |  | 20P000237 | FALSE | CHASS | SL5 HMNSS 1202A - PATCH AND PAINT SERVICE |  | HUM & SOC SC | 1202A | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTIAN BACK |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2019-11-22 | [8 empty] | PAUL DITTY | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/14/20. |  | 2020-02-14 | Spring 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000194 |  | 20P000194 | FALSE | CHASS | SL5 WATKINS 1224 - PAINT NEW FACULTY OFFICE ONLY |  | WATKINS | 1224 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-10-17 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/09/20 |  | Paul Ditty |  |  | 2020-01-09 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000575 |  | 19P000575 | FALSE | CHASS | SL5 WATKINS HALL PAINT/FLOORING |  | WATKINS | 1309A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-17 | [6 empty] | 11/26/2019 O-ANS: Paint phase completed per Paul Ditty. Awaiting completion of flooring. |  |  | 01/31/20 O-ANS: Completed per notes as of 09/05/19. |  | 2019-09-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000337 |  | 19P000337 | FALSE | CHASS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | Remove whiteboard (in front of room), mount LED mount, add double duplex and electrical power behind LED, patch and paint wall | PSYCHOLOGY1 | 3210 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 1 | 101 | FALSE |  |  | 2018-10-11 | site visit and schedule the work | 2019-09-16 | 2019-08-30 |  |  |  | 10/1/19, DL; This Project is Complete……………..9/3/19, DL; Space is blocked and schedculed to be completed by 9/27/19…..8/14/19, DL; Conducted site visit with Trades. We will schedule the space to be blocked out and start the work mid September….8/1/19, DL; Planning to start this project in two weeks……7/15/19, DL; I will walk the project in the near future and schedule the work if permits are not required…… | 2019-01-15 | Enrico Baez | Electricians 1. Install behind TV. Provide two duplex outlets and power. Also provide single gang box and conduit for data. Data lines have been run to T-bar in Hallway. 2. Secure loose Extron plate and cover next to TV. Painters 1. Patch and paint wall where TV is mounted | YES | 2019-10-01 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
20P000044 |  | 20P000044 | FALSE | CHASS | SL5 WATKINS 1312 - NEW HIRE RENOVATION - ELIZABETH BERGER | Install drywall over out dated would paneling | WATKINS | 1312 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-07-30 | Install drywall | 2020-01-13 | 2020-02-14 |  |  |  | 2/19/20, DL: This project is Complete…………..1/14/20, DL: We started this project today and should be complete with in 3-4 weeks………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will plan on starting the project the 2nd week in January but will not confirm until we have confirmation from the carpenter shop…………11/18/19 DH: Emailed Status Report to customer……11/11/19, DL: The Material is ordered. The carpenters may start the work the week of 11/18/19………10/30/19, DL: I received confirmation the space is vacant we will schedule the work in the next 6- 8 weeks……10/16/19, DL; The plans are approved and the work is complete. I need to schedule final inspection………. | 2019-09-23 | Enrico Baez | ABATEMENT NEEDED----remove mastic from walls at base on wood paneled wall CARPENTERS 1.) Remove chalk board 2.) Install 1/2" plywood over wood paneled walls. Including over plywood partition separating wall. Do not drywall over trim. 3.) Finish drywall. ELECTRICIANS 1.) Bring out electrical for new drywall and secure when drywall has been installed. PAINTERS 1.) Patch, paint and finish all walls. CUSTODIAL 1.) Clean space after construction. | YES | 2020-02-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000370 |  | 20P000370 | FALSE | CHASS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | SPACE RENOVATION PROJECT | WATKINS | 1311 | PLAN DEVELOPMENT/CHECK | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 2020-02-19 | work on plans and permit | [5 empty] | 1/19/21, DL: We will start working on the plans for this project in the next three weeks. We should have plans to submit for plan check review in the next 5- weeks……….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
19P000664 |  | 19P000664 | FALSE | CHASS | SL5 WATKINS HALL, RM 1343/1343A- PAINT OFFICE AND LAB |  | WATKINS | 1343 & 1343A | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-06-12 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-08 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000361 |  | 19P000361 | FALSE | CHASS | SL5 OLMSTED-PATCH & PAINT/REPLACE CARPET |  | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-29 |  |  | 2019-05-09 |  |  |  | 05/29/19 O-ANS: Project completed 05/09/19 per Paul Ditty. |  | Paul Ditty |  | N/A | 2019-05-09 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000606 |  | 19P000606 | FALSE | CHASS | SL5 PAINT ROOM |  | WATKINS | 1213 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 06/14/19 O-ANS: Stephen spoke with customer Becky Campbell via phone who confirmed that project was going to be canceled due to re-allocation of space by another dept. |  |  |  |  | 2019-06-14 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
18P000481 |  | 18P000481 | FALSE | CHASS | SL5 CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 |  | CHASS INT S | 3104 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000378 |  | 19P000378 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 |  | HUM & SOC SC | 1613 | COMPLETE | Juliet McMullin | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-11-13 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
19P000400 |  | 19P000400 | FALSE | CHASS | SL5 CREATE DOOR INTO HALLWAY | Create a door between the hallway and CHASS INTS 2117A. The door should be placed at the south end of 2117A. | CHASS INT S | 2117A | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 103 |  | FALSE |  |  | 2018-12-06 | [6 empty] | 05/21/19 O-ANS: Canceled by FS per conversation with Paul Richardson and combined with Project 19P000419. | 2019-04-15 | Enrico Baez | Add additional door into space 2117. Door in concrete wall was original location. Would require engineering. Suggest alternate location. | YES | 2019-05-21 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01
19W002930 |  | 19W002930 | FALSE | CHASS | HOLD - SL5 PATCH HOLES & PAINT - HUMANITIIES SOCSCI |  | HUM & SOC SC | 1203 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-08-17 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000585 |  | 19P000585 | FALSE | CHASS | SL5 HUMANITIES SS, RM 3604- PATCH/PAINT WEST WALL |  | HUM & SOC SC | 3604 | COMPLETE | Juliet McMullin | Cindy Williams | DARA CERDA |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-04-19 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
19P000306 |  | 19P000306 | FALSE | CHASS | SL5 HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 |  | CHASS INT N | 4017 | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-01 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000355 |  | 19P000355 | FALSE | CHASS | SL5 HYDRATION STATION FOR THE SECOND FLOOR WATKINS | Hydration station installed where the water fountain is. | WATKINS | 2122D | CANCELED BY FS | Juliet McMullin | Cindy Williams | CYNTHIA REDFIELD |  | Dan Lerman |  | 112 |  | FALSE |  |  | 2018-10-22 | [8 empty] | Enrico Baez |  |  | 2019-04-24 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01
19P000195 |  | 19P000195 | FALSE | CHASS | SL5 HUM & SOC SC-ROOM PAINTING |  | HUM & SOC SC | 2003 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000603 |  | 19P000603 | FALSE | CHASS | SL5 CHASS INT N, RM 3046- PATCH AND PAINT - NEW FACULTY OFFICE |  | CHASS INT N | 3046 | COMPLETE | Juliet McMullin | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  | 12 |  | TRUE |  |  | 2019-05-10 | [6 empty] | 06/18/19 O-ANS: Project complete per updates. 06/15/19 D-MMN: Painted remaining finish. Pulled masking and plastic. Replaced plates and vacuumed. |  |  |  |  | 2019-06-18 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
19P000640 |  | 19P000640 | FALSE | CHASS | SL5 NEW FACULTY - PATCH & PAINT SPROUL 3108 |  | SPROUL | 3108 | COMPLETE | Juliet McMullin | Cindy Williams | MELISA VICARIO |  | Paul Ditty |  | 13 |  | TRUE |  |  | 2019-05-20 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
19P000216 |  | 19P000216 | FALSE | CHASS | SL5 HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT |  | HUM & SOC SC | 1214 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-08-27 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000643 |  | 19P000643 | FALSE | CHASS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH |  | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2019-05-21 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000221 |  | 19P000221 | FALSE | CHASS | SL5 PATCH, PAINTING, AND REGULAR CLEANING OF A126A |  | OLMSTED | A0126A | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000196 |  | 19P000196 | FALSE | CHASS | SL5 PAINT OFFICE AT UNIVERSITY THEATER |  | THTR WKSH |  | COMPLETE | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000171 |  | 19P000171 | FALSE | CHASS | SL5 HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST |  | HUM & SOC SC | 1614 | COMPLETE | Juliet McMullin | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 16 |  | FALSE |  |  | 2018-08-09 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18W016621 |  | 18W016621 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Juliet McMullin | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2018-06-20 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000201 |  | 19P000201 | FALSE | CHASS | SL5 PATCH AND PAINT THE WALLS |  | CHASS INT S | 3111A | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 18 |  | FALSE |  |  | 2018-08-22 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000385 |  | 18P000385 | FALSE | CHASS | SL5 HMSS INSTALL TV IN CONFERENCE ROOM |  | HUM & SOC SC | 1001E | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Dan Lerman |  | 19 | 19 | FALSE |  |  | 2018-03-06 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..12/14/18; Monitor is Complete, we still need to install power. The space is vacant…DL, 6/16/18; Pasted notes from FAMIS; University Writing program wants to install a 65 inch TV in the conference room at HMNSS 1001E. 1. Request to install the TV mount/ bracket on the wall; 2. Request to remove the old projector screen but leave two wood blocks on the wall; 3. Request to add a new double power outlet around the TV bracket area. If you have any questions, please contact Shanshan Liao at (shanshan.liao@ucr.edu or X27753)……DL, 7/25/18; Work orders are not produced. Need to assign and schedule the work…..……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez |  | YES | 2019-03-18 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
20P000002 |  | 20P000002 | FALSE | CHASS | SL5 HMNSS, RM 1212- REMOVAL OF ROLL UP WINDOW |  | HUM & SOC SC | 1212 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-01 | schedule the work | 2020-01-06 | 2020-01-31 |  |  |  | 1/30/20, DL: This project is Complete. We will istall the monitor after IT services installls the Data lines. Michael or Aliosn will notify us when IT is complete and we will schedule th emonitor installation…………1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: This project is in progress and will be complete with in two weeks……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project was delayed. The material is currently ordered. We are planning to start the week of 1/6/20……. 11/19/19 DH: Emailed Status Report to customer….10/30/19, DL; We will plan on scheduling the work shortly after Thanksgiving……….10/16/19, DL: Plans are approved, we will order the material and schedule the work once material is on site. Projected start date is mid November………..9/16/19, DL; Plans will be submitted this week for building permit and plan check review….. | 2019-10-01 | Dan Lerman | Remove Roll up partition. Install outlet and data port, patch and paint walls. | YES | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel | ARTS | 150 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 2020-01-14 | Electrical Engineer design | [5 empty] | 1/19/21, DL: This project will require engineered plans. This is a priority 2 project. We will start the plans and permit process when all priority #1 projects are comple………… |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
20P000004 |  | 20P000004 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - COURTNEY BAKER |  | HUM & SOC SC | 2204 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-07-02 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000419 |  | 19P000419 | FALSE | CHASS | SL5 CHASS INT SOUTH 2117-CARD ACCESS | Remove Door and wall leading to 2117 Media Library and reconfigure to allow enterance into 2117 A & J without having to go through 2117C. | CHASS INT S | 2117 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 12/16/19, DL: This project is now complete…….11/19/19 DH: Emailed Status Report to customer…..11/11/19, The work is 98% Complete. We have one door that we had to send back to the vendor to have it prepared for door hardware. We should have the door back on site with in the next two weeks………..10/30/19, DL: Doors and Frame are on site. The paint team will prime and paint the doors and frame. Once the doors and frame are painted, we will schedule the work……………10/1/19, DL; This Project is 90% Complete. We are waiting on the doors to arrive. Once the doors arrive, we will schedule them to be painted and installed…………..9/3/19, DL; We started this project today. We are planning to be 90% complete by 9/27/19. Note, we have special order doors that have a 4-6 week lead time and that is the reason why we will be only 90% complete on 9/27/19. Paul Richardson is aware of the schedule…….8/15/19, DL; The plans were approved this week, we will order the needed material and start the work very soon…….This is a two part project. We will complete the construction process now. The four doors that need key card access still require a request for proposal and a contract. This portion of the project will take 3- months due to contracts administration, lead time on material and contractor scheduling…….8/1/19, DL; Gunther is working on plans. Once permit is approved, we will schedule the work…. | 2019-03-21 | Enrico Baez | Install 8 position control panel, keyless entry for 2117, 2117A, 2117D and 2117E. ***per Paul Richardson remove 2117G, 2117H and 2117J from request*** !!!!Project to reconfigure wall space, 19P000400 has been combined with 19P000419. !!! | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
20P000145 |  | 20P000145 | FALSE | CHASS | SL5 PSYCHOLOGY 1111 - PATCH AND PAINT FRONT OFFICE WALL |  | PSYCHOLOGY1 | 1111 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-09-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20 |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000214 |  | 20P000214 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | Remove walls and doors in spaces 2139 A,B and C. | PSYCHOLOGY1 | 2nd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-11-07 | Obtain building permit | [5 empty] | 9/30/20, DL: This Project is Complete…………8/5/20, DL: we will submiot plans this week.…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Plans were submitted for a permit on 2/12/20. Once plans are approved, we will order the material and schedule the work……… | 2020-01-10 | Enrico Baez | **************************************SCOPE********************************** 1.) Remove doors, and jambs 2139A, 2139B, 2139C. 2.) Remove drop ceiling in 2139A, 2139B, 2139C and repair as needed. 3.) Remove cabinets in 2139A, 2139B, 2139C. 4.) Remove walls between 2139A & B, and remove walls between 2139B & C. 5.) Change light fixture to match existing. 6.) Repair walls as needed. 7.) Patch and paint as needed. 8.) Replace carpet and base in 2139A, 2139B, 2139C and 2139 common area. 9.) HVAC duct work in individual spaces can be removed and simplified. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000362 |  | 19P000362 | FALSE | CHASS | SL5 PATCH & PAINT/REPLACE CARPET (HALLWAY) |  | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000607 |  | 19P000607 | FALSE | CHASS | SL5 PAINT FACULTY OFFICE |  | WATKINS | 1312 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2019-05-10 | [6 empty] | 08/26/19: Canceled by customer because duplicate of project 20P000044. 08/13/19 O-ANS: Customer scope of work includes more than just PAINT so project added to Fall 2019 list for prioritization by organization. 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18W008762 |  | 18W008762 | FALSE | CHASS | SL5 HUMANITIES: PATCH & PAINT |  | HUM & SOC SC | 2415 | COMPLETE | Juliet McMullin | Cindy Williams | ANDREW ALONSO |  | Paul Ditty |  | 20 | 22 | FALSE |  |  | 2018-01-02 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000126 |  | 18P000126 | FALSE | CHASS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS |  | HUM & SOC SC | 3611 | COMPLETE | Juliet McMullin | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 2017-09-28 | Order material and schedule work | 2019-06-19 | 2019-06-29 |  |  |  | 7/1/19,DL; This project is 100% Complete…..5/15/19, DL; Work is scheduled to start on 6/19/19…….5/1/19, DL; Plans are approved. Need to order material and schedule the work…..3/18/19, DL; Plans submitted to PD&C today…..02/2819, DL; Gunther will work on plans over the next three weeks to submit for a building permit. We will schedule the work if and after the plans are approved. If approved the door and window will more than likely have a 3- month lead time…………….12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez |  | YES | 2019-07-01 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01 | FY 19-20
18P000343 |  | 18P000343 | FALSE | CHASS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER |  | THTR WKSH | 0400A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 2018-03-16 | sheet metal to install handrail | [5 empty] | 11/15/19, DL: This project is complete…..10/30/19, DL: Sheet metal shop fabricated the hand rails. The paint shop will prime and paint the hand rails and the curb. Once the rails are painted, the sheet metal shop will complete the installation…….10/16/19, DL; Cory from the sheet metal shop is aware of the scope of work and they will schedule the work in the near future……..10/1/19, DL; Dan to show Cory from sheet metal the area where a hand rail will be installed for painting backdrops……..07/11/19 O-ANS: Dan and Chris P will walk the space. 05/21/19 O-ANS: Changed to In Progress per meeting with Dan L. Chris P is the PM for further updates. DL and CP will visit after commencement. 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez |  | YES | 2019-11-15 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
19P000173 |  | 19P000173 | FALSE | CHASS | SL5 PAINT/PATCH UNIVERSITY THEATER LOBBY |  | THTR WKSH | 0400A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000215 |  | 20P000215 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | Remove Vaughan wall seperating Olmsted 3349/3351.Add 4 single gang outlets and 2, 2gang outlets. | PSYCHOLOGY1 | 3rd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-11-07 | [6 empty] | 1/19/21, DL: This project is 100% complete…………9/30/20, DL: Plans were approved, we had the Vaughn Wall tested for Asbestos containing material. Once we have the results, we will schedule the work………….8/5/20, DL: We will submit plans by this Friday for a building permit | 2020-02-24 | Enrico Baez | 2/24/2020 E. Baez - 1.Remove Vaughan wall and electrical circuit in wall. 2. Add 4 Single Gan outlets and 2, 2gang outlets. 3. Patch vinyl plank flooring from removed wall and safe. 4. Remove panel in 2249 with wall paper on it next to window. 5. Remove handle set to 3351, install blank, render door inoperable. 6. Repair T-Bar ceiling as needed. 7. Patch and paint walls. 8. Coordinate with ITS for data line for 8 computers. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000063 |  | 19P000063 | FALSE | CHASS | SL5 NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS |  | PSYCHOLOGY1 | 2124 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-07-31 | [8 empty] | Paul Ditty |  | NO | 2018-09-26 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000005 |  | 20P000005 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - KIM FROST |  | HUM & SOC SC | 3215 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-07-02 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000574 |  | 19P000574 | FALSE | CHASS | SL5 FACULTY OFFICE PAINTING |  | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-04-12 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS | 245 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | ANDREA HIDALGO |  | DAN LERMAN |  | 3 |  | FALSE |  |  | 2020-01-02 | plans and permit application | [5 empty] | 1/19/21, DL: This is a priority 3 project. We will start the plans and permit for this project when all priortiy #2 projects are complete…….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
20P000120 |  | 20P000120 | FALSE | CHASS | SL5 OLMSTED 2139 SUITE - PATCH AND PAINT |  | OLMSTED | 2139 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2019-09-05 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/14/20 |  | Paul Ditty |  |  | 2020-01-14 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000356 |  | 19P000356 | FALSE | CHASS | SL5 PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT |  | HUM & SOC SC | 4401 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-24 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000011 |  | 19P000011 | FALSE | CHASS | SL5 PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED |  | PSYCHOLOGY1 | 2111A | COMPLETE | Juliet McMullin | Cindy Williams | LORENA QUINTANA |  | Paul Ditty |  | 4 |  | TRUE |  |  | 2018-07-03 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000112 |  | 20P000112 | FALSE | CHASS | SL5 PSYCHOLOGY 2123 - PATCH AND PAINT JOB |  | PSYCHOLOGY1 | 2123 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-09-04 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Cinvert Basement Library into Piano Lab | ARTS | 54 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 2019-11-19 | srt work when we strt prty 4 pr | [5 empty] | 1/19/21, DL: We will Start the plans, permit and the work once all priority #3 projects…………...11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks……….. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01
19P000371 |  | 19P000371 | FALSE | CHASS | SL5 URGENT PATCH AND PAINT IN CHAIR'S OFFICE |  | HUM & SOC SC | 1213 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-11-05 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000609 |  | 19P000609 | FALSE | CHASS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR |  | WATKINS | 1229 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 07/03/19 O-ANS: Paint phase complete and awaiting flooring change. 06/21/19 O-ANS: Customer requested to remove lighting change from project and only complete paint and carpeting via email to Paul Ditty (copied email below). Will create separate work order for lighting. Re-assigned to Paul Ditty to complete. "From: Becky L Campbell <becky.campbell@ucr.edu> Sent: Friday, June 21, 2019 10:51 AM In regards of the work order: 19P000609 - SL5 - PAINT FACULTY OFFICE – please cancel the connecting Work Order 19W015231 – REPLACING THE LIGHTING IN WATKINS 1229. Please do paint and replace flooring.For the lighting, please create new work order to be done at a later time." |  | Paul Ditty |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000605 |  | 19P000605 | FALSE | CHASS | SL5 PAINT NEW MAILROOM |  | WATKINS | 1320E | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000350 |  | 19P000350 | FALSE | CHASS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | MISC WORK IN ROOMS 3121 AND 1133 Patch and paint-relocate white boards, hang pictures. | PSYCHOLOGY1 | 3121, 1133 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 4 | 3 | TRUE |  |  | 2018-10-17 | Start this Friday. | 2019-08-02 | 2019-08-16 |  |  |  | 8/15/19, DL; This Project is 100% Complete…….. 8/1/19, DL; We will start this project this Friday…… 7/15/19, DL; Appears not plans and permits will be required for the work. I will verify and schedule the work in the near future if no plans or permits are required….. | 2019-04-15 | Enrico Baez | Carpentry: 1. Needs to occur after October 26 2. Remove the whiteboard in 3121, patch and paint 3. Remove Glass board in 1133 and relocate to 3121 (in the same way and place as it was in 1133) 3. Mount pictures on the wall in 3121 4. Secure shelving units in 1133 and 3121 5. There is a ceiling tile in 1133 that is stained and needs to be replaced Painters: 1. Room 3121 Patch and Paint walls | YES | 2019-08-15 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
20P000090 |  | 20P000090 | FALSE | CHASS | SL5 OLMSTED 3345 - PAINT WALL AND FILL HOLES |  | OLMSTED | 3345 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-08-20 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000604 |  | 19P000604 | FALSE | CHASS | SL5 HUMANITIES SS, RM 7704- PAINT OFFICE BY JULY 1, 2019 |  | HUM & SOC SC | 7704 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
20P000172 |  | 20P000172 | FALSE | CHASS | SL5 PYSCHOLOGY 2136B & 2136C - PAINT & PATCH |  | PSYCHOLOGY1 | 2136B & 2136C | COMPLETE | Juliet McMullin | Cindy Williams | ANNIKA KIRMAN | YERAM CHEONG | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-10-10 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000676 |  | 19P000676 | FALSE | CHASS | SL5 PATCH THE PAINT IN THIS OFFICE |  | HUM & SOC SC | 2501 | COMPLETE | Juliet McMullin | Cindy Williams | EVAN ISMAIL |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-06-19 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18P000419 |  | 18P000419 | FALSE | CHASS | SL5 COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | FS to coordinate with client to scope the work. | WATKINS | 1320C&E | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 5 | 8 | TRUE |  |  | 2018-04-27 | [6 empty] | 2/14/19,DL; This project was canceled by Paul R. 2/1/19, DL; We will custom make Sound panels and will start the installation in the next 6-8 Weeks……….. |  | Enrico Baez |  | NO | 2019-02-14 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000421 |  | 19P000421 | FALSE | CHASS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | Install door to access hallway directly | OLMSTED | 2139I | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 5 | 110 | TRUE |  |  | 2018-12-19 | Order material and schedule work | 2020-01-20 | 2020-03-06 |  |  |  | 2/28/20, DL: This Project is Complete….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This Project is 95% complete. We should be complete within the next week…………..1/31/20 O-DHN: Emailed Status Report to customer……1/30/20,DL; Project is in progress and should be complete with in 2- weeks………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will work on the construction schedule and material shortly after the new year. 11/21/19 DH: Emailed Status Report to customer…..10/30/19, DL: Plans are approved. Need to find out the status of the door. We will plan on scheduling the project shortly after Thanksgiving…………10/1/19, DL; Plans are approved. We need to order the door / Frame. Once door is on site, we will schedule the work……..9/16/19, DL; Plans are submitted for the permit review process……9/3/19, DL; Plans are at 50%. We will try and have plans to submit for review within the next two weeks…… | 2019-02-05 | Enrico Baez | *****This work is being performed to accommodate new faculty scheduled to arrive July 1, 2019***** Core work falls under SLA Carpenters • Open wall between corridor and 2139I. • Install metal frame and solid core door similar to 2139. Smoke and draft gasket. • Install carpet patch at threshold of new door. Carpet should match or complement existing carpet. • Remove bulletin board in hallway to facilitate doorway construction and relocate on same wall. See photos in shared drive.. • Replace base boards as needed. Painters • Prime, Patch and Paint walls, doors and trim. • Paint to match existing wall colors. Lock Shop • Furnish and install 1 each, ADA compliant handle sets, match existing hardware. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
19P000357 |  | 19P000357 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS, TIME SENSITIVE |  | HUM & SOC SC | 1302 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-10-25 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000171 |  | 20P000171 | FALSE | CHASS | SL5 CHASS INTN 2107 - PATCH UP HOLES IN THE WALL |  | CHASS INT N | 2017 | COMPLETE | Juliet McMullin | Cindy Williams | GENEVA AMADOR |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-10-10 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/03/20 |  | Paul Ditty |  |  | 2020-01-03 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000314 |  | 19P000314 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Juliet McMullin | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
18P000444 |  | 18P000444 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 |  | ARTS | 242 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-05-21 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-21 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000674 |  | 19P000674 | FALSE | CHASS | SL5 HMSS RM 2416 OFFICE ROOM PATCH AND PAINT |  | HUM & SOC SC | 2416 | TO BE PERFORMED BY PD&C | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-06-19 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-23 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000642 |  | 19P000642 | FALSE | CHASS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM |  | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-05-21 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000082 |  | 20P000082 | FALSE | CHASS | SL5 HUMANITIES THEATRE - PATCH & PAINT |  | THTR WKSH | 405 | COMPLETE | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-08-15 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000207 |  | 19P000207 | FALSE | CHASS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-08-23 | working on plans | 2019-06-03 | 2019-06-28 |  |  |  | 8/1/19, DL: This project is 100% Complete……7/15/19, DL; Floor covering will be installed next week. Floor covering is the last item for this project……..7/1/19, DL; This project is 95% complete except floor covering. Floor covering will be installed within 2- weeks……6/17/19, DL; This project is making good progress. We should be complete near July 1st…….5/31/19, DL; This project started this week and should be complete by June 28th…….3/18/19, DL; Working on plans and we will submit our plans and permit application this week….. | 2018-09-20 | Enrico Baez |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
19P000300 |  | 19P000300 | FALSE | CHASS | SL5 HUM & SOC SC--URGENT: PAINT AND PATCH WALLS |  | HUM & SOC SC | 4403 | COMPLETE | Juliet McMullin | Cindy Williams | ANDREA HERAZ |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000204 |  | 20P000204 | FALSE | CHASS | SL5 ARTS 166 - PATCH AND PAINT IN LOBBY AND GREEN ROOM |  | ARTS | 166 | COMPLETE | Juliet McMullin | Cindy Williams | ALBERT FETTER |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-10-31 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/20/19 |  | Paul Ditty |  |  | 2019-12-20 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000552 |  | 19P000552 | FALSE | CHASS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS |  | HUM & SOC SC | 1001 B, C, and D | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-03-27 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000194 |  | 19P000194 | FALSE | CHASS | SL5 PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 |  | HUM & SOC SC | 3304 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000226 |  | 20P000226 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 3401 - OFFICE PATCH AND PAINT |  | HUM & SOC SC | 3401 | COMPLETE | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON | TRACY AVERY | Paul Ditty |  | 8 |  | TRUE |  |  | 2019-11-18 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/03/20. |  | Paul Ditty |  |  | 2020-02-03 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000448 |  | 19P000448 | FALSE | CHASS | SL5 ARTS 333- PATCH AND PAINT |  | ARTS | 333 | COMPLETE | Juliet McMullin | Cindy Williams | SONJA SEKELY-ROWLAND |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-01-14 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-04 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000589 |  | 19P000589 | FALSE | CHASS | SL5 HMSS OFFICE 3405 RENOVATIONS | Construct partion, pending CBO approval, in room 3405. | HUM & SOC SC | 3405 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2019-04-23 | Install carpet | 2019-09-01 | 2019-11-15 |  |  |  | 11/19/19 DH: Emailed Status Report to customer…..11/19/19 DL: This project is complete….11/11/19, DL: The carpet is delayed and scheduled to be instlled on Friday, 11/15/19. The project will be complete once the carpet is installed……10/30/19, DL: This project is 90% Complete. We are planning to install carpet next week………..10/16/19, DL; This project is 80% complete. Target complete date is 3- weeks…..10/3/19 O-ANS: Updated status per minor reno meeting…. 10/1/19, DL; This project is in progress. We will call for rough electrical inspection….. 9/16/19, DL; We are ready to schedule the work. We are currently waiting for the space to be vacated. Once the space is vacant, we will start the project……9/3/19, DL; We are ready to start the work. The PI returned to work this week. I sent Paul R. an email letting him know we are available to start once we have confirmed dates from him…..8/15/19, DL; Plans are approved but the PI is not. We will probably start the project the 2nd week in September…… | 2019-06-27 | Enrico Baez | CARPENTERS: 1. Construct partition above T-bar ceiling, full height not required. Drywall 5/8" tape and finish. 2. Remove and store three book cases. 3. Cut in opening for 36" (stain grade to match) door in general area of were bookcases were in South wall leading to corridor. Painters: 1. Patch and paint as needed Electricians: 1. Isolate existing switches to control to operate lights in West half of partitioned space. 2. Install two additional switches in East partition. 3. Install additional single gang outlets one on each side of new partition. Telecom: 1. Install additional Voice and data connection in Western side of partitioned space. Flooring: 1. Remove carpet and base. 2. Install new customer selected base and flooring. HVAC: 1. Separate existing duct work from one to two zones controlled by separate stats in each office. | YES | 2019-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000286 |  | 19P000286 | FALSE | CHASS | SL5 FACULTY OFFICES: TOUCH UP PAINT |  | HUM & SOC SC | 2005 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-09-17 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000094 |  | 20P000094 | FALSE | CHASS | SL5 ARTS 0221 -PAINT OFFICE |  | ARTS | 221 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-08-22 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000232 |  | 20P000232 | FALSE | CHASS | SL5 PSYCHOLOGY 3111B - WALL PATCH FOR SMALL HOLES IN THE WALL |  | PSYCHOLOGY1 | 3111B | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-11-20 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000061 |  | 19P000061 | FALSE | CHASS | SL5 PSYCHOLOGY 1111H-PATCH HOLES IN WALL |  | PSYCHOLOGY1 | 1111H | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000608 |  | 19P000608 | FALSE | CHASS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE |  | WATKINS | 1345 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-27 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000429 |  | 19P000429 | FALSE | CHASS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | Patch & Paint | COLL BLDG NO | 103 | COMPLETE | Juliet McMullin | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-01-03 | [6 empty] | 07/26/19 O-ANS: Project complete per Paul Ditty. 06/06/19 O-ANS: Project scheduled to be completed. |  |  |  |  | 2019-07-26 | SPRING 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000540 |  | 19P000540 | FALSE | CHASS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | Remove metal roll up window, replace carpet, remove round column cover-reframe square. | HUM & SOC SC | 1202 | COMPLETE | Juliet McMullin | Cindy Williams | MICHAEL MOLINAR |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2019-03-20 | Plans and permit | 2020-01-06 | 2020-02-14 |  |  |  | 2/18/20, DL: Thois project is 100% Complete…….1/31/20 O-DHN: Emailed Status Report to customer…..1/30/20, DL; Project is 95% complete. We will install carpet this weekend………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is in progress and should be complete within 3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project was delayed. Material is ordered. We are currently scheduled to start shortly after 1/6/20………..11/19/19 DH: Emailed Status Report to customer…..10/30/19, DL: We will plan on scheduling the project shortly after Thanksgiving……….. 10/16/19, DL; Plans were approved, we will work on ordering material and schedule the work. Anticipated start date is mid-November…….10/1/19, DL; Plans were submitted last week. Once plans are approved, we will schedule the work…………9/16/19, DL; Plans are 90% Complete. We will submit plans for plan check review in the next two weeks……. 8/15/19, DL; Gunter has the project on his list. We will try and be ready for plan check review in the next two weeks…….. | 2019-07-25 | Enrico Baez | 7/1/2019 E. Baez Carpenters: 1. Remove roll up partition and stainless steel counter top. 2. Frame opening, hang drywall, tape and finish 3. Remove round decorative column from support pillar. 4. Frame over column for square foot print. Keep as narrow as possible. 5. Hang drywall, tape and finish. Painters: 1. Paint all new construction Flooring: 1. Remove carpet and base in 1202, lobby area of 1220 and hallway. Refer to drawing. 2. Replace customer selected carpet and base. | YES | 2020-02-18 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000226 |  | 19P000226 | FALSE | CHASS | SL5 PAINT OFFICE HMNSS 3304 |  | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-08-28 | [8 empty] | Paul Ditty |  |  | 2018-10-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000213 |  | 20P000213 | FALSE | CHASS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS |  | CHASS INT S | 2117A, 2117C, 2117D, 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-11-08 | approved permit | 2020-03-03 | 2020-03-21 |  |  |  | 8/5/20, DL: This Project is Complete……………..2819/20 O-DHN: Emailed Status Report to customer…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have a contract, we will order the material and schedule the work………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Plans are complete and submitted for building permit. We are also working on the contract. Once the plans are approved and the contract is complete, we will schedule the work………. |  | Enrico Baez |  |  | 2020-08-05 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21 | 1
19P000568 |  | 19P000568 | FALSE | CHASS | HOLD SL5 HMSS HANG WHITE BOARD, TV MOUNTING, PATCH AND PAINT | Remove Glass White Board, mount TV, patch and paint | HUM & SOC SC | 1214 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-04-09 | [8 empty] | Enrico Baez | No scope |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000211 |  | 20P000211 | FALSE | CHASS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | Install keyless entry system for door to Arts Building RM 54 | ARTS | 54 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 | R3 | FALSE |  |  | 2019-11-07 | [6 empty] | 1/19/21, DL: Enrico will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment installation. 8/5/20, DL: This Project is on hold until further notice……. | 2020-01-20 | Enrico Baez | 1/19/21, EB: Per Paul R., This project is canceled………….Provide new panel, power supply and door hardware for 2 doors. Prox reader only. | YES | 2021-01-19 | Winter 2021 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21 | 1
20P000183 |  | 20P000183 | FALSE | CHASS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | Install side walk | HUM & SOC SC | 1202 | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2019-10-18 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Also Existing door is compliant and there are other accessible exits to the building… 8/5/20, DL: This Project is on hold until further notice……. | 2019-11-13 | Enrico Baez | Construct Side walk. ADA compliance not required. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21 | 1
20P000446 |  | 20P000446 | FALSE | CHASS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. | CHASS INT N | 4047 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-04 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
20P000464 |  | 20P000464 | FALSE | CHASS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) | HUM & SOC SC | 3001 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
21P000111 |  | 21P000111 | FALSE | CHASS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. | WATKINS | 2144 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-11-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
21P000109 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Dr. Robert Clark. He started working July 1, 2020. | WATKINS | 1146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-11-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUM & SOC SC | 3210 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-24 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
20P000403 |  | 20P000403 | FALSE | CHASS | SL5 OLMSTED 232 - PAINT OFFICE | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). | OLMSTED | 2321 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | MELISA VICARIO | Paul Ditty |  | X |  | TRUE |  |  | 2020-03-13 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
20P000469 |  | 20P000469 | FALSE | CHASS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. | ARTS | 222 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | SUSAN KOMURA | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-23 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
20P000463 |  | 20P000463 | FALSE | CHASS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 | HUM & SOC SC | 2000 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
20P000453 |  | 20P000453 | FALSE | CHASS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | Paint Only - Please patch/paint to existing color office for faculty new hire. | ARTS | 142 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
21P000110 |  | 21P000110 | FALSE | CHASS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. | WATKINS | 2146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-11-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
3535 | 3535 |  | FALSE | CHASS | Life Sciences 452 Renovation | This request is for a new faculty hire. -Remove north countertop and sink. Install stainless counter and two sinks. -Install eye wash station -Install laminate flooring, remove existing. (Abatement) -Paint space to campus interior standard. -Remove east counter and replace with stainless. -Remove fume hood, discard. -Install new fume hood. | LIFE SCIENCE | 452 | Construction | Juliet McMullin | Cindy Williams | Paul Richardson |  | Tameesha Hayes | 1 |  |  | FALSE | 133500 |  | 2019-07-10 | Complete Construction | 2020-10-01 | 2021-02-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [12 empty] | PD&C | FALSE | 2017 | 2021-02-01
3557 | 3557 |  | FALSE | CHASS | Campus Sculpture Installation | We will bring 5 sculptures to campus that will go in public places that have already been identified by Uma Ramasubramanian and Jacqueline Norman . Please construct 5 concrete plinths at various locations around campus. Locations are on the attachment. |  |  | Construction | Juliet McMullin | Cindy Williams | Emily Rankin |  | Tameesha Hayes | 3 |  |  | FALSE | 82000 |  | 2019-11-27 | Complete Construction | 2020-10-01 | 2021-03-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | On Hold (COVID-19) | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 2018-06-22 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2018 | 2021-02-01
19P000319 |  | 19P000319 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB |  | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000058 |  | 19P000058 | FALSE | CNAS | SL5 Assess Feasiblity of Removing/Replacing Growth Chambers |  | GH18 | 18 | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-28 | [6 empty] | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing...DL, 5/9/18; Project is scoped. Need to schedule the work.....Plumbers and HVAC are working on this. Still need to have electrical removed. I am working wiht Patty on who can do the demo and removal.....DL, 7/11/18; I need to check in with Ken to see if refrigerant is recovered. will isue work order to disconnect electrical..... I checked in with our campus surplus and do not have any contacts to dis,matel the very large growth Chambers. I need to inform Patty and suggest that she have Burges demo and move the Growth Chambers......We will be complete with our portion of this project before 8/1/18.......DL, 8/10/18; All work is done except the disconnect for electrical. I need to check and see if the electrical. Per FAMIS complete on 8/22/18 |  |  |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000287 |  | 19P000287 | FALSE | CNAS | SL5 URGENT: PAINT SHOP TO PATCH AND PAINT |  | MAT SCI ENGR | 229 | COMPLETE | Kathryn Uhrich | TBD | HONG XU |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-19 | [8 empty] | Paul Ditty |  |  | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19W007474 |  | 19W007474 | FALSE | CNAS | SL5 BG - RAILROAD TIE WALLS | Repair Railroad Ties at Botanic Gardens | BOTAN INFO C |  | CANCELED BY FS | Kathryn Uhrich | TBD | AMBER RHEMREV | [5 empty] | FALSE |  |  | 2018-11-07 | [7 empty] | 2018-12-10 | Ron Veloz | Request For "ESTIMATE" to repair the raillroad ties used as a retaining wall at botanic gardens. | YES | 2019-03-11 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
18W011692 |  | 18W011692 | FALSE | CNAS | SL5 ENTOMOLOGY; PAINT/PATCH LAB |  | ENTOM MUSEUM | 211 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-03-08 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000346 |  | 19P000346 | FALSE | CNAS | SL5 I&Q--PAINTING ROOMS IN THE I&Q |  | EAST I&Q FAC |  | COMPLETE | Kathryn Uhrich | TBD | IMAD BAYOUN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2019-01-09 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
18W011161 |  | 18W011161 | FALSE | CNAS | SL5 REPLACE CARPET |  | SCIENCE LAB1 | 301 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-23 | [6 empty] | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project……DL, 5/21/18; Floor covering is selected. Work will be scheudled for Mid June….DL, 5/24/18; The install is scheduled for June 18th & 19th……DL, 7/11/18; This Project is 100% Complete...... |  | Dan Lerman |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000434 |  | 18P000434 | FALSE | CNAS | SL5 BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY |  | BOYCE | 4478 | COMPLETE | Kathryn Uhrich | TBD | CHERYL GERRY |  | Paul Ditty |  |  | 3 | TRUE |  |  | 2018-05-09 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18W000455 |  | 18W000455 | FALSE | CNAS | SL5 CHAPMAN CLEAN WINDOWS |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  |  | 37 | FALSE |  |  | 2017-07-11 | [6 empty] | Dl, 7/4/18; All Windows in Chapman were cleaned by Ductch Touch. This Project is 100% Complete |  | Ron Veloz |  | YES | 2018-07-11 | Summer 2018 | FS | FALSE | 2017 | 2021-02-01
18W011672 |  | 18W011672 | FALSE | CNAS | SL5 ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY |  | ENTOMOLOGY | 268 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-03-08 | [6 empty] | Relocate white board from East wall onto the West wall, where high table was removed, 24" away from North end of wall. |  | Paul Ditty |  | N/A | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000292 |  | 18P000292 | FALSE | CNAS | SL5 SKYE HALL PAINT MULTIPLE FACULTY OFFICES |  | SKYE HALL | 228 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000185 |  | 19P000185 | FALSE | CNAS | SL5 NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE |  | PIERCE | 206 (originially identified as Room 204) | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  |  | 6 | TRUE |  |  | 2018-06-18 | [6 empty] | 12/14/18, DL; This project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Pending glove box relocation to rm 319 and minor vent reconfiguration. Both tasks will be performed afet the glove boxes relocate to rm. 319. 10/29/18 All project related work is completed. |  | Ron Veloz |  | YES | 2018-12-14 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000213 |  | 19P000213 | FALSE | CNAS | SL5 NEEDS FOR NEW WALL DISPLAY (MONITOR) | Duplicate request to 19P000031; Work to be completed on other project. | BIOLOGIC SCI | 3101 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [11 empty] | 2018-10-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000186 |  | 19P000186 | FALSE | CNAS | SL5 NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION |  | PIERCE | 319 | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-06-18 | [6 empty] | Pending gas line installation scheduled for the week of 09/24 per Steve Burleson. Move glove boxes from 206 to Rm 319 after gas line are installed. All work is complete |  | Ron Veloz |  | YES | 2018-11-08 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000392 |  | 18P000392 | FALSE | CNAS | SL5 BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 |  | BATCHELOR | 0 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Paul Ditty |  |  | 8 | TRUE |  |  | 2018-04-12 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000189 |  | 19P000189 | FALSE | CNAS | SL5 PHYSICS- WALL HOLES PATCH | Duplicate work order to 19P000049. Work to be completed on other project. | PHYSICS | 3036 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | JAZMIN CHAVEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-16 | [10 empty] | NO | 2018-10-18 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000287 |  | 18P000287 | FALSE | CNAS | SL5 SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  |  | 33 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19/18; This project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000227 |  | 18P000227 | FALSE | CNAS | SL5 BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL |  | BATCHELOR | 4128 | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-12-12 | [6 empty] | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM.......DL, 5/24/18; Need to work on plans and permits. Project needs to be complete before Fall academic 2018.....DL, 6/16/18; Walked project with Jess. and he will schedule the abatment. We will not need plans for this project. We are not removing the exhasut hood which was the original purpose foor the plans......Carpenters started the demo. Still need to remove TSI. Once TSI is removed, we can schedule the plumbing work. Target Complete Date is 9/21/18....DL, 8/10/18; Abatement is scheduled for this weekend, we will start work soon.....DL, 8/22/18; Abatement and most demo complete. Still on track for 9/21/18.....DL, 9/19/18; Scope change. This project should be complete on 9/28/18.......DL, 10/4/18; Floor to be installed this Friday. Pianters will finalized the stain on the cabinets. Thsi project should be complete near 10/19/18.......Dl, 11/7/18; This project is 100% complete.... |  | Dan Lerman |  | YES | 2018-11-08 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
18P000288 |  | 18P000288 | FALSE | CNAS | SL5 SKYE HALL OFFICE SUITE PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000027 |  | 18P000027 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT LAB |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-05 | [6 empty] | 2/1/19, DL; This project is 100% Complete……………DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again…… DL, 4/2/18; This space is still on schedule for 7/1/18 completion date…..FAMIS work orders have been produced…..DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th…..TEST TEST |  | Dan Lerman |  | YES | 2018-07-12 | Fall 2017 | FS | FALSE | 2018 | 2021-02-01
18P000293 |  | 18P000293 | FALSE | CNAS | SL5 SKYE HALL COPIER ROOM PATCH AND PAINT |  | SKYE HALL | 278 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  |  | 32 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000247 |  | 18P000247 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 |  | PHYSICS | 3023 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Paul Ditty |  |  | 15 | FALSE |  |  | 2017-12-20 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Spring 2018 | FS | FALSE | 2017 | 2021-02-01
18P000296 |  | 18P000296 | FALSE | CNAS | SL5 SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES |  | SKYE HALL | 266 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  |  | 31 | FALSE |  |  | 2018-02-02 | [6 empty] | 01/17/19, DL; This project was completed last summer……..DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19 18; I neeed to check on this work order. I thought it was part of the 2nd floor Hallway project but it was not…… |  | Dan Lerman |  | YES | 2019-01-01 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000118 |  | 18P000118 | FALSE | CNAS | SL5 OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT |  | OLMSTED | 1337 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2017-09-20 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space.......DL, 6/16/18. New staff member schedule to start mid july. BKM is also scheduled for mid july. This project will require cabinets to be removed, new carpet, paint and blank out electrical outlets that will no longer be used.. new signage too.....DL, 7/11/18;This project is in progress. Complete date is 7/20/18......DL, 7/25/18; This project is 100% Complete....... |  | Dan Lerman |  | YES | 2018-07-25 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
18P000312 |  | 18P000312 | FALSE | CNAS | SL5 URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 |  | PARKING LOT P 42 |  | CANCELED BY FS | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  |  | 38 | FALSE |  |  | 2018-02-13 |  | 2019-02-04 | 2019-04-16 | [5 empty] | Enrico Baez |  | YES | 2018-09-19 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000256 |  | 18P000256 | FALSE | CNAS | SL5 BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES |  | BOYCE | 3451 | COMPLETE | Kathryn Uhrich | TBD | CHERYL GERRY |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave at Webber is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place.......DL, 5/9/18; Autoclave is destroyed. Pictures were sent to Cheryl. We are now waiting for the equipment to arrive. Steve B is working on Steam connection at Boyce......DL, 5/24/18; Autoclaves arrived. Day crew is scheduled to deliver the unit on 5/30/18. we will schule the plumbers and electricians shortly there after......DL, 6/16/18; Webber Autoclave is almost complete. This portion should be complete next week. WE will run the Webbber autoclave for two weeks before we start the Boyce Autoclave. The weldolet for the BOyce unit will be installed during the steam shutdown...... DL, 7/11/18; Webber Auto clave will be complete on 7/12/18. We will start the demo of the Boyce Auto clave next soon. Target date for this project is 8/10/18...... DL, 7/25/18; We had a delay with the Webber autoclave which will implact the Boyce Auto clave. New target complete date is 8/22/18.....DL, Plumbing is almost complete, need to schedule final elctrical and Commission equipment. Target date 8/31/18...... DL, 9/6/18; This project should be complete but we still need to schedule the electrical connections ASAP.........DL, 9/19/18; This project is 100% Complete. |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2017 | 2021-02-01
18P000028 |  | 18P000028 | FALSE | CNAS | SL5 CHAPMAN PATCH AND PAINT |  | CHAPMAN | 0010A | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced .......DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th.....Test test |  | Dan Lerman |  | YES | 2018-07-12 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
18P000029 |  | 18P000029 | FALSE | CNAS | SL5 CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS |  | CHAPMAN | 1 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain......DL, 5/24/18; This work is scheduled to be complete on or before 7/1/18.....DL, 6/16/18; Blinds are delayed to mid July but window clenaning is still on schedule......DL, 7/11/18; This Project is 100% Complete |  | Dan Lerman |  | YES | 2018-07-11 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
18P000341 |  | 18P000341 | FALSE | CNAS | SL5 PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL |  | PHYSICS | 1132 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-14 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process…DL, 6/16/18; Jess tested the matreial flooring and paint is hot. Jess will abate before we proceed with the project….Still need to scheudle the work. This project target complete date is late Fall……DL, 7/25/18; Jess sent out the 14-day notification to the AQMD last week. We will start the balance of the project after the ACM and Lead is abated or encapsulated…..8/10/18; Abatement is complete. We will work on the other items as time permits. This space is vacant with no occupancy date |  | Dan Lerman |  | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000356 |  | 18P000356 | FALSE | CNAS | SL5 ENTOMOLOGY PATCH AND PATCH |  | ENTOMOLOGY | 278 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  |  | 10 | TRUE |  |  | 2018-03-20 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000310 |  | 18P000310 | FALSE | CNAS | SL5 ADD INTERCOM/BUZZ IN SYSTEM |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-12 | [6 empty] | Dl, 7/4/18; This project is scoped. This will be a new ADA operator, door bell / Intercom and buzzer button to unlock door. Walked work with Contractor, need to work on producing contract with PD&C. Once Contract is confirmed, we will schedule the work..... DL, 7/11/18; We have the proposal. Need to execute the agreement and schedule the work. The target complete date is before 10/1/18.....Dl 8/10/18; Jason will try and complete the work with in the next three weeks......DL, 8/22/18; Jason order parts, parts have 6-8 week lead time. Work will be scheduled when material arrives.....DL, 10/4/18; This Project is 100% Complete....... |  | Dan Lerman |  | YES | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000117 |  | 18P000117 | FALSE | CNAS | SL5 PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION |  | WEBBER | 1303 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-21 | [6 empty] | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work....DL, 5/9/18; Produced work order for JEss to test for lead paint and ACM....Von wall is hot, everything else is good to go. I will schedule the work soon. The space is vacant......DL, 7/11/18; This project is in progress. Target Complete Date is 8/10/18....DL, 7/25/18; Vinyl plank and bullitin boards the balance of the task for this project. Still on target for complete on 8/10/18.....DL; 8/10/18; We were schedule to install the fllor and identified Asbestos,. Jess is working on the propsal and schedule for the abatment. This will require a 14- dat notification to the AQMD. This space is vacant with no scheduled move in date......DL, 8/22/18; Abatment is scheduled for this Tursday and Friday. We will scheule the carpet in dry errase boards for next week.Target complete date will be 8/31/18.....DL, 9/6/18; This project is 100% Complete...... |  | Dan Lerman |  | YES | 2018-09-10 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
18P000030 |  | 18P000030 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT FROM WATER DAMAGE |  | CHAPMAN | 100 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete..... |  | Dan Lerman |  | YES | 2018-11-08 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
20P000185 |  | 20P000185 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR (OFF WHITE) |  | PHYSICS | 3004S | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-18 | [6 empty] | 11/01/19 O-ANS: Canceling bc duplicate of 20P000187. Paul Ditty to speak with customer re: room. |  | Paul Ditty |  |  | 2019-11-01 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000187 |  | 20P000187 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR |  | PHYSICS | 3004S | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-23 | [8 empty] | Paul Ditty |  |  | 2019-11-05 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000220 |  | 20P000220 | FALSE | CNAS | SL5 SPIETH-NEW CLOSING/SECURITY MECHANISM FOR LOADING DOCK DOORS |  | SPIETH |  | CANCELED BY CLIENT | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | - |  | FALSE |  |  | 2019-11-14 | [8 empty] | Ron Veloz |  |  | 2019-11-22 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000390 |  | 19P000390 | FALSE | CNAS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  | 0 |  | TRUE |  |  | 2018-11-29 | Order material and schedule work | 2019-06-01 | 2019-06-28 |  |  |  | 7/1/19, DL; This project is 100% Complete…………6/17/19, DL; material is ordered. This project should be complete by July 1st…..5/31/19, DL; Plans were apprvied this week we will work on the contract and hopefully have the notice to proceed in the next two weeks. It is our goal to have the work complete on or before July 1st……5/15/19, DL; Need to order the special order door and frame…. | 2019-02-07 | Ron Veloz | Install new aluminum storefront door, frame and side lite(requested by Dan L.), patch & paint door opening and west interior wall. | YES | 2019-07-01 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
19P000358 |  | 19P000358 | FALSE | CNAS | SL5 GEOLOGY - ACCOMMODATION REQUEST |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-10-26 | Plans and Permits were submitted | 2019-02-14 | 2019-04-12 |  |  |  | 4/15/19, DL; This Project is 100% Complete……. 3/28/19, DL; Plans are approved. We will start the work on 4/1/19……3/18/19, DL; Waiting for approved plans from building official……2/28/19, DL; Plans were submitted to building official for review. Once plans are approved, we will schedule the work………..2/14/19, DL; Plans are in process and we will apply for building permit next week………….. | 2019-02-07 | Ron Veloz | SOW: Installation of Charging station Power Point of connection, concrete drive and charge station pad. Landscape: Clearing, cap and relocate irrigation lines and sprinklers. Replant vegetation as needed. Demolition: Concrete saw cutting curb Concrete: Excavation, form-work, place and finish concrete pad approx. 10'x10'. Signage: Provide the appropriate signage identifying parking designation, pavement markings-striping marked in front of the drive Electrical: Provide an Electrical POC and weather proof enclosure for the new cart charger. NOTES: Title changed to PHYSICS on 02/07/19, FORMERLY TITLED GEOLOGY BLD ACCOMMODATION REQUEST | YES | 2019-04-15 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000449 |  | 19P000449 | FALSE | CNAS | SL5 PAINT OFFICE AREA OF 229A FOR RELOCATION |  | FAWCETT LAB | 229A | COMPLETE | Kathryn Uhrich | TBD | CHERYL GERRY |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-01-14 | [6 empty] | 04/05/19 O-ANS: Project complete per Paul Ditty and closed in FAMIS. |  |  |  |  | 2019-04-05 | Winter 2019 | FS | FALSE | 2019 | 2021-02-01
19P000505 |  | 19P000505 | FALSE | CNAS | SL5 CHAPMAN HALL PAINT OFFICE WALL WHERE BOOK CASE WAS REMOVED |  | CHAPMAN | 10B | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-02-25 | [6 empty] | 05/10/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-05-10 | Winter 2019 | FS | FALSE | 2019 | 2021-02-01
19P000298 |  | 19P000298 | FALSE | CNAS | SL5 SPIETH - PREP LAB FOR FACULTY SEARCH |  | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-09-26 | work is in progress | 2019-02-14 | 2019-04-30 |  |  |  | 5/15/19, DL; This Project is 100% Complete… 5/1/19, Dl; This project will be complete next week…..4/15/19, DL; We are making good progress on this project and we should be complete the first week in May……..3/28/19, DL; This project is in progress and should be complete by or near May 1st….2/14/19, DL; Need to schedule trades and obtain quotes to refinish countertops…… |  | Ron Veloz | 12/13/18 O-RVL: Ron V was informed of this project by D. McWilliams on 12/12/18. RV reviewed the request and noticed it was assigned to Paint. RV changed to O-RVL for scoping for new faculty. RV added revised scope (12/13)of work provided by D.McWilliams email on 12/10. See below. REVISED SOW 1363 & 1364 Spieth 1363 Wet Lab Space Note: There is evidence in the ceiling and along one wall of a water intrusion issue, i.e. peeling paint, leaking and rusted pipes, etc. The cause of this damage needs to be investigated and repairs confirmed, including painting the wall and ceiling where damage is visible. Patch/paint Re-finish, re-surface the existing cabinets Re-finish and/or replace bench-tops If both sinks cannot be significantly cleaned, they should be replaced Replace faucets at both sink locations. Clean existing Chemical fume hood Repair or replace self-closing chemical / flammables storage cabinet On one bench remove overhead shelving unit and relocate electrical outlets to the ends of bench to accommodate large desktop equipment. Cap off remaining utilities for potential use/re-connection in the future. Remove shelves on west wall to accommodate siting of large floor-standing equipment before patch and painting. Also, add 120/240 electrical outlets (raceway) along this wall. Replace flooring -- this depends on what we decide about removing the walk-in fume hood listed below Add GFCI outlets near water sources Requires a connection to a DI water system Other utilities are required in this room and at what locations, e.g. air, oxygen, gas, vacuum, etc.? Remove existing walk-in Fume Hood (if cost for this issue does not trigger project over $50k)Please assess/cost out and advise prior to project. Spieth 1364 Lab Support Space Patch/paint, Re-finish, re-surface the existing cabinets (non-porous surface) Re-finish and/or replace bench-tops If sink cannot be significantly cleaned, they should be replaced Replace faucets at sink location. Add GFCI outlets near water sources Requires a connection to a DI water system | N/A | 2019-05-15 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000440 |  | 19P000440 | FALSE | CNAS | SL5 GH#21--INSTALLATION OF GROW POD BEHIND GREENHOUSE #21 |  | GH21 |  | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER | PATRICIA SPRINGER | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-08 | Install under ground utilites | 2019-04-01 | 2019-05-31 |  |  |  | 5/31/19, DL; This project is 100% complete :)……5/15/19, DL; Project is complete except for chain link fence. Fence will be installed some time early next week…….5/1/19, DL; Grow Pod is installed with power and water. Still need to install fence and door lock….. 4/15/19, DL; Grow Pod is scheduled for delivery this Thursay. Once on site, we will connect all utilities and this project will be complete. 2/28/19, DL; Demo is complete. We need to veify utilitiy point of connections. Once utilities are verified, we will install the water and power……. |  | Dan Lerman |  |  | 2019-05-31 | Winter 2019 | FS | FALSE | 2019 | 2021-02-01
19P000639 |  | 19P000639 | FALSE | CNAS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK | Make modifications to accommodate new PI | CHEMICAL SCI | 0435 | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-17 | finish electrical and plumbing.. | 2019-10-31 | 2019-12-06 |  |  |  | 12/16/19, DL: This project is complete…11/19/19 Emailed Status to customer….11/11/19, DL: This project is 90% Complete. We should be complete with the balance of the work in the next two weeks…………10/30/19, DL: This project is in progress and should be complete in 3- weeks……..10/16/19, DL; We will start the work in the next two weeks. 9/16/19, DL; We will start working on the plans in the next 3- weeks and submit them for plan check review. Once approved, we will schedule the work……..9/3/19, DL; Need to verify scope with Ron and start working on plans. Will start plans in the next two- three weeks…… | 2019-07-19 | Ron Veloz | For new Faculty Hire, Dr. Timothy Su we need the following done to CS 435: Original SOW: (1) Add a door between 435 and 439 (swinging outside of 435 into 439). (2) Exhaust connection for a biosafety cabinet (3) Vacuum line hook up (4) Gas cylinder rack Revised SOW 07/30/19: Room 435: (A) Remove mounted wooden cabinets (B) Remove standing wooden cabinet (C) Move flammable cabinet to Room 439 (D) Move flammable refrigerator to Room 447 Room 439: (A) Remove cabinets under sink Room 441: (A) Remove cabinets under sink (B) Remove top and bottom cabinets and bench, then deliver both items to Chemical Sciences Rm 108 (C) De-activate airflow in chemical fume hood #005855 if it does not disrupt air flow in the other chemical fume hoods. Can facilities check whether it is possible to turn valve off for this fume hood without disrupting others? (D) Move biosafety cabinet and incubator from Rm 458 to Rm 441, then hook up biosafety cabinet to house vacuum plumbing (E) Move flammable cabinet to Rm 439 | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000299 |  | 19P000299 | FALSE | CNAS | SL5 SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 |  | SPIETH | 3378 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000485 |  | 19P000485 | FALSE | CNAS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | CHAPMAN | 9 | IN PROGRESS | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-29 | connect the plumbing, electrical |  | 2021-03-01 |  |  |  | 2/1/21, DL: We have had a delay with the plumbing and it is our goal to be complete on or before 3/1/21…………1/10/21, DL: This project is almost complete. This project will be complete in the next 30- days…………9/30/20, DL: Fume Hood demolition and abatement will be completed on 10/2/20. Fume hood install should be coplete in mid Novemeber……8/5/20, DL: We will submit plans this week. Once plans are approved, we will schedule the work……………Work orders are produced. We need to work on plans and permits once we return.. | 2020-02-10 | Ron Veloz | Disconnect, cap and safe off the existing utility services. Provide the necessary abatement services to properly remove the fume hood from the site and deliver to the campus surplus yard. Install one new department furnished fume hood. Abatement Services: Provide the necessary abatement services to perform all utilities disconnections and floor repair. Floorcovering: Patch and or repair as necessary to match or provide a close match. Install rubber base. Access Control: Survey and adjust the entry door closer to increase latch pull to allow the door to closer completely. Patching and painting: Patch and paint wall at the old fume hood location. Mechanical: Disconnect metal duct, cap/safe off, reconnect/reconfigure new duct to accommodate the new fume hood. Electrical: Provide electrical disconnections and safe off. Reconnect/reconfigure power to the new fume hood. Plumbing: Disconnect Air, Gas, Vacuum, Cold water, and Drain, cap and safe off and reconnect/reconfigure service to the new fume hood. Resource Management: Properly remove the fume hood from the site and deliver to the campus surplus yard. | YES |  | Spring 2020 | FS | FALSE | 2019 | 2021-02-01
21P000009 |  | 21P000009 | FALSE | CNAS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | GLOVEBOX SYSTEM | CHEMICAL SCI |  | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | TBD | NATASHA GONZALES |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 2020-07-08 | building permit approval | [5 empty] | 1/19/21, DL: we will submit plans this week or earlier next ……………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS | 3009 | QUEUE TO START | Kathryn Uhrich | TBD | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 2019-10-11 | [6 empty] | 02/03/21 O-ANS: Reminder email sent to customer that PAINT ONLY portion would be completed and not the door removal at this time. Customer can resubmit request in next prioriization cycle…. 11/06/20 O-JLO: Emailed requestor and alternate regarding paint portion only, and that door/drywall removal will not occur during this time …. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. FS to confirm with customer that we can only complete the painting at this time but not the removal of the door…. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure. | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01
20P000036 |  | 20P000036 | FALSE | CNAS | SL5 ENTOMOLOGY 224 - PAINT OFFICE FOR NEW PI HANSEN |  | ENTOMOLOGY | 224 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-07-23 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20. 09/19/19 O-ANS: Project placed on HOLD for WINTER 2020 prioritization per customer request. |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000202 |  | 20P000202 | FALSE | CNAS | SL5 SKYE HALL 361 RENOVATION PROJECT | Renovete space for class room. | SKYE HALL | 361 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY | MELISSA GOMEX | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-10-30 | pending permit approval | 2020-02-05 | 2020-03-27 |  |  |  | 9/30/20, DL: This Project is Complete……….8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Permits were approved. Demolition is complete…..1/15/20 O-DHN: Emailed Status Report to customer……..1/14/20, DL: Plans have been submitted for a building permit. Once plans are approved, it is our goal to complete the work by the beginning of spring quarter….. |  | Ron Veloz | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
20P000075 |  | 20P000075 | FALSE | CNAS | SL5 SPIETH 2372 - PATCH/PAINT FACULTY OFFICE |  | SPIETH | 2372 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-08-13 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-27 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000335 |  | 20P000335 | FALSE | CNAS | SL5 ENTOMOLOGY BLDG 239-246 - PAINT AND PATCH OFFICE AND LAB |  | ENTOMOLOGY | 239 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-22 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY | 05/22/20 O-ANS: Project canceled per customer request (Bill Sutton). |  | 2020-05-22 | Spring 2020 | FS | FALSE | 2020 | 2021-02-01 | FY 19-20
20P000061 |  | 20P000061 | FALSE | CNAS | SL5 PHYSICS 1028 - MOVE UTILITIES FOR GLASS SHOP | Install utilities in Physics for the Glass shop equipment relocated from Pierce. | PHYSICS | 1028 | COMPLETE | Kathryn Uhrich | TBD | CHRISTOPHER BARDEEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-08-06 | Plans and permits | 2019-11-18 | 2020-01-24 |  |  |  | 04/23/20 O-ANS: Complete per Dan Lerman. Separate work order to install gas line created - 20W026489 …. 1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is 90% complete and should be 100% complete 1/24/20………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 95% complete. They are moving the equipment over. Once the equipment is delivered and setup, we will connect all of the power and plumbing……11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL; We are still working on plans for this project. 10/30/19, DL: We're planning to complete the project by 12/7/19. We are working on the plans and are planning to submit the plans for plan check review tomorrow. | 2019-10-16 | Ron Veloz | Electrical: Relocate existing power for the welder & other equipment. Install new power and safety switch for relocated equipment. Relocate power for welder and other equipment to the machine shop side of the north wall. Plumbing: Lab air and Natural Gas - relocate and install new POC's. Install water supply lines to Wet sander and diamond wet saw. Cap and or extend the existing Lab air and natural gas as necessary. Install drain lines for new equipment. Modify water supply and existing sink and faucet. Carpentry: Demo selected upper and lower cabinets at the West wall. | YES | 2020-04-23 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18P000473 |  | 18P000473 | FALSE | CNAS | SL5 PIERCE NEW CARPET & PAINT FACULTY OFFICE |  | PIERCE | 202 | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Paul Ditty |  | 1 | 5 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | 2018-09-26 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000244 |  | 19P000244 | FALSE | CNAS | SL5 PATCH & PAINT GEOLOGY |  | GEOLOGY | 2258A | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2018-09-06 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000571 |  | 19P000571 | FALSE | CNAS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 |  | SCIENCE LAB1 | 215 & 322 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2019-04-10 | [6 empty] | 07/30/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000242 |  | 20P000242 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 10 |  | TRUE |  |  | 2019-11-25 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000347 |  | 19P000347 | FALSE | CNAS | SL5 SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT |  | SPIETH | 3320 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-10-16 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT |  | SCIENCE LAB1 | 317 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 10 |  | FALSE |  |  | 2020-02-18 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-02-01
19P000324 |  | 19P000324 | FALSE | CNAS | SL6 SPIETH HALL ASSESS AIR VENT OR PURIFIER FOR LAB | Provide the single pass exhaust, air changes (6-12 ACH) and the negative air requirements for PI to perform surgeries in the room. | SPIETH | 1312 | CANCELED BY FS | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 106 |  | FALSE |  |  | 2018-10-05 | [7 empty] | 2018-10-10 | Ron Veloz | Upgrade infrastructure to accomodate surgical procedures in room 1312. | N/A | 2019-04-04 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01
20P000239 |  | 20P000239 | FALSE | CNAS | SL5 SKYE 382 - PATCH AND PAINT |  | SKYE HALL | 382 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-11-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18P000223 |  | 18P000223 | FALSE | CNAS | SL5 Provide requisite utility infrastructure to support 4 add'l chambers (on order). |  | FAWCETT LAB |  | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  | 11 | 21 | FALSE |  |  | 2017-12-11 | [6 empty] | 2/1/19, DL; This Project is 100% Complete……..01/15/19, DL; Plans are approved, Chambers are on site. Electrical is complete. Plumbing work is in progress. Our portion of the project should be complete by 2/1/19…………..12/14/18, DL; All Pre work is complete. The Chambers are scheduled to arrive on site within the next 30-days. We will finish this project when material on site……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans……..DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet….DL, 4/29/18; Still need to conduct site visit with the team….DL, 5/24/18; Per Patty, equipment is ordered but 5- months out…..DL, 9/6/18; We will submit plans to Bob W. tomorrow for review and approval……..DL, 9/19/18; Plans are approved. The equipment will be here in about 4- months. WE will start the work for this project in the Fall to ensure we are ready when the equipment arrives……DL, 9/19/18; Plans are currently being review by BO & FM……DL, 11/7/18; Plans are approved. WE are requesting to change the placement confirguration of the growth chamber and awaitng Bob's review and approval. WE are on track to have this work complete befoire the end of the new year….. |  | Dan Lerman |  | YES | 2019-02-01 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
19P000367 |  | 19P000367 | FALSE | CNAS | SL5 SCILAB 1 0211- PATCH & PAINT |  | SCIENCE LAB1 | 211 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-31 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000438 |  | 19P000438 | FALSE | CNAS | SL5 BOTANIC GARDENS RAILROAD TIE WALLS | Request for review and cost estimate for the repair of two railroad tie walls in the Botanic Gardens. 1) Retaining wall located below the Iris Garden (across from the Greenhouse). 2) Low wall located along the pathway just below the Garage Office. | BOTAN INFO C |  | CANCELED BY FS | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | 118 |  | FALSE |  |  | 2019-01-08 | [8 empty] | Ron Veloz | 03/05/19 O-RVL: RV noticed two requests on the O-UA1 bench and updated notes on this (19P000438) request with notes from 11/07/18 to 03/01/19. END ~ 03/01/19 O-RVL: RV will walk with Chad C to determine if FS is capable of repair/reinstall railroad ties true & plumb. Site walk is scheduled for 03/01 afternoon. END ~ 02/15/19 O-RVL: Updated SOW, RV will schedule a site visit with the Carpentry Supervisor to determine the construction feasibility and estimated costs. END ~ 01/09/19 O-RVL: REQUEST FOR ESTIMATE, Not a Project. RV To schedule a site visit with C. Pillen and Chad Chambers to evaluate if repairs are possible. ~ 12/10/18 O-RVL: REQUEST FOR ESTIMATE. Ron V walked with D. McWilliams & Jodie and identified the railroad tie retaining wall area requiring repairs. Jodie would like an estimate to repair the leaning railroad ties at specified areas. RV to meet with Chris P. and or Chad Chambers to determine if FS can perform work and or provide an estimated cost to perform work. ~ 11/07/18 O-RVL: Received an email form Deborah Mc. to discuss the wall at Thursday during our 1-1 meeting |  | 2019-03-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
18P000269 |  | 18P000269 | FALSE | CNAS | SL5 BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED |  | BATCHELOR | 1123 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  | 12 | 18 | FALSE |  |  | 2018-01-16 | schedule the work | 2019-03-21 | 2019-04-18 |  |  |  | 3/18/19, DL; went to schedule the work and the customer stated the power is no longer needed and confirmed this work order can be canceled. |  | Enrico Baez |  | YES | 2019-03-18 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000137 |  | 19P000137 | FALSE | CNAS | SL5 LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM |  | LIFE SCIENCE | 2545 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
20P000240 |  | 20P000240 | FALSE | CNAS | SL5 SKYE 384 - PATCH AND PAINT |  | SKYE HALL | 384 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 12 |  | FALSE |  |  | 2019-11-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18P000354 |  | 18P000354 | FALSE | CNAS | SL5 GH16-25 COOLING SYSTEM REPAIR |  | GH 16 25 |  | CANCELED BY FS | Kathryn Uhrich | TBD | MARK TANKERSLEY |  | Dan Lerman |  | 13 | 17 | FALSE |  |  | 2018-03-20 | [6 empty] | DL, 7/25/18; Reviewed Ron V. noted. I will check in with Chris on this to better determin the method complete this project. |  | Dan Lerman |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
20P000241 |  | 20P000241 | FALSE | CNAS | SL5 SKYE 386 - PATCH AND PAINT |  | SKYE HALL | 386 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 13 |  | FALSE |  |  | 2019-11-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000238 |  | 20P000238 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 14 |  | TRUE |  |  | 2019-11-25 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000045 |  | 19P000045 | FALSE | CNAS | SL5 PREPARE LOCATION AND UTILITIES FOR INSTALL |  | BOYCE | 2407 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Dan Lerman |  | 14 |  | FALSE |  |  | 2018-07-23 | [8 empty] | Ron Veloz |  | YES | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000200 |  | 20P000200 | FALSE | CNAS | SL5 COLLEGE BLDG NO 306 - PATCH AND PAINT ONE WALL ONLY |  | COLL BLDG NO | 306 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2019-10-29 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/06/20. |  | Paul Ditty |  |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000106 |  | 19P000106 | FALSE | CNAS | SL5 PHYICS 1134 - UTILITIES REQUEST |  | PHYSICS | 1134 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 15 |  | FALSE |  |  | 2018-08-01 | Installed Chilled water | 2019-03-28 | 2019-05-03 |  |  |  | 6/15/19, DL; This Project is 100% Complete…...5/1/19, DL; Project should be complete this week or early next week…..3/28/19, DL; Power is complete. Need to finish chilled water…… 2/1/19, DL; Review scope with Customer. Still need to review with Brian from the Electic shop…………….12/14/18, DL; No update…. | 2018-11-07 | Ron Veloz |  | YES | 2019-06-15 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000170 |  | 19P000170 | FALSE | CNAS | SL5 INSTALL NEW IRRADIATOR INSTRUMENT |  | MAT SCI ENGR | 51 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 16 |  | FALSE |  |  | 2018-08-08 |  | 2019-02-01 | 2019-02-14 |  |  |  | 2/14/19, DL; This project is 100% Complete………2/1/19, DL; Power is complete. Chilled water will be complete next week…………..1/15/19, DL; Electric is commplete, Water will be complete with in two weeks. Equipment should be on site soon…12/14/18, DL; This project is currently on hold per RED…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; The unit is schedukled for delivery in the next three weeks. | 2018-09-19 | Ron Veloz |  | YES | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | Modify the existing room in Soil House 1 (attached to the Delphino Lab at the Rubidoux Facilities) to expand CCPP quarantine services to include USDA/CDFA compliance for installation of new Economic Development Administration (EDA) citrus growth chambers. | DELFINO HHSE |  | TO BE PERFORMED BY PD&C | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | Research and plan development | [5 empty] | 12/7/20, DL: This project will be managed by PD&C…..9/30/20, DL: Project is still on Hold until Furhther notice………...8/5/20, DL: WE will work on plans in the next 30- 45 days……………6/17/20, DL: This project is under review and is on hold until further notice………10/3/19 O-ANS: Plan Development per Minor Reno Meeting. 10/1/19,DL; We are getting ready to start the plans as we are currently conducting resarch on products that will meet the needs of the space……………..5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman |  | YES | 2020-12-07 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 20-21
20P000105 |  | 20P000105 | FALSE | CNAS | SL5 PHYSICS 2029 - PATCH AND PAINT |  | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2019-08-28 | [8 empty] | Paul Ditty | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/06/20. |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000292 |  | 19P000292 | FALSE | CNAS | SL5 GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | 18 |  | FALSE |  |  | 2018-08-10 | Install Chain link fence…… | 2019-01-28 | 2019-03-29 |  |  |  | 3/28/19, DL; This Project is 100% Complete…….2/14/19, DL; The Concrete and Power is Complete. We still need to install the chain link which will be installed in about 3-4 weeks………..2/1/19, DL Electrical is complete. WE will pour Concrete next week. We will schedule the fence install 28- days after concrete is poured………; Th1/15/19, DL; Plans are approved, we will start the work in the next two weeks……12/14/18, DL; Plans are almost complete. We will schedule the work after plans are approved……DL, 11/7/18; Conducted site visit with Chris P. We need to confirm a feasable site location before we move forward with the work…. |  | Ron Veloz |  | YES | 2019-03-28 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000043 |  | 19P000043 | FALSE | CNAS | SL5 SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | Customer called and canceled the work on 10/23/18. | SCIENCE LAB1 | 309 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | 19 |  | FALSE |  |  | 2018-07-20 | [7 empty] | 2018-10-22 | Ron Veloz |  | YES | 2018-10-23 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000622 |  | 19P000622 | FALSE | CNAS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK | Replace doors & frame | FAWCETT LAB | 204 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-15 | order door and frame. | 2019-08-14 | 2019-10-16 |  |  |  | 11/11/19, DL: This project is complete……10/30/19,DL: The doors are scheduled to be installed this Friday…………10/16/19, DL; Doors shuld be here with in the next week. Once the doors arrive, we will prep and paint the first coat and schedule the install. Target complete date is 3-4 weeks depending on when the doors arrive…….9/16/19, DL The doors are ordered. Once the doors arrive, we will schedule them to be painted and installed……..9/3/19, DL; Contractor has PO# for the doors. I need to verify lead time on material and schedule the installation…….8/15/19, DL; PO# will be provided this week to order the doors and frame, lead time is 4- weeks for the doors/ frame. We will scheudule the install once the door / frame is on site……..8/1/19, DL ; Pending estimate from vendor. Once we have everything needed, we will schedule the work…. | 2019-07-15 | Ron Veloz | Replace existing dual egress doors with ne doors and frames. | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000340 |  | 19P000340 | FALSE | CNAS | SL5 PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE |  | SKYE HALL | 349 | COMPLETE | Kathryn Uhrich | TBD | VICTORIA AVALOS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000618 |  | 19P000618 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 205 AND 205A- PAINT |  | COLL BLDG NO | 205 AND 205A | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 06/11/19 O-ANS: Per Paul, conference room was in decent condition and does not need to be repainted. He will speak with customer to explain. |  |  |  |  | 2019-06-11 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
20P000189 |  | 20P000189 | FALSE | CNAS | SL5 SPIETH 3352 - ESTIMATE FOR PATCH AND PAINT |  | SPIETH | 3352 | COMPLETE | Kathryn Uhrich | TBD | NATALIE HOLT | SILVANA | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-10-23 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/28/20 |  | Paul Ditty |  |  | 2020-01-28 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000081 |  | 20P000081 | FALSE | CNAS | SL5 CHEM SCI 0441- INSTALL FUME HOODS | Install vacuum to new fume hood | CHEMICAL SCI | 441 | COMPLETE | Kathryn Uhrich | TBD | TIMOTHY SU |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-08-15 | schedule the work | 2019-10-25 | 2019-11-22 |  |  |  | 1/14/20, DL This Project is 100% Complete…….12/17/19 O-DHN: Emailed Status report to customer…..12/16/19, DL: This Project is almost Complete except for connecting the glove box. Cory will try and connect the glove box before the new year……...11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: This project should be complete with in the next two weeks……….10/30/19, DL: This project is in progress and we should be complete in 2- 3 weeks…………10/16/19, DL: We will start this project with in the next two weeks…. |  | Ron Veloz | Install eight (8ea) electrical swithced outlets behind cabinets for new vac pumps, remove doors and install sliding lower pump shelves. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000034 |  | 20P000034 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 451- PATCH AND PAINT 2 SMALL WALL SECTIONS |  | CHEMICAL SCI | 451 | COMPLETE | Kathryn Uhrich | TBD | KEVIN KOU |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-07-22 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-02 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000214 |  | 19P000214 | FALSE | CNAS | SL5 PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT |  | PHYSICS | 3005 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-08-24 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000341 |  | 19P000341 | FALSE | CNAS | SL5 PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL |  | PIERCE |  | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000355 |  | 20P000355 | FALSE | CNAS | SL5 GEOL 454A- PATCH & PAINT |  | GEOLOGY | 0454A | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | LAURIE GRAHAM | PAUL DITTY |  | 2 |  | FALSE |  |  | 2020-02-09 | [8 empty] | PAUL DITTY | 08/06/20 O-ANS: Closed per Paul Ditty as of 03/13/20. |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2020 | 2021-02-01 | FY 19-20
20P000445 |  | 20P000445 | FALSE | CNAS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY | 279 | PROJECT INTAKE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | DAN LERMAN |  | 2 |  | TRUE |  |  | 2020-06-03 | complete priority 1 projects | [5 empty] | 1/19/21, DL: This is a priority 2 project. We will start the project when all priority 1 projects are complete…………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
19P000283 |  | 19P000283 | FALSE | CNAS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | COMPLETE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 20 |  | FALSE |  |  | 2018-09-05 | Schedule site visit with contrac | 2019-06-03 | 2019-07-02 |  |  |  | 8/1/19, DL; This Project is 100% Complete……7/1/19, DL; Barricades are complete. Signage needs to be installed. Signage to be installed in the next 3- weeks………….6/17/19, DL; Yello Caution tape is installed. Still need to install barricades and signage. Target complete date in mid to late July……5/31/19, DL; The contractor has the PO#. We will start the work and complete the work in the next 30- days……5/15/19, DL; We are waiting on the quote, once we have the quote, we will proceed with the work……4/15/19, DL; We are trying to locate a roofing contractor that will complete the installation. This is a specialty product that requires a professional installation…….3/28/19, DL; We will install the yellow caution tape on the roof which is our most viable option. I will schedule a site visist / job walk with a contractor in the near future…… | 2018-09-19 | Ron Veloz | Install hand railing and marking for a leading edge as direcetd by EH&S. | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
18P000388 |  | 18P000388 | FALSE | CNAS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 2018-04-10 | schedule the work | 2019-06-03 | 2019-08-19 |  |  |  | 8/14/19, DL; This project is 100% Complete………8/1/19, DL; This project work from Facilities Services should be complete in about 2- weeks…..7/15/19, DL, Work is in progress. Goal is to be complete with our scope near the first week in August……6/17/19, DL; This will be scheduled in July…….5/31/19, DL; Demo and removal of the dishwasher is. We will work on the installation and elctrical / power connections over the next three weeks. Note. Steam shut down is taking priority and the installation may be delayed….. 5/15/19, DL; We will schedule the work……..DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but there is no hard date as this is vacant space and we will access the space as time permits…… DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter….DL, DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans….7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved….. |  | Enrico Baez |  | YES | 2019-08-14 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
18P000480 |  | 18P000480 | FALSE | CNAS | SL5 BG - LOWER RESTROOMS-PAINTING-FLOORS | Canceled by Facilities Services; Work is not within the SLA and is not needed. | BOTGDN RSTRM |  | CANCELED BY FS | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000486 |  | 18P000486 | FALSE | CNAS | SL5 PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 2018-06-28 | plans and permits | 2019-03-29 | 2019-07-01 |  |  |  | 8/1/19, DL; This project is 100% Complete…… 6/17/19, DL; This project is making good progreess and will be complete near mid- July…..5/31/19, DL; This project is making good progress and we are hopeful to be complete on or before July 1st……5/1/19, DL: This project is in grogress and moving forward. Target complete date is 6- weeks… 4/15/19, DL; Started Demolition phase….2/28/19, DL; We will work on the plans in the next 30-days.12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
19P000210 |  | 19P000210 | FALSE | CNAS | SL5 CHEMICAL SCI Install Door In Doorway |  | CHEMICAL SCI | 0225A | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  | 25 |  | FALSE |  |  | 2018-08-24 | contract the work and material | 2019-06-03 | 2019-07-01 |  |  |  | 7/1/19, DL; This project is 100% complete…..6/17/19, DL; Po is cut. Target complete date is before 7/1/19……Permit was approved this week. We are now working on the contract with the vendor. Our goal is start the work with in the next 30- days. 5/15/19, DL; Plans were approved. I am in the process of working with PD&C for the contract. We will order material and schedule the wrok once we have a signed contract……..3/28/19, DL; Plans were submitted last week… 3/18/19, DL; Conducted site visit last week. We are working on plans now we will try and submit plans for permit review next week…… | 2018-09-19 | Ron Veloz |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
18P000099 |  | 18P000099 | FALSE | CNAS | SL5 EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | TBD | LAURIE GRAHAM |  | Dan Lerman |  | 26 | 23 | FALSE |  |  | 2017-09-08 | Move Cabinets and install electr | 2019-05-01 | 2019-05-17 |  |  |  | 4/19/19, DL; This Project is 100% Complete :)…………….12/6/18, DL; This project is a priority #23 and may be completed in the next 12 - months…..DL 1/3: Chris to verify with customer on electrical requirements for completion……DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress…..DL, 7/11/18; Still need to work on plans…. Target date is 9/30/18….. |  | Dan Lerman | Install power to 4- cabinets in hallway | YES | 2019-04-19 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
17W012504 |  | 17W012504 | FALSE | CNAS | PAINT Business OFFICE AND CONF. ROOM |  | ENTOMOLOGY | 170 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 27 | 26 | FALSE |  |  | 2017-05-04 | [6 empty] | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. |  | Dan Lerman |  | YES | 2018-10-22 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
18P000257 |  | 18P000257 | FALSE | CNAS | SL5 SKYE HALL MOUNT 55 |  | SKYE HALL | 209 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | 28 | 28 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete…….1/15/19, DL, Site visit is scheduled with James M. this Thursday. We will schedule the work shortly after the site visit…….12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2017 | 2021-02-01
18P000258 |  | 18P000258 | FALSE | CNAS | SL5 SKYE HALL HALLWAY MOUNT |  | SKYE HALL | 212 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | 29 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete……1/15/19, DL, Site visit is scheduled with James M. this Thursday…………12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2017 | 2021-02-01
18P000284 |  | 18P000284 | FALSE | CNAS | SL5 SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT |  | SKYE HALL | 277 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  | 29 | 23 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install electrical utilities for new equipment | PHYSICS | 1132 | IN PROGRESS | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-03-19 | Install elect and Sink |  | 2021-03-01 |  |  |  | 1/19/21, DL: This project is in progress and will be complete with in 30- days………..9/30/20, DL: Plans were submitted for Plan Check review last week and we should have an update on the plan check review process soon………..8/5/20, DL: Need to meet with Kirk to verify electrical load. Once confirmed, we will work on plans for a permit | 2019-10-15 | Ron Veloz | Install utilities for new equipment | YES |  | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
20P000207 |  | 20P000207 | FALSE | CNAS | SL5 PHYSICS 3033 - PAINT & PATCH STAFF OFFICE |  | PHYSICS | 3033 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO | DAVID NEFF | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-11-04 | [6 empty] | 03/02/20 O-ANS: Completed per Paul Ditty as of 02/04/20. |  | Paul Ditty |  |  | 2020-02-04 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000301 |  | 19P000301 | FALSE | CNAS | SL5 SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH |  | SCIENCE LAB1 | 214 | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-09-27 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000006 |  | 19P000006 | FALSE | CNAS | SL5 MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 |  | MAT SCI ENGR | 310 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..2/14/19, DL; This project is 90% Complete. ………2/1/19, DL; This Project started to day. We are scheduled to be complete by the end of February………..1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. | 2018-09-28 | Ron Veloz |  | YES | 2019-03-18 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000266 |  | 20P000266 | FALSE | CNAS | SL5 GEOLOGY 2460B - PATCH & PAINT |  | GEOLOGY | 2460B | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 3 |  | FALSE |  |  | 2019-12-19 | [8 empty] | PAUL DITTY | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000144 |  | 20P000144 | FALSE | CNAS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A | BOYCE | 3432, 3432A, 3446, 3446A | IN PROGRESS | Kathryn Uhrich | TBD | MATTHEW ULRICH | CHERYL GERRY | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-09-26 | final paint and cabinets |  | 2021-02-22 |  |  |  | 2/1/21, DL: WE are making good progress and are target date is still 2/22/21………….1/19/20, DL: This project is in progress and will be complete in the next 30- days………….9/30/20, DL: WE have started a few items but we are waiting on Matt U. and the PI to remove their items so we can have access to the space. Once the space is cleared out, we will proceed with the work…………8/5/20, DL: We will start the work in the next 4-6 weeks. | 2020-02-18 | Ron Veloz | Boyce 3432, 3446, 3436 and 3436A . Patch and paint 3432, 3432A, 3436, 3436A, 3446, 3446A. Reface/replace water damaged cabinets near sink (3446). Install GCFI outlets near sink (replace existing) (3446). Install panel cover for electrical panel box. Replace many burnt out bulbs in ceiling lamps. Replace broken chemical plexi-glass on bench shelves. | YES |  | Winter 2020 | FS | FALSE | 2019 | 2021-02-01
20P000024 |  | 20P000024 | FALSE | CNAS | SL5 PHYSICS 1003- RENOVATION | New Faculty-Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 1003 | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-07-18 | clean out the space | 2020-01-13 | 2020-02-28 |  |  |  | 3/25/20, DL: This project is complete……2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: The paint is complete and the floor covering should be delivered this week. Once the floor covering is on site, we will schedule the installation……………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We started this project and should be complete in the next 6- weeks……….11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: David who is responsible for clearing out the space is in the process. Once the space is empty we will schedule the work. We will probably start the physical project shortly after Thanksgiving…….10/30/19, DL; We are planning to start this project within the next 6-8 weeks……. | 2019-10-16 | Ron Veloz | Test for ACM and or other hazardous materials in the room. Replace all existing flooring, remove power pole and miscellaneous wall mounted items shelving/racks, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks) and repair/replace top & bottom flush bolts, install new door closer(s), relamp with LED as needed. Replace faucet, clean sink/counter and infill pit. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000613 |  | 19P000613 | FALSE | CNAS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT |  | COLL BLDG NO | 0203B | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-21 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
21P000001 |  | 21P000001 | FALSE | CNAS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | NEW GROWTH CHAMBER PLACEMENT | FAWCETT LAB |  | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | TBD | LINDA WALLING |  | DAN LERMAN |  | 3 |  | TRUE |  |  | 2020-06-08 | complete priority 2 projects | [5 empty] | 1/19/21, DL: This is a priorty 3 project. We will start this project when all priority 2 projects are complete……. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
18P000347 |  | 18P000347 | FALSE | CNAS | SL5 GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) |  | GEOLOGY | 0 | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | 31 | Deferred to Fall Quarter - summer priority 27 | FALSE |  |  | 2018-03-18 | sheet metal to install handrail | 2019-02-25 | 2019-03-22 |  |  |  | 4/15/19, DL; Thios Project is 100% Complete….3/28/19, DL; Monitor is installed, need to finish power and data………………...2/14/19, DL: The monitor is on site. We need to schedule the installation. 2/1/19, DL; Conducted site visit with Amber. Amber will order the monitor. We will schedule the installation when the monitor is on site………….DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez |  | YES | 2019-04-15 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000055 |  | 19P000055 | FALSE | CNAS | SL5 CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM |  | COLL BLDG NO | 207 | COMPLETE | Kathryn Uhrich | TBD | LISA DUNMORE |  | Dan Lerman |  | 32 | 24 | FALSE |  |  | 2018-05-18 | order fan and schedule install | [5 empty] | 4/15/19, DL; This project is 100% Complete…….3/28/19, DL; Need to order material and schedule the work…… Work order is assigned. 12/14/18, Dl; This project is prioritized at 32 and will not be scheduled in the near futurer…….DL, 7/11/18; Correction, I did not scope this yet, I thought we were talking agout the door bell and ADA operator. I will check in with Ronda and verify the scope…… DND 7/30/18: Created project to replace WO #18015182; project #19P000055 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. | 2018-11-29 | Ron Veloz | SOW is to install a new exhaust fan at the second floor toilet room. Roof access is available from the access panel in the closet located in the room 210 next door. There is roof is transite per Jess. Abatement is necessary for roof penetrations and possibly has lead paint on ceilings and walls. | YES | 2019-04-15 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18W013160 |  | 18W013160 | FALSE | CNAS | BEES- PATCH & PAINT 2460D & 2460F |  | GEOLOGY | 2460 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO |  | Paul Ditty |  | 33 | 29 | FALSE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000191 |  | 19P000191 | FALSE | CNAS | SL5 PATCH AND PAINT HINDERAKER BASEMENT |  | HINDERAKER |  | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 34 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000464 |  | 18P000464 | FALSE | CNAS | SL5 PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 35 |  | FALSE |  |  | 2018-08-16 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000436 |  | 18P000436 | FALSE | CNAS | SL5 COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS |  | COLL BLDG NO | 210 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 36 | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000174 |  | 19P000174 | FALSE | CNAS | SL5 BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT |  | BATCHELOR | 2112 | COMPLETE | Kathryn Uhrich | TBD | AMY RICKS |  | Dan Lerman |  | 37 |  | FALSE |  |  | 2018-07-24 | final conduit and paint | 2019-04-15 | 2019-05-03 |  |  |  | 5/1/19, Dl; This project is 100% Complete….. 4/15/19, DL; This project should be complete in 2-weeks…… 12/14/18, DL; This project is priortized at 37 and will not be scheudled until further notice…… | 2018-09-19 | Ron Veloz |  | YES | 2019-05-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000042 |  | 19P000042 | FALSE | CNAS | SL5 COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL |  | COLL BLDG NO | 200 | COMPLETE | Kathryn Uhrich | TBD | LISA DUNMORE |  | Paul Ditty |  | 38 |  | FALSE |  |  | 2018-07-20 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000049 |  | 19P000049 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT |  | PHYSICS | 3036 | COMPLETE | Kathryn Uhrich | TBD | JAZMIN CHAVEZ |  | Paul Ditty |  | 39 |  | FALSE |  |  | 2018-07-25 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000235 |  | 20P000235 | FALSE | CNAS | SL5 SKYE 374 - PATCH AND PAINT |  | SKYE HALL | 374 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 4 |  | TRUE |  |  | 2019-11-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000508 |  | 19P000508 | FALSE | CNAS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | BOYCE | 3410 | COMPLETE | Kathryn Uhrich | TBD | CHERYL GERRY |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-02-21 |  | 2019-11-04 | 2019-12-06 |  |  |  | 1/30/20, DL: Project is now cxomplete. The electrical panel cover was installed this morning…………. 11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: We are not complete. We still need to complete the following items; Light bulbs, electrical panel cover, replace ACM ceiling tiles and deep clean the space…..10/30/19, DL: Progress is in progress. We should be done within two weeks…….10/16/19, DL; Paint is in progress and additional work to follow. Target date for complete is 11/19/19…..10/1/19, DL; Jess to survey space for ACM, Lead paint, etc… We will schedule work once we have confirmation from Jess….. | 2019-09-30 | Ron Veloz | ……….Remove lower base cabinets and upper cabinet in room 3410B. Repair delaminated flooring between room 3410 & 3426, Patch and Paint entire rooms 3410, 3410B & 3426 up to 8'H(no paint in in 3410 A&C). Repair damaged floor tiles in room 3410 A&B. Repace all burned out lamps w/ LED throughout labs and office. Strip & wax all floors in labs space. Remove cylinder racks in room 3410B. Fabricate a hinged metal door to cover the electrical panel in roon 3426 (panel is near door). | YES | 2020-01-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000267 |  | 20P000267 | FALSE | CNAS | SL5 GEOLOGY 2460C - PATCH & PAINT |  | GEOLOGY | 2460C | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 4 |  | FALSE |  |  | 2019-12-19 | [8 empty] | PAUL DITTY | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/04/20. |  | 2020-03-04 | Spring 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000614 |  | 19P000614 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 202- PAINT |  | COLL BLDG NO | 0202 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18W011691 |  | 18W011691 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | FS to coordinate with client to schedule work for completion. | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 4 | 11 | TRUE |  |  | 2018-03-08 | [6 empty] | 12/17/18 DND: Canceled by client on 12/17/18. |  | Paul Ditty |  | N/A | 2018-12-17 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
20P000320 |  | 20P000320 | FALSE | CNAS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | ACTIVATE VACUUM LINES | SPIETH | 1303 | PROJECT INTAKE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | DAN LERMAN |  | 4 |  | FALSE |  |  | 2019-11-20 | Sch wrk whn we comp. prty 3 proj | [5 empty] | 1/19/21, DL: This is a priority 4 project. We will start this project when all all priority 3 projects are complete……….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01
19P000318 |  | 19P000318 | FALSE | CNAS | SL5 GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE |  | GEOLOGY | 420 | COMPLETE | Kathryn Uhrich | TBD | KAREN CATO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-04 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000688 |  | 19P000688 | FALSE | CNAS | SL5 PHYSICS- RENOVATION OF THREE PHYSICS ROOMS | Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 2128 | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-06-28 | finish abatment | 2019-11-05 | 2019-12-15 |  |  |  | 1/14/20, DL: This Project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 99% Complete. Custodial will be there this week to complete the final clean. The space will be ready for occupancy starting 1/6/19…..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: The project is on track to be complete on 12/13/19. Once the abatement is complete, we will start the wall repair as the walls are severely damaged from the previous use of the space……10/30/19, DL: WE are working on this project. Our target date for completion is 12/17/19………… | 2019-10-16 | Ron Veloz | Test for ACM and or other hazardous materials in the room. RM 2124, 2128 & 2132: Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2128 Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2132: Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000031 |  | 19P000031 | FALSE | CNAS | SL5 BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) |  | BIOLOGIC SCI | 3101 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 40 |  | FALSE |  |  | 2018-07-16 | Schedule the work | [5 empty] | 6/15/19, DL; This Project is 100% Complete…...5/1/19, Dl; This project will be complete on 5/5/19…..3/28/19, DL; Need to schedule a site visit with Estella. Left voice mail message on 3/28/19 to schedule site visit……..12/14/18, DL; This is prioritized at #40 and will not be scheduled in the near future….. |  | Enrico Baez |  | YES | 2019-06-15 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | COMPLETE | Kathryn Uhrich | TBD | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | Work will be complete in 2 weeks | 2020-02-03 | 2020-03-13 |  |  |  | 8/5/20, DL: This project is complete……………..06/17/20, DL: This project should be complete with in the next two weeks……..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within two weeks. Once we have a contract, we will schedule the work……….1/15/20 O-DH: Emailed Status Report to customer……1/14/20, DL: Contracts is currently working on the contract. Once the contract is complete, we will order the material and schedule the work…………11/26/19, DL: Plans were approved. We will work on the construction contract. Once we have the notice to proceed, we will schedule the work……….10/15/19, DL: Sent PD&C and follow-up email on 11/11/19. We should have approved plans in the near future……10/30/19, DL: Sent PD&C an email asking for a status update on 10.30.19…… 10/16/19, DL; Plans are still in plan check. I sent the building official an email asking if any additional information is needed. This work will be completed by a contractor which means we need to allow time for the bid and contract process……… …………9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Ron Veloz | Request for Estimate to install three new FOB readers with electrified locksets. Work covered: Install one AC Fob Reader at door 2221 and one AC Fob reader at each Door 4231 & 4235. Connect card readers to the existing Hirsh ACP located in the IDF closet at each floor. 03/07/19: Scope revised to eliminate two FOB readers. Install one FOB reader at Genomics door 4231 only instead of all three rooms. | YES | 2020-08-05 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 20-21
19P000102 |  | 19P000102 | FALSE | CNAS | SL5 PATCH & PAINT FRONT CORNER OF OFFICE |  | LIFE SCIENCE | 2930 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 42 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000133 |  | 19P000133 | FALSE | CNAS | SL5 PATCH HOLES AND PAINT |  | BATCHELOR | 2203 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Paul Ditty |  | 43 |  | FALSE |  |  | 2018-08-07 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000197 |  | 19P000197 | FALSE | CNAS | SL5 PATCH AND PAINT OFFICE, LOBBY AND HALL |  | COLL BLDG NO | 0203B | CANCELED BY CLIENT | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 44 |  | FALSE |  |  | 2018-08-21 | [6 empty] | 05/07/19 O-ANS: Canceled per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000184 |  | 19P000184 | FALSE | CNAS | SL5 REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES |  | GEOLOGY | 1270 | COMPLETE | Kathryn Uhrich | TBD | LAURIE GRAHAM |  | Dan Lerman |  | 45 |  | FALSE |  |  | 2018-08-14 | Schedule the floor installation | 2019-02-11 | 2019-03-29 |  |  |  | 4/15/19, DL; This Project is 100% Complete…….. 3/28/19, DL; The project is 90% complete. Need to schedule floor installation…….. 2/14/19, DL; We will schedule the work soon. The space is vacant and ready…………….2/1/19, DL; This project has started. We would like to have the work complete by mid March…………..12/14/18, DL; This project is prioritized at 45 and will not be shceudled until further notice…… |  | Enrico Baez | SCOPE CARPENTERS-Remove all wall, base and center island cabinet work. Verify no ACM flooring under center island. PLUMBERS-Remove sinks in 1270 and 1270A. Terminate, at wall plumbing. Remove air/gas lines on wall in 1270 and 1270A. Remove lower chilled water, supply and return, lines on East wall. Remove air and gas line, flush with floor, from center island. FLOORING-Remove VCT in 1270 and 1270A, replace with customer selected VCT. Replace all cove base. ELECTRICIANS-Remove gray flexible conduit at raceway, terminate circuit. PAINTERS- Patch and paint walls in both spaces. | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000246 |  | 19P000246 | FALSE | CNAS | SL5 PHYSICS - PATCH AND PAINT |  | PHYSICS | 3007N | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Paul Ditty |  | 46 |  | FALSE |  |  | 2018-09-07 | [6 empty] | n/a |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000242 |  | 19P000242 | FALSE | CNAS | SL5 PAINT OFFICE |  | COLL BLDG NO | 210 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 47 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000231 |  | 19P000231 | FALSE | CNAS | SL5 OLMH 1428 PATCH AND PAINT |  | OLMSTED | 1428 | COMPLETE | Kathryn Uhrich | TBD | ANDREW CABRERO |  | Paul Ditty |  | 48 |  | FALSE |  |  | 2018-08-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000243 |  | 19P000243 | FALSE | CNAS | SL5 GENOMICS 1206 - PATCH AND PAINT WALLS |  | GENOMICS | 1206 | COMPLETE | Kathryn Uhrich | TBD | AIMEE GONZALES |  | Paul Ditty |  | 49 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000615 |  | 19P000615 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT |  | COLL BLDG NO | 203 AND 204 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000248 |  | 20P000248 | FALSE | CNAS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT |  | WEBBER | 1223 + 1223-A | PROJECT INTAKE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS | SHARYL MURDOCK | Dan Lerman |  | 5 | 4 | FALSE |  |  | 2019-11-27 | EH&S to sanitize space | 2021-03-02 | 2021-04-21 |  |  |  | 1/19/21, DL: This project is a priority #5. We will start this project when all priority #4 projects are complete…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….02/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Survey space for hazardous material. Once survey is complete, we will schedule abatement and the work. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01
20P000268 |  | 20P000268 | FALSE | CNAS | SL5 GEOLOGY 2460D - PATCH & PAINT |  | GEOLOGY | 2460D | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 5 |  | FALSE |  |  | 2019-12-19 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | PAUL DITTY |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000062 |  | 19P000062 | FALSE | CNAS | SL5 MSE 169-MINOR RENOVATION - NEW FACULTY |  | MAT SCI ENGR | 169 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 5 | 19 | TRUE |  |  | 2018-07-30 | Install water heater | 2018-11-12 | 2019-01-17 |  |  |  | 2/1/19, DL; This project is 100% Complete…………..1/15/19, DL; This project is 99% complete pending one water heater. Water heater is not here yet……12/14/18, DL; This project is 95% complete. The water heater is scheduled for delivery shortly after the new year. We will complete the install when the heater arrives…… 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 9/6/18; We will have the power and cabinets removed by 9/19/18. We are in the process of producing plans for this project. Once the plans are approved, we will proceed with the project. Note, we still need to obtain important information and some specifications regarding the procured base cabinets and counter tops, bio safety cabinet, diswasher, and freezer. ……DL, 7/7/18; The work is 90% complete. We are waiting on parts which have a 4-6 week lead time. We will finsh the balance of the project when the parts arrive….. | 2018-08-22 | Ron Veloz |  | YES | 2019-02-01 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
20P000019 |  | 20P000019 | FALSE | CNAS | SL5 PHYSICS 2029A- NEW EYEWASH STATION | PHYSICS 2029A- INSTALL A NEW EYEWASH STATION | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 5 |  | FALSE |  |  | 2019-07-16 | order material | 2020-02-28 | 2020-03-27 |  |  |  | 2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL; Permit was approved, we need to order material and schedule the work………. | 2019-11-27 | Ron Veloz | Install new eyewashing station | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000523 |  | 19P000523 | FALSE | CNAS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | PATCH & PAINT GRAD STUDENT OFFICE | SPIETH | 3366 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 5 | 9 | FALSE |  |  | 2019-03-12 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-20 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000236 |  | 20P000236 | FALSE | CNAS | SL5 SKYE 368 - PATCH AND PAINT |  | SKYE HALL | 368 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 5 |  | TRUE |  |  | 2019-11-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB. Patch Paint walls, replace flooring, refinish wood cabinets and sinks. | SPIETH | 2349 | TO BE PERFORMED BY PD&C | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 5 |  | FALSE |  |  | 2019-02-20 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold……….12/11/19: O-ANS: Reassigned as project allotment - priority #5 for Winter 2020. 11/27/19 O-ANS: Placed on Hold for re-prioritization by client for Winter 2020. | 2020-02-27 | Ron Veloz | Patch and paint and extra work to upgrade an old lab that we are now inhabiting. In addition to painting, we need to have floors re-surfaced, cabinets re-stained, and counter tops re-surfaced, if possible. There is also a metal sink that could be polished. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000285 |  | 19P000285 | FALSE | CNAS | SL5 PAINT AND PATCH PI OFFICE |  | ENTOMOLOGY | 269 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-09-17 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000176 |  | 19P000176 | FALSE | CNAS | SL5 PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY |  | PHYSICS | 1112 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Paul Ditty |  | 50 |  | FALSE |  |  | 2018-08-10 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2019-01-15 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19W003012 |  | 19W003012 | FALSE | CNAS | SL5 FIX RESTROOMS (PAINT AND FLOORS) | FS to coordinate with client to schedule work for completion. | CHAPMAN | 5 | CANCELED BY FS | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 51 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty |  | N/A | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000269 |  | 20P000269 | FALSE | CNAS | SL5 GEOLOGY 2460E - PATCH & PAINT |  | GEOLOGY | 2460E | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 6 |  | FALSE |  |  | 2019-12-19 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/05/20. |  | PAUL DITTY |  |  | 2020-03-05 | Spring 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000126 |  | 19P000126 | FALSE | CNAS | SL5 CHEMICAL SCIENCE - MINOR RENOVATIONS |  | CHEMICAL SCI | 455 | COMPLETE | Kathryn Uhrich | TBD | KEVIN KOU |  | Dan Lerman |  | 6 |  | TRUE |  |  | 2018-08-03 | [6 empty] | 12/14/18, DL; This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL,11/7/18; Paint is complete, Plumbing shop is planning to schedule the work in the near future…… |  | Ron Veloz |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000616 |  | 19P000616 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 208- PAINT |  | COLL BLDG NO | 208 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000023 |  | 20P000023 | FALSE | CNAS | SL5 PIERCE RM 1144 - PATCH AND PAINT DOOR WHERE WALL POCKET WAS |  | PIERCE | 1144 | COMPLETE | Kathryn Uhrich | TBD | JACQUELINE |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-07-18 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000247 |  | 20P000247 | FALSE | CNAS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | Refresh Lab: Patch paint, strip & clean floor, repair broken ceiling and floor (VCT) tiles at room 2110 & 2118. Install Electrical power & Co2 cylinder racks at each end of workbench/tables | SPIETH | 2110 + 2118 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS | SHERICE UNDERWOOD | Dan Lerman |  | 6 |  | TRUE |  |  | 2019-11-27 | [6 empty] | 1/19/21, DL: This project is complete…………..9/30/20, DL: This project is in progress and will be compete in the next 6- 8 weeks……………8/5/20, DL: We will start on this project in the next 6-8 weeks….. | 2020-04-17 | Ron Veloz | Spieth 2110: Carpentry: Seismic anchoring for “New” tables and equipment. Replace damaged ceiling tiles. Install misc. wall mounted items. Sheet Metal: Remove “existing” steel cage. Fabricate & install metal cylinder rack w/ restrains/seismic anchoring to floor. Plumbing: Install Co2 POC for gas cylinders at four (4ea) new free-standing work benches (see configuration on this document). Electrical: Install dedicated *120v power drop & connect to the existing power strips built-in the four (4ea) new workstation tables (see configuration on this document). *VERIFY/CONFIRM VOLTAGE W/ D. MCW. Relamp fixtures as needed. Spieth 2118 & 2110: Sheetmetal: Clean and or replace air distribution grilles. Flooring: Repair/patch broken floor tile and Replace broken ceiling tiles (abate floor tiles if required). Painting: Paint and patch all walls, verify recondition doors @ room side. Plumbing: Assess sinks to be fully operational & clean. *Replace sink in Rm 2118 for glassware, confirm with Faculty/Estella. Replace sink in room 2118 (Sink type TBD by Faculty). HVAC: Check lab air pressure is operational & proper pressure. Custodial: Strip and Wax floor, clean interior windows, wipe down doors and windowsills. EXCLUSIONS: Furnish, assemble, and install new workstations, tables or lab equipment. Removal of existing lab furniture or equipment. Natural gas or air output taps not required (per Faculty). | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
20P000121 |  | 20P000121 | FALSE | CNAS | SL5 SKYE 217 - PATCH AND PAINT |  | SKYE HALL | 217 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-09-05 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000230 |  | 19P000230 | FALSE | CNAS | SL5 NEW FACULTY OFFICE FOR PATCHWORK/PAINT |  | GEOLOGY | 1242A | COMPLETE | Kathryn Uhrich | TBD | KAREN CATO |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-08-30 | [6 empty] | n/a |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000270 |  | 20P000270 | FALSE | CNAS | SL5 GEOLOGY 2460F - PATCH & PAINT |  | GEOLOGY | 2460F | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 7 |  | FALSE |  |  | 2019-12-19 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | PAUL DITTY |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000113 |  | 20P000113 | FALSE | CNAS | SL5 GEOLOGY 2258 - PATCHPAINT RECEPTION WALL OVER BIN REMOVED |  | GEOLOGY | 2258 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-09-04 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GH08 | 881 | COMPLETE | Kathryn Uhrich | TBD | NANCY FERGUSON |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2019-01-29 | Schedule the work. | [5 empty] | 1/19/21, DL: This project is complete……………8/5/20, DL: This project is in Progress and should be complete in the next 8-12 weeks…………….3/25/20, DL: Work orders are produced. Once we are back to work, we will schedule the work………12/11/19 O-ANS: Re-assigned as project allotment - priority #7 for Winter 2020. 11/27/19 O-ANS: Hold by client for re-prioritization for Winter 2020. | 2020-03-04 | Ron Veloz | Install new 3 ton Packaged unit with heat pump and dedicated electrical service on the roof top. Provide 1ea return plenum, 2ea supply drops in the work space. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
20P000366 |  | 20P000366 | FALSE | CNAS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | MINOR LAB RENOVATION | SPIETH | 2375 / 2375-A | PROJECT INTAKE | Kathryn Uhrich | TBD | SHERICE UNDERWOOD |  | DAN LERMAN |  | 7 |  | TRUE |  |  | 2020-02-19 | Complete prty 6 projects | [5 empty] | 1/19/21, DL: This is a priority 7 project, we will start this project when all priority 6 projects are complete………….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
19P000617 |  | 19P000617 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 212- PAINT |  | COLL BLDG NO | 212 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000360 |  | 19P000360 | FALSE | CNAS | SL5 GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING |  | GEOLOGY | 1444 | COMPLETE | Kathryn Uhrich | TBD | KAREN CATO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000369 |  | 19P000369 | FALSE | CNAS | SL5 PIERCE - PAINT IS PEELING OFF WALLS |  | PIERCE | 3341 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000482 |  | 19P000482 | FALSE | CNAS | SL5 PIERCE HALL- PAINT/PATCH HOLES IN 1219C AND 1220D |  | PIERCE | 1219C | COMPLETE | Kathryn Uhrich | TBD | JACQUELINE HAMILTON |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-02-01 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
19P000251 |  | 19P000251 | FALSE | CNAS | SL5 CHEM SCI 428-PATCH DRY WALL HOLES |  | CHEMICAL SCI | 428 | COMPLETE | Kathryn Uhrich | TBD | KEVIN KOU |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000155 |  | 20P000155 | FALSE | CNAS | SL5 BOYCE 3407 - PAINT OFFICE FOR NEW FACULTY |  | BOYCE | 3407 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2019-10-01 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/30/20 |  | Paul Ditty |  |  | 2020-01-30 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000271 |  | 20P000271 | FALSE | CNAS | SL5 GEOLOGY 2460G - PATCH & PAINT |  | GEOLOGY | 2460G | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 8 |  | FALSE |  |  | 2019-12-19 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/06/20. |  | PAUL DITTY |  |  | 2020-03-06 | Spring 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LAB1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 2020-02-19 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-02-01
19P000291 |  | 19P000291 | FALSE | CNAS | SL5 MSE HELIUM RECOVERY SYSTEM |  | MAT SCI ENGR | 205 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 9 | HOLD | FALSE |  |  | 2017-07-24 |  |  | 2018-12-14 |  |  |  | 12/14/18, DL; This project is 100% Complete……DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB - spoke with Mayela who is determining status within her dept…. DL, 11/7/18; This project is complete but I need to conduct a final site visit….. |  | Ron Veloz |  | YES | 2018-12-14 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
18P000221 |  | 18P000221 | FALSE | CNAS | SL5 Provide add'l HVAC capacity to maintain lower temp |  | BOYCE | 4414 | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  | 9 | 16 | FALSE |  |  | 2017-12-11 | [6 empty] | 12/14/18, DL; This project is 100% Complete……….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob. DL, 5/9/18; We will work on plans and submit for review.....DL, 6/16/18. Had meeting with Bob W. to verify what is needed on plans. I will work with Gunther on plans for submittal and review......DL, 7/11/18; Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall.....DL, 11/7/18; Material is on site and will will schedule the work with in the next 30- days..... |  | Dan Lerman |  | YES | 2018-12-14 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | PIERCE | 2232A | PROJECT INTAKE | Kathryn Uhrich | TBD | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 2020-01-22 | complete prty 8 projects | [5 empty] | 1/19/21, DL: This is a priority #9 project. We will start this project when all priority #8 projects are complete…………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
19P000288 |  | 19P000288 | FALSE | CNAS | SL5 COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS |  | COLL BLDG NO | 202 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-19 | [6 empty] | 05/10/19 O-ANS: Project was canceled by FS in March 2019 because customer will have to submit separate work orders for each room since customer has requested to schedule and complete them separately in sequence (not all at once). 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000127 |  | 19P000127 | FALSE | CNAS | SL5 PIERCE PATCH & PAINT | Duplicate request to be combined with 19P000239 | PIERCE | 2301 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | MICHELLE KING |  | N/A |  | Canceled |  | FALSE |  |  | 2018-08-03 | [6 empty] | Paul Ditty |  | Paul Ditty |  |  | 2018-09-21 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000234 |  | 19P000234 | FALSE | CNAS | SL5 PHYSICS 3005-WALL HOLES PATCH |  | PHYSICS | 3005N | CANCELED BY FS | Kathryn Uhrich | TBD | JAZMIN CHAVEZ |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-09-04 | [6 empty] | **9/19/18 DUPLICATE REQUEST SENT IN SEE 19P000246 |  | Paul Ditty |  | N/A | 2018-09-19 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000465 |  | 18P000465 | FALSE | CNAS | SL 5 GEOLOGY 2258B AND 2258C - PATCH/PAINT |  | GEOLOGY | 2258B & 2258C | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 2018-06-06 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS |  | PROJECT INTAKE | Kathryn Uhrich | TBD | JOSE WUDKA |  | Enrico Baez |  | R1 |  | FALSE |  |  | 2019-12-19 | [6 empty] | 1/19/21 DL: Enrico is managing this project. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01 |  | 1
19P000413 |  | 19P000413 | FALSE | CNAS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | Batchelor 3111-Refresh BSL2 lab to accomodate Biosafety Cabinet. The Biosafety. Cabinet will be procured by BPSC. | BATCHELOR | 3111 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | MATTHEW ULRICH | PATTY SPRINGER | Dan Lerman |  | R1 | 107 | FALSE |  |  | 2018-12-17 | [6 empty] | 11/22/19 O-ANS: Project canceled per email from Deborah McWilliams. "The need for an appropriate space to accommodate use of a biosafety cabinet will be addressed in BH 2163 via the campus Batchelor Hall MEP-Tenant Improvement Project managed by PD&C." | 2019-06-12 | Ron Veloz | Preliminary assessment provided by Tiffany Kwok on 2/13/19 email. "For Batchelor 3111, there are a few items that need to be addressed before it can support BSL-2 work. • Floors should be patched to provide a smooth and easily cleanable surface. • Base coves along the wall should be replaced or repaired to provide a smooth and easily cleanable surface. • Base coves under the cabinets on the corners should be provided. • Provide a layer of sealant over the cabinets to ensure that the cabinets are moisture resistant and easily cleanable. • Seal, repair or replace the wooden rack on the wall to provide a moisture resistant and easily cleanable surface. • Ensure the door is self-closing. Since this is not a new facility and the space is not undergoing major renovations, it is not required to provide negative airflow into the space. However, it is still important that the air from the laboratory is not recirculated into clean spaces". | YES | 2019-08-26 | Winter 2020 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20 | 1
20P000038 |  | 20P000038 | FALSE | CNAS | SL5 BATCHELOR HALL 1151- QUOTE FOR ADDING FOB ACCESS TO A DOOR |  | BATCHELOR | 1151 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | RACHEL BEHAR |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-07-24 | [6 empty] | 09/24/19 O-ANS: PROJECT CANCELD BY CLIENT PER EMAIL FROM DEBORAH MCWILLIAMS. |  | Ron Veloz |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
19P000377 |  | 19P000377 | FALSE | CNAS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | Replace the gates on the Schneider House driveway, which secure the property, with the taller iron gates that used to be installed at the Gardens entrance. This will require new fence posts and hinges as well. The taller gates are stored along the side of the garage at Schneider House, and Facilities staff can come see them anytime. Please note this is a safety and security project. | BOT GDN HSE |  | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | R2 | 117 | FALSE |  |  | 2018-11-08 | PO#, schedule the work | 2019-11-18 | 2019-11-28 |  |  |  | 11/26/19, D: This Project is 100% Complete……………11/19/19 DH: Emailed Status Report to customer….11/15/19, DL: We should have A PO this week. Once we have the PO#, we will schedule the work……10/30/19, DL: Project was approved by customer with an FAU #. I will work on providing a PO# as this is maintenance and schedule the work. | 2019-04-05 | Ron Veloz | Replace Gates with new refurbished & modified gates furnished by BG. Install new steel posts and strip and repaint gates. Gate style revised by customer to purchase vendor fabricated light gauge meta gates without spike, per Jodie Holt 10/09/19. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20 | 1
20P000046 |  | 20P000046 | FALSE | CNAS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN | 0001 | PROJECT INTAKE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Enrico Baez |  | R2 |  | FALSE |  |  | 2019-07-31 | [6 empty] | 1/19/21, DL: Enrico B. will manage this priject………….11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Install wireless access controls systems at front and rear entry doors. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01 |  | 1
20P000086 |  | 20P000086 | FALSE | CNAS | SL5 SKYE 2ND FLOOR - KEY CARD ACCESS ESTIMATE |  | SKYE HALL | 2ND FLOOR | CANCELED BY CLIENT | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | R3 |  | FALSE |  |  | 2019-08-19 | [6 empty] | 09/26/19 O-ANS: CANCELED BY CUSTOMER - Estimated cost to go keyless outside of budget. | 2019-09-10 | Enrico Baez | Provide estimate for keyless entry. | YES | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | R3 |  | TRUE |  |  | 2019-03-26 | Schedule the work | 2020-01-31 | 2020-02-21 |  |  |  | 8/5/20, DL: This Project is COMPLETE…….3/25/20, DL: The material is here and we are 95% complete with the work. We will complete the work when we return from the campus closure…………1/31/20 O-DHN: Emailed Status Report to customer…….1/30/20,DL: The pump is now on site but we are still waiting for the fittings. In the mean time, our plumber is putting everything together and is working on the installation. Once the fittings arrive, we will make the connections and the system should be good to go………….1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: The pump is scheduled to arrive on or before 1/31/20. We will schedule the work once we have the pump and material on site…..11/26/19, DL; Emailed Natalie and Sherice the quote for the vacuum pump. We will order the material and schedule the work once we have approval and the pump on site……11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: I sent the vendor a 2nd email requesting an update on the proposal. I also included Natalie on the email so she is aware of where we stand with the proposal……10/30/19, DL: We had a followup meeting with the vendor last week. The vendor is now working on a pump that will best meet our needs……….10/16/19, DL; We are working with a vendor on a quote for a new lab vacuum pump. We are hoping to have a quote in the next week or two…..9/16/19, DL; Estimate was provided to customer last week. If the project is approved, we will work on the plans and permits. Once approved, we will schedule the work…… |  | Ron Veloz | Old SOW Revised SOWInstall exhaust hood, electical receptacle, vacuum pump, vac lines and valves (six valves total) and hood location. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21 | 1
19P000555 |  | 19P000555 | FALSE | CNAS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK | INSTALL OF FENCE FOR RAIN COLLECTOR AT TES TANK | SAT CHIL PL | 0 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | R4 |  | FALSE |  |  | 2019-04-03 | Estimate from contractor | [5 empty] | 10/30/19 O-RVL: RV sent Andrew a message to ask if a decision was made to proceed with this project or if it will be cancelled?" Pending response. END~ 10/16/19, DL; I placed this project on hold as we have not heard back from the customer. We notified the customer of the cost but have not heard back from them. If the project is approved, we will schedule the work………...10/1/19, DL; Ron provide Deborah the propsal and we are waiting for her response to proceed or cancel the project……...9/16/19, DL; Ron submitted the estimate to Debora and the Faculty member last week. If project is approved, we will schedule the work……9/3/19, DL; Plans and estimate are complete. Ron will provide Deborah with a formal estimate and let us know if we will proceed with the work…..8/15/19, DL; Plans are approved. We ware waiting for a estimate from our contractor. Once we have the quote, we will forward the quoted to Deborah for review and approval. Note, this is a recharge project…….8/1/19, DL; Plans are complete pending approval from building official…. |  | Ron Veloz | Install Chain Link fence with gate. Includes grading, gravel and fence posts set in concrete. |  | 2019-10-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000017 |  | 20P000017 | FALSE | CNAS | SL5 COLLEGE BLDG CR200 - PAINT PROJECT |  | COLL BLDG NO | CR0200 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Dan Lerman |  | R4 |  | FALSE |  |  | 2019-07-15 | [6 empty] | 1/30/20, DL: This Project was Canceled per Rohnda via email on 1/29/20……….11/26/19, DL; Provided Ronda with updated quote on 11/25/19: She will present the quote to her team and provide us with an update in the near future if they would like to proceed………11/20/19 O-ANS: Re-assigned to Dan Lerman. Project was originally a paint project but will be outsourced as Recharge project paid for by the customer's department. |  | Dan Lerman |  |  | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | CANCELED BY FS | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | R7 |  | FALSE |  |  | 2019-02-27 | We Need an FAU # | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced. We will schedule the work when we return from campus closure………11/11/19, DL: Project is in the queue to start but we do not have an FAU# as this is a recharge project. I sent Enrico and James an email requesting the FAU#. Once we have an FAU #, I will work on scheudling the work…..10/1/19, DL; Enrico is wtill working on estimate. | 2018-10-19 | Enrico Baez | E. Baez 1. Provide power in ceiling for projector. 2. Install projector center in room between two 4ft light fixtures. 3. Install 2 duplex outlets in 4S box on South West corner of room 4. Remove existing screen. 5. Install new screen centered on South wall. Extend power from existing screen to new screen location. 6. Use existing screen power switch to control new screen. | YES | 2020-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21 | 1
19P000543 |  | 19P000543 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION | TV Bracket &Power/Network box. | CHEMICAL SCI | 342 | CANCELED BY FS | Kathryn Uhrich | TBD | JEFFERY MATUTE |  | Dan Lerman |  | R8 |  | FALSE |  |  | 2019-03-21 | [7 empty] | 2019-10-01 | Ron Veloz | "The Chemistry Department is purchasing a 75" TV to mount in CS 342. The wall that will hold the TV needs to be inspected before any action of mounting the TV is done. The wall that we are hoping to place is the Brown-ish wall, where the projector screen is, opposite to the single whiteboard (Upon entry of CS 342, the leftmost wall). We would like a electrical outlet behind the TV, if possible". RV-Cut back sound proofing (sound soak) to accommodate TV brkt & electrical. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
19P000594 |  | 19P000594 | FALSE | CNAS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS | Take down a dividing wall in this office and move the desks to their old location and rehang the overhead desk bins back into their old locations with inserts still in the walls. | ENTOMOLOGY | 171 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  | R9 |  | FALSE |  |  | 2019-04-26 | [8 empty] | Ron Veloz | TBD | NO | 2019-09-18 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | QUEUE TO START | Kathryn Uhrich | TBD | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 2019-11-25 | [6 empty] | 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01
20P000419 |  | 20P000419 | FALSE | CNAS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | Paint Only | SPIETH | 2312 | QUEUE TO START | Kathryn Uhrich | TBD | ESTELLA DAVALOS | SHERICE UNDERWOOD | PAUL DITTY |  | X |  | TRUE |  |  | 2020-04-22 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Construction | Kathryn Uhrich | TBD | Tracey Kahn, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 1575000 |  | 2018-01-08 | Complete Construction | 2021-01-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2018 | 2021-02-01
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Design | Kathryn Uhrich | TBD | MaryLou Polek |  | Scott Donnell | 2 |  |  | FALSE | 2500 |  | 2019-10-04 | Construction by USDA | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
3560 | 3560 |  | FALSE | CNAS | USDA Modular Bldg Installation | B19-284: Provide and install one (1) 1400 square foot double-wide modular office building with five (5) offices, one (1) being ADA compliant, one (1) ADA compliant unisex restroom, one (1) multi-purpose room with sink. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Construction by USDA | Kathryn Uhrich | TBD | MaryLou Polek |  | Scott Donnell | 3 |  |  | FALSE | 2500 |  | 2019-10-04 | Complete Construction (by USDA) | 2020-12-01 | 2021-02-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | TBD | Wendi Tapia |  | Tameesha Hayes | 4 |  |  | FALSE |  |  | 2020-06-19 | Bidding | [12 empty] | PD&C | FALSE | 2020 | 2021-02-01
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | In Bidding | Kathryn Uhrich | TBD | Mireya Botello Santoyo |  | Scott Donnell | 5 |  |  | FALSE | 32871.65 |  | 2020-07-14 | Construction | [12 empty] | PD&C | FALSE | 2020 | 2021-02-01
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Design | Kathryn Uhrich | TBD | Richard Zapien |  | Scott Donnell | 6 |  |  | FALSE |  |  | 2020-05-08 | Bidding | 2021-04-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-01
3594 | 3594 |  | FALSE | CNAS | R'Garden Grow Pod Installation | R'Garden Gro Pod Installation |  |  | On Hold | Kathryn Uhrich | TBD | Richard Zapien |  | Scott Donnell | 7 |  |  | FALSE |  |  | 2020-05-21 | Secure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-02-01
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Construction | Kathryn Uhrich | TBD | Georgios Vidalakis |  | Scott Donnell | 8 |  |  | FALSE | 15000 |  | 2020-09-11 | Complete Construction | 2021-01-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-01
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Design (Phase 2) | Kathryn Uhrich | TBD | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 9 |  |  | FALSE |  |  | 2016-12-06 | RPU plan review/design (Phase 2) | 2021-06-01 | 2021-08-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-01
3621 | 3621 |  | FALSE | CNAS | NRS Emerson Main Residence Transfer Switch | We are looking to purchase and install a transfer switch to power either just our well pump or the pump and critical circuits at the breaker box by generator at Emerson Oaks when the power is out. What is the best way to contact the Campus Electricians for not only an estimate for the project but for guidance on the best way to set things up? |  |  | New (2/2/21) | Kathryn Uhrich | TBD | Joseph Messin |  | Rowan Reid | 10 |  |  | FALSE |  |  | 2021-02-02 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-02-01
3623 | 3623 |  | FALSE | CNAS | NRS Boyd Deep Canyon Repairs & Upgrades | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ |  |  | New (2/2/21) | Kathryn Uhrich | TBD | Heather Constable |  | Rowan Reid | 11 |  |  | FALSE |  |  | 2021-02-02 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-02-01
3618 | 3618 |  | FALSE | CNAS | NRS James Reserve Upgrades | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. |  |  | New (2/2/21) | Kathryn Uhrich | TBD | Heather Constable |  | Rowan Reid | 12 |  |  | FALSE |  |  | 2021-02-02 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-02-01
19P000428 |  | 19P000428 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES AVC OFFICE PREPARATION |  | STUDENT SERV | 3102 | CANCELED BY CLIENT | LaRae Lundgren | TBD | ANGIE GRAY |  |  |  | 0 |  | FALSE |  |  | 2019-01-03 | [8 empty] | Ron Veloz |  | N/A | 2019-01-22 | SPRING 2019 | FS | FALSE | 2019 | 2021-02-01
19P000370 |  | 19P000370 | FALSE | ENROLLMENT SERVICES | SL5 PATCH AND PAINT CAMPUS TOURS |  | STUDENT SERV | 1137 | COMPLETE | LaRae Lundgren | TBD | ELIZABETH TATUM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SERV | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | TBD | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-22 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-02-01
19P000517 |  | 19P000517 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | COMPLETE | LaRae Lundgren | TBD | DANIELLE GARCIA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-03-07 | Verify scope and schedule work | 2019-12-02 | 2020-12-20 |  |  |  | 1/19/21, DL: This project is complete…………..8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced, We will schedule the work when we return from the campus closure…………11/11/19, DL: I will work on scheduling this project… | 2019-06-17 | Enrico Baez | 6/17/19 E. Baez Conducted site visit with Sean. Will need carpenters to mount TV and electricians to add outlet to North wall. Data not needed. Might need painters depending on how carpenters install TV mount. | YES | 2021-01-19 | FALL 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000384 |  | 19P000384 | FALSE | ENROLLMENT SERVICES | SL5 PATCH HOLES IN WALL AND PAINT |  | STUDENT SERV | 2234 | COMPLETE | LaRae Lundgren | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-22 | finish plans/submit application | 2020-01-10 | 2020-03-27 |  |  |  | 8/5/20, DL: This Project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer…..2/18/20, DL: We are making great progress and still on schedule to be complete before Spring Break begins. We pass drywall inspection on 2/18/20………..1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: Plans are approved. All items have been removed from the space. Abatement is schedule to take place within two weeks…..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were submitted for plan check review. Fire marshal stamped the plans, we are waiting on the final stamp from our building official. Once plans are approved we will order material and schedule the work……..10/30/19, DL: Gunter is working on plans. We are planning to complete the work before Spring Quarter begins. |  | Dan Lerman |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000467 |  | 19P000467 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | WATKINS | 2101 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2019-01-22 | Finish project. | 2019-10-01 | 2019-12-20 |  |  |  | 1/14/20, DL: This project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Project is 99.9% complete. We should be complete with the work by this Friday. Furniture is scheduled to be install this Friday morning……..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL; The project is still on schedule to be completed on 12/12/19…………….10/30/19, DL: This Project is on Schedule to be completed on or before 12/17/19….10/16/19, DL; This project is in progress with a completion date of 12/15/19…….10/1/19, DL; We will schedule the work. Our portion of the project will be completed mid December……….9/16/19, DL; We will work on the plans soon. This project will be complete by 12/21/19….. 09/03/19 O-ANS: Updated Priority to #1 for Fall 2019 per Susan request. 9/3/19, We are scheduled to complete the work before winter break begins….. |  | Enrico Baez |  |  | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000085 |  | 20P000085 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 FACILITES ANNEX B - PAINT OFFICE SPACE |  | FS ANNEX B | 0001 | COMPLETE | Susan Marshburn | Da Lan Dinh | SANDRA MARTINEZ |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 2019-08-19 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000560 |  | 19P000560 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION |  | UV BLDG B | 0240B | COMPLETE | Susan Marshburn | Da Lan Dinh | LESLIE ROSE |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-04-04 | waiting for material to arrive | 2019-08-01 | 2019-08-23 |  |  |  | 9/3/19, DL; This project is 100% complete. We still need to conduct training but the work is complete and training is scheduled…..8/15/19, DL; This Project is 90% Complete and will be complete by the end of the week. Please note. ITS still needs to connect the data lines. Our portion of the work is complete………8/1/19, DL; Plans are approved. Material is ordered. We will schedule the work when the material is on site…. |  | Dan Lerman |  |  | 2019-09-03 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
19P000645 |  | 19P000645 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT | Termite Treatment/Cover Gate House and repair roughtd woos as necessary | BOTAN INFO C |  | CANCELED BY FS | Susan Marshburn | Da Lan Dinh | RONALD ANDERSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2019-05-22 | [8 empty] | Ron Veloz | BOTANIC GARDEN GATE HOUSE (AND OTHER STRUCTURES) REQUIRES EXTERMINATION OF TERMITES- WITH INSPECTION RESULTS RECEIVED BY ERS |  | 2019-08-29 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 2020-09-17 | Begin RFQ Process | [12 empty] | PD&C | FALSE | 2020 | 2021-02-01
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | In Bidding (Re-bid) | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 3 |  |  | FALSE | 1340000 |  | 2019-05-15 | Award Contract | 2021-03-01 | 2021-09-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3527 | 3527 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Central Utility Plant Fire Alarm | Replace aging and non-replaceable fire alarm system, and conduit. Conduit is damaged and only 10% of wiring is usable. ( fire alarm system and devices are failing and they are not supported by manufacture ) | CNTRL UTL PL |  | In Bidding | Susan Marshburn | Da Lan Dinh | Ben Kochevar |  | Daneca Stevens | 4 |  |  | FALSE |  |  | 2019-05-08 | Award Contract | 2021-03-01 | 2021-03-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 2020-03-30 | Projects to be assigned | [12 empty] | PD&C | FALSE | 2020 | 2021-02-01
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 6 |  |  | FALSE | 600000 |  | 2019-06-18 | Complete Construction | 2020-12-01 | 2021-05-28 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3550 | 3550 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Skye Hall HVAC Replacement | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | SKYE HALL |  | In Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 1177000 |  | 2019-09-05 | Award Contract | 2021-05-01 | 2021-08-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 432510 |  | 2016-02-25 | Bidding | 2021-03-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-01
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | In Programming | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 600000 |  | 2019-09-05 | FS Direction | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Programming | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 9 |  |  | FALSE | 500000 |  | 2019-09-05 | FS Direction | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 1500000 |  | 2019-11-06 | On Hold | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 2019-02-14 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 16 |  |  | FALSE | 1250000 | 0 | 2018-10-17 | FS Direction | [12 empty] | PD&C | FALSE | 2018 | 2021-02-01
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | Katie Sanchez |  | Gerald Caraig | 20 |  |  | FALSE | 2600000 |  | 2016-05-19 | Funding & Approval | [12 empty] | PD&C | FALSE | 2016 | 2021-02-01
3064 | 3064 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Botanic Gardens Basin Silt Removal | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | BOTAN INFO C |  | In Funding | Susan Marshburn | Da Lan Dinh | Toshio Ishida |  | Scott Donnell | 29 |  |  | FALSE | 110000 |  | 2016-04-20 | Decision Memo | [12 empty] | PD&C | FALSE | 2016 | 2021-02-01
3195 | 3195 |  | FALSE | FAC-PLNG-DESIGN-CONST | North District | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 4146146.55 |  | 2016-10-26 | Complete Construction | 2019-07-01 | 2021-08-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-01
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | 2021-03-01 | 2021-07-01 | [10 empty] | PD&C | FALSE | 1900 | 2021-02-01
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Rivera Library Arches/Arcade Repair | Paint and replace roof. | RIVERA LIB |  | Bids received, award on hold due to DM funding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Scott Donnell | 99 |  |  | FALSE | 240000 |  | 2016-05-06 | Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-02-01
19P000411 |  | 19P000411 | FALSE | GRAD DIV | SL5 PAINT, CARPET AND BLINDS |  | UNIV OFC BLD | 150 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-14 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
19P000572 |  | 19P000572 | FALSE | GRAD DIV | SL5 PATCH, PAINT, AND CARPET UOB 152 |  | UNIV OFC BLD | 152 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-11 | Awaiting installation of carpet | [5 empty] | 06/28/19 O-ANS: Paint phase complete and awaiting carpet change. |  |  |  |  | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000003 |  | 20P000003 | FALSE | GRAD DIV | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | ADD POWER/DATA, PATCH/PAINT | UNIV OFC BLD |  | PLAN DEVELOPMENT/CHECK | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS | CHERYL GERRY | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-07-02 | schedule the work | 2021-02-17 | 2021-03-27 |  |  |  | 2/1/21, DL: WE will schedule this project to start in 2- weeks……………….1/19/21, DL: Plans were approved and we will schedule the work in the near future………. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Permit is approved. We need to verify floor covering. Once floor covering is confirmed and ordered, we will schedule the work………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We will need plans as we are installing a new hydration station and a Counter top that needs to be ADA compliant…………We started the plans and will submit them for a permit and plan check review within 2- weeks……….10/30/19, DL: No Plans will be needed. We will plan on scheduling the work shortly after Thanksgiving……. | 2019-06-13 | Enrico Baez | 9/24/2019 E. Baez--SCOPE-- 1. Removal and disposal of one bulletin board and two director cases. 2. Removal and disposal of abandoned telephone mounting bracket. 3. Remove and dispose of abandoned alarm box in wall. 4. Patch and paint walls in lobby and public restroom area. 5. Provide electrical connection for wall mounted monitor. 6. Cut access for data boxes. 7. Install monitor mount on wall. 8. Construct 7" x 18" laminate counter top and install in Lobby. | YES |  | FALL 2019 | FS | FALSE | 2019 | 2021-02-01
19P000399 |  | 19P000399 | FALSE | GRAD DIV | SL5 NEW CARPET + WALL PAINT |  | UNIV OFC BLD | 100 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-06 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
18P000274 |  | 18P000274 | FALSE | GSOE | SL5 SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 |  | CHILD DEV N |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES | BRANDON BARBOSA | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-18 |  | 2018-05-01 | 2019-01-31 |  |  |  | 2/14/19, DL; This project is Complete………….2/1/19, DL; This project is 99.9% Complete. We still need to conduct Final inspection with Building inspector……1/15/19, DL; The door and automatic opener is scheduled to be installed on 1/22/19……..12/14/18, DL; This project is 95% complete. The contract for the door and ADA operator was awarded today. We will schedule the work shortly after the new year…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Conducted site visit with Gilbert. We need to have a meeting to determin if this work is part of the SLA…… DL, 6/16/18; We still need direction, SLA or Recharge?.......DL, 7/11/18; This Project will require Plans and Permits. We will start on the Plans next Week. We will also issue work orders for work we will complete with in house staff. The Concrete work and Entry Door will need to be contracted out. Target Complete date is 10/1/18……..DL, 7/25/18; Work orders are produced. Planing to walk the project with Chris, Steve B and Robert C. thisw week or next week. We will submit plans to Bob Williams for the contracted work next week……DL, 8/8/18; Completed site visit with Robert C. Steve B, Steve T. and Chris; the Plumbers are complete. The carpenters and electricians will work on their items over the next three weeks. The Plans will be ready to submit on 8/9/18. Once plans are approved, we will proceed to go out to bid for the Concrete and the ADA operator. Target complete date is 9/21/18…….DL, 8/22/18; Plans were apprroved, Concrete Contract is being executed. Still working on Door and ADA operator……..DL, 9/6/18; NTP for Concrete will be issued on Monday. I will schedule the work. I need to follow up on the door order and the ADA operator…….DL, 9/19/18; Concrete walkway scheduled to start on 9/20/18. The new door and Frame will arrieve in 3-5 weeks. We will schedule the install when the new door and frame are on site…….DL, 10/4/18; Concrete work is complete. Still need handrail, signage, door and ADA operator. Target date is Early November….DL, 11/7/18; Project is 95% complete. Contract is being processed to install the new Door, Door Fram and ADA operator. Goal is to have the work complete befor the winter break…… |  | Enrico Baez |  | YES | 2019-02-14 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000313 |  | 18P000313 | FALSE | GSOE | SL5 SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-15 | [6 empty] | 18W011689 Work order was cancelled because it has the same scope and is a duplicate………DL, 6/16/18; Contract is being awarded this week. Weill are scheduled to have this work completed by fiscal closing……DL, 7/25/18; This Project is 100% Complete…..9/13: Zee - Customer noted paint peeling; updated to status to back in progress for work to be addressed.......DL, 9/19/18; The contractor is on site repairing the walls and painting. The work should be complete this week.......dl, 10/4/18; tHIS PROJECT IS 100% Complete..... |  | Paul Ditty |  | N/A | 2018-10-22 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000628 |  | 19P000628 | FALSE | GSOE | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2129 | COMPLETE | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-05-15 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000031 |  | 20P000031 | FALSE | GSOE | SL5 SPROUL HALL 1124B- PATCH/PAINT OFFICE |  | SPROUL | 1124B | COMPLETE | Thomas Smith | Sally Tavizon | MARICELA ARCINIEGA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-07-22 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000054 |  | 19P000054 | FALSE | GSOE | SL5 PATCH & PAINT OFFICE |  | SPROUL | 2131 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-26 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000627 |  | 19P000627 | FALSE | GSOE | SL5 SPROUL HALL, RM 2120- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2120 | CANCELED BY CLIENT | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 | 2 | TRUE |  |  | 2019-05-15 | [6 empty] | 01/29/20 O-ANS: Canceled per email from customer Karen Naples: "I’ve checked with Sally and this request to paint the Sproul 2120 office can be cancelled. We will submit a new work order if we need to have the office painted at a later time." 08/13/19 O-ANS: Customer requested that project be moved to Fall 2019 list for prioritization. |  | Paul Ditty |  |  | 2019-01-29 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01
20P000077 |  | 20P000077 | FALSE | GSOE | SL5 SPROUL HALL 1223 - PATCH AND PAINT |  | SPROUL | 1223 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-08-06 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-25 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000237 |  | 19P000237 | FALSE | GSOE | SL5 PATCH AND PAINT OFFICE - SPROUL 1206 |  | SPROUL | 1206 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-09-05 | work is in progress | 2019-03-01 | 2019-04-18 |  |  |  | 4/15/19, DL; Project is 100% Complete….. 2/1/19, DL; This project will start on 3.1.19. We will need to abate ACM before we can start. Jess will isuue the 14- day notification to the AQMD. Once we have confirmation, we will schedule the work…….. | 2018-10-05 | Enrico Baez | Carpenters: Removes sliding chalk boards in 1206 and 1206 and fill in with wall. Remove patched in panels on left of chalk board in 1206. Patch where " do not enter" signs were removed. Electricians: Disconnect power to two "do not enter" signs above doors. Abatement: Remove approx 300 sq.ft. of ACM VCT Flooring: replace flooring with either VCT of vinyl plank. Painters: Patch and paint, at least one wall accent wall. | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000217 |  | 19P000217 | FALSE | GSOE | SL5 PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 |  | SPROUL | 1359 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-27 | Work has started | 2019-03-01 | 2019-05-23 |  |  |  | 4/15/19, DL; This project is 100% Complete…..2/1/19, DL; This proect will start on 3/1/18 and should be complete by 4/1/19…… | 2018-09-18 | Enrico Baez | Scope of work Carpentry Remove 20 feet of built-in wood cabinets and counter top. Install TV mount on South wall. Remove and replace white board on North wall. Abatement Abate approximately 200 square feet of 9â€ x 9â€ VCT tile and base cove Flooring Install carpet similar to what is in room 1357 Replace base cove. Walls Patch and paint walls. Electrical Install duplex outlet for TV Replace fluorescent lamps with LED lamps TV Install data point and Internet connection to support video conferencing. Custodial Vacuum dust from ceiling tiles. 9/18/18 EB-Conducted site visit. Request to remove cabinet, abate VCT, install carpet, mount TV. Electrical and date lines needed. Install white board. Replace fluorescent tube with LED. 9/13/18 EB-emailed Karen Naples to schedule site visit. | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000229 |  | 19P000229 | FALSE | GSOE | SL5 RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-08-29 | [6 empty] | 6/15/19, DL; This Project is 100% Complete….. |  | Enrico Baez |  | YES | 2019-06-15 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | In Funding | Gerry Bomotti | Sharyl Murdock | Gerald Caraig |  | Daneca Stevens | 2 |  |  | FALSE | 50000 |  | 2019-07-30 | Secure Funding | 2021-05-01 | 2021-06-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
18W007453 |  | 18W007453 | FALSE | ITS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-11-30 | waiting for bid from contractor | 2019-04-01 | 2019-06-29 |  |  |  | 07/22/19 O-ANS: Work Order converted to project # 19P000433. For further updates, see 19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  |  |  |  | 2019-07-22 | Winter 2019 | FS | FALSE | 2017 | 2021-02-01 | FY 19-20
18P000474 |  | 18P000474 | FALSE | ITS | SL5 MS&E ELECTRICAL MODIFICATIONS FOR ITS |  | MAT SCI ENGR | 119 | COMPLETE | Danna Gianforte | Shelley Gupta | MICHAEL CAPRIOTTI |  | Robert Corey |  |  | 1 | FALSE |  |  | 2018-06-13 | Complete the balance of electric | 2019-04-01 | 2019-04-12 |  |  |  | 3/28/19, DL; This Project is 100% Complete…….2/28/19, DL; Work is scheduled with Darrenn F. for Spring Break…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. |  | Enrico Baez |  | YES | 2019-03-28 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000293 |  | 19P000293 | FALSE | ITS | SL5 PAINT ESTIMATE REQUEST |  | TELEPHONE |  | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-21 | [6 empty] | n/a |  | Paul Ditty |  | N/A | 2018-10-24 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19W002419 |  | 19W002419 | FALSE | ITS | SL5 ITS CENTER - INSTALL CARD READER ACCESS |  | ITS CENTER | 161 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-08-09 | [11 empty] | 2019-01-08 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
18P000471 |  | 18P000471 | FALSE | ITS | SL5 WCH INSTALL SECURITY FENCE |  | CHUNG HALL | 134 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  |  | 5 | FALSE |  |  | 2018-06-12 | [6 empty] | DL, 7/4/18; Walked this project with Angel, This request is to install security fence with Sliding gate and welded webs to increase security. Space is vacant and ready to schedule work. Need to walk with Corey to see if this is a project they can do or sub out to De ANza fence......DL 7/25/18; Still need to walk project with Corey. Dl, 8/10/18; Site walk complete, we are waiting on estimates. WE will try and schedule the work with in the next 30- days....DL, 8/22/18; Work is scheduled for August 27th. Still need to order hardware.....DL, 9/6/18; The fence is installed and Angel is very Happy, but I need to check the project to verify we are good to go....DL, 9/19/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-09-19 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000373 |  | 19P000373 | FALSE | ITS | SL5 URGENT-INSTALL RECPTACLE, ENCLOSURE & MOUNT BRACKET |  | GERMPLASM | 881 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-07 | [6 empty] | <div>mount a bracket to the Network Pole at AgOps. This will include mounting a bracket, an enclosure and a 20 Amp electrical receptacle.</div> |  | Ron Veloz |  |  | 2019-02-26 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000252 |  | 18P000252 | FALSE | ITS | SL5 CHASS INT S REPLACE ELECTRICAL SCREENS |  | CHASS INT S | 2130 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | JORGE MACIAS |  | Dan Lerman |  | 1 | 2 | FALSE |  |  | 2017-12-21 | [7 empty] | 2018-06-21 | Ron Veloz |  | YES | 2019-01-24 | Summer 2018 | FS | FALSE | 2017 | 2021-02-01
18P000382 |  | 18P000382 | FALSE | ITS | SL5 ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | PHYLLIS FRANCO |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 2018-04-05 |  | 2018-12-14 |  |  |  |  | 1/15/19, DL, This project is Complete……12/14/18, DL; This project is scheduled to be complete shortly after the winter break…….This project was scoped previously with the IR Team. We may need plans or a permit because we are installing a Dutch door…..DL, 7/11/18; Need to produce work orders and schedule the work….. DL, 7/25/18; Still need to produce work orders and schedule the work. Target date is 10/1/18 | 2018-07-06 | Ron Veloz |  | YES | 2019-01-15 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000381 |  | 18P000381 | FALSE | ITS | SL5 ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 3 | 4 | FALSE |  |  | 2018-04-05 |  | 2018-12-14 |  |  |  |  | 1/15/19, DL; This project is complete. Note, Duffy only wanted the dutch door completed……..12/14/18, DL; This project is in progress and should be complete shortly after the new year……`DL, 7/11/18; Need to walk the project and schedule the work…… | 2018-07-06 | Ron Veloz |  | YES | 2019-01-15 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000021 |  | 19P000021 | FALSE | ITS | SL5 ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS |  | ITS CENTER |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-07-12 | Install Power and data | 2019-03-28 | 2019-04-26 |  |  |  | 4/15/19, DL; This project is 100% Complete…… 3/28/19, DL; Monitors are done. Nee to finish the install of data and power…….12/14/18, DL; Still need to review scope….. |  | Enrico Baez | 1. Telecom Building - Conference Space Electricians Power Requirements: • Install double duplex(quad outlet), AC power on East wall at display location (4S Box) low profile • All electrical junction boxes, J-boxes, and conduit can be surface mounted. J-boxes to be located behind TV. Data Requirements: • Install single gang junction box on East wall behind display with Panduit running to specified location (for telecom network drops) o Single gang, low profile junction box o (conduit to be lead through masonry wall above T Bar ceiling in adjacent room. O (Low profile boxes for data ports) • Single gang box, mounted behind TV location, for data. • Note: Non-traditional wall – masonry Carpenters • Install mounting bracket for display on East wall • note: Non-traditional wall – masonry Painters • Paint junction boxes and conduit to match wall. 2. Intellicenter - First Floor Common Area Carpenters • Install mounting brackets on East Wall for each display (2 total) • (ITS to note the top of the bracket) 3. SOM-E - 1675A DataCenter Electricians Power Requirements: • Install double duplex(quad outlet), AC power on North wall at each display location (2 total) o Surface mounted J Boxes and Conduit Data Requirements: • Install single gang junction box on North wall at each display location with conduit/panduit running to specified location (for telecom network drops) (2 total) o (Wire mold boxes for both power and data) (2inch boxes – low profile boxes for data ports) o Data conduit to stub up and terminate through T-bar ceiling panels. • All conduit and J-boxes to run upward through T-bar ceiling Carpenter • Install mounting bracket for each display on North wall (2 total) • Install backing for mounts in adjacent data room in shelving. Painters • Patch and paint installation area as needed Location Notes • Non-traditional wall – drywall over carpentry 4. ITS Building - 174 Electricians • Install double duplex, AC power on East wall at each display location (2 total) • Install single gang junction box on East wall at each display location with conduit above ceiling (for telecom network drops) (2 total) o Terminate Data conduit above T-bar ceilings Carpenters: • Install mounting bracket (marked on the wall) for each display on East wall (2 total) Location Notes: • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 5. ITS Building - Main Lobby Electricians • Install double duplex, AC power on South wall at display location • Install single gang junction box on South wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on South wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 6. ITS Building – AVC / CIO’s Office (ITS 147) Electricians • Install double duplex, AC power on North wall at display location • Install single gang junction box on North wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on North wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 7. ITS Building Room 138 Electricians • Install double duplex, AC power on East wall at display location • Install single gang junction box on East wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on East wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000194 |  | 18P000194 | FALSE | ITS | SL5 TELEPHONE WINDOW REPLACEMENT |  | TELEPHONE | 101 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 5 | 6 | FALSE |  |  | 2017-11-20 | [6 empty] | 07/23/19 O-ANS: Canceled by customer per notes in FAMIS. |  | Enrico Baez |  | YES | 2018-10-19 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | C&C CARPORT | 161 | COMPLETE | Danna Gianforte | Shelley Gupta | SHELLEY GUPTA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-01-07 | Waiting for bid for customer. | 2020-01-20 | 2020-03-31 |  |  |  | 8/5/20, DL: This Project is complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have the contract, we will schedule the work……………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Project was approved by Shelley. We will work on the contract. Once we have the notice to proceed from contracts, we will order the material and schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Sent Shelley another follow-up email today and she has not verified if she would like to move forward with the project………10/30/19, DL: Sent Shelley the updated quote last week and she has not responded. I sent Shelley a followup email today asking her to let me know if she would like to proceed with the work……..10/16/19, DL; Had a meeting with Shelley, we modified the scope of work and software for the project. We are now revising the quote with our vendor. We should have an updated quote within the next two weeks. If Shelley approves the work and scope, we will proceed….10/1/19, DL; I have a meeting with Shelley this afternoon to review proposal. If she approves the project we will submit plans for a building permit……8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was cancelled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; We have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28/19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21 | 1
18P000273 |  | 18P000273 | FALSE | LIBR | SL5 RIVERA LIB -RESTROOM REFRESH PROJECT |  | RIVERA LIB |  | TO BE PERFORMED BY PD&C | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2018-01-18 | [6 empty] | DND 12/13/18: Customer advised maintenance requests related to project request has been addressed. Renovation work to be performed by PD&C and customer submitted a CPMS request. DL, 6/16/18; Need to schedule site visit with Dave and Chris P…….DL, 7/11/18; Chris and I will walk this poroject next week…..Wlaked projects with Chris. We need to review in more detail to better determin the process for this project…..DL, 9/6/18. WE need to discuss what we are going to do with this project.... We walked the project but we now need Direction from Facilities leadership… |  | Dan Lerman |  | YES | 2018-12-13 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
20P000188 |  | 20P000188 | FALSE | LIBR | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 |  | ORBACH LIB | 204 | CANCELED BY FS | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-10-23 | Obtain floor covering samples | [5 empty] | 11/19/20 O-ANS: Declined to move forward by FS Admin but may revisit in future prioritization period. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: We are working on floor covering samples that will work for the space. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. | RIVERA LIB |  | On Hold | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 2018-11-27 | Client approval/funding | [12 empty] | PD&C | FALSE | 2018 | 2021-02-01
3104 | 3104 |  | FALSE | PALM DESERT GRAD CTR | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Funding | Tamara Hedges | Zelda Glenn | Zelda Glenn |  | Scott Donnell | 2 |  |  | FALSE | 22000 |  | 2016-05-12 | Approval & Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-02-01
19P000317 |  | 19P000317 | FALSE | PB&A | SL5 HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 | conversation with Susan Marshburn and Bob Brumbaugh. | PENTLAND A |  | CANCELED BY FS | Gerry Bomotti | TBD | RICHARD GEIGER | [5 empty] | FALSE |  |  | 2018-10-03 | [11 empty] | 2019-01-14 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
18P000459 |  | 18P000459 | FALSE | PB&A | SL5 BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 |  | BARN |  | COMPLETE | Gerry Bomotti | TBD | GUSTAVO PLASCENCIA |  | Dan Lerman |  |  | 6 | FALSE |  |  | 2018-05-31 | [8 empty] | Enrico Baez |  | YES | 2018-09-21 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18W011772 |  | 18W011772 | FALSE | PB&A | SL5 PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | Canceled per customer on priority list 7/3/18 | PRINT MOD |  | CANCELED BY CLIENT | Gerry Bomotti | TBD | PRISCILLA MARTIN |  | Dan Lerman |  |  | Canceled | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/29/18; Pasted from WO; install an outside electrical outlet based on the attached amazon specs. also estimate for removing and sealing the outside vent from the copier. fyi_the copier will be moving within the next few months…..DL, 7/11/18; Need to verfy scope and schedule the work...... |  | Enrico Baez |  | YES | 2018-07-03 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000209 |  | 19P000209 | FALSE | PB&A | SL5 OLD EH&S SITE- FS ANNEX A REMODEL |  | ENV HLTHSFTY | 100 | COMPLETE | Gerry Bomotti | TBD | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 2018-08-24 | Schedule the work | 2019-05-16 | 2019-06-28 |  |  |  | 7/1/19, DL; This project is 100% Complte….6/17/19, DL; This project is almost complete. Target complete date is 6/26………….5/31/19, DL; This project is in progress. Our goal is to have the projected completed by June 28th……. 5/15/19, DL; We are schedule to start the demo tomorrow. Project timeline is 3-4 weeks….3/28/19, DL; Gunther is working on plans……3/18/19, DL; Conducted site visit with Chris, Hassan and Francis last week. We will work on plans and permits…….9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
19P000208 |  | 19P000208 | FALSE | PB&A | SL5 PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | Canceled per customer on priority list 9/17/18 | THE PLAZA |  | CANCELED BY CLIENT | Gerry Bomotti | TBD | CARLA CHAPPLE |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-14 | [8 empty] | Enrico Baez |  | NO | 2018-09-17 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18W009630 |  | 18W009630 | FALSE | PB&A | SL5 BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. | PHYS PL STOR | 100 | CANCELED BY CLIENT | Gerry Bomotti | TBD | JUDY HODGE |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-22 | [6 empty] | 3/28/19, DL; This project is cancelled per Judy Hodge….DL, 6/16/18; Project includes demo wall/door install new wall, dry wall, paint, door, eletrical outlets, lighting, smoke relocation, lighting motion, new t-bar, relocate heat pump, andn install new carpet…...DL, 7/11/18; Need to work on plans….. Target complete date is late Fall..... |  | Enrico Baez |  | YES | 2019-03-28 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000432 |  | 18P000432 | FALSE | PB&A | SL5 BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 |  | BANNOCK H | H0101 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-05-04 | [8 empty] | Paul Ditty |  | N/A | 2018-07-13 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000390 |  | 18P000390 | FALSE | PB&A | SL5 UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD |  | UV BLDG B | 0240B | COMPLETE | Gerry Bomotti | TBD | LESLIE ROSE |  | Paul Ditty |  |  | 1 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000094 |  | 18P000094 | FALSE | PB&A | SL5 OBAN LAUNDRY ROOM RENOVATION |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2017-09-08 | [6 empty] | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on bid. 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/12 EB- rec'd approval to contract with Design West to consult on electrical panel upgrade. |  | Enrico Baez |  | YES | 2019-01-19 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
18P000106 |  | 18P000106 | FALSE | PB&A | SL5 HOUSING PROJECT - OBAN REC ROOM REMODEL |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 3 | FALSE |  |  | 2017-09-14 | [6 empty] | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. DL, 7/11/18; Per Susan this project is back on track. Project is scoped. Gunther will start working on the plans and permits. Once we have the approved permit. still need to check in with Susan on a few items.....Target complet date will be mid- fall...... |  | Enrico Baez |  | YES | 2019-01-19 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
17P000254 |  | 17P000254 | FALSE | PB&A | SL5 FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS | Emergency Egress | CORP PP WHSE | 0106B | CANCELED BY CLIENT | Gerry Bomotti | TBD | DALAN DINH |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-06-07 | Install data and power | [5 empty] | 05/08/19 O-ANS: Canceled by customer per email from Deborah McWilliams. .2/1/19, DL; Material is ordered with a 4-6 week lead time. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DD 10/6: On hold pending discussion on space…..DL, 7/11/18; I understand there is movement on this project but I need to check in with John P. or Chris P. for a status update. |  | John Peraino |  | NO | 2019-04-05 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
18P000373 |  | 18P000373 | FALSE | PB&A | SL5 POLICE BLDG PAINTING IN DISPATCH AREA |  | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | KELLY DUNCAN |  | Paul Ditty |  |  | 8 | FALSE |  |  | 2018-04-02 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000369 |  | 18P000369 | FALSE | PB&A | SL5 BOYCE X-RAY IRRADIATOR PROJECT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 1407 | CANCELED BY CLIENT | Gerry Bomotti | TBD | KAREN JANIGA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-27 | [6 empty] | 12/14/18, DL; This project was cancelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……DL, 5/9/18; Need to work on plans/permits…..DL, 6/16/18; Meeting with Bob and confirmed what is needed. I will work with Gunther on plans. Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall…..DL, 11/7/18; Material is on site. We will schedule the work soon…… |  | Ron Veloz |  | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000222 |  | 19P000222 | FALSE | PB&A | SL5 PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | TBD | RICHARD GEIGER |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-02 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-01 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000247 |  | 19P000247 | FALSE | PB&A | SL5 LOTHIAN FIRST FLOOR COMMON AREA FLOORING |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | TBD | RICHARD GEIGER |  | Jess Hernandez |  |  |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez |  |  | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000282 |  | 18P000282 | FALSE | PB&A | SL5 EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 |  | POLICE BLDG |  | COMPLETE | Gerry Bomotti | TBD | LISA MARTIN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-25 | [6 empty] | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work…..DL, 5/9/18; We need to submit plans……DL, 7/11/18; This still needs to be scheduled......DL, 8/8/18; Enrico Confirmed this project is 100% Complete.... |  | Enrico Baez |  | YES | 2018-08-10 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000324 |  | 18P000324 | FALSE | PB&A | SL5 HINDERAKER PATCH AND PAINT |  | HINDERAKER | 4118 | COMPLETE | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-02-26 | [8 empty] | Paul Ditty |  | N/A | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
20P000158 |  | 20P000158 | FALSE | PB&A | SL5 FS ADMIN OFFICE - TOUCH-UP PAINT AROUND BUILDING |  | FS ADMIN |  | COMPLETE | Gerry Bomotti | TBD | DA LAN DINH |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-03 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000169 |  | 20P000169 | FALSE | PB&A | SL5 LOTHIAN LO-G104-OFFICE - JOB WALK FOR REMODEL OF SCOTTY'S |  | LOTHIAN HALL | SCOTTY'S | CANCELED BY CLIENT | Gerry Bomotti | TBD | FRED OFFENEY |  | John Peraino |  | - |  | FALSE |  |  | 2019-10-09 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000401 |  | 19P000401 | FALSE | PB&A | SL5 PATCH HOLES IN WALL AND PAINT |  | HINDERAKER | 4148E | COMPLETE | Gerry Bomotti | TBD | SHANNON TIMMONS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
19P000414 |  | 19P000414 | FALSE | PB&A | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | Seth Morrison |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-12-17 | pending material delivery | 2019-10-16 | 2019-11-27 |  |  |  | 8/5/20, DL: This Project is Complete………….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: We have the motor on site, we are working on the permit for the crane. Once we have the crane lift permit, we will schedule the install…………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: We are working on the new motor platform. It is our goal to install the new motor in late January. Once the motor is installed, we will be able to identify if additional work is needed…….11/19/19 DH: Emailed Status Report to customer…..11/15/19, DL: Material has not arrived……..10/30/19, DL: The new exhaust fan is ordered with a 2- 4 lead time. Once the exhaust fan arrives, we will schedule the install……….10/16/19, DL; We are in the process of the work. At this current time, we are not modifying the building to where permits may not be required…….10/1/19, DL; This is in the queue for plans, we will start the plans in the next 3-4 weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 20-21
20P000008 |  | 20P000008 | FALSE | PB&A | SL5 EHS 1133 - PATCH / PAINT AND FIX HOLES IN WALLS |  | ENV HLTHSFTY | 1133 | COMPLETE | Gerry Bomotti | TBD | CESAR PLA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-07-08 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-07 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000083 |  | 20P000083 | FALSE | PB&A | SL5 STUDENT SERVICES - INSTALL 8 CUBICLES - CP00003537 | Installation of BKM Cubicles with electric and Data | STUDENT SERV | 3rd Floor | COMPLETE | Gerry Bomotti | TBD | SHARYL MURDOCK |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-06-25 | We are on schedule | 2019-12-16 | 2020-01-01 |  |  |  | 1/14/20, DL: This project is 100% Complete………..11/18/19 DH: Emailed Status Report to customer…..10/30/19, DL: The plans were approved and we are scheduled to do the work in December…………10/16/19, DL: Plans were submitted this week…….. |  | Enrico Baez | Scope completed by Dan Lerman | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000241 |  | 19P000241 | FALSE | PB&A | SL5 PATCH/PAINT IN OFFICE 2122 HINDERAKER |  | HINDERAKER | 2122 | CANCELED BY CLIENT | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-06 | [8 empty] | Paul Ditty |  | N/A | 2018-09-13 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 2019-12-04 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2019 | 2021-02-01
19P000236 |  | 19P000236 | FALSE | PB&A | SL5 EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION |  | ABER INVER | A0100 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 10 |  | FALSE |  |  | 2018-09-04 | [6 empty] | JP 04/04/19 2/8/19 This project is complete. JP Estimated completion end of February | 2018-11-01 | Enrico Baez |  | YES | 2019-04-04 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000192 |  | 19P000192 | FALSE | PB&A | SL5 MAIL-PAINTING |  | MAIL |  | COMPLETE | Gerry Bomotti | TBD | PRISCILLA MARTIN |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000235 |  | 19P000235 | FALSE | PB&A | SL5 RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | Customer to determine scope of work. | ABER INVER | A0100 | CANCELED BY CLIENT | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 11 |  | FALSE |  |  | 2018-09-04 | [6 empty] | JP 04/04/19 Project cancelled per Housing/Lisa | 2018-11-01 | Enrico Baez |  | YES | 2019-04-04 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000015 |  | 19P000015 | FALSE | PB&A | SL5 POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING |  | POLICE TRLR | 1 | COMPLETE | Gerry Bomotti | TBD | KELLY DUNCAN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-07-10 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000233 |  | 19P000233 | FALSE | PB&A | SL5 PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | FS to coordinate with customer to scope the work. | MAIL | 884 | CANCELED BY FS | Gerry Bomotti | TBD | AMY EVERETT |  |  |  | 12 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Enrico Baez |  | YES | 2018-09-24 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000363 |  | 18P000363 | FALSE | PB&A | SL5 PAINT STOREHOUSE ADMINISTRATIVE OFFICE |  | CORP B |  | COMPLETE | Gerry Bomotti | TBD | ERICA HENDERSON |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-03-26 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000665 |  | 19P000665 | FALSE | PB&A | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | Existing telephone-communications building on University Ave requires repairs and renovation in preparation for new use as fire safety offices. | TELEPHONE |  | COMPLETE | Gerry Bomotti | TBD | Carmen Long | Melissa Garrety | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-03 | tape, mud, prime&Paint | 2019-08-14 | 2020-01-17 |  |  |  | 2/19/20; This project is complete. We still need to paint the door black but this was not part of the original scope. The paint shop will paint the door in the next two weeks………… 1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL:. This project is 99.9% complete with a few minor punch list items…..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project is on track to finish before the new year with a punch items to be addressed after the new year. IT services still needs to install data and phone. Landscape services is working on the landscape but the landscape was not part of the original scope. Sharyl in is the process of coordinating keys, alarm code and setting up the delivery of the furniture for her team. Overall, we are all in good shape.…….11/19/19 DH: Emailed Status Report to customer…..11/11/19,DL: This project is still on schedule to be complete before the new year……….10/30/19, DL: This project is in progress and on track to be complete before the new year…………….10/16/19, DL: Drain, waste, vent and concrete is complete. We started framing this week. We will start rough electrical and rough plumbing next week……..9/3/19, DL; Abatement was complete this weekend. Trades are scheduled and we are on track for 11/15/19 completion date…..8/15/19, DL Plans were approved this week. Abatement is still needed and the 14- day notification to AQMD is complete. We are on track to complete the work by mid November……. |  | Enrico Baez |  |  | 2020-02-19 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000227 |  | 19P000227 | FALSE | PB&A | SL5 DINING STORAGE ROOM CONVERSION |  | BANNOCK J | J0100 | COMPLETE | Gerry Bomotti | TBD | DARCI LOMBARD |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 05/16/19 O-ANS: Project complete per John P as of 05/16/19. 04/04/19, JP: This project has been placed on hold per Housing Edwin. 2/8/19: JP storage room slated to be completed simultaneously with break room as water supply connections will be done together with break room. Completion date for both is approximately three weeks. |  | Enrico Baez |  | YES | 2019-05-16 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000425 |  | 19P000425 | FALSE | PB&A | SL5 PAINT VIDEO PRODUCTION SUITE & HANG ITEMS |  | HINDERAKER | 1159A | COMPLETE | Gerry Bomotti | TBD | LISA CUSICK |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-20 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
19P000224 |  | 19P000224 | FALSE | PB&A | SL5 PAINT EXTERIOR RAMP AT HUB MODULAR |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | TBD | MIKE CLEMONS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000308 |  | 19P000308 | FALSE | PB&A | SL5 ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK |  | ABER INVER |  | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | JP 04/04/19 Project Complete DL 10/4/18; Jess currently has this project scheduled for Winter break. |  | Enrico Baez |  |  | 2019-04-04 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000307 |  | 19P000307 | FALSE | PB&A | SL5 LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 5 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… | 2018-10-03 | Enrico Baez |  | N/A | 2019-01-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000232 |  | 19P000232 | FALSE | PB&A | SL5 BANNOCKBURN J-104 BREAK ROOM UPGRADE | Scheduled work with trades anticipated 60% completion by Jun 15th. | BANNOCK I | I0105 | COMPLETE | Gerry Bomotti | TBD | RICHARD GEIGER |  | John Peraino |  | 6 |  | FALSE |  |  | 2018-09-04 | [6 empty] | 6/14/19, JP; Project on schedule to be completed June 30th 2019. 05/16/19 O-ANS: Project to be 60% completed by June 15th per John P. 04/04/19 JP: This project placed on hold per Housing/Edwin. Finishing up the cabinet and lighting order, will be submitting to purchasing today. Scheduling installation of VCT flooring pending per Tony’s Flooring, will have date this week. New ceiling tiles have been delivered and will be installed when relocating of electrical components are complete. Awaiting confirmation and clearance from Jess to proceed with cutting into walls to facilitate electrical modifications |  | Enrico Baez |  | YES | 2019-06-14 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000483 |  | 18P000483 | FALSE | PB&A | SL5 INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | FS to coordinate with customer to scope the work. | PARKING LOT 1 |  | CANCELED BY CLIENT | Gerry Bomotti | TBD | AMANDA GREY |  | Enrico Baez |  | 7 |  | FALSE |  |  | 2018-06-26 | [6 empty] | Waiting for Amanda Grey to verify ownership of chain link fence. Once confirmed will contract with De Anza to install 36" wide gate. | 2018-08-29 | Enrico Baez |  | YES | 2018-12-03 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000022 |  | 19P000022 | FALSE | PB&A | SL5 HUB--PAINT TWO WALL AS SCOTTY'S HUB |  | HUB | 101 | COMPLETE | Gerry Bomotti | TBD | DIANE THOMAS |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-07-12 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-17 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000215 |  | 19P000215 | FALSE | PB&A | SL5 SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 |  | HUB | 346 | COMPLETE | Gerry Bomotti | TBD | GUSTAVO PLASCENCIA |  | John Peraino |  | 9 |  | FALSE |  |  | 2018-08-24 | 12/12/18 DND Project complete |  | 2018-12-12 |  |  |  | 12/12/18 DND Project complete; electrical was installed and all kitchen equipment was hooked up as requested. |  | Enrico Baez |  | YES | 2018-12-12 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000095 |  | 18P000095 | FALSE | PB&A | SL5 THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS |  | THE PLAZA | A0013 | CANCELED BY CLIENT | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Enrico Baez |  | C | HOLD | FALSE |  |  | 2017-09-08 | [6 empty] | 4/11/EB-On Hold per Robert Brumbaugh. 6/8 EB-emailed R. Brumbaugh for status update. |  | Enrico Baez |  | YES | 2018-06-08 | Fall 2017 | FS | FALSE | 2017 | 2021-02-01
20P000114 |  | 20P000114 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER DOOR, BASEBOARD, AND BRACKETS |  | PENTLAND A |  | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 2019-09-05 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000127 |  | 20P000127 | FALSE | PB&A | SL5 FALKIRK APARTMENTS EMERGENCY EGRESS |  | FALKIRK 1 | 10E | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 2019-09-13 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000037 |  | 20P000037 | FALSE | PB&A | SL5 FAC ADMINISTRATION -PAINT WALLS |  | FS ADMIN | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 2019-07-23 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
19P000687 |  | 19P000687 | FALSE | PB&A | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | COMPLETE | Gerry Bomotti | TBD | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-06-26 | plan check review | [5 empty] | 8/5/20, DL This Project is Complete……………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Contracts is processing the contract. Once the contract is complete, we will schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Plans were approved. I sent Brendan an email 11/11/19 requesting an FAU # as this is Recharge work. Once we have the FAU #, we will work on the contract agreement with the contractor………10/30/19, DL; Sent Lezlie and email asking if she has an update on the resubmitted plans on 10/30/19………..10/16/19, DL; The plans were resubmitted for plan check review this week. We are hopeful the plans will be approved this week. Once approved we will work on contract and scheduling the work…10/7/19 LB: This is a test. The timestamp will be reset when the test is done. 10/1/19, DL: We are working on plan check review. We should have approved plans in the next two weeks…..8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | Provide estimate to install key card access control |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21 | 1
19P000599 |  | 19P000599 | FALSE | PB&A | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 2019-05-09 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
21P000003 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | PROJECT INTAKE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Enrico Baez |  | R1 |  | FALSE |  |  | 2020-06-26 | [6 empty] | 1/19/21, DL: Enrico is managing this project………….. | 2020-12-02 | Enrico Baez | Remove tripod antenna. Apply spray roof coating to existing roof surface | YES |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01 |  | 1
19P000535 |  | 19P000535 | FALSE | PB&A | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV | Install TV Mount and additional electrical | BANNOCK H | H0108 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-03-14 | [7 empty] | 2019-07-08 | Enrico Baez | Install TV Mount and additional electrical | YES | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000205 |  | 20P000205 | FALSE | PB&A | SL5 THE PLAZA 12 & 14 - EMERGENCY DECK REPAIR | Deck repair | THE PLAZA | A0012 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R2 |  | FALSE |  |  | 2019-11-01 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
19P000573 |  | 19P000573 | FALSE | PB&A | SL5 UNIVERSITY VILLAGE PAINT /REMOVE NAILS |  | UV BLDG B | 0208L | CANCELED BY CLIENT | Gerry Bomotti | TBD | JUDITH ABBEY |  | Paul Ditty |  | R2 |  | FALSE |  |  | 2019-04-11 | [6 empty] | 06/14/19 O-ANS: Canceled by Customer via email from Georgianne Carlson "Project 19P000573, UV Room 208L. Human Resources Department has withdrawn the request for this patch and paint project. Not a priority, at this time." |  |  |  |  | 2019-06-14 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 |  | 1
20P000115 |  | 20P000115 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 1 - BALCONY COSMETIC REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R2 |  | FALSE |  |  | 2019-09-05 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000223 |  | 20P000223 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER PAN REPLACEMENTS | Shower Pan replacement | PENTLAND A | A238, B245, B325, C215, F325 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R3 |  | FALSE |  |  | 2019-11-15 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Sep 2019. |  | John Peraino |  |  | 2019-09-01 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000116 |  | 20P000116 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 5 - BALCONY EMERGENCY REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R3 |  | FALSE |  |  | 2019-09-05 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000243 |  | 20P000243 | FALSE | PB&A | SL5 ALUMNI CENTER - HYDRATION STATION INSTALL | Install hydration station | ALUM VISITOR | FIRST FLOOR | COMPLETE | Gerry Bomotti | TBD | LESLIE ANN GERRETSE |  | John Peraino |  | R4 |  | FALSE |  |  | 2019-11-16 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by June 2020. |  | John Peraino |  |  | 2020-06-01 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000117 |  | 20P000117 | FALSE | PB&A | SL5 PENTLAND HILLS A-H - LATTICE REBUILD |  | PENTLAND A | A-H | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R4 |  | FALSE |  |  | 2019-09-05 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
20P000118 |  | 20P000118 | FALSE | PB&A | SL5 FALKIRK 1, 2, & 12 - FIRST FLOOR PATIO FENCING |  | FALKIRK 1 | 1st Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R5 |  | FALSE |  |  | 2019-09-05 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Bidding Competition | Gerry Bomotti | TBD | Michelle Baniqued |  | Fernando Canon | 1 |  |  | FALSE | 33980000 |  | 2019-03-04 | Select Design Builder | 2021-10-01 | 2023-04-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 2019-03-08 | Complete Report-Arc Flash | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
3515c | 3515c |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Construction | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 2019-03-08 | Complete Construction | 2020-12-01 | 2021-06-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3523 | 3523 |  | FALSE | PB&A | 1907 Mt Rubidoux Facility Study | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. |  |  | Programming (Study) | Gerry Bomotti | TBD | Melissa Garrety |  | Scott Donnell | 3 |  |  | FALSE |  |  | 2019-04-22 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | Design | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 2019-03-04 | Bidding | 2021-05-01 | 2021-09-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3590b | 3590b |  | FALSE | PB&A | DMFI(FY17-20) Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Bidding | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 2019-11-27 | Award Contract | 2021-04-05 | 2021-06-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3610 | 3610 |  | FALSE | PB&A | Hulen Place Homeless Medical Clinic | SOM is acquiring additional space for a medical clinic to assist with the homeless population. |  |  | In Programming | Gerry Bomotti | TBD | Diana Armenta |  | Daneca Stevens | 5 |  |  | FALSE |  |  | 2020-10-06 | Design | 2021-03-01 | 2021-03-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-01
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Richard Geiger |  | John Franklin | 6 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [12 empty] | PD&C | FALSE | 2018 | 2021-02-01
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | Bidding | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 6950000 |  | 2019-03-04 | Award Contract | 2021-06-01 | 2023-05-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3533 | 3533 |  | FALSE | PB&A | Solar Rooftop Initiative | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. | MULTIPLE BUILDINGS |  | In Construction | Gerry Bomotti | TBD | Richard Geiger |  | John Franklin | 9 |  |  | FALSE | 2165000 |  | 2019-06-03 | Complete Construction | 2020-10-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | Michelle Baniqued |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 2019-03-04 | DB Competition | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Scott Donnell | 10 |  |  | FALSE | 65000 |  | 2019-03-04 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
3286 | 3286 |  | FALSE | PB&A | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 10 |  |  | FALSE | 3375000 |  | 2017-03-29 | Complete Construction | 2021-02-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2017 | 2021-02-01
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 2018-10-31 | CEQA | [12 empty] | PD&C | FALSE | 2018 | 2021-02-01
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | In Bidding (prequalification) | Gerry Bomotti | TBD | Sharyl Murdock |  | Rowan Reid | 16 |  |  | FALSE | 26329342.06 |  | 2015-12-15 | Start Construction | 2021-01-01 | 2023-08-01 | [10 empty] | PD&C | FALSE | 2015 | 2021-02-01
3467 | 3467 |  | FALSE | PB&A | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | Bidding - 3rd flr Walking Deck Only | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 17 |  |  | FALSE | 235000 |  | 2018-07-31 | Award Contract | 2021-04-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2018 | 2021-02-01
3597 | 3597 |  | FALSE | PB&A | Plaza F Roof Replacement | Plaza building F roof is well past its service life and is experiencing multiple leaks into the apartment spaces below. This scope of work is to replace the roof in total and repair damages observed to the apartments below as a result of roof leaks. REQUESTING JOHN FRANKLIN AS THE PROJECT MANAGER. |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 18 |  |  | FALSE | 250000 |  | 2020-06-17 | Complete Construction | 2021-02-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-01
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 19 |  |  | FALSE | 315000 |  | 2018-07-31 | Bidding | 2021-05-01 | 2021-07-01 | [10 empty] | PD&C | FALSE | 2018 | 2021-02-01
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 19 |  |  | FALSE | 916581 |  | 2018-11-06 | Complete Review | [12 empty] | PD&C | FALSE | 2018 | 2021-02-01
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | TBD | Richard Geiger |  | D.Hecht/J.Franklin | 20 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2021 | [12 empty] | PD&C | FALSE | 2017 | 2021-02-01
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Programming | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 22 |  |  | FALSE |  |  | 2016-10-10 | Design | [12 empty] | PD&C | FALSE | 2016 | 2021-02-01
3490 | 3490 |  | FALSE | PB&A | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | Parking Lot 13 |  | In Construction | Gerry Bomotti | TBD | Irma Henderson |  | D.Hecht/J.Franklin | 25 |  |  | FALSE | 31844000 |  | 2018-12-06 | Complete Construction | 2020-02-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2018 | 2021-02-01
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Bidding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 2020-09-23 | Award Contract | 2021-03-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-01
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Bidding | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 2020-09-15 | Award Contract | 2021-04-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-01
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Programming | [12 empty] | PD&C | FALSE | 1900 | 2021-02-01
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 2020-09-22 | Bidding | 2021-04-01 | 2021-07-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-01
9062 | 9062 |  | FALSE | PB&A | DM(FY20) Life Sci Sewer line |  |  |  | Bidding | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 116000 |  | 2020-09-15 | Award Contract | 2021-03-01 | 2021-03-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-01
20P000162 |  | 20P000162 | FALSE | PROVOST/EVC | SL5 HINDERAKER 1101B - PATCH HOLE IN WALL |  | HINDERAKER | 1101B | CANCELED BY FS | Thomas Smith | Luisa Levario | AMY GU |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-07 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000386 |  | 19P000386 | FALSE | PROVOST/EVC | SL5 ROOM CHANGES |  | STUDENT SERV | 3106A | COMPLETE | Thomas Smith | Luisa Levario | STEPHANIE ARCINIEGA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-20 | Schedule the work.. | 2019-03-11 | 2019-04-01 |  |  |  | 4/15/19, DL; This Project is 100% Complete…… 2/28/19, DL; Conducted site visit. We need to schedule the work in the next 2-3 weeks This is for room 3109 C&D ……….. | 2019-02-07 | Ron Veloz |  | YES | 2019-04-15 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
19P000473 |  | 19P000473 | FALSE | PROVOST/EVC | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 |  | HINDERAKER | 1100 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | TORRI MCGARITY | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-29 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-28 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000683 |  | 19P000683 | FALSE | PROVOST/EVC | SL5 PATHC/PAINTING REPAIR |  | HUM & SOC SC | 1103A | COMPLETE | Thomas Smith | Luisa Levario | JILL CANTONWINE |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-06-25 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000434 |  | 19P000434 | FALSE | PROVOST/EVC | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | Please patch 50 plus holes on the wall and repaint that wall in Skye hall 136 due to the BKM removing the furniture attached to the wall. Please call Anita Ortiz if you have any questions at x2-5229. Shanshan's extension x7753 has not been moved to her new location yet. | SKYE HALL | 136 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | SHANSHAN | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-07 | [6 empty] | 07/20/19 O-ANS: Work Complete per Paul Ditty. |  | Paul Ditty |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18P000351 |  | 18P000351 | FALSE | SoB | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 (S) | 21 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2018-03-19 |  | 2019-07-08 |  |  |  |  | 8/1/19, DL; This project is 100% Complete……7/15/19, DL; Work has started and should be complete on 7/16/19…….. 4/4/19 O-ANS: Moved to Queue to Start to complete during Summer 2019. DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week……8/8/18. The trades are ready to go after they finish current projects…..DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18………. DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date……..9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space……Note. The space is usable and everything works….. |  | Enrico Baez |  | YES | 2019-08-01 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
18P000463 |  | 18P000463 | FALSE | SoB | SL5 ANDERSON HALL PATCH/PAINT-102C |  | ANDERSON 1 (N) | 0102C | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-06-04 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000053 |  | 19P000053 | FALSE | SoB | SL5 ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S |  | ANDERSON 1 (N) |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-04-13 | [6 empty] | DL 8/22/18; two out of four monitors are complete. WE still need to install powree at four locations…….DL, 9/6/18; Still need Electrical installed……. Planing to have complete by 9/21/18……. This is aqctually 4- monitors in four locations. We should ensure each monitor is treated as an indidual project.......DL, 9/19/18; All monitors are installed. Robert will schedule the electricans this week or early next week...DL, 10/4/18; This project is 100% Complete..... |  | Enrico Baez |  | YES | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000482 |  | 18P000482 | FALSE | SoB | SL5 CARD ACCESS SYSTEM ANDERSON SOUTH |  | ANDERSON 2 (S) |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-26 | [6 empty] | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with JasonDL, 7/11/18; Need to check in with Jason on status for his side of the project.....DL, 7/25/18; JAson's team is ready to install but the Anderson IT department does not have the necesary software. We will start the work when the software is up and running...... 8/12/18 DND FAMIS Status noted completion on 8/2/18. |  | Dan Lerman |  | YES | 2018-08-02 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000017 |  | 19P000017 | FALSE | SoB | SL5 ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD |  | ANDERSON 1 (N) | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | DL, 9/6/18; Monitors are installed. Need to schedule the electrical. Target date is 9/21/18…… |  | Enrico Baez |  | YES | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000018 |  | 19P000018 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER |  | ANDERSON 1 (N) | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000428 |  | 18P000428 | FALSE | SoB | SL5 OLMSTED RM 2352 PATCH/PAINT |  | OLMSTED | 2352 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-05-02 | [8 empty] | Paul Ditty |  | N/A | 2018-08-17 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000033 |  | 19P000033 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT | Duplicate request to 19P000030; Canceling project to be completed on other request. | OLMSTED | 2301 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | Duplicate to project 19P000030. Canceling project. |  | Paul Ditty |  | N/A | 2018-10-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000199 |  | 20P000199 | FALSE | SoB | SL5 ANDERSON SO RM 0002 - KEYLESS ENTRY MINOR RENOVATION REQUEST |  | ANDERSON 2 (S) | 2 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG | KENNETT LAI | Dan Lerman |  | - |  | FALSE |  |  | 2019-10-25 | [8 empty] | Enrico Baez |  |  | 2019-11-14 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000521 |  | 19P000521 | FALSE | SoB | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT |  | ANDERSON 1 (N) | 138 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-03-08 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000030 |  | 19P000030 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT |  | OLMSTED | 2301 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000151 |  | 20P000151 | FALSE | SoB | SL5 ANDERSON HALL NO 113 - PATCH/PAINT HOLES |  | ANDERSON 1 (N) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-09-30 | [6 empty] | 03/02/20 O-ANS: Project complete per Paul Ditty as of 02/07/20. |  | Paul Ditty |  |  | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000451 |  | 19P000451 | FALSE | SOB | SL5 ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 |  | ANDERSON 1 (N) | 58 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-15 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  |  |  |  | 2019-02-01 | SPRING 2019 | FS | FALSE | 2019 | 2021-02-01
20P000192 |  | 20P000192 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 1st Floor | CANCELED BY FS | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-10-23 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000280 |  | 19P000280 | FALSE | SoB | SL5 ANDERSON HALL PAINT ONLY |  | ANDERSON 2 (S) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-13 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000193 |  | 20P000193 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 0001A | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-10-23 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/02/20 |  | Paul Ditty |  |  | 2020-01-02 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000353 |  | 19P000353 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT-2348 |  | OLMSTED | 2340 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-19 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Commencing Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Rowan Reid | 1 |  |  | FALSE | 1150000 |  | 2016-12-15 | Completion of Basis of Design | [12 empty] | PD&C | FALSE | 2016 | 2021-02-01
18P000380 |  | 18P000380 | FALSE | SOM | SL5 SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 | SOM RSCH | 330 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-05 | [6 empty] | Canceled per customer on 8/22/18. |  | Enrico Baez |  | NO | 2018-08-22 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000261 |  | 18P000261 | FALSE | SOM | SL5 WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR |  | WEBBER | 1143 | COMPLETE | Deborah Deas | Deborah Trujillo | LOURDES ESCAMILLA |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 7/11/18; Work orders are produced. Need to assign the work order and order material. I will review with Steve and verify target complete date….DL, 7/25/18; Still need to walk the project with Steve……DL, 8/10/18; Material is ordered. We will complete the install when the materila arrives.....DL, 8/22/18; Material should be on site with in 4- weeks. Will schedule install when material is on site. Target date is 9/20/18.......DL, 9/6/18; This Project is 100% Complete...... |  | Dan Lerman |  | YES | 2018-09-10 | Spring 2018 | FS | FALSE | 2017 | 2021-02-01
18P000400 |  | 18P000400 | FALSE | SOM | SL5 Covert suite 1116 and suite 1126 to office space | Provost has placed a hold on converting lab spaces into office spaces. | WEBBER | 1116 & 1126 | CANCELED BY FS | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-14 | [6 empty] | DL, 6/16/18; Waiting for update on Provost approval….DL, 7/11/18; Per email from Enrico on 7/10/18. The Provost put a hold on converting any lab space into officess…… |  | Enrico Baez |  | YES | 2018-07-10 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19S000833 |  | 19S000833 | FALSE | SOM | Add access control to entry doors |  | HECKMAN ICEM | Entry Doors | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-07-17 | [8 empty] | Ron Veloz |  | YES | 2018-09-19 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
19P000670 |  | 19P000670 | FALSE | SOM | SL5 SOME, RM 1670- RENOVATE FOR EXPANDED ENROLLMENT |  | SOM EDUC | 1670 | TO BE PERFORMED BY PD&C | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2019-06-18 | [8 empty] | Ron Veloz |  |  | 2019-09-06 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18W006022 |  | 18W006022 | FALSE | SOM | INSTALL CURTAIN ROD IN RESEARCH SPACE |  | SOM RSCH | 336 | COMPLETE | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-10-27 | [6 empty] | DL, 5/24/18; Need to review scope with Enrico….DL, 7/11/18; Enrico produced work orders for sheet metal shop. This is a singel trade project. |  | Enrico Baez |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2017 | 2021-02-01
20P000152 |  | 20P000152 | FALSE | SOM | SL5 SOME 2669 - PATCH & PAINT |  | SOM EDUC | 2669 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | TRACEY TRETTIN | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-30 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000408 |  | 19P000408 | FALSE | SOM | SL5 PATCH & PAINT - 2605 SOM ED |  | SOM EDUC | 2605 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
19P000009 |  | 19P000009 | FALSE | SOM | SL5 SOME -- PAINT, SPACKLE AND CLEANING NEEDED |  | SOM EDUC | 2615 | COMPLETE | Deborah Deas | Deborah Trujillo | BEVERLEY HERBERT |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-02 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000660 |  | 19P000660 | FALSE | SOM | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SL5 SOME RB, RM 330- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 9/30/20, DL: This Project is Complete………..8/5/20, DL: Dan to follow-up with customer…………..03/05/20 O-ANS: Removed room 330 per client request. Only updates to 107 & 111. |  | Ron Veloz | TBD | NO | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
20P000059 |  | 20P000059 | FALSE | SOM | SL5 SOME 2626- PATCH & PAINT |  | SOM EDUC | 2626 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-08-05 | [6 empty] | 11/26/2019 O-ANS: Project canceled per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000354 |  | 19P000354 | FALSE | SOM | SL5 WEBBER 2130A-PAINT CHERI'S NEW OFFICE |  | WEBBER | 2130A | COMPLETE | Deborah Deas | Deborah Trujillo | DOMINIC SALAZAR |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-19 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
20P000054 |  | 20P000054 | FALSE | SOM | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOMED-SOME G0600, G0621 & 1682B- ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-31 | [6 empty] | 9/30/20, DL: This Project is Complete…………..8/5/20, DL, Dan to follow-up with customer………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "Remove status Hold / Update project detail to include information on 1682B -ADD ELECTRICAL, PAINT/PATCH, AND RELOCATE WHITE BOARD." |  | Ron Veloz | Room G0600 Install Power behind and below the TV, install one TV Bracket, install one cut-in back box below the TV for data(data cabling by ITS), Paint the entire East wall to match existing. Room G0621 Insatll three(3) new double duplex receptacles and three(3) data back boxes only(no data cabling) in room G0621. Install SS tubing for Co2 from room G0621 to room G0623. Include Valves at both ends of P.O.C., Install one uni-strut siesmic cylinder support at the south wall. Steve Burleson has walked the site and has knowledge of the SOW. Loading Dock Install Pole & chains at Loading dock. |  | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000410 |  | 19P000410 | FALSE | SOM | SL5 PAINT OFFICES AT UC PATH |  | INTELLICTR |  | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-14 | [6 empty] | 06/06/19 O-ANS: Canceled per customer request. Paul spoke with customer who will outsource work. |  |  |  |  | 2019-06-06 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
19P000661 |  | 19P000661 | FALSE | SOM | SL5 SOM RB, CR0600- FY 19/20 PROJECT- PATCH & PAINT |  | SOM EDUC | CR0600 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000248 |  | 19P000248 | FALSE | SOM | SL5 SOME--SOME INSTALL ELECTRICAL 1682 |  | SOM EDUC | 1682 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  |  |  | 2 |  | FALSE |  |  | 2018-09-10 |  | 2019-01-28 | 2019-02-14 |  |  |  | 2/14/19, DL; This project is complete…… |  | Ron Veloz |  | YES | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000662 |  | 19P000662 | FALSE | SOM | SL5 FY19-20 PROJECT: DEANS CONF ROOM | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | SOM EDUC | 2652 | CANCELED BY FS | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-06-12 | [8 empty] | Ron Veloz | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | NO | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000060 |  | 20P000060 | FALSE | SOM | SL5 WEBBER HALL 1274- PATCH & PAINT OFFICE |  | WEBBER | 1274 | COMPLETE | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-08-05 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-28 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000249 |  | 19P000249 | FALSE | SOM | SL5 SOME-INSTALL LOCKERS | Lockers on order by customer; upon arrival to be installed. | SOM EDUC |  | CANCELED BY FS | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-07 | [6 empty] | DL, 11/7/18; It is my understanding the lockers are ordered, but we donot have a confirmed delivery date. Once the material is on site, we will schedule the installation…… |  | Ron Veloz |  | YES | 2019-02-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000245 |  | 19P000245 | FALSE | SOM | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY |  | SOM RSCH |  | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-09-07 | Plans are approved | 2019-06-03 | 2019-06-28 |  |  |  | 7/1/19, DL; This project is 100% Complete…..6/171/19, DL; Material is on site. Project should be complete in the next two weeks……..5/31/19, DL; Contracts is working on the contract. We should have a notice to proceed in the next two weeks. The project will be complete with in 30- from when we receive the notice to proceed……5/15/19, DL;, Plans were approved. I am working with PD&C on the contract. Once the contract is complete, we will schedule the work……3/28/19, DL; Plans were submitted and pending review and approval….. | 2018-10-29 | Ron Veloz | Install ADA complian auto door operator, push plates and electrified panic hardware. Auto operator will be outsourced through Capitol door. FS lock shop will perform acess control wiring. Electrical shop to provide a dedicated circuit for the auto door operator. | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20
19P000658 |  | 19P000658 | FALSE | SOM | SL5 SOM RB- PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD - PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 03/05/20 O-ANS: Canceled by client per Cynthia Carolina. |  | Ron Veloz | TBD | NO | 2020-03-05 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000666 |  | 19P000666 | FALSE | SOM | SL5 WEBBER, ROOM 1237- PATCH AND PAINT | TBD - SOM RM 107, 111 & 330- PROJECT: NEW PI, EQUIPMENT INSTALL | WEBBER | 1237 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-06-17 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-11 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000051 |  | 20P000051 | FALSE | SOM | SL5 SOMED 2611 - PATCH & PAINT |  | SOM EDUC | 2611 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-07-31 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000659 |  | 19P000659 | FALSE | SOM | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 5 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 08/05/20 O-ANS: Canceled by client (Cynthia Carolina) via email with Ron Veloz. 8/5/20, DL: Dan to follow -up with customer…………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "remove 330 from work order / update project details / Update: Furniture on order 3.30.2020 - delivery tbd" |  | Ron Veloz | TBD | NO | 2020-08-05 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000032 |  | 19P000032 | FALSE | SOM | SL5 Reconfigure recepetion desk to fit two FTEs. |  | SOM EDUC | 2608 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 5 | 1 | FALSE |  |  | 2018-07-17 | finish project | 2019-03-04 | 2019-03-15 |  |  |  | 5/1/19, DL; This project is 100% Complete….. 3/28/19, DL; Cabinet workl is complete. We need to finish the carpet and final laminate material…….2/28/19, DL; Conducted site visit with Chad. We will complete the work in the next two weeks…….2/1/19, DL; I Walked this project this week. We will try and schedule the work in the next 30- days…….12/14/18, DL, Still need to conduct site visit and schedule the work… | 2018-10-17 | Ron Veloz | Remove lower the left lower cabinet to create an additional work station. SOW: Remove/demo cabinet, install a new corbel patch floor with similar carpet and install 4" rubber base as needed. | YES | 2019-05-01 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000485 |  | 18P000485 | FALSE | SOM | SL5 SOMR PATCHING AND PAINTING |  | SOM RSCH |  | COMPLETE | Deborah Deas | Deborah Trujillo | DANA ABOU ABBAS |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000012 |  | 19P000012 | FALSE | SOM | SL5 SOME--PATCH & PAINT |  | SOM EDUC | 2638 | COMPLETE | Deborah Deas | Deborah Trujillo | MARISELA MARTINEZ |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-07-06 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000014 |  | 19P000014 | FALSE | SOM | SL5 SOME - PATCH & PAINT |  | SOM EDUC | 2609 | COMPLETE | Deborah Deas | Deborah Trujillo | MARISELA MARTINEZ |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-07-09 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000467 |  | 20P000467 | FALSE | SOM | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. | WEBBER | 1247 | QUEUE TO START | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | CYNTHIA CAROLINA | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-19 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
3603 | 3603 |  | FALSE | SOM | Orbach Libr SOM CSSS AV Equipment | AV for CSSS project - 954044 / re: Fernando Cortez. Please refer to MSRIV in the line reference field for the draw down. |  |  | In Construction | Deborah Deas | Deborah Trujillo | Deborah Trujillo |  | Fernando Canon | 1 |  |  | FALSE | 1652000 |  | 2020-07-27 | Complete Construction | 2020-12-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-01
3581 | 3581 |  | FALSE | SOM | SOMR Interior Egress Doors | All egress doors - Floors 1, 2, and 3 - need to be replaced with compliant structures. Please inspect, evaluate and provide quote. |  |  | In Pre-Programming | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 2020-03-04 | Design | [12 empty] | PD&C | FALSE | 2020 | 2021-02-01
18P000470 |  | 18P000470 | FALSE | SPP | SL5 Student Check-in Lobby |  | CHASS INT S | 4133 Corridor | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-11 | [6 empty] | DL, 6/16/18; I walked this project with Luis and Mark this week. They want this work completed by July 9th. Paint, data, electrical, chair rail and signage is requested. I need to review project with Paul and Robert C. DL, 7/11/18; Robert C. Ordered material and we will complete the install first part of next week We will scheudle the paint after Robert is Complete. Target Complete Date is 7/2018......DL, 7/25/18; WE have the electrical materila, plans were submitted. Once plans are reviewed and approved, we will proceed with the work. Target date is two weeks after plans are approved......DL, 8/10/18; Eletrical is complete. Pending paint. Paint will be scheduled in the near future. DL, 8/22/18; This project will be Complet on Saturday.....DL, 9/6/18. I miossed the chair rail request on this project. I will order the chair rail in the near future. The chair rail is the only item needed to complete this project. Aprroximately 20 lineal feet......DL, 9/19/18; Chair rail is ordered. We will schedule the install when the material arrives....... |  | Dan Lerman |  | YES | 2018-08-23 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000458 |  | 19P000458 | FALSE | SPP | SL5 CHASS INTS-BUILD PERM DRYWALL DIVIDER OR APPROVE BKM AIRWALL |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ | LUISA LEVARIO | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-19 | Order material & start the work | 2019-03-27 | 2019-06-15 |  |  |  | 6/17/19, DL; This project is 100% Complete…..5/31/19, DL; This prject is making good progress and we are scheduled to be complete on or before June 19th…….5/15/19, DL; This project is in progress and schedule for complete near 6/15/19…. 5/1/19; We started this project last week and we are planning to be complete in 4 - 6 Weeks….4/15/19, DL; Material is ordered, we will start the demolition this week. We hope to be complete in 8-weeks or less……2/28/19, DL; Plans are complete and were submitted to for review and approval from campus building official and fire marshal. Once plans are approved, we will shcedule the work….. | 2019-01-28 | Enrico Baez | 1/28/19 EB See Shared drive for additional information. Carpenters • Construct new approx. 4” metal stud walls with 5/8” drywall over 48” x 96”x1/2” sound insulating panels. See plans for location. • Remove T-bar drop ceiling under soffit in location of partitioned space, frame with metal stud, attach 5/8” drywall over sound insulating panels. • Extend soffit face flush to meet with new walls, frame under soffit, cover with sound insulating panels and 5/8” drywall. • Install 1 ADA compliant half lite, 36" wide, 3/4" thick, paint grade, entry door and trim in each space. • Finish and texture walls to match existing. • Install base cove to match. Electrical • No additional electrical outlets to be added. • Install switched recessed can lights, similar to existing, 4 in each new space. Fire Protection and Suppression • Relocate existing fire sprinklers to be compliant in each newly created space. • Relocate and add smoke detectors in each newly created space. Painters • Prime, Patch and Paint walls, ceiling, doors and trim. Lock Shop • Furnish and install 2 each, ADA compliant handle sets, match existing hardware HVAC • Relocate HVAC duct work in new extended soffit. Split 10” center duct or two new spaces with 6” Wye and registers. • Provide return air in ceiling. • No thermostat or zone controls will be installed. Customer informed. | YES | 2019-06-17 | Spring 2019 | FS | FALSE | 2019 | 2021-02-01
19P000255 |  | 19P000255 | FALSE | SPP | SL5 CHASS INT N REMODEL - 4022 PATCH AND PAINT |  | CHASS INT N | 4022 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000263 |  | 19P000263 | FALSE | SPP | SL5 CHASS NORTH REMODEL - 4009 PATCH AND PAINT |  | CHASS INT N | 4009 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-09-11 | [8 empty] | Paul Ditty |  |  | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000256 |  | 19P000256 | FALSE | SPP | SL5 CHASS REMODEL - 4146 PATCH AND PAINT |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  |  |  | 3 |  | TRUE |  |  | 2018-09-10 | [7 empty] | 2018-10-09 | Enrico Baez |  | YES | 2019-01-04 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000270 |  | 18P000270 | FALSE | SPP | SL5 CHASS INT S- EVALUATION FOR REMODEL |  | CHASS INT S | 4133 | CANCELED BY CLIENT | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Dan Lerman |  | 4 | 2 | TRUE |  |  | 2018-01-16 | [6 empty] | 4/24/18 EB- Per Christina Wong, no loner needed……DL, 5/5/18; Project is cancesled per notes DND 7/27; Please follow up with customer on the status and need for the work; customer advised to me that Dan has the scope of work for completion. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. |  | Enrico Baez |  | YES | 2018-04-24 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000478 |  | 18P000478 | FALSE | UNDERGRAD ED | SL5 CARPET, PAINT, & AIR HANDLING MODIFICATION |  | HINDERAKER | 1120H | COMPLETE |  |  | TRACEY SCHOLTEMEYER |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-16 | [6 empty] | DL, 7/4/18; This project is scoped; Need to remove Switch gear storage rack components, remove electrical conduits, plywood backer board from walls, paint and floor covering. We will schedule this work to be complete by Fall 2018 academic year....DL, 7/11/18; Need to produce work orders and schedule the work. Target Complete date is 9/14/18... Space is vacant....DL, 8/10/18; Work has started and we are on schedule...... DL, 8/22/18; Demo is almost complete. This target date is 9/21/18......9/19/18; All trades are complete. New carpet to be installed on 9/21/18. .....DL, 9/19/18; This project is scheduled to be complete this week....... |  | Dan Lerman |  | YES | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 2019-12-10 | Departmental Approval | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
18P000442 |  | 18P000442 | FALSE | VC-RED | SL5 FAWCETT LAB 203 PATCH & PAINT |  | FAWCETT LAB | 203 | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 3 | FALSE |  |  | 2018-05-18 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000379 |  | 18P000379 | FALSE | VC-RED | SL5 UOB PATCH AND PAINT |  | UNIV OFC BLD |  | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-05 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18W013973 |  | 18W013973 | FALSE | VC-RED | SL5 BSL3 FACILITY- ASSEMBLE AND INSTALL |  | UNIV OFC BLD |  | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2018-04-19 | [6 empty] | FAMIS NOTES 8/22: Plumbing filter system was installed and ice maker installed. Request for microscope and incubator moved into containment by customer. Complete 9/24/18 |  | Enrico Baez |  | YES | 2018-09-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18W015691 |  | 18W015691 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER AND DRYER |  | BOYCE | 6444 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  |  |  |  | 1 | FALSE |  |  | 2018-05-30 | [6 empty] | DL, 7/11/18; This project is in progress and almost complete. Target complete date is 7/20/18….. |  | Dan Lerman |  | YES | 2018-07-11 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000476 |  | 18P000476 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER & DRYER | Canceled project, work completed on 18W015691 in July. | BOYCE | 6444 | CANCELED BY CLIENT | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-14 | [6 empty] | Duplicate to 18W015691; complete |  |  |  | NO | 2018-07-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000149 |  | 20P000149 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 242 |  | UNIV OFC BLD | 242 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-25 | [8 empty] | Paul Ditty |  |  | 2019-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000150 |  | 20P000150 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 207 |  | UNIV OFC BLD | 207 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-25 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000553 |  | 19P000553 | FALSE | VC-RED | SL5 SPIETH HALL PATCH AND PAINT |  | SPIETH | 341 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-01 | [6 empty] | 07/26/19 O-ANS: Project Complete per Paul Ditty. |  |  |  |  | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000439 |  | 19P000439 | FALSE | VC-RED | SL5 SPIETH PATCH AND PAINT ROOM 335 |  | SPIETH | 335 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-08 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2019 | 2021-02-01
20P000230 |  | 20P000230 | FALSE | VC-RED | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | Install Ceilings, Widen Door & Extend Utilities | BOURNS | B116C & B116D | COMPLETE | Rodolfo Torres | Laura Manor | KRASSIMIR BOZHILOV | LAURA MANOR | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-11-18 | finish plans for building permit | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: This project is in progress and 50% complete. We should be complete with in the next 4-6 weeks…………...8/5/20, DL: We will submit plans in the next week………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We will start working on the plans and apply for a building permit in the next 2-3 weeks. | 2020-01-23 | Ron Veloz | Install new T-bar ceilings, lighting/switches, verify electrical service/disconnect. Relocate the existing eye washer, widen the exiting door opening and *reverse swing(*if approved by F.M). Install one customer furnished transformer. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000044 |  | 19P000044 | FALSE | VC-RED | SL5 PATCH AND PAINT |  | SPIETH | 345 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES |  | UNIV OFC BLD | 200 | HOLD - FACILITIES SERVICES | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-02-07 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-02-01
20P000026 |  | 20P000026 | FALSE | VC-RED | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | Install T-bar ceiling, Provide HVAC and Fire sprinklers drops. Install new 2x4 LED light fixtures | LIFE SCIENCE | Basement Level | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-07-19 | Work on Plans and permits. | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: The plans were submitted two weeks ago. We should receive the plan check review comments in the near future…………….8/5/20, DL: This Project will exceed $50,000. Monty A. will inform customer this is a project that will need to be managerd through PD&C……………3/25/20, DL: We will work on plans when we return back from the campus closure. | 2020-01-31 | Ron Veloz | Install T-bar ceiling with wipable(coated) ceiling tile. Provide HVAC and new Fire sprinklers drops to new ceiling. Install new 2x4 LED light fixtures. Verify Fire alarm systems work. | YES | 2021-01-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
21P000078 |  | 21P000078 | FALSE | VC-RED | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MRB |  | IN PROGRESS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 2020-09-23 | start 2nd floor install | [5 empty] | 1/19/21, DL: the First floor work will be complete today, we will start the 2nd floor this week……………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
19P000495 |  | 19P000495 | FALSE | VC-RED | SL5 UOB RM 209- PATCH & PAINT |  | UNIV OFC BLD | 209 | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-02-08 | [6 empty] | 07/30/19 O-ANS: Project closed per Paul Ditty. 07/30/19 D-MMN: Moved furniture and filled holes. Taped base and fixtures. Primed and painted one half of office. Pulled tape replaced plates and moved furniture to other side. Removed plates taped base and fixtures. Primed and painted other half. Used spray texture on patch under window. Pulled masking. Replaced plates. Moved furniture back. Vacuumed carpet during and after total process. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000197 |  | 20P000197 | FALSE | VC-RED | SL5 UOB 210 - SOUND PROOF INSTALLATION |  | UNIV OFC BLD | 210 | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-10-24 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
20P000218 |  | 20P000218 | FALSE | VC-RED | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | VIVARIUM UPDATE AIR COMPRESSOR | SPIETH | 347 | PROJECT INTAKE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | DAN LERMAN |  | 2 | R2 | FALSE |  |  | 2019-05-17 | Start when we start prty 2 proj | [5 empty] | 2/1/21, DL: WE will start the process for this project once we are closer to compleiong priority one projects. This is a prioity 2 project……1/19/21, DL: This project has been scoped. We will start the work when we are complete with all priority #1 projects…….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01
19W003050 |  | 19W003050 | FALSE | VC-RED | SL5 SPEITH HALL - PATCH & PAINT HOLE IN WALL |  | SPIETH | 0359A | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000045 |  | 20P000045 | FALSE | VC-RED | SL5 MRB SOUND BOOTH |  | MRB | 2210 & 2204 | COMPLETE | Rodolfo Torres | Laura Manor | DAN LERMAN |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-30 | Inspection | 2019-10-01 | 2019-11-07 |  |  |  | 11/11/19, DL: This project is complete…….10/30/19, DL: This project is complete but we need to conduct the final inspection with the building official………..10/16/19, DL: The plans are approved and the work is complete. I need to field verify and schedule the inspection. |  | Ron Veloz | Contact PM for SOW. | NO | 2019-11-11 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice. | 2018-09-27 | Enrico Baez |  | YES | 2020-11-19 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01 | FY 20-21
20P000047 |  | 20P000047 | FALSE | VC-RED | SL5 ADVANCED NEUROIMAGING | NEEDING TO TAKE DOWN OVERHEAD CABINETRY AND REPLACE WITH SOME KIND OF SHELVING TO OPTIMIZE SPACE. LOOKING FOR AN ESTIMATE AND A PLAN. | ADV NEURO |  | CANCELED BY FS | Rodolfo Torres | Laura Manor | CHELSEA EVELYN |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-07-31 | pending material delivery. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice…….3/23/20, DL: Shelves are ordered. We will schedule the work when we return from the campus closure……….1/15/20 O-DHN: Emailed Status Report to customer…...1/14/20, DL: We waiting for a revised quote from the vendor as there quote was not complete. We will process the quote for a PO# when we receive the correct quote……. 11/11/19, DL: Need to review scope with Ron as the shelving system is a special order item with a 3- month lead time….. | 2019-09-24 | Ron Veloz | Remove 5'-0" x3'-0" upper cabinet, and soffits. Patch and paint walls to match the existing grey . Install customer furnished adjustable shelf. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 20-21
19P000181 |  | 19P000181 | FALSE | VC-RED | SL5 PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS |  | UNIV OFC BLD | 249 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-14 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-19 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
21P000102 |  | 21P000102 | FALSE | VC-RED | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | AAALAC Certification updates to rooms 348, 352 & 363 | SPIETH | 348, 352 & 363 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS | YURIDIA REYNOSO | Paul Ditty |  | TBD |  | FALSE |  |  | 2020-10-29 | [6 empty] | 12/08/20 O-ANS: Customer Dierk Biggs confirmed via email that these room updates are complete. |  | Paul Ditty |  |  | 2020-12-08 | Winter 2021 | FS | FALSE | 2020 | 2021-02-01 | FY 20-21
20P000468 |  | 20P000468 | FALSE | VC-RED | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | Paint Only | SPIETH | 364 | QUEUE TO START | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-06-23 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
21P000079 |  | 21P000079 | FALSE | VC-RED | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. | PSYCHOLOGY1 |  | QUEUE TO START | Rodolfo Torres | Laura Manor | LESLIE KARPINSKI |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-09-25 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-01
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | On Hold | Rodolfo Torres | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Daneca Stevens | 1 |  |  | FALSE | 45000 |  | 2017-06-13 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-02-01
18P000456 |  | 18P000456 | FALSE | VC-STU AFF | SL5 HUB--UTILITY METERS | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. | HUB |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-05-30 | [8 empty] | Enrico Baez |  | YES | 2019-01-24 | Summer 2018 | FS | FALSE | 2018 | 2021-02-01
18P000337 |  | 18P000337 | FALSE | VC-STU AFF | SL5 MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET |  | HEALTH SERV | 414 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-12 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18….Need to work on plans and permits….DL, 7/11/18; Gunther is working on plans. Target complete date is 9/14/18….DL, 7/25/18; Planning to submit plans for review next week. We will schedule the work once we have approved plans…….DL, 8/8/18; This is a structual wall and needs to be engineered. We are meeting with the Structual engineer on 8/9/18 to determine if project is possible.....DL, 8/22/18; Working on EDPA for Structual engineer; project timeline is late Fall. 9/19/18; The Agreement / Cointract for the structual engineer is processed for this project. We should have plans from the structual engineer to submitt to the Building Official and fire marshal with in 4- weeks......dl, 10/4/18; Plans are almost complete and we will submit them for review by the end of the week.....DL, 11/7/18; Plans are approved. WE are schedule to start this Project on Tuesday 11/13/18. Target complete date is by the end of the winter break..... |  | Enrico Baez |  | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
18P000215 |  | 18P000215 | FALSE | VC-STU AFF | SL5 STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA HAGGINS |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2017-12-08 | floor covering and electric door | 2019-02-19 | 2019-06-01 |  |  |  | 6/17/19, DL; This project is 100% complete. This project was the wall removal at the check in entrance…...5/31/19, DL; Contracts is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks4/15/19; All work is comleted except the floor covering and elcetronic card readers for the doors…..2/28/19, DL; This project has started and is on schedule…….2/14/19, DL; This project is scheduled to start on 2/19/19…………2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………1/15/19, DL, Material is ordered, material should arrive on site in the next 3- 5 weeks……12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 5/24/18; Need to review scope and site visti with Enrico. Plans and permits will be required for this project….DL, 7/11/18; Planning to walk work with Gloria and her team next week. Will be able to project complete date after site visit is conducted……DL; 7/25/18; We walked this project with the team. This will require plans and permits. We will schedule this work for Fall…………DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-45 Days…… |  | Enrico Baez |  | YES | 2019-06-17 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01
20P000206 |  | 20P000206 | FALSE | VC-STU AFF | SL5 COSTO HALL 111-HUB 353/381- RENOVATIONS - CP0003486 |  | COSTO HALL | Lower Level | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | - |  | FALSE |  |  | 2019-11-01 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000455 |  | 19P000455 | FALSE | VC-STU AFF | SL5 FILL AND PAINT OVER HOLES ON WALL |  | HEALTH SERV | 100 | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-17 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/27/19 |  |  |  |  | 2019-12-27 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000380 |  | 19P000380 | FALSE | VC-STU AFF | SL5 PATCH AND PAITN- WALL PAINT IS PEELING |  | HEALTH SERV | 404 | COMPLETE | Brian Haynes | Cathy Eckman | SAMANTHA HARRIS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-19 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
20P000337 |  | 20P000337 | FALSE | VC-STU AFF | SL5 HEATLH SERVICE 382 - NEED OFFICE PAINTED |  | HEALTH SERV | 382 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-23 | [6 empty] | 08/06/20 O-ANS: Complete per D-BFA on 02/11/20. |  | PAUL DITTY |  |  | 2020-02-11 | Spring 2020 | FS | FALSE | 2020 | 2021-02-01 | FY 19-20
19P000431 |  | 19P000431 | FALSE | VC-STU AFF | SL5 STUDENT SERVICES REMOVE NAILS AND PATCH WALL |  | STUDENT SERV | 2128 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | VALERIE SANCHEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-04 | [6 empty] | 6/24/19 O-ANS: CANCEL WO/PROJECT PER DONNA POWELL EMAIL. |  |  |  |  | 2019-06-24 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01
20P000157 |  | 20P000157 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BUILDING - HOLES NEED PATCH AND PAINT |  | HEALTH SERV | 325 | COMPLETE | Brian Haynes | Cathy Eckman | CHRISTINA FARIA | WENDY ALEXIS | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-10-02 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 01/31/20. |  | Paul Ditty |  |  | 2020-01-31 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
18P000348 |  | 18P000348 | FALSE | VC-STU AFF | SL5 HUB ADD 3RD FLOOR WALLS |  | HUB | 0353E | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 2 | 6 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/1/19, DL; Per Chris P. This is a PD&C project………..DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Need to walk the project with Manny. Target date is late Fall…….. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000405 |  | 19P000405 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED |  | HEALTH SERV | 0100D | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-11 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-01
18P000214 |  | 18P000214 | FALSE | VC-STU AFF | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Install Card readers | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  | 2 | 2 | FALSE |  |  | 2017-12-08 | Pending special order part | 2019-02-19 | 2020-09-01 |  |  |  | 1/19/21, DL: This project is 100% Complete…….9/30/20, DL: Vendor should have the balance of the material in the next 30- days…….8/5/20, DL: This project is complete except the card reader portion of the project…………6/17/20, DL: The floor covering was completed two weeks ago. The card reader portion of this project is 95% complete but additional parts were needed and they are on order. Once they arrive, we will schedule the installation and this project will be 100% Complete………1/15/20 Emailed Status Report to customer…..1/14/20, DL: We were recently approved to proceed with the work. I have reached out to the vendor for the doors and card access. We are still waiting to hear back from them so we can order the material and schedule the work. I communicated with Nicole on the floor covering replacement. Nicole needs to verify what areas we will replace as we were going to complete several offices and a hallway as part of the scope but this will displace many team members for at least a week. We will work on scheduling the work once Nicole gets back to me……..12/17/19 - O-DHN: Emailed Status Report to Customer……12/19/19, DL; We are working with our contractor to order the material and schedule the work. Once we have confirmation on the material, we will be able to schedule the work. It Is our goal to start this project in late January……11/26/19, DL: This project was taken off of on hold and we can now proceed. I contacted the contractor last week and I am awaiting their response on when they can schedule the work. I also left a message with them this morning………..7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once material arrives, we will schedule the installation.….5/31/19, DL; Contract is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is completed except the floor covering and electronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being prepped for paint. We have a pre-construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, material is ordered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct site visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez |  | YES | 2021-01-19 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01 | FY 20-21
19P000534 |  | 19P000534 | FALSE | VC-STU AFF | SL5 PATCH WALLS AND PAINT |  | HEALTH SERV | 334 | CANCELED BY FS | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-03-15 | [6 empty] | 12/06/19 O-ANS: Canceled by FS because unable to identify room location even after inspecting rooms with staff support. Original requester has since retired. |  |  |  |  | 2019-12-06 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000037 |  | 19P000037 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BLDG--PATCH WORK AND PAINTING |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-07-17 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000483 |  | 19P000483 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED |  | HEALTH SERV | 404, 407, 412, 405 & 411 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-02-01 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-11-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000124 |  | 19P000124 | FALSE | VC-STU AFF | SL5 PAINT ROOMS 115 AND 116 |  | COSTO HALL | 125 | COMPLETE | Brian Haynes | Cathy Eckman | LINDA KELLEY |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
19P000172 |  | 19P000172 | FALSE | VC-STU AFF | SL5 HEALTH SERV- PAINT RESTROOM IN LABORATORY |  | HEALTH SERV | 0113A | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
20P000073 |  | 20P000073 | FALSE | VC-STU AFF | SL5 HUB - THE WELL -3RD FL RM 346 DOOR INSTALLATION CP00003544 | DOOR INSTALLATION | HUB | 346 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | JONATHAN GODOY |  | Dan Lerman |  | PENDING |  | FALSE |  |  | 2019-08-12 | [6 empty] | 12/13/19 O-ANS: Project canceled by client Brendan O-Brien. | 2019-10-02 | Enrico Baez | 1.) Remove Aluminum accordian door from opening. Customer to determine how to discard. 2.) Frame opening with metal 2"x4" stud and sheet with 3/4" drywall. Allow for oppening to accommodate 36"x 80" door. 3.) Install metal door jamb and casing to match exisiting openings. Door to match exisiting. Campus Fire Marshall to determine if door to be fire rated. Swing to be approved by Campus Building official and/or Campus Fire Marshall. 4.) Relocate single gang outlet on North side of opening , if needed. 5.) Finish drywall, prime and paint walls. Texture to match exisiting. Customer to approve final paint color. | YES | 2019-12-13 | FALL 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | COSTO HALL |  | PROJECT INTAKE | Brian Haynes | Cathy Eckman | BRENDAN O'BRIEN |  | Enrico Baez |  | R1 | R2 | FALSE |  |  | 2019-10-24 | [6 empty] | 1/19/21, DL: Enrico B. Will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-01 |  | 1
18P000198 |  | 18P000198 | FALSE | VC-STU AFF | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Install new Wall lights | HUB | 0 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | R1 | 5 | FALSE |  |  | 2017-11-21 | Canceled per Brendan. No funding | [5 empty] | 10/30/19, DL: This project is on Hold and may be canceled as funding is not availabel at this time. Plans are approved……10/16/19, DL; Plans were submitted for plan check review last week. I also notified Brendan that this will be a recharge project . The ball park estimate I provided to Brendan was $7,000 - $9,000. Brendan needs to confirm if funds are available. If funds are available, I will have a contractor bid on the project……… 10/16/19: O-ANS - Not a CORE location so project changed to Recharge. 10/1/19, DL; Plans will be submitted a building permit and plan check review this week…….9/3/19, DL; Gunter has plans at 60%, We will try and submitt with in the next two weeks. 8/14/19, DL;This project is now on Gunther's bench. Gunter will start the process in about 2- weeks and we should have plans top submitt with in the next 30- days….6/17/19, DL; I will walk this work in the next two weeks and work on plan to submit to our campus architech and building official for review…..DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…… | 2018-01-23 | Enrico Baez |  | YES | 2019-10-30 | Winter 2018 | FS | FALSE | 2017 | 2021-02-01 | FY 19-20 | 1
20P000184 |  | 20P000184 | FALSE | VC-STU AFF | SL5 HUB 261 - CONSTRUCT WALL FOR MEETING/CONFERENCE RM | In HUB 261 the administration is requesting a wall be constructed to create a meeting/conference room. We need a building zone manager to walk the area give estimate as well as reaching out to the fire marshals inspector for recommendations. | HUB | 261 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | Manny Sanchez |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-10-17 | [6 empty] | 02/07/2020 O-ANS: Canceled due to client request. | 2019-11-05 | Enrico Baez | 11/5/19 E.Baez conducted site visit. **********SCOPE********* 1. Construct, full height, partition wall with door in HUB 261. 2. Provide/install ADA compliant door in new partition wall. 3. Add and relocate fire sprinkler. 4. Re-position lighting in ceiling, add lighting control. 5. Patch and paint. 6. Install base board. 7. Add strobe and smoke detectors. 8. T-bar ceiling re-work. | YES | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20 | 1
3524 | 3524 |  | FALSE | VC-STU AFF | Student Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | STUDENT SERV |  | Biddging | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE | 450000 |  | 2019-04-16 | BKM Lead Time 10 Weeks | 2021-04-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-01
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | On Hold (COVID-19) | Brian Haynes | Cathy Eckman | Christina Wong |  | Tameesha Hayes | 2 |  |  | FALSE | 130000 |  | 2019-03-19 | On hold (COVID-19) | [12 empty] | PD&C | FALSE | 2019 | 2021-02-01
3471 | 3471 |  | FALSE | VC-STU AFF | HUB Electrical Sub Meter Installation | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Design | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 200000 |  | 2018-08-20 | Bidding | 2021-04-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2018 | 2021-02-01
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair/Replacement | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | Funding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 8 |  |  | FALSE |  |  | 2020-09-21 | Secure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-02-01
20P000225 |  | 20P000225 | FALSE | VC-UNIV ADV | SL5 HINDERAKER 0137 - BASEMENT RESTROOM SINK INSTALL | Install Kitchen Sink in entry room of Restroom 0137 | HINDERAKER | B137 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL | KIM MCDADE | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-11-15 | [6 empty] | 1/22/20 O-ANS: Canceled per customer request. | 2020-01-22 | Enrico Baez |  | YES | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
20P000309 |  | 20P000309 | FALSE | VC-UNIV ADV | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES |  | 1955 CHICAGO | 200 | CANCELED BY FS | Peter Hayashida | Naysia Caldwell | SARAH KARSON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-10 | [6 empty] | 12/16/20 O-ANS: Canceled by FS - Project location not serviced as FS CORE location and reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Please retain project # as reference. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  | 2020-12-16 | Spring 2020 | FS | FALSE | 2020 | 2021-02-01 | FY 20-21
19P000564 |  | 19P000564 | FALSE | VC-UNIV ADV | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | 1156C (AVC Johnny Cruz) – Patch molly holes, touch-up paint. 1156A (Jules Bernstein) – Remove (2) black & white photos from wall. Patch molly holes, touch-up paint. 1156B – Install picture frame (UCR campus map) onto wall. Suite 1159 – Patch holes. Remove film reels. Paint one accent wall “UCR Blue”. 1159B (Christy Zwicke) - Patch molly holes, touch-up paint. | HINDERAKER | 1156 | COMPLETE | Peter Hayashida | Naysia Caldwell | Lisa Cusick | Christy Zwicke | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-08 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-07 | Summer 2019 | FS | FALSE | 2019 | 2021-02-01 | FY 19-20
19P000238 |  | 19P000238 | FALSE | VC-UNIV ADV | SL5 PATCH & PAINT HINDERAKER 1136 |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-02-01
18P000281 |  | 18P000281 | FALSE | VC-UNIV ADV | SL5 ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS |  | ALUM VISITOR | 2202 | COMPLETE | Peter Hayashida | Naysia Caldwell | TRUDY COHEN |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-01-24 | execute the work | 2019-03-04 | 2019-03-15 |  |  |  | 3/28/19, DL; This Project is 100% Complete…..2/28/19, DL; This work is scheduled…….DL, 5/24/18; Need to verify scope of work with EnricoDL, 7/11/18; Still need to visit the site and schedule the work…..DL, 11/8/18; This project was transferred to John. The target date was 1/2/19….. |  | Enrico Baez |  | YES | 2019-03-28 | Spring 2018 | FS | FALSE | 2018 | 2021-02-01
19P000326 |  | 19P000326 | FALSE | VC-UNIV ADV | SL5 HINDERAKER - PATCH & PAINT |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-08 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-02-01
19P000417 |  | 19P000417 | FALSE | VC-UNIV ADV | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY |  | UV BLDG A | 201 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2018-12-18 | Schedule the work | 2019-08-14 | 2019-12-28 | [5 empty] | Enrico Baez |  |  | 2019-08-06 | Summer 2019 | FS | FALSE | 2018 | 2021-02-01 | FY 19-20 | 1
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | 10 |  | FALSE |  |  | 43355 | [6 empty] | 1/24/2020 E. Baez- Cancelled per Joe Erbland. 4/18/19, DL; Per Enrico, we are waiting for a proposal from HCI and approved funding from Athletics. We should have the proposal in 2- weeks…. | 2018-09-27 | Enrico Baez |  | YES | 2020-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
20P000093 |  | 20P000093 | FALSE | ATHLETICS | SL5 ATHLETICS 0078 - TELEVISION MOUNT/ ELECTRICAL |  | ATH DANCE | 0078 | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43697 | [6 empty] | 11/26/19 O-ANS: Project canceled per communication with Enrico. | 2019-10-04 | Enrico Baez | Install TV bracket on wall near weight room. Provide recessed/flush single gang outlet near bracket. | YES | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
19P000311 |  | 19P000311 | FALSE | ATHLETICS | SL5 ATHLETICS 150-KEYLESS ENTRY | Keyless entry system | ATH DANCE | 0150 | CANCELED BY CLIENT | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43375 | [6 empty] | 02/07/2020 O-ANS: Canceled by customer Joe Erbland due to lack of funding per email to EBZ. | 2018-09-27 | Enrico Baez | Install keyless entry system, part of larger project throughout the athletics building | YES | 2020-02-07 | Summer 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20 | 1
19P000565 |  | 19P000565 | FALSE | BCOE | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS |  | BOURNS | A0133 | CANCELED BY CLIENT | Christopher Lynch | TBD | NANCY FORD |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43563 | [6 empty] | 07/30/19 O-ANS: Per Paul Ditty, Customer Maggie Souder canceled project. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000607 |  | 19P000607 | FALSE | CHASS | SL5 PAINT FACULTY OFFICE |  | WATKINS | 1312 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 2 |  | TRUE |  |  | 43595 | [6 empty] | 08/26/19: Canceled by customer because duplicate of project 20P000044. 08/13/19 O-ANS: Customer scope of work includes more than just PAINT so project added to Fall 2019 list for prioritization by organization. 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000605 |  | 19P000605 | FALSE | CHASS | SL5 PAINT NEW MAILROOM |  | WATKINS | 1320E | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43595 | [6 empty] | 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000211 |  | 20P000211 | FALSE | CHASS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | Install keyless entry system for door to Arts Building RM 54 | ARTS | 54 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 | R3 | FALSE |  |  | 43776 | [6 empty] | 1/19/21, DL: Enrico will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment installation. 8/5/20, DL: This Project is on hold until further notice……. | 2020-01-20 | Enrico Baez | 1/19/21, EB: Per Paul R., This project is canceled………….Provide new panel, power supply and door hardware for 2 doors. Prox reader only. | YES | 2021-01-19 | Winter 2021 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21 | 1
20P000220 |  | 20P000220 | FALSE | CNAS | SL5 SPIETH-NEW CLOSING/SECURITY MECHANISM FOR LOADING DOCK DOORS |  | SPIETH |  | CANCELED BY CLIENT | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | - |  | FALSE |  |  | 43783 | [8 empty] | Ron Veloz |  |  | 2019-11-22 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000335 |  | 20P000335 | FALSE | CNAS | SL5 ENTOMOLOGY BLDG 239-246 - PAINT AND PATCH OFFICE AND LAB |  | ENTOMOLOGY | 239 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43852 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY | 05/22/20 O-ANS: Project canceled per customer request (Bill Sutton). |  | 2020-05-22 | Spring 2020 | FS | FALSE | 2020 | 2021-02-16 | FY 19-20
20P000038 |  | 20P000038 | FALSE | CNAS | SL5 BATCHELOR HALL 1151- QUOTE FOR ADDING FOB ACCESS TO A DOOR |  | BATCHELOR | 1151 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | RACHEL BEHAR |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43670 | [6 empty] | 09/24/19 O-ANS: PROJECT CANCELD BY CLIENT PER EMAIL FROM DEBORAH MCWILLIAMS. |  | Ron Veloz |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
19P000413 |  | 19P000413 | FALSE | CNAS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | Batchelor 3111-Refresh BSL2 lab to accomodate Biosafety Cabinet. The Biosafety. Cabinet will be procured by BPSC. | BATCHELOR | 3111 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | MATTHEW ULRICH | PATTY SPRINGER | Dan Lerman |  | R1 | 107 | FALSE |  |  | 43451 | [6 empty] | 11/22/19 O-ANS: Project canceled per email from Deborah McWilliams. "The need for an appropriate space to accommodate use of a biosafety cabinet will be addressed in BH 2163 via the campus Batchelor Hall MEP-Tenant Improvement Project managed by PD&C." | 2019-06-12 | Ron Veloz | Preliminary assessment provided by Tiffany Kwok on 2/13/19 email. "For Batchelor 3111, there are a few items that need to be addressed before it can support BSL-2 work. • Floors should be patched to provide a smooth and easily cleanable surface. • Base coves along the wall should be replaced or repaired to provide a smooth and easily cleanable surface. • Base coves under the cabinets on the corners should be provided. • Provide a layer of sealant over the cabinets to ensure that the cabinets are moisture resistant and easily cleanable. • Seal, repair or replace the wooden rack on the wall to provide a moisture resistant and easily cleanable surface. • Ensure the door is self-closing. Since this is not a new facility and the space is not undergoing major renovations, it is not required to provide negative airflow into the space. However, it is still important that the air from the laboratory is not recirculated into clean spaces". | YES | 2019-08-26 | Winter 2020 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20 | 1
20P000086 |  | 20P000086 | FALSE | CNAS | SL5 SKYE 2ND FLOOR - KEY CARD ACCESS ESTIMATE |  | SKYE HALL | 2ND FLOOR | CANCELED BY CLIENT | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | R3 |  | FALSE |  |  | 43696 | [6 empty] | 09/26/19 O-ANS: CANCELED BY CUSTOMER - Estimated cost to go keyless outside of budget. | 2019-09-10 | Enrico Baez | Provide estimate for keyless entry. | YES | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
19P000555 |  | 19P000555 | FALSE | CNAS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK | INSTALL OF FENCE FOR RAIN COLLECTOR AT TES TANK | SAT CHIL PL | 0 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | R4 |  | FALSE |  |  | 43558 | Estimate from contractor | [5 empty] | 10/30/19 O-RVL: RV sent Andrew a message to ask if a decision was made to proceed with this project or if it will be cancelled?" Pending response. END~ 10/16/19, DL; I placed this project on hold as we have not heard back from the customer. We notified the customer of the cost but have not heard back from them. If the project is approved, we will schedule the work………...10/1/19, DL; Ron provide Deborah the propsal and we are waiting for her response to proceed or cancel the project……...9/16/19, DL; Ron submitted the estimate to Debora and the Faculty member last week. If project is approved, we will schedule the work……9/3/19, DL; Plans and estimate are complete. Ron will provide Deborah with a formal estimate and let us know if we will proceed with the work…..8/15/19, DL; Plans are approved. We ware waiting for a estimate from our contractor. Once we have the quote, we will forward the quoted to Deborah for review and approval. Note, this is a recharge project…….8/1/19, DL; Plans are complete pending approval from building official…. |  | Ron Veloz | Install Chain Link fence with gate. Includes grading, gravel and fence posts set in concrete. |  | 2019-10-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000017 |  | 20P000017 | FALSE | CNAS | SL5 COLLEGE BLDG CR200 - PAINT PROJECT |  | COLL BLDG NO | CR0200 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Dan Lerman |  | R4 |  | FALSE |  |  | 43661 | [6 empty] | 1/30/20, DL: This Project was Canceled per Rohnda via email on 1/29/20……….11/26/19, DL; Provided Ronda with updated quote on 11/25/19: She will present the quote to her team and provide us with an update in the near future if they would like to proceed………11/20/19 O-ANS: Re-assigned to Dan Lerman. Project was originally a paint project but will be outsourced as Recharge project paid for by the customer's department. |  | Dan Lerman |  |  | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
19P000594 |  | 19P000594 | FALSE | CNAS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS | Take down a dividing wall in this office and move the desks to their old location and rehang the overhead desk bins back into their old locations with inserts still in the walls. | ENTOMOLOGY | 171 | CANCELED BY CLIENT | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  | R9 |  | FALSE |  |  | 43581 | [8 empty] | Ron Veloz | TBD | NO | 2019-09-18 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000169 |  | 20P000169 | FALSE | PB&A | SL5 LOTHIAN LO-G104-OFFICE - JOB WALK FOR REMODEL OF SCOTTY'S |  | LOTHIAN HALL | SCOTTY'S | CANCELED BY CLIENT | Gerry Bomotti | TBD | FRED OFFENEY |  | John Peraino |  | - |  | FALSE |  |  | 43747 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000199 |  | 20P000199 | FALSE | SoB | SL5 ANDERSON SO RM 0002 - KEYLESS ENTRY MINOR RENOVATION REQUEST |  | ANDERSON 2 (S) | 2 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG | KENNETT LAI | Dan Lerman |  | - |  | FALSE |  |  | 43763 | [8 empty] | Enrico Baez |  |  | 2019-11-14 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000059 |  | 20P000059 | FALSE | SOM | SL5 SOME 2626- PATCH & PAINT |  | SOM EDUC | 2626 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43682 | [6 empty] | 11/26/2019 O-ANS: Project canceled per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000658 |  | 19P000658 | FALSE | SOM | SL5 SOM RB- PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD - PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43627 | [6 empty] | 03/05/20 O-ANS: Canceled by client per Cynthia Carolina. |  | Ron Veloz | TBD | NO | 2020-03-05 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000659 |  | 19P000659 | FALSE | SOM | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43627 | [6 empty] | 08/05/20 O-ANS: Canceled by client (Cynthia Carolina) via email with Ron Veloz. 8/5/20, DL: Dan to follow -up with customer…………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "remove 330 from work order / update project details / Update: Furniture on order 3.30.2020 - delivery tbd" |  | Ron Veloz | TBD | NO | 2020-08-05 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000206 |  | 20P000206 | FALSE | VC-STU AFF | SL5 COSTO HALL 111-HUB 353/381- RENOVATIONS - CP0003486 |  | COSTO HALL | Lower Level | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | - |  | FALSE |  |  | 43770 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000073 |  | 20P000073 | FALSE | VC-STU AFF | SL5 HUB - THE WELL -3RD FL RM 346 DOOR INSTALLATION CP00003544 | DOOR INSTALLATION | HUB | 346 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | JONATHAN GODOY |  | Dan Lerman |  | PENDING |  | FALSE |  |  | 43689 | [6 empty] | 12/13/19 O-ANS: Project canceled by client Brendan O-Brien. | 2019-10-02 | Enrico Baez | 1.) Remove Aluminum accordian door from opening. Customer to determine how to discard. 2.) Frame opening with metal 2"x4" stud and sheet with 3/4" drywall. Allow for oppening to accommodate 36"x 80" door. 3.) Install metal door jamb and casing to match exisiting openings. Door to match exisiting. Campus Fire Marshall to determine if door to be fire rated. Swing to be approved by Campus Building official and/or Campus Fire Marshall. 4.) Relocate single gang outlet on North side of opening , if needed. 5.) Finish drywall, prime and paint walls. Texture to match exisiting. Customer to approve final paint color. | YES | 2019-12-13 | FALL 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
18P000198 |  | 18P000198 | FALSE | VC-STU AFF | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Install new Wall lights | HUB | 0 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | R1 | 5 | FALSE |  |  | 43060 | Canceled per Brendan. No funding | [5 empty] | 10/30/19, DL: This project is on Hold and may be canceled as funding is not availabel at this time. Plans are approved……10/16/19, DL; Plans were submitted for plan check review last week. I also notified Brendan that this will be a recharge project . The ball park estimate I provided to Brendan was $7,000 - $9,000. Brendan needs to confirm if funds are available. If funds are available, I will have a contractor bid on the project……… 10/16/19: O-ANS - Not a CORE location so project changed to Recharge. 10/1/19, DL; Plans will be submitted a building permit and plan check review this week…….9/3/19, DL; Gunter has plans at 60%, We will try and submitt with in the next two weeks. 8/14/19, DL;This project is now on Gunther's bench. Gunter will start the process in about 2- weeks and we should have plans top submitt with in the next 30- days….6/17/19, DL; I will walk this work in the next two weeks and work on plan to submit to our campus architech and building official for review…..DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…… | 2018-01-23 | Enrico Baez |  | YES | 2019-10-30 | Winter 2018 | FS | FALSE | 2017 | 2021-02-16 | FY 19-20 | 1
20P000184 |  | 20P000184 | FALSE | VC-STU AFF | SL5 HUB 261 - CONSTRUCT WALL FOR MEETING/CONFERENCE RM | In HUB 261 the administration is requesting a wall be constructed to create a meeting/conference room. We need a building zone manager to walk the area give estimate as well as reaching out to the fire marshals inspector for recommendations. | HUB | 261 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | Manny Sanchez |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43755 | [6 empty] | 02/07/2020 O-ANS: Canceled due to client request. | 2019-11-05 | Enrico Baez | 11/5/19 E.Baez conducted site visit. **********SCOPE********* 1. Construct, full height, partition wall with door in HUB 261. 2. Provide/install ADA compliant door in new partition wall. 3. Add and relocate fire sprinkler. 4. Re-position lighting in ceiling, add lighting control. 5. Patch and paint. 6. Install base board. 7. Add strobe and smoke detectors. 8. T-bar ceiling re-work. | YES | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000225 |  | 20P000225 | FALSE | VC-UNIV ADV | SL5 HINDERAKER 0137 - BASEMENT RESTROOM SINK INSTALL | Install Kitchen Sink in entry room of Restroom 0137 | HINDERAKER | B137 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL | KIM MCDADE | Dan Lerman |  | 1 |  | FALSE |  |  | 43784 | [6 empty] | 1/22/20 O-ANS: Canceled per customer request. | 2020-01-22 | Enrico Baez |  | YES | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000417 |  | 19P000417 | FALSE | VC-UNIV ADV | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY |  | UV BLDG A | 201 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43452 | Schedule the work | 43691 | 43827 | [5 empty] | Enrico Baez |  |  | 2019-08-06 | Summer 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20 | 1
19P000621 |  | 19P000621 | FALSE | BCOE | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0308 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 10 |  | TRUE |  |  | 43599 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000233 |  | 20P000233 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - A169 & A170 ENTRY AREA DAMAGED |  | BOURNS | A169 & A170 | CANCELED BY FS | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43791 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000210 |  | 20P000210 | FALSE | BCOE | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | Reduce noise. Replace doors with solid core doors and install an Acoustic Door Seal Kit. | CHUNG HALL | 224 | CANCELED BY FS | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43774 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……. | 2020-02-11 | Ron Veloz | Removal of the existing double doors and door hardware, install new solid core double doors with continuous hinges, install new acoustical jamb seals, threshold seal and a surface mounted Automatic Door Bottom utilizing a flat spring mechanism, which activates when closing the door, lowering a neoprene seal insert against the floor or threshold to create a sound seal. Install acoustic double door astragals with seal. Reinstall all existing door locksets, and door closers. Quote received from Brad Aduddell-American Door to perform this work. Quote & Specs are available in the project folder. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000624 |  | 19P000624 | FALSE | BCOE | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | Refurbish Room-Student Space, | BOURNS | A0346 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43600 | Pending information from Susanna | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Susanna is working on a cubicle layout. Once we have the information from her. We will schedule the work………… | 2019-11-07 | Ron Veloz | Remove all lower cabinets in room A0346 and all lower cabinets and mail boxes in Rm A0304 | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000039 |  | 20P000039 | FALSE | BCOE | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE |  | BOURNS | A0318 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43598 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……..09/19/19 O-ANS: HOLD FOR WINTER 2020 PER CUSTOMER (LOUIS SANDOVAL) REQUEST. EMAILED PAUL DITTY TO CONFIRM. PAUL STATED THIS IS NON-PAINT PROJECT B/C SCOPE OF WORK INCLUDES CARPENTERS AND ELECTRIC SHOPS. |  | Paul Ditty |  |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000620 |  | 19P000620 | FALSE | BCOE | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0304 | CANCELED BY FS | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 9 |  | TRUE |  |  | 43599 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000427 |  | 19P000427 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | Install Power and TV bracket, move white board | CHUNG HALL | 453 | CANCELED BY FS | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43468 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold……… | 2019-09-18 | Ron Veloz | Install Power and TV bracket, remove white board and relocate , patch and paint wall prior to installing | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21 | 1
19P000502 |  | 19P000502 | FALSE | BCOE | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | Install Electrical power & TV bracket.for a 75" TV to mount in CS 342. | CHUNG HALL | 444 | CANCELED BY FS | Christopher Lynch | TBD | RICHARD BAIN |  | Dan Lerman |  | R3 |  | FALSE |  |  | 43515 | Schedule the work. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This project is on hold……………3/25/20, DL: Work orders are produced. I will work on scheduling the work when we return back to work…….. | 2019-09-17 | Ron Veloz | Install Electrical power & TV bracket. Excludes network/data back box and stub up to ceiling. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21 | 1
20P000183 |  | 20P000183 | FALSE | CHASS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | Install side walk | HUM & SOC SC | 1202 | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43756 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Also Existing door is compliant and there are other accessible exits to the building… 8/5/20, DL: This Project is on hold until further notice……. | 2019-11-13 | Enrico Baez | Construct Side walk. ADA compliance not required. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21 | 1
20P000185 |  | 20P000185 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR (OFF WHITE) |  | PHYSICS | 3004S | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 43756 | [6 empty] | 11/01/19 O-ANS: Canceling bc duplicate of 20P000187. Paul Ditty to speak with customer re: room. |  | Paul Ditty |  |  | 2019-11-01 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000242 |  | 20P000242 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 10 |  | TRUE |  |  | 43794 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000238 |  | 20P000238 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 14 |  | TRUE |  |  | 43794 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000614 |  | 19P000614 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 202- PAINT |  | COLL BLDG NO | 0202 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000616 |  | 19P000616 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 208- PAINT |  | COLL BLDG NO | 208 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000617 |  | 19P000617 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 212- PAINT |  | COLL BLDG NO | 212 | CANCELED BY FS | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | CANCELED BY FS | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Dan Lerman |  | R7 |  | FALSE |  |  | 43523 | We Need an FAU # | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced. We will schedule the work when we return from campus closure………11/11/19, DL: Project is in the queue to start but we do not have an FAU# as this is a recharge project. I sent Enrico and James an email requesting the FAU#. Once we have an FAU #, I will work on scheudling the work…..10/1/19, DL; Enrico is wtill working on estimate. | 2018-10-19 | Enrico Baez | E. Baez 1. Provide power in ceiling for projector. 2. Install projector center in room between two 4ft light fixtures. 3. Install 2 duplex outlets in 4S box on South West corner of room 4. Remove existing screen. 5. Install new screen centered on South wall. Extend power from existing screen to new screen location. 6. Use existing screen power switch to control new screen. | YES | 2020-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21 | 1
19P000543 |  | 19P000543 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION | TV Bracket &Power/Network box. | CHEMICAL SCI | 342 | CANCELED BY FS | Kathryn Uhrich | TBD | JEFFERY MATUTE |  | Dan Lerman |  | R8 |  | FALSE |  |  | 43545 | [7 empty] | 2019-10-01 | Ron Veloz | "The Chemistry Department is purchasing a 75" TV to mount in CS 342. The wall that will hold the TV needs to be inspected before any action of mounting the TV is done. The wall that we are hoping to place is the Brown-ish wall, where the projector screen is, opposite to the single whiteboard (Upon entry of CS 342, the leftmost wall). We would like a electrical outlet behind the TV, if possible". RV-Cut back sound proofing (sound soak) to accommodate TV brkt & electrical. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
19P000645 |  | 19P000645 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT | Termite Treatment/Cover Gate House and repair roughtd woos as necessary | BOTAN INFO C |  | CANCELED BY FS | Susan Marshburn | Da Lan Dinh | RONALD ANDERSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43607 | [8 empty] | Ron Veloz | BOTANIC GARDEN GATE HOUSE (AND OTHER STRUCTURES) REQUIRES EXTERMINATION OF TERMITES- WITH INSPECTION RESULTS RECEIVED BY ERS |  | 2019-08-29 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
18W007453 |  | 18W007453 | FALSE | ITS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  |  |  | FALSE |  |  | 43069 | waiting for bid from contractor | 43556 | 43645 |  |  |  | 07/22/19 O-ANS: Work Order converted to project # 19P000433. For further updates, see 19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  |  |  |  | 2019-07-22 | Winter 2019 | FS | FALSE | 2017 | 2021-02-16 | FY 19-20
20P000188 |  | 20P000188 | FALSE | LIBR | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 |  | ORBACH LIB | 204 | CANCELED BY FS | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43761 | Obtain floor covering samples | [5 empty] | 11/19/20 O-ANS: Declined to move forward by FS Admin but may revisit in future prioritization period. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: We are working on floor covering samples that will work for the space. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000162 |  | 20P000162 | FALSE | PROVOST/EVC | SL5 HINDERAKER 1101B - PATCH HOLE IN WALL |  | HINDERAKER | 1101B | CANCELED BY FS | Thomas Smith | Luisa Levario | AMY GU |  | Paul Ditty |  | - |  | FALSE |  |  | 43745 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000192 |  | 20P000192 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 1st Floor | CANCELED BY FS | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43761 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000662 |  | 19P000662 | FALSE | SOM | SL5 FY19-20 PROJECT: DEANS CONF ROOM | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | SOM EDUC | 2652 | CANCELED BY FS | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43628 | [8 empty] | Ron Veloz | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | NO | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000197 |  | 20P000197 | FALSE | VC-RED | SL5 UOB 210 - SOUND PROOF INSTALLATION |  | UNIV OFC BLD | 210 | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43762 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43340 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice. | 2018-09-27 | Enrico Baez |  | YES | 2020-11-19 | Fall 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 20-21
20P000047 |  | 20P000047 | FALSE | VC-RED | SL5 ADVANCED NEUROIMAGING | NEEDING TO TAKE DOWN OVERHEAD CABINETRY AND REPLACE WITH SOME KIND OF SHELVING TO OPTIMIZE SPACE. LOOKING FOR AN ESTIMATE AND A PLAN. | ADV NEURO |  | CANCELED BY FS | Rodolfo Torres | Laura Manor | CHELSEA EVELYN |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43677 | pending material delivery. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice…….3/23/20, DL: Shelves are ordered. We will schedule the work when we return from the campus closure……….1/15/20 O-DHN: Emailed Status Report to customer…...1/14/20, DL: We waiting for a revised quote from the vendor as there quote was not complete. We will process the quote for a PO# when we receive the correct quote……. 11/11/19, DL: Need to review scope with Ron as the shelving system is a special order item with a 3- month lead time….. | 2019-09-24 | Ron Veloz | Remove 5'-0" x3'-0" upper cabinet, and soffits. Patch and paint walls to match the existing grey . Install customer furnished adjustable shelf. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000534 |  | 19P000534 | FALSE | VC-STU AFF | SL5 PATCH WALLS AND PAINT |  | HEALTH SERV | 334 | CANCELED BY FS | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43539 | [6 empty] | 12/06/19 O-ANS: Canceled by FS because unable to identify room location even after inspecting rooms with staff support. Original requester has since retired. |  |  |  |  | 2019-12-06 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000309 |  | 20P000309 | FALSE | VC-UNIV ADV | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES |  | 1955 CHICAGO | 200 | CANCELED BY FS | Peter Hayashida | Naysia Caldwell | SARAH KARSON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43840 | [6 empty] | 12/16/20 O-ANS: Canceled by FS - Project location not serviced as FS CORE location and reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Please retain project # as reference. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  | 2020-12-16 | Spring 2020 | FS | FALSE | 2020 | 2021-02-16 | FY 20-21
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | COMPLETE | Kim Wilcox | TBD | ALEXIS RAMBAUD |  | Dan Lerman |  | 1 | 0 | FALSE |  |  | 43445 | schedule the work | 43486 | 43551 |  |  |  | 8/5/20, DL: This project is complete…………3/25/20,DL: Doors are scheduled to arrive the second week in April……2/19/20 O-DHN: Emailed Status Report to customer……2/18/20, DL: Work is complete except for Door and final deep cleaned I do have final stain samples from the vendor. I need to verify color……… We will complete the project when the doors arrive……….1/14/20, DL: Plans are approved, PO# is cut for the ordering of the custom doors, we are currently scheduled to start the work on or shortly after 1/21/20,. Karim understands that we will start and finish the project but we will not be able to install the door until the door arrives on site. There is a minimum of 6-8 week lead time on the door delivery………….12/16/19, DL: Plans are still in plan check review. I sent the building department an email asking for a startus update today…….10/16/19, DL; Plans were submitted to our building official this week for plan check review and a permit……9/16/19, DL; Guther will work on plans in the next three weeks. Once plans are complete, we will proceed with the permit process… | 2018-12-20 | Ron Veloz | SOW: Wall: Construct a metal stud framed wall with drywall up to hard ceiling (ceiling has 12x12 glue up ceiling tiles). Hardware: Install new lockset & keys are required.***** French Door: Install new stain grade birch door with full lite. Door and finish to match the existing office doors.***** Hard Ceiling: * Ceiling is 8’-0” A.F.F. + - with 12x12 glue up ceiling tiles. Work may require a new access panel if access to space above is needed. The 12x12 glue up ceiling tiles may need to be removed where the new wall is constructed.***** Flooring: The existing flooring will remain. Install rubber base to match existing.***** Painting, Taping & Sanding: Taping sanding and painting is required at the new wall and connecting walls.***** HVAC: May require modifications to split the existing supply air to accommodate the open office space.***** Electrical: Provide light switch at new office, power(new or relocate); add and or relocate electrical and voice/data outlets required for a standard office.***** Lighting: Provide a new light switch/circuit near office entrance. The existing 2x4 fixture is on main lighting circuit and will require lighting circuit modifications. Verify if the existing lighting is sufficient for the proposed office. Field verify if additional lighting is required.***** Fire Alarm: Provide a new Smoke/chime detector at new office area, confirm requirements. | YES | 2020-08-05 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 20-21
19P000673 |  | 19P000673 | FALSE | SOB | SL5 ANDERSON HAL NO, RM 158- RECARPET 12 ROOMS / ELECTRICAL WORK |  | ANDERSON 1 (N) | 158 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43634 | Construction | 43720 | 43731 |  |  |  | 10/1/19, DL; This proect is complete… |  | Enrico Baez |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000208 |  | 20P000208 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | Men's locker room refresh | ATH DANCE | 50 | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND | EUGENE HUTCHINSON | Dan Lerman |  | 1 |  | FALSE |  |  | 43773 | [6 empty] | 1/28/21, DL: Project is complete. Paul will schedule the paint once he is back on projects……….1/19/21, DL: We will schedule the balance of the paint before the students return back to campus………..9/30/20, DL: The work is complete except for the paint……………..8/5/20, DL: The work is almost complete.……. |  | Dan Lerman |  |  | 2021-01-28 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000646 |  | 19P000646 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING |  | ATH DANCE | 20R, 20S | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOSEPH ERBLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43608 | tile wash and shower doors | 43678 | 43735 |  |  |  | 9/16/19, DL; This project is Complete…….9/3/19, DL; Project is 80% Complete. Floor covering is scheduled for this Friday. Target complete date is 9/13/19……8/15/19, DL; This project is in progress and slated for complete by the end of september…..8/1/19, DL; Project is in progress with a complete date of 3-4 weeks. |  | Dan Lerman | 06/19/19 O-ANS: Project 19P000647 was combined with this project. |  | 2019-09-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Eugene Hutchinson | JOHNATHAN JENSEN |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43355 | [6 empty] | 2/5/20, DL: This Project is 100% Complete………….3/28/19, Doors are in the process of being …. DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez |  | YES | 2020-02-05 | Fall 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
19P000623 |  | 19P000623 | FALSE | BCOE | HOLD SL5 WINSTON CHUNG HALL, RM 348- MOUNT TV |  | CHUNG HALL | 0348 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  |  |  | FALSE |  |  | 43600 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000175 |  | 20P000175 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 112 - PATCH & PAINT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | - |  | FALSE |  |  | 43749 | [8 empty] | Ron Veloz | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with metal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000161 |  | 20P000161 | FALSE | BCOE | SL5 WCH 112 - MODIFY ROOM FOR NEW OCCUPANT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | TBD | MARGARET SOUDER |  | Paul Ditty |  | - |  | FALSE |  |  | 43742 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000163 |  | 20P000163 | FALSE | BCOE | SL5 BOURNS A0223 - PATCH/PAINT WALLS, DEEP CLEAN/REPLACE CARPET |  | BOURNS | A0223 | COMPLETE | Christopher Lynch | TBD | SABRINA SCHUSTER | DEANNA VORHEES | Paul Ditty |  | - |  | FALSE |  |  | 43745 | [8 empty] | Paul Ditty |  |  | 2019-11-25 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000388 |  | 19P000388 | FALSE | BCOE | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | BCOE Advising is being reassigned to space on the 3rd floor of Skye (at the recommendation of the University Space Committee). | SKYE HALL | 308 | COMPLETE | Christopher Lynch | TBD | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 43430 | Order material and schedule work | 43586 | 43644 |  |  |  | 7/15/19, DL; This project is 100% Complete………..7/1/19, DL; This project ois 95% Complete. Floor covering install will start this Wednesday…………6/17/19, DL; This project is almost complete. Target complete date is July 1st….…..5/31/19, DL; We are making good progress on this project. we are on tract to be copmplete with this project on or before July 1st……5/15/19, DL; Work is in progress and we are on schedule for th3 6/28/19 complete date…….5/1/19, DL; We will start this project this week. 4/15/19, DL; Plans were approved today. We will work on material and schedule the work. We will start this project shortly after May 1st…….3/18/19, DL; We are working on plans and plan to apply for building permit an plan review process next week | 2019-02-13 | Ron Veloz | Customer Request: Frame new walls in rm. 0310B & 0326. Widen door opening, install sliding glass door rm. 0310 Work Covered: Install metal stud framed partition walls in room 0310B and 0326 and install electrical and voice data outlets as required for new furniture layout. Widen the existing door opening in room 0310 and install one new 6-0x7-0 sliding glass door. Install a viewing window (approximately 9-0x4-0 overall width) made with two pieces of glass within a storefront frame. Relocate utilities and one wall *cabinet (*location TBD) as needed. Inclusions: Demolition: Remove the side door and frame in room 0310 and widen the opening to accept a 6-0x7-0 sliding door. Room 0310 east wall, cut in opening (approx. 9-0x4-0) at 36”-48” A.F.F.(field verify). Carpentry: Framing & Drywall: Rooms 0310B & 0326; Construct metal stud partition walls and new cased openings, and install drywall with finished edge metal (room 0310). Intersect new walls into the window mullions with a finished edge or metal with neoprene expansion tape installed between the wall and million. Room 0310; Frame a new cased opening to accept a 6-0x7-0 sliding door and frame a new cased opening at the east wall opening (approx. 9-0x4-0, at 36”-48” A.F.F. field verify) to accept a new viewing window. Floorcovering: Install new 4” rubber base in rooms 0310B and 0326, base to match existing. Acoustical Ceilings: Modify the T-bar ceiling grid and cut ceiling tiles to accommodate the new partition walls in rooms 0310B and 0326. Painting: Tape, sand and paint the new partition walls, door/cased openings. Patch and paint other walls in the Advising room 0310 as needed. Glazing: Room 0310; Install a 6-0x7-0 sliding glass commercial door (outsourced to Hour Glass). Quote is on file. Electrical: Room 0310; Relocate light switch and or wall mounted devices at room 0310/corridor wall and possibly may need to relocate conduit in the east wall where the new window opening is created. Rooms 0310B & 0326; reconfigure/separate lighting circuits and switching. Note: “Installation of electrical and voice data outlets may be required in the new partition walls at rooms 0310B & 0326 depending the furniture configuration”. Fire Alarm: Investigate at rooms 0310B & 0326. Fire Sprinklers: Investigate at rooms 0310B & 0326. Exclusions: Replacement of the existing carpet floorcovering. Repaint all walls at rooms 0310B and 0326 (paint new and adjacent walls only). Installation of new mixing boxes and T-stats in rooms 0310B and 0326. | YES | 2019-07-15 | Spring 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
20P000135 |  | 20P000135 | FALSE | BCOE | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MS&E Rm 0075 - 3 Ph208 Power CHW S&R WATER PPMS TOOL, Install Chilled water loop & power in clean room 075. | MAT SCI ENGR | 75 | COMPLETE | Christopher Lynch | TBD | MARK HEIDEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43727 | Plans and permit | [5 empty] | 9/30/20, DL: This project is complete……..8/5/20, DL: This is in progress…….3/25/20, DL: We will work on plans and permits when we return back from the campus closure……. | 2020-02-18 | Ron Veloz | Intake/SOW: Install 208V 3ph power & disconnect/safety switch and one 3/4" Chilled water loop (Supply and Return) in the MSE southeast corner of clean room 0075. Create a 4" diameter pass-thru hole from this corner of room 0075 into the adjacent room 0071. FS to provide power and cooling to a compressor which will connect through the wall to the PPMS system with cryogenic helium lines. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000107 |  | 20P000107 | FALSE | BCOE | SL5 WINSTON CHUNG 322 - PATCH/PAINT NEW FACULTY FACULTY OFFICE |  | CHUNG HALL | 322 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43706 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000129 |  | 20P000129 | FALSE | BCOE | SL5 BOURNS HALL B0360C - PATCH & PAINT |  | BOURNS | B0360C | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES | KATHY COCKER | Paul Ditty |  | 1 |  | TRUE |  |  | 43720 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/22/20 |  | Paul Ditty |  |  | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000245 |  | 20P000245 | FALSE | BCOE | SL5 WCH RM 0325 - PATCH AND PAINT DAMAGE FROM WHITE BOARD |  | CHUNG HALL | 325 | COMPLETE | Christopher Lynch | TBD | SARA GALLOWAY |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43794 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/13/20 |  | PAUL DITTY |  |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000638 |  | 19P000638 | FALSE | BCOE | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM | renovate lab | BOURNS | B207 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43601 | order material and schedule work | 43681 | 43742 |  |  |  | 11/11/19, DL: This project is Complete……10/30/19, DL: This Project is 95% complete and we should be complete next week………..10/16/19, DL; This project is 99% complete. We need to insulate ducting and deep clean the lab………9/16/19, DL; Project is 95% complete. We are planning to be complete in the next 30 days……9/3/19, DL; Project is in progress and 75% complete. 8/15/19, DL; Plans were approved this week. We will order the material and schedule the work……..Plans are 90% complete and we will probably submit plans for plan check review this Monday | 2019-07-19 | Ron Veloz | 07-01-19 O-RVL: RV Received email from Luat on 06-28 with revised SOW. RV Uploaded the referenced sketch into FAMIS. Revisions read: "In efforts to be helpful, I've color coded comments related to the simple attached sketch. 1) Unchanged: HVAC ductwork needs to be insulated so that we cannot hear it— the vibrations from the noise affect precision optical measurements. 2) Revised to be more specific: only the first row of overhead lights should be on the main switch (dark green). The other lights should be lowered and have pull-down chains, like this but with a longer a longer chain: https://www.grainger.com/product/19YX62 3) Removed: it would be nice if cabinets are nicer and not broken, but we'll turn them into open shelves if there are no funds for this. 4) Removed: (unless fire marshalls object and request sprinklers be lowered) 5) 3) Revised: for air venting machined fumes and soldering, a flexible fume vent should be installed, something like this: https://www.grainger.com/product/EXTRACT-ALL-Extractor-Arm-2DBX4 I'm flexible about where this is hung... what are the options? 6) 4) Revised: the utility rack in the center of the room should be moved to be in line with the other, and centered with the whiteboard on the wall. (Pink) 5) Added: chilled water (blue) and compressed air (light green) should be piped over so it's available to the 10'x3' optical table. 6) Added: Black plywood would be installed at the height of the current 8 1/2" frame like Kevin's in 2 spaces: a) around the 10x3' marked optical table b) around the 6x3' overhead rack close to the doors. Luat T. Vuong" | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000070 |  | 20P000070 | FALSE | BCOE | SL5 BOURNS B342D - PREPARE LAB FOR NEW FACULTY | PREPARE LAB FOR NEW FACULTY | BOURNS | B0342D | COMPLETE | Christopher Lynch | TBD | SABRINA SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43686 | work on paint contract | 43843 | 43864 |  |  |  | 2/28/20, DL This Project is Complete……….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is 95% Complete, we need to install 3 power outlets. This project will be 100% complete within two weeks……..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is on schedule to be complete before the 2/3/20 complete date…….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19,DL: We conducted a site visit with the PI> We will do what we can to have the project complete before 2/3/20………… | 2019-11-06 | Ron Veloz | Paint all walls to match existing colors, paint the back of wood cabinets located at the east side of the room, replace stained or damaged ceiling tiles, replace and or replace all HVAC supply & return grilles, relamp as needed, Cal Labs to clean SS sinks, disconnect and dispose of the dishwasher, Plumbing and electrical to disconnect, Cal Labs to refurbish counter tops (light sand & seal), clean strip and wax sheet vinyl floor, repair and refurbish cabinets (white Rm 316, Blue Rm 328), customer to remove all chemical and sanitize fume hoods. | YES | 2020-02-28 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000477 |  | 19P000477 | FALSE | BCOE | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT |  | CHUNG HALL | 457 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 11 |  | FALSE |  |  | 43495 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43594 | Finish Gas cabinet installation | 43731 | 43868 |  |  |  | 8/5/20, DL: This Project is Complete…….3/25/20, DL: Project is 95% complete. We will install the fire sprinkler and exhaust duct to the gas cabinet when we return from the campus closure………..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Plans were approved and material is ordered. We are hopeful the material will arrive the 2nd or 3rd week in January. Once material is on site we will schedule the work…… 11/19/19 DH: Emailed Status Report to customer……10/16/19, DL: This project is 90% Complete. We are working on plans and permits for the two snorkels……….10/1/19, DL: This project is almost complete. We will be complete in the next 4- weeks except the Snorkel……….. 9/13/19, DL; The paint of the cabinets is scheduled for this week along with the power. We will submit the plans for the snorkel this with in the next two weeks…….9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Ron Veloz | SOW, Patch& Paint Walls, replace plexi glass on shelving, powder coat metal shelving & cabinets, clean & polish or replace chem sinks, polish counter tops, Validate all gas, water, drains, DI water & utilities. Replace damaged and dirty ceiling tiles, relamp as needed. Strip & wax floor. Dan L is requesting vendor pricing to restore finishes. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000028 |  | 20P000028 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0219- PAINT FACULTY OFFICES |  | BOURNS | A0219 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43665 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000602 |  | 19P000602 | FALSE | BCOE | SL5 BOURNS B328F- PREPARE LAB FOR NEW PI OCCUPANCY |  | BOURNS | B0328F | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43594 | Finish the work… | 43871 | 43897 |  |  |  | 3/25/20, DL: this Project is Complete………...2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is almost complete and should be complete in the next 2-3 weeks………..10/30/19, DL: Plans and permits will be required for the work. We will work on the plans shortly after Thanksgiving……….. | 2019-09-27 | Ron Veloz | Construct metal stud wall framing and bracing above ceiling to infill the opening. Remove and reinstallation wall mounted cabinets located near the cased opening to access and join to the existing wall to new drywall. Install sound insulation. Install drywall, tape, sand, prime and paint wall. Install install rubber base to match existing. Modify T-bar ceiling to accept the wall framing Provide dust containment (Zip Walls) at both rooms near construction area. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000487 |  | 19P000487 | FALSE | BCOE | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES |  | BOURNS | A219, A211, A241 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43501 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000601 |  | 19P000601 | FALSE | BCOE | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY | Renopvate lab space, Patch/paint, Re-finish, re-surface – existing cabinets/casework. Re-finish, bench-tops. Clean existing Chemical fume hood. Repair or replace self-closing chemical/flammables storage cabinet. Repair or replace bench shelves as needed. Clean and wax floors. | BOURNS | B0328E | COMPLETE | Christopher Lynch | TBD | KATHALENA COCKER |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43594 | Order material and scheudle work |  | 43868 |  |  |  | 2/28/20, DL: This project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL; This Project should be complete in the next 2-3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were approved. We will order material and schedule the work once the material is on site. The material should arrive around the 21st of January…….11/25/19, DL; Floor covering will be complete today. This project is complete except for the Snorkel vents. We are still waiting for plans check approval on the snorkels………11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Floor covering is delayed. We will schedule the floor covering installation when the material is on site. We submitted the plans for the snorkels last week. Once the plans are approved, we will order the phoenix valves and schedule the work………. 10/30/19, DL: This Project is 85% Complete. We will install new floor covering in the next two weeks. All work will be completed except the two snorkels. We still need to submit plans for the snorkels……..10/16/19, DL; This project is 80% complete. 9/16/19, DL; Project is in progress. We still need to submit plans for the snorkel for the power and snorkel. We will submit the plans for review within the next week. Once plans are approved, we will schedule the work……..Scope is complete, waiting on estimates from vendors. We will need to work up a contract which will add time to the project timeline… | 2019-08-06 | Ron Veloz | Provide two new 4” exhaust duct drops. One at the south wall above mobile table & one at the east wall above counter. Refinish two wood work station counter tops with chemical resistant coating (approx. 64lf) including one mobile table wood top. Install four(4) 208v / 30a Electrical receptacles and data drops at gutter racks above two work benches Provide drawer and door maintenance and or repairs at all metal cabinets and metal shelving. Powder coat all lower metal cabinets, shelving, fume hood doors and drawers. Replace damaged sheet vinyl flooring as needed. Move surplus items to materials management as identified by the PI. Install MilQ equipment at the east wall near sink. Relocated cylinder rack as necessary to accommodate “L” shaped work station. Provide and install two new cylinder racks at the south end of two work benches. Furnish and install two new metal cylinder racks. Replace damaged and/or stained 2x4 acoustical ceiling tiles. Relocate “L” shaped front cabinets. Relamp light fixtures and needed. Infill wall between rm 328E & D Patch and paint walls. Strip and wax floor. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000221 |  | 20P000221 | FALSE | BCOE | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | COMPLETE | Christopher Lynch | TBD | HONG XU | KEVIN FREEDMAN | Dan Lerman |  | 3 |  | FALSE |  |  | 43784 | [6 empty] | 1/19/21, DL: This project is 100% Complete……..9/30/20, DL: We are in the process of finishing up a few other projects. Once they are complete, we will schedule the work….8/5/20, DL: Plans are approved and we will start the work in the next 2-6 weeks…….. | 2020-02-25 | Ron Veloz | Install Plywood and supports. Paint Plywood black. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000029 |  | 20P000029 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0211- PAINT FACULTY OFFICES |  | BOURNS | A0211 | COMPLETE | Christopher Lynch | TBD | DEANNA VORHEES |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43665 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/12/19 |  | Paul Ditty |  |  | 2019-12-12 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000597 |  | 19P000597 | FALSE | BCOE | SL5 PATCH AND PAINT WALLS |  | CHUNG HALL | 355, 356, 351, & 353 | COMPLETE | Christopher Lynch | TBD | SARA GALLOWAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43588 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000625 |  | 19P000625 | FALSE | BCOE | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM |  | BOURNS | A0108 | COMPLETE | Christopher Lynch | TBD | LOUIS SANDOVAL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43600 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-01 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000558 |  | 19P000558 | FALSE | BCOE | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT |  | BOURNS | A0265 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43558 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000065 |  | 20P000065 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR CONFERENCE ROOM 205/206 - PATCH & PAINT |  | CHUNG HALL | 205 & 206 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43685 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000657 |  | 19P000657 | FALSE | BCOE | SL5 WINSTON CHUNG HALL, RM 406- PATCH/PAINT OFFICE |  | CHUNG HALL | 406 | COMPLETE | Christopher Lynch | TBD | BILL BINGHAM |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43623 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000526 |  | 19P000526 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT |  | CHUNG HALL | 0202 & 0203 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43536 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-08 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
21P000037 |  | 21P000037 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | Paint Only | CHUNG HALL | 427 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44043 | [6 empty] | 01/19/21 O-ANS: Paint complete per technician and closed project. 11/30/20 B-SBT: repatch & Paint north wall |  | Paul Ditty |  |  | 2020-11-30 | Winter 2021 | FS | FALSE | 2020 | 2021-02-16 | FY 20-21
20P000449 |  | 20P000449 | FALSE | BCOE | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | Paint Only - Chung Hall, Fourth Floor, Room 461 Patch & Paint: At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. Follow up with fresh paint. Thank you. | CHUNG HALL | 461 | COMPLETE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43993 | [6 empty] | 01/19/21 O-ANS: Complete per technician updates and closed project. Completed by Wendy M. 11/09 -SC |  | Paul Ditty |  |  | 2020-11-09 | Winter 2021 | FS | FALSE | 2020 | 2021-02-16 | FY 20-21
20P000068 |  | 20P000068 | FALSE | CHANCELLOR | SL5 SKYE 349 - COVER HOLES ON WALL |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | TBD | VICTORIA AVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43686 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000142 |  | 20P000142 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 5502 - PATCH AND PAINT FACULTY OFFICE |  | HUM & SOC SC | 5502 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000143 |  | 20P000143 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 6605 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 6605 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000141 |  | 20P000141 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4401- PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4401 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000140 |  | 20P000140 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4400 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4400 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-10-09 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000195 |  | 20P000195 | FALSE | CHASS | SL5 ARTS 0054 - PAINT PIANO LAB |  | ARTS | 54 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | - |  | FALSE |  |  | 43762 | [8 empty] | Paul Ditty |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000044 |  | 20P000044 | FALSE | CHASS | SL5 WATKINS 1312 - NEW HIRE RENOVATION - ELIZABETH BERGER | Install drywall over out dated would paneling | WATKINS | 1312 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43676 | Install drywall | 43843 | 43875 |  |  |  | 2/19/20, DL: This project is Complete…………..1/14/20, DL: We started this project today and should be complete with in 3-4 weeks………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will plan on starting the project the 2nd week in January but will not confirm until we have confirmation from the carpenter shop…………11/18/19 DH: Emailed Status Report to customer……11/11/19, DL: The Material is ordered. The carpenters may start the work the week of 11/18/19………10/30/19, DL: I received confirmation the space is vacant we will schedule the work in the next 6- 8 weeks……10/16/19, DL; The plans are approved and the work is complete. I need to schedule final inspection………. | 2019-09-23 | Enrico Baez | ABATEMENT NEEDED----remove mastic from walls at base on wood paneled wall CARPENTERS 1.) Remove chalk board 2.) Install 1/2" plywood over wood paneled walls. Including over plywood partition separating wall. Do not drywall over trim. 3.) Finish drywall. ELECTRICIANS 1.) Bring out electrical for new drywall and secure when drywall has been installed. PAINTERS 1.) Patch, paint and finish all walls. CUSTODIAL 1.) Clean space after construction. | YES | 2020-02-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000194 |  | 20P000194 | FALSE | CHASS | SL5 WATKINS 1224 - PAINT NEW FACULTY OFFICE ONLY |  | WATKINS | 1224 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43755 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/09/20 |  | Paul Ditty |  |  | 2020-01-09 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000237 |  | 20P000237 | FALSE | CHASS | SL5 HMNSS 1202A - PATCH AND PAINT SERVICE |  | HUM & SOC SC | 1202A | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTIAN BACK |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43791 | [8 empty] | PAUL DITTY | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/14/20. |  | 2020-02-14 | Spring 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000664 |  | 19P000664 | FALSE | CHASS | SL5 WATKINS HALL, RM 1343/1343A- PAINT OFFICE AND LAB |  | WATKINS | 1343 & 1343A | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43628 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-08 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000575 |  | 19P000575 | FALSE | CHASS | SL5 WATKINS HALL PAINT/FLOORING |  | WATKINS | 1309A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43572 | [6 empty] | 11/26/2019 O-ANS: Paint phase completed per Paul Ditty. Awaiting completion of flooring. |  |  | 01/31/20 O-ANS: Completed per notes as of 09/05/19. |  | 2019-09-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000337 |  | 19P000337 | FALSE | CHASS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | Remove whiteboard (in front of room), mount LED mount, add double duplex and electrical power behind LED, patch and paint wall | PSYCHOLOGY1 | 3210 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 1 | 101 | FALSE |  |  | 43384 | site visit and schedule the work | 43724 | 43707 |  |  |  | 10/1/19, DL; This Project is Complete……………..9/3/19, DL; Space is blocked and schedculed to be completed by 9/27/19…..8/14/19, DL; Conducted site visit with Trades. We will schedule the space to be blocked out and start the work mid September….8/1/19, DL; Planning to start this project in two weeks……7/15/19, DL; I will walk the project in the near future and schedule the work if permits are not required…… | 2019-01-15 | Enrico Baez | Electricians 1. Install behind TV. Provide two duplex outlets and power. Also provide single gang box and conduit for data. Data lines have been run to T-bar in Hallway. 2. Secure loose Extron plate and cover next to TV. Painters 1. Patch and paint wall where TV is mounted | YES | 2019-10-01 | Summer 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
19P000643 |  | 19P000643 | FALSE | CHASS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH |  | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 14 |  | FALSE |  |  | 43606 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000002 |  | 20P000002 | FALSE | CHASS | SL5 HMNSS, RM 1212- REMOVAL OF ROLL UP WINDOW |  | HUM & SOC SC | 1212 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43647 | schedule the work | 43836 | 43861 |  |  |  | 1/30/20, DL: This project is Complete. We will istall the monitor after IT services installls the Data lines. Michael or Aliosn will notify us when IT is complete and we will schedule th emonitor installation…………1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: This project is in progress and will be complete with in two weeks……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project was delayed. The material is currently ordered. We are planning to start the week of 1/6/20……. 11/19/19 DH: Emailed Status Report to customer….10/30/19, DL; We will plan on scheduling the work shortly after Thanksgiving……….10/16/19, DL: Plans are approved, we will order the material and schedule the work once material is on site. Projected start date is mid November………..9/16/19, DL; Plans will be submitted this week for building permit and plan check review….. | 2019-10-01 | Dan Lerman | Remove Roll up partition. Install outlet and data port, patch and paint walls. | YES | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000214 |  | 20P000214 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | Remove walls and doors in spaces 2139 A,B and C. | PSYCHOLOGY1 | 2nd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43776 | Obtain building permit | [5 empty] | 9/30/20, DL: This Project is Complete…………8/5/20, DL: we will submiot plans this week.…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Plans were submitted for a permit on 2/12/20. Once plans are approved, we will order the material and schedule the work……… | 2020-01-10 | Enrico Baez | **************************************SCOPE********************************** 1.) Remove doors, and jambs 2139A, 2139B, 2139C. 2.) Remove drop ceiling in 2139A, 2139B, 2139C and repair as needed. 3.) Remove cabinets in 2139A, 2139B, 2139C. 4.) Remove walls between 2139A & B, and remove walls between 2139B & C. 5.) Change light fixture to match existing. 6.) Repair walls as needed. 7.) Patch and paint as needed. 8.) Replace carpet and base in 2139A, 2139B, 2139C and 2139 common area. 9.) HVAC duct work in individual spaces can be removed and simplified. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000419 |  | 19P000419 | FALSE | CHASS | SL5 CHASS INT SOUTH 2117-CARD ACCESS | Remove Door and wall leading to 2117 Media Library and reconfigure to allow enterance into 2117 A & J without having to go through 2117C. | CHASS INT S | 2117 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43452 | [6 empty] | 12/16/19, DL: This project is now complete…….11/19/19 DH: Emailed Status Report to customer…..11/11/19, The work is 98% Complete. We have one door that we had to send back to the vendor to have it prepared for door hardware. We should have the door back on site with in the next two weeks………..10/30/19, DL: Doors and Frame are on site. The paint team will prime and paint the doors and frame. Once the doors and frame are painted, we will schedule the work……………10/1/19, DL; This Project is 90% Complete. We are waiting on the doors to arrive. Once the doors arrive, we will schedule them to be painted and installed…………..9/3/19, DL; We started this project today. We are planning to be 90% complete by 9/27/19. Note, we have special order doors that have a 4-6 week lead time and that is the reason why we will be only 90% complete on 9/27/19. Paul Richardson is aware of the schedule…….8/15/19, DL; The plans were approved this week, we will order the needed material and start the work very soon…….This is a two part project. We will complete the construction process now. The four doors that need key card access still require a request for proposal and a contract. This portion of the project will take 3- months due to contracts administration, lead time on material and contractor scheduling…….8/1/19, DL; Gunther is working on plans. Once permit is approved, we will schedule the work…. | 2019-03-21 | Enrico Baez | Install 8 position control panel, keyless entry for 2117, 2117A, 2117D and 2117E. ***per Paul Richardson remove 2117G, 2117H and 2117J from request*** !!!!Project to reconfigure wall space, 19P000400 has been combined with 19P000419. !!! | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
20P000004 |  | 20P000004 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - COURTNEY BAKER |  | HUM & SOC SC | 2204 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43648 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000145 |  | 20P000145 | FALSE | CHASS | SL5 PSYCHOLOGY 1111 - PATCH AND PAINT FRONT OFFICE WALL |  | PSYCHOLOGY1 | 1111 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43733 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20 |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
18P000126 |  | 18P000126 | FALSE | CHASS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS |  | HUM & SOC SC | 3611 | COMPLETE | Juliet McMullin | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 43006 | Order material and schedule work | 43635 | 43645 |  |  |  | 7/1/19,DL; This project is 100% Complete…..5/15/19, DL; Work is scheduled to start on 6/19/19…….5/1/19, DL; Plans are approved. Need to order material and schedule the work…..3/18/19, DL; Plans submitted to PD&C today…..02/2819, DL; Gunther will work on plans over the next three weeks to submit for a building permit. We will schedule the work if and after the plans are approved. If approved the door and window will more than likely have a 3- month lead time…………….12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez |  | YES | 2019-07-01 | Winter 2018 | FS | FALSE | 2017 | 2021-02-16 | FY 19-20
18P000343 |  | 18P000343 | FALSE | CHASS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER |  | THTR WKSH | 0400A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 43175 | sheet metal to install handrail | [5 empty] | 11/15/19, DL: This project is complete…..10/30/19, DL: Sheet metal shop fabricated the hand rails. The paint shop will prime and paint the hand rails and the curb. Once the rails are painted, the sheet metal shop will complete the installation…….10/16/19, DL; Cory from the sheet metal shop is aware of the scope of work and they will schedule the work in the near future……..10/1/19, DL; Dan to show Cory from sheet metal the area where a hand rail will be installed for painting backdrops……..07/11/19 O-ANS: Dan and Chris P will walk the space. 05/21/19 O-ANS: Changed to In Progress per meeting with Dan L. Chris P is the PM for further updates. DL and CP will visit after commencement. 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez |  | YES | 2019-11-15 | Spring 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
19P000574 |  | 19P000574 | FALSE | CHASS | SL5 FACULTY OFFICE PAINTING |  | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43567 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000120 |  | 20P000120 | FALSE | CHASS | SL5 OLMSTED 2139 SUITE - PATCH AND PAINT |  | OLMSTED | 2139 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 43713 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/14/20 |  | Paul Ditty |  |  | 2020-01-14 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000005 |  | 20P000005 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - KIM FROST |  | HUM & SOC SC | 3215 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43648 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000215 |  | 20P000215 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | Remove Vaughan wall seperating Olmsted 3349/3351.Add 4 single gang outlets and 2, 2gang outlets. | PSYCHOLOGY1 | 3rd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43776 | [6 empty] | 1/19/21, DL: This project is 100% complete…………9/30/20, DL: Plans were approved, we had the Vaughn Wall tested for Asbestos containing material. Once we have the results, we will schedule the work………….8/5/20, DL: We will submit plans by this Friday for a building permit | 2020-02-24 | Enrico Baez | 2/24/2020 E. Baez - 1.Remove Vaughan wall and electrical circuit in wall. 2. Add 4 Single Gan outlets and 2, 2gang outlets. 3. Patch vinyl plank flooring from removed wall and safe. 4. Remove panel in 2249 with wall paper on it next to window. 5. Remove handle set to 3351, install blank, render door inoperable. 6. Repair T-Bar ceiling as needed. 7. Patch and paint walls. 8. Coordinate with ITS for data line for 8 computers. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000609 |  | 19P000609 | FALSE | CHASS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR |  | WATKINS | 1229 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43595 | [6 empty] | 07/03/19 O-ANS: Paint phase complete and awaiting flooring change. 06/21/19 O-ANS: Customer requested to remove lighting change from project and only complete paint and carpeting via email to Paul Ditty (copied email below). Will create separate work order for lighting. Re-assigned to Paul Ditty to complete. "From: Becky L Campbell <becky.campbell@ucr.edu> Sent: Friday, June 21, 2019 10:51 AM In regards of the work order: 19P000609 - SL5 - PAINT FACULTY OFFICE – please cancel the connecting Work Order 19W015231 – REPLACING THE LIGHTING IN WATKINS 1229. Please do paint and replace flooring.For the lighting, please create new work order to be done at a later time." |  | Paul Ditty |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000090 |  | 20P000090 | FALSE | CHASS | SL5 OLMSTED 3345 - PAINT WALL AND FILL HOLES |  | OLMSTED | 3345 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43697 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000112 |  | 20P000112 | FALSE | CHASS | SL5 PSYCHOLOGY 2123 - PATCH AND PAINT JOB |  | PSYCHOLOGY1 | 2123 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43712 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000350 |  | 19P000350 | FALSE | CHASS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | MISC WORK IN ROOMS 3121 AND 1133 Patch and paint-relocate white boards, hang pictures. | PSYCHOLOGY1 | 3121, 1133 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 4 | 3 | TRUE |  |  | 43390 | Start this Friday. | 43679 | 43693 |  |  |  | 8/15/19, DL; This Project is 100% Complete…….. 8/1/19, DL; We will start this project this Friday…… 7/15/19, DL; Appears not plans and permits will be required for the work. I will verify and schedule the work in the near future if no plans or permits are required….. | 2019-04-15 | Enrico Baez | Carpentry: 1. Needs to occur after October 26 2. Remove the whiteboard in 3121, patch and paint 3. Remove Glass board in 1133 and relocate to 3121 (in the same way and place as it was in 1133) 3. Mount pictures on the wall in 3121 4. Secure shelving units in 1133 and 3121 5. There is a ceiling tile in 1133 that is stained and needs to be replaced Painters: 1. Room 3121 Patch and Paint walls | YES | 2019-08-15 | Summer 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
19P000676 |  | 19P000676 | FALSE | CHASS | SL5 PATCH THE PAINT IN THIS OFFICE |  | HUM & SOC SC | 2501 | COMPLETE | Juliet McMullin | Cindy Williams | EVAN ISMAIL |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43635 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000421 |  | 19P000421 | FALSE | CHASS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | Install door to access hallway directly | OLMSTED | 2139I | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 5 | 110 | TRUE |  |  | 43453 | Order material and schedule work | 43850 | 43896 |  |  |  | 2/28/20, DL: This Project is Complete….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This Project is 95% complete. We should be complete within the next week…………..1/31/20 O-DHN: Emailed Status Report to customer……1/30/20,DL; Project is in progress and should be complete with in 2- weeks………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will work on the construction schedule and material shortly after the new year. 11/21/19 DH: Emailed Status Report to customer…..10/30/19, DL: Plans are approved. Need to find out the status of the door. We will plan on scheduling the project shortly after Thanksgiving…………10/1/19, DL; Plans are approved. We need to order the door / Frame. Once door is on site, we will schedule the work……..9/16/19, DL; Plans are submitted for the permit review process……9/3/19, DL; Plans are at 50%. We will try and have plans to submit for review within the next two weeks…… | 2019-02-05 | Enrico Baez | *****This work is being performed to accommodate new faculty scheduled to arrive July 1, 2019***** Core work falls under SLA Carpenters • Open wall between corridor and 2139I. • Install metal frame and solid core door similar to 2139. Smoke and draft gasket. • Install carpet patch at threshold of new door. Carpet should match or complement existing carpet. • Remove bulletin board in hallway to facilitate doorway construction and relocate on same wall. See photos in shared drive.. • Replace base boards as needed. Painters • Prime, Patch and Paint walls, doors and trim. • Paint to match existing wall colors. Lock Shop • Furnish and install 1 each, ADA compliant handle sets, match existing hardware. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
20P000172 |  | 20P000172 | FALSE | CHASS | SL5 PYSCHOLOGY 2136B & 2136C - PAINT & PATCH |  | PSYCHOLOGY1 | 2136B & 2136C | COMPLETE | Juliet McMullin | Cindy Williams | ANNIKA KIRMAN | YERAM CHEONG | Paul Ditty |  | 5 |  | FALSE |  |  | 43748 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000171 |  | 20P000171 | FALSE | CHASS | SL5 CHASS INTN 2107 - PATCH UP HOLES IN THE WALL |  | CHASS INT N | 2017 | COMPLETE | Juliet McMullin | Cindy Williams | GENEVA AMADOR |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43748 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/03/20 |  | Paul Ditty |  |  | 2020-01-03 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000642 |  | 19P000642 | FALSE | CHASS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM |  | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43606 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000552 |  | 19P000552 | FALSE | CHASS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS |  | HUM & SOC SC | 1001 B, C, and D | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43551 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000207 |  | 19P000207 | FALSE | CHASS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43335 | working on plans | 43619 | 43644 |  |  |  | 8/1/19, DL: This project is 100% Complete……7/15/19, DL; Floor covering will be installed next week. Floor covering is the last item for this project……..7/1/19, DL; This project is 95% complete except floor covering. Floor covering will be installed within 2- weeks……6/17/19, DL; This project is making good progress. We should be complete near July 1st…….5/31/19, DL; This project started this week and should be complete by June 28th…….3/18/19, DL; Working on plans and we will submit our plans and permit application this week….. | 2018-09-20 | Enrico Baez |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
20P000082 |  | 20P000082 | FALSE | CHASS | SL5 HUMANITIES THEATRE - PATCH & PAINT |  | THTR WKSH | 405 | COMPLETE | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43692 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000204 |  | 20P000204 | FALSE | CHASS | SL5 ARTS 166 - PATCH AND PAINT IN LOBBY AND GREEN ROOM |  | ARTS | 166 | COMPLETE | Juliet McMullin | Cindy Williams | ALBERT FETTER |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43769 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/20/19 |  | Paul Ditty |  |  | 2019-12-20 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000094 |  | 20P000094 | FALSE | CHASS | SL5 ARTS 0221 -PAINT OFFICE |  | ARTS | 221 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43699 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000226 |  | 20P000226 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 3401 - OFFICE PATCH AND PAINT |  | HUM & SOC SC | 3401 | COMPLETE | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON | TRACY AVERY | Paul Ditty |  | 8 |  | TRUE |  |  | 43787 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/03/20. |  | Paul Ditty |  |  | 2020-02-03 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000448 |  | 19P000448 | FALSE | CHASS | SL5 ARTS 333- PATCH AND PAINT |  | ARTS | 333 | COMPLETE | Juliet McMullin | Cindy Williams | SONJA SEKELY-ROWLAND |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43479 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-04 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000589 |  | 19P000589 | FALSE | CHASS | SL5 HMSS OFFICE 3405 RENOVATIONS | Construct partion, pending CBO approval, in room 3405. | HUM & SOC SC | 3405 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 8 |  | FALSE |  |  | 43578 | Install carpet | 43709 | 43784 |  |  |  | 11/19/19 DH: Emailed Status Report to customer…..11/19/19 DL: This project is complete….11/11/19, DL: The carpet is delayed and scheduled to be instlled on Friday, 11/15/19. The project will be complete once the carpet is installed……10/30/19, DL: This project is 90% Complete. We are planning to install carpet next week………..10/16/19, DL; This project is 80% complete. Target complete date is 3- weeks…..10/3/19 O-ANS: Updated status per minor reno meeting…. 10/1/19, DL; This project is in progress. We will call for rough electrical inspection….. 9/16/19, DL; We are ready to schedule the work. We are currently waiting for the space to be vacated. Once the space is vacant, we will start the project……9/3/19, DL; We are ready to start the work. The PI returned to work this week. I sent Paul R. an email letting him know we are available to start once we have confirmed dates from him…..8/15/19, DL; Plans are approved but the PI is not. We will probably start the project the 2nd week in September…… | 2019-06-27 | Enrico Baez | CARPENTERS: 1. Construct partition above T-bar ceiling, full height not required. Drywall 5/8" tape and finish. 2. Remove and store three book cases. 3. Cut in opening for 36" (stain grade to match) door in general area of were bookcases were in South wall leading to corridor. Painters: 1. Patch and paint as needed Electricians: 1. Isolate existing switches to control to operate lights in West half of partitioned space. 2. Install two additional switches in East partition. 3. Install additional single gang outlets one on each side of new partition. Telecom: 1. Install additional Voice and data connection in Western side of partitioned space. Flooring: 1. Remove carpet and base. 2. Install new customer selected base and flooring. HVAC: 1. Separate existing duct work from one to two zones controlled by separate stats in each office. | YES | 2019-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000540 |  | 19P000540 | FALSE | CHASS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | Remove metal roll up window, replace carpet, remove round column cover-reframe square. | HUM & SOC SC | 1202 | COMPLETE | Juliet McMullin | Cindy Williams | MICHAEL MOLINAR |  | Dan Lerman |  | 9 |  | FALSE |  |  | 43544 | Plans and permit | 43836 | 43875 |  |  |  | 2/18/20, DL: Thois project is 100% Complete…….1/31/20 O-DHN: Emailed Status Report to customer…..1/30/20, DL; Project is 95% complete. We will install carpet this weekend………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is in progress and should be complete within 3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project was delayed. Material is ordered. We are currently scheduled to start shortly after 1/6/20………..11/19/19 DH: Emailed Status Report to customer…..10/30/19, DL: We will plan on scheduling the project shortly after Thanksgiving……….. 10/16/19, DL; Plans were approved, we will work on ordering material and schedule the work. Anticipated start date is mid-November…….10/1/19, DL; Plans were submitted last week. Once plans are approved, we will schedule the work…………9/16/19, DL; Plans are 90% Complete. We will submit plans for plan check review in the next two weeks……. 8/15/19, DL; Gunter has the project on his list. We will try and be ready for plan check review in the next two weeks…….. | 2019-07-25 | Enrico Baez | 7/1/2019 E. Baez Carpenters: 1. Remove roll up partition and stainless steel counter top. 2. Frame opening, hang drywall, tape and finish 3. Remove round decorative column from support pillar. 4. Frame over column for square foot print. Keep as narrow as possible. 5. Hang drywall, tape and finish. Painters: 1. Paint all new construction Flooring: 1. Remove carpet and base in 1202, lobby area of 1220 and hallway. Refer to drawing. 2. Replace customer selected carpet and base. | YES | 2020-02-18 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000608 |  | 19P000608 | FALSE | CHASS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE |  | WATKINS | 1345 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43595 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-27 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000232 |  | 20P000232 | FALSE | CHASS | SL5 PSYCHOLOGY 3111B - WALL PATCH FOR SMALL HOLES IN THE WALL |  | PSYCHOLOGY1 | 3111B | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43789 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000429 |  | 19P000429 | FALSE | CHASS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | Patch & Paint | COLL BLDG NO | 103 | COMPLETE | Juliet McMullin | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43468 | [6 empty] | 07/26/19 O-ANS: Project complete per Paul Ditty. 06/06/19 O-ANS: Project scheduled to be completed. |  |  |  |  | 2019-07-26 | SPRING 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000213 |  | 20P000213 | FALSE | CHASS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS |  | CHASS INT S | 2117A, 2117C, 2117D, 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43777 | approved permit | 43893 | 43911 |  |  |  | 8/5/20, DL: This Project is Complete……………..2819/20 O-DHN: Emailed Status Report to customer…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have a contract, we will order the material and schedule the work………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Plans are complete and submitted for building permit. We are also working on the contract. Once the plans are approved and the contract is complete, we will schedule the work………. |  | Enrico Baez |  |  | 2020-08-05 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21 | 1
19P000568 |  | 19P000568 | FALSE | CHASS | HOLD SL5 HMSS HANG WHITE BOARD, TV MOUNTING, PATCH AND PAINT | Remove Glass White Board, mount TV, patch and paint | HUM & SOC SC | 1214 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43564 | [8 empty] | Enrico Baez | No scope |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000187 |  | 20P000187 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR |  | PHYSICS | 3004S | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 43761 | [8 empty] | Paul Ditty |  |  | 2019-11-05 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000390 |  | 19P000390 | FALSE | CNAS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | COMPLETE | Kathryn Uhrich | TBD | APRIL MEINZER |  | Dan Lerman |  | 0 |  | TRUE |  |  | 43433 | Order material and schedule work | 43617 | 43644 |  |  |  | 7/1/19, DL; This project is 100% Complete…………6/17/19, DL; material is ordered. This project should be complete by July 1st…..5/31/19, DL; Plans were apprvied this week we will work on the contract and hopefully have the notice to proceed in the next two weeks. It is our goal to have the work complete on or before July 1st……5/15/19, DL; Need to order the special order door and frame…. | 2019-02-07 | Ron Veloz | Install new aluminum storefront door, frame and side lite(requested by Dan L.), patch & paint door opening and west interior wall. | YES | 2019-07-01 | SPRING 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
20P000202 |  | 20P000202 | FALSE | CNAS | SL5 SKYE HALL 361 RENOVATION PROJECT | Renovete space for class room. | SKYE HALL | 361 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY | MELISSA GOMEX | Dan Lerman |  | 1 |  | FALSE |  |  | 43768 | pending permit approval | 43866 | 43917 |  |  |  | 9/30/20, DL: This Project is Complete……….8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Permits were approved. Demolition is complete…..1/15/20 O-DHN: Emailed Status Report to customer……..1/14/20, DL: Plans have been submitted for a building permit. Once plans are approved, it is our goal to complete the work by the beginning of spring quarter….. |  | Ron Veloz | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000036 |  | 20P000036 | FALSE | CNAS | SL5 ENTOMOLOGY 224 - PAINT OFFICE FOR NEW PI HANSEN |  | ENTOMOLOGY | 224 | COMPLETE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43669 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20. 09/19/19 O-ANS: Project placed on HOLD for WINTER 2020 prioritization per customer request. |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000075 |  | 20P000075 | FALSE | CNAS | SL5 SPIETH 2372 - PATCH/PAINT FACULTY OFFICE |  | SPIETH | 2372 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43690 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-27 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000639 |  | 19P000639 | FALSE | CNAS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK | Make modifications to accommodate new PI | CHEMICAL SCI | 0435 | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43602 | finish electrical and plumbing.. | 43769 | 43805 |  |  |  | 12/16/19, DL: This project is complete…11/19/19 Emailed Status to customer….11/11/19, DL: This project is 90% Complete. We should be complete with the balance of the work in the next two weeks…………10/30/19, DL: This project is in progress and should be complete in 3- weeks……..10/16/19, DL; We will start the work in the next two weeks. 9/16/19, DL; We will start working on the plans in the next 3- weeks and submit them for plan check review. Once approved, we will schedule the work……..9/3/19, DL; Need to verify scope with Ron and start working on plans. Will start plans in the next two- three weeks…… | 2019-07-19 | Ron Veloz | For new Faculty Hire, Dr. Timothy Su we need the following done to CS 435: Original SOW: (1) Add a door between 435 and 439 (swinging outside of 435 into 439). (2) Exhaust connection for a biosafety cabinet (3) Vacuum line hook up (4) Gas cylinder rack Revised SOW 07/30/19: Room 435: (A) Remove mounted wooden cabinets (B) Remove standing wooden cabinet (C) Move flammable cabinet to Room 439 (D) Move flammable refrigerator to Room 447 Room 439: (A) Remove cabinets under sink Room 441: (A) Remove cabinets under sink (B) Remove top and bottom cabinets and bench, then deliver both items to Chemical Sciences Rm 108 (C) De-activate airflow in chemical fume hood #005855 if it does not disrupt air flow in the other chemical fume hoods. Can facilities check whether it is possible to turn valve off for this fume hood without disrupting others? (D) Move biosafety cabinet and incubator from Rm 458 to Rm 441, then hook up biosafety cabinet to house vacuum plumbing (E) Move flammable cabinet to Rm 439 | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000061 |  | 20P000061 | FALSE | CNAS | SL5 PHYSICS 1028 - MOVE UTILITIES FOR GLASS SHOP | Install utilities in Physics for the Glass shop equipment relocated from Pierce. | PHYSICS | 1028 | COMPLETE | Kathryn Uhrich | TBD | CHRISTOPHER BARDEEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43683 | Plans and permits | 43787 | 43854 |  |  |  | 04/23/20 O-ANS: Complete per Dan Lerman. Separate work order to install gas line created - 20W026489 …. 1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is 90% complete and should be 100% complete 1/24/20………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 95% complete. They are moving the equipment over. Once the equipment is delivered and setup, we will connect all of the power and plumbing……11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL; We are still working on plans for this project. 10/30/19, DL: We're planning to complete the project by 12/7/19. We are working on the plans and are planning to submit the plans for plan check review tomorrow. | 2019-10-16 | Ron Veloz | Electrical: Relocate existing power for the welder & other equipment. Install new power and safety switch for relocated equipment. Relocate power for welder and other equipment to the machine shop side of the north wall. Plumbing: Lab air and Natural Gas - relocate and install new POC's. Install water supply lines to Wet sander and diamond wet saw. Cap and or extend the existing Lab air and natural gas as necessary. Install drain lines for new equipment. Modify water supply and existing sink and faucet. Carpentry: Demo selected upper and lower cabinets at the West wall. | YES | 2020-04-23 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000571 |  | 19P000571 | FALSE | CNAS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 |  | SCIENCE LAB1 | 215 & 322 | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO |  | Paul Ditty |  | 10 |  | FALSE |  |  | 43565 | [6 empty] | 07/30/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000239 |  | 20P000239 | FALSE | CNAS | SL5 SKYE 382 - PATCH AND PAINT |  | SKYE HALL | 382 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 11 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000240 |  | 20P000240 | FALSE | CNAS | SL5 SKYE 384 - PATCH AND PAINT |  | SKYE HALL | 384 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 12 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000241 |  | 20P000241 | FALSE | CNAS | SL5 SKYE 386 - PATCH AND PAINT |  | SKYE HALL | 386 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 13 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000200 |  | 20P000200 | FALSE | CNAS | SL5 COLLEGE BLDG NO 306 - PATCH AND PAINT ONE WALL ONLY |  | COLL BLDG NO | 306 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 15 |  | FALSE |  |  | 43767 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/06/20. |  | Paul Ditty |  |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000105 |  | 20P000105 | FALSE | CNAS | SL5 PHYSICS 2029 - PATCH AND PAINT |  | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Paul Ditty |  | 17 |  | FALSE |  |  | 43705 | [8 empty] | Paul Ditty | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/06/20. |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000034 |  | 20P000034 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 451- PATCH AND PAINT 2 SMALL WALL SECTIONS |  | CHEMICAL SCI | 451 | COMPLETE | Kathryn Uhrich | TBD | KEVIN KOU |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43668 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-02 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000189 |  | 20P000189 | FALSE | CNAS | SL5 SPIETH 3352 - ESTIMATE FOR PATCH AND PAINT |  | SPIETH | 3352 | COMPLETE | Kathryn Uhrich | TBD | NATALIE HOLT | SILVANA | Paul Ditty |  | 2 |  | FALSE |  |  | 43761 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/28/20 |  | Paul Ditty |  |  | 2020-01-28 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000355 |  | 20P000355 | FALSE | CNAS | SL5 GEOL 454A- PATCH & PAINT |  | GEOLOGY | 0454A | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | LAURIE GRAHAM | PAUL DITTY |  | 2 |  | FALSE |  |  | 43870 | [8 empty] | PAUL DITTY | 08/06/20 O-ANS: Closed per Paul Ditty as of 03/13/20. |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2020 | 2021-02-16 | FY 19-20
19P000622 |  | 19P000622 | FALSE | CNAS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK | Replace doors & frame | FAWCETT LAB | 204 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43600 | order door and frame. | 43691 | 43754 |  |  |  | 11/11/19, DL: This project is complete……10/30/19,DL: The doors are scheduled to be installed this Friday…………10/16/19, DL; Doors shuld be here with in the next week. Once the doors arrive, we will prep and paint the first coat and schedule the install. Target complete date is 3-4 weeks depending on when the doors arrive…….9/16/19, DL The doors are ordered. Once the doors arrive, we will schedule them to be painted and installed……..9/3/19, DL; Contractor has PO# for the doors. I need to verify lead time on material and schedule the installation…….8/15/19, DL; PO# will be provided this week to order the doors and frame, lead time is 4- weeks for the doors/ frame. We will scheudule the install once the door / frame is on site……..8/1/19, DL ; Pending estimate from vendor. Once we have everything needed, we will schedule the work…. | 2019-07-15 | Ron Veloz | Replace existing dual egress doors with ne doors and frames. | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000081 |  | 20P000081 | FALSE | CNAS | SL5 CHEM SCI 0441- INSTALL FUME HOODS | Install vacuum to new fume hood | CHEMICAL SCI | 441 | COMPLETE | Kathryn Uhrich | TBD | TIMOTHY SU |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43692 | schedule the work | 43763 | 43791 |  |  |  | 1/14/20, DL This Project is 100% Complete…….12/17/19 O-DHN: Emailed Status report to customer…..12/16/19, DL: This Project is almost Complete except for connecting the glove box. Cory will try and connect the glove box before the new year……...11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: This project should be complete with in the next two weeks……….10/30/19, DL: This project is in progress and we should be complete in 2- 3 weeks…………10/16/19, DL: We will start this project with in the next two weeks…. |  | Ron Veloz | Install eight (8ea) electrical swithced outlets behind cabinets for new vac pumps, remove doors and install sliding lower pump shelves. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000283 |  | 19P000283 | FALSE | CNAS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | COMPLETE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 20 |  | FALSE |  |  | 43348 | Schedule site visit with contrac | 43619 | 43648 |  |  |  | 8/1/19, DL; This Project is 100% Complete……7/1/19, DL; Barricades are complete. Signage needs to be installed. Signage to be installed in the next 3- weeks………….6/17/19, DL; Yello Caution tape is installed. Still need to install barricades and signage. Target complete date in mid to late July……5/31/19, DL; The contractor has the PO#. We will start the work and complete the work in the next 30- days……5/15/19, DL; We are waiting on the quote, once we have the quote, we will proceed with the work……4/15/19, DL; We are trying to locate a roofing contractor that will complete the installation. This is a specialty product that requires a professional installation…….3/28/19, DL; We will install the yellow caution tape on the roof which is our most viable option. I will schedule a site visist / job walk with a contractor in the near future…… | 2018-09-19 | Ron Veloz | Install hand railing and marking for a leading edge as direcetd by EH&S. | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
18P000388 |  | 18P000388 | FALSE | CNAS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 43200 | schedule the work | 43619 | 43696 |  |  |  | 8/14/19, DL; This project is 100% Complete………8/1/19, DL; This project work from Facilities Services should be complete in about 2- weeks…..7/15/19, DL, Work is in progress. Goal is to be complete with our scope near the first week in August……6/17/19, DL; This will be scheduled in July…….5/31/19, DL; Demo and removal of the dishwasher is. We will work on the installation and elctrical / power connections over the next three weeks. Note. Steam shut down is taking priority and the installation may be delayed….. 5/15/19, DL; We will schedule the work……..DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but there is no hard date as this is vacant space and we will access the space as time permits…… DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter….DL, DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans….7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved….. |  | Enrico Baez |  | YES | 2019-08-14 | Summer 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
18P000486 |  | 18P000486 | FALSE | CNAS | SL5 PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 43279 | plans and permits | 43553 | 43647 |  |  |  | 8/1/19, DL; This project is 100% Complete…… 6/17/19, DL; This project is making good progreess and will be complete near mid- July…..5/31/19, DL; This project is making good progress and we are hopeful to be complete on or before July 1st……5/1/19, DL: This project is in grogress and moving forward. Target complete date is 6- weeks… 4/15/19, DL; Started Demolition phase….2/28/19, DL; We will work on the plans in the next 30-days.12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
19P000210 |  | 19P000210 | FALSE | CNAS | SL5 CHEMICAL SCI Install Door In Doorway |  | CHEMICAL SCI | 0225A | COMPLETE | Kathryn Uhrich | TBD | BARBARA OUTZEN |  | Dan Lerman |  | 25 |  | FALSE |  |  | 43336 | contract the work and material | 43619 | 43647 |  |  |  | 7/1/19, DL; This project is 100% complete…..6/17/19, DL; Po is cut. Target complete date is before 7/1/19……Permit was approved this week. We are now working on the contract with the vendor. Our goal is start the work with in the next 30- days. 5/15/19, DL; Plans were approved. I am in the process of working with PD&C for the contract. We will order material and schedule the wrok once we have a signed contract……..3/28/19, DL; Plans were submitted last week… 3/18/19, DL; Conducted site visit last week. We are working on plans now we will try and submit plans for permit review next week…… | 2018-09-19 | Ron Veloz |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
20P000207 |  | 20P000207 | FALSE | CNAS | SL5 PHYSICS 3033 - PAINT & PATCH STAFF OFFICE |  | PHYSICS | 3033 | COMPLETE | Kathryn Uhrich | TBD | MAYELA CASTILLO | DAVID NEFF | Paul Ditty |  | 3 |  | FALSE |  |  | 43773 | [6 empty] | 03/02/20 O-ANS: Completed per Paul Ditty as of 02/04/20. |  | Paul Ditty |  |  | 2020-02-04 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000613 |  | 19P000613 | FALSE | CNAS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT |  | COLL BLDG NO | 0203B | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43599 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-21 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000024 |  | 20P000024 | FALSE | CNAS | SL5 PHYSICS 1003- RENOVATION | New Faculty-Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 1003 | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43664 | clean out the space | 43843 | 43889 |  |  |  | 3/25/20, DL: This project is complete……2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: The paint is complete and the floor covering should be delivered this week. Once the floor covering is on site, we will schedule the installation……………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We started this project and should be complete in the next 6- weeks……….11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: David who is responsible for clearing out the space is in the process. Once the space is empty we will schedule the work. We will probably start the physical project shortly after Thanksgiving…….10/30/19, DL; We are planning to start this project within the next 6-8 weeks……. | 2019-10-16 | Ron Veloz | Test for ACM and or other hazardous materials in the room. Replace all existing flooring, remove power pole and miscellaneous wall mounted items shelving/racks, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks) and repair/replace top & bottom flush bolts, install new door closer(s), relamp with LED as needed. Replace faucet, clean sink/counter and infill pit. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000266 |  | 20P000266 | FALSE | CNAS | SL5 GEOLOGY 2460B - PATCH & PAINT |  | GEOLOGY | 2460B | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 3 |  | FALSE |  |  | 43818 | [8 empty] | PAUL DITTY | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000688 |  | 19P000688 | FALSE | CNAS | SL5 PHYSICS- RENOVATION OF THREE PHYSICS ROOMS | Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 2128 | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43644 | finish abatment | 43774 | 43814 |  |  |  | 1/14/20, DL: This Project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 99% Complete. Custodial will be there this week to complete the final clean. The space will be ready for occupancy starting 1/6/19…..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: The project is on track to be complete on 12/13/19. Once the abatement is complete, we will start the wall repair as the walls are severely damaged from the previous use of the space……10/30/19, DL: WE are working on this project. Our target date for completion is 12/17/19………… | 2019-10-16 | Ron Veloz | Test for ACM and or other hazardous materials in the room. RM 2124, 2128 & 2132: Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2128 Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2132: Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000267 |  | 20P000267 | FALSE | CNAS | SL5 GEOLOGY 2460C - PATCH & PAINT |  | GEOLOGY | 2460C | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 4 |  | FALSE |  |  | 43818 | [8 empty] | PAUL DITTY | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/04/20. |  | 2020-03-04 | Spring 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000235 |  | 20P000235 | FALSE | CNAS | SL5 SKYE 374 - PATCH AND PAINT |  | SKYE HALL | 374 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 4 |  | TRUE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000508 |  | 19P000508 | FALSE | CNAS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | BOYCE | 3410 | COMPLETE | Kathryn Uhrich | TBD | CHERYL GERRY |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43517 |  | 43773 | 43805 |  |  |  | 1/30/20, DL: Project is now cxomplete. The electrical panel cover was installed this morning…………. 11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: We are not complete. We still need to complete the following items; Light bulbs, electrical panel cover, replace ACM ceiling tiles and deep clean the space…..10/30/19, DL: Progress is in progress. We should be done within two weeks…….10/16/19, DL; Paint is in progress and additional work to follow. Target date for complete is 11/19/19…..10/1/19, DL; Jess to survey space for ACM, Lead paint, etc… We will schedule work once we have confirmation from Jess….. | 2019-09-30 | Ron Veloz | ……….Remove lower base cabinets and upper cabinet in room 3410B. Repair delaminated flooring between room 3410 & 3426, Patch and Paint entire rooms 3410, 3410B & 3426 up to 8'H(no paint in in 3410 A&C). Repair damaged floor tiles in room 3410 A&B. Repace all burned out lamps w/ LED throughout labs and office. Strip & wax all floors in labs space. Remove cylinder racks in room 3410B. Fabricate a hinged metal door to cover the electrical panel in roon 3426 (panel is near door). | YES | 2020-01-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | COMPLETE | Kathryn Uhrich | TBD | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 43332 | Work will be complete in 2 weeks | 43864 | 43903 |  |  |  | 8/5/20, DL: This project is complete……………..06/17/20, DL: This project should be complete with in the next two weeks……..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within two weeks. Once we have a contract, we will schedule the work……….1/15/20 O-DH: Emailed Status Report to customer……1/14/20, DL: Contracts is currently working on the contract. Once the contract is complete, we will order the material and schedule the work…………11/26/19, DL: Plans were approved. We will work on the construction contract. Once we have the notice to proceed, we will schedule the work……….10/15/19, DL: Sent PD&C and follow-up email on 11/11/19. We should have approved plans in the near future……10/30/19, DL: Sent PD&C an email asking for a status update on 10.30.19…… 10/16/19, DL; Plans are still in plan check. I sent the building official an email asking if any additional information is needed. This work will be completed by a contractor which means we need to allow time for the bid and contract process……… …………9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Ron Veloz | Request for Estimate to install three new FOB readers with electrified locksets. Work covered: Install one AC Fob Reader at door 2221 and one AC Fob reader at each Door 4231 & 4235. Connect card readers to the existing Hirsh ACP located in the IDF closet at each floor. 03/07/19: Scope revised to eliminate two FOB readers. Install one FOB reader at Genomics door 4231 only instead of all three rooms. | YES | 2020-08-05 | Fall 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 20-21
20P000236 |  | 20P000236 | FALSE | CNAS | SL5 SKYE 368 - PATCH AND PAINT |  | SKYE HALL | 368 | COMPLETE | Kathryn Uhrich | TBD | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 5 |  | TRUE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000268 |  | 20P000268 | FALSE | CNAS | SL5 GEOLOGY 2460D - PATCH & PAINT |  | GEOLOGY | 2460D | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 5 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | PAUL DITTY |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000615 |  | 19P000615 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT |  | COLL BLDG NO | 203 AND 204 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43599 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000019 |  | 20P000019 | FALSE | CNAS | SL5 PHYSICS 2029A- NEW EYEWASH STATION | PHYSICS 2029A- INSTALL A NEW EYEWASH STATION | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | TBD | DAVID NEFF |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43662 | order material | 43889 | 43917 |  |  |  | 2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL; Permit was approved, we need to order material and schedule the work………. | 2019-11-27 | Ron Veloz | Install new eyewashing station | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000523 |  | 19P000523 | FALSE | CNAS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | PATCH & PAINT GRAD STUDENT OFFICE | SPIETH | 3366 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Paul Ditty |  | 5 | 9 | FALSE |  |  | 43536 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-20 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000247 |  | 20P000247 | FALSE | CNAS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | Refresh Lab: Patch paint, strip & clean floor, repair broken ceiling and floor (VCT) tiles at room 2110 & 2118. Install Electrical power & Co2 cylinder racks at each end of workbench/tables | SPIETH | 2110 + 2118 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS | SHERICE UNDERWOOD | Dan Lerman |  | 6 |  | TRUE |  |  | 43796 | [6 empty] | 1/19/21, DL: This project is complete…………..9/30/20, DL: This project is in progress and will be compete in the next 6- 8 weeks……………8/5/20, DL: We will start on this project in the next 6-8 weeks….. | 2020-04-17 | Ron Veloz | Spieth 2110: Carpentry: Seismic anchoring for “New” tables and equipment. Replace damaged ceiling tiles. Install misc. wall mounted items. Sheet Metal: Remove “existing” steel cage. Fabricate & install metal cylinder rack w/ restrains/seismic anchoring to floor. Plumbing: Install Co2 POC for gas cylinders at four (4ea) new free-standing work benches (see configuration on this document). Electrical: Install dedicated *120v power drop & connect to the existing power strips built-in the four (4ea) new workstation tables (see configuration on this document). *VERIFY/CONFIRM VOLTAGE W/ D. MCW. Relamp fixtures as needed. Spieth 2118 & 2110: Sheetmetal: Clean and or replace air distribution grilles. Flooring: Repair/patch broken floor tile and Replace broken ceiling tiles (abate floor tiles if required). Painting: Paint and patch all walls, verify recondition doors @ room side. Plumbing: Assess sinks to be fully operational & clean. *Replace sink in Rm 2118 for glassware, confirm with Faculty/Estella. Replace sink in room 2118 (Sink type TBD by Faculty). HVAC: Check lab air pressure is operational & proper pressure. Custodial: Strip and Wax floor, clean interior windows, wipe down doors and windowsills. EXCLUSIONS: Furnish, assemble, and install new workstations, tables or lab equipment. Removal of existing lab furniture or equipment. Natural gas or air output taps not required (per Faculty). | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000121 |  | 20P000121 | FALSE | CNAS | SL5 SKYE 217 - PATCH AND PAINT |  | SKYE HALL | 217 | COMPLETE | Kathryn Uhrich | TBD | JAMES MARBERRY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43713 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000023 |  | 20P000023 | FALSE | CNAS | SL5 PIERCE RM 1144 - PATCH AND PAINT DOOR WHERE WALL POCKET WAS |  | PIERCE | 1144 | COMPLETE | Kathryn Uhrich | TBD | JACQUELINE |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43664 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000269 |  | 20P000269 | FALSE | CNAS | SL5 GEOLOGY 2460E - PATCH & PAINT |  | GEOLOGY | 2460E | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 6 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/05/20. |  | PAUL DITTY |  |  | 2020-03-05 | Spring 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000270 |  | 20P000270 | FALSE | CNAS | SL5 GEOLOGY 2460F - PATCH & PAINT |  | GEOLOGY | 2460F | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 7 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | PAUL DITTY |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GH08 | 881 | COMPLETE | Kathryn Uhrich | TBD | NANCY FERGUSON |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43494 | Schedule the work. | [5 empty] | 1/19/21, DL: This project is complete……………8/5/20, DL: This project is in Progress and should be complete in the next 8-12 weeks…………….3/25/20, DL: Work orders are produced. Once we are back to work, we will schedule the work………12/11/19 O-ANS: Re-assigned as project allotment - priority #7 for Winter 2020. 11/27/19 O-ANS: Hold by client for re-prioritization for Winter 2020. | 2020-03-04 | Ron Veloz | Install new 3 ton Packaged unit with heat pump and dedicated electrical service on the roof top. Provide 1ea return plenum, 2ea supply drops in the work space. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000113 |  | 20P000113 | FALSE | CNAS | SL5 GEOLOGY 2258 - PATCHPAINT RECEPTION WALL OVER BIN REMOVED |  | GEOLOGY | 2258 | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43712 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000271 |  | 20P000271 | FALSE | CNAS | SL5 GEOLOGY 2460G - PATCH & PAINT |  | GEOLOGY | 2460G | COMPLETE | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 8 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/06/20. |  | PAUL DITTY |  |  | 2020-03-06 | Spring 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000155 |  | 20P000155 | FALSE | CNAS | SL5 BOYCE 3407 - PAINT OFFICE FOR NEW FACULTY |  | BOYCE | 3407 | COMPLETE | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | TRUE |  |  | 43739 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/30/20 |  | Paul Ditty |  |  | 2020-01-30 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
18P000465 |  | 18P000465 | FALSE | CNAS | SL 5 GEOLOGY 2258B AND 2258C - PATCH/PAINT |  | GEOLOGY | 2258B & 2258C | COMPLETE | Kathryn Uhrich | TBD | RONDA INZUNZA |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 43257 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
19P000377 |  | 19P000377 | FALSE | CNAS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | Replace the gates on the Schneider House driveway, which secure the property, with the taller iron gates that used to be installed at the Gardens entrance. This will require new fence posts and hinges as well. The taller gates are stored along the side of the garage at Schneider House, and Facilities staff can come see them anytime. Please note this is a safety and security project. | BOT GDN HSE |  | COMPLETE | Kathryn Uhrich | TBD | AMBER RHEMREV |  | Dan Lerman |  | R2 | 117 | FALSE |  |  | 43412 | PO#, schedule the work | 43787 | 43797 |  |  |  | 11/26/19, D: This Project is 100% Complete……………11/19/19 DH: Emailed Status Report to customer….11/15/19, DL: We should have A PO this week. Once we have the PO#, we will schedule the work……10/30/19, DL: Project was approved by customer with an FAU #. I will work on providing a PO# as this is maintenance and schedule the work. | 2019-04-05 | Ron Veloz | Replace Gates with new refurbished & modified gates furnished by BG. Install new steel posts and strip and repaint gates. Gate style revised by customer to purchase vendor fabricated light gauge meta gates without spike, per Jodie Holt 10/09/19. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20 | 1
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | R3 |  | TRUE |  |  | 43550 | Schedule the work | 43861 | 43882 |  |  |  | 8/5/20, DL: This Project is COMPLETE…….3/25/20, DL: The material is here and we are 95% complete with the work. We will complete the work when we return from the campus closure…………1/31/20 O-DHN: Emailed Status Report to customer…….1/30/20,DL: The pump is now on site but we are still waiting for the fittings. In the mean time, our plumber is putting everything together and is working on the installation. Once the fittings arrive, we will make the connections and the system should be good to go………….1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: The pump is scheduled to arrive on or before 1/31/20. We will schedule the work once we have the pump and material on site…..11/26/19, DL; Emailed Natalie and Sherice the quote for the vacuum pump. We will order the material and schedule the work once we have approval and the pump on site……11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: I sent the vendor a 2nd email requesting an update on the proposal. I also included Natalie on the email so she is aware of where we stand with the proposal……10/30/19, DL: We had a followup meeting with the vendor last week. The vendor is now working on a pump that will best meet our needs……….10/16/19, DL; We are working with a vendor on a quote for a new lab vacuum pump. We are hoping to have a quote in the next week or two…..9/16/19, DL; Estimate was provided to customer last week. If the project is approved, we will work on the plans and permits. Once approved, we will schedule the work…… |  | Ron Veloz | Old SOW Revised SOWInstall exhaust hood, electical receptacle, vacuum pump, vac lines and valves (six valves total) and hood location. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21 | 1
19P000517 |  | 19P000517 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | COMPLETE | LaRae Lundgren | TBD | DANIELLE GARCIA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43531 | Verify scope and schedule work | 43801 | 44185 |  |  |  | 1/19/21, DL: This project is complete…………..8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced, We will schedule the work when we return from the campus closure…………11/11/19, DL: I will work on scheduling this project… | 2019-06-17 | Enrico Baez | 6/17/19 E. Baez Conducted site visit with Sean. Will need carpenters to mount TV and electricians to add outlet to North wall. Data not needed. Might need painters depending on how carpenters install TV mount. | YES | 2021-01-19 | FALL 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000467 |  | 19P000467 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | WATKINS | 2101 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 43487 | Finish project. | 43739 | 43819 |  |  |  | 1/14/20, DL: This project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Project is 99.9% complete. We should be complete with the work by this Friday. Furniture is scheduled to be install this Friday morning……..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL; The project is still on schedule to be completed on 12/12/19…………….10/30/19, DL: This Project is on Schedule to be completed on or before 12/17/19….10/16/19, DL; This project is in progress with a completion date of 12/15/19…….10/1/19, DL; We will schedule the work. Our portion of the project will be completed mid December……….9/16/19, DL; We will work on the plans soon. This project will be complete by 12/21/19….. 09/03/19 O-ANS: Updated Priority to #1 for Fall 2019 per Susan request. 9/3/19, We are scheduled to complete the work before winter break begins….. |  | Enrico Baez |  |  | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43487 | finish plans/submit application | 43840 | 43917 |  |  |  | 8/5/20, DL: This Project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer…..2/18/20, DL: We are making great progress and still on schedule to be complete before Spring Break begins. We pass drywall inspection on 2/18/20………..1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: Plans are approved. All items have been removed from the space. Abatement is schedule to take place within two weeks…..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were submitted for plan check review. Fire marshal stamped the plans, we are waiting on the final stamp from our building official. Once plans are approved we will order material and schedule the work……..10/30/19, DL: Gunter is working on plans. We are planning to complete the work before Spring Quarter begins. |  | Dan Lerman |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000085 |  | 20P000085 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 FACILITES ANNEX B - PAINT OFFICE SPACE |  | FS ANNEX B | 0001 | COMPLETE | Susan Marshburn | Da Lan Dinh | SANDRA MARTINEZ |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 43696 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000560 |  | 19P000560 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION |  | UV BLDG B | 0240B | COMPLETE | Susan Marshburn | Da Lan Dinh | LESLIE ROSE |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43559 | waiting for material to arrive | 43678 | 43700 |  |  |  | 9/3/19, DL; This project is 100% complete. We still need to conduct training but the work is complete and training is scheduled…..8/15/19, DL; This Project is 90% Complete and will be complete by the end of the week. Please note. ITS still needs to connect the data lines. Our portion of the work is complete………8/1/19, DL; Plans are approved. Material is ordered. We will schedule the work when the material is on site…. |  | Dan Lerman |  |  | 2019-09-03 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
19P000572 |  | 19P000572 | FALSE | GRAD DIV | SL5 PATCH, PAINT, AND CARPET UOB 152 |  | UNIV OFC BLD | 152 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43566 | Awaiting installation of carpet | [5 empty] | 06/28/19 O-ANS: Paint phase complete and awaiting carpet change. |  |  |  |  | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000031 |  | 20P000031 | FALSE | GSOE | SL5 SPROUL HALL 1124B- PATCH/PAINT OFFICE |  | SPROUL | 1124B | COMPLETE | Thomas Smith | Sally Tavizon | MARICELA ARCINIEGA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43668 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000628 |  | 19P000628 | FALSE | GSOE | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2129 | COMPLETE | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43600 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000077 |  | 20P000077 | FALSE | GSOE | SL5 SPROUL HALL 1223 - PATCH AND PAINT |  | SPROUL | 1223 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43683 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-25 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | C&C CARPORT | 161 | COMPLETE | Danna Gianforte | Shelley Gupta | SHELLEY GUPTA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43472 | Waiting for bid for customer. | 43850 | 43921 |  |  |  | 8/5/20, DL: This Project is complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have the contract, we will schedule the work……………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Project was approved by Shelley. We will work on the contract. Once we have the notice to proceed from contracts, we will order the material and schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Sent Shelley another follow-up email today and she has not verified if she would like to move forward with the project………10/30/19, DL: Sent Shelley the updated quote last week and she has not responded. I sent Shelley a followup email today asking her to let me know if she would like to proceed with the work……..10/16/19, DL; Had a meeting with Shelley, we modified the scope of work and software for the project. We are now revising the quote with our vendor. We should have an updated quote within the next two weeks. If Shelley approves the work and scope, we will proceed….10/1/19, DL; I have a meeting with Shelley this afternoon to review proposal. If she approves the project we will submit plans for a building permit……8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was cancelled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; We have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28/19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21 | 1
19P000209 |  | 19P000209 | FALSE | PB&A | SL5 OLD EH&S SITE- FS ANNEX A REMODEL |  | ENV HLTHSFTY | 100 | COMPLETE | Gerry Bomotti | TBD | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 43336 | Schedule the work | 43601 | 43644 |  |  |  | 7/1/19, DL; This project is 100% Complte….6/17/19, DL; This project is almost complete. Target complete date is 6/26………….5/31/19, DL; This project is in progress. Our goal is to have the projected completed by June 28th……. 5/15/19, DL; We are schedule to start the demo tomorrow. Project timeline is 3-4 weeks….3/28/19, DL; Gunther is working on plans……3/18/19, DL; Conducted site visit with Chris, Hassan and Francis last week. We will work on plans and permits…….9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
20P000158 |  | 20P000158 | FALSE | PB&A | SL5 FS ADMIN OFFICE - TOUCH-UP PAINT AROUND BUILDING |  | FS ADMIN |  | COMPLETE | Gerry Bomotti | TBD | DA LAN DINH |  | Paul Ditty |  | - |  | FALSE |  |  | 43741 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000083 |  | 20P000083 | FALSE | PB&A | SL5 STUDENT SERVICES - INSTALL 8 CUBICLES - CP00003537 | Installation of BKM Cubicles with electric and Data | STUDENT SERV | 3rd Floor | COMPLETE | Gerry Bomotti | TBD | SHARYL MURDOCK |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43641 | We are on schedule | 43815 | 43831 |  |  |  | 1/14/20, DL: This project is 100% Complete………..11/18/19 DH: Emailed Status Report to customer…..10/30/19, DL: The plans were approved and we are scheduled to do the work in December…………10/16/19, DL: Plans were submitted this week…….. |  | Enrico Baez | Scope completed by Dan Lerman | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000414 |  | 19P000414 | FALSE | PB&A | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | Seth Morrison |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43451 | pending material delivery | 43754 | 43796 |  |  |  | 8/5/20, DL: This Project is Complete………….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: We have the motor on site, we are working on the permit for the crane. Once we have the crane lift permit, we will schedule the install…………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: We are working on the new motor platform. It is our goal to install the new motor in late January. Once the motor is installed, we will be able to identify if additional work is needed…….11/19/19 DH: Emailed Status Report to customer…..11/15/19, DL: Material has not arrived……..10/30/19, DL: The new exhaust fan is ordered with a 2- 4 lead time. Once the exhaust fan arrives, we will schedule the install……….10/16/19, DL; We are in the process of the work. At this current time, we are not modifying the building to where permits may not be required…….10/1/19, DL; This is in the queue for plans, we will start the plans in the next 3-4 weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2018 | 2021-02-16 | FY 20-21
20P000008 |  | 20P000008 | FALSE | PB&A | SL5 EHS 1133 - PATCH / PAINT AND FIX HOLES IN WALLS |  | ENV HLTHSFTY | 1133 | COMPLETE | Gerry Bomotti | TBD | CESAR PLA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43654 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-07 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000665 |  | 19P000665 | FALSE | PB&A | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | Existing telephone-communications building on University Ave requires repairs and renovation in preparation for new use as fire safety offices. | TELEPHONE |  | COMPLETE | Gerry Bomotti | TBD | Carmen Long | Melissa Garrety | Dan Lerman |  | 2 |  | FALSE |  |  | 43649 | tape, mud, prime&Paint | 43691 | 43847 |  |  |  | 2/19/20; This project is complete. We still need to paint the door black but this was not part of the original scope. The paint shop will paint the door in the next two weeks………… 1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL:. This project is 99.9% complete with a few minor punch list items…..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project is on track to finish before the new year with a punch items to be addressed after the new year. IT services still needs to install data and phone. Landscape services is working on the landscape but the landscape was not part of the original scope. Sharyl in is the process of coordinating keys, alarm code and setting up the delivery of the furniture for her team. Overall, we are all in good shape.…….11/19/19 DH: Emailed Status Report to customer…..11/11/19,DL: This project is still on schedule to be complete before the new year……….10/30/19, DL: This project is in progress and on track to be complete before the new year…………….10/16/19, DL: Drain, waste, vent and concrete is complete. We started framing this week. We will start rough electrical and rough plumbing next week……..9/3/19, DL; Abatement was complete this weekend. Trades are scheduled and we are on track for 11/15/19 completion date…..8/15/19, DL Plans were approved this week. Abatement is still needed and the 14- day notification to AQMD is complete. We are on track to complete the work by mid November……. |  | Enrico Baez |  |  | 2020-02-19 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000114 |  | 20P000114 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER DOOR, BASEBOARD, AND BRACKETS |  | PENTLAND A |  | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
19P000535 |  | 19P000535 | FALSE | PB&A | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV | Install TV Mount and additional electrical | BANNOCK H | H0108 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43538 | [7 empty] | 2019-07-08 | Enrico Baez | Install TV Mount and additional electrical | YES | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000127 |  | 20P000127 | FALSE | PB&A | SL5 FALKIRK APARTMENTS EMERGENCY EGRESS |  | FALKIRK 1 | 10E | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 43721 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
19P000599 |  | 19P000599 | FALSE | PB&A | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 43594 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
19P000687 |  | 19P000687 | FALSE | PB&A | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | COMPLETE | Gerry Bomotti | TBD | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 43642 | plan check review | [5 empty] | 8/5/20, DL This Project is Complete……………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Contracts is processing the contract. Once the contract is complete, we will schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Plans were approved. I sent Brendan an email 11/11/19 requesting an FAU # as this is Recharge work. Once we have the FAU #, we will work on the contract agreement with the contractor………10/30/19, DL; Sent Lezlie and email asking if she has an update on the resubmitted plans on 10/30/19………..10/16/19, DL; The plans were resubmitted for plan check review this week. We are hopeful the plans will be approved this week. Once approved we will work on contract and scheduling the work…10/7/19 LB: This is a test. The timestamp will be reset when the test is done. 10/1/19, DL: We are working on plan check review. We should have approved plans in the next two weeks…..8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | Provide estimate to install key card access control |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21 | 1
20P000037 |  | 20P000037 | FALSE | PB&A | SL5 FAC ADMINISTRATION -PAINT WALLS |  | FS ADMIN | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 43669 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000205 |  | 20P000205 | FALSE | PB&A | SL5 THE PLAZA 12 & 14 - EMERGENCY DECK REPAIR | Deck repair | THE PLAZA | A0012 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R2 |  | FALSE |  |  | 43770 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000115 |  | 20P000115 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 1 - BALCONY COSMETIC REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R2 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000223 |  | 20P000223 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER PAN REPLACEMENTS | Shower Pan replacement | PENTLAND A | A238, B245, B325, C215, F325 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R3 |  | FALSE |  |  | 43784 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Sep 2019. |  | John Peraino |  |  | 2019-09-01 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000116 |  | 20P000116 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 5 - BALCONY EMERGENCY REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R3 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000243 |  | 20P000243 | FALSE | PB&A | SL5 ALUMNI CENTER - HYDRATION STATION INSTALL | Install hydration station | ALUM VISITOR | FIRST FLOOR | COMPLETE | Gerry Bomotti | TBD | LESLIE ANN GERRETSE |  | John Peraino |  | R4 |  | FALSE |  |  | 43785 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by June 2020. |  | John Peraino |  |  | 2020-06-01 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000117 |  | 20P000117 | FALSE | PB&A | SL5 PENTLAND HILLS A-H - LATTICE REBUILD |  | PENTLAND A | A-H | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R4 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
20P000118 |  | 20P000118 | FALSE | PB&A | SL5 FALKIRK 1, 2, & 12 - FIRST FLOOR PATIO FENCING |  | FALKIRK 1 | 1st Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R5 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20 | 1
19P000683 |  | 19P000683 | FALSE | PROVOST/EVC | SL5 PATHC/PAINTING REPAIR |  | HUM & SOC SC | 1103A | COMPLETE | Thomas Smith | Luisa Levario | JILL CANTONWINE |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43641 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000473 |  | 19P000473 | FALSE | PROVOST/EVC | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 |  | HINDERAKER | 1100 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | TORRI MCGARITY | Paul Ditty |  | 1 |  | FALSE |  |  | 43494 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-28 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000434 |  | 19P000434 | FALSE | PROVOST/EVC | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | Please patch 50 plus holes on the wall and repaint that wall in Skye hall 136 due to the BKM removing the furniture attached to the wall. Please call Anita Ortiz if you have any questions at x2-5229. Shanshan's extension x7753 has not been moved to her new location yet. | SKYE HALL | 136 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | SHANSHAN | Paul Ditty |  | 2 |  | FALSE |  |  | 43472 | [6 empty] | 07/20/19 O-ANS: Work Complete per Paul Ditty. |  | Paul Ditty |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
18P000351 |  | 18P000351 | FALSE | SoB | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 (S) | 21 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 43178 |  | 43654 |  |  |  |  | 8/1/19, DL; This project is 100% Complete……7/15/19, DL; Work has started and should be complete on 7/16/19…….. 4/4/19 O-ANS: Moved to Queue to Start to complete during Summer 2019. DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week……8/8/18. The trades are ready to go after they finish current projects…..DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18………. DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date……..9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space……Note. The space is usable and everything works….. |  | Enrico Baez |  | YES | 2019-08-01 | Spring 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
19P000521 |  | 19P000521 | FALSE | SoB | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT |  | ANDERSON 1 (N) | 138 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43532 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000151 |  | 20P000151 | FALSE | SoB | SL5 ANDERSON HALL NO 113 - PATCH/PAINT HOLES |  | ANDERSON 1 (N) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43738 | [6 empty] | 03/02/20 O-ANS: Project complete per Paul Ditty as of 02/07/20. |  | Paul Ditty |  |  | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000193 |  | 20P000193 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 0001A | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43761 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/02/20 |  | Paul Ditty |  |  | 2020-01-02 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000152 |  | 20P000152 | FALSE | SOM | SL5 SOME 2669 - PATCH & PAINT |  | SOM EDUC | 2669 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | TRACEY TRETTIN | Paul Ditty |  | - |  | FALSE |  |  | 43738 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000660 |  | 19P000660 | FALSE | SOM | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SL5 SOME RB, RM 330- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43627 | [6 empty] | 9/30/20, DL: This Project is Complete………..8/5/20, DL: Dan to follow-up with customer…………..03/05/20 O-ANS: Removed room 330 per client request. Only updates to 107 & 111. |  | Ron Veloz | TBD | NO | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000661 |  | 19P000661 | FALSE | SOM | SL5 SOM RB, CR0600- FY 19/20 PROJECT- PATCH & PAINT |  | SOM EDUC | CR0600 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43627 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000054 |  | 20P000054 | FALSE | SOM | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOMED-SOME G0600, G0621 & 1682B- ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43677 | [6 empty] | 9/30/20, DL: This Project is Complete…………..8/5/20, DL, Dan to follow-up with customer………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "Remove status Hold / Update project detail to include information on 1682B -ADD ELECTRICAL, PAINT/PATCH, AND RELOCATE WHITE BOARD." |  | Ron Veloz | Room G0600 Install Power behind and below the TV, install one TV Bracket, install one cut-in back box below the TV for data(data cabling by ITS), Paint the entire East wall to match existing. Room G0621 Insatll three(3) new double duplex receptacles and three(3) data back boxes only(no data cabling) in room G0621. Install SS tubing for Co2 from room G0621 to room G0623. Include Valves at both ends of P.O.C., Install one uni-strut siesmic cylinder support at the south wall. Steve Burleson has walked the site and has knowledge of the SOW. Loading Dock Install Pole & chains at Loading dock. |  | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000060 |  | 20P000060 | FALSE | SOM | SL5 WEBBER HALL 1274- PATCH & PAINT OFFICE |  | WEBBER | 1274 | COMPLETE | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43682 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-28 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000666 |  | 19P000666 | FALSE | SOM | SL5 WEBBER, ROOM 1237- PATCH AND PAINT | TBD - SOM RM 107, 111 & 330- PROJECT: NEW PI, EQUIPMENT INSTALL | WEBBER | 1237 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43633 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-11 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000245 |  | 19P000245 | FALSE | SOM | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY |  | SOM RSCH |  | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43350 | Plans are approved | 43619 | 43644 |  |  |  | 7/1/19, DL; This project is 100% Complete…..6/171/19, DL; Material is on site. Project should be complete in the next two weeks……..5/31/19, DL; Contracts is working on the contract. We should have a notice to proceed in the next two weeks. The project will be complete with in 30- from when we receive the notice to proceed……5/15/19, DL;, Plans were approved. I am working with PD&C on the contract. Once the contract is complete, we will schedule the work……3/28/19, DL; Plans were submitted and pending review and approval….. | 2018-10-29 | Ron Veloz | Install ADA complian auto door operator, push plates and electrified panic hardware. Auto operator will be outsourced through Capitol door. FS lock shop will perform acess control wiring. Electrical shop to provide a dedicated circuit for the auto door operator. | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 19-20
20P000051 |  | 20P000051 | FALSE | SOM | SL5 SOMED 2611 - PATCH & PAINT |  | SOM EDUC | 2611 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43677 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000150 |  | 20P000150 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 207 |  | UNIV OFC BLD | 207 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000149 |  | 20P000149 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 242 |  | UNIV OFC BLD | 242 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000026 |  | 20P000026 | FALSE | VC-RED | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | Install T-bar ceiling, Provide HVAC and Fire sprinklers drops. Install new 2x4 LED light fixtures | LIFE SCIENCE | Basement Level | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43665 | Work on Plans and permits. | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: The plans were submitted two weeks ago. We should receive the plan check review comments in the near future…………….8/5/20, DL: This Project will exceed $50,000. Monty A. will inform customer this is a project that will need to be managerd through PD&C……………3/25/20, DL: We will work on plans when we return back from the campus closure. | 2020-01-31 | Ron Veloz | Install T-bar ceiling with wipable(coated) ceiling tile. Provide HVAC and new Fire sprinklers drops to new ceiling. Install new 2x4 LED light fixtures. Verify Fire alarm systems work. | YES | 2021-01-19 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000553 |  | 19P000553 | FALSE | VC-RED | SL5 SPIETH HALL PATCH AND PAINT |  | SPIETH | 341 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43556 | [6 empty] | 07/26/19 O-ANS: Project Complete per Paul Ditty. |  |  |  |  | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
20P000230 |  | 20P000230 | FALSE | VC-RED | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | Install Ceilings, Widen Door & Extend Utilities | BOURNS | B116C & B116D | COMPLETE | Rodolfo Torres | Laura Manor | KRASSIMIR BOZHILOV | LAURA MANOR | Dan Lerman |  | 1 |  | FALSE |  |  | 43787 | finish plans for building permit | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: This project is in progress and 50% complete. We should be complete with in the next 4-6 weeks…………...8/5/20, DL: We will submit plans in the next week………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We will start working on the plans and apply for a building permit in the next 2-3 weeks. | 2020-01-23 | Ron Veloz | Install new T-bar ceilings, lighting/switches, verify electrical service/disconnect. Relocate the existing eye washer, widen the exiting door opening and *reverse swing(*if approved by F.M). Install one customer furnished transformer. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
20P000045 |  | 20P000045 | FALSE | VC-RED | SL5 MRB SOUND BOOTH |  | MRB | 2210 & 2204 | COMPLETE | Rodolfo Torres | Laura Manor | DAN LERMAN |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43676 | Inspection | 43739 | 43776 |  |  |  | 11/11/19, DL: This project is complete…….10/30/19, DL: This project is complete but we need to conduct the final inspection with the building official………..10/16/19, DL: The plans are approved and the work is complete. I need to field verify and schedule the inspection. |  | Ron Veloz | Contact PM for SOW. | NO | 2019-11-11 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000495 |  | 19P000495 | FALSE | VC-RED | SL5 UOB RM 209- PATCH & PAINT |  | UNIV OFC BLD | 209 | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43504 | [6 empty] | 07/30/19 O-ANS: Project closed per Paul Ditty. 07/30/19 D-MMN: Moved furniture and filled holes. Taped base and fixtures. Primed and painted one half of office. Pulled tape replaced plates and moved furniture to other side. Removed plates taped base and fixtures. Primed and painted other half. Used spray texture on patch under window. Pulled masking. Replaced plates. Moved furniture back. Vacuumed carpet during and after total process. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
21P000102 |  | 21P000102 | FALSE | VC-RED | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | AAALAC Certification updates to rooms 348, 352 & 363 | SPIETH | 348, 352 & 363 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS | YURIDIA REYNOSO | Paul Ditty |  | TBD |  | FALSE |  |  | 44133 | [6 empty] | 12/08/20 O-ANS: Customer Dierk Biggs confirmed via email that these room updates are complete. |  | Paul Ditty |  |  | 2020-12-08 | Winter 2021 | FS | FALSE | 2020 | 2021-02-16 | FY 20-21
20P000337 |  | 20P000337 | FALSE | VC-STU AFF | SL5 HEATLH SERVICE 382 - NEED OFFICE PAINTED |  | HEALTH SERV | 382 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43853 | [6 empty] | 08/06/20 O-ANS: Complete per D-BFA on 02/11/20. |  | PAUL DITTY |  |  | 2020-02-11 | Spring 2020 | FS | FALSE | 2020 | 2021-02-16 | FY 19-20
20P000157 |  | 20P000157 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BUILDING - HOLES NEED PATCH AND PAINT |  | HEALTH SERV | 325 | COMPLETE | Brian Haynes | Cathy Eckman | CHRISTINA FARIA | WENDY ALEXIS | Paul Ditty |  | 1 |  | FALSE |  |  | 43740 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 01/31/20. |  | Paul Ditty |  |  | 2020-01-31 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000455 |  | 19P000455 | FALSE | VC-STU AFF | SL5 FILL AND PAINT OVER HOLES ON WALL |  | HEALTH SERV | 100 | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43482 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/27/19 |  |  |  |  | 2019-12-27 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
18P000214 |  | 18P000214 | FALSE | VC-STU AFF | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Install Card readers | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  | 2 | 2 | FALSE |  |  | 43077 | Pending special order part | 43515 | 44075 |  |  |  | 1/19/21, DL: This project is 100% Complete…….9/30/20, DL: Vendor should have the balance of the material in the next 30- days…….8/5/20, DL: This project is complete except the card reader portion of the project…………6/17/20, DL: The floor covering was completed two weeks ago. The card reader portion of this project is 95% complete but additional parts were needed and they are on order. Once they arrive, we will schedule the installation and this project will be 100% Complete………1/15/20 Emailed Status Report to customer…..1/14/20, DL: We were recently approved to proceed with the work. I have reached out to the vendor for the doors and card access. We are still waiting to hear back from them so we can order the material and schedule the work. I communicated with Nicole on the floor covering replacement. Nicole needs to verify what areas we will replace as we were going to complete several offices and a hallway as part of the scope but this will displace many team members for at least a week. We will work on scheduling the work once Nicole gets back to me……..12/17/19 - O-DHN: Emailed Status Report to Customer……12/19/19, DL; We are working with our contractor to order the material and schedule the work. Once we have confirmation on the material, we will be able to schedule the work. It Is our goal to start this project in late January……11/26/19, DL: This project was taken off of on hold and we can now proceed. I contacted the contractor last week and I am awaiting their response on when they can schedule the work. I also left a message with them this morning………..7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once material arrives, we will schedule the installation.….5/31/19, DL; Contract is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is completed except the floor covering and electronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being prepped for paint. We have a pre-construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, material is ordered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct site visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez |  | YES | 2021-01-19 | Winter 2018 | FS | FALSE | 2017 | 2021-02-16 | FY 20-21
19P000483 |  | 19P000483 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED |  | HEALTH SERV | 404, 407, 412, 405 & 411 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43497 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-11-22 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000564 |  | 19P000564 | FALSE | VC-UNIV ADV | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | 1156C (AVC Johnny Cruz) – Patch molly holes, touch-up paint. 1156A (Jules Bernstein) – Remove (2) black & white photos from wall. Patch molly holes, touch-up paint. 1156B – Install picture frame (UCR campus map) onto wall. Suite 1159 – Patch holes. Remove film reels. Paint one accent wall “UCR Blue”. 1159B (Christy Zwicke) - Patch molly holes, touch-up paint. | HINDERAKER | 1156 | COMPLETE | Peter Hayashida | Naysia Caldwell | Lisa Cusick | Christy Zwicke | Paul Ditty |  | 1 |  | FALSE |  |  | 43563 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-07 | Summer 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
19P000485 |  | 19P000485 | FALSE | CNAS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | CHAPMAN | 9 | IN PROGRESS | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43494 | connect the Exhaust and electrical |  | 44256 |  |  |  | 2/16/21, DL: Plumbing is complete. We will now start the Exhasut vent, electrical and then Scismically anchor the Fume hood…………2/1/21, DL: We have had a delay with the plumbing and it is our goal to be complete on or before 3/1/21…………1/10/21, DL: This project is almost complete. This project will be complete in the next 30- days…………9/30/20, DL: Fume Hood demolition and abatement will be completed on 10/2/20. Fume hood install should be coplete in mid Novemeber……8/5/20, DL: We will submit plans this week. Once plans are approved, we will schedule the work……………Work orders are produced. We need to work on plans and permits once we return.. | 2020-02-10 | Ron Veloz | Disconnect, cap and safe off the existing utility services. Provide the necessary abatement services to properly remove the fume hood from the site and deliver to the campus surplus yard. Install one new department furnished fume hood. Abatement Services: Provide the necessary abatement services to perform all utilities disconnections and floor repair. Floorcovering: Patch and or repair as necessary to match or provide a close match. Install rubber base. Access Control: Survey and adjust the entry door closer to increase latch pull to allow the door to closer completely. Patching and painting: Patch and paint wall at the old fume hood location. Mechanical: Disconnect metal duct, cap/safe off, reconnect/reconfigure new duct to accommodate the new fume hood. Electrical: Provide electrical disconnections and safe off. Reconnect/reconfigure power to the new fume hood. Plumbing: Disconnect Air, Gas, Vacuum, Cold water, and Drain, cap and safe off and reconnect/reconfigure service to the new fume hood. Resource Management: Properly remove the fume hood from the site and deliver to the campus surplus yard. | YES |  | Spring 2020 | FS | FALSE | 2019 | 2021-02-16
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install electrical utilities for new equipment | PHYSICS | 1132 | IN PROGRESS | Kathryn Uhrich | TBD | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43543 | Install final electrical, countertop and Sink |  | 44256 |  |  |  | 2/16/21, DL: New sionk and Faucet arrived, we will now schedule the install of the countertop and sink…………..1/19/21, DL: This project is in progress and will be complete with in 30- days………..9/30/20, DL: Plans were submitted for Plan Check review last week and we should have an update on the plan check review process soon………..8/5/20, DL: Need to meet with Kirk to verify electrical load. Once confirmed, we will work on plans for a permit | 2019-10-15 | Ron Veloz | Install utilities for new equipment | YES |  | Summer 2019 | FS | FALSE | 2019 | 2021-02-16
20P000003 |  | 20P000003 | FALSE | GRAD DIV | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | ADD POWER/DATA, PATCH/PAINT | UNIV OFC BLD |  | QUEUE TO START | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS | CHERYL GERRY | Dan Lerman |  | 1 |  | FALSE |  |  | 43648 | schedule the demo, electrical and plumbing | 44244 | 44282 |  |  |  | 2/16/21, DL: Conducted a site visit with the plumber and capenter shop. We will start the demo next wee…………2/1/21, DL: We will schedule this project to start in 2- weeks……………….1/19/21, DL: Plans were approved and we will schedule the work in the near future………. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Permit is approved. We need to verify floor covering. Once floor covering is confirmed and ordered, we will schedule the work………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We will need plans as we are installing a new hydration station and a Counter top that needs to be ADA compliant…………We started the plans and will submit them for a permit and plan check review within 2- weeks……….10/30/19, DL: No Plans will be needed. We will plan on scheduling the work shortly after Thanksgiving……. | 2019-06-13 | Enrico Baez | 9/24/2019 E. Baez--SCOPE-- 1. Removal and disposal of one bulletin board and two director cases. 2. Removal and disposal of abandoned telephone mounting bracket. 3. Remove and dispose of abandoned alarm box in wall. 4. Patch and paint walls in lobby and public restroom area. 5. Provide electrical connection for wall mounted monitor. 6. Cut access for data boxes. 7. Install monitor mount on wall. 8. Construct 7" x 18" laminate counter top and install in Lobby. | YES |  | FALL 2019 | FS | FALSE | 2019 | 2021-02-16
20P000046 |  | 20P000046 | FALSE | CNAS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN | 0001 | PROJECT INTAKE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Enrico Baez |  | R2 |  | FALSE |  |  | 43677 | [6 empty] | 1/19/21, DL: Enrico B. will manage this priject………….11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Install wireless access controls systems at front and rear entry doors. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16 |  | 1
20P000144 |  | 20P000144 | FALSE | CNAS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A | BOYCE | 3432, 3432A, 3446, 3446A | IN PROGRESS | Kathryn Uhrich | TBD | MATTHEW ULRICH | CHERYL GERRY | Dan Lerman |  | 3 |  | FALSE |  |  | 43734 | final paint, floor covering and final cabinets |  | 44269 |  |  |  | 2/16/21, DL:Project Is on schedule. Paint is 90% complete. Once paint is complete, we will schedule the floor repairs and final deep clean……… 2/1/21, DL: We are making good progress and are target date is still 3/14/21………….1/19/20, DL: This project is in progress and will be complete in the next 30- days………….9/30/20, DL: WE have started a few items but we are waiting on Matt U. and the PI to remove their items so we can have access to the space. Once the space is cleared out, we will proceed with the work…………8/5/20, DL: We will start the work in the next 4-6 weeks. | 2020-02-18 | Ron Veloz | Boyce 3432, 3446, 3436 and 3436A . Patch and paint 3432, 3432A, 3436, 3436A, 3446, 3446A. Reface/replace water damaged cabinets near sink (3446). Install GCFI outlets near sink (replace existing) (3446). Install panel cover for electrical panel box. Replace many burnt out bulbs in ceiling lamps. Replace broken chemical plexi-glass on bench shelves. | YES |  | Winter 2020 | FS | FALSE | 2019 | 2021-02-16
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS | 3009 | QUEUE TO START | Kathryn Uhrich | TBD | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 43749 | [6 empty] | 02/03/21 O-ANS: Reminder email sent to customer that PAINT ONLY portion would be completed and not the door removal at this time. Customer can resubmit request in next prioriization cycle…. 11/06/20 O-JLO: Emailed requestor and alternate regarding paint portion only, and that door/drywall removal will not occur during this time …. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. FS to confirm with customer that we can only complete the painting at this time but not the removal of the door…. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure. | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | COSTO HALL |  | PROJECT INTAKE | Brian Haynes | Cathy Eckman | BRENDAN O'BRIEN |  | Enrico Baez |  | R1 | R2 | FALSE |  |  | 43762 | [6 empty] | 02/16/21 O-ANS: Will require plans/permits and may need to go to PD&C due to scope of work which includes construction. Will confirm with client before instructing to submit request to CPMS…. 1/19/21, DL: Enrico B. Will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16 |  | 1
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | BOURNS | B0328E | QUEUE TO START | Christopher Lynch | TBD | MARGARET SOUDER |  | Enrico Baez |  | R1 | R1 | FALSE |  |  | 43774 | [6 empty] | 1/19/21, DL: Todd has the estimate. Sent follow up email to Todd requesting update or FAU number………………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16 |  | 1
20P000218 |  | 20P000218 | FALSE | VC-RED | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | VIVARIUM UPDATE AIR COMPRESSOR | SPIETH | 347 | QUEUE TO START | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | DAN LERMAN |  | 2 | R2 | FALSE |  |  | 43602 | We will start once priority 1 projects are complet | [5 empty] | 2/1/21, DL: WE will start the process for this project once we are closer to completing priority one projects. This is a prioity 2 project……1/19/21, DL: This project has been scoped. We will start the work when we are complete with all priority #1 projects…….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Cinvert Basement Library into Piano Lab | ARTS | 54 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 43788 | start plans once priority 3 proj. are almost comp. | [5 empty] | 1/19/21, DL: We will Start the plans, permit and the work once all priority #3 projects…………...11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks……….. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | QUEUE TO START | Kathryn Uhrich | TBD | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 43794 | [6 empty] | 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16
20P000248 |  | 20P000248 | FALSE | CNAS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT |  | WEBBER | 1223 + 1223-A | PROJECT INTAKE | Kathryn Uhrich | TBD | DEBORAH MCWILLIAMS | SHARYL MURDOCK | Dan Lerman |  | 5 | 4 | FALSE |  |  | 43796 | EH&S to sanitize space | 44257 | 44307 |  |  |  | 1/19/21, DL: This project is a priority #5. We will start this project when all priority #4 projects are complete…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….02/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Survey space for hazardous material. Once survey is complete, we will schedule abatement and the work. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16
20P000253 |  | 20P000253 | FALSE | BCOE | SL5 BOURNS HALL LAB B156 - EXHAUST SYSTEM | EXHAUST SYSTEM | BOURNS | B0156 | PLAN DEVELOPMENT/CHECK | Christopher Lynch | TBD | LOUIS SANDOVAL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 43810 | coreect and resubmit plans for building permit | 44228 |  |  |  |  | 2/16/21, DL: Plans were submitted 2- weeks ago. We received the plans back last week with corrections needed. We will resubmit the plans back to the building official by the end of the week….1/19/21, DL: We will start working on the plans for this project in the next two weeks. We will start this project once the permit is approved…… |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS | 245 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | ANDREA HIDALGO |  | DAN LERMAN |  | 3 |  | FALSE |  |  | 43832 | plans and permit once we start priority 3 projects | [5 empty] | 1/19/21, DL: This is a priority 3 project. We will start the plans and permit for this project when all priortiy #2 projects are complete…….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 43803 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2019 | 2021-02-16
20P000310 |  | 20P000310 | FALSE | BCOE | SL5 BOURNS A-WING A129 - PATCH & PAINT | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. | BOURNS | A0129 | QUEUE TO START | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43840 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel | ARTS | 150 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 43844 | Electrical Engineer design | [5 empty] | 1/19/21, DL: This project will require engineered plans. This is a priority 2 project. We will start the plans and permit process when all priority #1 projects are comple………… |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000320 |  | 20P000320 | FALSE | CNAS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | ACTIVATE VACUUM LINES | SPIETH | 1303 | PROJECT INTAKE | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | DAN LERMAN |  | 4 |  | FALSE |  |  | 43789 | Will start the work once we start priority 3 proj | [5 empty] | 1/19/21, DL: This is a priority 4 project. We will start this project when all all priority 3 projects are complete……….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | PIERCE | 2232A | PROJECT INTAKE | Kathryn Uhrich | TBD | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 43852 | will start when we start priority 9 projects | [5 empty] | 1/19/21, DL: This is a priority #9 project. We will start this project when all priority #8 projects are complete…………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SERV | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | TBD | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 43852 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-02-16
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES |  | UNIV OFC BLD | 200 | HOLD - FACILITIES SERVICES | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43868 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-02-16
20P000363 |  | 20P000363 | FALSE | BCOE | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | Paint Only | CHUNG HALL | 433 | QUEUE TO START | Christopher Lynch | TBD | MANGLAI ZHOU | FARIBORZ KARGAR | PAUL DITTY |  | X |  | TRUE |  |  | 43874 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000366 |  | 20P000366 | FALSE | CNAS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | MINOR LAB RENOVATION | SPIETH | 2375 / 2375-A | PROJECT INTAKE | Kathryn Uhrich | TBD | SHERICE UNDERWOOD |  | DAN LERMAN |  | 7 |  | TRUE |  |  | 43880 | will start when we start priority 7 projects. | [5 empty] | 1/19/21, DL: This is a priority 7 project, we will start this project when all priority 6 projects are complete………….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LAB1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 43880 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-02-16
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT |  | SCIENCE LAB1 | 317 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | TBD | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 10 |  | FALSE |  |  | 43879 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-02-16
20P000370 |  | 20P000370 | FALSE | CHASS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | SPACE RENOVATION PROJECT | WATKINS | 1311 | PLAN DEVELOPMENT/CHECK | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 43880 | Plan are in plan check review process with offical | [5 empty] | 2/16/21, DL: Plasns were submitted with building permit last week. We are now in the plan check review process………1/19/21, DL: We will start working on the plans for this project in the next three weeks. We should have plans to submit for plan check review in the next 5- weeks……….. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000397 |  | 20P000397 | FALSE | CNAS | SL5 ENTOMOLOGY 139 - PATCH AND PAINT OFFICE | Patch and paint room 139 for the new faculty member | ENTOMOLOGY | 0139 | QUEUE TO START | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 43895 | [6 empty] | 02/10/21 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000403 |  | 20P000403 | FALSE | CHASS | SL5 OLMSTED 232 - PAINT OFFICE | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). | OLMSTED | 2321 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | MELISA VICARIO | Paul Ditty |  | X |  | TRUE |  |  | 43903 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000419 |  | 20P000419 | FALSE | CNAS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | Paint Only | SPIETH | 2312 | QUEUE TO START | Kathryn Uhrich | TBD | ESTELLA DAVALOS | SHERICE UNDERWOOD | PAUL DITTY |  | X |  | TRUE |  |  | 43943 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000445 |  | 20P000445 | FALSE | CNAS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY | 279 | PROJECT INTAKE | Kathryn Uhrich | TBD | WILLIAM SUTTON |  | DAN LERMAN |  | 3 |  | TRUE |  |  | 43985 | complete priority 1 projects | [5 empty] | 1/19/21, DL: This is a priority 2 project. We will start the project when all priority 1 projects are complete………….2/16/21, LB: Changed to Priority 3 per Dan. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000446 |  | 20P000446 | FALSE | CHASS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. | CHASS INT N | 4047 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 43986 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000453 |  | 20P000453 | FALSE | CHASS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | Paint Only - Please patch/paint to existing color office for faculty new hire. | ARTS | 142 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000462 |  | 20P000462 | FALSE | CHASS | SL5 HMSS 2001 - PAINT OFFICE / CLEAN FLOOR NEW FACULTY HIRE | Patch/paint to existing color for faculty new hire | HUM & SOC SC | 2001 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | Paul Ditty |  | X |  | TRUE |  |  | 44000 | [6 empty] | 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000463 |  | 20P000463 | FALSE | CHASS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 | HUM & SOC SC | 2000 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000464 |  | 20P000464 | FALSE | CHASS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) | HUM & SOC SC | 3001 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000467 |  | 20P000467 | FALSE | SOM | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. | WEBBER | 1247 | QUEUE TO START | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | CYNTHIA CAROLINA | PAUL DITTY |  | X |  | TRUE |  |  | 44001 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000468 |  | 20P000468 | FALSE | VC-RED | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | Paint Only | SPIETH | 364 | QUEUE TO START | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 44005 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000469 |  | 20P000469 | FALSE | CHASS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. | ARTS | 222 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | SUSAN KOMURA | PAUL DITTY |  | X |  | TRUE |  |  | 44005 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUM & SOC SC | 3210 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44006 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
21P000001 |  | 21P000001 | FALSE | CNAS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | NEW GROWTH CHAMBER PLACEMENT | FAWCETT LAB |  | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | TBD | LINDA WALLING |  | DAN LERMAN |  | 2 |  | TRUE |  |  | 43990 | complete priority 2 projects | [5 empty] | 1/19/21, DL: This is a priorty 3 project. We will start this project when all priority 2 projects are complete…….2/16/21, LB: Changed to Priority 2 per Dan. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
21P000003 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | PROJECT INTAKE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Enrico Baez |  | R1 |  | FALSE |  |  | 44008 | [6 empty] | 1/19/21, DL: Enrico is managing this project………….. | 2020-12-02 | Enrico Baez | Remove tripod antenna. Apply spray roof coating to existing roof surface | YES |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16 |  | 1
21P000009 |  | 21P000009 | FALSE | CNAS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | GLOVEBOX SYSTEM | CHEMICAL SCI |  | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | TBD | NATASHA GONZALES |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 44020 | building permit approval | [5 empty] | 2/16/21, DL: We submitted plans for building permit but corrrections are needed. We contacted the glove box manufacture for follow-up questions and we are waiting to hear back from them. Once we have confirmation on the needed information. We will resubmit the plans back to the building official……….1/19/21, DL: we will submit plans this week or earlier next ……………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
21P000019 |  | 21P000019 | FALSE | BCOE | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | Bourns Office A305 - Install Plank Floor Please remove old damaged carpet and install new plank floor. Match with that of the ME suite (same floor). Thank you. Note: Current PI has not moved out. We will contact Facilities once date is known and all items have been removed from the room. Questions: ME Department Manager (Interim) - William Bingham - bill@ece.ucr.edu , or Robert Lopez lopezra@engr.ucr.edu | BOURNS | A305 | PROJECT INTAKE | Christopher Lynch | TBD | ROBERT LOPEZ-A |  | Dan Lerman |  | 3 | 2 | TRUE |  |  | 44032 | complete priority 2 projects | [5 empty] | 1/19/21, DL: This a priority 3 project. We will start this project when all priority #2 projects are complete………..1/14/21 O-ANS: Updated prioritization to #3 (from #2) per org leadership request. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MAT SCI ENGR | 71 | PROJECT INTAKE | Christopher Lynch | TBD | XI CHEN |  | DAN LERMAN |  | 2 | 3 | FALSE |  |  | 44049 | plans and permits | [5 empty] | 1/19/21, DL: This is a priority #2 project. WE will start the plans and permit process for this project when all priority 1 projects are complete…………1/14/21 O-ANS: Updated prioritization to #2 (from #3) per org leadership request. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
21P000078 |  | 21P000078 | FALSE | VC-RED | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MRB |  | IN PROGRESS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 44097 | start 2nd floor install | [5 empty] | 1/19/21, DL: the First floor work will be complete today, we will start the 2nd floor this week……………. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
21P000079 |  | 21P000079 | FALSE | VC-RED | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. | PSYCHOLOGY1 |  | QUEUE TO START | Rodolfo Torres | Laura Manor | LESLIE KARPINSKI |  | PAUL DITTY |  | X |  | FALSE |  |  | 44099 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS |  | PROJECT INTAKE | Kathryn Uhrich | TBD | JOSE WUDKA |  | Enrico Baez |  | R1 |  | FALSE |  |  | 43818 | [6 empty] | 1/19/21 DL: Enrico is managing this project. |  | ENRICO BAEZ |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-02-16 |  | 1
21P000109 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Dr. Robert Clark. He started working July 1, 2020. | WATKINS | 1146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
21P000110 |  | 21P000110 | FALSE | CHASS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. | WATKINS | 2146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
21P000111 |  | 21P000111 | FALSE | CHASS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. | WATKINS | 2144 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-02-16
20P000067 |  | 20P000067 | FALSE | BCOE | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM | BOURNS | B-Wing | TO BE PERFORMED BY PD&C | Christopher Lynch | TBD | MARGARET SOUDER |  | Dan Lerman |  | R1 |  | FALSE |  |  | 42688 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold until further notice……. |  | Ron Veloz | Replace access controls at BCOE WCH & Bourns bldgs. |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2016 | 2021-02-16 | FY 20-21 | 1
19P000674 |  | 19P000674 | FALSE | CHASS | SL5 HMSS RM 2416 OFFICE ROOM PATCH AND PAINT |  | HUM & SOC SC | 2416 | TO BE PERFORMED BY PD&C | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43635 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-23 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | Modify the existing room in Soil House 1 (attached to the Delphino Lab at the Rubidoux Facilities) to expand CCPP quarantine services to include USDA/CDFA compliance for installation of new Economic Development Administration (EDA) citrus growth chambers. | DELFINO HHSE |  | TO BE PERFORMED BY PD&C | Kathryn Uhrich | TBD | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 43245 | Research and plan development | [5 empty] | 12/7/20, DL: This project will be managed by PD&C…..9/30/20, DL: Project is still on Hold until Furhther notice………...8/5/20, DL: WE will work on plans in the next 30- 45 days……………6/17/20, DL: This project is under review and is on hold until further notice………10/3/19 O-ANS: Plan Development per Minor Reno Meeting. 10/1/19,DL; We are getting ready to start the plans as we are currently conducting resarch on products that will meet the needs of the space……………..5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman |  | YES | 2020-12-07 | Summer 2018 | FS | FALSE | 2018 | 2021-02-16 | FY 20-21
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB. Patch Paint walls, replace flooring, refinish wood cabinets and sinks. | SPIETH | 2349 | TO BE PERFORMED BY PD&C | Kathryn Uhrich | TBD | ESTELLA DAVALOS |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43516 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold……….12/11/19: O-ANS: Reassigned as project allotment - priority #5 for Winter 2020. 11/27/19 O-ANS: Placed on Hold for re-prioritization by client for Winter 2020. | 2020-02-27 | Ron Veloz | Patch and paint and extra work to upgrade an old lab that we are now inhabiting. In addition to painting, we need to have floors re-surfaced, cabinets re-stained, and counter tops re-surfaced, if possible. There is also a metal sink that could be polished. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-02-16 | FY 20-21
19P000670 |  | 19P000670 | FALSE | SOM | SL5 SOME, RM 1670- RENOVATE FOR EXPANDED ENROLLMENT |  | SOM EDUC | 1670 | TO BE PERFORMED BY PD&C | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 43634 | [8 empty] | Ron Veloz |  |  | 2019-09-06 | Fall 2019 | FS | FALSE | 2019 | 2021-02-16 | FY 19-20
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | Katie Sanchez |  | Gerald Caraig | 20 |  |  | FALSE | 2600000 |  | 42509 | Funding & Approval | [12 empty] | PD&C | FALSE | 2016 | 2021-02-16
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Rivera Library Arches/Arcade Repair | Paint and replace roof. | RIVERA LIB |  | Bids received, award on hold due to DM funding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Scott Donnell | 99 |  |  | FALSE | 240000 |  | 42496 | Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-02-16
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 6 |  |  | FALSE | 600000 |  | 43634 | Complete Construction | 44166 | 44344 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | SOCCER FIELD AND AREA |  | On Hold | Tamica Smith Jones | Eugene Hutchinson | Joe Erbland |  | Gerald Caraig | 2 |  |  | FALSE | 0 |  | 41739 | Need direction by PM Director | [12 empty] | PD&C | FALSE | 2014 | 2021-02-16
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Commencing Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Rowan Reid | 1 |  |  | FALSE | 1150000 |  | 42719 | Completion of Basis of Design | [12 empty] | PD&C | FALSE | 2016 | 2021-02-16
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | In Bidding (prequalification) | Gerry Bomotti | TBD | Sharyl Murdock |  | Rowan Reid | 16 |  |  | FALSE | 26329342.06 |  | 42353 | Start Construction | 44197 | 45139 | [10 empty] | PD&C | FALSE | 2015 | 2021-02-16
2952 | 2952 |  | FALSE | CAP PROG | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jon Harvey |  | Gerald Caraig | 13 |  |  | FALSE | 23895000 |  | 42258 | Phase I Completion | 43467 | 44317 | [10 empty] | PD&C | FALSE | 2015 | 2021-02-16
2989 | 2989 |  | FALSE | ATHLETICS | Dance - Locker Room Remodel | We are requesting to utilize Base Architecture, Planning, & Engineering, Inc. to provide pro bono work on planning for locker room renovations in the Athletics & Dance Building. Rob Gayle is aware of our desire to utilize this company for services. |  |  | On Hold (COVID-19) | Tamica Smith Jones | Eugene Hutchinson | Joseph Erbland |  | Tameesha Hayes | 99 |  |  | FALSE | 28395 |  | 42327 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2015 | 2021-02-16
3104 | 3104 |  | FALSE | PALM DESERT GRAD CTR | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Funding | Tamara Hedges | Zelda Glenn | Zelda Glenn |  | Scott Donnell | 2 |  |  | FALSE | 22000 |  | 42502 | Approval & Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-02-16
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | 44256 | 44378 | [10 empty] | PD&C | FALSE | 1900 | 2021-02-16
3119 | 3119 |  | FALSE | CAP PROG | Plant Growth Environment Facility | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. |  |  | Furniture/Equipment | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 6 |  |  | FALSE | 27425000 |  | 42515 | Commisioning | 43617 | 44197 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-16
3195 | 3195 |  | FALSE | FAC-PLNG-DESIGN-CONST | North District | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 4146146.55 |  | 42669 | Complete Construction | 43647 | 44409 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-16
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Programming | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 22 |  |  | FALSE |  |  | 42653 | Design | [12 empty] | PD&C | FALSE | 2016 | 2021-02-16
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 15690389.32 |  | 42720 | Bidding | 44287 | 44470 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-16
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | John White |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 42725 | Complete Construction | 44197 | 44317 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-16
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 42886 | Department Approval/Funding | [12 empty] | PD&C | FALSE | 2017 | 2021-02-16
3286 | 3286 |  | FALSE | PB&A | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 10 |  |  | FALSE | 3375000 |  | 42823 | Complete Construction | 44228 | 44317 | [10 empty] | PD&C | FALSE | 2017 | 2021-02-16
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Mihai Gavan | 9 |  |  | FALSE | 57950000 |  | 42887 | Complete Construction | 43770 | 44409 | [10 empty] | PD&C | FALSE | 2017 | 2021-02-16
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | On Hold | Rodolfo Torres | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Daneca Stevens | 1 |  |  | FALSE | 45000 |  | 42899 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-02-16
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | TBD | Richard Geiger |  | D.Hecht/J.Franklin | 20 |  |  | FALSE | 0 |  | 43007 | Project pushed to 2021 | [12 empty] | PD&C | FALSE | 2017 | 2021-02-16
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Construction | Kathryn Uhrich | TBD | Tracey Kahn, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 1575000 |  | 43108 | Complete Construction | 44197 | 44287 | [10 empty] | PD&C | FALSE | 2018 | 2021-02-16
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 14 |  |  | FALSE | 0 |  | 43072 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-02-16
3401 | 3401 |  | FALSE | CAP PROG | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | In Construction | Jacqueline Norman | Sharyl Murdock | Mihai Gavan |  | Fernando Canon | 12 |  |  | FALSE | 8754623.11 |  | 43072 | Complete Construction | 43952 | 44228 | [10 empty] | PD&C | FALSE | 2017 | 2021-02-16
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Eugene Hutchinson | Johnathan Jensen |  | Fernando Nunez | 1 |  |  | FALSE | 0 |  | 43335 | Department approval to move fwd | [12 empty] | PD&C | FALSE | 2018 | 2021-02-16
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Richard Geiger |  | John Franklin | 6 |  |  | FALSE | 0 |  | 43178 | CIB Approval | [12 empty] | PD&C | FALSE | 2018 | 2021-02-16
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Funding | Christopher Lynch | TBD | Margaret Souder |  | Scott Donnell | 2 |  |  | FALSE | 700000 |  | 43194 | Secure Funding | [12 empty] | PD&C | FALSE | 2018 | 2021-02-16
3438 | 3438 |  | FALSE | CAP PROG | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | City to determine schedule | Jacqueline Norman | Sharyl Murdock | Dave Bomba |  | Scott Donnell | 15 |  |  | FALSE | 88500 |  | 43334 | City to determine schedule | 44013 | [11 empty] | PD&C | FALSE | 2018 | 2021-02-16
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | On Hold (COVID-19) | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 43273 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2018 | 2021-02-16
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 43297 | Complete Study | [12 empty] | PD&C | FALSE | 2018 | 2021-02-16
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 17 |  |  | FALSE | 0 |  | 43297 | Coordinating with North District | [12 empty] | PD&C | FALSE | 2018 | 2021-02-16
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 19 |  |  | FALSE | 315000 |  | 43312 | Bidding | 44317 | 44378 | [10 empty] | PD&C | FALSE | 2018 | 2021-02-16
3467 | 3467 |  | FALSE | PB&A | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | Bidding - 3rd flr Walking Deck Only | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 17 |  |  | FALSE | 235000 |  | 43312 | Award Contract | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2018 | 2021-02-16
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 19 |  |  | FALSE | 916581 |  | 43410 | Complete Review | [12 empty] | PD&C | FALSE | 2018 | 2021-02-16
3471 | 3471 |  | FALSE | VC-STU AFF | HUB Electrical Sub Meter Installation | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Design | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 200000 |  | 43332 | Bidding | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2018 | 2021-02-16
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 43404 | CEQA | [12 empty] | PD&C | FALSE | 2018 | 2021-02-16
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 16 |  |  | FALSE | 1250000 | 0 | 43390 | FS Direction | [12 empty] | PD&C | FALSE | 2018 | 2021-02-16
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. | RIVERA LIB |  | On Hold | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 43431 | Client approval/funding | [12 empty] | PD&C | FALSE | 2018 | 2021-02-16
3490 | 3490 |  | FALSE | PB&A | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | Parking Lot 13 |  | In Construction | Gerry Bomotti | TBD | Irma Henderson |  | D.Hecht/J.Franklin | 25 |  |  | FALSE | 31844000 |  | 43440 | Complete Construction | 43862 | 44287 | [10 empty] | PD&C | FALSE | 2018 | 2021-02-16
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Scott Donnell | 10 |  |  | FALSE | 65000 |  | 43528 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 43510 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | Michelle Baniqued |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 43528 | DB Competition | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | Bidding | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 6950000 |  | 43528 | Award Contract | 44348 | 45047 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | Design | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 43528 | Bidding | 44317 | 44440 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | On Hold (COVID-19) | Brian Haynes | Cathy Eckman | Christina Wong |  | Tameesha Hayes | 2 |  |  | FALSE | 130000 |  | 43543 | On hold (COVID-19) | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Bidding Competition | Gerry Bomotti | TBD | Michelle Baniqued |  | Fernando Canon | 1 |  |  | FALSE | 33980000 |  | 43528 | Select Design Builder | 44470 | 45017 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3523 | 3523 |  | FALSE | PB&A | 1907 Mt Rubidoux Facility Study | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. |  |  | Programming (Study) | Gerry Bomotti | TBD | Melissa Garrety |  | Scott Donnell | 3 |  |  | FALSE |  |  | 43577 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3524 | 3524 |  | FALSE | VC-STU AFF | Student Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | STUDENT SERV |  | Biddging | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE | 450000 |  | 43571 | BKM Lead Time 10 Weeks | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3527 | 3527 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Central Utility Plant Fire Alarm | Replace aging and non-replaceable fire alarm system, and conduit. Conduit is damaged and only 10% of wiring is usable. ( fire alarm system and devices are failing and they are not supported by manufacture ) | CNTRL UTL PL |  | In Bidding | Susan Marshburn | Da Lan Dinh | Ben Kochevar |  | Daneca Stevens | 4 |  |  | FALSE |  |  | 43593 | Award Contract | 44256 | 44256 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | In Bidding (Re-bid) | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 3 |  |  | FALSE | 1340000 |  | 43600 | Award Contract | 44256 | 44440 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3533 | 3533 |  | FALSE | PB&A | Solar Rooftop Initiative | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. | MULTIPLE BUILDINGS |  | In Construction | Gerry Bomotti | TBD | Richard Geiger |  | John Franklin | 9 |  |  | FALSE | 2165000 |  | 43619 | Complete Construction | 44105 | 44287 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3535 | 3535 |  | FALSE | CHASS | Life Sciences 452 Renovation | This request is for a new faculty hire. -Remove north countertop and sink. Install stainless counter and two sinks. -Install eye wash station -Install laminate flooring, remove existing. (Abatement) -Paint space to campus interior standard. -Remove east counter and replace with stainless. -Remove fume hood, discard. -Install new fume hood. | LIFE SCIENCE | 452 | Construction | Juliet McMullin | Cindy Williams | Paul Richardson |  | Tameesha Hayes | 1 |  |  | FALSE | 133500 |  | 43656 | Complete Construction | 44105 | 44228 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | In Funding | Gerry Bomotti | Sharyl Murdock | Gerald Caraig |  | Daneca Stevens | 2 |  |  | FALSE | 50000 |  | 43676 | Secure Funding | 44317 | 44348 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Programming | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 9 |  |  | FALSE | 500000 |  | 43713 | FS Direction | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | In Programming | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 600000 |  | 43713 | FS Direction | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3550 | 3550 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Skye Hall HVAC Replacement | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | SKYE HALL |  | In Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 1177000 |  | 43713 | Award Contract | 44317 | 44409 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3557 | 3557 |  | FALSE | CHASS | Campus Sculpture Installation | We will bring 5 sculptures to campus that will go in public places that have already been identified by Uma Ramasubramanian and Jacqueline Norman . Please construct 5 concrete plinths at various locations around campus. Locations are on the attachment. |  |  | Construction | Juliet McMullin | Cindy Williams | Emily Rankin |  | Tameesha Hayes | 3 |  |  | FALSE | 82000 |  | 43796 | Complete Construction | 44105 | 44256 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Design | Kathryn Uhrich | TBD | MaryLou Polek |  | Scott Donnell | 2 |  |  | FALSE | 2500 |  | 43742 | Construction by USDA | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3560 | 3560 |  | FALSE | CNAS | USDA Modular Bldg Installation | B19-284: Provide and install one (1) 1400 square foot double-wide modular office building with five (5) offices, one (1) being ADA compliant, one (1) ADA compliant unisex restroom, one (1) multi-purpose room with sink. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Construction by USDA | Kathryn Uhrich | TBD | MaryLou Polek |  | Scott Donnell | 3 |  |  | FALSE | 2500 |  | 43742 | Complete Construction (by USDA) | 44166 | 44228 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 1500000 |  | 43775 | On Hold | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 43809 | Departmental Approval | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3581 | 3581 |  | FALSE | SOM | SOMR Interior Egress Doors | All egress doors - Floors 1, 2, and 3 - need to be replaced with compliant structures. Please inspect, evaluate and provide quote. |  |  | In Pre-Programming | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 43894 | Design | [12 empty] | PD&C | FALSE | 2020 | 2021-02-16
3589 | 3589 |  | FALSE | CAP PROG | Various Bldgs LED Lighting Ph2 | LED Lighting Phase 2 - Package 1 - Replacing existing lamps to LED |  |  | Bidding | Jacqueline Norman | Sharyl Murdock | David Palacios |  | Fernando Nunez | 15 |  |  | FALSE | 780545 |  | 43901 | 100% Cd stamped approval | 44287 | 44407 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-16
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Design | Kathryn Uhrich | TBD | Richard Zapien |  | Scott Donnell | 6 |  |  | FALSE |  |  | 43959 | Bidding | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-16
3594 | 3594 |  | FALSE | CNAS | R'Garden Grow Pod Installation | R'Garden Gro Pod Installation |  |  | On Hold | Kathryn Uhrich | TBD | Richard Zapien |  | Scott Donnell | 7 |  |  | FALSE |  |  | 43972 | Secure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-02-16
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Construction | Kathryn Uhrich | TBD | Georgios Vidalakis |  | Scott Donnell | 8 |  |  | FALSE | 15000 |  | 44085 | Complete Construction | 44197 | 44317 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-16
3597 | 3597 |  | FALSE | PB&A | Plaza F Roof Replacement | Plaza building F roof is well past its service life and is experiencing multiple leaks into the apartment spaces below. This scope of work is to replace the roof in total and repair damages observed to the apartments below as a result of roof leaks. REQUESTING JOHN FRANKLIN AS THE PROJECT MANAGER. |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 18 |  |  | FALSE | 250000 |  | 43999 | Complete Construction | 44228 | 44287 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-16
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | TBD | Wendi Tapia |  | Tameesha Hayes | 4 |  |  | FALSE |  |  | 44001 | Bidding | [12 empty] | PD&C | FALSE | 2020 | 2021-02-16
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | In Bidding | Kathryn Uhrich | TBD | Mireya Botello Santoyo |  | Scott Donnell | 5 |  |  | FALSE | 32871.65 |  | 44026 | Construction | [12 empty] | PD&C | FALSE | 2020 | 2021-02-16
3603 | 3603 |  | FALSE | SOM | Orbach Libr SOM CSSS AV Equipment | AV for CSSS project - 954044 / re: Fernando Cortez. Please refer to MSRIV in the line reference field for the draw down. |  |  | In Construction | Deborah Deas | Deborah Trujillo | Deborah Trujillo |  | Fernando Canon | 1 |  |  | FALSE | 1652000 |  | 44039 | Complete Construction | 44166 | 44287 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-16
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 44091 | Begin RFQ Process | [12 empty] | PD&C | FALSE | 2020 | 2021-02-16
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair/Replacement | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | Funding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 8 |  |  | FALSE |  |  | 44095 | Secure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-02-16
3610 | 3610 |  | FALSE | PB&A | Hulen Place Homeless Medical Clinic | SOM is acquiring additional space for a medical clinic to assist with the homeless population. |  |  | In Programming | Gerry Bomotti | TBD | Diana Armenta |  | Daneca Stevens | 5 |  |  | FALSE |  |  | 44110 | Design | 44256 | 44256 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-16
3612 | 3612 |  | FALSE | CAP PROG | Native American Landscape Garden | Create a physical marker to commemorate the UCR Land Acknowledgement in the form of a Native American Landscape Garden (working name) at the proposed project location. |  | Ext | New (2/11) | Jacqueline Norman | Sharyl Murdock |  |  | G.Caraig/V.Kern |  |  |  | FALSE | 23000 |  | 44238 | New (2/11) | [12 empty] | PD&C | FALSE | 2021 | 2021-02-16
3617 | 3617 |  | FALSE | BCOE | WCH 108 Server Rm HVAC Upgrade | Winston Chung 108. Upgrade the HVAC system to provide cooling as needed for the server room. |  |  | In Pre-programming | Christopher Lynch | TBD | Michael Ambriz |  | Tameesha Hayes | 3 |  |  | FALSE |  |  | 44218 | Design | [12 empty] | PD&C | FALSE | 2021 | 2021-02-16
3618 | 3618 |  | FALSE | CNAS | NRS James Reserve Upgrades | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. |  |  | New (2/2/21) | Kathryn Uhrich | TBD | Heather Constable |  | Rowan Reid | 12 |  |  | FALSE |  |  | 44229 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-02-16
3621 | 3621 |  | FALSE | CNAS | NRS Emerson Main Residence Transfer Switch | We are looking to purchase and install a transfer switch to power either just our well pump or the pump and critical circuits at the breaker box by generator at Emerson Oaks when the power is out. What is the best way to contact the Campus Electricians for not only an estimate for the project but for guidance on the best way to set things up? |  |  | New (2/2/21) | Kathryn Uhrich | TBD | Joseph Messin |  | Rowan Reid | 10 |  |  | FALSE |  |  | 44229 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-02-16
3622 | 3622 |  | FALSE | ATHLETICS | Baseball Outfield Wall Repairs | Contractor to replace damaged panels and baseboards on outfield fence at Riverside Sports Complex. This is to be done with pressure treated wood. Metal rail at top to be reattached and secured. Entire wall to be painted to specific UCR Athletics colors attached. Damaged boards on scoreboard catwalk and camera scaffolding to be replaced. |  |  | New (2/10/21) | Tamica Smith Jones | Eugene Hutchinson | Eugene Hutchinson |  | Tameesha Hayes | 3 |  |  | FALSE | 49500 |  | 44237 | New (2/10/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-02-16
3623 | 3623 |  | FALSE | CNAS | NRS Boyd Deep Canyon Repairs & Upgrades | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ |  |  | New (2/2/21) | Kathryn Uhrich | TBD | Heather Constable |  | Rowan Reid | 11 |  |  | FALSE |  |  | 44229 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-02-16
3626 | 3626 |  | FALSE | UNDERGRADUATE EDUCATION | Rivera Library Room Modifications | Conduct room modifications to support new wall display on west wall Rivera A101A. Work needed: 1. West wall - ½” three-ply to support 12 x 55” displays over bookshelves. 2. West wall – drywall cover bookshelves any area not covered by the technology displays. 3. West wall – add electrical outlets as needed for new displays 4. North and south walls – add electrical for new motorized shades 5. Rivera A101A – add carpeting 6. Rivera A101A – paint room Notes: - Working with Chuck Forsyth in ITS and Bahram Mobasher from CNAS/Physics on project. - Israel and Chuck had a preliminary meeting with Enrico Baez from facilities to discuss project. - Point of contact: Israel Fletes and Charles Forsyth. Israel Fletes cellphone: 951-300-6693 |  | A101A | New (2/10/21) |  |  | Israel Fletes |  | Vilma Kern |  |  |  | FALSE |  |  | 44237 | New (2/10/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-02-16
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Bidding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 44097 | Award Contract | 44256 | 44317 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-16
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 44096 | Bidding | 44287 | 44378 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-16
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Bidding | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 44089 | Award Contract | 44287 | 44287 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-16
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Programming | [12 empty] | PD&C | FALSE | 1900 | 2021-02-16
9062 | 9062 |  | FALSE | PB&A | DM(FY20) Life Sci Sewer line |  |  |  | Bidding | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 116000 |  | 44089 | Award Contract | 44256 | 44256 | [10 empty] | PD&C | FALSE | 2020 | 2021-02-16
2970c | 2970c |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | Re-bid | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 42340 | Award Contract | 44256 | 44287 | [10 empty] | PD&C | FALSE | 2015 | 2021-02-16
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 42340 | Complete Design | [12 empty] | PD&C | FALSE | 2015 | 2021-02-16
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 432510 |  | 42425 | Bidding | 44256 | 44287 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-16
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Design (Phase 2) | Kathryn Uhrich | TBD | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 9 |  |  | FALSE |  |  | 42710 | RPU plan review/design (Phase 2) | 44348 | 44409 | [10 empty] | PD&C | FALSE | 2016 | 2021-02-16
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 43532 | Complete Report-Arc Flash | [12 empty] | PD&C | FALSE | 2019 | 2021-02-16
3515c | 3515c |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Construction | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 43532 | Complete Construction | 44166 | 44348 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 43920 | Projects to be assigned | [12 empty] | PD&C | FALSE | 2020 | 2021-02-16
3590b | 3590b |  | FALSE | PB&A | DMFI(FY17-20) Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Bidding | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 43796 | Award Contract | 44291 | 44348 | [10 empty] | PD&C | FALSE | 2019 | 2021-02-16
3589 | 3589 |  | FALSE | CAP PROG | Various Bldgs LED Lighting Ph2 | LED Lighting Phase 2 - Package 1 - Replacing existing lamps to LED |  |  | Bidding | Jacqueline Norman | Sharyl Murdock | David Palacios |  | Fernando Nunez | 15 |  |  | FALSE | 780545 |  | 43901 | 100% Cd stamped approval | 44287 | 44407 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-01
3467 | 3467 |  | FALSE | PB&A | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | Bidding - 3rd flr Walking Deck Only | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 17 |  |  | FALSE | 235000 |  | 43312 | Award Contract | 44317 | 44348 | [10 empty] | PD&C | FALSE | 2018 | 2021-03-01
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Bidding Competition | Gerry Bomotti | TBD | Michelle Baniqued |  | Fernando Canon | 1 |  |  | FALSE | 33980000 |  | 43528 | Select Design Builder | 44470 | 45017 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Rivera Library Arches/Arcade Repair | Paint and replace roof. | RIVERA LIB |  | Bids received, award on hold due to DM funding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Scott Donnell | 99 |  |  | FALSE | 240000 |  | 42496 | Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-03-01
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | CANCELED BY CLIENT | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  | 10 |  | FALSE |  |  | 43355 | [6 empty] | 1/24/2020 E. Baez- Cancelled per Joe Erbland. 4/18/19, DL; Per Enrico, we are waiting for a proposal from HCI and approved funding from Athletics. We should have the proposal in 2- weeks…. | 2018-09-27 | Enrico Baez |  | YES | 2020-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000093 |  | 20P000093 | FALSE | ATHLETICS | SL5 ATHLETICS 0078 - TELEVISION MOUNT/ ELECTRICAL |  | ATH DANCE | 0078 | CANCELED BY CLIENT | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43697 | [6 empty] | 11/26/19 O-ANS: Project canceled per communication with Enrico. | 2019-10-04 | Enrico Baez | Install TV bracket on wall near weight room. Provide recessed/flush single gang outlet near bracket. | YES | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
19P000311 |  | 19P000311 | FALSE | ATHLETICS | SL5 ATHLETICS 150-KEYLESS ENTRY | Keyless entry system | ATH DANCE | 0150 | CANCELED BY CLIENT | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43375 | [6 empty] | 02/07/2020 O-ANS: Canceled by customer Joe Erbland due to lack of funding per email to EBZ. | 2018-09-27 | Enrico Baez | Install keyless entry system, part of larger project throughout the athletics building | YES | 2020-02-07 | Summer 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20 | 1
19P000565 |  | 19P000565 | FALSE | BCOE | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS |  | BOURNS | A0133 | CANCELED BY CLIENT | Christopher Lynch | Todd Ambriz | NANCY FORD |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43563 | [6 empty] | 07/30/19 O-ANS: Per Paul Ditty, Customer Maggie Souder canceled project. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000607 |  | 19P000607 | FALSE | CHASS | SL5 PAINT FACULTY OFFICE |  | WATKINS | 1312 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 2 |  | TRUE |  |  | 43595 | [6 empty] | 08/26/19: Canceled by customer because duplicate of project 20P000044. 08/13/19 O-ANS: Customer scope of work includes more than just PAINT so project added to Fall 2019 list for prioritization by organization. 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000605 |  | 19P000605 | FALSE | CHASS | SL5 PAINT NEW MAILROOM |  | WATKINS | 1320E | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43595 | [6 empty] | 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000211 |  | 20P000211 | FALSE | CHASS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | Install keyless entry system for door to Arts Building RM 54 | ARTS | 54 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 | R3 | FALSE |  |  | 43776 | [6 empty] | 1/19/21, DL: Enrico will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment installation. 8/5/20, DL: This Project is on hold until further notice……. | 2020-01-20 | Enrico Baez | 1/19/21, EB: Per Paul R., This project is canceled………….Provide new panel, power supply and door hardware for 2 doors. Prox reader only. | YES | 2021-01-19 | Winter 2021 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21 | 1
20P000220 |  | 20P000220 | FALSE | CNAS | SL5 SPIETH-NEW CLOSING/SECURITY MECHANISM FOR LOADING DOCK DOORS |  | SPIETH |  | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | - |  | FALSE |  |  | 43783 | [8 empty] | Enrico Baez |  |  | 2019-11-22 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000335 |  | 20P000335 | FALSE | CNAS | SL5 ENTOMOLOGY BLDG 239-246 - PAINT AND PATCH OFFICE AND LAB |  | ENTOMOLOGY | 239 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43852 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty | 05/22/20 O-ANS: Project canceled per customer request (Bill Sutton). |  | 2020-05-22 | Spring 2020 | FS | FALSE | 2020 | 2021-03-01 | FY 19-20
20P000038 |  | 20P000038 | FALSE | CNAS | SL5 BATCHELOR HALL 1151- QUOTE FOR ADDING FOB ACCESS TO A DOOR |  | BATCHELOR | 1151 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | RACHEL BEHAR |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43670 | [6 empty] | 09/24/19 O-ANS: PROJECT CANCELD BY CLIENT PER EMAIL FROM DEBORAH MCWILLIAMS. |  | Enrico Baez |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
19P000413 |  | 19P000413 | FALSE | CNAS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | Batchelor 3111-Refresh BSL2 lab to accomodate Biosafety Cabinet. The Biosafety. Cabinet will be procured by BPSC. | BATCHELOR | 3111 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH | PATTY SPRINGER | Dan Lerman |  | R1 | 107 | FALSE |  |  | 43451 | [6 empty] | 11/22/19 O-ANS: Project canceled per email from Deborah McWilliams. "The need for an appropriate space to accommodate use of a biosafety cabinet will be addressed in BH 2163 via the campus Batchelor Hall MEP-Tenant Improvement Project managed by PD&C." | 2019-06-12 | Enrico Baez | Preliminary assessment provided by Tiffany Kwok on 2/13/19 email. "For Batchelor 3111, there are a few items that need to be addressed before it can support BSL-2 work. • Floors should be patched to provide a smooth and easily cleanable surface. • Base coves along the wall should be replaced or repaired to provide a smooth and easily cleanable surface. • Base coves under the cabinets on the corners should be provided. • Provide a layer of sealant over the cabinets to ensure that the cabinets are moisture resistant and easily cleanable. • Seal, repair or replace the wooden rack on the wall to provide a moisture resistant and easily cleanable surface. • Ensure the door is self-closing. Since this is not a new facility and the space is not undergoing major renovations, it is not required to provide negative airflow into the space. However, it is still important that the air from the laboratory is not recirculated into clean spaces". | YES | 2019-08-26 | Winter 2020 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20 | 1
20P000086 |  | 20P000086 | FALSE | CNAS | SL5 SKYE 2ND FLOOR - KEY CARD ACCESS ESTIMATE |  | SKYE HALL | 2ND FLOOR | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  | R3 |  | FALSE |  |  | 43696 | [6 empty] | 09/26/19 O-ANS: CANCELED BY CUSTOMER - Estimated cost to go keyless outside of budget. | 2019-09-10 | Enrico Baez | Provide estimate for keyless entry. | YES | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
19P000555 |  | 19P000555 | FALSE | CNAS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK | INSTALL OF FENCE FOR RAIN COLLECTOR AT TES TANK | SAT CHIL PL | 0 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Dan Lerman |  | R4 |  | FALSE |  |  | 43558 | Estimate from contractor | [5 empty] | 10/30/19 O-RVL: RV sent Andrew a message to ask if a decision was made to proceed with this project or if it will be cancelled?" Pending response. END~ 10/16/19, DL; I placed this project on hold as we have not heard back from the customer. We notified the customer of the cost but have not heard back from them. If the project is approved, we will schedule the work………...10/1/19, DL; Ron provide Deborah the propsal and we are waiting for her response to proceed or cancel the project……...9/16/19, DL; Ron submitted the estimate to Debora and the Faculty member last week. If project is approved, we will schedule the work……9/3/19, DL; Plans and estimate are complete. Ron will provide Deborah with a formal estimate and let us know if we will proceed with the work…..8/15/19, DL; Plans are approved. We ware waiting for a estimate from our contractor. Once we have the quote, we will forward the quoted to Deborah for review and approval. Note, this is a recharge project…….8/1/19, DL; Plans are complete pending approval from building official…. |  | Enrico Baez | Install Chain Link fence with gate. Includes grading, gravel and fence posts set in concrete. |  | 2019-10-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000017 |  | 20P000017 | FALSE | CNAS | SL5 COLLEGE BLDG CR200 - PAINT PROJECT |  | COLL BLDG NO | CR0200 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Dan Lerman |  | R4 |  | FALSE |  |  | 43661 | [6 empty] | 1/30/20, DL: This Project was Canceled per Rohnda via email on 1/29/20……….11/26/19, DL; Provided Ronda with updated quote on 11/25/19: She will present the quote to her team and provide us with an update in the near future if they would like to proceed………11/20/19 O-ANS: Re-assigned to Dan Lerman. Project was originally a paint project but will be outsourced as Recharge project paid for by the customer's department. |  | Dan Lerman |  |  | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
19P000594 |  | 19P000594 | FALSE | CNAS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS | Take down a dividing wall in this office and move the desks to their old location and rehang the overhead desk bins back into their old locations with inserts still in the walls. | ENTOMOLOGY | 171 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  | R9 |  | FALSE |  |  | 43581 | [8 empty] | Enrico Baez | TBD | NO | 2019-09-18 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000169 |  | 20P000169 | FALSE | PB&A | SL5 LOTHIAN LO-G104-OFFICE - JOB WALK FOR REMODEL OF SCOTTY'S |  | LOTHIAN HALL | SCOTTY'S | CANCELED BY CLIENT | Gerry Bomotti | TBD | FRED OFFENEY |  | John Peraino |  | - |  | FALSE |  |  | 43747 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000199 |  | 20P000199 | FALSE | SoB | SL5 ANDERSON SO RM 0002 - KEYLESS ENTRY MINOR RENOVATION REQUEST |  | ANDERSON 2 (S) | 2 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG | KENNETT LAI | Dan Lerman |  | - |  | FALSE |  |  | 43763 | [8 empty] | Enrico Baez |  |  | 2019-11-14 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000059 |  | 20P000059 | FALSE | SOM | SL5 SOME 2626- PATCH & PAINT |  | SOM EDUC | 2626 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43682 | [6 empty] | 11/26/2019 O-ANS: Project canceled per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000658 |  | 19P000658 | FALSE | SOM | SL5 SOM RB- PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD - PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43627 | [6 empty] | 03/05/20 O-ANS: Canceled by client per Cynthia Carolina. |  | Enrico Baez | TBD | NO | 2020-03-05 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000659 |  | 19P000659 | FALSE | SOM | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43627 | [6 empty] | 08/05/20 O-ANS: Canceled by client (Cynthia Carolina) via email with Ron Veloz. 8/5/20, DL: Dan to follow -up with customer…………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "remove 330 from work order / update project details / Update: Furniture on order 3.30.2020 - delivery tbd" |  | Enrico Baez | TBD | NO | 2020-08-05 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000206 |  | 20P000206 | FALSE | VC-STU AFF | SL5 COSTO HALL 111-HUB 353/381- RENOVATIONS - CP0003486 |  | COSTO HALL | Lower Level | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | - |  | FALSE |  |  | 43770 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000073 |  | 20P000073 | FALSE | VC-STU AFF | SL5 HUB - THE WELL -3RD FL RM 346 DOOR INSTALLATION CP00003544 | DOOR INSTALLATION | HUB | 346 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | JONATHAN GODOY |  | Dan Lerman |  | PENDING |  | FALSE |  |  | 43689 | [6 empty] | 12/13/19 O-ANS: Project canceled by client Brendan O-Brien. | 2019-10-02 | Enrico Baez | 1.) Remove Aluminum accordian door from opening. Customer to determine how to discard. 2.) Frame opening with metal 2"x4" stud and sheet with 3/4" drywall. Allow for oppening to accommodate 36"x 80" door. 3.) Install metal door jamb and casing to match exisiting openings. Door to match exisiting. Campus Fire Marshall to determine if door to be fire rated. Swing to be approved by Campus Building official and/or Campus Fire Marshall. 4.) Relocate single gang outlet on North side of opening , if needed. 5.) Finish drywall, prime and paint walls. Texture to match exisiting. Customer to approve final paint color. | YES | 2019-12-13 | FALL 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
18P000198 |  | 18P000198 | FALSE | VC-STU AFF | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Install new Wall lights | HUB | 0 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | R1 | 5 | FALSE |  |  | 43060 | Canceled per Brendan. No funding | [5 empty] | 10/30/19, DL: This project is on Hold and may be canceled as funding is not availabel at this time. Plans are approved……10/16/19, DL; Plans were submitted for plan check review last week. I also notified Brendan that this will be a recharge project . The ball park estimate I provided to Brendan was $7,000 - $9,000. Brendan needs to confirm if funds are available. If funds are available, I will have a contractor bid on the project……… 10/16/19: O-ANS - Not a CORE location so project changed to Recharge. 10/1/19, DL; Plans will be submitted a building permit and plan check review this week…….9/3/19, DL; Gunter has plans at 60%, We will try and submitt with in the next two weeks. 8/14/19, DL;This project is now on Gunther's bench. Gunter will start the process in about 2- weeks and we should have plans top submitt with in the next 30- days….6/17/19, DL; I will walk this work in the next two weeks and work on plan to submit to our campus architech and building official for review…..DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…… | 2018-01-23 | Enrico Baez |  | YES | 2019-10-30 | Winter 2018 | FS | FALSE | 2017 | 2021-03-01 | FY 19-20 | 1
20P000184 |  | 20P000184 | FALSE | VC-STU AFF | SL5 HUB 261 - CONSTRUCT WALL FOR MEETING/CONFERENCE RM | In HUB 261 the administration is requesting a wall be constructed to create a meeting/conference room. We need a building zone manager to walk the area give estimate as well as reaching out to the fire marshals inspector for recommendations. | HUB | 261 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | Manny Sanchez |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43755 | [6 empty] | 02/07/2020 O-ANS: Canceled due to client request. | 2019-11-05 | Enrico Baez | 11/5/19 E.Baez conducted site visit. **********SCOPE********* 1. Construct, full height, partition wall with door in HUB 261. 2. Provide/install ADA compliant door in new partition wall. 3. Add and relocate fire sprinkler. 4. Re-position lighting in ceiling, add lighting control. 5. Patch and paint. 6. Install base board. 7. Add strobe and smoke detectors. 8. T-bar ceiling re-work. | YES | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000225 |  | 20P000225 | FALSE | VC-UNIV ADV | SL5 HINDERAKER 0137 - BASEMENT RESTROOM SINK INSTALL | Install Kitchen Sink in entry room of Restroom 0137 | HINDERAKER | B137 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL | KIM MCDADE | Dan Lerman |  | 1 |  | FALSE |  |  | 43784 | [6 empty] | 1/22/20 O-ANS: Canceled per customer request. | 2020-01-22 | Enrico Baez |  | YES | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000417 |  | 19P000417 | FALSE | VC-UNIV ADV | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY |  | UV BLDG A | 201 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43452 | Schedule the work | 43691 | 43827 | [5 empty] | Enrico Baez |  |  | 2019-08-06 | Summer 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20 | 1
19P000621 |  | 19P000621 | FALSE | BCOE | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0308 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Paul Ditty |  | 10 |  | TRUE |  |  | 43599 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000210 |  | 20P000210 | FALSE | BCOE | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | Reduce noise. Replace doors with solid core doors and install an Acoustic Door Seal Kit. | CHUNG HALL | 224 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43774 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……. | 2020-02-11 | Enrico Baez | Removal of the existing double doors and door hardware, install new solid core double doors with continuous hinges, install new acoustical jamb seals, threshold seal and a surface mounted Automatic Door Bottom utilizing a flat spring mechanism, which activates when closing the door, lowering a neoprene seal insert against the floor or threshold to create a sound seal. Install acoustic double door astragals with seal. Reinstall all existing door locksets, and door closers. Quote received from Brad Aduddell-American Door to perform this work. Quote & Specs are available in the project folder. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000233 |  | 20P000233 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - A169 & A170 ENTRY AREA DAMAGED |  | BOURNS | A169 & A170 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43791 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000624 |  | 19P000624 | FALSE | BCOE | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | Refurbish Room-Student Space, | BOURNS | A0346 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43600 | Pending information from Susanna | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Susanna is working on a cubicle layout. Once we have the information from her. We will schedule the work………… | 2019-11-07 | Enrico Baez | Remove all lower cabinets in room A0346 and all lower cabinets and mail boxes in Rm A0304 | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000039 |  | 20P000039 | FALSE | BCOE | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE |  | BOURNS | A0318 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43598 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……..09/19/19 O-ANS: HOLD FOR WINTER 2020 PER CUSTOMER (LOUIS SANDOVAL) REQUEST. EMAILED PAUL DITTY TO CONFIRM. PAUL STATED THIS IS NON-PAINT PROJECT B/C SCOPE OF WORK INCLUDES CARPENTERS AND ELECTRIC SHOPS. |  | Paul Ditty |  |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
19P000620 |  | 19P000620 | FALSE | BCOE | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0304 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Paul Ditty |  | 9 |  | TRUE |  |  | 43599 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000427 |  | 19P000427 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | Install Power and TV bracket, move white board | CHUNG HALL | 453 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43468 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold……… | 2019-09-18 | Enrico Baez | Install Power and TV bracket, remove white board and relocate , patch and paint wall prior to installing | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21 | 1
19P000502 |  | 19P000502 | FALSE | BCOE | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | Install Electrical power & TV bracket.for a 75" TV to mount in CS 342. | CHUNG HALL | 444 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | RICHARD BAIN |  | Dan Lerman |  | R3 |  | FALSE |  |  | 43515 | Schedule the work. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This project is on hold……………3/25/20, DL: Work orders are produced. I will work on scheduling the work when we return back to work…….. | 2019-09-17 | Enrico Baez | Install Electrical power & TV bracket. Excludes network/data back box and stub up to ceiling. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21 | 1
20P000183 |  | 20P000183 | FALSE | CHASS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | Install side walk | HUM & SOC SC | 1202 | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43756 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Also Existing door is compliant and there are other accessible exits to the building… 8/5/20, DL: This Project is on hold until further notice……. | 2019-11-13 | Enrico Baez | Construct Side walk. ADA compliance not required. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21 | 1
20P000185 |  | 20P000185 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR (OFF WHITE) |  | PHYSICS | 3004S | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 43756 | [6 empty] | 11/01/19 O-ANS: Canceling bc duplicate of 20P000187. Paul Ditty to speak with customer re: room. |  | Paul Ditty |  |  | 2019-11-01 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000242 |  | 20P000242 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 10 |  | TRUE |  |  | 43794 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000238 |  | 20P000238 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 14 |  | TRUE |  |  | 43794 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000614 |  | 19P000614 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 202- PAINT |  | COLL BLDG NO | 0202 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000616 |  | 19P000616 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 208- PAINT |  | COLL BLDG NO | 208 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000617 |  | 19P000617 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 212- PAINT |  | COLL BLDG NO | 212 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43599 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  | R7 |  | FALSE |  |  | 43523 | We Need an FAU # | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced. We will schedule the work when we return from campus closure………11/11/19, DL: Project is in the queue to start but we do not have an FAU# as this is a recharge project. I sent Enrico and James an email requesting the FAU#. Once we have an FAU #, I will work on scheudling the work…..10/1/19, DL; Enrico is wtill working on estimate. | 2018-10-19 | Enrico Baez | E. Baez 1. Provide power in ceiling for projector. 2. Install projector center in room between two 4ft light fixtures. 3. Install 2 duplex outlets in 4S box on South West corner of room 4. Remove existing screen. 5. Install new screen centered on South wall. Extend power from existing screen to new screen location. 6. Use existing screen power switch to control new screen. | YES | 2020-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21 | 1
19P000543 |  | 19P000543 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION | TV Bracket &Power/Network box. | CHEMICAL SCI | 342 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | JEFFERY MATUTE |  | Dan Lerman |  | R8 |  | FALSE |  |  | 43545 | [7 empty] | 2019-10-01 | Enrico Baez | "The Chemistry Department is purchasing a 75" TV to mount in CS 342. The wall that will hold the TV needs to be inspected before any action of mounting the TV is done. The wall that we are hoping to place is the Brown-ish wall, where the projector screen is, opposite to the single whiteboard (Upon entry of CS 342, the leftmost wall). We would like a electrical outlet behind the TV, if possible". RV-Cut back sound proofing (sound soak) to accommodate TV brkt & electrical. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
19P000645 |  | 19P000645 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT | Termite Treatment/Cover Gate House and repair roughtd woos as necessary | BOTAN INFO C |  | CANCELED BY FS | Susan Marshburn | Da Lan Dinh | RONALD ANDERSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43607 | [8 empty] | Enrico Baez | BOTANIC GARDEN GATE HOUSE (AND OTHER STRUCTURES) REQUIRES EXTERMINATION OF TERMITES- WITH INSPECTION RESULTS RECEIVED BY ERS |  | 2019-08-29 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
18W007453 |  | 18W007453 | FALSE | ITS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  |  |  | FALSE |  |  | 43069 | waiting for bid from contractor | 43556 | 43645 |  |  |  | 07/22/19 O-ANS: Work Order converted to project # 19P000433. For further updates, see 19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  |  |  |  | 2019-07-22 | Winter 2019 | FS | FALSE | 2017 | 2021-03-01 | FY 19-20
20P000188 |  | 20P000188 | FALSE | LIBR | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 |  | ORBACH LIB | 204 | CANCELED BY FS | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43761 | Obtain floor covering samples | [5 empty] | 11/19/20 O-ANS: Declined to move forward by FS Admin but may revisit in future prioritization period. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: We are working on floor covering samples that will work for the space. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000162 |  | 20P000162 | FALSE | PROVOST/EVC | SL5 HINDERAKER 1101B - PATCH HOLE IN WALL |  | HINDERAKER | 1101B | CANCELED BY FS | Thomas Smith | Luisa Levario | AMY GU |  | Paul Ditty |  | - |  | FALSE |  |  | 43745 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000192 |  | 20P000192 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 1st Floor | CANCELED BY FS | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43761 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000662 |  | 19P000662 | FALSE | SOM | SL5 FY19-20 PROJECT: DEANS CONF ROOM | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | SOM EDUC | 2652 | CANCELED BY FS | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43628 | [8 empty] | Enrico Baez | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | NO | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000197 |  | 20P000197 | FALSE | VC-RED | SL5 UOB 210 - SOUND PROOF INSTALLATION |  | UNIV OFC BLD | 210 | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43762 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000047 |  | 20P000047 | FALSE | VC-RED | SL5 ADVANCED NEUROIMAGING | NEEDING TO TAKE DOWN OVERHEAD CABINETRY AND REPLACE WITH SOME KIND OF SHELVING TO OPTIMIZE SPACE. LOOKING FOR AN ESTIMATE AND A PLAN. | ADV NEURO |  | CANCELED BY FS | Rodolfo Torres | Laura Manor | CHELSEA EVELYN |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43677 | pending material delivery. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice…….3/23/20, DL: Shelves are ordered. We will schedule the work when we return from the campus closure……….1/15/20 O-DHN: Emailed Status Report to customer…...1/14/20, DL: We waiting for a revised quote from the vendor as there quote was not complete. We will process the quote for a PO# when we receive the correct quote……. 11/11/19, DL: Need to review scope with Ron as the shelving system is a special order item with a 3- month lead time….. | 2019-09-24 | Enrico Baez | Remove 5'-0" x3'-0" upper cabinet, and soffits. Patch and paint walls to match the existing grey . Install customer furnished adjustable shelf. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43340 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice. | 2018-09-27 | Enrico Baez |  | YES | 2020-11-19 | Fall 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 20-21
19P000534 |  | 19P000534 | FALSE | VC-STU AFF | SL5 PATCH WALLS AND PAINT |  | HEALTH SERV | 334 | CANCELED BY FS | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43539 | [6 empty] | 12/06/19 O-ANS: Canceled by FS because unable to identify room location even after inspecting rooms with staff support. Original requester has since retired. |  |  |  |  | 2019-12-06 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000309 |  | 20P000309 | FALSE | VC-UNIV ADV | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES |  | 1955 CHICAGO | 200 | CANCELED BY FS | Peter Hayashida | Naysia Caldwell | SARAH KARSON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43840 | [6 empty] | 12/16/20 O-ANS: Canceled by FS - Project location not serviced as FS CORE location and reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Please retain project # as reference. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2020-12-16 | Spring 2020 | FS | FALSE | 2020 | 2021-03-01 | FY 20-21
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Commencing Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Rowan Reid | 1 |  |  | FALSE | 1150000 |  | 42719 | Completion of Basis of Design | [12 empty] | PD&C | FALSE | 2016 | 2021-03-01
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | COMPLETE | Kim Wilcox | TBD | ALEXIS RAMBAUD |  | Dan Lerman |  | 1 | 0 | FALSE |  |  | 43445 | schedule the work | 43486 | 43551 |  |  |  | 8/5/20, DL: This project is complete…………3/25/20,DL: Doors are scheduled to arrive the second week in April……2/19/20 O-DHN: Emailed Status Report to customer……2/18/20, DL: Work is complete except for Door and final deep cleaned I do have final stain samples from the vendor. I need to verify color……… We will complete the project when the doors arrive……….1/14/20, DL: Plans are approved, PO# is cut for the ordering of the custom doors, we are currently scheduled to start the work on or shortly after 1/21/20,. Karim understands that we will start and finish the project but we will not be able to install the door until the door arrives on site. There is a minimum of 6-8 week lead time on the door delivery………….12/16/19, DL: Plans are still in plan check review. I sent the building department an email asking for a startus update today…….10/16/19, DL; Plans were submitted to our building official this week for plan check review and a permit……9/16/19, DL; Guther will work on plans in the next three weeks. Once plans are complete, we will proceed with the permit process… | 2018-12-20 | Enrico Baez | SOW: Wall: Construct a metal stud framed wall with drywall up to hard ceiling (ceiling has 12x12 glue up ceiling tiles). Hardware: Install new lockset & keys are required.***** French Door: Install new stain grade birch door with full lite. Door and finish to match the existing office doors.***** Hard Ceiling: * Ceiling is 8’-0” A.F.F. + - with 12x12 glue up ceiling tiles. Work may require a new access panel if access to space above is needed. The 12x12 glue up ceiling tiles may need to be removed where the new wall is constructed.***** Flooring: The existing flooring will remain. Install rubber base to match existing.***** Painting, Taping & Sanding: Taping sanding and painting is required at the new wall and connecting walls.***** HVAC: May require modifications to split the existing supply air to accommodate the open office space.***** Electrical: Provide light switch at new office, power(new or relocate); add and or relocate electrical and voice/data outlets required for a standard office.***** Lighting: Provide a new light switch/circuit near office entrance. The existing 2x4 fixture is on main lighting circuit and will require lighting circuit modifications. Verify if the existing lighting is sufficient for the proposed office. Field verify if additional lighting is required.***** Fire Alarm: Provide a new Smoke/chime detector at new office area, confirm requirements. | YES | 2020-08-05 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 20-21
19P000673 |  | 19P000673 | FALSE | SOB | SL5 ANDERSON HAL NO, RM 158- RECARPET 12 ROOMS / ELECTRICAL WORK |  | ANDERSON 1 (N) | 158 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43634 | Construction | 43720 | 43731 |  |  |  | 10/1/19, DL; This proect is complete… |  | Enrico Baez |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000208 |  | 20P000208 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | Men's locker room refresh | ATH DANCE | 50 | COMPLETE | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND | EUGENE HUTCHINSON | Dan Lerman |  | 1 |  | FALSE |  |  | 43773 | [6 empty] | 1/28/21, DL: Project is complete. Paul will schedule the paint once he is back on projects……….1/19/21, DL: We will schedule the balance of the paint before the students return back to campus………..9/30/20, DL: The work is complete except for the paint……………..8/5/20, DL: The work is almost complete.……. |  | Dan Lerman |  |  | 2021-01-28 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
19P000646 |  | 19P000646 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING |  | ATH DANCE | 20R, 20S | COMPLETE | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43608 | tile wash and shower doors | 43678 | 43735 |  |  |  | 9/16/19, DL; This project is Complete…….9/3/19, DL; Project is 80% Complete. Floor covering is scheduled for this Friday. Target complete date is 9/13/19……8/15/19, DL; This project is in progress and slated for complete by the end of september…..8/1/19, DL; Project is in progress with a complete date of 3-4 weeks. |  | Dan Lerman | 06/19/19 O-ANS: Project 19P000647 was combined with this project. |  | 2019-09-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43355 | [6 empty] | 2/5/20, DL: This Project is 100% Complete………….3/28/19, Doors are in the process of being …. DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez |  | YES | 2020-02-05 | Fall 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
19P000623 |  | 19P000623 | FALSE | BCOE | HOLD SL5 WINSTON CHUNG HALL, RM 348- MOUNT TV |  | CHUNG HALL | 0348 | COMPLETE | Christopher Lynch | Todd Ambriz | BILL BINGHAM |  | Paul Ditty |  |  |  | FALSE |  |  | 43600 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000175 |  | 20P000175 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 112 - PATCH & PAINT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | - |  | FALSE |  |  | 43749 | [8 empty] | Enrico Baez | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with metal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000161 |  | 20P000161 | FALSE | BCOE | SL5 WCH 112 - MODIFY ROOM FOR NEW OCCUPANT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Paul Ditty |  | - |  | FALSE |  |  | 43742 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000163 |  | 20P000163 | FALSE | BCOE | SL5 BOURNS A0223 - PATCH/PAINT WALLS, DEEP CLEAN/REPLACE CARPET |  | BOURNS | A0223 | COMPLETE | Christopher Lynch | Todd Ambriz | SABRINA SCHUSTER | DEANNA VORHEES | Paul Ditty |  | - |  | FALSE |  |  | 43745 | [8 empty] | Paul Ditty |  |  | 2019-11-25 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000388 |  | 19P000388 | FALSE | BCOE | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | BCOE Advising is being reassigned to space on the 3rd floor of Skye (at the recommendation of the University Space Committee). | SKYE HALL | 308 | COMPLETE | Christopher Lynch | Todd Ambriz | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 43430 | Order material and schedule work | 43586 | 43644 |  |  |  | 7/15/19, DL; This project is 100% Complete………..7/1/19, DL; This project ois 95% Complete. Floor covering install will start this Wednesday…………6/17/19, DL; This project is almost complete. Target complete date is July 1st….…..5/31/19, DL; We are making good progress on this project. we are on tract to be copmplete with this project on or before July 1st……5/15/19, DL; Work is in progress and we are on schedule for th3 6/28/19 complete date…….5/1/19, DL; We will start this project this week. 4/15/19, DL; Plans were approved today. We will work on material and schedule the work. We will start this project shortly after May 1st…….3/18/19, DL; We are working on plans and plan to apply for building permit an plan review process next week | 2019-02-13 | Enrico Baez | Customer Request: Frame new walls in rm. 0310B & 0326. Widen door opening, install sliding glass door rm. 0310 Work Covered: Install metal stud framed partition walls in room 0310B and 0326 and install electrical and voice data outlets as required for new furniture layout. Widen the existing door opening in room 0310 and install one new 6-0x7-0 sliding glass door. Install a viewing window (approximately 9-0x4-0 overall width) made with two pieces of glass within a storefront frame. Relocate utilities and one wall *cabinet (*location TBD) as needed. Inclusions: Demolition: Remove the side door and frame in room 0310 and widen the opening to accept a 6-0x7-0 sliding door. Room 0310 east wall, cut in opening (approx. 9-0x4-0) at 36”-48” A.F.F.(field verify). Carpentry: Framing & Drywall: Rooms 0310B & 0326; Construct metal stud partition walls and new cased openings, and install drywall with finished edge metal (room 0310). Intersect new walls into the window mullions with a finished edge or metal with neoprene expansion tape installed between the wall and million. Room 0310; Frame a new cased opening to accept a 6-0x7-0 sliding door and frame a new cased opening at the east wall opening (approx. 9-0x4-0, at 36”-48” A.F.F. field verify) to accept a new viewing window. Floorcovering: Install new 4” rubber base in rooms 0310B and 0326, base to match existing. Acoustical Ceilings: Modify the T-bar ceiling grid and cut ceiling tiles to accommodate the new partition walls in rooms 0310B and 0326. Painting: Tape, sand and paint the new partition walls, door/cased openings. Patch and paint other walls in the Advising room 0310 as needed. Glazing: Room 0310; Install a 6-0x7-0 sliding glass commercial door (outsourced to Hour Glass). Quote is on file. Electrical: Room 0310; Relocate light switch and or wall mounted devices at room 0310/corridor wall and possibly may need to relocate conduit in the east wall where the new window opening is created. Rooms 0310B & 0326; reconfigure/separate lighting circuits and switching. Note: “Installation of electrical and voice data outlets may be required in the new partition walls at rooms 0310B & 0326 depending the furniture configuration”. Fire Alarm: Investigate at rooms 0310B & 0326. Fire Sprinklers: Investigate at rooms 0310B & 0326. Exclusions: Replacement of the existing carpet floorcovering. Repaint all walls at rooms 0310B and 0326 (paint new and adjacent walls only). Installation of new mixing boxes and T-stats in rooms 0310B and 0326. | YES | 2019-07-15 | Spring 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000070 |  | 20P000070 | FALSE | BCOE | SL5 BOURNS B342D - PREPARE LAB FOR NEW FACULTY | PREPARE LAB FOR NEW FACULTY | BOURNS | B0342D | COMPLETE | Christopher Lynch | Todd Ambriz | SABRINA SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43686 | work on paint contract | 43843 | 43864 |  |  |  | 2/28/20, DL This Project is Complete……….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is 95% Complete, we need to install 3 power outlets. This project will be 100% complete within two weeks……..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is on schedule to be complete before the 2/3/20 complete date…….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19,DL: We conducted a site visit with the PI> We will do what we can to have the project complete before 2/3/20………… | 2019-11-06 | Enrico Baez | Paint all walls to match existing colors, paint the back of wood cabinets located at the east side of the room, replace stained or damaged ceiling tiles, replace and or replace all HVAC supply & return grilles, relamp as needed, Cal Labs to clean SS sinks, disconnect and dispose of the dishwasher, Plumbing and electrical to disconnect, Cal Labs to refurbish counter tops (light sand & seal), clean strip and wax sheet vinyl floor, repair and refurbish cabinets (white Rm 316, Blue Rm 328), customer to remove all chemical and sanitize fume hoods. | YES | 2020-02-28 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000135 |  | 20P000135 | FALSE | BCOE | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MS&E Rm 0075 - 3 Ph208 Power CHW S&R WATER PPMS TOOL, Install Chilled water loop & power in clean room 075. | MAT SCI ENGR | 75 | COMPLETE | Christopher Lynch | Todd Ambriz | MARK HEIDEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43727 | Plans and permit | [5 empty] | 9/30/20, DL: This project is complete……..8/5/20, DL: This is in progress…….3/25/20, DL: We will work on plans and permits when we return back from the campus closure……. | 2020-02-18 | Enrico Baez | Intake/SOW: Install 208V 3ph power & disconnect/safety switch and one 3/4" Chilled water loop (Supply and Return) in the MSE southeast corner of clean room 0075. Create a 4" diameter pass-thru hole from this corner of room 0075 into the adjacent room 0071. FS to provide power and cooling to a compressor which will connect through the wall to the PPMS system with cryogenic helium lines. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000129 |  | 20P000129 | FALSE | BCOE | SL5 BOURNS HALL B0360C - PATCH & PAINT |  | BOURNS | B0360C | COMPLETE | Christopher Lynch | Todd Ambriz | DEANNA VORHEES | KATHY COCKER | Paul Ditty |  | 1 |  | TRUE |  |  | 43720 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/22/20 |  | Paul Ditty |  |  | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000107 |  | 20P000107 | FALSE | BCOE | SL5 WINSTON CHUNG 322 - PATCH/PAINT NEW FACULTY FACULTY OFFICE |  | CHUNG HALL | 322 | COMPLETE | Christopher Lynch | Todd Ambriz | BILL BINGHAM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43706 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000245 |  | 20P000245 | FALSE | BCOE | SL5 WCH RM 0325 - PATCH AND PAINT DAMAGE FROM WHITE BOARD |  | CHUNG HALL | 325 | COMPLETE | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43794 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/13/20 |  | Paul Ditty |  |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000638 |  | 19P000638 | FALSE | BCOE | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM | renovate lab | BOURNS | B207 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43601 | order material and schedule work | 43681 | 43742 |  |  |  | 11/11/19, DL: This project is Complete……10/30/19, DL: This Project is 95% complete and we should be complete next week………..10/16/19, DL; This project is 99% complete. We need to insulate ducting and deep clean the lab………9/16/19, DL; Project is 95% complete. We are planning to be complete in the next 30 days……9/3/19, DL; Project is in progress and 75% complete. 8/15/19, DL; Plans were approved this week. We will order the material and schedule the work……..Plans are 90% complete and we will probably submit plans for plan check review this Monday | 2019-07-19 | Enrico Baez | 07-01-19 O-RVL: RV Received email from Luat on 06-28 with revised SOW. RV Uploaded the referenced sketch into FAMIS. Revisions read: "In efforts to be helpful, I've color coded comments related to the simple attached sketch. 1) Unchanged: HVAC ductwork needs to be insulated so that we cannot hear it— the vibrations from the noise affect precision optical measurements. 2) Revised to be more specific: only the first row of overhead lights should be on the main switch (dark green). The other lights should be lowered and have pull-down chains, like this but with a longer a longer chain: https://www.grainger.com/product/19YX62 3) Removed: it would be nice if cabinets are nicer and not broken, but we'll turn them into open shelves if there are no funds for this. 4) Removed: (unless fire marshalls object and request sprinklers be lowered) 5) 3) Revised: for air venting machined fumes and soldering, a flexible fume vent should be installed, something like this: https://www.grainger.com/product/EXTRACT-ALL-Extractor-Arm-2DBX4 I'm flexible about where this is hung... what are the options? 6) 4) Revised: the utility rack in the center of the room should be moved to be in line with the other, and centered with the whiteboard on the wall. (Pink) 5) Added: chilled water (blue) and compressed air (light green) should be piped over so it's available to the 10'x3' optical table. 6) Added: Black plywood would be installed at the height of the current 8 1/2" frame like Kevin's in 2 spaces: a) around the 10x3' marked optical table b) around the 6x3' overhead rack close to the doors. Luat T. Vuong" | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000477 |  | 19P000477 | FALSE | BCOE | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT |  | CHUNG HALL | 457 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 11 |  | FALSE |  |  | 43495 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000602 |  | 19P000602 | FALSE | BCOE | SL5 BOURNS B328F- PREPARE LAB FOR NEW PI OCCUPANCY |  | BOURNS | B0328F | COMPLETE | Christopher Lynch | Todd Ambriz | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43594 | Finish the work… | 43871 | 43897 |  |  |  | 3/25/20, DL: this Project is Complete………...2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is almost complete and should be complete in the next 2-3 weeks………..10/30/19, DL: Plans and permits will be required for the work. We will work on the plans shortly after Thanksgiving……….. | 2019-09-27 | Enrico Baez | Construct metal stud wall framing and bracing above ceiling to infill the opening. Remove and reinstallation wall mounted cabinets located near the cased opening to access and join to the existing wall to new drywall. Install sound insulation. Install drywall, tape, sand, prime and paint wall. Install install rubber base to match existing. Modify T-bar ceiling to accept the wall framing Provide dust containment (Zip Walls) at both rooms near construction area. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000028 |  | 20P000028 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0219- PAINT FACULTY OFFICES |  | BOURNS | A0219 | COMPLETE | Christopher Lynch | Todd Ambriz | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43665 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000487 |  | 19P000487 | FALSE | BCOE | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES |  | BOURNS | A219, A211, A241 | COMPLETE | Christopher Lynch | Todd Ambriz | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43501 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | COMPLETE | Christopher Lynch | Todd Ambriz | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43594 | Finish Gas cabinet installation | 43731 | 43868 |  |  |  | 8/5/20, DL: This Project is Complete…….3/25/20, DL: Project is 95% complete. We will install the fire sprinkler and exhaust duct to the gas cabinet when we return from the campus closure………..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Plans were approved and material is ordered. We are hopeful the material will arrive the 2nd or 3rd week in January. Once material is on site we will schedule the work…… 11/19/19 DH: Emailed Status Report to customer……10/16/19, DL: This project is 90% Complete. We are working on plans and permits for the two snorkels……….10/1/19, DL: This project is almost complete. We will be complete in the next 4- weeks except the Snorkel……….. 9/13/19, DL; The paint of the cabinets is scheduled for this week along with the power. We will submit the plans for the snorkel this with in the next two weeks…….9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Enrico Baez | SOW, Patch& Paint Walls, replace plexi glass on shelving, powder coat metal shelving & cabinets, clean & polish or replace chem sinks, polish counter tops, Validate all gas, water, drains, DI water & utilities. Replace damaged and dirty ceiling tiles, relamp as needed. Strip & wax floor. Dan L is requesting vendor pricing to restore finishes. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000029 |  | 20P000029 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0211- PAINT FACULTY OFFICES |  | BOURNS | A0211 | COMPLETE | Christopher Lynch | Todd Ambriz | DEANNA VORHEES |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43665 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/12/19 |  | Paul Ditty |  |  | 2019-12-12 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000601 |  | 19P000601 | FALSE | BCOE | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY | Renopvate lab space, Patch/paint, Re-finish, re-surface – existing cabinets/casework. Re-finish, bench-tops. Clean existing Chemical fume hood. Repair or replace self-closing chemical/flammables storage cabinet. Repair or replace bench shelves as needed. Clean and wax floors. | BOURNS | B0328E | COMPLETE | Christopher Lynch | Todd Ambriz | KATHALENA COCKER |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43594 | Order material and scheudle work |  | 43868 |  |  |  | 2/28/20, DL: This project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL; This Project should be complete in the next 2-3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were approved. We will order material and schedule the work once the material is on site. The material should arrive around the 21st of January…….11/25/19, DL; Floor covering will be complete today. This project is complete except for the Snorkel vents. We are still waiting for plans check approval on the snorkels………11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Floor covering is delayed. We will schedule the floor covering installation when the material is on site. We submitted the plans for the snorkels last week. Once the plans are approved, we will order the phoenix valves and schedule the work………. 10/30/19, DL: This Project is 85% Complete. We will install new floor covering in the next two weeks. All work will be completed except the two snorkels. We still need to submit plans for the snorkels……..10/16/19, DL; This project is 80% complete. 9/16/19, DL; Project is in progress. We still need to submit plans for the snorkel for the power and snorkel. We will submit the plans for review within the next week. Once plans are approved, we will schedule the work……..Scope is complete, waiting on estimates from vendors. We will need to work up a contract which will add time to the project timeline… | 2019-08-06 | Enrico Baez | Provide two new 4” exhaust duct drops. One at the south wall above mobile table & one at the east wall above counter. Refinish two wood work station counter tops with chemical resistant coating (approx. 64lf) including one mobile table wood top. Install four(4) 208v / 30a Electrical receptacles and data drops at gutter racks above two work benches Provide drawer and door maintenance and or repairs at all metal cabinets and metal shelving. Powder coat all lower metal cabinets, shelving, fume hood doors and drawers. Replace damaged sheet vinyl flooring as needed. Move surplus items to materials management as identified by the PI. Install MilQ equipment at the east wall near sink. Relocated cylinder rack as necessary to accommodate “L” shaped work station. Provide and install two new cylinder racks at the south end of two work benches. Furnish and install two new metal cylinder racks. Replace damaged and/or stained 2x4 acoustical ceiling tiles. Relocate “L” shaped front cabinets. Relamp light fixtures and needed. Infill wall between rm 328E & D Patch and paint walls. Strip and wax floor. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000597 |  | 19P000597 | FALSE | BCOE | SL5 PATCH AND PAINT WALLS |  | CHUNG HALL | 355, 356, 351, & 353 | COMPLETE | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43588 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000221 |  | 20P000221 | FALSE | BCOE | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | COMPLETE | Christopher Lynch | Todd Ambriz | HONG XU | KEVIN FREEDMAN | Dan Lerman |  | 3 |  | FALSE |  |  | 43784 | [6 empty] | 1/19/21, DL: This project is 100% Complete……..9/30/20, DL: We are in the process of finishing up a few other projects. Once they are complete, we will schedule the work….8/5/20, DL: Plans are approved and we will start the work in the next 2-6 weeks…….. | 2020-02-25 | Enrico Baez | Install Plywood and supports. Paint Plywood black. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
19P000625 |  | 19P000625 | FALSE | BCOE | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM |  | BOURNS | A0108 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43600 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-01 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000558 |  | 19P000558 | FALSE | BCOE | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT |  | BOURNS | A0265 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43558 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000065 |  | 20P000065 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR CONFERENCE ROOM 205/206 - PATCH & PAINT |  | CHUNG HALL | 205 & 206 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43685 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000657 |  | 19P000657 | FALSE | BCOE | SL5 WINSTON CHUNG HALL, RM 406- PATCH/PAINT OFFICE |  | CHUNG HALL | 406 | COMPLETE | Christopher Lynch | Todd Ambriz | BILL BINGHAM |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43623 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000526 |  | 19P000526 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT |  | CHUNG HALL | 0202 & 0203 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43536 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-08 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
21P000037 |  | 21P000037 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | Paint Only | CHUNG HALL | 427 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44043 | [6 empty] | 01/19/21 O-ANS: Paint complete per technician and closed project. 11/30/20 B-SBT: repatch & Paint north wall |  | Paul Ditty |  |  | 2020-11-30 | Winter 2021 | FS | FALSE | 2020 | 2021-03-01 | FY 20-21
20P000449 |  | 20P000449 | FALSE | BCOE | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | Paint Only - Chung Hall, Fourth Floor, Room 461 Patch & Paint: At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. Follow up with fresh paint. Thank you. | CHUNG HALL | 461 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43993 | [6 empty] | 01/19/21 O-ANS: Complete per technician updates and closed project. Completed by Wendy M. 11/09 -SC |  | Paul Ditty |  |  | 2020-11-09 | Winter 2021 | FS | FALSE | 2020 | 2021-03-01 | FY 20-21
20P000068 |  | 20P000068 | FALSE | CHANCELLOR | SL5 SKYE 349 - COVER HOLES ON WALL |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | TBD | VICTORIA AVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43686 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000195 |  | 20P000195 | FALSE | CHASS | SL5 ARTS 0054 - PAINT PIANO LAB |  | ARTS | 54 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | - |  | FALSE |  |  | 43762 | [8 empty] | Paul Ditty |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000142 |  | 20P000142 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 5502 - PATCH AND PAINT FACULTY OFFICE |  | HUM & SOC SC | 5502 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000141 |  | 20P000141 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4401- PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4401 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000143 |  | 20P000143 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 6605 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 6605 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43734 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000140 |  | 20P000140 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4400 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4400 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-10-09 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000575 |  | 19P000575 | FALSE | CHASS | SL5 WATKINS HALL PAINT/FLOORING |  | WATKINS | 1309A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43572 | [6 empty] | 11/26/2019 O-ANS: Paint phase completed per Paul Ditty. Awaiting completion of flooring. |  |  | 01/31/20 O-ANS: Completed per notes as of 09/05/19. |  | 2019-09-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000337 |  | 19P000337 | FALSE | CHASS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | Remove whiteboard (in front of room), mount LED mount, add double duplex and electrical power behind LED, patch and paint wall | PSYCHOLOGY1 | 3210 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 1 | 101 | FALSE |  |  | 43384 | site visit and schedule the work | 43724 | 43707 |  |  |  | 10/1/19, DL; This Project is Complete……………..9/3/19, DL; Space is blocked and schedculed to be completed by 9/27/19…..8/14/19, DL; Conducted site visit with Trades. We will schedule the space to be blocked out and start the work mid September….8/1/19, DL; Planning to start this project in two weeks……7/15/19, DL; I will walk the project in the near future and schedule the work if permits are not required…… | 2019-01-15 | Enrico Baez | Electricians 1. Install behind TV. Provide two duplex outlets and power. Also provide single gang box and conduit for data. Data lines have been run to T-bar in Hallway. 2. Secure loose Extron plate and cover next to TV. Painters 1. Patch and paint wall where TV is mounted | YES | 2019-10-01 | Summer 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000237 |  | 20P000237 | FALSE | CHASS | SL5 HMNSS 1202A - PATCH AND PAINT SERVICE |  | HUM & SOC SC | 1202A | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTIAN BACK |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43791 | [8 empty] | Paul Ditty | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/14/20. |  | 2020-02-14 | Spring 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000194 |  | 20P000194 | FALSE | CHASS | SL5 WATKINS 1224 - PAINT NEW FACULTY OFFICE ONLY |  | WATKINS | 1224 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43755 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/09/20 |  | Paul Ditty |  |  | 2020-01-09 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000044 |  | 20P000044 | FALSE | CHASS | SL5 WATKINS 1312 - NEW HIRE RENOVATION - ELIZABETH BERGER | Install drywall over out dated would paneling | WATKINS | 1312 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43676 | Install drywall | 43843 | 43875 |  |  |  | 2/19/20, DL: This project is Complete…………..1/14/20, DL: We started this project today and should be complete with in 3-4 weeks………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will plan on starting the project the 2nd week in January but will not confirm until we have confirmation from the carpenter shop…………11/18/19 DH: Emailed Status Report to customer……11/11/19, DL: The Material is ordered. The carpenters may start the work the week of 11/18/19………10/30/19, DL: I received confirmation the space is vacant we will schedule the work in the next 6- 8 weeks……10/16/19, DL; The plans are approved and the work is complete. I need to schedule final inspection………. | 2019-09-23 | Enrico Baez | ABATEMENT NEEDED----remove mastic from walls at base on wood paneled wall CARPENTERS 1.) Remove chalk board 2.) Install 1/2" plywood over wood paneled walls. Including over plywood partition separating wall. Do not drywall over trim. 3.) Finish drywall. ELECTRICIANS 1.) Bring out electrical for new drywall and secure when drywall has been installed. PAINTERS 1.) Patch, paint and finish all walls. CUSTODIAL 1.) Clean space after construction. | YES | 2020-02-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000664 |  | 19P000664 | FALSE | CHASS | SL5 WATKINS HALL, RM 1343/1343A- PAINT OFFICE AND LAB |  | WATKINS | 1343 & 1343A | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43628 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-08 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000643 |  | 19P000643 | FALSE | CHASS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH |  | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 14 |  | FALSE |  |  | 43606 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000002 |  | 20P000002 | FALSE | CHASS | SL5 HMNSS, RM 1212- REMOVAL OF ROLL UP WINDOW |  | HUM & SOC SC | 1212 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43647 | schedule the work | 43836 | 43861 |  |  |  | 1/30/20, DL: This project is Complete. We will istall the monitor after IT services installls the Data lines. Michael or Aliosn will notify us when IT is complete and we will schedule th emonitor installation…………1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: This project is in progress and will be complete with in two weeks……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project was delayed. The material is currently ordered. We are planning to start the week of 1/6/20……. 11/19/19 DH: Emailed Status Report to customer….10/30/19, DL; We will plan on scheduling the work shortly after Thanksgiving……….10/16/19, DL: Plans are approved, we will order the material and schedule the work once material is on site. Projected start date is mid November………..9/16/19, DL; Plans will be submitted this week for building permit and plan check review….. | 2019-10-01 | Dan Lerman | Remove Roll up partition. Install outlet and data port, patch and paint walls. | YES | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000214 |  | 20P000214 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | Remove walls and doors in spaces 2139 A,B and C. | PSYCHOLOGY1 | 2nd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43776 | Obtain building permit | [5 empty] | 9/30/20, DL: This Project is Complete…………8/5/20, DL: we will submiot plans this week.…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Plans were submitted for a permit on 2/12/20. Once plans are approved, we will order the material and schedule the work……… | 2020-01-10 | Enrico Baez | **************************************SCOPE********************************** 1.) Remove doors, and jambs 2139A, 2139B, 2139C. 2.) Remove drop ceiling in 2139A, 2139B, 2139C and repair as needed. 3.) Remove cabinets in 2139A, 2139B, 2139C. 4.) Remove walls between 2139A & B, and remove walls between 2139B & C. 5.) Change light fixture to match existing. 6.) Repair walls as needed. 7.) Patch and paint as needed. 8.) Replace carpet and base in 2139A, 2139B, 2139C and 2139 common area. 9.) HVAC duct work in individual spaces can be removed and simplified. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000145 |  | 20P000145 | FALSE | CHASS | SL5 PSYCHOLOGY 1111 - PATCH AND PAINT FRONT OFFICE WALL |  | PSYCHOLOGY1 | 1111 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43733 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20 |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000419 |  | 19P000419 | FALSE | CHASS | SL5 CHASS INT SOUTH 2117-CARD ACCESS | Remove Door and wall leading to 2117 Media Library and reconfigure to allow enterance into 2117 A & J without having to go through 2117C. | CHASS INT S | 2117 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43452 | [6 empty] | 12/16/19, DL: This project is now complete…….11/19/19 DH: Emailed Status Report to customer…..11/11/19, The work is 98% Complete. We have one door that we had to send back to the vendor to have it prepared for door hardware. We should have the door back on site with in the next two weeks………..10/30/19, DL: Doors and Frame are on site. The paint team will prime and paint the doors and frame. Once the doors and frame are painted, we will schedule the work……………10/1/19, DL; This Project is 90% Complete. We are waiting on the doors to arrive. Once the doors arrive, we will schedule them to be painted and installed…………..9/3/19, DL; We started this project today. We are planning to be 90% complete by 9/27/19. Note, we have special order doors that have a 4-6 week lead time and that is the reason why we will be only 90% complete on 9/27/19. Paul Richardson is aware of the schedule…….8/15/19, DL; The plans were approved this week, we will order the needed material and start the work very soon…….This is a two part project. We will complete the construction process now. The four doors that need key card access still require a request for proposal and a contract. This portion of the project will take 3- months due to contracts administration, lead time on material and contractor scheduling…….8/1/19, DL; Gunther is working on plans. Once permit is approved, we will schedule the work…. | 2019-03-21 | Enrico Baez | Install 8 position control panel, keyless entry for 2117, 2117A, 2117D and 2117E. ***per Paul Richardson remove 2117G, 2117H and 2117J from request*** !!!!Project to reconfigure wall space, 19P000400 has been combined with 19P000419. !!! | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000004 |  | 20P000004 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - COURTNEY BAKER |  | HUM & SOC SC | 2204 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43648 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
18P000126 |  | 18P000126 | FALSE | CHASS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS |  | HUM & SOC SC | 3611 | COMPLETE | Juliet McMullin | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 43006 | Order material and schedule work | 43635 | 43645 |  |  |  | 7/1/19,DL; This project is 100% Complete…..5/15/19, DL; Work is scheduled to start on 6/19/19…….5/1/19, DL; Plans are approved. Need to order material and schedule the work…..3/18/19, DL; Plans submitted to PD&C today…..02/2819, DL; Gunther will work on plans over the next three weeks to submit for a building permit. We will schedule the work if and after the plans are approved. If approved the door and window will more than likely have a 3- month lead time…………….12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez |  | YES | 2019-07-01 | Winter 2018 | FS | FALSE | 2017 | 2021-03-01 | FY 19-20
18P000343 |  | 18P000343 | FALSE | CHASS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER |  | HUM & SOC SC | 0400A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 43175 | sheet metal to install handrail | [5 empty] | 11/15/19, DL: This project is complete…..10/30/19, DL: Sheet metal shop fabricated the hand rails. The paint shop will prime and paint the hand rails and the curb. Once the rails are painted, the sheet metal shop will complete the installation…….10/16/19, DL; Cory from the sheet metal shop is aware of the scope of work and they will schedule the work in the near future……..10/1/19, DL; Dan to show Cory from sheet metal the area where a hand rail will be installed for painting backdrops……..07/11/19 O-ANS: Dan and Chris P will walk the space. 05/21/19 O-ANS: Changed to In Progress per meeting with Dan L. Chris P is the PM for further updates. DL and CP will visit after commencement. 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez |  | YES | 2019-11-15 | Spring 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000120 |  | 20P000120 | FALSE | CHASS | SL5 OLMSTED 2139 SUITE - PATCH AND PAINT |  | OLMSTED | 2139 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 43713 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/14/20 |  | Paul Ditty |  |  | 2020-01-14 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000215 |  | 20P000215 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | Remove Vaughan wall seperating Olmsted 3349/3351.Add 4 single gang outlets and 2, 2gang outlets. | PSYCHOLOGY1 | 3rd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43776 | [6 empty] | 1/19/21, DL: This project is 100% complete…………9/30/20, DL: Plans were approved, we had the Vaughn Wall tested for Asbestos containing material. Once we have the results, we will schedule the work………….8/5/20, DL: We will submit plans by this Friday for a building permit | 2020-02-24 | Enrico Baez | 2/24/2020 E. Baez - 1.Remove Vaughan wall and electrical circuit in wall. 2. Add 4 Single Gan outlets and 2, 2gang outlets. 3. Patch vinyl plank flooring from removed wall and safe. 4. Remove panel in 2249 with wall paper on it next to window. 5. Remove handle set to 3351, install blank, render door inoperable. 6. Repair T-Bar ceiling as needed. 7. Patch and paint walls. 8. Coordinate with ITS for data line for 8 computers. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
19P000574 |  | 19P000574 | FALSE | CHASS | SL5 FACULTY OFFICE PAINTING |  | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43567 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000005 |  | 20P000005 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - KIM FROST |  | HUM & SOC SC | 3215 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43648 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000090 |  | 20P000090 | FALSE | CHASS | SL5 OLMSTED 3345 - PAINT WALL AND FILL HOLES |  | OLMSTED | 3345 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43697 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000350 |  | 19P000350 | FALSE | CHASS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | MISC WORK IN ROOMS 3121 AND 1133 Patch and paint-relocate white boards, hang pictures. | PSYCHOLOGY1 | 3121, 1133 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 4 | 3 | TRUE |  |  | 43390 | Start this Friday. | 43679 | 43693 |  |  |  | 8/15/19, DL; This Project is 100% Complete…….. 8/1/19, DL; We will start this project this Friday…… 7/15/19, DL; Appears not plans and permits will be required for the work. I will verify and schedule the work in the near future if no plans or permits are required….. | 2019-04-15 | Enrico Baez | Carpentry: 1. Needs to occur after October 26 2. Remove the whiteboard in 3121, patch and paint 3. Remove Glass board in 1133 and relocate to 3121 (in the same way and place as it was in 1133) 3. Mount pictures on the wall in 3121 4. Secure shelving units in 1133 and 3121 5. There is a ceiling tile in 1133 that is stained and needs to be replaced Painters: 1. Room 3121 Patch and Paint walls | YES | 2019-08-15 | Summer 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000112 |  | 20P000112 | FALSE | CHASS | SL5 PSYCHOLOGY 2123 - PATCH AND PAINT JOB |  | PSYCHOLOGY1 | 2123 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43712 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000609 |  | 19P000609 | FALSE | CHASS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR |  | WATKINS | 1229 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43595 | [6 empty] | 07/03/19 O-ANS: Paint phase complete and awaiting flooring change. 06/21/19 O-ANS: Customer requested to remove lighting change from project and only complete paint and carpeting via email to Paul Ditty (copied email below). Will create separate work order for lighting. Re-assigned to Paul Ditty to complete. "From: Becky L Campbell <becky.campbell@ucr.edu> Sent: Friday, June 21, 2019 10:51 AM In regards of the work order: 19P000609 - SL5 - PAINT FACULTY OFFICE – please cancel the connecting Work Order 19W015231 – REPLACING THE LIGHTING IN WATKINS 1229. Please do paint and replace flooring.For the lighting, please create new work order to be done at a later time." |  | Paul Ditty |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000421 |  | 19P000421 | FALSE | CHASS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | Install door to access hallway directly | OLMSTED | 2139I | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 5 | 110 | TRUE |  |  | 43453 | Order material and schedule work | 43850 | 43896 |  |  |  | 2/28/20, DL: This Project is Complete….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This Project is 95% complete. We should be complete within the next week…………..1/31/20 O-DHN: Emailed Status Report to customer……1/30/20,DL; Project is in progress and should be complete with in 2- weeks………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will work on the construction schedule and material shortly after the new year. 11/21/19 DH: Emailed Status Report to customer…..10/30/19, DL: Plans are approved. Need to find out the status of the door. We will plan on scheduling the project shortly after Thanksgiving…………10/1/19, DL; Plans are approved. We need to order the door / Frame. Once door is on site, we will schedule the work……..9/16/19, DL; Plans are submitted for the permit review process……9/3/19, DL; Plans are at 50%. We will try and have plans to submit for review within the next two weeks…… | 2019-02-05 | Enrico Baez | *****This work is being performed to accommodate new faculty scheduled to arrive July 1, 2019***** Core work falls under SLA Carpenters • Open wall between corridor and 2139I. • Install metal frame and solid core door similar to 2139. Smoke and draft gasket. • Install carpet patch at threshold of new door. Carpet should match or complement existing carpet. • Remove bulletin board in hallway to facilitate doorway construction and relocate on same wall. See photos in shared drive.. • Replace base boards as needed. Painters • Prime, Patch and Paint walls, doors and trim. • Paint to match existing wall colors. Lock Shop • Furnish and install 1 each, ADA compliant handle sets, match existing hardware. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000172 |  | 20P000172 | FALSE | CHASS | SL5 PYSCHOLOGY 2136B & 2136C - PAINT & PATCH |  | PSYCHOLOGY1 | 2136B & 2136C | COMPLETE | Juliet McMullin | Cindy Williams | ANNIKA KIRMAN | YERAM CHEONG | Paul Ditty |  | 5 |  | FALSE |  |  | 43748 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000676 |  | 19P000676 | FALSE | CHASS | SL5 PATCH THE PAINT IN THIS OFFICE |  | HUM & SOC SC | 2501 | COMPLETE | Juliet McMullin | Cindy Williams | EVAN ISMAIL |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43635 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000171 |  | 20P000171 | FALSE | CHASS | SL5 CHASS INTN 2107 - PATCH UP HOLES IN THE WALL |  | CHASS INT N | 2017 | COMPLETE | Juliet McMullin | Cindy Williams | GENEVA AMADOR |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43748 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/03/20 |  | Paul Ditty |  |  | 2020-01-03 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000642 |  | 19P000642 | FALSE | CHASS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM |  | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43606 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000207 |  | 19P000207 | FALSE | CHASS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43335 | working on plans | 43619 | 43644 |  |  |  | 8/1/19, DL: This project is 100% Complete……7/15/19, DL; Floor covering will be installed next week. Floor covering is the last item for this project……..7/1/19, DL; This project is 95% complete except floor covering. Floor covering will be installed within 2- weeks……6/17/19, DL; This project is making good progress. We should be complete near July 1st…….5/31/19, DL; This project started this week and should be complete by June 28th…….3/18/19, DL; Working on plans and we will submit our plans and permit application this week….. | 2018-09-20 | Enrico Baez |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000082 |  | 20P000082 | FALSE | CHASS | SL5 HUMANITIES THEATRE - PATCH & PAINT |  | THTR WKSH | 405 | COMPLETE | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43692 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000204 |  | 20P000204 | FALSE | CHASS | SL5 ARTS 166 - PATCH AND PAINT IN LOBBY AND GREEN ROOM |  | ARTS | 166 | COMPLETE | Juliet McMullin | Cindy Williams | ALBERT FETTER |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43769 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/20/19 |  | Paul Ditty |  |  | 2019-12-20 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000552 |  | 19P000552 | FALSE | CHASS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS |  | HUM & SOC SC | 1001 B, C, and D | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43551 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000094 |  | 20P000094 | FALSE | CHASS | SL5 ARTS 0221 -PAINT OFFICE |  | ARTS | 221 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43699 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000589 |  | 19P000589 | FALSE | CHASS | SL5 HMSS OFFICE 3405 RENOVATIONS | Construct partion, pending CBO approval, in room 3405. | HUM & SOC SC | 3405 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 8 |  | FALSE |  |  | 43578 | Install carpet | 43709 | 43784 |  |  |  | 11/19/19 DH: Emailed Status Report to customer…..11/19/19 DL: This project is complete….11/11/19, DL: The carpet is delayed and scheduled to be instlled on Friday, 11/15/19. The project will be complete once the carpet is installed……10/30/19, DL: This project is 90% Complete. We are planning to install carpet next week………..10/16/19, DL; This project is 80% complete. Target complete date is 3- weeks…..10/3/19 O-ANS: Updated status per minor reno meeting…. 10/1/19, DL; This project is in progress. We will call for rough electrical inspection….. 9/16/19, DL; We are ready to schedule the work. We are currently waiting for the space to be vacated. Once the space is vacant, we will start the project……9/3/19, DL; We are ready to start the work. The PI returned to work this week. I sent Paul R. an email letting him know we are available to start once we have confirmed dates from him…..8/15/19, DL; Plans are approved but the PI is not. We will probably start the project the 2nd week in September…… | 2019-06-27 | Enrico Baez | CARPENTERS: 1. Construct partition above T-bar ceiling, full height not required. Drywall 5/8" tape and finish. 2. Remove and store three book cases. 3. Cut in opening for 36" (stain grade to match) door in general area of were bookcases were in South wall leading to corridor. Painters: 1. Patch and paint as needed Electricians: 1. Isolate existing switches to control to operate lights in West half of partitioned space. 2. Install two additional switches in East partition. 3. Install additional single gang outlets one on each side of new partition. Telecom: 1. Install additional Voice and data connection in Western side of partitioned space. Flooring: 1. Remove carpet and base. 2. Install new customer selected base and flooring. HVAC: 1. Separate existing duct work from one to two zones controlled by separate stats in each office. | YES | 2019-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000226 |  | 20P000226 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 3401 - OFFICE PATCH AND PAINT |  | HUM & SOC SC | 3401 | COMPLETE | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON | TRACY AVERY | Paul Ditty |  | 8 |  | TRUE |  |  | 43787 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/03/20. |  | Paul Ditty |  |  | 2020-02-03 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000448 |  | 19P000448 | FALSE | CHASS | SL5 ARTS 333- PATCH AND PAINT |  | ARTS | 333 | COMPLETE | Juliet McMullin | Cindy Williams | SONJA SEKELY-ROWLAND |  | Paul Ditty |  | 8 |  | FALSE |  |  | 43479 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-04 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000232 |  | 20P000232 | FALSE | CHASS | SL5 PSYCHOLOGY 3111B - WALL PATCH FOR SMALL HOLES IN THE WALL |  | PSYCHOLOGY1 | 3111B | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43789 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000608 |  | 19P000608 | FALSE | CHASS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE |  | WATKINS | 1345 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43595 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-27 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000540 |  | 19P000540 | FALSE | CHASS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | Remove metal roll up window, replace carpet, remove round column cover-reframe square. | HUM & SOC SC | 1202 | COMPLETE | Juliet McMullin | Cindy Williams | MICHAEL MOLINAR |  | Dan Lerman |  | 9 |  | FALSE |  |  | 43544 | Plans and permit | 43836 | 43875 |  |  |  | 2/18/20, DL: Thois project is 100% Complete…….1/31/20 O-DHN: Emailed Status Report to customer…..1/30/20, DL; Project is 95% complete. We will install carpet this weekend………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is in progress and should be complete within 3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project was delayed. Material is ordered. We are currently scheduled to start shortly after 1/6/20………..11/19/19 DH: Emailed Status Report to customer…..10/30/19, DL: We will plan on scheduling the project shortly after Thanksgiving……….. 10/16/19, DL; Plans were approved, we will work on ordering material and schedule the work. Anticipated start date is mid-November…….10/1/19, DL; Plans were submitted last week. Once plans are approved, we will schedule the work…………9/16/19, DL; Plans are 90% Complete. We will submit plans for plan check review in the next two weeks……. 8/15/19, DL; Gunter has the project on his list. We will try and be ready for plan check review in the next two weeks…….. | 2019-07-25 | Enrico Baez | 7/1/2019 E. Baez Carpenters: 1. Remove roll up partition and stainless steel counter top. 2. Frame opening, hang drywall, tape and finish 3. Remove round decorative column from support pillar. 4. Frame over column for square foot print. Keep as narrow as possible. 5. Hang drywall, tape and finish. Painters: 1. Paint all new construction Flooring: 1. Remove carpet and base in 1202, lobby area of 1220 and hallway. Refer to drawing. 2. Replace customer selected carpet and base. | YES | 2020-02-18 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000429 |  | 19P000429 | FALSE | CHASS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | Patch & Paint | COLL BLDG NO | 103 | COMPLETE | Juliet McMullin | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 43468 | [6 empty] | 07/26/19 O-ANS: Project complete per Paul Ditty. 06/06/19 O-ANS: Project scheduled to be completed. |  |  |  |  | 2019-07-26 | SPRING 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000568 |  | 19P000568 | FALSE | CHASS | HOLD SL5 HMSS HANG WHITE BOARD, TV MOUNTING, PATCH AND PAINT | Remove Glass White Board, mount TV, patch and paint | HUM & SOC SC | 1214 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43564 | [8 empty] | Enrico Baez | No scope |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000213 |  | 20P000213 | FALSE | CHASS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS |  | CHASS INT S | 2117A, 2117C, 2117D, 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43777 | approved permit | 43893 | 43911 |  |  |  | 8/5/20, DL: This Project is Complete……………..2819/20 O-DHN: Emailed Status Report to customer…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have a contract, we will order the material and schedule the work………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Plans are complete and submitted for building permit. We are also working on the contract. Once the plans are approved and the contract is complete, we will schedule the work………. |  | Enrico Baez |  |  | 2020-08-05 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21 | 1
20P000187 |  | 20P000187 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR |  | PHYSICS | 3004S | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 43761 | [8 empty] | Paul Ditty |  |  | 2019-11-05 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000390 |  | 19P000390 | FALSE | CNAS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | COMPLETE | Kathryn Uhrich | Jose Wudka | APRIL MEINZER |  | Dan Lerman |  | 0 |  | TRUE |  |  | 43433 | Order material and schedule work | 43617 | 43644 |  |  |  | 7/1/19, DL; This project is 100% Complete…………6/17/19, DL; material is ordered. This project should be complete by July 1st…..5/31/19, DL; Plans were apprvied this week we will work on the contract and hopefully have the notice to proceed in the next two weeks. It is our goal to have the work complete on or before July 1st……5/15/19, DL; Need to order the special order door and frame…. | 2019-02-07 | Enrico Baez | Install new aluminum storefront door, frame and side lite(requested by Dan L.), patch & paint door opening and west interior wall. | YES | 2019-07-01 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
19P000639 |  | 19P000639 | FALSE | CNAS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK | Make modifications to accommodate new PI | CHEMICAL SCI | 0435 | COMPLETE | Kathryn Uhrich | Jose Wudka | BARBARA OUTZEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43602 | finish electrical and plumbing.. | 43769 | 43805 |  |  |  | 12/16/19, DL: This project is complete…11/19/19 Emailed Status to customer….11/11/19, DL: This project is 90% Complete. We should be complete with the balance of the work in the next two weeks…………10/30/19, DL: This project is in progress and should be complete in 3- weeks……..10/16/19, DL; We will start the work in the next two weeks. 9/16/19, DL; We will start working on the plans in the next 3- weeks and submit them for plan check review. Once approved, we will schedule the work……..9/3/19, DL; Need to verify scope with Ron and start working on plans. Will start plans in the next two- three weeks…… | 2019-07-19 | Enrico Baez | For new Faculty Hire, Dr. Timothy Su we need the following done to CS 435: Original SOW: (1) Add a door between 435 and 439 (swinging outside of 435 into 439). (2) Exhaust connection for a biosafety cabinet (3) Vacuum line hook up (4) Gas cylinder rack Revised SOW 07/30/19: Room 435: (A) Remove mounted wooden cabinets (B) Remove standing wooden cabinet (C) Move flammable cabinet to Room 439 (D) Move flammable refrigerator to Room 447 Room 439: (A) Remove cabinets under sink Room 441: (A) Remove cabinets under sink (B) Remove top and bottom cabinets and bench, then deliver both items to Chemical Sciences Rm 108 (C) De-activate airflow in chemical fume hood #005855 if it does not disrupt air flow in the other chemical fume hoods. Can facilities check whether it is possible to turn valve off for this fume hood without disrupting others? (D) Move biosafety cabinet and incubator from Rm 458 to Rm 441, then hook up biosafety cabinet to house vacuum plumbing (E) Move flammable cabinet to Rm 439 | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000036 |  | 20P000036 | FALSE | CNAS | SL5 ENTOMOLOGY 224 - PAINT OFFICE FOR NEW PI HANSEN |  | ENTOMOLOGY | 224 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | 1 |  | TRUE |  |  | 43669 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20. 09/19/19 O-ANS: Project placed on HOLD for WINTER 2020 prioritization per customer request. |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000202 |  | 20P000202 | FALSE | CNAS | SL5 SKYE HALL 361 RENOVATION PROJECT | Renovete space for class room. | SKYE HALL | 361 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY | MELISSA GOMEX | Dan Lerman |  | 1 |  | FALSE |  |  | 43768 | pending permit approval | 43866 | 43917 |  |  |  | 9/30/20, DL: This Project is Complete……….8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Permits were approved. Demolition is complete…..1/15/20 O-DHN: Emailed Status Report to customer……..1/14/20, DL: Plans have been submitted for a building permit. Once plans are approved, it is our goal to complete the work by the beginning of spring quarter….. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000075 |  | 20P000075 | FALSE | CNAS | SL5 SPIETH 2372 - PATCH/PAINT FACULTY OFFICE |  | SPIETH | 2372 | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH MCWILLIAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43690 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-27 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000061 |  | 20P000061 | FALSE | CNAS | SL5 PHYSICS 1028 - MOVE UTILITIES FOR GLASS SHOP | Install utilities in Physics for the Glass shop equipment relocated from Pierce. | PHYSICS | 1028 | COMPLETE | Kathryn Uhrich | Jose Wudka | CHRISTOPHER BARDEEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43683 | Plans and permits | 43787 | 43854 |  |  |  | 04/23/20 O-ANS: Complete per Dan Lerman. Separate work order to install gas line created - 20W026489 …. 1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is 90% complete and should be 100% complete 1/24/20………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 95% complete. They are moving the equipment over. Once the equipment is delivered and setup, we will connect all of the power and plumbing……11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL; We are still working on plans for this project. 10/30/19, DL: We're planning to complete the project by 12/7/19. We are working on the plans and are planning to submit the plans for plan check review tomorrow. | 2019-10-16 | Enrico Baez | Electrical: Relocate existing power for the welder & other equipment. Install new power and safety switch for relocated equipment. Relocate power for welder and other equipment to the machine shop side of the north wall. Plumbing: Lab air and Natural Gas - relocate and install new POC's. Install water supply lines to Wet sander and diamond wet saw. Cap and or extend the existing Lab air and natural gas as necessary. Install drain lines for new equipment. Modify water supply and existing sink and faucet. Carpentry: Demo selected upper and lower cabinets at the West wall. | YES | 2020-04-23 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000571 |  | 19P000571 | FALSE | CNAS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 |  | SCIENCE LAB1 | 215 & 322 | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO |  | Paul Ditty |  | 10 |  | FALSE |  |  | 43565 | [6 empty] | 07/30/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000239 |  | 20P000239 | FALSE | CNAS | SL5 SKYE 382 - PATCH AND PAINT |  | SKYE HALL | 382 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 11 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000240 |  | 20P000240 | FALSE | CNAS | SL5 SKYE 384 - PATCH AND PAINT |  | SKYE HALL | 384 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 12 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000241 |  | 20P000241 | FALSE | CNAS | SL5 SKYE 386 - PATCH AND PAINT |  | SKYE HALL | 386 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 13 |  | FALSE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000200 |  | 20P000200 | FALSE | CNAS | SL5 COLLEGE BLDG NO 306 - PATCH AND PAINT ONE WALL ONLY |  | COLL BLDG NO | 306 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 15 |  | FALSE |  |  | 43767 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/06/20. |  | Paul Ditty |  |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000105 |  | 20P000105 | FALSE | CNAS | SL5 PHYSICS 2029 - PATCH AND PAINT |  | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | Paul Ditty |  | 17 |  | FALSE |  |  | 43705 | [8 empty] | Paul Ditty | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/06/20. |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000622 |  | 19P000622 | FALSE | CNAS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK | Replace doors & frame | FAWCETT LAB | 204 | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43600 | order door and frame. | 43691 | 43754 |  |  |  | 11/11/19, DL: This project is complete……10/30/19,DL: The doors are scheduled to be installed this Friday…………10/16/19, DL; Doors shuld be here with in the next week. Once the doors arrive, we will prep and paint the first coat and schedule the install. Target complete date is 3-4 weeks depending on when the doors arrive…….9/16/19, DL The doors are ordered. Once the doors arrive, we will schedule them to be painted and installed……..9/3/19, DL; Contractor has PO# for the doors. I need to verify lead time on material and schedule the installation…….8/15/19, DL; PO# will be provided this week to order the doors and frame, lead time is 4- weeks for the doors/ frame. We will scheudule the install once the door / frame is on site……..8/1/19, DL ; Pending estimate from vendor. Once we have everything needed, we will schedule the work…. | 2019-07-15 | Enrico Baez | Replace existing dual egress doors with ne doors and frames. | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000355 |  | 20P000355 | FALSE | CNAS | SL5 GEOL 454A- PATCH & PAINT |  | GEOLOGY | 0454A | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | LAURIE GRAHAM | PAUL DITTY |  | 2 |  | FALSE |  |  | 43870 | [8 empty] | Paul Ditty | 08/06/20 O-ANS: Closed per Paul Ditty as of 03/13/20. |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2020 | 2021-03-01 | FY 19-20
20P000081 |  | 20P000081 | FALSE | CNAS | SL5 CHEM SCI 0441- INSTALL FUME HOODS | Install vacuum to new fume hood | CHEMICAL SCI | 441 | COMPLETE | Kathryn Uhrich | Jose Wudka | TIMOTHY SU |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43692 | schedule the work | 43763 | 43791 |  |  |  | 1/14/20, DL This Project is 100% Complete…….12/17/19 O-DHN: Emailed Status report to customer…..12/16/19, DL: This Project is almost Complete except for connecting the glove box. Cory will try and connect the glove box before the new year……...11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: This project should be complete with in the next two weeks……….10/30/19, DL: This project is in progress and we should be complete in 2- 3 weeks…………10/16/19, DL: We will start this project with in the next two weeks…. |  | Enrico Baez | Install eight (8ea) electrical swithced outlets behind cabinets for new vac pumps, remove doors and install sliding lower pump shelves. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000034 |  | 20P000034 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 451- PATCH AND PAINT 2 SMALL WALL SECTIONS |  | CHEMICAL SCI | 451 | COMPLETE | Kathryn Uhrich | Jose Wudka | KEVIN KOU |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43668 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-02 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000189 |  | 20P000189 | FALSE | CNAS | SL5 SPIETH 3352 - ESTIMATE FOR PATCH AND PAINT |  | SPIETH | 3352 | COMPLETE | Kathryn Uhrich | Jose Wudka | NATALIE HOLT | SILVANA | Paul Ditty |  | 2 |  | FALSE |  |  | 43761 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/28/20 |  | Paul Ditty |  |  | 2020-01-28 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000283 |  | 19P000283 | FALSE | CNAS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 20 |  | FALSE |  |  | 43348 | Schedule site visit with contrac | 43619 | 43648 |  |  |  | 8/1/19, DL; This Project is 100% Complete……7/1/19, DL; Barricades are complete. Signage needs to be installed. Signage to be installed in the next 3- weeks………….6/17/19, DL; Yello Caution tape is installed. Still need to install barricades and signage. Target complete date in mid to late July……5/31/19, DL; The contractor has the PO#. We will start the work and complete the work in the next 30- days……5/15/19, DL; We are waiting on the quote, once we have the quote, we will proceed with the work……4/15/19, DL; We are trying to locate a roofing contractor that will complete the installation. This is a specialty product that requires a professional installation…….3/28/19, DL; We will install the yellow caution tape on the roof which is our most viable option. I will schedule a site visist / job walk with a contractor in the near future…… | 2018-09-19 | Enrico Baez | Install hand railing and marking for a leading edge as direcetd by EH&S. | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
18P000388 |  | 18P000388 | FALSE | CNAS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 43200 | schedule the work | 43619 | 43696 |  |  |  | 8/14/19, DL; This project is 100% Complete………8/1/19, DL; This project work from Facilities Services should be complete in about 2- weeks…..7/15/19, DL, Work is in progress. Goal is to be complete with our scope near the first week in August……6/17/19, DL; This will be scheduled in July…….5/31/19, DL; Demo and removal of the dishwasher is. We will work on the installation and elctrical / power connections over the next three weeks. Note. Steam shut down is taking priority and the installation may be delayed….. 5/15/19, DL; We will schedule the work……..DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but there is no hard date as this is vacant space and we will access the space as time permits…… DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter….DL, DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans….7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved….. |  | Enrico Baez |  | YES | 2019-08-14 | Summer 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
18P000486 |  | 18P000486 | FALSE | CNAS | SL5 PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 43279 | plans and permits | 43553 | 43647 |  |  |  | 8/1/19, DL; This project is 100% Complete…… 6/17/19, DL; This project is making good progreess and will be complete near mid- July…..5/31/19, DL; This project is making good progress and we are hopeful to be complete on or before July 1st……5/1/19, DL: This project is in grogress and moving forward. Target complete date is 6- weeks… 4/15/19, DL; Started Demolition phase….2/28/19, DL; We will work on the plans in the next 30-days.12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
19P000210 |  | 19P000210 | FALSE | CNAS | SL5 CHEMICAL SCI Install Door In Doorway |  | CHEMICAL SCI | 0225A | COMPLETE | Kathryn Uhrich | Jose Wudka | BARBARA OUTZEN |  | Dan Lerman |  | 25 |  | FALSE |  |  | 43336 | contract the work and material | 43619 | 43647 |  |  |  | 7/1/19, DL; This project is 100% complete…..6/17/19, DL; Po is cut. Target complete date is before 7/1/19……Permit was approved this week. We are now working on the contract with the vendor. Our goal is start the work with in the next 30- days. 5/15/19, DL; Plans were approved. I am in the process of working with PD&C for the contract. We will order material and schedule the wrok once we have a signed contract……..3/28/19, DL; Plans were submitted last week… 3/18/19, DL; Conducted site visit last week. We are working on plans now we will try and submit plans for permit review next week…… | 2018-09-19 | Enrico Baez |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000266 |  | 20P000266 | FALSE | CNAS | SL5 GEOLOGY 2460B - PATCH & PAINT |  | GEOLOGY | 2460B | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 3 |  | FALSE |  |  | 43818 | [8 empty] | Paul Ditty | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000613 |  | 19P000613 | FALSE | CNAS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT |  | COLL BLDG NO | 0203B | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43599 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-21 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000024 |  | 20P000024 | FALSE | CNAS | SL5 PHYSICS 1003- RENOVATION | New Faculty-Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 1003 | COMPLETE | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43664 | clean out the space | 43843 | 43889 |  |  |  | 3/25/20, DL: This project is complete……2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: The paint is complete and the floor covering should be delivered this week. Once the floor covering is on site, we will schedule the installation……………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We started this project and should be complete in the next 6- weeks……….11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: David who is responsible for clearing out the space is in the process. Once the space is empty we will schedule the work. We will probably start the physical project shortly after Thanksgiving…….10/30/19, DL; We are planning to start this project within the next 6-8 weeks……. | 2019-10-16 | Enrico Baez | Test for ACM and or other hazardous materials in the room. Replace all existing flooring, remove power pole and miscellaneous wall mounted items shelving/racks, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks) and repair/replace top & bottom flush bolts, install new door closer(s), relamp with LED as needed. Replace faucet, clean sink/counter and infill pit. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000207 |  | 20P000207 | FALSE | CNAS | SL5 PHYSICS 3033 - PAINT & PATCH STAFF OFFICE |  | PHYSICS | 3033 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO | DAVID NEFF | Paul Ditty |  | 3 |  | FALSE |  |  | 43773 | [6 empty] | 03/02/20 O-ANS: Completed per Paul Ditty as of 02/04/20. |  | Paul Ditty |  |  | 2020-02-04 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000235 |  | 20P000235 | FALSE | CNAS | SL5 SKYE 374 - PATCH AND PAINT |  | SKYE HALL | 374 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 4 |  | TRUE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000688 |  | 19P000688 | FALSE | CNAS | SL5 PHYSICS- RENOVATION OF THREE PHYSICS ROOMS | Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 2128 | COMPLETE | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43644 | finish abatment | 43774 | 43814 |  |  |  | 1/14/20, DL: This Project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 99% Complete. Custodial will be there this week to complete the final clean. The space will be ready for occupancy starting 1/6/19…..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: The project is on track to be complete on 12/13/19. Once the abatement is complete, we will start the wall repair as the walls are severely damaged from the previous use of the space……10/30/19, DL: WE are working on this project. Our target date for completion is 12/17/19………… | 2019-10-16 | Enrico Baez | Test for ACM and or other hazardous materials in the room. RM 2124, 2128 & 2132: Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2128 Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2132: Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000508 |  | 19P000508 | FALSE | CNAS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | BOYCE | 3410 | COMPLETE | Kathryn Uhrich | Jose Wudka | CHERYL GERRY |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43517 |  | 43773 | 43805 |  |  |  | 1/30/20, DL: Project is now cxomplete. The electrical panel cover was installed this morning…………. 11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: We are not complete. We still need to complete the following items; Light bulbs, electrical panel cover, replace ACM ceiling tiles and deep clean the space…..10/30/19, DL: Progress is in progress. We should be done within two weeks…….10/16/19, DL; Paint is in progress and additional work to follow. Target date for complete is 11/19/19…..10/1/19, DL; Jess to survey space for ACM, Lead paint, etc… We will schedule work once we have confirmation from Jess….. | 2019-09-30 | Enrico Baez | ……….Remove lower base cabinets and upper cabinet in room 3410B. Repair delaminated flooring between room 3410 & 3426, Patch and Paint entire rooms 3410, 3410B & 3426 up to 8'H(no paint in in 3410 A&C). Repair damaged floor tiles in room 3410 A&B. Repace all burned out lamps w/ LED throughout labs and office. Strip & wax all floors in labs space. Remove cylinder racks in room 3410B. Fabricate a hinged metal door to cover the electrical panel in roon 3426 (panel is near door). | YES | 2020-01-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000267 |  | 20P000267 | FALSE | CNAS | SL5 GEOLOGY 2460C - PATCH & PAINT |  | GEOLOGY | 2460C | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 4 |  | FALSE |  |  | 43818 | [8 empty] | Paul Ditty | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/04/20. |  | 2020-03-04 | Spring 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | COMPLETE | Kathryn Uhrich | Jose Wudka | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 43332 | Work will be complete in 2 weeks | 43864 | 43903 |  |  |  | 8/5/20, DL: This project is complete……………..06/17/20, DL: This project should be complete with in the next two weeks……..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within two weeks. Once we have a contract, we will schedule the work……….1/15/20 O-DH: Emailed Status Report to customer……1/14/20, DL: Contracts is currently working on the contract. Once the contract is complete, we will order the material and schedule the work…………11/26/19, DL: Plans were approved. We will work on the construction contract. Once we have the notice to proceed, we will schedule the work……….10/15/19, DL: Sent PD&C and follow-up email on 11/11/19. We should have approved plans in the near future……10/30/19, DL: Sent PD&C an email asking for a status update on 10.30.19…… 10/16/19, DL; Plans are still in plan check. I sent the building official an email asking if any additional information is needed. This work will be completed by a contractor which means we need to allow time for the bid and contract process……… …………9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Enrico Baez | Request for Estimate to install three new FOB readers with electrified locksets. Work covered: Install one AC Fob Reader at door 2221 and one AC Fob reader at each Door 4231 & 4235. Connect card readers to the existing Hirsh ACP located in the IDF closet at each floor. 03/07/19: Scope revised to eliminate two FOB readers. Install one FOB reader at Genomics door 4231 only instead of all three rooms. | YES | 2020-08-05 | Fall 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 20-21
20P000236 |  | 20P000236 | FALSE | CNAS | SL5 SKYE 368 - PATCH AND PAINT |  | SKYE HALL | 368 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 5 |  | TRUE |  |  | 43794 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000019 |  | 20P000019 | FALSE | CNAS | SL5 PHYSICS 2029A- NEW EYEWASH STATION | PHYSICS 2029A- INSTALL A NEW EYEWASH STATION | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43662 | order material | 43889 | 43917 |  |  |  | 2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL; Permit was approved, we need to order material and schedule the work………. | 2019-11-27 | Enrico Baez | Install new eyewashing station | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000268 |  | 20P000268 | FALSE | CNAS | SL5 GEOLOGY 2460D - PATCH & PAINT |  | GEOLOGY | 2460D | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 5 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | Paul Ditty |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000615 |  | 19P000615 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT |  | COLL BLDG NO | 203 AND 204 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43599 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000523 |  | 19P000523 | FALSE | CNAS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | PATCH & PAINT GRAD STUDENT OFFICE | SPIETH | 3366 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Paul Ditty |  | 5 | 9 | FALSE |  |  | 43536 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-20 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000121 |  | 20P000121 | FALSE | CNAS | SL5 SKYE 217 - PATCH AND PAINT |  | SKYE HALL | 217 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43713 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000247 |  | 20P000247 | FALSE | CNAS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | Refresh Lab: Patch paint, strip & clean floor, repair broken ceiling and floor (VCT) tiles at room 2110 & 2118. Install Electrical power & Co2 cylinder racks at each end of workbench/tables | SPIETH | 2110 + 2118 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | Dan Lerman |  | 6 |  | TRUE |  |  | 43796 | [6 empty] | 1/19/21, DL: This project is complete…………..9/30/20, DL: This project is in progress and will be compete in the next 6- 8 weeks……………8/5/20, DL: We will start on this project in the next 6-8 weeks….. | 2020-04-17 | Enrico Baez | Spieth 2110: Carpentry: Seismic anchoring for “New” tables and equipment. Replace damaged ceiling tiles. Install misc. wall mounted items. Sheet Metal: Remove “existing” steel cage. Fabricate & install metal cylinder rack w/ restrains/seismic anchoring to floor. Plumbing: Install Co2 POC for gas cylinders at four (4ea) new free-standing work benches (see configuration on this document). Electrical: Install dedicated *120v power drop & connect to the existing power strips built-in the four (4ea) new workstation tables (see configuration on this document). *VERIFY/CONFIRM VOLTAGE W/ D. MCW. Relamp fixtures as needed. Spieth 2118 & 2110: Sheetmetal: Clean and or replace air distribution grilles. Flooring: Repair/patch broken floor tile and Replace broken ceiling tiles (abate floor tiles if required). Painting: Paint and patch all walls, verify recondition doors @ room side. Plumbing: Assess sinks to be fully operational & clean. *Replace sink in Rm 2118 for glassware, confirm with Faculty/Estella. Replace sink in room 2118 (Sink type TBD by Faculty). HVAC: Check lab air pressure is operational & proper pressure. Custodial: Strip and Wax floor, clean interior windows, wipe down doors and windowsills. EXCLUSIONS: Furnish, assemble, and install new workstations, tables or lab equipment. Removal of existing lab furniture or equipment. Natural gas or air output taps not required (per Faculty). | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000269 |  | 20P000269 | FALSE | CNAS | SL5 GEOLOGY 2460E - PATCH & PAINT |  | GEOLOGY | 2460E | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 6 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/05/20. |  | Paul Ditty |  |  | 2020-03-05 | Spring 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000023 |  | 20P000023 | FALSE | CNAS | SL5 PIERCE RM 1144 - PATCH AND PAINT DOOR WHERE WALL POCKET WAS |  | PIERCE | 1144 | COMPLETE | Kathryn Uhrich | Jose Wudka | JACQUELINE |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43664 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GH08 | 881 | COMPLETE | Kathryn Uhrich | Jose Wudka | NANCY FERGUSON |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43494 | Schedule the work. | [5 empty] | 1/19/21, DL: This project is complete……………8/5/20, DL: This project is in Progress and should be complete in the next 8-12 weeks…………….3/25/20, DL: Work orders are produced. Once we are back to work, we will schedule the work………12/11/19 O-ANS: Re-assigned as project allotment - priority #7 for Winter 2020. 11/27/19 O-ANS: Hold by client for re-prioritization for Winter 2020. | 2020-03-04 | Enrico Baez | Install new 3 ton Packaged unit with heat pump and dedicated electrical service on the roof top. Provide 1ea return plenum, 2ea supply drops in the work space. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000270 |  | 20P000270 | FALSE | CNAS | SL5 GEOLOGY 2460F - PATCH & PAINT |  | GEOLOGY | 2460F | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 7 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | Paul Ditty |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000113 |  | 20P000113 | FALSE | CNAS | SL5 GEOLOGY 2258 - PATCHPAINT RECEPTION WALL OVER BIN REMOVED |  | GEOLOGY | 2258 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 43712 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000271 |  | 20P000271 | FALSE | CNAS | SL5 GEOLOGY 2460G - PATCH & PAINT |  | GEOLOGY | 2460G | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 8 |  | FALSE |  |  | 43818 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/06/20. |  | Paul Ditty |  |  | 2020-03-06 | Spring 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000155 |  | 20P000155 | FALSE | CNAS | SL5 BOYCE 3407 - PAINT OFFICE FOR NEW FACULTY |  | BOYCE | 3407 | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | TRUE |  |  | 43739 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/30/20 |  | Paul Ditty |  |  | 2020-01-30 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
18P000465 |  | 18P000465 | FALSE | CNAS | SL 5 GEOLOGY 2258B AND 2258C - PATCH/PAINT |  | GEOLOGY | 2258B & 2258C | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 43257 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
19P000377 |  | 19P000377 | FALSE | CNAS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | Replace the gates on the Schneider House driveway, which secure the property, with the taller iron gates that used to be installed at the Gardens entrance. This will require new fence posts and hinges as well. The taller gates are stored along the side of the garage at Schneider House, and Facilities staff can come see them anytime. Please note this is a safety and security project. | BOT GDN HSE |  | COMPLETE | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Dan Lerman |  | R2 | 117 | FALSE |  |  | 43412 | PO#, schedule the work | 43787 | 43797 |  |  |  | 11/26/19, D: This Project is 100% Complete……………11/19/19 DH: Emailed Status Report to customer….11/15/19, DL: We should have A PO this week. Once we have the PO#, we will schedule the work……10/30/19, DL: Project was approved by customer with an FAU #. I will work on providing a PO# as this is maintenance and schedule the work. | 2019-04-05 | Enrico Baez | Replace Gates with new refurbished & modified gates furnished by BG. Install new steel posts and strip and repaint gates. Gate style revised by customer to purchase vendor fabricated light gauge meta gates without spike, per Jodie Holt 10/09/19. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20 | 1
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | R3 |  | TRUE |  |  | 43550 | Schedule the work | 43861 | 43882 |  |  |  | 8/5/20, DL: This Project is COMPLETE…….3/25/20, DL: The material is here and we are 95% complete with the work. We will complete the work when we return from the campus closure…………1/31/20 O-DHN: Emailed Status Report to customer…….1/30/20,DL: The pump is now on site but we are still waiting for the fittings. In the mean time, our plumber is putting everything together and is working on the installation. Once the fittings arrive, we will make the connections and the system should be good to go………….1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: The pump is scheduled to arrive on or before 1/31/20. We will schedule the work once we have the pump and material on site…..11/26/19, DL; Emailed Natalie and Sherice the quote for the vacuum pump. We will order the material and schedule the work once we have approval and the pump on site……11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: I sent the vendor a 2nd email requesting an update on the proposal. I also included Natalie on the email so she is aware of where we stand with the proposal……10/30/19, DL: We had a followup meeting with the vendor last week. The vendor is now working on a pump that will best meet our needs……….10/16/19, DL; We are working with a vendor on a quote for a new lab vacuum pump. We are hoping to have a quote in the next week or two…..9/16/19, DL; Estimate was provided to customer last week. If the project is approved, we will work on the plans and permits. Once approved, we will schedule the work…… |  | Enrico Baez | Old SOW Revised SOWInstall exhaust hood, electical receptacle, vacuum pump, vac lines and valves (six valves total) and hood location. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21 | 1
19P000517 |  | 19P000517 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | COMPLETE | LaRae Lundgren | Emily Engelschall, Sean Cason | DANIELLE GARCIA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43531 | Verify scope and schedule work | 43801 | 44185 |  |  |  | 1/19/21, DL: This project is complete…………..8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced, We will schedule the work when we return from the campus closure…………11/11/19, DL: I will work on scheduling this project… | 2019-06-17 | Enrico Baez | 6/17/19 E. Baez Conducted site visit with Sean. Will need carpenters to mount TV and electricians to add outlet to North wall. Data not needed. Might need painters depending on how carpenters install TV mount. | YES | 2021-01-19 | FALL 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43487 | finish plans/submit application | 43840 | 43917 |  |  |  | 8/5/20, DL: This Project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer…..2/18/20, DL: We are making great progress and still on schedule to be complete before Spring Break begins. We pass drywall inspection on 2/18/20………..1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: Plans are approved. All items have been removed from the space. Abatement is schedule to take place within two weeks…..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were submitted for plan check review. Fire marshal stamped the plans, we are waiting on the final stamp from our building official. Once plans are approved we will order material and schedule the work……..10/30/19, DL: Gunter is working on plans. We are planning to complete the work before Spring Quarter begins. |  | Dan Lerman |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
19P000467 |  | 19P000467 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | WATKINS | 2101 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 43487 | Finish project. | 43739 | 43819 |  |  |  | 1/14/20, DL: This project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Project is 99.9% complete. We should be complete with the work by this Friday. Furniture is scheduled to be install this Friday morning……..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL; The project is still on schedule to be completed on 12/12/19…………….10/30/19, DL: This Project is on Schedule to be completed on or before 12/17/19….10/16/19, DL; This project is in progress with a completion date of 12/15/19…….10/1/19, DL; We will schedule the work. Our portion of the project will be completed mid December……….9/16/19, DL; We will work on the plans soon. This project will be complete by 12/21/19….. 09/03/19 O-ANS: Updated Priority to #1 for Fall 2019 per Susan request. 9/3/19, We are scheduled to complete the work before winter break begins….. |  | Enrico Baez |  |  | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000085 |  | 20P000085 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 FACILITES ANNEX B - PAINT OFFICE SPACE |  | CUST AND GRD | 0001 | COMPLETE | Susan Marshburn | Da Lan Dinh | SANDRA MARTINEZ |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 43696 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000560 |  | 19P000560 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION |  | UV BLDG B | 0240B | COMPLETE | Susan Marshburn | Da Lan Dinh | LESLIE ROSE |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43559 | waiting for material to arrive | 43678 | 43700 |  |  |  | 9/3/19, DL; This project is 100% complete. We still need to conduct training but the work is complete and training is scheduled…..8/15/19, DL; This Project is 90% Complete and will be complete by the end of the week. Please note. ITS still needs to connect the data lines. Our portion of the work is complete………8/1/19, DL; Plans are approved. Material is ordered. We will schedule the work when the material is on site…. |  | Dan Lerman |  |  | 2019-09-03 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
19P000572 |  | 19P000572 | FALSE | GRAD DIV | SL5 PATCH, PAINT, AND CARPET UOB 152 |  | UNIV OFC BLD | 152 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43566 | Awaiting installation of carpet | [5 empty] | 06/28/19 O-ANS: Paint phase complete and awaiting carpet change. |  |  |  |  | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000031 |  | 20P000031 | FALSE | GSOE | SL5 SPROUL HALL 1124B- PATCH/PAINT OFFICE |  | SPROUL | 1124B | COMPLETE | Thomas Smith | Sally Tavizon | MARICELA ARCINIEGA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43668 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000628 |  | 19P000628 | FALSE | GSOE | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2129 | COMPLETE | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43600 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000077 |  | 20P000077 | FALSE | GSOE | SL5 SPROUL HALL 1223 - PATCH AND PAINT |  | SPROUL | 1223 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43683 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-25 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | C&C CARPORT | 161 | COMPLETE | Danna Gianforte | Shelley Gupta | SHELLEY GUPTA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43472 | Waiting for bid for customer. | 43850 | 43921 |  |  |  | 8/5/20, DL: This Project is complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have the contract, we will schedule the work……………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Project was approved by Shelley. We will work on the contract. Once we have the notice to proceed from contracts, we will order the material and schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Sent Shelley another follow-up email today and she has not verified if she would like to move forward with the project………10/30/19, DL: Sent Shelley the updated quote last week and she has not responded. I sent Shelley a followup email today asking her to let me know if she would like to proceed with the work……..10/16/19, DL; Had a meeting with Shelley, we modified the scope of work and software for the project. We are now revising the quote with our vendor. We should have an updated quote within the next two weeks. If Shelley approves the work and scope, we will proceed….10/1/19, DL; I have a meeting with Shelley this afternoon to review proposal. If she approves the project we will submit plans for a building permit……8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was cancelled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; We have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28/19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21 | 1
19P000209 |  | 19P000209 | FALSE | PB&A | SL5 OLD EH&S SITE- FS ANNEX A REMODEL |  | ENV HLTHSFTY | 100 | COMPLETE | Gerry Bomotti | TBD | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 43336 | Schedule the work | 43601 | 43644 |  |  |  | 7/1/19, DL; This project is 100% Complte….6/17/19, DL; This project is almost complete. Target complete date is 6/26………….5/31/19, DL; This project is in progress. Our goal is to have the projected completed by June 28th……. 5/15/19, DL; We are schedule to start the demo tomorrow. Project timeline is 3-4 weeks….3/28/19, DL; Gunther is working on plans……3/18/19, DL; Conducted site visit with Chris, Hassan and Francis last week. We will work on plans and permits…….9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000158 |  | 20P000158 | FALSE | PB&A | SL5 FS ADMIN OFFICE - TOUCH-UP PAINT AROUND BUILDING |  | CORP B |  | COMPLETE | Gerry Bomotti | TBD | DA LAN DINH |  | Paul Ditty |  | - |  | FALSE |  |  | 43741 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000083 |  | 20P000083 | FALSE | PB&A | SL5 STUDENT SERVICES - INSTALL 8 CUBICLES - CP00003537 | Installation of BKM Cubicles with electric and Data | STUDENT SERV | 3rd Floor | COMPLETE | Gerry Bomotti | TBD | SHARYL MURDOCK |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43641 | We are on schedule | 43815 | 43831 |  |  |  | 1/14/20, DL: This project is 100% Complete………..11/18/19 DH: Emailed Status Report to customer…..10/30/19, DL: The plans were approved and we are scheduled to do the work in December…………10/16/19, DL: Plans were submitted this week…….. |  | Enrico Baez | Scope completed by Dan Lerman | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000414 |  | 19P000414 | FALSE | PB&A | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | Seth Morrison |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43451 | pending material delivery | 43754 | 43796 |  |  |  | 8/5/20, DL: This Project is Complete………….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: We have the motor on site, we are working on the permit for the crane. Once we have the crane lift permit, we will schedule the install…………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: We are working on the new motor platform. It is our goal to install the new motor in late January. Once the motor is installed, we will be able to identify if additional work is needed…….11/19/19 DH: Emailed Status Report to customer…..11/15/19, DL: Material has not arrived……..10/30/19, DL: The new exhaust fan is ordered with a 2- 4 lead time. Once the exhaust fan arrives, we will schedule the install……….10/16/19, DL; We are in the process of the work. At this current time, we are not modifying the building to where permits may not be required…….10/1/19, DL; This is in the queue for plans, we will start the plans in the next 3-4 weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2018 | 2021-03-01 | FY 20-21
20P000008 |  | 20P000008 | FALSE | PB&A | SL5 EHS 1133 - PATCH / PAINT AND FIX HOLES IN WALLS |  | ENV HLTHSFTY | 1133 | COMPLETE | Gerry Bomotti | TBD | CESAR PLA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43654 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-07 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000665 |  | 19P000665 | FALSE | PB&A | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | Existing telephone-communications building on University Ave requires repairs and renovation in preparation for new use as fire safety offices. | TELEPHONE |  | COMPLETE | Gerry Bomotti | TBD | Carmen Long | Melissa Garrety | Dan Lerman |  | 2 |  | FALSE |  |  | 43649 | tape, mud, prime&Paint | 43691 | 43847 |  |  |  | 2/19/20; This project is complete. We still need to paint the door black but this was not part of the original scope. The paint shop will paint the door in the next two weeks………… 1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL:. This project is 99.9% complete with a few minor punch list items…..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project is on track to finish before the new year with a punch items to be addressed after the new year. IT services still needs to install data and phone. Landscape services is working on the landscape but the landscape was not part of the original scope. Sharyl in is the process of coordinating keys, alarm code and setting up the delivery of the furniture for her team. Overall, we are all in good shape.…….11/19/19 DH: Emailed Status Report to customer…..11/11/19,DL: This project is still on schedule to be complete before the new year……….10/30/19, DL: This project is in progress and on track to be complete before the new year…………….10/16/19, DL: Drain, waste, vent and concrete is complete. We started framing this week. We will start rough electrical and rough plumbing next week……..9/3/19, DL; Abatement was complete this weekend. Trades are scheduled and we are on track for 11/15/19 completion date…..8/15/19, DL Plans were approved this week. Abatement is still needed and the 14- day notification to AQMD is complete. We are on track to complete the work by mid November……. |  | Enrico Baez |  |  | 2020-02-19 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000037 |  | 20P000037 | FALSE | PB&A | SL5 FAC ADMINISTRATION -PAINT WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 43669 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
19P000535 |  | 19P000535 | FALSE | PB&A | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV | Install TV Mount and additional electrical | BANNOCK H | H0108 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43538 | [7 empty] | 2019-07-08 | Enrico Baez | Install TV Mount and additional electrical | YES | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
19P000687 |  | 19P000687 | FALSE | PB&A | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | COMPLETE | Gerry Bomotti | TBD | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 43642 | plan check review | [5 empty] | 8/5/20, DL This Project is Complete……………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Contracts is processing the contract. Once the contract is complete, we will schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Plans were approved. I sent Brendan an email 11/11/19 requesting an FAU # as this is Recharge work. Once we have the FAU #, we will work on the contract agreement with the contractor………10/30/19, DL; Sent Lezlie and email asking if she has an update on the resubmitted plans on 10/30/19………..10/16/19, DL; The plans were resubmitted for plan check review this week. We are hopeful the plans will be approved this week. Once approved we will work on contract and scheduling the work…10/7/19 LB: This is a test. The timestamp will be reset when the test is done. 10/1/19, DL: We are working on plan check review. We should have approved plans in the next two weeks…..8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | Provide estimate to install key card access control |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21 | 1
19P000599 |  | 19P000599 | FALSE | PB&A | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 43594 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000127 |  | 20P000127 | FALSE | PB&A | SL5 FALKIRK APARTMENTS EMERGENCY EGRESS |  | FALKIRK 1 | 10E | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 43721 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000114 |  | 20P000114 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER DOOR, BASEBOARD, AND BRACKETS |  | PENTLAND A |  | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000115 |  | 20P000115 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 1 - BALCONY COSMETIC REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R2 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000205 |  | 20P000205 | FALSE | PB&A | SL5 THE PLAZA 12 & 14 - EMERGENCY DECK REPAIR | Deck repair | THE PLAZA | A0012 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R2 |  | FALSE |  |  | 43770 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000223 |  | 20P000223 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER PAN REPLACEMENTS | Shower Pan replacement | PENTLAND A | A238, B245, B325, C215, F325 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R3 |  | FALSE |  |  | 43784 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Sep 2019. |  | John Peraino |  |  | 2019-09-01 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000116 |  | 20P000116 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 5 - BALCONY EMERGENCY REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R3 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000117 |  | 20P000117 | FALSE | PB&A | SL5 PENTLAND HILLS A-H - LATTICE REBUILD |  | PENTLAND A | A-H | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R4 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000243 |  | 20P000243 | FALSE | PB&A | SL5 ALUMNI CENTER - HYDRATION STATION INSTALL | Install hydration station | ALUM VISITOR | FIRST FLOOR | COMPLETE | Gerry Bomotti | TBD | LESLIE ANN GERRETSE |  | John Peraino |  | R4 |  | FALSE |  |  | 43785 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by June 2020. |  | John Peraino |  |  | 2020-06-01 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
20P000118 |  | 20P000118 | FALSE | PB&A | SL5 FALKIRK 1, 2, & 12 - FIRST FLOOR PATIO FENCING |  | FALKIRK 1 | 1st Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R5 |  | FALSE |  |  | 43713 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20 | 1
19P000683 |  | 19P000683 | FALSE | PROVOST/EVC | SL5 PATHC/PAINTING REPAIR |  | HUM & SOC SC | 1103A | COMPLETE | Thomas Smith | Luisa Levario | JILL CANTONWINE |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43641 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000473 |  | 19P000473 | FALSE | PROVOST/EVC | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 |  | HINDERAKER | 1100 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | TORRI MCGARITY | Paul Ditty |  | 1 |  | FALSE |  |  | 43494 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-28 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000434 |  | 19P000434 | FALSE | PROVOST/EVC | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | Please patch 50 plus holes on the wall and repaint that wall in Skye hall 136 due to the BKM removing the furniture attached to the wall. Please call Anita Ortiz if you have any questions at x2-5229. Shanshan's extension x7753 has not been moved to her new location yet. | SKYE HALL | 136 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | SHANSHAN | Paul Ditty |  | 2 |  | FALSE |  |  | 43472 | [6 empty] | 07/20/19 O-ANS: Work Complete per Paul Ditty. |  | Paul Ditty |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
18P000351 |  | 18P000351 | FALSE | SoB | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 1 (N) | 21 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 43178 |  | 43654 |  |  |  |  | 8/1/19, DL; This project is 100% Complete……7/15/19, DL; Work has started and should be complete on 7/16/19…….. 4/4/19 O-ANS: Moved to Queue to Start to complete during Summer 2019. DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week……8/8/18. The trades are ready to go after they finish current projects…..DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18………. DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date……..9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space……Note. The space is usable and everything works….. |  | Enrico Baez |  | YES | 2019-08-01 | Spring 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000151 |  | 20P000151 | FALSE | SoB | SL5 ANDERSON HALL NO 113 - PATCH/PAINT HOLES |  | ANDERSON 1 (N) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43738 | [6 empty] | 03/02/20 O-ANS: Project complete per Paul Ditty as of 02/07/20. |  | Paul Ditty |  |  | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000521 |  | 19P000521 | FALSE | SoB | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT |  | ANDERSON 1 (N) | 138 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43532 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000193 |  | 20P000193 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 0001A | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43761 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/02/20 |  | Paul Ditty |  |  | 2020-01-02 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000152 |  | 20P000152 | FALSE | SOM | SL5 SOME 2669 - PATCH & PAINT |  | SOM EDUC | 2669 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | TRACEY TRETTIN | Paul Ditty |  | - |  | FALSE |  |  | 43738 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000660 |  | 19P000660 | FALSE | SOM | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SL5 SOME RB, RM 330- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43627 | [6 empty] | 9/30/20, DL: This Project is Complete………..8/5/20, DL: Dan to follow-up with customer…………..03/05/20 O-ANS: Removed room 330 per client request. Only updates to 107 & 111. |  | Enrico Baez | TBD | NO | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000054 |  | 20P000054 | FALSE | SOM | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOMED-SOME G0600, G0621 & 1682B- ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43677 | [6 empty] | 9/30/20, DL: This Project is Complete…………..8/5/20, DL, Dan to follow-up with customer………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "Remove status Hold / Update project detail to include information on 1682B -ADD ELECTRICAL, PAINT/PATCH, AND RELOCATE WHITE BOARD." |  | Enrico Baez | Room G0600 Install Power behind and below the TV, install one TV Bracket, install one cut-in back box below the TV for data(data cabling by ITS), Paint the entire East wall to match existing. Room G0621 Insatll three(3) new double duplex receptacles and three(3) data back boxes only(no data cabling) in room G0621. Install SS tubing for Co2 from room G0621 to room G0623. Include Valves at both ends of P.O.C., Install one uni-strut siesmic cylinder support at the south wall. Steve Burleson has walked the site and has knowledge of the SOW. Loading Dock Install Pole & chains at Loading dock. |  | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
19P000661 |  | 19P000661 | FALSE | SOM | SL5 SOM RB, CR0600- FY 19/20 PROJECT- PATCH & PAINT |  | SOM EDUC | CR0600 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43627 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000060 |  | 20P000060 | FALSE | SOM | SL5 WEBBER HALL 1274- PATCH & PAINT OFFICE |  | WEBBER | 1274 | COMPLETE | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43682 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-28 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000666 |  | 19P000666 | FALSE | SOM | SL5 WEBBER, ROOM 1237- PATCH AND PAINT | TBD - SOM RM 107, 111 & 330- PROJECT: NEW PI, EQUIPMENT INSTALL | WEBBER | 1237 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 43633 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-11 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000245 |  | 19P000245 | FALSE | SOM | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY |  | SOM RSCH |  | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43350 | Plans are approved | 43619 | 43644 |  |  |  | 7/1/19, DL; This project is 100% Complete…..6/171/19, DL; Material is on site. Project should be complete in the next two weeks……..5/31/19, DL; Contracts is working on the contract. We should have a notice to proceed in the next two weeks. The project will be complete with in 30- from when we receive the notice to proceed……5/15/19, DL;, Plans were approved. I am working with PD&C on the contract. Once the contract is complete, we will schedule the work……3/28/19, DL; Plans were submitted and pending review and approval….. | 2018-10-29 | Enrico Baez | Install ADA complian auto door operator, push plates and electrified panic hardware. Auto operator will be outsourced through Capitol door. FS lock shop will perform acess control wiring. Electrical shop to provide a dedicated circuit for the auto door operator. | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 19-20
20P000051 |  | 20P000051 | FALSE | SOM | SL5 SOMED 2611 - PATCH & PAINT |  | SOM EDUC | 2611 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 5 |  | FALSE |  |  | 43677 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000150 |  | 20P000150 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 207 |  | UNIV OFC BLD | 207 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000149 |  | 20P000149 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 242 |  | UNIV OFC BLD | 242 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 43733 | [8 empty] | Paul Ditty |  |  | 2019-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000026 |  | 20P000026 | FALSE | VC-RED | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | Install T-bar ceiling, Provide HVAC and Fire sprinklers drops. Install new 2x4 LED light fixtures | LIFE SCIENCE | Basement Level | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43665 | Work on Plans and permits. | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: The plans were submitted two weeks ago. We should receive the plan check review comments in the near future…………….8/5/20, DL: This Project will exceed $50,000. Monty A. will inform customer this is a project that will need to be managerd through PD&C……………3/25/20, DL: We will work on plans when we return back from the campus closure. | 2020-01-31 | Enrico Baez | Install T-bar ceiling with wipable(coated) ceiling tile. Provide HVAC and new Fire sprinklers drops to new ceiling. Install new 2x4 LED light fixtures. Verify Fire alarm systems work. | YES | 2021-01-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
20P000230 |  | 20P000230 | FALSE | VC-RED | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | Install Ceilings, Widen Door & Extend Utilities | BOURNS | B116C & B116D | COMPLETE | Rodolfo Torres | Laura Manor | KRASSIMIR BOZHILOV | LAURA MANOR | Dan Lerman |  | 1 |  | FALSE |  |  | 43787 | finish plans for building permit | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: This project is in progress and 50% complete. We should be complete with in the next 4-6 weeks…………...8/5/20, DL: We will submit plans in the next week………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We will start working on the plans and apply for a building permit in the next 2-3 weeks. | 2020-01-23 | Enrico Baez | Install new T-bar ceilings, lighting/switches, verify electrical service/disconnect. Relocate the existing eye washer, widen the exiting door opening and *reverse swing(*if approved by F.M). Install one customer furnished transformer. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
19P000553 |  | 19P000553 | FALSE | VC-RED | SL5 SPIETH HALL PATCH AND PAINT |  | SPIETH | 341 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43556 | [6 empty] | 07/26/19 O-ANS: Project Complete per Paul Ditty. |  |  |  |  | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000495 |  | 19P000495 | FALSE | VC-RED | SL5 UOB RM 209- PATCH & PAINT |  | UNIV OFC BLD | 209 | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  | 2 |  | FALSE |  |  | 43504 | [6 empty] | 07/30/19 O-ANS: Project closed per Paul Ditty. 07/30/19 D-MMN: Moved furniture and filled holes. Taped base and fixtures. Primed and painted one half of office. Pulled tape replaced plates and moved furniture to other side. Removed plates taped base and fixtures. Primed and painted other half. Used spray texture on patch under window. Pulled masking. Replaced plates. Moved furniture back. Vacuumed carpet during and after total process. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000045 |  | 20P000045 | FALSE | VC-RED | SL5 MRB SOUND BOOTH |  | MRB | 2210 & 2204 | COMPLETE | Rodolfo Torres | Laura Manor | DAN LERMAN |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43676 | Inspection | 43739 | 43776 |  |  |  | 11/11/19, DL: This project is complete…….10/30/19, DL: This project is complete but we need to conduct the final inspection with the building official………..10/16/19, DL: The plans are approved and the work is complete. I need to field verify and schedule the inspection. |  | Enrico Baez | Contact PM for SOW. | NO | 2019-11-11 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
21P000102 |  | 21P000102 | FALSE | VC-RED | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | AAALAC Certification updates to rooms 348, 352 & 363 | SPIETH | 348, 352 & 363 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS | YURIDIA REYNOSO | Paul Ditty |  | TBD |  | FALSE |  |  | 44133 | [6 empty] | 12/08/20 O-ANS: Customer Dierk Biggs confirmed via email that these room updates are complete. |  | Paul Ditty |  |  | 2020-12-08 | Winter 2021 | FS | FALSE | 2020 | 2021-03-01 | FY 20-21
20P000157 |  | 20P000157 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BUILDING - HOLES NEED PATCH AND PAINT |  | HEALTH SERV | 325 | COMPLETE | Brian Haynes | Cathy Eckman | CHRISTINA FARIA | WENDY ALEXIS | Paul Ditty |  | 1 |  | FALSE |  |  | 43740 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 01/31/20. |  | Paul Ditty |  |  | 2020-01-31 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
20P000337 |  | 20P000337 | FALSE | VC-STU AFF | SL5 HEATLH SERVICE 382 - NEED OFFICE PAINTED |  | HEALTH SERV | 382 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43853 | [6 empty] | 08/06/20 O-ANS: Complete per D-BFA on 02/11/20. |  | Paul Ditty |  |  | 2020-02-11 | Spring 2020 | FS | FALSE | 2020 | 2021-03-01 | FY 19-20
19P000455 |  | 19P000455 | FALSE | VC-STU AFF | SL5 FILL AND PAINT OVER HOLES ON WALL |  | HEALTH SERV | 100 | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 1 |  | FALSE |  |  | 43482 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/27/19 |  |  |  |  | 2019-12-27 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
18P000214 |  | 18P000214 | FALSE | VC-STU AFF | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Install Card readers | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  | 2 | 2 | FALSE |  |  | 43077 | Pending special order part | 43515 | 44075 |  |  |  | 1/19/21, DL: This project is 100% Complete…….9/30/20, DL: Vendor should have the balance of the material in the next 30- days…….8/5/20, DL: This project is complete except the card reader portion of the project…………6/17/20, DL: The floor covering was completed two weeks ago. The card reader portion of this project is 95% complete but additional parts were needed and they are on order. Once they arrive, we will schedule the installation and this project will be 100% Complete………1/15/20 Emailed Status Report to customer…..1/14/20, DL: We were recently approved to proceed with the work. I have reached out to the vendor for the doors and card access. We are still waiting to hear back from them so we can order the material and schedule the work. I communicated with Nicole on the floor covering replacement. Nicole needs to verify what areas we will replace as we were going to complete several offices and a hallway as part of the scope but this will displace many team members for at least a week. We will work on scheduling the work once Nicole gets back to me……..12/17/19 - O-DHN: Emailed Status Report to Customer……12/19/19, DL; We are working with our contractor to order the material and schedule the work. Once we have confirmation on the material, we will be able to schedule the work. It Is our goal to start this project in late January……11/26/19, DL: This project was taken off of on hold and we can now proceed. I contacted the contractor last week and I am awaiting their response on when they can schedule the work. I also left a message with them this morning………..7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once material arrives, we will schedule the installation.….5/31/19, DL; Contract is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is completed except the floor covering and electronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being prepped for paint. We have a pre-construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, material is ordered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct site visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez |  | YES | 2021-01-19 | Winter 2018 | FS | FALSE | 2017 | 2021-03-01 | FY 20-21
19P000483 |  | 19P000483 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED |  | HEALTH SERV | 404, 407, 412, 405 & 411 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 43497 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-11-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
19P000564 |  | 19P000564 | FALSE | VC-UNIV ADV | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | 1156C (AVC Johnny Cruz) – Patch molly holes, touch-up paint. 1156A (Jules Bernstein) – Remove (2) black & white photos from wall. Patch molly holes, touch-up paint. 1156B – Install picture frame (UCR campus map) onto wall. Suite 1159 – Patch holes. Remove film reels. Paint one accent wall “UCR Blue”. 1159B (Christy Zwicke) - Patch molly holes, touch-up paint. | HINDERAKER | 1156 | COMPLETE | Peter Hayashida | Naysia Caldwell | Lisa Cusick | Christy Zwicke | Paul Ditty |  | 1 |  | FALSE |  |  | 43563 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-07 | Summer 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
3557 | 3557 |  | FALSE | CHASS | Campus Sculpture Installation | We will bring 5 sculptures to campus that will go in public places that have already been identified by Uma Ramasubramanian and Jacqueline Norman . Please construct 5 concrete plinths at various locations around campus. Locations are on the attachment. |  |  | Construction | Juliet McMullin | Cindy Williams | Emily Rankin |  | Tameesha Hayes | 3 |  |  | FALSE | 82000 |  | 43796 | Complete Construction | 44105 | 44256 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | Design | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 6950000 |  | 43528 | Construction | 44378 | 45047 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 19 |  |  | FALSE | 315000 |  | 43312 | Bidding | 44348 | 44409 | [10 empty] | PD&C | FALSE | 2018 | 2021-03-01
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Design | Gerry Bomotti | TBD |  |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Bidding | [12 empty] | PD&C | FALSE | 1900 | 2021-03-01
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 44096 | Bidding | 44378 | 44470 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-01
3524 | 3524 |  | FALSE | VC-STU AFF | Student Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | STUDENT SERV |  | Design | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE | 450000 |  | 43571 | BKM Lead Time 10 Weeks | 44348 | 44378 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3119 | 3119 |  | FALSE | CAP PROG | Plant Growth Environment Facility | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. |  |  | Furniture/Equipment | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 6 |  |  | FALSE | 27425000 |  | 42515 | Equipment and Furnishing | 43617 | 44253 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-01
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT |  | SCIENCE LABORATORIES 1 | 317 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 10 |  | FALSE |  |  | 43879 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-03-01
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LABORATORIES 1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 43880 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-03-01
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SUPPORT SERVICES BUILDING | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | Emily Engelschall, Sean Cason | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 43852 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-03-01
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL BUILDING | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 43803 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | FALSE | 2019 | 2021-03-01
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES |  | UNIVERSITY OFFICE BUILDING | 200 | HOLD - FACILITIES SERVICES | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43868 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-03-01
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | In Bidding | Kathryn Uhrich | Jose Wudka | Mireya Botello Santoyo |  | Scott Donnell | 5 |  |  | FALSE | 32871.65 |  | 44026 | Construction | [12 empty] | PD&C | FALSE | 2020 | 2021-03-01
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Bidding | Kathryn Uhrich | Jose Wudka | Richard Zapien |  | Scott Donnell | 6 |  |  | FALSE |  |  | 43959 | Award Contract | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-01
3550 | 3550 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Skye Hall HVAC Replacement | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | SKYE HALL |  | In Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 1177000 |  | 43713 | Award Contract | 44317 | 44409 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | In Bidding | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 43528 | Award Contract | 44317 | 44440 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3590b | 3590b |  | FALSE | PB&A | DMFI(FY17-20) Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Bidding | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 43796 | Award Contract | 44291 | 44348 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Bidding | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 44089 | Award Contract | 44287 | 44287 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-01
3471 | 3471 |  | FALSE | VC-STU AFF | HUB Electrical Sub Meter Installation | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | In Bidding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 200000 |  | 43332 | Award Contract | 44287 | 44317 | [10 empty] | PD&C | FALSE | 2018 | 2021-03-01
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair/Replacement | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | In Bidding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 8 |  |  | FALSE |  |  | 44095 | Award Contract | [12 empty] | PD&C | FALSE | 2020 | 2021-03-01
2970c | 2970c |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Bidding (Phase 3) | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 42340 | Award Contract (Phase 3) | 44287 | 44348 | [10 empty] | PD&C | FALSE | 2015 | 2021-03-01
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | In Bidding (Re-bid) | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 3 |  |  | FALSE | 1340000 |  | 43600 | Award Contract | 44348 | 44440 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | John White |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 42725 | Complete Construction | 44197 | 44317 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-01
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Mihai Gavan | 9 |  |  | FALSE | 57950000 |  | 42887 | Complete Construction | 43770 | 44409 | [10 empty] | PD&C | FALSE | 2017 | 2021-03-01
2952 | 2952 |  | FALSE | CAP PROG | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jon Harvey |  | Gerald Caraig | 13 |  |  | FALSE | 23895000 |  | 42258 | Phase I Completion | 43467 | 44317 | [10 empty] | PD&C | FALSE | 2015 | 2021-03-01
3438 | 3438 |  | FALSE | CAP PROG | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 15 |  |  | FALSE | 88500 |  | 43334 | City to determine schedule | 44013 | [11 empty] | PD&C | FALSE | 2018 | 2021-03-01
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Tracey Kahn, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 1575000 |  | 43108 | Complete Construction | 44228 | 44409 | [10 empty] | PD&C | FALSE | 2018 | 2021-03-01
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Georgios Vidalakis |  | Scott Donnell | 8 |  |  | FALSE | 15000 |  | 44085 | Complete Construction | 44197 | 44317 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-01
3527 | 3527 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Central Utility Plant Fire Alarm | Replace aging and non-replaceable fire alarm system, and conduit. Conduit is damaged and only 10% of wiring is usable. ( fire alarm system and devices are failing and they are not supported by manufacture ) | CNTRL UTL PL |  | In Construction | Susan Marshburn | Da Lan Dinh | Ben Kochevar |  | Daneca Stevens | 4 |  |  | FALSE |  |  | 43593 | Complete Construction | 44256 | 44287 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 6 |  |  | FALSE | 600000 |  | 43634 | Complete Construction | 44166 | 44344 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3195 | 3195 |  | FALSE | FAC-PLNG-DESIGN-CONST | North District | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 4146146.55 |  | 42669 | Complete Construction | 43647 | 44409 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-01
3515c | 3515c |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Construction | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 43532 | Complete Construction | 44166 | 44348 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3610 | 3610 |  | FALSE | PB&A | Hulen Place Homeless Medical Clinic | SOM is acquiring additional space for a medical clinic to assist with the homeless population. |  |  | In Construction | Gerry Bomotti | TBD | Diana Armenta |  | Daneca Stevens | 5 |  |  | FALSE |  |  | 44110 | Complete Construction | 44256 | 44256 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-01
3501 | 3501 |  | FALSE | PB&A | DMFI(FY17-19) Watkins 1000 Lecture Hall Reno | Renovation of Watkins 1000 lecture hall, to include lighting, HVAC, flooring, paint, and seating upgrades. This requests appears as projects Q-T on the approved 2017-2019 DMFI Program list. | WATKINS |  | In Construction | Gerry Bomotti | TBD | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 750000 |  | 43528 | Complete Construction | 44013 | 44256 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3533 | 3533 |  | FALSE | PB&A | Solar Rooftop Initiative | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. | MULTIPLE BUILDINGS |  | In Construction | Gerry Bomotti | TBD | Richard Geiger |  | John Franklin | 9 |  |  | FALSE | 2165000 |  | 43619 | Complete Construction | 44105 | 44317 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3286 | 3286 |  | FALSE | PB&A | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 10 |  |  | FALSE | 3375000 |  | 42823 | Complete Construction | 44228 | 44317 | [10 empty] | PD&C | FALSE | 2017 | 2021-03-01
3597 | 3597 |  | FALSE | PB&A | Plaza F Roof Replacement | Plaza building F roof is well past its service life and is experiencing multiple leaks into the apartment spaces below. This scope of work is to replace the roof in total and repair damages observed to the apartments below as a result of roof leaks. REQUESTING JOHN FRANKLIN AS THE PROJECT MANAGER. |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 18 |  |  | FALSE | 250000 |  | 43999 | Complete Construction | 44228 | 44287 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-01
3490 | 3490 |  | FALSE | PB&A | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | Parking Lot 13 |  | In Construction | Gerry Bomotti | TBD | Irma Henderson |  | D.Hecht/J.Franklin | 25 |  |  | FALSE | 31844000 |  | 43440 | Complete Construction | 43862 | 44317 | [10 empty] | PD&C | FALSE | 2018 | 2021-03-01
9062 | 9062 |  | FALSE | PB&A | DM(FY20) Life Sci Sewer line |  |  |  | In Construction | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 116000 |  | 44089 | Complete Construction | 44256 | 44256 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-01
3603 | 3603 |  | FALSE | SOM | Orbach Libr SOM CSSS AV Equipment | AV for CSSS project - 954044 / re: Fernando Cortez. Please refer to MSRIV in the line reference field for the draw down. |  |  | In Construction | Deborah Deas | Deborah Trujillo | Deborah Trujillo |  | Fernando Canon | 1 |  |  | FALSE | 1652000 |  | 44039 | Complete Construction | 44166 | 44287 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-01
3622 | 3622 |  | FALSE | ATHLETICS | Baseball Outfield Wall Repairs | Contractor to replace damaged panels and baseboards on outfield fence at Riverside Sports Complex. This is to be done with pressure treated wood. Metal rail at top to be reattached and secured. Entire wall to be painted to specific UCR Athletics colors attached. Damaged boards on scoreboard catwalk and camera scaffolding to be replaced. |  |  | In Design | Tamica Smith Jones | Joe Erbland | Eugene Hutchinson |  | Tameesha Hayes | 3 |  |  | FALSE | 49500 |  | 44237 | Permitting | [12 empty] | PD&C | FALSE | 2021 | 2021-03-01
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 3182452.32 |  | 42720 | Bidding | 44317 | 44501 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-01
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Design | Kathryn Uhrich | Jose Wudka | MaryLou Polek |  | Scott Donnell | 2 |  |  | FALSE | 2500 |  | 43742 | Construction by USDA | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | Jose Wudka | Wendi Tapia |  | Tameesha Hayes | 4 |  |  | FALSE |  |  | 44001 | Waiting for equipment from overseas | [12 empty] | PD&C | FALSE | 2020 | 2021-03-01
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 432510 |  | 42425 | Bidding | 44256 | 44287 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-01
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | Katie Sanchez |  | Gerald Caraig | 20 |  |  | FALSE | 2600000 |  | 42509 | Funding & Approval | [12 empty] | PD&C | FALSE | 2016 | 2021-03-01
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 44097 | Bidding | 44348 | 44440 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-01
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Design (Phase 2) | Kathryn Uhrich | Jose Wudka | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 9 |  |  | FALSE |  |  | 42710 | RPU plan review/design (Phase 2) | 44409 | 44470 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-01
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Design (Phase 4) | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 42340 | Complete Design (Phase 4) | [12 empty] | PD&C | FALSE | 2015 | 2021-03-01
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Funding | Christopher Lynch | Todd Ambriz | Margaret Souder |  | Scott Donnell | 2 |  |  | FALSE | 700000 |  | 43194 | Secure Funding | [12 empty] | PD&C | FALSE | 2018 | 2021-03-01
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | In Funding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 600000 |  | 43713 | Procure Funding | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Funding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 9 |  |  | FALSE | 500000 |  | 43713 | Procure Funding | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | In Funding | Gerry Bomotti | Sharyl Murdock | Gerald Caraig |  | Daneca Stevens | 2 |  |  | FALSE | 50000 |  | 43676 | Secure Funding | 44348 | 44378 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-01
3104 | 3104 |  | FALSE | PALM DESERT GRAD CTR | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Funding | Tamara Hedges | Zelda Glenn | Zelda Glenn |  | Scott Donnell | 2 |  |  | FALSE | 22000 |  | 42502 | Approval & Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-03-01
3581 | 3581 |  | FALSE | SOM | SOMR Interior Egress Doors | All egress doors - Floors 1, 2, and 3 - need to be replaced with compliant structures. Please inspect, evaluate and provide quote. |  |  | In Funding | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 43894 | Procure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-03-01
3617 | 3617 |  | FALSE | BCOE | WCH 108 Server Rm HVAC Upgrade | Winston Chung 108. Upgrade the HVAC system to provide cooling as needed for the server room. |  |  | In Pre-programming | Christopher Lynch | Todd Ambriz | Michael Ambriz |  | Tameesha Hayes | 3 |  |  | FALSE |  |  | 44218 | Design | [12 empty] | PD&C | FALSE | 2021 | 2021-03-01
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 43532 | Complete Report-Arc Flash | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | Michelle Baniqued |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 43528 | DB Competition | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Programming | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 22 |  |  | FALSE |  |  | 42653 | Design | [12 empty] | PD&C | FALSE | 2016 | 2021-03-01
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 43297 | Complete Study | [12 empty] | PD&C | FALSE | 2018 | 2021-03-01
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis (RE Proj) | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 43510 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 43404 | CEQA | [12 empty] | PD&C | FALSE | 2018 | 2021-03-01
20P000253 |  | 20P000253 | FALSE | BCOE | SL5 BOURNS HALL LAB B156 - EXHAUST SYSTEM | EXHAUST SYSTEM | MARLAN & ROSEMARY BOURNS HALL | B0156 | IN PROGRESS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 43810 | install exhaust vent and dedicated circuit | 44256 | 44323 |  |  |  | 2/16/21, DL: Plans were submitted 2- weeks ago. We received the plans back last week with corrections needed. We will resubmit the plans back to the building official by the end of the week….1/19/21, DL: We will start working on the plans for this project in the next two weeks. We will start this project once the permit is approved…… |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01
20P000370 |  | 20P000370 | FALSE | CHASS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | SPACE RENOVATION PROJECT | GORDON S. WATKINS HALL | 1311 | IN PROGRESS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 43880 | 14 daay notification to AQMD for Asbestos Abatment | 44274 | 44379 |  |  |  | 3/1/21, DL: Plans were approved. We now need to send our 14- day notice to the AQMD and schedule the demolition……..2/16/21, DL: Plasns were submitted with building permit last week. We are now in the plan check review process………1/19/21, DL: We will start working on the plans for this project in the next three weeks. We should have plans to submit for plan check review in the next 5- weeks……….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
21P000009 |  | 21P000009 | FALSE | CNAS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | GLOVEBOX SYSTEM | CHEMICAL SCIENCES |  | IN PROGRESS | Kathryn Uhrich | Jose Wudka | NATASHA GONZALES |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 44020 | We will start the demolition early next week. | 44263 | 44309 |  |  |  | 3/1/21, DL: The plans were approved last week. We will try and schedule demo this week or early next week……..2/16/21, DL: We submitted plans for building permit but corrrections are needed. We contacted the glove box manufacture for follow-up questions and we are waiting to hear back from them. Once we have confirmation on the needed information. We will resubmit the plans back to the building official……….1/19/21, DL: we will submit plans this week or earlier next ……………. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
19P000485 |  | 19P000485 | FALSE | CNAS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | HOMER D. CHAPMAN HALL | 9 | IN PROGRESS | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43494 | Connect air monitor and internal fire extinguiser |  | 44267 |  |  |  | 3/1/21, DL: We need toi install the fire extinguisher and air monitor. I sent Bill S. an email asking him if he ordered the air monitor as we do not have one. I also contact EH&S and made them aware that we will be commisioning the fume hood in the very near future…..2/16/21, DL: Plumbing is complete. We will now start the Exhasut vent, electrical and then Scismically anchor the Fume hood…………2/1/21, DL: We have had a delay with the plumbing and it is our goal to be complete on or before 3/1/21…………1/10/21, DL: This project is almost complete. This project will be complete in the next 30- days…………9/30/20, DL: Fume Hood demolition and abatement will be completed on 10/2/20. Fume hood install should be coplete in mid Novemeber……8/5/20, DL: We will submit plans this week. Once plans are approved, we will schedule the work……………Work orders are produced. We need to work on plans and permits once we return.. | 2020-02-10 | Enrico Baez | Disconnect, cap and safe off the existing utility services. Provide the necessary abatement services to properly remove the fume hood from the site and deliver to the campus surplus yard. Install one new department furnished fume hood. Abatement Services: Provide the necessary abatement services to perform all utilities disconnections and floor repair. Floorcovering: Patch and or repair as necessary to match or provide a close match. Install rubber base. Access Control: Survey and adjust the entry door closer to increase latch pull to allow the door to closer completely. Patching and painting: Patch and paint wall at the old fume hood location. Mechanical: Disconnect metal duct, cap/safe off, reconnect/reconfigure new duct to accommodate the new fume hood. Electrical: Provide electrical disconnections and safe off. Reconnect/reconfigure power to the new fume hood. Plumbing: Disconnect Air, Gas, Vacuum, Cold water, and Drain, cap and safe off and reconnect/reconfigure service to the new fume hood. Resource Management: Properly remove the fume hood from the site and deliver to the campus surplus yard. | YES |  | Spring 2020 | FS | FALSE | 2019 | 2021-03-01
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install electrical utilities for new equipment | PHYSICS BUILDING | 1132 | IN PROGRESS | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43543 | Install final electrical, countertop and Sink |  | 44267 |  |  |  | 2/16/21, DL: New sink and Faucet arrived, we will now schedule the install of the countertop and sink…………..1/19/21, DL: This project is in progress and will be complete with in 30- days………..9/30/20, DL: Plans were submitted for Plan Check review last week and we should have an update on the plan check review process soon………..8/5/20, DL: Need to meet with Kirk to verify electrical load. Once confirmed, we will work on plans for a permit | 2019-10-15 | Enrico Baez | Install utilities for new equipment | YES |  | Summer 2019 | FS | FALSE | 2019 | 2021-03-01
20P000144 |  | 20P000144 | FALSE | CNAS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A | ALFRED M. BOYCE HALL | 3432, 3432A, 3446, 3446A | IN PROGRESS | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH | CHERYL GERRY | Dan Lerman |  | 3 |  | FALSE |  |  | 43734 | final paint, floor covering and final cabinets |  | 44288 |  |  |  | 2/16/21, DL:Project Is on schedule. Paint is 90% complete. Once paint is complete, we will schedule the floor repairs and final deep clean……… 2/1/21, DL: We are making good progress and are target date is still 3/14/21………….1/19/20, DL: This project is in progress and will be complete in the next 30- days………….9/30/20, DL: WE have started a few items but we are waiting on Matt U. and the PI to remove their items so we can have access to the space. Once the space is cleared out, we will proceed with the work…………8/5/20, DL: We will start the work in the next 4-6 weeks. | 2020-02-18 | Enrico Baez | Boyce 3432, 3446, 3436 and 3436A . Patch and paint 3432, 3432A, 3436, 3436A, 3446, 3446A. Reface/replace water damaged cabinets near sink (3446). Install GCFI outlets near sink (replace existing) (3446). Install panel cover for electrical panel box. Replace many burnt out bulbs in ceiling lamps. Replace broken chemical plexi-glass on bench shelves. | YES |  | Winter 2020 | FS | FALSE | 2019 | 2021-03-01
20P000003 |  | 20P000003 | FALSE | GRAD DIV | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | ADD POWER/DATA, PATCH/PAINT | UNIVERSITY OFFICE BUILDING |  | IN PROGRESS | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS | CHERYL GERRY | Dan Lerman |  | 1 |  | FALSE |  |  | 43648 | schedule the demo, electrical and plumbing | 44244 | 44295 |  |  |  | 2/16/21, DL: Conducted a site visit with the plumber and capenter shop. We will start the demo next wee…………2/1/21, DL: We will schedule this project to start in 2- weeks……………….1/19/21, DL: Plans were approved and we will schedule the work in the near future………. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Permit is approved. We need to verify floor covering. Once floor covering is confirmed and ordered, we will schedule the work………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We will need plans as we are installing a new hydration station and a Counter top that needs to be ADA compliant…………We started the plans and will submit them for a permit and plan check review within 2- weeks……….10/30/19, DL: No Plans will be needed. We will plan on scheduling the work shortly after Thanksgiving……. | 2019-06-13 | Enrico Baez | 9/24/2019 E. Baez--SCOPE-- 1. Removal and disposal of one bulletin board and two director cases. 2. Removal and disposal of abandoned telephone mounting bracket. 3. Remove and dispose of abandoned alarm box in wall. 4. Patch and paint walls in lobby and public restroom area. 5. Provide electrical connection for wall mounted monitor. 6. Cut access for data boxes. 7. Install monitor mount on wall. 8. Construct 7" x 18" laminate counter top and install in Lobby. | YES |  | FALL 2019 | FS | FALSE | 2019 | 2021-03-01
21P000078 |  | 21P000078 | FALSE | VC-RED | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MULTIDISCIPLINARY RESEARCH BUILDING |  | IN PROGRESS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 44097 | start 2nd floor install | [5 empty] | 1/19/21, DL: the First floor work will be complete today, we will start the 2nd floor this week……………. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
3626 | 3626 |  | FALSE | UNDERGRADUATE EDUCATION | Rivera Library Room Modifications | Conduct room modifications to support new wall display on west wall Rivera A101A. Work needed: 1. West wall - ½” three-ply to support 12 x 55” displays over bookshelves. 2. West wall – drywall cover bookshelves any area not covered by the technology displays. 3. West wall – add electrical outlets as needed for new displays 4. North and south walls – add electrical for new motorized shades 5. Rivera A101A – add carpeting 6. Rivera A101A – paint room Notes: - Working with Chuck Forsyth in ITS and Bahram Mobasher from CNAS/Physics on project. - Israel and Chuck had a preliminary meeting with Enrico Baez from facilities to discuss project. - Point of contact: Israel Fletes and Charles Forsyth. Israel Fletes cellphone: 951-300-6693 |  | A101A | New (2/10/21) |  |  | Israel Fletes |  | Vilma Kern |  |  |  | FALSE |  |  | 44237 | New (2/10/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-01
3612 | 3612 |  | FALSE | CAP PROG | Native American Landscape Garden | Create a physical marker to commemorate the UCR Land Acknowledgement in the form of a Native American Landscape Garden (working name) at the proposed project location. |  | Ext | New (2/11) | Jacqueline Norman | Sharyl Murdock | Uma R. |  | G.Caraig/V.Kern |  |  |  | FALSE | 23000 |  | 44238 | New (2/11) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-01
3621 | 3621 |  | FALSE | CNAS | NRS Emerson Main Residence Transfer Switch | We are looking to purchase and install a transfer switch to power either just our well pump or the pump and critical circuits at the breaker box by generator at Emerson Oaks when the power is out. What is the best way to contact the Campus Electricians for not only an estimate for the project but for guidance on the best way to set things up? |  |  | New (2/2/21) | Kathryn Uhrich | Jose Wudka | Joseph Messin |  | Vilma Kern | 10 |  |  | FALSE |  |  | 44229 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-01
3623 | 3623 |  | FALSE | CNAS | NRS Boyd Deep Canyon Repairs & Upgrades | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ |  |  | New (2/2/21) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Rowan Reid | 11 |  |  | FALSE |  |  | 44229 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-01
3618 | 3618 |  | FALSE | CNAS | NRS James Reserve Upgrades | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. |  |  | New (2/2/21) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Rowan Reid | 12 |  |  | FALSE |  |  | 44229 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-01
3616 | 3616 |  | FALSE | CAP PROG | University Ave/Canyon Crest Dr Improvements | $100,000 in Violent Acts Mitigation and Prevention funding have been awarded to study short and long-term safety improvements at the intersection at University Avenue and Canyon Crest Drive. Subsequent activities will involve the construction of identified improvements. |  |  | New (3/1) | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Uma R. |  |  |  | FALSE | 100000 |  | 44256 | New (3/1) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-01
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Joe Erbland | Johnathan Jensen |  | Fernando Nunez | 1 |  |  | FALSE | 0 |  | 43335 | Department approval to move fwd | [12 empty] | PD&C | FALSE | 2018 | 2021-03-01
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | SOCCER FIELD AND AREA |  | On Hold | Tamica Smith Jones | Joe Erbland | Joe Erbland |  | Gerald Caraig | 2 |  |  | FALSE | 0 |  | 41739 | Need direction by PM Director | [12 empty] | PD&C | FALSE | 2014 | 2021-03-01
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 14 |  |  | FALSE | 0 |  | 43072 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-03-01
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 17 |  |  | FALSE | 0 |  | 43297 | Coordinating with North District | [12 empty] | PD&C | FALSE | 2018 | 2021-03-01
3594 | 3594 |  | FALSE | CNAS | R'Garden Grow Pod Installation | R'Garden Gro Pod Installation |  |  | On Hold | Kathryn Uhrich | Jose Wudka | Richard Zapien |  | Scott Donnell | 7 |  |  | FALSE |  |  | 43972 | Secure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-03-01
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 1500000 |  | 43775 | On Hold | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 43809 | Departmental Approval | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | On Hold | Rodolfo Torres | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Daneca Stevens | 1 |  |  | FALSE | 45000 |  | 42899 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-03-01
2989 | 2989 |  | FALSE | ATHLETICS | Dance - Locker Room Remodel | We are requesting to utilize Base Architecture, Planning, & Engineering, Inc. to provide pro bono work on planning for locker room renovations in the Athletics & Dance Building. Rob Gayle is aware of our desire to utilize this company for services. |  |  | On Hold (COVID-19) | Tamica Smith Jones | Joe Erbland | Joseph Erbland |  | Tameesha Hayes | 99 |  |  | FALSE | 28395 |  | 42327 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2015 | 2021-03-01
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | On Hold (COVID-19) | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 43273 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2018 | 2021-03-01
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | On Hold (COVID-19) | Brian Haynes | Cathy Eckman | Christina Wong |  | Tameesha Hayes | 2 |  |  | FALSE | 130000 |  | 43543 | On hold (COVID-19) | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 42886 | Department Approval/Funding | [12 empty] | PD&C | FALSE | 2017 | 2021-03-01
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 6 |  |  | FALSE | 0 |  | 43178 | CIB Approval | [12 empty] | PD&C | FALSE | 2018 | 2021-03-01
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MATERIALS SCIENCE & ENGINEERING | 71 | PLAN DEVELOPMENT/CHECK | Christopher Lynch | Todd Ambriz | XI CHEN |  | DAN LERMAN |  | 2 | 3 | FALSE |  |  | 44049 | Start working on CAD drawings and building permit | [5 empty] | 3/1/21, DL: We will start the plans by early next week and we are planning to submit the plans to the building department the 2nd or 3rd week in march……1/19/21, DL: This is a priority #2 project. WE will start the plans and permit process for this project when all priority 1 projects are complete…………1/14/21 O-ANS: Updated prioritization to #2 (from #3) per org leadership request. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
21P000001 |  | 21P000001 | FALSE | CNAS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | NEW GROWTH CHAMBER PLACEMENT | HOWARD SAMUEL FAWCETT LABORATORY |  | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Jose Wudka | LINDA WALLING |  | DAN LERMAN |  | 2 |  | TRUE |  |  | 43990 | Still pending plan check review. | [5 empty] | 3/1/21, DL: This was recently change to a priority 2 project. Once plans are approved, we will work on the schedule noting, the schedule for this will work around pending priority 1 projects……1/19/21, DL: This is a priorty 3 project. We will start this project when all priority 2 projects are complete…….2/16/21, LB: Changed to Priority 2 per Dan. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 44091 | Begin RFQ Process | [12 empty] | PD&C | FALSE | 2020 | 2021-03-01
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 16 |  |  | FALSE | 1250000 | 0 | 43390 | FS Direction | [12 empty] | PD&C | FALSE | 2018 | 2021-03-01
3523 | 3523 |  | FALSE | PB&A | 1907 Mt Rubidoux Facility Study | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. |  |  | Programming (Study) | Gerry Bomotti | TBD | Melissa Garrety |  | Scott Donnell | 3 |  |  | FALSE |  |  | 43577 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Scott Donnell | 10 |  |  | FALSE | 65000 |  | 43528 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-03-01
21P000019 |  | 21P000019 | FALSE | BCOE | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | Bourns Office A305 - Install Plank Floor Please remove old damaged carpet and install new plank floor. Match with that of the ME suite (same floor). Thank you. Note: Current PI has not moved out. We will contact Facilities once date is known and all items have been removed from the room. Questions: ME Department Manager (Interim) - William Bingham - bill@ece.ucr.edu , or Robert Lopez lopezra@engr.ucr.edu | MARLAN & ROSEMARY BOURNS HALL | A305 | PROJECT INTAKE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | 3 | 2 | TRUE |  |  | 44032 | complete priority 2 projects | [5 empty] | 1/19/21, DL: This a priority 3 project. We will start this project when all priority #2 projects are complete………..1/14/21 O-ANS: Updated prioritization to #3 (from #2) per org leadership request. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 150 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 43844 | Electrical Engineer design | [5 empty] | 1/19/21, DL: This project will require engineered plans. This is a priority 2 project. We will start the plans and permit process when all priority #1 projects are comple………… |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 245 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | ANDREA HIDALGO |  | DAN LERMAN |  | 3 |  | FALSE |  |  | 43832 | plans and permit once we start priority 3 projects | [5 empty] | 1/19/21, DL: This is a priority 3 project. We will start the plans and permit for this project when all priortiy #2 projects are complete…….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Convert Basement Library into Piano Lab | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 54 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 43788 | start plans once priority 3 proj. are almost comp. | [5 empty] | 1/19/21, DL: We will Start the plans, permit and the work once all priority #3 projects…………...11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks……….. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01
20P000445 |  | 20P000445 | FALSE | CNAS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 279 | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | DAN LERMAN |  | 3 |  | TRUE |  |  | 43985 | complete priority 2 projects | [5 empty] | 1/19/21, DL: This is a priority 3 project. We will start the project when all priority 1 projects are complete………….2/16/21, LB: Changed to Priority 3 per Dan. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000320 |  | 20P000320 | FALSE | CNAS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | ACTIVATE VACUUM LINES | HERMAN T. SPIETH HALL | 1303 | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | DAN LERMAN |  | 4 |  | FALSE |  |  | 43789 | Will start the work once we start priority 3 proj | [5 empty] | 1/19/21, DL: This is a priority 4 project. We will start this project when all all priority 3 projects are complete……….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01
20P000248 |  | 20P000248 | FALSE | CNAS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT | Space Management has temporarily allocated Rooms 1223 and 1223-A in Webber Hall to CNAS. We need this lab cleaned and modified to accommodate relocating an existing (and active) lab. | HERBERT JOHN WEBBER HALL | 1223 + 1223-A | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | DEBORAH MCWILLIAMS | SHARYL MURDOCK | Dan Lerman |  | 5 | 4 | FALSE |  |  | 43796 | EH&S to sanitize space | 44257 | 44307 |  |  |  | 1/19/21, DL: This project is a priority #5. We will start this project when all priority #4 projects are complete…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….02/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Survey space for hazardous material. Once survey is complete, we will schedule abatement and the work. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01
20P000366 |  | 20P000366 | FALSE | CNAS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | MINOR LAB RENOVATION | HERMAN T. SPIETH HALL | 2375 / 2375-A | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | SHERICE UNDERWOOD |  | DAN LERMAN |  | 7 |  | TRUE |  |  | 43880 | will start when we start priority 7 projects. | [5 empty] | 1/19/21, DL: This is a priority 7 project, we will start this project when all priority 6 projects are complete………….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | W. CONWAY PIERCE HALL | 2232A | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 43852 | will start when we start priority 9 projects | [5 empty] | 1/19/21, DL: This is a priority #9 project. We will start this project when all priority #8 projects are complete…………. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS BUILDING |  | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | JOSE WUDKA |  | Enrico Baez |  | R1 |  | FALSE |  |  | 43818 | [6 empty] | 1/19/21 DL: Enrico is managing this project. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01 |  | 1
20P000046 |  | 20P000046 | FALSE | CNAS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | HOMER D. CHAPMAN HALL | 0001 | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Enrico Baez |  | R2 |  | FALSE |  |  | 43677 | [6 empty] | 1/19/21, DL: Enrico B. will manage this priject………….11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Install wireless access controls systems at front and rear entry doors. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01 |  | 1
21P000003 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | PROJECT INTAKE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Enrico Baez |  | R1 |  | FALSE |  |  | 44008 | [6 empty] | 1/19/21, DL: Enrico is managing this project………….. | 2020-12-02 | Enrico Baez | Remove tripod antenna. Apply spray roof coating to existing roof surface | YES |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01 |  | 1
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | JEANETTE AND RUPERT COSTO HALL |  | PROJECT INTAKE | Brian Haynes | Cathy Eckman | BRENDAN O'BRIEN |  | Enrico Baez |  | R1 | R2 | FALSE |  |  | 43762 | [6 empty] | 02/16/21 O-ANS: Will require plans/permits and may need to go to PD&C due to scope of work which includes construction. Will confirm with client before instructing to submit request to CPMS…. 01/19/21, DL: Enrico B. Will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01 |  | 1
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | [12 empty] | PD&C | FALSE | 1900 | 2021-03-01
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | TBD | Sean Hatfield |  | D.Hecht/J.Franklin | 20 |  |  | FALSE | 0 |  | 43007 | Project pushed to 2021 | [12 empty] | PD&C | FALSE | 2017 | 2021-03-01
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 43920 | Projects to be assigned | [12 empty] | PD&C | FALSE | 2020 | 2021-03-01
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | MARLAN & ROSEMARY BOURNS HALL | B0328E | QUEUE TO START | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Enrico Baez |  | R1 | R1 | FALSE |  |  | 43774 | [6 empty] | 1/19/21, DL: Todd has the estimate. Sent follow up email to Todd requesting update or FAU number………………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01 |  | 1
20P000363 |  | 20P000363 | FALSE | BCOE | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | Paint Only | WINSTON CHUNG HALL | 433 | QUEUE TO START | Christopher Lynch | Todd Ambriz | MANGLAI ZHOU | FARIBORZ KARGAR | PAUL DITTY |  | X |  | TRUE |  |  | 43874 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000310 |  | 20P000310 | FALSE | BCOE | SL5 BOURNS A-WING A129 - PATCH & PAINT | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. | MARLAN & ROSEMARY BOURNS HALL | A0129 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43840 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUMANITIES BUILDING | 3210 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44006 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000446 |  | 20P000446 | FALSE | CHASS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. | CHASS INTERDISCIPLINARY NORTH | 4047 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 43986 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000453 |  | 20P000453 | FALSE | CHASS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | Paint Only - Please patch/paint to existing color office for faculty new hire. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 142 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000463 |  | 20P000463 | FALSE | CHASS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 | HUMANITIES BUILDING | 2000 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000469 |  | 20P000469 | FALSE | CHASS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 222 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | SUSAN KOMURA | PAUL DITTY |  | X |  | TRUE |  |  | 44005 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000462 |  | 20P000462 | FALSE | CHASS | SL5 HMSS 2001 - PAINT OFFICE / CLEAN FLOOR NEW FACULTY HIRE | Patch/paint to existing color for faculty new hire | HUMANITIES BUILDING | 2001 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | Paul Ditty |  | X |  | TRUE |  |  | 44000 | [6 empty] | 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000464 |  | 20P000464 | FALSE | CHASS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) | HUMANITIES BUILDING | 3001 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
21P000111 |  | 21P000111 | FALSE | CHASS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. | GORDON S. WATKINS HALL | 2144 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
21P000110 |  | 21P000110 | FALSE | CHASS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. | GORDON S. WATKINS HALL | 2146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000403 |  | 20P000403 | FALSE | CHASS | SL5 OLMSTED 232 - PAINT OFFICE | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). | JOHN W. OLMSTED HALL | 2321 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | MELISA VICARIO | Paul Ditty |  | X |  | TRUE |  |  | 43903 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
21P000109 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Dr. Robert Clark. He started working July 1, 2020. | GORDON S. WATKINS HALL | 1146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 44153 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS BUILDING | 3009 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 43749 | [6 empty] | 02/03/21 O-ANS: Reminder email sent to customer that PAINT ONLY portion would be completed and not the door removal at this time. Customer can resubmit request in next prioriization cycle…. 11/06/20 O-JLO: Emailed requestor and alternate regarding paint portion only, and that door/drywall removal will not occur during this time …. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. FS to confirm with customer that we can only complete the painting at this time but not the removal of the door…. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure. | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 43794 | [6 empty] | 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01
20P000419 |  | 20P000419 | FALSE | CNAS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | Paint Only | HERMAN T. SPIETH HALL | 2312 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | PAUL DITTY |  | X |  | TRUE |  |  | 43943 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000397 |  | 20P000397 | FALSE | CNAS | SL5 ENTOMOLOGY 139 - PATCH AND PAINT OFFICE | Patch and paint room 139 for the new faculty member | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 0139 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 43895 | [6 empty] | 02/10/21 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000467 |  | 20P000467 | FALSE | SOM | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. | HERBERT JOHN WEBBER HALL | 1247 | QUEUE TO START | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | CYNTHIA CAROLINA | PAUL DITTY |  | X |  | TRUE |  |  | 44001 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000218 |  | 20P000218 | FALSE | VC-RED | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | VIVARIUM UPDATE AIR COMPRESSOR | HERMAN T. SPIETH HALL | 347 | QUEUE TO START | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | DAN LERMAN |  | 2 | R2 | FALSE |  |  | 43602 | We will start once priority 1 projects are complet | [5 empty] | 2/1/21, DL: WE will start the process for this project once we are closer to completing priority one projects. This is a prioity 2 project……1/19/21, DL: This project has been scoped. We will start the work when we are complete with all priority #1 projects…….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-01
21P000079 |  | 21P000079 | FALSE | VC-RED | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. | PSYCHOLOGY BUILDING |  | QUEUE TO START | Rodolfo Torres | Laura Manor | LESLIE KARPINSKI |  | PAUL DITTY |  | X |  | FALSE |  |  | 44099 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
20P000468 |  | 20P000468 | FALSE | VC-RED | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | Paint Only | HERMAN T. SPIETH HALL | 364 | QUEUE TO START | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 44005 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-01
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | Sub-contractor bidding | Gerry Bomotti | TBD | Sharyl Murdock |  | Rowan Reid | 16 |  |  | FALSE | 26329342.06 |  | 42353 | Start Construction | 44287 | 45139 | [10 empty] | PD&C | FALSE | 2015 | 2021-03-01
3401 | 3401 |  | FALSE | CAP PROG | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | Substantial Completion 2/5/21 | Jacqueline Norman | Sharyl Murdock | Mihai Gavan |  | Fernando Canon | 12 |  |  | FALSE | 8754623.11 |  | 43072 | Complete Furniture & Equipment | 43952 | 44228 | [8 empty] | 2021-02-05 |  | PD&C | FALSE | 2017 | 2021-03-01 | FY 20-21
3515d | 3515d |  | FALSE | PB&A | Multiple SF6 Primary Switches | Sub-project of 950568 |  |  | TBD | Gerry Bomotti | TBD | John Franklin |  | J.Franklin/G.Caraig |  |  |  | FALSE |  |  | 44256 | TBD | [12 empty] | PD&C | FALSE | 2021 | 2021-03-01
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 19 |  |  | FALSE | 916581 |  | 43410 | Complete Review | [12 empty] | PD&C | FALSE | 2018 | 2021-03-01
20P000067 |  | 20P000067 | FALSE | BCOE | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM | BOURNS | B-Wing | TO BE PERFORMED BY PD&C | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | R1 |  | FALSE |  |  | 42688 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Replace access controls at BCOE WCH & Bourns bldgs. |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2016 | 2021-03-01 | FY 20-21 | 1
19P000674 |  | 19P000674 | FALSE | CHASS | SL5 HMSS RM 2416 OFFICE ROOM PATCH AND PAINT |  | HUM & SOC SC | 2416 | TO BE PERFORMED BY PD&C | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 43635 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-23 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | Modify the existing room in Soil House 1 (attached to the Delphino Lab at the Rubidoux Facilities) to expand CCPP quarantine services to include USDA/CDFA compliance for installation of new Economic Development Administration (EDA) citrus growth chambers. | DELFINO HHSE |  | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 43245 | Research and plan development | [5 empty] | 12/7/20, DL: This project will be managed by PD&C…..9/30/20, DL: Project is still on Hold until Furhther notice………...8/5/20, DL: WE will work on plans in the next 30- 45 days……………6/17/20, DL: This project is under review and is on hold until further notice………10/3/19 O-ANS: Plan Development per Minor Reno Meeting. 10/1/19,DL; We are getting ready to start the plans as we are currently conducting resarch on products that will meet the needs of the space……………..5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman |  | YES | 2020-12-07 | Summer 2018 | FS | FALSE | 2018 | 2021-03-01 | FY 20-21
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB. Patch Paint walls, replace flooring, refinish wood cabinets and sinks. | SPIETH | 2349 | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43516 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold……….12/11/19: O-ANS: Reassigned as project allotment - priority #5 for Winter 2020. 11/27/19 O-ANS: Placed on Hold for re-prioritization by client for Winter 2020. | 2020-02-27 | Enrico Baez | Patch and paint and extra work to upgrade an old lab that we are now inhabiting. In addition to painting, we need to have floors re-surfaced, cabinets re-stained, and counter tops re-surfaced, if possible. There is also a metal sink that could be polished. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-01 | FY 20-21
19P000670 |  | 19P000670 | FALSE | SOM | SL5 SOME, RM 1670- RENOVATE FOR EXPANDED ENROLLMENT |  | SOM EDUC | 1670 | TO BE PERFORMED BY PD&C | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 43634 | [8 empty] | Enrico Baez |  |  | 2019-09-06 | Fall 2019 | FS | FALSE | 2019 | 2021-03-01 | FY 19-20
3589 | 3589 |  | FALSE | CAP PROG | Various Bldgs LED Lighting Ph2 | LED Lighting Phase 2 - Package 1 - Replacing existing lamps to LED |  |  | Bidding | Jacqueline Norman | Sharyl Murdock | David Palacios |  | Fernando Nunez | 15 |  |  | FALSE | 780545 |  | 2020-03-11 | 100% Cd stamped approval | 2021-04-01 | 2021-07-30 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-16
3467 | 3467 |  | FALSE | PB&A | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | Bidding - 3rd flr Walking Deck Only | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 17 |  |  | FALSE | 235000 |  | 2018-07-31 | Award Contract | 2021-05-01 | 2021-06-01 | [10 empty] | PD&C | FALSE | 2018 | 2021-03-16
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Bidding Competition | Gerry Bomotti | TBD | Michelle Baniqued |  | Fernando Canon | 1 |  |  | FALSE | 33980000 |  | 2019-03-04 | Select Design Builder | 2021-10-01 | 2023-04-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Rivera Library Arches/Arcade Repair | Paint and replace roof. | RIVERA LIB |  | Bids received, award on hold due to DM funding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Scott Donnell | 99 |  |  | FALSE | 240000 |  | 2016-05-06 | Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-03-16
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5 ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | CANCELED BY CLIENT | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  | 10 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 1/24/2020 E. Baez- Cancelled per Joe Erbland. 4/18/19, DL; Per Enrico, we are waiting for a proposal from HCI and approved funding from Athletics. We should have the proposal in 2- weeks…. | 2018-09-27 | Enrico Baez |  | YES | 2020-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000275 |  | 19P000275 | FALSE | ATHLETICS | SL5 SOFTBALL STG PRESS BOX AC ADDITION | FS to coordinate with customer to scope the work. | PRESS BOX |  | CANCELED BY CLIENT | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  |  |  | 6 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project was canceled by Johnathan J. as there is not funding at this time…………DL, 10/4/18; I checked on this recently and this is not a building, it is stoarge and should be recharge work…. | 2018-09-27 | Enrico Baez |  |  | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000093 |  | 20P000093 | FALSE | ATHLETICS | SL5 ATHLETICS 0078 - TELEVISION MOUNT/ ELECTRICAL |  | ATH DANCE | 0078 | CANCELED BY CLIENT | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-08-20 | [6 empty] | 11/26/19 O-ANS: Project canceled per communication with Enrico. | 2019-10-04 | Enrico Baez | Install TV bracket on wall near weight room. Provide recessed/flush single gang outlet near bracket. | YES | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
19P000311 |  | 19P000311 | FALSE | ATHLETICS | SL5 ATHLETICS 150-KEYLESS ENTRY | Keyless entry system | ATH DANCE | 0150 | CANCELED BY CLIENT | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2018-10-02 | [6 empty] | 02/07/2020 O-ANS: Canceled by customer Joe Erbland due to lack of funding per email to EBZ. | 2018-09-27 | Enrico Baez | Install keyless entry system, part of larger project throughout the athletics building | YES | 2020-02-07 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20 | 1
19P000029 |  | 19P000029 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | Canceled; duplicate request to be completed with 19P000059 | CHUNG HALL | 205 | CANCELED BY CLIENT | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-16 | [6 empty] | Canceled; duplicate request to be completed with 19P000059 |  | Enrico Baez |  | NO | 2018-09-18 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000565 |  | 19P000565 | FALSE | BCOE | SL5 BOURNS PATCH AND PAINT: 1ST FLOOR HALLWAYS |  | BOURNS | A0133 | CANCELED BY CLIENT | Christopher Lynch | Todd Ambriz | NANCY FORD |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-04-08 | [6 empty] | 07/30/19 O-ANS: Per Paul Ditty, Customer Maggie Souder canceled project. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000023 |  | 19P000023 | FALSE | BCOE | SL5 PAINT ACCENT WALL | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-13 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-18 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000026 |  | 19P000026 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALLS | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-18 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000209 |  | 18P000209 | FALSE | CHANCELLOR | SL5 VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 |  | STUDENT SERV | 0 | CANCELED BY CLIENT | Kim Wilcox | TBD | ANGIE GRAY |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2017-11-30 | waiting to hear back from Angie | [5 empty] | 5/16/19, DL Angie Grey canceled project on 5/15/19 via email….. 5/1/19, DL; Sent Angie an email this morning. Waiting to hear back from Angie to see if project will be canceled or sent to PD&C…..3/28/19, DL; Provided Angie with an estimate and waiting for her response. The esimate was for 65,000. this work will be redirected to PD&C if she wants to proceed…….2/14/19, DL; Ron V. to follow up with Doug from Capitol Door for alternate pricing .1/15/19, DL; Ron V is still working with Angie on verifying a vendor and product…………..12/14/18, DL; Ron V. is currently working to find a more affortable turnstyle system. When a sytem is approved, we will schedule the work…. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope and conduct site visit……DL, 7/11/18; This work will require plans and permits. Will schedule meeting with Scott to verify if the project request will be approved. If this is approved, we will plan the target complete date to be mid October…..The Request is to reverese Emergency Exit Doors and install Prox card access……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..DL, 8/22/18; Confirmed with Scott that we can reverse the door swing. We will work on plans for review process. This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 9/19/18; I mis understood this for a project at Health Services. I have a meeting with Angie this week. This project is to install turn styles for access to the building. I will need to discuss the equipment to be purchased by Angie verify the specs. We will start on the plans in the early Fall……DL, 11/7/18; Conducted site visit with Vendor. Informed Angie the cost of the project will be at $45K for the project. Angie is checking to verify if funds are availabe for the equipment. |  | Enrico Baez | Install automatic swing gates at the student services lobby. Include Access controls relay cabling | YES | 2019-05-16 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
18P000294 |  | 18P000294 | FALSE | CHASS | SL5 HMSS REMOVE DOOR, INSTALL WALL |  | HUM & SOC SC | 3610 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2018-02-01 | [8 empty] | Enrico Baez |  | YES | 2018-07-16 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000415 |  | 18P000415 | FALSE | CHASS | SL5 PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | Door and frame have been painted; construction to commence upon availability of the teams. | OLMSTED | 0 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | RYAN LIPINSKI |  | Dan Lerman |  |  | 10 | TRUE |  |  | 2018-05-08 | [6 empty] | 12/14/18, DL; Angel cancelled this project as it is no longer needed at this time……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 7/11/18; This project was scoped and part of the IRT. Plans and permits are approved. We will schedule the work and we will plan to have this project complet by 9/21/18…..8/10/18; WE have approved plans, this project is scheduled to start late August and will be complete early October……DL, 10/4/18; The door and frame is scheduled for delivery in 3-5 weeks, We will start the project when the doors and frame are on site……..DL, 11/7/18; Door and frame and painted. We will start the contruction in the near future…… |  | Dan Lerman |  | YES | 2018-12-14 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000420 |  | 18P000420 | FALSE | CHASS | SL5 COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | Canceled by Customer on prioritization 7/2/18 | WATKINS | 0 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  |  |  |  | Cancel | TRUE |  |  | 2018-04-27 | [10 empty] | YES | 2018-07-02 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000606 |  | 19P000606 | FALSE | CHASS | SL5 PAINT ROOM |  | WATKINS | 1213 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 06/14/19 O-ANS: Stephen spoke with customer Becky Campbell via phone who confirmed that project was going to be canceled due to re-allocation of space by another dept. |  |  |  |  | 2019-06-14 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
19P000607 |  | 19P000607 | FALSE | CHASS | SL5 PAINT FACULTY OFFICE |  | WATKINS | 1312 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2019-05-10 | [6 empty] | 08/26/19: Canceled by customer because duplicate of project 20P000044. 08/13/19 O-ANS: Customer scope of work includes more than just PAINT so project added to Fall 2019 list for prioritization by organization. 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000605 |  | 19P000605 | FALSE | CHASS | SL5 PAINT NEW MAILROOM |  | WATKINS | 1320E | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 07/16/19 O-ANS: Customer Becky Campbell called to cancel project via phone. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000419 |  | 18P000419 | FALSE | CHASS | SL5 COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | FS to coordinate with client to scope the work. | WATKINS | 1320C&E | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 5 | 8 | TRUE |  |  | 2018-04-27 | [6 empty] | 2/14/19,DL; This project was canceled by Paul R. 2/1/19, DL; We will custom make Sound panels and will start the installation in the next 6-8 Weeks……….. |  | Enrico Baez |  | NO | 2019-02-14 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000226 |  | 19P000226 | FALSE | CHASS | SL5 PAINT OFFICE HMNSS 3304 |  | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-08-28 | [8 empty] | Paul Ditty |  |  | 2018-10-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000211 |  | 20P000211 | FALSE | CHASS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | Install keyless entry system for door to Arts Building RM 54 | ARTS | 54 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 | R3 | FALSE |  |  | 2019-11-07 | [6 empty] | 1/19/21, DL: Enrico will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment installation. 8/5/20, DL: This Project is on hold until further notice……. | 2020-01-20 | Enrico Baez | 1/19/21, EB: Per Paul R., This project is canceled………….Provide new panel, power supply and door hardware for 2 doors. Prox reader only. | YES | 2021-01-19 | Winter 2021 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21 | 1
19P000189 |  | 19P000189 | FALSE | CNAS | SL5 PHYSICS- WALL HOLES PATCH | Duplicate work order to 19P000049. Work to be completed on other project. | PHYSICS | 3036 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | JAZMIN CHAVEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-16 | [10 empty] | NO | 2018-10-18 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000213 |  | 19P000213 | FALSE | CNAS | SL5 NEEDS FOR NEW WALL DISPLAY (MONITOR) | Duplicate request to 19P000031; Work to be completed on other project. | BIOLOGIC SCI | 3101 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [11 empty] | 2018-10-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000319 |  | 19P000319 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB |  | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000220 |  | 20P000220 | FALSE | CNAS | SL5 SPIETH-NEW CLOSING/SECURITY MECHANISM FOR LOADING DOCK DOORS |  | SPIETH |  | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | - |  | FALSE |  |  | 2019-11-14 | [8 empty] | Enrico Baez |  |  | 2019-11-22 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000335 |  | 20P000335 | FALSE | CNAS | SL5 ENTOMOLOGY BLDG 239-246 - PAINT AND PATCH OFFICE AND LAB |  | ENTOMOLOGY | 239 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-22 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty | 05/22/20 O-ANS: Project canceled per customer request (Bill Sutton). |  | 2020-05-22 | Spring 2020 | FS | FALSE | 2020 | 2021-03-16 | FY 19-20
18P000269 |  | 18P000269 | FALSE | CNAS | SL5 BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED |  | BATCHELOR | 1123 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | APRIL MEINZER |  | Dan Lerman |  | 12 | 18 | FALSE |  |  | 2018-01-16 | schedule the work | 2019-03-21 | 2019-04-18 |  |  |  | 3/18/19, DL; went to schedule the work and the customer stated the power is no longer needed and confirmed this work order can be canceled. |  | Enrico Baez |  | YES | 2019-03-18 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000043 |  | 19P000043 | FALSE | CNAS | SL5 SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | Customer called and canceled the work on 10/23/18. | SCIENCE LAB1 | 309 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Dan Lerman |  | 19 |  | FALSE |  |  | 2018-07-20 | [7 empty] | 2018-10-22 | Enrico Baez |  | YES | 2018-10-23 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18W011691 |  | 18W011691 | FALSE | CNAS | SL5 ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | FS to coordinate with client to schedule work for completion. | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | 4 | 11 | TRUE |  |  | 2018-03-08 | [6 empty] | 12/17/18 DND: Canceled by client on 12/17/18. |  | Paul Ditty |  | N/A | 2018-12-17 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000197 |  | 19P000197 | FALSE | CNAS | SL5 PATCH AND PAINT OFFICE, LOBBY AND HALL |  | COLL BLDG NO | 0203B | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 44 |  | FALSE |  |  | 2018-08-21 | [6 empty] | 05/07/19 O-ANS: Canceled per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000127 |  | 19P000127 | FALSE | CNAS | SL5 PIERCE PATCH & PAINT | Duplicate request to be combined with 19P000239 | PIERCE | 2301 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | MICHELLE KING |  | N/A |  | Canceled |  | FALSE |  |  | 2018-08-03 | [6 empty] | Paul Ditty |  | Paul Ditty |  |  | 2018-09-21 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000413 |  | 19P000413 | FALSE | CNAS | SL5 RENOVATE BATCHELOR HALL BSL-2 LAB ROOM 3111 | Batchelor 3111-Refresh BSL2 lab to accomodate Biosafety Cabinet. The Biosafety. Cabinet will be procured by BPSC. | BATCHELOR | 3111 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH | PATTY SPRINGER | Dan Lerman |  | R1 | 107 | FALSE |  |  | 2018-12-17 | [6 empty] | 11/22/19 O-ANS: Project canceled per email from Deborah McWilliams. "The need for an appropriate space to accommodate use of a biosafety cabinet will be addressed in BH 2163 via the campus Batchelor Hall MEP-Tenant Improvement Project managed by PD&C." | 2019-06-12 | Enrico Baez | Preliminary assessment provided by Tiffany Kwok on 2/13/19 email. "For Batchelor 3111, there are a few items that need to be addressed before it can support BSL-2 work. • Floors should be patched to provide a smooth and easily cleanable surface. • Base coves along the wall should be replaced or repaired to provide a smooth and easily cleanable surface. • Base coves under the cabinets on the corners should be provided. • Provide a layer of sealant over the cabinets to ensure that the cabinets are moisture resistant and easily cleanable. • Seal, repair or replace the wooden rack on the wall to provide a moisture resistant and easily cleanable surface. • Ensure the door is self-closing. Since this is not a new facility and the space is not undergoing major renovations, it is not required to provide negative airflow into the space. However, it is still important that the air from the laboratory is not recirculated into clean spaces". | YES | 2019-08-26 | Winter 2020 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20 | 1
20P000038 |  | 20P000038 | FALSE | CNAS | SL5 BATCHELOR HALL 1151- QUOTE FOR ADDING FOB ACCESS TO A DOOR |  | BATCHELOR | 1151 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | RACHEL BEHAR |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-07-24 | [6 empty] | 09/24/19 O-ANS: PROJECT CANCELD BY CLIENT PER EMAIL FROM DEBORAH MCWILLIAMS. |  | Enrico Baez |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000086 |  | 20P000086 | FALSE | CNAS | SL5 SKYE 2ND FLOOR - KEY CARD ACCESS ESTIMATE |  | SKYE HALL | 2ND FLOOR | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  | R3 |  | FALSE |  |  | 2019-08-19 | [6 empty] | 09/26/19 O-ANS: CANCELED BY CUSTOMER - Estimated cost to go keyless outside of budget. | 2019-09-10 | Enrico Baez | Provide estimate for keyless entry. | YES | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000017 |  | 20P000017 | FALSE | CNAS | SL5 COLLEGE BLDG CR200 - PAINT PROJECT |  | COLL BLDG NO | CR0200 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Dan Lerman |  | R4 |  | FALSE |  |  | 2019-07-15 | [6 empty] | 1/30/20, DL: This Project was Canceled per Rohnda via email on 1/29/20……….11/26/19, DL; Provided Ronda with updated quote on 11/25/19: She will present the quote to her team and provide us with an update in the near future if they would like to proceed………11/20/19 O-ANS: Re-assigned to Dan Lerman. Project was originally a paint project but will be outsourced as Recharge project paid for by the customer's department. |  | Dan Lerman |  |  | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
19P000555 |  | 19P000555 | FALSE | CNAS | SL5 SAT CHIL PL – GRADE, INSTALL FENCE FOR RAIN COLLECTOR AT TES TANK | INSTALL OF FENCE FOR RAIN COLLECTOR AT TES TANK | SAT CHIL PL | 0 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Dan Lerman |  | R4 |  | FALSE |  |  | 2019-04-03 | Estimate from contractor | [5 empty] | 10/30/19 O-RVL: RV sent Andrew a message to ask if a decision was made to proceed with this project or if it will be cancelled?" Pending response. END~ 10/16/19, DL; I placed this project on hold as we have not heard back from the customer. We notified the customer of the cost but have not heard back from them. If the project is approved, we will schedule the work………...10/1/19, DL; Ron provide Deborah the propsal and we are waiting for her response to proceed or cancel the project……...9/16/19, DL; Ron submitted the estimate to Debora and the Faculty member last week. If project is approved, we will schedule the work……9/3/19, DL; Plans and estimate are complete. Ron will provide Deborah with a formal estimate and let us know if we will proceed with the work…..8/15/19, DL; Plans are approved. We ware waiting for a estimate from our contractor. Once we have the quote, we will forward the quoted to Deborah for review and approval. Note, this is a recharge project…….8/1/19, DL; Plans are complete pending approval from building official…. |  | Enrico Baez | Install Chain Link fence with gate. Includes grading, gravel and fence posts set in concrete. |  | 2019-10-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
19P000594 |  | 19P000594 | FALSE | CNAS | SL5 ENTOMOLOGY 171- TAKE DOWN STEELCASE WALL AND MOVE DESKS | Take down a dividing wall in this office and move the desks to their old location and rehang the overhead desk bins back into their old locations with inserts still in the walls. | ENTOMOLOGY | 171 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  | R9 |  | FALSE |  |  | 2019-04-26 | [8 empty] | Enrico Baez | TBD | NO | 2019-09-18 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
19P000428 |  | 19P000428 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES AVC OFFICE PREPARATION |  | STUDENT SERV | 3102 | CANCELED BY CLIENT | LaRae Lundgren | Emily Engelschall, Sean Cason | ANGIE GRAY |  |  |  | 0 |  | FALSE |  |  | 2019-01-03 | [8 empty] | Enrico Baez |  | N/A | 2019-01-22 | SPRING 2019 | FS | FALSE | 2019 | 2021-03-16
19P000627 |  | 19P000627 | FALSE | GSOE | SL5 SPROUL HALL, RM 2120- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2120 | CANCELED BY CLIENT | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 | 2 | TRUE |  |  | 2019-05-15 | [6 empty] | 01/29/20 O-ANS: Canceled per email from customer Karen Naples: "I’ve checked with Sally and this request to paint the Sproul 2120 office can be cancelled. We will submit a new work order if we need to have the office painted at a later time." 08/13/19 O-ANS: Customer requested that project be moved to Fall 2019 list for prioritization. |  | Paul Ditty |  |  | 2019-01-29 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16
19P000293 |  | 19P000293 | FALSE | ITS | SL5 PAINT ESTIMATE REQUEST |  | TELEPHONE |  | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-21 | [6 empty] | n/a |  | Paul Ditty |  | N/A | 2018-10-24 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000252 |  | 18P000252 | FALSE | ITS | SL5 CHASS INT S REPLACE ELECTRICAL SCREENS |  | CHASS INT S | 2130 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | JORGE MACIAS |  | Dan Lerman |  | 1 | 2 | FALSE |  |  | 2017-12-21 | [7 empty] | 2018-06-21 | Enrico Baez |  | YES | 2019-01-24 | Summer 2018 | FS | FALSE | 2017 | 2021-03-16
18P000194 |  | 18P000194 | FALSE | ITS | SL5 TELEPHONE WINDOW REPLACEMENT |  | TELEPHONE | 101 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 5 | 6 | FALSE |  |  | 2017-11-20 | [6 empty] | 07/23/19 O-ANS: Canceled by customer per notes in FAMIS. |  | Enrico Baez |  | YES | 2018-10-19 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
17P000254 |  | 17P000254 | FALSE | PB&A | SL5 FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS | Emergency Egress | CORP PP WHSE | 0106B | CANCELED BY CLIENT | Gerry Bomotti | TBD | DALAN DINH |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-06-07 | Install data and power | [5 empty] | 05/08/19 O-ANS: Canceled by customer per email from Deborah McWilliams. .2/1/19, DL; Material is ordered with a 4-6 week lead time. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DD 10/6: On hold pending discussion on space…..DL, 7/11/18; I understand there is movement on this project but I need to check in with John P. or Chris P. for a status update. |  | John Peraino |  | NO | 2019-04-05 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
19P000208 |  | 19P000208 | FALSE | PB&A | SL5 PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | Canceled per customer on priority list 9/17/18 | THE PLAZA |  | CANCELED BY CLIENT | Gerry Bomotti | TBD | CARLA CHAPPLE |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-14 | [8 empty] | Enrico Baez |  | NO | 2018-09-17 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000369 |  | 18P000369 | FALSE | PB&A | SL5 BOYCE X-RAY IRRADIATOR PROJECT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 1407 | CANCELED BY CLIENT | Gerry Bomotti | TBD | KAREN JANIGA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-27 | [6 empty] | 12/14/18, DL; This project was cancelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……DL, 5/9/18; Need to work on plans/permits…..DL, 6/16/18; Meeting with Bob and confirmed what is needed. I will work with Gunther on plans. Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall…..DL, 11/7/18; Material is on site. We will schedule the work soon…… |  | Enrico Baez |  | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18W009630 |  | 18W009630 | FALSE | PB&A | SL5 BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. | PHYS PL STOR | 100 | CANCELED BY CLIENT | Gerry Bomotti | TBD | JUDY HODGE |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-22 | [6 empty] | 3/28/19, DL; This project is cancelled per Judy Hodge….DL, 6/16/18; Project includes demo wall/door install new wall, dry wall, paint, door, eletrical outlets, lighting, smoke relocation, lighting motion, new t-bar, relocate heat pump, andn install new carpet…...DL, 7/11/18; Need to work on plans….. Target complete date is late Fall..... |  | Enrico Baez |  | YES | 2019-03-28 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18W011772 |  | 18W011772 | FALSE | PB&A | SL5 PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | Canceled per customer on priority list 7/3/18 | PRINT MOD |  | CANCELED BY CLIENT | Gerry Bomotti | TBD | PRISCILLA MARTIN |  | Dan Lerman |  |  | Canceled | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/29/18; Pasted from WO; install an outside electrical outlet based on the attached amazon specs. also estimate for removing and sealing the outside vent from the copier. fyi_the copier will be moving within the next few months…..DL, 7/11/18; Need to verfy scope and schedule the work...... |  | Enrico Baez |  | YES | 2018-07-03 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
20P000169 |  | 20P000169 | FALSE | PB&A | SL5 LOTHIAN LO-G104-OFFICE - JOB WALK FOR REMODEL OF SCOTTY'S |  | LOTHIAN HALL | SCOTTY'S | CANCELED BY CLIENT | Gerry Bomotti | TBD | FRED OFFENEY |  | John Peraino |  | - |  | FALSE |  |  | 2019-10-09 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000241 |  | 19P000241 | FALSE | PB&A | SL5 PATCH/PAINT IN OFFICE 2122 HINDERAKER |  | HINDERAKER | 2122 | CANCELED BY CLIENT | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-06 | [8 empty] | Paul Ditty |  | N/A | 2018-09-13 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000235 |  | 19P000235 | FALSE | PB&A | SL5 RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | Customer to determine scope of work. | ABER INVER | A0100 | CANCELED BY CLIENT | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 11 |  | FALSE |  |  | 2018-09-04 | [6 empty] | JP 04/04/19 Project cancelled per Housing/Lisa | 2018-11-01 | Enrico Baez |  | YES | 2019-04-04 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000483 |  | 18P000483 | FALSE | PB&A | SL5 INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | FS to coordinate with customer to scope the work. | PARKING LOT 1 |  | CANCELED BY CLIENT | Gerry Bomotti | TBD | AMANDA GREY |  | Enrico Baez |  | 7 |  | FALSE |  |  | 2018-06-26 | [6 empty] | Waiting for Amanda Grey to verify ownership of chain link fence. Once confirmed will contract with De Anza to install 36" wide gate. | 2018-08-29 | Enrico Baez |  | YES | 2018-12-03 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000095 |  | 18P000095 | FALSE | PB&A | SL5 THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS |  | THE PLAZA | A0013 | CANCELED BY CLIENT | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Enrico Baez |  | C | HOLD | FALSE |  |  | 2017-09-08 | [6 empty] | 4/11/EB-On Hold per Robert Brumbaugh. 6/8 EB-emailed R. Brumbaugh for status update. |  | Enrico Baez |  | YES | 2018-06-08 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
19P000573 |  | 19P000573 | FALSE | PB&A | SL5 UNIVERSITY VILLAGE PAINT /REMOVE NAILS |  | UV BLDG B | 0208L | CANCELED BY CLIENT | Gerry Bomotti | TBD | JUDITH ABBEY |  | Paul Ditty |  | R2 |  | FALSE |  |  | 2019-04-11 | [6 empty] | 06/14/19 O-ANS: Canceled by Customer via email from Georgianne Carlson "Project 19P000573, UV Room 208L. Human Resources Department has withdrawn the request for this patch and paint project. Not a priority, at this time." |  |  |  |  | 2019-06-14 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 |  | 1
19P000033 |  | 19P000033 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT | Duplicate request to 19P000030; Canceling project to be completed on other request. | OLMSTED | 2301 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | Duplicate to project 19P000030. Canceling project. |  | Paul Ditty |  | N/A | 2018-10-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000199 |  | 20P000199 | FALSE | SoB | SL5 ANDERSON SO RM 0002 - KEYLESS ENTRY MINOR RENOVATION REQUEST |  | ANDERSON 2 (S) | 2 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG | KENNETT LAI | Dan Lerman |  | - |  | FALSE |  |  | 2019-10-25 | [8 empty] | Enrico Baez |  |  | 2019-11-14 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19S000833 |  | 19S000833 | FALSE | SOM | Add access control to entry doors |  | HECKMAN ICEM | Entry Doors | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-07-17 | [8 empty] | Enrico Baez |  | YES | 2018-09-19 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000380 |  | 18P000380 | FALSE | SOM | SL5 SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 | SOM RSCH | 330 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-05 | [6 empty] | Canceled per customer on 8/22/18. |  | Enrico Baez |  | NO | 2018-08-22 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
20P000059 |  | 20P000059 | FALSE | SOM | SL5 SOME 2626- PATCH & PAINT |  | SOM EDUC | 2626 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-08-05 | [6 empty] | 11/26/2019 O-ANS: Project canceled per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000410 |  | 19P000410 | FALSE | SOM | SL5 PAINT OFFICES AT UC PATH |  | INTELLICTR |  | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-14 | [6 empty] | 06/06/19 O-ANS: Canceled per customer request. Paul spoke with customer who will outsource work. |  |  |  |  | 2019-06-06 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
19P000658 |  | 19P000658 | FALSE | SOM | SL5 SOM RB- PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD - PLACEHOLDER PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 03/05/20 O-ANS: Canceled by client per Cynthia Carolina. |  | Enrico Baez | TBD | NO | 2020-03-05 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000659 |  | 19P000659 | FALSE | SOM | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 5 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 08/05/20 O-ANS: Canceled by client (Cynthia Carolina) via email with Ron Veloz. 8/5/20, DL: Dan to follow -up with customer…………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "remove 330 from work order / update project details / Update: Furniture on order 3.30.2020 - delivery tbd" |  | Enrico Baez | TBD | NO | 2020-08-05 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
18P000270 |  | 18P000270 | FALSE | SPP | SL5 CHASS INT S- EVALUATION FOR REMODEL |  | CHASS INT S | 4133 | CANCELED BY CLIENT | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Dan Lerman |  | 4 | 2 | TRUE |  |  | 2018-01-16 | [6 empty] | 4/24/18 EB- Per Christina Wong, no loner needed……DL, 5/5/18; Project is cancesled per notes DND 7/27; Please follow up with customer on the status and need for the work; customer advised to me that Dan has the scope of work for completion. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. |  | Enrico Baez |  | YES | 2018-04-24 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000476 |  | 18P000476 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER & DRYER | Canceled project, work completed on 18W015691 in July. | BOYCE | 6444 | CANCELED BY CLIENT | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-14 | [6 empty] | Duplicate to 18W015691; complete |  |  |  | NO | 2018-07-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000206 |  | 20P000206 | FALSE | VC-STU AFF | SL5 COSTO HALL 111-HUB 353/381- RENOVATIONS - CP0003486 |  | COSTO HALL | Lower Level | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | - |  | FALSE |  |  | 2019-11-01 | [8 empty] | Enrico Baez |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000431 |  | 19P000431 | FALSE | VC-STU AFF | SL5 STUDENT SERVICES REMOVE NAILS AND PATCH WALL |  | STUDENT SERV | 2128 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | VALERIE SANCHEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-04 | [6 empty] | 6/24/19 O-ANS: CANCEL WO/PROJECT PER DONNA POWELL EMAIL. |  |  |  |  | 2019-06-24 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
20P000073 |  | 20P000073 | FALSE | VC-STU AFF | SL5 HUB - THE WELL -3RD FL RM 346 DOOR INSTALLATION CP00003544 | DOOR INSTALLATION | HUB | 346 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | JONATHAN GODOY |  | Dan Lerman |  | PENDING |  | FALSE |  |  | 2019-08-12 | [6 empty] | 12/13/19 O-ANS: Project canceled by client Brendan O-Brien. | 2019-10-02 | Enrico Baez | 1.) Remove Aluminum accordian door from opening. Customer to determine how to discard. 2.) Frame opening with metal 2"x4" stud and sheet with 3/4" drywall. Allow for oppening to accommodate 36"x 80" door. 3.) Install metal door jamb and casing to match exisiting openings. Door to match exisiting. Campus Fire Marshall to determine if door to be fire rated. Swing to be approved by Campus Building official and/or Campus Fire Marshall. 4.) Relocate single gang outlet on North side of opening , if needed. 5.) Finish drywall, prime and paint walls. Texture to match exisiting. Customer to approve final paint color. | YES | 2019-12-13 | FALL 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000198 |  | 18P000198 | FALSE | VC-STU AFF | SL5 HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Install new Wall lights | HUB | 0 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | R1 | 5 | FALSE |  |  | 2017-11-21 | Canceled per Brendan. No funding | [5 empty] | 10/30/19, DL: This project is on Hold and may be canceled as funding is not availabel at this time. Plans are approved……10/16/19, DL; Plans were submitted for plan check review last week. I also notified Brendan that this will be a recharge project . The ball park estimate I provided to Brendan was $7,000 - $9,000. Brendan needs to confirm if funds are available. If funds are available, I will have a contractor bid on the project……… 10/16/19: O-ANS - Not a CORE location so project changed to Recharge. 10/1/19, DL; Plans will be submitted a building permit and plan check review this week…….9/3/19, DL; Gunter has plans at 60%, We will try and submitt with in the next two weeks. 8/14/19, DL;This project is now on Gunther's bench. Gunter will start the process in about 2- weeks and we should have plans top submitt with in the next 30- days….6/17/19, DL; I will walk this work in the next two weeks and work on plan to submit to our campus architech and building official for review…..DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…… | 2018-01-23 | Enrico Baez |  | YES | 2019-10-30 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16 | FY 19-20 | 1
20P000184 |  | 20P000184 | FALSE | VC-STU AFF | SL5 HUB 261 - CONSTRUCT WALL FOR MEETING/CONFERENCE RM | In HUB 261 the administration is requesting a wall be constructed to create a meeting/conference room. We need a building zone manager to walk the area give estimate as well as reaching out to the fire marshals inspector for recommendations. | HUB | 261 | CANCELED BY CLIENT | Brian Haynes | Cathy Eckman | Manny Sanchez |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-10-17 | [6 empty] | 02/07/2020 O-ANS: Canceled due to client request. | 2019-11-05 | Enrico Baez | 11/5/19 E.Baez conducted site visit. **********SCOPE********* 1. Construct, full height, partition wall with door in HUB 261. 2. Provide/install ADA compliant door in new partition wall. 3. Add and relocate fire sprinkler. 4. Re-position lighting in ceiling, add lighting control. 5. Patch and paint. 6. Install base board. 7. Add strobe and smoke detectors. 8. T-bar ceiling re-work. | YES | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000225 |  | 20P000225 | FALSE | VC-UNIV ADV | SL5 HINDERAKER 0137 - BASEMENT RESTROOM SINK INSTALL | Install Kitchen Sink in entry room of Restroom 0137 | HINDERAKER | B137 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL | KIM MCDADE | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-11-15 | [6 empty] | 1/22/20 O-ANS: Canceled per customer request. | 2020-01-22 | Enrico Baez |  | YES | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000417 |  | 19P000417 | FALSE | VC-UNIV ADV | SL5 UNIV VILL OFFICE LEASE 201-(P) INSTALL KEY PAD FOR OFFICE ENTRY |  | UV BLDG A | 201 | CANCELED BY CLIENT | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2018-12-18 | Schedule the work | 2019-08-14 | 2019-12-28 | [5 empty] | Enrico Baez |  |  | 2019-08-06 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20 | 1
19P000272 |  | 19P000272 | FALSE | ATHLETICS | SL5 NEED URINAL DIVIDERS | FS to coordinate with customer to scope the work. | ATH DANCE | 50E | CANCELED BY FS | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  |  |  | 13 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez |  |  | 2019-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000274 |  | 19P000274 | FALSE | ATHLETICS | SL5 RIV SPORTS CPX - REPLACE URINALS | FS to coordinate with customer to scope the work. | W LCKRM/CONC |  | CANCELED BY FS | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  |  |  | 15 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-10-15 | Enrico Baez |  | YES | 2019-01-24 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000647 |  | 19P000647 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- LOCKER ROOM REFRESH |  | ATH DANCE | Men's & Women's Locker Rooms | CANCELED BY FS | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-23 | [6 empty] | 6/19/19 O-ANS: Combined with project 19P000646 since work in the same area. Dan Lerman to perform scope. |  | Dan Lerman |  |  | 2019-06-19 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
19P000266 |  | 19P000266 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty |  | N/A | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000269 |  | 19P000269 | FALSE | ATHLETICS | SL5 ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | Project is not within the purview for completion; condition is fair and usable. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  |  |  | 5 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18…..This is a cooman area. Is this recharge work……. | 2018-09-27 | Enrico Baez |  | YES | 2018-10-04 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000445 |  | 19P000445 | FALSE | BCOE | SL5 BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT |  | BOURNS | B0328D | CANCELED BY FS | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  |  |  | 0 |  | FALSE |  |  | 2019-01-11 | [8 empty] | Enrico Baez | Install new wall at room 0328 | N/A | 2019-02-27 | SPRING 2019 | FS | FALSE | 2019 | 2021-03-16
19P000059 |  | 19P000059 | FALSE | BCOE | SL5 CHUNG HALL 201 SECURITY SYSTEM INSTALL | ITS to install cameras, no work by FS Required. | CHUNG HALL | 201 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | MAGARET SOUDER |  | Dan Lerman |  | 10 | 7 | FALSE |  |  | 2018-07-17 | [6 empty] | DND 7/30/18 Project #19P000059 to replace REF CPMS # 9054 Ron to speak with ITS to complete installation. |  | Enrico Baez |  | YES | 2018-07-30 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000621 |  | 19P000621 | FALSE | BCOE | SL5 BOURNS, RM A0308- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0308 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2019-05-14 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000435 |  | 19P000435 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR WEST HALLWAYS - FLOORING | FS to coordinate with client to scope work. | BOURNS | A0145 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-19 | [6 empty] | 2/14/19, DL; This project was a repair and not complete replacement | 2018-10-25 | Enrico Baez |  | YES | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000233 |  | 20P000233 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - A169 & A170 ENTRY AREA DAMAGED |  | BOURNS | A169 & A170 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-11-22 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000210 |  | 20P000210 | FALSE | BCOE | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | Reduce noise. Replace doors with solid core doors and install an Acoustic Door Seal Kit. | CHUNG HALL | 224 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-11-05 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……. | 2020-02-11 | Enrico Baez | Removal of the existing double doors and door hardware, install new solid core double doors with continuous hinges, install new acoustical jamb seals, threshold seal and a surface mounted Automatic Door Bottom utilizing a flat spring mechanism, which activates when closing the door, lowering a neoprene seal insert against the floor or threshold to create a sound seal. Install acoustic double door astragals with seal. Reinstall all existing door locksets, and door closers. Quote received from Brad Aduddell-American Door to perform this work. Quote & Specs are available in the project folder. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000624 |  | 19P000624 | FALSE | BCOE | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | Refurbish Room-Student Space, | BOURNS | A0346 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-05-15 | Pending information from Susanna | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Susanna is working on a cubicle layout. Once we have the information from her. We will schedule the work………… | 2019-11-07 | Enrico Baez | Remove all lower cabinets in room A0346 and all lower cabinets and mail boxes in Rm A0304 | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
20P000039 |  | 20P000039 | FALSE | BCOE | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE |  | BOURNS | A0318 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-05-13 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……..09/19/19 O-ANS: HOLD FOR WINTER 2020 PER CUSTOMER (LOUIS SANDOVAL) REQUEST. EMAILED PAUL DITTY TO CONFIRM. PAUL STATED THIS IS NON-PAINT PROJECT B/C SCOPE OF WORK INCLUDES CARPENTERS AND ELECTRIC SHOPS. |  | Paul Ditty |  |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000620 |  | 19P000620 | FALSE | BCOE | SL5 BOURNS, RM A0304- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0304 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Paul Ditty |  | 9 |  | TRUE |  |  | 2019-05-14 | [6 empty] | 05/22/20 O-ANS: CANCELED BY FS per Paul Ditty - Customer unable to confirm availability of room for renovation. Project older than one year since submission and canceled per FS policy. 01/23/20 O-ANS: Room is unavailable per customer and currently placed on HOLD until room is available. Customer to follow-up when available. |  |  |  |  | 2020-05-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000427 |  | 19P000427 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | Install Power and TV bracket, move white board | CHUNG HALL | 453 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2019-01-03 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold……… | 2019-09-18 | Enrico Baez | Install Power and TV bracket, remove white board and relocate , patch and paint wall prior to installing | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21 | 1
19P000502 |  | 19P000502 | FALSE | BCOE | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | Install Electrical power & TV bracket.for a 75" TV to mount in CS 342. | CHUNG HALL | 444 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | RICHARD BAIN |  | Dan Lerman |  | R3 |  | FALSE |  |  | 2019-02-19 | Schedule the work. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This project is on hold……………3/25/20, DL: Work orders are produced. I will work on scheduling the work when we return back to work…….. | 2019-09-17 | Enrico Baez | Install Electrical power & TV bracket. Excludes network/data back box and stub up to ceiling. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21 | 1
18P000121 |  | 18P000121 | FALSE | CAMPUS | SL5 PHYSICS HYDRATION STATION - PHYSICS HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | order parts | 2019-04-20 | 2019-05-31 |  |  |  | 5/1/19, DL; Per Chris, we will not be compelting this project. There is currently a Water dispenser on the drinking fountain. 3/28/19, DL; We will look into installing a bottle filler on this fountain verse a complete change out…..12/6/18, DL; This project is currently on hold…… DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman |  | NO | 2019-05-01 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
18P000122 |  | 18P000122 | FALSE | CAMPUS | SL5 MS&E HYDRATION STATION - MS&E HALL |  | PHYSICS | 0 | CANCELED BY FS |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman |  | NO | 2018-04-02 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
19P000212 |  | 19P000212 | FALSE | CAMPUS | SL5 REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500A | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000211 |  | 19P000211 | FALSE | CAMPUS | SL5 LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | Reviewing campus standards for these project requests. | LIFE SCIENCE | 2545 | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000188 |  | 19P000188 | FALSE | CAMPUS | SL5 PAINT - HALLWAY DOORS & INSIDE RESTROOMS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500 | CANCELED BY FS |  |  | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-16 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000400 |  | 19P000400 | FALSE | CHASS | SL5 CREATE DOOR INTO HALLWAY | Create a door between the hallway and CHASS INTS 2117A. The door should be placed at the south end of 2117A. | CHASS INT S | 2117A | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 103 |  | FALSE |  |  | 2018-12-06 | [6 empty] | 05/21/19 O-ANS: Canceled by FS per conversation with Paul Richardson and combined with Project 19P000419. | 2019-04-15 | Enrico Baez | Add additional door into space 2117. Door in concrete wall was original location. Would require engineering. Suggest alternate location. | YES | 2019-05-21 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16
19P000355 |  | 19P000355 | FALSE | CHASS | SL5 HYDRATION STATION FOR THE SECOND FLOOR WATKINS | Hydration station installed where the water fountain is. | WATKINS | 2122D | CANCELED BY FS | Juliet McMullin | Cindy Williams | CYNTHIA REDFIELD |  | Dan Lerman |  | 112 |  | FALSE |  |  | 2018-10-22 | [8 empty] | Enrico Baez |  |  | 2019-04-24 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16
20P000183 |  | 20P000183 | FALSE | CHASS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | Install side walk | HUM & SOC SC | 1202 | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2019-10-18 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Also Existing door is compliant and there are other accessible exits to the building… 8/5/20, DL: This Project is on hold until further notice……. | 2019-11-13 | Enrico Baez | Construct Side walk. ADA compliance not required. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21 | 1
18P000312 |  | 18P000312 | FALSE | CNAS | SL5 URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 |  | PARKING LOT P 42 |  | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Dan Lerman |  |  | 38 | FALSE |  |  | 2018-02-13 |  | 2019-02-04 | 2019-04-16 | [5 empty] | Enrico Baez |  | YES | 2018-09-19 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19W007474 |  | 19W007474 | FALSE | CNAS | SL5 BG - RAILROAD TIE WALLS | Repair Railroad Ties at Botanic Gardens | BOTAN INFO C |  | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV | [5 empty] | FALSE |  |  | 2018-11-07 | [7 empty] | 2018-12-10 | Enrico Baez | Request For "ESTIMATE" to repair the raillroad ties used as a retaining wall at botanic gardens. | YES | 2019-03-11 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000185 |  | 20P000185 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR (OFF WHITE) |  | PHYSICS | 3004S | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-18 | [6 empty] | 11/01/19 O-ANS: Canceling bc duplicate of 20P000187. Paul Ditty to speak with customer re: room. |  | Paul Ditty |  |  | 2019-11-01 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000242 |  | 20P000242 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 10 |  | TRUE |  |  | 2019-11-25 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000324 |  | 19P000324 | FALSE | CNAS | SL6 SPIETH HALL ASSESS AIR VENT OR PURIFIER FOR LAB | Provide the single pass exhaust, air changes (6-12 ACH) and the negative air requirements for PI to perform surgeries in the room. | SPIETH | 1312 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 106 |  | FALSE |  |  | 2018-10-05 | [7 empty] | 2018-10-10 | Enrico Baez | Upgrade infrastructure to accomodate surgical procedures in room 1312. | N/A | 2019-04-04 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16
19P000438 |  | 19P000438 | FALSE | CNAS | SL5 BOTANIC GARDENS RAILROAD TIE WALLS | Request for review and cost estimate for the repair of two railroad tie walls in the Botanic Gardens. 1) Retaining wall located below the Iris Garden (across from the Greenhouse). 2) Low wall located along the pathway just below the Garage Office. | BOTAN INFO C |  | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Dan Lerman |  | 118 |  | FALSE |  |  | 2019-01-08 | [8 empty] | Enrico Baez | 03/05/19 O-RVL: RV noticed two requests on the O-UA1 bench and updated notes on this (19P000438) request with notes from 11/07/18 to 03/01/19. END ~ 03/01/19 O-RVL: RV will walk with Chad C to determine if FS is capable of repair/reinstall railroad ties true & plumb. Site walk is scheduled for 03/01 afternoon. END ~ 02/15/19 O-RVL: Updated SOW, RV will schedule a site visit with the Carpentry Supervisor to determine the construction feasibility and estimated costs. END ~ 01/09/19 O-RVL: REQUEST FOR ESTIMATE, Not a Project. RV To schedule a site visit with C. Pillen and Chad Chambers to evaluate if repairs are possible. ~ 12/10/18 O-RVL: REQUEST FOR ESTIMATE. Ron V walked with D. McWilliams & Jodie and identified the railroad tie retaining wall area requiring repairs. Jodie would like an estimate to repair the leaning railroad ties at specified areas. RV to meet with Chris P. and or Chad Chambers to determine if FS can perform work and or provide an estimated cost to perform work. ~ 11/07/18 O-RVL: Received an email form Deborah Mc. to discuss the wall at Thursday during our 1-1 meeting |  | 2019-03-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
18P000354 |  | 18P000354 | FALSE | CNAS | SL5 GH16-25 COOLING SYSTEM REPAIR |  | GH 16 25 |  | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | MARK TANKERSLEY |  | Dan Lerman |  | 13 | 17 | FALSE |  |  | 2018-03-20 | [6 empty] | DL, 7/25/18; Reviewed Ron V. noted. I will check in with Chris on this to better determin the method complete this project. |  | Dan Lerman |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
20P000238 |  | 20P000238 | FALSE | CNAS | SL5 SKYE 366 - PATCH AND PAINT |  | SKYE HALL | 366 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 14 |  | TRUE |  |  | 2019-11-25 | [6 empty] | 12/13/19 O-ANS: Canceled by FS because duplicate of project # 20P000238. |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000618 |  | 19P000618 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 205 AND 205A- PAINT |  | COLL BLDG NO | 205 AND 205A | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 06/11/19 O-ANS: Per Paul, conference room was in decent condition and does not need to be repainted. He will speak with customer to explain. |  |  |  |  | 2019-06-11 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
18P000480 |  | 18P000480 | FALSE | CNAS | SL5 BG - LOWER RESTROOMS-PAINTING-FLOORS | Canceled by Facilities Services; Work is not within the SLA and is not needed. | BOTGDN RSTRM |  | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000614 |  | 19P000614 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 202- PAINT |  | COLL BLDG NO | 0202 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19W003012 |  | 19W003012 | FALSE | CNAS | SL5 FIX RESTROOMS (PAINT AND FLOORS) | FS to coordinate with client to schedule work for completion. | CHAPMAN | 5 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | 51 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty |  | N/A | 2018-12-13 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000616 |  | 19P000616 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 208- PAINT |  | COLL BLDG NO | 208 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000617 |  | 19P000617 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 212- PAINT |  | COLL BLDG NO | 212 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 07/16/19 O-ANS: Per Paul Ditty, consolidated with projects 19P000613 & 19P000615 and coorinated with customer Ronda Inzunza regarding consolidation and move. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000234 |  | 19P000234 | FALSE | CNAS | SL5 PHYSICS 3005-WALL HOLES PATCH |  | PHYSICS | 3005N | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | JAZMIN CHAVEZ |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-09-04 | [6 empty] | **9/19/18 DUPLICATE REQUEST SENT IN SEE 19P000246 |  | Paul Ditty |  | N/A | 2018-09-19 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  | R7 |  | FALSE |  |  | 2019-02-27 | We Need an FAU # | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced. We will schedule the work when we return from campus closure………11/11/19, DL: Project is in the queue to start but we do not have an FAU# as this is a recharge project. I sent Enrico and James an email requesting the FAU#. Once we have an FAU #, I will work on scheudling the work…..10/1/19, DL; Enrico is wtill working on estimate. | 2018-10-19 | Enrico Baez | E. Baez 1. Provide power in ceiling for projector. 2. Install projector center in room between two 4ft light fixtures. 3. Install 2 duplex outlets in 4S box on South West corner of room 4. Remove existing screen. 5. Install new screen centered on South wall. Extend power from existing screen to new screen location. 6. Use existing screen power switch to control new screen. | YES | 2020-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21 | 1
19P000543 |  | 19P000543 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 342-WALL INSPECTION | TV Bracket &Power/Network box. | CHEMICAL SCI | 342 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | JEFFERY MATUTE |  | Dan Lerman |  | R8 |  | FALSE |  |  | 2019-03-21 | [7 empty] | 2019-10-01 | Enrico Baez | "The Chemistry Department is purchasing a 75" TV to mount in CS 342. The wall that will hold the TV needs to be inspected before any action of mounting the TV is done. The wall that we are hoping to place is the Brown-ish wall, where the projector screen is, opposite to the single whiteboard (Upon entry of CS 342, the leftmost wall). We would like a electrical outlet behind the TV, if possible". RV-Cut back sound proofing (sound soak) to accommodate TV brkt & electrical. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
19P000645 |  | 19P000645 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UCR BOTANIC GARDEN GATE HOUSE-EXT PROJECT | Termite Treatment/Cover Gate House and repair roughtd woos as necessary | BOTAN INFO C |  | CANCELED BY FS | Susan Marshburn | Da Lan Dinh | RONALD ANDERSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2019-05-22 | [8 empty] | Enrico Baez | BOTANIC GARDEN GATE HOUSE (AND OTHER STRUCTURES) REQUIRES EXTERMINATION OF TERMITES- WITH INSPECTION RESULTS RECEIVED BY ERS |  | 2019-08-29 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
18W007453 |  | 18W007453 | FALSE | ITS | SL5 (P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-11-30 | waiting for bid from contractor | 2019-04-01 | 2019-06-29 |  |  |  | 07/22/19 O-ANS: Work Order converted to project # 19P000433. For further updates, see 19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; WE have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  |  |  |  | 2019-07-22 | Winter 2019 | FS | FALSE | 2017 | 2021-03-16 | FY 19-20
19W002419 |  | 19W002419 | FALSE | ITS | SL5 ITS CENTER - INSTALL CARD READER ACCESS |  | ITS CENTER | 161 | CANCELED BY FS | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-08-09 | [11 empty] | 2019-01-08 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000188 |  | 20P000188 | FALSE | LIBR | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 |  | ORBACH LIB | 204 | CANCELED BY FS | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-10-23 | Obtain floor covering samples | [5 empty] | 11/19/20 O-ANS: Declined to move forward by FS Admin but may revisit in future prioritization period. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: We are working on floor covering samples that will work for the space. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000317 |  | 19P000317 | FALSE | PB&A | SL5 HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 | conversation with Susan Marshburn and Bob Brumbaugh. | PENTLAND A |  | CANCELED BY FS | Gerry Bomotti | TBD | RICHARD GEIGER | [5 empty] | FALSE |  |  | 2018-10-03 | [11 empty] | 2019-01-14 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000233 |  | 19P000233 | FALSE | PB&A | SL5 PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | FS to coordinate with customer to scope the work. | MAIL | 884 | CANCELED BY FS | Gerry Bomotti | TBD | AMY EVERETT |  |  |  | 12 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Enrico Baez |  | YES | 2018-09-24 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000162 |  | 20P000162 | FALSE | PROVOST/EVC | SL5 HINDERAKER 1101B - PATCH HOLE IN WALL |  | HINDERAKER | 1101B | CANCELED BY FS | Thomas Smith | Luisa Levario | AMY GU |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-07 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000192 |  | 20P000192 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 1st Floor | CANCELED BY FS | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-10-23 | [6 empty] | 01/07/20 O-ANS: Project canceled by FS. Paint work determined to be in public non-assignable space and added to Facilities Services deferred maintenance list for future completion. |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000400 |  | 18P000400 | FALSE | SOM | SL5 Covert suite 1116 and suite 1126 to office space | Provost has placed a hold on converting lab spaces into office spaces. | WEBBER | 1116 & 1126 | CANCELED BY FS | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-14 | [6 empty] | DL, 6/16/18; Waiting for update on Provost approval….DL, 7/11/18; Per email from Enrico on 7/10/18. The Provost put a hold on converting any lab space into officess…… |  | Enrico Baez |  | YES | 2018-07-10 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000662 |  | 19P000662 | FALSE | SOM | SL5 FY19-20 PROJECT: DEANS CONF ROOM | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | SOM EDUC | 2652 | CANCELED BY FS | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-06-12 | [8 empty] | Enrico Baez | Repair/replace or retouch up the spots on the wood veneered panels in the Dean's conference room. | NO | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000249 |  | 19P000249 | FALSE | SOM | SL5 SOME-INSTALL LOCKERS | Lockers on order by customer; upon arrival to be installed. | SOM EDUC |  | CANCELED BY FS | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-07 | [6 empty] | DL, 11/7/18; It is my understanding the lockers are ordered, but we donot have a confirmed delivery date. Once the material is on site, we will schedule the installation…… |  | Enrico Baez |  | YES | 2019-02-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000197 |  | 20P000197 | FALSE | VC-RED | SL5 UOB 210 - SOUND PROOF INSTALLATION |  | UNIV OFC BLD | 210 | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-10-24 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
20P000047 |  | 20P000047 | FALSE | VC-RED | SL5 ADVANCED NEUROIMAGING | NEEDING TO TAKE DOWN OVERHEAD CABINETRY AND REPLACE WITH SOME KIND OF SHELVING TO OPTIMIZE SPACE. LOOKING FOR AN ESTIMATE AND A PLAN. | ADV NEURO |  | CANCELED BY FS | Rodolfo Torres | Laura Manor | CHELSEA EVELYN |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-07-31 | pending material delivery. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice…….3/23/20, DL: Shelves are ordered. We will schedule the work when we return from the campus closure……….1/15/20 O-DHN: Emailed Status Report to customer…...1/14/20, DL: We waiting for a revised quote from the vendor as there quote was not complete. We will process the quote for a PO# when we receive the correct quote……. 11/11/19, DL: Need to review scope with Ron as the shelving system is a special order item with a 3- month lead time….. | 2019-09-24 | Enrico Baez | Remove 5'-0" x3'-0" upper cabinet, and soffits. Patch and paint walls to match the existing grey . Install customer furnished adjustable shelf. | YES | 2020-11-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice. | 2018-09-27 | Enrico Baez |  | YES | 2020-11-19 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 20-21
19P000534 |  | 19P000534 | FALSE | VC-STU AFF | SL5 PATCH WALLS AND PAINT |  | HEALTH SERV | 334 | CANCELED BY FS | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-03-15 | [6 empty] | 12/06/19 O-ANS: Canceled by FS because unable to identify room location even after inspecting rooms with staff support. Original requester has since retired. |  |  |  |  | 2019-12-06 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000309 |  | 20P000309 | FALSE | VC-UNIV ADV | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES |  | 1955 CHICAGO | 200 | CANCELED BY FS | Peter Hayashida | Naysia Caldwell | SARAH KARSON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-10 | [6 empty] | 12/16/20 O-ANS: Canceled by FS - Project location not serviced as FS CORE location and reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Please retain project # as reference. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2020-12-16 | Spring 2020 | FS | FALSE | 2020 | 2021-03-16 | FY 20-21
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Commencing Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Rowan Reid | 1 |  |  | FALSE | 1150000 |  | 2016-12-15 | Completion of Basis of Design | [12 empty] | PD&C | FALSE | 2016 | 2021-03-16
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | COMPLETE | Kim Wilcox | TBD | ALEXIS RAMBAUD |  | Dan Lerman |  | 1 | 0 | FALSE |  |  | 2018-12-11 | schedule the work | 2019-01-21 | 2019-03-27 |  |  |  | 8/5/20, DL: This project is complete…………3/25/20,DL: Doors are scheduled to arrive the second week in April……2/19/20 O-DHN: Emailed Status Report to customer……2/18/20, DL: Work is complete except for Door and final deep cleaned I do have final stain samples from the vendor. I need to verify color……… We will complete the project when the doors arrive……….1/14/20, DL: Plans are approved, PO# is cut for the ordering of the custom doors, we are currently scheduled to start the work on or shortly after 1/21/20,. Karim understands that we will start and finish the project but we will not be able to install the door until the door arrives on site. There is a minimum of 6-8 week lead time on the door delivery………….12/16/19, DL: Plans are still in plan check review. I sent the building department an email asking for a startus update today…….10/16/19, DL; Plans were submitted to our building official this week for plan check review and a permit……9/16/19, DL; Guther will work on plans in the next three weeks. Once plans are complete, we will proceed with the permit process… | 2018-12-20 | Enrico Baez | SOW: Wall: Construct a metal stud framed wall with drywall up to hard ceiling (ceiling has 12x12 glue up ceiling tiles). Hardware: Install new lockset & keys are required.***** French Door: Install new stain grade birch door with full lite. Door and finish to match the existing office doors.***** Hard Ceiling: * Ceiling is 8’-0” A.F.F. + - with 12x12 glue up ceiling tiles. Work may require a new access panel if access to space above is needed. The 12x12 glue up ceiling tiles may need to be removed where the new wall is constructed.***** Flooring: The existing flooring will remain. Install rubber base to match existing.***** Painting, Taping & Sanding: Taping sanding and painting is required at the new wall and connecting walls.***** HVAC: May require modifications to split the existing supply air to accommodate the open office space.***** Electrical: Provide light switch at new office, power(new or relocate); add and or relocate electrical and voice/data outlets required for a standard office.***** Lighting: Provide a new light switch/circuit near office entrance. The existing 2x4 fixture is on main lighting circuit and will require lighting circuit modifications. Verify if the existing lighting is sufficient for the proposed office. Field verify if additional lighting is required.***** Fire Alarm: Provide a new Smoke/chime detector at new office area, confirm requirements. | YES | 2020-08-05 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 20-21
19P000673 |  | 19P000673 | FALSE | SOB | SL5 ANDERSON HAL NO, RM 158- RECARPET 12 ROOMS / ELECTRICAL WORK |  | ANDERSON 1 (N) | 158 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-06-18 | Construction | 2019-09-12 | 2019-09-23 |  |  |  | 10/1/19, DL; This proect is complete… |  | Enrico Baez |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000346 |  | 18P000346 | FALSE | ATHLETICS | SL5 ATHLETICS INSTALL WALL VOLLEYBALL OFFICES |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-18 | [6 empty] | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. DL, 5/24/18; We will start working on plans in the near future.... DL, 6/16/18; Need to submit plans asap.......DL, 7/11/18; The plans were approved today. This project is scheduled to start on 7/14/18. We will will be complete will all items related to this project on 8/27/18. Note, The door and sidelite are special order items and this item will probalby have a 6-8 week lead time. Steve T is going to order the door soon.. Customer is aware of the delay for the door and is not concerned......DL, 7/25/18; Passed framing and Electrical inspection. We will be finished with the project next week except for the door and window that is ordered but has a 6-8 week lead time. DL, 8/10/18; This Project is Complete except for special order door and window.......DL, 8/22/18; Door and Glass still not on site., Will check in with Steve T on delivery date......Will also schedule final inspection for Certificate of occupancy......9/6/18; The Glass window is installed but we are waiting on the door. this projects is 98% complete.......DL, 9/19/18; The door will be shipped on 9/24/18. We will schedule the door install when the door is on site......DL, 11/7/18; This Project is 100% Complete.... |  | Dan Lerman |  | YES | 2018-11-08 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000027 |  | 19P000027 | FALSE | ATHLETICS | SL5 ATHLETICS PATCH & PAINT ROOM | 9/19/18 | ATH DANCE | 0120C | COMPLETE | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | DL, 9/19/18; This Project is 100% Complete……. |  | Paul Ditty |  | N/A | 2018-09-19 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000328 |  | 18P000328 | FALSE | ATHLETICS | SL5 HINDERAKER BASEMENT OFFICE REPAIR |  | HINDERAKER |  | COMPLETE | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-01 | [6 empty] | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with Paul. Paul will complete as in the near future. Carpet will be installed shortly after......5/21/18, Painters started paint. Should be complete with paint by the end of the week....DL, 5/24/18; Painters are complete. Jess will schedule the carpet install.....DL, 6/12/18; Project is 98% Complete. Carpenters need to under cut two doors to accomodate the carpet.....DL, 7/11/18; This Project 100% Complete..... |  | Dan Lerman |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000646 |  | 19P000646 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE, BASEMENT- PATCH/PAINT/FLOORING |  | ATH DANCE | 20R, 20S | COMPLETE | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-23 | tile wash and shower doors | 2019-08-01 | 2019-09-27 |  |  |  | 9/16/19, DL; This project is Complete…….9/3/19, DL; Project is 80% Complete. Floor covering is scheduled for this Friday. Target complete date is 9/13/19……8/15/19, DL; This project is in progress and slated for complete by the end of september…..8/1/19, DL; Project is in progress with a complete date of 3-4 weeks. |  | Dan Lerman | 06/19/19 O-ANS: Project 19P000647 was combined with this project. |  | 2019-09-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000265 |  | 19P000265 | FALSE | ATHLETICS | SL5 ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000208 |  | 20P000208 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | Men's locker room refresh | ATH DANCE | 50 | COMPLETE | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND | EUGENE HUTCHINSON | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-11-04 | [6 empty] | 1/28/21, DL: Project is complete. Paul will schedule the paint once he is back on projects……….1/19/21, DL: We will schedule the balance of the paint before the students return back to campus………..9/30/20, DL: The work is complete except for the paint……………..8/5/20, DL: The work is almost complete.……. |  | Dan Lerman |  |  | 2021-01-28 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000271 |  | 19P000271 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 |  | ATH DANCE | 3 | COMPLETE | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000295 |  | 19P000295 | FALSE | ATHLETICS | SL5 PATCH & PAINT |  | ATH DANCE | 50B | COMPLETE | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 12 | 18 - 19 | FALSE |  |  | 2018-09-12 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000270 |  | 19P000270 | FALSE | ATHLETICS | SL5 ATH DANCE-WEIGHT ROOM DROP DOWN CEILING |  | ATH DANCE | 78 | COMPLETE | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  |  |  | 14 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project is 100% Complete….. |  | Enrico Baez |  |  | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000252 |  | 19P000252 | FALSE | ATHLETICS | SL5 ATH DANCE SHOWER DOORS |  | ATH DANCE | 0050K | COMPLETE | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-10 | schedule the work | 2019-04-01 | 2019-04-26 |  |  |  | 5/31/19, DL; This project is 100% Complete……..5/15/19, DL; This work will be 100% complete this Friday…….4/15/19, DL; This project should stat is 2-weeks. We have a signed po# for the shower doors. Walked the needed tile repairs with the contractor today……..3/18/19, DL; Woring on quotes for the repairs. We will scheudle the work to be completed in the next 45- days…… |  | Enrico Baez |  | YES | 2019-05-31 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000268 |  | 19P000268 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH AND PAINT 20C |  | ATH DANCE | 20C | COMPLETE | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5 RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/5/20, DL: This Project is 100% Complete………….3/28/19, Doors are in the process of being …. DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez |  | YES | 2020-02-05 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000273 |  | 19P000273 | FALSE | ATHLETICS | SL5 ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS |  | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000267 |  | 18P000267 | FALSE | BCOE | SL5 CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-01-16 | [6 empty] | DL, 5/19/18; High table mounted on West wall to be relocated to South wall by light "Centered". Relocate white board from East Wall to West walll wher high table was removed. Paint and new flooring. Need to schedule work with Paul and Jess. BKM furniture is scheduled 4-6 weeks. DL, 6/16/18; Lower electrical outlets on North wall, repair blinds, paint and new flooring. The space is vacant as of June 16th. I will scheudle the workl.....BKM delivery is currently scheduled for July 23rd.......This project is 100% complete. There were two items added to the scope and they will be complete by 7/20/18..... |  | Enrico Baez |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000391 |  | 18P000391 | FALSE | BCOE | SL5 CHUNG HALL PATCH, PAINT, NEW FLOOR | PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN | CHUNG HALL | 446 449 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 5/5/18; Conducted scope visit with Paul and Maggie. This project is target date is August 30th. As of now, we have 10 business days to complete the work……. Dean's Office….DL, 6/16/18;Walked project with Jess and Paul. This will be a project will now incluclude flooring is 7- additional offices due to additional trip hazzards identified in 3 of 7 offices during the carpet scope. Maggie will pay four four of the office since they are still in good condition. We are still on schedule with the work.......Dan, 7/11/18; This project is still on schedule. Complete Date is 8/18/18 and scheduled to be complete on 8/31/18.....DL, 8/10/18; The project is on schedule and we will start on Monday.......Ahead of schedule, project will be complete on 8/29/18......DL, 9/6/18; This project is 100% complete. Note, Maggie did request Jess to come back and remove some glue and he has this scheduled..... |  | Dan Lerman |  | YES | 2018-09-10 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000394 |  | 18P000394 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK |  | BOURNS | A0159A | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 2 | TRUE |  |  | 2018-04-12 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………….1/15/19, DL; Sound Soak is ordered and should arrive within two weeks……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; Need to review and scheudle…….DL, 7/11/18; Still need to review and scheudle…..DL, 8/22/18; This Project is complete but Maggie wants to see if the Faculty are happy with the results. We may install Sound Soak as a final option…… DL 9/6/18; Sent Maggie an email to see if she is satified with the work performed in regards to the sound proofing. I will have an update by the next Excel update….. DL, 9/19/18; The PI is out of town. Maggie will confirm the PI is satisiofd with the work when they return……on 9/18/18…DL, 10/8/18; Customer not satisfied with first round of sound proofing. We will proceed with Sound Soak material….. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000623 |  | 19P000623 | FALSE | BCOE | HOLD SL5 WINSTON CHUNG HALL, RM 348- MOUNT TV |  | CHUNG HALL | 0348 | COMPLETE | Christopher Lynch | Todd Ambriz | BILL BINGHAM |  | Paul Ditty |  |  |  | FALSE |  |  | 2019-05-15 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000472 |  | 18P000472 | FALSE | BCOE | SL5 WCH PATCH AND PAINT WALL |  | CHUNG HALL | 458 | COMPLETE | Christopher Lynch | Todd Ambriz | JANNA LE BLANC |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000028 |  | 19P000028 | FALSE | BCOE | SL5 BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS |  | BOURNS | A0169 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | Schedule the patch and paint | 2019-04-01 | 2019-05-01 |  |  |  | 5/1/19, DL; This project is 100% Complete…..3/28/19, DL; Monitor mounts were removed, Patch and paint will be completed in the near future……2/28/19, DL; Will schedule the project to be complete the first week in April…… | 2018-11-14 | Enrico Baez |  | YES | 2019-05-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000315 |  | 18P000315 | FALSE | BCOE | SL5 BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB |  | BOURNS | B0235 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  |  | HOLD | TRUE |  |  | 2018-02-16 | [6 empty] | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction to scope, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... Need to walk project with Ron and schedule the work....DL, 5/24/18; Conducted site visit with Ron V. Ron will order material and schedule the work once material is on site.....DL, 6/16/18; Need to verify delivery date for material.......DL. 7/11/18; Plumbing is disconnected. Corey is tentatively scheduled to disconnect the Fume hood. Once the Fume hood is disconnected, we will schedule the removeal of the fume hood and start the framing of the wall. Target complete date is 8/8/18....DL, 7/25/18; Fume hood is disconnected. Need to move Fume hood and start framing target date is delayed to creep scope but should be complete near 8/16/18.....DL, 8/10/18; Carp[enters will install the wall this week. Corey has parts orders. Corey will complete the install when the material arrives.......DL, 8/22/18; This Project is Complete |  | Dan Lerman |  | YES | 2018-08-23 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000454 |  | 18P000454 | FALSE | BCOE | SL5 BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS |  | BOURNS | A0346 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  |  | 9 | FALSE |  |  | 2018-05-29 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000321 |  | 18P000321 | FALSE | BCOE | SL5 STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST |  | STUDENT SERV | 1228 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Enrico Baez |  |  |  | FALSE |  |  | 2018-02-22 | [6 empty] | DL, 4/29/18; Enrico is cordinationg this. The permits are approved……. DL, 7/11/18; Just received confirmation the door is ready for delivery and installed. I need to check in with Paul about the paint and prep of the door. I also need to check in with Jason on lock hardware......Dl, 7/25/18; Door is painted and ready for install. Called Dugmore to schedule the install. This should be compolete within the next two weeks......DL, 8/8/18; This Project is 100% Complete |  | Enrico Baez |  | YES | 2018-08-10 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000349 |  | 18P000349 | FALSE | BCOE | SL5 PHYSICS INSTALL PARTITION WALL FOR LAB ROOM |  | PHYSICS | 1037 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 5/24/18; Ron V. has detailed scope and he is ordering material. Once material arives, we will schedule the work…. DL, 6/16/18; Materila is ordered, When door/frame arrives, we will prep, paint and start the work…….DL, 7/11/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000429 |  | 18P000429 | FALSE | BCOE | SL5 INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 |  | BOURNS | B0262 B0256 | COMPLETE | Christopher Lynch | Todd Ambriz | KEVIN SCHULTE |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment…..DL, 5/9/18; We are working on plans to submitt to A&E soon....DL, 5/24/18; Plans were submitted on 5/24/18.......DL, 6/12/18; Plans were approved. Cabinets are ordered. Materila is 6-8 Weeks out.....DL, 7/11/18; We have confirmation for delivery of material for mid August. Target Complete date is 9/7/18......DL, 8/10/18; Project has started. We will be complete with in two weeks......DL, 8/22/18; Work is 90% Complete..Project should be complete by 8/31/18........ DL 9/6/1/8; This project is 99% complete. The parts arrived today. I will be sending out an email to schedule the installation time for next week.......DL, 9/19/18; This project is 100% Complete........ |  | Dan Lerman |  | YES | 2018-09-19 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000427 |  | 18P000427 | FALSE | BCOE | SL5 BOURNS A0373 NEW FLOORING & PAINT | NEW FLOORING & PAINT INCOMING FACULTY MEMBER | BOURNS | A0373 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie email; This is our new Dean’s faculty office. Dean Lynch is already on site getting up to speed one-two days a week. This office is an ASAP...... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected.....DL, 7/11/18; This project is 100% complete...... |  | Paul Ditty |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000426 |  | 18P000426 | FALSE | BCOE | SL5 BOURNS A037-NEW FLOORING & PAINT | NEW FLOORING & PAINT INCOMING FACULTY MEMBER | BOURNS | A0375 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; A-375: Bhargav Rallabandi arrives on or about August 1….. DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/1/18.....DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000425 |  | 18P000425 | FALSE | BCOE | SL5 BOURNS A379-NEW FLOORING & PAINT | NEW FLOORING & PAINT INCOMING FACULTY MEMBER | BOURNS | A0379 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; Luat Vuong arrives on or about August 15…... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected..…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/15/18........DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
20P000161 |  | 20P000161 | FALSE | BCOE | SL5 WCH 112 - MODIFY ROOM FOR NEW OCCUPANT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-04 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000163 |  | 20P000163 | FALSE | BCOE | SL5 BOURNS A0223 - PATCH/PAINT WALLS, DEEP CLEAN/REPLACE CARPET |  | BOURNS | A0223 | COMPLETE | Christopher Lynch | Todd Ambriz | SABRINA SCHUSTER | DEANNA VORHEES | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-07 | [8 empty] | Paul Ditty |  |  | 2019-11-25 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000175 |  | 20P000175 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 112 - PATCH & PAINT |  | CHUNG HALL | 112 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-11 | [8 empty] | Enrico Baez | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with metal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000388 |  | 19P000388 | FALSE | BCOE | SL5 SKYE PROJECT: CAMPUS INITIATED - BCOE ADVISING SPACE | BCOE Advising is being reassigned to space on the 3rd floor of Skye (at the recommendation of the University Space Committee). | SKYE HALL | 308 | COMPLETE | Christopher Lynch | Todd Ambriz | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-26 | Order material and schedule work | 2019-05-01 | 2019-06-28 |  |  |  | 7/15/19, DL; This project is 100% Complete………..7/1/19, DL; This project ois 95% Complete. Floor covering install will start this Wednesday…………6/17/19, DL; This project is almost complete. Target complete date is July 1st….…..5/31/19, DL; We are making good progress on this project. we are on tract to be copmplete with this project on or before July 1st……5/15/19, DL; Work is in progress and we are on schedule for th3 6/28/19 complete date…….5/1/19, DL; We will start this project this week. 4/15/19, DL; Plans were approved today. We will work on material and schedule the work. We will start this project shortly after May 1st…….3/18/19, DL; We are working on plans and plan to apply for building permit an plan review process next week | 2019-02-13 | Enrico Baez | Customer Request: Frame new walls in rm. 0310B & 0326. Widen door opening, install sliding glass door rm. 0310 Work Covered: Install metal stud framed partition walls in room 0310B and 0326 and install electrical and voice data outlets as required for new furniture layout. Widen the existing door opening in room 0310 and install one new 6-0x7-0 sliding glass door. Install a viewing window (approximately 9-0x4-0 overall width) made with two pieces of glass within a storefront frame. Relocate utilities and one wall *cabinet (*location TBD) as needed. Inclusions: Demolition: Remove the side door and frame in room 0310 and widen the opening to accept a 6-0x7-0 sliding door. Room 0310 east wall, cut in opening (approx. 9-0x4-0) at 36”-48” A.F.F.(field verify). Carpentry: Framing & Drywall: Rooms 0310B & 0326; Construct metal stud partition walls and new cased openings, and install drywall with finished edge metal (room 0310). Intersect new walls into the window mullions with a finished edge or metal with neoprene expansion tape installed between the wall and million. Room 0310; Frame a new cased opening to accept a 6-0x7-0 sliding door and frame a new cased opening at the east wall opening (approx. 9-0x4-0, at 36”-48” A.F.F. field verify) to accept a new viewing window. Floorcovering: Install new 4” rubber base in rooms 0310B and 0326, base to match existing. Acoustical Ceilings: Modify the T-bar ceiling grid and cut ceiling tiles to accommodate the new partition walls in rooms 0310B and 0326. Painting: Tape, sand and paint the new partition walls, door/cased openings. Patch and paint other walls in the Advising room 0310 as needed. Glazing: Room 0310; Install a 6-0x7-0 sliding glass commercial door (outsourced to Hour Glass). Quote is on file. Electrical: Room 0310; Relocate light switch and or wall mounted devices at room 0310/corridor wall and possibly may need to relocate conduit in the east wall where the new window opening is created. Rooms 0310B & 0326; reconfigure/separate lighting circuits and switching. Note: “Installation of electrical and voice data outlets may be required in the new partition walls at rooms 0310B & 0326 depending the furniture configuration”. Fire Alarm: Investigate at rooms 0310B & 0326. Fire Sprinklers: Investigate at rooms 0310B & 0326. Exclusions: Replacement of the existing carpet floorcovering. Repaint all walls at rooms 0310B and 0326 (paint new and adjacent walls only). Installation of new mixing boxes and T-stats in rooms 0310B and 0326. | YES | 2019-07-15 | Spring 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
20P000070 |  | 20P000070 | FALSE | BCOE | SL5 BOURNS B342D - PREPARE LAB FOR NEW FACULTY | PREPARE LAB FOR NEW FACULTY | BOURNS | B0342D | COMPLETE | Christopher Lynch | Todd Ambriz | SABRINA SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-08-09 | work on paint contract | 2020-01-13 | 2020-02-03 |  |  |  | 2/28/20, DL This Project is Complete……….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is 95% Complete, we need to install 3 power outlets. This project will be 100% complete within two weeks……..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is on schedule to be complete before the 2/3/20 complete date…….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19,DL: We conducted a site visit with the PI> We will do what we can to have the project complete before 2/3/20………… | 2019-11-06 | Enrico Baez | Paint all walls to match existing colors, paint the back of wood cabinets located at the east side of the room, replace stained or damaged ceiling tiles, replace and or replace all HVAC supply & return grilles, relamp as needed, Cal Labs to clean SS sinks, disconnect and dispose of the dishwasher, Plumbing and electrical to disconnect, Cal Labs to refurbish counter tops (light sand & seal), clean strip and wax sheet vinyl floor, repair and refurbish cabinets (white Rm 316, Blue Rm 328), customer to remove all chemical and sanitize fume hoods. | YES | 2020-02-28 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000619 |  | 19P000619 | FALSE | BCOE | SL5 BOURNS, RM A0311- NEW FLOORING/PAINT FOR INCOMING FACULTY |  | BOURNS | A0311 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-05-14 | Awaiting Flooring Install | [5 empty] | 06/28/19 O-ANS: Paint phase complete and awaitin flooring install. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
20P000245 |  | 20P000245 | FALSE | BCOE | SL5 WCH RM 0325 - PATCH AND PAINT DAMAGE FROM WHITE BOARD |  | CHUNG HALL | 325 | COMPLETE | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2019-11-25 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/13/20 |  | Paul Ditty |  |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000135 |  | 20P000135 | FALSE | BCOE | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MS&E Rm 0075 - 3 Ph208 Power CHW S&R WATER PPMS TOOL, Install Chilled water loop & power in clean room 075. | MAT SCI ENGR | 75 | COMPLETE | Christopher Lynch | Todd Ambriz | MARK HEIDEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-09-19 | Plans and permit | [5 empty] | 9/30/20, DL: This project is complete……..8/5/20, DL: This is in progress…….3/25/20, DL: We will work on plans and permits when we return back from the campus closure……. | 2020-02-18 | Enrico Baez | Intake/SOW: Install 208V 3ph power & disconnect/safety switch and one 3/4" Chilled water loop (Supply and Return) in the MSE southeast corner of clean room 0075. Create a 4" diameter pass-thru hole from this corner of room 0075 into the adjacent room 0071. FS to provide power and cooling to a compressor which will connect through the wall to the PPMS system with cryogenic helium lines. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
20P000129 |  | 20P000129 | FALSE | BCOE | SL5 BOURNS HALL B0360C - PATCH & PAINT |  | BOURNS | B0360C | COMPLETE | Christopher Lynch | Todd Ambriz | DEANNA VORHEES | KATHY COCKER | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-09-12 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/22/20 |  | Paul Ditty |  |  | 2020-01-22 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000638 |  | 19P000638 | FALSE | BCOE | SL5 BOURNS HALL, RM B0207- MODIFICATIONS FOR LAB ROOM | renovate lab | BOURNS | B207 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-16 | order material and schedule work | 2019-08-04 | 2019-10-04 |  |  |  | 11/11/19, DL: This project is Complete……10/30/19, DL: This Project is 95% complete and we should be complete next week………..10/16/19, DL; This project is 99% complete. We need to insulate ducting and deep clean the lab………9/16/19, DL; Project is 95% complete. We are planning to be complete in the next 30 days……9/3/19, DL; Project is in progress and 75% complete. 8/15/19, DL; Plans were approved this week. We will order the material and schedule the work……..Plans are 90% complete and we will probably submit plans for plan check review this Monday | 2019-07-19 | Enrico Baez | 07-01-19 O-RVL: RV Received email from Luat on 06-28 with revised SOW. RV Uploaded the referenced sketch into FAMIS. Revisions read: "In efforts to be helpful, I've color coded comments related to the simple attached sketch. 1) Unchanged: HVAC ductwork needs to be insulated so that we cannot hear it— the vibrations from the noise affect precision optical measurements. 2) Revised to be more specific: only the first row of overhead lights should be on the main switch (dark green). The other lights should be lowered and have pull-down chains, like this but with a longer a longer chain: https://www.grainger.com/product/19YX62 3) Removed: it would be nice if cabinets are nicer and not broken, but we'll turn them into open shelves if there are no funds for this. 4) Removed: (unless fire marshalls object and request sprinklers be lowered) 5) 3) Revised: for air venting machined fumes and soldering, a flexible fume vent should be installed, something like this: https://www.grainger.com/product/EXTRACT-ALL-Extractor-Arm-2DBX4 I'm flexible about where this is hung... what are the options? 6) 4) Revised: the utility rack in the center of the room should be moved to be in line with the other, and centered with the whiteboard on the wall. (Pink) 5) Added: chilled water (blue) and compressed air (light green) should be piped over so it's available to the 10'x3' optical table. 6) Added: Black plywood would be installed at the height of the current 8 1/2" frame like Kevin's in 2 spaces: a) around the 10x3' marked optical table b) around the 6x3' overhead rack close to the doors. Luat T. Vuong" | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000453 |  | 19P000453 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT |  | CHUNG HALL | 447 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-17 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2019 | 2021-03-16
20P000107 |  | 20P000107 | FALSE | BCOE | SL5 WINSTON CHUNG 322 - PATCH/PAINT NEW FACULTY FACULTY OFFICE |  | CHUNG HALL | 322 | COMPLETE | Christopher Lynch | Todd Ambriz | BILL BINGHAM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-08-29 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000278 |  | 19P000278 | FALSE | BCOE | SL5 REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR |  | BOURNS | A0165 | COMPLETE | Christopher Lynch | Todd Ambriz | NANCY FORD |  | Dan Lerman |  | 1 |  | TRUE |  |  | 2018-08-03 | [6 empty] | DL, 10/4/18; This Project is 100% Complete…….. |  | Enrico Baez |  | YES | 2018-10-04 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000477 |  | 19P000477 | FALSE | BCOE | SL5 WINSTON CHUNG HALL 4TH FLOOR ROOM 457 - PATCH & PAINT |  | CHUNG HALL | 457 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-01-30 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000316 |  | 19P000316 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL |  | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 2018-10-03 |  | 2018-08-30 | 2018-12-14 |  |  |  | 12/14/18, DL; This Project is 100% Complete…Anticipated completion 11/9/18. | 2018-10-03 | Enrico Baez |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000442 |  | 19P000442 | FALSE | BCOE | SL5 WINSTON CHUNG- PATCH/PAINT ROOM 319 |  | CHUNG HALL | 319 | COMPLETE | Christopher Lynch | Todd Ambriz | BILL BINGHAM |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-09 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2019 | 2021-03-16
19P000046 |  | 19P000046 | FALSE | BCOE | SL5 PATCH AND PAINT PLUS REPLACE BLINDS |  | BOURNS | A0131 | COMPLETE | Christopher Lynch | Todd Ambriz | NANCY FORD |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000028 |  | 20P000028 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0219- PAINT FACULTY OFFICES |  | BOURNS | A0219 | COMPLETE | Christopher Lynch | Todd Ambriz | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-07-19 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000602 |  | 19P000602 | FALSE | BCOE | SL5 BOURNS B328F- PREPARE LAB FOR NEW PI OCCUPANCY |  | BOURNS | B0328F | COMPLETE | Christopher Lynch | Todd Ambriz | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-09 | Finish the work… | 2020-02-10 | 2020-03-07 |  |  |  | 3/25/20, DL: this Project is Complete………...2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This project is almost complete and should be complete in the next 2-3 weeks………..10/30/19, DL: Plans and permits will be required for the work. We will work on the plans shortly after Thanksgiving……….. | 2019-09-27 | Enrico Baez | Construct metal stud wall framing and bracing above ceiling to infill the opening. Remove and reinstallation wall mounted cabinets located near the cased opening to access and join to the existing wall to new drywall. Install sound insulation. Install drywall, tape, sand, prime and paint wall. Install install rubber base to match existing. Modify T-bar ceiling to accept the wall framing Provide dust containment (Zip Walls) at both rooms near construction area. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000487 |  | 19P000487 | FALSE | BCOE | SL5 BOURNS HALL, RM A0220- PAINT FACULTY OFFICES |  | BOURNS | A219, A211, A241 | COMPLETE | Christopher Lynch | Todd Ambriz | DEANNA VORHEES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-02-05 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | COMPLETE | Christopher Lynch | Todd Ambriz | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-09 | Finish Gas cabinet installation | 2019-09-23 | 2020-02-07 |  |  |  | 8/5/20, DL: This Project is Complete…….3/25/20, DL: Project is 95% complete. We will install the fire sprinkler and exhaust duct to the gas cabinet when we return from the campus closure………..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Plans were approved and material is ordered. We are hopeful the material will arrive the 2nd or 3rd week in January. Once material is on site we will schedule the work…… 11/19/19 DH: Emailed Status Report to customer……10/16/19, DL: This project is 90% Complete. We are working on plans and permits for the two snorkels……….10/1/19, DL: This project is almost complete. We will be complete in the next 4- weeks except the Snorkel……….. 9/13/19, DL; The paint of the cabinets is scheduled for this week along with the power. We will submit the plans for the snorkel this with in the next two weeks…….9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Enrico Baez | SOW, Patch& Paint Walls, replace plexi glass on shelving, powder coat metal shelving & cabinets, clean & polish or replace chem sinks, polish counter tops, Validate all gas, water, drains, DI water & utilities. Replace damaged and dirty ceiling tiles, relamp as needed. Strip & wax floor. Dan L is requesting vendor pricing to restore finishes. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
20P000221 |  | 20P000221 | FALSE | BCOE | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | COMPLETE | Christopher Lynch | Todd Ambriz | HONG XU | KEVIN FREEDMAN | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-11-15 | [6 empty] | 1/19/21, DL: This project is 100% Complete……..9/30/20, DL: We are in the process of finishing up a few other projects. Once they are complete, we will schedule the work….8/5/20, DL: Plans are approved and we will start the work in the next 2-6 weeks…….. | 2020-02-25 | Enrico Baez | Install Plywood and supports. Paint Plywood black. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
20P000029 |  | 20P000029 | FALSE | BCOE | SL5 BOURNS HALL 2ND FL A0211- PAINT FACULTY OFFICES |  | BOURNS | A0211 | COMPLETE | Christopher Lynch | Todd Ambriz | DEANNA VORHEES |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-07-19 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/12/19 |  | Paul Ditty |  |  | 2019-12-12 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000601 |  | 19P000601 | FALSE | BCOE | SL5 BOURNS B328E- PREPARE LAB FOR NEW PI OCCUPANCY | Renopvate lab space, Patch/paint, Re-finish, re-surface – existing cabinets/casework. Re-finish, bench-tops. Clean existing Chemical fume hood. Repair or replace self-closing chemical/flammables storage cabinet. Repair or replace bench shelves as needed. Clean and wax floors. | BOURNS | B0328E | COMPLETE | Christopher Lynch | Todd Ambriz | KATHALENA COCKER |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-05-09 | Order material and scheudle work |  | 2020-02-07 |  |  |  | 2/28/20, DL: This project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL; This Project should be complete in the next 2-3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were approved. We will order material and schedule the work once the material is on site. The material should arrive around the 21st of January…….11/25/19, DL; Floor covering will be complete today. This project is complete except for the Snorkel vents. We are still waiting for plans check approval on the snorkels………11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Floor covering is delayed. We will schedule the floor covering installation when the material is on site. We submitted the plans for the snorkels last week. Once the plans are approved, we will order the phoenix valves and schedule the work………. 10/30/19, DL: This Project is 85% Complete. We will install new floor covering in the next two weeks. All work will be completed except the two snorkels. We still need to submit plans for the snorkels……..10/16/19, DL; This project is 80% complete. 9/16/19, DL; Project is in progress. We still need to submit plans for the snorkel for the power and snorkel. We will submit the plans for review within the next week. Once plans are approved, we will schedule the work……..Scope is complete, waiting on estimates from vendors. We will need to work up a contract which will add time to the project timeline… | 2019-08-06 | Enrico Baez | Provide two new 4” exhaust duct drops. One at the south wall above mobile table & one at the east wall above counter. Refinish two wood work station counter tops with chemical resistant coating (approx. 64lf) including one mobile table wood top. Install four(4) 208v / 30a Electrical receptacles and data drops at gutter racks above two work benches Provide drawer and door maintenance and or repairs at all metal cabinets and metal shelving. Powder coat all lower metal cabinets, shelving, fume hood doors and drawers. Replace damaged sheet vinyl flooring as needed. Move surplus items to materials management as identified by the PI. Install MilQ equipment at the east wall near sink. Relocated cylinder rack as necessary to accommodate “L” shaped work station. Provide and install two new cylinder racks at the south end of two work benches. Furnish and install two new metal cylinder racks. Replace damaged and/or stained 2x4 acoustical ceiling tiles. Relocate “L” shaped front cabinets. Relamp light fixtures and needed. Infill wall between rm 328E & D Patch and paint walls. Strip and wax floor. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000312 |  | 19P000312 | FALSE | BCOE | SL5 VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP |  | STUDENT SERV | 1227 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000175 |  | 19P000175 | FALSE | BCOE | SL5 PAINTING |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT CHAVARRIA-VIVAR |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000597 |  | 19P000597 | FALSE | BCOE | SL5 PATCH AND PAINT WALLS |  | CHUNG HALL | 355, 356, 351, & 353 | COMPLETE | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-05-03 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000205 |  | 19P000205 | FALSE | BCOE | SL5 LABORATORY RENOVATION FOR NEW FACULTY |  | BOURNS | A0328 | COMPLETE | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | 4 |  | TRUE |  |  | 2018-08-23 | electrostatic Paint | 2018-11-01 | 2019-01-14 |  |  |  | 2/28/19, DL; This Project is 100% Complete…….2/1/19, DL; This project is 99.9% Complete………..1/15/19, DL; This project is 90% complete. WE still need to finish snorkels and ceiling tiles. We should be 100% complete by 2/1/19……12/14/18, DL; This project is on schedule..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/4/18; This is a large scale project, we will walk with the trade supervisors next week. We will also work on the plans and schedule the work. Target Date is 1/1/19…..DL, 11/7/18; work is scheduled. We are working on the electrostatic paint contract. We are in plan check review process. There are questions about the fire sprinklers from Scott J. Sent Scott J. an email requesting a site visit to better determine if any work will be required on the sprinkler system….. |  | Enrico Baez |  | YES | 2019-02-18 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000625 |  | 19P000625 | FALSE | BCOE | SL5 BOURNS, RM A0108 - NEW PAINT FOR MECHATRONICS LAB ROOM |  | BOURNS | A0108 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-15 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-01 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000322 |  | 19P000322 | FALSE | BCOE | SL5 CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-05 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000250 |  | 19P000250 | FALSE | BCOE | SL5 BOURNS A303-PAINT AND PATCH WALL |  | BOURNS | A0303 | COMPLETE | Christopher Lynch | Todd Ambriz | JUANA GUERRERO |  | Paul Ditty |  | 5 |  | TRUE |  |  | 2018-09-10 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000424 |  | 19P000424 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET |  | CHUNG HALL | 445 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-12-20 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
19P000558 |  | 19P000558 | FALSE | BCOE | SL5 BOURNS HALL A-WING CONFERENCE ROOM A265 - PATCH & PAINT |  | BOURNS | A0265 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-04-03 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000065 |  | 20P000065 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR CONFERENCE ROOM 205/206 - PATCH & PAINT |  | CHUNG HALL | 205 & 206 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-08-08 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000526 |  | 19P000526 | FALSE | BCOE | SL5 CHUNG HALL 2ND FLOOR 202/203 VESTIBULE - PATCH & PAINT |  | CHUNG HALL | 0202 & 0203 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-03-12 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-08 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000657 |  | 19P000657 | FALSE | BCOE | SL5 WINSTON CHUNG HALL, RM 406- PATCH/PAINT OFFICE |  | CHUNG HALL | 406 | COMPLETE | Christopher Lynch | Todd Ambriz | BILL BINGHAM |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-06-07 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000588 |  | 19P000588 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR - PATCH & PAINT OFFICES |  | BOURNS | A127 Office, A129 Office, A131 Office, A133 Office, A135 Office, A137 Office, A139 Office, and A141 Office | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-04-22 | [6 empty] | 06/28/19 O-ANS: Paint phase complete. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
19P000129 |  | 19P000129 | FALSE | BCOE | SL5 HANG MONITORS AND BOARDS |  | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Todd Ambriz | RICHARD BAIN |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2018-08-06 |  | 2018-11-05 | 2018-12-14 |  |  |  | 12/14/18, DL; This Project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Dry errase boards and Monitor mounts are installed. Still need to install monitors, corner guards and monitors….. |  | Enrico Baez |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000226 |  | 18P000226 | FALSE | BCOE | SL5 BOURNS FUME HOOD INSTALLATION |  | BOURNS | B0235A | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 8 | HOLD | TRUE |  |  | 2017-12-11 |  | 2018-11-26 | 2019-01-31 |  |  |  | 2/14/19, DL; This project is Complete…..2/1/19, DL; The Fume hood is complete. The vendor will be back in two weeks to comissison the clean room…..…1/15/9, DL; This project is 95% complete and should be complete on or near 2/1/19…………12/14/18, DL; This Project is 90% Complete. Fume hood is scheduled for install next week. We will finish balance of project after Fume hood is installed…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. WE are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans…..DL, 5/9/18; planning to submit plans on 5/11/18 for plan check review….. DL, 5/24/18; Plans were submitted to Bob W. on 5/24/18……DL, 6/12/18; Project is on Hold until Shane can provide plans/specs for the clean room……DL, 7/11/18; Still no change to the status……DL, 7/25/18, Maggie confirmed this project is on the books. I need to discuss the status with the team because the priority list is on Hold…….DL, 8/22/18; This project is no longer on hold. We will per shane we will submit what we have from the clena room suupplier for review from FM and BO……DL, 9/6/18; WE are almost complete with Plans and will submit the plans next week………DL, 9/19/18; Submitted plans to PD&C on 9/14/18…..DL, 10/4/18; Plans were approved thais week. WE will scheudle the project around the delivery date for the Clean room……..DL, 11/7/18; This is in progress. We will complete the install of the utilities so the clean room can be installed. WE will finish the balance of the project once the Clean room install is complete. The clen room is being install by an outside vendor….. |  | Dan Lerman |  | YES | 2019-02-14 | Spring 2018 | FS | FALSE | 2017 | 2021-03-16
19P000035 |  | 19P000035 | FALSE | BCOE | SL5 WCH--INSTALL NEW LED DISPLAY IN OFFICE |  | CHUNG HALL | 354 | COMPLETE | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This Porject is 100% Complet…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Install scheduled for this Friday. | 2018-10-03 | Enrico Baez |  | YES | 2018-11-19 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000438 |  | 18P000438 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING |  | CHUNG HALL | 415 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 10 | FALSE |  |  | 2018-05-14 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000439 |  | 18P000439 | FALSE | BCOE | SL5 CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING |  | CHUNG HALL | 315 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 11 | FALSE |  |  | 2018-05-15 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
21P000037 |  | 21P000037 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | Paint Only | CHUNG HALL | 427 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-07-31 | [6 empty] | 01/19/21 O-ANS: Paint complete per technician and closed project. 11/30/20 B-SBT: repatch & Paint north wall |  | Paul Ditty |  |  | 2020-11-30 | Winter 2021 | FS | FALSE | 2020 | 2021-03-16 | FY 20-21
20P000449 |  | 20P000449 | FALSE | BCOE | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | Paint Only - Chung Hall, Fourth Floor, Room 461 Patch & Paint: At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. Follow up with fresh paint. Thank you. | CHUNG HALL | 461 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-11 | [6 empty] | 01/19/21 O-ANS: Complete per technician updates and closed project. Completed by Wendy M. 11/09 -SC |  | Paul Ditty |  |  | 2020-11-09 | Winter 2021 | FS | FALSE | 2020 | 2021-03-16 | FY 20-21
19P000296 |  | 19P000296 | FALSE | CAMPUS | SL5 MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB |  | MAT SCI ENGR |  | COMPLETE |  |  | MILLY PAREDEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-09-25 |  | 2019-02-01 | 2019-02-28 |  |  |  | 2/28/19, DL; Project is 100% Complete…….2/14/19, DL; This project is 90% Complete and should be complete by the end of the month………….2/1/19, DL; Permits are approved, we will schedule the project in the next 2- weeks and hope to be complete by the end of February….12/14/18, DL; Rendering has been given to Ron R. Ron will present to Gerry for review and approval. Once approved, we will proceed with plans and permits……DL, 11/7/18; Need to find out where this project stands in regards to the priioroity….. Site vist was conducted and scope of work is verified. Plans and permits will be required for the work….. |  | Enrico Baez |  | YES | 2019-02-28 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000435 |  | 18P000435 | FALSE | CAMPUS | SL5 HMSS HYDRATION STATION REQUEST |  | HUM & SOC SC | 3600 | COMPLETE |  |  | NELDA THOMAS |  | Dan Lerman |  |  | 30 | FALSE |  |  | 2018-05-10 | schedule the work | 2019-03-28 | 2019-04-26 |  |  |  | 4/15/19, DL; This project is 100% Complete…..3/28/19, DL; Fountain is in. working on power and paint….. |  |  |  | NO | 2019-04-15 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000284 |  | 19P000284 | FALSE | CAMPUS | SL5 GEOLOGY ACCOMMODATION DOCK DOORS |  | GEOLOGY |  | COMPLETE |  |  | DEBORAH TERAO |  | Chris Pillen |  | Canceled | Canceled | FALSE |  |  | 2018-08-07 | [8 empty] | Enrico Baez |  | YES | 2019-01-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000396 |  | 19P000396 | FALSE | CAP PROG | SL5 TRAILER #14 - CAMPUS INITIATED - STRUCTURE |  | T14 |  | COMPLETE | Jacqueline Norman | Sharyl Murdock | SHARYL MURDOCK |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-31 | Install underground utilites | 2019-02-01 | 2019-05-01 |  |  |  | 2/28/19, DL; This Project is 100% Complete…..Trailers were demolished. We need to install the utilities. Once the Grow Pod is on site, we will connect the utilities to the structure…… |  | Enrico Baez |  |  | 2019-02-28 | Winter 2018 | FS | FALSE | 2019 | 2021-03-16
18P000410 |  | 18P000410 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 3148B | COMPLETE | Kim Wilcox | TBD | CANDICE GOMEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-25 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000421 |  | 18P000421 | FALSE | CHANCELLOR | SL5 HINDERAKER PAINT AND PATCH WALL |  | HINDERAKER | 2120 | COMPLETE | Kim Wilcox | TBD | CANDICE GOMEZ |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-04-30 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000329 |  | 18P000329 | FALSE | CHANCELLOR | SL5 SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST |  | SKYE HALL | 170 | COMPLETE | Kim Wilcox | TBD | DA LAN DINH |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18…..DL, 5/24/18; Plans were approved. Demo work has started......DL, 6/12/18; MArshal and Kate are working on Carpet order......DL, 7/11/18; Carpet is ordered. We have a challenge with Title 24. I am working on the title 24 documents. We are still planning to have this project complete on 8/17/18......DL, 8/10/18; We now have the Title 24 plans. The are being reviewed by Bob and Scott.....Title 24 plans approved. Robert is working on PO#. Most parts are on site and Electricans are working on project. All other Trades to follow once Lights are in...... Hard Date of 9/7/18............9/6/18 As of today, Carpet is scheduled for install tomorrow morning and furniture is scheduled for delivery this Monday......WE will more than likely have electrical punch items and touch up paint but this propject should be 100% complete in regards to FS the end of next week next week......100% PROJECT COMPLETE... GREAT WORK DAN! |  | Dan Lerman |  | YES | 2018-09-18 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000375 |  | 19P000375 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT HOLES |  | SKYE HALL | 365 | COMPLETE | Kim Wilcox | TBD | FELECIA GARRETT |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-07 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000068 |  | 20P000068 | FALSE | CHANCELLOR | SL5 SKYE 349 - COVER HOLES ON WALL |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | TBD | VICTORIA AVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-08-09 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000414 |  | 18P000414 | FALSE | CHANCELLOR | SL5 CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL |  | STUDENT SERV | 0 | COMPLETE | Kim Wilcox | TBD | DANIELLE GARCIA |  | Paul Ditty |  | 1 | 2 | FALSE |  |  | 2018-04-26 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000487 |  | 18P000487 | FALSE | CHANCELLOR | SL5 SKYE HALL PATCH HOLES AND PAINT |  | SKYE HALL | 349 | COMPLETE | Kim Wilcox | TBD | SONIA ZAMORA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000122 |  | 19P000122 | FALSE | CHANCELLOR | SL5 REMOVE, PATCH & PAINT AND HANG |  | STUDENT SERV | 2222 | COMPLETE | Kim Wilcox | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000420 |  | 19P000420 | FALSE | CHANCELLOR | SL5 PATCH AND PAINT WALL |  | SKYE HALL | 325 | COMPLETE | Kim Wilcox | TBD | REYNA ALARCON |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-19 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
18P000297 |  | 18P000297 | FALSE | CHANCELLOR | SL5 SKYE HALL CHECK LOCATION FOR TV INSTALL |  | SKYE HALL | 390 | COMPLETE | Kim Wilcox | TBD | CANDICE GOMEZ |  | Dan Lerman |  | 4 | 3 | FALSE |  |  | 2018-02-02 | [6 empty] | 2/1/19, DL; This Project is 100% Complete………1/18/19, DL; This Project is scheduled to be complete next week.….. DL, 5/24/18; Need to verify scope with Enrico…..DL, 7/11/18; Work orders are produced and need to be issued. Target complete date is 9/3/18…. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000364 |  | 19P000364 | FALSE | CHASS | SL5 PATCH AND PAINT |  | CHASS INT S | 3106 | COMPLETE | Juliet McMullin | Cindy Williams | FRANCESCA MOREIRA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-30 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2019-03-15 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
18W016588 |  | 18W016588 | FALSE | CHASS | PATCH AND PAINT FOR FACULTY |  | SPROUL | 4105 | COMPLETE | Juliet McMullin | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | N/A | TRUE |  |  | 2018-06-19 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000469 |  | 18P000469 | FALSE | CHASS | SL5 WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS |  | WATKINS | 1317 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | 2018-07-25 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000445 |  | 18P000445 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 |  | ARTS | 225 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 11 | TRUE |  |  | 2018-05-21 | [8 empty] | Paul Ditty |  | N/A | 2018-09-10 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000314 |  | 18P000314 | FALSE | CHASS | SL5 CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR |  | CA MUS PHOTO | 1000 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY PAPAVERO |  | Dan Lerman |  |  | 17 | FALSE |  |  | 2018-02-16 | [6 empty] | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date.......DL, 7/25/18; This project is 100% Complete..... |  | Enrico Baez |  | YES | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000056 |  | 19P000056 | FALSE | CHASS | SL5 HMSS CAPABILITY OF MOUNTING A TV |  | HUM & SOC SC | 1212 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  |  | 18 | FALSE |  |  | 2017-10-03 | Install power after winter break | 2018-12-07 | 2019-01-17 |  |  |  | 12/14/18, DL; Monitor is complete. Still need to work on electrical……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope with Enrico and schedule the work…. Work orders are not produced. Need to assign and schedule the work DND 7/30/18: Closed work order #18W004822; created project #19P000056……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | 3/04/19, DL; Allison Rodgers confirmed this project is 100% Complete…. | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2017 | 2021-03-16
18W001170 |  | 18W001170 | FALSE | CHASS | SL5 ARTS: PAINT CLASSROOMS |  | ARTS | 407 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 27 | FALSE |  |  | 2017-07-25 | [8 empty] | Enrico Baez |  | YES | 2018-09-24 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
18P000318 |  | 18P000318 | FALSE | CHASS | SL5 CHASS INT S FLAT SCREEN INSTALLATION |  | CHASS INT S |  | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Dan Lerman |  |  | 20 | FALSE |  |  | 2018-02-21 | schedule the work | 2019-03-14 | 2019-04-12 |  |  |  | 4/15/19, DL; This is 100% Complete….3/28/19, DL; Monitor is installed. Need to finishe power and data next week……2/28/19, DL; Scheduled to complete the install mid March…..2/1/19, DL; Francesca contacted me and informed me this project is now back on the books. She needs to gather more information and order the monitor. When the monitor arrives, we will schedule the installation…….1/29/19, DL; Francesca confirmed this project is not needed and requested this project to be cencelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; we have the brackets. Will scheule the work after the project is approved…..DL, 7/11/18; Work order are not produced. Need to assign and schedule the work…. Target complete date is 8/3/18……DL; 7/25/18; Need to change target date.. |  | Enrico Baez |  | YES | 2019-04-15 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000468 |  | 18P000468 | FALSE | CHASS | SL5 WATKINS 1222/1223 PATCH/PAINT |  | WATKINS | 1222 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 13 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000300 |  | 18P000300 | FALSE | CHASS | SL5 ARTS PATCH AND PAINT - DANCE HALLWAYS |  | ARTS |  | COMPLETE | Juliet McMullin | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 24 | FALSE |  |  | 2018-02-02 | [6 empty] | centered. |  | Paul Ditty |  | N/A | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000295 |  | 18P000295 | FALSE | CHASS | SL5 CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL |  | CHASS INT S | 2117J | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-02-01 | [6 empty] | DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18……..DL, 5/24/18; Plans were approved. We need to scheudle the work….DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets.......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date.....DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18...........DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware..... |  | Enrico Baez |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000418 |  | 18P000418 | FALSE | CHASS | SL5 HMSS OFFICE PAINTING |  | HUM & SOC SC | 2002 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 15 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000383 |  | 18P000383 | FALSE | CHASS | SL5 HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT |  | HUM & SOC SC | 1302 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  | 4 | TRUE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | 2018-08-10 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000205 |  | 18P000205 | FALSE | CHASS | SL5 CHASS INT S CREATE DOOR |  | CHASS INT S | 2117H | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-11-27 | [6 empty] | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18……DL, 5/24/18; Plans were approved. WE need to schedule the work…..DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18...........DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... .. DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date..........DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18............DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware.....DL, 9/19/18; This Project is 100% Complete...... |  | Enrico Baez |  | YES | 2018-09-21 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
18P000396 |  | 18P000396 | FALSE | CHASS | SL5 WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | Please patch and paint these two Political Science Staff Offices in the Watkins Hall 2122 "suite". 2122A belongs to Tanya Wine, FAO; 2122D belongs to Cindy Redfield, Principal Analyst. | WATKINS | 2122 | COMPLETE | Juliet McMullin | Cindy Williams | DAMARIS CARLOS | CINDY REDFIELD | Paul Ditty |  |  |  | TRUE |  |  | 2018-04-13 | [6 empty] | 08/10/18 D-MMN: Completed painting the finish. Pulled our masking and plastic wiped down the furniture. Replaced fixture covers. vacuumed the carpets and moved furniture back.08/07/18 D-MMN: Removed anchors, related boards. Filled holes with spackle and topped with joint compound. used one 4x4 wall patch. Returned and applied second coat of joint compound. 08/09/18 D-MMN: Completed applying primer, and then began applying Suprema. 08/08/18 D-MMN: Removed steel case and file cabinets from walls. Pulled anchors and filled with smooth se 20 and 2 coats of joint compound. Also finished any other patching. Taped the base and fixtures and covered furniture with plastic. Used a fan to dry patching. Sanded patches and began primer. Vacuumed debris. |  | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000387 |  | 18P000387 | FALSE | CHASS | SL5 HMSS PATCH/PAINT |  | HUM & SOC SC | 3600 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 28 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000367 |  | 18P000367 | FALSE | CHASS | SL5 CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE |  | CHASS INT N | 3033 | COMPLETE | Juliet McMullin | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 23 | FALSE |  |  | 2018-03-27 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000353 |  | 18P000353 | FALSE | CHASS | SL5 PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT |  | PSYCHOLOGY1 | 1111A | COMPLETE | Juliet McMullin | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 26 | FALSE |  |  | 2018-03-20 | [6 empty] | DL; 7/4/18;This project is scoped. We will only paint one out of the two offices. Working on PO# to install frosted glass with Sun Down Window coverings……DL, 7/25/18; PO# is produced and material is ordered. Target date mid August…….DL, 8/22/18; This project is complete.... |  | Paul Ditty |  | N/A | 2018-08-23 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000313 |  | 19P000313 | FALSE | CHASS | SL5 HUMANITIIES SOCSCI - PATCH HOLES & PAINT - |  | HUM & SOC SC | 1203 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-01 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
18P000417 |  | 18P000417 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTIONAL OFFICE PAINTING |  | HUM & SOC SC | 2106 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000389 |  | 18P000389 | FALSE | CHASS | SL5 PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A |  | PSYCHOLOGY1 | 2122 | COMPLETE | Juliet McMullin | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 5 | TRUE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000253 |  | 19P000253 | FALSE | CHASS | SL5 ARTS RENOVATION |  | ARTS | 157 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 16 | FALSE |  |  | 2018-04-17 | [6 empty] | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access……DL, 7/11/18; This project needs to be complete before Fall 2018. Space is vacant and ready go. Need to walk and confirm Schdule with Paul D. Tony's Flooring is ready to go after paint is complete.... Target complete date is 9/21/18......DL, 8/22/18; Walked with PAul, Paul will scheudle the work. Jess still need to cordinate with Tony's Flooring .....DL, 9/19/18; The paint and flooring is complete. The seams need to be welded and this will be complete. this will be complete by 9/21/18......9/19/21; This Project is 100% Complete....... |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000344 |  | 18P000344 | FALSE | CHASS | SL5 CHASS INTS PAINT MULTIPLE ROOMS - FACULTY |  | CHASS INT S | 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 1 | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 7/11/18; This was transferd in to my quque in the past week. I need to scope this project. I belive this is part of project # 18P000205 and 18P000295. If this is part of the other project. We will try to have the paint completed by 8/17/18…......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/10/18; Work has started. We passed rough electrical and framing inspection. The work should be complete in about three weeks......DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18.......DL, 9/6/18; This Project is 100% Complete....... |  | Paul Ditty |  | N/A | 2018-09-10 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000111 |  | 18P000111 | FALSE | CHASS | SL5 KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 |  | CHASS INT S |  | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Jason Williams |  |  |  | FALSE |  |  | 2017-09-15 | [6 empty] | EB 1/31/18 Work was assigned to lock shop 12/7/17…. DND 5/11: Spoke with Jason, all work complete to be completed as trade is available. Only work remaining is on 3150 A; Jason short staffed to finish project but it's on his radar. 07/13/18 H-FMS: Troubleshoot programming and settings for this controller. Clear all data from panel and reset, perform required downloads, re-test and verify both doors working correctly. |  | Enrico Baez |  | YES | 2018-07-13 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
18P000416 |  | 18P000416 | FALSE | CHASS | SL5 HMSS UWP INSTRUCTOR OFFICE PAINTING |  | HUM & SOC SC | 3002 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000201 |  | 18P000201 | FALSE | CHASS | SL5 ARTS REMOVE COUNTERTOP/SHELVES |  | ARTS | 0106A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 3 | TRUE |  |  | 2017-11-21 | [6 empty] | DL, 6/16/18; Ned to walk, scope and submit plans ASAP…..Sent Paul an email requesting information on Status of Faculty hire status……DL, 7/11/18; Paul is on Jury Duty and he said he should return back to work next week. Current Targe complete date is mid September......DL, 7/25/18; Carpentery and Electrical is complete. Patch and paint has started. Target complete date is 8/3/18......DL, 8/8/18; Space is VAcant and ready for paint. The paint department is working on several other projects that require their attention. The paint department will complete the work in the near future......DL, 8/22/18; This Project is 100% Complete....... |  | Enrico Baez |  | YES | 2018-08-23 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
20P000142 |  | 20P000142 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 5502 - PATCH AND PAINT FACULTY OFFICE |  | HUM & SOC SC | 5502 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-26 | [8 empty] | Paul Ditty |  |  | 2019-10-14 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000141 |  | 20P000141 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4401- PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4401 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-26 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000195 |  | 20P000195 | FALSE | CHASS | SL5 ARTS 0054 - PAINT PIANO LAB |  | ARTS | 54 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-24 | [8 empty] | Paul Ditty |  |  | 2019-11-06 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000140 |  | 20P000140 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 4400 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 4400 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-25 | [8 empty] | Paul Ditty |  |  | 2019-10-09 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000143 |  | 20P000143 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 6605 - PATCH AND PAINT IN FACULTY OFFICE |  | HUM & SOC SC | 6605 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-26 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000664 |  | 19P000664 | FALSE | CHASS | SL5 WATKINS HALL, RM 1343/1343A- PAINT OFFICE AND LAB |  | WATKINS | 1343 & 1343A | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-06-12 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-08 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000194 |  | 20P000194 | FALSE | CHASS | SL5 WATKINS 1224 - PAINT NEW FACULTY OFFICE ONLY |  | WATKINS | 1224 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-10-17 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/09/20 |  | Paul Ditty |  |  | 2020-01-09 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000220 |  | 19P000220 | FALSE | CHASS | SL5 ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT |  | ARTS | 333 | COMPLETE | Juliet McMullin | Cindy Williams | SONJA SEKELY-ROWLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 12/14/18, DL; This project is 100% Complete….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/8/18; Screeen is scheduled to be removed this Friday. We will schedule the installation and the patch / Paint repairs once we receive the repaired screen back from the vendor…….DL, 11/7/18; This project should already be complete. However, The vnedor did not deliver the correct screen. The correct screen is currently scheduled for this Friday..... |  | Enrico Baez |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000044 |  | 20P000044 | FALSE | CHASS | SL5 WATKINS 1312 - NEW HIRE RENOVATION - ELIZABETH BERGER | Install drywall over out dated would paneling | WATKINS | 1312 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-07-30 | Install drywall | 2020-01-13 | 2020-02-14 |  |  |  | 2/19/20, DL: This project is Complete…………..1/14/20, DL: We started this project today and should be complete with in 3-4 weeks………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will plan on starting the project the 2nd week in January but will not confirm until we have confirmation from the carpenter shop…………11/18/19 DH: Emailed Status Report to customer……11/11/19, DL: The Material is ordered. The carpenters may start the work the week of 11/18/19………10/30/19, DL: I received confirmation the space is vacant we will schedule the work in the next 6- 8 weeks……10/16/19, DL; The plans are approved and the work is complete. I need to schedule final inspection………. | 2019-09-23 | Enrico Baez | ABATEMENT NEEDED----remove mastic from walls at base on wood paneled wall CARPENTERS 1.) Remove chalk board 2.) Install 1/2" plywood over wood paneled walls. Including over plywood partition separating wall. Do not drywall over trim. 3.) Finish drywall. ELECTRICIANS 1.) Bring out electrical for new drywall and secure when drywall has been installed. PAINTERS 1.) Patch, paint and finish all walls. CUSTODIAL 1.) Clean space after construction. | YES | 2020-02-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000237 |  | 20P000237 | FALSE | CHASS | SL5 HMNSS 1202A - PATCH AND PAINT SERVICE |  | HUM & SOC SC | 1202A | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTIAN BACK |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2019-11-22 | [8 empty] | Paul Ditty | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/14/20. |  | 2020-02-14 | Spring 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000337 |  | 19P000337 | FALSE | CHASS | SL5 PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY BUILDING | Remove whiteboard (in front of room), mount LED mount, add double duplex and electrical power behind LED, patch and paint wall | PSYCHOLOGY1 | 3210 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 1 | 101 | FALSE |  |  | 2018-10-11 | site visit and schedule the work | 2019-09-16 | 2019-08-30 |  |  |  | 10/1/19, DL; This Project is Complete……………..9/3/19, DL; Space is blocked and schedculed to be completed by 9/27/19…..8/14/19, DL; Conducted site visit with Trades. We will schedule the space to be blocked out and start the work mid September….8/1/19, DL; Planning to start this project in two weeks……7/15/19, DL; I will walk the project in the near future and schedule the work if permits are not required…… | 2019-01-15 | Enrico Baez | Electricians 1. Install behind TV. Provide two duplex outlets and power. Also provide single gang box and conduit for data. Data lines have been run to T-bar in Hallway. 2. Secure loose Extron plate and cover next to TV. Painters 1. Patch and paint wall where TV is mounted | YES | 2019-10-01 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000575 |  | 19P000575 | FALSE | CHASS | SL5 WATKINS HALL PAINT/FLOORING |  | WATKINS | 1309A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-17 | [6 empty] | 11/26/2019 O-ANS: Paint phase completed per Paul Ditty. Awaiting completion of flooring. |  |  | 01/31/20 O-ANS: Completed per notes as of 09/05/19. |  | 2019-09-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000361 |  | 19P000361 | FALSE | CHASS | SL5 OLMSTED-PATCH & PAINT/REPLACE CARPET |  | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-29 |  |  | 2019-05-09 |  |  |  | 05/29/19 O-ANS: Project completed 05/09/19 per Paul Ditty. |  | Paul Ditty |  | N/A | 2019-05-09 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000378 |  | 19P000378 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 |  | HUM & SOC SC | 1613 | COMPLETE | Juliet McMullin | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-11-13 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
18P000481 |  | 18P000481 | FALSE | CHASS | SL5 CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 |  | CHASS INT S | 3104 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000306 |  | 19P000306 | FALSE | CHASS | SL5 HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 |  | CHASS INT N | 4017 | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-01 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000585 |  | 19P000585 | FALSE | CHASS | SL5 HUMANITIES SS, RM 3604- PATCH/PAINT WEST WALL |  | HUM & SOC SC | 3604 | COMPLETE | Juliet McMullin | Cindy Williams | DARA CERDA |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-04-19 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
19W002930 |  | 19W002930 | FALSE | CHASS | HOLD - SL5 PATCH HOLES & PAINT - HUMANITIIES SOCSCI |  | HUM & SOC SC | 1203 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-08-17 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000195 |  | 19P000195 | FALSE | CHASS | SL5 HUM & SOC SC-ROOM PAINTING |  | HUM & SOC SC | 2003 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000603 |  | 19P000603 | FALSE | CHASS | SL5 CHASS INT N, RM 3046- PATCH AND PAINT - NEW FACULTY OFFICE |  | CHASS INT N | 3046 | COMPLETE | Juliet McMullin | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  | 12 |  | TRUE |  |  | 2019-05-10 | [6 empty] | 06/18/19 O-ANS: Project complete per updates. 06/15/19 D-MMN: Painted remaining finish. Pulled masking and plastic. Replaced plates and vacuumed. |  |  |  |  | 2019-06-18 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
19P000216 |  | 19P000216 | FALSE | CHASS | SL5 HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT |  | HUM & SOC SC | 1214 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-08-27 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000640 |  | 19P000640 | FALSE | CHASS | SL5 NEW FACULTY - PATCH & PAINT SPROUL 3108 |  | SPROUL | 3108 | COMPLETE | Juliet McMullin | Cindy Williams | MELISA VICARIO |  | Paul Ditty |  | 13 |  | TRUE |  |  | 2019-05-20 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
19P000221 |  | 19P000221 | FALSE | CHASS | SL5 PATCH, PAINTING, AND REGULAR CLEANING OF A126A |  | OLMSTED | A0126A | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000643 |  | 19P000643 | FALSE | CHASS | SL5 HMNSS, RM 2003- ROOM PAINTING - ENGLISH |  | HUM & SOC SC | 2003, 2004, 2008, 2111, 3003, 3007 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2019-05-21 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000196 |  | 19P000196 | FALSE | CHASS | SL5 PAINT OFFICE AT UNIVERSITY THEATER |  | THTR WKSH |  | COMPLETE | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000171 |  | 19P000171 | FALSE | CHASS | SL5 HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST |  | HUM & SOC SC | 1614 | COMPLETE | Juliet McMullin | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 16 |  | FALSE |  |  | 2018-08-09 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18W016621 |  | 18W016621 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Juliet McMullin | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2018-06-20 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000201 |  | 19P000201 | FALSE | CHASS | SL5 PATCH AND PAINT THE WALLS |  | CHASS INT S | 3111A | COMPLETE | Juliet McMullin | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 18 |  | FALSE |  |  | 2018-08-22 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000385 |  | 18P000385 | FALSE | CHASS | SL5 HMSS INSTALL TV IN CONFERENCE ROOM |  | HUM & SOC SC | 1001E | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Dan Lerman |  | 19 | 19 | FALSE |  |  | 2018-03-06 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..12/14/18; Monitor is Complete, we still need to install power. The space is vacant…DL, 6/16/18; Pasted notes from FAMIS; University Writing program wants to install a 65 inch TV in the conference room at HMNSS 1001E. 1. Request to install the TV mount/ bracket on the wall; 2. Request to remove the old projector screen but leave two wood blocks on the wall; 3. Request to add a new double power outlet around the TV bracket area. If you have any questions, please contact Shanshan Liao at (shanshan.liao@ucr.edu or X27753)……DL, 7/25/18; Work orders are not produced. Need to assign and schedule the work…..……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez |  | YES | 2019-03-18 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
20P000145 |  | 20P000145 | FALSE | CHASS | SL5 PSYCHOLOGY 1111 - PATCH AND PAINT FRONT OFFICE WALL |  | PSYCHOLOGY1 | 1111 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-09-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20 |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000362 |  | 19P000362 | FALSE | CHASS | SL5 PATCH & PAINT/REPLACE CARPET (HALLWAY) |  | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000004 |  | 20P000004 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - COURTNEY BAKER |  | HUM & SOC SC | 2204 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-07-02 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000002 |  | 20P000002 | FALSE | CHASS | SL5 HMNSS, RM 1212- REMOVAL OF ROLL UP WINDOW |  | HUM & SOC SC | 1212 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-01 | schedule the work | 2020-01-06 | 2020-01-31 |  |  |  | 1/30/20, DL: This project is Complete. We will istall the monitor after IT services installls the Data lines. Michael or Aliosn will notify us when IT is complete and we will schedule th emonitor installation…………1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: This project is in progress and will be complete with in two weeks……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project was delayed. The material is currently ordered. We are planning to start the week of 1/6/20……. 11/19/19 DH: Emailed Status Report to customer….10/30/19, DL; We will plan on scheduling the work shortly after Thanksgiving……….10/16/19, DL: Plans are approved, we will order the material and schedule the work once material is on site. Projected start date is mid November………..9/16/19, DL; Plans will be submitted this week for building permit and plan check review….. | 2019-10-01 | Dan Lerman | Remove Roll up partition. Install outlet and data port, patch and paint walls. | YES | 2020-01-30 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000214 |  | 20P000214 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | Remove walls and doors in spaces 2139 A,B and C. | PSYCHOLOGY1 | 2nd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-11-07 | Obtain building permit | [5 empty] | 9/30/20, DL: This Project is Complete…………8/5/20, DL: we will submiot plans this week.…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Plans were submitted for a permit on 2/12/20. Once plans are approved, we will order the material and schedule the work……… | 2020-01-10 | Enrico Baez | **************************************SCOPE********************************** 1.) Remove doors, and jambs 2139A, 2139B, 2139C. 2.) Remove drop ceiling in 2139A, 2139B, 2139C and repair as needed. 3.) Remove cabinets in 2139A, 2139B, 2139C. 4.) Remove walls between 2139A & B, and remove walls between 2139B & C. 5.) Change light fixture to match existing. 6.) Repair walls as needed. 7.) Patch and paint as needed. 8.) Replace carpet and base in 2139A, 2139B, 2139C and 2139 common area. 9.) HVAC duct work in individual spaces can be removed and simplified. | YES | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000419 |  | 19P000419 | FALSE | CHASS | SL5 CHASS INT SOUTH 2117-CARD ACCESS | Remove Door and wall leading to 2117 Media Library and reconfigure to allow enterance into 2117 A & J without having to go through 2117C. | CHASS INT S | 2117 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 12/16/19, DL: This project is now complete…….11/19/19 DH: Emailed Status Report to customer…..11/11/19, The work is 98% Complete. We have one door that we had to send back to the vendor to have it prepared for door hardware. We should have the door back on site with in the next two weeks………..10/30/19, DL: Doors and Frame are on site. The paint team will prime and paint the doors and frame. Once the doors and frame are painted, we will schedule the work……………10/1/19, DL; This Project is 90% Complete. We are waiting on the doors to arrive. Once the doors arrive, we will schedule them to be painted and installed…………..9/3/19, DL; We started this project today. We are planning to be 90% complete by 9/27/19. Note, we have special order doors that have a 4-6 week lead time and that is the reason why we will be only 90% complete on 9/27/19. Paul Richardson is aware of the schedule…….8/15/19, DL; The plans were approved this week, we will order the needed material and start the work very soon…….This is a two part project. We will complete the construction process now. The four doors that need key card access still require a request for proposal and a contract. This portion of the project will take 3- months due to contracts administration, lead time on material and contractor scheduling…….8/1/19, DL; Gunther is working on plans. Once permit is approved, we will schedule the work…. | 2019-03-21 | Enrico Baez | Install 8 position control panel, keyless entry for 2117, 2117A, 2117D and 2117E. ***per Paul Richardson remove 2117G, 2117H and 2117J from request*** !!!!Project to reconfigure wall space, 19P000400 has been combined with 19P000419. !!! | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
18W008762 |  | 18W008762 | FALSE | CHASS | SL5 HUMANITIES: PATCH & PAINT |  | HUM & SOC SC | 2415 | COMPLETE | Juliet McMullin | Cindy Williams | ANDREW ALONSO |  | Paul Ditty |  | 20 | 22 | FALSE |  |  | 2018-01-02 | [8 empty] | Paul Ditty |  | N/A | 2018-11-08 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000126 |  | 18P000126 | FALSE | CHASS | SL5 HMSS ESTIMATE REMOVE WALL & CHANGE DOORS |  | HUM & SOC SC | 3611 | COMPLETE | Juliet McMullin | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 2017-09-28 | Order material and schedule work | 2019-06-19 | 2019-06-29 |  |  |  | 7/1/19,DL; This project is 100% Complete…..5/15/19, DL; Work is scheduled to start on 6/19/19…….5/1/19, DL; Plans are approved. Need to order material and schedule the work…..3/18/19, DL; Plans submitted to PD&C today…..02/2819, DL; Gunther will work on plans over the next three weeks to submit for a building permit. We will schedule the work if and after the plans are approved. If approved the door and window will more than likely have a 3- month lead time…………….12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez |  | YES | 2019-07-01 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16 | FY 19-20
18P000343 |  | 18P000343 | FALSE | CHASS | SL5 UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER |  | HUM & SOC SC | 0400A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 2018-03-16 | sheet metal to install handrail | [5 empty] | 11/15/19, DL: This project is complete…..10/30/19, DL: Sheet metal shop fabricated the hand rails. The paint shop will prime and paint the hand rails and the curb. Once the rails are painted, the sheet metal shop will complete the installation…….10/16/19, DL; Cory from the sheet metal shop is aware of the scope of work and they will schedule the work in the near future……..10/1/19, DL; Dan to show Cory from sheet metal the area where a hand rail will be installed for painting backdrops……..07/11/19 O-ANS: Dan and Chris P will walk the space. 05/21/19 O-ANS: Changed to In Progress per meeting with Dan L. Chris P is the PM for further updates. DL and CP will visit after commencement. 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez |  | YES | 2019-11-15 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000173 |  | 19P000173 | FALSE | CHASS | SL5 PAINT/PATCH UNIVERSITY THEATER LOBBY |  | HUM & SOC SC | 0400A | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000215 |  | 20P000215 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | Remove Vaughan wall seperating Olmsted 3349/3351.Add 4 single gang outlets and 2, 2gang outlets. | PSYCHOLOGY1 | 3rd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-11-07 | [6 empty] | 1/19/21, DL: This project is 100% complete…………9/30/20, DL: Plans were approved, we had the Vaughn Wall tested for Asbestos containing material. Once we have the results, we will schedule the work………….8/5/20, DL: We will submit plans by this Friday for a building permit | 2020-02-24 | Enrico Baez | 2/24/2020 E. Baez - 1.Remove Vaughan wall and electrical circuit in wall. 2. Add 4 Single Gan outlets and 2, 2gang outlets. 3. Patch vinyl plank flooring from removed wall and safe. 4. Remove panel in 2249 with wall paper on it next to window. 5. Remove handle set to 3351, install blank, render door inoperable. 6. Repair T-Bar ceiling as needed. 7. Patch and paint walls. 8. Coordinate with ITS for data line for 8 computers. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000063 |  | 19P000063 | FALSE | CHASS | SL5 NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS |  | PSYCHOLOGY1 | 2124 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-07-31 | [8 empty] | Paul Ditty |  | NO | 2018-09-26 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000356 |  | 19P000356 | FALSE | CHASS | SL5 PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT |  | HUM & SOC SC | 4401 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-24 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000574 |  | 19P000574 | FALSE | CHASS | SL5 FACULTY OFFICE PAINTING |  | HUM & SOC SC | 2208, 2210, 2300, 2302, 2303, 2305, 2307, 2308 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-04-12 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000005 |  | 20P000005 | FALSE | CHASS | SL5 NEW FACULTY HIRE - ROOM PAINTING - KIM FROST |  | HUM & SOC SC | 3215 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-07-02 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-17 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000120 |  | 20P000120 | FALSE | CHASS | SL5 OLMSTED 2139 SUITE - PATCH AND PAINT |  | OLMSTED | 2139 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2019-09-05 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/14/20 |  | Paul Ditty |  |  | 2020-01-14 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000609 |  | 19P000609 | FALSE | CHASS | SL5 WATKINS HALL, RM 1229-NEW FACULTY HIRE, PAINT, LIGHTS, FLOOR |  | WATKINS | 1229 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 07/03/19 O-ANS: Paint phase complete and awaiting flooring change. 06/21/19 O-ANS: Customer requested to remove lighting change from project and only complete paint and carpeting via email to Paul Ditty (copied email below). Will create separate work order for lighting. Re-assigned to Paul Ditty to complete. "From: Becky L Campbell <becky.campbell@ucr.edu> Sent: Friday, June 21, 2019 10:51 AM In regards of the work order: 19P000609 - SL5 - PAINT FACULTY OFFICE – please cancel the connecting Work Order 19W015231 – REPLACING THE LIGHTING IN WATKINS 1229. Please do paint and replace flooring.For the lighting, please create new work order to be done at a later time." |  | Paul Ditty |  |  | 2019-07-03 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000371 |  | 19P000371 | FALSE | CHASS | SL5 URGENT PATCH AND PAINT IN CHAIR'S OFFICE |  | HUM & SOC SC | 1213 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-11-05 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000112 |  | 20P000112 | FALSE | CHASS | SL5 PSYCHOLOGY 2123 - PATCH AND PAINT JOB |  | PSYCHOLOGY1 | 2123 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-09-04 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000350 |  | 19P000350 | FALSE | CHASS | SL5 PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 | MISC WORK IN ROOMS 3121 AND 1133 Patch and paint-relocate white boards, hang pictures. | PSYCHOLOGY1 | 3121, 1133 | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 4 | 3 | TRUE |  |  | 2018-10-17 | Start this Friday. | 2019-08-02 | 2019-08-16 |  |  |  | 8/15/19, DL; This Project is 100% Complete…….. 8/1/19, DL; We will start this project this Friday…… 7/15/19, DL; Appears not plans and permits will be required for the work. I will verify and schedule the work in the near future if no plans or permits are required….. | 2019-04-15 | Enrico Baez | Carpentry: 1. Needs to occur after October 26 2. Remove the whiteboard in 3121, patch and paint 3. Remove Glass board in 1133 and relocate to 3121 (in the same way and place as it was in 1133) 3. Mount pictures on the wall in 3121 4. Secure shelving units in 1133 and 3121 5. There is a ceiling tile in 1133 that is stained and needs to be replaced Painters: 1. Room 3121 Patch and Paint walls | YES | 2019-08-15 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000011 |  | 19P000011 | FALSE | CHASS | SL5 PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED |  | PSYCHOLOGY1 | 2111A | COMPLETE | Juliet McMullin | Cindy Williams | LORENA QUINTANA |  | Paul Ditty |  | 4 |  | TRUE |  |  | 2018-07-03 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000090 |  | 20P000090 | FALSE | CHASS | SL5 OLMSTED 3345 - PAINT WALL AND FILL HOLES |  | OLMSTED | 3345 | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-08-20 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000421 |  | 19P000421 | FALSE | CHASS | SL5 INSTALLATION OF DOOR IN ORDER TO ACCESS HALLWAY DIRECTLY | Install door to access hallway directly | OLMSTED | 2139I | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 5 | 110 | TRUE |  |  | 2018-12-19 | Order material and schedule work | 2020-01-20 | 2020-03-06 |  |  |  | 2/28/20, DL: This Project is Complete….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: This Project is 95% complete. We should be complete within the next week…………..1/31/20 O-DHN: Emailed Status Report to customer……1/30/20,DL; Project is in progress and should be complete with in 2- weeks………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: This project is delayed. We will work on the construction schedule and material shortly after the new year. 11/21/19 DH: Emailed Status Report to customer…..10/30/19, DL: Plans are approved. Need to find out the status of the door. We will plan on scheduling the project shortly after Thanksgiving…………10/1/19, DL; Plans are approved. We need to order the door / Frame. Once door is on site, we will schedule the work……..9/16/19, DL; Plans are submitted for the permit review process……9/3/19, DL; Plans are at 50%. We will try and have plans to submit for review within the next two weeks…… | 2019-02-05 | Enrico Baez | *****This work is being performed to accommodate new faculty scheduled to arrive July 1, 2019***** Core work falls under SLA Carpenters • Open wall between corridor and 2139I. • Install metal frame and solid core door similar to 2139. Smoke and draft gasket. • Install carpet patch at threshold of new door. Carpet should match or complement existing carpet. • Remove bulletin board in hallway to facilitate doorway construction and relocate on same wall. See photos in shared drive.. • Replace base boards as needed. Painters • Prime, Patch and Paint walls, doors and trim. • Paint to match existing wall colors. Lock Shop • Furnish and install 1 each, ADA compliant handle sets, match existing hardware. | YES | 2020-02-28 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
20P000172 |  | 20P000172 | FALSE | CHASS | SL5 PYSCHOLOGY 2136B & 2136C - PAINT & PATCH |  | PSYCHOLOGY1 | 2136B & 2136C | COMPLETE | Juliet McMullin | Cindy Williams | ANNIKA KIRMAN | YERAM CHEONG | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-10-10 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/15/20 |  | Paul Ditty |  |  | 2020-01-15 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000604 |  | 19P000604 | FALSE | CHASS | SL5 HUMANITIES SS, RM 7704- PAINT OFFICE BY JULY 1, 2019 |  | HUM & SOC SC | 7704 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 06/20/19 O-ANS: Project complete per Paul Ditty updates. |  |  |  |  | 2019-06-20 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
19P000676 |  | 19P000676 | FALSE | CHASS | SL5 PATCH THE PAINT IN THIS OFFICE |  | HUM & SOC SC | 2501 | COMPLETE | Juliet McMullin | Cindy Williams | EVAN ISMAIL |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-06-19 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-04 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000357 |  | 19P000357 | FALSE | CHASS | SL5 PATCH AND PAINT WALLS, TIME SENSITIVE |  | HUM & SOC SC | 1302 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-10-25 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000314 |  | 19P000314 | FALSE | CHASS | SL5 HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Juliet McMullin | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000642 |  | 19P000642 | FALSE | CHASS | SL5 HMNSS, RM 3003- ROOM PAINTING - PHIL ROOM |  | HUM & SOC SC | 3202, 3204, 3205, 3213, 3214, 3217, 3307 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-05-21 | [6 empty] | 07/16/19 O-ANS: Project complete as of 07/16/19 per Paul Ditty. |  |  |  |  | 2019-07-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000444 |  | 18P000444 | FALSE | CHASS | SL5 PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 |  | ARTS | 242 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-05-21 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-21 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000171 |  | 20P000171 | FALSE | CHASS | SL5 CHASS INTN 2107 - PATCH UP HOLES IN THE WALL |  | CHASS INT N | 2017 | COMPLETE | Juliet McMullin | Cindy Williams | GENEVA AMADOR |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-10-10 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/03/20 |  | Paul Ditty |  |  | 2020-01-03 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000082 |  | 20P000082 | FALSE | CHASS | SL5 HUMANITIES THEATRE - PATCH & PAINT |  | THTR WKSH | 405 | COMPLETE | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-08-15 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-26 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000204 |  | 20P000204 | FALSE | CHASS | SL5 ARTS 166 - PATCH AND PAINT IN LOBBY AND GREEN ROOM |  | ARTS | 166 | COMPLETE | Juliet McMullin | Cindy Williams | ALBERT FETTER |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-10-31 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/20/19 |  | Paul Ditty |  |  | 2019-12-20 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000552 |  | 19P000552 | FALSE | CHASS | SL5 HUMANITITIES SS, RM 1001B, C, D- PAINTING - TUTORIAL ROOMS |  | HUM & SOC SC | 1001 B, C, and D | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-03-27 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000207 |  | 19P000207 | FALSE | CHASS | SL5 QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-08-23 | working on plans | 2019-06-03 | 2019-06-28 |  |  |  | 8/1/19, DL: This project is 100% Complete……7/15/19, DL; Floor covering will be installed next week. Floor covering is the last item for this project……..7/1/19, DL; This project is 95% complete except floor covering. Floor covering will be installed within 2- weeks……6/17/19, DL; This project is making good progress. We should be complete near July 1st…….5/31/19, DL; This project started this week and should be complete by June 28th…….3/18/19, DL; Working on plans and we will submit our plans and permit application this week….. | 2018-09-20 | Enrico Baez |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000300 |  | 19P000300 | FALSE | CHASS | SL5 HUM & SOC SC--URGENT: PAINT AND PATCH WALLS |  | HUM & SOC SC | 4403 | COMPLETE | Juliet McMullin | Cindy Williams | ANDREA HERAZ |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000226 |  | 20P000226 | FALSE | CHASS | SL5 HUMANITIES SOCSCI 3401 - OFFICE PATCH AND PAINT |  | HUM & SOC SC | 3401 | COMPLETE | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON | TRACY AVERY | Paul Ditty |  | 8 |  | TRUE |  |  | 2019-11-18 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/03/20. |  | Paul Ditty |  |  | 2020-02-03 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000448 |  | 19P000448 | FALSE | CHASS | SL5 ARTS 333- PATCH AND PAINT |  | ARTS | 333 | COMPLETE | Juliet McMullin | Cindy Williams | SONJA SEKELY-ROWLAND |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-01-14 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-04 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000286 |  | 19P000286 | FALSE | CHASS | SL5 FACULTY OFFICES: TOUCH UP PAINT |  | HUM & SOC SC | 2005 | COMPLETE | Juliet McMullin | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-09-17 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000194 |  | 19P000194 | FALSE | CHASS | SL5 PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 |  | HUM & SOC SC | 3304 | COMPLETE | Juliet McMullin | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000094 |  | 20P000094 | FALSE | CHASS | SL5 ARTS 0221 -PAINT OFFICE |  | ARTS | 221 | COMPLETE | Juliet McMullin | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-08-22 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000589 |  | 19P000589 | FALSE | CHASS | SL5 HMSS OFFICE 3405 RENOVATIONS | Construct partion, pending CBO approval, in room 3405. | HUM & SOC SC | 3405 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2019-04-23 | Install carpet | 2019-09-01 | 2019-11-15 |  |  |  | 11/19/19 DH: Emailed Status Report to customer…..11/19/19 DL: This project is complete….11/11/19, DL: The carpet is delayed and scheduled to be instlled on Friday, 11/15/19. The project will be complete once the carpet is installed……10/30/19, DL: This project is 90% Complete. We are planning to install carpet next week………..10/16/19, DL; This project is 80% complete. Target complete date is 3- weeks…..10/3/19 O-ANS: Updated status per minor reno meeting…. 10/1/19, DL; This project is in progress. We will call for rough electrical inspection….. 9/16/19, DL; We are ready to schedule the work. We are currently waiting for the space to be vacated. Once the space is vacant, we will start the project……9/3/19, DL; We are ready to start the work. The PI returned to work this week. I sent Paul R. an email letting him know we are available to start once we have confirmed dates from him…..8/15/19, DL; Plans are approved but the PI is not. We will probably start the project the 2nd week in September…… | 2019-06-27 | Enrico Baez | CARPENTERS: 1. Construct partition above T-bar ceiling, full height not required. Drywall 5/8" tape and finish. 2. Remove and store three book cases. 3. Cut in opening for 36" (stain grade to match) door in general area of were bookcases were in South wall leading to corridor. Painters: 1. Patch and paint as needed Electricians: 1. Isolate existing switches to control to operate lights in West half of partitioned space. 2. Install two additional switches in East partition. 3. Install additional single gang outlets one on each side of new partition. Telecom: 1. Install additional Voice and data connection in Western side of partitioned space. Flooring: 1. Remove carpet and base. 2. Install new customer selected base and flooring. HVAC: 1. Separate existing duct work from one to two zones controlled by separate stats in each office. | YES | 2019-11-19 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000232 |  | 20P000232 | FALSE | CHASS | SL5 PSYCHOLOGY 3111B - WALL PATCH FOR SMALL HOLES IN THE WALL |  | PSYCHOLOGY1 | 3111B | COMPLETE | Juliet McMullin | Cindy Williams | EMILY LAM |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-11-20 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000061 |  | 19P000061 | FALSE | CHASS | SL5 PSYCHOLOGY 1111H-PATCH HOLES IN WALL |  | PSYCHOLOGY1 | 1111H | COMPLETE | Juliet McMullin | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000608 |  | 19P000608 | FALSE | CHASS | SL5 PAINT LARGE TEACHING ASSISTANTS OFFICE |  | WATKINS | 1345 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-05-10 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-27 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000429 |  | 19P000429 | FALSE | CHASS | SL5 CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | Patch & Paint | COLL BLDG NO | 103 | COMPLETE | Juliet McMullin | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-01-03 | [6 empty] | 07/26/19 O-ANS: Project complete per Paul Ditty. 06/06/19 O-ANS: Project scheduled to be completed. |  |  |  |  | 2019-07-26 | SPRING 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000540 |  | 19P000540 | FALSE | CHASS | SL5 HUMANITIES SOCSCI ENGLISH DEPT ROLL UP RENO | Remove metal roll up window, replace carpet, remove round column cover-reframe square. | HUM & SOC SC | 1202 | COMPLETE | Juliet McMullin | Cindy Williams | MICHAEL MOLINAR |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2019-03-20 | Plans and permit | 2020-01-06 | 2020-02-14 |  |  |  | 2/18/20, DL: Thois project is 100% Complete…….1/31/20 O-DHN: Emailed Status Report to customer…..1/30/20, DL; Project is 95% complete. We will install carpet this weekend………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is in progress and should be complete within 3 weeks……….12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project was delayed. Material is ordered. We are currently scheduled to start shortly after 1/6/20………..11/19/19 DH: Emailed Status Report to customer…..10/30/19, DL: We will plan on scheduling the project shortly after Thanksgiving……….. 10/16/19, DL; Plans were approved, we will work on ordering material and schedule the work. Anticipated start date is mid-November…….10/1/19, DL; Plans were submitted last week. Once plans are approved, we will schedule the work…………9/16/19, DL; Plans are 90% Complete. We will submit plans for plan check review in the next two weeks……. 8/15/19, DL; Gunter has the project on his list. We will try and be ready for plan check review in the next two weeks…….. | 2019-07-25 | Enrico Baez | 7/1/2019 E. Baez Carpenters: 1. Remove roll up partition and stainless steel counter top. 2. Frame opening, hang drywall, tape and finish 3. Remove round decorative column from support pillar. 4. Frame over column for square foot print. Keep as narrow as possible. 5. Hang drywall, tape and finish. Painters: 1. Paint all new construction Flooring: 1. Remove carpet and base in 1202, lobby area of 1220 and hallway. Refer to drawing. 2. Replace customer selected carpet and base. | YES | 2020-02-18 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000568 |  | 19P000568 | FALSE | CHASS | HOLD SL5 HMSS HANG WHITE BOARD, TV MOUNTING, PATCH AND PAINT | Remove Glass White Board, mount TV, patch and paint | HUM & SOC SC | 1214 | COMPLETE | Juliet McMullin | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-04-09 | [8 empty] | Enrico Baez | No scope |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000213 |  | 20P000213 | FALSE | CHASS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS |  | CHASS INT S | 2117A, 2117C, 2117D, 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-11-08 | approved permit | 2020-03-03 | 2020-03-21 |  |  |  | 8/5/20, DL: This Project is Complete……………..2819/20 O-DHN: Emailed Status Report to customer…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have a contract, we will order the material and schedule the work………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Plans are complete and submitted for building permit. We are also working on the contract. Once the plans are approved and the contract is complete, we will schedule the work………. |  | Enrico Baez |  |  | 2020-08-05 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21 | 1
19P000186 |  | 19P000186 | FALSE | CNAS | SL5 NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION |  | PIERCE | 319 | COMPLETE | Kathryn Uhrich | Jose Wudka | BARBARA OUTZEN |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-06-18 | [6 empty] | Pending gas line installation scheduled for the week of 09/24 per Steve Burleson. Move glove boxes from 206 to Rm 319 after gas line are installed. All work is complete |  | Enrico Baez |  | YES | 2018-11-08 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000296 |  | 18P000296 | FALSE | CNAS | SL5 SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES |  | SKYE HALL | 266 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  |  | 31 | FALSE |  |  | 2018-02-02 | [6 empty] | 01/17/19, DL; This project was completed last summer……..DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19 18; I neeed to check on this work order. I thought it was part of the 2nd floor Hallway project but it was not…… |  | Dan Lerman |  | YES | 2019-01-01 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000185 |  | 19P000185 | FALSE | CNAS | SL5 NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE |  | W. CONWAY PIERCE HALL | 206 (originially identified as Room 204) | COMPLETE | Kathryn Uhrich | Jose Wudka | BARBARA OUTZEN |  | Dan Lerman |  |  | 6 | TRUE |  |  | 2018-06-18 | [6 empty] | 12/14/18, DL; This project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Pending glove box relocation to rm 319 and minor vent reconfiguration. Both tasks will be performed afet the glove boxes relocate to rm. 319. 10/29/18 All project related work is completed. |  | Enrico Baez |  | YES | 2018-12-14 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000310 |  | 18P000310 | FALSE | CNAS | SL5 ADD INTERCOM/BUZZ IN SYSTEM |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-12 | [6 empty] | Dl, 7/4/18; This project is scoped. This will be a new ADA operator, door bell / Intercom and buzzer button to unlock door. Walked work with Contractor, need to work on producing contract with PD&C. Once Contract is confirmed, we will schedule the work..... DL, 7/11/18; We have the proposal. Need to execute the agreement and schedule the work. The target complete date is before 10/1/18.....Dl 8/10/18; Jason will try and complete the work with in the next three weeks......DL, 8/22/18; Jason order parts, parts have 6-8 week lead time. Work will be scheduled when material arrives.....DL, 10/4/18; This Project is 100% Complete....... |  | Dan Lerman |  | YES | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000227 |  | 18P000227 | FALSE | CNAS | SL5 BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL |  | BATCHELOR | 4128 | COMPLETE | Kathryn Uhrich | Jose Wudka | APRIL MEINZER |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-12-12 | [6 empty] | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM.......DL, 5/24/18; Need to work on plans and permits. Project needs to be complete before Fall academic 2018.....DL, 6/16/18; Walked project with Jess. and he will schedule the abatment. We will not need plans for this project. We are not removing the exhasut hood which was the original purpose foor the plans......Carpenters started the demo. Still need to remove TSI. Once TSI is removed, we can schedule the plumbing work. Target Complete Date is 9/21/18....DL, 8/10/18; Abatement is scheduled for this weekend, we will start work soon.....DL, 8/22/18; Abatement and most demo complete. Still on track for 9/21/18.....DL, 9/19/18; Scope change. This project should be complete on 9/28/18.......DL, 10/4/18; Floor to be installed this Friday. Pianters will finalized the stain on the cabinets. Thsi project should be complete near 10/19/18.......Dl, 11/7/18; This project is 100% complete.... |  | Dan Lerman |  | YES | 2018-11-08 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
18P000247 |  | 18P000247 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 |  | PHYSICS | 3023 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Paul Ditty |  |  | 15 | FALSE |  |  | 2017-12-20 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Spring 2018 | FS | FALSE | 2017 | 2021-03-16
18P000028 |  | 18P000028 | FALSE | CNAS | SL5 CHAPMAN PATCH AND PAINT |  | CHAPMAN | 0010A | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced .......DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th.....Test test |  | Dan Lerman |  | YES | 2018-07-12 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
18P000434 |  | 18P000434 | FALSE | CNAS | SL5 BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY |  | BOYCE | 4478 | COMPLETE | Kathryn Uhrich | Jose Wudka | Sabrina Schuster |  | Paul Ditty |  |  | 3 | TRUE |  |  | 2018-05-09 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000392 |  | 18P000392 | FALSE | CNAS | SL5 BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 |  | BATCHELOR | 0 | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Paul Ditty |  |  | 8 | TRUE |  |  | 2018-04-12 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000341 |  | 18P000341 | FALSE | CNAS | SL5 PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL |  | PHYSICS | 1132 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-14 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process…DL, 6/16/18; Jess tested the matreial flooring and paint is hot. Jess will abate before we proceed with the project….Still need to scheudle the work. This project target complete date is late Fall……DL, 7/25/18; Jess sent out the 14-day notification to the AQMD last week. We will start the balance of the project after the ACM and Lead is abated or encapsulated…..8/10/18; Abatement is complete. We will work on the other items as time permits. This space is vacant with no occupancy date |  | Dan Lerman |  | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000287 |  | 18P000287 | FALSE | CNAS | SL5 SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  |  | 33 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19/18; This project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000288 |  | 18P000288 | FALSE | CNAS | SL5 SKYE HALL OFFICE SUITE PAINTING |  | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000292 |  | 18P000292 | FALSE | CNAS | SL5 SKYE HALL PAINT MULTIPLE FACULTY OFFICES |  | SKYE HALL | 228 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000027 |  | 18P000027 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT LAB |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-05 | [6 empty] | 2/1/19, DL; This project is 100% Complete……………DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again…… DL, 4/2/18; This space is still on schedule for 7/1/18 completion date…..FAMIS work orders have been produced…..DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th…..TEST TEST |  | Dan Lerman |  | YES | 2018-07-12 | Fall 2017 | FS | FALSE | 2018 | 2021-03-16
18P000256 |  | 18P000256 | FALSE | CNAS | SL5 BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES |  | BOYCE | 3451 | COMPLETE | Kathryn Uhrich | Jose Wudka | Sabrina Schuster |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave at Webber is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place.......DL, 5/9/18; Autoclave is destroyed. Pictures were sent to Cheryl. We are now waiting for the equipment to arrive. Steve B is working on Steam connection at Boyce......DL, 5/24/18; Autoclaves arrived. Day crew is scheduled to deliver the unit on 5/30/18. we will schule the plumbers and electricians shortly there after......DL, 6/16/18; Webber Autoclave is almost complete. This portion should be complete next week. WE will run the Webbber autoclave for two weeks before we start the Boyce Autoclave. The weldolet for the BOyce unit will be installed during the steam shutdown...... DL, 7/11/18; Webber Auto clave will be complete on 7/12/18. We will start the demo of the Boyce Auto clave next soon. Target date for this project is 8/10/18...... DL, 7/25/18; We had a delay with the Webber autoclave which will implact the Boyce Auto clave. New target complete date is 8/22/18.....DL, Plumbing is almost complete, need to schedule final elctrical and Commission equipment. Target date 8/31/18...... DL, 9/6/18; This project should be complete but we still need to schedule the electrical connections ASAP.........DL, 9/19/18; This project is 100% Complete. |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2017 | 2021-03-16
18P000029 |  | 18P000029 | FALSE | CNAS | SL5 CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS |  | CHAPMAN | 1 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain......DL, 5/24/18; This work is scheduled to be complete on or before 7/1/18.....DL, 6/16/18; Blinds are delayed to mid July but window clenaning is still on schedule......DL, 7/11/18; This Project is 100% Complete |  | Dan Lerman |  | YES | 2018-07-11 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
18P000356 |  | 18P000356 | FALSE | CNAS | SL5 ENTOMOLOGY PATCH AND PATCH |  | ENTOMOLOGY | 278 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  |  | 10 | TRUE |  |  | 2018-03-20 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000030 |  | 18P000030 | FALSE | CNAS | SL5 CHAPMAN PREP AND PAINT FROM WATER DAMAGE |  | CHAPMAN | 100 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete..... |  | Dan Lerman |  | YES | 2018-11-08 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
18P000117 |  | 18P000117 | FALSE | CNAS | SL5 PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION |  | WEBBER | 1303 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-21 | [6 empty] | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work....DL, 5/9/18; Produced work order for JEss to test for lead paint and ACM....Von wall is hot, everything else is good to go. I will schedule the work soon. The space is vacant......DL, 7/11/18; This project is in progress. Target Complete Date is 8/10/18....DL, 7/25/18; Vinyl plank and bullitin boards the balance of the task for this project. Still on target for complete on 8/10/18.....DL; 8/10/18; We were schedule to install the fllor and identified Asbestos,. Jess is working on the propsal and schedule for the abatment. This will require a 14- dat notification to the AQMD. This space is vacant with no scheduled move in date......DL, 8/22/18; Abatment is scheduled for this Tursday and Friday. We will scheule the carpet in dry errase boards for next week.Target complete date will be 8/31/18.....DL, 9/6/18; This project is 100% Complete...... |  | Dan Lerman |  | YES | 2018-09-10 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
18P000118 |  | 18P000118 | FALSE | CNAS | SL5 OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT |  | OLMSTED | 1337 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2017-09-20 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space.......DL, 6/16/18. New staff member schedule to start mid july. BKM is also scheduled for mid july. This project will require cabinets to be removed, new carpet, paint and blank out electrical outlets that will no longer be used.. new signage too.....DL, 7/11/18;This project is in progress. Complete date is 7/20/18......DL, 7/25/18; This project is 100% Complete....... |  | Dan Lerman |  | YES | 2018-07-25 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
19P000287 |  | 19P000287 | FALSE | CNAS | SL5 URGENT: PAINT SHOP TO PATCH AND PAINT |  | MAT SCI ENGR | 229 | COMPLETE | Kathryn Uhrich | Jose Wudka | HONG XU |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-19 | [8 empty] | Paul Ditty |  |  | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000058 |  | 19P000058 | FALSE | CNAS | SL5 Assess Feasiblity of Removing/Replacing Growth Chambers |  | GH18 | 18 | COMPLETE | Kathryn Uhrich | Jose Wudka | APRIL MEINZER |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-28 | [6 empty] | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing...DL, 5/9/18; Project is scoped. Need to schedule the work.....Plumbers and HVAC are working on this. Still need to have electrical removed. I am working wiht Patty on who can do the demo and removal.....DL, 7/11/18; I need to check in with Ken to see if refrigerant is recovered. will isue work order to disconnect electrical..... I checked in with our campus surplus and do not have any contacts to dis,matel the very large growth Chambers. I need to inform Patty and suggest that she have Burges demo and move the Growth Chambers......We will be complete with our portion of this project before 8/1/18.......DL, 8/10/18; All work is done except the disconnect for electrical. I need to check and see if the electrical. Per FAMIS complete on 8/22/18 |  |  |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000346 |  | 19P000346 | FALSE | CNAS | SL5 I&Q--PAINTING ROOMS IN THE I&Q |  | EAST I&Q FAC |  | COMPLETE | Kathryn Uhrich | Jose Wudka | IMAD BAYOUN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2019-01-09 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
18P000293 |  | 18P000293 | FALSE | CNAS | SL5 SKYE HALL COPIER ROOM PATCH AND PAINT |  | SKYE HALL | 278 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Paul Ditty |  |  | 32 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman |  | YES | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18W000455 |  | 18W000455 | FALSE | CNAS | SL5 CHAPMAN CLEAN WINDOWS |  | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  |  | 37 | FALSE |  |  | 2017-07-11 | [6 empty] | Dl, 7/4/18; All Windows in Chapman were cleaned by Ductch Touch. This Project is 100% Complete |  | Enrico Baez |  | YES | 2018-07-11 | Summer 2018 | FS | FALSE | 2017 | 2021-03-16
18W011161 |  | 18W011161 | FALSE | CNAS | SL5 REPLACE CARPET |  | SCIENCE LAB1 | 301 | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-23 | [6 empty] | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project……DL, 5/21/18; Floor covering is selected. Work will be scheudled for Mid June….DL, 5/24/18; The install is scheduled for June 18th & 19th……DL, 7/11/18; This Project is 100% Complete...... |  | Dan Lerman |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18W011692 |  | 18W011692 | FALSE | CNAS | SL5 ENTOMOLOGY; PAINT/PATCH LAB |  | ENTOM MUSEUM | 211 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-03-08 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18W011672 |  | 18W011672 | FALSE | CNAS | SL5 ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY |  | ENTOMOLOGY | 268 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-03-08 | [6 empty] | Relocate white board from East wall onto the West wall, where high table was removed, 24" away from North end of wall. |  | Paul Ditty |  | N/A | 2018-07-25 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
20P000187 |  | 20P000187 | FALSE | CNAS | SL5 PHYSICS 3004S - PATCH AND PAINT WALLS SAME COLOR |  | PHYSICS | 3004S | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA | DEBORAH MCWILLIAMS | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-23 | [8 empty] | Paul Ditty |  |  | 2019-11-05 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000298 |  | 19P000298 | FALSE | CNAS | SL5 SPIETH - PREP LAB FOR FACULTY SEARCH |  | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-09-26 | work is in progress | 2019-02-14 | 2019-04-30 |  |  |  | 5/15/19, DL; This Project is 100% Complete… 5/1/19, Dl; This project will be complete next week…..4/15/19, DL; We are making good progress on this project and we should be complete the first week in May……..3/28/19, DL; This project is in progress and should be complete by or near May 1st….2/14/19, DL; Need to schedule trades and obtain quotes to refinish countertops…… |  | Enrico Baez | 12/13/18 O-RVL: Ron V was informed of this project by D. McWilliams on 12/12/18. RV reviewed the request and noticed it was assigned to Paint. RV changed to O-RVL for scoping for new faculty. RV added revised scope (12/13)of work provided by D.McWilliams email on 12/10. See below. REVISED SOW 1363 & 1364 Spieth 1363 Wet Lab Space Note: There is evidence in the ceiling and along one wall of a water intrusion issue, i.e. peeling paint, leaking and rusted pipes, etc. The cause of this damage needs to be investigated and repairs confirmed, including painting the wall and ceiling where damage is visible. Patch/paint Re-finish, re-surface the existing cabinets Re-finish and/or replace bench-tops If both sinks cannot be significantly cleaned, they should be replaced Replace faucets at both sink locations. Clean existing Chemical fume hood Repair or replace self-closing chemical / flammables storage cabinet On one bench remove overhead shelving unit and relocate electrical outlets to the ends of bench to accommodate large desktop equipment. Cap off remaining utilities for potential use/re-connection in the future. Remove shelves on west wall to accommodate siting of large floor-standing equipment before patch and painting. Also, add 120/240 electrical outlets (raceway) along this wall. Replace flooring -- this depends on what we decide about removing the walk-in fume hood listed below Add GFCI outlets near water sources Requires a connection to a DI water system Other utilities are required in this room and at what locations, e.g. air, oxygen, gas, vacuum, etc.? Remove existing walk-in Fume Hood (if cost for this issue does not trigger project over $50k)Please assess/cost out and advise prior to project. Spieth 1364 Lab Support Space Patch/paint, Re-finish, re-surface the existing cabinets (non-porous surface) Re-finish and/or replace bench-tops If sink cannot be significantly cleaned, they should be replaced Replace faucets at sink location. Add GFCI outlets near water sources Requires a connection to a DI water system | N/A | 2019-05-15 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000449 |  | 19P000449 | FALSE | CNAS | SL5 PAINT OFFICE AREA OF 229A FOR RELOCATION |  | FAWCETT LAB | 229A | COMPLETE | Kathryn Uhrich | Jose Wudka | Sabrina Schuster |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-01-14 | [6 empty] | 04/05/19 O-ANS: Project complete per Paul Ditty and closed in FAMIS. |  |  |  |  | 2019-04-05 | Winter 2019 | FS | FALSE | 2019 | 2021-03-16
19P000440 |  | 19P000440 | FALSE | CNAS | SL5 GH#21--INSTALLATION OF GROW POD BEHIND GREENHOUSE #21 |  | GH21 |  | COMPLETE | Kathryn Uhrich | Jose Wudka | APRIL MEINZER | PATRICIA SPRINGER | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-08 | Install under ground utilites | 2019-04-01 | 2019-05-31 |  |  |  | 5/31/19, DL; This project is 100% complete :)……5/15/19, DL; Project is complete except for chain link fence. Fence will be installed some time early next week…….5/1/19, DL; Grow Pod is installed with power and water. Still need to install fence and door lock….. 4/15/19, DL; Grow Pod is scheduled for delivery this Thursay. Once on site, we will connect all utilities and this project will be complete. 2/28/19, DL; Demo is complete. We need to veify utilitiy point of connections. Once utilities are verified, we will install the water and power……. |  | Dan Lerman |  |  | 2019-05-31 | Winter 2019 | FS | FALSE | 2019 | 2021-03-16
19P000390 |  | 19P000390 | FALSE | CNAS | SL5 BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | COMPLETE | Kathryn Uhrich | Jose Wudka | APRIL MEINZER |  | Dan Lerman |  | 0 |  | TRUE |  |  | 2018-11-29 | Order material and schedule work | 2019-06-01 | 2019-06-28 |  |  |  | 7/1/19, DL; This project is 100% Complete…………6/17/19, DL; material is ordered. This project should be complete by July 1st…..5/31/19, DL; Plans were apprvied this week we will work on the contract and hopefully have the notice to proceed in the next two weeks. It is our goal to have the work complete on or before July 1st……5/15/19, DL; Need to order the special order door and frame…. | 2019-02-07 | Enrico Baez | Install new aluminum storefront door, frame and side lite(requested by Dan L.), patch & paint door opening and west interior wall. | YES | 2019-07-01 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000358 |  | 19P000358 | FALSE | CNAS | SL5 GEOLOGY - ACCOMMODATION REQUEST |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-10-26 | Plans and Permits were submitted | 2019-02-14 | 2019-04-12 |  |  |  | 4/15/19, DL; This Project is 100% Complete……. 3/28/19, DL; Plans are approved. We will start the work on 4/1/19……3/18/19, DL; Waiting for approved plans from building official……2/28/19, DL; Plans were submitted to building official for review. Once plans are approved, we will schedule the work………..2/14/19, DL; Plans are in process and we will apply for building permit next week………….. | 2019-02-07 | Enrico Baez | SOW: Installation of Charging station Power Point of connection, concrete drive and charge station pad. Landscape: Clearing, cap and relocate irrigation lines and sprinklers. Replant vegetation as needed. Demolition: Concrete saw cutting curb Concrete: Excavation, form-work, place and finish concrete pad approx. 10'x10'. Signage: Provide the appropriate signage identifying parking designation, pavement markings-striping marked in front of the drive Electrical: Provide an Electrical POC and weather proof enclosure for the new cart charger. NOTES: Title changed to PHYSICS on 02/07/19, FORMERLY TITLED GEOLOGY BLD ACCOMMODATION REQUEST | YES | 2019-04-15 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000505 |  | 19P000505 | FALSE | CNAS | SL5 CHAPMAN HALL PAINT OFFICE WALL WHERE BOOK CASE WAS REMOVED |  | CHAPMAN | 10B | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-02-25 | [6 empty] | 05/10/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-05-10 | Winter 2019 | FS | FALSE | 2019 | 2021-03-16
18P000473 |  | 18P000473 | FALSE | CNAS | SL5 PIERCE NEW CARPET & PAINT FACULTY OFFICE |  | W. CONWAY PIERCE HALL | 202 | COMPLETE | Kathryn Uhrich | Jose Wudka | BARBARA OUTZEN |  | Paul Ditty |  | 1 | 5 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | 2018-09-26 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
20P000036 |  | 20P000036 | FALSE | CNAS | SL5 ENTOMOLOGY 224 - PAINT OFFICE FOR NEW PI HANSEN |  | ENTOMOLOGY | 224 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-07-23 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/08/20. 09/19/19 O-ANS: Project placed on HOLD for WINTER 2020 prioritization per customer request. |  | Paul Ditty |  |  | 2020-01-08 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000061 |  | 20P000061 | FALSE | CNAS | SL5 PHYSICS 1028 - MOVE UTILITIES FOR GLASS SHOP | Install utilities in Physics for the Glass shop equipment relocated from Pierce. | PHYSICS | 1028 | COMPLETE | Kathryn Uhrich | Jose Wudka | CHRISTOPHER BARDEEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-08-06 | Plans and permits | 2019-11-18 | 2020-01-24 |  |  |  | 04/23/20 O-ANS: Complete per Dan Lerman. Separate work order to install gas line created - 20W026489 …. 1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: This project is 90% complete and should be 100% complete 1/24/20………….12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 95% complete. They are moving the equipment over. Once the equipment is delivered and setup, we will connect all of the power and plumbing……11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL; We are still working on plans for this project. 10/30/19, DL: We're planning to complete the project by 12/7/19. We are working on the plans and are planning to submit the plans for plan check review tomorrow. | 2019-10-16 | Enrico Baez | Electrical: Relocate existing power for the welder & other equipment. Install new power and safety switch for relocated equipment. Relocate power for welder and other equipment to the machine shop side of the north wall. Plumbing: Lab air and Natural Gas - relocate and install new POC's. Install water supply lines to Wet sander and diamond wet saw. Cap and or extend the existing Lab air and natural gas as necessary. Install drain lines for new equipment. Modify water supply and existing sink and faucet. Carpentry: Demo selected upper and lower cabinets at the West wall. | YES | 2020-04-23 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000075 |  | 20P000075 | FALSE | CNAS | SL5 SPIETH 2372 - PATCH/PAINT FACULTY OFFICE |  | SPIETH | 2372 | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH MCWILLIAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-08-13 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-27 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000299 |  | 19P000299 | FALSE | CNAS | SL5 SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 |  | SPIETH | 3378 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000202 |  | 20P000202 | FALSE | CNAS | SL5 SKYE HALL 361 RENOVATION PROJECT | Renovete space for class room. | SKYE HALL | 361 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY | MELISSA GOMEX | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-10-30 | pending permit approval | 2020-02-05 | 2020-03-27 |  |  |  | 9/30/20, DL: This Project is Complete……….8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Permits were approved. Demolition is complete…..1/15/20 O-DHN: Emailed Status Report to customer……..1/14/20, DL: Plans have been submitted for a building permit. Once plans are approved, it is our goal to complete the work by the beginning of spring quarter….. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2020-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000639 |  | 19P000639 | FALSE | CNAS | SL5 DOOR/EXHAUST CONNECTION/VACUUM LINE HOOKUP/GAS CYL RACK | Make modifications to accommodate new PI | CHEMICAL SCI | 0435 | COMPLETE | Kathryn Uhrich | Jose Wudka | BARBARA OUTZEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-05-17 | finish electrical and plumbing.. | 2019-10-31 | 2019-12-06 |  |  |  | 12/16/19, DL: This project is complete…11/19/19 Emailed Status to customer….11/11/19, DL: This project is 90% Complete. We should be complete with the balance of the work in the next two weeks…………10/30/19, DL: This project is in progress and should be complete in 3- weeks……..10/16/19, DL; We will start the work in the next two weeks. 9/16/19, DL; We will start working on the plans in the next 3- weeks and submit them for plan check review. Once approved, we will schedule the work……..9/3/19, DL; Need to verify scope with Ron and start working on plans. Will start plans in the next two- three weeks…… | 2019-07-19 | Enrico Baez | For new Faculty Hire, Dr. Timothy Su we need the following done to CS 435: Original SOW: (1) Add a door between 435 and 439 (swinging outside of 435 into 439). (2) Exhaust connection for a biosafety cabinet (3) Vacuum line hook up (4) Gas cylinder rack Revised SOW 07/30/19: Room 435: (A) Remove mounted wooden cabinets (B) Remove standing wooden cabinet (C) Move flammable cabinet to Room 439 (D) Move flammable refrigerator to Room 447 Room 439: (A) Remove cabinets under sink Room 441: (A) Remove cabinets under sink (B) Remove top and bottom cabinets and bench, then deliver both items to Chemical Sciences Rm 108 (C) De-activate airflow in chemical fume hood #005855 if it does not disrupt air flow in the other chemical fume hoods. Can facilities check whether it is possible to turn valve off for this fume hood without disrupting others? (D) Move biosafety cabinet and incubator from Rm 458 to Rm 441, then hook up biosafety cabinet to house vacuum plumbing (E) Move flammable cabinet to Rm 439 | YES | 2019-12-16 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000571 |  | 19P000571 | FALSE | CNAS | SL5 SCI LAB 1- PATCH & PAINT 322 & 215 |  | SCIENCE LAB1 | 215 & 322 | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2019-04-10 | [6 empty] | 07/30/19 O-ANS: Project complete per Paul Ditty. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000244 |  | 19P000244 | FALSE | CNAS | SL5 PATCH & PAINT GEOLOGY |  | GEOLOGY | 2258A | COMPLETE | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2018-09-06 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000347 |  | 19P000347 | FALSE | CNAS | SL5 SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT |  | SPIETH | 3320 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-10-16 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
18P000223 |  | 18P000223 | FALSE | CNAS | SL5 Provide requisite utility infrastructure to support 4 add'l chambers (on order). |  | FAWCETT LAB |  | COMPLETE | Kathryn Uhrich | Jose Wudka | APRIL MEINZER |  | Dan Lerman |  | 11 | 21 | FALSE |  |  | 2017-12-11 | [6 empty] | 2/1/19, DL; This Project is 100% Complete……..01/15/19, DL; Plans are approved, Chambers are on site. Electrical is complete. Plumbing work is in progress. Our portion of the project should be complete by 2/1/19…………..12/14/18, DL; All Pre work is complete. The Chambers are scheduled to arrive on site within the next 30-days. We will finish this project when material on site……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans……..DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet….DL, 4/29/18; Still need to conduct site visit with the team….DL, 5/24/18; Per Patty, equipment is ordered but 5- months out…..DL, 9/6/18; We will submit plans to Bob W. tomorrow for review and approval……..DL, 9/19/18; Plans are approved. The equipment will be here in about 4- months. WE will start the work for this project in the Fall to ensure we are ready when the equipment arrives……DL, 9/19/18; Plans are currently being review by BO & FM……DL, 11/7/18; Plans are approved. WE are requesting to change the placement confirguration of the growth chamber and awaitng Bob's review and approval. WE are on track to have this work complete befoire the end of the new year….. |  | Dan Lerman |  | YES | 2019-02-01 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
20P000239 |  | 20P000239 | FALSE | CNAS | SL5 SKYE 382 - PATCH AND PAINT |  | SKYE HALL | 382 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 11 |  | FALSE |  |  | 2019-11-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000367 |  | 19P000367 | FALSE | CNAS | SL5 SCILAB 1 0211- PATCH & PAINT |  | SCIENCE LAB1 | 211 | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-31 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000240 |  | 20P000240 | FALSE | CNAS | SL5 SKYE 384 - PATCH AND PAINT |  | SKYE HALL | 384 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 12 |  | FALSE |  |  | 2019-11-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000137 |  | 19P000137 | FALSE | CNAS | SL5 LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM |  | LIFE SCIENCE | 2545 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
20P000241 |  | 20P000241 | FALSE | CNAS | SL5 SKYE 386 - PATCH AND PAINT |  | SKYE HALL | 386 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 13 |  | FALSE |  |  | 2019-11-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/07/20 |  | Paul Ditty |  |  | 2020-01-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000045 |  | 19P000045 | FALSE | CNAS | SL5 PREPARE LOCATION AND UTILITIES FOR INSTALL |  | BOYCE | 2407 | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 14 |  | FALSE |  |  | 2018-07-23 | [8 empty] | Enrico Baez |  | YES | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000200 |  | 20P000200 | FALSE | CNAS | SL5 COLLEGE BLDG NO 306 - PATCH AND PAINT ONE WALL ONLY |  | COLL BLDG NO | 306 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2019-10-29 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 02/06/20. |  | Paul Ditty |  |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000106 |  | 19P000106 | FALSE | CNAS | SL5 PHYICS 1134 - UTILITIES REQUEST |  | PHYSICS | 1134 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Dan Lerman |  | 15 |  | FALSE |  |  | 2018-08-01 | Installed Chilled water | 2019-03-28 | 2019-05-03 |  |  |  | 6/15/19, DL; This Project is 100% Complete…...5/1/19, DL; Project should be complete this week or early next week…..3/28/19, DL; Power is complete. Need to finish chilled water…… 2/1/19, DL; Review scope with Customer. Still need to review with Brian from the Electic shop…………….12/14/18, DL; No update…. | 2018-11-07 | Enrico Baez |  | YES | 2019-06-15 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000170 |  | 19P000170 | FALSE | CNAS | SL5 INSTALL NEW IRRADIATOR INSTRUMENT |  | MAT SCI ENGR | 51 | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 16 |  | FALSE |  |  | 2018-08-08 |  | 2019-02-01 | 2019-02-14 |  |  |  | 2/14/19, DL; This project is 100% Complete………2/1/19, DL; Power is complete. Chilled water will be complete next week…………..1/15/19, DL; Electric is commplete, Water will be complete with in two weeks. Equipment should be on site soon…12/14/18, DL; This project is currently on hold per RED…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; The unit is schedukled for delivery in the next three weeks. | 2018-09-19 | Enrico Baez |  | YES | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000105 |  | 20P000105 | FALSE | CNAS | SL5 PHYSICS 2029 - PATCH AND PAINT |  | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2019-08-28 | [8 empty] | Paul Ditty | 08/06/20 O-ANS: Closed per Paul Ditty as of 02/06/20. |  | 2020-02-06 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000292 |  | 19P000292 | FALSE | CNAS | SL5 GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Dan Lerman |  | 18 |  | FALSE |  |  | 2018-08-10 | Install Chain link fence…… | 2019-01-28 | 2019-03-29 |  |  |  | 3/28/19, DL; This Project is 100% Complete…….2/14/19, DL; The Concrete and Power is Complete. We still need to install the chain link which will be installed in about 3-4 weeks………..2/1/19, DL Electrical is complete. WE will pour Concrete next week. We will schedule the fence install 28- days after concrete is poured………; Th1/15/19, DL; Plans are approved, we will start the work in the next two weeks……12/14/18, DL; Plans are almost complete. We will schedule the work after plans are approved……DL, 11/7/18; Conducted site visit with Chris P. We need to confirm a feasable site location before we move forward with the work…. |  | Enrico Baez |  | YES | 2019-03-28 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000214 |  | 19P000214 | FALSE | CNAS | SL5 PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT |  | PHYSICS | 3005 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-08-24 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000034 |  | 20P000034 | FALSE | CNAS | SL5 CHEMICAL SCIENCES 451- PATCH AND PAINT 2 SMALL WALL SECTIONS |  | CHEMICAL SCI | 451 | COMPLETE | Kathryn Uhrich | Jose Wudka | KEVIN KOU |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-07-22 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-02 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000081 |  | 20P000081 | FALSE | CNAS | SL5 CHEM SCI 0441- INSTALL FUME HOODS | Install vacuum to new fume hood | CHEMICAL SCI | 441 | COMPLETE | Kathryn Uhrich | Jose Wudka | TIMOTHY SU |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-08-15 | schedule the work | 2019-10-25 | 2019-11-22 |  |  |  | 1/14/20, DL This Project is 100% Complete…….12/17/19 O-DHN: Emailed Status report to customer…..12/16/19, DL: This Project is almost Complete except for connecting the glove box. Cory will try and connect the glove box before the new year……...11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: This project should be complete with in the next two weeks……….10/30/19, DL: This project is in progress and we should be complete in 2- 3 weeks…………10/16/19, DL: We will start this project with in the next two weeks…. |  | Enrico Baez | Install eight (8ea) electrical swithced outlets behind cabinets for new vac pumps, remove doors and install sliding lower pump shelves. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000341 |  | 19P000341 | FALSE | CNAS | SL5 PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL |  | PIERCE |  | COMPLETE | Kathryn Uhrich | Jose Wudka | BARBARA OUTZEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000189 |  | 20P000189 | FALSE | CNAS | SL5 SPIETH 3352 - ESTIMATE FOR PATCH AND PAINT |  | SPIETH | 3352 | COMPLETE | Kathryn Uhrich | Jose Wudka | NATALIE HOLT | SILVANA | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-10-23 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/28/20 |  | Paul Ditty |  |  | 2020-01-28 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000340 |  | 19P000340 | FALSE | CNAS | SL5 PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE |  | SKYE HALL | 349 | COMPLETE | Kathryn Uhrich | Jose Wudka | VICTORIA AVALOS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000622 |  | 19P000622 | FALSE | CNAS | SL5 FAWCETT LAB, RM 204- REPLACE DOOR OR DOOR LOCK | Replace doors & frame | FAWCETT LAB | 204 | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-15 | order door and frame. | 2019-08-14 | 2019-10-16 |  |  |  | 11/11/19, DL: This project is complete……10/30/19,DL: The doors are scheduled to be installed this Friday…………10/16/19, DL; Doors shuld be here with in the next week. Once the doors arrive, we will prep and paint the first coat and schedule the install. Target complete date is 3-4 weeks depending on when the doors arrive…….9/16/19, DL The doors are ordered. Once the doors arrive, we will schedule them to be painted and installed……..9/3/19, DL; Contractor has PO# for the doors. I need to verify lead time on material and schedule the installation…….8/15/19, DL; PO# will be provided this week to order the doors and frame, lead time is 4- weeks for the doors/ frame. We will scheudule the install once the door / frame is on site……..8/1/19, DL ; Pending estimate from vendor. Once we have everything needed, we will schedule the work…. | 2019-07-15 | Enrico Baez | Replace existing dual egress doors with ne doors and frames. | YES | 2019-11-11 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000355 |  | 20P000355 | FALSE | CNAS | SL5 GEOL 454A- PATCH & PAINT |  | GEOLOGY | 0454A | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | LAURIE GRAHAM | PAUL DITTY |  | 2 |  | FALSE |  |  | 2020-02-09 | [8 empty] | Paul Ditty | 08/06/20 O-ANS: Closed per Paul Ditty as of 03/13/20. |  | 2020-03-13 | Spring 2020 | FS | FALSE | 2020 | 2021-03-16 | FY 19-20
19P000283 |  | 19P000283 | FALSE | CNAS | SL5 HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 20 |  | FALSE |  |  | 2018-09-05 | Schedule site visit with contrac | 2019-06-03 | 2019-07-02 |  |  |  | 8/1/19, DL; This Project is 100% Complete……7/1/19, DL; Barricades are complete. Signage needs to be installed. Signage to be installed in the next 3- weeks………….6/17/19, DL; Yello Caution tape is installed. Still need to install barricades and signage. Target complete date in mid to late July……5/31/19, DL; The contractor has the PO#. We will start the work and complete the work in the next 30- days……5/15/19, DL; We are waiting on the quote, once we have the quote, we will proceed with the work……4/15/19, DL; We are trying to locate a roofing contractor that will complete the installation. This is a specialty product that requires a professional installation…….3/28/19, DL; We will install the yellow caution tape on the roof which is our most viable option. I will schedule a site visist / job walk with a contractor in the near future…… | 2018-09-19 | Enrico Baez | Install hand railing and marking for a leading edge as direcetd by EH&S. | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
18P000388 |  | 18P000388 | FALSE | CNAS | SL5 SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 2018-04-10 | schedule the work | 2019-06-03 | 2019-08-19 |  |  |  | 8/14/19, DL; This project is 100% Complete………8/1/19, DL; This project work from Facilities Services should be complete in about 2- weeks…..7/15/19, DL, Work is in progress. Goal is to be complete with our scope near the first week in August……6/17/19, DL; This will be scheduled in July…….5/31/19, DL; Demo and removal of the dishwasher is. We will work on the installation and elctrical / power connections over the next three weeks. Note. Steam shut down is taking priority and the installation may be delayed….. 5/15/19, DL; We will schedule the work……..DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but there is no hard date as this is vacant space and we will access the space as time permits…… DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter….DL, DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans….7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved….. |  | Enrico Baez |  | YES | 2019-08-14 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
18P000486 |  | 18P000486 | FALSE | CNAS | SL5 PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 2018-06-28 | plans and permits | 2019-03-29 | 2019-07-01 |  |  |  | 8/1/19, DL; This project is 100% Complete…… 6/17/19, DL; This project is making good progreess and will be complete near mid- July…..5/31/19, DL; This project is making good progress and we are hopeful to be complete on or before July 1st……5/1/19, DL: This project is in grogress and moving forward. Target complete date is 6- weeks… 4/15/19, DL; Started Demolition phase….2/28/19, DL; We will work on the plans in the next 30-days.12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman |  | YES | 2019-08-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000210 |  | 19P000210 | FALSE | CNAS | SL5 CHEMICAL SCI Install Door In Doorway |  | CHEMICAL SCI | 0225A | COMPLETE | Kathryn Uhrich | Jose Wudka | BARBARA OUTZEN |  | Dan Lerman |  | 25 |  | FALSE |  |  | 2018-08-24 | contract the work and material | 2019-06-03 | 2019-07-01 |  |  |  | 7/1/19, DL; This project is 100% complete…..6/17/19, DL; Po is cut. Target complete date is before 7/1/19……Permit was approved this week. We are now working on the contract with the vendor. Our goal is start the work with in the next 30- days. 5/15/19, DL; Plans were approved. I am in the process of working with PD&C for the contract. We will order material and schedule the wrok once we have a signed contract……..3/28/19, DL; Plans were submitted last week… 3/18/19, DL; Conducted site visit last week. We are working on plans now we will try and submit plans for permit review next week…… | 2018-09-19 | Enrico Baez |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
18P000099 |  | 18P000099 | FALSE | CNAS | SL5 EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 |  | GEOLOGY |  | COMPLETE | Kathryn Uhrich | Jose Wudka | LAURIE GRAHAM |  | Dan Lerman |  | 26 | 23 | FALSE |  |  | 2017-09-08 | Move Cabinets and install electr | 2019-05-01 | 2019-05-17 |  |  |  | 4/19/19, DL; This Project is 100% Complete :)…………….12/6/18, DL; This project is a priority #23 and may be completed in the next 12 - months…..DL 1/3: Chris to verify with customer on electrical requirements for completion……DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress…..DL, 7/11/18; Still need to work on plans…. Target date is 9/30/18….. |  | Dan Lerman | Install power to 4- cabinets in hallway | YES | 2019-04-19 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
17W012504 |  | 17W012504 | FALSE | CNAS | PAINT Business OFFICE AND CONF. ROOM |  | ENTOMOLOGY | 170 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | 27 | 26 | FALSE |  |  | 2017-05-04 | [6 empty] | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. |  | Dan Lerman |  | YES | 2018-10-22 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
18P000257 |  | 18P000257 | FALSE | CNAS | SL5 SKYE HALL MOUNT 55 |  | SKYE HALL | 209 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  | 28 | 28 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete…….1/15/19, DL, Site visit is scheduled with James M. this Thursday. We will schedule the work shortly after the site visit…….12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2017 | 2021-03-16
18P000258 |  | 18P000258 | FALSE | CNAS | SL5 SKYE HALL HALLWAY MOUNT |  | SKYE HALL | 212 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  | 29 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete……1/15/19, DL, Site visit is scheduled with James M. this Thursday…………12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2017 | 2021-03-16
18P000284 |  | 18P000284 | FALSE | CNAS | SL5 SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT |  | SKYE HALL | 277 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Paul Ditty |  | 29 | 23 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman |  | YES | 2018-09-21 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
20P000024 |  | 20P000024 | FALSE | CNAS | SL5 PHYSICS 1003- RENOVATION | New Faculty-Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 1003 | COMPLETE | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-07-18 | clean out the space | 2020-01-13 | 2020-02-28 |  |  |  | 3/25/20, DL: This project is complete……2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: The paint is complete and the floor covering should be delivered this week. Once the floor covering is on site, we will schedule the installation……………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We started this project and should be complete in the next 6- weeks……….11/18/19 DH: Emailed Status Report to customer…..11/11/19, DL: David who is responsible for clearing out the space is in the process. Once the space is empty we will schedule the work. We will probably start the physical project shortly after Thanksgiving…….10/30/19, DL; We are planning to start this project within the next 6-8 weeks……. | 2019-10-16 | Enrico Baez | Test for ACM and or other hazardous materials in the room. Replace all existing flooring, remove power pole and miscellaneous wall mounted items shelving/racks, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks) and repair/replace top & bottom flush bolts, install new door closer(s), relamp with LED as needed. Replace faucet, clean sink/counter and infill pit. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000207 |  | 20P000207 | FALSE | CNAS | SL5 PHYSICS 3033 - PAINT & PATCH STAFF OFFICE |  | PHYSICS | 3033 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO | DAVID NEFF | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-11-04 | [6 empty] | 03/02/20 O-ANS: Completed per Paul Ditty as of 02/04/20. |  | Paul Ditty |  |  | 2020-02-04 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000006 |  | 19P000006 | FALSE | CNAS | SL5 MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 |  | MAT SCI ENGR | 310 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 3/18/19, DL; This project is 100% Complete…..2/14/19, DL; This project is 90% Complete. ………2/1/19, DL; This Project started to day. We are scheduled to be complete by the end of February………..1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. | 2018-09-28 | Enrico Baez |  | YES | 2019-03-18 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000266 |  | 20P000266 | FALSE | CNAS | SL5 GEOLOGY 2460B - PATCH & PAINT |  | GEOLOGY | 2460B | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 3 |  | FALSE |  |  | 2019-12-19 | [8 empty] | Paul Ditty | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000301 |  | 19P000301 | FALSE | CNAS | SL5 SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH |  | SCIENCE LAB1 | 214 | COMPLETE | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-09-27 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000613 |  | 19P000613 | FALSE | CNAS | SL5 COLLEGE BUILDING NORTH, RM 203B AND 206- PAINT |  | COLL BLDG NO | 0203B | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-21 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000347 |  | 18P000347 | FALSE | CNAS | SL5 GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) |  | GEOLOGY | 0 | COMPLETE | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Dan Lerman |  | 31 | Deferred to Fall Quarter - summer priority 27 | FALSE |  |  | 2018-03-18 | sheet metal to install handrail | 2019-02-25 | 2019-03-22 |  |  |  | 4/15/19, DL; Thios Project is 100% Complete….3/28/19, DL; Monitor is installed, need to finish power and data………………...2/14/19, DL: The monitor is on site. We need to schedule the installation. 2/1/19, DL; Conducted site visit with Amber. Amber will order the monitor. We will schedule the installation when the monitor is on site………….DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez |  | YES | 2019-04-15 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000055 |  | 19P000055 | FALSE | CNAS | SL5 CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM |  | COLL BLDG SO | 207 | COMPLETE | Kathryn Uhrich | Jose Wudka | LISA DUNMORE |  | Dan Lerman |  | 32 | 24 | FALSE |  |  | 2018-05-18 | order fan and schedule install | [5 empty] | 4/15/19, DL; This project is 100% Complete…….3/28/19, DL; Need to order material and schedule the work…… Work order is assigned. 12/14/18, Dl; This project is prioritized at 32 and will not be scheduled in the near futurer…….DL, 7/11/18; Correction, I did not scope this yet, I thought we were talking agout the door bell and ADA operator. I will check in with Ronda and verify the scope…… DND 7/30/18: Created project to replace WO #18015182; project #19P000055 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. | 2018-11-29 | Enrico Baez | SOW is to install a new exhaust fan at the second floor toilet room. Roof access is available from the access panel in the closet located in the room 210 next door. There is roof is transite per Jess. Abatement is necessary for roof penetrations and possibly has lead paint on ceilings and walls. | YES | 2019-04-15 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18W013160 |  | 18W013160 | FALSE | CNAS | BEES- PATCH & PAINT 2460D & 2460F |  | GEOLOGY | 2460 | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO |  | Paul Ditty |  | 33 | 29 | FALSE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000191 |  | 19P000191 | FALSE | CNAS | SL5 PATCH AND PAINT HINDERAKER BASEMENT |  | HINDERAKER |  | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 34 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000464 |  | 18P000464 | FALSE | CNAS | SL5 PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED |  | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 35 |  | FALSE |  |  | 2018-08-16 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000436 |  | 18P000436 | FALSE | CNAS | SL5 COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS |  | COLL BLDG SO | 210 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 36 | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000174 |  | 19P000174 | FALSE | CNAS | SL5 BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT |  | BATCHELOR | 2112 | COMPLETE | Kathryn Uhrich | Jose Wudka | AMY RICKS |  | Dan Lerman |  | 37 |  | FALSE |  |  | 2018-07-24 | final conduit and paint | 2019-04-15 | 2019-05-03 |  |  |  | 5/1/19, Dl; This project is 100% Complete….. 4/15/19, DL; This project should be complete in 2-weeks…… 12/14/18, DL; This project is priortized at 37 and will not be scheudled until further notice…… | 2018-09-19 | Enrico Baez |  | YES | 2019-05-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000042 |  | 19P000042 | FALSE | CNAS | SL5 COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL |  | COLL BLDG SO | 200 | COMPLETE | Kathryn Uhrich | Jose Wudka | LISA DUNMORE |  | Paul Ditty |  | 38 |  | FALSE |  |  | 2018-07-20 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000049 |  | 19P000049 | FALSE | CNAS | SL5 PHYSICS PATCH & PAINT |  | PHYSICS | 3036 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAZMIN CHAVEZ |  | Paul Ditty |  | 39 |  | FALSE |  |  | 2018-07-25 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000267 |  | 20P000267 | FALSE | CNAS | SL5 GEOLOGY 2460C - PATCH & PAINT |  | GEOLOGY | 2460C | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 4 |  | FALSE |  |  | 2019-12-19 | [8 empty] | Paul Ditty | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/04/20. |  | 2020-03-04 | Spring 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000235 |  | 20P000235 | FALSE | CNAS | SL5 SKYE 374 - PATCH AND PAINT |  | SKYE HALL | 374 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 4 |  | TRUE |  |  | 2019-11-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000318 |  | 19P000318 | FALSE | CNAS | SL5 GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE |  | GEOLOGY | 420 | COMPLETE | Kathryn Uhrich | Jose Wudka | KAREN CATO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-04 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000508 |  | 19P000508 | FALSE | CNAS | SL5 BOYCE, RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | RM 3410/3426- LAB PREPARATION FOR NEW FACULTY HIRE | BOYCE | 3410 | COMPLETE | Kathryn Uhrich | Jose Wudka | Sabrina Schuster |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-02-21 |  | 2019-11-04 | 2019-12-06 |  |  |  | 1/30/20, DL: Project is now cxomplete. The electrical panel cover was installed this morning…………. 11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: We are not complete. We still need to complete the following items; Light bulbs, electrical panel cover, replace ACM ceiling tiles and deep clean the space…..10/30/19, DL: Progress is in progress. We should be done within two weeks…….10/16/19, DL; Paint is in progress and additional work to follow. Target date for complete is 11/19/19…..10/1/19, DL; Jess to survey space for ACM, Lead paint, etc… We will schedule work once we have confirmation from Jess….. | 2019-09-30 | Enrico Baez | ……….Remove lower base cabinets and upper cabinet in room 3410B. Repair delaminated flooring between room 3410 & 3426, Patch and Paint entire rooms 3410, 3410B & 3426 up to 8'H(no paint in in 3410 A&C). Repair damaged floor tiles in room 3410 A&B. Repace all burned out lamps w/ LED throughout labs and office. Strip & wax all floors in labs space. Remove cylinder racks in room 3410B. Fabricate a hinged metal door to cover the electrical panel in roon 3426 (panel is near door). | YES | 2020-01-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000688 |  | 19P000688 | FALSE | CNAS | SL5 PHYSICS- RENOVATION OF THREE PHYSICS ROOMS | Renovate Room Finishes and Verify Utilities are Code Compliant. | PHYSICS | 2128 | COMPLETE | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-06-28 | finish abatment | 2019-11-05 | 2019-12-15 |  |  |  | 1/14/20, DL: This Project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: The project looks great. We are 99% Complete. Custodial will be there this week to complete the final clean. The space will be ready for occupancy starting 1/6/19…..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: The project is on track to be complete on 12/13/19. Once the abatement is complete, we will start the wall repair as the walls are severely damaged from the previous use of the space……10/30/19, DL: WE are working on this project. Our target date for completion is 12/17/19………… | 2019-10-16 | Enrico Baez | Test for ACM and or other hazardous materials in the room. RM 2124, 2128 & 2132: Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2128 Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. RM 2132: Remove copper/mesh at walls and ceiling. Repair wall finishes. Replace all existing flooring, patch and paint all walls up to 10’ A.F.F., service door lock (key sticks), install new door closer(s), relamp with LED as needed. Clean sink. Confirm all Electrical, Plumbing and HVAC systems are operational and code compliant. | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000031 |  | 19P000031 | FALSE | CNAS | SL5 BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) |  | BIOLOGIC SCI | 3101 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 40 |  | FALSE |  |  | 2018-07-16 | Schedule the work | [5 empty] | 6/15/19, DL; This Project is 100% Complete…...5/1/19, Dl; This project will be complete on 5/5/19…..3/28/19, DL; Need to schedule a site visit with Estella. Left voice mail message on 3/28/19 to schedule site visit……..12/14/18, DL; This is prioritized at #40 and will not be scheduled in the near future….. |  | Enrico Baez |  | YES | 2019-06-15 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | COMPLETE | Kathryn Uhrich | Jose Wudka | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | Work will be complete in 2 weeks | 2020-02-03 | 2020-03-13 |  |  |  | 8/5/20, DL: This project is complete……………..06/17/20, DL: This project should be complete with in the next two weeks……..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within two weeks. Once we have a contract, we will schedule the work……….1/15/20 O-DH: Emailed Status Report to customer……1/14/20, DL: Contracts is currently working on the contract. Once the contract is complete, we will order the material and schedule the work…………11/26/19, DL: Plans were approved. We will work on the construction contract. Once we have the notice to proceed, we will schedule the work……….10/15/19, DL: Sent PD&C and follow-up email on 11/11/19. We should have approved plans in the near future……10/30/19, DL: Sent PD&C an email asking for a status update on 10.30.19…… 10/16/19, DL; Plans are still in plan check. I sent the building official an email asking if any additional information is needed. This work will be completed by a contractor which means we need to allow time for the bid and contract process……… …………9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Enrico Baez | Request for Estimate to install three new FOB readers with electrified locksets. Work covered: Install one AC Fob Reader at door 2221 and one AC Fob reader at each Door 4231 & 4235. Connect card readers to the existing Hirsh ACP located in the IDF closet at each floor. 03/07/19: Scope revised to eliminate two FOB readers. Install one FOB reader at Genomics door 4231 only instead of all three rooms. | YES | 2020-08-05 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 20-21
19P000102 |  | 19P000102 | FALSE | CNAS | SL5 PATCH & PAINT FRONT CORNER OF OFFICE |  | LIFE SCIENCE | 2930 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Paul Ditty |  | 42 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000133 |  | 19P000133 | FALSE | CNAS | SL5 PATCH HOLES AND PAINT |  | BATCHELOR | 2203 | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Paul Ditty |  | 43 |  | FALSE |  |  | 2018-08-07 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000184 |  | 19P000184 | FALSE | CNAS | SL5 REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES |  | GEOLOGY | 1270 | COMPLETE | Kathryn Uhrich | Jose Wudka | LAURIE GRAHAM |  | Dan Lerman |  | 45 |  | FALSE |  |  | 2018-08-14 | Schedule the floor installation | 2019-02-11 | 2019-03-29 |  |  |  | 4/15/19, DL; This Project is 100% Complete…….. 3/28/19, DL; The project is 90% complete. Need to schedule floor installation…….. 2/14/19, DL; We will schedule the work soon. The space is vacant and ready…………….2/1/19, DL; This project has started. We would like to have the work complete by mid March…………..12/14/18, DL; This project is prioritized at 45 and will not be shceudled until further notice…… |  | Enrico Baez | SCOPE CARPENTERS-Remove all wall, base and center island cabinet work. Verify no ACM flooring under center island. PLUMBERS-Remove sinks in 1270 and 1270A. Terminate, at wall plumbing. Remove air/gas lines on wall in 1270 and 1270A. Remove lower chilled water, supply and return, lines on East wall. Remove air and gas line, flush with floor, from center island. FLOORING-Remove VCT in 1270 and 1270A, replace with customer selected VCT. Replace all cove base. ELECTRICIANS-Remove gray flexible conduit at raceway, terminate circuit. PAINTERS- Patch and paint walls in both spaces. | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000246 |  | 19P000246 | FALSE | CNAS | SL5 PHYSICS - PATCH AND PAINT |  | PHYSICS | 3007N | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Paul Ditty |  | 46 |  | FALSE |  |  | 2018-09-07 | [6 empty] | n/a |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000242 |  | 19P000242 | FALSE | CNAS | SL5 PAINT OFFICE |  | COLL BLDG NO | 210 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 47 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000231 |  | 19P000231 | FALSE | CNAS | SL5 OLMH 1428 PATCH AND PAINT |  | OLMSTED | 1428 | COMPLETE | Kathryn Uhrich | Jose Wudka | ANDREW CABRERO |  | Paul Ditty |  | 48 |  | FALSE |  |  | 2018-08-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000243 |  | 19P000243 | FALSE | CNAS | SL5 GENOMICS 1206 - PATCH AND PAINT WALLS |  | GENOMICS | 1206 | COMPLETE | Kathryn Uhrich | Jose Wudka | AIMEE GONZALES |  | Paul Ditty |  | 49 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000019 |  | 20P000019 | FALSE | CNAS | SL5 PHYSICS 2029A- NEW EYEWASH STATION | PHYSICS 2029A- INSTALL A NEW EYEWASH STATION | PHYSICS | 2029A | COMPLETE | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | Dan Lerman |  | 5 |  | FALSE |  |  | 2019-07-16 | order material | 2020-02-28 | 2020-03-27 |  |  |  | 2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL; Permit was approved, we need to order material and schedule the work………. | 2019-11-27 | Enrico Baez | Install new eyewashing station | YES | 2020-03-25 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000615 |  | 19P000615 | FALSE | CNAS | SL5 COLLEGE BLDG NO, RM 203 AND 204- PAINT |  | COLL BLDG NO | 203 AND 204 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-05-14 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000236 |  | 20P000236 | FALSE | CNAS | SL5 SKYE 368 - PATCH AND PAINT |  | SKYE HALL | 368 | COMPLETE | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ | JAMES MARBERRY | Paul Ditty |  | 5 |  | TRUE |  |  | 2019-11-25 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/17/19 |  | Paul Ditty |  |  | 2019-12-17 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000268 |  | 20P000268 | FALSE | CNAS | SL5 GEOLOGY 2460D - PATCH & PAINT |  | GEOLOGY | 2460D | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 5 |  | FALSE |  |  | 2019-12-19 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | Paul Ditty |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000285 |  | 19P000285 | FALSE | CNAS | SL5 PAINT AND PATCH PI OFFICE |  | ENTOMOLOGY | 269 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-09-17 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000062 |  | 19P000062 | FALSE | CNAS | SL5 MSE 169-MINOR RENOVATION - NEW FACULTY |  | MAT SCI ENGR | 169 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Dan Lerman |  | 5 | 19 | TRUE |  |  | 2018-07-30 | Install water heater | 2018-11-12 | 2019-01-17 |  |  |  | 2/1/19, DL; This project is 100% Complete…………..1/15/19, DL; This project is 99% complete pending one water heater. Water heater is not here yet……12/14/18, DL; This project is 95% complete. The water heater is scheduled for delivery shortly after the new year. We will complete the install when the heater arrives…… 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 9/6/18; We will have the power and cabinets removed by 9/19/18. We are in the process of producing plans for this project. Once the plans are approved, we will proceed with the project. Note, we still need to obtain important information and some specifications regarding the procured base cabinets and counter tops, bio safety cabinet, diswasher, and freezer. ……DL, 7/7/18; The work is 90% complete. We are waiting on parts which have a 4-6 week lead time. We will finsh the balance of the project when the parts arrive….. | 2018-08-22 | Enrico Baez |  | YES | 2019-02-01 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000523 |  | 19P000523 | FALSE | CNAS | SL5 PATCH & PAINT GRAD STUDENT OFFICE | PATCH & PAINT GRAD STUDENT OFFICE | SPIETH | 3366 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Paul Ditty |  | 5 | 9 | FALSE |  |  | 2019-03-12 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-20 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000176 |  | 19P000176 | FALSE | CNAS | SL5 PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY |  | PHYSICS | 1112 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Paul Ditty |  | 50 |  | FALSE |  |  | 2018-08-10 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2019-01-15 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000023 |  | 20P000023 | FALSE | CNAS | SL5 PIERCE RM 1144 - PATCH AND PAINT DOOR WHERE WALL POCKET WAS |  | PIERCE | 1144 | COMPLETE | Kathryn Uhrich | Jose Wudka | JACQUELINE |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-07-18 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000269 |  | 20P000269 | FALSE | CNAS | SL5 GEOLOGY 2460E - PATCH & PAINT |  | GEOLOGY | 2460E | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 6 |  | FALSE |  |  | 2019-12-19 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/05/20. |  | Paul Ditty |  |  | 2020-03-05 | Spring 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000121 |  | 20P000121 | FALSE | CNAS | SL5 SKYE 217 - PATCH AND PAINT |  | SKYE HALL | 217 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-09-05 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/18/19 |  | Paul Ditty |  |  | 2019-12-18 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000126 |  | 19P000126 | FALSE | CNAS | SL5 CHEMICAL SCIENCE - MINOR RENOVATIONS |  | CHEMICAL SCI | 455 | COMPLETE | Kathryn Uhrich | Jose Wudka | KEVIN KOU |  | Dan Lerman |  | 6 |  | TRUE |  |  | 2018-08-03 | [6 empty] | 12/14/18, DL; This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL,11/7/18; Paint is complete, Plumbing shop is planning to schedule the work in the near future…… |  | Enrico Baez |  | YES | 2018-12-14 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000247 |  | 20P000247 | FALSE | CNAS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | Refresh Lab: Patch paint, strip & clean floor, repair broken ceiling and floor (VCT) tiles at room 2110 & 2118. Install Electrical power & Co2 cylinder racks at each end of workbench/tables | SPIETH | 2110 + 2118 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | Dan Lerman |  | 6 |  | TRUE |  |  | 2019-11-27 | [6 empty] | 1/19/21, DL: This project is complete…………..9/30/20, DL: This project is in progress and will be compete in the next 6- 8 weeks……………8/5/20, DL: We will start on this project in the next 6-8 weeks….. | 2020-04-17 | Enrico Baez | Spieth 2110: Carpentry: Seismic anchoring for “New” tables and equipment. Replace damaged ceiling tiles. Install misc. wall mounted items. Sheet Metal: Remove “existing” steel cage. Fabricate & install metal cylinder rack w/ restrains/seismic anchoring to floor. Plumbing: Install Co2 POC for gas cylinders at four (4ea) new free-standing work benches (see configuration on this document). Electrical: Install dedicated *120v power drop & connect to the existing power strips built-in the four (4ea) new workstation tables (see configuration on this document). *VERIFY/CONFIRM VOLTAGE W/ D. MCW. Relamp fixtures as needed. Spieth 2118 & 2110: Sheetmetal: Clean and or replace air distribution grilles. Flooring: Repair/patch broken floor tile and Replace broken ceiling tiles (abate floor tiles if required). Painting: Paint and patch all walls, verify recondition doors @ room side. Plumbing: Assess sinks to be fully operational & clean. *Replace sink in Rm 2118 for glassware, confirm with Faculty/Estella. Replace sink in room 2118 (Sink type TBD by Faculty). HVAC: Check lab air pressure is operational & proper pressure. Custodial: Strip and Wax floor, clean interior windows, wipe down doors and windowsills. EXCLUSIONS: Furnish, assemble, and install new workstations, tables or lab equipment. Removal of existing lab furniture or equipment. Natural gas or air output taps not required (per Faculty). | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GH08 | 881 | COMPLETE | Kathryn Uhrich | Jose Wudka | NANCY FERGUSON |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2019-01-29 | Schedule the work. | [5 empty] | 1/19/21, DL: This project is complete……………8/5/20, DL: This project is in Progress and should be complete in the next 8-12 weeks…………….3/25/20, DL: Work orders are produced. Once we are back to work, we will schedule the work………12/11/19 O-ANS: Re-assigned as project allotment - priority #7 for Winter 2020. 11/27/19 O-ANS: Hold by client for re-prioritization for Winter 2020. | 2020-03-04 | Enrico Baez | Install new 3 ton Packaged unit with heat pump and dedicated electrical service on the roof top. Provide 1ea return plenum, 2ea supply drops in the work space. | YES | 2021-01-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
20P000113 |  | 20P000113 | FALSE | CNAS | SL5 GEOLOGY 2258 - PATCHPAINT RECEPTION WALL OVER BIN REMOVED |  | GEOLOGY | 2258 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2019-09-04 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/13/19 |  | Paul Ditty |  |  | 2019-12-13 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000230 |  | 19P000230 | FALSE | CNAS | SL5 NEW FACULTY OFFICE FOR PATCHWORK/PAINT |  | GEOLOGY | 1242A | COMPLETE | Kathryn Uhrich | Jose Wudka | KAREN CATO |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-08-30 | [6 empty] | n/a |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000360 |  | 19P000360 | FALSE | CNAS | SL5 GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING |  | GEOLOGY | 1444 | COMPLETE | Kathryn Uhrich | Jose Wudka | KAREN CATO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-10-29 | [6 empty] | 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000270 |  | 20P000270 | FALSE | CNAS | SL5 GEOLOGY 2460F - PATCH & PAINT |  | GEOLOGY | 2460F | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 7 |  | FALSE |  |  | 2019-12-19 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/03/20. |  | Paul Ditty |  |  | 2020-03-03 | Spring 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000155 |  | 20P000155 | FALSE | CNAS | SL5 BOYCE 3407 - PAINT OFFICE FOR NEW FACULTY |  | BOYCE | 3407 | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2019-10-01 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/30/20 |  | Paul Ditty |  |  | 2020-01-30 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000251 |  | 19P000251 | FALSE | CNAS | SL5 CHEM SCI 428-PATCH DRY WALL HOLES |  | CHEMICAL SCI | 428 | COMPLETE | Kathryn Uhrich | Jose Wudka | KEVIN KOU |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000482 |  | 19P000482 | FALSE | CNAS | SL5 PIERCE HALL- PAINT/PATCH HOLES IN 1219C AND 1220D |  | PIERCE | 1219C | COMPLETE | Kathryn Uhrich | Jose Wudka | JACQUELINE HAMILTON |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2019-02-01 | [6 empty] | 06/28/19 O-ANS: Paint complete per Paul Ditty. |  |  |  |  | 2019-06-28 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
20P000271 |  | 20P000271 | FALSE | CNAS | SL5 GEOLOGY 2460G - PATCH & PAINT |  | GEOLOGY | 2460G | COMPLETE | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 8 |  | FALSE |  |  | 2019-12-19 | [6 empty] | 04/29/20 O-ANS: Complete per Paul Ditty as of 03/06/20. |  | Paul Ditty |  |  | 2020-03-06 | Spring 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000369 |  | 19P000369 | FALSE | CNAS | SL5 PIERCE - PAINT IS PEELING OFF WALLS |  | PIERCE | 3341 | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
18P000221 |  | 18P000221 | FALSE | CNAS | SL5 Provide add'l HVAC capacity to maintain lower temp |  | BOYCE | 4414 | COMPLETE | Kathryn Uhrich | Jose Wudka | APRIL MEINZER |  | Dan Lerman |  | 9 | 16 | FALSE |  |  | 2017-12-11 | [6 empty] | 12/14/18, DL; This project is 100% Complete……….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob. DL, 5/9/18; We will work on plans and submit for review.....DL, 6/16/18. Had meeting with Bob W. to verify what is needed on plans. I will work with Gunther on plans for submittal and review......DL, 7/11/18; Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall.....DL, 11/7/18; Material is on site and will will schedule the work with in the next 30- days..... |  | Dan Lerman |  | YES | 2018-12-14 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
19P000288 |  | 19P000288 | FALSE | CNAS | SL5 COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS |  | COLL BLDG NO | 202 | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-19 | [6 empty] | 05/10/19 O-ANS: Project was canceled by FS in March 2019 because customer will have to submit separate work orders for each room since customer has requested to schedule and complete them separately in sequence (not all at once). 3/4/19 DND Complete per PD |  | Paul Ditty |  | N/A | 2019-03-04 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000291 |  | 19P000291 | FALSE | CNAS | SL5 MSE HELIUM RECOVERY SYSTEM |  | MAT SCI ENGR | 205 | COMPLETE | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Dan Lerman |  | 9 | HOLD | FALSE |  |  | 2017-07-24 |  |  | 2018-12-14 |  |  |  | 12/14/18, DL; This project is 100% Complete……DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB - spoke with Mayela who is determining status within her dept…. DL, 11/7/18; This project is complete but I need to conduct a final site visit….. |  | Enrico Baez |  | YES | 2018-12-14 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
18P000465 |  | 18P000465 | FALSE | CNAS | SL 5 GEOLOGY 2258B AND 2258C - PATCH/PAINT |  | GEOLOGY | 2258B & 2258C | COMPLETE | Kathryn Uhrich | Jose Wudka | RONDA INZUNZA |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 2018-06-06 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000377 |  | 19P000377 | FALSE | CNAS | SL5 BG - SCHNEIDER HOUSE DRIVEWAY GATE | Replace the gates on the Schneider House driveway, which secure the property, with the taller iron gates that used to be installed at the Gardens entrance. This will require new fence posts and hinges as well. The taller gates are stored along the side of the garage at Schneider House, and Facilities staff can come see them anytime. Please note this is a safety and security project. | BOT GDN HSE |  | COMPLETE | Kathryn Uhrich | Jose Wudka | AMBER RHEMREV |  | Dan Lerman |  | R2 | 117 | FALSE |  |  | 2018-11-08 | PO#, schedule the work | 2019-11-18 | 2019-11-28 |  |  |  | 11/26/19, D: This Project is 100% Complete……………11/19/19 DH: Emailed Status Report to customer….11/15/19, DL: We should have A PO this week. Once we have the PO#, we will schedule the work……10/30/19, DL: Project was approved by customer with an FAU #. I will work on providing a PO# as this is maintenance and schedule the work. | 2019-04-05 | Enrico Baez | Replace Gates with new refurbished & modified gates furnished by BG. Install new steel posts and strip and repaint gates. Gate style revised by customer to purchase vendor fabricated light gauge meta gates without spike, per Jodie Holt 10/09/19. | YES | 2019-11-26 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20 | 1
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | R3 |  | TRUE |  |  | 2019-03-26 | Schedule the work | 2020-01-31 | 2020-02-21 |  |  |  | 8/5/20, DL: This Project is COMPLETE…….3/25/20, DL: The material is here and we are 95% complete with the work. We will complete the work when we return from the campus closure…………1/31/20 O-DHN: Emailed Status Report to customer…….1/30/20,DL: The pump is now on site but we are still waiting for the fittings. In the mean time, our plumber is putting everything together and is working on the installation. Once the fittings arrive, we will make the connections and the system should be good to go………….1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: The pump is scheduled to arrive on or before 1/31/20. We will schedule the work once we have the pump and material on site…..11/26/19, DL; Emailed Natalie and Sherice the quote for the vacuum pump. We will order the material and schedule the work once we have approval and the pump on site……11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: I sent the vendor a 2nd email requesting an update on the proposal. I also included Natalie on the email so she is aware of where we stand with the proposal……10/30/19, DL: We had a followup meeting with the vendor last week. The vendor is now working on a pump that will best meet our needs……….10/16/19, DL; We are working with a vendor on a quote for a new lab vacuum pump. We are hoping to have a quote in the next week or two…..9/16/19, DL; Estimate was provided to customer last week. If the project is approved, we will work on the plans and permits. Once approved, we will schedule the work…… |  | Enrico Baez | Old SOW Revised SOWInstall exhaust hood, electical receptacle, vacuum pump, vac lines and valves (six valves total) and hood location. | YES | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21 | 1
19P000384 |  | 19P000384 | FALSE | ENROLLMENT SERVICES | SL5 PATCH HOLES IN WALL AND PAINT |  | STUDENT SERV | 2234 | COMPLETE | LaRae Lundgren | Emily Engelschall, Sean Cason | CHRISTINE SMITH |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
19P000370 |  | 19P000370 | FALSE | ENROLLMENT SERVICES | SL5 PATCH AND PAINT CAMPUS TOURS |  | STUDENT SERV | 1137 | COMPLETE | LaRae Lundgren | Emily Engelschall, Sean Cason | ELIZABETH TATUM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000517 |  | 19P000517 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | COMPLETE | LaRae Lundgren | Emily Engelschall, Sean Cason | DANIELLE GARCIA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-03-07 | Verify scope and schedule work | 2019-12-02 | 2020-12-20 |  |  |  | 1/19/21, DL: This project is complete…………..8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced, We will schedule the work when we return from the campus closure…………11/11/19, DL: I will work on scheduling this project… | 2019-06-17 | Enrico Baez | 6/17/19 E. Baez Conducted site visit with Sean. Will need carpenters to mount TV and electricians to add outlet to North wall. Data not needed. Might need painters depending on how carpenters install TV mount. | YES | 2021-01-19 | FALL 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000467 |  | 19P000467 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 WATKINS HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | WATKINS | 2101 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2019-01-22 | Finish project. | 2019-10-01 | 2019-12-20 |  |  |  | 1/14/20, DL: This project is 100% Complete……..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Project is 99.9% complete. We should be complete with the work by this Friday. Furniture is scheduled to be install this Friday morning……..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL; The project is still on schedule to be completed on 12/12/19…………….10/30/19, DL: This Project is on Schedule to be completed on or before 12/17/19….10/16/19, DL; This project is in progress with a completion date of 12/15/19…….10/1/19, DL; We will schedule the work. Our portion of the project will be completed mid December……….9/16/19, DL; We will work on the plans soon. This project will be complete by 12/21/19….. 09/03/19 O-ANS: Updated Priority to #1 for Fall 2019 per Susan request. 9/3/19, We are scheduled to complete the work before winter break begins….. |  | Enrico Baez |  |  | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-22 | finish plans/submit application | 2020-01-10 | 2020-03-27 |  |  |  | 8/5/20, DL: This Project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer…..2/18/20, DL: We are making great progress and still on schedule to be complete before Spring Break begins. We pass drywall inspection on 2/18/20………..1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: Plans are approved. All items have been removed from the space. Abatement is schedule to take place within two weeks…..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were submitted for plan check review. Fire marshal stamped the plans, we are waiting on the final stamp from our building official. Once plans are approved we will order material and schedule the work……..10/30/19, DL: Gunter is working on plans. We are planning to complete the work before Spring Quarter begins. |  | Dan Lerman |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
20P000085 |  | 20P000085 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 FACILITES ANNEX B - PAINT OFFICE SPACE |  | CUST AND GRD | 0001 | COMPLETE | Susan Marshburn | Da Lan Dinh | SANDRA MARTINEZ |  | Paul Ditty |  | COMPLETED |  | FALSE |  |  | 2019-08-19 | [8 empty] | Paul Ditty |  |  | 2019-09-16 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000560 |  | 19P000560 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 UNIVERSITY VILLAGE BLDG B, RM 240B- KEYWATCHER INSTALLATION |  | UV BLDG B | 0240B | COMPLETE | Susan Marshburn | Da Lan Dinh | LESLIE ROSE |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-04-04 | waiting for material to arrive | 2019-08-01 | 2019-08-23 |  |  |  | 9/3/19, DL; This project is 100% complete. We still need to conduct training but the work is complete and training is scheduled…..8/15/19, DL; This Project is 90% Complete and will be complete by the end of the week. Please note. ITS still needs to connect the data lines. Our portion of the work is complete………8/1/19, DL; Plans are approved. Material is ordered. We will schedule the work when the material is on site…. |  | Dan Lerman |  |  | 2019-09-03 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
19P000411 |  | 19P000411 | FALSE | GRAD DIV | SL5 PAINT, CARPET AND BLINDS |  | UNIV OFC BLD | 150 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-14 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
19P000572 |  | 19P000572 | FALSE | GRAD DIV | SL5 PATCH, PAINT, AND CARPET UOB 152 |  | UNIV OFC BLD | 152 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-11 | Awaiting installation of carpet | [5 empty] | 06/28/19 O-ANS: Paint phase complete and awaiting carpet change. |  |  |  |  | 2019-11-26 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000399 |  | 19P000399 | FALSE | GRAD DIV | SL5 NEW CARPET + WALL PAINT |  | UNIV OFC BLD | 100 | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-06 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
18P000274 |  | 18P000274 | FALSE | GSOE | SL5 SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 |  | EDUC CLINIC |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES | BRANDON BARBOSA | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-18 |  | 2018-05-01 | 2019-01-31 |  |  |  | 2/14/19, DL; This project is Complete………….2/1/19, DL; This project is 99.9% Complete. We still need to conduct Final inspection with Building inspector……1/15/19, DL; The door and automatic opener is scheduled to be installed on 1/22/19……..12/14/18, DL; This project is 95% complete. The contract for the door and ADA operator was awarded today. We will schedule the work shortly after the new year…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Conducted site visit with Gilbert. We need to have a meeting to determin if this work is part of the SLA…… DL, 6/16/18; We still need direction, SLA or Recharge?.......DL, 7/11/18; This Project will require Plans and Permits. We will start on the Plans next Week. We will also issue work orders for work we will complete with in house staff. The Concrete work and Entry Door will need to be contracted out. Target Complete date is 10/1/18……..DL, 7/25/18; Work orders are produced. Planing to walk the project with Chris, Steve B and Robert C. thisw week or next week. We will submit plans to Bob Williams for the contracted work next week……DL, 8/8/18; Completed site visit with Robert C. Steve B, Steve T. and Chris; the Plumbers are complete. The carpenters and electricians will work on their items over the next three weeks. The Plans will be ready to submit on 8/9/18. Once plans are approved, we will proceed to go out to bid for the Concrete and the ADA operator. Target complete date is 9/21/18…….DL, 8/22/18; Plans were apprroved, Concrete Contract is being executed. Still working on Door and ADA operator……..DL, 9/6/18; NTP for Concrete will be issued on Monday. I will schedule the work. I need to follow up on the door order and the ADA operator…….DL, 9/19/18; Concrete walkway scheduled to start on 9/20/18. The new door and Frame will arrieve in 3-5 weeks. We will schedule the install when the new door and frame are on site…….DL, 10/4/18; Concrete work is complete. Still need handrail, signage, door and ADA operator. Target date is Early November….DL, 11/7/18; Project is 95% complete. Contract is being processed to install the new Door, Door Fram and ADA operator. Goal is to have the work complete befor the winter break…… |  | Enrico Baez |  | YES | 2019-02-14 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000313 |  | 18P000313 | FALSE | GSOE | SL5 SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-15 | [6 empty] | 18W011689 Work order was cancelled because it has the same scope and is a duplicate………DL, 6/16/18; Contract is being awarded this week. Weill are scheduled to have this work completed by fiscal closing……DL, 7/25/18; This Project is 100% Complete…..9/13: Zee - Customer noted paint peeling; updated to status to back in progress for work to be addressed.......DL, 9/19/18; The contractor is on site repairing the walls and painting. The work should be complete this week.......dl, 10/4/18; tHIS PROJECT IS 100% Complete..... |  | Paul Ditty |  | N/A | 2018-10-22 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000628 |  | 19P000628 | FALSE | GSOE | SL5 SPROUL HALL, RM 2129- PATCH/PAINT FACULTY OFFICE |  | SPROUL | 2129 | COMPLETE | Thomas Smith | Sally Tavizon | SALLY TAVIZON |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-05-15 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-08-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000031 |  | 20P000031 | FALSE | GSOE | SL5 SPROUL HALL 1124B- PATCH/PAINT OFFICE |  | SPROUL | 1124B | COMPLETE | Thomas Smith | Sally Tavizon | MARICELA ARCINIEGA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-07-22 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000054 |  | 19P000054 | FALSE | GSOE | SL5 PATCH & PAINT OFFICE |  | SPROUL | 2131 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-26 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000237 |  | 19P000237 | FALSE | GSOE | SL5 PATCH AND PAINT OFFICE - SPROUL 1206 |  | SPROUL | 1206 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-09-05 | work is in progress | 2019-03-01 | 2019-04-18 |  |  |  | 4/15/19, DL; Project is 100% Complete….. 2/1/19, DL; This project will start on 3.1.19. We will need to abate ACM before we can start. Jess will isuue the 14- day notification to the AQMD. Once we have confirmation, we will schedule the work…….. | 2018-10-05 | Enrico Baez | Carpenters: Removes sliding chalk boards in 1206 and 1206 and fill in with wall. Remove patched in panels on left of chalk board in 1206. Patch where " do not enter" signs were removed. Electricians: Disconnect power to two "do not enter" signs above doors. Abatement: Remove approx 300 sq.ft. of ACM VCT Flooring: replace flooring with either VCT of vinyl plank. Painters: Patch and paint, at least one wall accent wall. | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000077 |  | 20P000077 | FALSE | GSOE | SL5 SPROUL HALL 1223 - PATCH AND PAINT |  | SPROUL | 1223 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-08-06 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-11-25 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000217 |  | 19P000217 | FALSE | GSOE | SL5 PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 |  | SPROUL | 1359 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-27 | Work has started | 2019-03-01 | 2019-05-23 |  |  |  | 4/15/19, DL; This project is 100% Complete…..2/1/19, DL; This proect will start on 3/1/18 and should be complete by 4/1/19…… | 2018-09-18 | Enrico Baez | Scope of work Carpentry Remove 20 feet of built-in wood cabinets and counter top. Install TV mount on South wall. Remove and replace white board on North wall. Abatement Abate approximately 200 square feet of 9â€ x 9â€ VCT tile and base cove Flooring Install carpet similar to what is in room 1357 Replace base cove. Walls Patch and paint walls. Electrical Install duplex outlet for TV Replace fluorescent lamps with LED lamps TV Install data point and Internet connection to support video conferencing. Custodial Vacuum dust from ceiling tiles. 9/18/18 EB-Conducted site visit. Request to remove cabinet, abate VCT, install carpet, mount TV. Electrical and date lines needed. Install white board. Replace fluorescent tube with LED. 9/13/18 EB-emailed Karen Naples to schedule site visit. | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000229 |  | 19P000229 | FALSE | GSOE | SL5 RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR |  | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-08-29 | [6 empty] | 6/15/19, DL; This Project is 100% Complete….. |  | Enrico Baez |  | YES | 2019-06-15 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000471 |  | 18P000471 | FALSE | ITS | SL5 WCH INSTALL SECURITY FENCE |  | CHUNG HALL | 134 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  |  | 5 | FALSE |  |  | 2018-06-12 | [6 empty] | DL, 7/4/18; Walked this project with Angel, This request is to install security fence with Sliding gate and welded webs to increase security. Space is vacant and ready to schedule work. Need to walk with Corey to see if this is a project they can do or sub out to De ANza fence......DL 7/25/18; Still need to walk project with Corey. Dl, 8/10/18; Site walk complete, we are waiting on estimates. WE will try and schedule the work with in the next 30- days....DL, 8/22/18; Work is scheduled for August 27th. Still need to order hardware.....DL, 9/6/18; The fence is installed and Angel is very Happy, but I need to check the project to verify we are good to go....DL, 9/19/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | 2018-09-19 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000474 |  | 18P000474 | FALSE | ITS | SL5 MS&E ELECTRICAL MODIFICATIONS FOR ITS |  | MAT SCI ENGR | 119 | COMPLETE | Danna Gianforte | Shelley Gupta | MICHAEL CAPRIOTTI |  | Robert Corey |  |  | 1 | FALSE |  |  | 2018-06-13 | Complete the balance of electric | 2019-04-01 | 2019-04-12 |  |  |  | 3/28/19, DL; This Project is 100% Complete…….2/28/19, DL; Work is scheduled with Darrenn F. for Spring Break…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. |  | Enrico Baez |  | YES | 2019-03-28 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000373 |  | 19P000373 | FALSE | ITS | SL5 URGENT-INSTALL RECPTACLE, ENCLOSURE & MOUNT BRACKET |  | GERMPLASM | 881 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-07 | [6 empty] | <div>mount a bracket to the Network Pole at AgOps. This will include mounting a bracket, an enclosure and a 20 Amp electrical receptacle.</div> |  | Enrico Baez |  |  | 2019-02-26 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000382 |  | 18P000382 | FALSE | ITS | SL5 ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | PHYLLIS FRANCO |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 2018-04-05 |  | 2018-12-14 |  |  |  |  | 1/15/19, DL, This project is Complete……12/14/18, DL; This project is scheduled to be complete shortly after the winter break…….This project was scoped previously with the IR Team. We may need plans or a permit because we are installing a Dutch door…..DL, 7/11/18; Need to produce work orders and schedule the work….. DL, 7/25/18; Still need to produce work orders and schedule the work. Target date is 10/1/18 | 2018-07-06 | Enrico Baez |  | YES | 2019-01-15 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000381 |  | 18P000381 | FALSE | ITS | SL5 ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 |  | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 3 | 4 | FALSE |  |  | 2018-04-05 |  | 2018-12-14 |  |  |  |  | 1/15/19, DL; This project is complete. Note, Duffy only wanted the dutch door completed……..12/14/18, DL; This project is in progress and should be complete shortly after the new year……`DL, 7/11/18; Need to walk the project and schedule the work…… | 2018-07-06 | Enrico Baez |  | YES | 2019-01-15 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000021 |  | 19P000021 | FALSE | ITS | SL5 ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS |  | ITS CENTER |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-07-12 | Install Power and data | 2019-03-28 | 2019-04-26 |  |  |  | 4/15/19, DL; This project is 100% Complete…… 3/28/19, DL; Monitors are done. Nee to finish the install of data and power…….12/14/18, DL; Still need to review scope….. |  | Enrico Baez | 1. Telecom Building - Conference Space Electricians Power Requirements: • Install double duplex(quad outlet), AC power on East wall at display location (4S Box) low profile • All electrical junction boxes, J-boxes, and conduit can be surface mounted. J-boxes to be located behind TV. Data Requirements: • Install single gang junction box on East wall behind display with Panduit running to specified location (for telecom network drops) o Single gang, low profile junction box o (conduit to be lead through masonry wall above T Bar ceiling in adjacent room. O (Low profile boxes for data ports) • Single gang box, mounted behind TV location, for data. • Note: Non-traditional wall – masonry Carpenters • Install mounting bracket for display on East wall • note: Non-traditional wall – masonry Painters • Paint junction boxes and conduit to match wall. 2. Intellicenter - First Floor Common Area Carpenters • Install mounting brackets on East Wall for each display (2 total) • (ITS to note the top of the bracket) 3. SOM-E - 1675A DataCenter Electricians Power Requirements: • Install double duplex(quad outlet), AC power on North wall at each display location (2 total) o Surface mounted J Boxes and Conduit Data Requirements: • Install single gang junction box on North wall at each display location with conduit/panduit running to specified location (for telecom network drops) (2 total) o (Wire mold boxes for both power and data) (2inch boxes – low profile boxes for data ports) o Data conduit to stub up and terminate through T-bar ceiling panels. • All conduit and J-boxes to run upward through T-bar ceiling Carpenter • Install mounting bracket for each display on North wall (2 total) • Install backing for mounts in adjacent data room in shelving. Painters • Patch and paint installation area as needed Location Notes • Non-traditional wall – drywall over carpentry 4. ITS Building - 174 Electricians • Install double duplex, AC power on East wall at each display location (2 total) • Install single gang junction box on East wall at each display location with conduit above ceiling (for telecom network drops) (2 total) o Terminate Data conduit above T-bar ceilings Carpenters: • Install mounting bracket (marked on the wall) for each display on East wall (2 total) Location Notes: • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 5. ITS Building - Main Lobby Electricians • Install double duplex, AC power on South wall at display location • Install single gang junction box on South wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on South wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 6. ITS Building – AVC / CIO’s Office (ITS 147) Electricians • Install double duplex, AC power on North wall at display location • Install single gang junction box on North wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on North wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 7. ITS Building Room 138 Electricians • Install double duplex, AC power on East wall at display location • Install single gang junction box on East wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on East wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) | YES | 2019-04-15 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | C&C CARPORT | 161 | COMPLETE | Danna Gianforte | Shelley Gupta | SHELLEY GUPTA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-01-07 | Waiting for bid for customer. | 2020-01-20 | 2020-03-31 |  |  |  | 8/5/20, DL: This Project is complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have the contract, we will schedule the work……………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Project was approved by Shelley. We will work on the contract. Once we have the notice to proceed from contracts, we will order the material and schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Sent Shelley another follow-up email today and she has not verified if she would like to move forward with the project………10/30/19, DL: Sent Shelley the updated quote last week and she has not responded. I sent Shelley a followup email today asking her to let me know if she would like to proceed with the work……..10/16/19, DL; Had a meeting with Shelley, we modified the scope of work and software for the project. We are now revising the quote with our vendor. We should have an updated quote within the next two weeks. If Shelley approves the work and scope, we will proceed….10/1/19, DL; I have a meeting with Shelley this afternoon to review proposal. If she approves the project we will submit plans for a building permit……8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was cancelled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; We have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28/19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21 | 1
18P000432 |  | 18P000432 | FALSE | PB&A | SL5 BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 |  | BANNOCK A | H0101 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-05-04 | [8 empty] | Paul Ditty |  | N/A | 2018-07-13 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000373 |  | 18P000373 | FALSE | PB&A | SL5 POLICE BLDG PAINTING IN DISPATCH AREA |  | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | KELLY DUNCAN |  | Paul Ditty |  |  | 8 | FALSE |  |  | 2018-04-02 | [8 empty] | Paul Ditty |  | N/A | 2018-07-14 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000222 |  | 19P000222 | FALSE | PB&A | SL5 PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | TBD | RICHARD GEIGER |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-02 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-01 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000247 |  | 19P000247 | FALSE | PB&A | SL5 LOTHIAN FIRST FLOOR COMMON AREA FLOORING |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | TBD | RICHARD GEIGER |  | Jess Hernandez |  |  |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez |  |  | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000282 |  | 18P000282 | FALSE | PB&A | SL5 EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP00003080 |  | POLICE BLDG |  | COMPLETE | Gerry Bomotti | TBD | LISA MARTIN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-25 | [6 empty] | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work…..DL, 5/9/18; We need to submit plans……DL, 7/11/18; This still needs to be scheduled......DL, 8/8/18; Enrico Confirmed this project is 100% Complete.... |  | Enrico Baez |  | YES | 2018-08-10 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000390 |  | 18P000390 | FALSE | PB&A | SL5 UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD |  | UNIVERSITY VILLAGE BUILDING B | 0240B | COMPLETE | Gerry Bomotti | TBD | LESLIE ROSE |  | Paul Ditty |  |  | 1 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000209 |  | 19P000209 | FALSE | PB&A | SL5 OLD EH&S SITE- FS ANNEX A REMODEL |  | ENV HLTHSFTY | 100 | COMPLETE | Gerry Bomotti | TBD | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 2018-08-24 | Schedule the work | 2019-05-16 | 2019-06-28 |  |  |  | 7/1/19, DL; This project is 100% Complte….6/17/19, DL; This project is almost complete. Target complete date is 6/26………….5/31/19, DL; This project is in progress. Our goal is to have the projected completed by June 28th……. 5/15/19, DL; We are schedule to start the demo tomorrow. Project timeline is 3-4 weeks….3/28/19, DL; Gunther is working on plans……3/18/19, DL; Conducted site visit with Chris, Hassan and Francis last week. We will work on plans and permits…….9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen |  | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
18P000324 |  | 18P000324 | FALSE | PB&A | SL5 HINDERAKER PATCH AND PAINT |  | HINDERAKER | 4118 | COMPLETE | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-02-26 | [8 empty] | Paul Ditty |  | N/A | 2018-07-11 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000459 |  | 18P000459 | FALSE | PB&A | SL5 BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 |  | THE BARN |  | COMPLETE | Gerry Bomotti | TBD | GUSTAVO PLASCENCIA |  | Dan Lerman |  |  | 6 | FALSE |  |  | 2018-05-31 | [8 empty] | Enrico Baez |  | YES | 2018-09-21 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
20P000158 |  | 20P000158 | FALSE | PB&A | SL5 FS ADMIN OFFICE - TOUCH-UP PAINT AROUND BUILDING |  | CORP B |  | COMPLETE | Gerry Bomotti | TBD | DA LAN DINH |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-10-03 | [8 empty] | Paul Ditty |  |  | 2019-10-10 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000401 |  | 19P000401 | FALSE | PB&A | SL5 PATCH HOLES IN WALL AND PAINT |  | HINDERAKER | 4148E | COMPLETE | Gerry Bomotti | TBD | SHANNON TIMMONS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
19P000414 |  | 19P000414 | FALSE | PB&A | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | Seth Morrison |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-12-17 | pending material delivery | 2019-10-16 | 2019-11-27 |  |  |  | 8/5/20, DL: This Project is Complete………….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: We have the motor on site, we are working on the permit for the crane. Once we have the crane lift permit, we will schedule the install…………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: We are working on the new motor platform. It is our goal to install the new motor in late January. Once the motor is installed, we will be able to identify if additional work is needed…….11/19/19 DH: Emailed Status Report to customer…..11/15/19, DL: Material has not arrived……..10/30/19, DL: The new exhaust fan is ordered with a 2- 4 lead time. Once the exhaust fan arrives, we will schedule the install……….10/16/19, DL; We are in the process of the work. At this current time, we are not modifying the building to where permits may not be required…….10/1/19, DL; This is in the queue for plans, we will start the plans in the next 3-4 weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2018 | 2021-03-16 | FY 20-21
20P000083 |  | 20P000083 | FALSE | PB&A | SL5 STUDENT SERVICES - INSTALL 8 CUBICLES - CP00003537 | Installation of BKM Cubicles with electric and Data | STUDENT SERV | 3rd Floor | COMPLETE | Gerry Bomotti | TBD | SHARYL MURDOCK |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-06-25 | We are on schedule | 2019-12-16 | 2020-01-01 |  |  |  | 1/14/20, DL: This project is 100% Complete………..11/18/19 DH: Emailed Status Report to customer…..10/30/19, DL: The plans were approved and we are scheduled to do the work in December…………10/16/19, DL: Plans were submitted this week…….. |  | Enrico Baez | Scope completed by Dan Lerman | YES | 2020-01-14 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000008 |  | 20P000008 | FALSE | PB&A | SL5 EHS 1133 - PATCH / PAINT AND FIX HOLES IN WALLS |  | ENV HLTHSFTY | 1133 | COMPLETE | Gerry Bomotti | TBD | CESAR PLA |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-07-08 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-07 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000236 |  | 19P000236 | FALSE | PB&A | SL5 EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION |  | ABER INVER | A0100 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 10 |  | FALSE |  |  | 2018-09-04 | [6 empty] | JP 04/04/19 2/8/19 This project is complete. JP Estimated completion end of February | 2018-11-01 | Enrico Baez |  | YES | 2019-04-04 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000192 |  | 19P000192 | FALSE | PB&A | SL5 MAIL-PAINTING |  | MAIL |  | COMPLETE | Gerry Bomotti | TBD | PRISCILLA MARTIN |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000015 |  | 19P000015 | FALSE | PB&A | SL5 POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING |  | POLICE TRAILER | 1 | COMPLETE | Gerry Bomotti | TBD | KELLY DUNCAN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-07-10 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000363 |  | 18P000363 | FALSE | PB&A | SL5 PAINT STOREHOUSE ADMINISTRATIVE OFFICE |  | CORP B |  | COMPLETE | Gerry Bomotti | TBD | ERICA HENDERSON |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-03-26 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000227 |  | 19P000227 | FALSE | PB&A | SL5 DINING STORAGE ROOM CONVERSION |  | BANNOCK J | J0100 | COMPLETE | Gerry Bomotti | TBD | DARCI LOMBARD |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 05/16/19 O-ANS: Project complete per John P as of 05/16/19. 04/04/19, JP: This project has been placed on hold per Housing Edwin. 2/8/19: JP storage room slated to be completed simultaneously with break room as water supply connections will be done together with break room. Completion date for both is approximately three weeks. |  | Enrico Baez |  | YES | 2019-05-16 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000665 |  | 19P000665 | FALSE | PB&A | SL5 PD&C TELECOMM BLDG - MINOR RENOVATION | Existing telephone-communications building on University Ave requires repairs and renovation in preparation for new use as fire safety offices. | TELEPHONE |  | COMPLETE | Gerry Bomotti | TBD | Carmen Long | Melissa Garrety | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-03 | tape, mud, prime&Paint | 2019-08-14 | 2020-01-17 |  |  |  | 2/19/20; This project is complete. We still need to paint the door black but this was not part of the original scope. The paint shop will paint the door in the next two weeks………… 1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL:. This project is 99.9% complete with a few minor punch list items…..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: This project is on track to finish before the new year with a punch items to be addressed after the new year. IT services still needs to install data and phone. Landscape services is working on the landscape but the landscape was not part of the original scope. Sharyl in is the process of coordinating keys, alarm code and setting up the delivery of the furniture for her team. Overall, we are all in good shape.…….11/19/19 DH: Emailed Status Report to customer…..11/11/19,DL: This project is still on schedule to be complete before the new year……….10/30/19, DL: This project is in progress and on track to be complete before the new year…………….10/16/19, DL: Drain, waste, vent and concrete is complete. We started framing this week. We will start rough electrical and rough plumbing next week……..9/3/19, DL; Abatement was complete this weekend. Trades are scheduled and we are on track for 11/15/19 completion date…..8/15/19, DL Plans were approved this week. Abatement is still needed and the 14- day notification to AQMD is complete. We are on track to complete the work by mid November……. |  | Enrico Baez |  |  | 2020-02-19 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000425 |  | 19P000425 | FALSE | PB&A | SL5 PAINT VIDEO PRODUCTION SUITE & HANG ITEMS |  | HINDERAKER | 1159A | COMPLETE | Gerry Bomotti | TBD | LISA CUSICK |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-20 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
19P000224 |  | 19P000224 | FALSE | PB&A | SL5 PAINT EXTERIOR RAMP AT HUB MODULAR |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | TBD | MIKE CLEMONS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000308 |  | 19P000308 | FALSE | PB&A | SL5 ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK |  | ABER INVER |  | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | JP 04/04/19 Project Complete DL 10/4/18; Jess currently has this project scheduled for Winter break. |  | Enrico Baez |  |  | 2019-04-04 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000307 |  | 19P000307 | FALSE | PB&A | SL5 LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK |  | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | John Peraino |  | 5 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… | 2018-10-03 | Enrico Baez |  | N/A | 2019-01-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000232 |  | 19P000232 | FALSE | PB&A | SL5 BANNOCKBURN J-104 BREAK ROOM UPGRADE | Scheduled work with trades anticipated 60% completion by Jun 15th. | BANNOCK I | I0105 | COMPLETE | Gerry Bomotti | TBD | RICHARD GEIGER |  | John Peraino |  | 6 |  | FALSE |  |  | 2018-09-04 | [6 empty] | 6/14/19, JP; Project on schedule to be completed June 30th 2019. 05/16/19 O-ANS: Project to be 60% completed by June 15th per John P. 04/04/19 JP: This project placed on hold per Housing/Edwin. Finishing up the cabinet and lighting order, will be submitting to purchasing today. Scheduling installation of VCT flooring pending per Tony’s Flooring, will have date this week. New ceiling tiles have been delivered and will be installed when relocating of electrical components are complete. Awaiting confirmation and clearance from Jess to proceed with cutting into walls to facilitate electrical modifications |  | Enrico Baez |  | YES | 2019-06-14 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000022 |  | 19P000022 | FALSE | PB&A | SL5 HUB--PAINT TWO WALL AS SCOTTY'S HUB |  | HUB | 101 | COMPLETE | Gerry Bomotti | TBD | DIANE THOMAS |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-07-12 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-09-17 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000215 |  | 19P000215 | FALSE | PB&A | SL5 SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 |  | HUB | 346 | COMPLETE | Gerry Bomotti | TBD | GUSTAVO PLASCENCIA |  | John Peraino |  | 9 |  | FALSE |  |  | 2018-08-24 | 12/12/18 DND Project complete |  | 2018-12-12 |  |  |  | 12/12/18 DND Project complete; electrical was installed and all kitchen equipment was hooked up as requested. |  | Enrico Baez |  | YES | 2018-12-12 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000114 |  | 20P000114 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER DOOR, BASEBOARD, AND BRACKETS |  | PENTLAND A |  | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 2019-09-05 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
19P000535 |  | 19P000535 | FALSE | PB&A | SL5 BANNOCKBURN H108-MOVE POWER AND DATA FOR FOURWINDS TV | Install TV Mount and additional electrical | BANNOCK H | H0108 | COMPLETE | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-03-14 | [7 empty] | 2019-07-08 | Enrico Baez | Install TV Mount and additional electrical | YES | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
19P000599 |  | 19P000599 | FALSE | PB&A | SL5 FAC ADMINISTRATION- PAINT OFFICE WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 2019-05-09 | [6 empty] | 07/22/19 O-ANS: Work Complete per Paul Ditty. |  |  |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000037 |  | 20P000037 | FALSE | PB&A | SL5 FAC ADMINISTRATION -PAINT WALLS |  | CORP B | 126 | COMPLETE | Gerry Bomotti | TBD | HELMA AVILA |  | Paul Ditty |  | R1 |  | FALSE |  |  | 2019-07-23 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-24 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000127 |  | 20P000127 | FALSE | PB&A | SL5 FALKIRK APARTMENTS EMERGENCY EGRESS |  | FALKIRK 1 | 10E | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R1 |  | FALSE |  |  | 2019-09-13 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
19P000687 |  | 19P000687 | FALSE | PB&A | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | COMPLETE | Gerry Bomotti | TBD | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-06-26 | plan check review | [5 empty] | 8/5/20, DL This Project is Complete……………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Contracts is processing the contract. Once the contract is complete, we will schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Plans were approved. I sent Brendan an email 11/11/19 requesting an FAU # as this is Recharge work. Once we have the FAU #, we will work on the contract agreement with the contractor………10/30/19, DL; Sent Lezlie and email asking if she has an update on the resubmitted plans on 10/30/19………..10/16/19, DL; The plans were resubmitted for plan check review this week. We are hopeful the plans will be approved this week. Once approved we will work on contract and scheduling the work…10/7/19 LB: This is a test. The timestamp will be reset when the test is done. 10/1/19, DL: We are working on plan check review. We should have approved plans in the next two weeks…..8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | Provide estimate to install key card access control |  | 2020-08-05 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21 | 1
20P000115 |  | 20P000115 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 1 - BALCONY COSMETIC REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R2 |  | FALSE |  |  | 2019-09-05 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000205 |  | 20P000205 | FALSE | PB&A | SL5 THE PLAZA 12 & 14 - EMERGENCY DECK REPAIR | Deck repair | THE PLAZA | A0012 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R2 |  | FALSE |  |  | 2019-11-01 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Jan 2020. |  | John Peraino |  |  | 2020-01-01 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000116 |  | 20P000116 | FALSE | PB&A | SL5 FALKIRK APARTMENTS 5 - BALCONY EMERGENCY REPAIRS |  | FALKIRK 1 | 2nd Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R3 |  | FALSE |  |  | 2019-09-05 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000223 |  | 20P000223 | FALSE | PB&A | SL5 PENTLAND HILLS - SHOWER PAN REPLACEMENTS | Shower Pan replacement | PENTLAND A | A238, B245, B325, C215, F325 | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | BOB BRUMBAUGH | John Peraino |  | R3 |  | FALSE |  |  | 2019-11-15 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by Sep 2019. |  | John Peraino |  |  | 2019-09-01 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000243 |  | 20P000243 | FALSE | PB&A | SL5 ALUMNI CENTER - HYDRATION STATION INSTALL | Install hydration station | ALUM VISITOR | FIRST FLOOR | COMPLETE | Gerry Bomotti | TBD | LESLIE ANN GERRETSE |  | John Peraino |  | R4 |  | FALSE |  |  | 2019-11-16 | [6 empty] | 07/20/20 O-ANS: Complete per John Peraino by June 2020. |  | John Peraino |  |  | 2020-06-01 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000117 |  | 20P000117 | FALSE | PB&A | SL5 PENTLAND HILLS A-H - LATTICE REBUILD |  | PENTLAND A | A-H | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R4 |  | FALSE |  |  | 2019-09-05 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
20P000118 |  | 20P000118 | FALSE | PB&A | SL5 FALKIRK 1, 2, & 12 - FIRST FLOOR PATIO FENCING |  | FALKIRK 1 | 1st Floor | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD |  | John Peraino |  | R5 |  | FALSE |  |  | 2019-09-05 | [8 empty] | John Peraino |  |  | 2019-09-18 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20 | 1
19P000386 |  | 19P000386 | FALSE | PROVOST/EVC | SL5 ROOM CHANGES |  | STUDENT SERV | 3106A | COMPLETE | Thomas Smith | Luisa Levario | STEPHANIE ARCINIEGA |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-20 | Schedule the work.. | 2019-03-11 | 2019-04-01 |  |  |  | 4/15/19, DL; This Project is 100% Complete…… 2/28/19, DL; Conducted site visit. We need to schedule the work in the next 2-3 weeks This is for room 3109 C&D ……….. | 2019-02-07 | Enrico Baez |  | YES | 2019-04-15 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
19P000683 |  | 19P000683 | FALSE | PROVOST/EVC | SL5 PATHC/PAINTING REPAIR |  | HUM & SOC SC | 1103A | COMPLETE | Thomas Smith | Luisa Levario | JILL CANTONWINE |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-06-25 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-03 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000473 |  | 19P000473 | FALSE | PROVOST/EVC | SL5 HINDERAKER VPDUE SUITE MOVES/REDESIGN HINDERAKER 1100 |  | HINDERAKER | 1100 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | TORRI MCGARITY | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-29 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-28 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000434 |  | 19P000434 | FALSE | PROVOST/EVC | SL5 UE IT SHANSHAN LIAO OFFICE NEEDS | Please patch 50 plus holes on the wall and repaint that wall in Skye hall 136 due to the BKM removing the furniture attached to the wall. Please call Anita Ortiz if you have any questions at x2-5229. Shanshan's extension x7753 has not been moved to her new location yet. | SKYE HALL | 136 | COMPLETE | Thomas Smith | Luisa Levario | THERESA WAGNER | SHANSHAN | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-07 | [6 empty] | 07/20/19 O-ANS: Work Complete per Paul Ditty. |  | Paul Ditty |  |  | 2019-07-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000017 |  | 19P000017 | FALSE | SoB | SL5 ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD |  | ANDERSON 2 (S) | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | DL, 9/6/18; Monitors are installed. Need to schedule the electrical. Target date is 9/21/18…… |  | Enrico Baez |  | YES | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000482 |  | 18P000482 | FALSE | SoB | SL5 CARD ACCESS SYSTEM ANDERSON SOUTH |  | ANDERSON 2 (S) |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-26 | [6 empty] | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with JasonDL, 7/11/18; Need to check in with Jason on status for his side of the project.....DL, 7/25/18; JAson's team is ready to install but the Anderson IT department does not have the necesary software. We will start the work when the software is up and running...... 8/12/18 DND FAMIS Status noted completion on 8/2/18. |  | Dan Lerman |  | YES | 2018-08-02 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000053 |  | 19P000053 | FALSE | SoB | SL5 ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S |  | ANDERSON 2 (S) |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-04-13 | [6 empty] | DL 8/22/18; two out of four monitors are complete. WE still need to install powree at four locations…….DL, 9/6/18; Still need Electrical installed……. Planing to have complete by 9/21/18……. This is aqctually 4- monitors in four locations. We should ensure each monitor is treated as an indidual project.......DL, 9/19/18; All monitors are installed. Robert will schedule the electricans this week or early next week...DL, 10/4/18; This project is 100% Complete..... |  | Enrico Baez |  | YES | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000351 |  | 18P000351 | FALSE | SoB | SL5 REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 1 (N) | 21 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2018-03-19 |  | 2019-07-08 |  |  |  |  | 8/1/19, DL; This project is 100% Complete……7/15/19, DL; Work has started and should be complete on 7/16/19…….. 4/4/19 O-ANS: Moved to Queue to Start to complete during Summer 2019. DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week……8/8/18. The trades are ready to go after they finish current projects…..DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18………. DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date……..9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space……Note. The space is usable and everything works….. |  | Enrico Baez |  | YES | 2019-08-01 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000018 |  | 19P000018 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER |  | ANDERSON 2 (S) | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000428 |  | 18P000428 | FALSE | SoB | SL5 OLMSTED RM 2352 PATCH/PAINT |  | OLMSTED | 2352 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-05-02 | [8 empty] | Paul Ditty |  | N/A | 2018-08-17 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000463 |  | 18P000463 | FALSE | SoB | SL5 ANDERSON HALL PATCH/PAINT-102C |  | ANDERSON 2 (S) | 0102C | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-06-04 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
19P000030 |  | 19P000030 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT |  | OLMSTED | 2301 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000451 |  | 19P000451 | FALSE | SOB | SL5 ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 |  | ANDERSON 1 (N) | 58 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-15 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  |  |  |  | 2019-02-01 | SPRING 2019 | FS | FALSE | 2019 | 2021-03-16
19P000521 |  | 19P000521 | FALSE | SoB | SL5 ANDERSON HALL NO, RM 138- PATCH/PAINT |  | ANDERSON 1 (N) | 138 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-03-08 | [6 empty] | 07/09/19 O-ANS: Project complete per Paul Ditty as of 07/09/19. |  |  |  |  | 2019-07-09 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000151 |  | 20P000151 | FALSE | SoB | SL5 ANDERSON HALL NO 113 - PATCH/PAINT HOLES |  | ANDERSON 1 (N) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-09-30 | [6 empty] | 03/02/20 O-ANS: Project complete per Paul Ditty as of 02/07/20. |  | Paul Ditty |  |  | 2020-02-07 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000280 |  | 19P000280 | FALSE | SoB | SL5 ANDERSON HALL PAINT ONLY |  | ANDERSON 2 (S) | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-13 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty |  | N/A | 2019-02-01 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
20P000193 |  | 20P000193 | FALSE | SoB | SL5 ANDERSON HALL SO - PATCH/PAINT |  | ANDERSON 2 (S) | 0001A | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-10-23 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 01/02/20 |  | Paul Ditty |  |  | 2020-01-02 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000353 |  | 19P000353 | FALSE | SoB | SL5 OLMSTED PATCH/PAINT-2348 |  | OLMSTED | 2340 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-19 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
18P000261 |  | 18P000261 | FALSE | SOM | SL5 WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR |  | WEBBER | 1143 | COMPLETE | Deborah Deas | Deborah Trujillo | LOURDES ESCAMILLA |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 7/11/18; Work orders are produced. Need to assign the work order and order material. I will review with Steve and verify target complete date….DL, 7/25/18; Still need to walk the project with Steve……DL, 8/10/18; Material is ordered. We will complete the install when the materila arrives.....DL, 8/22/18; Material should be on site with in 4- weeks. Will schedule install when material is on site. Target date is 9/20/18.......DL, 9/6/18; This Project is 100% Complete...... |  | Dan Lerman |  | YES | 2018-09-10 | Spring 2018 | FS | FALSE | 2017 | 2021-03-16
18W006022 |  | 18W006022 | FALSE | SOM | INSTALL CURTAIN ROD IN RESEARCH SPACE |  | SOM RSCH | 336 | COMPLETE | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-10-27 | [6 empty] | DL, 5/24/18; Need to review scope with Enrico….DL, 7/11/18; Enrico produced work orders for sheet metal shop. This is a singel trade project. |  | Enrico Baez |  | YES | 2018-07-11 | Spring 2018 | FS | FALSE | 2017 | 2021-03-16
20P000152 |  | 20P000152 | FALSE | SOM | SL5 SOME 2669 - PATCH & PAINT |  | SOM EDUC | 2669 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | TRACEY TRETTIN | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-30 | [8 empty] | Paul Ditty |  |  | 2019-10-03 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000408 |  | 19P000408 | FALSE | SOM | SL5 PATCH & PAINT - 2605 SOM ED |  | SOM EDUC | 2605 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | 2019-02-08 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
19P000660 |  | 19P000660 | FALSE | SOM | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SL5 SOME RB, RM 330- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 9/30/20, DL: This Project is Complete………..8/5/20, DL: Dan to follow-up with customer…………..03/05/20 O-ANS: Removed room 330 per client request. Only updates to 107 & 111. |  | Enrico Baez | TBD | NO | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000009 |  | 19P000009 | FALSE | SOM | SL5 SOME -- PAINT, SPACKLE AND CLEANING NEEDED |  | SOM EDUC | 2615 | COMPLETE | Deborah Deas | Deborah Trujillo | BEVERLEY HERBERT |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-02 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000354 |  | 19P000354 | FALSE | SOM | SL5 WEBBER 2130A-PAINT CHERI'S NEW OFFICE |  | WEBBER | 2130A | COMPLETE | Deborah Deas | Deborah Trujillo | DOMINIC SALAZAR |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-19 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  | Paul Ditty |  | N/A | 2019-05-07 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
19P000661 |  | 19P000661 | FALSE | SOM | SL5 SOM RB, CR0600- FY 19/20 PROJECT- PATCH & PAINT |  | SOM EDUC | CR0600 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000248 |  | 19P000248 | FALSE | SOM | SL5 SOME--SOME INSTALL ELECTRICAL 1682 |  | SOM EDUC | 1682 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  |  |  | 2 |  | FALSE |  |  | 2018-09-10 |  | 2019-01-28 | 2019-02-14 |  |  |  | 2/14/19, DL; This project is complete…… |  | Enrico Baez |  | YES | 2019-02-14 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000054 |  | 20P000054 | FALSE | SOM | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOMED-SOME G0600, G0621 & 1682B- ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-31 | [6 empty] | 9/30/20, DL: This Project is Complete…………..8/5/20, DL, Dan to follow-up with customer………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "Remove status Hold / Update project detail to include information on 1682B -ADD ELECTRICAL, PAINT/PATCH, AND RELOCATE WHITE BOARD." |  | Enrico Baez | Room G0600 Install Power behind and below the TV, install one TV Bracket, install one cut-in back box below the TV for data(data cabling by ITS), Paint the entire East wall to match existing. Room G0621 Insatll three(3) new double duplex receptacles and three(3) data back boxes only(no data cabling) in room G0621. Install SS tubing for Co2 from room G0621 to room G0623. Include Valves at both ends of P.O.C., Install one uni-strut siesmic cylinder support at the south wall. Steve Burleson has walked the site and has knowledge of the SOW. Loading Dock Install Pole & chains at Loading dock. |  | 2020-09-30 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
20P000060 |  | 20P000060 | FALSE | SOM | SL5 WEBBER HALL 1274- PATCH & PAINT OFFICE |  | WEBBER | 1274 | COMPLETE | Deborah Deas | Deborah Trujillo | TARA BARTHOL |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-08-05 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-28 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000245 |  | 19P000245 | FALSE | SOM | SL5 ADA COMPLIANT - AUTOMATIC DOOR ENTRY |  | SOM RSCH |  | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-09-07 | Plans are approved | 2019-06-03 | 2019-06-28 |  |  |  | 7/1/19, DL; This project is 100% Complete…..6/171/19, DL; Material is on site. Project should be complete in the next two weeks……..5/31/19, DL; Contracts is working on the contract. We should have a notice to proceed in the next two weeks. The project will be complete with in 30- from when we receive the notice to proceed……5/15/19, DL;, Plans were approved. I am working with PD&C on the contract. Once the contract is complete, we will schedule the work……3/28/19, DL; Plans were submitted and pending review and approval….. | 2018-10-29 | Enrico Baez | Install ADA complian auto door operator, push plates and electrified panic hardware. Auto operator will be outsourced through Capitol door. FS lock shop will perform acess control wiring. Electrical shop to provide a dedicated circuit for the auto door operator. | YES | 2019-07-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 19-20
19P000666 |  | 19P000666 | FALSE | SOM | SL5 WEBBER, ROOM 1237- PATCH AND PAINT | TBD - SOM RM 107, 111 & 330- PROJECT: NEW PI, EQUIPMENT INSTALL | WEBBER | 1237 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2019-06-17 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-11 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000032 |  | 19P000032 | FALSE | SOM | SL5 Reconfigure recepetion desk to fit two FTEs. |  | SOM EDUC | 2608 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 5 | 1 | FALSE |  |  | 2018-07-17 | finish project | 2019-03-04 | 2019-03-15 |  |  |  | 5/1/19, DL; This project is 100% Complete….. 3/28/19, DL; Cabinet workl is complete. We need to finish the carpet and final laminate material…….2/28/19, DL; Conducted site visit with Chad. We will complete the work in the next two weeks…….2/1/19, DL; I Walked this project this week. We will try and schedule the work in the next 30- days…….12/14/18, DL, Still need to conduct site visit and schedule the work… | 2018-10-17 | Enrico Baez | Remove lower the left lower cabinet to create an additional work station. SOW: Remove/demo cabinet, install a new corbel patch floor with similar carpet and install 4" rubber base as needed. | YES | 2019-05-01 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
20P000051 |  | 20P000051 | FALSE | SOM | SL5 SOMED 2611 - PATCH & PAINT |  | SOM EDUC | 2611 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2019-07-31 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-10-01 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000485 |  | 18P000485 | FALSE | SOM | SL5 SOMR PATCHING AND PAINTING |  | SOM RSCH |  | COMPLETE | Deborah Deas | Deborah Trujillo | DANA ABOU ABBAS |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000012 |  | 19P000012 | FALSE | SOM | SL5 SOME--PATCH & PAINT |  | SOM EDUC | 2638 | COMPLETE | Deborah Deas | Deborah Trujillo | MARISELA MARTINEZ |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-07-06 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000014 |  | 19P000014 | FALSE | SOM | SL5 SOME - PATCH & PAINT |  | SOM EDUC | 2609 | COMPLETE | Deborah Deas | Deborah Trujillo | MARISELA MARTINEZ |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-07-09 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000470 |  | 18P000470 | FALSE | SPP | SL5 Student Check-in Lobby |  | CHASS INT S | 4133 Corridor | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-11 | [6 empty] | DL, 6/16/18; I walked this project with Luis and Mark this week. They want this work completed by July 9th. Paint, data, electrical, chair rail and signage is requested. I need to review project with Paul and Robert C. DL, 7/11/18; Robert C. Ordered material and we will complete the install first part of next week We will scheudle the paint after Robert is Complete. Target Complete Date is 7/2018......DL, 7/25/18; WE have the electrical materila, plans were submitted. Once plans are reviewed and approved, we will proceed with the work. Target date is two weeks after plans are approved......DL, 8/10/18; Eletrical is complete. Pending paint. Paint will be scheduled in the near future. DL, 8/22/18; This project will be Complet on Saturday.....DL, 9/6/18. I miossed the chair rail request on this project. I will order the chair rail in the near future. The chair rail is the only item needed to complete this project. Aprroximately 20 lineal feet......DL, 9/19/18; Chair rail is ordered. We will schedule the install when the material arrives....... |  | Dan Lerman |  | YES | 2018-08-23 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
19P000458 |  | 19P000458 | FALSE | SPP | SL5 CHASS INTS-BUILD PERM DRYWALL DIVIDER OR APPROVE BKM AIRWALL |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ | LUISA LEVARIO | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-19 | Order material & start the work | 2019-03-27 | 2019-06-15 |  |  |  | 6/17/19, DL; This project is 100% Complete…..5/31/19, DL; This prject is making good progress and we are scheduled to be complete on or before June 19th…….5/15/19, DL; This project is in progress and schedule for complete near 6/15/19…. 5/1/19; We started this project last week and we are planning to be complete in 4 - 6 Weeks….4/15/19, DL; Material is ordered, we will start the demolition this week. We hope to be complete in 8-weeks or less……2/28/19, DL; Plans are complete and were submitted to for review and approval from campus building official and fire marshal. Once plans are approved, we will shcedule the work….. | 2019-01-28 | Enrico Baez | 1/28/19 EB See Shared drive for additional information. Carpenters • Construct new approx. 4” metal stud walls with 5/8” drywall over 48” x 96”x1/2” sound insulating panels. See plans for location. • Remove T-bar drop ceiling under soffit in location of partitioned space, frame with metal stud, attach 5/8” drywall over sound insulating panels. • Extend soffit face flush to meet with new walls, frame under soffit, cover with sound insulating panels and 5/8” drywall. • Install 1 ADA compliant half lite, 36" wide, 3/4" thick, paint grade, entry door and trim in each space. • Finish and texture walls to match existing. • Install base cove to match. Electrical • No additional electrical outlets to be added. • Install switched recessed can lights, similar to existing, 4 in each new space. Fire Protection and Suppression • Relocate existing fire sprinklers to be compliant in each newly created space. • Relocate and add smoke detectors in each newly created space. Painters • Prime, Patch and Paint walls, ceiling, doors and trim. Lock Shop • Furnish and install 2 each, ADA compliant handle sets, match existing hardware HVAC • Relocate HVAC duct work in new extended soffit. Split 10” center duct or two new spaces with 6” Wye and registers. • Provide return air in ceiling. • No thermostat or zone controls will be installed. Customer informed. | YES | 2019-06-17 | Spring 2019 | FS | FALSE | 2019 | 2021-03-16
19P000255 |  | 19P000255 | FALSE | SPP | SL5 CHASS INT N REMODEL - 4022 PATCH AND PAINT |  | CHASS INT N | 4022 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000263 |  | 19P000263 | FALSE | SPP | SL5 CHASS NORTH REMODEL - 4009 PATCH AND PAINT |  | CHASS INT N | 4009 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-09-11 | [8 empty] | Paul Ditty |  |  | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000256 |  | 19P000256 | FALSE | SPP | SL5 CHASS REMODEL - 4146 PATCH AND PAINT |  | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  |  |  | 3 |  | TRUE |  |  | 2018-09-10 | [7 empty] | 2018-10-09 | Enrico Baez |  | YES | 2019-01-04 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
18P000478 |  | 18P000478 | FALSE | UNDERGRAD ED | SL5 CARPET, PAINT, & AIR HANDLING MODIFICATION |  | HINDERAKER | 1120H | COMPLETE |  |  | TRACEY SCHOLTEMEYER |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-16 | [6 empty] | DL, 7/4/18; This project is scoped; Need to remove Switch gear storage rack components, remove electrical conduits, plywood backer board from walls, paint and floor covering. We will schedule this work to be complete by Fall 2018 academic year....DL, 7/11/18; Need to produce work orders and schedule the work. Target Complete date is 9/14/18... Space is vacant....DL, 8/10/18; Work has started and we are on schedule...... DL, 8/22/18; Demo is almost complete. This target date is 9/21/18......9/19/18; All trades are complete. New carpet to be installed on 9/21/18. .....DL, 9/19/18; This project is scheduled to be complete this week....... |  | Dan Lerman |  | YES | 2018-10-22 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18W015691 |  | 18W015691 | FALSE | VC-RED | SL5 BOYCE CONNECT WASHER AND DRYER |  | BOYCE | 6444 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  |  |  |  | 1 | FALSE |  |  | 2018-05-30 | [6 empty] | DL, 7/11/18; This project is in progress and almost complete. Target complete date is 7/20/18….. |  | Dan Lerman |  | YES | 2018-07-11 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18W013973 |  | 18W013973 | FALSE | VC-RED | SL5 BSL3 FACILITY- ASSEMBLE AND INSTALL |  | UNIVERSITY OFFICE BUILDING |  | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2018-04-19 | [6 empty] | FAMIS NOTES 8/22: Plumbing filter system was installed and ice maker installed. Request for microscope and incubator moved into containment by customer. Complete 9/24/18 |  | Enrico Baez |  | YES | 2018-09-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000442 |  | 18P000442 | FALSE | VC-RED | SL5 FAWCETT LAB 203 PATCH & PAINT |  | FAWCETT LAB | 203 | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 3 | FALSE |  |  | 2018-05-18 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000379 |  | 18P000379 | FALSE | VC-RED | SL5 UOB PATCH AND PAINT |  | UNIVERSITY OFFICE BUILDING |  | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-05 | [8 empty] | Paul Ditty |  | N/A | 2018-08-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
20P000150 |  | 20P000150 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 207 |  | UNIV OFC BLD | 207 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-25 | [8 empty] | Paul Ditty |  |  | 2019-12-11 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
20P000149 |  | 20P000149 | FALSE | VC-RED | SL5 UNIV OFFICE BLD 242 - PATCH HOLES AND PAINT ROOM 242 |  | UNIV OFC BLD | 242 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | - |  | FALSE |  |  | 2019-09-25 | [8 empty] | Paul Ditty |  |  | 2019-09-30 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000044 |  | 19P000044 | FALSE | VC-RED | SL5 PATCH AND PAINT |  | SPIETH | 345 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000230 |  | 20P000230 | FALSE | VC-RED | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | Install Ceilings, Widen Door & Extend Utilities | BOURNS | B116C & B116D | COMPLETE | Rodolfo Torres | Laura Manor | KRASSIMIR BOZHILOV | LAURA MANOR | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-11-18 | finish plans for building permit | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: This project is in progress and 50% complete. We should be complete with in the next 4-6 weeks…………...8/5/20, DL: We will submit plans in the next week………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We will start working on the plans and apply for a building permit in the next 2-3 weeks. | 2020-01-23 | Enrico Baez | Install new T-bar ceilings, lighting/switches, verify electrical service/disconnect. Relocate the existing eye washer, widen the exiting door opening and *reverse swing(*if approved by F.M). Install one customer furnished transformer. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
20P000026 |  | 20P000026 | FALSE | VC-RED | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | Install T-bar ceiling, Provide HVAC and Fire sprinklers drops. Install new 2x4 LED light fixtures | LIFE SCIENCE | Basement Level | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-07-19 | Work on Plans and permits. | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: The plans were submitted two weeks ago. We should receive the plan check review comments in the near future…………….8/5/20, DL: This Project will exceed $50,000. Monty A. will inform customer this is a project that will need to be managerd through PD&C……………3/25/20, DL: We will work on plans when we return back from the campus closure. | 2020-01-31 | Enrico Baez | Install T-bar ceiling with wipable(coated) ceiling tile. Provide HVAC and new Fire sprinklers drops to new ceiling. Install new 2x4 LED light fixtures. Verify Fire alarm systems work. | YES | 2021-01-19 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
19P000439 |  | 19P000439 | FALSE | VC-RED | SL5 SPIETH PATCH AND PAINT ROOM 335 |  | SPIETH | 335 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-08 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2019 | 2021-03-16
19P000553 |  | 19P000553 | FALSE | VC-RED | SL5 SPIETH HALL PATCH AND PAINT |  | SPIETH | 341 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-01 | [6 empty] | 07/26/19 O-ANS: Project Complete per Paul Ditty. |  |  |  |  | 2019-07-26 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000495 |  | 19P000495 | FALSE | VC-RED | SL5 UOB RM 209- PATCH & PAINT |  | UNIV OFC BLD | 209 | COMPLETE | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-02-08 | [6 empty] | 07/30/19 O-ANS: Project closed per Paul Ditty. 07/30/19 D-MMN: Moved furniture and filled holes. Taped base and fixtures. Primed and painted one half of office. Pulled tape replaced plates and moved furniture to other side. Removed plates taped base and fixtures. Primed and painted other half. Used spray texture on patch under window. Pulled masking. Replaced plates. Moved furniture back. Vacuumed carpet during and after total process. |  |  |  |  | 2019-07-30 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19W003050 |  | 19W003050 | FALSE | VC-RED | SL5 SPEITH HALL - PATCH & PAINT HOLE IN WALL |  | SPIETH | 0359A | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-10 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
20P000045 |  | 20P000045 | FALSE | VC-RED | SL5 MRB SOUND BOOTH |  | MRB | 2210 & 2204 | COMPLETE | Rodolfo Torres | Laura Manor | DAN LERMAN |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-30 | Inspection | 2019-10-01 | 2019-11-07 |  |  |  | 11/11/19, DL: This project is complete…….10/30/19, DL: This project is complete but we need to conduct the final inspection with the building official………..10/16/19, DL: The plans are approved and the work is complete. I need to field verify and schedule the inspection. |  | Enrico Baez | Contact PM for SOW. | NO | 2019-11-11 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000181 |  | 19P000181 | FALSE | VC-RED | SL5 PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS |  | UNIVERSITY OFFICE BUILDING | 249 | COMPLETE | Rodolfo Torres | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-14 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-19 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
21P000102 |  | 21P000102 | FALSE | VC-RED | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | AAALAC Certification updates to rooms 348, 352 & 363 | SPIETH | 348, 352 & 363 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS | YURIDIA REYNOSO | Paul Ditty |  | TBD |  | FALSE |  |  | 2020-10-29 | [6 empty] | 12/08/20 O-ANS: Customer Dierk Biggs confirmed via email that these room updates are complete. |  | Paul Ditty |  |  | 2020-12-08 | Winter 2021 | FS | FALSE | 2020 | 2021-03-16 | FY 20-21
18P000337 |  | 18P000337 | FALSE | VC-STU AFF | SL5 MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET |  | HEALTH SERV | 414 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-12 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18….Need to work on plans and permits….DL, 7/11/18; Gunther is working on plans. Target complete date is 9/14/18….DL, 7/25/18; Planning to submit plans for review next week. We will schedule the work once we have approved plans…….DL, 8/8/18; This is a structual wall and needs to be engineered. We are meeting with the Structual engineer on 8/9/18 to determine if project is possible.....DL, 8/22/18; Working on EDPA for Structual engineer; project timeline is late Fall. 9/19/18; The Agreement / Cointract for the structual engineer is processed for this project. We should have plans from the structual engineer to submitt to the Building Official and fire marshal with in 4- weeks......dl, 10/4/18; Plans are almost complete and we will submit them for review by the end of the week.....DL, 11/7/18; Plans are approved. WE are schedule to start this Project on Tuesday 11/13/18. Target complete date is by the end of the winter break..... |  | Enrico Baez |  | YES | 2018-12-14 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000215 |  | 18P000215 | FALSE | VC-STU AFF | SL5 STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA HAGGINS |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2017-12-08 | floor covering and electric door | 2019-02-19 | 2019-06-01 |  |  |  | 6/17/19, DL; This project is 100% complete. This project was the wall removal at the check in entrance…...5/31/19, DL; Contracts is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks4/15/19; All work is comleted except the floor covering and elcetronic card readers for the doors…..2/28/19, DL; This project has started and is on schedule…….2/14/19, DL; This project is scheduled to start on 2/19/19…………2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………1/15/19, DL, Material is ordered, material should arrive on site in the next 3- 5 weeks……12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 5/24/18; Need to review scope and site visti with Enrico. Plans and permits will be required for this project….DL, 7/11/18; Planning to walk work with Gloria and her team next week. Will be able to project complete date after site visit is conducted……DL; 7/25/18; We walked this project with the team. This will require plans and permits. We will schedule this work for Fall…………DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-45 Days…… |  | Enrico Baez |  | YES | 2019-06-17 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16
20P000337 |  | 20P000337 | FALSE | VC-STU AFF | SL5 HEATLH SERVICE 382 - NEED OFFICE PAINTED |  | HEALTH SERV | 382 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-23 | [6 empty] | 08/06/20 O-ANS: Complete per D-BFA on 02/11/20. |  | Paul Ditty |  |  | 2020-02-11 | Spring 2020 | FS | FALSE | 2020 | 2021-03-16 | FY 19-20
19P000380 |  | 19P000380 | FALSE | VC-STU AFF | SL5 PATCH AND PAITN- WALL PAINT IS PEELING |  | HEALTH SERV | 404 | COMPLETE | Brian Haynes | Cathy Eckman | SAMANTHA HARRIS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-19 | [6 empty] | 3/4/19 DND Complete per PD |  |  |  |  | 2019-03-04 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
20P000157 |  | 20P000157 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BUILDING - HOLES NEED PATCH AND PAINT |  | HEALTH SERV | 325 | COMPLETE | Brian Haynes | Cathy Eckman | CHRISTINA FARIA | WENDY ALEXIS | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-10-02 | [6 empty] | 02/19/20 O-ANS: Complete per Paul Ditty as of 01/31/20. |  | Paul Ditty |  |  | 2020-01-31 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000455 |  | 19P000455 | FALSE | VC-STU AFF | SL5 FILL AND PAINT OVER HOLES ON WALL |  | HEALTH SERV | 100 | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-17 | [6 empty] | 01/31/20 O-ANS: Complete per Paul Ditty as of 12/27/19 |  |  |  |  | 2019-12-27 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000405 |  | 19P000405 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED |  | HEALTH SERV | 0100D | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-11 | [6 empty] | 05/07/19 O-ANS: Complete per Paul Ditty as 05/07/19. |  |  |  |  | 2019-05-07 | SPRING 2019 | FS | FALSE | 2018 | 2021-03-16
18P000214 |  | 18P000214 | FALSE | VC-STU AFF | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Install Card readers | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  | 2 | 2 | FALSE |  |  | 2017-12-08 | Pending special order part | 2019-02-19 | 2020-09-01 |  |  |  | 1/19/21, DL: This project is 100% Complete…….9/30/20, DL: Vendor should have the balance of the material in the next 30- days…….8/5/20, DL: This project is complete except the card reader portion of the project…………6/17/20, DL: The floor covering was completed two weeks ago. The card reader portion of this project is 95% complete but additional parts were needed and they are on order. Once they arrive, we will schedule the installation and this project will be 100% Complete………1/15/20 Emailed Status Report to customer…..1/14/20, DL: We were recently approved to proceed with the work. I have reached out to the vendor for the doors and card access. We are still waiting to hear back from them so we can order the material and schedule the work. I communicated with Nicole on the floor covering replacement. Nicole needs to verify what areas we will replace as we were going to complete several offices and a hallway as part of the scope but this will displace many team members for at least a week. We will work on scheduling the work once Nicole gets back to me……..12/17/19 - O-DHN: Emailed Status Report to Customer……12/19/19, DL; We are working with our contractor to order the material and schedule the work. Once we have confirmation on the material, we will be able to schedule the work. It Is our goal to start this project in late January……11/26/19, DL: This project was taken off of on hold and we can now proceed. I contacted the contractor last week and I am awaiting their response on when they can schedule the work. I also left a message with them this morning………..7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once material arrives, we will schedule the installation.….5/31/19, DL; Contract is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is completed except the floor covering and electronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being prepped for paint. We have a pre-construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, material is ordered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct site visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez |  | YES | 2021-01-19 | Winter 2018 | FS | FALSE | 2017 | 2021-03-16 | FY 20-21
19P000037 |  | 19P000037 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BLDG--PATCH WORK AND PAINTING |  | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-07-17 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000483 |  | 19P000483 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BLDG, RM 408- NEED A FEW OFFICES PAINTED |  | HEALTH SERV | 404, 407, 412, 405 & 411 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2019-02-01 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-11-22 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000124 |  | 19P000124 | FALSE | VC-STU AFF | SL5 PAINT ROOMS 115 AND 116 |  | COSTO HALL | 125 | COMPLETE | Brian Haynes | Cathy Eckman | LINDA KELLEY |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-10-22 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000172 |  | 19P000172 | FALSE | VC-STU AFF | SL5 HEALTH SERV- PAINT RESTROOM IN LABORATORY |  | HEALTH SERV | 0113A | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty |  | N/A | 2018-11-08 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000564 |  | 19P000564 | FALSE | VC-UNIV ADV | SL5 HINDERAKER HALL- MULTIPLE ROOMS NEED CARPENTRY/PAINT SHOPS | 1156C (AVC Johnny Cruz) – Patch molly holes, touch-up paint. 1156A (Jules Bernstein) – Remove (2) black & white photos from wall. Patch molly holes, touch-up paint. 1156B – Install picture frame (UCR campus map) onto wall. Suite 1159 – Patch holes. Remove film reels. Paint one accent wall “UCR Blue”. 1159B (Christy Zwicke) - Patch molly holes, touch-up paint. | HINDERAKER | 1156 | COMPLETE | Peter Hayashida | Naysia Caldwell | Lisa Cusick | Christy Zwicke | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-04-08 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  |  |  |  | 2019-09-07 | Summer 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
19P000238 |  | 19P000238 | FALSE | VC-UNIV ADV | SL5 PATCH & PAINT HINDERAKER 1136 |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | 2019-01-11 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000326 |  | 19P000326 | FALSE | VC-UNIV ADV | SL5 HINDERAKER - PATCH & PAINT |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-08 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty |  | N/A | 2019-02-08 | Winter 2019 | FS | FALSE | 2018 | 2021-03-16
18P000281 |  | 18P000281 | FALSE | VC-UNIV ADV | SL5 ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS |  | ALUM VISITOR | 2202 | COMPLETE | Peter Hayashida | Naysia Caldwell | TRUDY COHEN |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-01-24 | execute the work | 2019-03-04 | 2019-03-15 |  |  |  | 3/28/19, DL; This Project is 100% Complete…..2/28/19, DL; This work is scheduled…….DL, 5/24/18; Need to verify scope of work with EnricoDL, 7/11/18; Still need to visit the site and schedule the work…..DL, 11/8/18; This project was transferred to John. The target date was 1/2/19….. |  | Enrico Baez |  | YES | 2019-03-28 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
3557 | 3557 |  | FALSE | CHASS | Campus Sculpture Installation | We will bring 5 sculptures to campus that will go in public places that have already been identified by Uma Ramasubramanian and Jacqueline Norman . Please construct 5 concrete plinths at various locations around campus. Locations are on the attachment. |  |  | Construction | Juliet McMullin | Cindy Williams | Emily Rankin |  | Tameesha Hayes | 3 |  |  | FALSE | 82000 |  | 2019-11-27 | Complete Construction | 2020-10-01 | 2021-03-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | Design | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 6950000 |  | 2019-03-04 | Construction | 2021-07-01 | 2023-05-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 19 |  |  | FALSE | 315000 |  | 2018-07-31 | Bidding | 2021-06-01 | 2021-08-01 | [10 empty] | PD&C | FALSE | 2018 | 2021-03-16
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 2020-09-22 | Bidding | 2021-07-01 | 2021-10-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-16
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Design | Gerry Bomotti | TBD |  |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Bidding | [12 empty] | PD&C | FALSE | 1900 | 2021-03-16
3524 | 3524 |  | FALSE | VC-STU AFF | Student Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | STUDENT SERV |  | Design | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE | 450000 |  | 2019-04-16 | BKM Lead Time 10 Weeks | 2021-06-01 | 2021-07-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3119 | 3119 |  | FALSE | CAP PROG | Plant Growth Environment Facility | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. |  |  | Furniture/Equipment | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 6 |  |  | FALSE | 27425000 |  | 2016-05-25 | Equipment and Furnishing | 2019-06-01 | 2021-02-26 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-16
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT |  | SCIENCE LABORATORIES 1 | 317 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 10 |  | FALSE |  |  | 2020-02-18 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-03-16
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LABORATORIES 1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 2020-02-19 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-03-16
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SUPPORT SERVICES BUILDING | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | Emily Engelschall, Sean Cason | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-22 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-03-16
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL BUILDING | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 2019-12-04 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | FALSE | 2019 | 2021-03-16
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES |  | UNIVERSITY OFFICE BUILDING | 200 | HOLD - FACILITIES SERVICES | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-02-07 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | FALSE | 2020 | 2021-03-16
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | In Bidding | Kathryn Uhrich | Jose Wudka | Mireya Botello Santoyo |  | Scott Donnell | 4 |  |  | FALSE | 32871.65 |  | 2020-07-14 | Construction | [12 empty] | PD&C | FALSE | 2020 | 2021-03-16
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Bidding | Kathryn Uhrich | Jose Wudka | Richard Zapien |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2020-05-08 | Award Contract | 2021-04-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-16
3550 | 3550 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Skye Hall HVAC Replacement | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | SKYE HALL |  | In Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 1177000 |  | 2019-09-05 | Award Contract | 2021-05-01 | 2021-08-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3590b | 3590b |  | FALSE | PB&A | DMFI(FY17-20) Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Bidding | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 2019-11-27 | Award Contract | 2021-04-05 | 2021-06-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | In Bidding | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 2019-03-04 | Award Contract | 2021-05-01 | 2021-09-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Bidding | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 2020-09-15 | Award Contract | 2021-04-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-16
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair/Replacement | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | In Bidding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 61918 |  | 2020-09-21 | Award Contract | [12 empty] | PD&C | FALSE | 2020 | 2021-03-16
3471 | 3471 |  | FALSE | VC-STU AFF | HUB Electrical Sub Meter Installation | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | In Bidding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 4 |  |  | FALSE | 200000 |  | 2018-08-20 | Award Contract | 2021-04-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2018 | 2021-03-16
2970c | 2970c |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Bidding (Phase 3) | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 2015-12-02 | Award Contract (Phase 3) | 2021-04-01 | 2021-06-01 | [10 empty] | PD&C | FALSE | 2015 | 2021-03-16
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | In Bidding (Re-bid) | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 3 |  |  | FALSE | 1340000 |  | 2019-05-15 | Award Contract | 2021-06-01 | 2021-09-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | John White |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete Construction | 2021-01-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-16
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Mihai Gavan | 9 |  |  | FALSE | 60430000 |  | 2017-06-01 | Complete Construction | 2019-11-01 | 2021-08-01 | [10 empty] | PD&C | FALSE | 2017 | 2021-03-16
2952 | 2952 |  | FALSE | CAP PROG | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jon Harvey |  | Gerald Caraig | 13 |  |  | FALSE | 23895000 |  | 2015-09-11 | Phase I Completion | 2019-01-02 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2015 | 2021-03-16
3438 | 3438 |  | FALSE | CAP PROG | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 15 |  |  | FALSE | 88500 |  | 2018-08-22 | City to determine schedule | 2020-07-01 | [11 empty] | PD&C | FALSE | 2018 | 2021-03-16
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Georgios Vidalakis |  | Scott Donnell | 7 |  |  | FALSE | 15000 |  | 2020-09-11 | Complete Construction | 2021-01-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-16
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Tracey Kahn, D. McWilliams |  | Scott Donnell | 12 |  |  | FALSE | 1575000 |  | 2018-01-08 | Complete Construction | 2021-02-01 | 2021-08-01 | [10 empty] | PD&C | FALSE | 2018 | 2021-03-16
3527 | 3527 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Central Utility Plant Fire Alarm | Replace aging and non-replaceable fire alarm system, and conduit. Conduit is damaged and only 10% of wiring is usable. ( fire alarm system and devices are failing and they are not supported by manufacture ) | CNTRL UTL PL |  | In Construction | Susan Marshburn | Da Lan Dinh | Ben Kochevar |  | Daneca Stevens | 4 |  |  | FALSE |  |  | 2019-05-08 | Complete Construction | 2021-03-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 6 |  |  | FALSE | 600000 |  | 2019-06-18 | Complete Construction | 2020-12-01 | 2021-05-28 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3195 | 3195 |  | FALSE | FAC-PLNG-DESIGN-CONST | North District | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 4146146.55 |  | 2016-10-26 | Complete Construction | 2019-07-01 | 2021-08-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-16
3515c | 3515c |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Construction | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 2019-03-08 | Complete Construction | 2020-12-01 | 2021-06-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3610 | 3610 |  | FALSE | PB&A | Hulen Place Homeless Medical Clinic | SOM is acquiring additional space for a medical clinic to assist with the homeless population. |  |  | In Construction | Gerry Bomotti | TBD | Diana Armenta |  | Daneca Stevens | 5 |  |  | FALSE |  |  | 2020-10-06 | Complete Construction | 2021-03-01 | 2021-03-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-16
3501 | 3501 |  | FALSE | PB&A | DMFI(FY17-19) Watkins 1000 Lecture Hall Reno | Renovation of Watkins 1000 lecture hall, to include lighting, HVAC, flooring, paint, and seating upgrades. This requests appears as projects Q-T on the approved 2017-2019 DMFI Program list. | WATKINS |  | In Construction | Gerry Bomotti | TBD | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 750000 |  | 2019-03-04 | Complete Construction | 2020-07-01 | 2021-03-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3533 | 3533 |  | FALSE | PB&A | Solar Rooftop Initiative | New solar PV installation that will optimize the mix of high quality, high output and most reliable solar PV installation. ~Task One will be to hire a consultant to draft a Basis of Design and compose specifications to maximize the use of available funding including reviews for roof structural integrity, electrical systems, safety / fall protection and estimated cost of construction. Locations to be considered; Hinderaker, Student Services, SRC South. ~Task Two will be to provide Design Development Documents with a refreshed cost estimate. ~Task Three will be to develop Construction Documents and construct the system. | MULTIPLE BUILDINGS |  | In Construction | Gerry Bomotti | TBD | Richard Geiger |  | John Franklin | 9 |  |  | FALSE | 2165000 |  | 2019-06-03 | Complete Construction | 2020-10-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3286 | 3286 |  | FALSE | PB&A | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 10 |  |  | FALSE | 3375000 |  | 2017-03-29 | Complete Construction | 2021-02-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2017 | 2021-03-16
3597 | 3597 |  | FALSE | PB&A | Plaza F Roof Replacement | Plaza building F roof is well past its service life and is experiencing multiple leaks into the apartment spaces below. This scope of work is to replace the roof in total and repair damages observed to the apartments below as a result of roof leaks. REQUESTING JOHN FRANKLIN AS THE PROJECT MANAGER. |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 18 |  |  | FALSE | 250000 |  | 2020-06-17 | Complete Construction | 2021-02-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-16
3490 | 3490 |  | FALSE | PB&A | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | Parking Lot 13 |  | In Construction | Gerry Bomotti | TBD | Irma Henderson |  | D.Hecht/J.Franklin | 25 |  |  | FALSE | 31844000 |  | 2018-12-06 | Complete Construction | 2020-02-01 | 2021-05-01 | [10 empty] | PD&C | FALSE | 2018 | 2021-03-16
9062 | 9062 |  | FALSE | PB&A | DM(FY20) Life Sci Sewer line |  |  |  | In Construction | Gerry Bomotti | TBD |  |  | Daneca Stevens | 99 |  |  | FALSE | 116000 |  | 2020-09-15 | Complete Construction | 2021-03-01 | 2021-03-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-16
3603 | 3603 |  | FALSE | SOM | Orbach Libr SOM CSSS AV Equipment | AV for CSSS project - 954044 / re: Fernando Cortez. Please refer to MSRIV in the line reference field for the draw down. |  |  | In Construction | Deborah Deas | Deborah Trujillo | Deborah Trujillo |  | Fernando Canon | 1 |  |  | FALSE | 1652000 |  | 2020-07-27 | Complete Construction | 2020-12-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-16
3622 | 3622 |  | FALSE | ATHLETICS | Baseball Outfield Wall Repairs | Contractor to replace damaged panels and baseboards on outfield fence at Riverside Sports Complex. This is to be done with pressure treated wood. Metal rail at top to be reattached and secured. Entire wall to be painted to specific UCR Athletics colors attached. Damaged boards on scoreboard catwalk and camera scaffolding to be replaced. |  |  | In Design | Tamica Smith Jones | Joe Erbland | Eugene Hutchinson |  | Tameesha Hayes | 3 |  |  | FALSE | 49500 |  | 2021-02-10 | Permitting | [12 empty] | PD&C | FALSE | 2021 | 2021-03-16
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 3182452.32 |  | 2016-12-16 | Bidding | 2021-05-01 | 2021-11-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-16
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Design | Kathryn Uhrich | Jose Wudka | MaryLou Polek |  | Scott Donnell | 1 |  |  | FALSE | 2500 |  | 2019-10-04 | Construction by USDA | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | Jose Wudka | Wendi Tapia |  | Tameesha Hayes | 3 |  |  | FALSE |  |  | 2020-06-19 | Waiting for equipment from overseas | [12 empty] | PD&C | FALSE | 2020 | 2021-03-16
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 432510 |  | 2016-02-25 | Bidding | 2021-03-01 | 2021-04-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-16
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | Katie Sanchez |  | Gerald Caraig | 20 |  |  | FALSE | 2600000 |  | 2016-05-19 | Funding & Approval | [12 empty] | PD&C | FALSE | 2016 | 2021-03-16
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 2020-09-23 | Bidding | 2021-06-01 | 2021-09-01 | [10 empty] | PD&C | FALSE | 2020 | 2021-03-16
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Design (Phase 2) | Kathryn Uhrich | Jose Wudka | Sabrina Schuster, D. McWilliams |  | Scott Donnell | 8 |  |  | FALSE |  |  | 2016-12-06 | RPU plan review/design (Phase 2) | 2021-08-01 | 2021-10-01 | [10 empty] | PD&C | FALSE | 2016 | 2021-03-16
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Design (Phase 4) | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 2015-12-02 | Complete Design (Phase 4) | [12 empty] | PD&C | FALSE | 2015 | 2021-03-16
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Funding | Christopher Lynch | Todd Ambriz | Margaret Souder |  | Scott Donnell | 2 |  |  | FALSE | 700000 |  | 2018-04-04 | Secure Funding | [12 empty] | PD&C | FALSE | 2018 | 2021-03-16
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | In Funding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 600000 |  | 2019-09-05 | Procure Funding | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Funding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 9 |  |  | FALSE | 500000 |  | 2019-09-05 | Procure Funding | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | In Funding | Gerry Bomotti | Sharyl Murdock | Gerald Caraig |  | Daneca Stevens | 2 |  |  | FALSE | 50000 |  | 2019-07-30 | Secure Funding | 2021-06-01 | 2021-07-01 | [10 empty] | PD&C | FALSE | 2019 | 2021-03-16
3104 | 3104 |  | FALSE | PALM DESERT GRAD CTR | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Funding | Tamara Hedges | Zelda Glenn | Zelda Glenn |  | Scott Donnell | 1 |  |  | FALSE | 22000 |  | 2016-05-12 | Approval & Funding | [12 empty] | PD&C | FALSE | 2016 | 2021-03-16
3581 | 3581 |  | FALSE | SOM | SOMR Interior Egress Doors | All egress doors - Floors 1, 2, and 3 - need to be replaced with compliant structures. Please inspect, evaluate and provide quote. |  |  | In Funding | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 2020-03-04 | Procure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-03-16
3617 | 3617 |  | FALSE | BCOE | WCH 108 Server Rm HVAC Upgrade | Winston Chung 108. Upgrade the HVAC system to provide cooling as needed for the server room. |  |  | In Pre-programming | Christopher Lynch | Todd Ambriz | Michael Ambriz |  | Tameesha Hayes | 3 |  |  | FALSE |  |  | 2021-01-22 | Design | [12 empty] | PD&C | FALSE | 2021 | 2021-03-16
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 2019-03-08 | Complete Report-Arc Flash | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | Michelle Baniqued |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 2019-03-04 | DB Competition | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Programming | Gerry Bomotti | TBD | Richard Geiger |  | Daneca Stevens | 22 |  |  | FALSE |  |  | 2016-10-10 | Design | [12 empty] | PD&C | FALSE | 2016 | 2021-03-16
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Study | [12 empty] | PD&C | FALSE | 2018 | 2021-03-16
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis (RE Proj) | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 2019-02-14 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 2018-10-31 | CEQA | [12 empty] | PD&C | FALSE | 2018 | 2021-03-16
20P000253 |  | 20P000253 | FALSE | BCOE | SL5 BOURNS HALL LAB B156 - EXHAUST SYSTEM | EXHAUST SYSTEM | MARLAN & ROSEMARY BOURNS HALL | B0156 | IN PROGRESS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 2019-12-11 | Demolish cabinets and schedule paint and flooring | 2021-03-01 | 2021-05-07 |  |  |  | 3/15/21, DL: The new dedicated electrical outlet is complete. We are also in the process of ordering the exhasut vents for the printer…………..2/16/21, DL: Plans were submitted 2- weeks ago. We received the plans back last week with corrections needed. We will resubmit the plans back to the building official by the end of the week….1/19/21, DL: We will start working on the plans for this project in the next two weeks. We will start this project once the permit is approved…… |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16
20P000370 |  | 20P000370 | FALSE | CHASS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | SPACE RENOVATION PROJECT | GORDON S. WATKINS HALL | 1311 | IN PROGRESS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 2020-02-19 | 14 day notification to AQMD for Asbestos Abatement | 2021-03-19 | 2021-07-02 |  |  |  | 3/1/21, DL: Plans were approved. We now need to send our 14- day notice to the AQMD and schedule the demolition……..2/16/21, DL: Plans were submitted with building permit last week. We are now in the plan check review process………1/19/21, DL: We will start working on the plans for this project in the next three weeks. We should have plans to submit for plan check review in the next 5- weeks……….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
21P000009 |  | 21P000009 | FALSE | CNAS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | GLOVEBOX SYSTEM | CHEMICAL SCIENCES |  | IN PROGRESS | Kathryn Uhrich | Jose Wudka | NATASHA GONZALES |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 2020-07-08 | We will start the demolition early next week. | 2021-03-08 | 2021-04-23 |  |  |  | 3/15/21, DL: We will demolish the cabinets this week. We will also schedule the paint and floor replacement. The venting for the glove box and snorkel should be ordered this week………3/1/21, DL: The plans were approved last week. We will try and schedule demo this week or early next week……..2/16/21, DL: We submitted plans for building permit but corrrections are needed. We contacted the glove box manufacture for follow-up questions and we are waiting to hear back from them. Once we have confirmation on the needed information, we will resubmit the plans back to the building official……….1/19/21, DL: we will submit plans this week or earlier next ……………. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
19P000485 |  | 19P000485 | FALSE | CNAS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | HOMER D. CHAPMAN HALL | 9 | IN PROGRESS | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-29 | Connect and install air flow monitor |  | 2021-03-12 |  |  |  | 3/15/21,DL: Bill S. is still working on obtaining the air flow monitor. Once the air flow monitor arrives, we will complete the installation and Bill will be able to have the fume hood certified by a 3rd party vendor…………3/1/21, DL: We need to install the fire extinguisher and air monitor. I sent Bill S. an email asking him if he ordered the air monitor as we do not have one. I also contact EH&S and made them aware that we will be commisioning the fume hood in the very near future…..2/16/21, DL: Plumbing is complete. We will now start the exhasut vent, electrical and then seismically anchor the fume hood…………2/1/21, DL: We have had a delay with the plumbing and it is our goal to be complete on or before 3/1/21…………1/10/21, DL: This project is almost complete. This project will be complete in the next 30- days…………9/30/20, DL: Fume Hood demolition and abatement will be completed on 10/2/20. Fume hood install should be coplete in mid Novemeber……8/5/20, DL: We will submit plans this week. Once plans are approved, we will schedule the work……………Work orders are produced. We need to work on plans and permits once we return. | 2020-02-10 | Enrico Baez | Disconnect, cap and safe off the existing utility services. Provide the necessary abatement services to properly remove the fume hood from the site and deliver to the campus surplus yard. Install one new department furnished fume hood. Abatement Services: Provide the necessary abatement services to perform all utilities disconnections and floor repair. Floorcovering: Patch and or repair as necessary to match or provide a close match. Install rubber base. Access Control: Survey and adjust the entry door closer to increase latch pull to allow the door to closer completely. Patching and painting: Patch and paint wall at the old fume hood location. Mechanical: Disconnect metal duct, cap/safe off, reconnect/reconfigure new duct to accommodate the new fume hood. Electrical: Provide electrical disconnections and safe off. Reconnect/reconfigure power to the new fume hood. Plumbing: Disconnect Air, Gas, Vacuum, Cold water, and Drain, cap and safe off and reconnect/reconfigure service to the new fume hood. Resource Management: Properly remove the fume hood from the site and deliver to the campus surplus yard. | YES |  | Spring 2020 | FS | FALSE | 2019 | 2021-03-16
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install electrical utilities for new equipment | PHYSICS BUILDING | 1132 | IN PROGRESS | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-03-19 | Install final electrical, countertop and Sink |  | 2021-03-26 |  |  |  | 3/15/21, DL: This project was supposed be be complete but we still have a plumbing drain assembly that is back ordered. We will connect the plumbing once the material arrives…………2/16/21, DL: New sink and faucet arrived, we will now schedule the install of the countertop and sink…………..1/19/21, DL: This project is in progress and will be complete with in 30- days………..9/30/20, DL: Plans were submitted for Plan Check review last week and we should have an update on the plan check review process soon………..8/5/20, DL: Need to meet with Kirk to verify electrical load. Once confirmed, we will work on plans for a permit. | 2019-10-15 | Enrico Baez | Install utilities for new equipment | YES |  | Summer 2019 | FS | FALSE | 2019 | 2021-03-16
20P000144 |  | 20P000144 | FALSE | CNAS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A | ALFRED M. BOYCE HALL | 3432, 3432A, 3446, 3446A | IN PROGRESS | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH | CHERYL GERRY | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-09-26 | final paint, floor covering and final cabinets |  | 2021-04-02 |  |  |  | 2/16/21, DL: Project Is on schedule. Paint is 90% complete. Once paint is complete, we will schedule the floor repairs and final deep clean……… 2/1/21, DL: We are making good progress and are target date is still 3/14/21………….1/19/20, DL: This project is in progress and will be complete in the next 30- days………….9/30/20, DL: We have started a few items but we are waiting on Matt U. and the PI to remove their items so we can have access to the space. Once the space is cleared out, we will proceed with the work…………8/5/20, DL: We will start the work in the next 4-6 weeks. | 2020-02-18 | Enrico Baez | Boyce 3432, 3446, 3436 and 3436A . Patch and paint 3432, 3432A, 3436, 3436A, 3446, 3446A. Reface/replace water damaged cabinets near sink (3446). Install GCFI outlets near sink (replace existing) (3446). Install panel cover for electrical panel box. Replace many burnt out bulbs in ceiling lamps. Replace broken chemical plexi-glass on bench shelves. | YES |  | Winter 2020 | FS | FALSE | 2019 | 2021-03-16
20P000003 |  | 20P000003 | FALSE | GRAD DIV | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | ADD POWER/DATA, PATCH/PAINT | UNIVERSITY OFFICE BUILDING |  | IN PROGRESS | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS | CHERYL GERRY | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-07-02 | schedule inspection by the building inspector | 2021-02-17 | 2021-04-20 |  |  |  | 3/15/21, DL: The demo, electrical and rough plumbing is complete. We will schedule inspection this week. Once we pass inspection, we will schedule the drywall installation, prime, paint and new floor covering……..2/16/21, DL: Conducted a site visit with the plumber and capenter shop. We will start the demo next week…………2/1/21, DL: We will schedule this project to start in 2- weeks……………….1/19/21, DL: Plans were approved and we will schedule the work in the near future………. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Permit is approved. We need to verify floor covering. Once floor covering is confirmed and ordered, we will schedule the work………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We will need plans as we are installing a new hydration station and a counter top that needs to be ADA compliant…………We started the plans and will submit them for a permit and plan check review within 2- weeks……….10/30/19, DL: No Plans will be needed. We will plan on scheduling the work shortly after Thanksgiving……. | 2019-06-13 | Enrico Baez | 9/24/2019 E. Baez--SCOPE-- 1. Removal and disposal of one bulletin board and two director cases. 2. Removal and disposal of abandoned telephone mounting bracket. 3. Remove and dispose of abandoned alarm box in wall. 4. Patch and paint walls in lobby and public restroom area. 5. Provide electrical connection for wall mounted monitor. 6. Cut access for data boxes. 7. Install monitor mount on wall. 8. Construct 7" x 18" laminate counter top and install in Lobby. | YES |  | FALL 2019 | FS | FALSE | 2019 | 2021-03-16
21P000078 |  | 21P000078 | FALSE | VC-RED | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MULTIDISCIPLINARY RESEARCH BUILDING |  | IN PROGRESS | Rodolfo Torres | Laura Manor | TARA BARTHOL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 2020-09-23 | Start 2nd floor install | [5 empty] | 1/19/21, DL: the First floor work will be complete today, we will start the 2nd floor this week……………. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
3626 | 3626 |  | FALSE | UNDERGRADUATE EDUCATION | Rivera Library Room Modifications | Conduct room modifications to support new wall display on west wall Rivera A101A. Work needed: 1. West wall - ½” three-ply to support 12 x 55” displays over bookshelves. 2. West wall – drywall cover bookshelves any area not covered by the technology displays. 3. West wall – add electrical outlets as needed for new displays 4. North and south walls – add electrical for new motorized shades 5. Rivera A101A – add carpeting 6. Rivera A101A – paint room Notes: - Working with Chuck Forsyth in ITS and Bahram Mobasher from CNAS/Physics on project. - Israel and Chuck had a preliminary meeting with Enrico Baez from facilities to discuss project. - Point of contact: Israel Fletes and Charles Forsyth. Israel Fletes cellphone: 951-300-6693 |  | A101A | New (2/10/21) |  |  | Israel Fletes |  | Vilma Kern | 1 |  |  | FALSE |  |  | 2021-02-10 | New (2/10/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-16
3612 | 3612 |  | FALSE | CAP PROG | Native American Landscape Garden | Create a physical marker to commemorate the UCR Land Acknowledgement in the form of a Native American Landscape Garden (working name) at the proposed project location. |  | Ext | New (2/11) | Jacqueline Norman | Sharyl Murdock | Uma R. |  | G.Caraig/V.Kern | 16 |  |  | FALSE | 23000 |  | 2021-02-11 | New (2/11) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-16
3623 | 3623 |  | FALSE | CNAS | NRS Boyd Deep Canyon Repairs & Upgrades | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ |  |  | New (2/2/21) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Rowan Reid | 10 |  |  | FALSE |  |  | 2021-02-02 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-16
3618 | 3618 |  | FALSE | CNAS | NRS James Reserve Upgrades | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. |  |  | New (2/2/21) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Rowan Reid | 11 |  |  | FALSE |  |  | 2021-02-02 | New (2/2/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-16
3616 | 3616 |  | FALSE | CAP PROG | University Ave/Canyon Crest Dr Improvements | $100,000 in Violent Acts Mitigation and Prevention funding have been awarded to study short and long-term safety improvements at the intersection at University Avenue and Canyon Crest Drive. Subsequent activities will involve the construction of identified improvements. |  |  | New (3/1) | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Uma R. | 17 |  |  | FALSE | 100000 |  | 2021-03-01 | New (3/1) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-16
3624 | 3624 |  | FALSE | BCOE | CE-CERT Circuit Upgrade | We have an existing 208 VAC 100 Amp circuit. We would like to upgrade to a 200 Amp service. The existing service is located in the electrical room at 1084 Columbia. |  |  | New (3/3) | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Tameesha Hayes |  |  |  | FALSE |  |  | 2021-03-03 | Need PM Assignment | [12 empty] | PD&C | FALSE | 2021 | 2021-03-16
3615 | 3615 |  | FALSE | CAP PROG | Student Success Center Buildout | Buildout and furnishing of the SSC dining venue for temporary use as seating/study area and other as needed construction scope related to the overall building project that was not described in the Basis of Design. |  |  | New (3/9/21) | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Mihai Gavan |  |  |  | FALSE | 980000 |  | 2021-03-09 | New (3/9/21) | [12 empty] | PD&C | FALSE | 2021 | 2021-03-16
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Joe Erbland | Johnathan Jensen |  | Fernando Nunez | 1 |  |  | FALSE | 0 |  | 2018-08-23 | Department approval to move fwd | [12 empty] | PD&C | FALSE | 2018 | 2021-03-16
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | SOCCER FIELD AND AREA |  | On Hold | Tamica Smith Jones | Joe Erbland | Joe Erbland |  | Gerald Caraig | 2 |  |  | FALSE | 0 |  | 2014-04-10 | Need direction by PM Director | [12 empty] | PD&C | FALSE | 2014 | 2021-03-16
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 14 |  |  | FALSE | 0 |  | 2017-12-03 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-03-16
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 17 |  |  | FALSE | 0 |  | 2018-07-16 | Coordinating with North District | [12 empty] | PD&C | FALSE | 2018 | 2021-03-16
3594 | 3594 |  | FALSE | CNAS | R'Garden Grow Pod Installation | R'Garden Gro Pod Installation |  |  | On Hold | Kathryn Uhrich | Jose Wudka | Richard Zapien |  | Scott Donnell | 6 |  |  | FALSE |  |  | 2020-05-21 | Secure Funding | [12 empty] | PD&C | FALSE | 2020 | 2021-03-16
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 1500000 |  | 2019-11-06 | On Hold | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 2019-12-10 | Departmental Approval | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | On Hold | Rodolfo Torres | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Daneca Stevens | 1 |  |  | FALSE | 45000 |  | 2017-06-13 | On Hold | [12 empty] | PD&C | FALSE | 2017 | 2021-03-16
2989 | 2989 |  | FALSE | ATHLETICS | Dance - Locker Room Remodel | We are requesting to utilize Base Architecture, Planning, & Engineering, Inc. to provide pro bono work on planning for locker room renovations in the Athletics & Dance Building. Rob Gayle is aware of our desire to utilize this company for services. |  |  | On Hold (COVID-19) | Tamica Smith Jones | Joe Erbland | Joseph Erbland |  | Tameesha Hayes | 99 |  |  | FALSE | 28395 |  | 2015-11-19 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2015 | 2021-03-16
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | On Hold (COVID-19) | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 2018-06-22 | On Hold (COVID-19) | [12 empty] | PD&C | FALSE | 2018 | 2021-03-16
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | On Hold (COVID-19) | Brian Haynes | Cathy Eckman | Christina Wong |  | Tameesha Hayes | 5 |  |  | FALSE | 130000 |  | 2019-03-19 | On hold (COVID-19) | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [12 empty] | PD&C | FALSE | 2017 | 2021-03-16
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 6 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [12 empty] | PD&C | FALSE | 2018 | 2021-03-16
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MATERIALS SCIENCE & ENGINEERING | 71 | PLAN DEVELOPMENT/CHECK | Christopher Lynch | Todd Ambriz | XI CHEN |  | DAN LERMAN |  | 2 | 3 | FALSE |  |  | 2020-08-06 | Start working on CAD drawings and building permit | [5 empty] | 3/1/21, DL: We will start the plans by early next week and we are planning to submit the plans to the building department the 2nd or 3rd week in March……1/19/21, DL: This is a priority #2 project. We will start the plans and permit process for this project when all priority 1 projects are complete…………1/14/21 O-ANS: Updated prioritization to #2 (from #3) per org leadership request. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
21P000001 |  | 21P000001 | FALSE | CNAS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | NEW GROWTH CHAMBER PLACEMENT | HOWARD SAMUEL FAWCETT LABORATORY |  | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Jose Wudka | LINDA WALLING |  | DAN LERMAN |  | 2 |  | TRUE |  |  | 2020-06-08 | Still pending plan check review. | [5 empty] | 3/1/21, DL: This was recently changed to a priority 2 project. Once plans are approved, we will work on the schedule noting, the schedule for this will work around pending priority 1 projects……1/19/21, DL: This is a priorty 3 project. We will start this project when all priority 2 projects are complete…….2/16/21, LB: Changed to Priority 2 per Dan. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 2020-09-17 | Begin RFQ Process | [12 empty] | PD&C | FALSE | 2020 | 2021-03-16
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 16 |  |  | FALSE | 1250000 | 0 | 2018-10-17 | FS Direction | [12 empty] | PD&C | FALSE | 2018 | 2021-03-16
3523 | 3523 |  | FALSE | PB&A | 1907 Mt Rubidoux Facility Study | This is a study to evaluate the existing conditions of the historic Mt. Rubidoux CES, and explore options for returning the building to a condition in which it can be occupied. |  |  | Programming (Study) | Gerry Bomotti | TBD | Melissa Garrety |  | Scott Donnell | 3 |  |  | FALSE |  |  | 2019-04-22 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Scott Donnell | 10 |  |  | FALSE | 65000 |  | 2019-03-04 | Complete Study | [12 empty] | PD&C | FALSE | 2019 | 2021-03-16
21P000019 |  | 21P000019 | FALSE | BCOE | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | Bourns Office A305 - Install Plank Floor | MARLAN & ROSEMARY BOURNS HALL | A305 | PROJECT INTAKE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | 3 | 2 | TRUE |  |  | 2020-07-20 | Complete priority 2 projects | [5 empty] | 1/19/21, DL: This a priority 3 project. We will start this project when all priority #2 projects are complete………..1/14/21 O-ANS: Updated prioritization to #3 (from #2) per org leadership request. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 150 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 2020-01-14 | Electrical Engineer design | [5 empty] | 1/19/21, DL: This project will require engineered plans. This is a priority 2 project. We will start the plans and permit process when all priority #1 projects are complete………… |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 245 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | ANDREA HIDALGO |  | DAN LERMAN |  | 3 |  | FALSE |  |  | 2020-01-02 | Plans and permit once we start priority 3 projects | [5 empty] | 1/19/21, DL: This is a priority 3 project. We will start the plans and permit for this project when all priortiy #2 projects are complete…….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Convert Basement Library into Piano Lab | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 54 | PROJECT INTAKE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 2019-11-19 | start plans once priority 3 proj. are almost comp. | [5 empty] | 1/19/21, DL: We will Start the plans, permit and the work once all priority #3 projects…………...11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks……….. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16
20P000320 |  | 20P000320 | FALSE | CNAS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | ACTIVATE VACUUM LINES | HERMAN T. SPIETH HALL | 1303 | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | DAN LERMAN |  | 4 |  | FALSE |  |  | 2019-11-20 | Will start the work once we start priority 4 proj | [5 empty] | 1/19/21, DL: This is a priority 4 project. We will start this project when all all priority 3 projects are complete……….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16
20P000248 |  | 20P000248 | FALSE | CNAS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT | Space Management has temporarily allocated Rooms 1223 and 1223-A in Webber Hall to CNAS. We need this lab cleaned and modified to accommodate relocating an existing (and active) lab. | HERBERT JOHN WEBBER HALL | 1223 + 1223-A | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | SHARYL MURDOCK |  | Dan Lerman |  | 5 | 4 | FALSE |  |  | 2019-11-27 | EH&S to sanitize space | 2021-03-02 | 2021-04-21 |  |  |  | 1/19/21, DL: This project is a priority #5. We will start this project when all priority #4 projects are complete…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….02/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Survey space for hazardous material. Once survey is complete, we will schedule abatement and the work. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16
20P000366 |  | 20P000366 | FALSE | CNAS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | MINOR LAB RENOVATION | HERMAN T. SPIETH HALL | 2375 / 2375-A | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | SHERICE UNDERWOOD |  | DAN LERMAN |  | 7 |  | TRUE |  |  | 2020-02-19 | Will start when we start priority 7 projects. | [5 empty] | 1/19/21, DL: This is a priority 7 project, we will start this project when all priority 6 projects are complete………….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | W. CONWAY PIERCE HALL | 2232A | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 2020-01-22 | will start when we start priority 9 projects | [5 empty] | 1/19/21, DL: This is a priority #9 project. We will start this project when all priority #8 projects are complete…………. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS BUILDING |  | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | JOSE WUDKA |  | Enrico Baez |  | R1 |  | FALSE |  |  | 2019-12-19 | [6 empty] | 1/19/21 DL: Enrico is managing this project. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16 |  | 1
20P000046 |  | 20P000046 | FALSE | CNAS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | HOMER D. CHAPMAN HALL | 0001 | PROJECT INTAKE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Enrico Baez |  | R2 |  | FALSE |  |  | 2019-07-31 | [6 empty] | 1/19/21, DL: Enrico B. will manage this priject………….11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Install wireless access controls systems at front and rear entry doors. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16 |  | 1
21P000003 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | PROJECT INTAKE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Enrico Baez |  | R1 |  | FALSE |  |  | 2020-06-26 | [6 empty] | 1/19/21, DL: Enrico is managing this project………….. | 2020-12-02 | Enrico Baez | Remove tripod antenna. Apply spray roof coating to existing roof surface | YES |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16 |  | 1
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | JEANETTE AND RUPERT COSTO HALL |  | PROJECT INTAKE | Brian Haynes | Cathy Eckman | BRENDAN O'BRIEN |  | Enrico Baez |  | R1 | R2 | FALSE |  |  | 2019-10-24 | [6 empty] | 02/16/21 O-ANS: Will require plans/permits and may need to go to PD&C due to scope of work which includes construction. Will confirm with client before instructing to submit request to CPMS…. 01/19/21, DL: Enrico B. Will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16 |  | 1
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | [12 empty] | PD&C | FALSE | 1900 | 2021-03-16
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | TBD | Sean Hatfield |  | D.Hecht/J.Franklin | 20 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2021 | [12 empty] | PD&C | FALSE | 2017 | 2021-03-16
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 2020-03-30 | Projects to be assigned | [12 empty] | PD&C | FALSE | 2020 | 2021-03-16
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | MARLAN & ROSEMARY BOURNS HALL | B0328E | QUEUE TO START | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Enrico Baez |  | R1 | R1 | FALSE |  |  | 2019-11-05 | [6 empty] | 1/19/21, DL: Todd has the estimate. Sent follow up email to Todd requesting update or FAU number………………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16 |  | 1
20P000310 |  | 20P000310 | FALSE | BCOE | SL5 BOURNS A-WING A129 - PATCH & PAINT | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. | MARLAN & ROSEMARY BOURNS HALL | A0129 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-01-10 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000363 |  | 20P000363 | FALSE | BCOE | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | Paint Only | WINSTON CHUNG HALL | 433 | QUEUE TO START | Christopher Lynch | Todd Ambriz | MANGLAI ZHOU | FARIBORZ KARGAR | PAUL DITTY |  | X |  | TRUE |  |  | 2020-02-13 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUMANITIES BUILDING | 3210 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-24 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000446 |  | 20P000446 | FALSE | CHASS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. | CHASS INTERDISCIPLINARY NORTH | 4047 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-04 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000464 |  | 20P000464 | FALSE | CHASS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) | HUMANITIES BUILDING | 3001 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000453 |  | 20P000453 | FALSE | CHASS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | Paint Only - Please patch/paint to existing color office for faculty new hire. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 142 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
21P000110 |  | 21P000110 | FALSE | CHASS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. | GORDON S. WATKINS HALL | 2146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-11-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000469 |  | 20P000469 | FALSE | CHASS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 222 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | SUSAN KOMURA | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-23 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000403 |  | 20P000403 | FALSE | CHASS | SL5 OLMSTED 232 - PAINT OFFICE | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). | JOHN W. OLMSTED HALL | 2321 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | MELISA VICARIO | Paul Ditty |  | X |  | TRUE |  |  | 2020-03-13 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000462 |  | 20P000462 | FALSE | CHASS | SL5 HMSS 2001 - PAINT OFFICE / CLEAN FLOOR NEW FACULTY HIRE | Patch/paint to existing color for faculty new hire | HUMANITIES BUILDING | 2001 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | Paul Ditty |  | X |  | TRUE |  |  | 2020-06-18 | [6 empty] | 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
21P000109 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Dr. Robert Clark. He started working July 1, 2020. | GORDON S. WATKINS HALL | 1146 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-11-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
21P000111 |  | 21P000111 | FALSE | CHASS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. | GORDON S. WATKINS HALL | 2144 | QUEUE TO START | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-11-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000463 |  | 20P000463 | FALSE | CHASS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 | HUMANITIES BUILDING | 2000 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS BUILDING | 3009 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 2019-10-11 | [6 empty] | 02/03/21 O-ANS: Reminder email sent to customer that PAINT ONLY portion would be completed and not the door removal at this time. Customer can resubmit request in next prioriization cycle…. 11/06/20 O-JLO: Emailed requestor and alternate regarding paint portion only, and that door/drywall removal will not occur during this time …. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. FS to confirm with customer that we can only complete the painting at this time but not the removal of the door…. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure. | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16
20P000445 |  | 20P000445 | FALSE | CNAS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 279 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | DAN LERMAN |  | 3 |  | TRUE |  |  | 2020-06-03 | schedule work inline with current proj. in progres | [5 empty] | 3/15/21, DL: The building permit was approved today. We will work this project in to our schedule and we will schedule the work once we are ready to and in line with our other projects that are already in progress……….2/16/21, LB: Changed to Priority 3 per Dan…….1/19/21, DL: This is a priority 3 project. We will start the project when all priority 1 &2 projects are in process or almost complete… |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000397 |  | 20P000397 | FALSE | CNAS | SL5 ENTOMOLOGY 139 - PATCH AND PAINT OFFICE | Patch and paint room 139 for the new faculty member | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 0139 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-03-05 | [6 empty] | 02/10/21 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 2019-11-25 | [6 empty] | 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16
20P000419 |  | 20P000419 | FALSE | CNAS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | Paint Only | HERMAN T. SPIETH HALL | 2312 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | PAUL DITTY |  | X |  | TRUE |  |  | 2020-04-22 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000467 |  | 20P000467 | FALSE | SOM | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. | HERBERT JOHN WEBBER HALL | 1247 | QUEUE TO START | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-19 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
20P000218 |  | 20P000218 | FALSE | VC-RED | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | VIVARIUM UPDATE AIR COMPRESSOR | HERMAN T. SPIETH HALL | 347 | QUEUE TO START | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | DAN LERMAN |  | 2 | R2 | FALSE |  |  | 2019-05-17 | We will start once priority 1 projects are complet | [5 empty] | 3/15/21, DL: We received confirmation the Compressor is on site. We will schedule the work once as soon as we are able to………….2/1/21, DL: WE will start the process for this project once we are closer to completing priority 1 projects. This is a prioity 2 project……1/19/21, /DL: This project has been scoped. We will start the work when we are complete with all priority #1 projects……. |  | Enrico Baez |  |  |  | Winter 2021 | FS | FALSE | 2019 | 2021-03-16
20P000468 |  | 20P000468 | FALSE | VC-RED | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | Paint Only | HERMAN T. SPIETH HALL | 364 | QUEUE TO START | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-06-23 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
21P000079 |  | 21P000079 | FALSE | VC-RED | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. | PSYCHOLOGY BUILDING |  | QUEUE TO START | Rodolfo Torres | Laura Manor | LESLIE KARPINSKI |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-09-25 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | FALSE | 2020 | 2021-03-16
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | Sub-contractor bidding | Gerry Bomotti | TBD | Sharyl Murdock |  | Rowan Reid | 16 |  |  | FALSE | 26329342.06 |  | 2015-12-15 | Start Construction | 2021-04-01 | 2023-08-01 | [10 empty] | PD&C | FALSE | 2015 | 2021-03-16
3401 | 3401 |  | FALSE | CAP PROG | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | Substantial Completion 2/5/21 | Jacqueline Norman | Sharyl Murdock | Mihai Gavan |  | Fernando Canon | 12 |  |  | FALSE | 8754623.11 |  | 2017-12-03 | Complete Furniture & Equipment | 2020-05-01 | 2021-02-01 | [8 empty] | 2021-02-05 |  | PD&C | FALSE | 2017 | 2021-03-16 | FY 20-21
3515d | 3515d |  | FALSE | PB&A | Multiple SF6 Primary Switches | Sub-project of 950568 |  |  | TBD | Gerry Bomotti | TBD | John Franklin |  | J.Franklin/G.Caraig | 2 |  |  | FALSE |  |  | 2021-03-01 | TBD | [12 empty] | PD&C | FALSE | 2021 | 2021-03-16
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 19 |  |  | FALSE | 2586581 |  | 2018-11-06 | Complete Review | [12 empty] | PD&C | FALSE | 2018 | 2021-03-16
18P000484 |  | 18P000484 | FALSE | ATHLETICS | SL5 INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | Project will be managed by A&E for completion. | SOFTBALL STG |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-26 | [6 empty] | 2/1/19, DL; This is a PD&C Project due to IRT walk. Project will exceed $50,000……….. |  | Enrico Baez |  | NO | 2019-02-01 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000276 |  | 19P000276 | FALSE | ATHLETICS | SL5 TRACK BLEACH-PUBLIC RESTROOMS UPGRADE |  | TRACK BLEACH |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joe Erbland | JOHNATHAN JENSEN |  |  |  | 16 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez |  | YES | 2018-11-20 | Fall 2018 | FS | FALSE | 2018 | 2021-03-16
19P000060 |  | 19P000060 | FALSE | BCOE | SL5 CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | CHUNG HALL | 223 & 224 | TO BE PERFORMED BY PD&C | Christopher Lynch | Todd Ambriz | MAGARET SOUDER |  | Dan Lerman |  | 6 | 4 | FALSE |  |  | 2018-05-15 | [6 empty] | 2/1/19, DL; Thios is a PD&C project. Maggie S. is aware this project may be a $130,00. project……DL, 7/25/18; This project is complicated and plans/permits will be required. This project will also require Air Hanlers to be shut down so Vibration dampners can be instlled. We will work on the plans in the next 45 days. This project should be scheduled during the Winter. We may also need to rent a large portable air handler to ensure the Large server room can maintain temp……. Project #19P000060 to replace REF CPMS # 9043. DL, 11/7/18; Sent Maggie an email on 11/7/18 informing her this project is well beyond our scope and $50K threshold. |  | Dan Lerman |  | YES | 2019-02-01 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
20P000067 |  | 20P000067 | FALSE | BCOE | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM | BOURNS | B-Wing | TO BE PERFORMED BY PD&C | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2016-11-14 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Replace access controls at BCOE WCH & Bourns bldgs. |  | 2020-11-19 | Fall 2019 | FS | FALSE | 2016 | 2021-03-16 | FY 20-21 | 1
19P000674 |  | 19P000674 | FALSE | CHASS | SL5 HMSS RM 2416 OFFICE ROOM PATCH AND PAINT |  | HUM & SOC SC | 2416 | TO BE PERFORMED BY PD&C | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2019-06-19 | [6 empty] | 11/26/2019 O-ANS: Project completed per Paul Ditty. |  | Paul Ditty |  |  | 2019-09-23 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | Modify the existing room in Soil House 1 (attached to the Delphino Lab at the Rubidoux Facilities) to expand CCPP quarantine services to include USDA/CDFA compliance for installation of new Economic Development Administration (EDA) citrus growth chambers. | DELFINO HHSE |  | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | Research and plan development | [5 empty] | 12/7/20, DL: This project will be managed by PD&C…..9/30/20, DL: Project is still on Hold until Furhther notice………...8/5/20, DL: WE will work on plans in the next 30- 45 days……………6/17/20, DL: This project is under review and is on hold until further notice………10/3/19 O-ANS: Plan Development per Minor Reno Meeting. 10/1/19,DL; We are getting ready to start the plans as we are currently conducting resarch on products that will meet the needs of the space……………..5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman |  | YES | 2020-12-07 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16 | FY 20-21
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB. Patch Paint walls, replace flooring, refinish wood cabinets and sinks. | SPIETH | 2349 | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 5 |  | FALSE |  |  | 2019-02-20 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold……….12/11/19: O-ANS: Reassigned as project allotment - priority #5 for Winter 2020. 11/27/19 O-ANS: Placed on Hold for re-prioritization by client for Winter 2020. | 2020-02-27 | Enrico Baez | Patch and paint and extra work to upgrade an old lab that we are now inhabiting. In addition to painting, we need to have floors re-surfaced, cabinets re-stained, and counter tops re-surfaced, if possible. There is also a metal sink that could be polished. | YES | 2020-11-19 | Winter 2020 | FS | FALSE | 2019 | 2021-03-16 | FY 20-21
18P000273 |  | 18P000273 | FALSE | LIBR | SL5 RIVERA LIB -RESTROOM REFRESH PROJECT |  | RIVERA LIB |  | TO BE PERFORMED BY PD&C | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2018-01-18 | [6 empty] | DND 12/13/18: Customer advised maintenance requests related to project request has been addressed. Renovation work to be performed by PD&C and customer submitted a CPMS request. DL, 6/16/18; Need to schedule site visit with Dave and Chris P…….DL, 7/11/18; Chris and I will walk this poroject next week…..Wlaked projects with Chris. We need to review in more detail to better determin the process for this project…..DL, 9/6/18. WE need to discuss what we are going to do with this project.... We walked the project but we now need Direction from Facilities leadership… |  | Dan Lerman |  | YES | 2018-12-13 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16
18P000106 |  | 18P000106 | FALSE | PB&A | SL5 HOUSING PROJECT - OBAN REC ROOM REMODEL |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 3 | FALSE |  |  | 2017-09-14 | [6 empty] | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. DL, 7/11/18; Per Susan this project is back on track. Project is scoped. Gunther will start working on the plans and permits. Once we have the approved permit. still need to check in with Susan on a few items.....Target complet date will be mid- fall...... |  | Enrico Baez |  | YES | 2019-01-19 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
18P000094 |  | 18P000094 | FALSE | PB&A | SL5 OBAN LAUNDRY ROOM RENOVATION |  | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | TBD | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2017-09-08 | [6 empty] | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on bid. 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/12 EB- rec'd approval to contract with Design West to consult on electrical panel upgrade. |  | Enrico Baez |  | YES | 2019-01-19 | Fall 2017 | FS | FALSE | 2017 | 2021-03-16
19P000670 |  | 19P000670 | FALSE | SOM | SL5 SOME, RM 1670- RENOVATE FOR EXPANDED ENROLLMENT |  | SOM EDUC | 1670 | TO BE PERFORMED BY PD&C | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2019-06-18 | [8 empty] | Enrico Baez |  |  | 2019-09-06 | Fall 2019 | FS | FALSE | 2019 | 2021-03-16 | FY 19-20
18P000456 |  | 18P000456 | FALSE | VC-STU AFF | SL5 HUB--UTILITY METERS | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. | HUB |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-05-30 | [8 empty] | Enrico Baez |  | YES | 2019-01-24 | Summer 2018 | FS | FALSE | 2018 | 2021-03-16
18P000348 |  | 18P000348 | FALSE | VC-STU AFF | SL5 HUB ADD 3RD FLOOR WALLS |  | HUB | 0353E | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 2 | 6 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/1/19, DL; Per Chris P. This is a PD&C project………..DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Need to walk the project with Manny. Target date is late Fall…….. |  | Enrico Baez |  | YES | 2019-02-01 | Spring 2018 | FS | FALSE | 2018 | 2021-03-16

## Data Validation (hidden)
|  | 1 |  | Data As Of (Scheduled Data Pull) | Date of Previous Report | Proj_Mgr | PM_Ph | PM_Email | Dept |  |  |  |  | CAAN | Official | Building | CNC | FS Project # | Quarter Prioritized | Quarter | Chronology
0 | 3590b | 20P000086 | 20P000086 | 2020-12-16 | 2020-12-01 | B. Wilson/J. Franklin | 951-827-1485 | blythe.wilson@ucr.edu | PDC | A | 1 | Project Ref No. | Proj_Ref_No | P5186 | BIOLOGICAL SCIENCES | BIOLOGIC SCI | CORE | 19P000277 | Fall 2018 | Fall 2017 | 1
0 | 3590a |  |  | 2021-01-01 | 2020-12-16 | Blair Fickett |  |  | PDC | B | 2 |  | CPMS_No | P5187 | LATH HOUSE BUILDING B | LATH B FLD16 | CORE | 19P000225 | Fall 2018 | Winter 2018 | 2
0 | 3515c |  |  | 2021-01-16 | 2021-01-01 | Blythe Wilson | 951-827-1485 | blythe.wilson@ucr.edu | PDC | C | 3 |  | Work_Order_No | P5188 | MITE WASHER BUILDING C | MITE C FLD16 | CORE | 19P000193 | Fall 2018 | Spring 2018 | 3
0 | 3515b |  |  | 2021-02-01 | 2021-01-16 | CAS |  |  | PDC | D | 4 |  | IRT | P5189 | COMMON COVERED WORKHOUSE BLDG A (PART OF WEST CAMPUS I&Q) | COM WRK FD16 | NON-CORE | 19P000309 | Fall 2018 | Summer 2018 | 4
0 | 3228b |  |  | 2021-02-16 | 2021-02-01 | Chris Pillen | 951-827-4214 | christopher.pillen@ucr.edu | FS | E | 5 | Organization | Org | P5190 | PLANT TRANSFORMATION FACILITY | PLANT TRANSF | CORE | 20P000031 | Fall 2019 | Fall 2018 | 5
0 | 3035a |  |  | 2021-03-01 | 2021-02-16 | Cliff Stokes |  |  | FORMER | F | 6 | Project Title | Project_Title | P5192 | EAST CAMPUS INSECTARY AND QUARANTINE FACILITY GREENHOUSE | EAST I&Q GH | CORE | 20P000026 | Fall 2019 | Winter 2019 | 6
0 | 2970d |  |  | 2021-03-16 | 2021-03-01 | Craig/Chris Pillen | 951-827-4214 | christopher.pillen@ucr.edu | FS | G | 7 | Project Description | Project_Description | P5194 | WINSTON CHUNG HALL | CHUNG HALL | CORE | 19P000517 | Fall 2019 | SPRING 2019 | 7
0 | 2970c |  |  | 2021-04-01 | 2021-03-16 | D. Hecht/J. Franklin | 951-827-7358 | drew.hecht@ucr.edu | PDC | H | 8 | Building | t_CPMS_Data.Building | P5195 | MATERIALS SCIENCE & ENGINEERING | MAT SCI ENGR | CORE | 20P000003 | Fall 2019 | Summer 2019 | 8
0 | 21P000111 |  |  | 2021-04-16 | 2021-04-01 | Dan Lerman | 951-827-6224 | daniel.lerman@ucr.edu | FS | I | 9 |  | t_Building.Building | P5196 | GENOMICS BUILDING | GENOMICS | CORE | 20P000070 | Fall 2019 | Fall 2019 | 9
0 | 21P000110 |  |  | 2021-05-01 | 2021-04-16 | Daryl Korluck |  |  | FORMER | J | 10 | Room | Room | P5197 | ALUMNI & VISITORS CENTER | ALUM VISITOR | NON-CORE | 20P000107 | Fall 2019 | Winter 2020 | 10
0 | 21P000109 |  |  | 2021-05-16 | 2021-05-01 | Dave Bomba | 951-827-1412 | dave.bomba@ucr.edu | PDC | K | 11 | Current Status | Current_Status | P5198 | UCR CHILD DEVELOPMENT CENTER NORTH | CHILD DEV N | CORE | 20P000068 | Fall 2019 | Spring 2020 | 11
0 | 21P000102 |  |  | 2021-06-01 | 2021-05-16 | Drew Hecht | 951-827-7358 | drew.hecht@ucr.edu | PDC | L | 12 |  | Org_Name | P5199 | HIGHLANDER UNION 2 ACTIVITY CENTER | HUB 2 | NON-CORE | 20P000044 | Fall 2019 | Summer 2020 | 12
0 | 21P000083 |  |  | 2021-06-16 | 2021-06-01 | Enrico Baez | 951-827-4214 | enrico.baez@ucr.edu | FS | M | 13 | Organization Leader | Org_Leadership | P5200 | GREENHOUSE #9 | GH09 | CORE | 19P000664 | Fall 2019 | Fall 2020 | 13
0 | 21P000079 |  |  | 2021-07-01 | 2021-06-16 | Enrico Baez - Managing Contractor | 951-827-4214 | enrico.baez@ucr.edu | FS | N | 14 | Prioritization Designate | Org_Contact | P5205 | UNIVERSITY OFFICE BUILDING | UNIV OFC BLD | CORE | 20P000061 | Fall 2019 | Winter 2021 | 14
0 | 21P000078 |  |  | 2021-07-16 | 2021-07-01 | Fernando Nunez | 951-827-2466 | fernando.nunez@ucr.edu | PDC | O | 15 | Contact | Contact | P5210 | GREENHOUSE #15 | GH15 | CORE | 20P000075 | Fall 2019 | Spring 2021 | 15
0 | 21P000049 |  |  | 2021-08-01 | 2021-07-16 | George MacMullin |  |  | FORMER | P | 16 |  | Contact_2 | P5215 | HOMER D. CHAPMAN HALL | CHAPMAN | CORE | 19P000467 | Fall 2019 | Summer 2021 | 16
0 | 21P000037 |  |  | 2021-08-16 | 2021-08-01 | Jacqueline Norman | 951-827-6316 | jacqueline.norman@ucr.edu | PDC | Q | 17 | Project Manager | Proj_Mgr | P5216 | CHICKEN COOP #1 | CHICK COOP 1 | NON-CORE | 20P000083 | Fall 2019 | Fall 2021 | 17
0 | 21P000019 |  |  | 2021-09-01 | 2021-08-16 | Jason Williams |  | jason.williams@ucr.edu | FS | R | 18 | PD&C Org Priority No. | Org_Priority | P5217 | PHYSICAL PLANT STORAGE UNIT | PHYS PL STOR | CORE | 20P000008 | Fall 2019
0 | 21P000009 |  |  | 2021-09-16 | 2021-09-01 | Jerrod Walters | 951-827-6955 | jerrod.walters@ucr.edu | PDC | S | 19 | FS Org Priority No. | FS_Priority | P5218 | THE COTTAGE | COTTAGE | NON-CORE | 19P000683 | Fall 2019
0 | 21P000003 |  |  | 2021-10-01 | 2021-09-16 | Jess Hernandez | 951-827-4214 | jesus.hernandez@ucr.edu | FS | T | 20 | For Faculty Hire | For_Faculty_Hire | P5219 | WORKMAN'S COTTAGE #2 | WORKMN COT 2 | NON-CORE | 19P000673 | Fall 2019
0 | 21P000001 |  |  | 2021-10-16 | 2021-10-01 | John Franklin | 951-827-6953 | john.franklin@ucr.edu | PDC | U | 21 | PD&C Approved Budget | Approved_Budget | P5220 | WORKMAN'S COTTAGE #3 | WORKMN COT 3 | NON-CORE | 19P000660 | Fall 2019
0 | 20P000470 |  |  | 2021-11-01 | 2021-10-16 | John Peraino | 951-827-2121 | john.peraino@ucr.edu | FS | V | 22 | FS Recharge Actuals To Date | FS_Recharge_Costs | P5224 | UNIVERSITY BOOKSTORE | BOOKSTORE | NON-CORE | 20P000059 | Fall 2019
0 | 20P000469 |  |  | 2021-11-16 | 2021-11-01 | Marianne Valenti |  |  | FORMER | W | 23 | Request Date | Project_Initiated | P5230 | STORAGE SHED #8 | STOR 8 | CORE | 20P000077 | Fall 2019
0 | 20P000468 |  |  | 2021-12-01 | 2021-11-16 | Mihai Gavan | 951-827-6959 | mihai.gavan@ucr.edu | PDC | X | 24 | Next Steps | Next_Major_Milestone | P5231 | COLLEGE BUILDING SOUTH | COLL BLDG SO | CORE | 20P000045 | Fall 2019
0 | 20P000467 |  |  | 2021-12-16 | 2021-12-01 | Mihai Gavan-MRB1 |  | mihai.gavan@ucr.edu | PDC | Y | 25 | Start Date | Const_Start | P5241 | ENVIRONMENTAL HEALTH AND SAFETY BUILDING | ENV H AND S | CORE | 19P000602 | Fall 2019
0 | 20P000464 |  |  |  |  | N/A | 951-827-4214 |  |  | Z | 26 | Complete Date | Construction_Completion | P5242 | LATHHOUSE #1 | LATH 1 | CORE | 20P000028 | Fall 2019
0 | 20P000463 |  |  |  |  | Not Assigned | 951-827-4214 |  |  | AA | 27 | Impact Description | Impact_Description | P5251 | THEATRE WORKSHOP | THTR WKSH | CORE | 20P000002 | Fall 2019
0 | 20P000453 |  |  |  |  | Paul Ditty | 951-827-4214 | paul.ditty@ucr.edu | FS | AB | 28 | Impact Date Start | Impact_Date_Start | P5253 | MAIL BUILDING | MAIL | CORE | 20P000004 | Fall 2019
0 | 20P000449 |  |  |  |  | R. Amescua/D. Hecht |  | raoul.amescua@ucr.edu | PDC | AC | 29 | Impact Date End | Impact_Date_End | P5254 | BOTANIC GARDENS INFORMATION CENTER | BOTAN INFO C | NON-CORE | 20P000081 | Fall 2019
0 | 20P000446 |  |  |  |  | R. Amescua/J. Kaplan |  | raoul.amescua@ucr.edu | PDC | AD | 30 | Project Service Unit | PM_Notes | P5255 | BOTANY & PLANT SCIENCES FIELDHOUSE FIELD 15A | BOT FLDHS15A | NON-CORE | 20P000034 | Fall 2019
0 | 20P000445 |  |  |  |  | Raoul Amescua | 951-827-6951 | raoul.amescua@ucr.edu | PDC | AE | 31 |  | PM_Date | P5256 | ENTOMOLOGY MUSEUM | ENTOM MUSEUM | CORE | 20P000054 | Fall 2019
0 | 20P000419 |  |  |  |  | Robert Corey |  |  | FORMER | AF | 32 |  | Scope_Date | P5258 | GLASSHOUSE FIELD 16 #45 | GH 16 45 | CORE | 19P000661 | Fall 2019
0 | 20P000403 |  |  |  |  | Ron Veloz | 951-827-4214 | ron.veloz@ucr.edu | FS | AG | 33 |  | Scope_Reviewer | P5259 | GREENHOUSE #2A | GH02A | CORE | 20P000047 | Fall 2019
0 | 20P000370 |  |  |  |  | Rowan Reid | 951-827-5825 | rowan.reid@ucr.edu | PDC | AH | 34 |  | Scope_Notes | P5260 | GLASSHOUSE FIELD 16 #46 | GH 16 46 | CORE | 19P000624 | Fall 2019
0 | 20P000368 |  |  |  |  | Scott Donnell | 951-827-4706 | scott.donnell@ucr.edu | PDC | AI | 35 |  | Scope_Complete | P5261 | MARLAN & ROSEMARY BOURNS HALL | BOURNS | CORE | 20P000029 | Fall 2019
0 | 20P000367 |  |  |  |  | Tameesha Hayes |  |  | FORMER | AJ | 36 |  | Owner | P5263 | UNIVERSITY LABORATORY BUILDING | UNIV LAB BLD | CORE | 20P000005 | Fall 2019
0 | 20P000366 |  |  |  |  | Uma R. | 951-827-5610 | uma.ramasubramanian@ucr.edu | PDC | AK | 37 |  | IRT? | P5265 | TRAILER #10A | T10A | CORE | 20P000036 | Fall 2019
0 | 20P000363 |  |  |  |  | xxxxx |  |  |  | AL | 38 |  | Requested Year | P5266 | TRAILER #9A | T9A | CORE | 20P000024 | Fall 2019
0 | 20P000355 |  |  |  |  | Yvonne Lujan | 951-827-5154 | yvonne.lujan@ucr.edu | PDC | AM | 39 |  | Data Pulled On | P5267 | GLASSHOUSE FIELD 16 #26 | GH 16 26 | CORE | 19P000662 | Fall 2019
0 | 20P000354 | [12 empty] | P5268 | STORAGE SHED #5 | STOR 5 | CORE | 20P000060 | Fall 2019
0 | 20P000337 | [12 empty] | P5269 | GLASSHOUSE FIELD 16 #27 | GH 16 27 | CORE | 20P000039 | Fall 2019
0 | 20P000336 | [12 empty] | P5270 | GARAGE COTTAGE #3 | GAR C3 | CORE | 20P000090 | Fall 2019
0 | 20P000335 | [12 empty] | P5271 | BARN STABLE | BARN STABLE | NON-CORE | 19P000688 | Fall 2019
0 | 20P000333 | [12 empty] | P5272 | PARKING SERVICES BUILDING | PARKING SERV | NON-CORE | 20P000017 | Fall 2019
0 | 20P000320 | [12 empty] | P5273 | GLASSHOUSE FIELD 16 #22 | GH 16 22 | CORE | 19P000658 | Fall 2019
0 | 20P000317 | [12 empty] | P5274 | GARAGE COTTAGE #1 | GAR C1 | CORE | 19P000666 | Fall 2019
0 | 20P000310 | [12 empty] | P5275 | GREENHOUSE #6 | GH06 | CORE | 20P000065 | Fall 2019
0 | 20P000309 | [12 empty] | P5276 | GREENHOUSE #7 | GH07 | CORE | 19P000676 | Fall 2019
0 | 20P000275 | [12 empty] | P5277 | GREENHOUSE #8 | GH08 | CORE | 20P000019 | Fall 2019
0 | 20P000272 | [12 empty] | P5278 | GREENHOUSE #10 | GH10 | CORE | 19P000523 | Fall 2019
0 | 20P000271 | [12 empty] | P5279 | GREENHOUSE #11 | GH11 | CORE | 19P000659 | Fall 2019
0 | 20P000270 | [12 empty] | P5280 | GREENHOUSE #12 | GH12 | CORE | 20P000051 | Fall 2019
0 | 20P000269 | [12 empty] | P5281 | GREENHOUSE #13 | GH13 | CORE | 19P000657 | Fall 2019
0 | 20P000268 | [12 empty] | P5282 | GREENHOUSE #21 | GH21 | CORE | 19P000674 | Fall 2019
0 | 20P000267 | [12 empty] | P5284 | GREENHOUSE #16 | GH16 | CORE | 20P000023 | Fall 2019
0 | 20P000266 | [12 empty] | P5285 | RESTROOMS & TICKET BOOTH BUILDING | TICKET BOOTH | CORE | 20P000082 | Fall 2019
0 | 20P000253 | [12 empty] | P5286 | RESTROOM / MAINTENANCE | RSTRM/MAINT | CORE | 20P000094 | Fall 2019
0 | 20P000248 | [12 empty] | P5287 | STORAGE BUILDING PLANT PATHOLOGY FIELD 16E | STOR PL PATH | CORE | 20P000069 | Fall 2019
0 | 20P000247 | [12 empty] | P5288 | NEMATOLOGY MICROPLOT STORAGE BUILDING FIELD 15A | NEM MICRO ST | CORE | 19P000302 | Fall 2019
0 | 20P000245 | [12 empty] | P5289 | EAST CAMPUS INSECTARY AND QUARANTINE FACILITY | EAST I&Q FAC | CORE | 20P000057 | Fall 2019
0 | 20P000244 | [12 empty] | P5290 | HAY BARN | HAY BN | CORE | 20P000049 | Fall 2019
0 | 20P000243 | [12 empty] | P5291 | TURF PLOT STORAGE AGRICULTURAL OPERATIONS | TURF PL STOR | CORE | 20P000050 | Fall 2019
0 | 20P000242 | [12 empty] | P5292 | STORAGE BUILDING AT LOADING DOCK OF PIERCE HALL | STOR PRCE | CORE | 20P000053 | Fall 2019
0 | 20P000241 | [12 empty] | P5293 | GLASSHOUSE FIELD 16 #25 | GH 16 25 | CORE | 20P000092 | Fall 2019
0 | 20P000240 | [12 empty] | P5295 | CENTRAL UTILITY PLANT | CNTRL UTL PL | CORE | 19P000607 | Fall 2019
0 | 20P000239 | [12 empty] | P5296 | GLASSHOUSE FIELD 16 #9 | GH 16 09 | CORE | 20P000100 | Fall 2019
0 | 20P000238 | [12 empty] | P5297 | GLASSHOUSE FIELD 16 #23 | GH 16 23 | CORE | 20P000101 | Fall 2019
0 | 20P000237 | [12 empty] | P5298 | SHED BUILDING FIELD 16 #25 | SHED 16 25 | CORE | 20P000102 | Fall 2019
0 | 20P000236 | [12 empty] | P5299 | GLASSHOUSE FIELD 16 #10 | GH 16 10 | CORE | 20P000103 | Fall 2019
0 | 20P000235 | [12 empty] | P5300 | GLASSHOUSE FIELD 16 #11 | GH 16 11 | CORE | 20P000052 | Fall 2019
0 | 20P000233 | [12 empty] | P5302 | EQUIPMENT SHED | EQUIP SHED | CORE | 19P000626 | Fall 2019
0 | 20P000232 | [12 empty] | P5304 | INSECTICIDE COMPOUNDING & STORAGE BUILDING | INSECT COMP | CORE | 18P000465 | Fall 2019
0 | 20P000231 | [12 empty] | P5305 | STORED PRODUCTS INSECTICIDE BUILDING | SPI | CORE | 20P000085 | Fall 2019
0 | 20P000230 | [12 empty] | P5307 | HUMANITIES & SOCIAL SCIENCES | HUM & SOC SC | CORE | 19P000623 | Fall 2019
0 | 20P000226 | [12 empty] | P5308 | SOUTH LOCKERROOM & CONCESSION STAND | S LCKRM/CONC | CORE | 20P000055 | Fall 2019
0 | 20P000225 | [12 empty] | P5310 | WEST LOCKERROOM & CLUBHOUSE CONCESSION STAND | W LCKRM/CONC | CORE | 19P000627 | Fall 2019
0 | 20P000223 | [12 empty] | P5311 | JEANETTE AND RUPERT COSTO HALL | COSTO HALL | NON-CORE | 20P000073 | Fall 2019
0 | 20P000221 | [12 empty] | P5312 | LATHHOUSE #32 | LATH 32 | CORE | 20P000067 | Fall 2019
0 | 20P000220 | [12 empty] | P5315 | LATHHOUSE #36 | LATH 36 | CORE | 20P000093 | Fall 2019
0 | 20P000218 | [12 empty] | P5316 | LIFE SCIENCES | LIFE SCIENCE | CORE | 19P000568 | Fall 2019
0 | 20P000215 | [12 empty] | P5319 | HERBARIUM | HERBARIUM | CORE | 20P000038 | Fall 2019
0 | 20P000214 | [12 empty] | P5321 | STORAGE SHED #37 | STOR 37 | CORE | 20P000114 | Fall 2019
0 | 20P000213 | [12 empty] | P5322 | TOMAS RIVERA LIBRARY | RIVERA LIB | CORE | 20P000037 | Fall 2019
0 | 20P000212 | [12 empty] | P5323 | HERMAN T. SPIETH HALL | SPIETH | CORE | 19P000427 | Fall 2019
0 | 20P000211 | [12 empty] | P5324 | STORAGE SHED #49 | STOR 49 | CORE | 20P000046 | Fall 2019
0 | 20P000210 | [12 empty] | P5325 | A. GARY ANDERSON HALL 1 | ANDERSON 1 | CORE | 20P000115 | Fall 2019
0 | 20P000208 | [12 empty] | P5326 | COBALT 60 BUILDING #38 | COBALT 60 | CORE | 19P000502 | Fall 2019
0 | 20P000207 | [12 empty] | P5327 | PHYSICAL PLANT STORAGE UNIT 2 | PHYS PL STR2 | CORE | 20P000086 | Fall 2019
0 | 20P000206 | [12 empty] | P5328 | HAZARDOUS WASTE STORAGE UNIT 1 | HAZ WST STR1 | CORE | 20P000116 | Fall 2019
0 | 20P000205 | [12 empty] | P5329 | HAZARDOUS WASTE STORAGE UNIT 2 | HAZ WST STR2 | CORE | 20P000117 | Fall 2019
0 | 20P000204 | [12 empty] | P5330 | TRAILER #21 3984 | T21 3984 | CORE | 20P000118 | Fall 2019
0 | 20P000202 | [12 empty] | P5334 | ATHLETICS AND DANCE BUILDING | ATH DANCE | CORE | 19P000670 | Fall 2019
0 | 20P000200 | [12 empty] | P5335 | GEOLOGY BUILDING | GEOLOGY | CORE | 19P000687 | Fall 2019
0 | 20P000199 | [12 empty] | P5336 | GLASSHOUSE FIELD 16 #24A | GH 16 24A | CORE | 20P000067 | Fall 2019
0 | 20P000197 | [12 empty] | P5337 | GLASSHOUSE FIELD 16 #24B | GH 16 24B | CORE | 19P000413 | Fall 2019
0 | 20P000196 | [12 empty] | P5338 | GLASSHOUSE FIELD 16 #24C | GH 16 24C | CORE | 18P000343 | Spring 2018
0 | 20P000195 | [12 empty] | P5339 | GLASSHOUSE FIELD 16 #24D | GH 16 24D | CORE | 18P000453 | Summer 2018
0 | 20P000194 | [12 empty] | P5340 | PUMPHOUSE #2 | PUMP 2 | CORE | 19P000646 | Summer 2019
0 | 20P000193 | [12 empty] | P5341 | ALFRED M. BOYCE HALL | BOYCE | CORE | 19P000638 | Summer 2019
0 | 20P000192 | [12 empty] | P5342 | HERBERT JOHN WEBBER HALL | WEBBER | CORE | 19P000619 | Summer 2019
0 | 20P000189 | [12 empty] | P5343 | ABERDEEN-INVERNESS RESIDENCE HALL | ABER INVER | NON-CORE | 19P000337 | Summer 2019
0 | 20P000188 | [12 empty] | P5344 | GLASSHOUSE FIELD 16 #28 | GH 16 28 | CORE | 19P000575 | Summer 2019
0 | 20P000187 | [12 empty] | P5345 | ASBESTOS ABATEMENT & EMERGENCY RESPONSE EQUIP/SUPPLY | ABAT EMG RSP | NON-CORE | 19P000639 | Summer 2019
0 | 20P000185 | [12 empty] | P5346 | DECAY STORAGE UNIT 1 | DECAY STOR 1 | CORE | 19P000466 | Summer 2019
0 | 20P000184 | [12 empty] | P5347 | DECAY STORAGE UNIT 2 | DECAY STOR 2 | CORE | 19P000572 | Summer 2019
0 | 20P000183 | [12 empty] | P5348 | WAREHOUSE #2 | WHSE 2 | CORE | 19P000628 | Summer 2019
0 | 20P000175 | [12 empty] | P5349 | FARM GROUP E WAREHOUSE #1 | FARM E | CORE | 19P000414 | Summer 2019
0 | 20P000174 | [12 empty] | P5350 | GROWTH CHAMBER BUILDING | GRTH CH BLDG | CORE | 19P000473 | Summer 2019
0 | 20P000172 | [12 empty] | P5351 | ENTOMOLOGY POULTRY BUILDING | ENT PLTRY BD | CORE | 19P000521 | Summer 2019
0 | 20P000171 | [12 empty] | P5353 | INSECT LABORATORY #39 | INSECT 39 | CORE | 19P000553 | Summer 2019
0 | 20P000169 | [12 empty] | P5354 | GORDON S. WATKINS HALL | WATKINS | CORE | 19P000455 | Summer 2019
0 | 20P000163 | [12 empty] | P5355 | SCREENHOUSE BOTANY | SCRNHSE BOT | CORE | 19P000564 | Summer 2019
0 | 20P000162 | [12 empty] | P5356 | STORAGE SHED #6 | STOR 6 | CORE | 19P000621 | Summer 2019
0 | 20P000161 | [12 empty] | P5357 | A. GARY ANDERSON HALL 2 | ANDERSON 2 | CORE | 19P000571 | Summer 2019
0 | 20P000158 | [12 empty] | P5358 | THE BARN | BARN | NON-CORE | 19P000477 | Summer 2019
0 | 20P000157 | [12 empty] | P5359 | SUPERINTENDENT'S GARAGE | SUPERINT GAR | NON-CORE | 19P000643 | Summer 2019
0 | 20P000155 | [12 empty] | P5360 | SUPERINTENDENT'S COTTAGE | SUPERINT COT | NON-CORE | 19P000487 | Summer 2019
0 | 20P000152 | [12 empty] | P5361 | INSECT LABORATORY #44 | INSECT 44 | CORE | 19P000600 | Summer 2019
0 | 20P000151 | [12 empty] | P5363 | PLANT DRYING BUILDING | PLNT DRY BLD | CORE | 19P000419 | Summer 2019
0 | 20P000150 | [12 empty] | P5364 | CORPORATION YARD PHYSICAL PLANT WAREHOUSE | CORP PP WHSE | CORE | 19P000622 | Summer 2019
0 | 20P000149 | [12 empty] | P5365 | PENTLAND HILLS RESIDENCE HALL A | PENTLAND A | NON-CORE | 19P000665 | Summer 2019
0 | 20P000145 | [12 empty] | P5367 | SATELLITE CHILLER PLANT | SAT CHIL PL | CORE | 19P000434 | Summer 2019
0 | 20P000144 | [12 empty] | P5369 | PENTLAND HILLS RESIDENCE HALL | PENTLAND I | NON-CORE | 19P000495 | Summer 2019
0 | 20P000143 | [12 empty] | P5371 | GLASSHOUSE FIELD 16 #47 | GH 16 47 | CORE | 19P000534 | Summer 2019
0 | 20P000142 | [12 empty] | P5372 | CHASS INTERDISCIPLINARY SOUTH | CHASS INT S | CORE | 19P000597 | Summer 2019
0 | 20P000141 | [12 empty] | P5373 | PSYCHOLOGY BUILDING | PSYCHOLOGY1 | CORE | 19P000601 | Summer 2019
0 | 20P000140 | [12 empty] | P5374 | GREENHOUSE #1 RESEARCH | GH01 RESRCH | CORE | 19P000415 | Summer 2019
0 | 20P000135 | [12 empty] | P5375 | GLASSHOUSE FIELD 16 #48 | GH 16 48 | CORE | 19P000574 | Summer 2019
0 | 20P000129 | [12 empty] | P5376 | TRAILER CNAS (Surge Trailer) | T CNAS | CORE | 19P000539 | Summer 2019
0 | 20P000127 | [12 empty] | P5377 | SHED BUILDING TRACTOR | SHED TRACTOR | CORE | 19P000613 | Summer 2019
0 | 20P000121 | [12 empty] | P5378 | GREENHOUSE #2 RESEARCH | GH03 RESRCH | CORE | 19P000483 | Summer 2019
0 | 20P000120 | [12 empty] | P5380 | Skye Hall (Surge Hall) | SKYE HALL | CORE | 19P000625 | Summer 2019
0 | 20P000118 | [12 empty] | P5381 | COMPUTING & COMMUNICATIONS CENTER | ITS CENTER | CORE | 19P000609 | Summer 2019
0 | 20P000117 | [12 empty] | P5382 | COMPUTING & COMMUNICATIONS ELECTRIC CART CARPORT | ITS CARPORT | CORE | 19P000508 | Summer 2019
0 | 20P000116 | [12 empty] | P5383 | UNIVERSITY LECTURE HALL | UNIV LEC HAL | CORE | 19P000558 | Summer 2019
0 | 20P000115 | [12 empty] | P5385 | TRAILER BIOMEDICAL SCIENCES #1 | T BIOMED1 | CORE | 19P000421 | Summer 2019
0 | 20P000114 | [12 empty] | P5386 | EH&S TRIPLE WIDE TRAILER | T EH&S | CORE | 19P000615 | Summer 2019
0 | 20P000113 | [12 empty] | P5387 | VIVARIA TRAILER | T VIVARIA | CORE | 19P000526 | Summer 2019
0 | 20P000112 | [12 empty] | P5388 | ENVIRONMENTAL HEALTH AND SAFETY EXPANSION | ENV HLTHSFTY | CORE | 19P000642 | Summer 2019
0 | 20P000107 | [12 empty] | P5391 | BOTANIC GARDENS RESTROOM | BOTGDN RSTRM | NON-CORE | 19P000552 | Summer 2019
0 | 20P000105 | [12 empty] | P5393 | METEOROLOGICAL BUILDING | METEOR BLDG | CORE | 19P000589 | Summer 2019
0 | 20P000094 | [12 empty] | P5396 | UCR CHILD DEVELOPMENT SOUTH | CHILD DEV S | NON-CORE | 19P000448 | Summer 2019
0 | 20P000093 | [12 empty] | P5397 | SCHOOL OF EDUCATION CLINIC | EDUC CLINIC | CORE | 19P000620 | Summer 2019
0 | 20P000090 | [12 empty] | P5398 | PARKING TRAILER 1 | PARKING T1 | NON-CORE | 19P000429 | Summer 2019
1 | 20P000086 | [12 empty] | P5399 | PARKING TRAILER 2 | PARKING T2 | NON-CORE | 19P000540 | Summer 2019
0 | 20P000085 | [12 empty] | P5400 | PARKING TRAILER 3 | PARKING T3 | NON-CORE | 19P000608 | Summer 2019
0 | 20P000083 | [12 empty] | P5402 | Arabadopsis 1 | ARAB 1 | NON-CORE | 19P000560 | Summer 2019
0 | 20P000082 | [12 empty] | P5403 | CHASS INTERDISCIPLINARY NORTH | CHASS INT N | CORE | 19P000433 | Summer 2019
0 | 20P000081 | [12 empty] | P5404 | HIGHLANDER UNION BUILIDNG | HUB | NON-CORE | 19P000599 | Summer 2019
0 | 20P000077 | [12 empty] | P5405 | HIGHLANDER UNION COFFEE PAVILION | HUB COFFEE | NON-CORE | 19P000311 | Summer 2019
0 | 20P000075 | [12 empty] | P5406 | SCHOOL OF MEDICINE HEALTH SCIENCE RESEARCH BUILDING | SOM RSCH | CORE | 19P000377 | Summer 2019
0 | 20P000073 | [12 empty] | P5408 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16A | GH 16-54 ENT | CORE | 19P000645 | Summer 2019
0 | 20P000070 | [12 empty] | P5409 | STORAGE SHED #1 | STOR 1 | CORE | 19P000547 | Summer 2019
0 | 20P000068 | [12 empty] | P5410 | STORAGE SHED #2 | STOR 3 | CORE | 19P000555 | Summer 2019
0 | 20P000067 | [12 empty] | P5411 | ARTS BUILDING FINE ARTS SEISMIC FACILITY | ARTS | CORE | 19P000474 | Summer 2019
0 | 20P000065 | [12 empty] | P5412 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16B | GH 16-55 ENT | CORE | 19P000504 | Summer 2019
0 | 20P000061 | [12 empty] | P5413 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16C | GH 16-56 ENT | CORE | 19P000514 | Summer 2019
0 | 20P000060 | [12 empty] | P5414 | CHEMICAL SCIENCES | CHEMICAL SCI | CORE | 19P000543 | Summer 2019
0 | 20P000059 | [12 empty] | P5415 | CANYON CREST KIOSK | KIOSK 2 | NON-CORE | 19P000594 | Summer 2019
0 | 20P000054 | [12 empty] | P5416 | SCIENCE LABORATORIES 1 | SCIENCE LAB1 | CORE | 19P000407 | Summer 2019
0 | 20P000051 | [12 empty] | P5417 | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | ENTOMOLOGY | CORE | 18P000214 | Winter 2018
0 | 20P000047 | [12 empty] | P5418 | RAYMOND L. ORBACH SCIENCE LIBRARY | ORBACH LIB | CORE | 18P000198 | Winter 2018
0 | 20P000046 | [12 empty] | P5419 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16D | GH 16-57 ENT | CORE
0 | 20P000045 | [12 empty] | P5420 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16E | GH 16-58 ENT | CORE
0 | 20P000044 | [12 empty] | P5421 | BOTANIC GARDENS HOUSE | BOT GDN HSE | NON-CORE
0 | 20P000039 | [12 empty] | P5422 | GLASSHOUSE FIELD 8 AIR POLLUTION | GH5 | CORE
0 | 20P000038 | [12 empty] | P5423 | GLASSHOUSE FIELD 7 AIR POLLUTION | GH4 | CORE
0 | 20P000037 | [12 empty] | P5424 | LATHHOUSE #8 | LATH 8 | CORE
0 | 20P000036 | [12 empty] | P5425 | LATHHOUSE #3 | LATH 3 | CORE
0 | 20P000034 | [12 empty] | P5426 | HEADHOUSE STORAGE BUILDING | HH STOR | CORE
0 | 20P000031 | [12 empty] | P5427 | SOIL FACILITY BUILDING | SOIL BLDG | CORE
0 | 20P000029 | [12 empty] | P5428 | STORAGE BUILDING RADIOACTIVE MATERIAL | STOR RA | CORE
0 | 20P000028 | [12 empty] | P5430 | AGRICULTURE EXPERIMENT STATION STORAGE BUILDING | AES STOR | CORE
0 | 20P000026 | [12 empty] | P5434 | GLASSHOUSE FIELD 16 #50 | GH 16 50 | CORE
0 | 20P000024 | [12 empty] | P5435 | EHS STORAGE 1 | EHS STOR 1 | CORE
0 | 20P000023 | [12 empty] | P5436 | EHS STORAGE 2 | EHS STOR 2 | CORE
0 | 20P000019 | [12 empty] | P5437 | EHS STORAGE 3 | EHS STOR 3 | CORE
0 | 20P000017 | [12 empty] | P5438 | EHS STORAGE 4 | EHS STOR 4 | CORE
0 | 20P000008 | [12 empty] | P5439 | EHS STORAGE 5 | EHS STOR 5 | CORE
0 | 20P000005 | [12 empty] | P5440 | 4558 SANDANO STREET | 4558 SANDANO | NON-CORE
0 | 20P000004 | [12 empty] | P5441 | 4566 SANDANO STREET | 4566 SANDANO | NON-CORE
0 | 20P000003 | [12 empty] | P5442 | 1871 ESCALANTE WAY | 1871 ESCALAN | NON-CORE
0 | 20P000002 | [12 empty] | P5443 | 4531 SANDANO STREET | 4531 SANDANO | NON-CORE
0 | 19W007474 | [12 empty] | P5444 | 4522 SANDANO STREET | 4522 SANDANO | NON-CORE
0 | 19W003050 | [12 empty] | P5445 | 4538 SANDANO STREET | 4538 SANDANO | NON-CORE
0 | 19W003012 | [12 empty] | P5446 | POLICE TRAILER | POLICE TRLR | CORE
0 | 19W002930 | [12 empty] | P5449 | GENOMICS SHED | GENOM SHED | CORE
0 | 19W002419 | [12 empty] | P5451 | EDGEMOOR HOUSE | EDGEMOOR HSE | NON-CORE
0 | 19S000833 | [12 empty] | P5452 | EDGEMOOR GARAGE | EDGEMOOR GAR | NON-CORE
0 | 19P000688 | [12 empty] | P5453 | GARAGE COTTAGE #2 | GAR C2 | CORE
0 | 19P000687 | [12 empty] | P5455 | TRAILER CECERT 1 | T CECERT 1 | NON-CORE
0 | 19P000683 | [12 empty] | P5457 | PRINTING MODULAR | PRINT MOD | NON-CORE
0 | 19P000676 | [12 empty] | P5460 | WOODSHED | WOODSHED | CORE
0 | 19P000674 | [12 empty] | P5461 | FIELD LABORATORY | FLDLAB | CORE
0 | 19P000673 | [12 empty] | P5462 | TRAILER CECERT 2 | T CECERT 2 | NON-CORE
0 | 19P000670 | [12 empty] | P5464 | STORAGE SHED #2 | STOR 2 | CORE
0 | 19P000666 | [12 empty] | P5466 | BIO CONTROL CULTURE BUILDING REPLACEMENT | BIO CTRL BLD | CORE
0 | 19P000665 | [12 empty] | P5467 | RICHARD J HECKMANN INTL CENTER FOR ENTREPRENEURIAL MGMT | HECKMAN ICEM | NON-CORE
0 | 19P000664 | [12 empty] | P5468 | HECKMANN CENTER COMPLEX PH 2 | HECKMANN PH2 | NON-CORE
0 | 19P000662 | [12 empty] | P5469 | VERLEY BARN | VERLEY BARN | CORE
0 | 19P000661 | [12 empty] | P5470 | GLEN MOR HOUSING A | GLEN MOR A | NON-CORE
0 | 19P000660 | [12 empty] | P5471 | GLEN MOR HOUSING B | GLEN MOR B | NON-CORE
0 | 19P000659 | [12 empty] | P5472 | GLEN MOR HOUSING C1 | GLEN MOR C1 | NON-CORE
0 | 19P000658 | [12 empty] | P5473 | GLEN MOR HOUSING D | GLEN MOR D | NON-CORE
0 | 19P000657 | [12 empty] | P5474 | GLEN MOR HOUSING E | GLEN MOR E | NON-CORE
0 | 19P000647 | [12 empty] | P5475 | GLEN MOR HOUSING C2 | GLEN MOR C2 | NON-CORE
0 | 19P000646 | [12 empty] | P5476 | TRAILER ANTHROPOLOGY | T ANTHROP | CORE
0 | 19P000645 | [12 empty] | P5478 | GLASSHOUSE FIELD 3 AIR POLLUTION | GH AP FL2 | CORE
0 | 19P000643 | [12 empty] | P5479 | GLASSHOUSE FIELD 3 AIR POLLUTION | GH AP FL3 | CORE
0 | 19P000642 | [12 empty] | P5480 | IVAN HINDERAKER HALL | HINDERAKER | CORE
0 | 19P000640 | [12 empty] | P5481 | GREENHOUSE #14 | GH14 | CORE
0 | 19P000639 | [12 empty] | P5482 | PATRICK BOYDEN LABORATORY | BOYDEN LAB | CORE
0 | 19P000638 | [12 empty] | P5483 | GREENHOUSE #17 | GH17 | CORE
0 | 19P000628 | [12 empty] | P5484 | CORPORATION YARD D CAR SHELTER | CORP CAR SHD | CORE
0 | 19P000627 | [12 empty] | P5485 | CORPORATION YARD C | CORP C | CORE
0 | 19P000625 | [12 empty] | P5486 | CORPORATION YARD B | CORP B | CORE
0 | 19P000624 | [12 empty] | P5487 | CORPORATION YARD A | CORP A | CORE
0 | 19P000623 | [12 empty] | P5488 | CHANCELLOR'S RESIDENCE | CHANC HOUSE | NON-CORE
0 | 19P000622 | [12 empty] | P5489 | FARM A | FARM A | CORE
0 | 19P000621 | [12 empty] | P5490 | FARM B | FARM B | CORE
0 | 19P000620 | [12 empty] | P5491 | GARAGE 4 CAR | GARAGE 4 CAR | NON-CORE
0 | 19P000619 | [12 empty] | P5492 | SHED BUILDING FIELD 11A | SHED FLD 11A | CORE
0 | 19P000618 | [12 empty] | P5493 | TRAILER #14 | T14 | CORE
0 | 19P000617 | [12 empty] | P5495 | HEALTH SERVICE BUILDING | HEALTH SERV | CORE
0 | 19P000616 | [12 empty] | P5496 | PHYSICAL EDUCATION UTILITY BUILDING | PE UTIL BLDG | CORE
0 | 19P000615 | [12 empty] | P5497 | JOHN W. OLMSTED HALL | OLMSTED | CORE
0 | 19P000614 | [12 empty] | P5498 | HUMANITIES BUILDING | HUMANITIES | CORE
0 | 19P000613 | [12 empty] | P5499 | GLASSHOUSE FIELD 16 #21 | GH 16 21 | CORE
0 | 19P000609 | [12 empty] | P5500 | VEGETABLE CROPS STOREHOUSE | VEG CROP STR | CORE
0 | 19P000608 | [12 empty] | P5501 | LEON DEXTER BATCHELOR HALL | BATCHELOR | CORE
0 | 19P000607 | [12 empty] | P5502 | LOTHIAN RESIDENCE HALL | LOTHIAN HALL | NON-CORE
0 | 19P000606 | [12 empty] | P5503 | HOWARD SAMUEL FAWCETT LABORATORY | FAWCETT LAB | CORE
0 | 19P000605 | [12 empty] | P5504 | PHYSICS BUILDING | PHYSICS | CORE
0 | 19P000604 | [12 empty] | P5505 | GEODESIC DOME BOTANIC GARDENS | GEODESIC DM | CORE
0 | 19P000603 | [12 empty] | P5506 | COLD BOXES ROOF BUILDING | COLD BX ROOF | CORE
0 | 19P000602 | [12 empty] | P5507 | CUSTODIAL & GROUNDS BUILDING | CUST AND GRD | CORE
0 | 19P000601 | [12 empty] | P5508 | W. CONWAY PIERCE HALL | PIERCE | CORE
0 | 19P000600 | [12 empty] | P5509 | TRAILER #7 AIR POLLUTION | T7 AP | CORE
0 | 19P000599 | [12 empty] | P5511 | STUDENT RECREATION CENTER NORTH | SRC NORTH | NON-CORE
0 | 19P000597 | [12 empty] | P5513 | GREENHOUSE #18 | GH18 | CORE
0 | 19P000594 | [12 empty] | P5514 | GREENHOUSE #19 | GH19 | CORE
0 | 19P000589 | [12 empty] | P5515 | GREENHOUSE #20 | GH20 | CORE
0 | 19P000588 | [12 empty] | P5516 | GLASSHOUSE FIELD 15A #40 | GH 15A-40 | CORE
0 | 19P000585 | [12 empty] | P5517 | COLLEGE BUILDING NORTH | COLL BLDG NO | CORE
0 | 19P000575 | [12 empty] | P5518 | AGRICULTURE ENGINEERING SHOP | AG ENG SHOPS | CORE
0 | 19P000574 | [12 empty] | P5519 | GLASSHOUSE FIELD 15A #41 | GH 15A-41 | CORE
0 | 19P000573 | [12 empty] | P5520 | MIDGE CONTROL BUILDING | MIDGE CONTRL | CORE
0 | 19P000572 | [12 empty] | P5521 | STORAGE DOCK | STORAGE DOCK | CORE
0 | 19P000571 | [12 empty] | P5522 | GLASSHOUSE FIELD 15A #42 | GH 15A-42 | CORE
0 | 19P000568 | [12 empty] | P5523 | ROBERT GORDON SPROUL HALL | SPROUL | CORE
0 | 19P000565 | [12 empty] | P5524 | GLASSHOUSE FIELD 15A #43 | GH 15A-43 | CORE
0 | 19P000564 | [12 empty] | P5525 | HORTICULTURE GREENHOUSE D1 | GH 16 49 | CORE
0 | 19P000560 | [12 empty] | P5526 | HORTICULTURE GREENHOUSE D2 | GH 16 51 | CORE
0 | 19P000558 | [12 empty] | P5527 | HORTICULTURE GREENHOUSE D3 | GH 16 52 | CORE
0 | 19P000555 | [12 empty] | P5528 | LATHHOUSE LIFE SCIENCES EXPERIMENTAL AREA | LATH LS | CORE
0 | 19P000553 | [12 empty] | P5529 | GLASSHOUSE FIELD 15A #48 | GH 15A-48 | CORE
0 | 19P000552 | [12 empty] | P5530 | BELLTOWER | BELLTOWER | CORE
0 | 19P000547 | [12 empty] | P5531 | HORTICULTURE GREENHOUSE D4 | GH 16 53 | CORE
0 | 19P000543 | [12 empty] | P5532 | TELEPHONE BUILDING | TELEPHONE | CORE
0 | 19P000540 | [12 empty] | P5533 | CANYON CREST HOUSING 3458 AVOCADO AVENUE | CC AVOC 3458 | NON-CORE
0 | 19P000539 | [12 empty] | P5534 | MULTIPURPOSE BUILDING BOTANIC GARDEN | MULTI PURP | NON-CORE
0 | 19P000535 | [12 empty] | P5535 | LATHHOUSE B | LATH B | CORE
0 | 19P000534 | [12 empty] | P5539 | AGRONOMY FIELD HEADQUARTERS BUILDING | AGRON FLDHSE | CORE
0 | 19P000526 | [12 empty] | P5540 | GLASSHOUSE #1 PLASTIC COVERED | GH PLASTC 01 | CORE
0 | 19P000523 | [12 empty] | P5541 | GLASSHOUSE #2 PLASTIC COVERED | GH PLASTC 02 | CORE
0 | 19P000521 | [12 empty] | P5542 | GLASSHOUSE #3 PLASTIC COVERED FIELD 16 | GH PLA 16-03 | CORE
0 | 19P000517 | [12 empty] | P5543 | GLASSHOUSE #4 PLASTIC COVERED | GH PLASTC 04 | CORE
0 | 19P000514 | [12 empty] | P5544 | GLASSHOUSE #5 PLASTIC COVERED | GH PLASTC 05 | CORE
0 | 19P000508 | [12 empty] | P5545 | GLASSHOUSE #6 PLASTIC COVERED | GH PLASTC 06 | CORE
0 | 19P000505 | [12 empty] | P5546 | GLASSHOUSE #7 PLASTIC COVERED | GH PLASTC 07 | CORE
0 | 19P000504 | [12 empty] | P5547 | GLASSHOUSE #8 PLASTIC COVERED | GH PLASTC 08 | CORE
0 | 19P000502 | [12 empty] | P5548 | AGRICULTURAL OPERATIONS STORAGE SHED #9 | AGOPS SHED 9 | CORE
0 | 19P000495 | [12 empty] | P5549 | BOTANY & PLANT SCIENCE STORAGE FACILITY | BOT STOR 8C | NON-CORE
0 | 19P000487 | [12 empty] | P5550 | GLASSHOUSE #51 | GH 51 | CORE
0 | 19P000485 | [12 empty] | P5551 | GLASSHOUSE FIELD 16 #30 | GH 16 30 | CORE
0 | 19P000483 | [12 empty] | P5552 | GLASSHOUSE FIELD 16 #29 | GH 16 29 | CORE
0 | 19P000482 | [12 empty] | P5553 | GLASSHOUSE #52 | GH 52 | CORE
0 | 19P000477 | [12 empty] | P5554 | ENTOMOLOGY FUMIGATOR | ENT FUMIGATR | CORE
0 | 19P000474 | [12 empty] | P5559 | TRAILER PHYSICAL PLANT | T PHYS PLANT | CORE
0 | 19P000473 | [12 empty] | P5561 | BIOMEDICAL SCIENCES UNIT 2 TRAILER | T BIOMED2 | CORE
0 | 19P000467 | [12 empty] | P5562 | BOTANY & PLANT SCIENCE GREENHOUSE-POLY | GH BOT POLY | CORE
0 | 19P000466 | [12 empty] | P5564 | KIOSK/INFORMATION BOOTH | KIOSK | NON-CORE
0 | 19P000458 | [12 empty] | P5565 | GREENHOUSE BOTANIC GARDENS | GH BOT GDNS | NON-CORE
0 | 19P000455 | [12 empty] | P5566 | POLICE BUILDING | POLICE BLDG | CORE
0 | 19P000453 | [12 empty] | P5567 | GLASSHOUSE FIELD 16 #20 | GH 16 20 | CORE
0 | 19P000451 | [12 empty] | P5568 | HEADHOUSE BOTANIC GARDENS | HHSE BOT GDN | CORE
0 | 19P000449 | [12 empty] | P5571 | METAL RESEARCH BUILDING | METAL RSHBLD | CORE
0 | 19P000448 | [12 empty] | P5573 | CONTROL TEMPERATURE STRUCTURE | CONTROL TEMP | NON-CORE
0 | 19P000445 | [12 empty] | P5575 | STORED PRODUCTS TEST BUILDING | STOR PR TEST | CORE
0 | 19P000442 | [12 empty] | P5579 | PUMPHOUSE #4 | PUMP 4 | CORE
0 | 19P000440 | [12 empty] | P5581 | HOUSING ADMINISTRATION | HOUSING ADM | NON-CORE
0 | 19P000439 | [12 empty] | P5582 | VOLATILE LIQUID STORAGE BUILDING | VOLA LIQ STG | CORE
0 | 19P000438 | [12 empty] | P5583 | GLASSHOUSE #16 PLASTIC COVERED | GH PLASTC 16 | CORE
0 | 19P000435 | [12 empty] | P5584 | GLASSHOUSE #14 PLASTIC COVERED | GH PLASTC 14 | CORE
0 | 19P000434 | [12 empty] | P5585 | GLASSHOUSE #13 PLASTIC COVERED | GH PLASTC 13 | CORE
0 | 19P000433 | [12 empty] | P5586 | GLASSHOUSE #12 PLASTIC COVERED | GH PLASTC 12 | CORE
0 | 19P000431 | [12 empty] | P5587 | GLASSHOUSE #15 PLASTIC COVERED | GH PLASTC 15 | CORE
0 | 19P000429 | [12 empty] | P5588 | SCHOOL OF MEDICINE - EDUCATION BUILDING | SOM EDUC | CORE
0 | 19P000428 | [12 empty] | P5589 | CORPORATION YARD COMPRESSED GAS STORAGE BUILDING | CORP GAS STG | CORE
0 | 19P000427 | [12 empty] | P5590 | BANNOCKBURN VILLAGE BLDG A | BANNOCK A | NON-CORE
0 | 19P000425 | [12 empty] | P5591 | BANNOCKBURN VILLAGE BLDG B | BANNOCK B | NON-CORE
0 | 19P000424 | [12 empty] | P5592 | BANNOCKBURN VILLAGE BLDG C | BANNOCK C | NON-CORE
0 | 19P000421 | [12 empty] | P5593 | BANNOCKBURN VILLAGE BLDG D | BANNOCK D | NON-CORE
0 | 19P000420 | [12 empty] | P5594 | BANNOCKBURN VILLAGE BLDG E | BANNOCK E | NON-CORE
0 | 19P000419 | [12 empty] | P5595 | BANNOCKBURN VILLAGE BLDG F | BANNOCK F | NON-CORE
0 | 19P000417 | [12 empty] | P5596 | BANNOCKBURN VILLAGE BLDG G | BANNOCK G | NON-CORE
0 | 19P000414 | [12 empty] | P5597 | BANNOCKBURN VILLAGE BLDG H | BANNOCK H | NON-CORE
0 | 19P000413 | [12 empty] | P5598 | BANNOCKBURN VILLAGE BLDG I | BANNOCK I | NON-CORE
0 | 19P000411 | [12 empty] | P5599 | BANNOCKBURN VILLAGE BLDG J | BANNOCK J | NON-CORE
0 | 19P000410 | [12 empty] | P5600 | BANNOCKBURN VILLAGE BLDG K | BANNOCK K | NON-CORE
0 | 19P000408 | [12 empty] | P5601 | BANNOCKBURN VILLAGE BLDG L | BANNOCK L | NON-CORE
0 | 19P000407 | [12 empty] | P5602 | BANNOCKBURN VILLAGE BLDG M | BANNOCK M | NON-CORE
0 | 19P000405 | [12 empty] | P5603 | BANNOCKBURN VILLAGE BLDG N | BANNOCK N | NON-CORE
0 | 19P000401 | [12 empty] | P5604 | BANNOCKBURN VILLAGE BLDG O | BANNOCK O | NON-CORE
0 | 19P000400 | [12 empty] | P5605 | BANNOCKBURN VILLAGE BLDG P | BANNOCK P | NON-CORE
0 | 19P000399 | [12 empty] | P5606 | BANNOCKBURN VILLAGE BLDG Q | BANNOCK Q | NON-CORE
0 | 19P000396 | [12 empty] | P5607 | BANNOCKBURN VILLAGE BLDG R | BANNOCK R | NON-CORE
0 | 19P000390 | [12 empty] | P5608 | BANNOCKBURN VILLAGE BLDG S | BANNOCK S | NON-CORE
0 | 19P000388 | [12 empty] | P5609 | BANNOCKBURN VILLAGE BLDG T | BANNOCK T | NON-CORE
0 | 19P000386 | [12 empty] | P5610 | BANNOCKBURN VILLAGE BLDG U | BANNOCK U | NON-CORE
0 | 19P000384 | [12 empty] | P5611 | BANNOCKBURN VILLAGE BLDG V | BANNOCK V | NON-CORE
0 | 19P000380 | [12 empty] | P5614 | STUDENT SUPPORT SERVICES BUILDING | STUDENT SERV | CORE
0 | 19P000378 | [12 empty] | P5616 | SCHOOL OF MEDICINE DINING FACILITY | SOM DINING | CORE
0 | 19P000377 | [12 empty] | P5620 | 5029 MONACHELLO LANE | 5029 MONACHE | NON-CORE
0 | 19P000375 | [12 empty] | P5621 | 5037 MONACHELLO LANE | 5037 MONACHE | NON-CORE
0 | 19P000373 | [12 empty] | P5622 | 5045 MONACHELLO LANE | 5045 MONACHE | NON-CORE
0 | 19P000371 | [12 empty] | P5623 | 1670 OROBLANCO AVE | 1670 OROBLAN | NON-CORE
0 | 19P000370 | [12 empty] | P5624 | 1654 OROBLANCO AVE | 1654 OROBLAN | NON-CORE
0 | 19P000369 | [12 empty] | P5625 | 1640 OROBLANCO AVE | 1640 OROBLAN | NON-CORE
0 | 19P000367 | [12 empty] | P5626 | 1626 OROBLANCO AVE | 1626 OROBLAN | NON-CORE
0 | 19P000364 | [12 empty] | P5628 | 1606 OROBLANCO AVE | 1606 OROBLAN | NON-CORE
0 | 19P000362 | [12 empty] | P5629 | 1598 OROBLANCO AVE | 1598 OROBLAN | NON-CORE
0 | 19P000361 | [12 empty] | P5630 | 1590 OROBLANCO AVE | 1590 OROBLAN | NON-CORE
0 | 19P000360 | [12 empty] | P5631 | 1582 OROBLANCO AVE | 1582 OROBLAN | NON-CORE
0 | 19P000358 | [12 empty] | P5632 | 5141 PIXIE WAY | 5141 PIXIE | NON-CORE
0 | 19P000357 | [12 empty] | P5633 | 5133 PIXIE WAY | 5133 PIXIE | NON-CORE
0 | 19P000356 | [12 empty] | P5634 | 5125 PIXIE WAY | 5125 PIXIE | NON-CORE
0 | 19P000355 | [12 empty] | P5636 | PENTLAND HILLS RESIDENCE HALL BC | PENTLAND BC | NON-CORE
0 | 19P000354 | [12 empty] | P5637 | PENTLAND HILLS RESIDENCE HALL D | PENTLAND D | NON-CORE
0 | 19P000353 | [12 empty] | P5638 | PENTLAND HILLS RESIDENCE HALL E | PENTLAND E | NON-CORE
0 | 19P000350 | [12 empty] | P5639 | PENTLAND HILLS RESIDENCE HALL FG | PENTLAND FG | NON-CORE
0 | 19P000347 | [12 empty] | P5640 | PENTLAND HILLS RESIDENCE HALL H | PENTLAND H | NON-CORE
0 | 19P000346 | [12 empty] | P5641 | PENTLAND HILLS RESIDENCE HALL J | PENTLAND J | NON-CORE
0 | 19P000341 | [12 empty] | P5642 | PENTLAND HILLS RESIDENCE HALL K | PENTLAND K | NON-CORE
0 | 19P000340 | [12 empty] | P5643 | PENTLAND HILLS RESIDENCE HALL L | PENTLAND L | NON-CORE
0 | 19P000337 | [12 empty] | P5644 | PENTLAND HILLS RESIDENCE HALL M | PENTLAND M | NON-CORE
0 | 19P000326 | [12 empty] | P5645 | PENTLAND HILLS RESIDENCE HALL N | PENTLAND N | NON-CORE
0 | 19P000324 | [12 empty] | P5646 | PENTLAND HILLS RESIDENCE HALL O | PENTLAND O | NON-CORE
0 | 19P000322 | [12 empty] | P5647 | PENTLAND HILLS RESIDENCE HALL P | PENTLAND P | NON-CORE
0 | 19P000319 | [12 empty] | P5648 | PENTLAND HILLS RESIDENCE HALL Q | PENTLAND Q | NON-CORE
0 | 19P000318 | [12 empty] | P5649 | 5117 PIXIE WAY | 5117 PIXIE | NON-CORE
0 | 19P000317 | [12 empty] | P5650 | 5109 PIXIE WAY | 5109 PIXIE | NON-CORE
0 | 19P000316 | [12 empty] | P5651 | 5108 PIXIE WAY | 5108 PIXIE | NON-CORE
0 | 19P000314 | [12 empty] | P5652 | 5116 PIXIE WAY | 5116 PIXIE | NON-CORE
0 | 19P000313 | [12 empty] | P5653 | 5124 PIXIE WAY | 5124 PIXIE | NON-CORE
0 | 19P000312 | [12 empty] | P5654 | 5132 PIXIE WAY | 5132 PIXIE | NON-CORE
0 | 19P000311 | [12 empty] | P5655 | 1531 OROBLANCO AVE | 1531 OROBLAN | NON-CORE
0 | 19P000309 | [12 empty] | P5657 | 1563 OROBLANCO AVE | 1563 OROBLAN | NON-CORE
0 | 19P000308 | [12 empty] | P5658 | 1571 OROBLANCO AVE | 1571 OROBLAN | NON-CORE
0 | 19P000307 | [12 empty] | P5659 | 1579 OROBLANCO AVE | 1579 OROBLAN | NON-CORE
0 | 19P000306 | [12 empty] | P5660 | 1595 OROBLANCO AVE | 1595 OROBLAN | NON-CORE
0 | 19P000301 | [12 empty] | P5661 | OBAN APARTMENTS BLDG A | OBAN APTS A | NON-CORE
0 | 19P000300 | [12 empty] | P5662 | OBAN APARTMENTS BLDG B | OBAN APTS B | NON-CORE
0 | 19P000299 | [12 empty] | P5663 | OBAN APARTMENTS BLDG C | OBAN APTS C | NON-CORE
0 | 19P000298 | [12 empty] | P5664 | OBAN APARTMENTS BLDG D | OBAN APTS D | NON-CORE
0 | 19P000296 | [12 empty] | P5665 | OBAN APARTMENTS BLDG E | OBAN APTS E | NON-CORE
0 | 19P000295 | [12 empty] | P5666 | OBAN APARTMENTS BLDG F | OBAN APTS F | NON-CORE
0 | 19P000293 | [12 empty] | P5667 | OBAN APARTMENTS BLDG G | OBAN APTS G | NON-CORE
0 | 19P000292 | [12 empty] | P5668 | OBAN APARTMENTS BLDG H | OBAN APTS H | NON-CORE
0 | 19P000291 | [12 empty] | P5669 | OBAN APARTMENTS BLDG J | OBAN APTS J | NON-CORE
0 | 19P000288 | [12 empty] | P5670 | OBAN APARTMENTS OFFICE BLDG | OBAN OFFICE | NON-CORE
0 | 19P000287 | [12 empty] | P5671 | FALKIRK APARTMENTS 1 | FALKIRK 1 | NON-CORE
0 | 19P000286 | [12 empty] | P5672 | FALKIRK APARTMENTS 2 | FALKIRK 2 | NON-CORE
0 | 19P000285 | [12 empty] | P5673 | FALKIRK APARTMENTS 3 | FALKIRK 3 | NON-CORE
0 | 19P000284 | [12 empty] | P5674 | FALKIRK APARTMENTS 4 | FALKIRK 4 | NON-CORE
0 | 19P000283 | [12 empty] | P5675 | FALKIRK APARTMENTS 5 | FALKIRK 5 | NON-CORE
0 | 19P000280 | [12 empty] | P5676 | FALKIRK APARTMENTS 6 | FALKIRK 6 | NON-CORE
0 | 19P000278 | [12 empty] | P5677 | FALKIRK APARTMENTS 7 | FALKIRK 7 | NON-CORE
0 | 19P000277 | [12 empty] | P5678 | FALKIRK APARTMENTS 8 | FALKIRK 8 | NON-CORE
0 | 19P000276 | [12 empty] | P5679 | FALKIRK APARTMENTS 9 | FALKIRK 9 | NON-CORE
0 | 19P000275 | [12 empty] | P5680 | FALKIRK APARTMENTS 10 | FALKIRK 10 | NON-CORE
0 | 19P000274 | [12 empty] | P5681 | FALKIRK APARTMENTS 11 | FALKIRK 11 | NON-CORE
0 | 19P000273 | [12 empty] | P5682 | FALKIRK APARTMENTS 12 | FALKIRK 12 | NON-CORE
0 | 19P000272 | [12 empty] | P5683 | FALKIRK APARTMENTS 13 | FALKIRK 13 | NON-CORE
0 | 19P000271 | [12 empty] | P5684 | FALKIRK APARTMENTS 14 | FALKIRK 14 | NON-CORE
0 | 19P000270 | [12 empty] | P5685 | FALKIRK APARTMENTS 15 | FALKIRK 15 | NON-CORE
0 | 19P000269 | [12 empty] | P5686 | FALKIRK APARTMENTS 16 | FALKIRK 16 | NON-CORE
0 | 19P000268 | [12 empty] | P5687 | FALKIRK APARTMENTS 17 | FALKIRK 17 | NON-CORE
0 | 19P000266 | [12 empty] | P5688 | FALKIRK APARTMENTS 18 | FALKIRK 18 | NON-CORE
0 | 19P000265 | [12 empty] | P5689 | FALKIRK APARTMENTS 19 | FALKIRK 19 | NON-CORE
0 | 19P000263 | [12 empty] | P5690 | FALKIRK APARTMENTS LR1 | FALKIRK LR1 | NON-CORE
0 | 19P000256 | [12 empty] | P5691 | FALKIRK APARTMENTS LR2 | FALKIRK LR2 | NON-CORE
0 | 19P000255 | [12 empty] | P5692 | FALKIRK APARTMENTS LR3 | FALKIRK LR3 | NON-CORE
0 | 19P000253 | [12 empty] | P5693 | FALKIRK APARTMENTS OFFICE | FALKIRK OFF | NON-CORE
0 | 19P000252 | [12 empty] | P5694 | FALKIRK APARTMENTS MOD | FALKIRK MOD | NON-CORE
0 | 19P000251 | [12 empty] | P5695 | STUDENT RECREATION CENTER SOUTH | SRC SOUTH | NON-CORE
0 | 19P000250 | [12 empty] | P5696 | STUDENT RECREATION CENTER POOL EQUIPMENT BUILDING | SRC POOLBLDG | NON-CORE
0 | 19P000249 | [12 empty] | P5698 | UCR BUILDING | UCR BUILDING
0 | 19P000248 | [12 empty] | P5699 | OP BUILDING | OP BUILDING
0 | 19P000247 | [12 empty] | P5704 | GLASSHOUSE FIELD 15 #35 | GH 15-35 | CORE
0 | 19P000246 | [12 empty] | P5705 | PRESS BOX | PRESS BOX | NON-CORE
0 | 19P000245 | [12 empty] | P5706 | CONSTRUCTION TRAILER | T CONSTRUCT | CORE
0 | 19P000244 | [12 empty] | P5708 | DELFINO FAMILY PLANT LABORATORY | DELFINO HHSE | CORE
0 | 19P000243 | [12 empty] | P5709 | RUBIDOUX SOIL HOUSE 1 | RUBID SOIL 1 | NON-CORE
0 | 19P000242 | [12 empty] | P5710 | RUBIDOUX GREENHOUSE | RUBIDOUX GRH | CORE
0 | 19P000241 | [12 empty] | P5711 | RUBIDOUX QUARANTINE FACILITY | RUBIDOUX QUA | CORE
0 | 19P000238 | [12 empty] | P5712 | RUBIDOUX SCREENHOUSE | RUBIDOUX SCR | CORE
0 | 19P000237 | [12 empty] | P5713 | RUBIDOUX LABORATORY #2 | RUBIDOX LAB2 | CORE
0 | 19P000236 | [12 empty] | P5714 | RUBIDOUX LABORATORY #1 | RUBIDOUX LAB | CORE
0 | 19P000235 | [12 empty] | P5715 | THE PLAZA APARTMENTS | THE PLAZA | NON-CORE
0 | 19P000234 | [12 empty] | P5717 | 2100 ATLANTA AVENUE RIVERSIDE | ATLANTA | CORE
0 | 19P000233 | [12 empty] | P5718 | MOURADICK FARM LABORATORY BUILDING | MOURADK LAB | CORE
0 | 19P000232 | [12 empty] | P5719 | MOURADICK FARM SHOP BUILDING | MOURADK SHOP | CORE
0 | 19P000231 | [12 empty] | P5720 | CALIFORNIA MUSEUM OF PHOTOGRAPHY BUILDING | CA MUS PHOTO | CORE
0 | 19P000230 | [12 empty] | P5721 | RUBIDOUX GARAGE | RUBIDOUX GAR | CORE
0 | 19P000229 | [12 empty] | P5722 | UC RIVERSIDE UNIVERSITY EXTENSION CENTER | UCR EXTEN CT | NON-CORE
0 | 19P000227 | [12 empty] | P5724 | TRAILER PLANT PATH2 | T PLNT PATH2 | CORE
0 | 19P000226 | [12 empty] | P5725 | PHILIP BOYD DEEP CANYON RESERVE RESEARCH LAB | DC RES LAB | NON-CORE
0 | 19P000225 | [12 empty] | P5726 | PHILIP BOYD DEEP CANYON RESERVE ADMIN BLDG | DC ADMIN BLD | NON-CORE
0 | 19P000224 | [12 empty] | P5727 | PHILIP BOYD DEEP CANYON RESERVE CAR PORT | DC CAR PORT | NON-CORE
0 | 19P000222 | [12 empty] | P5728 | PHILIP BOYD DEEP CANYON RESERVE RESIDENCE | DC RESIDENCE | NON-CORE
0 | 19P000221 | [12 empty] | P5729 | MOTTE RIMROCK RESERVE RESIDENCE | MOTTE RESDNC | NON-CORE
0 | 19P000220 | [12 empty] | P5730 | GRANITE MOUNTAIN RESERVE DORNERS CAMP CHATEAU | GR MT DORNER | NON-CORE
0 | 19P000217 | [12 empty] | P5731 | DEEP CANYON COTTAGE/OFFICE/STORAGE | DC COTTAGE | NON-CORE
0 | 19P000216 | [12 empty] | P5732 | PHILIP BOYD DEEP CANYON RESERVE WILBUR MAYHEW BLDG | DC MAYHEW BL | NON-CORE
0 | 19P000215 | [12 empty] | P5733 | SIBYL & AL ALLANSON CENTER LABORATORY | GM ALLAN LAB | NON-CORE
0 | 19P000214 | [12 empty] | P5734 | SIBYL & AL ALLANSON CENTER RESEARCHER CABIN | GM ALLAN CAB | NON-CORE
0 | 19P000213 | [12 empty] | P5735 | SIBYL & AL ALLANSON CENTER EAST RESEARCHER CABIN | GM ALLAN ECB | NON-CORE
0 | 19P000212 | [12 empty] | P5736 | SIBYL & AL ALLANSON CENTER WEST RESEARCHER CABIN | GM ALLAN WCB | NON-CORE
0 | 19P000211 | [12 empty] | P5737 | T PLANT PATH3 | T PLNT PATH3 | CORE
0 | 19P000210 | [12 empty] | P5739 | EMERSON OAKS RESERVE RESTROOM | EMERSON RR | CORE
0 | 19P000209 | [12 empty] | P5740 | GRANITE MOUNTAIN BIN 1 | GR MT BIN 1 | NON-CORE
0 | 19P000208 | [12 empty] | P5741 | GRANITE MOUNTAIN BIN 2 | GR MT BIN 2 | NON-CORE
0 | 19P000207 | [12 empty] | P5742 | GRANITE MOUNTAIN BIN 3 | GR MT BIN 3 | NON-CORE
0 | 19P000205 | [12 empty] | P5743 | GRANITE MOUNTAIN ROLL-UP BIN | GR MT ROLLUP | NON-CORE
0 | 19P000201 | [12 empty] | P5744 | GRANITE MOUNTAIN STAPLES-ICE HOUSE (HISTORIC) | GR MT ICEHSE | NON-CORE
0 | 19P000197 | [12 empty] | P5745 | GRANITE MOUNTAIN TACK HOUSE | GR MT TACK | NON-CORE
0 | 19P000196 | [12 empty] | P5746 | GRANITE MOUNTAIN WORKSHOP | GR MT SHOP | NON-CORE
0 | 19P000195 | [12 empty] | P5747 | GRANITE MOUNTAIN ALLANSON CENTER RESEARCH CABIN | GM ALLAN ICB | NON-CORE
0 | 19P000194 | [12 empty] | P5748 | GRANITE MOUNTAIN ALLANSON CENTER MEETING/STUDY ROOM | GM ALLAN MR | NON-CORE
0 | 19P000193 | [12 empty] | P5749 | GRANITE MOUNTAIN ALLANSON CENTER BIN | GM ALLAN BIN | NON-CORE
0 | 19P000192 | [12 empty] | P5750 | MOTTE SHED 4 | MOTTE SHED 4 | NON-CORE
0 | 19P000191 | [12 empty] | P5751 | BOYD DEEP CANYON SHOP | DC SHOP | NON-CORE
0 | 19P000189 | [12 empty] | P5753 | MOTTE-RIMROCK RESERVE SHED #1 | MOTTE SHED 1 | NON-CORE
0 | 19P000188 | [12 empty] | P5754 | MOTTE-RIMROCK RESERVE SHED #2 | MOTTE SHED 2 | NON-CORE
0 | 19P000186 | [12 empty] | P5755 | MOTTE-RIMROCK RESERVE SHED #3 | MOTTE SHED 3 | NON-CORE
0 | 19P000185 | [12 empty] | P5757 | CULVER CENTER FOR THE ARTS | CULVER ROUSE | CORE
0 | 19P000184 | [12 empty] | P5779 | GRANITE MOUNTAIN RESEARCH TRAILER | GR MT RS TR | NON-CORE
0 | 19P000181 | [12 empty] | P5781 | JAMES SAN JACINTO MTN RESERVE LOLOMI LODGE | JR LOLOMI LG | NON-CORE
0 | 19P000176 | [12 empty] | P5782 | JAMES SAN JACINTO MTN RESERVE GARAGE | JAMES R GARG | NON-CORE
0 | 19P000175 | [12 empty] | P5784 | JAMES SAN JACINTO MTN RESERVE TRAILFINDERS LODGE | JR TRAIL FLG | NON-CORE
0 | 19P000174 | [12 empty] | P5785 | GRANITE MOUNTAIN RESEARCH TRAILER | GR MT RES TR | NON-CORE
0 | 19P000173 | [12 empty] | P5786 | GRANITE MOUNTAIN RESERVE STAPLES RANCH HOUSE | GR MT STAPLE | NON-CORE
0 | 19P000172 | [12 empty] | P5787 | GRANITE MOUNTAIN RESERVE RESIDENCE | GR MT RESIDN | NON-CORE
0 | 19P000171 | [12 empty] | P5788 | HUMAN RESOURCES | HUMAN RSOURC | CORE
0 | 19P000170 | [12 empty] | P5789 | DEEP CANYON AGARE HILL RESEARCH BEDROOM | DC AGARE | NON-CORE
0 | 19P000137 | [12 empty] | P5799 | GRANITE MOUNTAIN RESIDENCE 2 | GR MT RESID2 | NON-CORE
0 | 19P000133 | [12 empty] | P5801 | JR EQUIPMENT SHED 1 | JR SHED 1 | NON-CORE
0 | 19P000129 | [12 empty] | P5802 | JR EQUIPMENT SHED 2 | JR SHED 2 | NON-CORE
0 | 19P000127 | [12 empty] | P5804 | EMERSON MAIN RESIDENCE | EMERSON RES | NON-CORE
0 | 19P000126 | [12 empty] | P5805 | JAMES SAN JACINTO RESERVE CABIN | JR CABIN | NON-CORE
0 | 19P000124 | [12 empty] | P5806 | MOTTE-RIMROCK RESERVE SHOP | MOTTE SHOP | NON-CORE
0 | 19P000122 | [12 empty] | P5807 | JAMES RESERVE CLASSROOM | JR CLASSROOM | NON-CORE
0 | 19P000106 | [12 empty] | P5808 | JAMES RESERVE CABIN C | JR CABIN C | NON-CORE
0 | 19P000102 | [12 empty] | P5809 | JAMES RESERVE CABIN B | JR CABIN B | NON-CORE
0 | 19P000063 | [12 empty] | P5810 | JAMES RESERVE CABIN A | JR CABIN A | NON-CORE
0 | 19P000062 | [12 empty] | P5817 | LATHHOUSE 4 | LATHHOUSE 4 | NON-CORE
0 | 19P000061 | [12 empty] | P5820 | FMRI | FMRI | CORE
0 | 19P000060 | [12 empty] | P5821 | SOLAR GREENHOUSE | SOLAR GREENH | NON-CORE
0 | 19P000059 | [12 empty] | P5825 | SCHOOL OF MEDICINE TRAILER | T MEDICINE | NON-CORE
0 | 19P000058 | [12 empty] | P5829 | 4125 WATKINS DRIVE | 4125 WATKINS | NON-CORE
0 | 19P000056 | [12 empty] | P5900 | UNIVERSITY VILLAGE BUILDING E | UV BLDG E | NON-CORE
0 | 19P000055 | [12 empty] | P5901 | 1935 CHICAGO AVENUE | 1935 CHICAGO | NON-CORE
0 | 19P000054 | [12 empty] | P5905 | 555 E TACHEVAH | 555 TACHEVAH | NON-CORE
0 | 19P000053 | [12 empty] | P5906 | CE-CERT CHASSIS DYNAMOMETER FACILITY | DYNAMOMETER | CORE
0 | 19P000049 | [12 empty] | P5912 | TRAILER STUDENT HEALTH | T STU HEALTH | CORE
0 | 19P000046 | [12 empty] | P5913 | 1190 COLUMBIA CE-CERT LEASE | 1190COLUMBIA | NON-CORE
0 | 19P000045 | [12 empty] | P5914 | EL MIRADOR MEDICAL PLAZA | EL MIRADOR | NON-CORE
0 | 19P000044 | [12 empty] | P5915 | 1111 CITRUS STREET | 1111 CITRUS | NON-CORE
0 | 19P000043 | [12 empty] | P5916 | UNIVERSITY VILLAGE BUILDING B | UV BLDG B | NON-CORE
0 | 19P000042 | [12 empty] | P5917 | INTELLICENTER - UC PATH | INTELLICTR | NON-CORE
0 | 19P000037 | [12 empty] | P5918 | 4510 BROCKTON AVENUE | 4510BROCKTON | NON-CORE
0 | 19P000035 | [12 empty] | P5919 | 1955 CHICAGO AVENUE | 1955 CHICAGO | NON-CORE
0 | 19P000033 | [12 empty] | P5920 | FROST STUDIO | FROST STUDIO | NON-CORE
0 | 19P000032 | [12 empty] | P5921 | 266 FROST COURT MAIN HOUSE | 266 FROST HOUSE | NON-CORE
0 | 19P000031 | [12 empty] | P5922 | FROST APT | FROST APT | NON-CORE
0 | 19P000030 | [12 empty] | P5923 | FROST GARAGE | FROST GARAGE | NON-CORE
0 | 19P000029 | [12 empty] | P5924 | FROST SHED 1 | FROST SHED 1 | NON-CORE
0 | 19P000028 | [12 empty] | P5925 | FROST LAUND | FROST LAUND | NON-CORE
0 | 19P000027 | [12 empty] | P5926 | FROST SHED 2 | FROST SHED 2 | NON-CORE
0 | 19P000026 | [12 empty] | P5927 | FROST BARN | FROST BARN | NON-CORE
0 | 19P000023 | [12 empty] | P5928 | 285 FROST CT | 285 FROST CT | NON-CORE
0 | 19P000022 | [12 empty] | P5930 | 286 FROST COURT | 286 FROST | NON-CORE
0 | 19P000021 | [12 empty] | P5932 | CITRUS TOWER | CITRUS TOWER | NON-CORE
0 | 19P000018 | [12 empty] | P5933 | PROGENCY PSYCHIATRIC GROUP | PROGENCY | NON-CORE
0 | 19P000017 | [12 empty] | P5934 | ORANGE COUNTY PSYCHIATRY | 18881 VONKAR | NON-CORE
0 | 19P000015 | [12 empty] | P5935 | SILVER OAKS WOMENS HEALTH | 19330 JESSE | NON-CORE
0 | 19P000014 | [12 empty] | P5936 | EVANS PARK NEUROLOGY | 4500BROCKTON | NON-CORE
0 | 19P000012 | [12 empty] | P5937 | APPLE VALLEY NEUROSURGERY | 16143KOKANEE | NON-CORE
0 | 19P000011 | [12 empty] | P5938 | 3333 14TH ST | 3333 14th ST | NON-CORE
0 | 19P000009 | [12 empty] | P5950 | GLEN MOR F | GLEN MOR F | NON-CORE
0 | 19P000006 | [12 empty] | P5951 | GLEN MOR G | GLEN MOR G | NON-CORE
0 | 18W016621 | [12 empty] | P5952 | GLEN MOR H | GLEN MOR H | NON-CORE
0 | 18W016588 | [12 empty] | P5953 | GLEN MOR I | GLEN MOR I | NON-CORE
0 | 18W015691 | [12 empty] | P5954 | GLEN MOR J | GLEN MOR J | NON-CORE
0 | 18W013973 | [12 empty] | P5955 | GLEN MOR K | GLEN MOR K | NON-CORE
0 | 18W013160 | [12 empty] | P5956 | GLEN MOR L | GLEN MOR L | NON-CORE
0 | 18W011772 | [12 empty] | P5957 | GLEN MOR M | GLEN MOR M | NON-CORE
0 | 18W011692 | [12 empty] | P5959 | BIG SPRINGS PARKING STRUCTURE | BIG SPR PARK | NON-CORE
0 | 18W011691 | [12 empty] | P5980 | CE-CERT OFFICE BUILDING | 1084COLUMBIA | NON-CORE
0 | 18W011672 | [12 empty] | P5981 | CE-CERT CHAMBER BUILDING | 1086COLUMBIA | NON-CORE
0 | 18W011161 | [12 empty] | P5983 | 1200 COLUMBIA AVENUE, RIVERSIDE | 1200COLUMBIA | NON-CORE
0 | 18W009630 | [12 empty] | P5985 | MOTTE RIMROCK RESERVE TRAILER | MOTTE TRAILR | NON-CORE
0 | 18W008762 | [12 empty] | P5986 | USDA SALINITY LABORATORY | SALINITY LAB | NON-CORE
0 | 18W007453 | [12 empty] | P5987 | UNIVERSITY VILLAGE OFFICE LEASE | UV BLDG A | NON-CORE
0 | 18W006022 | [12 empty] | P5990 | CHAVEZ COMCT | CHAVEZ COMCT
0 | 18W001170 | [12 empty] | P5991 | STONEHAVEN APARTMENTS | STONEHAVEN | NON-CORE
0 | 18W000455 | [12 empty] | P5994 | USDA CLONAL GERMPLASM RESPOSITORY | GERMPLASM | CORE
0 | 18P000487 | [12 empty] | P5998 | INTERNATIONAL VILLAGE (UNEX) | INTER VILLAG | NON-CORE
0 | 18P000486 | [12 empty] | PG650 | SUBSTATION | SUBSTATION
0 | 18P000485 | [12 empty] | T MRB1 | MRB1 T1 | MRB1 T1
0 | 18P000484 | [12 empty] | T MRB2 | MRB1 T2 | MRB1 T2
0 | 18P000483 | [12 empty] | T MRB3 | MRB1 T3 | MRB1 T3
0 | 18P000482 | [12 empty] | Z1005 | SOFTBALL STG | SOFTBALL STG
0 | 18P000481 | [12 empty] | Z1016 | FIELD 9 SHED | FIELD 9 SHED
0 | 18P000480 | [12 empty] | Z1017 | T MORSE HALL | T MORSE HALL
0 | 18P000478 | [12 empty] | Z1018 | T SEELEY HAL | T SEELEY HAL
0 | 18P000476 | [12 empty] | Z1019 | SHIP 29 | SHIP 29
0 | 18P000474 | [12 empty] | Z1020 | T SBUR HALL | T SBUR HALL
0 | 18P000473 | [12 empty] | Z1021 | STOR 14-1 | STOR 14-1
0 | 18P000472 | [12 empty] | Z1023 | COLD 1 | COLD 1
0 | 18P000471 | [12 empty] | Z1024 | COLD 2 | COLD 2
0 | 18P000470 | [12 empty] | Z1025 | COLD 3 | COLD 3
0 | 18P000469 | [12 empty] | Z1026 | COLD 4 | COLD 4
0 | 18P000468 | [12 empty] | Z1027 | COLD 5 | COLD 5
0 | 18P000465 | [12 empty] | Z1028 | COLD 6 | COLD 6
0 | 18P000464 | [12 empty] | Z1029 | COLD 7 | COLD 7
0 | 18P000463 | [12 empty] | Z1030 | T2 FIELD 14-1 | T2 FIELD 14-1
0 | 18P000459 | [12 empty] | Z1031 | SHED 20 | SHED 20
0 | 18P000456 | [12 empty] | Z1032 | T1 STOR | T1 STOR
0 | 18P000454 | [12 empty] | Z1033 | 21 1623 STOR | 21 1623 STOR
0 | 18P000453 | [12 empty] | Z1034 | STOR 23 | STOR 23
0 | 18P000445 | [12 empty] | Z1035 | 21 1775 STOR | 21 1775 STOR
0 | 18P000444 | [12 empty] | Z1036 | 21 1776 STOR | 21 1776 STOR
0 | 18P000442 | [12 empty] | Z1037 | STOR 26 | STOR 26
0 | 18P000439 | [12 empty] | Z1038 | 21 1595 STOR | 21 1595 STOR
0 | 18P000438 | [12 empty] | Z1039 | STOR 3 | STOR 3
0 | 18P000436 | [12 empty] | Z1040 | STOR 4 | STOR 4
0 | 18P000435 | [12 empty] | Z1041 | STOR 5 | STOR 5
0 | 18P000434 | [12 empty] | Z1042 | STOR 6 | STOR 6
0 | 18P000432 | [12 empty] | Z1043 | STOR 21 6075 | STOR 21 6075
0 | 18P000429 | [12 empty] | Z1044 | SHED 21 | SHED 21
0 | 18P000428 | [12 empty] | Z1046 | COLD STOR | COLD STOR
0 | 18P000427 | [12 empty] | Z1048 | GH 15-49 | GH 15-49
0 | 18P000426 | [12 empty] | Z1049 | SHED 30 | SHED 30
0 | 18P000425 | [12 empty] | Z1050 | SHED 31 | SHED 31
0 | 18P000421 | [12 empty] | Z1051 | SHED 32 | SHED 32
0 | 18P000420 | [12 empty] | Z1052 | FENCE 1 | FENCE 1
0 | 18P000419 | [12 empty] | Z1053 | STOR 33 | STOR 33
0 | 18P000418 | [12 empty] | Z1054 | STOR 34 | STOR 34
0 | 18P000417 | [12 empty] | Z1055 | FENCE 2 | FENCE 2
0 | 18P000416 | [12 empty] | Z1056 | COOP 1 | COOP 1
0 | 18P000415 | [12 empty] | Z1057 | COOP 4 | COOP 4
0 | 18P000414 | [12 empty] | Z1058 | FENCE 4 | FENCE 4
0 | 18P000410 | [12 empty] | Z1059 | FENCE 3 | FENCE 3
0 | 18P000400 | [12 empty] | Z1060 | COOP 3 | COOP 3
0 | 18P000396 | [12 empty] | Z1061 | COOP 2 | COOP 2
0 | 18P000394 | [12 empty] | Z1062 | SCREEN 35 | SCREEN 35
0 | 18P000392 | [12 empty] | Z1063 | STOR CANVAS | STOR CANVAS
0 | 18P000391 | [12 empty] | Z1064 | SHED 8 | SHED 8
0 | 18P000390 | [12 empty] | Z1065 | SHED 36 | SHED 36
0 | 18P000389 | [12 empty] | Z1066 | CARGO 1 | CARGO 1
0 | 18P000388 | [12 empty] | Z1067 | SHED 37 | SHED 37
0 | 18P000387 | [12 empty] | Z1068 | SHED 38 | SHED 38
0 | 18P000385 | [12 empty] | Z1069 | SHED 39 | SHED 39
0 | 18P000383 | [12 empty] | Z1070 | SCREEN 1 | SCREEN 1
0 | 18P000382 | [12 empty] | Z1071 | CARGO 2 | CARGO 2
0 | 18P000381 | [12 empty] | Z1072 | SHED 40 | SHED 40
0 | 18P000380 | [12 empty] | Z1073 | CANOPY FUM | CANOPY FUM
0 | 18P000379 | [12 empty] | Z1074 | STOR 38 | STOR 38
0 | 18P000373 | [12 empty] | Z1075 | STOR 39 | STOR 39
0 | 18P000369 | [12 empty] | Z1076 | STOR 40 | STOR 40
0 | 18P000367 | [12 empty] | Z1077 | STOR 41 | STOR 41
0 | 18P000363 | [12 empty] | Z1078 | STOR 42 | STOR 42
0 | 18P000356 | [12 empty] | Z1079 | STOR 43 | STOR 43
0 | 18P000354 | [12 empty] | Z1080 | SCREEN 2 | SCREEN 2
0 | 18P000353 | [12 empty] | Z1081 | SHED 41 | SHED 41
0 | 18P000351 | [12 empty] | Z1089 | SHED 42 | SHED 42
0 | 18P000349 | [12 empty] | Z1090 | GH K1 | GH K1
0 | 18P000348 | [12 empty] | Z1093 | PICNIC 1 | PICNIC 1
0 | 18P000347 | [12 empty] | Z1094 | PICNIC 2 | PICNIC 2
0 | 18P000346 | [12 empty] | Z1096 | METEOR 9C | METEOR 9C
0 | 18P000344 | [12 empty] | Z1097 | SHED 8 | SHED 8
0 | 18P000343 | [12 empty] | Z1098 | TURF FERTIL | TURF FERTIL
0 | 18P000341 | [12 empty] | Z1099 | SHED 9 | SHED 9
0 | 18P000337 | [12 empty] | Z1100 | COLD BOX 2 | COLD BOX 2
0 | 18P000329 | [12 empty] | Z1101 | INST TOWER | INST TOWER
0 | 18P000328 | [12 empty] | Z1102 | PUMP 5 | PUMP 5
0 | 18P000324 | [12 empty] | Z1103 | PUMP SHED | PUMP SHED
0 | 18P000321 | [12 empty] | Z1104 | TANK STORAGE | TANK STORAGE
0 | 18P000318 | [12 empty] | Z1105 | METAL SHED 1 | METAL SHED 1
0 | 18P000315 | [12 empty] | Z1106 | METAL SHED 2 | METAL SHED 2
0 | 18P000314 | [12 empty] | Z1107 | METAL SHED 3 | METAL SHED 3
0 | 18P000313 | [12 empty] | Z1108 | METAL SHED 4 | METAL SHED 4
0 | 18P000312 | [12 empty] | Z1109 | METAL SHED 5 | METAL SHED 5
0 | 18P000310 | [12 empty] | Z1110 | METAL SHED 6 | METAL SHED 6
0 | 18P000300 | [12 empty] | Z1111 | METAL SHED 7 | METAL SHED 7
0 | 18P000297 | [12 empty] | Z1112 | METAL SHED 8 | METAL SHED 8
0 | 18P000296 | [12 empty] | Z1113 | SOC BLEACHER | SOC BLEACHER
0 | 18P000295 | [12 empty] | Z1114 | SOC TRAILER1 | SOC TRAILER1
0 | 18P000294 | [12 empty] | Z1115 | SOC TRAILER2 | SOC TRAILER2
0 | 18P000293 | [12 empty] | Z1116 | TRACK BLEACH | TRACK BLEACH
0 | 18P000292 | [12 empty] | Z1117 | LATH C | LATH C
0 | 18P000288 | [12 empty] | Z1118 | LATH 10 | LATH 10
0 | 18P000287 | [12 empty] | Z1119 | STEAM GENER | STEAM GENER
0 | 18P000284 | [12 empty] | Z1121 | FENCE 6 | FENCE 6
0 | 18P000282 | [12 empty] | Z1122 | FENCE 7 | FENCE 7
0 | 18P000281 | [12 empty] | Z1123 | METAL TANK 1 | METAL TANK 1
0 | 18P000274 | [12 empty] | Z1124 | METAL STOR 1 | METAL STOR 1
0 | 18P000273 | [12 empty] | Z1125 | METAL STOR 2 | METAL STOR 2
0 | 18P000270 | [12 empty] | Z1126 | COLD 8 | COLD 8
0 | 18P000269 | [12 empty] | Z1127 | COLD 9 | COLD 9
0 | 18P000267 | [12 empty] | Z1128 | METAL CANOPY | METAL CANOPY
0 | 18P000261 | [12 empty] | Z1129 | SHED 45 | SHED 45
0 | 18P000258 | [12 empty] | Z1133 | BOT GDN SHD | BOT GDN SHD
0 | 18P000257 | [12 empty] | Z1134 | BOT GDN SHD2 | BOT GDN SHD2
0 | 18P000256 | [12 empty] | Z1136 | HSNG STOR | HSNG STOR
0 | 18P000252 | [12 empty] | Z1137 | CVAR SHADE 1 | CVAR SHADE 1
0 | 18P000247 | [12 empty] | Z1138 | CVAR PAD 1 | CVAR PAD 1
0 | 18P000227 | [12 empty] | Z1139 | CVAR T1 | CVAR T1
0 | 18P000226 | [12 empty] | Z1140 | CVAR OLD ICE | CVAR OLD ICE
0 | 18P000223 | [12 empty] | Z1141 | CVAR T LAB | CVAR T LAB
0 | 18P000221 | [12 empty] | Z1142 | CVAR STOR 2 | CVAR STOR 2
0 | 18P000215 | [12 empty] | Z1143 | CVAR FUEL | CVAR FUEL
0 | 18P000214 | [12 empty] | Z1144 | CVAR GH 1 | CVAR GH 1
0 | 18P000209 | [12 empty] | Z1145 | CVAR GH 2 | CVAR GH 2
0 | 18P000205 | [12 empty] | Z1146 | CVAR INSECT 1 | CVAR INSECT 1
0 | 18P000201 | [12 empty] | Z1147 | CVAR INSECT 2 | CVAR INSECT 2
0 | 18P000198 | [12 empty] | Z1148 | CVAR INSECT 3 | CVAR INSECT 3
0 | 18P000194 | [12 empty] | Z1149 | CVAR SHED 1 | CVAR SHED 1
0 | 18P000126 | [12 empty] | Z1150 | CVAR PAD 2 | CVAR PAD 2
0 | 18P000122 | [12 empty] | Z1151 | CVAR SHED 2 | CVAR SHED 2
0 | 18P000121 | [12 empty] | Z1152 | CVAR SHADE 2 | CVAR SHADE 2
0 | 18P000118 | [12 empty] | Z1153 | CVAR STOR 2 | CVAR STOR 2
0 | 18P000117 | [12 empty] | Z1154 | CVAR SHADE 3 | CVAR SHADE 3
0 | 18P000111 | [12 empty] | Z1155 | CVAR FENCE 1 | CVAR FENCE 1
0 | 18P000106 | [12 empty] | Z1156 | CVAR PUMP | CVAR PUMP
0 | 18P000099 | [12 empty] | Z1157 | CVAR CONT 1 | CVAR CONT 1
0 | 18P000095 | [12 empty] | Z1158 | CVAR CONT 2 | CVAR CONT 2
0 | 18P000094 | [12 empty] | Z1159 | CVAR CONT 3 | CVAR CONT 3
0 | 18P000030 | [12 empty] | Z2000 | BSL3 LAB | BSL3 LAB
0 | 18P000029
0 | 18P000028
0 | 18P000027
0 | 17W012504
0 | 17P000254
0 | 9062
0 | 9061
0 | 9060
0 | 9059
0 | 9058
0 | 3617
0 | 3610
0 | 3608
0 | 3607
0 | 3603
0 | 3602
0 | 3599
0 | 3597
0 | 3596
0 | 3594
0 | 3593
0 | 3589
0 | 3581
0 | 3574
0 | 3564
0 | 3560
0 | 3559
0 | 3557
0 | 3550
0 | 3549
0 | 3548
0 | 3541
0 | 3535
0 | 3533
0 | 3529
0 | 3527
0 | 3524
0 | 3523
0 | 3516
0 | 3512
0 | 3510
0 | 3508
0 | 3507
0 | 3505
0 | 3499
0 | 3492
0 | 3490
0 | 3481
0 | 3476
0 | 3474
0 | 3471
0 | 3470
0 | 3467
0 | 3466
0 | 3458
0 | 3452
0 | 3441
0 | 3438
0 | 3428
0 | 3421
0 | 3407
0 | 3401
0 | 3395
0 | 3390
0 | 3382
0 | 3326
0 | 3319
0 | 3286
0 | 3280
0 | 3234
0 | 3233
0 | 3203
0 | 3195
0 | 3119
0 | 3110
0 | 3104
0 | 3064
0 | 2989
0 | 2952
0 | 2900
0 | 2899
0 | 2725
0 | 2696
0 | 2687
0 | 2682
0 | 2368
0
0

## Legend
Legend and Contacts
FS | Facilities Services
PD&C | Planning, Design & Construction (formerly A&E - Architects & Engineers)
FS Current Statuses | Definitions
Project Intake | Building Zone Manager (BZM) to meet with customer to understand and define scope of work.
Queue to Start | Initial scope of work has been identified by BZM; project in queue for FS Project Manager to develop drawings and coordinate trades for execution.
Plan Development / Check | Project Manager is coordinating plan development and review by Building Official and/or Fire Marshal.
In Progress | Project is in progress which includes but not limited to plan development, scheduling and coordination of trades for work execution.
Hold - Customer Equipment/Schedule | Project is on hold pending customer provided equipment or scheduling availability.
Hold - Facilities Services | Project is on hold pending FS; determining ability to complete project within FS purview or parts ordered by FS for completion.
Quality Check of Work | Project is being reviewed to ensure work is completed to customer and FS standards.
Canceled by Client | Project is canceled at the request of the customer or duplicative project request.
Canceled by FS | Project is canceled by FS administration or duplicative project request.
IRT Review | Project is to be reviewed by PD&C/FS or to be completed by PD&C with a project submittal by customer within CPMS.
Complete | Project is complete to customer and FS standards.
TO BE PERFORMED BY PD&C | Project is no longer an FS project and will be managed and completed by PD&C.
PD&C Current Statuses | Definitions
"Open Field" | PD&C project managers will input most recent update in this field.
| FS | PD&C
Org | Org Delegate/Contact | CPMS Department Approver
ATHLETICS | Joseph Erbland / Eugene Hutchinson Jr. | Joseph Erbland
BCOE | Todd Ambriz | Susana Aparicio
CAMPUS | TBD
CAP.PROG. | Sharyl Murdock | John White
CHANCELLOR | Luis Alvarez / Jackie Rodriguez
CHASS | Cindy Williams | Cindy Williams KatriceCalloway
CNAS | Jose Wudka | Beverly McNeil Kimberly Hammond
ENROLLMENT SERVICES | Emily Engelschall / Sean Cason
FAC-PLNG-DESIGN-CONST | Susan Marshburn | Susan Marshburn
GRAD.DIV | Kennett Lai
GSOE | Sally Tavizon
ITS | Shelley Gupta | Shelley Gupta
LIBR | Dave Shuster | Jacqueline Bates
PALM DESERT |  | Tamara Hedges
PLANNING BUDGET & ADMINISTRATION | TBD | Jeff Kaplan / Andy Plumley
PROVOST/EVC | Luis Alvarez / Jackie Rodriguez
SoB | Angela Chang | Laurie Gustafson
SOM | Cynthia Carolina | Laura Manor
SPP | Luke Hoepfner
VC-RED | Laura Manor | Laura Manor
VC-STU.AFF. | Cathy Eckman | Karen McComb Lindy Fenex Cathy Eckman
VC-UNIV.ADV. | Naysia Caldwell | Margene Mastin-Schepps