## Active Project Summary
ACTIVE Project Status Report
[6 empty] | Total Active PD&C Projects |  | 90
[6 empty] | Total Active FS Projects |  | 38
Last Updated | 2021-10-01 | Project Summary |  |  |  | Project Status |  |  |  |  | Project Details | [6 empty] | Internal Use Only
Organization | Project Ref No. | Project Service Unit | Project Title | Building | Room | Request Date | Current Status | Next Steps | START Date | COMPLETE Date | Project Description | PD&C Org Priority No. | FS Org Priority No. | For New Faculty Hire? | FS Org Prior. Quarter & Year | Contact / Requestor | Proj Manager | Chronology
BCOE | 21P000049 | FS | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MATERIALS SCIENCE & ENGINEERING | 71 | 2020-08-06 | IN PROGRESS | Schedule the work once the permit is approved | 2021-06-02 | 2021-09-15 | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS |  | 2 |  | Winter 2021 | DONG YAN | DAN LERMAN | 14
CNAS | 20P000333 | FS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | W. CONWAY PIERCE HALL | 2232A | 2020-01-22 | IN PROGRESS | Schedule the work once the permit is approved | 2021-06-04 | 2021-10-29 | MINOR RENOVATIONS CASEWORK SINK UTL LINES |  | 9 |  | Winter 2021 | KEVIN SIMPSON | DAN LERMAN | 14
CHASS | 20P000272 | FS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 245 | 2020-01-02 | IN PROGRESS | Make corrections and resubmit plans on 7/15/21 | 2021-05-24 | 2021-09-23 | LIGHTING UPGRADE/PROJECTOR INSTALLATION |  | 3 |  | Winter 2021 | ANDREA HIDALGO | DAN LERMAN | 14
CHASS | 20P000231 | FS | SL5 ARTS 54 - CONVERT TO PIANO LAB | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 54 | 2019-11-19 | IN PROGRESS | Framing and electrical | 2021-05-14 | 2021-10-31 | Convert Basement Library into Piano Lab |  | 4 |  | Winter 2021 | PAUL RICHARDSON | Dan Lerman | 14
CAMPUS | 22P000006 | FS | SL5 MRB 4210 - INSTALL AC & ELECTRICAL INFRASTRUCTURE |  | 4210 | 2021-07-12 | PROJECT INTAKE | Work on plans and apply for building permit | 2021-09-06 | 2021-10-29 | We have a project at MRB 4210 where we will be installing Air conditioning and electrical infrastructure to accommodate equipment that will be relocated from Batchelor Hall to MRB which is a result of the Batchelor Hall renovation. |  | 1 |  | Summer 2021 | SHARYL MURDOCK | Dan Lerman | 16
VC-UNIV ADV | 22P000065 | FS | SL5 CAMPUS INTERIOR - HANG BANNERS, INSTALL HARDWARE |  |  | 2021-09-09 | QUEUE TO START |  |  |  | Banners to be hung within Campus interior. Installation of banner hardware on Pierce Hall and Skye Hall. |  |  |  | FY 21-22 | LISA CUSICK | Dan Lerman | 18
CHASS | 20P000317 | FS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 150 | 2020-01-14 | QUEUE TO START | Order material once permit is approved | 2021-06-14 | 2021-10-31 | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel |  | 2 |  | Winter 2021 | PAUL RICHARDSON | DAN LERMAN | 14
CNAS | 21P000083 | FS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS BUILDING |  | 2019-12-19 | ESTIMATE | Awaiting Response from Client |  |  | UPDATE KEYCARD SYSTEM FOR BUILDING |  | R1 |  | Winter 2021 | JOSE WUDKA | Enrico Baez | 14
BCOE | 20P000212 | FS | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | MARLAN & ROSEMARY BOURNS HALL | B0328E | 2019-11-05 | QUEUE TO START |  |  |  | Repair the damaged exhaust duct at Fume hood in BCOE 328E |  | R1 |  | Winter 2021 | MARGARET SOUDER | Enrico Baez | 14
CNAS | 20P000367 | FS | SL5 SCI LAB ROOM 315-PATCH & PAINT | SCIENCE LABORATORIES 1 | 315 | 2020-02-19 | HOLD - FACILITIES SERVICES | [5 empty] | 9 |  | Spring 2020 | DEBORAH TERAO | PAUL DITTY | 11
ENROLLMENT SERVICES | 20P000336 | FS | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS | STUDENT SUPPORT SERVICES BUILDING | 2109B | 2020-01-22 | HOLD - FACILITIES SERVICES | [5 empty] | 1 |  | Spring 2020 | SELENA SANCHEZ | PAUL DITTY | 11
PB&A | 20P000275 | FS | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE | MAIL BUILDING | 884 | 2019-12-04 | HOLD - FACILITIES SERVICES | [5 empty] | 1 |  | Spring 2020 | JENNIFER TENNEY STRATTON | PAUL DITTY | 11
SOM | 22P000027 | FS | SL5 WEBBER HALL 1143 - PAINT/PATCH |  | 1143 | 2021-06-16 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | CLARK HAPEMAN | PAUL DITTY | 18
CHASS | 22P000022 | FS | SL5 HUMANITIES A3414 - NAIL REMOVAL, PATCH, AND PAINT |  | 3414 | 2021-07-29 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | JENNIFER HAMILTON | PAUL DITTY | 18
CNAS | 21P000212 | FS | SL5 LIFE SCIENCES 0418D - PAINT CEILING, DOOR, DOOR FRAME |  | 418D | 2021-06-29 | QUEUE TO START |  |  |  | PATCH & PAINT (RESEARCH RELATED) |  | X |  | FY 21-22 | DIERK BIGGS | PAUL DITTY | 18
GRAD DIV | 21P000211 | FS | SL5 UNIV OFFICE BLD 0144 - PATCH & PAINT |  | 144 | 2021-06-24 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | CARLOS RIVAS | PAUL DITTY | 18
SOM | 21P000204 | FS | SL5 WEBBER HALL 1126A - PAINT/PATCH |  | 1126A | 2021-06-16 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | CLARK HAPEMAN | PAUL DITTY | 18
CHASS | 21P000190 | FS | SL5 PSYCHOLOGY 3119 - PATCH & PAINT / REMOVE WALL FIXTURE |  | 3119 | 2021-05-27 | QUEUE TO START |  |  |  | PATCH & PAINT / REMOVE WALL FIXTURE |  | X |  | FY 21-22 | AERIKA LOYD | PAUL DITTY | 18
CNAS | 21P000162 | FS | SL5 ENTOMOLOGY 0282 - PAINT NEW FACULTY MEMBER'S OFFICE |  | 0282 | 2021-04-14 | QUEUE TO START |  |  |  | PAINT NEW FACULTY MEMBER'S OFFICE |  | X | YES | Winter 2021 | WILLIAM SUTTON | Paul Ditty | 14
PB&A | 21P000158 | FS | SL5 POLICE BUILDING 0100 - PAINT ATRIUM |  | 0100 | 2021-04-05 | QUEUE TO START |  |  |  | Request to Paint Atrium |  |  |  | Summer 2021 | ROCIO STERN | Paul Ditty | 16
CNAS | 21P000157 | FS | SL5 PHYSICS 1119 - PATCH AND PAINT FOR NEW HIRE |  | 1119 | 2021-04-06 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X | YES | FY 21-22 | DAVID NEFF | PAUL DITTY | 18
CNAS | 21P000155 | FS | SL5 OLMSTED 1342 - NEW FACULTY ARIVAL CARPET CLEAN / PATCH/PAINT |  | 1342 | 2021-04-02 | QUEUE TO START |  |  |  | CARPET CLEAN / PATCH & PAINT |  | X | YES | FY 21-22 | SOPHIA JURISCH | PAUL DITTY | 18
CNAS | 21P000151 | FS | SL5 SPIETH HALL 3310 - NEW FACULTY OFFICE - PATCH & PAINT |  | 3310 | 2021-03-31 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X | YES | FY 21-22 | ESTELLA DAVALOS | PAUL DITTY | 18
BCOE | 21P000146 | FS | SL5 BOURNS A308 - OFFICE PATCH & PAINT |  | A0308 | 2021-03-17 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | ROBERT LOPEZ-A | PAUL DITTY | 18
SOM | 21P000144 | FS | SL5 WEBBER HALL 1116A - SHELVING REMOVED /PATCH & PAINT |  | 1116A | 2021-03-17 | QUEUE TO START |  |  |  | SHELVING REMOVED /PATCH & PAINT |  | X |  | FY 21-22 | DEBORAH TRUJILLO | PAUL DITTY | 18
CNAS | 21P000134 | FS | SL5 LIFE SCIENCES 2550 - CONF ROOM PATCH & PAINT |  | 2550 | 2021-03-04 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | ESTELLA DAVALOS | PAUL DITTY | 18
VC-STU AFF | 21P000088 | FS | SL5 HEALTH SERVICE BUILDING 100D - FILL HOLES/PAINT |  | 0100D | 2020-10-12 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | WILLIAM RALL | PAUL DITTY | 18
BCOE | 21P000011 | FS | SL5 CHUNG HALL 4TH FLOOR OFFICE 414 - PATCH & PAINT |  | 414 | 2020-07-13 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | ROBERT LOPEZ-A | PAUL DITTY | 18
FAC-PLNG-DESIGN-CONST | 20P000401 | FS | SL5 FS ANNEX B 5 & 6 - PAINT SUPERVISORS OFFICE |  |  | 2020-03-13 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | MARK JONES | PAUL DITTY | 18
CHASS | 20P000384 | FS | SL5 CHASS INTS 3111A - PATCHING HOLES AND PAINTING THE WALLS |  | 3111A | 2020-02-27 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | LESLIE ANN GERRETSE | PAUL DITTY | 18
VC-STU AFF | 20P000374 | FS | SL5 HEALTH SERVICES 334 - OFFICES PAINTED AND CONFERENCE ROOM |  | 334 | 2020-02-20 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | GLORIA VERA | PAUL DITTY | 18
VC-STU AFF | 20P000372 | FS | SL5 HEALTH SERVICES 391 - OFFICES PAINTED AND CONFERENCE ROOM |  | 391 | 2020-02-20 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | GLORIA VERA | PAUL DITTY | 18
CNAS | 20P000368 | FS | SL5 SCI LAB ROOM 317 - PATCH & PAINT |  | 317 | 2020-02-18 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | ESTELLA DAVALOS | PAUL DITTY | 18
VC-RED | 20P000354 | FS | SL5 UOB 200 - PAINT & PATCH OFFICES |  | 200 | 2020-02-07 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | MARISELA MARTINEZ | PAUL DITTY | 18
CHASS | 20P000321 | FS | SL5 UNIV THEATRE 400A - PAINT LOBBY |  | 0400A | 2020-01-15 | QUEUE TO START |  |  |  | PATCH & PAINT |  | X |  | FY 21-22 | ALBERT FETTER | PAUL DITTY | 18
FAC-PLNG-DESIGN-CONST | 20P000282 | FS | SL5 PIERCE HALL 3374 - RENOVATE GA CLASSROOM SUMMER 2020 |  | 3374 | 2020-01-09 | QUEUE TO START |  |  |  | Project to renovate GA classroom in Pierce Hall for prioritization and execution in Summer 2020. |  | X |  | Winter 2021 | DA LAN DINH | Paul Ditty | 14
CNAS | 20P000244 | FS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | SKYE HALL | 242 | 2019-11-25 | QUEUE TO START |  |  |  | Paint Only |  | X | YES | Winter 2021 | MELISSA GOMEZ | PAUL DITTY | 14
CNAS | 20P000174 | FS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | PHYSICS BUILDING | 3009 | 2019-10-11 | QUEUE TO START |  |  |  | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 |  | 1 | YES | Winter 2021 | MAYELA CASTILLO | PAUL DITTY | 14
CAP PROG | 2970d | PD&C | ADA Improvements/Transition Plan |  |  | 2015-12-02 | Bidding | Award Contract |  |  | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) | 11 |  |  |  | Blythe Wilson | Tameesha Hayes
FAC-PLNG-DESIGN-CONST | 3550 | PD&C | DMFI(FY17-19) Skye Hall HVAC Replacement | SKYE HALL |  | 2019-09-05 | Bidding | Award Contract |  |  | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | 6 |  |  |  | Scott Donnell | Tameesha Hayes
CAP PROG | 3438 | PD&C | Iowa Street Widening |  |  | 2018-08-22 | Completed | Completed | 2020-07-01 | 2021-07-01 | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. | 14 |  |  |  | Scott Donnell | Scott Donnell
ATHLETICS | 3632 | PD&C | SRC North Instant Replay System |  |  | 2021-04-01 | Delayed until 8/2022 per Athletics | Delayed until 8/2022 per Athletics |  |  | Possible update of instant replay system in Student Recreation Center North to include volleyball if mandate by Big West Conference is enacted. This will include placing cameras on the ends of the court that will send signal back to the control room and could involve additional wiring to courtside connection boxes. Scope may include upgrading audio connections. Volleyball season starts in late August... first home game TBD. No charges to this FAU unless Athletics notified in advance of work to be performed. Work Notes: Project will require coordination not only with Athletics but must also with Recreation (Mike Eason), and their scheduling may affect above dates. Possible vendor to be consulted is TechNet who has indicated ability to do such a project in recent times. | 3 |  |  |  | Joe Erbland | Tameesha Hayes
PB&A | 3515d | PD&C | Multiple SF6 Primary Switches |  |  | 2021-03-01 | Design | Bidding |  |  | Sub-project of 950568 | 2 |  |  |  | John Franklin | John Franklin
PB&A | 9061 | PD&C | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Design | Bidding |  |  |  | 99 |  |  |  | ---- | Tameesha Hayes
PB&A | 9059 | PD&C | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches |  |  | 2020-09-22 | Design | Bidding | 2022-01-01 | 2022-04-01 | Replace ten gas filled - medium voltage switches | 99 |  |  |  | David Palacios | John Franklin
SOM | 3630 | PD&C | SOMR Egress Doors/Cameras |  |  | 2020-03-04 | Design | Bidding |  |  | All egress doors for floors 1-3. need to be replaced with compliant standards. Project to also include security cameras for entry and exit on 1st and 2nd floor. | 2 |  |  |  | Cynthia Carolina | Tameesha Hayes
CAP PROG | 3616 | PD&C | University Ave/Canyon Crest Dr Improvements |  |  | 2021-03-01 | Design | Construction | 2022-01-01 | 2022-02-01 | $100,000 in Violent Acts Mitigation and Prevention funding have been awarded to study short and long-term safety improvements at the intersection at University Avenue and Canyon Crest Drive. Subsequent activities will involve the construction of identified improvements. | 16 |  |  |  | Jaime Engbrecht | Uma R.
FAC-PLNG-DESIGN-CONST | 3607 | PD&C | DM(FY20) Central Utility Plant Controls |  |  | 2020-09-17 | Design | UCR Decision for Controls Manufacturer |  |  | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) | 1 |  |  |  | David Palacios | Fernando Nunez
PB&A | 3516 | PD&C | Student Health & Counseling Center (SHCC) |  |  | 2019-03-04 | Design | Construction | 2021-12-01 | 2023-05-01 | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. | 1 |  |  |  | ---- | Fernando Canon
PB&A | 3466 | PD&C | Oban Porch and Stair Repair | OBAN APTS A |  | 2018-07-31 | Design | Bidding TBD |  |  | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | 19 |  |  |  | Sean Hatfield | Daneca Stevens
PB&A | 9067 | PD&C | DM(FY20) Campus Infrastructure Access Control |  |  |  | DM project to be funded | DM project to be funded |  |  | Access Control: Automate Access Controls focusing on General Assignment Classrooms. | [5 empty] | Fernando Nunez
PB&A | 3655 | PD&C | ECS Playground Improvements |  |  | 2021-09-08 | Funding | Secure Funding |  |  | Provide professional design services to complete schematic design, design development, and cost estimate for ECS North and South playgrounds. Scope of work includes reconfiguring pathways to mitigate trip hazards and meet ADA requirements, improve playground equipment and surfaces, add shade structures. Refer to John Franklin for more details. |  |  |  |  | Sean Hatfield | John Franklin
ITS | 3631 | PD&C | SOM-ED 1 UPS |  | 1625 | 2021-07-22 | Funding | Design |  |  | The Information Technology Solutions (ITS) intends to replace its existing UPS unit with a state of the art systems that will support all of the requirements set-forth by the University of California, Riverside ITS and Facilities departments. Our primary objective is to provide ITS critical services and various other software applications. The ITS department would like to Procure (1) redundant UPS System with all accessories and maintenance for three years after warranty (AMC). Procure One Replacement 500KW UPS Unit, Installation of New UPS, Removal and Disposal of Old UPS components, Startup Services for New UPS, Electrical Installation of New UPS and Removal of Rental UPS connections (High Voltage) | 1 |  |  |  | Cesar Higueros | Tameesha Hayes
PB&A | 3610 | PD&C | Hulen Place Homeless Medical Clinic |  |  | 2020-10-06 | Funding | Secure Funding |  |  | SOM is acquiring additional space for a medical clinic to assist with the homeless population. | 5 |  |  |  | Diana Armenta | Daneca Stevens
FAC-PLNG-DESIGN-CONST | 3564 | PD&C | DM(FY17-19) Rivera Library North Wing AHU Replacement | RIVERA LIB |  | 2019-11-06 | Funding | Secure Funding |  |  | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | 9 |  |  |  | Scott Donnell | Tameesha Hayes
FAC-PLNG-DESIGN-CONST | 3549 | PD&C | DMFI(FY17-19) Fine Arts Decking | ARTS |  | 2019-09-05 | Funding | Combine with Exterior Proj CP3548 |  |  | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | 7 |  |  |  | Scott Donnell | Tameesha Hayes
CAP PROG | 3615 | PD&C | Student Success Center Buildout |  |  | 2021-03-09 | Furniture & Equipment | Close-out | 2021-03-01 | 2021-08-01 | Buildout and furnishing of the SSC dining venue for temporary use as seating/study area and other as needed construction scope related to the overall building project that was not described in the Basis of Design. | 17 |  |  |  | Jaime Engbrecht | Mihai Gavan
CAP PROG | 3319 | PD&C | Student Success Center |  |  | 2017-06-01 | Furniture & Equipment | Close-out | 2019-11-01 | 2021-08-01 | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. | 9 |  |  |  | ---- | Mihai Gavan
PB&A | 9060 | PD&C | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  | 2020-09-15 | In Bidding | Award Contract |  |  |  | 99 |  |  |  | ---- | Daneca Stevens
INACTIVE P&B | 3614 | PD&C | MLK Water Meters |  |  | 2021-04-30 | In Bidding | Award Contract | 2021-11-01 | 2021-12-01 | Provide by contract plumbing point of connections and irrigation infrastructures to north and south sides of Martin Luther King Blvd. for watering of UCR palm trees. City of Riverside shall install two (2) ¾” [City] water meters at points of connection. Provide approximately 300’ of new irrigation main-line with associated trenching via contract and/or via facilities work order TBD. | 17 |  |  |  | Scott Donnell | Vilma Kern
PB&A | 3510 | PD&C | SOMED Data Center Upgrade | SOM EDUC |  | 2019-03-04 | In Bidding | Award Contract | 2021-11-21 | 2022-03-01 | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | 4 |  |  |  | Daneca Stevens | Tameesha Hayes
CNAS | 3228b | PD&C | Rubidoux Screenhouse Conv |  |  | 2016-12-06 | In Bidding (Phase 2) | Award Contract (Phase 2) | 2021-10-01 | 2022-01-01 | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. | 6 |  |  |  | Sabrina Schuster | Tameesha Hayes
PB&A | 3590b | PD&C | DMFI(FY17-20) Physics Elevator Modernization | PHYSICS |  | 2019-11-27 | In Construction | Submittal approval | 2021-07-01 | 2022-02-01 | Physics Elevator Modernization | 4 |  |  |  | Ben Kochevar | Fernando Nunez
PB&A | 9058 | PD&C | Lothian West Rooftop Solar |  |  | 2020-09-23 | In Construction | Complete Construction | 2021-07-01 | 2022-02-01 |  | 99 |  |  |  | Sean Hatfield | John Franklin
PB&A | 3648 | PD&C | Bannockburn Walkway Repairs |  |  | 2021-07-12 | In Construction | Complete Construction | 2021-10-01 | 2021-12-01 | Several walkway locations at Bannockburn have deteriorated to the point that they must be replaced. The topcoat is past it’s service life and has lost all waterproofing effectiveness. As a result, the underlying sheathing, T&G, and support beams have suffered extreme water damage. Scope of Work: Replace support beams, T&G, and topcoat system at 2 locations: L bldg. & V bldg. Requesting JOHN FRANKLIN as PM. | 1 |  |  |  | Sean Hatfield | John Franklin
CAP PROG | 3613 | PD&C | Corp Yard Modular Building Relocation Study |  |  | 2021-04-23 | In Construction | Complete Construction |  |  | This project will be to relocate the existing School of Medicine modular trailer (P5825) to the Corp Yard (specific location to be determined). This modular needs to be relocated due to the new School of Medicine Education Building II project being located on this site. | 18 |  |  |  | Jaime Engbrecht | Tameesha Hayes
CNAS | 3596 | PD&C | Rubidoux MPGU |  |  | 2020-09-11 | In Construction | Complete Construction | 2021-01-01 | 2022-01-01 | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. | 5 |  |  |  | Georgios Vidalakis | Tameesha Hayes
CNAS | 3593 | PD&C | R'Garden Walk-in Cooler Installation |  |  | 2020-05-08 | In Construction | Complete Construction | 2021-06-01 | 2021-10-01 | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. | 3 |  |  |  | Richard Zapien | Vilma Kern
FAC-PLNG-DESIGN-CONST | 3529 | PD&C | DMFI(FY17-19) Physics 2000 Renewal - Handrail | PHYSICS |  | 2019-05-15 | In Construction | Complete Construction | 2021-05-01 | 2021-10-01 | Renewal of Physics 2000 Lecture Hall. May incl--ude paint, flooring, seating, A/V and lighting improvements. | 3 |  |  |  | Scott Donnell | John Franklin
PB&A | 3508 | PD&C | SOM Education Bldg 2 |  |  | 2019-03-04 | In Construction | Complete Construction | 2021-07-01 | 2023-05-01 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. | 8 |  |  |  | Melissa Garrety | Mihai Gavan
BCOE | 3428 | PD&C | MS&E Cleanroom Expansion | MAT SCI ENGR |  | 2018-04-04 | In Construction | Complete Construction | 2021-09-01 | 2021-10-01 | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | 1 |  |  |  | Todd Ambriz | Vilma Kern
CNAS | 3390 | PD&C | Field 11C-D CVC Screenhouse |  |  | 2018-01-08 | In Construction | Complete Construction | 2021-02-01 | 2021-12-01 | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. | 9 |  |  |  | Tracey Kahn | John Franklin
CAP PROG | 3234 | PD&C | UC Intellicenter 2nd Floor TI |  |  | 2016-12-21 | In Construction | Re-evaluating TABB Project Scope of Work | 2021-01-01 | 2021-12-31 | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. | 4 |  |  |  | ---- | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 2687 | PD&C | DM(FY14) Bourns Fire Alarm Sys Replcmt | BOURNS |  | 2019-06-18 | In Construction | Installaton of NFACP | 2021-06-01 | 2021-12-03 | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | 5 |  |  |  | ----- | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3035a | PD&C | DM(FY16) Spieth Hall Roof Replacement | SPIETH |  | 2016-02-25 | In Design | Bidding | 2021-12-01 | 2022-02-01 | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | 7 |  |  |  | ---- | Fernando Canon
UNDERGRADUATE EDUCATION | 3626 | PD&C | Rivera Library Room Modifications |  | A101A | 2021-02-10 | In Design | Bidding |  |  | Conduct room modifications to support new wall display on west wall Rivera A101A. Work needed: 1. West wall - ½” three-ply to support 12 x 55” displays over bookshelves. 2. West wall – drywall cover bookshelves any area not covered by the technology displays. 3. West wall – add electrical outlets as needed for new displays 4. North and south walls – add electrical for new motorized shades 5. Rivera A101A – add carpeting 6. Rivera A101A – paint room Notes: - Working with Chuck Forsyth in ITS and Bahram Mobasher from CNAS/Physics on project. - Israel and Chuck had a preliminary meeting with Enrico Baez from facilities to discuss project. - Point of contact: Israel Fletes and Charles Forsyth. Israel Fletes cellphone: 951-300-6693 | 1 |  |  |  | Israel Fletes | Vilma Kern
BCOE | 3624 | PD&C | CE-CERT Circuit Upgrade |  |  | 2021-03-03 | In Design | Bidding |  |  | We have an existing 208 VAC 100 Amp circuit. We would like to upgrade to a 200 Amp service. The existing service is located in the electrical room at 1084 Columbia. | 5 |  |  |  | Todd Ambriz | Tameesha Hayes
CNAS | 3599 | PD&C | MS&E 155 Pulsed Laser Deposition |  | 0155 | 2020-06-19 | In Design | Waiting for equipment from overseas |  |  | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. | 12 |  |  |  | Wendi Tapia | Tameesha Hayes
FAC-PLNG-DESIGN-CONST | 3548 | PD&C | DMFI(FY17-19) Fine Arts Performance Lab Ext | ARTS |  | 2019-09-05 | In Design | Bidding |  |  | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | 8 |  |  |  | Scott Donnell | Tameesha Hayes
CAP PROG | 3233 | PD&C | South Recreation Mall |  |  | 2016-12-16 | In Design | Bidding |  |  | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. | 99 |  |  |  | Jaime Enghbrecht | Daneca Stevens
PB&A | 3203 | PD&C | Plaza Seismic Structural Repairs | THE PLAZA |  | 2016-10-10 | In Design | Bidding |  |  | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | 22 |  |  |  | Sean Hatfield | Daneca Stevens
FAC-PLNG-DESIGN-CONST | 2368 | PD&C | Creekside Drainage Channel |  |  | 2016-05-19 | In Design | Funding & Approval |  |  | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. | 18 |  |  |  | ---- | Fernando Canon
FAC-PLNG-DESIGN-CONST | 3270 | PD&C | DM(FY17) Chapman Hall - Replace HVAC System | CHAPMAN |  | 2017-03-07 | In Design (Re-opened) | Bidding |  |  | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | 11 |  |  |  | Fernando Nunez | Tameesha Hayes
CNAS | 3559 | PD&C | USDA Screen House Expansion | GERMPLASM |  | 2019-10-04 | In Design by USDA | Construction by USDA |  |  | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | 10 |  |  |  | MaryLou Polek | Daneca Stevens
PB&A | 3636 | PD&C | Tunnel DAS |  |  | 2021-05-05 | In Funding | Bidding |  |  | Adding radio repeaters to the tunnel system to improve coverage in a high hazard work area. The project consists of adding a rooftop antenna, battery back-up, amplifier, repeater antennas, and coax runs through the tunnel system. A few items need to be mounted. Golden State Communications will need to interface additional system to the existing radio system. | 1 |  |  |  | Tracy Stark | Vilma Kern
VC-STU AFF | 3608 | PD&C | HUB2 Roof Repair |  |  | 2020-09-21 | In Funding | Secure Funding | 2021-09-01 | 2021-09-01 | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. | 3 |  |  |  | Brendan O'Brien | Tameesha Hayes
PB&A | 3515b | PD&C | DM(FY18) Elec Substation & Infra. Renewal |  |  | 2019-03-08 | In Programming | Complete Programming |  |  | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. | 2 |  |  |  | Ron Rector | John Franklin
PB&A | 9063 | PD&C | DM(FY20) Boyce Building Systems Improvements |  |  |  | In Programming | Design |  |  | Provide improvements to antiquated mechanical-electrical-plumbing systems to extend building useful life | [5 empty] | Tameesha Hayes
PB&A | 3507 | PD&C | Undergraduate Teaching & Learning Facility |  |  | 2019-03-04 | In Programming | DB Competition |  |  | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. | 9 |  |  |  | ---- | Dexter Galang
LIBR | 3644 | PD&C | Rivera Library Fire Suppression Study |  |  | 2021-06-25 | In Programming (Study) | Design |  |  | Request for estimate for installing fire suppression system in Rivera Library 4th floor and Secured area on Basement floor. | 1 |  |  |  | David Schuster | Vilma Kern
CAP PROG | 3612 | PD&C | Native American Landscape Garden |  | Ext | 2021-02-11 | In Programming (Study) | Design |  |  | Create a physical marker to commemorate the UCR Land Acknowledgement in the form of a Native American Landscape Garden (working name) at the proposed project location. | 15 |  |  |  | Uma R. | Vilma Kern
FAC-PLNG-DESIGN-CONST | 3499 | PD&C | Creekside Terrace Analysis (RE Proj) |  |  | 2019-02-14 | In Programming (Study) | Complete Study |  |  | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. | 13 |  |  |  | Blythe Wilson | Thomas Toepfer
PB&A | 3474 | PD&C | RUSD STEM High School |  |  | 2018-10-31 | In Programming (Study) | CEQA |  |  | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. | 14 |  |  |  | ----- | Thomas Toepfer
CAP PROG | 3452 | PD&C | Long Range Dev Plan - 2018 |  |  | 2018-07-16 | In Programming (Study) | Complete Study |  |  | New Long Range Development Plan (LRDP), with all required technical studies | 12 |  |  |  | Jacqueline Norman | Uma R.
VC-STU AFF | 3627 | PD&C | Costo Hall New Doors |  |  | 2021-03-04 | On Hold | On Hold |  |  | Add three (3) doors to divide new office designations in Costo Hall. Two of the doors require new frames | 8 |  |  |  | Brendan O'Brien | Daneca Stevens
UNEX | 3574 | PD&C | UNEX Roof Repair/Solar | UCR EXTEN CT |  | 2019-12-10 | On Hold | Departmental Approval |  |  | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | 2 |  |  |  | Sandy Navarro | Tameesha Hayes
CAP PROG | 3458 | PD&C | KUCR Replacement Project |  |  | 2018-07-16 | On Hold | Coordinating with North District |  |  | Proposed replacement of KUCR radio station facility | 16 |  |  |  | Blythe Wilson | Blythe Wilson
ATHLETICS | 3407 | PD&C | Athletics Media Room | S LCKRM/CONC |  | 2018-08-23 | On Hold | Department approval to move fwd |  |  | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | 4 |  |  |  | Johnathan Jensen | Fernando Nunez
CAP PROG | 3395 | PD&C | Recreation Fields Replacement |  |  | 2017-12-03 | On Hold | On Hold |  |  | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. | 13 |  |  |  | Tameesha Hayes | Daneca Stevens
CHASS | 3280 | PD&C | Athletics Dance Bldg Repairs | ATH DANCE |  | 2017-05-31 | On Hold/Funding | Department Approval/Funding |  |  | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | 1 |  |  |  | Paul Richardson | Fernando Nunez
PB&A | 3421 | PD&C | A-I Boiler Replacement | ABER INVER |  | 2018-03-19 | On Hold-Funding | CIB Approval |  |  | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | 6 |  |  |  | Sean Hatfield | John Franklin
VC-RED | 3640 | PD&C | MRB Circulation Pumps E-Power |  |  | 2021-06-30 | On-Hold | On-Hold |  |  | MRB Circulation Pumps e-Power | 1 |  |  |  | Tara Barthol | Vilma Kern
CNAS | 3618 | PD&C | NRS Prop 68 Study-James Reserve |  |  | 2021-02-02 | On-Hold | Approval to close or move forward |  |  | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. | 8 |  |  |  | Heather Constable | Fernando Nunez
CNAS | 3602 | PD&C | GH 16 Retractable Shade Cloth |  |  | 2020-07-14 | On-Hold | Secure Funding for Additional Scope |  |  | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 | 1 |  |  |  | Mireya Botello Santoyo | Vilma Kern
CNAS | 3391 | PD&C | NRS Motte Rimrock Res Cost Study |  |  | 2017-11-02 | On-Hold | Approval to close or move forward |  |  | Requesting recheck and recost of formal estimate for Motte Reserve Prop 84 for the Natural Reserve System. The former estimate was $763K. Purpose of study is to confirm, or augment the initial project valuation included with the Proposition 84 NRS grant application to install new structures at the Motte Rimrock Reserve site. | 99 |  |  |  | Kimberly Hammond, D. McWilliams | Fernando Nunez
PB&A | 9066 | PD&C | DM(FY20) Sproul HVAC |  |  |  | Pre-Programming | Programming |  |  | Equipment/Controls - Replace Heat Exchangers/VFD Pumps | [5 empty] | Daneca Stevens
PB&A | 9065 | PD&C | DM(FY20) Olmsted HVAC Repairs to Air Handlers |  |  |  | Pre-Programming | Programming |  |  | Equipment/Controls - Repairs to Air Handlers | [5 empty] | Vilma Kern
PB&A | 9064 | PD&C | DM(FY20) Olmsted HVAC Replace Economizers |  |  |  | Pre-Programming | Programming |  |  | Equipment/Controls: Replace economizers for fresh air controls for all Air handlers | [5 empty] | Vilma Kern
CNAS | 3658 | PD&C | CVWD Canal Water Delivery Design |  |  | 2021-09-02 | Pre-Programming | Programming |  |  | CVWD is under construction for delivering Colorado River (canal) water to the Oasis area. The project includes delivery to UCR at two sites, one North (60 acres) and one South (200 acres) of Avenue 72. Canal water should be available at both Delivery Points by January, 2023. IID engineering, PVC material, steel pipe, electrical supplies will require significant lead times. Hence, I recommend starting the design phase of these projects sooner than later. I included a Water Cost Comparison analysis presented in late 2020 to help justify capital improvements required prior to CVWD canal water delivery. |  |  |  |  | Sue Lee | Daneca Stevens
PB&A | 3656 | PD&C | Falkirk Standardized Balcony Drawings |  |  | 2021-09-02 | Pre-Programming | Programming |  |  | Provide professional design services to complete construction drawings that will standardize balcony demolition and window frame-in at each balcony location type. Miyamoto is the architect for the Falkirk Seismic project. Given their extensive knowledge of the facility, we would like to negotiate design services with them for this project. |  |  |  |  | Sean Hatfiled | Daneca Stevens
FAC-PLNG-DESIGN-CONST | 3652 | PD&C | 266 Frost Ct. Fence, Electric Meter, Lighting, Irrigation |  |  | 2021-08-17 | Pre-Programming | Programming |  |  | 266 Frost Court - Install fence utilizing rod iron gates already on hand at BG; install electrical meter and lighting for security purposes; install battery operated irrigation. |  |  |  |  | Yvonne Lujan | Daneca Stevens
CNAS | 3634 | PD&C | Botanic Garden Dome |  |  | 2021-04-13 | Pre-Programming | Secure Funding |  |  | Request is for an architect to draw a design for a replacement of current geodesic dome. Design can then be used as basis for fund-raising campaign to construct new dome. Dr. Holt, UCRBG Director, has been in discussions with Jacqueline Norman and Drew Hecht. Dome was constructed on site in 1980s, all wood, greatly deteriorated. Dome is unrepairable, unsafe, and closed to the public. Goal is to replace it with a structure as close to the original dome shape as possible but with modern functionality. We envision a structure with partial solid walls near the ground, then lath on upper walls and top, possibly cross shaped with doors at ends of the arms, and a domed center for taller plants. Should have “wood look” or at least maintain original sensibility since it is beloved as is, but needs a durable material! Function—house the collection of shade-requiring plants including prehistoric plants, subtropical plants, and others. Design should include space for plants inside around the edges and a wide walkway in a circle around a central display, suitable for tour groups, small gatherings, and photography. Arms extending in cross shape could house additional plants, displays, even sale plants. | 2 |  |  |  | Jodie Holt | Fernando Nunez
VC-STU AFF | 3583 | PD&C | SRC North Replace Bleachers |  |  | 2020-03-03 | Pre-Programming | Updated Proposal for Bleachers Cost |  |  | Replacement of the 3 set of bleachers on the SRC North main gym. | 7 |  |  |  | Michael Eason | Fernando Nunez
VC-STU AFF | 3512 | PD&C | Hinderaker VCSA Office | HINDERAKER | 2108ACDEF | 2019-03-19 | Pre-Programming | Programming |  |  | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | 5 |  |  |  | Christina Wong | Vilma Kern
CNAS | 3650 | PD&C | Greenhouse 16-3 Rebuild Estimate |  |  | 2021-08-02 | Pre-Programming (Insurance Claim) | Programming |  |  | We need an estimate to rebuild greenhouse 16-3 that burned down in a fire | 13 |  |  |  | Sue Lee | Vilma Kern
PB&A | 9068 | PD&C | Ag Ops Field 6B Pump Station |  |  | 2021-09-16 | Programming | Design |  |  | Provide downstream electrical engineering as-needed to facilitate UCR plan-check and inspection of Owner Furnished Contractor Installed agricultural pump station equipment. Power provided by Riverside Public Utilities and confirm existing RPU meter account based upon street address or if new account is required UCR shall apply. |  |  |  |  | Tom Toepfer | Daneca Stevens
CHASS | 3441 | PD&C | CHASS INTS 1121 Exercise Room | CHASS INT S |  | 2018-06-22 | Programming | Approval & Funding |  |  | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | 11 |  |  |  | Anna Finn | Daneca Stevens
PB&A | 3645 | PD&C | Falkirk Seismic Rating Study |  |  | 2021-07-12 | Programming (Study) | Complete Study |  |  | FALKIRK STRUCTURAL STUDY - provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | 2 |  |  |  | Sean Hatfield | D.Hecht/J.Franklin
CAP PROG | 3642 | PD&C | South District Planning Study |  |  | 2021-06-10 | Programming (Study) | Complete Study |  |  | The “South District” presents a unique opportunity to create a strong identity for academic and research expansion across the campus loop road with an emphasis on creating a transformative and synergistic new campus neighborhood. Its hillside location makes it highly visible from the freeway and the Core Campus, presenting a significant opportunity to enhance campus identity. The site’s high elevation also gives it unobstructed views outward. A holistic and integrated planning framework for its development is important to ensure alignment with broad planning strategies and principles in place for the campus, as established in land planning per the DRAFT 2021 Long Range Master Plan and the more detailed physical planning vision from the 2016 Physical Master Plan Study for this “opportunity site”, and its immediate context. The upcoming effort to update the campus’ Physical Design Framework document will further analyze the unique opportunities afforded by the South District, and leverage the design of the School of Business Building to establish organizing principles for how the area could be optimally redeveloped to its highest potential. | 19 |  |  |  | Uma R. | Uma R.
CNAS | 3623 | PD&C | NRS Prop 68 Study - Boyd |  |  | 2021-02-02 | Programming (Study) | Pending submittal of Prop 68 items |  |  | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ | 7 |  |  |  | Heather Constable | Fernando Nunez
PB&A | 3492 | PD&C | W.Campus Irrigation System Study |  |  | 2019-03-04 | Programming (Study) | Complete Study |  |  | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. | 10 |  |  |  | Scott Donnell | Daneca Stevens
FAC-PLNG-DESIGN-CONST | 3110 | PD&C | Ag Ops Cell Tower - New |  |  |  | Project is not funded or approved | Approve in CPMS & fund |  |  | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. | 99 |  |  |  | Yvonne Lujan | Yvonne Lujan
PB&A | 3382 | PD&C | West Lothian Restroom & Common Area Design | LOTHIAN HALL |  | 2017-09-29 | Project pushed to 2022 | Project pushed to 2022 |  |  | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | 20 |  |  |  | Sean Hatfield | John Franklin
FAC-PLNG-DESIGN-CONST | 3590a | PD&C | DMFI(FY17-19) Multiple Projects |  |  | 2020-03-30 | Projects to be assigned | Projects to be assigned |  |  | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. | 4 |  |  |  | Susan McFadden | Scott Donnell
INACTIVE P&B | 3541 | PD&C | Olmsted Sidewk/Tunnel V16 Repair | WATKINS |  | 2019-07-30 | Re-bid | Award Contract | 2021-11-01 | 2022-01-01 | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | 2 |  |  |  | Daneca Stevens | Daneca Stevens
PB&A | 2900 | PD&C | Batchelor Hall Systems Renewal | BATCHELOR |  | 2015-12-15 | Re-bid | Award Contract | 2021-12-01 | 2024-07-01 | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | 15 |  |  |  | Sharyl Murdock | John Franklin
SoB | 2725 | PD&C | School of Business Professional Schools |  |  | 2016-12-15 | Technical Criteria Phase | Design Builder Prequalification | 2022-09-26 | 2024-06-19 | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. | 1 |  |  |  | Leo Gonzalez | Blythe Wilson
PB&A | 3470 | PD&C | 2018 Campus Seismic Audit |  |  | 2018-11-06 | Tier III evaluations pending | Complete Review |  |  | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. | 17 |  |  |  | Drew Hecht | Drew Hecht
To view projects for a specific organization ONLY, click on the filter options HERE.

## Project Detail
Project Status Report | [5 empty] | Last Updated | 2021-10-01
FS
SL5 CAMPUS INTERIOR - HANG BANNERS, INSTALL HARDWARE
Project Reference No. | 22P000065
FS
Financials
Project Manager | Dan Lerman | Organization | VC-UNIV ADV | Prioritization Designate | Naysia Caldwell | PD&C Approved Budget
Contact/ Requestor | LISA CUSICK | Building |  | Project Service Unit | FS | FS Recharge Actuals To Date
CPMS # |  | Room |  | PD&C Org Priority No. |  | Core / Non-Core | #N/A
FS # | 22P000065 | Request Date | 2021-09-09 | FS Org Priority No.
For Faculty Hire
Project Description | Banners to be hung within Campus interior. Installation of banner hardware on Pierce Hall and Skye Hall.
FS
Project Status
Project Status | QUEUE TO START |  |  |  | START Date
Next Steps |  |  |  |  | COMPLETION Date
IRT Status
FS
Campus Impact (i.e. excessive noise / limited access / utility shutdown)
Description
Impact Start
Impact End
FS
PM Notes |  | Project Manager | Dan Lerman | PM Email | daniel.lerman@ucr.edu | PM Phone | 951-827-6224
09/29/21 O-ANS: Converted to project per Paul D / Dan L to manage installation of banner hardware. Coordinating with customer Brad Rowe re: specs of banners prior to install.
FS
Scope |  | Reviewer | Dan Lerman | BZM Email | daniel.lerman@ucr.edu | BZM Phone | 951-827-4214
Scope Completed
To view more detailed information for a specific project, type in the Project Reference No. or clear the field and then scroll through the dropdown list HERE.

## FS Closed Projects
CLOSED Facilities Services Summary Report | [7 empty] | **Closed FS Projects include projects that have been Completed, Canceled by FS, Canceled by Client and projects To Be Performed by PD&C.
Total Closed FS Projects |  | 99
Last Updated | 2021-10-01 | FS Project Summary
Organization | Project Ref No. | Project Service Unit | Project Title | Building | Room | Request Date | Current Status | Completed Date | Fiscal Year | FS Org Priority No. | For New Faculty Hire? | Contact | Proj Manager
BCOE | 21P000173 | FS | SL5 BOURNS HALL OFFICE B353 - PATCH & PAINT (POSS TOUCH UP) |  | B0353 | 2021-05-05 | CANCELED BY CLIENT | 2021-09-13 | FY 21-22 | X |  | ROBERT LOPEZ-A | PAUL DITTY
CHASS | 20P000211 | FS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | ARTS | 54 | 2019-11-07 | CANCELED BY CLIENT | 2021-01-19 | FY 20-21 | R1 |  | PAUL RICHARDSON | Dan Lerman
CNAS | 20P000046 | FS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | HOMER D. CHAPMAN HALL | 0001 | 2019-07-31 | CANCELED BY CLIENT | 2021-05-12 | FY 20-21 | R2 |  | WILLIAM SUTTON | Enrico Baez
SOM | 19P000659 | FS | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 230 | 2019-06-11 | CANCELED BY CLIENT | 2020-08-05 | FY 20-21 | 5 |  | CYNTHIA CAROLINA | Dan Lerman
VC-UNIV ADV | 20P000309 | FS | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES | 1955 CHICAGO | 200 | 2020-01-10 | CANCELED BY FS | 2020-12-16 | FY 20-21 | 1 |  | SARAH KARSON | PAUL DITTY
BCOE | 20P000210 | FS | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | CHUNG HALL | 224 | 2019-11-05 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 2 |  | MARGARET SOUDER | Dan Lerman
VC-RED | 20P000197 | FS | SL5 UOB 210 - SOUND PROOF INSTALLATION | UNIV OFC BLD | 210 | 2019-10-24 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 2 |  | CRYSTAL JIMENEZ | Dan Lerman
LIBR | 20P000188 | FS | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 | ORBACH LIB | 204 | 2019-10-23 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 1 |  | DAVID SCHUSTER | Dan Lerman
CHASS | 20P000183 | FS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | HUM & SOC SC | 1202 | 2019-10-18 | CANCELED BY FS | 2020-11-19 | FY 20-21 | R2 |  | PAUL RICHARDSON | Dan Lerman
VC-RED | 20P000047 | FS | SL5 ADVANCED NEUROIMAGING | ADV NEURO |  | 2019-07-31 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 3 |  | CHELSEA EVELYN | Dan Lerman
BCOE | 20P000039 | FS | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE | BOURNS | A0318 | 2019-05-13 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 4 |  | LOUIS SANDOVAL | Dan Lerman
BCOE | 19P000624 | FS | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | BOURNS | A0346 | 2019-05-15 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 3 |  | LOUIS SANDOVAL | Dan Lerman
CNAS | 19P000514 | FS | SL5 SKYE 268-PROJECTOR INSTALL | SKYE HALL | 0268 | 2019-02-27 | CANCELED BY FS | 2020-11-19 | FY 20-21 | R7 |  | JAMES MARBERRY | Dan Lerman
BCOE | 19P000502 | FS | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | CHUNG HALL | 444 | 2019-02-19 | CANCELED BY FS | 2020-11-19 | FY 20-21 | R3 |  | RICHARD BAIN | Dan Lerman
BCOE | 19P000427 | FS | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | CHUNG HALL | 453 | 2019-01-03 | CANCELED BY FS | 2020-11-19 | FY 20-21 | R2 |  | ROBERT LOPEZ-A | Dan Lerman
VC-RED | 19P000225 | FS | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | UV BLDG A | 0204A | 2018-08-28 | CANCELED BY FS | 2020-11-19 | FY 20-21 | 3 |  | CRYSTAL JIMENEZ | Dan Lerman
VC-RED | 22P000008 | FS | SL5 MRB VARIOUS LAB SUPPORT - IACUC INSP TINTED WINDOWS NEEDED |  |  | 2021-07-14 | COMPLETE | 2021-08-25 | FY 21-22 | R1 | YES | TARA BARTHOL | Enrico Baez
SoB | 21P000215 | FS | SL5 ANDERSON 0202 - PATCH/PAINT NEW HIRE |  | 202 | 2021-06-30 | COMPLETE | 2021-09-29 | FY 21-22 | X | YES | ANGELA CHANG | PAUL DITTY
BCOE | 21P000214 | FS | SL5 CHUNG HALL NEW FACULTY OFFICE 454 - PATCH & PAINT |  | 454 | 2021-06-29 | COMPLETE | 2021-09-15 | FY 21-22 | X | YES | ROBERT LOPEZ-A | PAUL DITTY
BCOE | 21P000213 | FS | SL5 CHUNG HALL 0452 - PATCH AND PAINT NEW FACULTY |  | 452 | 2021-06-29 | COMPLETE | 2021-09-15 | FY 21-22 | X | YES | ROBERT LOPEZ-A | PAUL DITTY
BCOE | 21P000207 | FS | SL5 BOURNS HALL A325 OFFICE - PATCH & PAINT INCOMING FACULTY |  | A0325 | 2021-06-18 | COMPLETE | 2021-09-09 | FY 21-22 | X | YES | ROBERT LOPEZ-A | PAUL DITTY
BCOE | 21P000198 | FS | SL5 CHUNG HALL OFFICE 409 - PATCH & PAINT (NEW FACULTY) |  | 409 | 2021-06-04 | COMPLETE | 2021-09-20 | FY 21-22 | X | YES | ROBERT LOPEZ-A | PAUL DITTY
SOM | 21P000191 | FS | SL5 ORBACH LIB BASEMENT - PAINT WALL AT NEW SIM CENTER |  | BASEMENT | 2021-05-28 | COMPLETE | 2021-08-19 | FY 21-22 | X |  | CYNTHIA CAROLINA | PAUL DITTY
BCOE | 21P000189 | FS | SL5 CHUNG HALL 0355 - WALLS NEED TO BE PATCHED AND PAINTED |  | 355 | 2021-05-27 | COMPLETE | 2021-09-23 | FY 21-22 | X |  | SARA GALLOWAY | PAUL DITTY
PB&A | 21P000183 | FS | SL5 OBAN A&B - PROJECT PORCH REPAIRS 2, 10, 18, 26 |  |  | 2021-05-13 | COMPLETE | 2021-09-02 | FY 21-22 |  |  | TRENTON MABEE | Chris Pillen
BCOE | 21P000174 | FS | SL5 BOURNS HALL OFFICE B355 - PATCH & PAINT |  | B0355 | 2021-05-05 | COMPLETE | 2021-09-13 | FY 21-22 | X |  | ROBERT LOPEZ-A | PAUL DITTY
FAC-PLNG-DESIGN-CONST | 21P000160 | FS | SL5 CHAPMAN HALL 109 - REPAIR COUNTERTOPS |  | 109 | 2021-08-06 | COMPLETE | 2021-09-02 | FY 21-22 |  |  | DAN LERMAN | Dan Lerman
BCOE | 21P000154 | FS | SL5 CHUNG HALL OFFICE 455 - MINOR PATCH & PAINT TOUCH UP |  | 455 | 2021-04-02 | COMPLETE | 2021-09-15 | FY 21-22 | X | YES | ROBERT LOPEZ-A | PAUL DITTY
SOM | 21P000137 | FS | SL5 WEBBER HALL - ACCESS CONTROL |  | 1247 | 2021-03-09 | COMPLETE | 2021-07-15 | FY 21-22 | R1 |  | DEBORAH TRUJILLO | Dan Lerman
CHASS | 21P000111 | FS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | GORDON S. WATKINS HALL | 2144 | 2020-11-18 | COMPLETE | 2021-05-24 | FY 20-21 | X | YES | BECKY CAMPBELL | Paul Ditty
CHASS | 21P000110 | FS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | GORDON S. WATKINS HALL | 2146 | 2020-11-18 | COMPLETE | 2021-05-24 | FY 20-21 | X | YES | BECKY CAMPBELL | Paul Ditty
CHASS | 21P000109 | FS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY |  | 1146 | 2020-11-18 | COMPLETE | 2021-05-24 | FY 20-21 | X | YES | BECKY CAMPBELL | PAUL DITTY
VC-RED | 21P000102 | FS | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | SPIETH | 348, 352 & 363 | 2020-10-29 | COMPLETE | 2020-12-08 | FY 20-21 | TBD |  | DIERK BIGGS | Paul Ditty
VC-RED | 21P000079 | FS | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | PSYCHOLOGY BUILDING |  | 2020-09-25 | COMPLETE | 2021-04-01 | FY 20-21 | X |  | LESLIE KARPINSKI | PAUL DITTY
VC-RED | 21P000078 | FS | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MULTIDISCIPLINARY RESEARCH BUILDING |  | 2020-09-23 | COMPLETE | 2021-04-15 | FY 20-21 | 1 |  | TARA BARTHOL | DAN LERMAN
CHASS | 21P000058 | FS | SL5 HUMNITIES 3413 (DEAN SUITE) NAIL REMOVAL, PATCH, AND PAINT |  | 3413 | 2020-08-25 | COMPLETE | 2021-08-16 | FY 21-22 | X |  | JENNIFER HAMILTON | PAUL DITTY
BCOE | 21P000037 | FS | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | CHUNG HALL | 427 | 2020-07-31 | COMPLETE | 2020-11-30 | FY 20-21 | X | YES | ROBERT LOPEZ-A | PAUL DITTY
BCOE | 21P000019 | FS | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | MARLAN & ROSEMARY BOURNS HALL | A305 | 2020-07-20 | COMPLETE | 2021-06-02 | FY 20-21 | 3 | YES | ROBERT LOPEZ-A | Dan Lerman
BCOE | 21P000014 | FS | SL5 BOURNS HALL OFFICE A149 - PATCH & PAINT HOLES ON WEST WALL |  | A0149 | 2020-07-14 | COMPLETE | 2021-08-13 | FY 21-22 | X |  | ROBERT LOPEZ-A | PAUL DITTY
CNAS | 21P000009 | FS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | CHEMICAL SCIENCES |  | 2020-07-08 | COMPLETE | 2021-06-02 | FY 20-21 | 1 | YES | NATASHA GONZALES | DAN LERMAN
PB&A | 21P000003 | FS | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | CC LIND 691 | ROOF | 2020-06-26 | COMPLETE | 2021-04-09 | FY 20-21 | R1 |  | SEAN HATFIELD | Enrico Baez
CNAS | 21P000001 | FS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | HOWARD SAMUEL FAWCETT LABORATORY |  | 2020-06-08 | COMPLETE | 2021-07-15 | FY 21-22 | 2 | YES | LINDA WALLING | DAN LERMAN
CHASS | 20P000470 | FS | SL5 HMSS 3210 - PATCH/PAINT | HUMANITIES BUILDING | 3210 | 2020-06-24 | COMPLETE | 2021-02-18 | FY 20-21 | X | YES | PAUL RICHARDSON | PAUL DITTY
CHASS | 20P000469 | FS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 222 | 2020-06-23 | COMPLETE | 2021-02-12 | FY 20-21 | X | YES | PAUL RICHARDSON | PAUL DITTY
VC-RED | 20P000468 | FS | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | HERMAN T. SPIETH HALL | 364 | 2020-06-23 | COMPLETE | 2021-04-01 | FY 20-21 | X |  | JOHNNY PHAN | PAUL DITTY
SOM | 20P000467 | FS | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | HERBERT JOHN WEBBER HALL | 1247 | 2020-06-19 | COMPLETE | 2021-02-22 | FY 20-21 | X | YES | CYNTHIA CAROLINA | PAUL DITTY
CHASS | 20P000464 | FS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | HUMANITIES BUILDING | 3001 | 2020-06-18 | COMPLETE | 2021-02-18 | FY 20-21 | X | YES | PAUL RICHARDSON | PAUL DITTY
CHASS | 20P000463 | FS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | HUMANITIES BUILDING | 2000 | 2020-06-18 | COMPLETE | 2021-02-18 | FY 20-21 | X | YES | PAUL RICHARDSON | PAUL DITTY
CHASS | 20P000462 | FS | SL5 HMSS 2001 - PAINT OFFICE / CLEAN FLOOR NEW FACULTY HIRE | HUMANITIES BUILDING | 2001 | 2020-06-18 | COMPLETE | 2021-03-19 | FY 20-21 | X | YES | PAUL RICHARDSON | Paul Ditty
CHASS | 20P000453 | FS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 142 | 2020-06-18 | COMPLETE | 2021-04-05 | FY 20-21 | X | YES | PAUL RICHARDSON | PAUL DITTY
BCOE | 20P000450 | FS | SL5 CHUNG HALL ROOMS 217, 218, 219 - PATCH & PAINT |  | 217, 218, 219 | 2020-06-12 | COMPLETE | 2021-05-13 | FY 20-21 | X | YES | ROBERT LOPEZ-A | Paul Ditty
BCOE | 20P000449 | FS | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | CHUNG HALL | 461 | 2020-06-11 | COMPLETE | 2020-11-09 | FY 20-21 | X | YES | ROBERT LOPEZ-A | PAUL DITTY
BCOE | 20P000448 | FS | SL5 CHUNG HALL ROOM 216 - PATCH & PAINT |  | 216 | 2020-06-11 | COMPLETE | 2021-05-11 | FY 20-21 | X | YES | ROBERT LOPEZ-A | Paul Ditty
CHASS | 20P000446 | FS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | CHASS INTERDISCIPLINARY NORTH | 4047 | 2020-06-04 | COMPLETE | 2021-02-12 | FY 20-21 | X | YES | PAUL RICHARDSON | PAUL DITTY
CNAS | 20P000445 | FS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 279 | 2020-06-03 | COMPLETE | 2021-05-14 | FY 20-21 | 3 | YES | WILLIAM SUTTON | DAN LERMAN
CNAS | 20P000419 | FS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | HERMAN T. SPIETH HALL | 2312 | 2020-04-22 | COMPLETE | 2021-03-18 | FY 20-21 | X | YES | ESTELLA DAVALOS | PAUL DITTY
BCOE | 20P000413 | FS | SL5 BOURNS A-WING 1ST FLOOR ROOM A159A - EAST WALL PATCH & PAINT |  | A0159A | 2020-04-09 | COMPLETE | 2021-08-13 | FY 21-22 | X |  | ROBERT LOPEZ-A | PAUL DITTY
CHASS | 20P000403 | FS | SL5 OLMSTED 232 - PAINT OFFICE | JOHN W. OLMSTED HALL | 2321 | 2020-03-13 | COMPLETE | 2021-02-11 | FY 20-21 | X | YES | PAUL RICHARDSON | Paul Ditty
CNAS | 20P000397 | FS | SL5 ENTOMOLOGY 139 - PATCH AND PAINT OFFICE | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 0139 | 2020-03-05 | COMPLETE | 2021-04-16 | FY 20-21 | X | YES | WILLIAM SUTTON | Paul Ditty
CHASS | 20P000387 | FS | SL5 HMSS RM 3610 - PLEASE PATCH AND PAINT WALL |  | 3610 | 2020-03-02 | COMPLETE | 2021-09-29 | FY 21-22 | X |  | JULIE SALGADO | PAUL DITTY
CHASS | 20P000370 | FS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | GORDON S. WATKINS HALL | 1311 | 2020-02-19 | COMPLETE | 2021-04-30 | FY 20-21 | 1 | YES | PAUL RICHARDSON | DAN LERMAN
CNAS | 20P000366 | FS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | HERMAN T. SPIETH HALL | 2375 / 2375-A | 2020-02-19 | COMPLETE | 2021-07-16 | FY 21-22 | 7 | YES | SHERICE UNDERWOOD | DAN LERMAN
BCOE | 20P000363 | FS | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | WINSTON CHUNG HALL | 433 | 2020-02-13 | COMPLETE | 2021-02-22 | FY 20-21 | X | YES | MANGLAI ZHOU | PAUL DITTY
CNAS | 20P000320 | FS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | HERMAN T. SPIETH HALL | 1303 | 2019-11-20 | COMPLETE | 2021-06-11 | FY 20-21 | 4 |  | ESTELLA DAVALOS | DAN LERMAN
BCOE | 20P000310 | FS | SL5 BOURNS A-WING A129 - PATCH & PAINT | MARLAN & ROSEMARY BOURNS HALL | A0129 | 2020-01-10 | COMPLETE | 2021-02-04 | FY 20-21 | X | YES | ROBERT LOPEZ-A | PAUL DITTY
BCOE | 20P000253 | FS | SL5 BOURNS HALL LAB B156 - EXHAUST SYSTEM | MARLAN & ROSEMARY BOURNS HALL | B0156 | 2019-12-11 | COMPLETE | 2021-04-30 | FY 20-21 | 1 |  | LOUIS SANDOVAL | DAN LERMAN
CNAS | 20P000248 | FS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT | HERBERT JOHN WEBBER HALL | 1223 + 1223-A | 2019-11-27 | COMPLETE | 2021-06-02 | FY 20-21 | 5 |  | SHARYL MURDOCK | Dan Lerman
CNAS | 20P000247 | FS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | SPIETH | 2110 + 2118 | 2019-11-27 | COMPLETE | 2021-01-19 | FY 20-21 | 6 | YES | ESTELLA DAVALOS | Dan Lerman
VC-RED | 20P000230 | FS | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | BOURNS | B116C & B116D | 2019-11-18 | COMPLETE | 2020-11-19 | FY 20-21 | 1 |  | KRASSIMIR BOZHILOV | Dan Lerman
BCOE | 20P000221 | FS | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | 2019-11-15 | COMPLETE | 2021-01-19 | FY 20-21 | 3 |  | HONG XU | Dan Lerman
VC-RED | 20P000218 | FS | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | HERMAN T. SPIETH HALL | 347 | 2019-05-17 | COMPLETE | 2021-05-14 | FY 20-21 | 2 |  | DIERK BIGGS | DAN LERMAN
CHASS | 20P000215 | FS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | PSYCHOLOGY1 | 3rd Floor | 2019-11-07 | COMPLETE | 2021-01-19 | FY 20-21 | 3 |  | JAY MELASHENKO | Dan Lerman
CHASS | 20P000214 | FS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | PSYCHOLOGY1 | 2nd Floor | 2019-11-07 | COMPLETE | 2020-09-30 | FY 20-21 | 2 |  | JAY MELASHENKO | Dan Lerman
CHASS | 20P000213 | FS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS | CHASS INT S | 2117A, 2117C, 2117D, 2117E | 2019-11-08 | COMPLETE | 2020-08-05 | FY 20-21 | R1 |  | PAUL RICHARDSON | Dan Lerman
ATHLETICS | 20P000208 | FS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | ATH DANCE | 50 | 2019-11-04 | COMPLETE | 2021-01-28 | FY 20-21 | 1 |  | JOSEPH ERBLAND | Dan Lerman
CNAS | 20P000202 | FS | SL5 SKYE HALL 361 RENOVATION PROJECT | SKYE HALL | 361 | 2019-10-30 | COMPLETE | 2020-09-30 | FY 20-21 | 1 |  | JAMES MARBERRY | Dan Lerman
CNAS | 20P000144 | FS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | ALFRED M. BOYCE HALL | 3432, 3432A, 3446, 3446A | 2019-09-26 | COMPLETE | 2021-04-30 | FY 20-21 | 3 |  | MATTHEW ULRICH | Dan Lerman
BCOE | 20P000135 | FS | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MAT SCI ENGR | 75 | 2019-09-19 | COMPLETE | 2020-09-30 | FY 20-21 | 1 |  | MARK HEIDEN | Dan Lerman
SOM | 20P000054 | FS | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | 2019-07-31 | COMPLETE | 2020-09-30 | FY 20-21 | 2 |  | CYNTHIA CAROLINA | Dan Lerman
VC-RED | 20P000026 | FS | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | LIFE SCIENCE | Basement Level | 2019-07-19 | COMPLETE | 2021-01-19 | FY 20-21 | 1 |  | DIERK BIGGS | Dan Lerman
GRAD DIV | 20P000003 | FS | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | UNIVERSITY OFFICE BUILDING |  | 2019-07-02 | COMPLETE | 2021-04-15 | FY 20-21 | 1 |  | CYNTHIA CARDENAS | Dan Lerman
PB&A | 19P000687 | FS | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | HUB | Various | 2019-06-26 | COMPLETE | 2020-08-05 | FY 20-21 | R1 |  | MANNY SANCHEZ | Dan Lerman
SOM | 19P000660 | FS | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | 2019-06-11 | COMPLETE | 2020-09-30 | FY 20-21 | 1 |  | BRANDON BARBOSA | Dan Lerman
BCOE | 19P000600 | FS | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | BOURNS | B0316 | 2019-05-09 | COMPLETE | 2020-08-05 | FY 20-21 | 2 |  | KATHALENA COCKER | Dan Lerman
CNAS | 19P000547 | FS | SL5 SPIETH HALL 1363-RENOVATION | SPIETH | 1363 | 2019-03-26 | COMPLETE | 2020-08-05 | FY 20-21 | R3 | YES | ESTELLA DAVALOS | Dan Lerman
CNAS | 19P000539 | FS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | PHYSICS BUILDING | 1132 | 2019-03-19 | COMPLETE | 2021-04-15 | FY 20-21 | 3 |  | WENDI TAPIA | Dan Lerman
ENROLLMENT SERVICES | 19P000517 | FS | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | 2019-03-07 | COMPLETE | 2021-01-19 | FY 20-21 | 1 |  | DANIELLE GARCIA | Dan Lerman
CNAS | 19P000485 | FS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | HOMER D. CHAPMAN HALL | 9 | 2019-01-29 | COMPLETE | 2021-04-01 | FY 20-21 | 1 |  | WILLIAM SUTTON | Dan Lerman
CNAS | 19P000474 | FS | SL5 HEADHOUSE 8-AC INSTALLATION | GH08 | 881 | 2019-01-29 | COMPLETE | 2021-01-19 | FY 20-21 | 7 |  | NANCY FERGUSON | Dan Lerman
FAC-PLNG-DESIGN-CONST | 19P000466 | FS | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | SPROUL | 2225 | 2019-01-22 | COMPLETE | 2020-08-05 | FY 20-21 | 1 |  | Monty Anderson | Dan Lerman
ITS | 19P000433 | FS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | C&C CARPORT | 161 | 2019-01-07 | COMPLETE | 2020-08-05 | FY 20-21 | R1 |  | SHELLEY GUPTA | Dan Lerman
PB&A | 19P000414 | FS | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | POLICE BLDG | 100 | 2018-12-17 | COMPLETE | 2020-08-05 | FY 20-21 | 1 |  | Seth Morrison | Dan Lerman
CHANCELLOR | 19P000407 | FS | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | HINDERAKER | 1101 | 2018-12-11 | COMPLETE | 2020-08-05 | FY 20-21 | 1 |  | ALEXIS RAMBAUD | Dan Lerman
CNAS | 19P000193 | FS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | GENOMICS | 4231 | 2018-08-20 | COMPLETE | 2020-08-05 | FY 20-21 | 41 |  | AIMEE GONZALES | Dan Lerman
VC-STU AFF | 18P000214 | FS | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | HEALTH SERV |  | 2017-12-08 | COMPLETE | 2021-01-19 | FY 20-21 | 2 |  | GLORIA VERA | Dan Lerman
FAC-PLNG-DESIGN-CONST | 2682 | PD&C | DM(FY14) Rivera Library Arches/Arcade Repair | RIVERA LIB |  | 2016-05-06 | Complete | 2021-07-01 | FY 21-22 |  |  | Monty Anderson | Scott Donnell
VC-STU AFF | 20P000196 | FS | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | JEANETTE AND RUPERT COSTO HALL |  | 2019-10-24 | TO BE PERFORMED BY PD&C | 2021-02-25 | FY 20-21 | R1 |  | BRENDAN O'BRIEN | Enrico Baez
BCOE | 20P000067 | FS | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS | B-Wing | 2016-11-14 | TO BE PERFORMED BY PD&C | 2020-11-19 | FY 20-21 | R1 |  | MARGARET SOUDER | Dan Lerman
CNAS | 19P000504 | FS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH | 2349 | 2019-02-20 | TO BE PERFORMED BY PD&C | 2020-11-19 | FY 20-21 | 5 |  | ESTELLA DAVALOS | Dan Lerman
CNAS | 18P000453 | FS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | DELFINO HHSE |  | 2018-05-25 | TO BE PERFORMED BY PD&C | 2020-12-07 | FY 20-21 | 17 |  | MATTHEW ULRICH | Dan Lerman

## FS Summary by Org
College/Org | PROJECT INTAKE | ESTIMATE | QUEUE TO START | PLAN DEVELOPMENT/CHECK | IN PROGRESS | QUALITY CHECK OF WORK | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | HOLD - FACILITIES SERVICES | IRT REVIEW | CANCELED BY CLIENT | CANCELED BY FS | TO BE PERFORMED BY PD&C | COMPLETE | Grand Totals
ATHLETICS | [13 empty] | 0
BAS | [13 empty] | 0
BCOE |  |  | 3 |  | 1 | [5 empty] | 5 | 1 | 9 | 19
CAMPUS | 1 | [12 empty] | 1
CAP PROG | [13 empty] | 0
CAS | [13 empty] | 0
CHANCELLOR | [13 empty] | 0
CHASS |  |  | 5 |  | 2 |  |  |  |  | 1 | 1 |  | 2 | 11
CNAS |  | 1 | 9 |  | 1 |  |  | 1 |  | 1 | 1 | 2 | 2 | 18
ENROLLMENT SERVICES | [7 empty] | 1 | [5 empty] | 1
FAC-PLNG-DESIGN-CONST |  |  | 2 | [9 empty] | 2 | 4
GRAD DIV |  |  | 1 | [10 empty] | 1
GSOE | [13 empty] | 0
ITS | [13 empty] | 0
LIBR | [10 empty] | 1 |  |  | 1
PALM DESERT GRAD CTR | [13 empty] | 0
PB&A |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 | 3
PROVOST/EVC | [13 empty] | 0
SoB | [12 empty] | 1 | 1
SOM |  |  | 3 | [6 empty] | 1 |  |  | 2 | 6
SPP | [13 empty] | 0
UNDERGRAD ED | [13 empty] | 0
VC-RED |  |  | 1 | [7 empty] | 3 |  | 1 | 5
VC-STU AFF |  |  | 3 | [8 empty] | 1 |  | 4
VC-UNIV ADV |  |  | 1 | [7 empty] | 1 |  |  | 2
Grand Totals | 1 | 1 | 29 | 0 | 4 | 0 | 0 | 3 | 0 | 3 | 12 | 4 | 20 | 77
44470

## FS High Level Summary
38 | 15 | 20 | 6 | [5 empty] | 263 | 277 | 159 | 58
Active Projects1 | Inactive Projects2 | Completed in FY 21 - 22 | Faculty Hire Related Projects (Active Projects) | [5 empty] | Completed FY 17 - 18 | Completed FY 18 - 19 | Completed FY 19 - 20 | Completed FY 20 - 21
Progress Summary between Minor Renovation Meetings | [5 empty] | Data as of | 2021-10-01
STATUS | Stats Last Meeting | CURRENT Stats | Progress made between report periods
PROJECT INTAKE | 2 | 1 | 1 removed from PROJECT INTAKE
ESTIMATE | 1 | 1 | 0 added to ESTIMATE
QUEUE TO START | 38 | 29 | 9 removed from QUEUE TO START
PLAN DEVELOPMENT/CHECK | 0 | 0 | 0 added to PLAN DEVELOPMENT/CHECK
IN PROGRESS | 4 | 4 | 0 added to IN PROGRESS
QUALITY CHECK OF WORK | 0 | 0 | 0 added to QUALITY CHECK OF WORK
HOLD - CUSTOMER EQUIPMENT/SCHEDULE | 0 | 0 | 0 added to HOLD - CUSTOMER EQUIPMENT/SCHEDULE
HOLD - FACILITIES SERVICES | 3 | 3 | 0 added to HOLD - FACILITIES SERVICES
IRT REVIEW | 0 | 0 | 0 added to IRT REVIEW
CANCELED BY CLIENT | 3 | 3 | 0 added to CANCELED BY CLIENT
CANCELED BY FS | 12 | 12 | 0 added to CANCELED BY FS
TO BE PERFORMED BY PD&C | 4 | 4 | 0 added to TO BE PERFORMED BY PD&C
COMPLETE | 60 | 20 | 40 removed from COMPLETE
1 Green text denotes "Active Project"
2 Red text denotes "Inactive Project" (IRT Review Status defined as project scope reviewed by FS and is beyond FS scope; project to be reviewed by IRT Review/PD&C)
Progress Summary Stats Paint Only Projects vs. Multi-Trade |  |  | 2021-10-01 | 2021-09-16 | Paul Ditty |  |  | 2021-10-01 |  | 2021-09-16
| PAINT ONLY PROJECTS |  |  |  |  | MULTI-TRADE PROJECTS
| FACULTY HIRE | NOT FACULTY HIRE | PAINT TOTAL | Previous Stats | Change | FACULTY HIRE | NOT FACULTY HIRE | MULTI-TRADE TOTAL |  | Previous Stats | Change
PROJECT INTAKE | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  | 2 | -1
ESTIMATE | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  | 1 | 0
QUEUE TO START | 6 | 20 | 26 | 36 | -10 | 0 | 3 | 3 |  | 2 | 1
PLAN DEVELOPMENT/CHECK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
IN PROGRESS | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 |  | 4 | 0
QUALITY CHECK OF WORK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
HOLD - CUSTOMER EQUIPMENT/SCHEDULE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
HOLD - FACILITIES SERVICES | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 |  | 0 | 0
IRT REVIEW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
ALL ACTIVE Projects Total | 6 | 23 | 29 | 39 | -10 | 0 | 9 | 9 |  | 9 | 0
CANCELED BY CLIENT | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 |  | 3 | 0
CANCELED BY FS | 0 | 1 | 1 | 1 | 0 | 0 | 11 | 11 |  | 11 | 0
TO BE PERFORMED BY PD&C | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 |  | 4 | 0
ALL INACTIVE Projects Total | 0 | 1 | 1 | 1 | 0 | 0 | 18 | 18 |  | 18 | 0
COMPLETE | 20 | 3 | 23 | 23 | 0 | 6 | 31 | 37 |  | 37 | 0

## q_Report_Integrated (hidden)
Proj_Ref_No | CPMS_No | Work_Order_No | IRT | Org | Project_Title | Project_Description | Building | Room | Current_Status | Org_Leadership | Org_Contact (Prioritization Designate) | Contact | Contact_2 | Proj_Mgr | Org_Priority | FS_Priority | FS_Priority_Last | For_Faculty_Hire | Approved_Budget | FS_Recharge_Costs | Project_Initiated | Next_Major_Milestone | Const_Start | Construction_Completion | Impact_Description | Impact_Date_Start | Impact_Date_End | PM_Notes | Scope_Date | Scope_Reviewer | Scope_Notes | Scope_Complete | Completed Date | Quarter Submitted | Owner | IRT? | Requested Year | Data Pulled On | FY | Recharge?
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUMANITIES BUILDING | 3210 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-24 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/10/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-08-01 | FY 20-21
3471 | 3471 |  | FALSE | VC-STU AFF | HUB Electrical Sub Meter Installation | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Bidding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 4 |  |  | FALSE | 200000 |  | 2018-08-20 | Award Contract | 2021-09-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2018 | 2021-08-01
3632 | 3632 |  | FALSE | ATHLETICS | SRC North Instant Replay System | Possible update of instant replay system in Student Recreation Center North to include volleyball if mandate by Big West Conference is enacted. This will include placing cameras on the ends of the court that will send signal back to the control room and could involve additional wiring to courtside connection boxes. Scope may include upgrading audio connections. Volleyball season starts in late August... first home game TBD. No charges to this FAU unless Athletics notified in advance of work to be performed. Work Notes: Project will require coordination not only with Athletics but must also with Recreation (Mike Eason), and their scheduling may affect above dates. Possible vendor to be consulted is TechNet who has indicated ability to do such a project in recent times. |  |  | Delayed until 8/2022 per Athletics | Tamica Smith Jones | Joe Erbland | Joe Erbland |  | Tameesha Hayes |  |  |  | FALSE |  |  | 2021-04-01 | Delayed until 8/2022 per Athletics | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | Design | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 2015-12-02 | Bidding | [12 empty] | PD&C | 0 | 2015 | 2021-08-01
3631 | 3631 |  | FALSE | ITS | SOMED 1 UPS | The Information Technology Solutions (ITS) intends to replace its existing UPS unit with a state of the art systems that will support all of the requirements set-forth by the University of California, Riverside ITS and Facilities departments. Our primary objective is to provide ITS critical services and various other software applications. The ITS department would like to Procure (1) redundant UPS System with all accessories and maintenance for three years after warranty (AMC). Procure One Replacement 500KW UPS Unit, Installation of New UPS, Removal and Disposal of Old UPS components, Startup Services for New UPS, Electrical Installation of New UPS and Removal of Rental UPS connections (High Voltage) |  | 1625 | Design | Danna Gianforte | Shelley Gupta | Cesar Higueros |  | Tameesha Hayes |  |  |  | FALSE |  |  | 2021-07-22 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Design | Gerry Bomotti | TBD | ---- |  | Fernando Canon | 1 |  |  | FALSE | 33980000 |  | 2019-03-04 | Construction | 2021-10-01 | 2023-05-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-01
3515d | 3515d |  | FALSE | PB&A | Multiple SF6 Primary Switches | Sub-project of 950568 |  |  | Design | Gerry Bomotti | TBD | John Franklin |  | John Franklin | 2 |  |  | FALSE |  |  | 2021-03-01 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 19 |  |  | FALSE | 320000 |  | 2018-07-31 | Bidding (Spring 2022 per Housing) | [12 empty] | PD&C | 0 | 2018 | 2021-08-01
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 2020-09-22 | Bidding | 2021-12-01 | 2022-03-01 | [10 empty] | PD&C | 0 | 2020 | 2021-08-01
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Design | Gerry Bomotti | TBD | ---- |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Bidding | [12 empty] | PD&C | 0 | 1900 | 2021-08-01
3630 | 3630 |  | FALSE | SOM | SOMR Egress Doors/Cameras | All egress doors for floors 1-3. need to be replaced with compliant standards. Project to also include security cameras for entry and exit on 1st and 2nd floor. |  |  | Design | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes |  |  |  | FALSE | 65000 |  | 2020-03-04 | Bidding | [12 empty] | PD&C | 0 | 2020 | 2021-08-01
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS BUILDING |  | ESTIMATE | Kathryn Uhrich | Jose Wudka | JOSE WUDKA |  | Enrico Baez |  | R1 |  | FALSE |  |  | 2019-12-19 | Awaiting Response from Client | [5 empty] | 05/13/21 O-ANS: Enrico corresponded with Dr. Wudka on 3/14/2021. He had emailed me stating that the College was going to discuss the project. Still awaiting a response to that inquiry. I follow up today requesting an update. 1/19/21 DL: Enrico is managing this project. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-08-01 |  | 1
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT |  | SCIENCE LABORATORIES 1 | 317 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 10 |  | FALSE |  |  | 2020-02-18 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-08-01
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LABORATORIES 1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 2020-02-19 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-08-01
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SUPPORT SERVICES BUILDING | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | Emily Engelschall, Sean Cason | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-22 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-08-01
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL BUILDING | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 2019-12-04 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2019 | 2021-08-01
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES |  | UNIVERSITY OFFICE BUILDING | 200 | HOLD - FACILITIES SERVICES | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-02-07 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-08-01
3636 | 3636 |  | FALSE | PB&A | Tunnel DAS | Adding radio repeaters to the tunnel system to improve coverage in a high hazard work area. The project consists of adding a rooftop antenna, battery back-up, amplifier, repeater antennas, and coax runs through the tunnel system. A few items need to be mounted. Golden State Communications will need to interface additional system to the existing radio system. |  |  | In Bidding | Gerry Bomotti | TBD | Tracy Stark |  | Tameesha Hayes |  |  |  | FALSE | 77271 |  | 2021-05-05 | Award Contract | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Bidding | Gerry Bomotti | TBD | ---- |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 2020-09-15 | Award Contract | [12 empty] | PD&C | 0 | 2020 | 2021-08-01
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | In Bidding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 61918 |  | 2020-09-21 | Award Contract | 2021-09-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2020 | 2021-08-01
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Bidding (Phase 2) | Kathryn Uhrich | Jose Wudka | Sabrina Schuster |  | Scott Donnell | 8 |  |  | FALSE |  |  | 2016-12-06 | Award Contract (Phase 2) | 2021-10-01 | 2021-11-01 | [10 empty] | PD&C | 0 | 2016 | 2021-08-01
3637 | 3637 |  | FALSE | ATHLETICS | Soccer Field Spiideo Video Installation | We are making an addition to the soccer stadium by adding a 40 foot pole at center field with a cloud based camera operating system. |  |  | In Construction | Tamica Smith Jones | Joe Erbland | Eugene Hutchinson |  | Tameesha Hayes |  |  |  | FALSE |  |  | 2021-04-16 | Complete Construction | 2021-08-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2021 | 2021-08-01
3615 | 3615 |  | FALSE | CAP PROG | Student Success Center Buildout | Buildout and furnishing of the SSC dining venue for temporary use as seating/study area and other as needed construction scope related to the overall building project that was not described in the Basis of Design. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Mihai Gavan |  |  |  | FALSE | 980000 |  | 2021-03-09 | Complete Construction | 2021-03-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2021 | 2021-08-01
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | ---- |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete installation of UPS | 2021-01-01 | 2021-12-31 | [10 empty] | PD&C | 0 | 2016 | 2021-08-01
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | ---- |  | Mihai Gavan | 9 |  |  | FALSE | 60430000 |  | 2017-06-01 | Complete Construction | 2019-11-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2017 | 2021-08-01
3557 | 3557 |  | FALSE | CHASS | Campus Sculpture Installation | We will bring 5 sculptures to campus that will go in public places that have already been identified by Uma Ramasubramanian and Jacqueline Norman . Please construct 5 concrete plinths at various locations around campus. Locations are on the attachment. |  |  | In Construction | Juliet McMullin | Cindy Williams | Emily Rankin |  | Tameesha Hayes | 3 |  |  | FALSE | 82000 |  | 2019-11-27 | Complete Construction | 2020-10-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-01
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Richard Zapien |  | Scott Donnell | 5 |  |  | FALSE | 39000 |  | 2020-05-08 | Cooler Delivery | 2021-06-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2020 | 2021-08-01
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Georgios Vidalakis |  | Scott Donnell | 7 |  |  | FALSE | 640745 |  | 2020-09-11 | Complete Construction | 2021-01-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2020 | 2021-08-01
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Tracey Kahn |  | Scott Donnell | 12 |  |  | FALSE | 1575000 |  | 2018-01-08 | Complete Construction | 2021-02-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2018 | 2021-08-01
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | In Construction | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 3 |  |  | FALSE | 1340000 |  | 2019-05-15 | Complete Construction | 2021-05-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-01
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 6 |  |  | FALSE | 600000 |  | 2019-06-18 | Wire pull, programming of NFACP | 2021-06-01 | 2021-08-27 | [10 empty] | PD&C | 0 | 2019 | 2021-08-01
3195 | 3195 |  | FALSE | FAC-PLNG-DESIGN-CONST | North District | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 4146146.55 |  | 2016-10-26 | Complete Construction | 2019-07-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2016 | 2021-08-01
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | In Construction | Gerry Bomotti | Sharyl Murdock | Daneca Stevens |  | Daneca Stevens | 2 |  |  | FALSE | 507364 |  | 2019-07-30 | Complete Construction | 2021-08-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-01
3590b | 3590b |  | FALSE | PB&A | DMFI(FY17-20) Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Construction | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 2019-11-27 | Complete Construction | 2021-07-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-01
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | In Construction | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 97050000 |  | 2019-03-04 | Complete Construction | 2021-07-01 | 2023-05-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-01
3286 | 3286 |  | FALSE | PB&A | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 10 |  |  | FALSE | 3375000 |  | 2017-03-29 | Complete Construction | 2021-02-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2017 | 2021-08-01
3467 | 3467 |  | FALSE | PB&A | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 17 |  |  | FALSE | 405000 |  | 2018-07-31 | Complete Construction | 2021-08-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2018 | 2021-08-01
3490 | 3490 |  | FALSE | PB&A | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | Parking Lot 13 |  | In Construction | Gerry Bomotti | TBD | Irma Henderson |  | John Franklin | 25 |  |  | FALSE | 31844000 |  | 2018-12-06 | Complete Construction | 2020-02-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2018 | 2021-08-01
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 2020-09-23 | Complete Construction | 2021-07-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2020 | 2021-08-01
3524 | 3524 |  | FALSE | VC-STU AFF | Student Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | STUDENT SERV |  | In Construction | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE | 450000 |  | 2019-04-16 | Complete Construction | 2021-08-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-01
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Construction by USDA | Kathryn Uhrich | Jose Wudka | MaryLou Polek |  | Scott Donnell | 1 |  |  | FALSE | 2500 |  | 2019-10-04 | Complete Construction by USDA | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
3624 | 3624 |  | FALSE | BCOE | CE-CERT Circuit Upgrade | We have an existing 208 VAC 100 Amp circuit. We would like to upgrade to a 200 Amp service. The existing service is located in the electrical room at 1084 Columbia. |  |  | In Design | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Tameesha Hayes | 6 |  |  | FALSE | 4100 |  | 2021-03-03 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 3182452.32 |  | 2016-12-16 | Bidding | 2021-11-01 | 2022-01-01 | [10 empty] | PD&C | 0 | 2016 | 2021-08-01
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | Jose Wudka | Wendi Tapia |  | Tameesha Hayes | 3 |  |  | FALSE |  |  | 2020-06-19 | Waiting for equipment from overseas | [12 empty] | PD&C | 0 | 2020 | 2021-08-01
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | ---- |  | Fernando Canon | 7 |  |  | FALSE | 432510 |  | 2016-02-25 | Bidding | 2021-12-01 | 2022-02-01 | [10 empty] | PD&C | 0 | 2016 | 2021-08-01
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 9 |  |  | FALSE | 500000 |  | 2019-09-05 | Bidding | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | ---- |  | Fernando Canon | 20 |  |  | FALSE | 2600000 |  | 2016-05-19 | Funding & Approval | [12 empty] | PD&C | 0 | 2016 | 2021-08-01
3614 | 3614 |  | FALSE | INACTIVE P&B | MLK Water Meters | Provide by contract plumbing point of connections and irrigation infrastructures to north and south sides of Martin Luther King Blvd. for watering of UCR palm trees. City of Riverside shall install two (2) ¾” [City] water meters at points of connection. Provide approximately 300’ of new irrigation main-line with associated trenching via contract and/or via facilities work order TBD. |  |  | In Design | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell |  |  |  | FALSE | 31790 |  | 2021-04-30 | Bidding | 2021-10-01 | 2021-11-01 | [10 empty] | PD&C | 0 | 2021 | 2021-08-01
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | In Design | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 2019-03-04 | Bidding | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 22 |  |  | FALSE |  |  | 2016-10-10 | Bidding | 2022-02-01 | 2022-06-01 | [10 empty] | PD&C | 0 | 2016 | 2021-08-01
3626 | 3626 |  | FALSE | UNDERGRADUATE EDUCATION | Rivera Library Room Modifications | Conduct room modifications to support new wall display on west wall Rivera A101A. Work needed: 1. West wall - ½” three-ply to support 12 x 55” displays over bookshelves. 2. West wall – drywall cover bookshelves any area not covered by the technology displays. 3. West wall – add electrical outlets as needed for new displays 4. North and south walls – add electrical for new motorized shades 5. Rivera A101A – add carpeting 6. Rivera A101A – paint room Notes: - Working with Chuck Forsyth in ITS and Bahram Mobasher from CNAS/Physics on project. - Israel and Chuck had a preliminary meeting with Enrico Baez from facilities to discuss project. - Point of contact: Israel Fletes and Charles Forsyth. Israel Fletes cellphone: 951-300-6693 |  | A101A | In Design |  |  | Israel Fletes |  | Vilma Kern | 1 |  |  | FALSE | 120000 |  | 2021-02-10 | Construction | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Funding | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Scott Donnell | 2 |  |  | FALSE | 700000 |  | 2018-04-04 | Complete Funding | [12 empty] | PD&C | 0 | 2018 | 2021-08-01
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | In Funding | Kathryn Uhrich | Jose Wudka | Mireya Botello Santoyo |  | Scott Donnell | 4 |  |  | FALSE | 32871.65 |  | 2020-07-14 | Secure Funding for Additional Scope | [12 empty] | PD&C | 0 | 2020 | 2021-08-01
3612 | 3612 |  | FALSE | CAP PROG | Native American Landscape Garden | Create a physical marker to commemorate the UCR Land Acknowledgement in the form of a Native American Landscape Garden (working name) at the proposed project location. |  | Ext | In Programming | Jacqueline Norman | Sharyl Murdock | Uma R. |  | Vilma Kern | 16 |  |  | FALSE | 103000 |  | 2021-02-11 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | John Franklin | 2 |  |  | FALSE |  |  | 2019-03-08 | Complete Report-Arc Flash | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | ---- |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 2019-03-04 | DB Competition | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Study | [12 empty] | PD&C | 0 | 2018 | 2021-08-01
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis (RE Proj) | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 2019-02-14 | Complete Study | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 2018-10-31 | CEQA | [12 empty] | PD&C | 0 | 2018 | 2021-08-01
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 245 | IN PROGRESS | Juliet McMullin | Cindy Williams | ANDREA HIDALGO |  | DAN LERMAN |  | 3 |  | FALSE |  |  | 2020-01-02 | Make corrections and resubmit plans on 7/15/21 | 2021-05-24 | 2021-09-23 |  |  |  | 08/02/21, DL: The plans are now approved. We ordered the light fixtures and have also started the work. It is our plan to be complete with the project by September 23rd and the Arts Department currently has an exhibit they are planning to present on or near the 23rd……7/15/21, DL: We are still in plan check review with the building department and a few corrections were needed. We will resubmit the corrections tomorrow. Hopefully the permit will be approved in the next two weeks……..6/2/21, DL: We are almost complete with the plans. We will submit the plans to the customer for review by the end of the week. Once the cutomer approves the plans, we will apply for the building permit………4/20/21, DL: Conducted site vist with the Arts team. We will start working on the plans in the next two weeks…………1/19/21, DL: This is a priority 3 project. We will start the plans and permit for this project when all priortiy #2 projects are complete…….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-08-01
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Convert Basement Library into Piano Lab | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 54 | IN PROGRESS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 2019-11-19 | Framing and electrical | 2021-05-14 | 2021-10-31 |  |  |  | 08/02/21, DL: Most of the demolition is complete. We started the framing today. It is our goal to be 100% complete with this project by the end of October....7/15/21, DL: Plans were approved this week. Carpenter shop is ordering material and we should start the work next week…… 6/2/21, DL: We applied for the building permit last week. We should have approved plans in the next 1-2 weeks…..5/14/21, DL: We sent Paul R. the 75% complete plans today for review. Once Paul approves the plans and layout of the pianos, we will proceed with completing the plans and apply for the building permit. The demolition of the cabinets and floor covering is complete. The carpenter shop is also pre-ordering their material to help expedite the project once we have the approved building permit……4/1/21, DL: We will start the plans process over the next two weeks and try and apply for a building permit in the next 2-3 weeks…1/19/21, DL: We will Start the plans, permit and the work once all priority #3 projects…11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks…. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | 0 | 2019 | 2021-08-01
3645 | 3645 |  | FALSE | PB&A | Falkirk Seismic Rating Study | FALKIRK STRUCTURAL STUDY - provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. |  |  | New (7/12/21) | Gerry Bomotti | TBD | Sean Hatfield |  | D.Hecht/J.Franklin |  |  |  | FALSE |  |  | 2021-07-12 | New (7/12/21) | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3648 | 3648 |  | FALSE | PB&A | Bannockburn Walkway Repairs | Several walkway locations at Bannockburn have deteriorated to the point that they must be replaced. The topcoat is past it’s service life and has lost all waterproofing effectiveness. As a result, the underlying sheathing, T&G, and support beams have suffered extreme water damage. Scope of Work: Replace support beams, T&G, and topcoat system at 2 locations: L bldg. & V bldg. Requesting JOHN FRANKLIN as PM. |  |  | New (7/12/21) | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin |  |  |  | FALSE |  |  | 2021-07-12 | New (7/12/21) | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3650 | 3650 |  | FALSE | CNAS | Greenhouse 16-3 Rebuild Estimate | We need an estimate to rebuild greenhouse 16-3 that burned down in a fire |  |  | New (8/2/21) | Kathryn Uhrich | Jose Wudka | Sue Lee |  | Scott Donnell |  |  |  | FALSE |  |  | 2021-08-02 | New (8/2/21) | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Joe Erbland | Johnathan Jensen |  | Fernando Nunez | 1 |  |  | FALSE | 0 |  | 2018-08-23 | Department approval to move fwd | [12 empty] | PD&C | 0 | 2018 | 2021-08-01
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | SOCCER FIELD AND AREA |  | On Hold | Tamica Smith Jones | Joe Erbland | Joe Erbland |  | Daneca Stevens | 2 |  |  | FALSE | 0 |  | 2014-04-10 | Need direction by PM Director | [12 empty] | PD&C | 0 | 2014 | 2021-08-01
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 14 |  |  | FALSE | 0 |  | 2017-12-03 | On Hold | [12 empty] | PD&C | 0 | 2017 | 2021-08-01
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 17 |  |  | FALSE | 0 |  | 2018-07-16 | Coordinating with North District | [12 empty] | PD&C | 0 | 2018 | 2021-08-01
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | On Hold | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 2018-06-22 | Awaiting direction by Provost | [12 empty] | PD&C | 0 | 2018 | 2021-08-01
3594 | 3594 |  | FALSE | CNAS | R'Garden Grow Pod Installation | R'Garden Gro Pod Installation |  |  | On Hold | Kathryn Uhrich | Jose Wudka | Richard Zapien |  | Scott Donnell | 6 |  |  | FALSE |  |  | 2020-05-21 | Secure Funding | [12 empty] | PD&C | 0 | 2020 | 2021-08-01
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 600000 |  | 2019-09-05 | On Hold | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 1500000 |  | 2019-11-06 | On Hold | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 2019-12-10 | Departmental Approval | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
3627 | 3627 |  | FALSE | VC-STU AFF | Costo Hall New Doors | Add three (3) doors to divide new office designations in Costo Hall. Two of the doors require new frames |  |  | On Hold | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens |  |  |  | FALSE |  |  | 2021-03-04 | On Hold | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | On Hold (COVID-19) | Brian Haynes | Cathy Eckman | Christina Wong |  | Tameesha Hayes | 5 |  |  | FALSE | 130000 |  | 2019-03-19 | On hold (COVID-19) | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [12 empty] | PD&C | 0 | 2017 | 2021-08-01
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 6 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [12 empty] | PD&C | 0 | 2018 | 2021-08-01
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MATERIALS SCIENCE & ENGINEERING | 71 | PLAN DEVELOPMENT/CHECK | Christopher Lynch | Todd Ambriz | DONG YAN |  | DAN LERMAN |  | 2 | 3 | FALSE |  |  | 2020-08-06 | Schedule the work once the permit is approved | 2021-06-02 | 2021-09-15 |  |  |  | 08/02/21, DL: We are still in the plan check review process. Once the permit is approved, we will schedule the work….7/15/21, DL: Plans are complete, we will apply for the building permit today and the permit should be reviewed and approved in the next 2-4 weeks. Once the permit is approved, we will order the material and schedule the work……6/2/21, DL: We will work on the final plans the week of 6/14/21 and try to apply for building permit on or before 6/22/21. Once the permit is approved, we will schedule the work…. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-08-01
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | W. CONWAY PIERCE HALL | 2232A | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Jose Wudka | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 2020-01-22 | Schedule the work once the permit is approved | 2021-06-04 | 2021-09-30 |  |  |  | 08/02/21, DL: The plans are still being review by the building department adn EH&S. Once the plans are approved, we will schedule the work....7/15/21, DL: Plans will be complete and we will apply for the building permit by tomorrow enveing. If the permit is appproved, which should take 2-4 weeks for the review and approval process, we will order the material and schedule the work……5/14/21, DL: Project is scoped, we will work on plans and submit them to Kevin for review in about 3- weeks…….1/19/21, DL: This is a priority #9 project. We will start this project when all priority #8 projects are complete… |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-08-01
3634 | 3634 |  | FALSE | CNAS | Botanic Garden Geodesic Dome | Request is for an architect to draw a design for a replacement of current geodesic dome. Design can then be used as basis for fund-raising campaign to construct new dome. Dr. Holt, UCRBG Director, has been in discussions with Jacqueline Norman and Drew Hecht. Dome was constructed on site in 1980s, all wood, greatly deteriorated. Dome is unrepairable, unsafe, and closed to the public. Goal is to replace it with a structure as close to the original dome shape as possible but with modern functionality. We envision a structure with partial solid walls near the ground, then lath on upper walls and top, possibly cross shaped with doors at ends of the arms, and a domed center for taller plants. Should have “wood look” or at least maintain original sensibility since it is beloved as is, but needs a durable material! Function—house the collection of shade-requiring plants including prehistoric plants, subtropical plants, and others. Design should include space for plants inside around the edges and a wide walkway in a circle around a central display, suitable for tour groups, small gatherings, and photography. Arms extending in cross shape could house additional plants, displays, even sale plants. |  |  | Pre-Programming | Kathryn Uhrich | Jose Wudka | Jodie Holt |  | Fernando Nunez |  |  |  | FALSE |  |  | 2021-04-13 | Receive add'l info from Client | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3640 | 3640 |  | FALSE | VC-RED | MRB Circulation Pumps E-Power | MRB Circulation Pumps e-Power |  |  | Pre-Programming | Rodolfo Torres | Laura Manor | Tara Barthol |  | Vilma Kern |  |  |  | FALSE |  |  | 2021-06-30 | Programming | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3613 | 3613 |  | FALSE | CAP PROG | SOM Modular Trailer Relocation | This project will be to relocate the existing School of Medicine modular trailer (P5825) to the Corp Yard (specific location to be determined). This modular needs to be relocated due to the new School of Medicine Education Building II project being located on this site. |  |  | Programming | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Tameesha Hayes |  |  |  | FALSE |  |  | 2021-04-23 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3616 | 3616 |  | FALSE | CAP PROG | University Ave/Canyon Crest Dr Improvements | $100,000 in Violent Acts Mitigation and Prevention funding have been awarded to study short and long-term safety improvements at the intersection at University Avenue and Canyon Crest Drive. Subsequent activities will involve the construction of identified improvements. |  |  | Programming | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Uma R. | 17 |  |  | FALSE | 100000 |  | 2021-03-01 | Design | 2022-01-01 | 2022-02-01 | [10 empty] | PD&C | 0 | 2021 | 2021-08-01
3644 | 3644 |  | FALSE | LIBR | Rivera Library Fire Suppression Study | Request for estimate for installing fire suppression system in Rivera Library 4th floor and Secured area on Basement floor. |  |  | Programming | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Vilma Kern |  |  |  | FALSE |  |  | 2021-06-25 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3642 | 3642 |  | FALSE | CAP PROG | South District Planning Study | The “South District” presents a unique opportunity to create a strong identity for academic and research expansion across the campus loop road with an emphasis on creating a transformative and synergistic new campus neighborhood. Its hillside location makes it highly visible from the freeway and the Core Campus, presenting a significant opportunity to enhance campus identity. The site’s high elevation also gives it unobstructed views outward. A holistic and integrated planning framework for its development is important to ensure alignment with broad planning strategies and principles in place for the campus, as established in land planning per the DRAFT 2021 Long Range Master Plan and the more detailed physical planning vision from the 2016 Physical Master Plan Study for this “opportunity site”, and its immediate context. The upcoming effort to update the campus’ Physical Design Framework document will further analyze the unique opportunities afforded by the South District, and leverage the design of the School of Business Building to establish organizing principles for how the area could be optimally redeveloped to its highest potential. |  |  | Programming (Study) | Jacqueline Norman | Sharyl Murdock | Uma R. |  | Uma R. |  |  |  | FALSE | 50000 |  | 2021-06-10 | Complete Study | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3391 | 3391 |  | FALSE | CNAS | NRS Motte Rimrock Res Cost Study | Requesting recheck and recost of formal estimate for Motte Reserve Prop 84 for the Natural Reserve System. The former estimate was $763K. Purpose of study is to confirm, or augment the initial project valuation included with the Proposition 84 NRS grant application to install new structures at the Motte Rimrock Reserve site. |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Kimberly Hammond, D. McWilliams |  | Fernando Nunez |  |  |  | FALSE | 0 |  | 2017-11-02 | Prepare updated cost estimate | [12 empty] | PD&C | 0 | 2017 | 2021-08-01
3623 | 3623 |  | FALSE | CNAS | NRS Prop 68 Study - Boyd | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Fernando Nunez | 10 |  |  | FALSE |  |  | 2021-02-02 | Project Estimate | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3618 | 3618 |  | FALSE | CNAS | NRS Prop 68 Study-James Reserve | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Fernando Nunez | 11 |  |  | FALSE | 8380 |  | 2021-02-02 | Project Estimate | [12 empty] | PD&C | 0 | 2021 | 2021-08-01
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Programming (Study) | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 2020-09-17 | Negotiations with Consultant | [12 empty] | PD&C | 0 | 2020 | 2021-08-01
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Scott Donnell | 10 |  |  | FALSE | 65000 |  | 2019-03-04 | Complete Study | [12 empty] | PD&C | 0 | 2019 | 2021-08-01
22P000006 |  | 22P000006 | FALSE | CAMPUS | SL5 MRB 4210 - Install AC and Electrical Infrastructure | We have a project at MRB 4210 where we will be installing Air conditioning and electrical infrastructure to accommodate equipment that will be relocated from Batchelor Hall to MRB which is a result of the Batchelor Hall renovation. |  | 4210 | PROJECT INTAKE |  |  | SHARYL MURDOCK | GERRY BOMOTTI | Dan Lerman |  | 1 |  | FALSE |  |  | 2021-07-12 | Work on plans and apply for building permit | 2021-09-06 | 2021-10-29 |  |  |  | 8/2/21, DL: We are currently in the design phase and still trying to verify the logistics of the project. We are planning to apply for a building permit in the next 2- 3 weeks……… |  | Dan Lerman |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-08-01
21P000003 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | PROJECT INTAKE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Enrico Baez |  | R1 |  | FALSE |  |  | 2020-06-26 | [6 empty] | 1/19/21, DL: Enrico is managing this project………….. | 2020-12-02 | Enrico Baez | Remove tripod antenna. Apply spray roof coating to existing roof surface | YES |  | Winter 2021 | FS | 0 | 2020 | 2021-08-01 |  | 1
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | JEANETTE AND RUPERT COSTO HALL |  | PROJECT INTAKE | Brian Haynes | Cathy Eckman | BRENDAN O'BRIEN |  | Enrico Baez |  | R1 | R2 | FALSE |  |  | 2019-10-24 | [6 empty] | 02/16/21 O-ANS: Will require plans/permits and may need to go to PD&C due to scope of work which includes construction. Will confirm with client before instructing to submit request to CPMS…. 01/19/21, DL: Enrico B. Will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-08-01 |  | 1
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | [12 empty] | PD&C | 0 | 1900 | 2021-08-01
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 20 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2021 | [12 empty] | PD&C | 0 | 2017 | 2021-08-01
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 2020-03-30 | Projects to be assigned | [12 empty] | PD&C | 0 | 2020 | 2021-08-01
22P000008 |  | 22P000008 | FALSE | VC-RED | SL5 MRB VARIOUS LAB SUPPORT - IACUC INSP TINTED WINDOWS NEEDED | ER IACUC INSPECTION- TINTED WINDOW NEEDED ON LAB SUPPORT ROOMS. ORIGINAL SERVICE REQUEST 22S000637 See list of rooms for window tint request. Korzus 1204E 1204F 1212A 1212B 1229B Zagha 1212A 1212B 1204F 1204E 1231C Abdulrazak 2204A 2204G 2204F 2208B Binder 3214 3218 3215 Cho 3216 3219 Tiwari- Woodruff 3204G Hickmott 2221 Zheng 2225 2213-C |  |  | QUEUE TO START | Rodolfo Torres | Laura Manor | TARA BARTHOL |  | Enrico Baez |  | R1 |  | TRUE |  |  | 2021-07-14 | [6 empty] | 07/27/21 EBZ: Project to begin 07/29/21. |  | Enrico Baez |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-08-01 |  | 1
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | MARLAN & ROSEMARY BOURNS HALL | B0328E | QUEUE TO START | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Enrico Baez |  | R1 | R1 | FALSE |  |  | 2019-11-05 | [6 empty] | 1/19/21, DL: Todd has the estimate. Sent follow up email to Todd requesting update or FAU number………………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | 0 | 2019 | 2021-08-01 |  | 1
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 150 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 2020-01-14 | Order material once permit is approved | 2021-06-14 | 2021-10-01 |  |  |  | 08/02/21, DL: The plans and permit are approved. This is a large project and it will consume our electricans for at least 4- weeks. At the current time we are working on completing several other projects. Once we are caught up on the noted projects, we will schedule the work. Paul Richardson is currently aware of the plan noted above.....7/15/21, DL: The engineering is complete. We submitted the plans and applied for the building permit last week. Once the permit is approved, we will order material and schedule the work…….5/14/21, DL: We are still working on the contract to be approved for the electrical engineer before we can proceed…….4/15/21, DL: We had a meeting with the engineer this week and we should be applying for a permit within the next three weeks…….3/1/21, DL: We will reach out to the electrical engineer this week…….1/19/21, DL: This project will require engineered plans. This is a priority 2 project. We will start the plans and permit process when all priority #1 projects are complete. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-08-01
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS BUILDING | 3009 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 2019-10-11 | [6 empty] | 05/05/21 O-ANS: Updated contact info from Dr. Wudka. 05/05/21 O-ANS: Multiple failed attempts to contact requestor to schedule work. Project placed on HOLD and emailed CNAS partner to continue to hold or cancel. 02/03/21 O-ANS: Reminder email sent to customer that PAINT ONLY portion would be completed and not the door removal at this time. Customer can resubmit request in next prioriization cycle…. 11/06/20 O-JLO: Emailed requestor and alternate regarding paint portion only, and that door/drywall removal will not occur during this time …. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. FS to confirm with customer that we can only complete the painting at this time but not the removal of the door…. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure." | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | 0 | 2019 | 2021-08-01
21P000162 |  | 21P000162 | FALSE | CNAS | SL5 ENTOMOLOGY 0282 - PAINT NEW FACULTY MEMBER'S OFFICE | PAINT NEW FACULTY MEMBER'S OFFICE |  | 0282 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 2021-04-14 | [12 empty] | Winter 2021 | FS | 0 | 2021 | 2021-08-01
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 2019-11-25 | [6 empty] | 05/06/21 O-ANS: Updated contact person info from Dr. Wudka and reaching out to coordinate. 5/05/21 O-ANS: Multiple failed attempts to contact requestor to schedule work. Project placed on HOLD and emailed CNAS partner to continue to hold or cancel. 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-08-01
20P000282 |  | 20P000282 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 PIERCE HALL 3374 - RENOVATE GA CLASSROOM SUMMER 2020 | Project to renovate GA classroom in Pierce Hall for prioritization and execution in Summer 2020. |  | 3374 | QUEUE TO START | Susan Marshburn | Da Lan Dinh | DA LAN DINH |  | Paul Ditty |  | X |  | FALSE |  |  | 2020-01-09 | [8 empty] | Paul Ditty |  |  |  | Winter 2020 | FS | 0 | 2020 | 2021-08-01
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | Re-bid | Gerry Bomotti | TBD | Sharyl Murdock |  | John Franklin | 16 |  |  | FALSE | 33099342.06 |  | 2015-12-15 | Award Contract | 2021-12-01 | 2024-07-01 | [10 empty] | PD&C | 0 | 2015 | 2021-08-01
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Blythe Wilson | 1 |  |  | FALSE | 1150000 |  | 2016-12-15 | Design Builder Prequalification | 2022-09-26 | 2024-06-19 | [10 empty] | PD&C | 0 | 2016 | 2021-08-01
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 19 |  |  | FALSE | 2586581 |  | 2018-11-06 | Complete Review | [12 empty] | PD&C | 0 | 2018 | 2021-08-01
3471 | 3471 |  | FALSE | VC-STU AFF | HUB Electrical Sub Meter Installation | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Bidding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 4 |  |  | FALSE | 200000 |  | 2018-08-20 | Award Contract | 2021-09-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2018 | 2021-08-16
19P000659 |  | 19P000659 | FALSE | SOM | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 5 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 08/05/20 O-ANS: Canceled by client (Cynthia Carolina) via email with Ron Veloz. 8/5/20, DL: Dan to follow -up with customer…………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "remove 330 from work order / update project details / Update: Furniture on order 3.30.2020 - delivery tbd" |  | Enrico Baez | TBD | NO | 2020-08-05 | Fall 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000211 |  | 20P000211 | FALSE | CHASS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | Install keyless entry system for door to Arts Building RM 54 | ARTS | 54 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 | R3 | FALSE |  |  | 2019-11-07 | [6 empty] | 1/19/21, DL: Enrico will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment installation. 8/5/20, DL: This Project is on hold until further notice……. | 2020-01-20 | Enrico Baez | 1/19/21, EB: Per Paul R., This project is canceled………….Provide new panel, power supply and door hardware for 2 doors. Prox reader only. | YES | 2021-01-19 | Winter 2021 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
20P000046 |  | 20P000046 | FALSE | CNAS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | HOMER D. CHAPMAN HALL | 0001 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Enrico Baez |  | R2 |  | FALSE |  |  | 2019-07-31 | [6 empty] | 05/12/21 O-ANS: Per email from Bill Sutton, this project was requested to be cancelled. 1/19/21, DL: Enrico B. will manage this priject………….11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Install wireless access controls systems at front and rear entry doors. | YES | 2021-05-12 | Winter 2021 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
20P000210 |  | 20P000210 | FALSE | BCOE | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | Reduce noise. Replace doors with solid core doors and install an Acoustic Door Seal Kit. | CHUNG HALL | 224 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-11-05 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……. | 2020-02-11 | Enrico Baez | Removal of the existing double doors and door hardware, install new solid core double doors with continuous hinges, install new acoustical jamb seals, threshold seal and a surface mounted Automatic Door Bottom utilizing a flat spring mechanism, which activates when closing the door, lowering a neoprene seal insert against the floor or threshold to create a sound seal. Install acoustic double door astragals with seal. Reinstall all existing door locksets, and door closers. Quote received from Brad Aduddell-American Door to perform this work. Quote & Specs are available in the project folder. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000197 |  | 20P000197 | FALSE | VC-RED | SL5 UOB 210 - SOUND PROOF INSTALLATION |  | UNIV OFC BLD | 210 | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-10-24 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000188 |  | 20P000188 | FALSE | LIBR | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 |  | ORBACH LIB | 204 | CANCELED BY FS | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-10-23 | Obtain floor covering samples | [5 empty] | 11/19/20 O-ANS: Declined to move forward by FS Admin but may revisit in future prioritization period. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: We are working on floor covering samples that will work for the space. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000183 |  | 20P000183 | FALSE | CHASS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | Install side walk | HUM & SOC SC | 1202 | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2019-10-18 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Also Existing door is compliant and there are other accessible exits to the building… 8/5/20, DL: This Project is on hold until further notice……. | 2019-11-13 | Enrico Baez | Construct Side walk. ADA compliance not required. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
20P000047 |  | 20P000047 | FALSE | VC-RED | SL5 ADVANCED NEUROIMAGING | NEEDING TO TAKE DOWN OVERHEAD CABINETRY AND REPLACE WITH SOME KIND OF SHELVING TO OPTIMIZE SPACE. LOOKING FOR AN ESTIMATE AND A PLAN. | ADV NEURO |  | CANCELED BY FS | Rodolfo Torres | Laura Manor | CHELSEA EVELYN |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-07-31 | pending material delivery. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice…….3/23/20, DL: Shelves are ordered. We will schedule the work when we return from the campus closure……….1/15/20 O-DHN: Emailed Status Report to customer…...1/14/20, DL: We waiting for a revised quote from the vendor as there quote was not complete. We will process the quote for a PO# when we receive the correct quote……. 11/11/19, DL: Need to review scope with Ron as the shelving system is a special order item with a 3- month lead time….. | 2019-09-24 | Enrico Baez | Remove 5'-0" x3'-0" upper cabinet, and soffits. Patch and paint walls to match the existing grey . Install customer furnished adjustable shelf. | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000039 |  | 20P000039 | FALSE | BCOE | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE |  | BOURNS | A0318 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-05-13 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……..09/19/19 O-ANS: HOLD FOR WINTER 2020 PER CUSTOMER (LOUIS SANDOVAL) REQUEST. EMAILED PAUL DITTY TO CONFIRM. PAUL STATED THIS IS NON-PAINT PROJECT B/C SCOPE OF WORK INCLUDES CARPENTERS AND ELECTRIC SHOPS. |  | Paul Ditty |  |  | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
19P000624 |  | 19P000624 | FALSE | BCOE | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | Refurbish Room-Student Space, | BOURNS | A0346 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-05-15 | Pending information from Susanna | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Susanna is working on a cubicle layout. Once we have the information from her. We will schedule the work………… | 2019-11-07 | Enrico Baez | Remove all lower cabinets in room A0346 and all lower cabinets and mail boxes in Rm A0304 | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  | R7 |  | FALSE |  |  | 2019-02-27 | We Need an FAU # | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced. We will schedule the work when we return from campus closure………11/11/19, DL: Project is in the queue to start but we do not have an FAU# as this is a recharge project. I sent Enrico and James an email requesting the FAU#. Once we have an FAU #, I will work on scheudling the work…..10/1/19, DL; Enrico is wtill working on estimate. | 2018-10-19 | Enrico Baez | E. Baez 1. Provide power in ceiling for projector. 2. Install projector center in room between two 4ft light fixtures. 3. Install 2 duplex outlets in 4S box on South West corner of room 4. Remove existing screen. 5. Install new screen centered on South wall. Extend power from existing screen to new screen location. 6. Use existing screen power switch to control new screen. | YES | 2020-11-19 | Summer 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
19P000502 |  | 19P000502 | FALSE | BCOE | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | Install Electrical power & TV bracket.for a 75" TV to mount in CS 342. | CHUNG HALL | 444 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | RICHARD BAIN |  | Dan Lerman |  | R3 |  | FALSE |  |  | 2019-02-19 | Schedule the work. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This project is on hold……………3/25/20, DL: Work orders are produced. I will work on scheduling the work when we return back to work…….. | 2019-09-17 | Enrico Baez | Install Electrical power & TV bracket. Excludes network/data back box and stub up to ceiling. | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
19P000427 |  | 19P000427 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | Install Power and TV bracket, move white board | CHUNG HALL | 453 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2019-01-03 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold……… | 2019-09-18 | Enrico Baez | Install Power and TV bracket, remove white board and relocate , patch and paint wall prior to installing | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice. | 2018-09-27 | Enrico Baez |  | YES | 2020-11-19 | Fall 2018 | FS | 0 | 2018 | 2021-08-16 | FY 20-21
20P000309 |  | 20P000309 | FALSE | VC-UNIV ADV | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES |  | 1955 CHICAGO | 200 | CANCELED BY FS | Peter Hayashida | Naysia Caldwell | SARAH KARSON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-10 | [6 empty] | 12/16/20 O-ANS: Canceled by FS - Project location not serviced as FS CORE location and reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Please retain project # as reference. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2020-12-16 | Spring 2020 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | COMPLETE | Kim Wilcox | TBD | ALEXIS RAMBAUD |  | Dan Lerman |  | 1 | 0 | FALSE |  |  | 2018-12-11 | schedule the work | 2019-01-21 | 2019-03-27 |  |  |  | 8/5/20, DL: This project is complete…………3/25/20,DL: Doors are scheduled to arrive the second week in April……2/19/20 O-DHN: Emailed Status Report to customer……2/18/20, DL: Work is complete except for Door and final deep cleaned I do have final stain samples from the vendor. I need to verify color……… We will complete the project when the doors arrive……….1/14/20, DL: Plans are approved, PO# is cut for the ordering of the custom doors, we are currently scheduled to start the work on or shortly after 1/21/20,. Karim understands that we will start and finish the project but we will not be able to install the door until the door arrives on site. There is a minimum of 6-8 week lead time on the door delivery………….12/16/19, DL: Plans are still in plan check review. I sent the building department an email asking for a startus update today…….10/16/19, DL; Plans were submitted to our building official this week for plan check review and a permit……9/16/19, DL; Guther will work on plans in the next three weeks. Once plans are complete, we will proceed with the permit process… | 2018-12-20 | Enrico Baez | SOW: Wall: Construct a metal stud framed wall with drywall up to hard ceiling (ceiling has 12x12 glue up ceiling tiles). Hardware: Install new lockset & keys are required.***** French Door: Install new stain grade birch door with full lite. Door and finish to match the existing office doors.***** Hard Ceiling: * Ceiling is 8’-0” A.F.F. + - with 12x12 glue up ceiling tiles. Work may require a new access panel if access to space above is needed. The 12x12 glue up ceiling tiles may need to be removed where the new wall is constructed.***** Flooring: The existing flooring will remain. Install rubber base to match existing.***** Painting, Taping & Sanding: Taping sanding and painting is required at the new wall and connecting walls.***** HVAC: May require modifications to split the existing supply air to accommodate the open office space.***** Electrical: Provide light switch at new office, power(new or relocate); add and or relocate electrical and voice/data outlets required for a standard office.***** Lighting: Provide a new light switch/circuit near office entrance. The existing 2x4 fixture is on main lighting circuit and will require lighting circuit modifications. Verify if the existing lighting is sufficient for the proposed office. Field verify if additional lighting is required.***** Fire Alarm: Provide a new Smoke/chime detector at new office area, confirm requirements. | YES | 2020-08-05 | SPRING 2019 | FS | 0 | 2018 | 2021-08-16 | FY 20-21
20P000213 |  | 20P000213 | FALSE | CHASS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS |  | CHASS INT S | 2117A, 2117C, 2117D, 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-11-08 | approved permit | 2020-03-03 | 2020-03-21 |  |  |  | 8/5/20, DL: This Project is Complete……………..2819/20 O-DHN: Emailed Status Report to customer…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have a contract, we will order the material and schedule the work………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Plans are complete and submitted for building permit. We are also working on the contract. Once the plans are approved and the contract is complete, we will schedule the work………. |  | Enrico Baez |  |  | 2020-08-05 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
19P000687 |  | 19P000687 | FALSE | PB&A | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | COMPLETE | Gerry Bomotti | TBD | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-06-26 | plan check review | [5 empty] | 8/5/20, DL This Project is Complete……………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Contracts is processing the contract. Once the contract is complete, we will schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Plans were approved. I sent Brendan an email 11/11/19 requesting an FAU # as this is Recharge work. Once we have the FAU #, we will work on the contract agreement with the contractor………10/30/19, DL; Sent Lezlie and email asking if she has an update on the resubmitted plans on 10/30/19………..10/16/19, DL; The plans were resubmitted for plan check review this week. We are hopeful the plans will be approved this week. Once approved we will work on contract and scheduling the work…10/7/19 LB: This is a test. The timestamp will be reset when the test is done. 10/1/19, DL: We are working on plan check review. We should have approved plans in the next two weeks…..8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | Provide estimate to install key card access control |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | COMPLETE | Christopher Lynch | Todd Ambriz | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-09 | Finish Gas cabinet installation | 2019-09-23 | 2020-02-07 |  |  |  | 8/5/20, DL: This Project is Complete…….3/25/20, DL: Project is 95% complete. We will install the fire sprinkler and exhaust duct to the gas cabinet when we return from the campus closure………..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Plans were approved and material is ordered. We are hopeful the material will arrive the 2nd or 3rd week in January. Once material is on site we will schedule the work…… 11/19/19 DH: Emailed Status Report to customer……10/16/19, DL: This project is 90% Complete. We are working on plans and permits for the two snorkels……….10/1/19, DL: This project is almost complete. We will be complete in the next 4- weeks except the Snorkel……….. 9/13/19, DL; The paint of the cabinets is scheduled for this week along with the power. We will submit the plans for the snorkel this with in the next two weeks…….9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Enrico Baez | SOW, Patch& Paint Walls, replace plexi glass on shelving, powder coat metal shelving & cabinets, clean & polish or replace chem sinks, polish counter tops, Validate all gas, water, drains, DI water & utilities. Replace damaged and dirty ceiling tiles, relamp as needed. Strip & wax floor. Dan L is requesting vendor pricing to restore finishes. | YES | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | R3 |  | TRUE |  |  | 2019-03-26 | Schedule the work | 2020-01-31 | 2020-02-21 |  |  |  | 8/5/20, DL: This Project is COMPLETE…….3/25/20, DL: The material is here and we are 95% complete with the work. We will complete the work when we return from the campus closure…………1/31/20 O-DHN: Emailed Status Report to customer…….1/30/20,DL: The pump is now on site but we are still waiting for the fittings. In the mean time, our plumber is putting everything together and is working on the installation. Once the fittings arrive, we will make the connections and the system should be good to go………….1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: The pump is scheduled to arrive on or before 1/31/20. We will schedule the work once we have the pump and material on site…..11/26/19, DL; Emailed Natalie and Sherice the quote for the vacuum pump. We will order the material and schedule the work once we have approval and the pump on site……11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: I sent the vendor a 2nd email requesting an update on the proposal. I also included Natalie on the email so she is aware of where we stand with the proposal……10/30/19, DL: We had a followup meeting with the vendor last week. The vendor is now working on a pump that will best meet our needs……….10/16/19, DL; We are working with a vendor on a quote for a new lab vacuum pump. We are hoping to have a quote in the next week or two…..9/16/19, DL; Estimate was provided to customer last week. If the project is approved, we will work on the plans and permits. Once approved, we will schedule the work…… |  | Enrico Baez | Old SOW Revised SOWInstall exhaust hood, electical receptacle, vacuum pump, vac lines and valves (six valves total) and hood location. | YES | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-22 | finish plans/submit application | 2020-01-10 | 2020-03-27 |  |  |  | 8/5/20, DL: This Project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer…..2/18/20, DL: We are making great progress and still on schedule to be complete before Spring Break begins. We pass drywall inspection on 2/18/20………..1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: Plans are approved. All items have been removed from the space. Abatement is schedule to take place within two weeks…..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were submitted for plan check review. Fire marshal stamped the plans, we are waiting on the final stamp from our building official. Once plans are approved we will order material and schedule the work……..10/30/19, DL: Gunter is working on plans. We are planning to complete the work before Spring Quarter begins. |  | Dan Lerman |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | C&C CARPORT | 161 | COMPLETE | Danna Gianforte | Shelley Gupta | SHELLEY GUPTA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-01-07 | Waiting for bid for customer. | 2020-01-20 | 2020-03-31 |  |  |  | 8/5/20, DL: This Project is complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have the contract, we will schedule the work……………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Project was approved by Shelley. We will work on the contract. Once we have the notice to proceed from contracts, we will order the material and schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Sent Shelley another follow-up email today and she has not verified if she would like to move forward with the project………10/30/19, DL: Sent Shelley the updated quote last week and she has not responded. I sent Shelley a followup email today asking her to let me know if she would like to proceed with the work……..10/16/19, DL; Had a meeting with Shelley, we modified the scope of work and software for the project. We are now revising the quote with our vendor. We should have an updated quote within the next two weeks. If Shelley approves the work and scope, we will proceed….10/1/19, DL; I have a meeting with Shelley this afternoon to review proposal. If she approves the project we will submit plans for a building permit……8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was cancelled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; We have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28/19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
19P000414 |  | 19P000414 | FALSE | PB&A | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | Seth Morrison |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-12-17 | pending material delivery | 2019-10-16 | 2019-11-27 |  |  |  | 8/5/20, DL: This Project is Complete………….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: We have the motor on site, we are working on the permit for the crane. Once we have the crane lift permit, we will schedule the install…………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: We are working on the new motor platform. It is our goal to install the new motor in late January. Once the motor is installed, we will be able to identify if additional work is needed…….11/19/19 DH: Emailed Status Report to customer…..11/15/19, DL: Material has not arrived……..10/30/19, DL: The new exhaust fan is ordered with a 2- 4 lead time. Once the exhaust fan arrives, we will schedule the install……….10/16/19, DL; We are in the process of the work. At this current time, we are not modifying the building to where permits may not be required…….10/1/19, DL; This is in the queue for plans, we will start the plans in the next 3-4 weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2018 | 2021-08-16 | FY 20-21
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | COMPLETE | Kathryn Uhrich | Jose Wudka | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | Work will be complete in 2 weeks | 2020-02-03 | 2020-03-13 |  |  |  | 8/5/20, DL: This project is complete……………..06/17/20, DL: This project should be complete with in the next two weeks……..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within two weeks. Once we have a contract, we will schedule the work……….1/15/20 O-DH: Emailed Status Report to customer……1/14/20, DL: Contracts is currently working on the contract. Once the contract is complete, we will order the material and schedule the work…………11/26/19, DL: Plans were approved. We will work on the construction contract. Once we have the notice to proceed, we will schedule the work……….10/15/19, DL: Sent PD&C and follow-up email on 11/11/19. We should have approved plans in the near future……10/30/19, DL: Sent PD&C an email asking for a status update on 10.30.19…… 10/16/19, DL; Plans are still in plan check. I sent the building official an email asking if any additional information is needed. This work will be completed by a contractor which means we need to allow time for the bid and contract process……… …………9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Enrico Baez | Request for Estimate to install three new FOB readers with electrified locksets. Work covered: Install one AC Fob Reader at door 2221 and one AC Fob reader at each Door 4231 & 4235. Connect card readers to the existing Hirsh ACP located in the IDF closet at each floor. 03/07/19: Scope revised to eliminate two FOB readers. Install one FOB reader at Genomics door 4231 only instead of all three rooms. | YES | 2020-08-05 | Fall 2018 | FS | 0 | 2018 | 2021-08-16 | FY 20-21
20P000214 |  | 20P000214 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | Remove walls and doors in spaces 2139 A,B and C. | PSYCHOLOGY1 | 2nd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-11-07 | Obtain building permit | [5 empty] | 9/30/20, DL: This Project is Complete…………8/5/20, DL: we will submiot plans this week.…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Plans were submitted for a permit on 2/12/20. Once plans are approved, we will order the material and schedule the work……… | 2020-01-10 | Enrico Baez | **************************************SCOPE********************************** 1.) Remove doors, and jambs 2139A, 2139B, 2139C. 2.) Remove drop ceiling in 2139A, 2139B, 2139C and repair as needed. 3.) Remove cabinets in 2139A, 2139B, 2139C. 4.) Remove walls between 2139A & B, and remove walls between 2139B & C. 5.) Change light fixture to match existing. 6.) Repair walls as needed. 7.) Patch and paint as needed. 8.) Replace carpet and base in 2139A, 2139B, 2139C and 2139 common area. 9.) HVAC duct work in individual spaces can be removed and simplified. | YES | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000202 |  | 20P000202 | FALSE | CNAS | SL5 SKYE HALL 361 RENOVATION PROJECT | Renovete space for class room. | SKYE HALL | 361 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY | MELISSA GOMEX | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-10-30 | pending permit approval | 2020-02-05 | 2020-03-27 |  |  |  | 9/30/20, DL: This Project is Complete……….8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Permits were approved. Demolition is complete…..1/15/20 O-DHN: Emailed Status Report to customer……..1/14/20, DL: Plans have been submitted for a building permit. Once plans are approved, it is our goal to complete the work by the beginning of spring quarter….. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000135 |  | 20P000135 | FALSE | BCOE | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MS&E Rm 0075 - 3 Ph208 Power CHW S&R WATER PPMS TOOL, Install Chilled water loop & power in clean room 075. | MAT SCI ENGR | 75 | COMPLETE | Christopher Lynch | Todd Ambriz | MARK HEIDEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-09-19 | Plans and permit | [5 empty] | 9/30/20, DL: This project is complete……..8/5/20, DL: This is in progress…….3/25/20, DL: We will work on plans and permits when we return back from the campus closure……. | 2020-02-18 | Enrico Baez | Intake/SOW: Install 208V 3ph power & disconnect/safety switch and one 3/4" Chilled water loop (Supply and Return) in the MSE southeast corner of clean room 0075. Create a 4" diameter pass-thru hole from this corner of room 0075 into the adjacent room 0071. FS to provide power and cooling to a compressor which will connect through the wall to the PPMS system with cryogenic helium lines. | YES | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000054 |  | 20P000054 | FALSE | SOM | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOMED-SOME G0600, G0621 & 1682B- ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-31 | [6 empty] | 9/30/20, DL: This Project is Complete…………..8/5/20, DL, Dan to follow-up with customer………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "Remove status Hold / Update project detail to include information on 1682B -ADD ELECTRICAL, PAINT/PATCH, AND RELOCATE WHITE BOARD." |  | Enrico Baez | Room G0600 Install Power behind and below the TV, install one TV Bracket, install one cut-in back box below the TV for data(data cabling by ITS), Paint the entire East wall to match existing. Room G0621 Insatll three(3) new double duplex receptacles and three(3) data back boxes only(no data cabling) in room G0621. Install SS tubing for Co2 from room G0621 to room G0623. Include Valves at both ends of P.O.C., Install one uni-strut siesmic cylinder support at the south wall. Steve Burleson has walked the site and has knowledge of the SOW. Loading Dock Install Pole & chains at Loading dock. |  | 2020-09-30 | Fall 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
19P000660 |  | 19P000660 | FALSE | SOM | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SL5 SOME RB, RM 330- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 9/30/20, DL: This Project is Complete………..8/5/20, DL: Dan to follow-up with customer…………..03/05/20 O-ANS: Removed room 330 per client request. Only updates to 107 & 111. |  | Enrico Baez | TBD | NO | 2020-09-30 | Fall 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000449 |  | 20P000449 | FALSE | BCOE | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | Paint Only - Chung Hall, Fourth Floor, Room 461 Patch & Paint: At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. Follow up with fresh paint. Thank you. | CHUNG HALL | 461 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-11 | [6 empty] | 01/19/21 O-ANS: Complete per technician updates and closed project. Completed by Wendy M. 11/09 -SC |  | Paul Ditty |  |  | 2020-11-09 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000230 |  | 20P000230 | FALSE | VC-RED | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | Install Ceilings, Widen Door & Extend Utilities | BOURNS | B116C & B116D | COMPLETE | Rodolfo Torres | Laura Manor | KRASSIMIR BOZHILOV | LAURA MANOR | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-11-18 | finish plans for building permit | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: This project is in progress and 50% complete. We should be complete with in the next 4-6 weeks…………...8/5/20, DL: We will submit plans in the next week………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We will start working on the plans and apply for a building permit in the next 2-3 weeks. | 2020-01-23 | Enrico Baez | Install new T-bar ceilings, lighting/switches, verify electrical service/disconnect. Relocate the existing eye washer, widen the exiting door opening and *reverse swing(*if approved by F.M). Install one customer furnished transformer. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
21P000037 |  | 21P000037 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | Paint Only | CHUNG HALL | 427 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-07-31 | [6 empty] | 01/19/21 O-ANS: Paint complete per technician and closed project. 11/30/20 B-SBT: repatch & Paint north wall |  | Paul Ditty |  |  | 2020-11-30 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
21P000102 |  | 21P000102 | FALSE | VC-RED | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | AAALAC Certification updates to rooms 348, 352 & 363 | SPIETH | 348, 352 & 363 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS | YURIDIA REYNOSO | Paul Ditty |  | TBD |  | FALSE |  |  | 2020-10-29 | [6 empty] | 12/08/20 O-ANS: Customer Dierk Biggs confirmed via email that these room updates are complete. |  | Paul Ditty |  |  | 2020-12-08 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000247 |  | 20P000247 | FALSE | CNAS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | Refresh Lab: Patch paint, strip & clean floor, repair broken ceiling and floor (VCT) tiles at room 2110 & 2118. Install Electrical power & Co2 cylinder racks at each end of workbench/tables | SPIETH | 2110 + 2118 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | Dan Lerman |  | 6 |  | TRUE |  |  | 2019-11-27 | [6 empty] | 1/19/21, DL: This project is complete…………..9/30/20, DL: This project is in progress and will be compete in the next 6- 8 weeks……………8/5/20, DL: We will start on this project in the next 6-8 weeks….. | 2020-04-17 | Enrico Baez | Spieth 2110: Carpentry: Seismic anchoring for “New” tables and equipment. Replace damaged ceiling tiles. Install misc. wall mounted items. Sheet Metal: Remove “existing” steel cage. Fabricate & install metal cylinder rack w/ restrains/seismic anchoring to floor. Plumbing: Install Co2 POC for gas cylinders at four (4ea) new free-standing work benches (see configuration on this document). Electrical: Install dedicated *120v power drop & connect to the existing power strips built-in the four (4ea) new workstation tables (see configuration on this document). *VERIFY/CONFIRM VOLTAGE W/ D. MCW. Relamp fixtures as needed. Spieth 2118 & 2110: Sheetmetal: Clean and or replace air distribution grilles. Flooring: Repair/patch broken floor tile and Replace broken ceiling tiles (abate floor tiles if required). Painting: Paint and patch all walls, verify recondition doors @ room side. Plumbing: Assess sinks to be fully operational & clean. *Replace sink in Rm 2118 for glassware, confirm with Faculty/Estella. Replace sink in room 2118 (Sink type TBD by Faculty). HVAC: Check lab air pressure is operational & proper pressure. Custodial: Strip and Wax floor, clean interior windows, wipe down doors and windowsills. EXCLUSIONS: Furnish, assemble, and install new workstations, tables or lab equipment. Removal of existing lab furniture or equipment. Natural gas or air output taps not required (per Faculty). | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000221 |  | 20P000221 | FALSE | BCOE | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | COMPLETE | Christopher Lynch | Todd Ambriz | HONG XU | KEVIN FREEDMAN | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-11-15 | [6 empty] | 1/19/21, DL: This project is 100% Complete……..9/30/20, DL: We are in the process of finishing up a few other projects. Once they are complete, we will schedule the work….8/5/20, DL: Plans are approved and we will start the work in the next 2-6 weeks…….. | 2020-02-25 | Enrico Baez | Install Plywood and supports. Paint Plywood black. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000215 |  | 20P000215 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | Remove Vaughan wall seperating Olmsted 3349/3351.Add 4 single gang outlets and 2, 2gang outlets. | PSYCHOLOGY1 | 3rd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-11-07 | [6 empty] | 1/19/21, DL: This project is 100% complete…………9/30/20, DL: Plans were approved, we had the Vaughn Wall tested for Asbestos containing material. Once we have the results, we will schedule the work………….8/5/20, DL: We will submit plans by this Friday for a building permit | 2020-02-24 | Enrico Baez | 2/24/2020 E. Baez - 1.Remove Vaughan wall and electrical circuit in wall. 2. Add 4 Single Gan outlets and 2, 2gang outlets. 3. Patch vinyl plank flooring from removed wall and safe. 4. Remove panel in 2249 with wall paper on it next to window. 5. Remove handle set to 3351, install blank, render door inoperable. 6. Repair T-Bar ceiling as needed. 7. Patch and paint walls. 8. Coordinate with ITS for data line for 8 computers. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000026 |  | 20P000026 | FALSE | VC-RED | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | Install T-bar ceiling, Provide HVAC and Fire sprinklers drops. Install new 2x4 LED light fixtures | LIFE SCIENCE | Basement Level | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-07-19 | Work on Plans and permits. | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: The plans were submitted two weeks ago. We should receive the plan check review comments in the near future…………….8/5/20, DL: This Project will exceed $50,000. Monty A. will inform customer this is a project that will need to be managerd through PD&C……………3/25/20, DL: We will work on plans when we return back from the campus closure. | 2020-01-31 | Enrico Baez | Install T-bar ceiling with wipable(coated) ceiling tile. Provide HVAC and new Fire sprinklers drops to new ceiling. Install new 2x4 LED light fixtures. Verify Fire alarm systems work. | YES | 2021-01-19 | Fall 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
19P000517 |  | 19P000517 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | COMPLETE | LaRae Lundgren | Emily Engelschall, Sean Cason | DANIELLE GARCIA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-03-07 | Verify scope and schedule work | 2019-12-02 | 2020-12-20 |  |  |  | 1/19/21, DL: This project is complete…………..8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced, We will schedule the work when we return from the campus closure…………11/11/19, DL: I will work on scheduling this project… | 2019-06-17 | Enrico Baez | 6/17/19 E. Baez Conducted site visit with Sean. Will need carpenters to mount TV and electricians to add outlet to North wall. Data not needed. Might need painters depending on how carpenters install TV mount. | YES | 2021-01-19 | FALL 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GH08 | 881 | COMPLETE | Kathryn Uhrich | Jose Wudka | NANCY FERGUSON |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2019-01-29 | Schedule the work. | [5 empty] | 1/19/21, DL: This project is complete……………8/5/20, DL: This project is in Progress and should be complete in the next 8-12 weeks…………….3/25/20, DL: Work orders are produced. Once we are back to work, we will schedule the work………12/11/19 O-ANS: Re-assigned as project allotment - priority #7 for Winter 2020. 11/27/19 O-ANS: Hold by client for re-prioritization for Winter 2020. | 2020-03-04 | Enrico Baez | Install new 3 ton Packaged unit with heat pump and dedicated electrical service on the roof top. Provide 1ea return plenum, 2ea supply drops in the work space. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
18P000214 |  | 18P000214 | FALSE | VC-STU AFF | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Install Card readers | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  | 2 | 2 | FALSE |  |  | 2017-12-08 | Pending special order part | 2019-02-19 | 2020-09-01 |  |  |  | 1/19/21, DL: This project is 100% Complete…….9/30/20, DL: Vendor should have the balance of the material in the next 30- days…….8/5/20, DL: This project is complete except the card reader portion of the project…………6/17/20, DL: The floor covering was completed two weeks ago. The card reader portion of this project is 95% complete but additional parts were needed and they are on order. Once they arrive, we will schedule the installation and this project will be 100% Complete………1/15/20 Emailed Status Report to customer…..1/14/20, DL: We were recently approved to proceed with the work. I have reached out to the vendor for the doors and card access. We are still waiting to hear back from them so we can order the material and schedule the work. I communicated with Nicole on the floor covering replacement. Nicole needs to verify what areas we will replace as we were going to complete several offices and a hallway as part of the scope but this will displace many team members for at least a week. We will work on scheduling the work once Nicole gets back to me……..12/17/19 - O-DHN: Emailed Status Report to Customer……12/19/19, DL; We are working with our contractor to order the material and schedule the work. Once we have confirmation on the material, we will be able to schedule the work. It Is our goal to start this project in late January……11/26/19, DL: This project was taken off of on hold and we can now proceed. I contacted the contractor last week and I am awaiting their response on when they can schedule the work. I also left a message with them this morning………..7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once material arrives, we will schedule the installation.….5/31/19, DL; Contract is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is completed except the floor covering and electronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being prepped for paint. We have a pre-construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, material is ordered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct site visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez |  | YES | 2021-01-19 | Winter 2018 | FS | 0 | 2017 | 2021-08-16 | FY 20-21
20P000208 |  | 20P000208 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | Men's locker room refresh | ATH DANCE | 50 | COMPLETE | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND | EUGENE HUTCHINSON | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-11-04 | [6 empty] | 1/28/21, DL: Project is complete. Paul will schedule the paint once he is back on projects……….1/19/21, DL: We will schedule the balance of the paint before the students return back to campus………..9/30/20, DL: The work is complete except for the paint……………..8/5/20, DL: The work is almost complete.……. |  | Dan Lerman |  |  | 2021-01-28 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000310 |  | 20P000310 | FALSE | BCOE | SL5 BOURNS A-WING A129 - PATCH & PAINT | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. | MARLAN & ROSEMARY BOURNS HALL | A0129 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-01-10 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty. 2/3/2021 B-SBT Patch holes, mask room, sand patches, prime room. 2/4/2021 B-SBT paint room, pull masking, clean room. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2021-02-04 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000403 |  | 20P000403 | FALSE | CHASS | SL5 OLMSTED 232 - PAINT OFFICE | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). | JOHN W. OLMSTED HALL | 2321 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | MELISA VICARIO | Paul Ditty |  | X |  | TRUE |  |  | 2020-03-13 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/11/21. 02/11/21 D-JPO: finished sanding water damage spot primed painted room 2 coats pulled tape vacuumed complete. |  | Paul Ditty |  |  | 2021-02-11 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000469 |  | 20P000469 | FALSE | CHASS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 222 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | SUSAN KOMURA | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-23 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/12/21. |  | Paul Ditty |  |  | 2021-02-12 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000446 |  | 20P000446 | FALSE | CHASS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. | CHASS INTERDISCIPLINARY NORTH | 4047 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-04 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/12/21. |  | Paul Ditty |  |  | 2021-02-12 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUMANITIES BUILDING | 3210 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-24 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/10/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000464 |  | 20P000464 | FALSE | CHASS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) | HUMANITIES BUILDING | 3001 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/09/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000463 |  | 20P000463 | FALSE | CHASS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 | HUMANITIES BUILDING | 2000 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/11/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000467 |  | 20P000467 | FALSE | SOM | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. | HERBERT JOHN WEBBER HALL | 1247 | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-19 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/22/21. 2/22/21 D-JPO CLEANED UP DONE. 02/17/21 D-JPO: primed room and door. 02/16/21 D-JPO: finished prep. |  | Paul Ditty |  |  | 2021-02-22 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000363 |  | 20P000363 | FALSE | BCOE | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | Paint Only | WINSTON CHUNG HALL | 433 | COMPLETE | Christopher Lynch | Todd Ambriz | MANGLAI ZHOU | FARIBORZ KARGAR | PAUL DITTY |  | X |  | TRUE |  |  | 2020-02-13 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/22/21. 2/22/2021 B-SBT pull tape, install plates, clean base/room. 2/19/2021 B-SBT prime and paint room. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2021-02-22 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000419 |  | 20P000419 | FALSE | CNAS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | Paint Only | HERMAN T. SPIETH HALL | 2312 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | PAUL DITTY |  | X |  | TRUE |  |  | 2020-04-22 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 3/18/21. 03/18/21 D-JPO: cleaned room patched masked sanded and primed all walls |  | Paul Ditty |  |  | 2021-03-18 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000462 |  | 20P000462 | FALSE | CHASS | SL5 HMSS 2001 - PAINT OFFICE / CLEAN FLOOR NEW FACULTY HIRE | Patch/paint to existing color for faculty new hire | HUMANITIES BUILDING | 2001 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | Paul Ditty |  | X |  | TRUE |  |  | 2020-06-18 | [6 empty] | 03/19/21 O-ANS: Project complete per Paul Ditty. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  | 2021-03-19 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
21P000079 |  | 21P000079 | FALSE | VC-RED | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. | PSYCHOLOGY BUILDING |  | COMPLETE | Rodolfo Torres | Laura Manor | LESLIE KARPINSKI |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-09-25 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/25/21. 02/25/21 D-BFA: continued painting the black room. Patched in the Quarantine rooms. 02/23/21 D-BFA: Continued painting finish on all green and all repaired cracks. 02/16/21 D-MMN: prepped cracks with caulking. |  | Paul Ditty |  |  | 2021-04-01 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000468 |  | 20P000468 | FALSE | VC-RED | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | Paint Only | HERMAN T. SPIETH HALL | 364 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-06-23 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 12/02/20. 12/09/20 D-MMN: removed masking and reinstalled fallen base with base and wall glue. 12/08/20 D-MMN: applied finish to all the patches in the hallway and storage room. 12/07/20 D-MMN: Applied 3rd. coat of joint compound. returned and sanded then primed patches. these were located in the main hallway and the bedding supply room. vacuumed dust. 12/04/20 D-MMN: Continued scraping, treating and filling efflorescence and cracking paint. started taping baseboards and priming where it was so ready. |  | Paul Ditty |  |  | 2021-04-01 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
19P000485 |  | 19P000485 | FALSE | CNAS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | HOMER D. CHAPMAN HALL | 9 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-29 | This Project is Complete.. |  | 2021-03-12 |  |  |  | 4/1/21, DL: This Project is Complete…………..3/15/21,DL: Bill S. is still working on obtaining the air flow monitor. Once the air flow monitor arrives, we will complete the installation and Bill will be able to have the fume hood certified by a 3rd party vendor…………3/1/21, DL: We need to install the fire extinguisher and air monitor. I sent Bill S. an email asking him if he ordered the air monitor as we do not have one. I also contact EH&S and made them aware that we will be commisioning the fume hood in the very near future…..2/16/21, DL: Plumbing is complete. We will now start the exhasut vent, electrical and then seismically anchor the fume hood…………2/1/21, DL: We have had a delay with the plumbing and it is our goal to be complete on or before 3/1/21…………1/10/21, DL: This project is almost complete. This project will be complete in the next 30- days…………9/30/20, DL: Fume Hood demolition and abatement will be completed on 10/2/20. Fume hood install should be coplete in mid Novemeber……8/5/20, DL: We will submit plans this week. Once plans are approved, we will schedule the work……………Work orders are produced. We need to work on plans and permits once we return. | 2020-02-10 | Enrico Baez | Disconnect, cap and safe off the existing utility services. Provide the necessary abatement services to properly remove the fume hood from the site and deliver to the campus surplus yard. Install one new department furnished fume hood. Abatement Services: Provide the necessary abatement services to perform all utilities disconnections and floor repair. Floorcovering: Patch and or repair as necessary to match or provide a close match. Install rubber base. Access Control: Survey and adjust the entry door closer to increase latch pull to allow the door to closer completely. Patching and painting: Patch and paint wall at the old fume hood location. Mechanical: Disconnect metal duct, cap/safe off, reconnect/reconfigure new duct to accommodate the new fume hood. Electrical: Provide electrical disconnections and safe off. Reconnect/reconfigure power to the new fume hood. Plumbing: Disconnect Air, Gas, Vacuum, Cold water, and Drain, cap and safe off and reconnect/reconfigure service to the new fume hood. Resource Management: Properly remove the fume hood from the site and deliver to the campus surplus yard. | YES | 2021-04-01 | Spring 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000453 |  | 20P000453 | FALSE | CHASS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | Paint Only - Please patch/paint to existing color office for faculty new hire. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 142 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty…..6/18/20 o-dms: trans from 20w028936 to Project Phase - custodial please clean office floor for faculty new hire |  | Paul Ditty |  |  | 2021-04-05 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
21P000003 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Enrico Baez |  | R1 |  | FALSE |  |  | 2020-06-26 | [6 empty] | 4/9/2021 E. Baez roof repairs completed…1/20/2021 E. Baez- Proposal for $24,366 received from Rite-Way Roofing.….01/19/21, DL: Enrico is managing this project………….. | 2020-12-02 | Enrico Baez | Remove tripod antenna. Apply spray roof coating to existing roof surface | YES | 2021-04-09 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21 | 1
21P000078 |  | 21P000078 | FALSE | VC-RED | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MULTIDISCIPLINARY RESEARCH BUILDING |  | COMPLETE | Rodolfo Torres | Laura Manor | TARA BARTHOL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 2020-09-23 | [6 empty] | 4/15/21, DL: The work is complete. We still need to connect several minus 80 freezers. Tara will check in with us when they are ready to be connected……….1/19/21, DL: the First floor work will be complete today, we will start the 2nd floor this week……………. |  | Enrico Baez |  |  | 2021-04-15 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000003 |  | 20P000003 | FALSE | GRAD DIV | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | ADD POWER/DATA, PATCH/PAINT | UNIVERSITY OFFICE BUILDING |  | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS | CHERYL GERRY | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-07-02 | Install hydration station when it arrives | 2021-02-17 | 2021-04-20 |  |  |  | 4/15/21, DL: This project is complete. We will install the hydration station when it arrives…..4/1/21, DL: Electrical, rough plumbing, drywall, and paint is complete. The next step is to install the floor covering with in two weeks……………3/15/21, DL: The demo, electrical and rough plumbing is complete. We will schedule inspection this week. Once we pass inspection, we will schedule the drywall installation, prime, paint and new floor covering……..2/16/21, DL: Conducted a site visit with the plumber and capenter shop. We will start the demo next week…………2/1/21, DL: We will schedule this project to start in 2- weeks……………….1/19/21, DL: Plans were approved and we will schedule the work in the near future………. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Permit is approved. We need to verify floor covering. Once floor covering is confirmed and ordered, we will schedule the work………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We will need plans as we are installing a new hydration station and a counter top that needs to be ADA compliant…………We started the plans and will submit them for a permit and plan check review within 2- weeks……….10/30/19, DL: No Plans will be needed. We will plan on scheduling the work shortly after Thanksgiving……. | 2019-06-13 | Enrico Baez | 9/24/2019 E. Baez--SCOPE-- 1. Removal and disposal of one bulletin board and two director cases. 2. Removal and disposal of abandoned telephone mounting bracket. 3. Remove and dispose of abandoned alarm box in wall. 4. Patch and paint walls in lobby and public restroom area. 5. Provide electrical connection for wall mounted monitor. 6. Cut access for data boxes. 7. Install monitor mount on wall. 8. Construct 7" x 18" laminate counter top and install in Lobby. | YES | 2021-04-15 | FALL 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install electrical utilities for new equipment | PHYSICS BUILDING | 1132 | COMPLETE | Kathryn Uhrich | Jose Wudka | WENDI TAPIA |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-03-19 | site visit with customer for review |  | 2021-03-26 |  |  |  | 4/15/21, DL: This project is 100% Complete……..4/1/21, DL: This project is complete except the sink drain and custodial. Custodial is scheduled to service the room in two weeks………3/15/21, DL: This project was supposed be be complete but we still have a plumbing drain assembly that is back ordered. We will connect the plumbing once the material arrives…………2/16/21, DL: New sink and faucet arrived, we will now schedule the install of the countertop and sink…………..1/19/21, DL: This project is in progress and will be complete with in 30- days………..9/30/20, DL: Plans were submitted for Plan Check review last week and we should have an update on the plan check review process soon………..8/5/20, DL: Need to meet with Kirk to verify electrical load. Once confirmed, we will work on plans for a permit. | 2019-10-15 | Enrico Baez | Install utilities for new equipment | YES | 2021-04-15 | Summer 2019 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000397 |  | 20P000397 | FALSE | CNAS | SL5 ENTOMOLOGY 139 - PATCH AND PAINT OFFICE | Patch and paint room 139 for the new faculty member | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 0139 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-03-05 | [6 empty] | 04/16/21 O-ANS: Project complete per Paul Ditty. 02/10/21 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  | 2021-04-16 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000370 |  | 20P000370 | FALSE | CHASS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | SPACE RENOVATION PROJECT | GORDON S. WATKINS HALL | 1311 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 2020-02-19 | This Project is complete…. | 2021-03-19 | 2021-07-02 |  |  |  | 4/30/21, DL: The paint is complete. The floor covering is ordered and will be installed in about two weeks………………4/15/21, DL: Asbestos, electrical, and drywall are complete. Painters are in the space prepping the walls…..4/1/21. DL: Asbestos abatment is scheduled to be complete by this Monday. We will start the framing and electrical next week……………..3/1/21, DL: Plans were approved. We now need to send our 14- day notice to the AQMD and schedule the demolition……..2/16/21, DL: Plans were submitted with building permit last week. We are now in the plan check review process………1/19/21, DL: We will start working on the plans for this project in the next three weeks. We should have plans to submit for plan check review in the next 5- weeks……….. |  | Enrico Baez |  |  | 2021-04-30 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000253 |  | 20P000253 | FALSE | BCOE | SL5 BOURNS HALL LAB B156 - EXHAUST SYSTEM | EXHAUST SYSTEM | MARLAN & ROSEMARY BOURNS HALL | B0156 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 2019-12-11 | Demolish cabinets and schedule paint and flooring | 2021-03-01 | 2021-05-14 |  |  |  | 4/30/21, DL: This project is 100% Complete :) ……… 4/15/21, DL: The power is complete. The exhaust is scheduled to be complete with in the next 30 days……….3/15/21, DL: The new dedicated electrical outlet is complete. We are also in the process of ordering the exhaust vents for the printer…………..2/16/21, DL: Plans were submitted 2- weeks ago. We received the plans back last week with corrections needed. We will resubmit the plans back to the building official by the end of the week….1/19/21, DL: We will start working on the plans for this project in the next two weeks. We will start this project once the permit is approved…… |  | Enrico Baez |  |  | 2021-04-30 | Winter 2021 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000144 |  | 20P000144 | FALSE | CNAS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A | ALFRED M. BOYCE HALL | 3432, 3432A, 3446, 3446A | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-09-26 | Install floor covering |  | 2021-04-23 |  |  |  | 4/30/21, DL: This Project is 100% Complete………..4/15/21, DL: The asbestos abatement is complete. The floor covering will be complete by the end of next week……………4/1/21, DL: Asbestos abatement is scheduled for April 8th - 12th. We will install the floor covering shortly after and deep clean the space. This project is on schedule to be complete on or near 4/20/21…………..2/16/21, DL: Project Is on schedule. Paint is 90% complete. Once paint is complete, we will schedule the floor repairs and final deep clean……… 2/1/21, DL: We are making good progress and are target date is still 3/14/21………….1/19/20, DL: This project is in progress and will be complete in the next 30- days………….9/30/20, DL: We have started a few items but we are waiting on Matt U. and the PI to remove their items so we can have access to the space. Once the space is cleared out, we will proceed with the work…………8/5/20, DL: We will start the work in the next 4-6 weeks. | 2020-02-18 | Enrico Baez | This project is 100% Complete… ;) Boyce 3432, 3446, 3436 and 3436A . Patch and paint 3432, 3432A, 3436, 3436A, 3446, 3446A. Reface/replace water damaged cabinets near sink (3446). Install GCFI outlets near sink (replace existing) (3446). Install panel cover for electrical panel box. Replace many burnt out bulbs in ceiling lamps. Replace broken chemical plexi-glass on bench shelves. | YES | 2021-04-30 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000448 |  | 20P000448 | FALSE | BCOE | SL5 CHUNG HALL ROOM 216 - PATCH & PAINT | At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. |  | 216 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-06-11 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  |  |  |  | 2021-05-11 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000450 |  | 20P000450 | FALSE | BCOE | SL5 CHUNG HALL ROOMS 217, 218, 219 - PATCH & PAINT | Please patch and paint these adjoining rooms within suite 216. |  | 217, 218, 219 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-06-12 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  |  |  |  | 2021-05-13 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000445 |  | 20P000445 | FALSE | CNAS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 279 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | DAN LERMAN |  | 3 |  | TRUE |  |  | 2020-06-03 |  | 2021-04-22 | 2021-05-31 |  |  |  | 5/14/21, DL: This project is 100% Complete……4/30/21, DL: The floor will be installed tomorrow. The project will be 100% next week………………4/15/21, DL: The plumbing and electrical is complete. The painters will be done this week. The floor covering is ordered and will be installed with in two weeks…..4/1/21, DL: We will try and start this project with in the next three weeks…………3/15/21, DL: The building permit was approved today. We will work this project in to our schedule and we will schedule the work once we are ready to and in line with our other projects that are already in progress……….2/16/21, LB: Changed to Priority 3 per Dan…….1/19/21, DL: This is a priority 3 project. We will start the project when all priority 1 &2 projects are in process or almost complete… |  | Enrico Baez |  |  | 2021-05-14 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000218 |  | 20P000218 | FALSE | VC-RED | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | VIVARIUM UPDATE AIR COMPRESSOR | HERMAN T. SPIETH HALL | 347 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | DAN LERMAN |  | 2 | R2 | FALSE |  |  | 2019-05-17 | Set & place the compressor. Start elect. / plumbin | 2021-04-07 | 2021-05-14 |  |  |  | 5/14/21, DL: This project is 100% Complete….4/30/21, DL: The plumbers are 75% complete. Once the plumbing is complete, the electricians will start…………4/15/21, DL: The compressor was delivered to the permanent location. The plumbers will start the air lines and drain assembly next week. The electricians will connect the electrical within a month, as they have a few other projects in their queue that need to be completed before they start this project………….4/1/21, DL: We are scheduled to relocate the compressor next week. Once the compressor is placed, we will anchor the compressor and start the electrical and plumbing……………….3/15/21, DL: We received confirmation the Compressor is on site. We will schedule the work once as soon as we are able to………….2/1/21, DL: WE will start the process for this project once we are closer to completing priority 1 projects. This is a prioity 2 project……1/19/21, /DL: This project has been scoped. We will start the work when we are complete with all priority #1 projects……. |  | Enrico Baez |  |  | 2021-05-14 | Winter 2021 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
21P000111 |  | 21P000111 | FALSE | CHASS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. | GORDON S. WATKINS HALL | 2144 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-11-18 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
21P000110 |  | 21P000110 | FALSE | CHASS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. | GORDON S. WATKINS HALL | 2146 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-11-18 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
21P000109 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | PATCH, PAINT & NEW FLOORING |  | 1146 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-11-18 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | PAUL DITTY |  |  | 2021-05-24 | FY 21-22 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
21P000019 |  | 21P000019 | FALSE | BCOE | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | Bourns Office A305 - Install Plank Floor | MARLAN & ROSEMARY BOURNS HALL | A305 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | 3 | 2 | TRUE |  |  | 2020-07-20 | This project is Complte. | 2021-04-30 | 2021-05-21 |  |  |  | 6/2/21, DL: This project is complete…4/30/21, DL: This project started this week. The paint will be complete next week. The floor will be installed in about two weeks…………..4/1/21, DL: We will schedule the work with in the next three weeks. We are only doing this work early as the two primary trades are available. The damaged window covering will be replaced by a vendor…………..1/19/21, DL: This a priority 3 project. We will start this project when all priority #2 projects are complete………..1/14/21 O-ANS: Updated prioritization to #3 (from #2) per org leadership request. |  | Enrico Baez |  |  | 2021-06-02 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
21P000009 |  | 21P000009 | FALSE | CNAS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | GLOVEBOX SYSTEM | CHEMICAL SCIENCES |  | COMPLETE | Kathryn Uhrich | Jose Wudka | NATASHA GONZALES |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 2020-07-08 | This project is complete….. | 2021-03-08 | 2021-04-23 |  |  |  | 6/2/21, DL; This project is complete……4/15/21, DL This project is complete. When the glove box arrives, we will make the final connections………..4/1/21, DL: Demolition, paint, electrical and venting is done for the glove box. The snorkel parts are ordered. The flooring is ordered and should be here next week. We will schedule the floor install once we have the material on site………….3/15/21, DL: We will demolish the cabinets this week. We will also schedule the paint and floor replacement. The venting for the glove box and snorkel should be ordered this week………3/1/21, DL: The plans were approved last week. We will try and schedule demo this week or early next week……..2/16/21, DL: We submitted plans for building permit but corrrections are needed. We contacted the glove box manufacture for follow-up questions and we are waiting to hear back from them. Once we have confirmation on the needed information, we will resubmit the plans back to the building official……….1/19/21, DL: we will submit plans this week or earlier next ……………. |  | Enrico Baez |  |  | 2021-06-02 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 20-21
20P000248 |  | 20P000248 | FALSE | CNAS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT | Space Management has temporarily allocated Rooms 1223 and 1223-A in Webber Hall to CNAS. We need this lab cleaned and modified to accommodate relocating an existing (and active) lab. | HERBERT JOHN WEBBER HALL | 1223 + 1223-A | COMPLETE | Kathryn Uhrich | Jose Wudka | SHARYL MURDOCK |  | Dan Lerman |  | 5 | 4 | FALSE |  |  | 2019-11-27 | Project is Complete. | 2021-04-12 | 2021-05-31 |  |  |  | 6/2/21, DL: This project is complete……5/14/21, DL: This project is 95% complete. Items that need to be completed are: remove window AC unit, replace glass where the AC unit was removed and install window covering…………..4/30/21, DL: Demolition is complete, we will start the electrical and painting in the next two weeks…………..4/15/21, DL: The space was surveyed for hazardous material. There were rodent droppings, which will be disposed of this weekend, the ceiling tiles had mold. The ceiling tiles were removed. We will start the demo of the floor and some other items with in the next three weeks………..4/1/21, DL: We need to survey the space for hazardous material and arrange to have the space sanitized………………1/19/21, DL: This project is a priority #5. We will start this project when all priority #4 projects are complete…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….02/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Survey space for hazardous material. Once survey is complete, we will schedule abatement and the work. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2021-06-02 | Winter 2021 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
20P000320 |  | 20P000320 | FALSE | CNAS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | ACTIVATE VACUUM LINES | HERMAN T. SPIETH HALL | 1303 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | DAN LERMAN |  | 4 |  | FALSE |  |  | 2019-11-20 | Project is complete. | 2021-05-03 | 2021-06-11 |  |  |  | 7/15/21, DL: This project is complete……..6/2/21, DL: Electrical work is complete. The Plumbing shop will start to install the vacuum lines this Thursday. This project should be 100% complete by next Friday…….5/14/21, DL: The space was surveyed for hazardous material. Once we have the survey we will schedule work…………4/30/21, DL: Conducted site visit this week; we will survey the space for hazardous material before we conduct any work. We should start the work in about two weeks…………….1/19/21, DL: This is a priority 4 project. We will start this project when all all priority 3 projects are complete……….. |  | Enrico Baez |  |  | 2021-06-11 | Winter 2021 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
21P000137 |  | 21P000137 | FALSE | SOM | SL5 WEBBER HALL - ACCESS CONTROL | Per attached Sales Quote 43830-7 dated 11/6/2020, from Enterprise Security in Tustin, please proceed with the proposal, planning. permit, and contract to complete this project. |  | 1247 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | CYNTHIA CAROLINA | Dan Lerman |  | R1 |  | FALSE |  |  | 2021-03-09 | Final inspection and payment | [5 empty] | 7/15/21, DL; This project is complete. We still need to conduct the final inspection. There was a problem identified during the project where a repair is needed via an FAU number. We will conduct the repair under an SL6. Cynthia Carolina is aware of the additional needed repair that was not part of the scope or work……/9/21, O-DMS: EMAIL TO DAN LERMAN PROJECT # AND ASSIGNED TO J-DLN. |  | Dan Lerman |  |  | 2021-07-15 | Winter 2021 | FS | 0 | 2021 | 2021-08-16 | FY 21-22 | 1
21P000001 |  | 21P000001 | FALSE | CNAS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | NEW GROWTH CHAMBER PLACEMENT | HOWARD SAMUEL FAWCETT LABORATORY |  | COMPLETE | Kathryn Uhrich | Jose Wudka | LINDA WALLING |  | DAN LERMAN |  | 2 |  | TRUE |  |  | 2020-06-08 | This project is complete | 2021-04-20 | 2021-05-22 |  |  |  | 7/15/21, DL: This project is complete. Linda is requesting a sensored light switch which we will install under an SL6 work order………..4/30/21, DL: for most part this growth chamber is complete except the air curtain which is still not on site……………4/15/21, DL: This project is in progress. Linda will schedule the installation to take place in two weeks. We are waitng on the air curtain. This project should be 100% complete with in the next 4- weeks………4/1/21, DL: Plans were approved. We will try and start this project with in the next 3-weeks or sooner if possible…..3/1/21, DL: This was recently changed to a priority 2 project. Once plans are approved, we will work on the schedule noting, the schedule for this will work around pending priority 1 projects……2/16/21, LB: Changed to Priority 2 per Dan….1/19/21, DL: This is a priorty 3 project. We will start this project when all priority 2 projects are complete. |  | Enrico Baez |  |  | 2021-07-15 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 21-22
20P000366 |  | 20P000366 | FALSE | CNAS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | MINOR LAB RENOVATION | HERMAN T. SPIETH HALL | 2375 / 2375-A | COMPLETE | Kathryn Uhrich | Jose Wudka | SHERICE UNDERWOOD |  | DAN LERMAN |  | 7 |  | TRUE |  |  | 2020-02-19 | Final walk and punch list items. | 2021-05-14 | 2021-07-16 |  |  |  | 7/15/21, DL: This project is complete. I am meeting with Kate for a final walk through tomorrow morning………….5/14/21, DL: We will start the project in the next three weeks, the door will be ordered next week. We will schdule paint to take place in the next 3-4 weeks….1/19/21, DL: This is a priority 7 project, we will start this project when all priority 6 projects are complete………….. |  | Enrico Baez |  |  | 2021-07-16 | Winter 2021 | FS | 0 | 2020 | 2021-08-16 | FY 21-22
3632 | 3632 |  | FALSE | ATHLETICS | SRC North Instant Replay System | Possible update of instant replay system in Student Recreation Center North to include volleyball if mandate by Big West Conference is enacted. This will include placing cameras on the ends of the court that will send signal back to the control room and could involve additional wiring to courtside connection boxes. Scope may include upgrading audio connections. Volleyball season starts in late August... first home game TBD. No charges to this FAU unless Athletics notified in advance of work to be performed. Work Notes: Project will require coordination not only with Athletics but must also with Recreation (Mike Eason), and their scheduling may affect above dates. Possible vendor to be consulted is TechNet who has indicated ability to do such a project in recent times. |  |  | Delayed until 8/2022 per Athletics | Tamica Smith Jones | Joe Erbland | Joe Erbland |  | Tameesha Hayes | 3 |  |  | FALSE |  |  | 2021-04-01 | Delayed until 8/2022 per Athletics | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3515d | 3515d |  | FALSE | PB&A | Multiple SF6 Primary Switches | Sub-project of 950568 |  |  | Design | Gerry Bomotti | TBD | John Franklin |  | John Franklin | 2 |  |  | FALSE |  |  | 2021-03-01 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | Design | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 2015-12-02 | Bidding | [12 empty] | PD&C | 0 | 2015 | 2021-08-16
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Design | Gerry Bomotti | TBD | ---- |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Bidding | [12 empty] | PD&C | 0 | 1900 | 2021-08-16
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 2020-09-22 | Bidding | 2021-12-01 | 2022-03-01 | [10 empty] | PD&C | 0 | 2020 | 2021-08-16
3631 | 3631 |  | FALSE | ITS | SOMED 1 UPS | The Information Technology Solutions (ITS) intends to replace its existing UPS unit with a state of the art systems that will support all of the requirements set-forth by the University of California, Riverside ITS and Facilities departments. Our primary objective is to provide ITS critical services and various other software applications. The ITS department would like to Procure (1) redundant UPS System with all accessories and maintenance for three years after warranty (AMC). Procure One Replacement 500KW UPS Unit, Installation of New UPS, Removal and Disposal of Old UPS components, Startup Services for New UPS, Electrical Installation of New UPS and Removal of Rental UPS connections (High Voltage) |  | 1625 | Design | Danna Gianforte | Shelley Gupta | Cesar Higueros |  | Tameesha Hayes | 1 |  |  | FALSE |  |  | 2021-07-22 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3630 | 3630 |  | FALSE | SOM | SOMR Egress Doors/Cameras | All egress doors for floors 1-3. need to be replaced with compliant standards. Project to also include security cameras for entry and exit on 1st and 2nd floor. |  |  | Design | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes | 2 |  |  | FALSE | 65000 |  | 2020-03-04 | Bidding | [12 empty] | PD&C | 0 | 2020 | 2021-08-16
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Design | Gerry Bomotti | TBD | ---- |  | Fernando Canon | 1 |  |  | FALSE | 33980000 |  | 2019-03-04 | Construction | 2021-10-01 | 2023-05-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-16
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 19 |  |  | FALSE | 320000 |  | 2018-07-31 | Bidding (Spring 2022 per Housing) | [12 empty] | PD&C | 0 | 2018 | 2021-08-16
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS BUILDING |  | ESTIMATE | Kathryn Uhrich | Jose Wudka | JOSE WUDKA |  | Enrico Baez |  | R1 |  | FALSE |  |  | 2019-12-19 | Awaiting Response from Client | [5 empty] | 05/13/21 O-ANS: Enrico corresponded with Dr. Wudka on 3/14/2021. He had emailed me stating that the College was going to discuss the project. Still awaiting a response to that inquiry. I follow up today requesting an update. 1/19/21 DL: Enrico is managing this project. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-08-16 |  | 1
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LABORATORIES 1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 2020-02-19 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-08-16
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SUPPORT SERVICES BUILDING | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | Emily Engelschall, Sean Cason | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-22 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-08-16
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL BUILDING | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 2019-12-04 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2019 | 2021-08-16
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Bidding | Gerry Bomotti | TBD | ---- |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 2020-09-15 | Award Contract | [12 empty] | PD&C | 0 | 2020 | 2021-08-16
3636 | 3636 |  | FALSE | PB&A | Tunnel DAS | Adding radio repeaters to the tunnel system to improve coverage in a high hazard work area. The project consists of adding a rooftop antenna, battery back-up, amplifier, repeater antennas, and coax runs through the tunnel system. A few items need to be mounted. Golden State Communications will need to interface additional system to the existing radio system. |  |  | In Bidding | Gerry Bomotti | TBD | Tracy Stark |  | Tameesha Hayes | 1 |  |  | FALSE | 77271 |  | 2021-05-05 | Award Contract | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | In Bidding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 61918 |  | 2020-09-21 | Award Contract | 2021-09-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2020 | 2021-08-16
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Bidding (Phase 2) | Kathryn Uhrich | Jose Wudka | Sabrina Schuster |  | Scott Donnell | 6 |  |  | FALSE |  |  | 2016-12-06 | Award Contract (Phase 2) | 2021-10-01 | 2021-11-01 | [10 empty] | PD&C | 0 | 2016 | 2021-08-16
3590b | 3590b |  | FALSE | PB&A | DMFI(FY17-20) Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Construction | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 2019-11-27 | Complete Construction | 2021-07-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-16
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 2020-09-23 | Complete Construction | 2021-07-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2020 | 2021-08-16
3637 | 3637 |  | FALSE | ATHLETICS | Soccer Field Spiideo Video Installation | We are making an addition to the soccer stadium by adding a 40 foot pole at center field with a cloud based camera operating system. |  |  | In Construction | Tamica Smith Jones | Joe Erbland | Eugene Hutchinson |  | Tameesha Hayes | 1 |  |  | FALSE |  |  | 2021-04-16 | Complete Construction | 2021-08-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2021 | 2021-08-16
3615 | 3615 |  | FALSE | CAP PROG | Student Success Center Buildout | Buildout and furnishing of the SSC dining venue for temporary use as seating/study area and other as needed construction scope related to the overall building project that was not described in the Basis of Design. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Mihai Gavan | 17 |  |  | FALSE | 980000 |  | 2021-03-09 | Complete Construction | 2021-03-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2021 | 2021-08-16
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Georgios Vidalakis |  | Scott Donnell | 5 |  |  | FALSE | 640745 |  | 2020-09-11 | Complete Construction | 2021-01-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2020 | 2021-08-16
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Richard Zapien |  | Scott Donnell | 3 |  |  | FALSE | 39000 |  | 2020-05-08 | Cooler Delivery | 2021-06-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2020 | 2021-08-16
3557 | 3557 |  | FALSE | CHASS | Campus Sculpture Installation | We will bring 5 sculptures to campus that will go in public places that have already been identified by Uma Ramasubramanian and Jacqueline Norman . Please construct 5 concrete plinths at various locations around campus. Locations are on the attachment. |  |  | In Construction | Juliet McMullin | Cindy Williams | Emily Rankin |  | Tameesha Hayes | 4 |  |  | FALSE | 82000 |  | 2019-11-27 | Complete Construction | 2020-10-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-16
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | In Construction | Gerry Bomotti | Sharyl Murdock | Daneca Stevens |  | Daneca Stevens | 2 |  |  | FALSE | 507364 |  | 2019-07-30 | Complete Construction | 2021-08-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-16
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | In Construction | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 3 |  |  | FALSE | 1340000 |  | 2019-05-15 | Complete Construction | 2021-05-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-16
3524 | 3524 |  | FALSE | VC-STU AFF | Student Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | STUDENT SERV |  | In Construction | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE | 450000 |  | 2019-04-16 | Complete Construction | 2021-08-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-16
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | In Construction | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 97050000 |  | 2019-03-04 | Complete Construction | 2021-07-01 | 2023-05-01 | [10 empty] | PD&C | 0 | 2019 | 2021-08-16
3490 | 3490 |  | FALSE | PB&A | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | Parking Lot 13 |  | In Construction | Gerry Bomotti | TBD | Irma Henderson |  | John Franklin | 25 |  |  | FALSE | 31844000 |  | 2018-12-06 | Complete Construction | 2020-02-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2018 | 2021-08-16
3467 | 3467 |  | FALSE | PB&A | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 17 |  |  | FALSE | 405000 |  | 2018-07-31 | Complete Construction | 2021-08-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2018 | 2021-08-16
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Tracey Kahn |  | Scott Donnell | 9 |  |  | FALSE | 1575000 |  | 2018-01-08 | Complete Construction | 2021-02-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2018 | 2021-08-16
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | ---- |  | Mihai Gavan | 9 |  |  | FALSE | 60430000 |  | 2017-06-01 | Complete Construction | 2019-11-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2017 | 2021-08-16
3286 | 3286 |  | FALSE | PB&A | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 10 |  |  | FALSE | 3375000 |  | 2017-03-29 | Complete Construction | 2021-02-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2017 | 2021-08-16
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | ---- |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete installation of UPS | 2021-01-01 | 2021-12-31 | [10 empty] | PD&C | 0 | 2016 | 2021-08-16
3195 | 3195 |  | FALSE | FAC-PLNG-DESIGN-CONST | North District | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | In Construction | Susan Marshburn | Da Lan Dinh | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 4146146.55 |  | 2016-10-26 | Complete Construction | 2019-07-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2016 | 2021-08-16
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 5 |  |  | FALSE | 600000 |  | 2019-06-18 | Wire pull, programming of NFACP | 2021-06-01 | 2021-08-27 | [10 empty] | PD&C | 0 | 2019 | 2021-08-16
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Construction by USDA | Kathryn Uhrich | Jose Wudka | MaryLou Polek |  | Scott Donnell | 10 |  |  | FALSE | 2500 |  | 2019-10-04 | Complete Construction by USDA | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | ---- |  | Fernando Canon | 7 |  |  | FALSE | 432510 |  | 2016-02-25 | Bidding | 2021-12-01 | 2022-02-01 | [10 empty] | PD&C | 0 | 2016 | 2021-08-16
3626 | 3626 |  | FALSE | UNDERGRADUATE EDUCATION | Rivera Library Room Modifications | Conduct room modifications to support new wall display on west wall Rivera A101A. Work needed: 1. West wall - ½” three-ply to support 12 x 55” displays over bookshelves. 2. West wall – drywall cover bookshelves any area not covered by the technology displays. 3. West wall – add electrical outlets as needed for new displays 4. North and south walls – add electrical for new motorized shades 5. Rivera A101A – add carpeting 6. Rivera A101A – paint room Notes: - Working with Chuck Forsyth in ITS and Bahram Mobasher from CNAS/Physics on project. - Israel and Chuck had a preliminary meeting with Enrico Baez from facilities to discuss project. - Point of contact: Israel Fletes and Charles Forsyth. Israel Fletes cellphone: 951-300-6693 |  | A101A | In Design |  |  | Israel Fletes |  | Vilma Kern | 1 |  |  | FALSE | 32000 |  | 2021-02-10 | Construction | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3624 | 3624 |  | FALSE | BCOE | CE-CERT Circuit Upgrade | We have an existing 208 VAC 100 Amp circuit. We would like to upgrade to a 200 Amp service. The existing service is located in the electrical room at 1084 Columbia. |  |  | In Design | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Tameesha Hayes | 5 |  |  | FALSE | 4100 |  | 2021-03-03 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3614 | 3614 |  | FALSE | INACTIVE P&B | MLK Water Meters | Provide by contract plumbing point of connections and irrigation infrastructures to north and south sides of Martin Luther King Blvd. for watering of UCR palm trees. City of Riverside shall install two (2) ¾” [City] water meters at points of connection. Provide approximately 300’ of new irrigation main-line with associated trenching via contract and/or via facilities work order TBD. |  |  | In Design | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 17 |  |  | FALSE | 31790 |  | 2021-04-30 | Bidding | 2021-10-01 | 2021-11-01 | [10 empty] | PD&C | 0 | 2021 | 2021-08-16
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | Jose Wudka | Wendi Tapia |  | Tameesha Hayes | 12 |  |  | FALSE |  |  | 2020-06-19 | Waiting for equipment from overseas | [12 empty] | PD&C | 0 | 2020 | 2021-08-16
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 500000 |  | 2019-09-05 | Bidding | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | In Design | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 2019-03-04 | Bidding | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 3182452.32 |  | 2016-12-16 | Bidding | 2021-11-01 | 2022-01-01 | [10 empty] | PD&C | 0 | 2016 | 2021-08-16
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 22 |  |  | FALSE |  |  | 2016-10-10 | Bidding | 2022-02-01 | 2022-06-01 | [10 empty] | PD&C | 0 | 2016 | 2021-08-16
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | ---- |  | Fernando Canon | 18 |  |  | FALSE | 2600000 |  | 2016-05-19 | Funding & Approval | [12 empty] | PD&C | 0 | 2016 | 2021-08-16
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | In Funding | Kathryn Uhrich | Jose Wudka | Mireya Botello Santoyo |  | Scott Donnell | 1 |  |  | FALSE | 32871.65 |  | 2020-07-14 | Secure Funding for Additional Scope | [12 empty] | PD&C | 0 | 2020 | 2021-08-16
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Funding | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Scott Donnell | 1 |  |  | FALSE | 700000 |  | 2018-04-04 | Complete Funding | [12 empty] | PD&C | 0 | 2018 | 2021-08-16
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | John Franklin | 2 |  |  | FALSE |  |  | 2019-03-08 | Complete Report-Arc Flash | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3612 | 3612 |  | FALSE | CAP PROG | Native American Landscape Garden | Create a physical marker to commemorate the UCR Land Acknowledgement in the form of a Native American Landscape Garden (working name) at the proposed project location. |  | Ext | In Programming | Jacqueline Norman | Sharyl Murdock | Uma R. |  | Vilma Kern | 15 |  |  | FALSE | 103000 |  | 2021-02-11 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | ---- |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 2019-03-04 | DB Competition | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis (RE Proj) | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 2019-02-14 | Complete Study | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 2018-10-31 | CEQA | [12 empty] | PD&C | 0 | 2018 | 2021-08-16
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Study | [12 empty] | PD&C | 0 | 2018 | 2021-08-16
21P000183 |  | 21P000183 | FALSE | PB&A | SL5 OBAN A&B - PROJECT PORCH REPAIRS 2, 10, 18, 26 | TRENTON MABEE SL5 PROJECT FOR OBAN A & B APT 2, 10, 18, AND 16. PORCH REPAIRS. ZONE MAINTENANCE CARPENTER SHOP |  |  | IN PROGRESS | Gerry Bomotti | TBD | TRENTON MABEE |  | Chris Pillen |  |  |  | FALSE |  |  | 2021-05-13 | [6 empty] | 08/06/21 O-ANS: Assigned to Trenton Mabee to manage project. |  | Chris Pillen |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-08-16
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 245 | IN PROGRESS | Juliet McMullin | Cindy Williams | ANDREA HIDALGO |  | DAN LERMAN |  | 3 |  | FALSE |  |  | 2020-01-02 | Make corrections and resubmit plans on 7/15/21 | 2021-05-24 | 2021-09-23 |  |  |  | 08/02/21, DL: The plans are now approved. We ordered the light fixtures and have also started the work. It is our plan to be complete with the project by September 23rd and the Arts Department currently has an exhibit they are planning to present on or near the 23rd……7/15/21, DL: We are still in plan check review with the building department and a few corrections were needed. We will resubmit the corrections tomorrow. Hopefully the permit will be approved in the next two weeks……..6/2/21, DL: We are almost complete with the plans. We will submit the plans to the customer for review by the end of the week. Once the cutomer approves the plans, we will apply for the building permit………4/20/21, DL: Conducted site vist with the Arts team. We will start working on the plans in the next two weeks…………1/19/21, DL: This is a priority 3 project. We will start the plans and permit for this project when all priortiy #2 projects are complete…….. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-08-16
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Convert Basement Library into Piano Lab | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 54 | IN PROGRESS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 2019-11-19 | Framing and electrical | 2021-05-14 | 2021-10-31 |  |  |  | 08/02/21, DL: Most of the demolition is complete. We started the framing today. It is our goal to be 100% complete with this project by the end of October....7/15/21, DL: Plans were approved this week. Carpenter shop is ordering material and we should start the work next week…… 6/2/21, DL: We applied for the building permit last week. We should have approved plans in the next 1-2 weeks…..5/14/21, DL: We sent Paul R. the 75% complete plans today for review. Once Paul approves the plans and layout of the pianos, we will proceed with completing the plans and apply for the building permit. The demolition of the cabinets and floor covering is complete. The carpenter shop is also pre-ordering their material to help expedite the project once we have the approved building permit……4/1/21, DL: We will start the plans process over the next two weeks and try and apply for a building permit in the next 2-3 weeks…1/19/21, DL: We will Start the plans, permit and the work once all priority #3 projects…11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks…. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | 0 | 2019 | 2021-08-16
3648 | 3648 |  | FALSE | PB&A | Bannockburn Walkway Repairs | Several walkway locations at Bannockburn have deteriorated to the point that they must be replaced. The topcoat is past it’s service life and has lost all waterproofing effectiveness. As a result, the underlying sheathing, T&G, and support beams have suffered extreme water damage. Scope of Work: Replace support beams, T&G, and topcoat system at 2 locations: L bldg. & V bldg. Requesting JOHN FRANKLIN as PM. |  |  | New (7/12/21) | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 1 |  |  | FALSE |  |  | 2021-07-12 | New (7/12/21) | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3645 | 3645 |  | FALSE | PB&A | Falkirk Seismic Rating Study | FALKIRK STRUCTURAL STUDY - provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. |  |  | New (7/12/21) | Gerry Bomotti | TBD | Sean Hatfield |  | D.Hecht/J.Franklin | 2 |  |  | FALSE |  |  | 2021-07-12 | New (7/12/21) | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3651 | 3651 |  | FALSE | UNDERGRADUATE EDUCATION | XCITE RISE Classroms-Adhesive Wall Decals | Install 110 RISE Adhesive Wall Decals in the new RISE classrooms throughout campus. |  |  | New (8/12/21) |  |  | Sohail Wasif |  | Vilma Kern |  |  |  | FALSE |  |  | 2021-08-12 | New (8/12/21) | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3650 | 3650 |  | FALSE | CNAS | Greenhouse 16-3 Rebuild Estimate | We need an estimate to rebuild greenhouse 16-3 that burned down in a fire |  |  | New (8/2/21) | Kathryn Uhrich | Jose Wudka | Sue Lee |  | Scott Donnell | 13 |  |  | FALSE |  |  | 2021-08-02 | New (8/2/21) | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3627 | 3627 |  | FALSE | VC-STU AFF | Costo Hall New Doors | Add three (3) doors to divide new office designations in Costo Hall. Two of the doors require new frames |  |  | On Hold | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 8 |  |  | FALSE |  |  | 2021-03-04 | On Hold | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 2019-12-10 | Departmental Approval | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 9 |  |  | FALSE | 1500000 |  | 2019-11-06 | On Hold | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 600000 |  | 2019-09-05 | On Hold | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 16 |  |  | FALSE | 0 |  | 2018-07-16 | Coordinating with North District | [12 empty] | PD&C | 0 | 2018 | 2021-08-16
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | On Hold | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 2018-06-22 | Awaiting direction by Provost | [12 empty] | PD&C | 0 | 2018 | 2021-08-16
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Joe Erbland | Johnathan Jensen |  | Fernando Nunez | 4 |  |  | FALSE | 0 |  | 2018-08-23 | Department approval to move fwd | [12 empty] | PD&C | 0 | 2018 | 2021-08-16
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 13 |  |  | FALSE | 0 |  | 2017-12-03 | On Hold | [12 empty] | PD&C | 0 | 2017 | 2021-08-16
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | SOCCER FIELD AND AREA |  | On Hold | Tamica Smith Jones | Joe Erbland | Joe Erbland |  | Daneca Stevens | 5 |  |  | FALSE | 0 |  | 2014-04-10 | Need direction by PM Director | [12 empty] | PD&C | 0 | 2014 | 2021-08-16
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | On Hold (COVID-19) | Brian Haynes | Cathy Eckman | Christina Wong |  | Tameesha Hayes | 5 |  |  | FALSE | 130000 |  | 2019-03-19 | On hold (COVID-19) | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 1 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [12 empty] | PD&C | 0 | 2017 | 2021-08-16
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 6 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [12 empty] | PD&C | 0 | 2018 | 2021-08-16
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MATERIALS SCIENCE & ENGINEERING | 71 | PLAN DEVELOPMENT/CHECK | Christopher Lynch | Todd Ambriz | DONG YAN |  | DAN LERMAN |  | 2 | 3 | FALSE |  |  | 2020-08-06 | Schedule the work once the permit is approved | 2021-06-02 | 2021-09-15 |  |  |  | 08/02/21, DL: We are still in the plan check review process. Once the permit is approved, we will schedule the work….7/15/21, DL: Plans are complete, we will apply for the building permit today and the permit should be reviewed and approved in the next 2-4 weeks. Once the permit is approved, we will order the material and schedule the work……6/2/21, DL: We will work on the final plans the week of 6/14/21 and try to apply for building permit on or before 6/22/21. Once the permit is approved, we will schedule the work…. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-08-16
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | W. CONWAY PIERCE HALL | 2232A | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Jose Wudka | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 2020-01-22 | Schedule the work once the permit is approved | 2021-06-04 | 2021-09-30 |  |  |  | 08/02/21, DL: The plans are still being review by the building department adn EH&S. Once the plans are approved, we will schedule the work....7/15/21, DL: Plans will be complete and we will apply for the building permit by tomorrow enveing. If the permit is appproved, which should take 2-4 weeks for the review and approval process, we will order the material and schedule the work……5/14/21, DL: Project is scoped, we will work on plans and submit them to Kevin for review in about 3- weeks…….1/19/21, DL: This is a priority #9 project. We will start this project when all priority #8 projects are complete… |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-08-16
3640 | 3640 |  | FALSE | VC-RED | MRB Circulation Pumps E-Power | MRB Circulation Pumps e-Power |  |  | Pre-Programming | Rodolfo Torres | Laura Manor | Tara Barthol |  | Vilma Kern | 1 |  |  | FALSE |  |  | 2021-06-30 | Programming | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3634 | 3634 |  | FALSE | CNAS | Botanic Garden Geodesic Dome | Request is for an architect to draw a design for a replacement of current geodesic dome. Design can then be used as basis for fund-raising campaign to construct new dome. Dr. Holt, UCRBG Director, has been in discussions with Jacqueline Norman and Drew Hecht. Dome was constructed on site in 1980s, all wood, greatly deteriorated. Dome is unrepairable, unsafe, and closed to the public. Goal is to replace it with a structure as close to the original dome shape as possible but with modern functionality. We envision a structure with partial solid walls near the ground, then lath on upper walls and top, possibly cross shaped with doors at ends of the arms, and a domed center for taller plants. Should have “wood look” or at least maintain original sensibility since it is beloved as is, but needs a durable material! Function—house the collection of shade-requiring plants including prehistoric plants, subtropical plants, and others. Design should include space for plants inside around the edges and a wide walkway in a circle around a central display, suitable for tour groups, small gatherings, and photography. Arms extending in cross shape could house additional plants, displays, even sale plants. |  |  | Pre-Programming | Kathryn Uhrich | Jose Wudka | Jodie Holt |  | Fernando Nunez | 2 |  |  | FALSE |  |  | 2021-04-13 | Receive add'l info from Client | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3644 | 3644 |  | FALSE | LIBR | Rivera Library Fire Suppression Study | Request for estimate for installing fire suppression system in Rivera Library 4th floor and Secured area on Basement floor. |  |  | Programming | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Vilma Kern | 1 |  |  | FALSE |  |  | 2021-06-25 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3616 | 3616 |  | FALSE | CAP PROG | University Ave/Canyon Crest Dr Improvements | $100,000 in Violent Acts Mitigation and Prevention funding have been awarded to study short and long-term safety improvements at the intersection at University Avenue and Canyon Crest Drive. Subsequent activities will involve the construction of identified improvements. |  |  | Programming | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Uma R. | 16 |  |  | FALSE | 100000 |  | 2021-03-01 | Design | 2022-01-01 | 2022-02-01 | [10 empty] | PD&C | 0 | 2021 | 2021-08-16
3613 | 3613 |  | FALSE | CAP PROG | SOM Modular Trailer Relocation | This project will be to relocate the existing School of Medicine modular trailer (P5825) to the Corp Yard (specific location to be determined). This modular needs to be relocated due to the new School of Medicine Education Building II project being located on this site. |  |  | Programming | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Tameesha Hayes | 18 |  |  | FALSE |  |  | 2021-04-23 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3642 | 3642 |  | FALSE | CAP PROG | South District Planning Study | The “South District” presents a unique opportunity to create a strong identity for academic and research expansion across the campus loop road with an emphasis on creating a transformative and synergistic new campus neighborhood. Its hillside location makes it highly visible from the freeway and the Core Campus, presenting a significant opportunity to enhance campus identity. The site’s high elevation also gives it unobstructed views outward. A holistic and integrated planning framework for its development is important to ensure alignment with broad planning strategies and principles in place for the campus, as established in land planning per the DRAFT 2021 Long Range Master Plan and the more detailed physical planning vision from the 2016 Physical Master Plan Study for this “opportunity site”, and its immediate context. The upcoming effort to update the campus’ Physical Design Framework document will further analyze the unique opportunities afforded by the South District, and leverage the design of the School of Business Building to establish organizing principles for how the area could be optimally redeveloped to its highest potential. |  |  | Programming (Study) | Jacqueline Norman | Sharyl Murdock | Uma R. |  | Uma R. | 19 |  |  | FALSE | 51000 |  | 2021-06-10 | Complete Study | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3623 | 3623 |  | FALSE | CNAS | NRS Prop 68 Study - Boyd | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Fernando Nunez | 7 |  |  | FALSE |  |  | 2021-02-02 | Project Estimate | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3618 | 3618 |  | FALSE | CNAS | NRS Prop 68 Study-James Reserve | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Fernando Nunez | 8 |  |  | FALSE | 8380 |  | 2021-02-02 | Project Estimate | [12 empty] | PD&C | 0 | 2021 | 2021-08-16
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Programming (Study) | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 2020-09-17 | Negotiations with Consultant | [12 empty] | PD&C | 0 | 2020 | 2021-08-16
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Scott Donnell | 10 |  |  | FALSE | 65000 |  | 2019-03-04 | Complete Study | [12 empty] | PD&C | 0 | 2019 | 2021-08-16
3391 | 3391 |  | FALSE | CNAS | NRS Motte Rimrock Res Cost Study | Requesting recheck and recost of formal estimate for Motte Reserve Prop 84 for the Natural Reserve System. The former estimate was $763K. Purpose of study is to confirm, or augment the initial project valuation included with the Proposition 84 NRS grant application to install new structures at the Motte Rimrock Reserve site. |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Kimberly Hammond, D. McWilliams |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2017-11-02 | Prepare updated cost estimate | [12 empty] | PD&C | 0 | 2017 | 2021-08-16
99p000001 |  | 99p000001 | FALSE | ATHLETICS | Test | test |  | 1234 | PROJECT INTAKE | Tamica Smith Jones | Joe Erbland | Test |  | Enrico Baez |  | x |  | FALSE |  |  | 2021-08-16 | [13 empty] | FS | 0 | 2021 | 2021-08-16
22P000006 |  | 22P000006 | FALSE | CAMPUS | SL5 MRB 4210 - Install AC and Electrical Infrastructure | We have a project at MRB 4210 where we will be installing Air conditioning and electrical infrastructure to accommodate equipment that will be relocated from Batchelor Hall to MRB which is a result of the Batchelor Hall renovation. |  | 4210 | PROJECT INTAKE |  |  | SHARYL MURDOCK | GERRY BOMOTTI | Dan Lerman |  | 1 |  | FALSE |  |  | 2021-07-12 | Work on plans and apply for building permit | 2021-09-06 | 2021-10-29 |  |  |  | 8/2/21, DL: We are currently in the design phase and still trying to verify the logistics of the project. We are planning to apply for a building permit in the next 2- 3 weeks……… |  | Dan Lerman |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-08-16
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | [12 empty] | PD&C | 0 | 1900 | 2021-08-16
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 20 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2021 | [12 empty] | PD&C | 0 | 2017 | 2021-08-16
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 2020-03-30 | Projects to be assigned | [12 empty] | PD&C | 0 | 2020 | 2021-08-16
22P000027 |  | 22P000027 | FALSE | SOM | SL5 WEBBER HALL 1143 - PAINT/PATCH | PATCH & PAINT |  | 1143 | QUEUE TO START | Deborah Deas | Deborah Trujillo | CLARK HAPEMAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-06-16 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
22P000022 |  | 22P000022 | FALSE | CHASS | SL5 HUMANITIES A3414 - NAIL REMOVAL, PATCH, AND PAINT | PATCH & PAINT |  | 3414 | QUEUE TO START | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-07-29 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
22P000008 |  | 22P000008 | FALSE | VC-RED | SL5 MRB VARIOUS LAB SUPPORT - IACUC INSP TINTED WINDOWS NEEDED | ER IACUC INSPECTION- TINTED WINDOW NEEDED ON LAB SUPPORT ROOMS. ORIGINAL SERVICE REQUEST 22S000637 See list of rooms for window tint request. Korzus 1204E 1204F 1212A 1212B 1229B Zagha 1212A 1212B 1204F 1204E 1231C Abdulrazak 2204A 2204G 2204F 2208B Binder 3214 3218 3215 Cho 3216 3219 Tiwari- Woodruff 3204G Hickmott 2221 Zheng 2225 2213-C |  |  | QUEUE TO START | Rodolfo Torres | Laura Manor | TARA BARTHOL |  | Enrico Baez |  | R1 |  | TRUE |  |  | 2021-07-14 | [6 empty] | 07/27/21 EBZ: Project to begin 07/29/21. |  | Enrico Baez |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-08-16 |  | 1
21P000215 |  | 21P000215 | FALSE | SoB | SL5 ANDERSON 0202 - PATCH/PAINT NEW HIRE | PATCH & PAINT |  | 202 | QUEUE TO START | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-06-30 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000214 |  | 21P000214 | FALSE | BCOE | SL5 CHUNG HALL NEW FACULTY OFFICE 454 - PATCH & PAINT | PATCH & PAINT |  | 454 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-06-29 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000213 |  | 21P000213 | FALSE | BCOE | SL5 CHUNG HALL 0452 - PATCH AND PAINT NEW FACULTY | PATCH & PAINT |  | 452 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-06-29 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000212 |  | 21P000212 | FALSE | CNAS | SL5 LIFE SCIENCES 0418D - PAINT CEILING, DOOR, DOOR FRAME | PATCH & PAINT (RESEARCH RELATED) |  | 418D | QUEUE TO START | Kathryn Uhrich | Jose Wudka | DIERK BIGGS |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-06-29 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000211 |  | 21P000211 | FALSE | GRAD DIV | SL5 UNIV OFFICE BLD 0144 - PATCH & PAINT | PATCH & PAINT |  | 144 | QUEUE TO START | Shaun Bowler | Kennett Lai | CARLOS RIVAS |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-06-24 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000207 |  | 21P000207 | FALSE | BCOE | SL5 BOURNS HALL A325 OFFICE - PATCH & PAINT INCOMING FACULTY | PATCH & PAINT |  | A0325 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-06-18 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000204 |  | 21P000204 | FALSE | SOM | SL5 WEBBER HALL 1126A - PAINT/PATCH | PATCH & PAINT |  | 1126A | QUEUE TO START | Deborah Deas | Deborah Trujillo | CLARK HAPEMAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-06-16 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000198 |  | 21P000198 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 409 - PATCH & PAINT (NEW FACULTY) | PATCH & PAINT |  | 409 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-06-04 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000191 |  | 21P000191 | FALSE | SOM | SL5 ORBACH LIB BASEMENT - PAINT WALL AT NEW SIM CENTER | PATCH & PAINT |  | BASEMENT | QUEUE TO START | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-05-28 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000190 |  | 21P000190 | FALSE | CHASS | SL5 PSYCHOLOGY 3119 - PATCH & PAINT / REMOVE WALL FIXTURE | PATCH & PAINT / REMOVE WALL FIXTURE |  | 3119 | QUEUE TO START | Juliet McMullin | Cindy Williams | AERIKA LOYD |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-05-27 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000189 |  | 21P000189 | FALSE | BCOE | SL5 CHUNG HALL 0355 - WALLS NEED TO BE PATCHED AND PAINTED | PATCH & PAINT |  | 355 | QUEUE TO START | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-05-27 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000174 |  | 21P000174 | FALSE | BCOE | SL5 BOURNS HALL OFFICE B355 - PATCH & PAINT | PATCH & PAINT |  | B0355 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-05-05 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000173 |  | 21P000173 | FALSE | BCOE | SL5 BOURNS HALL OFFICE B353 - PATCH & PAINT (POSS TOUCH UP) | PATCH & PAINT |  | B0353 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-05-05 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000162 |  | 21P000162 | FALSE | CNAS | SL5 ENTOMOLOGY 0282 - PAINT NEW FACULTY MEMBER'S OFFICE | PAINT NEW FACULTY MEMBER'S OFFICE |  | 0282 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 2021-04-14 | [12 empty] | Winter 2021 | FS | 0 | 2021 | 2021-08-16
21P000157 |  | 21P000157 | FALSE | CNAS | SL5 PHYSICS 1119 - PATCH AND PAINT FOR NEW HIRE | PATCH & PAINT |  | 1119 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-04-06 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000155 |  | 21P000155 | FALSE | CNAS | SL5 OLMSTED 1342 - NEW FACULTY ARIVAL CARPET CLEAN / PATCH/PAINT | CARPET CLEAN / PATCH & PAINT |  | 1342 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | SOPHIA JURISCH |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-04-02 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000154 |  | 21P000154 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 455 - MINOR PATCH & PAINT TOUCH UP | PATCH & PAINT (NEW DEAN) |  | 455 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-04-02 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000151 |  | 21P000151 | FALSE | CNAS | SL5 SPIETH HALL 3310 - NEW FACULTY OFFICE - PATCH & PAINT | PATCH & PAINT |  | 3310 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-03-31 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000146 |  | 21P000146 | FALSE | BCOE | SL5 BOURNS A308 - OFFICE PATCH & PAINT | PATCH & PAINT |  | A0308 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-03-17 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000144 |  | 21P000144 | FALSE | SOM | SL5 WEBBER HALL 1116A - SHELVING REMOVED /PATCH & PAINT | SHELVING REMOVED /PATCH & PAINT |  | 1116A | QUEUE TO START | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-03-17 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000134 |  | 21P000134 | FALSE | CNAS | SL5 LIFE SCIENCES 2550 - CONF ROOM PATCH & PAINT | PATCH & PAINT |  | 2550 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-03-04 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-08-16
21P000088 |  | 21P000088 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BUILDING 100D - FILL HOLES/PAINT | PATCH & PAINT |  | 0100D | QUEUE TO START | Brian Haynes | Cathy Eckman | WILLIAM RALL |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-10-12 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
21P000058 |  | 21P000058 | FALSE | CHASS | SL5 HUMNITIES 3413 (DEAN SUITE) NAIL REMOVAL, PATCH, AND PAINT | PATCH & PAINT |  | 3413 | QUEUE TO START | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-08-25 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
21P000014 |  | 21P000014 | FALSE | BCOE | SL5 BOURNS HALL OFFICE A149 - PATCH & PAINT HOLES ON WEST WALL | PATCH & PAINT |  | A0149 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-07-14 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
21P000011 |  | 21P000011 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 414 - PATCH & PAINT | PATCH & PAINT |  | 414 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-07-13 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
20P000413 |  | 20P000413 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR ROOM A159A - EAST WALL PATCH & PAINT | PATCH & PAINT |  | A0159A | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-04-09 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
20P000401 |  | 20P000401 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 FS ANNEX B 5 & 6 - PAINT SUPERVISORS OFFICE | PATCH & PAINT |  |  | QUEUE TO START | Susan Marshburn | Da Lan Dinh | MARK JONES |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-03-13 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
20P000387 |  | 20P000387 | FALSE | CHASS | SL5 HMSS RM 3610 - PLEASE PATCH AND PAINT WALL | PATCH & PAINT |  | 3610 | QUEUE TO START | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-03-02 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
20P000384 |  | 20P000384 | FALSE | CHASS | SL5 CHASS INTS 3111A - PATCHING HOLES AND PAINTING THE WALLS | PATCH & PAINT |  | 3111A | QUEUE TO START | Juliet McMullin | Cindy Williams | LESLIE ANN GERRETSE |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-02-27 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
20P000374 |  | 20P000374 | FALSE | VC-STU AFF | SL5 HEALTH SERVICES 334 - OFFICES PAINTED AND CONFERENCE ROOM | PATCH & PAINT |  | 334 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-02-20 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
20P000372 |  | 20P000372 | FALSE | VC-STU AFF | SL5 HEALTH SERVICES 391 - OFFICES PAINTED AND CONFERENCE ROOM | PATCH & PAINT |  | 391 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-02-20 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT | PATCH & PAINT |  | 317 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-02-18 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES | PATCH & PAINT |  | 200 | QUEUE TO START | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-02-07 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
20P000321 |  | 20P000321 | FALSE | CHASS | SL5 UNIV THEATRE 400A - PAINT LOBBY | PATCH & PAINT |  | 0400A | QUEUE TO START | Juliet McMullin | Cindy Williams | ALBERT FETTER |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-01-15 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-08-16
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 150 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 2 |  | FALSE |  |  | 2020-01-14 | Order material once permit is approved | 2021-06-14 | 2021-10-01 |  |  |  | 08/02/21, DL: The plans and permit are approved. This is a large project and it will consume our electricans for at least 4- weeks. At the current time we are working on completing several other projects. Once we are caught up on the noted projects, we will schedule the work. Paul Richardson is currently aware of the plan noted above.....7/15/21, DL: The engineering is complete. We submitted the plans and applied for the building permit last week. Once the permit is approved, we will order material and schedule the work…….5/14/21, DL: We are still working on the contract to be approved for the electrical engineer before we can proceed…….4/15/21, DL: We had a meeting with the engineer this week and we should be applying for a permit within the next three weeks…….3/1/21, DL: We will reach out to the electrical engineer this week…….1/19/21, DL: This project will require engineered plans. This is a priority 2 project. We will start the plans and permit process when all priority #1 projects are complete. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-08-16
20P000282 |  | 20P000282 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 PIERCE HALL 3374 - RENOVATE GA CLASSROOM SUMMER 2020 | Project to renovate GA classroom in Pierce Hall for prioritization and execution in Summer 2020. |  | 3374 | QUEUE TO START | Susan Marshburn | Da Lan Dinh | DA LAN DINH |  | Paul Ditty |  | X |  | FALSE |  |  | 2020-01-09 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-08-16
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 2019-11-25 | [6 empty] | 05/06/21 O-ANS: Updated contact person info from Dr. Wudka and reaching out to coordinate. 5/05/21 O-ANS: Multiple failed attempts to contact requestor to schedule work. Project placed on HOLD and emailed CNAS partner to continue to hold or cancel. 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-08-16
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | MARLAN & ROSEMARY BOURNS HALL | B0328E | QUEUE TO START | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Enrico Baez |  | R1 | R1 | FALSE |  |  | 2019-11-05 | [6 empty] | 1/19/21, DL: Todd has the estimate. Sent follow up email to Todd requesting update or FAU number………………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | 0 | 2019 | 2021-08-16 |  | 1
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS BUILDING | 3009 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 2019-10-11 | [6 empty] | 05/05/21 O-ANS: Updated contact info from Dr. Wudka. 05/05/21 O-ANS: Multiple failed attempts to contact requestor to schedule work. Project placed on HOLD and emailed CNAS partner to continue to hold or cancel. 02/03/21 O-ANS: Reminder email sent to customer that PAINT ONLY portion would be completed and not the door removal at this time. Customer can resubmit request in next prioriization cycle…. 11/06/20 O-JLO: Emailed requestor and alternate regarding paint portion only, and that door/drywall removal will not occur during this time …. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. FS to confirm with customer that we can only complete the painting at this time but not the removal of the door…. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure." | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | 0 | 2019 | 2021-08-16
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | Re-bid | Gerry Bomotti | TBD | Sharyl Murdock |  | John Franklin | 15 |  |  | FALSE | 33099342.06 |  | 2015-12-15 | Award Contract | 2021-12-01 | 2024-07-01 | [10 empty] | PD&C | 0 | 2015 | 2021-08-16
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Blythe Wilson | 1 |  |  | FALSE | 3350000 |  | 2016-12-15 | Design Builder Prequalification | 2022-09-26 | 2024-06-19 | [10 empty] | PD&C | 0 | 2016 | 2021-08-16
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 17 |  |  | FALSE | 2586581 |  | 2018-11-06 | Complete Review | [12 empty] | PD&C | 0 | 2018 | 2021-08-16
20P000067 |  | 20P000067 | FALSE | BCOE | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM | BOURNS | B-Wing | TO BE PERFORMED BY PD&C | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2016-11-14 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Replace access controls at BCOE WCH & Bourns bldgs. |  | 2020-11-19 | Fall 2019 | FS | 0 | 2016 | 2021-08-16 | FY 20-21 | 1
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB. Patch Paint walls, replace flooring, refinish wood cabinets and sinks. | SPIETH | 2349 | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 5 |  | FALSE |  |  | 2019-02-20 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold……….12/11/19: O-ANS: Reassigned as project allotment - priority #5 for Winter 2020. 11/27/19 O-ANS: Placed on Hold for re-prioritization by client for Winter 2020. | 2020-02-27 | Enrico Baez | Patch and paint and extra work to upgrade an old lab that we are now inhabiting. In addition to painting, we need to have floors re-surfaced, cabinets re-stained, and counter tops re-surfaced, if possible. There is also a metal sink that could be polished. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-08-16 | FY 20-21
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | Modify the existing room in Soil House 1 (attached to the Delphino Lab at the Rubidoux Facilities) to expand CCPP quarantine services to include USDA/CDFA compliance for installation of new Economic Development Administration (EDA) citrus growth chambers. | DELFINO HHSE |  | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | Research and plan development | [5 empty] | 12/7/20, DL: This project will be managed by PD&C…..9/30/20, DL: Project is still on Hold until Furhther notice………...8/5/20, DL: WE will work on plans in the next 30- 45 days……………6/17/20, DL: This project is under review and is on hold until further notice………10/3/19 O-ANS: Plan Development per Minor Reno Meeting. 10/1/19,DL; We are getting ready to start the plans as we are currently conducting resarch on products that will meet the needs of the space……………..5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman |  | YES | 2020-12-07 | Summer 2018 | FS | 0 | 2018 | 2021-08-16 | FY 20-21
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | JEANETTE AND RUPERT COSTO HALL |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN O'BRIEN |  | Enrico Baez |  | R1 | R2 | FALSE |  |  | 2019-10-24 | [6 empty] | 2/25/2021 E. Baez Project will require several trades to complete. FS unable to support recharge project. Asked Brendan O'Brien to submit Project Request through CPMS for PD&C. …...02/16/21 O-ANS: Will require plans/permits and may need to go to PD&C due to scope of work which includes construction. Will confirm with client before instructing to submit request to CPMS…. 01/19/21, DL: Enrico B. Will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2021-02-25 | Winter 2021 | FS | 0 | 2019 | 2021-08-16 | FY 20-21 | 1
19P000659 |  | 19P000659 | FALSE | SOM | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43627 | [6 empty] | 08/05/20 O-ANS: Canceled by client (Cynthia Carolina) via email with Ron Veloz. 8/5/20, DL: Dan to follow -up with customer…………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "remove 330 from work order / update project details / Update: Furniture on order 3.30.2020 - delivery tbd" |  | Enrico Baez | TBD | NO | 2020-08-05 | Fall 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | COMPLETE | Christopher Lynch | Todd Ambriz | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43594 | Finish Gas cabinet installation | 43731 | 43868 |  |  |  | 8/5/20, DL: This Project is Complete…….3/25/20, DL: Project is 95% complete. We will install the fire sprinkler and exhaust duct to the gas cabinet when we return from the campus closure………..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Plans were approved and material is ordered. We are hopeful the material will arrive the 2nd or 3rd week in January. Once material is on site we will schedule the work…… 11/19/19 DH: Emailed Status Report to customer……10/16/19, DL: This project is 90% Complete. We are working on plans and permits for the two snorkels……….10/1/19, DL: This project is almost complete. We will be complete in the next 4- weeks except the Snorkel……….. 9/13/19, DL; The paint of the cabinets is scheduled for this week along with the power. We will submit the plans for the snorkel this with in the next two weeks…….9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Enrico Baez | SOW, Patch& Paint Walls, replace plexi glass on shelving, powder coat metal shelving & cabinets, clean & polish or replace chem sinks, polish counter tops, Validate all gas, water, drains, DI water & utilities. Replace damaged and dirty ceiling tiles, relamp as needed. Strip & wax floor. Dan L is requesting vendor pricing to restore finishes. | YES | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | COMPLETE | Kim Wilcox | TBD | ALEXIS RAMBAUD |  | Dan Lerman |  | 1 | 0 | FALSE |  |  | 43445 | schedule the work | 43486 | 43551 |  |  |  | 8/5/20, DL: This project is complete…………3/25/20,DL: Doors are scheduled to arrive the second week in April……2/19/20 O-DHN: Emailed Status Report to customer……2/18/20, DL: Work is complete except for Door and final deep cleaned I do have final stain samples from the vendor. I need to verify color……… We will complete the project when the doors arrive……….1/14/20, DL: Plans are approved, PO# is cut for the ordering of the custom doors, we are currently scheduled to start the work on or shortly after 1/21/20,. Karim understands that we will start and finish the project but we will not be able to install the door until the door arrives on site. There is a minimum of 6-8 week lead time on the door delivery………….12/16/19, DL: Plans are still in plan check review. I sent the building department an email asking for a startus update today…….10/16/19, DL; Plans were submitted to our building official this week for plan check review and a permit……9/16/19, DL; Guther will work on plans in the next three weeks. Once plans are complete, we will proceed with the permit process… | 2018-12-20 | Enrico Baez | SOW: Wall: Construct a metal stud framed wall with drywall up to hard ceiling (ceiling has 12x12 glue up ceiling tiles). Hardware: Install new lockset & keys are required.***** French Door: Install new stain grade birch door with full lite. Door and finish to match the existing office doors.***** Hard Ceiling: * Ceiling is 8’-0” A.F.F. + - with 12x12 glue up ceiling tiles. Work may require a new access panel if access to space above is needed. The 12x12 glue up ceiling tiles may need to be removed where the new wall is constructed.***** Flooring: The existing flooring will remain. Install rubber base to match existing.***** Painting, Taping & Sanding: Taping sanding and painting is required at the new wall and connecting walls.***** HVAC: May require modifications to split the existing supply air to accommodate the open office space.***** Electrical: Provide light switch at new office, power(new or relocate); add and or relocate electrical and voice/data outlets required for a standard office.***** Lighting: Provide a new light switch/circuit near office entrance. The existing 2x4 fixture is on main lighting circuit and will require lighting circuit modifications. Verify if the existing lighting is sufficient for the proposed office. Field verify if additional lighting is required.***** Fire Alarm: Provide a new Smoke/chime detector at new office area, confirm requirements. | YES | 2020-08-05 | SPRING 2019 | FS | 0 | 2018 | 2021-09-01 | FY 20-21
20P000213 |  | 20P000213 | FALSE | CHASS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS |  | CHASS INT S | 2117A, 2117C, 2117D, 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43777 | approved permit | 43893 | 43911 |  |  |  | 8/5/20, DL: This Project is Complete……………..2819/20 O-DHN: Emailed Status Report to customer…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have a contract, we will order the material and schedule the work………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Plans are complete and submitted for building permit. We are also working on the contract. Once the plans are approved and the contract is complete, we will schedule the work………. |  | Enrico Baez |  |  | 2020-08-05 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | COMPLETE | Kathryn Uhrich | Jose Wudka | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 43332 | Work will be complete in 2 weeks | 43864 | 43903 |  |  |  | 8/5/20, DL: This project is complete……………..06/17/20, DL: This project should be complete with in the next two weeks……..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within two weeks. Once we have a contract, we will schedule the work……….1/15/20 O-DH: Emailed Status Report to customer……1/14/20, DL: Contracts is currently working on the contract. Once the contract is complete, we will order the material and schedule the work…………11/26/19, DL: Plans were approved. We will work on the construction contract. Once we have the notice to proceed, we will schedule the work……….10/15/19, DL: Sent PD&C and follow-up email on 11/11/19. We should have approved plans in the near future……10/30/19, DL: Sent PD&C an email asking for a status update on 10.30.19…… 10/16/19, DL; Plans are still in plan check. I sent the building official an email asking if any additional information is needed. This work will be completed by a contractor which means we need to allow time for the bid and contract process……… …………9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Enrico Baez | Request for Estimate to install three new FOB readers with electrified locksets. Work covered: Install one AC Fob Reader at door 2221 and one AC Fob reader at each Door 4231 & 4235. Connect card readers to the existing Hirsh ACP located in the IDF closet at each floor. 03/07/19: Scope revised to eliminate two FOB readers. Install one FOB reader at Genomics door 4231 only instead of all three rooms. | YES | 2020-08-05 | Fall 2018 | FS | 0 | 2018 | 2021-09-01 | FY 20-21
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | R3 |  | TRUE |  |  | 43550 | Schedule the work | 43861 | 43882 |  |  |  | 8/5/20, DL: This Project is COMPLETE…….3/25/20, DL: The material is here and we are 95% complete with the work. We will complete the work when we return from the campus closure…………1/31/20 O-DHN: Emailed Status Report to customer…….1/30/20,DL: The pump is now on site but we are still waiting for the fittings. In the mean time, our plumber is putting everything together and is working on the installation. Once the fittings arrive, we will make the connections and the system should be good to go………….1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: The pump is scheduled to arrive on or before 1/31/20. We will schedule the work once we have the pump and material on site…..11/26/19, DL; Emailed Natalie and Sherice the quote for the vacuum pump. We will order the material and schedule the work once we have approval and the pump on site……11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: I sent the vendor a 2nd email requesting an update on the proposal. I also included Natalie on the email so she is aware of where we stand with the proposal……10/30/19, DL: We had a followup meeting with the vendor last week. The vendor is now working on a pump that will best meet our needs……….10/16/19, DL; We are working with a vendor on a quote for a new lab vacuum pump. We are hoping to have a quote in the next week or two…..9/16/19, DL; Estimate was provided to customer last week. If the project is approved, we will work on the plans and permits. Once approved, we will schedule the work…… |  | Enrico Baez | Old SOW Revised SOWInstall exhaust hood, electical receptacle, vacuum pump, vac lines and valves (six valves total) and hood location. | YES | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43487 | finish plans/submit application | 43840 | 43917 |  |  |  | 8/5/20, DL: This Project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer…..2/18/20, DL: We are making great progress and still on schedule to be complete before Spring Break begins. We pass drywall inspection on 2/18/20………..1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: Plans are approved. All items have been removed from the space. Abatement is schedule to take place within two weeks…..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were submitted for plan check review. Fire marshal stamped the plans, we are waiting on the final stamp from our building official. Once plans are approved we will order material and schedule the work……..10/30/19, DL: Gunter is working on plans. We are planning to complete the work before Spring Quarter begins. |  | Dan Lerman |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | C&C CARPORT | 161 | COMPLETE | Danna Gianforte | Shelley Gupta | SHELLEY GUPTA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43472 | Waiting for bid for customer. | 43850 | 43921 |  |  |  | 8/5/20, DL: This Project is complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have the contract, we will schedule the work……………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Project was approved by Shelley. We will work on the contract. Once we have the notice to proceed from contracts, we will order the material and schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Sent Shelley another follow-up email today and she has not verified if she would like to move forward with the project………10/30/19, DL: Sent Shelley the updated quote last week and she has not responded. I sent Shelley a followup email today asking her to let me know if she would like to proceed with the work……..10/16/19, DL; Had a meeting with Shelley, we modified the scope of work and software for the project. We are now revising the quote with our vendor. We should have an updated quote within the next two weeks. If Shelley approves the work and scope, we will proceed….10/1/19, DL; I have a meeting with Shelley this afternoon to review proposal. If she approves the project we will submit plans for a building permit……8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was cancelled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; We have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28/19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
19P000414 |  | 19P000414 | FALSE | PB&A | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | Seth Morrison |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43451 | pending material delivery | 43754 | 43796 |  |  |  | 8/5/20, DL: This Project is Complete………….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: We have the motor on site, we are working on the permit for the crane. Once we have the crane lift permit, we will schedule the install…………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: We are working on the new motor platform. It is our goal to install the new motor in late January. Once the motor is installed, we will be able to identify if additional work is needed…….11/19/19 DH: Emailed Status Report to customer…..11/15/19, DL: Material has not arrived……..10/30/19, DL: The new exhaust fan is ordered with a 2- 4 lead time. Once the exhaust fan arrives, we will schedule the install……….10/16/19, DL; We are in the process of the work. At this current time, we are not modifying the building to where permits may not be required…….10/1/19, DL; This is in the queue for plans, we will start the plans in the next 3-4 weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2018 | 2021-09-01 | FY 20-21
19P000687 |  | 19P000687 | FALSE | PB&A | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | COMPLETE | Gerry Bomotti | TBD | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 43642 | plan check review | [5 empty] | 8/5/20, DL This Project is Complete……………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Contracts is processing the contract. Once the contract is complete, we will schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Plans were approved. I sent Brendan an email 11/11/19 requesting an FAU # as this is Recharge work. Once we have the FAU #, we will work on the contract agreement with the contractor………10/30/19, DL; Sent Lezlie and email asking if she has an update on the resubmitted plans on 10/30/19………..10/16/19, DL; The plans were resubmitted for plan check review this week. We are hopeful the plans will be approved this week. Once approved we will work on contract and scheduling the work…10/7/19 LB: This is a test. The timestamp will be reset when the test is done. 10/1/19, DL: We are working on plan check review. We should have approved plans in the next two weeks…..8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | Provide estimate to install key card access control |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
20P000135 |  | 20P000135 | FALSE | BCOE | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MS&E Rm 0075 - 3 Ph208 Power CHW S&R WATER PPMS TOOL, Install Chilled water loop & power in clean room 075. | MAT SCI ENGR | 75 | COMPLETE | Christopher Lynch | Todd Ambriz | MARK HEIDEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43727 | Plans and permit | [5 empty] | 9/30/20, DL: This project is complete……..8/5/20, DL: This is in progress…….3/25/20, DL: We will work on plans and permits when we return back from the campus closure……. | 2020-02-18 | Enrico Baez | Intake/SOW: Install 208V 3ph power & disconnect/safety switch and one 3/4" Chilled water loop (Supply and Return) in the MSE southeast corner of clean room 0075. Create a 4" diameter pass-thru hole from this corner of room 0075 into the adjacent room 0071. FS to provide power and cooling to a compressor which will connect through the wall to the PPMS system with cryogenic helium lines. | YES | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000214 |  | 20P000214 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | Remove walls and doors in spaces 2139 A,B and C. | PSYCHOLOGY1 | 2nd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43776 | Obtain building permit | [5 empty] | 9/30/20, DL: This Project is Complete…………8/5/20, DL: we will submiot plans this week.…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Plans were submitted for a permit on 2/12/20. Once plans are approved, we will order the material and schedule the work……… | 2020-01-10 | Enrico Baez | **************************************SCOPE********************************** 1.) Remove doors, and jambs 2139A, 2139B, 2139C. 2.) Remove drop ceiling in 2139A, 2139B, 2139C and repair as needed. 3.) Remove cabinets in 2139A, 2139B, 2139C. 4.) Remove walls between 2139A & B, and remove walls between 2139B & C. 5.) Change light fixture to match existing. 6.) Repair walls as needed. 7.) Patch and paint as needed. 8.) Replace carpet and base in 2139A, 2139B, 2139C and 2139 common area. 9.) HVAC duct work in individual spaces can be removed and simplified. | YES | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000202 |  | 20P000202 | FALSE | CNAS | SL5 SKYE HALL 361 RENOVATION PROJECT | Renovete space for class room. | SKYE HALL | 361 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY | MELISSA GOMEX | Dan Lerman |  | 1 |  | FALSE |  |  | 43768 | pending permit approval | 43866 | 43917 |  |  |  | 9/30/20, DL: This Project is Complete……….8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Permits were approved. Demolition is complete…..1/15/20 O-DHN: Emailed Status Report to customer……..1/14/20, DL: Plans have been submitted for a building permit. Once plans are approved, it is our goal to complete the work by the beginning of spring quarter….. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
19P000660 |  | 19P000660 | FALSE | SOM | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SL5 SOME RB, RM 330- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43627 | [6 empty] | 9/30/20, DL: This Project is Complete………..8/5/20, DL: Dan to follow-up with customer…………..03/05/20 O-ANS: Removed room 330 per client request. Only updates to 107 & 111. |  | Enrico Baez | TBD | NO | 2020-09-30 | Fall 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000054 |  | 20P000054 | FALSE | SOM | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOMED-SOME G0600, G0621 & 1682B- ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43677 | [6 empty] | 9/30/20, DL: This Project is Complete…………..8/5/20, DL, Dan to follow-up with customer………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "Remove status Hold / Update project detail to include information on 1682B -ADD ELECTRICAL, PAINT/PATCH, AND RELOCATE WHITE BOARD." |  | Enrico Baez | Room G0600 Install Power behind and below the TV, install one TV Bracket, install one cut-in back box below the TV for data(data cabling by ITS), Paint the entire East wall to match existing. Room G0621 Insatll three(3) new double duplex receptacles and three(3) data back boxes only(no data cabling) in room G0621. Install SS tubing for Co2 from room G0621 to room G0623. Include Valves at both ends of P.O.C., Install one uni-strut siesmic cylinder support at the south wall. Steve Burleson has walked the site and has knowledge of the SOW. Loading Dock Install Pole & chains at Loading dock. |  | 2020-09-30 | Fall 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000449 |  | 20P000449 | FALSE | BCOE | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | Paint Only - Chung Hall, Fourth Floor, Room 461 Patch & Paint: At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. Follow up with fresh paint. Thank you. | CHUNG HALL | 461 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43993 | [6 empty] | 01/19/21 O-ANS: Complete per technician updates and closed project. Completed by Wendy M. 11/09 -SC |  | Paul Ditty |  |  | 2020-11-09 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000210 |  | 20P000210 | FALSE | BCOE | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | Reduce noise. Replace doors with solid core doors and install an Acoustic Door Seal Kit. | CHUNG HALL | 224 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43774 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……. | 2020-02-11 | Enrico Baez | Removal of the existing double doors and door hardware, install new solid core double doors with continuous hinges, install new acoustical jamb seals, threshold seal and a surface mounted Automatic Door Bottom utilizing a flat spring mechanism, which activates when closing the door, lowering a neoprene seal insert against the floor or threshold to create a sound seal. Install acoustic double door astragals with seal. Reinstall all existing door locksets, and door closers. Quote received from Brad Aduddell-American Door to perform this work. Quote & Specs are available in the project folder. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
19P000624 |  | 19P000624 | FALSE | BCOE | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | Refurbish Room-Student Space, | BOURNS | A0346 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43600 | Pending information from Susanna | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Susanna is working on a cubicle layout. Once we have the information from her. We will schedule the work………… | 2019-11-07 | Enrico Baez | Remove all lower cabinets in room A0346 and all lower cabinets and mail boxes in Rm A0304 | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000039 |  | 20P000039 | FALSE | BCOE | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE |  | BOURNS | A0318 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43598 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……..09/19/19 O-ANS: HOLD FOR WINTER 2020 PER CUSTOMER (LOUIS SANDOVAL) REQUEST. EMAILED PAUL DITTY TO CONFIRM. PAUL STATED THIS IS NON-PAINT PROJECT B/C SCOPE OF WORK INCLUDES CARPENTERS AND ELECTRIC SHOPS. |  | Paul Ditty |  |  | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
19P000427 |  | 19P000427 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | Install Power and TV bracket, move white board | CHUNG HALL | 453 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43468 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold……… | 2019-09-18 | Enrico Baez | Install Power and TV bracket, remove white board and relocate , patch and paint wall prior to installing | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
19P000502 |  | 19P000502 | FALSE | BCOE | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | Install Electrical power & TV bracket.for a 75" TV to mount in CS 342. | CHUNG HALL | 444 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | RICHARD BAIN |  | Dan Lerman |  | R3 |  | FALSE |  |  | 43515 | Schedule the work. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This project is on hold……………3/25/20, DL: Work orders are produced. I will work on scheduling the work when we return back to work…….. | 2019-09-17 | Enrico Baez | Install Electrical power & TV bracket. Excludes network/data back box and stub up to ceiling. | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
20P000183 |  | 20P000183 | FALSE | CHASS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | Install side walk | HUM & SOC SC | 1202 | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43756 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Also Existing door is compliant and there are other accessible exits to the building… 8/5/20, DL: This Project is on hold until further notice……. | 2019-11-13 | Enrico Baez | Construct Side walk. ADA compliance not required. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  | R7 |  | FALSE |  |  | 43523 | We Need an FAU # | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced. We will schedule the work when we return from campus closure………11/11/19, DL: Project is in the queue to start but we do not have an FAU# as this is a recharge project. I sent Enrico and James an email requesting the FAU#. Once we have an FAU #, I will work on scheudling the work…..10/1/19, DL; Enrico is wtill working on estimate. | 2018-10-19 | Enrico Baez | E. Baez 1. Provide power in ceiling for projector. 2. Install projector center in room between two 4ft light fixtures. 3. Install 2 duplex outlets in 4S box on South West corner of room 4. Remove existing screen. 5. Install new screen centered on South wall. Extend power from existing screen to new screen location. 6. Use existing screen power switch to control new screen. | YES | 2020-11-19 | Summer 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
20P000188 |  | 20P000188 | FALSE | LIBR | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 |  | ORBACH LIB | 204 | CANCELED BY FS | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43761 | Obtain floor covering samples | [5 empty] | 11/19/20 O-ANS: Declined to move forward by FS Admin but may revisit in future prioritization period. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: We are working on floor covering samples that will work for the space. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000197 |  | 20P000197 | FALSE | VC-RED | SL5 UOB 210 - SOUND PROOF INSTALLATION |  | UNIV OFC BLD | 210 | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43762 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000047 |  | 20P000047 | FALSE | VC-RED | SL5 ADVANCED NEUROIMAGING | NEEDING TO TAKE DOWN OVERHEAD CABINETRY AND REPLACE WITH SOME KIND OF SHELVING TO OPTIMIZE SPACE. LOOKING FOR AN ESTIMATE AND A PLAN. | ADV NEURO |  | CANCELED BY FS | Rodolfo Torres | Laura Manor | CHELSEA EVELYN |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43677 | pending material delivery. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice…….3/23/20, DL: Shelves are ordered. We will schedule the work when we return from the campus closure……….1/15/20 O-DHN: Emailed Status Report to customer…...1/14/20, DL: We waiting for a revised quote from the vendor as there quote was not complete. We will process the quote for a PO# when we receive the correct quote……. 11/11/19, DL: Need to review scope with Ron as the shelving system is a special order item with a 3- month lead time….. | 2019-09-24 | Enrico Baez | Remove 5'-0" x3'-0" upper cabinet, and soffits. Patch and paint walls to match the existing grey . Install customer furnished adjustable shelf. | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43340 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice. | 2018-09-27 | Enrico Baez |  | YES | 2020-11-19 | Fall 2018 | FS | 0 | 2018 | 2021-09-01 | FY 20-21
20P000230 |  | 20P000230 | FALSE | VC-RED | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | Install Ceilings, Widen Door & Extend Utilities | BOURNS | B116C & B116D | COMPLETE | Rodolfo Torres | Laura Manor | KRASSIMIR BOZHILOV | LAURA MANOR | Dan Lerman |  | 1 |  | FALSE |  |  | 43787 | finish plans for building permit | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: This project is in progress and 50% complete. We should be complete with in the next 4-6 weeks…………...8/5/20, DL: We will submit plans in the next week………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We will start working on the plans and apply for a building permit in the next 2-3 weeks. | 2020-01-23 | Enrico Baez | Install new T-bar ceilings, lighting/switches, verify electrical service/disconnect. Relocate the existing eye washer, widen the exiting door opening and *reverse swing(*if approved by F.M). Install one customer furnished transformer. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000067 |  | 20P000067 | FALSE | BCOE | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM | BOURNS | B-Wing | TO BE PERFORMED BY PD&C | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | R1 |  | FALSE |  |  | 42688 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Replace access controls at BCOE WCH & Bourns bldgs. |  | 2020-11-19 | Fall 2019 | FS | 0 | 2016 | 2021-09-01 | FY 20-21 | 1
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB. Patch Paint walls, replace flooring, refinish wood cabinets and sinks. | SPIETH | 2349 | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43516 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold……….12/11/19: O-ANS: Reassigned as project allotment - priority #5 for Winter 2020. 11/27/19 O-ANS: Placed on Hold for re-prioritization by client for Winter 2020. | 2020-02-27 | Enrico Baez | Patch and paint and extra work to upgrade an old lab that we are now inhabiting. In addition to painting, we need to have floors re-surfaced, cabinets re-stained, and counter tops re-surfaced, if possible. There is also a metal sink that could be polished. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
21P000037 |  | 21P000037 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | Paint Only | CHUNG HALL | 427 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44043 | [6 empty] | 01/19/21 O-ANS: Paint complete per technician and closed project. 11/30/20 B-SBT: repatch & Paint north wall |  | Paul Ditty |  |  | 2020-11-30 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | Modify the existing room in Soil House 1 (attached to the Delphino Lab at the Rubidoux Facilities) to expand CCPP quarantine services to include USDA/CDFA compliance for installation of new Economic Development Administration (EDA) citrus growth chambers. | DELFINO HHSE |  | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 43245 | Research and plan development | [5 empty] | 12/7/20, DL: This project will be managed by PD&C…..9/30/20, DL: Project is still on Hold until Furhther notice………...8/5/20, DL: WE will work on plans in the next 30- 45 days……………6/17/20, DL: This project is under review and is on hold until further notice………10/3/19 O-ANS: Plan Development per Minor Reno Meeting. 10/1/19,DL; We are getting ready to start the plans as we are currently conducting resarch on products that will meet the needs of the space……………..5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman |  | YES | 2020-12-07 | Summer 2018 | FS | 0 | 2018 | 2021-09-01 | FY 20-21
21P000102 |  | 21P000102 | FALSE | VC-RED | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | AAALAC Certification updates to rooms 348, 352 & 363 | SPIETH | 348, 352 & 363 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS | YURIDIA REYNOSO | Paul Ditty |  | TBD |  | FALSE |  |  | 44133 | [6 empty] | 12/08/20 O-ANS: Customer Dierk Biggs confirmed via email that these room updates are complete. |  | Paul Ditty |  |  | 2020-12-08 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000309 |  | 20P000309 | FALSE | VC-UNIV ADV | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES |  | 1955 CHICAGO | 200 | CANCELED BY FS | Peter Hayashida | Naysia Caldwell | SARAH KARSON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43840 | [6 empty] | 12/16/20 O-ANS: Canceled by FS - Project location not serviced as FS CORE location and reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Please retain project # as reference. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2020-12-16 | Spring 2020 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000211 |  | 20P000211 | FALSE | CHASS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | Install keyless entry system for door to Arts Building RM 54 | ARTS | 54 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 | R3 | FALSE |  |  | 43776 | [6 empty] | 1/19/21, DL: Enrico will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment installation. 8/5/20, DL: This Project is on hold until further notice……. | 2020-01-20 | Enrico Baez | 1/19/21, EB: Per Paul R., This project is canceled………….Provide new panel, power supply and door hardware for 2 doors. Prox reader only. | YES | 2021-01-19 | Winter 2021 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
20P000221 |  | 20P000221 | FALSE | BCOE | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | COMPLETE | Christopher Lynch | Todd Ambriz | HONG XU | KEVIN FREEDMAN | Dan Lerman |  | 3 |  | FALSE |  |  | 43784 | [6 empty] | 1/19/21, DL: This project is 100% Complete……..9/30/20, DL: We are in the process of finishing up a few other projects. Once they are complete, we will schedule the work….8/5/20, DL: Plans are approved and we will start the work in the next 2-6 weeks…….. | 2020-02-25 | Enrico Baez | Install Plywood and supports. Paint Plywood black. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000215 |  | 20P000215 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | Remove Vaughan wall seperating Olmsted 3349/3351.Add 4 single gang outlets and 2, 2gang outlets. | PSYCHOLOGY1 | 3rd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43776 | [6 empty] | 1/19/21, DL: This project is 100% complete…………9/30/20, DL: Plans were approved, we had the Vaughn Wall tested for Asbestos containing material. Once we have the results, we will schedule the work………….8/5/20, DL: We will submit plans by this Friday for a building permit | 2020-02-24 | Enrico Baez | 2/24/2020 E. Baez - 1.Remove Vaughan wall and electrical circuit in wall. 2. Add 4 Single Gan outlets and 2, 2gang outlets. 3. Patch vinyl plank flooring from removed wall and safe. 4. Remove panel in 2249 with wall paper on it next to window. 5. Remove handle set to 3351, install blank, render door inoperable. 6. Repair T-Bar ceiling as needed. 7. Patch and paint walls. 8. Coordinate with ITS for data line for 8 computers. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000247 |  | 20P000247 | FALSE | CNAS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | Refresh Lab: Patch paint, strip & clean floor, repair broken ceiling and floor (VCT) tiles at room 2110 & 2118. Install Electrical power & Co2 cylinder racks at each end of workbench/tables | SPIETH | 2110 + 2118 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | Dan Lerman |  | 6 |  | TRUE |  |  | 43796 | [6 empty] | 1/19/21, DL: This project is complete…………..9/30/20, DL: This project is in progress and will be compete in the next 6- 8 weeks……………8/5/20, DL: We will start on this project in the next 6-8 weeks….. | 2020-04-17 | Enrico Baez | Spieth 2110: Carpentry: Seismic anchoring for “New” tables and equipment. Replace damaged ceiling tiles. Install misc. wall mounted items. Sheet Metal: Remove “existing” steel cage. Fabricate & install metal cylinder rack w/ restrains/seismic anchoring to floor. Plumbing: Install Co2 POC for gas cylinders at four (4ea) new free-standing work benches (see configuration on this document). Electrical: Install dedicated *120v power drop & connect to the existing power strips built-in the four (4ea) new workstation tables (see configuration on this document). *VERIFY/CONFIRM VOLTAGE W/ D. MCW. Relamp fixtures as needed. Spieth 2118 & 2110: Sheetmetal: Clean and or replace air distribution grilles. Flooring: Repair/patch broken floor tile and Replace broken ceiling tiles (abate floor tiles if required). Painting: Paint and patch all walls, verify recondition doors @ room side. Plumbing: Assess sinks to be fully operational & clean. *Replace sink in Rm 2118 for glassware, confirm with Faculty/Estella. Replace sink in room 2118 (Sink type TBD by Faculty). HVAC: Check lab air pressure is operational & proper pressure. Custodial: Strip and Wax floor, clean interior windows, wipe down doors and windowsills. EXCLUSIONS: Furnish, assemble, and install new workstations, tables or lab equipment. Removal of existing lab furniture or equipment. Natural gas or air output taps not required (per Faculty). | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GH08 | 881 | COMPLETE | Kathryn Uhrich | Jose Wudka | NANCY FERGUSON |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43494 | Schedule the work. | [5 empty] | 1/19/21, DL: This project is complete……………8/5/20, DL: This project is in Progress and should be complete in the next 8-12 weeks…………….3/25/20, DL: Work orders are produced. Once we are back to work, we will schedule the work………12/11/19 O-ANS: Re-assigned as project allotment - priority #7 for Winter 2020. 11/27/19 O-ANS: Hold by client for re-prioritization for Winter 2020. | 2020-03-04 | Enrico Baez | Install new 3 ton Packaged unit with heat pump and dedicated electrical service on the roof top. Provide 1ea return plenum, 2ea supply drops in the work space. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
19P000517 |  | 19P000517 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | COMPLETE | LaRae Lundgren | Emily Engelschall, Sean Cason | DANIELLE GARCIA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43531 | Verify scope and schedule work | 43801 | 44185 |  |  |  | 1/19/21, DL: This project is complete…………..8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced, We will schedule the work when we return from the campus closure…………11/11/19, DL: I will work on scheduling this project… | 2019-06-17 | Enrico Baez | 6/17/19 E. Baez Conducted site visit with Sean. Will need carpenters to mount TV and electricians to add outlet to North wall. Data not needed. Might need painters depending on how carpenters install TV mount. | YES | 2021-01-19 | FALL 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000026 |  | 20P000026 | FALSE | VC-RED | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | Install T-bar ceiling, Provide HVAC and Fire sprinklers drops. Install new 2x4 LED light fixtures | LIFE SCIENCE | Basement Level | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43665 | Work on Plans and permits. | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: The plans were submitted two weeks ago. We should receive the plan check review comments in the near future…………….8/5/20, DL: This Project will exceed $50,000. Monty A. will inform customer this is a project that will need to be managerd through PD&C……………3/25/20, DL: We will work on plans when we return back from the campus closure. | 2020-01-31 | Enrico Baez | Install T-bar ceiling with wipable(coated) ceiling tile. Provide HVAC and new Fire sprinklers drops to new ceiling. Install new 2x4 LED light fixtures. Verify Fire alarm systems work. | YES | 2021-01-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
18P000214 |  | 18P000214 | FALSE | VC-STU AFF | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Install Card readers | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  | 2 | 2 | FALSE |  |  | 43077 | Pending special order part | 43515 | 44075 |  |  |  | 1/19/21, DL: This project is 100% Complete…….9/30/20, DL: Vendor should have the balance of the material in the next 30- days…….8/5/20, DL: This project is complete except the card reader portion of the project…………6/17/20, DL: The floor covering was completed two weeks ago. The card reader portion of this project is 95% complete but additional parts were needed and they are on order. Once they arrive, we will schedule the installation and this project will be 100% Complete………1/15/20 Emailed Status Report to customer…..1/14/20, DL: We were recently approved to proceed with the work. I have reached out to the vendor for the doors and card access. We are still waiting to hear back from them so we can order the material and schedule the work. I communicated with Nicole on the floor covering replacement. Nicole needs to verify what areas we will replace as we were going to complete several offices and a hallway as part of the scope but this will displace many team members for at least a week. We will work on scheduling the work once Nicole gets back to me……..12/17/19 - O-DHN: Emailed Status Report to Customer……12/19/19, DL; We are working with our contractor to order the material and schedule the work. Once we have confirmation on the material, we will be able to schedule the work. It Is our goal to start this project in late January……11/26/19, DL: This project was taken off of on hold and we can now proceed. I contacted the contractor last week and I am awaiting their response on when they can schedule the work. I also left a message with them this morning………..7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once material arrives, we will schedule the installation.….5/31/19, DL; Contract is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is completed except the floor covering and electronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being prepped for paint. We have a pre-construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, material is ordered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct site visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez |  | YES | 2021-01-19 | Winter 2018 | FS | 0 | 2017 | 2021-09-01 | FY 20-21
20P000208 |  | 20P000208 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | Men's locker room refresh | ATH DANCE | 50 | COMPLETE | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND | EUGENE HUTCHINSON | Dan Lerman |  | 1 |  | FALSE |  |  | 43773 | [6 empty] | 1/28/21, DL: Project is complete. Paul will schedule the paint once he is back on projects……….1/19/21, DL: We will schedule the balance of the paint before the students return back to campus………..9/30/20, DL: The work is complete except for the paint……………..8/5/20, DL: The work is almost complete.……. |  | Dan Lerman |  |  | 2021-01-28 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000310 |  | 20P000310 | FALSE | BCOE | SL5 BOURNS A-WING A129 - PATCH & PAINT | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. | MARLAN & ROSEMARY BOURNS HALL | A0129 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43840 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty. 2/3/2021 B-SBT Patch holes, mask room, sand patches, prime room. 2/4/2021 B-SBT paint room, pull masking, clean room. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2021-02-04 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000403 |  | 20P000403 | FALSE | CHASS | SL5 OLMSTED 232 - PAINT OFFICE | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). | JOHN W. OLMSTED HALL | 2321 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | MELISA VICARIO | Paul Ditty |  | X |  | TRUE |  |  | 43903 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/11/21. 02/11/21 D-JPO: finished sanding water damage spot primed painted room 2 coats pulled tape vacuumed complete. |  | Paul Ditty |  |  | 2021-02-11 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000469 |  | 20P000469 | FALSE | CHASS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 222 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | SUSAN KOMURA | PAUL DITTY |  | X |  | TRUE |  |  | 44005 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/12/21. |  | Paul Ditty |  |  | 2021-02-12 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000446 |  | 20P000446 | FALSE | CHASS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. | CHASS INTERDISCIPLINARY NORTH | 4047 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 43986 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/12/21. |  | Paul Ditty |  |  | 2021-02-12 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000463 |  | 20P000463 | FALSE | CHASS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 | HUMANITIES BUILDING | 2000 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/11/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUMANITIES BUILDING | 3210 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44006 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/10/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000464 |  | 20P000464 | FALSE | CHASS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) | HUMANITIES BUILDING | 3001 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/09/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000363 |  | 20P000363 | FALSE | BCOE | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | Paint Only | WINSTON CHUNG HALL | 433 | COMPLETE | Christopher Lynch | Todd Ambriz | MANGLAI ZHOU | FARIBORZ KARGAR | PAUL DITTY |  | X |  | TRUE |  |  | 43874 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/22/21. 2/22/2021 B-SBT pull tape, install plates, clean base/room. 2/19/2021 B-SBT prime and paint room. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2021-02-22 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000467 |  | 20P000467 | FALSE | SOM | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. | HERBERT JOHN WEBBER HALL | 1247 | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | PAUL DITTY |  | X |  | TRUE |  |  | 44001 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/22/21. 2/22/21 D-JPO CLEANED UP DONE. 02/17/21 D-JPO: primed room and door. 02/16/21 D-JPO: finished prep. |  | Paul Ditty |  |  | 2021-02-22 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | JEANETTE AND RUPERT COSTO HALL |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN O'BRIEN |  | Enrico Baez |  | R1 | R2 | FALSE |  |  | 43762 | [6 empty] | 2/25/2021 E. Baez Project will require several trades to complete. FS unable to support recharge project. Asked Brendan O'Brien to submit Project Request through CPMS for PD&C. …...02/16/21 O-ANS: Will require plans/permits and may need to go to PD&C due to scope of work which includes construction. Will confirm with client before instructing to submit request to CPMS…. 01/19/21, DL: Enrico B. Will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2021-02-25 | Winter 2021 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
20P000419 |  | 20P000419 | FALSE | CNAS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | Paint Only | HERMAN T. SPIETH HALL | 2312 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | PAUL DITTY |  | X |  | TRUE |  |  | 43943 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 3/18/21. 03/18/21 D-JPO: cleaned room patched masked sanded and primed all walls |  | Paul Ditty |  |  | 2021-03-18 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000462 |  | 20P000462 | FALSE | CHASS | SL5 HMSS 2001 - PAINT OFFICE / CLEAN FLOOR NEW FACULTY HIRE | Patch/paint to existing color for faculty new hire | HUMANITIES BUILDING | 2001 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | Paul Ditty |  | X |  | TRUE |  |  | 44000 | [6 empty] | 03/19/21 O-ANS: Project complete per Paul Ditty. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  | 2021-03-19 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
19P000485 |  | 19P000485 | FALSE | CNAS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | HOMER D. CHAPMAN HALL | 9 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43494 | This Project is Complete.. |  | 44267 |  |  |  | 4/1/21, DL: This Project is Complete…………..3/15/21,DL: Bill S. is still working on obtaining the air flow monitor. Once the air flow monitor arrives, we will complete the installation and Bill will be able to have the fume hood certified by a 3rd party vendor…………3/1/21, DL: We need to install the fire extinguisher and air monitor. I sent Bill S. an email asking him if he ordered the air monitor as we do not have one. I also contact EH&S and made them aware that we will be commisioning the fume hood in the very near future…..2/16/21, DL: Plumbing is complete. We will now start the exhasut vent, electrical and then seismically anchor the fume hood…………2/1/21, DL: We have had a delay with the plumbing and it is our goal to be complete on or before 3/1/21…………1/10/21, DL: This project is almost complete. This project will be complete in the next 30- days…………9/30/20, DL: Fume Hood demolition and abatement will be completed on 10/2/20. Fume hood install should be coplete in mid Novemeber……8/5/20, DL: We will submit plans this week. Once plans are approved, we will schedule the work……………Work orders are produced. We need to work on plans and permits once we return. | 2020-02-10 | Enrico Baez | Disconnect, cap and safe off the existing utility services. Provide the necessary abatement services to properly remove the fume hood from the site and deliver to the campus surplus yard. Install one new department furnished fume hood. Abatement Services: Provide the necessary abatement services to perform all utilities disconnections and floor repair. Floorcovering: Patch and or repair as necessary to match or provide a close match. Install rubber base. Access Control: Survey and adjust the entry door closer to increase latch pull to allow the door to closer completely. Patching and painting: Patch and paint wall at the old fume hood location. Mechanical: Disconnect metal duct, cap/safe off, reconnect/reconfigure new duct to accommodate the new fume hood. Electrical: Provide electrical disconnections and safe off. Reconnect/reconfigure power to the new fume hood. Plumbing: Disconnect Air, Gas, Vacuum, Cold water, and Drain, cap and safe off and reconnect/reconfigure service to the new fume hood. Resource Management: Properly remove the fume hood from the site and deliver to the campus surplus yard. | YES | 2021-04-01 | Spring 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000468 |  | 20P000468 | FALSE | VC-RED | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | Paint Only | HERMAN T. SPIETH HALL | 364 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 44005 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 12/02/20. 12/09/20 D-MMN: removed masking and reinstalled fallen base with base and wall glue. 12/08/20 D-MMN: applied finish to all the patches in the hallway and storage room. 12/07/20 D-MMN: Applied 3rd. coat of joint compound. returned and sanded then primed patches. these were located in the main hallway and the bedding supply room. vacuumed dust. 12/04/20 D-MMN: Continued scraping, treating and filling efflorescence and cracking paint. started taping baseboards and priming where it was so ready. |  | Paul Ditty |  |  | 2021-04-01 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
21P000079 |  | 21P000079 | FALSE | VC-RED | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. | PSYCHOLOGY BUILDING |  | COMPLETE | Rodolfo Torres | Laura Manor | LESLIE KARPINSKI |  | PAUL DITTY |  | X |  | FALSE |  |  | 44099 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/25/21. 02/25/21 D-BFA: continued painting the black room. Patched in the Quarantine rooms. 02/23/21 D-BFA: Continued painting finish on all green and all repaired cracks. 02/16/21 D-MMN: prepped cracks with caulking. |  | Paul Ditty |  |  | 2021-04-01 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000453 |  | 20P000453 | FALSE | CHASS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | Paint Only - Please patch/paint to existing color office for faculty new hire. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 142 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty…..6/18/20 o-dms: trans from 20w028936 to Project Phase - custodial please clean office floor for faculty new hire |  | Paul Ditty |  |  | 2021-04-05 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
21P000003 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Enrico Baez |  | R1 |  | FALSE |  |  | 44008 | [6 empty] | 4/9/2021 E. Baez roof repairs completed…1/20/2021 E. Baez- Proposal for $24,366 received from Rite-Way Roofing.….01/19/21, DL: Enrico is managing this project………….. | 2020-12-02 | Enrico Baez | Remove tripod antenna. Apply spray roof coating to existing roof surface | YES | 2021-04-09 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21 | 1
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install electrical utilities for new equipment | PHYSICS BUILDING | 1132 | COMPLETE | Kathryn Uhrich | Jose Wudka | WENDI TAPIA |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43543 | site visit with customer for review |  | 44281 |  |  |  | 4/15/21, DL: This project is 100% Complete……..4/1/21, DL: This project is complete except the sink drain and custodial. Custodial is scheduled to service the room in two weeks………3/15/21, DL: This project was supposed be be complete but we still have a plumbing drain assembly that is back ordered. We will connect the plumbing once the material arrives…………2/16/21, DL: New sink and faucet arrived, we will now schedule the install of the countertop and sink…………..1/19/21, DL: This project is in progress and will be complete with in 30- days………..9/30/20, DL: Plans were submitted for Plan Check review last week and we should have an update on the plan check review process soon………..8/5/20, DL: Need to meet with Kirk to verify electrical load. Once confirmed, we will work on plans for a permit. | 2019-10-15 | Enrico Baez | Install utilities for new equipment | YES | 2021-04-15 | Summer 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000003 |  | 20P000003 | FALSE | GRAD DIV | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | ADD POWER/DATA, PATCH/PAINT | UNIVERSITY OFFICE BUILDING |  | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS | CHERYL GERRY | Dan Lerman |  | 1 |  | FALSE |  |  | 43648 | Install hydration station when it arrives | 44244 | 44306 |  |  |  | 4/15/21, DL: This project is complete. We will install the hydration station when it arrives…..4/1/21, DL: Electrical, rough plumbing, drywall, and paint is complete. The next step is to install the floor covering with in two weeks……………3/15/21, DL: The demo, electrical and rough plumbing is complete. We will schedule inspection this week. Once we pass inspection, we will schedule the drywall installation, prime, paint and new floor covering……..2/16/21, DL: Conducted a site visit with the plumber and capenter shop. We will start the demo next week…………2/1/21, DL: We will schedule this project to start in 2- weeks……………….1/19/21, DL: Plans were approved and we will schedule the work in the near future………. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Permit is approved. We need to verify floor covering. Once floor covering is confirmed and ordered, we will schedule the work………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We will need plans as we are installing a new hydration station and a counter top that needs to be ADA compliant…………We started the plans and will submit them for a permit and plan check review within 2- weeks……….10/30/19, DL: No Plans will be needed. We will plan on scheduling the work shortly after Thanksgiving……. | 2019-06-13 | Enrico Baez | 9/24/2019 E. Baez--SCOPE-- 1. Removal and disposal of one bulletin board and two director cases. 2. Removal and disposal of abandoned telephone mounting bracket. 3. Remove and dispose of abandoned alarm box in wall. 4. Patch and paint walls in lobby and public restroom area. 5. Provide electrical connection for wall mounted monitor. 6. Cut access for data boxes. 7. Install monitor mount on wall. 8. Construct 7" x 18" laminate counter top and install in Lobby. | YES | 2021-04-15 | FALL 2019 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
21P000078 |  | 21P000078 | FALSE | VC-RED | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MULTIDISCIPLINARY RESEARCH BUILDING |  | COMPLETE | Rodolfo Torres | Laura Manor | TARA BARTHOL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 44097 | [6 empty] | 4/15/21, DL: The work is complete. We still need to connect several minus 80 freezers. Tara will check in with us when they are ready to be connected……….1/19/21, DL: the First floor work will be complete today, we will start the 2nd floor this week……………. |  | Enrico Baez |  |  | 2021-04-15 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000397 |  | 20P000397 | FALSE | CNAS | SL5 ENTOMOLOGY 139 - PATCH AND PAINT OFFICE | Patch and paint room 139 for the new faculty member | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 0139 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 43895 | [6 empty] | 04/16/21 O-ANS: Project complete per Paul Ditty. 02/10/21 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  | 2021-04-16 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000253 |  | 20P000253 | FALSE | BCOE | SL5 BOURNS HALL LAB B156 - EXHAUST SYSTEM | EXHAUST SYSTEM | MARLAN & ROSEMARY BOURNS HALL | B0156 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 43810 | Demolish cabinets and schedule paint and flooring | 44256 | 44330 |  |  |  | 4/30/21, DL: This project is 100% Complete :) ……… 4/15/21, DL: The power is complete. The exhaust is scheduled to be complete with in the next 30 days……….3/15/21, DL: The new dedicated electrical outlet is complete. We are also in the process of ordering the exhaust vents for the printer…………..2/16/21, DL: Plans were submitted 2- weeks ago. We received the plans back last week with corrections needed. We will resubmit the plans back to the building official by the end of the week….1/19/21, DL: We will start working on the plans for this project in the next two weeks. We will start this project once the permit is approved…… |  | Enrico Baez |  |  | 2021-04-30 | Winter 2021 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000370 |  | 20P000370 | FALSE | CHASS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | SPACE RENOVATION PROJECT | GORDON S. WATKINS HALL | 1311 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 43880 | This Project is complete…. | 44274 | 44379 |  |  |  | 4/30/21, DL: The paint is complete. The floor covering is ordered and will be installed in about two weeks………………4/15/21, DL: Asbestos, electrical, and drywall are complete. Painters are in the space prepping the walls…..4/1/21. DL: Asbestos abatment is scheduled to be complete by this Monday. We will start the framing and electrical next week……………..3/1/21, DL: Plans were approved. We now need to send our 14- day notice to the AQMD and schedule the demolition……..2/16/21, DL: Plans were submitted with building permit last week. We are now in the plan check review process………1/19/21, DL: We will start working on the plans for this project in the next three weeks. We should have plans to submit for plan check review in the next 5- weeks……….. |  | Enrico Baez |  |  | 2021-04-30 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000144 |  | 20P000144 | FALSE | CNAS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A | ALFRED M. BOYCE HALL | 3432, 3432A, 3446, 3446A | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43734 | Install floor covering |  | 44309 |  |  |  | 4/30/21, DL: This Project is 100% Complete………..4/15/21, DL: The asbestos abatement is complete. The floor covering will be complete by the end of next week……………4/1/21, DL: Asbestos abatement is scheduled for April 8th - 12th. We will install the floor covering shortly after and deep clean the space. This project is on schedule to be complete on or near 4/20/21…………..2/16/21, DL: Project Is on schedule. Paint is 90% complete. Once paint is complete, we will schedule the floor repairs and final deep clean……… 2/1/21, DL: We are making good progress and are target date is still 3/14/21………….1/19/20, DL: This project is in progress and will be complete in the next 30- days………….9/30/20, DL: We have started a few items but we are waiting on Matt U. and the PI to remove their items so we can have access to the space. Once the space is cleared out, we will proceed with the work…………8/5/20, DL: We will start the work in the next 4-6 weeks. | 2020-02-18 | Enrico Baez | This project is 100% Complete… ;) Boyce 3432, 3446, 3436 and 3436A . Patch and paint 3432, 3432A, 3436, 3436A, 3446, 3446A. Reface/replace water damaged cabinets near sink (3446). Install GCFI outlets near sink (replace existing) (3446). Install panel cover for electrical panel box. Replace many burnt out bulbs in ceiling lamps. Replace broken chemical plexi-glass on bench shelves. | YES | 2021-04-30 | Winter 2020 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000448 |  | 20P000448 | FALSE | BCOE | SL5 CHUNG HALL ROOM 216 - PATCH & PAINT | At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. |  | 216 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | X |  | TRUE |  |  | 43993 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  |  |  |  | 2021-05-11 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000046 |  | 20P000046 | FALSE | CNAS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | HOMER D. CHAPMAN HALL | 0001 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Enrico Baez |  | R2 |  | FALSE |  |  | 43677 | [6 empty] | 05/12/21 O-ANS: Per email from Bill Sutton, this project was requested to be cancelled. 1/19/21, DL: Enrico B. will manage this priject………….11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Install wireless access controls systems at front and rear entry doors. | YES | 2021-05-12 | Winter 2021 | FS | 0 | 2019 | 2021-09-01 | FY 20-21 | 1
20P000450 |  | 20P000450 | FALSE | BCOE | SL5 CHUNG HALL ROOMS 217, 218, 219 - PATCH & PAINT | Please patch and paint these adjoining rooms within suite 216. |  | 217, 218, 219 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | X |  | TRUE |  |  | 43994 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  |  |  |  | 2021-05-13 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000445 |  | 20P000445 | FALSE | CNAS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 279 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | DAN LERMAN |  | 3 |  | TRUE |  |  | 43985 |  | 44308 | 44347 |  |  |  | 5/14/21, DL: This project is 100% Complete……4/30/21, DL: The floor will be installed tomorrow. The project will be 100% next week………………4/15/21, DL: The plumbing and electrical is complete. The painters will be done this week. The floor covering is ordered and will be installed with in two weeks…..4/1/21, DL: We will try and start this project with in the next three weeks…………3/15/21, DL: The building permit was approved today. We will work this project in to our schedule and we will schedule the work once we are ready to and in line with our other projects that are already in progress……….2/16/21, LB: Changed to Priority 3 per Dan…….1/19/21, DL: This is a priority 3 project. We will start the project when all priority 1 &2 projects are in process or almost complete… |  | Enrico Baez |  |  | 2021-05-14 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000218 |  | 20P000218 | FALSE | VC-RED | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | VIVARIUM UPDATE AIR COMPRESSOR | HERMAN T. SPIETH HALL | 347 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | DAN LERMAN |  | 2 | R2 | FALSE |  |  | 43602 | Set & place the compressor. Start elect. / plumbin | 44293 | 44330 |  |  |  | 5/14/21, DL: This project is 100% Complete….4/30/21, DL: The plumbers are 75% complete. Once the plumbing is complete, the electricians will start…………4/15/21, DL: The compressor was delivered to the permanent location. The plumbers will start the air lines and drain assembly next week. The electricians will connect the electrical within a month, as they have a few other projects in their queue that need to be completed before they start this project………….4/1/21, DL: We are scheduled to relocate the compressor next week. Once the compressor is placed, we will anchor the compressor and start the electrical and plumbing……………….3/15/21, DL: We received confirmation the Compressor is on site. We will schedule the work once as soon as we are able to………….2/1/21, DL: WE will start the process for this project once we are closer to completing priority 1 projects. This is a prioity 2 project……1/19/21, /DL: This project has been scoped. We will start the work when we are complete with all priority #1 projects……. |  | Enrico Baez |  |  | 2021-05-14 | Winter 2021 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
21P000109 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | PATCH, PAINT & NEW FLOORING |  | 1146 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | PAUL DITTY |  | X |  | TRUE |  |  | 44153 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | FY 21-22 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
21P000111 |  | 21P000111 | FALSE | CHASS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. | GORDON S. WATKINS HALL | 2144 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 44153 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
21P000110 |  | 21P000110 | FALSE | CHASS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. | GORDON S. WATKINS HALL | 2146 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 44153 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
21P000109 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | PATCH, PAINT & NEW FLOORING |  | 1146 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | PAUL DITTY |  | X |  | TRUE |  |  | 44153 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | PAUL DITTY |  |  | 2021-05-24 | FY 21-22 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
21P000019 |  | 21P000019 | FALSE | BCOE | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | Bourns Office A305 - Install Plank Floor | MARLAN & ROSEMARY BOURNS HALL | A305 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | 3 | 2 | TRUE |  |  | 44032 | This project is Complte. | 44316 | 44337 |  |  |  | 6/2/21, DL: This project is complete…4/30/21, DL: This project started this week. The paint will be complete next week. The floor will be installed in about two weeks…………..4/1/21, DL: We will schedule the work with in the next three weeks. We are only doing this work early as the two primary trades are available. The damaged window covering will be replaced by a vendor…………..1/19/21, DL: This a priority 3 project. We will start this project when all priority #2 projects are complete………..1/14/21 O-ANS: Updated prioritization to #3 (from #2) per org leadership request. |  | Enrico Baez |  |  | 2021-06-02 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
21P000009 |  | 21P000009 | FALSE | CNAS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | GLOVEBOX SYSTEM | CHEMICAL SCIENCES |  | COMPLETE | Kathryn Uhrich | Jose Wudka | NATASHA GONZALES |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 44020 | This project is complete….. | 44263 | 44309 |  |  |  | 6/2/21, DL; This project is complete……4/15/21, DL This project is complete. When the glove box arrives, we will make the final connections………..4/1/21, DL: Demolition, paint, electrical and venting is done for the glove box. The snorkel parts are ordered. The flooring is ordered and should be here next week. We will schedule the floor install once we have the material on site………….3/15/21, DL: We will demolish the cabinets this week. We will also schedule the paint and floor replacement. The venting for the glove box and snorkel should be ordered this week………3/1/21, DL: The plans were approved last week. We will try and schedule demo this week or early next week……..2/16/21, DL: We submitted plans for building permit but corrrections are needed. We contacted the glove box manufacture for follow-up questions and we are waiting to hear back from them. Once we have confirmation on the needed information, we will resubmit the plans back to the building official……….1/19/21, DL: we will submit plans this week or earlier next ……………. |  | Enrico Baez |  |  | 2021-06-02 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 20-21
20P000248 |  | 20P000248 | FALSE | CNAS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT | Space Management has temporarily allocated Rooms 1223 and 1223-A in Webber Hall to CNAS. We need this lab cleaned and modified to accommodate relocating an existing (and active) lab. | HERBERT JOHN WEBBER HALL | 1223 + 1223-A | COMPLETE | Kathryn Uhrich | Jose Wudka | SHARYL MURDOCK |  | Dan Lerman |  | 5 | 4 | FALSE |  |  | 43796 | Project is Complete. | 44298 | 44347 |  |  |  | 6/2/21, DL: This project is complete……5/14/21, DL: This project is 95% complete. Items that need to be completed are: remove window AC unit, replace glass where the AC unit was removed and install window covering…………..4/30/21, DL: Demolition is complete, we will start the electrical and painting in the next two weeks…………..4/15/21, DL: The space was surveyed for hazardous material. There were rodent droppings, which will be disposed of this weekend, the ceiling tiles had mold. The ceiling tiles were removed. We will start the demo of the floor and some other items with in the next three weeks………..4/1/21, DL: We need to survey the space for hazardous material and arrange to have the space sanitized………………1/19/21, DL: This project is a priority #5. We will start this project when all priority #4 projects are complete…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….02/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Survey space for hazardous material. Once survey is complete, we will schedule abatement and the work. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2021-06-02 | Winter 2021 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
20P000320 |  | 20P000320 | FALSE | CNAS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | ACTIVATE VACUUM LINES | HERMAN T. SPIETH HALL | 1303 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | DAN LERMAN |  | 4 |  | FALSE |  |  | 43789 | Project is complete. | 44319 | 44358 |  |  |  | 7/15/21, DL: This project is complete……..6/2/21, DL: Electrical work is complete. The Plumbing shop will start to install the vacuum lines this Thursday. This project should be 100% complete by next Friday…….5/14/21, DL: The space was surveyed for hazardous material. Once we have the survey we will schedule work…………4/30/21, DL: Conducted site visit this week; we will survey the space for hazardous material before we conduct any work. We should start the work in about two weeks…………….1/19/21, DL: This is a priority 4 project. We will start this project when all all priority 3 projects are complete……….. |  | Enrico Baez |  |  | 2021-06-11 | Winter 2021 | FS | 0 | 2019 | 2021-09-01 | FY 20-21
21P000001 |  | 21P000001 | FALSE | CNAS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | NEW GROWTH CHAMBER PLACEMENT | HOWARD SAMUEL FAWCETT LABORATORY |  | COMPLETE | Kathryn Uhrich | Jose Wudka | LINDA WALLING |  | DAN LERMAN |  | 2 |  | TRUE |  |  | 43990 | This project is complete | 44306 | 44338 |  |  |  | 7/15/21, DL: This project is complete. Linda is requesting a sensored light switch which we will install under an SL6 work order………..4/30/21, DL: for most part this growth chamber is complete except the air curtain which is still not on site……………4/15/21, DL: This project is in progress. Linda will schedule the installation to take place in two weeks. We are waitng on the air curtain. This project should be 100% complete with in the next 4- weeks………4/1/21, DL: Plans were approved. We will try and start this project with in the next 3-weeks or sooner if possible…..3/1/21, DL: This was recently changed to a priority 2 project. Once plans are approved, we will work on the schedule noting, the schedule for this will work around pending priority 1 projects……2/16/21, LB: Changed to Priority 2 per Dan….1/19/21, DL: This is a priorty 3 project. We will start this project when all priority 2 projects are complete. |  | Enrico Baez |  |  | 2021-07-15 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 21-22
21P000137 |  | 21P000137 | FALSE | SOM | SL5 WEBBER HALL - ACCESS CONTROL | Per attached Sales Quote 43830-7 dated 11/6/2020, from Enterprise Security in Tustin, please proceed with the proposal, planning. permit, and contract to complete this project. |  | 1247 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | CYNTHIA CAROLINA | Dan Lerman |  | R1 |  | FALSE |  |  | 44264 | Final inspection and payment | [5 empty] | 7/15/21, DL; This project is complete. We still need to conduct the final inspection. There was a problem identified during the project where a repair is needed via an FAU number. We will conduct the repair under an SL6. Cynthia Carolina is aware of the additional needed repair that was not part of the scope or work……/9/21, O-DMS: EMAIL TO DAN LERMAN PROJECT # AND ASSIGNED TO J-DLN. |  | Dan Lerman |  |  | 2021-07-15 | Winter 2021 | FS | 0 | 2021 | 2021-09-01 | FY 21-22 | 1
20P000366 |  | 20P000366 | FALSE | CNAS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | MINOR LAB RENOVATION | HERMAN T. SPIETH HALL | 2375 / 2375-A | COMPLETE | Kathryn Uhrich | Jose Wudka | SHERICE UNDERWOOD |  | DAN LERMAN |  | 7 |  | TRUE |  |  | 43880 | Final walk and punch list items. | 44330 | 44393 |  |  |  | 7/15/21, DL: This project is complete. I am meeting with Kate for a final walk through tomorrow morning………….5/14/21, DL: We will start the project in the next three weeks, the door will be ordered next week. We will schdule paint to take place in the next 3-4 weeks….1/19/21, DL: This is a priority 7 project, we will start this project when all priority 6 projects are complete………….. |  | Enrico Baez |  |  | 2021-07-16 | Winter 2021 | FS | 0 | 2020 | 2021-09-01 | FY 21-22
20P000413 |  | 20P000413 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR ROOM A159A - EAST WALL PATCH & PAINT | PATCH & PAINT |  | A0159A | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 43930 | [6 empty] | 08/13/21 O-ANS: Project complete per Paint Crew. 08/12/21 D-JPO: sanded spot primed and spot painted entire room. 08/10/21 D-JPO: patched and masked |  | PAUL DITTY |  |  | 2021-08-13 | FY 21-22 | FS | 0 | 2020 | 2021-09-01 | FY 21-22
21P000014 |  | 21P000014 | FALSE | BCOE | SL5 BOURNS HALL OFFICE A149 - PATCH & PAINT HOLES ON WEST WALL | PATCH & PAINT |  | A0149 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 44026 | [6 empty] | 08/13/21 O-ANS: Project complete per Paint Crew. 08/13/21 D-JPO: cleaned up job done. 08/12/21 D-JPO: sanded spot primed and spot painted two walls. 08/10/21 D-JPO: patched and masked |  | PAUL DITTY |  |  | 2021-08-13 | FY 21-22 | FS | 0 | 2020 | 2021-09-01 | FY 21-22
3471 | 3471 |  | FALSE | VC-STU AFF | HUB Electrical Sub Meter Installation | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Bidding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 4 |  |  | FALSE | 200000 |  | 43332 | Award Contract | 44470 | 44501 | [10 empty] | PD&C | 0 | 2018 | 2021-09-01
3632 | 3632 |  | FALSE | ATHLETICS | SRC North Instant Replay System | Possible update of instant replay system in Student Recreation Center North to include volleyball if mandate by Big West Conference is enacted. This will include placing cameras on the ends of the court that will send signal back to the control room and could involve additional wiring to courtside connection boxes. Scope may include upgrading audio connections. Volleyball season starts in late August... first home game TBD. No charges to this FAU unless Athletics notified in advance of work to be performed. Work Notes: Project will require coordination not only with Athletics but must also with Recreation (Mike Eason), and their scheduling may affect above dates. Possible vendor to be consulted is TechNet who has indicated ability to do such a project in recent times. |  |  | Delayed until 8/2022 per Athletics | Tamica Smith Jones | Joe Erbland | Joe Erbland |  | Tameesha Hayes | 3 |  |  | FALSE |  |  | 44287 | Delayed until 8/2022 per Athletics | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | Design | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 42340 | Bidding | [12 empty] | PD&C | 0 | 2015 | 2021-09-01
3616 | 3616 |  | FALSE | CAP PROG | University Ave/Canyon Crest Dr Improvements | $100,000 in Violent Acts Mitigation and Prevention funding have been awarded to study short and long-term safety improvements at the intersection at University Avenue and Canyon Crest Drive. Subsequent activities will involve the construction of identified improvements. |  |  | Design | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Uma R. | 16 |  |  | FALSE | 100000 |  | 44256 | Construction | 44562 | 44593 | [10 empty] | PD&C | 0 | 2021 | 2021-09-01
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Design | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 44091 | 2nd site visit w/ consultant | [12 empty] | PD&C | 0 | 2020 | 2021-09-01
3631 | 3631 |  | FALSE | ITS | SOM-ED 1 UPS | The Information Technology Solutions (ITS) intends to replace its existing UPS unit with a state of the art systems that will support all of the requirements set-forth by the University of California, Riverside ITS and Facilities departments. Our primary objective is to provide ITS critical services and various other software applications. The ITS department would like to Procure (1) redundant UPS System with all accessories and maintenance for three years after warranty (AMC). Procure One Replacement 500KW UPS Unit, Installation of New UPS, Removal and Disposal of Old UPS components, Startup Services for New UPS, Electrical Installation of New UPS and Removal of Rental UPS connections (High Voltage) |  | 1625 | Design | Danna Gianforte | Shelley Gupta | Cesar Higueros |  | Tameesha Hayes | 1 |  |  | FALSE |  |  | 44399 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Design | Gerry Bomotti | TBD | ---- |  | Fernando Canon | 1 |  |  | FALSE | 33980000 |  | 43528 | Construction | 44531 | 45047 | [10 empty] | PD&C | 0 | 2019 | 2021-09-01
3515d | 3515d |  | FALSE | PB&A | Multiple SF6 Primary Switches | Sub-project of 950568 |  |  | Design | Gerry Bomotti | TBD | John Franklin |  | John Franklin | 2 |  |  | FALSE |  |  | 44256 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 19 |  |  | FALSE | 320000 |  | 43312 | Bidding TBD | [12 empty] | PD&C | 0 | 2018 | 2021-09-01
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 44096 | Bidding | 44562 | 44652 | [10 empty] | PD&C | 0 | 2020 | 2021-09-01
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Design | Gerry Bomotti | TBD | ---- |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Bidding | [12 empty] | PD&C | 0 | 1900 | 2021-09-01
3630 | 3630 |  | FALSE | SOM | SOMR Egress Doors/Cameras | All egress doors for floors 1-3. need to be replaced with compliant standards. Project to also include security cameras for entry and exit on 1st and 2nd floor. |  |  | Design | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes | 2 |  |  | FALSE | 65000 |  | 43894 | Bidding | [12 empty] | PD&C | 0 | 2020 | 2021-09-01
9067 | 9067 |  | FALSE | PB&A | DM(FY20) Campus Infrastructure Access Control | Access Control: Automate Access Controls focusing on General Assignment Classrooms. |  |  | DM project to be funded | Gerry Bomotti | TBD |  |  | Fernando Nunez |  |  |  | FALSE | 200000 |  |  | DM project to be funded | [12 empty] | PD&C | 0 | 1900 | 2021-09-01
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS BUILDING |  | ESTIMATE | Kathryn Uhrich | Jose Wudka | JOSE WUDKA |  | Enrico Baez |  | R1 |  | FALSE |  |  | 43818 | Awaiting Response from Client | [5 empty] | 05/13/21 O-ANS: Enrico corresponded with Dr. Wudka on 3/14/2021. He had emailed me stating that the College was going to discuss the project. Still awaiting a response to that inquiry. I follow up today requesting an update. 1/19/21 DL: Enrico is managing this project. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-09-01 |  | 1
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | Funding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 600000 |  | 43713 | Combine with Exterior Proj CP3548 | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | Furniture & Equipment | Jacqueline Norman | Sharyl Murdock | ---- |  | Mihai Gavan | 9 |  |  | FALSE | 60430000 |  | 42887 | Close-out | 43770 | 44409 | [10 empty] | PD&C | 0 | 2017 | 2021-09-01
3615 | 3615 |  | FALSE | CAP PROG | Student Success Center Buildout | Buildout and furnishing of the SSC dining venue for temporary use as seating/study area and other as needed construction scope related to the overall building project that was not described in the Basis of Design. |  |  | Furniture & Equipment | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Mihai Gavan | 17 |  |  | FALSE | 980000 |  | 44264 | Close-out | 44256 | 44409 | [10 empty] | PD&C | 0 | 2021 | 2021-09-01
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LABORATORIES 1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 43880 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-09-01
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SUPPORT SERVICES BUILDING | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | Emily Engelschall, Sean Cason | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 43852 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-09-01
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL BUILDING | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 43803 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2019 | 2021-09-01
3614 | 3614 |  | FALSE | INACTIVE P&B | MLK Water Meters | Provide by contract plumbing point of connections and irrigation infrastructures to north and south sides of Martin Luther King Blvd. for watering of UCR palm trees. City of Riverside shall install two (2) ¾” [City] water meters at points of connection. Provide approximately 300’ of new irrigation main-line with associated trenching via contract and/or via facilities work order TBD. |  |  | In Bidding | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 17 |  |  | FALSE | 31790 |  | 44316 | Award Contract | 44470 | 44501 | [10 empty] | PD&C | 0 | 2021 | 2021-09-01
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | In Bidding | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 43528 | Award Contract | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Bidding | Gerry Bomotti | TBD | ---- |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 44089 | Award Contract | [12 empty] | PD&C | 0 | 2020 | 2021-09-01
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Bidding (Phase 2) | Kathryn Uhrich | Jose Wudka | Sabrina Schuster |  | Scott Donnell | 6 |  |  | FALSE |  |  | 42710 | Award Contract (Phase 2) | 44470 | 44531 | [10 empty] | PD&C | 0 | 2016 | 2021-09-01
3637 | 3637 |  | FALSE | ATHLETICS | Soccer Field Spiideo Video Installation | We are making an addition to the soccer stadium by adding a 40 foot pole at center field with a cloud based camera operating system. |  |  | In Construction | Tamica Smith Jones | Joe Erbland | Eugene Hutchinson |  | Tameesha Hayes | 1 |  |  | FALSE |  |  | 44302 | Complete Construction | 44409 | 44440 | [10 empty] | PD&C | 0 | 2021 | 2021-09-01
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Construction | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Scott Donnell | 1 |  |  | FALSE | 700000 |  | 43194 | Complete Construction | [12 empty] | PD&C | 0 | 2018 | 2021-09-01
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | ---- |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 42725 | Pending proposal from JCI | 44197 | 44561 | [10 empty] | PD&C | 0 | 2016 | 2021-09-01
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Richard Zapien |  | Scott Donnell | 3 |  |  | FALSE | 39000 |  | 43959 | Cooler Delivery | 44348 | 44470 | [10 empty] | PD&C | 0 | 2020 | 2021-09-01
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Georgios Vidalakis |  | Scott Donnell | 5 |  |  | FALSE | 640745 |  | 44085 | Complete Construction | 44197 | 44501 | [10 empty] | PD&C | 0 | 2020 | 2021-09-01
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Tracey Kahn |  | Scott Donnell | 9 |  |  | FALSE | 1575000 |  | 43108 | Complete Construction | 44228 | 44470 | [10 empty] | PD&C | 0 | 2018 | 2021-09-01
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May include paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | In Construction | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 3 |  |  | FALSE | 1340000 |  | 43600 | Complete Construction | 44317 | 44440 | [10 empty] | PD&C | 0 | 2019 | 2021-09-01
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 5 |  |  | FALSE | 600000 |  | 43634 | Installaton of NFACP | 44348 | 44469 | [10 empty] | PD&C | 0 | 2019 | 2021-09-01
3590b | 3590b |  | FALSE | PB&A | DMFI(FY17-20) Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Construction | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 43796 | Submittal approval | 44378 | 44530 | [10 empty] | PD&C | 0 | 2019 | 2021-09-01
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | In Construction | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 97050000 |  | 43528 | Complete Construction | 44378 | 45047 | [10 empty] | PD&C | 0 | 2019 | 2021-09-01
3467 | 3467 |  | FALSE | PB&A | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 17 |  |  | FALSE | 405000 |  | 43312 | Complete Construction | 44409 | 44440 | [10 empty] | PD&C | 0 | 2018 | 2021-09-01
3490 | 3490 |  | FALSE | PB&A | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | Parking Lot 13 |  | In Construction | Gerry Bomotti | TBD | Irma Henderson |  | John Franklin | 25 |  |  | FALSE | 31844000 |  | 43440 | Complete Construction | 43862 | 44440 | [10 empty] | PD&C | 0 | 2018 | 2021-09-01
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 44097 | Complete Construction | 44378 | 44531 | [10 empty] | PD&C | 0 | 2020 | 2021-09-01
3524 | 3524 |  | FALSE | VC-STU AFF | Student Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | STUDENT SERV |  | In Construction | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE | 450000 |  | 43571 | Complete Construction | 44409 | 44440 | [10 empty] | PD&C | 0 | 2019 | 2021-09-01
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | In Construction | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 61918 |  | 44095 | Complete Construction | 44440 | 44440 | [10 empty] | PD&C | 0 | 2020 | 2021-09-01
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Construction by USDA | Kathryn Uhrich | Jose Wudka | MaryLou Polek |  | Scott Donnell | 10 |  |  | FALSE | 2500 |  | 43742 | Complete Construction by USDA | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
3624 | 3624 |  | FALSE | BCOE | CE-CERT Circuit Upgrade | We have an existing 208 VAC 100 Amp circuit. We would like to upgrade to a 200 Amp service. The existing service is located in the electrical room at 1084 Columbia. |  |  | In Design | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Tameesha Hayes | 5 |  |  | FALSE | 4100 |  | 44258 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3613 | 3613 |  | FALSE | CAP PROG | Corp Yard Modular Building Relocation Study | This project will be to relocate the existing School of Medicine modular trailer (P5825) to the Corp Yard (specific location to be determined). This modular needs to be relocated due to the new School of Medicine Education Building II project being located on this site. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Tameesha Hayes | 18 |  |  | FALSE |  |  | 44309 | Complete Design | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 3182452.32 |  | 42720 | Bidding | 44562 | 44652 | [10 empty] | PD&C | 0 | 2016 | 2021-09-01
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | Jose Wudka | Wendi Tapia |  | Tameesha Hayes | 12 |  |  | FALSE |  |  | 44001 | Waiting for equipment from overseas | [12 empty] | PD&C | 0 | 2020 | 2021-09-01
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | ---- |  | Fernando Canon | 7 |  |  | FALSE | 432510 |  | 42425 | Bidding | 44531 | 44593 | [10 empty] | PD&C | 0 | 2016 | 2021-09-01
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 500000 |  | 43713 | Bidding | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | ---- |  | Fernando Canon | 18 |  |  | FALSE | 2600000 |  | 42509 | Funding & Approval | [12 empty] | PD&C | 0 | 2016 | 2021-09-01
3648 | 3648 |  | FALSE | PB&A | Bannockburn Walkway Repairs | Several walkway locations at Bannockburn have deteriorated to the point that they must be replaced. The topcoat is past it’s service life and has lost all waterproofing effectiveness. As a result, the underlying sheathing, T&G, and support beams have suffered extreme water damage. Scope of Work: Replace support beams, T&G, and topcoat system at 2 locations: L bldg. & V bldg. Requesting JOHN FRANKLIN as PM. |  |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 1 |  |  | FALSE |  |  | 44389 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 22 |  |  | FALSE |  |  | 42653 | Bidding | [12 empty] | PD&C | 0 | 2016 | 2021-09-01
3626 | 3626 |  | FALSE | UNDERGRADUATE EDUCATION | Rivera Library Room Modifications | Conduct room modifications to support new wall display on west wall Rivera A101A. Work needed: 1. West wall - ½” three-ply to support 12 x 55” displays over bookshelves. 2. West wall – drywall cover bookshelves any area not covered by the technology displays. 3. West wall – add electrical outlets as needed for new displays 4. North and south walls – add electrical for new motorized shades 5. Rivera A101A – add carpeting 6. Rivera A101A – paint room Notes: - Working with Chuck Forsyth in ITS and Bahram Mobasher from CNAS/Physics on project. - Israel and Chuck had a preliminary meeting with Enrico Baez from facilities to discuss project. - Point of contact: Israel Fletes and Charles Forsyth. Israel Fletes cellphone: 951-300-6693 |  | A101A | In Design |  |  | Israel Fletes |  | Vilma Kern | 1 |  |  | FALSE | 32000 |  | 44237 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3270 | 3270 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Chapman Hall - Replace HVAC System | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | CHAPMAN |  | In Design (Re-opened) | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Tameesha Hayes | 11 |  |  | FALSE | 595819 |  | 42801 | Bidding | [12 empty] | PD&C | 0 | 2017 | 2021-09-01
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | In Funding | Kathryn Uhrich | Jose Wudka | Mireya Botello Santoyo |  | Scott Donnell | 1 |  |  | FALSE | 32871.65 |  | 44026 | Secure Funding for Additional Scope | [12 empty] | PD&C | 0 | 2020 | 2021-09-01
3636 | 3636 |  | FALSE | PB&A | Tunnel DAS | Adding radio repeaters to the tunnel system to improve coverage in a high hazard work area. The project consists of adding a rooftop antenna, battery back-up, amplifier, repeater antennas, and coax runs through the tunnel system. A few items need to be mounted. Golden State Communications will need to interface additional system to the existing radio system. |  |  | In Funding | Gerry Bomotti | TBD | Tracy Stark |  | Tameesha Hayes | 1 |  |  | FALSE | 77271 |  | 44321 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | In Pre-Programming | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 9 |  |  | FALSE | 1500000 |  | 43775 | Programming | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | John Franklin | 2 |  |  | FALSE |  |  | 43532 | Complete Programming | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | ---- |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 43528 | DB Competition | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 43297 | Complete Study | [12 empty] | PD&C | 0 | 2018 | 2021-09-01
3612 | 3612 |  | FALSE | CAP PROG | Native American Landscape Garden | Create a physical marker to commemorate the UCR Land Acknowledgement in the form of a Native American Landscape Garden (working name) at the proposed project location. |  | Ext | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Uma R. |  | Vilma Kern | 15 |  |  | FALSE | 103000 |  | 44238 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis (RE Proj) | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 43510 | Complete Study | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
3644 | 3644 |  | FALSE | LIBR | Rivera Library Fire Suppression Study | Request for estimate for installing fire suppression system in Rivera Library 4th floor and Secured area on Basement floor. |  |  | In Programming (Study) | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Vilma Kern | 1 |  |  | FALSE |  |  | 44372 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 43404 | CEQA | [12 empty] | PD&C | 0 | 2018 | 2021-09-01
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MATERIALS SCIENCE & ENGINEERING | 71 | IN PROGRESS | Christopher Lynch | Todd Ambriz | DONG YAN |  | DAN LERMAN |  | 2 | 3 | FALSE |  |  | 44049 | Schedule the work once the permit is approved | 44349 | 44454 |  |  |  | 8/18/21, DL: The electrical is complete. We are ordering material for the exhaust vents this week. We will schedule the installation when the material is on site……08/02/21, DL: We are still in the plan check review process. Once the permit is approved, we will schedule the work….7/15/21, DL: Plans are complete, we will apply for the building permit today and the permit should be reviewed and approved in the next 2-4 weeks. Once the permit is approved, we will order the material and schedule the work……6/2/21, DL: We will work on the final plans the week of 6/14/21 and try to apply for building permit on or before 6/22/21. Once the permit is approved, we will schedule the work…. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-09-01
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 245 | IN PROGRESS | Juliet McMullin | Cindy Williams | ANDREA HIDALGO | Susan Komura | DAN LERMAN |  | 3 |  | FALSE |  |  | 43832 | Make corrections and resubmit plans on 7/15/21 | 44340 | 44462 |  |  |  | 8/18/21, DL: We are making great progress and we should be done with project by Sept. 21. All light fixures are here on site. ……08/02/21, DL: The plans are now approved. We ordered the light fixtures and have also started the work. It is our plan to be complete with the project by September 23rd and the Arts Department currently has an exhibit they are planning to present on or near the 23rd……7/15/21, DL: We are still in plan check review with the building department and a few corrections were needed. We will resubmit the corrections tomorrow. Hopefully the permit will be approved in the next two weeks……..6/2/21, DL: We are almost complete with the plans. We will submit the plans to the customer for review by the end of the week. Once the cutomer approves the plans, we will apply for the building permit……4/20/21, DL: Conducted site vist with the Arts team. We will start working on the plans in the next two weeks……1/19/21, DL: This is a priority 3 project. We will start the plans and permit for this project when all priortiy #2 projects are complete… |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-09-01
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Convert Basement Library into Piano Lab | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 54 | IN PROGRESS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 43788 | Framing and electrical | 44330 | 44500 |  |  |  | 8/18/21, DL: We are making great progress and we should be complete with this project within the next 6 weeks. 08/02/21, DL: Most of the demolition is complete. We started the framing today. It is our goal to be 100% complete with this project by the end of October….7/15/21, DL: Plans were approved this week. Carpenter shop is ordering material and we should start the work next week…… 6/2/21, DL: We applied for the building permit last week. We should have approved plans in the next 1-2 weeks…..5/14/21, DL: We sent Paul R. the 75% complete plans today for review. Once Paul approves the plans and layout of the pianos, we will proceed with completing the plans and apply for the building permit. The demolition of the cabinets and floor covering is complete. The carpenter shop is also pre-ordering their material to help expedite the project once we have the approved building permit……4/1/21, DL: We will start the plans process over the next two weeks and try and apply for a building permit in the next 2-3 weeks…1/19/21, DL: We will Start the plans, permit and the work once all priority #3 projects…11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks…. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | 0 | 2019 | 2021-09-01
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | W. CONWAY PIERCE HALL | 2232A | IN PROGRESS | Kathryn Uhrich | Jose Wudka | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 43852 | Schedule the work once the permit is approved | 44351 | 44498 |  |  |  | 8/18/21, DL: We are scheduled to start the abatment and demo on 8/24/21. We will try and complete this project by mid-october or sooner…… 08/02/21, DL: The plans are still being review by the building department and EH&S. Once the plans are approved, we will schedule the work….7/15/21, DL: Plans will be complete and we will apply for the building permit by tomorrow enveing. If the permit is appproved, which should take 2-4 weeks for the review and approval process, we will order the material and schedule the work……5/14/21, DL: Project is scoped, we will work on plans and submit them to Kevin for review in about 3- weeks…….1/19/21, DL: This is a priority #9 project. We will start this project when all priority #8 projects are complete… |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-09-01
21P000183 |  | 21P000183 | FALSE | PB&A | SL5 OBAN A&B - PROJECT PORCH REPAIRS 2, 10, 18, 26 | TRENTON MABEE SL5 PROJECT FOR OBAN A & B APT 2, 10, 18, AND 16. PORCH REPAIRS. ZONE MAINTENANCE CARPENTER SHOP |  |  | IN PROGRESS | Gerry Bomotti | TBD | TRENTON MABEE |  | Chris Pillen |  |  |  | FALSE |  |  | 44329 | [6 empty] | 08/06/21 O-ANS: Assigned to Trenton Mabee to manage project. |  | Chris Pillen |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-09-01
3195 | 3195 |  | FALSE | FAC-PLNG-DESIGN-CONST | North District | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | Move-in | Susan Marshburn | Da Lan Dinh | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 4146146.55 |  | 42669 | Close-out | 43647 | 44409 | [10 empty] | PD&C | 0 | 2016 | 2021-09-01
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Joe Erbland | Johnathan Jensen |  | Fernando Nunez | 4 |  |  | FALSE | 0 |  | 43335 | Department approval to move fwd | [12 empty] | PD&C | 0 | 2018 | 2021-09-01
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 13 |  |  | FALSE | 0 |  | 43072 | On Hold | [12 empty] | PD&C | 0 | 2017 | 2021-09-01
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 16 |  |  | FALSE | 0 |  | 43297 | Coordinating with North District | [12 empty] | PD&C | 0 | 2018 | 2021-09-01
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | On Hold | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 43273 | Awaiting direction by Provost | [12 empty] | PD&C | 0 | 2018 | 2021-09-01
3550 | 3550 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Skye Hall HVAC Replacement | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | SKYE HALL |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 6 |  |  | FALSE | 1177000 |  | 43713 | On Hold | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 43809 | Departmental Approval | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | On Hold | Brian Haynes | Cathy Eckman | Christina Wong |  | Tameesha Hayes | 5 |  |  | FALSE | 130000 |  | 43543 | On Hold | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
3627 | 3627 |  | FALSE | VC-STU AFF | Costo Hall New Doors | Add three (3) doors to divide new office designations in Costo Hall. Two of the doors require new frames |  |  | On Hold | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 8 |  |  | FALSE |  |  | 44259 | On Hold | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3610 | 3610 |  | FALSE | PB&A | Hulen Place Homeless Medical Clinic | SOM is acquiring additional space for a medical clinic to assist with the homeless population. |  |  | On Hold, May Move Forward | Gerry Bomotti | TBD | Diana Armenta |  | Daneca Stevens | 5 |  |  | FALSE |  |  | 44110 | On Hold, May Move Forward | [12 empty] | PD&C | 0 | 2020 | 2021-09-01
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 1 |  |  | FALSE | 0 |  | 42886 | Department Approval/Funding | [12 empty] | PD&C | 0 | 2017 | 2021-09-01
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 6 |  |  | FALSE | 0 |  | 43178 | CIB Approval | [12 empty] | PD&C | 0 | 2018 | 2021-09-01
3640 | 3640 |  | FALSE | VC-RED | MRB Circulation Pumps E-Power | MRB Circulation Pumps e-Power |  |  | On-Hold | Rodolfo Torres | Laura Manor | Tara Barthol |  | Vilma Kern | 1 |  |  | FALSE |  |  | 44377 | On-Hold | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3634 | 3634 |  | FALSE | CNAS | Botanic Garden Geodesic Dome | Request is for an architect to draw a design for a replacement of current geodesic dome. Design can then be used as basis for fund-raising campaign to construct new dome. Dr. Holt, UCRBG Director, has been in discussions with Jacqueline Norman and Drew Hecht. Dome was constructed on site in 1980s, all wood, greatly deteriorated. Dome is unrepairable, unsafe, and closed to the public. Goal is to replace it with a structure as close to the original dome shape as possible but with modern functionality. We envision a structure with partial solid walls near the ground, then lath on upper walls and top, possibly cross shaped with doors at ends of the arms, and a domed center for taller plants. Should have “wood look” or at least maintain original sensibility since it is beloved as is, but needs a durable material! Function—house the collection of shade-requiring plants including prehistoric plants, subtropical plants, and others. Design should include space for plants inside around the edges and a wide walkway in a circle around a central display, suitable for tour groups, small gatherings, and photography. Arms extending in cross shape could house additional plants, displays, even sale plants. |  |  | Pre-Programming | Kathryn Uhrich | Jose Wudka | Jodie Holt |  | Fernando Nunez | 2 |  |  | FALSE |  |  | 44299 | Meeting w/ client regarding budget | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3652 | 3652 |  | FALSE | FAC-PLNG-DESIGN-CONST | 266 Frost Ct. Fence, Electric Meter, Lighting, Irrigation | 266 Frost Court - Install fence utilizing rod iron gates already on hand at BG; install electrical meter and lighting for security purposes; install battery operated irrigation. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Daneca Stevens |  |  |  | FALSE |  |  | 44425 | New (8/17/21) | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
9065 | 9065 |  | FALSE | PB&A | DM(FY20) Olmsted HVAC Repairs to Air Handlers | Equipment/Controls - Repairs to Air Handlers |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Vilma Kern |  |  |  | FALSE | 200000 |  |  | Programming | [12 empty] | PD&C | 0 | 1900 | 2021-09-01
9063 | 9063 |  | FALSE | PB&A | DM(FY20) Boyce Building Systems Improvements | Provide improvements to antiquated mechanical-electrical-plumbing systems to extend building useful life |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Tameesha Hayes |  |  |  | FALSE | 900000 |  |  | Programming | [12 empty] | PD&C | 0 | 1900 | 2021-09-01
9064 | 9064 |  | FALSE | PB&A | DM(FY20) Olmsted HVAC Replace Economizers | Equipment/Controls: Replace economizers for fresh air controls for all Air handlers |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Vilma Kern |  |  |  | FALSE | 200000 |  |  | Programming | [12 empty] | PD&C | 0 | 1900 | 2021-09-01
9066 | 9066 |  | FALSE | PB&A | DM(FY20) Sproul HVAC | Equipment/Controls - Replace Heat Exchangers/VFD Pumps |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Daneca Stevens |  |  |  | FALSE | 226000 |  |  | TBD (Assigned in July) | [12 empty] | PD&C | 0 | 1900 | 2021-09-01
3650 | 3650 |  | FALSE | CNAS | Greenhouse 16-3 Rebuild Estimate | We need an estimate to rebuild greenhouse 16-3 that burned down in a fire |  |  | Pre-Programming (Insurance Claim) | Kathryn Uhrich | Jose Wudka | Sue Lee |  | Scott Donnell | 13 |  |  | FALSE |  |  | 44410 | Programming | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3642 | 3642 |  | FALSE | CAP PROG | South District Planning Study | The “South District” presents a unique opportunity to create a strong identity for academic and research expansion across the campus loop road with an emphasis on creating a transformative and synergistic new campus neighborhood. Its hillside location makes it highly visible from the freeway and the Core Campus, presenting a significant opportunity to enhance campus identity. The site’s high elevation also gives it unobstructed views outward. A holistic and integrated planning framework for its development is important to ensure alignment with broad planning strategies and principles in place for the campus, as established in land planning per the DRAFT 2021 Long Range Master Plan and the more detailed physical planning vision from the 2016 Physical Master Plan Study for this “opportunity site”, and its immediate context. The upcoming effort to update the campus’ Physical Design Framework document will further analyze the unique opportunities afforded by the South District, and leverage the design of the School of Business Building to establish organizing principles for how the area could be optimally redeveloped to its highest potential. |  |  | Programming (Study) | Jacqueline Norman | Sharyl Murdock | Uma R. |  | Uma R. | 19 |  |  | FALSE | 51000 |  | 44357 | Complete Study | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3623 | 3623 |  | FALSE | CNAS | NRS Prop 68 Study - Boyd | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Fernando Nunez | 7 |  |  | FALSE |  |  | 44229 | Pending submittal of Prop 68 items | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3618 | 3618 |  | FALSE | CNAS | NRS Prop 68 Study-James Reserve | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Fernando Nunez | 8 |  |  | FALSE | 8380 |  | 44229 | Pending submittal of Prop 68 items | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3391 | 3391 |  | FALSE | CNAS | NRS Motte Rimrock Res Cost Study | Requesting recheck and recost of formal estimate for Motte Reserve Prop 84 for the Natural Reserve System. The former estimate was $763K. Purpose of study is to confirm, or augment the initial project valuation included with the Proposition 84 NRS grant application to install new structures at the Motte Rimrock Reserve site. |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Kimberly Hammond, D. McWilliams |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 43041 | Pending submittal of Prop 68 items | [12 empty] | PD&C | 0 | 2017 | 2021-09-01
3645 | 3645 |  | FALSE | PB&A | Falkirk Seismic Rating Study | FALKIRK STRUCTURAL STUDY - provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. |  |  | Programming (Study) | Gerry Bomotti | TBD | Sean Hatfield |  | D.Hecht/J.Franklin | 2 |  |  | FALSE |  |  | 44389 | Complete Study | [12 empty] | PD&C | 0 | 2021 | 2021-09-01
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Scott Donnell | 10 |  |  | FALSE | 65000 |  | 43528 | Complete Study | [12 empty] | PD&C | 0 | 2019 | 2021-09-01
99p000001 |  | 99p000001 | FALSE | ATHLETICS | Test | test |  | 1234 | PROJECT INTAKE | Tamica Smith Jones | Joe Erbland | Test |  | Enrico Baez |  | x |  | FALSE |  |  | 44424 | [13 empty] | FS | 0 | 2021 | 2021-09-01
22P000006 |  | 22P000006 | FALSE | CAMPUS | SL5 MRB 4210 - Install AC and Electrical Infrastructure | We have a project at MRB 4210 where we will be installing Air conditioning and electrical infrastructure to accommodate equipment that will be relocated from Batchelor Hall to MRB which is a result of the Batchelor Hall renovation. |  | 4210 | PROJECT INTAKE |  |  | SHARYL MURDOCK | GERRY BOMOTTI | Dan Lerman |  | 1 |  | FALSE |  |  | 44389 | Work on plans and apply for building permit | 44445 | 44498 |  |  |  | 8/2/21, DL: We are currently in the design phase and still trying to verify the logistics of the project. We are planning to apply for a building permit in the next 2- 3 weeks……… |  | Dan Lerman |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-09-01
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | [12 empty] | PD&C | 0 | 1900 | 2021-09-01
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2022 | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 20 |  |  | FALSE | 0 |  | 43007 | Project pushed to 2022 | [12 empty] | PD&C | 0 | 2017 | 2021-09-01
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 43920 | Projects to be assigned | [12 empty] | PD&C | 0 | 2020 | 2021-09-01
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | MARLAN & ROSEMARY BOURNS HALL | B0328E | QUEUE TO START | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Enrico Baez |  | R1 | R1 | FALSE |  |  | 43774 | [6 empty] | 1/19/21, DL: Todd has the estimate. Sent follow up email to Todd requesting update or FAU number………………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | 0 | 2019 | 2021-09-01 |  | 1
21P000146 |  | 21P000146 | FALSE | BCOE | SL5 BOURNS A308 - OFFICE PATCH & PAINT | PATCH & PAINT |  | A0308 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 44272 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000213 |  | 21P000213 | FALSE | BCOE | SL5 CHUNG HALL 0452 - PATCH AND PAINT NEW FACULTY | PATCH & PAINT |  | 452 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44376 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000207 |  | 21P000207 | FALSE | BCOE | SL5 BOURNS HALL A325 OFFICE - PATCH & PAINT INCOMING FACULTY | PATCH & PAINT |  | A0325 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44365 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000174 |  | 21P000174 | FALSE | BCOE | SL5 BOURNS HALL OFFICE B355 - PATCH & PAINT | PATCH & PAINT |  | B0355 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 44321 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000173 |  | 21P000173 | FALSE | BCOE | SL5 BOURNS HALL OFFICE B353 - PATCH & PAINT (POSS TOUCH UP) | PATCH & PAINT |  | B0353 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 44321 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000198 |  | 21P000198 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 409 - PATCH & PAINT (NEW FACULTY) | PATCH & PAINT |  | 409 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44351 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000189 |  | 21P000189 | FALSE | BCOE | SL5 CHUNG HALL 0355 - WALLS NEED TO BE PATCHED AND PAINTED | PATCH & PAINT |  | 355 | QUEUE TO START | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | PAUL DITTY |  | X |  | FALSE |  |  | 44343 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000011 |  | 21P000011 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 414 - PATCH & PAINT | PATCH & PAINT |  | 414 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 44025 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
21P000214 |  | 21P000214 | FALSE | BCOE | SL5 CHUNG HALL NEW FACULTY OFFICE 454 - PATCH & PAINT | PATCH & PAINT |  | 454 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44376 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000154 |  | 21P000154 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 455 - MINOR PATCH & PAINT TOUCH UP | PATCH & PAINT (NEW DEAN) |  | 455 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44288 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 150 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | ANDREA HILDAGO, SUSAN KOMURA | DAN LERMAN |  | 2 |  | FALSE |  |  | 43844 | Order material once permit is approved | 44361 | 44470 |  |  |  | 08/02/21, DL: The plans and permit are approved. This is a large project and it will consume our electricans for at least 4- weeks. At the current time we are working on completing several other projects. Once we are caught up on the noted projects, we will schedule the work. Paul Richardson is currently aware of the plan noted above.....7/15/21, DL: The engineering is complete. We submitted the plans and applied for the building permit last week. Once the permit is approved, we will order material and schedule the work…….5/14/21, DL: We are still working on the contract to be approved for the electrical engineer before we can proceed…….4/15/21, DL: We had a meeting with the engineer this week and we should be applying for a permit within the next three weeks…….3/1/21, DL: We will reach out to the electrical engineer this week…….1/19/21, DL: This project will require engineered plans. This is a priority 2 project. We will start the plans and permit process when all priority #1 projects are complete. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-09-01
22P000022 |  | 22P000022 | FALSE | CHASS | SL5 HUMANITIES A3414 - NAIL REMOVAL, PATCH, AND PAINT | PATCH & PAINT |  | 3414 | QUEUE TO START | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | PAUL DITTY |  | X |  | FALSE |  |  | 44406 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
20P000387 |  | 20P000387 | FALSE | CHASS | SL5 HMSS RM 3610 - PLEASE PATCH AND PAINT WALL | PATCH & PAINT |  | 3610 | QUEUE TO START | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | PAUL DITTY |  | X |  | FALSE |  |  | 43892 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
20P000384 |  | 20P000384 | FALSE | CHASS | SL5 CHASS INTS 3111A - PATCHING HOLES AND PAINTING THE WALLS | PATCH & PAINT |  | 3111A | QUEUE TO START | Juliet McMullin | Cindy Williams | LESLIE ANN GERRETSE |  | PAUL DITTY |  | X |  | FALSE |  |  | 43888 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
20P000321 |  | 20P000321 | FALSE | CHASS | SL5 UNIV THEATRE 400A - PAINT LOBBY | PATCH & PAINT |  | 0400A | QUEUE TO START | Juliet McMullin | Cindy Williams | ALBERT FETTER |  | PAUL DITTY |  | X |  | FALSE |  |  | 43845 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
21P000190 |  | 21P000190 | FALSE | CHASS | SL5 PSYCHOLOGY 3119 - PATCH & PAINT / REMOVE WALL FIXTURE | PATCH & PAINT / REMOVE WALL FIXTURE |  | 3119 | QUEUE TO START | Juliet McMullin | Cindy Williams | AERIKA LOYD |  | PAUL DITTY |  | X |  | FALSE |  |  | 44343 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000058 |  | 21P000058 | FALSE | CHASS | SL5 HUMNITIES 3413 (DEAN SUITE) NAIL REMOVAL, PATCH, AND PAINT | PATCH & PAINT |  | 3413 | QUEUE TO START | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | PAUL DITTY |  | X |  | FALSE |  |  | 44068 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS BUILDING | 3009 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 43749 | [6 empty] | 05/05/21 O-ANS: Updated contact info from Dr. Wudka. 05/05/21 O-ANS: Multiple failed attempts to contact requestor to schedule work. Project placed on HOLD and emailed CNAS partner to continue to hold or cancel. 02/03/21 O-ANS: Reminder email sent to customer that PAINT ONLY portion would be completed and not the door removal at this time. Customer can resubmit request in next prioriization cycle…. 11/06/20 O-JLO: Emailed requestor and alternate regarding paint portion only, and that door/drywall removal will not occur during this time …. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. FS to confirm with customer that we can only complete the painting at this time but not the removal of the door…. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure." | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | 0 | 2019 | 2021-09-01
21P000157 |  | 21P000157 | FALSE | CNAS | SL5 PHYSICS 1119 - PATCH AND PAINT FOR NEW HIRE | PATCH & PAINT |  | 1119 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | PAUL DITTY |  | X |  | TRUE |  |  | 44292 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000151 |  | 21P000151 | FALSE | CNAS | SL5 SPIETH HALL 3310 - NEW FACULTY OFFICE - PATCH & PAINT | PATCH & PAINT |  | 3310 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | TRUE |  |  | 44286 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000155 |  | 21P000155 | FALSE | CNAS | SL5 OLMSTED 1342 - NEW FACULTY ARIVAL CARPET CLEAN / PATCH/PAINT | CARPET CLEAN / PATCH & PAINT |  | 1342 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | SOPHIA JURISCH |  | PAUL DITTY |  | X |  | TRUE |  |  | 44288 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000134 |  | 21P000134 | FALSE | CNAS | SL5 LIFE SCIENCES 2550 - CONF ROOM PATCH & PAINT | PATCH & PAINT |  | 2550 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | FALSE |  |  | 44259 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 43794 | [6 empty] | 05/06/21 O-ANS: Updated contact person info from Dr. Wudka and reaching out to coordinate. 5/05/21 O-ANS: Multiple failed attempts to contact requestor to schedule work. Project placed on HOLD and emailed CNAS partner to continue to hold or cancel. 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-09-01
21P000212 |  | 21P000212 | FALSE | CNAS | SL5 LIFE SCIENCES 0418D - PAINT CEILING, DOOR, DOOR FRAME | PATCH & PAINT (RESEARCH RELATED) |  | 418D | QUEUE TO START | Kathryn Uhrich | Jose Wudka | DIERK BIGGS |  | PAUL DITTY |  | X |  | FALSE |  |  | 44376 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000162 |  | 21P000162 | FALSE | CNAS | SL5 ENTOMOLOGY 0282 - PAINT NEW FACULTY MEMBER'S OFFICE | PAINT NEW FACULTY MEMBER'S OFFICE |  | 0282 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 44300 | [12 empty] | Winter 2021 | FS | 0 | 2021 | 2021-09-01
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT | PATCH & PAINT |  | 317 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | FALSE |  |  | 43879 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
20P000401 |  | 20P000401 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 FS ANNEX B 5 & 6 - PAINT SUPERVISORS OFFICE | PATCH & PAINT |  |  | QUEUE TO START | Susan Marshburn | Da Lan Dinh | MARK JONES |  | PAUL DITTY |  | X |  | FALSE |  |  | 43903 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
20P000282 |  | 20P000282 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 PIERCE HALL 3374 - RENOVATE GA CLASSROOM SUMMER 2020 | Project to renovate GA classroom in Pierce Hall for prioritization and execution in Summer 2020. |  | 3374 | QUEUE TO START | Susan Marshburn | Da Lan Dinh | DA LAN DINH |  | Paul Ditty |  | X |  | FALSE |  |  | 43839 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-09-01
21P000211 |  | 21P000211 | FALSE | GRAD DIV | SL5 UNIV OFFICE BLD 0144 - PATCH & PAINT | PATCH & PAINT |  | 144 | QUEUE TO START | Shaun Bowler | Kennett Lai | CARLOS RIVAS |  | PAUL DITTY |  | X |  | FALSE |  |  | 44371 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000215 |  | 21P000215 | FALSE | SoB | SL5 ANDERSON 0202 - PATCH/PAINT NEW HIRE | PATCH & PAINT |  | 202 | QUEUE TO START | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | PAUL DITTY |  | X |  | TRUE |  |  | 44377 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000144 |  | 21P000144 | FALSE | SOM | SL5 WEBBER HALL 1116A - SHELVING REMOVED /PATCH & PAINT | SHELVING REMOVED /PATCH & PAINT |  | 1116A | QUEUE TO START | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | PAUL DITTY |  | X |  | FALSE |  |  | 44272 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000204 |  | 21P000204 | FALSE | SOM | SL5 WEBBER HALL 1126A - PAINT/PATCH | PATCH & PAINT |  | 1126A | QUEUE TO START | Deborah Deas | Deborah Trujillo | CLARK HAPEMAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 44363 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
22P000027 |  | 22P000027 | FALSE | SOM | SL5 WEBBER HALL 1143 - PAINT/PATCH | PATCH & PAINT |  | 1143 | QUEUE TO START | Deborah Deas | Deborah Trujillo | CLARK HAPEMAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 44363 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
21P000191 |  | 21P000191 | FALSE | SOM | SL5 ORBACH LIB BASEMENT - PAINT WALL AT NEW SIM CENTER | PATCH & PAINT |  | BASEMENT | QUEUE TO START | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | PAUL DITTY |  | X |  | FALSE |  |  | 44344 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-01
22P000008 |  | 22P000008 | FALSE | VC-RED | SL5 MRB VARIOUS LAB SUPPORT - IACUC INSP TINTED WINDOWS NEEDED | ER IACUC INSPECTION- TINTED WINDOW NEEDED ON LAB SUPPORT ROOMS. ORIGINAL SERVICE REQUEST 22S000637 See list of rooms for window tint request. Korzus 1204E 1204F 1212A 1212B 1229B Zagha 1212A 1212B 1204F 1204E 1231C Abdulrazak 2204A 2204G 2204F 2208B Binder 3214 3218 3215 Cho 3216 3219 Tiwari- Woodruff 3204G Hickmott 2221 Zheng 2225 2213-C |  |  | QUEUE TO START | Rodolfo Torres | Laura Manor | TARA BARTHOL |  | Enrico Baez |  | R1 |  | TRUE |  |  | 44391 | [6 empty] | 07/27/21 EBZ: Project to begin 07/29/21. |  | Enrico Baez |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-09-01 |  | 1
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES | PATCH & PAINT |  | 200 | QUEUE TO START | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | X |  | FALSE |  |  | 43868 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
21P000088 |  | 21P000088 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BUILDING 100D - FILL HOLES/PAINT | PATCH & PAINT |  | 0100D | QUEUE TO START | Brian Haynes | Cathy Eckman | WILLIAM RALL |  | PAUL DITTY |  | X |  | FALSE |  |  | 44116 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
20P000372 |  | 20P000372 | FALSE | VC-STU AFF | SL5 HEALTH SERVICES 391 - OFFICES PAINTED AND CONFERENCE ROOM | PATCH & PAINT |  | 391 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | X |  | FALSE |  |  | 43881 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
20P000374 |  | 20P000374 | FALSE | VC-STU AFF | SL5 HEALTH SERVICES 334 - OFFICES PAINTED AND CONFERENCE ROOM | PATCH & PAINT |  | 334 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | X |  | FALSE |  |  | 43881 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-01
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | Re-bid | Gerry Bomotti | Sharyl Murdock | Daneca Stevens |  | Daneca Stevens | 2 |  |  | FALSE | 507364 |  | 43676 | Award Contract | 44501 | 44562 | [10 empty] | PD&C | 0 | 2019 | 2021-09-01
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | Re-bid | Gerry Bomotti | TBD | Sharyl Murdock |  | John Franklin | 15 |  |  | FALSE | 33099342.06 |  | 42353 | Award Contract | 44531 | 45474 | [10 empty] | PD&C | 0 | 2015 | 2021-09-01
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Blythe Wilson | 1 |  |  | FALSE | 3350000 |  | 42719 | Design Builder Prequalification | 44830 | 45462 | [10 empty] | PD&C | 0 | 2016 | 2021-09-01
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 17 |  |  | FALSE | 2586581 |  | 43410 | Complete Review | [12 empty] | PD&C | 0 | 2018 | 2021-09-01
3471 | 3471 |  | FALSE | VC-STU AFF | HUB Electrical Sub Meter Installation | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Bidding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 4 |  |  | FALSE | 200000 |  | 43332 | Award Contract | 44470 | 44501 | [10 empty] | PD&C | 0 | 2018 | 2021-09-16
21P000173 |  | 21P000173 | FALSE | BCOE | SL5 BOURNS HALL OFFICE B353 - PATCH & PAINT (POSS TOUCH UP) | PATCH & PAINT |  | B0353 | CANCELED BY CLIENT | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 44321 | [6 empty] | CANCELLED BY REQUESTOR 9/13/21 PDY |  | PAUL DITTY |  |  | 2021-09-13 | FY 21-22 | FS | 0 | 2021 | 2021-09-16 | FY 21-22
20P000211 |  | 20P000211 | FALSE | CHASS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | Install keyless entry system for door to Arts Building RM 54 | ARTS | 54 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 | R3 | FALSE |  |  | 43776 | [6 empty] | 1/19/21, DL: Enrico will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment installation. 8/5/20, DL: This Project is on hold until further notice……. | 2020-01-20 | Enrico Baez | 1/19/21, EB: Per Paul R., This project is canceled………….Provide new panel, power supply and door hardware for 2 doors. Prox reader only. | YES | 2021-01-19 | Winter 2021 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
20P000046 |  | 20P000046 | FALSE | CNAS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | HOMER D. CHAPMAN HALL | 0001 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Enrico Baez |  | R2 |  | FALSE |  |  | 43677 | [6 empty] | 05/12/21 O-ANS: Per email from Bill Sutton, this project was requested to be cancelled. 1/19/21, DL: Enrico B. will manage this priject………….11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Install wireless access controls systems at front and rear entry doors. | YES | 2021-05-12 | Winter 2021 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
19P000659 |  | 19P000659 | FALSE | SOM | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43627 | [6 empty] | 08/05/20 O-ANS: Canceled by client (Cynthia Carolina) via email with Ron Veloz. 8/5/20, DL: Dan to follow -up with customer…………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "remove 330 from work order / update project details / Update: Furniture on order 3.30.2020 - delivery tbd" |  | Enrico Baez | TBD | NO | 2020-08-05 | Fall 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000210 |  | 20P000210 | FALSE | BCOE | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | Reduce noise. Replace doors with solid core doors and install an Acoustic Door Seal Kit. | CHUNG HALL | 224 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43774 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……. | 2020-02-11 | Enrico Baez | Removal of the existing double doors and door hardware, install new solid core double doors with continuous hinges, install new acoustical jamb seals, threshold seal and a surface mounted Automatic Door Bottom utilizing a flat spring mechanism, which activates when closing the door, lowering a neoprene seal insert against the floor or threshold to create a sound seal. Install acoustic double door astragals with seal. Reinstall all existing door locksets, and door closers. Quote received from Brad Aduddell-American Door to perform this work. Quote & Specs are available in the project folder. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
19P000624 |  | 19P000624 | FALSE | BCOE | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | Refurbish Room-Student Space, | BOURNS | A0346 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43600 | Pending information from Susanna | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Susanna is working on a cubicle layout. Once we have the information from her. We will schedule the work………… | 2019-11-07 | Enrico Baez | Remove all lower cabinets in room A0346 and all lower cabinets and mail boxes in Rm A0304 | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000039 |  | 20P000039 | FALSE | BCOE | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE |  | BOURNS | A0318 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 4 |  | FALSE |  |  | 43598 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……..09/19/19 O-ANS: HOLD FOR WINTER 2020 PER CUSTOMER (LOUIS SANDOVAL) REQUEST. EMAILED PAUL DITTY TO CONFIRM. PAUL STATED THIS IS NON-PAINT PROJECT B/C SCOPE OF WORK INCLUDES CARPENTERS AND ELECTRIC SHOPS. |  | Paul Ditty |  |  | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
19P000427 |  | 19P000427 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | Install Power and TV bracket, move white board | CHUNG HALL | 453 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43468 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold……… | 2019-09-18 | Enrico Baez | Install Power and TV bracket, remove white board and relocate , patch and paint wall prior to installing | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
19P000502 |  | 19P000502 | FALSE | BCOE | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | Install Electrical power & TV bracket.for a 75" TV to mount in CS 342. | CHUNG HALL | 444 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | RICHARD BAIN |  | Dan Lerman |  | R3 |  | FALSE |  |  | 43515 | Schedule the work. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This project is on hold……………3/25/20, DL: Work orders are produced. I will work on scheduling the work when we return back to work…….. | 2019-09-17 | Enrico Baez | Install Electrical power & TV bracket. Excludes network/data back box and stub up to ceiling. | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
20P000183 |  | 20P000183 | FALSE | CHASS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | Install side walk | HUM & SOC SC | 1202 | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 43756 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Also Existing door is compliant and there are other accessible exits to the building… 8/5/20, DL: This Project is on hold until further notice……. | 2019-11-13 | Enrico Baez | Construct Side walk. ADA compliance not required. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  | R7 |  | FALSE |  |  | 43523 | We Need an FAU # | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced. We will schedule the work when we return from campus closure………11/11/19, DL: Project is in the queue to start but we do not have an FAU# as this is a recharge project. I sent Enrico and James an email requesting the FAU#. Once we have an FAU #, I will work on scheudling the work…..10/1/19, DL; Enrico is wtill working on estimate. | 2018-10-19 | Enrico Baez | E. Baez 1. Provide power in ceiling for projector. 2. Install projector center in room between two 4ft light fixtures. 3. Install 2 duplex outlets in 4S box on South West corner of room 4. Remove existing screen. 5. Install new screen centered on South wall. Extend power from existing screen to new screen location. 6. Use existing screen power switch to control new screen. | YES | 2020-11-19 | Summer 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
20P000188 |  | 20P000188 | FALSE | LIBR | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 |  | ORBACH LIB | 204 | CANCELED BY FS | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43761 | Obtain floor covering samples | [5 empty] | 11/19/20 O-ANS: Declined to move forward by FS Admin but may revisit in future prioritization period. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: We are working on floor covering samples that will work for the space. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000197 |  | 20P000197 | FALSE | VC-RED | SL5 UOB 210 - SOUND PROOF INSTALLATION |  | UNIV OFC BLD | 210 | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43762 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000047 |  | 20P000047 | FALSE | VC-RED | SL5 ADVANCED NEUROIMAGING | NEEDING TO TAKE DOWN OVERHEAD CABINETRY AND REPLACE WITH SOME KIND OF SHELVING TO OPTIMIZE SPACE. LOOKING FOR AN ESTIMATE AND A PLAN. | ADV NEURO |  | CANCELED BY FS | Rodolfo Torres | Laura Manor | CHELSEA EVELYN |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43677 | pending material delivery. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice…….3/23/20, DL: Shelves are ordered. We will schedule the work when we return from the campus closure……….1/15/20 O-DHN: Emailed Status Report to customer…...1/14/20, DL: We waiting for a revised quote from the vendor as there quote was not complete. We will process the quote for a PO# when we receive the correct quote……. 11/11/19, DL: Need to review scope with Ron as the shelving system is a special order item with a 3- month lead time….. | 2019-09-24 | Enrico Baez | Remove 5'-0" x3'-0" upper cabinet, and soffits. Patch and paint walls to match the existing grey . Install customer furnished adjustable shelf. | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43340 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice. | 2018-09-27 | Enrico Baez |  | YES | 2020-11-19 | Fall 2018 | FS | 0 | 2018 | 2021-09-16 | FY 20-21
20P000309 |  | 20P000309 | FALSE | VC-UNIV ADV | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES |  | 1955 CHICAGO | 200 | CANCELED BY FS | Peter Hayashida | Naysia Caldwell | SARAH KARSON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 43840 | [6 empty] | 12/16/20 O-ANS: Canceled by FS - Project location not serviced as FS CORE location and reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Please retain project # as reference. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2020-12-16 | Spring 2020 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
21P000109 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | PATCH, PAINT & NEW FLOORING |  | 1146 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | PAUL DITTY |  | X |  | TRUE |  |  | 44153 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | FY 21-22 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000208 |  | 20P000208 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | Men's locker room refresh | ATH DANCE | 50 | COMPLETE | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND | EUGENE HUTCHINSON | Dan Lerman |  | 1 |  | FALSE |  |  | 43773 | [6 empty] | 1/28/21, DL: Project is complete. Paul will schedule the paint once he is back on projects……….1/19/21, DL: We will schedule the balance of the paint before the students return back to campus………..9/30/20, DL: The work is complete except for the paint……………..8/5/20, DL: The work is almost complete.……. |  | Dan Lerman |  |  | 2021-01-28 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000253 |  | 20P000253 | FALSE | BCOE | SL5 BOURNS HALL LAB B156 - EXHAUST SYSTEM | EXHAUST SYSTEM | MARLAN & ROSEMARY BOURNS HALL | B0156 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 43810 | Demolish cabinets and schedule paint and flooring | 44256 | 44330 |  |  |  | 4/30/21, DL: This project is 100% Complete :) ……… 4/15/21, DL: The power is complete. The exhaust is scheduled to be complete with in the next 30 days……….3/15/21, DL: The new dedicated electrical outlet is complete. We are also in the process of ordering the exhaust vents for the printer…………..2/16/21, DL: Plans were submitted 2- weeks ago. We received the plans back last week with corrections needed. We will resubmit the plans back to the building official by the end of the week….1/19/21, DL: We will start working on the plans for this project in the next two weeks. We will start this project once the permit is approved…… |  | Enrico Baez |  |  | 2021-04-30 | Winter 2021 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000135 |  | 20P000135 | FALSE | BCOE | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MS&E Rm 0075 - 3 Ph208 Power CHW S&R WATER PPMS TOOL, Install Chilled water loop & power in clean room 075. | MAT SCI ENGR | 75 | COMPLETE | Christopher Lynch | Todd Ambriz | MARK HEIDEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43727 | Plans and permit | [5 empty] | 9/30/20, DL: This project is complete……..8/5/20, DL: This is in progress…….3/25/20, DL: We will work on plans and permits when we return back from the campus closure……. | 2020-02-18 | Enrico Baez | Intake/SOW: Install 208V 3ph power & disconnect/safety switch and one 3/4" Chilled water loop (Supply and Return) in the MSE southeast corner of clean room 0075. Create a 4" diameter pass-thru hole from this corner of room 0075 into the adjacent room 0071. FS to provide power and cooling to a compressor which will connect through the wall to the PPMS system with cryogenic helium lines. | YES | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | COMPLETE | Christopher Lynch | Todd Ambriz | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43594 | Finish Gas cabinet installation | 43731 | 43868 |  |  |  | 8/5/20, DL: This Project is Complete…….3/25/20, DL: Project is 95% complete. We will install the fire sprinkler and exhaust duct to the gas cabinet when we return from the campus closure………..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Plans were approved and material is ordered. We are hopeful the material will arrive the 2nd or 3rd week in January. Once material is on site we will schedule the work…… 11/19/19 DH: Emailed Status Report to customer……10/16/19, DL: This project is 90% Complete. We are working on plans and permits for the two snorkels……….10/1/19, DL: This project is almost complete. We will be complete in the next 4- weeks except the Snorkel……….. 9/13/19, DL; The paint of the cabinets is scheduled for this week along with the power. We will submit the plans for the snorkel this with in the next two weeks…….9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Enrico Baez | SOW, Patch& Paint Walls, replace plexi glass on shelving, powder coat metal shelving & cabinets, clean & polish or replace chem sinks, polish counter tops, Validate all gas, water, drains, DI water & utilities. Replace damaged and dirty ceiling tiles, relamp as needed. Strip & wax floor. Dan L is requesting vendor pricing to restore finishes. | YES | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000221 |  | 20P000221 | FALSE | BCOE | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | COMPLETE | Christopher Lynch | Todd Ambriz | HONG XU | KEVIN FREEDMAN | Dan Lerman |  | 3 |  | FALSE |  |  | 43784 | [6 empty] | 1/19/21, DL: This project is 100% Complete……..9/30/20, DL: We are in the process of finishing up a few other projects. Once they are complete, we will schedule the work….8/5/20, DL: Plans are approved and we will start the work in the next 2-6 weeks…….. | 2020-02-25 | Enrico Baez | Install Plywood and supports. Paint Plywood black. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
21P000019 |  | 21P000019 | FALSE | BCOE | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | Bourns Office A305 - Install Plank Floor | MARLAN & ROSEMARY BOURNS HALL | A305 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | 3 | 2 | TRUE |  |  | 44032 | This project is Complte. | 44316 | 44337 |  |  |  | 6/2/21, DL: This project is complete…4/30/21, DL: This project started this week. The paint will be complete next week. The floor will be installed in about two weeks…………..4/1/21, DL: We will schedule the work with in the next three weeks. We are only doing this work early as the two primary trades are available. The damaged window covering will be replaced by a vendor…………..1/19/21, DL: This a priority 3 project. We will start this project when all priority #2 projects are complete………..1/14/21 O-ANS: Updated prioritization to #3 (from #2) per org leadership request. |  | Enrico Baez |  |  | 2021-06-02 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000363 |  | 20P000363 | FALSE | BCOE | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | Paint Only | WINSTON CHUNG HALL | 433 | COMPLETE | Christopher Lynch | Todd Ambriz | MANGLAI ZHOU | FARIBORZ KARGAR | PAUL DITTY |  | X |  | TRUE |  |  | 43874 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/22/21. 2/22/2021 B-SBT pull tape, install plates, clean base/room. 2/19/2021 B-SBT prime and paint room. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2021-02-22 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000449 |  | 20P000449 | FALSE | BCOE | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | Paint Only - Chung Hall, Fourth Floor, Room 461 Patch & Paint: At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. Follow up with fresh paint. Thank you. | CHUNG HALL | 461 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43993 | [6 empty] | 01/19/21 O-ANS: Complete per technician updates and closed project. Completed by Wendy M. 11/09 -SC |  | Paul Ditty |  |  | 2020-11-09 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
21P000014 |  | 21P000014 | FALSE | BCOE | SL5 BOURNS HALL OFFICE A149 - PATCH & PAINT HOLES ON WEST WALL | PATCH & PAINT |  | A0149 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 44026 | [6 empty] | 08/13/21 O-ANS: Project complete per Paint Crew. 08/13/21 D-JPO: cleaned up job done. 08/12/21 D-JPO: sanded spot primed and spot painted two walls. 08/10/21 D-JPO: patched and masked |  | PAUL DITTY |  |  | 2021-08-13 | FY 21-22 | FS | 0 | 2020 | 2021-09-16 | FY 21-22
21P000174 |  | 21P000174 | FALSE | BCOE | SL5 BOURNS HALL OFFICE B355 - PATCH & PAINT | PATCH & PAINT |  | B0355 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 44321 | [6 empty] | 09/13/21 O-ANS: Complete per Paint Supervisor. |  | PAUL DITTY |  |  | 2021-09-13 | FY 21-22 | FS | 0 | 2021 | 2021-09-16 | FY 21-22
20P000310 |  | 20P000310 | FALSE | BCOE | SL5 BOURNS A-WING A129 - PATCH & PAINT | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. | MARLAN & ROSEMARY BOURNS HALL | A0129 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 43840 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty. 2/3/2021 B-SBT Patch holes, mask room, sand patches, prime room. 2/4/2021 B-SBT paint room, pull masking, clean room. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2021-02-04 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000413 |  | 20P000413 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR ROOM A159A - EAST WALL PATCH & PAINT | PATCH & PAINT |  | A0159A | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 43930 | [6 empty] | 08/13/21 O-ANS: Project complete per Paint Crew. 08/12/21 D-JPO: sanded spot primed and spot painted entire room. 08/10/21 D-JPO: patched and masked |  | PAUL DITTY |  |  | 2021-08-13 | FY 21-22 | FS | 0 | 2020 | 2021-09-16 | FY 21-22
20P000448 |  | 20P000448 | FALSE | BCOE | SL5 CHUNG HALL ROOM 216 - PATCH & PAINT | At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. |  | 216 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | X |  | TRUE |  |  | 43993 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  |  |  |  | 2021-05-11 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
21P000037 |  | 21P000037 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | Paint Only | CHUNG HALL | 427 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44043 | [6 empty] | 01/19/21 O-ANS: Paint complete per technician and closed project. 11/30/20 B-SBT: repatch & Paint north wall |  | Paul Ditty |  |  | 2020-11-30 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000450 |  | 20P000450 | FALSE | BCOE | SL5 CHUNG HALL ROOMS 217, 218, 219 - PATCH & PAINT | Please patch and paint these adjoining rooms within suite 216. |  | 217, 218, 219 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | X |  | TRUE |  |  | 43994 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  |  |  |  | 2021-05-13 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | COMPLETE | Kim Wilcox | TBD | ALEXIS RAMBAUD |  | Dan Lerman |  | 1 | 0 | FALSE |  |  | 43445 | schedule the work | 43486 | 43551 |  |  |  | 8/5/20, DL: This project is complete…………3/25/20,DL: Doors are scheduled to arrive the second week in April……2/19/20 O-DHN: Emailed Status Report to customer……2/18/20, DL: Work is complete except for Door and final deep cleaned I do have final stain samples from the vendor. I need to verify color……… We will complete the project when the doors arrive……….1/14/20, DL: Plans are approved, PO# is cut for the ordering of the custom doors, we are currently scheduled to start the work on or shortly after 1/21/20,. Karim understands that we will start and finish the project but we will not be able to install the door until the door arrives on site. There is a minimum of 6-8 week lead time on the door delivery………….12/16/19, DL: Plans are still in plan check review. I sent the building department an email asking for a startus update today…….10/16/19, DL; Plans were submitted to our building official this week for plan check review and a permit……9/16/19, DL; Guther will work on plans in the next three weeks. Once plans are complete, we will proceed with the permit process… | 2018-12-20 | Enrico Baez | SOW: Wall: Construct a metal stud framed wall with drywall up to hard ceiling (ceiling has 12x12 glue up ceiling tiles). Hardware: Install new lockset & keys are required.***** French Door: Install new stain grade birch door with full lite. Door and finish to match the existing office doors.***** Hard Ceiling: * Ceiling is 8’-0” A.F.F. + - with 12x12 glue up ceiling tiles. Work may require a new access panel if access to space above is needed. The 12x12 glue up ceiling tiles may need to be removed where the new wall is constructed.***** Flooring: The existing flooring will remain. Install rubber base to match existing.***** Painting, Taping & Sanding: Taping sanding and painting is required at the new wall and connecting walls.***** HVAC: May require modifications to split the existing supply air to accommodate the open office space.***** Electrical: Provide light switch at new office, power(new or relocate); add and or relocate electrical and voice/data outlets required for a standard office.***** Lighting: Provide a new light switch/circuit near office entrance. The existing 2x4 fixture is on main lighting circuit and will require lighting circuit modifications. Verify if the existing lighting is sufficient for the proposed office. Field verify if additional lighting is required.***** Fire Alarm: Provide a new Smoke/chime detector at new office area, confirm requirements. | YES | 2020-08-05 | SPRING 2019 | FS | 0 | 2018 | 2021-09-16 | FY 20-21
20P000370 |  | 20P000370 | FALSE | CHASS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | SPACE RENOVATION PROJECT | GORDON S. WATKINS HALL | 1311 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 43880 | This Project is complete…. | 44274 | 44379 |  |  |  | 4/30/21, DL: The paint is complete. The floor covering is ordered and will be installed in about two weeks………………4/15/21, DL: Asbestos, electrical, and drywall are complete. Painters are in the space prepping the walls…..4/1/21. DL: Asbestos abatment is scheduled to be complete by this Monday. We will start the framing and electrical next week……………..3/1/21, DL: Plans were approved. We now need to send our 14- day notice to the AQMD and schedule the demolition……..2/16/21, DL: Plans were submitted with building permit last week. We are now in the plan check review process………1/19/21, DL: We will start working on the plans for this project in the next three weeks. We should have plans to submit for plan check review in the next 5- weeks……….. |  | Enrico Baez |  |  | 2021-04-30 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000214 |  | 20P000214 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | Remove walls and doors in spaces 2139 A,B and C. | PSYCHOLOGY1 | 2nd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43776 | Obtain building permit | [5 empty] | 9/30/20, DL: This Project is Complete…………8/5/20, DL: we will submiot plans this week.…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Plans were submitted for a permit on 2/12/20. Once plans are approved, we will order the material and schedule the work……… | 2020-01-10 | Enrico Baez | **************************************SCOPE********************************** 1.) Remove doors, and jambs 2139A, 2139B, 2139C. 2.) Remove drop ceiling in 2139A, 2139B, 2139C and repair as needed. 3.) Remove cabinets in 2139A, 2139B, 2139C. 4.) Remove walls between 2139A & B, and remove walls between 2139B & C. 5.) Change light fixture to match existing. 6.) Repair walls as needed. 7.) Patch and paint as needed. 8.) Replace carpet and base in 2139A, 2139B, 2139C and 2139 common area. 9.) HVAC duct work in individual spaces can be removed and simplified. | YES | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000215 |  | 20P000215 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | Remove Vaughan wall seperating Olmsted 3349/3351.Add 4 single gang outlets and 2, 2gang outlets. | PSYCHOLOGY1 | 3rd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43776 | [6 empty] | 1/19/21, DL: This project is 100% complete…………9/30/20, DL: Plans were approved, we had the Vaughn Wall tested for Asbestos containing material. Once we have the results, we will schedule the work………….8/5/20, DL: We will submit plans by this Friday for a building permit | 2020-02-24 | Enrico Baez | 2/24/2020 E. Baez - 1.Remove Vaughan wall and electrical circuit in wall. 2. Add 4 Single Gan outlets and 2, 2gang outlets. 3. Patch vinyl plank flooring from removed wall and safe. 4. Remove panel in 2249 with wall paper on it next to window. 5. Remove handle set to 3351, install blank, render door inoperable. 6. Repair T-Bar ceiling as needed. 7. Patch and paint walls. 8. Coordinate with ITS for data line for 8 computers. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000213 |  | 20P000213 | FALSE | CHASS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS |  | CHASS INT S | 2117A, 2117C, 2117D, 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43777 | approved permit | 43893 | 43911 |  |  |  | 8/5/20, DL: This Project is Complete……………..2819/20 O-DHN: Emailed Status Report to customer…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have a contract, we will order the material and schedule the work………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Plans are complete and submitted for building permit. We are also working on the contract. Once the plans are approved and the contract is complete, we will schedule the work………. |  | Enrico Baez |  |  | 2020-08-05 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
20P000462 |  | 20P000462 | FALSE | CHASS | SL5 HMSS 2001 - PAINT OFFICE / CLEAN FLOOR NEW FACULTY HIRE | Patch/paint to existing color for faculty new hire | HUMANITIES BUILDING | 2001 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | Paul Ditty |  | X |  | TRUE |  |  | 44000 | [6 empty] | 03/19/21 O-ANS: Project complete per Paul Ditty. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  | 2021-03-19 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
21P000110 |  | 21P000110 | FALSE | CHASS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. | GORDON S. WATKINS HALL | 2146 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 44153 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000403 |  | 20P000403 | FALSE | CHASS | SL5 OLMSTED 232 - PAINT OFFICE | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). | JOHN W. OLMSTED HALL | 2321 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | MELISA VICARIO | Paul Ditty |  | X |  | TRUE |  |  | 43903 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/11/21. 02/11/21 D-JPO: finished sanding water damage spot primed painted room 2 coats pulled tape vacuumed complete. |  | Paul Ditty |  |  | 2021-02-11 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000469 |  | 20P000469 | FALSE | CHASS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 222 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | SUSAN KOMURA | PAUL DITTY |  | X |  | TRUE |  |  | 44005 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/12/21. |  | Paul Ditty |  |  | 2021-02-12 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000453 |  | 20P000453 | FALSE | CHASS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | Paint Only - Please patch/paint to existing color office for faculty new hire. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 142 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty…..6/18/20 o-dms: trans from 20w028936 to Project Phase - custodial please clean office floor for faculty new hire |  | Paul Ditty |  |  | 2021-04-05 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000446 |  | 20P000446 | FALSE | CHASS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. | CHASS INTERDISCIPLINARY NORTH | 4047 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 43986 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/12/21. |  | Paul Ditty |  |  | 2021-02-12 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000463 |  | 20P000463 | FALSE | CHASS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 | HUMANITIES BUILDING | 2000 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/11/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000464 |  | 20P000464 | FALSE | CHASS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) | HUMANITIES BUILDING | 3001 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44000 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/09/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUMANITIES BUILDING | 3210 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 44006 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/10/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
21P000111 |  | 21P000111 | FALSE | CHASS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. | GORDON S. WATKINS HALL | 2144 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 44153 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
19P000485 |  | 19P000485 | FALSE | CNAS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | HOMER D. CHAPMAN HALL | 9 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43494 | This Project is Complete.. |  | 44267 |  |  |  | 4/1/21, DL: This Project is Complete…………..3/15/21,DL: Bill S. is still working on obtaining the air flow monitor. Once the air flow monitor arrives, we will complete the installation and Bill will be able to have the fume hood certified by a 3rd party vendor…………3/1/21, DL: We need to install the fire extinguisher and air monitor. I sent Bill S. an email asking him if he ordered the air monitor as we do not have one. I also contact EH&S and made them aware that we will be commisioning the fume hood in the very near future…..2/16/21, DL: Plumbing is complete. We will now start the exhasut vent, electrical and then seismically anchor the fume hood…………2/1/21, DL: We have had a delay with the plumbing and it is our goal to be complete on or before 3/1/21…………1/10/21, DL: This project is almost complete. This project will be complete in the next 30- days…………9/30/20, DL: Fume Hood demolition and abatement will be completed on 10/2/20. Fume hood install should be coplete in mid Novemeber……8/5/20, DL: We will submit plans this week. Once plans are approved, we will schedule the work……………Work orders are produced. We need to work on plans and permits once we return. | 2020-02-10 | Enrico Baez | Disconnect, cap and safe off the existing utility services. Provide the necessary abatement services to properly remove the fume hood from the site and deliver to the campus surplus yard. Install one new department furnished fume hood. Abatement Services: Provide the necessary abatement services to perform all utilities disconnections and floor repair. Floorcovering: Patch and or repair as necessary to match or provide a close match. Install rubber base. Access Control: Survey and adjust the entry door closer to increase latch pull to allow the door to closer completely. Patching and painting: Patch and paint wall at the old fume hood location. Mechanical: Disconnect metal duct, cap/safe off, reconnect/reconfigure new duct to accommodate the new fume hood. Electrical: Provide electrical disconnections and safe off. Reconnect/reconfigure power to the new fume hood. Plumbing: Disconnect Air, Gas, Vacuum, Cold water, and Drain, cap and safe off and reconnect/reconfigure service to the new fume hood. Resource Management: Properly remove the fume hood from the site and deliver to the campus surplus yard. | YES | 2021-04-01 | Spring 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000202 |  | 20P000202 | FALSE | CNAS | SL5 SKYE HALL 361 RENOVATION PROJECT | Renovete space for class room. | SKYE HALL | 361 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY | MELISSA GOMEX | Dan Lerman |  | 1 |  | FALSE |  |  | 43768 | pending permit approval | 43866 | 43917 |  |  |  | 9/30/20, DL: This Project is Complete……….8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Permits were approved. Demolition is complete…..1/15/20 O-DHN: Emailed Status Report to customer……..1/14/20, DL: Plans have been submitted for a building permit. Once plans are approved, it is our goal to complete the work by the beginning of spring quarter….. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
21P000009 |  | 21P000009 | FALSE | CNAS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | GLOVEBOX SYSTEM | CHEMICAL SCIENCES |  | COMPLETE | Kathryn Uhrich | Jose Wudka | NATASHA GONZALES |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 44020 | This project is complete….. | 44263 | 44309 |  |  |  | 6/2/21, DL; This project is complete……4/15/21, DL This project is complete. When the glove box arrives, we will make the final connections………..4/1/21, DL: Demolition, paint, electrical and venting is done for the glove box. The snorkel parts are ordered. The flooring is ordered and should be here next week. We will schedule the floor install once we have the material on site………….3/15/21, DL: We will demolish the cabinets this week. We will also schedule the paint and floor replacement. The venting for the glove box and snorkel should be ordered this week………3/1/21, DL: The plans were approved last week. We will try and schedule demo this week or early next week……..2/16/21, DL: We submitted plans for building permit but corrrections are needed. We contacted the glove box manufacture for follow-up questions and we are waiting to hear back from them. Once we have confirmation on the needed information, we will resubmit the plans back to the building official……….1/19/21, DL: we will submit plans this week or earlier next ……………. |  | Enrico Baez |  |  | 2021-06-02 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
21P000001 |  | 21P000001 | FALSE | CNAS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | NEW GROWTH CHAMBER PLACEMENT | HOWARD SAMUEL FAWCETT LABORATORY |  | COMPLETE | Kathryn Uhrich | Jose Wudka | LINDA WALLING |  | DAN LERMAN |  | 2 |  | TRUE |  |  | 43990 | This project is complete | 44306 | 44338 |  |  |  | 7/15/21, DL: This project is complete. Linda is requesting a sensored light switch which we will install under an SL6 work order………..4/30/21, DL: for most part this growth chamber is complete except the air curtain which is still not on site……………4/15/21, DL: This project is in progress. Linda will schedule the installation to take place in two weeks. We are waitng on the air curtain. This project should be 100% complete with in the next 4- weeks………4/1/21, DL: Plans were approved. We will try and start this project with in the next 3-weeks or sooner if possible…..3/1/21, DL: This was recently changed to a priority 2 project. Once plans are approved, we will work on the schedule noting, the schedule for this will work around pending priority 1 projects……2/16/21, LB: Changed to Priority 2 per Dan….1/19/21, DL: This is a priorty 3 project. We will start this project when all priority 2 projects are complete. |  | Enrico Baez |  |  | 2021-07-15 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 21-22
20P000144 |  | 20P000144 | FALSE | CNAS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A | ALFRED M. BOYCE HALL | 3432, 3432A, 3446, 3446A | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43734 | Install floor covering |  | 44309 |  |  |  | 4/30/21, DL: This Project is 100% Complete………..4/15/21, DL: The asbestos abatement is complete. The floor covering will be complete by the end of next week……………4/1/21, DL: Asbestos abatement is scheduled for April 8th - 12th. We will install the floor covering shortly after and deep clean the space. This project is on schedule to be complete on or near 4/20/21…………..2/16/21, DL: Project Is on schedule. Paint is 90% complete. Once paint is complete, we will schedule the floor repairs and final deep clean……… 2/1/21, DL: We are making good progress and are target date is still 3/14/21………….1/19/20, DL: This project is in progress and will be complete in the next 30- days………….9/30/20, DL: We have started a few items but we are waiting on Matt U. and the PI to remove their items so we can have access to the space. Once the space is cleared out, we will proceed with the work…………8/5/20, DL: We will start the work in the next 4-6 weeks. | 2020-02-18 | Enrico Baez | This project is 100% Complete… ;) Boyce 3432, 3446, 3436 and 3436A . Patch and paint 3432, 3432A, 3436, 3436A, 3446, 3446A. Reface/replace water damaged cabinets near sink (3446). Install GCFI outlets near sink (replace existing) (3446). Install panel cover for electrical panel box. Replace many burnt out bulbs in ceiling lamps. Replace broken chemical plexi-glass on bench shelves. | YES | 2021-04-30 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000445 |  | 20P000445 | FALSE | CNAS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 279 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | DAN LERMAN |  | 3 |  | TRUE |  |  | 43985 |  | 44308 | 44347 |  |  |  | 5/14/21, DL: This project is 100% Complete……4/30/21, DL: The floor will be installed tomorrow. The project will be 100% next week………………4/15/21, DL: The plumbing and electrical is complete. The painters will be done this week. The floor covering is ordered and will be installed with in two weeks…..4/1/21, DL: We will try and start this project with in the next three weeks…………3/15/21, DL: The building permit was approved today. We will work this project in to our schedule and we will schedule the work once we are ready to and in line with our other projects that are already in progress……….2/16/21, LB: Changed to Priority 3 per Dan…….1/19/21, DL: This is a priority 3 project. We will start the project when all priority 1 &2 projects are in process or almost complete… |  | Enrico Baez |  |  | 2021-05-14 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install electrical utilities for new equipment | PHYSICS BUILDING | 1132 | COMPLETE | Kathryn Uhrich | Jose Wudka | WENDI TAPIA |  | Dan Lerman |  | 3 |  | FALSE |  |  | 43543 | site visit with customer for review |  | 44281 |  |  |  | 4/15/21, DL: This project is 100% Complete……..4/1/21, DL: This project is complete except the sink drain and custodial. Custodial is scheduled to service the room in two weeks………3/15/21, DL: This project was supposed be be complete but we still have a plumbing drain assembly that is back ordered. We will connect the plumbing once the material arrives…………2/16/21, DL: New sink and faucet arrived, we will now schedule the install of the countertop and sink…………..1/19/21, DL: This project is in progress and will be complete with in 30- days………..9/30/20, DL: Plans were submitted for Plan Check review last week and we should have an update on the plan check review process soon………..8/5/20, DL: Need to meet with Kirk to verify electrical load. Once confirmed, we will work on plans for a permit. | 2019-10-15 | Enrico Baez | Install utilities for new equipment | YES | 2021-04-15 | Summer 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000320 |  | 20P000320 | FALSE | CNAS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | ACTIVATE VACUUM LINES | HERMAN T. SPIETH HALL | 1303 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | DAN LERMAN |  | 4 |  | FALSE |  |  | 43789 | Project is complete. | 44319 | 44358 |  |  |  | 7/15/21, DL: This project is complete……..6/2/21, DL: Electrical work is complete. The Plumbing shop will start to install the vacuum lines this Thursday. This project should be 100% complete by next Friday…….5/14/21, DL: The space was surveyed for hazardous material. Once we have the survey we will schedule work…………4/30/21, DL: Conducted site visit this week; we will survey the space for hazardous material before we conduct any work. We should start the work in about two weeks…………….1/19/21, DL: This is a priority 4 project. We will start this project when all all priority 3 projects are complete……….. |  | Enrico Baez |  |  | 2021-06-11 | Winter 2021 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | COMPLETE | Kathryn Uhrich | Jose Wudka | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 43332 | Work will be complete in 2 weeks | 43864 | 43903 |  |  |  | 8/5/20, DL: This project is complete……………..06/17/20, DL: This project should be complete with in the next two weeks……..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within two weeks. Once we have a contract, we will schedule the work……….1/15/20 O-DH: Emailed Status Report to customer……1/14/20, DL: Contracts is currently working on the contract. Once the contract is complete, we will order the material and schedule the work…………11/26/19, DL: Plans were approved. We will work on the construction contract. Once we have the notice to proceed, we will schedule the work……….10/15/19, DL: Sent PD&C and follow-up email on 11/11/19. We should have approved plans in the near future……10/30/19, DL: Sent PD&C an email asking for a status update on 10.30.19…… 10/16/19, DL; Plans are still in plan check. I sent the building official an email asking if any additional information is needed. This work will be completed by a contractor which means we need to allow time for the bid and contract process……… …………9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Enrico Baez | Request for Estimate to install three new FOB readers with electrified locksets. Work covered: Install one AC Fob Reader at door 2221 and one AC Fob reader at each Door 4231 & 4235. Connect card readers to the existing Hirsh ACP located in the IDF closet at each floor. 03/07/19: Scope revised to eliminate two FOB readers. Install one FOB reader at Genomics door 4231 only instead of all three rooms. | YES | 2020-08-05 | Fall 2018 | FS | 0 | 2018 | 2021-09-16 | FY 20-21
20P000248 |  | 20P000248 | FALSE | CNAS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT | Space Management has temporarily allocated Rooms 1223 and 1223-A in Webber Hall to CNAS. We need this lab cleaned and modified to accommodate relocating an existing (and active) lab. | HERBERT JOHN WEBBER HALL | 1223 + 1223-A | COMPLETE | Kathryn Uhrich | Jose Wudka | SHARYL MURDOCK |  | Dan Lerman |  | 5 | 4 | FALSE |  |  | 43796 | Project is Complete. | 44298 | 44347 |  |  |  | 6/2/21, DL: This project is complete……5/14/21, DL: This project is 95% complete. Items that need to be completed are: remove window AC unit, replace glass where the AC unit was removed and install window covering…………..4/30/21, DL: Demolition is complete, we will start the electrical and painting in the next two weeks…………..4/15/21, DL: The space was surveyed for hazardous material. There were rodent droppings, which will be disposed of this weekend, the ceiling tiles had mold. The ceiling tiles were removed. We will start the demo of the floor and some other items with in the next three weeks………..4/1/21, DL: We need to survey the space for hazardous material and arrange to have the space sanitized………………1/19/21, DL: This project is a priority #5. We will start this project when all priority #4 projects are complete…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….02/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Survey space for hazardous material. Once survey is complete, we will schedule abatement and the work. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2021-06-02 | Winter 2021 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000247 |  | 20P000247 | FALSE | CNAS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | Refresh Lab: Patch paint, strip & clean floor, repair broken ceiling and floor (VCT) tiles at room 2110 & 2118. Install Electrical power & Co2 cylinder racks at each end of workbench/tables | SPIETH | 2110 + 2118 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | Dan Lerman |  | 6 |  | TRUE |  |  | 43796 | [6 empty] | 1/19/21, DL: This project is complete…………..9/30/20, DL: This project is in progress and will be compete in the next 6- 8 weeks……………8/5/20, DL: We will start on this project in the next 6-8 weeks….. | 2020-04-17 | Enrico Baez | Spieth 2110: Carpentry: Seismic anchoring for “New” tables and equipment. Replace damaged ceiling tiles. Install misc. wall mounted items. Sheet Metal: Remove “existing” steel cage. Fabricate & install metal cylinder rack w/ restrains/seismic anchoring to floor. Plumbing: Install Co2 POC for gas cylinders at four (4ea) new free-standing work benches (see configuration on this document). Electrical: Install dedicated *120v power drop & connect to the existing power strips built-in the four (4ea) new workstation tables (see configuration on this document). *VERIFY/CONFIRM VOLTAGE W/ D. MCW. Relamp fixtures as needed. Spieth 2118 & 2110: Sheetmetal: Clean and or replace air distribution grilles. Flooring: Repair/patch broken floor tile and Replace broken ceiling tiles (abate floor tiles if required). Painting: Paint and patch all walls, verify recondition doors @ room side. Plumbing: Assess sinks to be fully operational & clean. *Replace sink in Rm 2118 for glassware, confirm with Faculty/Estella. Replace sink in room 2118 (Sink type TBD by Faculty). HVAC: Check lab air pressure is operational & proper pressure. Custodial: Strip and Wax floor, clean interior windows, wipe down doors and windowsills. EXCLUSIONS: Furnish, assemble, and install new workstations, tables or lab equipment. Removal of existing lab furniture or equipment. Natural gas or air output taps not required (per Faculty). | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000366 |  | 20P000366 | FALSE | CNAS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | MINOR LAB RENOVATION | HERMAN T. SPIETH HALL | 2375 / 2375-A | COMPLETE | Kathryn Uhrich | Jose Wudka | SHERICE UNDERWOOD |  | DAN LERMAN |  | 7 |  | TRUE |  |  | 43880 | Final walk and punch list items. | 44330 | 44393 |  |  |  | 7/15/21, DL: This project is complete. I am meeting with Kate for a final walk through tomorrow morning………….5/14/21, DL: We will start the project in the next three weeks, the door will be ordered next week. We will schdule paint to take place in the next 3-4 weeks….1/19/21, DL: This is a priority 7 project, we will start this project when all priority 6 projects are complete………….. |  | Enrico Baez |  |  | 2021-07-16 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 21-22
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GH08 | 881 | COMPLETE | Kathryn Uhrich | Jose Wudka | NANCY FERGUSON |  | Dan Lerman |  | 7 |  | FALSE |  |  | 43494 | Schedule the work. | [5 empty] | 1/19/21, DL: This project is complete……………8/5/20, DL: This project is in Progress and should be complete in the next 8-12 weeks…………….3/25/20, DL: Work orders are produced. Once we are back to work, we will schedule the work………12/11/19 O-ANS: Re-assigned as project allotment - priority #7 for Winter 2020. 11/27/19 O-ANS: Hold by client for re-prioritization for Winter 2020. | 2020-03-04 | Enrico Baez | Install new 3 ton Packaged unit with heat pump and dedicated electrical service on the roof top. Provide 1ea return plenum, 2ea supply drops in the work space. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | R3 |  | TRUE |  |  | 43550 | Schedule the work | 43861 | 43882 |  |  |  | 8/5/20, DL: This Project is COMPLETE…….3/25/20, DL: The material is here and we are 95% complete with the work. We will complete the work when we return from the campus closure…………1/31/20 O-DHN: Emailed Status Report to customer…….1/30/20,DL: The pump is now on site but we are still waiting for the fittings. In the mean time, our plumber is putting everything together and is working on the installation. Once the fittings arrive, we will make the connections and the system should be good to go………….1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: The pump is scheduled to arrive on or before 1/31/20. We will schedule the work once we have the pump and material on site…..11/26/19, DL; Emailed Natalie and Sherice the quote for the vacuum pump. We will order the material and schedule the work once we have approval and the pump on site……11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: I sent the vendor a 2nd email requesting an update on the proposal. I also included Natalie on the email so she is aware of where we stand with the proposal……10/30/19, DL: We had a followup meeting with the vendor last week. The vendor is now working on a pump that will best meet our needs……….10/16/19, DL; We are working with a vendor on a quote for a new lab vacuum pump. We are hoping to have a quote in the next week or two…..9/16/19, DL; Estimate was provided to customer last week. If the project is approved, we will work on the plans and permits. Once approved, we will schedule the work…… |  | Enrico Baez | Old SOW Revised SOWInstall exhaust hood, electical receptacle, vacuum pump, vac lines and valves (six valves total) and hood location. | YES | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
20P000397 |  | 20P000397 | FALSE | CNAS | SL5 ENTOMOLOGY 139 - PATCH AND PAINT OFFICE | Patch and paint room 139 for the new faculty member | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 0139 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 43895 | [6 empty] | 04/16/21 O-ANS: Project complete per Paul Ditty. 02/10/21 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  | 2021-04-16 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000419 |  | 20P000419 | FALSE | CNAS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | Paint Only | HERMAN T. SPIETH HALL | 2312 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | PAUL DITTY |  | X |  | TRUE |  |  | 43943 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 3/18/21. 03/18/21 D-JPO: cleaned room patched masked sanded and primed all walls |  | Paul Ditty |  |  | 2021-03-18 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
19P000517 |  | 19P000517 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | COMPLETE | LaRae Lundgren | Emily Engelschall, Sean Cason | DANIELLE GARCIA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43531 | Verify scope and schedule work | 43801 | 44185 |  |  |  | 1/19/21, DL: This project is complete…………..8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced, We will schedule the work when we return from the campus closure…………11/11/19, DL: I will work on scheduling this project… | 2019-06-17 | Enrico Baez | 6/17/19 E. Baez Conducted site visit with Sean. Will need carpenters to mount TV and electricians to add outlet to North wall. Data not needed. Might need painters depending on how carpenters install TV mount. | YES | 2021-01-19 | FALL 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
21P000160 |  | 21P000160 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 CHAPMAN HALL 109 - REPAIR COUNTERTOPS | REPAIR COUNTERTOPS IN CHAPMAN HALL 109 |  | 109 | COMPLETE | Susan Marshburn | Da Lan Dinh | DAN LERMAN |  | Dan Lerman |  |  |  | FALSE |  |  | 44414 | [6 empty] | 09/02/21 O-ANS: Project complete per Dan L. |  | Dan Lerman |  |  | 2021-09-02 | Summer 2021 | FS | 0 | 2021 | 2021-09-16 | FY 21-22
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43487 | finish plans/submit application | 43840 | 43917 |  |  |  | 8/5/20, DL: This Project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer…..2/18/20, DL: We are making great progress and still on schedule to be complete before Spring Break begins. We pass drywall inspection on 2/18/20………..1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: Plans are approved. All items have been removed from the space. Abatement is schedule to take place within two weeks…..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were submitted for plan check review. Fire marshal stamped the plans, we are waiting on the final stamp from our building official. Once plans are approved we will order material and schedule the work……..10/30/19, DL: Gunter is working on plans. We are planning to complete the work before Spring Quarter begins. |  | Dan Lerman |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000003 |  | 20P000003 | FALSE | GRAD DIV | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | ADD POWER/DATA, PATCH/PAINT | UNIVERSITY OFFICE BUILDING |  | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS | CHERYL GERRY | Dan Lerman |  | 1 |  | FALSE |  |  | 43648 | Install hydration station when it arrives | 44244 | 44306 |  |  |  | 4/15/21, DL: This project is complete. We will install the hydration station when it arrives…..4/1/21, DL: Electrical, rough plumbing, drywall, and paint is complete. The next step is to install the floor covering with in two weeks……………3/15/21, DL: The demo, electrical and rough plumbing is complete. We will schedule inspection this week. Once we pass inspection, we will schedule the drywall installation, prime, paint and new floor covering……..2/16/21, DL: Conducted a site visit with the plumber and capenter shop. We will start the demo next week…………2/1/21, DL: We will schedule this project to start in 2- weeks……………….1/19/21, DL: Plans were approved and we will schedule the work in the near future………. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Permit is approved. We need to verify floor covering. Once floor covering is confirmed and ordered, we will schedule the work………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We will need plans as we are installing a new hydration station and a counter top that needs to be ADA compliant…………We started the plans and will submit them for a permit and plan check review within 2- weeks……….10/30/19, DL: No Plans will be needed. We will plan on scheduling the work shortly after Thanksgiving……. | 2019-06-13 | Enrico Baez | 9/24/2019 E. Baez--SCOPE-- 1. Removal and disposal of one bulletin board and two director cases. 2. Removal and disposal of abandoned telephone mounting bracket. 3. Remove and dispose of abandoned alarm box in wall. 4. Patch and paint walls in lobby and public restroom area. 5. Provide electrical connection for wall mounted monitor. 6. Cut access for data boxes. 7. Install monitor mount on wall. 8. Construct 7" x 18" laminate counter top and install in Lobby. | YES | 2021-04-15 | FALL 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | C&C CARPORT | 161 | COMPLETE | Danna Gianforte | Shelley Gupta | SHELLEY GUPTA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 43472 | Waiting for bid for customer. | 43850 | 43921 |  |  |  | 8/5/20, DL: This Project is complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have the contract, we will schedule the work……………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Project was approved by Shelley. We will work on the contract. Once we have the notice to proceed from contracts, we will order the material and schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Sent Shelley another follow-up email today and she has not verified if she would like to move forward with the project………10/30/19, DL: Sent Shelley the updated quote last week and she has not responded. I sent Shelley a followup email today asking her to let me know if she would like to proceed with the work……..10/16/19, DL; Had a meeting with Shelley, we modified the scope of work and software for the project. We are now revising the quote with our vendor. We should have an updated quote within the next two weeks. If Shelley approves the work and scope, we will proceed….10/1/19, DL; I have a meeting with Shelley this afternoon to review proposal. If she approves the project we will submit plans for a building permit……8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was cancelled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; We have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28/19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
21P000183 |  | 21P000183 | FALSE | PB&A | SL5 OBAN A&B - PROJECT PORCH REPAIRS 2, 10, 18, 26 | TRENTON MABEE SL5 PROJECT FOR OBAN A & B APT 2, 10, 18, AND 16. PORCH REPAIRS. ZONE MAINTENANCE CARPENTER SHOP |  |  | COMPLETE | Gerry Bomotti | TBD | TRENTON MABEE |  | Chris Pillen |  |  |  | FALSE |  |  | 44329 | [6 empty] | 09/02/21 O-ANS: Complete per Chris P. 08/06/21 O-ANS: Assigned to Trenton Mabee to manage project. |  | Chris Pillen |  |  | 2021-09-02 | Summer 2021 | FS | 0 | 2021 | 2021-09-16 | FY 21-22
19P000414 |  | 19P000414 | FALSE | PB&A | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | Seth Morrison |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43451 | pending material delivery | 43754 | 43796 |  |  |  | 8/5/20, DL: This Project is Complete………….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: We have the motor on site, we are working on the permit for the crane. Once we have the crane lift permit, we will schedule the install…………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: We are working on the new motor platform. It is our goal to install the new motor in late January. Once the motor is installed, we will be able to identify if additional work is needed…….11/19/19 DH: Emailed Status Report to customer…..11/15/19, DL: Material has not arrived……..10/30/19, DL: The new exhaust fan is ordered with a 2- 4 lead time. Once the exhaust fan arrives, we will schedule the install……….10/16/19, DL; We are in the process of the work. At this current time, we are not modifying the building to where permits may not be required…….10/1/19, DL; This is in the queue for plans, we will start the plans in the next 3-4 weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2018 | 2021-09-16 | FY 20-21
21P000003 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Enrico Baez |  | R1 |  | FALSE |  |  | 44008 | [6 empty] | 4/9/2021 E. Baez roof repairs completed…1/20/2021 E. Baez- Proposal for $24,366 received from Rite-Way Roofing.….01/19/21, DL: Enrico is managing this project………….. | 2020-12-02 | Enrico Baez | Remove tripod antenna. Apply spray roof coating to existing roof surface | YES | 2021-04-09 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21 | 1
19P000687 |  | 19P000687 | FALSE | PB&A | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | COMPLETE | Gerry Bomotti | TBD | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 43642 | plan check review | [5 empty] | 8/5/20, DL This Project is Complete……………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Contracts is processing the contract. Once the contract is complete, we will schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Plans were approved. I sent Brendan an email 11/11/19 requesting an FAU # as this is Recharge work. Once we have the FAU #, we will work on the contract agreement with the contractor………10/30/19, DL; Sent Lezlie and email asking if she has an update on the resubmitted plans on 10/30/19………..10/16/19, DL; The plans were resubmitted for plan check review this week. We are hopeful the plans will be approved this week. Once approved we will work on contract and scheduling the work…10/7/19 LB: This is a test. The timestamp will be reset when the test is done. 10/1/19, DL: We are working on plan check review. We should have approved plans in the next two weeks…..8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | Provide estimate to install key card access control |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
19P000660 |  | 19P000660 | FALSE | SOM | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SL5 SOME RB, RM 330- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43627 | [6 empty] | 9/30/20, DL: This Project is Complete………..8/5/20, DL: Dan to follow-up with customer…………..03/05/20 O-ANS: Removed room 330 per client request. Only updates to 107 & 111. |  | Enrico Baez | TBD | NO | 2020-09-30 | Fall 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000054 |  | 20P000054 | FALSE | SOM | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOMED-SOME G0600, G0621 & 1682B- ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 2 |  | FALSE |  |  | 43677 | [6 empty] | 9/30/20, DL: This Project is Complete…………..8/5/20, DL, Dan to follow-up with customer………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "Remove status Hold / Update project detail to include information on 1682B -ADD ELECTRICAL, PAINT/PATCH, AND RELOCATE WHITE BOARD." |  | Enrico Baez | Room G0600 Install Power behind and below the TV, install one TV Bracket, install one cut-in back box below the TV for data(data cabling by ITS), Paint the entire East wall to match existing. Room G0621 Insatll three(3) new double duplex receptacles and three(3) data back boxes only(no data cabling) in room G0621. Install SS tubing for Co2 from room G0621 to room G0623. Include Valves at both ends of P.O.C., Install one uni-strut siesmic cylinder support at the south wall. Steve Burleson has walked the site and has knowledge of the SOW. Loading Dock Install Pole & chains at Loading dock. |  | 2020-09-30 | Fall 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
21P000137 |  | 21P000137 | FALSE | SOM | SL5 WEBBER HALL - ACCESS CONTROL | Per attached Sales Quote 43830-7 dated 11/6/2020, from Enterprise Security in Tustin, please proceed with the proposal, planning. permit, and contract to complete this project. |  | 1247 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | CYNTHIA CAROLINA | Dan Lerman |  | R1 |  | FALSE |  |  | 44264 | Final inspection and payment | [5 empty] | 7/15/21, DL; This project is complete. We still need to conduct the final inspection. There was a problem identified during the project where a repair is needed via an FAU number. We will conduct the repair under an SL6. Cynthia Carolina is aware of the additional needed repair that was not part of the scope or work……/9/21, O-DMS: EMAIL TO DAN LERMAN PROJECT # AND ASSIGNED TO J-DLN. |  | Dan Lerman |  |  | 2021-07-15 | Winter 2021 | FS | 0 | 2021 | 2021-09-16 | FY 21-22 | 1
20P000467 |  | 20P000467 | FALSE | SOM | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. | HERBERT JOHN WEBBER HALL | 1247 | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | PAUL DITTY |  | X |  | TRUE |  |  | 44001 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/22/21. 2/22/21 D-JPO CLEANED UP DONE. 02/17/21 D-JPO: primed room and door. 02/16/21 D-JPO: finished prep. |  | Paul Ditty |  |  | 2021-02-22 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000026 |  | 20P000026 | FALSE | VC-RED | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | Install T-bar ceiling, Provide HVAC and Fire sprinklers drops. Install new 2x4 LED light fixtures | LIFE SCIENCE | Basement Level | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  | 1 |  | FALSE |  |  | 43665 | Work on Plans and permits. | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: The plans were submitted two weeks ago. We should receive the plan check review comments in the near future…………….8/5/20, DL: This Project will exceed $50,000. Monty A. will inform customer this is a project that will need to be managerd through PD&C……………3/25/20, DL: We will work on plans when we return back from the campus closure. | 2020-01-31 | Enrico Baez | Install T-bar ceiling with wipable(coated) ceiling tile. Provide HVAC and new Fire sprinklers drops to new ceiling. Install new 2x4 LED light fixtures. Verify Fire alarm systems work. | YES | 2021-01-19 | Fall 2019 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000230 |  | 20P000230 | FALSE | VC-RED | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | Install Ceilings, Widen Door & Extend Utilities | BOURNS | B116C & B116D | COMPLETE | Rodolfo Torres | Laura Manor | KRASSIMIR BOZHILOV | LAURA MANOR | Dan Lerman |  | 1 |  | FALSE |  |  | 43787 | finish plans for building permit | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: This project is in progress and 50% complete. We should be complete with in the next 4-6 weeks…………...8/5/20, DL: We will submit plans in the next week………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We will start working on the plans and apply for a building permit in the next 2-3 weeks. | 2020-01-23 | Enrico Baez | Install new T-bar ceilings, lighting/switches, verify electrical service/disconnect. Relocate the existing eye washer, widen the exiting door opening and *reverse swing(*if approved by F.M). Install one customer furnished transformer. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
21P000078 |  | 21P000078 | FALSE | VC-RED | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MULTIDISCIPLINARY RESEARCH BUILDING |  | COMPLETE | Rodolfo Torres | Laura Manor | TARA BARTHOL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 44097 | [6 empty] | 4/15/21, DL: The work is complete. We still need to connect several minus 80 freezers. Tara will check in with us when they are ready to be connected……….1/19/21, DL: the First floor work will be complete today, we will start the 2nd floor this week……………. |  | Enrico Baez |  |  | 2021-04-15 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000218 |  | 20P000218 | FALSE | VC-RED | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | VIVARIUM UPDATE AIR COMPRESSOR | HERMAN T. SPIETH HALL | 347 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | DAN LERMAN |  | 2 | R2 | FALSE |  |  | 43602 | Set & place the compressor. Start elect. / plumbin | 44293 | 44330 |  |  |  | 5/14/21, DL: This project is 100% Complete….4/30/21, DL: The plumbers are 75% complete. Once the plumbing is complete, the electricians will start…………4/15/21, DL: The compressor was delivered to the permanent location. The plumbers will start the air lines and drain assembly next week. The electricians will connect the electrical within a month, as they have a few other projects in their queue that need to be completed before they start this project………….4/1/21, DL: We are scheduled to relocate the compressor next week. Once the compressor is placed, we will anchor the compressor and start the electrical and plumbing……………….3/15/21, DL: We received confirmation the Compressor is on site. We will schedule the work once as soon as we are able to………….2/1/21, DL: WE will start the process for this project once we are closer to completing priority 1 projects. This is a prioity 2 project……1/19/21, /DL: This project has been scoped. We will start the work when we are complete with all priority #1 projects……. |  | Enrico Baez |  |  | 2021-05-14 | Winter 2021 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
22P000008 |  | 22P000008 | FALSE | VC-RED | SL5 MRB VARIOUS LAB SUPPORT - IACUC INSP TINTED WINDOWS NEEDED | ER IACUC INSPECTION- TINTED WINDOW NEEDED ON LAB SUPPORT ROOMS. ORIGINAL SERVICE REQUEST 22S000637 See list of rooms for window tint request. Korzus 1204E 1204F 1212A 1212B 1229B Zagha 1212A 1212B 1204F 1204E 1231C Abdulrazak 2204A 2204G 2204F 2208B Binder 3214 3218 3215 Cho 3216 3219 Tiwari- Woodruff 3204G Hickmott 2221 Zheng 2225 2213-C |  |  | COMPLETE | Rodolfo Torres | Laura Manor | TARA BARTHOL |  | Enrico Baez |  | R1 |  | TRUE |  |  | 44391 |  | 44406 |  |  |  |  | 09/02/2021 ANS: Project is complete per EBZ. 07/27/21 EBZ: Project to begin 07/29/21. |  | Enrico Baez |  |  | 2021-08-25 | Summer 2021 | FS | 0 | 2021 | 2021-09-16 | FY 21-22 | 1
21P000102 |  | 21P000102 | FALSE | VC-RED | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | AAALAC Certification updates to rooms 348, 352 & 363 | SPIETH | 348, 352 & 363 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS | YURIDIA REYNOSO | Paul Ditty |  | TBD |  | FALSE |  |  | 44133 | [6 empty] | 12/08/20 O-ANS: Customer Dierk Biggs confirmed via email that these room updates are complete. |  | Paul Ditty |  |  | 2020-12-08 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
21P000079 |  | 21P000079 | FALSE | VC-RED | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. | PSYCHOLOGY BUILDING |  | COMPLETE | Rodolfo Torres | Laura Manor | LESLIE KARPINSKI |  | PAUL DITTY |  | X |  | FALSE |  |  | 44099 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/25/21. 02/25/21 D-BFA: continued painting the black room. Patched in the Quarantine rooms. 02/23/21 D-BFA: Continued painting finish on all green and all repaired cracks. 02/16/21 D-MMN: prepped cracks with caulking. |  | Paul Ditty |  |  | 2021-04-01 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
20P000468 |  | 20P000468 | FALSE | VC-RED | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | Paint Only | HERMAN T. SPIETH HALL | 364 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 44005 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 12/02/20. 12/09/20 D-MMN: removed masking and reinstalled fallen base with base and wall glue. 12/08/20 D-MMN: applied finish to all the patches in the hallway and storage room. 12/07/20 D-MMN: Applied 3rd. coat of joint compound. returned and sanded then primed patches. these were located in the main hallway and the bedding supply room. vacuumed dust. 12/04/20 D-MMN: Continued scraping, treating and filling efflorescence and cracking paint. started taping baseboards and priming where it was so ready. |  | Paul Ditty |  |  | 2021-04-01 | Winter 2021 | FS | 0 | 2020 | 2021-09-16 | FY 20-21
18P000214 |  | 18P000214 | FALSE | VC-STU AFF | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Install Card readers | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  | 2 | 2 | FALSE |  |  | 43077 | Pending special order part | 43515 | 44075 |  |  |  | 1/19/21, DL: This project is 100% Complete…….9/30/20, DL: Vendor should have the balance of the material in the next 30- days…….8/5/20, DL: This project is complete except the card reader portion of the project…………6/17/20, DL: The floor covering was completed two weeks ago. The card reader portion of this project is 95% complete but additional parts were needed and they are on order. Once they arrive, we will schedule the installation and this project will be 100% Complete………1/15/20 Emailed Status Report to customer…..1/14/20, DL: We were recently approved to proceed with the work. I have reached out to the vendor for the doors and card access. We are still waiting to hear back from them so we can order the material and schedule the work. I communicated with Nicole on the floor covering replacement. Nicole needs to verify what areas we will replace as we were going to complete several offices and a hallway as part of the scope but this will displace many team members for at least a week. We will work on scheduling the work once Nicole gets back to me……..12/17/19 - O-DHN: Emailed Status Report to Customer……12/19/19, DL; We are working with our contractor to order the material and schedule the work. Once we have confirmation on the material, we will be able to schedule the work. It Is our goal to start this project in late January……11/26/19, DL: This project was taken off of on hold and we can now proceed. I contacted the contractor last week and I am awaiting their response on when they can schedule the work. I also left a message with them this morning………..7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once material arrives, we will schedule the installation.….5/31/19, DL; Contract is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is completed except the floor covering and electronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being prepped for paint. We have a pre-construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, material is ordered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct site visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez |  | YES | 2021-01-19 | Winter 2018 | FS | 0 | 2017 | 2021-09-16 | FY 20-21
3632 | 3632 |  | FALSE | ATHLETICS | SRC North Instant Replay System | Possible update of instant replay system in Student Recreation Center North to include volleyball if mandate by Big West Conference is enacted. This will include placing cameras on the ends of the court that will send signal back to the control room and could involve additional wiring to courtside connection boxes. Scope may include upgrading audio connections. Volleyball season starts in late August... first home game TBD. No charges to this FAU unless Athletics notified in advance of work to be performed. Work Notes: Project will require coordination not only with Athletics but must also with Recreation (Mike Eason), and their scheduling may affect above dates. Possible vendor to be consulted is TechNet who has indicated ability to do such a project in recent times. |  |  | Delayed until 8/2022 per Athletics | Tamica Smith Jones | Joe Erbland | Joe Erbland |  | Tameesha Hayes | 3 |  |  | FALSE |  |  | 44287 | Delayed until 8/2022 per Athletics | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | Design | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 42340 | Bidding | [12 empty] | PD&C | 0 | 2015 | 2021-09-16
3616 | 3616 |  | FALSE | CAP PROG | University Ave/Canyon Crest Dr Improvements | $100,000 in Violent Acts Mitigation and Prevention funding have been awarded to study short and long-term safety improvements at the intersection at University Avenue and Canyon Crest Drive. Subsequent activities will involve the construction of identified improvements. |  |  | Design | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Uma R. | 16 |  |  | FALSE | 100000 |  | 44256 | Construction | 44562 | 44593 | [10 empty] | PD&C | 0 | 2021 | 2021-09-16
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Design | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 44091 | 2nd site visit w/ consultant | [12 empty] | PD&C | 0 | 2020 | 2021-09-16
3631 | 3631 |  | FALSE | ITS | SOM-ED 1 UPS | The Information Technology Solutions (ITS) intends to replace its existing UPS unit with a state of the art systems that will support all of the requirements set-forth by the University of California, Riverside ITS and Facilities departments. Our primary objective is to provide ITS critical services and various other software applications. The ITS department would like to Procure (1) redundant UPS System with all accessories and maintenance for three years after warranty (AMC). Procure One Replacement 500KW UPS Unit, Installation of New UPS, Removal and Disposal of Old UPS components, Startup Services for New UPS, Electrical Installation of New UPS and Removal of Rental UPS connections (High Voltage) |  | 1625 | Design | Danna Gianforte | Shelley Gupta | Cesar Higueros |  | Tameesha Hayes | 1 |  |  | FALSE |  |  | 44399 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Design | Gerry Bomotti | TBD | ---- |  | Fernando Canon | 1 |  |  | FALSE | 33980000 |  | 43528 | Construction | 44531 | 45047 | [10 empty] | PD&C | 0 | 2019 | 2021-09-16
3515d | 3515d |  | FALSE | PB&A | Multiple SF6 Primary Switches | Sub-project of 950568 |  |  | Design | Gerry Bomotti | TBD | John Franklin |  | John Franklin | 2 |  |  | FALSE |  |  | 44256 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 19 |  |  | FALSE | 320000 |  | 43312 | Bidding TBD | [12 empty] | PD&C | 0 | 2018 | 2021-09-16
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Design | Gerry Bomotti | TBD | ---- |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Bidding | [12 empty] | PD&C | 0 | 1900 | 2021-09-16
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 44096 | Bidding | 44562 | 44652 | [10 empty] | PD&C | 0 | 2020 | 2021-09-16
3630 | 3630 |  | FALSE | SOM | SOMR Egress Doors/Cameras | All egress doors for floors 1-3. need to be replaced with compliant standards. Project to also include security cameras for entry and exit on 1st and 2nd floor. |  |  | Design | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes | 2 |  |  | FALSE | 65000 |  | 43894 | Bidding | [12 empty] | PD&C | 0 | 2020 | 2021-09-16
9067 | 9067 |  | FALSE | PB&A | DM(FY20) Campus Infrastructure Access Control | Access Control: Automate Access Controls focusing on General Assignment Classrooms. |  |  | DM project to be funded | Gerry Bomotti | TBD |  |  | Fernando Nunez |  |  |  | FALSE | 200000 |  |  | DM project to be funded | [12 empty] | PD&C | 0 | 1900 | 2021-09-16
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS BUILDING |  | ESTIMATE | Kathryn Uhrich | Jose Wudka | JOSE WUDKA |  | Enrico Baez |  | R1 |  | FALSE |  |  | 43818 | Awaiting Response from Client | [5 empty] | 05/13/21 O-ANS: Enrico corresponded with Dr. Wudka on 3/14/2021. He had emailed me stating that the College was going to discuss the project. Still awaiting a response to that inquiry. I follow up today requesting an update. 1/19/21 DL: Enrico is managing this project. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-09-16 |  | 1
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | Funding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 600000 |  | 43713 | Combine with Exterior Proj CP3548 | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | Furniture & Equipment | Jacqueline Norman | Sharyl Murdock | ---- |  | Mihai Gavan | 9 |  |  | FALSE | 60430000 |  | 42887 | Close-out | 43770 | 44409 | [10 empty] | PD&C | 0 | 2017 | 2021-09-16
3615 | 3615 |  | FALSE | CAP PROG | Student Success Center Buildout | Buildout and furnishing of the SSC dining venue for temporary use as seating/study area and other as needed construction scope related to the overall building project that was not described in the Basis of Design. |  |  | Furniture & Equipment | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Mihai Gavan | 17 |  |  | FALSE | 980000 |  | 44264 | Close-out | 44256 | 44409 | [10 empty] | PD&C | 0 | 2021 | 2021-09-16
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LABORATORIES 1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 43880 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-09-16
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SUPPORT SERVICES BUILDING | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | Emily Engelschall, Sean Cason | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 43852 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-09-16
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL BUILDING | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 43803 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2019 | 2021-09-16
3614 | 3614 |  | FALSE | INACTIVE P&B | MLK Water Meters | Provide by contract plumbing point of connections and irrigation infrastructures to north and south sides of Martin Luther King Blvd. for watering of UCR palm trees. City of Riverside shall install two (2) ¾” [City] water meters at points of connection. Provide approximately 300’ of new irrigation main-line with associated trenching via contract and/or via facilities work order TBD. |  |  | In Bidding | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 17 |  |  | FALSE | 31790 |  | 44316 | Award Contract | 44470 | 44501 | [10 empty] | PD&C | 0 | 2021 | 2021-09-16
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | In Bidding | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 43528 | Award Contract | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Bidding | Gerry Bomotti | TBD | ---- |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 44089 | Award Contract | [12 empty] | PD&C | 0 | 2020 | 2021-09-16
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Bidding (Phase 2) | Kathryn Uhrich | Jose Wudka | Sabrina Schuster |  | Scott Donnell | 6 |  |  | FALSE |  |  | 42710 | Award Contract (Phase 2) | 44470 | 44531 | [10 empty] | PD&C | 0 | 2016 | 2021-09-16
3637 | 3637 |  | FALSE | ATHLETICS | Soccer Field Spiideo Video Installation | We are making an addition to the soccer stadium by adding a 40 foot pole at center field with a cloud based camera operating system. |  |  | In Construction | Tamica Smith Jones | Joe Erbland | Eugene Hutchinson |  | Tameesha Hayes | 1 |  |  | FALSE |  |  | 44302 | Complete Construction | 44409 | 44440 | [10 empty] | PD&C | 0 | 2021 | 2021-09-16
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Construction | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Scott Donnell | 1 |  |  | FALSE | 700000 |  | 43194 | Complete Construction | [12 empty] | PD&C | 0 | 2018 | 2021-09-16
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | ---- |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 42725 | Pending proposal from JCI | 44197 | 44561 | [10 empty] | PD&C | 0 | 2016 | 2021-09-16
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Richard Zapien |  | Scott Donnell | 3 |  |  | FALSE | 39000 |  | 43959 | Cooler Delivery | 44348 | 44470 | [10 empty] | PD&C | 0 | 2020 | 2021-09-16
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Georgios Vidalakis |  | Scott Donnell | 5 |  |  | FALSE | 643925.09 |  | 44085 | Complete Construction | 44197 | 44501 | [10 empty] | PD&C | 0 | 2020 | 2021-09-16
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Tracey Kahn |  | Scott Donnell | 9 |  |  | FALSE | 1575000 |  | 43108 | Complete Construction | 44228 | 44470 | [10 empty] | PD&C | 0 | 2018 | 2021-09-16
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May incl--ude paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | In Construction | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Scott Donnell | 3 |  |  | FALSE | 1340000 |  | 43600 | Complete Construction | 44317 | 44440 | [10 empty] | PD&C | 0 | 2019 | 2021-09-16
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 5 |  |  | FALSE | 600000 |  | 43634 | Installaton of NFACP | 44348 | 44469 | [10 empty] | PD&C | 0 | 2019 | 2021-09-16
3590b | 3590b |  | FALSE | PB&A | DMFI(FY17-20) Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Construction | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 43796 | Submittal approval | 44378 | 44530 | [10 empty] | PD&C | 0 | 2019 | 2021-09-16
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | In Construction | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 97050000 |  | 43528 | Complete Construction | 44378 | 45047 | [10 empty] | PD&C | 0 | 2019 | 2021-09-16
3467 | 3467 |  | FALSE | PB&A | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 17 |  |  | FALSE | 405000 |  | 43312 | Complete Construction | 44409 | 44440 | [10 empty] | PD&C | 0 | 2018 | 2021-09-16
3490 | 3490 |  | FALSE | PB&A | Parking Structure 1 | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | Parking Lot 13 |  | In Construction | Gerry Bomotti | TBD | Irma Henderson |  | John Franklin | 25 |  |  | FALSE | 31844000 |  | 43440 | Complete Construction | 43862 | 44440 | [10 empty] | PD&C | 0 | 2018 | 2021-09-16
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 44097 | Complete Construction | 44378 | 44531 | [10 empty] | PD&C | 0 | 2020 | 2021-09-16
3524 | 3524 |  | FALSE | VC-STU AFF | Student Srvs Bldg 1st Floor Reno | Vice Chancellor Haynes and Vice Chancellor Bomotti have directed the Student Disability Resource Center (SDRC) to consolidate from three locations (currently Costo Hall, Student Services Building, and Skye Hall) to one location on the first floor of Student Services Building (SSB). Alterations need to be made in current SDRC space (SSB 1213 suite) and new SDRC space (SSB 1228 suite), before SDRC can assume full occupation of the spaces. The expected occupancy date is no later than September 9, 2019. Alterations to the SSB 1213 Suite could begin as early as June 18, 2019. Alterations to the SSB 1228 suite would not be expected to begin until July 2019, when BCOE Student Academic Affairs is scheduled to move out. This project cannot move forward until an estimate for the project can be received and put forth to VC Haynes and VC Bomotti for funding. | STUDENT SERV |  | In Construction | Brian Haynes | Cathy Eckman | Laura Riley |  | Daneca Stevens | 1 |  |  | FALSE | 450000 |  | 43571 | Complete Construction | 44409 | 44440 | [10 empty] | PD&C | 0 | 2019 | 2021-09-16
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | In Construction | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 61918 |  | 44095 | Complete Construction | 44440 | 44440 | [10 empty] | PD&C | 0 | 2020 | 2021-09-16
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Construction by USDA | Kathryn Uhrich | Jose Wudka | MaryLou Polek |  | Scott Donnell | 10 |  |  | FALSE | 2500 |  | 43742 | Complete Construction by USDA | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
3624 | 3624 |  | FALSE | BCOE | CE-CERT Circuit Upgrade | We have an existing 208 VAC 100 Amp circuit. We would like to upgrade to a 200 Amp service. The existing service is located in the electrical room at 1084 Columbia. |  |  | In Design | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Tameesha Hayes | 5 |  |  | FALSE | 4100 |  | 44258 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3613 | 3613 |  | FALSE | CAP PROG | Corp Yard Modular Building Relocation Study | This project will be to relocate the existing School of Medicine modular trailer (P5825) to the Corp Yard (specific location to be determined). This modular needs to be relocated due to the new School of Medicine Education Building II project being located on this site. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Tameesha Hayes | 18 |  |  | FALSE |  |  | 44309 | Complete Design | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 3182452.32 |  | 42720 | Bidding | 44562 | 44652 | [10 empty] | PD&C | 0 | 2016 | 2021-09-16
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | Jose Wudka | Wendi Tapia |  | Tameesha Hayes | 12 |  |  | FALSE |  |  | 44001 | Waiting for equipment from overseas | [12 empty] | PD&C | 0 | 2020 | 2021-09-16
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | ---- |  | Fernando Canon | 7 |  |  | FALSE | 432510 |  | 42425 | Bidding | 44531 | 44593 | [10 empty] | PD&C | 0 | 2016 | 2021-09-16
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 500000 |  | 43713 | Bidding | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | ---- |  | Fernando Canon | 18 |  |  | FALSE | 2600000 |  | 42509 | Funding & Approval | [12 empty] | PD&C | 0 | 2016 | 2021-09-16
3648 | 3648 |  | FALSE | PB&A | Bannockburn Walkway Repairs | Several walkway locations at Bannockburn have deteriorated to the point that they must be replaced. The topcoat is past it’s service life and has lost all waterproofing effectiveness. As a result, the underlying sheathing, T&G, and support beams have suffered extreme water damage. Scope of Work: Replace support beams, T&G, and topcoat system at 2 locations: L bldg. & V bldg. Requesting JOHN FRANKLIN as PM. |  |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 1 |  |  | FALSE |  |  | 44389 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 22 |  |  | FALSE |  |  | 42653 | Bidding | [12 empty] | PD&C | 0 | 2016 | 2021-09-16
3626 | 3626 |  | FALSE | UNDERGRADUATE EDUCATION | Rivera Library Room Modifications | Conduct room modifications to support new wall display on west wall Rivera A101A. Work needed: 1. West wall - ½” three-ply to support 12 x 55” displays over bookshelves. 2. West wall – drywall cover bookshelves any area not covered by the technology displays. 3. West wall – add electrical outlets as needed for new displays 4. North and south walls – add electrical for new motorized shades 5. Rivera A101A – add carpeting 6. Rivera A101A – paint room Notes: - Working with Chuck Forsyth in ITS and Bahram Mobasher from CNAS/Physics on project. - Israel and Chuck had a preliminary meeting with Enrico Baez from facilities to discuss project. - Point of contact: Israel Fletes and Charles Forsyth. Israel Fletes cellphone: 951-300-6693 |  | A101A | In Design |  |  | Israel Fletes |  | Vilma Kern | 1 |  |  | FALSE | 32000 |  | 44237 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3270 | 3270 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Chapman Hall - Replace HVAC System | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | CHAPMAN |  | In Design (Re-opened) | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Tameesha Hayes | 11 |  |  | FALSE | 595819 |  | 42801 | Bidding | [12 empty] | PD&C | 0 | 2017 | 2021-09-16
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | In Funding | Kathryn Uhrich | Jose Wudka | Mireya Botello Santoyo |  | Scott Donnell | 1 |  |  | FALSE | 32871.65 |  | 44026 | Secure Funding for Additional Scope | [12 empty] | PD&C | 0 | 2020 | 2021-09-16
3636 | 3636 |  | FALSE | PB&A | Tunnel DAS | Adding radio repeaters to the tunnel system to improve coverage in a high hazard work area. The project consists of adding a rooftop antenna, battery back-up, amplifier, repeater antennas, and coax runs through the tunnel system. A few items need to be mounted. Golden State Communications will need to interface additional system to the existing radio system. |  |  | In Funding | Gerry Bomotti | TBD | Tracy Stark |  | Tameesha Hayes | 1 |  |  | FALSE | 106625 |  | 44321 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | In Pre-Programming | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 9 |  |  | FALSE | 3000000 |  | 43775 | Programming | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | John Franklin | 2 |  |  | FALSE | 10290000 |  | 43532 | Complete Programming | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | ---- |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 43528 | DB Competition | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 43297 | Complete Study | [12 empty] | PD&C | 0 | 2018 | 2021-09-16
3612 | 3612 |  | FALSE | CAP PROG | Native American Landscape Garden | Create a physical marker to commemorate the UCR Land Acknowledgement in the form of a Native American Landscape Garden (working name) at the proposed project location. |  | Ext | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Uma R. |  | Vilma Kern | 15 |  |  | FALSE | 103000 |  | 44238 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis (RE Proj) | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 43510 | Complete Study | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
3644 | 3644 |  | FALSE | LIBR | Rivera Library Fire Suppression Study | Request for estimate for installing fire suppression system in Rivera Library 4th floor and Secured area on Basement floor. |  |  | In Programming (Study) | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Vilma Kern | 1 |  |  | FALSE |  |  | 44372 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 43404 | CEQA | [12 empty] | PD&C | 0 | 2018 | 2021-09-16
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MATERIALS SCIENCE & ENGINEERING | 71 | IN PROGRESS | Christopher Lynch | Todd Ambriz | DONG YAN |  | DAN LERMAN |  | 2 | 3 | FALSE |  |  | 44049 | Schedule the work once the permit is approved | 44349 | 44454 |  |  |  | 8/18/21, DL: The electrical is complete. We are ordering material for the exhaust vents this week. We will schedule the installation when the material is on site……08/02/21, DL: We are still in the plan check review process. Once the permit is approved, we will schedule the work….7/15/21, DL: Plans are complete, we will apply for the building permit today and the permit should be reviewed and approved in the next 2-4 weeks. Once the permit is approved, we will order the material and schedule the work……6/2/21, DL: We will work on the final plans the week of 6/14/21 and try to apply for building permit on or before 6/22/21. Once the permit is approved, we will schedule the work…. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-09-16
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 245 | IN PROGRESS | Juliet McMullin | Cindy Williams | ANDREA HIDALGO | Susan Komura | DAN LERMAN |  | 3 |  | FALSE |  |  | 43832 | Make corrections and resubmit plans on 7/15/21 | 44340 | 44462 |  |  |  | 8/18/21, DL: We are making great progress and we should be done with project by Sept. 21. All light fixures are here on site. ……08/02/21, DL: The plans are now approved. We ordered the light fixtures and have also started the work. It is our plan to be complete with the project by September 23rd and the Arts Department currently has an exhibit they are planning to present on or near the 23rd……7/15/21, DL: We are still in plan check review with the building department and a few corrections were needed. We will resubmit the corrections tomorrow. Hopefully the permit will be approved in the next two weeks……..6/2/21, DL: We are almost complete with the plans. We will submit the plans to the customer for review by the end of the week. Once the cutomer approves the plans, we will apply for the building permit……4/20/21, DL: Conducted site vist with the Arts team. We will start working on the plans in the next two weeks……1/19/21, DL: This is a priority 3 project. We will start the plans and permit for this project when all priortiy #2 projects are complete… |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-09-16
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Convert Basement Library into Piano Lab | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 54 | IN PROGRESS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 43788 | Framing and electrical | 44330 | 44500 |  |  |  | 8/18/21, DL: We are making great progress and we should be complete with this project within the next 6 weeks. 08/02/21, DL: Most of the demolition is complete. We started the framing today. It is our goal to be 100% complete with this project by the end of October….7/15/21, DL: Plans were approved this week. Carpenter shop is ordering material and we should start the work next week…… 6/2/21, DL: We applied for the building permit last week. We should have approved plans in the next 1-2 weeks…..5/14/21, DL: We sent Paul R. the 75% complete plans today for review. Once Paul approves the plans and layout of the pianos, we will proceed with completing the plans and apply for the building permit. The demolition of the cabinets and floor covering is complete. The carpenter shop is also pre-ordering their material to help expedite the project once we have the approved building permit……4/1/21, DL: We will start the plans process over the next two weeks and try and apply for a building permit in the next 2-3 weeks…1/19/21, DL: We will Start the plans, permit and the work once all priority #3 projects…11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks…. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | 0 | 2019 | 2021-09-16
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | W. CONWAY PIERCE HALL | 2232A | IN PROGRESS | Kathryn Uhrich | Jose Wudka | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 43852 | Schedule the work once the permit is approved | 44351 | 44498 |  |  |  | 8/18/21, DL: We are scheduled to start the abatment and demo on 8/24/21. We will try and complete this project by mid-october or sooner…… 08/02/21, DL: The plans are still being review by the building department and EH&S. Once the plans are approved, we will schedule the work….7/15/21, DL: Plans will be complete and we will apply for the building permit by tomorrow enveing. If the permit is appproved, which should take 2-4 weeks for the review and approval process, we will order the material and schedule the work……5/14/21, DL: Project is scoped, we will work on plans and submit them to Kevin for review in about 3- weeks…….1/19/21, DL: This is a priority #9 project. We will start this project when all priority #8 projects are complete… |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-09-16
3195 | 3195 |  | FALSE | FAC-PLNG-DESIGN-CONST | North District | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | Move-in | Susan Marshburn | Da Lan Dinh | Raoula Amescua |  | Drew Hecht | 99 |  |  | FALSE | 4146146.55 |  | 42669 | Close-out | 43647 | 44409 | [10 empty] | PD&C | 0 | 2016 | 2021-09-16
3658 | 3658 |  | FALSE | CNAS | CVWD Canal Water Delivery Design | CVWD is under construction for delivering Colorado River (canal) water to the Oasis area. The project includes delivery to UCR at two sites, one North (60 acres) and one South (200 acres) of Avenue 72. Canal water should be available at both Delivery Points by January, 2023. IID engineering, PVC material, steel pipe, electrical supplies will require significant lead times. Hence, I recommend starting the design phase of these projects sooner than later. I included a Water Cost Comparison analysis presented in late 2020 to help justify capital improvements required prior to CVWD canal water delivery. |  |  | New (9/2/21) | Kathryn Uhrich | Jose Wudka | Sue Lee |  | Daneca Stevens |  |  |  | FALSE |  |  | 44441 | New (9/2/21) | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3656 | 3656 |  | FALSE | PB&A | Falkirk Standardized Balcony Drawings | Provide professional design services to complete construction drawings that will standardize balcony demolition and window frame-in at each balcony location type. Miyamoto is the architect for the Falkirk Seismic project. Given their extensive knowledge of the facility, we would like to negotiate design services with them for this project. |  |  | New (9/2/21) | Gerry Bomotti | TBD | Sean Hatfiled |  | Daneca Stevens |  |  |  | FALSE | 10000 |  | 44441 | New (9/2/21) | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3655 | 3655 |  | FALSE | PB&A | ECS Playground Improvements | Provide professional design services to complete schematic design, design development, and cost estimate for ECS North and South playgrounds. Scope of work includes reconfiguring pathways to mitigate trip hazards and meet ADA requirements, improve playground equipment and surfaces, add shade structures. Refer to John Franklin for more details. |  |  | New (9/8/21) | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin |  |  |  | FALSE |  |  | 44447 | New (9/8/21) | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Joe Erbland | Johnathan Jensen |  | Fernando Nunez | 4 |  |  | FALSE | 0 |  | 43335 | Department approval to move fwd | [12 empty] | PD&C | 0 | 2018 | 2021-09-16
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 13 |  |  | FALSE | 0 |  | 43072 | On Hold | [12 empty] | PD&C | 0 | 2017 | 2021-09-16
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 16 |  |  | FALSE | 0 |  | 43297 | Coordinating with North District | [12 empty] | PD&C | 0 | 2018 | 2021-09-16
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | On Hold | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 43273 | Awaiting direction by Provost | [12 empty] | PD&C | 0 | 2018 | 2021-09-16
3550 | 3550 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Skye Hall HVAC Replacement | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | SKYE HALL |  | On Hold | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 6 |  |  | FALSE | 2250000 |  | 43713 | On Hold | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 43809 | Departmental Approval | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | On Hold | Brian Haynes | Cathy Eckman | Christina Wong |  | Tameesha Hayes | 5 |  |  | FALSE | 130000 |  | 43543 | On Hold | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
3627 | 3627 |  | FALSE | VC-STU AFF | Costo Hall New Doors | Add three (3) doors to divide new office designations in Costo Hall. Two of the doors require new frames |  |  | On Hold | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 8 |  |  | FALSE |  |  | 44259 | On Hold | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3610 | 3610 |  | FALSE | PB&A | Hulen Place Homeless Medical Clinic | SOM is acquiring additional space for a medical clinic to assist with the homeless population. |  |  | On Hold, May Move Forward | Gerry Bomotti | TBD | Diana Armenta |  | Daneca Stevens | 5 |  |  | FALSE |  |  | 44110 | On Hold, May Move Forward | [12 empty] | PD&C | 0 | 2020 | 2021-09-16
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 1 |  |  | FALSE | 0 |  | 42886 | Department Approval/Funding | [12 empty] | PD&C | 0 | 2017 | 2021-09-16
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 6 |  |  | FALSE | 0 |  | 43178 | CIB Approval | [12 empty] | PD&C | 0 | 2018 | 2021-09-16
3640 | 3640 |  | FALSE | VC-RED | MRB Circulation Pumps E-Power | MRB Circulation Pumps e-Power |  |  | On-Hold | Rodolfo Torres | Laura Manor | Tara Barthol |  | Vilma Kern | 1 |  |  | FALSE |  |  | 44377 | On-Hold | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3634 | 3634 |  | FALSE | CNAS | Botanic Garden Geodesic Dome | Request is for an architect to draw a design for a replacement of current geodesic dome. Design can then be used as basis for fund-raising campaign to construct new dome. Dr. Holt, UCRBG Director, has been in discussions with Jacqueline Norman and Drew Hecht. Dome was constructed on site in 1980s, all wood, greatly deteriorated. Dome is unrepairable, unsafe, and closed to the public. Goal is to replace it with a structure as close to the original dome shape as possible but with modern functionality. We envision a structure with partial solid walls near the ground, then lath on upper walls and top, possibly cross shaped with doors at ends of the arms, and a domed center for taller plants. Should have “wood look” or at least maintain original sensibility since it is beloved as is, but needs a durable material! Function—house the collection of shade-requiring plants including prehistoric plants, subtropical plants, and others. Design should include space for plants inside around the edges and a wide walkway in a circle around a central display, suitable for tour groups, small gatherings, and photography. Arms extending in cross shape could house additional plants, displays, even sale plants. |  |  | Pre-Programming | Kathryn Uhrich | Jose Wudka | Jodie Holt |  | Fernando Nunez | 2 |  |  | FALSE |  |  | 44299 | Meeting w/ client regarding budget | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3652 | 3652 |  | FALSE | FAC-PLNG-DESIGN-CONST | 266 Frost Ct. Fence, Electric Meter, Lighting, Irrigation | 266 Frost Court - Install fence utilizing rod iron gates already on hand at BG; install electrical meter and lighting for security purposes; install battery operated irrigation. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Daneca Stevens |  |  |  | FALSE |  |  | 44425 | New (8/17/21) | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
9066 | 9066 |  | FALSE | PB&A | DM(FY20) Sproul HVAC | Equipment/Controls - Replace Heat Exchangers/VFD Pumps |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Daneca Stevens |  |  |  | FALSE | 226000 |  |  | TBD (Assigned in July) | [12 empty] | PD&C | 0 | 1900 | 2021-09-16
9065 | 9065 |  | FALSE | PB&A | DM(FY20) Olmsted HVAC Repairs to Air Handlers | Equipment/Controls - Repairs to Air Handlers |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Vilma Kern |  |  |  | FALSE | 200000 |  |  | Programming | [12 empty] | PD&C | 0 | 1900 | 2021-09-16
9064 | 9064 |  | FALSE | PB&A | DM(FY20) Olmsted HVAC Replace Economizers | Equipment/Controls: Replace economizers for fresh air controls for all Air handlers |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Vilma Kern |  |  |  | FALSE | 200000 |  |  | Programming | [12 empty] | PD&C | 0 | 1900 | 2021-09-16
9063 | 9063 |  | FALSE | PB&A | DM(FY20) Boyce Building Systems Improvements | Provide improvements to antiquated mechanical-electrical-plumbing systems to extend building useful life |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Tameesha Hayes |  |  |  | FALSE | 900000 |  |  | Programming | [12 empty] | PD&C | 0 | 1900 | 2021-09-16
3650 | 3650 |  | FALSE | CNAS | Greenhouse 16-3 Rebuild Estimate | We need an estimate to rebuild greenhouse 16-3 that burned down in a fire |  |  | Pre-Programming (Insurance Claim) | Kathryn Uhrich | Jose Wudka | Sue Lee |  | Scott Donnell | 13 |  |  | FALSE |  |  | 44410 | Programming | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3642 | 3642 |  | FALSE | CAP PROG | South District Planning Study | The “South District” presents a unique opportunity to create a strong identity for academic and research expansion across the campus loop road with an emphasis on creating a transformative and synergistic new campus neighborhood. Its hillside location makes it highly visible from the freeway and the Core Campus, presenting a significant opportunity to enhance campus identity. The site’s high elevation also gives it unobstructed views outward. A holistic and integrated planning framework for its development is important to ensure alignment with broad planning strategies and principles in place for the campus, as established in land planning per the DRAFT 2021 Long Range Master Plan and the more detailed physical planning vision from the 2016 Physical Master Plan Study for this “opportunity site”, and its immediate context. The upcoming effort to update the campus’ Physical Design Framework document will further analyze the unique opportunities afforded by the South District, and leverage the design of the School of Business Building to establish organizing principles for how the area could be optimally redeveloped to its highest potential. |  |  | Programming (Study) | Jacqueline Norman | Sharyl Murdock | Uma R. |  | Uma R. | 19 |  |  | FALSE | 51000 |  | 44357 | Complete Study | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3623 | 3623 |  | FALSE | CNAS | NRS Prop 68 Study - Boyd | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Fernando Nunez | 7 |  |  | FALSE |  |  | 44229 | Pending submittal of Prop 68 items | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3618 | 3618 |  | FALSE | CNAS | NRS Prop 68 Study-James Reserve | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Fernando Nunez | 8 |  |  | FALSE | 8380 |  | 44229 | Pending submittal of Prop 68 items | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3391 | 3391 |  | FALSE | CNAS | NRS Motte Rimrock Res Cost Study | Requesting recheck and recost of formal estimate for Motte Reserve Prop 84 for the Natural Reserve System. The former estimate was $763K. Purpose of study is to confirm, or augment the initial project valuation included with the Proposition 84 NRS grant application to install new structures at the Motte Rimrock Reserve site. |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Kimberly Hammond, D. McWilliams |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 43041 | Pending submittal of Prop 68 items | [12 empty] | PD&C | 0 | 2017 | 2021-09-16
3645 | 3645 |  | FALSE | PB&A | Falkirk Seismic Rating Study | FALKIRK STRUCTURAL STUDY - provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. |  |  | Programming (Study) | Gerry Bomotti | TBD | Sean Hatfield |  | D.Hecht/J.Franklin | 2 |  |  | FALSE |  |  | 44389 | Complete Study | [12 empty] | PD&C | 0 | 2021 | 2021-09-16
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Scott Donnell | 10 |  |  | FALSE | 65000 |  | 43528 | Complete Study | [12 empty] | PD&C | 0 | 2019 | 2021-09-16
99p000001 |  | 99p000001 | FALSE | ATHLETICS | Test | test |  | 1234 | PROJECT INTAKE | Tamica Smith Jones | Joe Erbland | Test |  | Enrico Baez |  | x |  | FALSE |  |  | 44424 | [13 empty] | FS | 0 | 2021 | 2021-09-16
22P000006 |  | 22P000006 | FALSE | CAMPUS | SL5 MRB 4210 - INSTALL AC & ELECTRICAL INFRASTRUCTURE | We have a project at MRB 4210 where we will be installing Air conditioning and electrical infrastructure to accommodate equipment that will be relocated from Batchelor Hall to MRB which is a result of the Batchelor Hall renovation. |  | 4210 | PROJECT INTAKE |  |  | SHARYL MURDOCK | GERRY BOMOTTI | Dan Lerman |  | 1 |  | FALSE |  |  | 44389 | Work on plans and apply for building permit | 44445 | 44498 |  |  |  | 8/2/21, DL: We are currently in the design phase and still trying to verify the logistics of the project. We are planning to apply for a building permit in the next 2- 3 weeks……… |  | Dan Lerman |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-09-16
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | [12 empty] | PD&C | 0 | 1900 | 2021-09-16
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2022 | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 20 |  |  | FALSE | 0 |  | 43007 | Project pushed to 2022 | [12 empty] | PD&C | 0 | 2017 | 2021-09-16
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 43920 | Projects to be assigned | [12 empty] | PD&C | 0 | 2020 | 2021-09-16
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | MARLAN & ROSEMARY BOURNS HALL | B0328E | QUEUE TO START | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Enrico Baez |  | R1 | R1 | FALSE |  |  | 43774 | [6 empty] | 1/19/21, DL: Todd has the estimate. Sent follow up email to Todd requesting update or FAU number………………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | 0 | 2019 | 2021-09-16 |  | 1
21P000198 |  | 21P000198 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 409 - PATCH & PAINT (NEW FACULTY) | PATCH & PAINT |  | 409 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44351 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000146 |  | 21P000146 | FALSE | BCOE | SL5 BOURNS A308 - OFFICE PATCH & PAINT | PATCH & PAINT |  | A0308 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 44272 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000011 |  | 21P000011 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 414 - PATCH & PAINT | PATCH & PAINT |  | 414 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 44025 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
21P000154 |  | 21P000154 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 455 - MINOR PATCH & PAINT TOUCH UP | PATCH & PAINT (NEW DEAN) |  | 455 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44288 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000189 |  | 21P000189 | FALSE | BCOE | SL5 CHUNG HALL 0355 - WALLS NEED TO BE PATCHED AND PAINTED | PATCH & PAINT |  | 355 | QUEUE TO START | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | PAUL DITTY |  | X |  | FALSE |  |  | 44343 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000213 |  | 21P000213 | FALSE | BCOE | SL5 CHUNG HALL 0452 - PATCH AND PAINT NEW FACULTY | PATCH & PAINT |  | 452 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44376 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000214 |  | 21P000214 | FALSE | BCOE | SL5 CHUNG HALL NEW FACULTY OFFICE 454 - PATCH & PAINT | PATCH & PAINT |  | 454 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44376 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000207 |  | 21P000207 | FALSE | BCOE | SL5 BOURNS HALL A325 OFFICE - PATCH & PAINT INCOMING FACULTY | PATCH & PAINT |  | A0325 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 44365 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 150 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | ANDREA HILDAGO, SUSAN KOMURA | DAN LERMAN |  | 2 |  | FALSE |  |  | 43844 | Order material once permit is approved | 44361 | 44500 |  |  |  | 08/02/21, DL: The plans and permit are approved. This is a large project and it will consume our electricans for at least 4- weeks. At the current time we are working on completing several other projects. Once we are caught up on the noted projects, we will schedule the work. Paul Richardson is currently aware of the plan noted above.....7/15/21, DL: The engineering is complete. We submitted the plans and applied for the building permit last week. Once the permit is approved, we will order material and schedule the work…….5/14/21, DL: We are still working on the contract to be approved for the electrical engineer before we can proceed…….4/15/21, DL: We had a meeting with the engineer this week and we should be applying for a permit within the next three weeks…….3/1/21, DL: We will reach out to the electrical engineer this week…….1/19/21, DL: This project will require engineered plans. This is a priority 2 project. We will start the plans and permit process when all priority #1 projects are complete. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-09-16
21P000058 |  | 21P000058 | FALSE | CHASS | SL5 HUMNITIES 3413 (DEAN SUITE) NAIL REMOVAL, PATCH, AND PAINT | PATCH & PAINT |  | 3413 | QUEUE TO START | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | PAUL DITTY |  | X |  | FALSE |  |  | 44068 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
20P000387 |  | 20P000387 | FALSE | CHASS | SL5 HMSS RM 3610 - PLEASE PATCH AND PAINT WALL | PATCH & PAINT |  | 3610 | QUEUE TO START | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | PAUL DITTY |  | X |  | FALSE |  |  | 43892 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
22P000022 |  | 22P000022 | FALSE | CHASS | SL5 HUMANITIES A3414 - NAIL REMOVAL, PATCH, AND PAINT | PATCH & PAINT |  | 3414 | QUEUE TO START | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | PAUL DITTY |  | X |  | FALSE |  |  | 44406 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
20P000321 |  | 20P000321 | FALSE | CHASS | SL5 UNIV THEATRE 400A - PAINT LOBBY | PATCH & PAINT |  | 0400A | QUEUE TO START | Juliet McMullin | Cindy Williams | ALBERT FETTER |  | PAUL DITTY |  | X |  | FALSE |  |  | 43845 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
21P000190 |  | 21P000190 | FALSE | CHASS | SL5 PSYCHOLOGY 3119 - PATCH & PAINT / REMOVE WALL FIXTURE | PATCH & PAINT / REMOVE WALL FIXTURE |  | 3119 | QUEUE TO START | Juliet McMullin | Cindy Williams | AERIKA LOYD |  | PAUL DITTY |  | X |  | FALSE |  |  | 44343 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
20P000384 |  | 20P000384 | FALSE | CHASS | SL5 CHASS INTS 3111A - PATCHING HOLES AND PAINTING THE WALLS | PATCH & PAINT |  | 3111A | QUEUE TO START | Juliet McMullin | Cindy Williams | LESLIE ANN GERRETSE |  | PAUL DITTY |  | X |  | FALSE |  |  | 43888 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS BUILDING | 3009 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 43749 | [6 empty] | 05/05/21 O-ANS: Updated contact info from Dr. Wudka. 05/05/21 O-ANS: Multiple failed attempts to contact requestor to schedule work. Project placed on HOLD and emailed CNAS partner to continue to hold or cancel. 02/03/21 O-ANS: Reminder email sent to customer that PAINT ONLY portion would be completed and not the door removal at this time. Customer can resubmit request in next prioriization cycle…. 11/06/20 O-JLO: Emailed requestor and alternate regarding paint portion only, and that door/drywall removal will not occur during this time …. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. FS to confirm with customer that we can only complete the painting at this time but not the removal of the door…. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure." | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | 0 | 2019 | 2021-09-16
21P000151 |  | 21P000151 | FALSE | CNAS | SL5 SPIETH HALL 3310 - NEW FACULTY OFFICE - PATCH & PAINT | PATCH & PAINT |  | 3310 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | TRUE |  |  | 44286 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000134 |  | 21P000134 | FALSE | CNAS | SL5 LIFE SCIENCES 2550 - CONF ROOM PATCH & PAINT | PATCH & PAINT |  | 2550 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | FALSE |  |  | 44259 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000155 |  | 21P000155 | FALSE | CNAS | SL5 OLMSTED 1342 - NEW FACULTY ARIVAL CARPET CLEAN / PATCH/PAINT | CARPET CLEAN / PATCH & PAINT |  | 1342 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | SOPHIA JURISCH |  | PAUL DITTY |  | X |  | TRUE |  |  | 44288 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 43794 | [6 empty] | 05/06/21 O-ANS: Updated contact person info from Dr. Wudka and reaching out to coordinate. 5/05/21 O-ANS: Multiple failed attempts to contact requestor to schedule work. Project placed on HOLD and emailed CNAS partner to continue to hold or cancel. 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-09-16
21P000162 |  | 21P000162 | FALSE | CNAS | SL5 ENTOMOLOGY 0282 - PAINT NEW FACULTY MEMBER'S OFFICE | PAINT NEW FACULTY MEMBER'S OFFICE |  | 0282 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 44300 | [12 empty] | Winter 2021 | FS | 0 | 2021 | 2021-09-16
21P000212 |  | 21P000212 | FALSE | CNAS | SL5 LIFE SCIENCES 0418D - PAINT CEILING, DOOR, DOOR FRAME | PATCH & PAINT (RESEARCH RELATED) |  | 418D | QUEUE TO START | Kathryn Uhrich | Jose Wudka | DIERK BIGGS |  | PAUL DITTY |  | X |  | FALSE |  |  | 44376 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000157 |  | 21P000157 | FALSE | CNAS | SL5 PHYSICS 1119 - PATCH AND PAINT FOR NEW HIRE | PATCH & PAINT |  | 1119 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | PAUL DITTY |  | X |  | TRUE |  |  | 44292 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT | PATCH & PAINT |  | 317 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | FALSE |  |  | 43879 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
20P000401 |  | 20P000401 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 FS ANNEX B 5 & 6 - PAINT SUPERVISORS OFFICE | PATCH & PAINT |  |  | QUEUE TO START | Susan Marshburn | Da Lan Dinh | MARK JONES |  | PAUL DITTY |  | X |  | FALSE |  |  | 43903 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
20P000282 |  | 20P000282 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 PIERCE HALL 3374 - RENOVATE GA CLASSROOM SUMMER 2020 | Project to renovate GA classroom in Pierce Hall for prioritization and execution in Summer 2020. |  | 3374 | QUEUE TO START | Susan Marshburn | Da Lan Dinh | DA LAN DINH |  | Paul Ditty |  | X |  | FALSE |  |  | 43839 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-09-16
21P000211 |  | 21P000211 | FALSE | GRAD DIV | SL5 UNIV OFFICE BLD 0144 - PATCH & PAINT | PATCH & PAINT |  | 144 | QUEUE TO START | Shaun Bowler | Kennett Lai | CARLOS RIVAS |  | PAUL DITTY |  | X |  | FALSE |  |  | 44371 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000158 |  | 21P000158 | FALSE | PB&A | SL5 POLICE BUILDING 0100 - PAINT ATRIUM | Request to Paint Atrium |  | 0100 | QUEUE TO START | Gerry Bomotti | TBD | ROCIO STERN |  | Paul Ditty |  |  |  | FALSE |  |  | 44291 | [6 empty] | 09/09/21 O-ANS: Project is CORE location and does not require FAU. Assigned to PDY to proceed. |  | Paul Ditty |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-09-16
21P000215 |  | 21P000215 | FALSE | SoB | SL5 ANDERSON 0202 - PATCH/PAINT NEW HIRE | PATCH & PAINT |  | 202 | QUEUE TO START | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | PAUL DITTY |  | X |  | TRUE |  |  | 44377 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
22P000027 |  | 22P000027 | FALSE | SOM | SL5 WEBBER HALL 1143 - PAINT/PATCH | PATCH & PAINT |  | 1143 | QUEUE TO START | Deborah Deas | Deborah Trujillo | CLARK HAPEMAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 44363 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000204 |  | 21P000204 | FALSE | SOM | SL5 WEBBER HALL 1126A - PAINT/PATCH | PATCH & PAINT |  | 1126A | QUEUE TO START | Deborah Deas | Deborah Trujillo | CLARK HAPEMAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 44363 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000144 |  | 21P000144 | FALSE | SOM | SL5 WEBBER HALL 1116A - SHELVING REMOVED /PATCH & PAINT | SHELVING REMOVED /PATCH & PAINT |  | 1116A | QUEUE TO START | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | PAUL DITTY |  | X |  | FALSE |  |  | 44272 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-09-16
21P000191 |  | 21P000191 | FALSE | SOM | SL5 ORBACH LIB BASEMENT - PAINT WALL AT NEW SIM CENTER | PATCH & PAINT |  | BASEMENT | QUEUE TO START | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | PAUL DITTY |  | X |  | FALSE |  |  | 44344 | [6 empty] | 08/19/21 D-MMN: taped wall applied two coats finish. pulled tape and cleaned up. |  | PAUL DITTY |  |  | 2021-08-19 | FY 21-22 | FS | 0 | 2021 | 2021-09-16 | FY 21-22
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES | PATCH & PAINT |  | 200 | QUEUE TO START | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | X |  | FALSE |  |  | 43868 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
20P000374 |  | 20P000374 | FALSE | VC-STU AFF | SL5 HEALTH SERVICES 334 - OFFICES PAINTED AND CONFERENCE ROOM | PATCH & PAINT |  | 334 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | X |  | FALSE |  |  | 43881 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
21P000088 |  | 21P000088 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BUILDING 100D - FILL HOLES/PAINT | PATCH & PAINT |  | 0100D | QUEUE TO START | Brian Haynes | Cathy Eckman | WILLIAM RALL |  | PAUL DITTY |  | X |  | FALSE |  |  | 44116 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
20P000372 |  | 20P000372 | FALSE | VC-STU AFF | SL5 HEALTH SERVICES 391 - OFFICES PAINTED AND CONFERENCE ROOM | PATCH & PAINT |  | 391 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | X |  | FALSE |  |  | 43881 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-09-16
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | Re-bid | Gerry Bomotti | Sharyl Murdock | Daneca Stevens |  | Daneca Stevens | 2 |  |  | FALSE | 507364 |  | 43676 | Award Contract | 44501 | 44562 | [10 empty] | PD&C | 0 | 2019 | 2021-09-16
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | Re-bid | Gerry Bomotti | TBD | Sharyl Murdock |  | John Franklin | 15 |  |  | FALSE | 33099342.06 |  | 42353 | Award Contract | 44531 | 45474 | [10 empty] | PD&C | 0 | 2015 | 2021-09-16
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Blythe Wilson | 1 |  |  | FALSE | 3350000 |  | 42719 | Design Builder Prequalification | 44830 | 45462 | [10 empty] | PD&C | 0 | 2016 | 2021-09-16
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 17 |  |  | FALSE | 2586581 |  | 43410 | Complete Review | [12 empty] | PD&C | 0 | 2018 | 2021-09-16
20P000067 |  | 20P000067 | FALSE | BCOE | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM | BOURNS | B-Wing | TO BE PERFORMED BY PD&C | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | R1 |  | FALSE |  |  | 42688 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Replace access controls at BCOE WCH & Bourns bldgs. |  | 2020-11-19 | Fall 2019 | FS | 0 | 2016 | 2021-09-16 | FY 20-21 | 1
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | Modify the existing room in Soil House 1 (attached to the Delphino Lab at the Rubidoux Facilities) to expand CCPP quarantine services to include USDA/CDFA compliance for installation of new Economic Development Administration (EDA) citrus growth chambers. | DELFINO HHSE |  | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 43245 | Research and plan development | [5 empty] | 12/7/20, DL: This project will be managed by PD&C…..9/30/20, DL: Project is still on Hold until Furhther notice………...8/5/20, DL: WE will work on plans in the next 30- 45 days……………6/17/20, DL: This project is under review and is on hold until further notice………10/3/19 O-ANS: Plan Development per Minor Reno Meeting. 10/1/19,DL; We are getting ready to start the plans as we are currently conducting resarch on products that will meet the needs of the space……………..5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman |  | YES | 2020-12-07 | Summer 2018 | FS | 0 | 2018 | 2021-09-16 | FY 20-21
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB. Patch Paint walls, replace flooring, refinish wood cabinets and sinks. | SPIETH | 2349 | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 5 |  | FALSE |  |  | 43516 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold……….12/11/19: O-ANS: Reassigned as project allotment - priority #5 for Winter 2020. 11/27/19 O-ANS: Placed on Hold for re-prioritization by client for Winter 2020. | 2020-02-27 | Enrico Baez | Patch and paint and extra work to upgrade an old lab that we are now inhabiting. In addition to painting, we need to have floors re-surfaced, cabinets re-stained, and counter tops re-surfaced, if possible. There is also a metal sink that could be polished. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-09-16 | FY 20-21
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | JEANETTE AND RUPERT COSTO HALL |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN O'BRIEN |  | Enrico Baez |  | R1 | R2 | FALSE |  |  | 43762 | [6 empty] | 2/25/2021 E. Baez Project will require several trades to complete. FS unable to support recharge project. Asked Brendan O'Brien to submit Project Request through CPMS for PD&C. …...02/16/21 O-ANS: Will require plans/permits and may need to go to PD&C due to scope of work which includes construction. Will confirm with client before instructing to submit request to CPMS…. 01/19/21, DL: Enrico B. Will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2021-02-25 | Winter 2021 | FS | 0 | 2019 | 2021-09-16 | FY 20-21 | 1
3590b | 3590b |  | FALSE | PB&A | DMFI(FY17-20) Physics Elevator Modernization | Physics Elevator Modernization | PHYSICS |  | In Construction | Gerry Bomotti | TBD | Ben Kochevar |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 2019-11-27 | Submittal approval | 2021-07-01 | 2022-02-01 | [10 empty] | PD&C | 0 | 2019 | 2021-10-01
3590a | 3590a |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Multiple Projects | Multiple projects approved as part of the FY2017-19 DMFI program will comprise one major capital project to facilitate project management by Facilities, Planning, Design and Construction. Individual projects will be identified with cost centers to aid with tracking. All projects managed within this group will have a total budget of less than $1 million. |  |  | Projects to be assigned | Susan Marshburn | Da Lan Dinh | Susan McFadden |  | Scott Donnell | 4 |  |  | FALSE | 2178000 |  | 2020-03-30 | Projects to be assigned | [12 empty] | PD&C | 0 | 2020 | 2021-10-01
3515d | 3515d |  | FALSE | PB&A | Multiple SF6 Primary Switches | Sub-project of 950568 |  |  | Design | Gerry Bomotti | TBD | John Franklin |  | John Franklin | 2 |  |  | FALSE |  |  | 2021-03-01 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3515b | 3515b |  | FALSE | PB&A | DM(FY18) Elec Substation & Infra. Renewal | Improvement of UCR's electrical infrastructure which are old and antiquated. Repairs and upgrades are necessary to reduce disruption of research and academic activities. High voltage cable feeders, electrical switches and transformers need to be replace and the electrical systems transitioned to a robust loop distribution system. Engineering and evaluation to detail and prioritize specific improvements. |  |  | In Programming | Gerry Bomotti | TBD | Ron Rector |  | John Franklin | 2 |  |  | FALSE | 10290000 |  | 2019-03-08 | Complete Programming | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3228b | 3228b |  | FALSE | CNAS | Rubidoux Screenhouse Conv | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. |  |  | In Bidding (Phase 2) | Kathryn Uhrich | Jose Wudka | Sabrina Schuster |  | Tameesha Hayes | 6 |  |  | FALSE |  |  | 2016-12-06 | Award Contract (Phase 2) | 2021-10-01 | 2022-01-01 | [10 empty] | PD&C | 0 | 2016 | 2021-10-01
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY16) Spieth Hall Roof Replacement | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | SPIETH |  | In Design | Susan Marshburn | Da Lan Dinh | ---- |  | Fernando Canon | 7 |  |  | FALSE | 432510 |  | 2016-02-25 | Bidding | 2021-12-01 | 2022-02-01 | [10 empty] | PD&C | 0 | 2016 | 2021-10-01
2970d | 2970d |  | FALSE | CAP PROG | ADA Improvements/Transition Plan | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | Bidding | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Tameesha Hayes | 11 |  |  | FALSE |  |  | 2015-12-02 | Award Contract | [12 empty] | PD&C | 0 | 2015 | 2021-10-01
22P000065 |  | 22P000065 | FALSE | VC-UNIV ADV | SL5 CAMPUS INTERIOR - HANG BANNERS, INSTALL HARDWARE | Banners to be hung within Campus interior. Installation of banner hardware on Pierce Hall and Skye Hall. |  |  | QUEUE TO START | Peter Hayashida | Naysia Caldwell | LISA CUSICK | BRAD ROWE | Dan Lerman |  |  |  | FALSE |  |  | 2021-09-09 | [6 empty] | 09/29/21 O-ANS: Converted to project per Paul D / Dan L to manage installation of banner hardware. Coordinating with customer Brad Rowe re: specs of banners prior to install. |  | Dan Lerman |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
22P000027 |  | 22P000027 | FALSE | SOM | SL5 WEBBER HALL 1143 - PAINT/PATCH | PATCH & PAINT |  | 1143 | QUEUE TO START | Deborah Deas | Deborah Trujillo | CLARK HAPEMAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-06-16 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
22P000022 |  | 22P000022 | FALSE | CHASS | SL5 HUMANITIES A3414 - NAIL REMOVAL, PATCH, AND PAINT | PATCH & PAINT |  | 3414 | QUEUE TO START | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-07-29 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
22P000008 |  | 22P000008 | FALSE | VC-RED | SL5 MRB VARIOUS LAB SUPPORT - IACUC INSP TINTED WINDOWS NEEDED | ER IACUC INSPECTION- TINTED WINDOW NEEDED ON LAB SUPPORT ROOMS. ORIGINAL SERVICE REQUEST 22S000637 See list of rooms for window tint request. Korzus 1204E 1204F 1212A 1212B 1229B Zagha 1212A 1212B 1204F 1204E 1231C Abdulrazak 2204A 2204G 2204F 2208B Binder 3214 3218 3215 Cho 3216 3219 Tiwari- Woodruff 3204G Hickmott 2221 Zheng 2225 2213-C |  |  | COMPLETE | Rodolfo Torres | Laura Manor | TARA BARTHOL |  | Enrico Baez |  | R1 |  | TRUE |  |  | 2021-07-14 |  | 2021-07-29 |  |  |  |  | 09/02/2021 ANS: Project is complete per EBZ. 07/27/21 EBZ: Project to begin 07/29/21. |  | Enrico Baez |  |  | 2021-08-25 | Summer 2021 | FS | 0 | 2021 | 2021-10-01 | FY 21-22 | 1
22P000006 |  | 22P000006 | FALSE | CAMPUS | SL5 MRB 4210 - INSTALL AC & ELECTRICAL INFRASTRUCTURE | We have a project at MRB 4210 where we will be installing Air conditioning and electrical infrastructure to accommodate equipment that will be relocated from Batchelor Hall to MRB which is a result of the Batchelor Hall renovation. |  | 4210 | PROJECT INTAKE |  |  | SHARYL MURDOCK | GERRY BOMOTTI | Dan Lerman |  | 1 |  | FALSE |  |  | 2021-07-12 | Work on plans and apply for building permit | 2021-09-06 | 2021-10-29 |  |  |  | 8/2/21, DL: We are currently in the design phase and still trying to verify the logistics of the project. We are planning to apply for a building permit in the next 2- 3 weeks……… |  | Dan Lerman |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-10-01
21P000215 |  | 21P000215 | FALSE | SoB | SL5 ANDERSON 0202 - PATCH/PAINT NEW HIRE | PATCH & PAINT |  | 202 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-06-30 | [6 empty] | 09/29/21 D-JPO: PAINTED CLEANED UP JOB DONE |  | PAUL DITTY |  |  | 2021-09-29 | FY 21-22 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000214 |  | 21P000214 | FALSE | BCOE | SL5 CHUNG HALL NEW FACULTY OFFICE 454 - PATCH & PAINT | PATCH & PAINT |  | 454 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-06-29 | [6 empty] | 09/15/21 B-SBT: pull masking, clean room 09/14/21 B-SBT: sand, prime, paint 09/13/21 B-SBT: patch and mask |  | PAUL DITTY |  |  | 2021-09-15 | FY 21-22 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000213 |  | 21P000213 | FALSE | BCOE | SL5 CHUNG HALL 0452 - PATCH AND PAINT NEW FACULTY | PATCH & PAINT |  | 452 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-06-29 | [6 empty] | 09/15/21 B-SBT: paint room, pull masking, clean room |  | PAUL DITTY |  |  | 2021-09-15 | FY 21-22 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000212 |  | 21P000212 | FALSE | CNAS | SL5 LIFE SCIENCES 0418D - PAINT CEILING, DOOR, DOOR FRAME | PATCH & PAINT (RESEARCH RELATED) |  | 418D | QUEUE TO START | Kathryn Uhrich | Jose Wudka | DIERK BIGGS |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-06-29 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
21P000211 |  | 21P000211 | FALSE | GRAD DIV | SL5 UNIV OFFICE BLD 0144 - PATCH & PAINT | PATCH & PAINT |  | 144 | QUEUE TO START | Shaun Bowler | Kennett Lai | CARLOS RIVAS |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-06-24 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
21P000207 |  | 21P000207 | FALSE | BCOE | SL5 BOURNS HALL A325 OFFICE - PATCH & PAINT INCOMING FACULTY | PATCH & PAINT |  | A0325 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-06-18 | [6 empty] | 09/09/21 B-SBT: paint room, pull masking, install plates, clean room 09/08/21 D-JPO: prep room |  | PAUL DITTY |  |  | 2021-09-09 | FY 21-22 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000204 |  | 21P000204 | FALSE | SOM | SL5 WEBBER HALL 1126A - PAINT/PATCH | PATCH & PAINT |  | 1126A | QUEUE TO START | Deborah Deas | Deborah Trujillo | CLARK HAPEMAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-06-16 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
21P000198 |  | 21P000198 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 409 - PATCH & PAINT (NEW FACULTY) | PATCH & PAINT |  | 409 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-06-04 | [6 empty] | 09/20/21 B-SBT: clean room 09/17/21 B-SBT: paint room |  | PAUL DITTY |  |  | 2021-09-20 | FY 21-22 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000191 |  | 21P000191 | FALSE | SOM | SL5 ORBACH LIB BASEMENT - PAINT WALL AT NEW SIM CENTER | PATCH & PAINT |  | BASEMENT | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-05-28 | [6 empty] | 08/19/21 D-MMN: taped wall applied two coats finish. pulled tape and cleaned up. |  | PAUL DITTY |  |  | 2021-08-19 | FY 21-22 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000190 |  | 21P000190 | FALSE | CHASS | SL5 PSYCHOLOGY 3119 - PATCH & PAINT / REMOVE WALL FIXTURE | PATCH & PAINT / REMOVE WALL FIXTURE |  | 3119 | QUEUE TO START | Juliet McMullin | Cindy Williams | AERIKA LOYD |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-05-27 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
21P000189 |  | 21P000189 | FALSE | BCOE | SL5 CHUNG HALL 0355 - WALLS NEED TO BE PATCHED AND PAINTED | PATCH & PAINT |  | 355 | COMPLETE | Christopher Lynch | Todd Ambriz | SARA GALLOWAY |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-05-27 | [6 empty] | 09/22/21 D-JPO: patched sanded spot primed and masked 09/23/21 D-JPO: finished painting cleaned up |  | PAUL DITTY |  |  | 2021-09-23 | FY 21-22 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000183 |  | 21P000183 | FALSE | PB&A | SL5 OBAN A&B - PROJECT PORCH REPAIRS 2, 10, 18, 26 | TRENTON MABEE SL5 PROJECT FOR OBAN A & B APT 2, 10, 18, AND 16. PORCH REPAIRS. ZONE MAINTENANCE CARPENTER SHOP |  |  | COMPLETE | Gerry Bomotti | TBD | TRENTON MABEE |  | Chris Pillen |  |  |  | FALSE |  |  | 2021-05-13 | [6 empty] | 09/02/21 O-ANS: Complete per Chris P. 08/06/21 O-ANS: Assigned to Trenton Mabee to manage project. |  | Chris Pillen |  |  | 2021-09-02 | Summer 2021 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000174 |  | 21P000174 | FALSE | BCOE | SL5 BOURNS HALL OFFICE B355 - PATCH & PAINT | PATCH & PAINT |  | B0355 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-05-05 | [6 empty] | 09/13/21 O-ANS: Complete per Paint Supervisor. |  | PAUL DITTY |  |  | 2021-09-13 | FY 21-22 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000173 |  | 21P000173 | FALSE | BCOE | SL5 BOURNS HALL OFFICE B353 - PATCH & PAINT (POSS TOUCH UP) | PATCH & PAINT |  | B0353 | CANCELED BY CLIENT | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-05-05 | [6 empty] | CANCELLED BY REQUESTOR 9/13/21 PDY |  | PAUL DITTY |  |  | 2021-09-13 | FY 21-22 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000162 |  | 21P000162 | FALSE | CNAS | SL5 ENTOMOLOGY 0282 - PAINT NEW FACULTY MEMBER'S OFFICE | PAINT NEW FACULTY MEMBER'S OFFICE |  | 0282 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 2021-04-14 | [12 empty] | Winter 2021 | FS | 0 | 2021 | 2021-10-01
21P000160 |  | 21P000160 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 CHAPMAN HALL 109 - REPAIR COUNTERTOPS | REPAIR COUNTERTOPS IN CHAPMAN HALL 109 |  | 109 | COMPLETE | Susan Marshburn | Da Lan Dinh | DAN LERMAN |  | Dan Lerman |  |  |  | FALSE |  |  | 2021-08-06 | [6 empty] | 09/02/21 O-ANS: Project complete per Dan L. |  | Dan Lerman |  |  | 2021-09-02 | Summer 2021 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000158 |  | 21P000158 | FALSE | PB&A | SL5 POLICE BUILDING 0100 - PAINT ATRIUM | Request to Paint Atrium |  | 0100 | QUEUE TO START | Gerry Bomotti | TBD | ROCIO STERN |  | Paul Ditty |  |  |  | FALSE |  |  | 2021-04-05 | [6 empty] | 09/09/21 O-ANS: Project is CORE location and does not require FAU. Assigned to PDY to proceed. |  | Paul Ditty |  |  |  | Summer 2021 | FS | 0 | 2021 | 2021-10-01
21P000157 |  | 21P000157 | FALSE | CNAS | SL5 PHYSICS 1119 - PATCH AND PAINT FOR NEW HIRE | PATCH & PAINT |  | 1119 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | DAVID NEFF |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-04-06 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
21P000155 |  | 21P000155 | FALSE | CNAS | SL5 OLMSTED 1342 - NEW FACULTY ARIVAL CARPET CLEAN / PATCH/PAINT | CARPET CLEAN / PATCH & PAINT |  | 1342 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | SOPHIA JURISCH |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-04-02 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
21P000154 |  | 21P000154 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 455 - MINOR PATCH & PAINT TOUCH UP | PATCH & PAINT (NEW DEAN) |  | 455 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-04-02 | [6 empty] | 09/15/21 B-SBT: paint wall, pull masking, clean room |  | PAUL DITTY |  |  | 2021-09-15 | FY 21-22 | FS | 0 | 2021 | 2021-10-01 | FY 21-22
21P000151 |  | 21P000151 | FALSE | CNAS | SL5 SPIETH HALL 3310 - NEW FACULTY OFFICE - PATCH & PAINT | PATCH & PAINT |  | 3310 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | TRUE |  |  | 2021-03-31 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
21P000146 |  | 21P000146 | FALSE | BCOE | SL5 BOURNS A308 - OFFICE PATCH & PAINT | PATCH & PAINT |  | A0308 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-03-17 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
21P000144 |  | 21P000144 | FALSE | SOM | SL5 WEBBER HALL 1116A - SHELVING REMOVED /PATCH & PAINT | SHELVING REMOVED /PATCH & PAINT |  | 1116A | QUEUE TO START | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-03-17 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
21P000137 |  | 21P000137 | FALSE | SOM | SL5 WEBBER HALL - ACCESS CONTROL | Per attached Sales Quote 43830-7 dated 11/6/2020, from Enterprise Security in Tustin, please proceed with the proposal, planning. permit, and contract to complete this project. |  | 1247 | COMPLETE | Deborah Deas | Deborah Trujillo | DEBORAH TRUJILLO | CYNTHIA CAROLINA | Dan Lerman |  | R1 |  | FALSE |  |  | 2021-03-09 | Final inspection and payment | [5 empty] | 7/15/21, DL; This project is complete. We still need to conduct the final inspection. There was a problem identified during the project where a repair is needed via an FAU number. We will conduct the repair under an SL6. Cynthia Carolina is aware of the additional needed repair that was not part of the scope or work……/9/21, O-DMS: EMAIL TO DAN LERMAN PROJECT # AND ASSIGNED TO J-DLN. |  | Dan Lerman |  |  | 2021-07-15 | Winter 2021 | FS | 0 | 2021 | 2021-10-01 | FY 21-22 | 1
21P000134 |  | 21P000134 | FALSE | CNAS | SL5 LIFE SCIENCES 2550 - CONF ROOM PATCH & PAINT | PATCH & PAINT |  | 2550 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | FALSE |  |  | 2021-03-04 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2021 | 2021-10-01
21P000111 |  | 21P000111 | FALSE | CHASS | SL5 WATKINS 2144 - PATCH, PAINT & NEW FLOORING FOR NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Wei Zhao. He started working July 1, 2020. | GORDON S. WATKINS HALL | 2144 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-11-18 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
21P000110 |  | 21P000110 | FALSE | CHASS | SL5 WATKINS 2146 - PATCH, PAINT AND NEW FLOORING NEW FACULTY | Please patch, paint the room and install new flooring for new faculty member, Professor Amy Kroska. She started working July 1, 2020. | GORDON S. WATKINS HALL | 2146 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-11-18 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
21P000109 |  | 21P000109 | FALSE | CHASS | SL5 WATKINS HALL 1146 - PATCH, PAINT & NEW FLOORING NEW FACULTY | PATCH, PAINT & NEW FLOORING |  | 1146 | COMPLETE | Juliet McMullin | Cindy Williams | BECKY CAMPBELL |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-11-18 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  | Paul Ditty |  |  | 2021-05-24 | FY 21-22 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
21P000102 |  | 21P000102 | FALSE | VC-RED | SL5 SPIETH HALL VIVARIUM - PATCH & PAINT 348, 352 & 363 | AAALAC Certification updates to rooms 348, 352 & 363 | SPIETH | 348, 352 & 363 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS | YURIDIA REYNOSO | Paul Ditty |  | TBD |  | FALSE |  |  | 2020-10-29 | [6 empty] | 12/08/20 O-ANS: Customer Dierk Biggs confirmed via email that these room updates are complete. |  | Paul Ditty |  |  | 2020-12-08 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
21P000088 |  | 21P000088 | FALSE | VC-STU AFF | SL5 HEALTH SERVICE BUILDING 100D - FILL HOLES/PAINT | PATCH & PAINT |  | 0100D | QUEUE TO START | Brian Haynes | Cathy Eckman | WILLIAM RALL |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-10-12 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-10-01
21P000083 |  | 21P000083 | FALSE | CNAS | SL5 PHYSICS - UPDATE KEYCARD SYSTEM FOR BUILDING | UPDATE KEYCARD SYSTEM FOR BUILDING | PHYSICS BUILDING |  | ESTIMATE | Kathryn Uhrich | Jose Wudka | JOSE WUDKA |  | Enrico Baez |  | R1 |  | FALSE |  |  | 2019-12-19 | Awaiting Response from Client | [5 empty] | 05/13/21 O-ANS: Enrico corresponded with Dr. Wudka on 3/14/2021. He had emailed me stating that the College was going to discuss the project. Still awaiting a response to that inquiry. I follow up today requesting an update. 1/19/21 DL: Enrico is managing this project. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-10-01 |  | 1
21P000079 |  | 21P000079 | FALSE | VC-RED | SL5 PSYCHOLOGY V3 - AAALAC INSPECTION PATCH AND PAINT NEEDED | Patch and paint V3 vivarium and support areas prior to AAALAC inspection. | PSYCHOLOGY BUILDING |  | COMPLETE | Rodolfo Torres | Laura Manor | LESLIE KARPINSKI |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-09-25 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/25/21. 02/25/21 D-BFA: continued painting the black room. Patched in the Quarantine rooms. 02/23/21 D-BFA: Continued painting finish on all green and all repaired cracks. 02/16/21 D-MMN: prepped cracks with caulking. |  | Paul Ditty |  |  | 2021-04-01 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
21P000078 |  | 21P000078 | FALSE | VC-RED | SL5 MRB - QTY 32 -80 FREEZERS CHILLED CONNECTIONS | QTY 32 -80 FREEZERS CHILLED CONNECTIONS | MULTIDISCIPLINARY RESEARCH BUILDING |  | COMPLETE | Rodolfo Torres | Laura Manor | TARA BARTHOL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 2020-09-23 | [6 empty] | 4/15/21, DL: The work is complete. We still need to connect several minus 80 freezers. Tara will check in with us when they are ready to be connected……….1/19/21, DL: the First floor work will be complete today, we will start the 2nd floor this week……………. |  | Enrico Baez |  |  | 2021-04-15 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
21P000058 |  | 21P000058 | FALSE | CHASS | SL5 HUMNITIES 3413 (DEAN SUITE) NAIL REMOVAL, PATCH, AND PAINT | PATCH & PAINT |  | 3413 | COMPLETE | Juliet McMullin | Cindy Williams | JENNIFER HAMILTON |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-08-25 | [6 empty] | 08/16/21 D-MMN: Completed the finish on the walls, and painted window seals in provost office. pulled masking, attached plates. moved what furniture we moved. |  | PAUL DITTY |  |  | 2021-08-16 | FY 21-22 | FS | 0 | 2020 | 2021-10-01 | FY 21-22
21P000049 |  | 21P000049 | FALSE | BCOE | SL5 MS&E 0071 - MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MOVE EXHAUST CONNECTION AND INSTALL NEW OUTLETS | MATERIALS SCIENCE & ENGINEERING | 71 | IN PROGRESS | Christopher Lynch | Todd Ambriz | DONG YAN |  | DAN LERMAN |  | 2 | 3 | FALSE |  |  | 2020-08-06 | Schedule the work once the permit is approved | 2021-06-02 | 2021-09-15 |  |  |  | 8/18/21, DL: The electrical is complete. We are ordering material for the exhaust vents this week. We will schedule the installation when the material is on site……08/02/21, DL: We are still in the plan check review process. Once the permit is approved, we will schedule the work….7/15/21, DL: Plans are complete, we will apply for the building permit today and the permit should be reviewed and approved in the next 2-4 weeks. Once the permit is approved, we will order the material and schedule the work……6/2/21, DL: We will work on the final plans the week of 6/14/21 and try to apply for building permit on or before 6/22/21. Once the permit is approved, we will schedule the work…. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-10-01
21P000037 |  | 21P000037 | FALSE | BCOE | SL5 CHUNG HALL OFFICE 427 - PATCH & PAINT | Paint Only | CHUNG HALL | 427 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-07-31 | [6 empty] | 01/19/21 O-ANS: Paint complete per technician and closed project. 11/30/20 B-SBT: repatch & Paint north wall |  | Paul Ditty |  |  | 2020-11-30 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
21P000019 |  | 21P000019 | FALSE | BCOE | SL5 BOURNS OFFICE A305 - Incoming Faculty/PI Renovations | Bourns Office A305 - Install Plank Floor | MARLAN & ROSEMARY BOURNS HALL | A305 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | 3 | 2 | TRUE |  |  | 2020-07-20 | This project is Complte. | 2021-04-30 | 2021-05-21 |  |  |  | 6/2/21, DL: This project is complete…4/30/21, DL: This project started this week. The paint will be complete next week. The floor will be installed in about two weeks…………..4/1/21, DL: We will schedule the work with in the next three weeks. We are only doing this work early as the two primary trades are available. The damaged window covering will be replaced by a vendor…………..1/19/21, DL: This a priority 3 project. We will start this project when all priority #2 projects are complete………..1/14/21 O-ANS: Updated prioritization to #3 (from #2) per org leadership request. |  | Enrico Baez |  |  | 2021-06-02 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
21P000014 |  | 21P000014 | FALSE | BCOE | SL5 BOURNS HALL OFFICE A149 - PATCH & PAINT HOLES ON WEST WALL | PATCH & PAINT |  | A0149 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-07-14 | [6 empty] | 08/13/21 O-ANS: Project complete per Paint Crew. 08/13/21 D-JPO: cleaned up job done. 08/12/21 D-JPO: sanded spot primed and spot painted two walls. 08/10/21 D-JPO: patched and masked |  | PAUL DITTY |  |  | 2021-08-13 | FY 21-22 | FS | 0 | 2020 | 2021-10-01 | FY 21-22
21P000011 |  | 21P000011 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 414 - PATCH & PAINT | PATCH & PAINT |  | 414 | QUEUE TO START | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-07-13 | [6 empty] | 09/17/21 B-SBT: paint room 09/20/21 B-SBT: clean room |  | PAUL DITTY |  |  | 2021-09-20 | FY 21-22 | FS | 0 | 2020 | 2021-10-01 | FY 21-22
21P000009 |  | 21P000009 | FALSE | CNAS | SL5 CHEMICAL SCI ANA'S LAB - GLOVEBOX SYSTEM | GLOVEBOX SYSTEM | CHEMICAL SCIENCES |  | COMPLETE | Kathryn Uhrich | Jose Wudka | NATASHA GONZALES |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 2020-07-08 | This project is complete….. | 2021-03-08 | 2021-04-23 |  |  |  | 6/2/21, DL; This project is complete……4/15/21, DL This project is complete. When the glove box arrives, we will make the final connections………..4/1/21, DL: Demolition, paint, electrical and venting is done for the glove box. The snorkel parts are ordered. The flooring is ordered and should be here next week. We will schedule the floor install once we have the material on site………….3/15/21, DL: We will demolish the cabinets this week. We will also schedule the paint and floor replacement. The venting for the glove box and snorkel should be ordered this week………3/1/21, DL: The plans were approved last week. We will try and schedule demo this week or early next week……..2/16/21, DL: We submitted plans for building permit but corrrections are needed. We contacted the glove box manufacture for follow-up questions and we are waiting to hear back from them. Once we have confirmation on the needed information, we will resubmit the plans back to the building official……….1/19/21, DL: we will submit plans this week or earlier next ……………. |  | Enrico Baez |  |  | 2021-06-02 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
21P000003 |  | 21P000003 | FALSE | PB&A | SL5 KUCR 2 STATION ROOF - ROOF MAINTENANCE SYSTEM INSTALLATION | The KUCR Station is consistently experiencing roof leaks, causing the interior ceiling to bulge in places and leak in others, so a solution to fix this issue is required. This is a project request to install a monoform roof maintenance system on the KUCR Station roof. This system will not require a roof replacement and we understand that abatement will be required for liability purposes. We are requesting the same roofing system that was used on the KUCR Annex roof project in spring 2020 For reference: WO# 20W026304. Trent Mabee acted as PM. | CC LIND 691 | ROOF | COMPLETE | Gerry Bomotti | TBD | SEAN HATFIELD | MONICA TAYLOR | Enrico Baez |  | R1 |  | FALSE |  |  | 2020-06-26 | [6 empty] | 4/9/2021 E. Baez roof repairs completed…1/20/2021 E. Baez- Proposal for $24,366 received from Rite-Way Roofing.….01/19/21, DL: Enrico is managing this project………….. | 2020-12-02 | Enrico Baez | Remove tripod antenna. Apply spray roof coating to existing roof surface | YES | 2021-04-09 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21 | 1
21P000001 |  | 21P000001 | FALSE | CNAS | SL5 FAWCETT LAB - NEW GROWTH CHAMBER PLACEMENT | NEW GROWTH CHAMBER PLACEMENT | HOWARD SAMUEL FAWCETT LABORATORY |  | COMPLETE | Kathryn Uhrich | Jose Wudka | LINDA WALLING |  | DAN LERMAN |  | 2 |  | TRUE |  |  | 2020-06-08 | This project is complete | 2021-04-20 | 2021-05-22 |  |  |  | 7/15/21, DL: This project is complete. Linda is requesting a sensored light switch which we will install under an SL6 work order………..4/30/21, DL: for most part this growth chamber is complete except the air curtain which is still not on site……………4/15/21, DL: This project is in progress. Linda will schedule the installation to take place in two weeks. We are waitng on the air curtain. This project should be 100% complete with in the next 4- weeks………4/1/21, DL: Plans were approved. We will try and start this project with in the next 3-weeks or sooner if possible…..3/1/21, DL: This was recently changed to a priority 2 project. Once plans are approved, we will work on the schedule noting, the schedule for this will work around pending priority 1 projects……2/16/21, LB: Changed to Priority 2 per Dan….1/19/21, DL: This is a priorty 3 project. We will start this project when all priority 2 projects are complete. |  | Enrico Baez |  |  | 2021-07-15 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 21-22
20P000470 |  | 20P000470 | FALSE | CHASS | SL5 HMSS 3210 - PATCH/PAINT | Paint Only | HUMANITIES BUILDING | 3210 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-24 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/10/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000469 |  | 20P000469 | FALSE | CHASS | SL5 ARTS 222, 225, 234 - PAINT FACULTY NEW HIRE | Please patch/paint to existing color Arts 222, 225, 234 for incoming new faculty. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 222 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | SUSAN KOMURA | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-23 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/12/21. |  | Paul Ditty |  |  | 2021-02-12 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000468 |  | 20P000468 | FALSE | VC-RED | SL5 SPIETH HALL 0364, 361, 363 - PATCH AND PAINT PROBLEM AREAS - AAALAC SITE VISIT | Paint Only | HERMAN T. SPIETH HALL | 364 | COMPLETE | Rodolfo Torres | Laura Manor | JOHNNY PHAN |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-06-23 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 12/02/20. 12/09/20 D-MMN: removed masking and reinstalled fallen base with base and wall glue. 12/08/20 D-MMN: applied finish to all the patches in the hallway and storage room. 12/07/20 D-MMN: Applied 3rd. coat of joint compound. returned and sanded then primed patches. these were located in the main hallway and the bedding supply room. vacuumed dust. 12/04/20 D-MMN: Continued scraping, treating and filling efflorescence and cracking paint. started taping baseboards and priming where it was so ready. |  | Paul Ditty |  |  | 2021-04-01 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000467 |  | 20P000467 | FALSE | SOM | SL5 WEBBER HALL 1247 - PATCH & PAINT OFFICE FOR BIOMED CHAIR | Paint Only - Attn: RON VELOZ - PLEASE RESPOND TO CYNTHIA CAROLINA. Please patch and paint 1247 Webber Hall. The Biomed Chair is moving into this office when it is available, which should be within 30 days. | HERBERT JOHN WEBBER HALL | 1247 | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-19 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 02/22/21. 2/22/21 D-JPO CLEANED UP DONE. 02/17/21 D-JPO: primed room and door. 02/16/21 D-JPO: finished prep. |  | Paul Ditty |  |  | 2021-02-22 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000464 |  | 20P000464 | FALSE | CHASS | SL5 HMSS 3001 - PAINT OFFICE CLEAN/WAX FLOOR NEW FACULTY HIRE | Paint Only - Paint Shop - Please patch/paint to existing color HUMSS 3001 for faculty new hire. ~ Custodial - Please clean/was HMSS 3001 for faculty new hire arriving September 2020. (trans from 20s026956) | HUMANITIES BUILDING | 3001 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/09/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000463 |  | 20P000463 | FALSE | CHASS | SL5 HMSS 2000 - PAINT OFFICE / CLEAN OFFICE NEW FACULTY HIRE - | Paint Only - Patch/paint to existing color Humanities Social Science 2000 for new faculty hire arriving 6/30/2020. Custodial Please clean and wax office floor for faculty new hire arriving 6/30/2020 HMSS 2000 | HUMANITIES BUILDING | 2000 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/18/21. 2/18/2021 B-SBT remove tape, sweep and clean room. 2/17/2021 B-SBT paint window sills. 2/16/2021 B-SBT pull masking, install plates. 2/11/2021 B-SBT patch, mask, sand, prime, and paint room. |  | Paul Ditty |  |  | 2021-02-18 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000462 |  | 20P000462 | FALSE | CHASS | SL5 HMSS 2001 - PAINT OFFICE / CLEAN FLOOR NEW FACULTY HIRE | Patch/paint to existing color for faculty new hire | HUMANITIES BUILDING | 2001 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | CHRISTY GRAY | Paul Ditty |  | X |  | TRUE |  |  | 2020-06-18 | [6 empty] | 03/19/21 O-ANS: Project complete per Paul Ditty. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  | 2021-03-19 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000453 |  | 20P000453 | FALSE | CHASS | SL5 ARTS 0142 - PAINT OFFICE, NEW FACULTY HIRE - | Paint Only - Please patch/paint to existing color office for faculty new hire. | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 142 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-18 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty…..6/18/20 o-dms: trans from 20w028936 to Project Phase - custodial please clean office floor for faculty new hire |  | Paul Ditty |  |  | 2021-04-05 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000450 |  | 20P000450 | FALSE | BCOE | SL5 CHUNG HALL ROOMS 217, 218, 219 - PATCH & PAINT | Please patch and paint these adjoining rooms within suite 216. |  | 217, 218, 219 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-06-12 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  |  |  |  | 2021-05-13 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000449 |  | 20P000449 | FALSE | BCOE | SL5 CHUNG HALL ROOM 461 - PATCH & PAINT | Paint Only - Chung Hall, Fourth Floor, Room 461 Patch & Paint: At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. Follow up with fresh paint. Thank you. | CHUNG HALL | 461 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-11 | [6 empty] | 01/19/21 O-ANS: Complete per technician updates and closed project. Completed by Wendy M. 11/09 -SC |  | Paul Ditty |  |  | 2020-11-09 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000448 |  | 20P000448 | FALSE | BCOE | SL5 CHUNG HALL ROOM 216 - PATCH & PAINT | At minimum, please patch holes in the walls that will be inevitable once the occupant move in and/or move out happen. |  | 216 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-06-11 | [6 empty] | 06/02/21 O-ANS: Paint Project complete per Paul Ditty. |  |  |  |  | 2021-05-11 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000446 |  | 20P000446 | FALSE | CHASS | SL5 CHASS INTN 4047 - FACULTY NEW HIRE PAINT | Paint Only - Please paint office CHASS INTN 4047 for faculty new hire in Ethnic Studies, Jasmin Young. Paint and patch to match existing color. | CHASS INTERDISCIPLINARY NORTH | 4047 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-06-04 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/12/21. |  | Paul Ditty |  |  | 2021-02-12 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000445 |  | 20P000445 | FALSE | CNAS | SL5 Entomology 279 - Add Air + Vacuum / Remove Sink + Cabinet | Add Air + Vacuum / Remove Sink + Cabinet | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 279 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | DAN LERMAN |  | 3 |  | TRUE |  |  | 2020-06-03 |  | 2021-04-22 | 2021-05-31 |  |  |  | 5/14/21, DL: This project is 100% Complete……4/30/21, DL: The floor will be installed tomorrow. The project will be 100% next week………………4/15/21, DL: The plumbing and electrical is complete. The painters will be done this week. The floor covering is ordered and will be installed with in two weeks…..4/1/21, DL: We will try and start this project with in the next three weeks…………3/15/21, DL: The building permit was approved today. We will work this project in to our schedule and we will schedule the work once we are ready to and in line with our other projects that are already in progress……….2/16/21, LB: Changed to Priority 3 per Dan…….1/19/21, DL: This is a priority 3 project. We will start the project when all priority 1 &2 projects are in process or almost complete… |  | Enrico Baez |  |  | 2021-05-14 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000419 |  | 20P000419 | FALSE | CNAS | SL5 SPIETH 2312 - PATCH & PAINT WALLS | Paint Only | HERMAN T. SPIETH HALL | 2312 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | PAUL DITTY |  | X |  | TRUE |  |  | 2020-04-22 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 3/18/21. 03/18/21 D-JPO: cleaned room patched masked sanded and primed all walls |  | Paul Ditty |  |  | 2021-03-18 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000413 |  | 20P000413 | FALSE | BCOE | SL5 BOURNS A-WING 1ST FLOOR ROOM A159A - EAST WALL PATCH & PAINT | PATCH & PAINT |  | A0159A | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-04-09 | [6 empty] | 08/13/21 O-ANS: Project complete per Paint Crew. 08/12/21 D-JPO: sanded spot primed and spot painted entire room. 08/10/21 D-JPO: patched and masked |  | PAUL DITTY |  |  | 2021-08-13 | FY 21-22 | FS | 0 | 2020 | 2021-10-01 | FY 21-22
20P000403 |  | 20P000403 | FALSE | CHASS | SL5 OLMSTED 232 - PAINT OFFICE | Please fill holes and paint office OLM 2321. The room is empty for now. Match existing color (UCR white). | JOHN W. OLMSTED HALL | 2321 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | MELISA VICARIO | Paul Ditty |  | X |  | TRUE |  |  | 2020-03-13 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/11/21. 02/11/21 D-JPO: finished sanding water damage spot primed painted room 2 coats pulled tape vacuumed complete. |  | Paul Ditty |  |  | 2021-02-11 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000401 |  | 20P000401 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 FS ANNEX B 5 & 6 - PAINT SUPERVISORS OFFICE | PATCH & PAINT |  |  | QUEUE TO START | Susan Marshburn | Da Lan Dinh | MARK JONES |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-03-13 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-10-01
20P000397 |  | 20P000397 | FALSE | CNAS | SL5 ENTOMOLOGY 139 - PATCH AND PAINT OFFICE | Patch and paint room 139 for the new faculty member | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | 0139 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Paul Ditty |  | X |  | TRUE |  |  | 2020-03-05 | [6 empty] | 04/16/21 O-ANS: Project complete per Paul Ditty. 02/10/21 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. |  | Paul Ditty |  |  | 2021-04-16 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000387 |  | 20P000387 | FALSE | CHASS | SL5 HMSS RM 3610 - PLEASE PATCH AND PAINT WALL | PATCH & PAINT |  | 3610 | COMPLETE | Juliet McMullin | Cindy Williams | JULIE SALGADO |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-03-02 | [6 empty] | 09/28/21 D-JPO: sanded vacuumed spot primed and painted went back to clean up room was occupied 09/29/21 D-JPO: CLEANED UP JOB DONE |  | PAUL DITTY |  |  | 2021-09-29 | FY 21-22 | FS | 0 | 2020 | 2021-10-01 | FY 21-22
20P000384 |  | 20P000384 | FALSE | CHASS | SL5 CHASS INTS 3111A - PATCHING HOLES AND PAINTING THE WALLS | PATCH & PAINT |  | 3111A | QUEUE TO START | Juliet McMullin | Cindy Williams | LESLIE ANN GERRETSE |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-02-27 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-10-01
20P000374 |  | 20P000374 | FALSE | VC-STU AFF | SL5 HEALTH SERVICES 334 - OFFICES PAINTED AND CONFERENCE ROOM | PATCH & PAINT |  | 334 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-02-20 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-10-01
20P000372 |  | 20P000372 | FALSE | VC-STU AFF | SL5 HEALTH SERVICES 391 - OFFICES PAINTED AND CONFERENCE ROOM | PATCH & PAINT |  | 391 | QUEUE TO START | Brian Haynes | Cathy Eckman | GLORIA VERA |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-02-20 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-10-01
20P000370 |  | 20P000370 | FALSE | CHASS | SL5 WATKINS HALL 1311 - SPACE RENOVATION PROJECT | SPACE RENOVATION PROJECT | GORDON S. WATKINS HALL | 1311 | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | DAN LERMAN |  | 1 |  | TRUE |  |  | 2020-02-19 | This Project is complete…. | 2021-03-19 | 2021-07-02 |  |  |  | 4/30/21, DL: The paint is complete. The floor covering is ordered and will be installed in about two weeks………………4/15/21, DL: Asbestos, electrical, and drywall are complete. Painters are in the space prepping the walls…..4/1/21. DL: Asbestos abatment is scheduled to be complete by this Monday. We will start the framing and electrical next week……………..3/1/21, DL: Plans were approved. We now need to send our 14- day notice to the AQMD and schedule the demolition……..2/16/21, DL: Plans were submitted with building permit last week. We are now in the plan check review process………1/19/21, DL: We will start working on the plans for this project in the next three weeks. We should have plans to submit for plan check review in the next 5- weeks……….. |  | Enrico Baez |  |  | 2021-04-30 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000368 |  | 20P000368 | FALSE | CNAS | SL5 SCI LAB ROOM 317 - PATCH & PAINT | PATCH & PAINT |  | 317 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-02-18 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-10-01
20P000367 |  | 20P000367 | FALSE | CNAS | SL5 SCI LAB ROOM 315-PATCH & PAINT |  | SCIENCE LABORATORIES 1 | 315 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Jose Wudka | DEBORAH TERAO | ABRAHAM JULIOT | PAUL DITTY |  | 9 |  | FALSE |  |  | 2020-02-19 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-10-01
20P000366 |  | 20P000366 | FALSE | CNAS | SL5 SPIETH 2375 / 2375-A - MINOR LAB RENOVATION | MINOR LAB RENOVATION | HERMAN T. SPIETH HALL | 2375 / 2375-A | COMPLETE | Kathryn Uhrich | Jose Wudka | SHERICE UNDERWOOD |  | DAN LERMAN |  | 7 |  | TRUE |  |  | 2020-02-19 | Final walk and punch list items. | 2021-05-14 | 2021-07-16 |  |  |  | 7/15/21, DL: This project is complete. I am meeting with Kate for a final walk through tomorrow morning………….5/14/21, DL: We will start the project in the next three weeks, the door will be ordered next week. We will schdule paint to take place in the next 3-4 weeks….1/19/21, DL: This is a priority 7 project, we will start this project when all priority 6 projects are complete………….. |  | Enrico Baez |  |  | 2021-07-16 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 21-22
20P000363 |  | 20P000363 | FALSE | BCOE | SL5 CHUNG 433 - MINOR OFFICE ROOM CHANGE | Paint Only | WINSTON CHUNG HALL | 433 | COMPLETE | Christopher Lynch | Todd Ambriz | MANGLAI ZHOU | FARIBORZ KARGAR | PAUL DITTY |  | X |  | TRUE |  |  | 2020-02-13 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty on 2/22/21. 2/22/2021 B-SBT pull tape, install plates, clean base/room. 2/19/2021 B-SBT prime and paint room. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2021-02-22 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000354 |  | 20P000354 | FALSE | VC-RED | SL5 UOB 200 - PAINT & PATCH OFFICES | PATCH & PAINT |  | 200 | QUEUE TO START | Rodolfo Torres | Laura Manor | MARISELA MARTINEZ |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-02-07 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-10-01
20P000336 |  | 20P000336 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 2109B - PATCH AND PAINT WALLS |  | STUDENT SUPPORT SERVICES BUILDING | 2109B | HOLD - FACILITIES SERVICES | LaRae Lundgren | Emily Engelschall, Sean Cason | SELENA SANCHEZ | DONNA POWELL | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-22 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2020 | 2021-10-01
20P000333 |  | 20P000333 | FALSE | CNAS | SL5 PIERCE 2232A - MINOR RENOVATIONS CASEWORK SINK UTL LINES | MINOR RENOVATIONS CASEWORK SINK UTL LINES | W. CONWAY PIERCE HALL | 2232A | IN PROGRESS | Kathryn Uhrich | Jose Wudka | KEVIN SIMPSON |  | DAN LERMAN |  | 9 |  | FALSE |  |  | 2020-01-22 | Schedule the work once the permit is approved | 2021-06-04 | 2021-10-29 |  |  |  | 8/18/21, DL: We are scheduled to start the abatment and demo on 8/24/21. We will try and complete this project by mid-october or sooner…… 08/02/21, DL: The plans are still being review by the building department and EH&S. Once the plans are approved, we will schedule the work….7/15/21, DL: Plans will be complete and we will apply for the building permit by tomorrow enveing. If the permit is appproved, which should take 2-4 weeks for the review and approval process, we will order the material and schedule the work……5/14/21, DL: Project is scoped, we will work on plans and submit them to Kevin for review in about 3- weeks…….1/19/21, DL: This is a priority #9 project. We will start this project when all priority #8 projects are complete… |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-10-01
20P000321 |  | 20P000321 | FALSE | CHASS | SL5 UNIV THEATRE 400A - PAINT LOBBY | PATCH & PAINT |  | 0400A | QUEUE TO START | Juliet McMullin | Cindy Williams | ALBERT FETTER |  | PAUL DITTY |  | X |  | FALSE |  |  | 2020-01-15 | [8 empty] | PAUL DITTY |  |  |  | FY 21-22 | FS | 0 | 2020 | 2021-10-01
20P000320 |  | 20P000320 | FALSE | CNAS | SL5 SPIETH 1303 - ACTIVATE VACUUM LINES | ACTIVATE VACUUM LINES | HERMAN T. SPIETH HALL | 1303 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | DAN LERMAN |  | 4 |  | FALSE |  |  | 2019-11-20 | Project is complete. | 2021-05-03 | 2021-06-11 |  |  |  | 7/15/21, DL: This project is complete……..6/2/21, DL: Electrical work is complete. The Plumbing shop will start to install the vacuum lines this Thursday. This project should be 100% complete by next Friday…….5/14/21, DL: The space was surveyed for hazardous material. Once we have the survey we will schedule work…………4/30/21, DL: Conducted site visit this week; we will survey the space for hazardous material before we conduct any work. We should start the work in about two weeks…………….1/19/21, DL: This is a priority 4 project. We will start this project when all all priority 3 projects are complete……….. |  | Enrico Baez |  |  | 2021-06-11 | Winter 2021 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000317 |  | 20P000317 | FALSE | CHASS | SL5 ARTS 150 - EXTERIOR EXTENSION OF SCULPTURE LAB | EXTERIOR EXTENSION OF SCULPTURE LAB including 200 amp electrical panel | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 150 | QUEUE TO START | Juliet McMullin | Cindy Williams | PAUL RICHARDSON | ANDREA HILDAGO, SUSAN KOMURA | DAN LERMAN |  | 2 |  | FALSE |  |  | 2020-01-14 | Order material once permit is approved | 2021-06-14 | 2021-10-31 |  |  |  | 08/02/21, DL: The plans and permit are approved. This is a large project and it will consume our electricans for at least 4- weeks. At the current time we are working on completing several other projects. Once we are caught up on the noted projects, we will schedule the work. Paul Richardson is currently aware of the plan noted above.....7/15/21, DL: The engineering is complete. We submitted the plans and applied for the building permit last week. Once the permit is approved, we will order material and schedule the work…….5/14/21, DL: We are still working on the contract to be approved for the electrical engineer before we can proceed…….4/15/21, DL: We had a meeting with the engineer this week and we should be applying for a permit within the next three weeks…….3/1/21, DL: We will reach out to the electrical engineer this week…….1/19/21, DL: This project will require engineered plans. This is a priority 2 project. We will start the plans and permit process when all priority #1 projects are complete. |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-10-01
20P000310 |  | 20P000310 | FALSE | BCOE | SL5 BOURNS A-WING A129 - PATCH & PAINT | Paint Only - Please patch & paint. East wall has holes. Determine if entire room needs repainting to match color. Thank you. | MARLAN & ROSEMARY BOURNS HALL | A0129 | COMPLETE | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | PAUL DITTY |  | X |  | TRUE |  |  | 2020-01-10 | [6 empty] | 04/01/21 O-ANS: Project Complete per Paul Ditty. 2/3/2021 B-SBT Patch holes, mask room, sand patches, prime room. 2/4/2021 B-SBT paint room, pull masking, clean room. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2021-02-04 | Winter 2021 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000309 |  | 20P000309 | FALSE | VC-UNIV ADV | SL5 1955 CHICAGO AVE 200 - PAINT & PATCH HOLES AND HANG PICTURES |  | 1955 CHICAGO | 200 | CANCELED BY FS | Peter Hayashida | Naysia Caldwell | SARAH KARSON |  | PAUL DITTY |  | 1 |  | FALSE |  |  | 2020-01-10 | [6 empty] | 12/16/20 O-ANS: Canceled by FS - Project location not serviced as FS CORE location and reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Please retain project # as reference. 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  | 2020-12-16 | Spring 2020 | FS | 0 | 2020 | 2021-10-01 | FY 20-21
20P000282 |  | 20P000282 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 PIERCE HALL 3374 - RENOVATE GA CLASSROOM SUMMER 2020 | Project to renovate GA classroom in Pierce Hall for prioritization and execution in Summer 2020. |  | 3374 | QUEUE TO START | Susan Marshburn | Da Lan Dinh | DA LAN DINH |  | Paul Ditty |  | X |  | FALSE |  |  | 2020-01-09 | [8 empty] | Paul Ditty |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-10-01
20P000275 |  | 20P000275 | FALSE | PB&A | SL5 MAIL BLDG 884 - MISC PAINTING FOR NEW DRIVE-THRU SERVICE |  | MAIL BUILDING | 884 | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | JENNIFER TENNEY STRATTON | JENNIFER TENNEY | PAUL DITTY |  | 1 |  | FALSE |  |  | 2019-12-04 | [6 empty] | 08/06/20 O-ANS: ON HOLD due to campus closures until further notice. |  | Paul Ditty |  |  |  | Spring 2020 | FS | 0 | 2019 | 2021-10-01
20P000272 |  | 20P000272 | FALSE | CHASS | SL5 ARTS 245 - LIGHTING UPGRADE/PROJECTOR INSTALLATION | LIGHTING UPGRADE/PROJECTOR INSTALLATION | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 245 | IN PROGRESS | Juliet McMullin | Cindy Williams | ANDREA HIDALGO | Susan Komura | DAN LERMAN |  | 3 |  | FALSE |  |  | 2020-01-02 | Make corrections and resubmit plans on 7/15/21 | 2021-05-24 | 2021-09-23 |  |  |  | 8/18/21, DL: We are making great progress and we should be done with project by Sept. 21. All light fixures are here on site. ……08/02/21, DL: The plans are now approved. We ordered the light fixtures and have also started the work. It is our plan to be complete with the project by September 23rd and the Arts Department currently has an exhibit they are planning to present on or near the 23rd……7/15/21, DL: We are still in plan check review with the building department and a few corrections were needed. We will resubmit the corrections tomorrow. Hopefully the permit will be approved in the next two weeks……..6/2/21, DL: We are almost complete with the plans. We will submit the plans to the customer for review by the end of the week. Once the cutomer approves the plans, we will apply for the building permit……4/20/21, DL: Conducted site vist with the Arts team. We will start working on the plans in the next two weeks……1/19/21, DL: This is a priority 3 project. We will start the plans and permit for this project when all priortiy #2 projects are complete… |  | Enrico Baez |  |  |  | Winter 2021 | FS | 0 | 2020 | 2021-10-01
20P000253 |  | 20P000253 | FALSE | BCOE | SL5 BOURNS HALL LAB B156 - EXHAUST SYSTEM | EXHAUST SYSTEM | MARLAN & ROSEMARY BOURNS HALL | B0156 | COMPLETE | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | DAN LERMAN |  | 1 |  | FALSE |  |  | 2019-12-11 | Demolish cabinets and schedule paint and flooring | 2021-03-01 | 2021-05-14 |  |  |  | 4/30/21, DL: This project is 100% Complete :) ……… 4/15/21, DL: The power is complete. The exhaust is scheduled to be complete with in the next 30 days……….3/15/21, DL: The new dedicated electrical outlet is complete. We are also in the process of ordering the exhaust vents for the printer…………..2/16/21, DL: Plans were submitted 2- weeks ago. We received the plans back last week with corrections needed. We will resubmit the plans back to the building official by the end of the week….1/19/21, DL: We will start working on the plans for this project in the next two weeks. We will start this project once the permit is approved…… |  | Enrico Baez |  |  | 2021-04-30 | Winter 2021 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000248 |  | 20P000248 | FALSE | CNAS | SL 5 WEBBER 1223- MINOR RENOVATION PROJECT | Space Management has temporarily allocated Rooms 1223 and 1223-A in Webber Hall to CNAS. We need this lab cleaned and modified to accommodate relocating an existing (and active) lab. | HERBERT JOHN WEBBER HALL | 1223 + 1223-A | COMPLETE | Kathryn Uhrich | Jose Wudka | SHARYL MURDOCK |  | Dan Lerman |  | 5 | 4 | FALSE |  |  | 2019-11-27 | Project is Complete. | 2021-04-12 | 2021-05-31 |  |  |  | 6/2/21, DL: This project is complete……5/14/21, DL: This project is 95% complete. Items that need to be completed are: remove window AC unit, replace glass where the AC unit was removed and install window covering…………..4/30/21, DL: Demolition is complete, we will start the electrical and painting in the next two weeks…………..4/15/21, DL: The space was surveyed for hazardous material. There were rodent droppings, which will be disposed of this weekend, the ceiling tiles had mold. The ceiling tiles were removed. We will start the demo of the floor and some other items with in the next three weeks………..4/1/21, DL: We need to survey the space for hazardous material and arrange to have the space sanitized………………1/19/21, DL: This project is a priority #5. We will start this project when all priority #4 projects are complete…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…….02/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Survey space for hazardous material. Once survey is complete, we will schedule abatement and the work. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2021-06-02 | Winter 2021 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000247 |  | 20P000247 | FALSE | CNAS | SL5 SPIETH 2110/2118 - PREP LAB FOR NEW FACULTY HIRE | Refresh Lab: Patch paint, strip & clean floor, repair broken ceiling and floor (VCT) tiles at room 2110 & 2118. Install Electrical power & Co2 cylinder racks at each end of workbench/tables | SPIETH | 2110 + 2118 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS | SHERICE UNDERWOOD | Dan Lerman |  | 6 |  | TRUE |  |  | 2019-11-27 | [6 empty] | 1/19/21, DL: This project is complete…………..9/30/20, DL: This project is in progress and will be compete in the next 6- 8 weeks……………8/5/20, DL: We will start on this project in the next 6-8 weeks….. | 2020-04-17 | Enrico Baez | Spieth 2110: Carpentry: Seismic anchoring for “New” tables and equipment. Replace damaged ceiling tiles. Install misc. wall mounted items. Sheet Metal: Remove “existing” steel cage. Fabricate & install metal cylinder rack w/ restrains/seismic anchoring to floor. Plumbing: Install Co2 POC for gas cylinders at four (4ea) new free-standing work benches (see configuration on this document). Electrical: Install dedicated *120v power drop & connect to the existing power strips built-in the four (4ea) new workstation tables (see configuration on this document). *VERIFY/CONFIRM VOLTAGE W/ D. MCW. Relamp fixtures as needed. Spieth 2118 & 2110: Sheetmetal: Clean and or replace air distribution grilles. Flooring: Repair/patch broken floor tile and Replace broken ceiling tiles (abate floor tiles if required). Painting: Paint and patch all walls, verify recondition doors @ room side. Plumbing: Assess sinks to be fully operational & clean. *Replace sink in Rm 2118 for glassware, confirm with Faculty/Estella. Replace sink in room 2118 (Sink type TBD by Faculty). HVAC: Check lab air pressure is operational & proper pressure. Custodial: Strip and Wax floor, clean interior windows, wipe down doors and windowsills. EXCLUSIONS: Furnish, assemble, and install new workstations, tables or lab equipment. Removal of existing lab furniture or equipment. Natural gas or air output taps not required (per Faculty). | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000244 |  | 20P000244 | FALSE | CNAS | SL5 SKYE RM 0242 - PATCH AND PAINT FOR NEW FACULTY HOLD HOLD | Paint Only | SKYE HALL | 242 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MELISSA GOMEZ |  | PAUL DITTY |  | X |  | TRUE |  |  | 2019-11-25 | [6 empty] | 05/06/21 O-ANS: Updated contact person info from Dr. Wudka and reaching out to coordinate. 5/05/21 O-ANS: Multiple failed attempts to contact requestor to schedule work. Project placed on HOLD and emailed CNAS partner to continue to hold or cancel. 05/22/20 O-ANS: ON HOLD BY FS per Paul Ditty - After multiple attempts to reach out to customer, PDY was unable to establish contact with customer regarding availability and scope of work for the room. Awaiting customer response. D-PDY 1/16/2020 I SPOKE WITH MELISSA WHO THINKS THE ROOM WILL BE VACANT AT THE END OF FEBRUARY |  | Paul Ditty |  |  |  | Winter 2021 | FS | 0 | 2019 | 2021-10-01
20P000231 |  | 20P000231 | FALSE | CHASS | SL5 ARTS 54 - CONVERT TO PIANO LAB | Convert Basement Library into Piano Lab | ARTS BUILDING FINE ARTS SEISMIC FACILITY | 54 | IN PROGRESS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 4 | 1 | FALSE |  |  | 2019-11-19 | Framing and electrical | 2021-05-14 | 2021-10-31 |  |  |  | 8/18/21, DL: We are making great progress and we should be complete with this project within the next 6 weeks. 08/02/21, DL: Most of the demolition is complete. We started the framing today. It is our goal to be 100% complete with this project by the end of October….7/15/21, DL: Plans were approved this week. Carpenter shop is ordering material and we should start the work next week…… 6/2/21, DL: We applied for the building permit last week. We should have approved plans in the next 1-2 weeks…..5/14/21, DL: We sent Paul R. the 75% complete plans today for review. Once Paul approves the plans and layout of the pianos, we will proceed with completing the plans and apply for the building permit. The demolition of the cabinets and floor covering is complete. The carpenter shop is also pre-ordering their material to help expedite the project once we have the approved building permit……4/1/21, DL: We will start the plans process over the next two weeks and try and apply for a building permit in the next 2-3 weeks…1/19/21, DL: We will Start the plans, permit and the work once all priority #3 projects…11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Completed site visit. Need to work on plans and permit. Plan to submit plans for building permit in the next 2-3 weeks…. | 2019-11-21 | Enrico Baez | 1.) Remove track in floor-patch floor. 2.) Build walls between columns. Install two doors, one in each new wall. Include small wall in column on West wall. 3.) Install power poles for electric pianos-number and location to be determine one Paul has piano layout. 4.) Remove counter and terminate electrical at counter. 5.) Patch wall as needed after counter removal. 6.) Install customer selected flooring and base. | YES |  | Winter 2021 | FS | 0 | 2019 | 2021-10-01
20P000230 |  | 20P000230 | FALSE | VC-RED | SL5 BOURNS B0116C - INSTALL HANGING CEILING/WIDEN DOOR | Install Ceilings, Widen Door & Extend Utilities | BOURNS | B116C & B116D | COMPLETE | Rodolfo Torres | Laura Manor | KRASSIMIR BOZHILOV | LAURA MANOR | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-11-18 | finish plans for building permit | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: This project is in progress and 50% complete. We should be complete with in the next 4-6 weeks…………...8/5/20, DL: We will submit plans in the next week………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We will start working on the plans and apply for a building permit in the next 2-3 weeks. | 2020-01-23 | Enrico Baez | Install new T-bar ceilings, lighting/switches, verify electrical service/disconnect. Relocate the existing eye washer, widen the exiting door opening and *reverse swing(*if approved by F.M). Install one customer furnished transformer. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000221 |  | 20P000221 | FALSE | BCOE | SL5 BOURNS B0207 - INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | INSTALL BLACK WOOD ON TOP OF LASER CURTAIN | BOURNS | B0207 | COMPLETE | Christopher Lynch | Todd Ambriz | HONG XU | KEVIN FREEDMAN | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-11-15 | [6 empty] | 1/19/21, DL: This project is 100% Complete……..9/30/20, DL: We are in the process of finishing up a few other projects. Once they are complete, we will schedule the work….8/5/20, DL: Plans are approved and we will start the work in the next 2-6 weeks…….. | 2020-02-25 | Enrico Baez | Install Plywood and supports. Paint Plywood black. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000218 |  | 20P000218 | FALSE | VC-RED | SL5 SPIETH 347 - VIVARIUM UPDATE AIR COMPRESSOR | VIVARIUM UPDATE AIR COMPRESSOR | HERMAN T. SPIETH HALL | 347 | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | DAN LERMAN |  | 2 | R2 | FALSE |  |  | 2019-05-17 | Set & place the compressor. Start elect. / plumbin | 2021-04-07 | 2021-05-14 |  |  |  | 5/14/21, DL: This project is 100% Complete….4/30/21, DL: The plumbers are 75% complete. Once the plumbing is complete, the electricians will start…………4/15/21, DL: The compressor was delivered to the permanent location. The plumbers will start the air lines and drain assembly next week. The electricians will connect the electrical within a month, as they have a few other projects in their queue that need to be completed before they start this project………….4/1/21, DL: We are scheduled to relocate the compressor next week. Once the compressor is placed, we will anchor the compressor and start the electrical and plumbing……………….3/15/21, DL: We received confirmation the Compressor is on site. We will schedule the work once as soon as we are able to………….2/1/21, DL: WE will start the process for this project once we are closer to completing priority 1 projects. This is a prioity 2 project……1/19/21, /DL: This project has been scoped. We will start the work when we are complete with all priority #1 projects……. |  | Enrico Baez |  |  | 2021-05-14 | Winter 2021 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000215 |  | 20P000215 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL - OPEN SPACE CP00003568 | Remove Vaughan wall seperating Olmsted 3349/3351.Add 4 single gang outlets and 2, 2gang outlets. | PSYCHOLOGY1 | 3rd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-11-07 | [6 empty] | 1/19/21, DL: This project is 100% complete…………9/30/20, DL: Plans were approved, we had the Vaughn Wall tested for Asbestos containing material. Once we have the results, we will schedule the work………….8/5/20, DL: We will submit plans by this Friday for a building permit | 2020-02-24 | Enrico Baez | 2/24/2020 E. Baez - 1.Remove Vaughan wall and electrical circuit in wall. 2. Add 4 Single Gan outlets and 2, 2gang outlets. 3. Patch vinyl plank flooring from removed wall and safe. 4. Remove panel in 2249 with wall paper on it next to window. 5. Remove handle set to 3351, install blank, render door inoperable. 6. Repair T-Bar ceiling as needed. 7. Patch and paint walls. 8. Coordinate with ITS for data line for 8 computers. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000214 |  | 20P000214 | FALSE | CHASS | SL5 PSYCHOLOGY OLMSTED HALL MODIFICATION CP00003566 | Remove walls and doors in spaces 2139 A,B and C. | PSYCHOLOGY1 | 2nd Floor | COMPLETE | Juliet McMullin | Cindy Williams | JAY MELASHENKO |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-11-07 | Obtain building permit | [5 empty] | 9/30/20, DL: This Project is Complete…………8/5/20, DL: we will submiot plans this week.…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Plans were submitted for a permit on 2/12/20. Once plans are approved, we will order the material and schedule the work……… | 2020-01-10 | Enrico Baez | **************************************SCOPE********************************** 1.) Remove doors, and jambs 2139A, 2139B, 2139C. 2.) Remove drop ceiling in 2139A, 2139B, 2139C and repair as needed. 3.) Remove cabinets in 2139A, 2139B, 2139C. 4.) Remove walls between 2139A & B, and remove walls between 2139B & C. 5.) Change light fixture to match existing. 6.) Repair walls as needed. 7.) Patch and paint as needed. 8.) Replace carpet and base in 2139A, 2139B, 2139C and 2139 common area. 9.) HVAC duct work in individual spaces can be removed and simplified. | YES | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000213 |  | 20P000213 | FALSE | CHASS | SL5 CHASS INT SO RM 2117C - CARD ACCESS NEEDED FOR MANY ROOMS |  | CHASS INT S | 2117A, 2117C, 2117D, 2117E | COMPLETE | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-11-08 | approved permit | 2020-03-03 | 2020-03-21 |  |  |  | 8/5/20, DL: This Project is Complete……………..2819/20 O-DHN: Emailed Status Report to customer…..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have a contract, we will order the material and schedule the work………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Plans are complete and submitted for building permit. We are also working on the contract. Once the plans are approved and the contract is complete, we will schedule the work………. |  | Enrico Baez |  |  | 2020-08-05 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
20P000212 |  | 20P000212 | FALSE | BCOE | SL5 BOURNS B0328E - CONFIRM DAMAGE & REPAIR/REPLACE FUME HOOD | Repair the damaged exhaust duct at Fume hood in BCOE 328E | MARLAN & ROSEMARY BOURNS HALL | B0328E | QUEUE TO START | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Enrico Baez |  | R1 | R1 | FALSE |  |  | 2019-11-05 | [6 empty] | 1/19/21, DL: Todd has the estimate. Sent follow up email to Todd requesting update or FAU number………………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment insallation. 8/5/20, DL: This Project is on hold until further notice…….Ron V. to send Todd A. and Robert L. an email with an update. The email was sent from Dan to Ron V on 7/31/20………….. |  | Enrico Baez | Demo portion of ceiling to access the duct system, procure a hazardous material vendor to remove the damaged duct work and phoenix valve. Install new ducting, Install new phoenix valve and re-install ceiling tile grid and ceiling tiles. |  |  | Winter 2021 | FS | 0 | 2019 | 2021-10-01 |  | 1
20P000211 |  | 20P000211 | FALSE | CHASS | SL5 ARTS RM 0054 -INSTALL CARD READER - ARTS 54 | Install keyless entry system for door to Arts Building RM 54 | ARTS | 54 | CANCELED BY CLIENT | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R1 | R3 | FALSE |  |  | 2019-11-07 | [6 empty] | 1/19/21, DL: Enrico will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21 - Research equipment installation. 8/5/20, DL: This Project is on hold until further notice……. | 2020-01-20 | Enrico Baez | 1/19/21, EB: Per Paul R., This project is canceled………….Provide new panel, power supply and door hardware for 2 doors. Prox reader only. | YES | 2021-01-19 | Winter 2021 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
20P000210 |  | 20P000210 | FALSE | BCOE | SL5 WCH 2ND FL RM 0224 - NOISE CONTROL | Reduce noise. Replace doors with solid core doors and install an Acoustic Door Seal Kit. | CHUNG HALL | 224 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-11-05 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……. | 2020-02-11 | Enrico Baez | Removal of the existing double doors and door hardware, install new solid core double doors with continuous hinges, install new acoustical jamb seals, threshold seal and a surface mounted Automatic Door Bottom utilizing a flat spring mechanism, which activates when closing the door, lowering a neoprene seal insert against the floor or threshold to create a sound seal. Install acoustic double door astragals with seal. Reinstall all existing door locksets, and door closers. Quote received from Brad Aduddell-American Door to perform this work. Quote & Specs are available in the project folder. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000208 |  | 20P000208 | FALSE | ATHLETICS | SL5 ATHLETICS AND DANCE 0050 - LOCKER ROOM REFRESH | Men's locker room refresh | ATH DANCE | 50 | COMPLETE | Tamica Smith Jones | Joe Erbland | JOSEPH ERBLAND | EUGENE HUTCHINSON | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-11-04 | [6 empty] | 1/28/21, DL: Project is complete. Paul will schedule the paint once he is back on projects……….1/19/21, DL: We will schedule the balance of the paint before the students return back to campus………..9/30/20, DL: The work is complete except for the paint……………..8/5/20, DL: The work is almost complete.……. |  | Dan Lerman |  |  | 2021-01-28 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000202 |  | 20P000202 | FALSE | CNAS | SL5 SKYE HALL 361 RENOVATION PROJECT | Renovete space for class room. | SKYE HALL | 361 | COMPLETE | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY | MELISSA GOMEX | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-10-30 | pending permit approval | 2020-02-05 | 2020-03-27 |  |  |  | 9/30/20, DL: This Project is Complete……….8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer…..2/19/20, DL: Permits were approved. Demolition is complete…..1/15/20 O-DHN: Emailed Status Report to customer……..1/14/20, DL: Plans have been submitted for a building permit. Once plans are approved, it is our goal to complete the work by the beginning of spring quarter….. |  | Enrico Baez | 12/12/19 O-ANS: Project intake already completed by Dan Lerman. |  | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000197 |  | 20P000197 | FALSE | VC-RED | SL5 UOB 210 - SOUND PROOF INSTALLATION |  | UNIV OFC BLD | 210 | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-10-24 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000196 |  | 20P000196 | FALSE | VC-STU AFF | SL5 COSTO HALL REZONING - DOORS TO SEPARATE OFFICE SPACES | We are in need of some doors to be installed in various hallways to separate office spaces. This is regarding the Costo Hall office space rezoning. | JEANETTE AND RUPERT COSTO HALL |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN O'BRIEN |  | Enrico Baez |  | R1 | R2 | FALSE |  |  | 2019-10-24 | [6 empty] | 2/25/2021 E. Baez Project will require several trades to complete. FS unable to support recharge project. Asked Brendan O'Brien to submit Project Request through CPMS for PD&C. …...02/16/21 O-ANS: Will require plans/permits and may need to go to PD&C due to scope of work which includes construction. Will confirm with client before instructing to submit request to CPMS…. 01/19/21, DL: Enrico B. Will manage this project…………..11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez |  |  | 2021-02-25 | Winter 2021 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
20P000188 |  | 20P000188 | FALSE | LIBR | SL5 ORBACH 204 - REPLACE FLOORING PROJECT - WINTER 2020 |  | ORBACH LIB | 204 | CANCELED BY FS | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-10-23 | Obtain floor covering samples | [5 empty] | 11/19/20 O-ANS: Declined to move forward by FS Admin but may revisit in future prioritization period. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: We are working on floor covering samples that will work for the space. |  | Enrico Baez |  |  | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000183 |  | 20P000183 | FALSE | CHASS | SL5 HMNSS 1202- CREATE COMPLIANT WALKWAY FROM EXIT DOOR RECHARGE | Install side walk | HUM & SOC SC | 1202 | CANCELED BY FS | Juliet McMullin | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2019-10-18 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period. Also Existing door is compliant and there are other accessible exits to the building… 8/5/20, DL: This Project is on hold until further notice……. | 2019-11-13 | Enrico Baez | Construct Side walk. ADA compliance not required. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
20P000174 |  | 20P000174 | FALSE | CNAS | SL5 PHYSICS RM 3009 - NEW HIRE PATCH AND PAINT ONLY | Paint Only - Paint, patch office 3009 for new Assistant Professor, Miguel Arratia Munoz. MIGUEL ARRATIA MUNOZ-NEW FACULTY HIRE 1/01/2020 | PHYSICS BUILDING | 3009 | QUEUE TO START | Kathryn Uhrich | Jose Wudka | MAYELA CASTILLO | DAVID NEFF | PAUL DITTY |  | 1 |  | TRUE |  |  | 2019-10-11 | [6 empty] | 05/05/21 O-ANS: Updated contact info from Dr. Wudka. 05/05/21 O-ANS: Multiple failed attempts to contact requestor to schedule work. Project placed on HOLD and emailed CNAS partner to continue to hold or cancel. 02/03/21 O-ANS: Reminder email sent to customer that PAINT ONLY portion would be completed and not the door removal at this time. Customer can resubmit request in next prioriization cycle…. 11/06/20 O-JLO: Emailed requestor and alternate regarding paint portion only, and that door/drywall removal will not occur during this time …. 11/06/20 O-ANS: FY 21 Paint Project Approved by FS Admin and meets criteria of Direct Research or New Faculty Upgrade. Assigned to D-PDY for completion. FS to confirm with customer that we can only complete the painting at this time but not the removal of the door…. 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: WE will work on plans and permits when we return back from the campus closure." | 2020-01-31 | Paul Ditty | Patch and paint all walls in room 3009, deep clean carpet stains and or replace carpet, remove tack board, remove two doors and frames and infill openings with meatal stud framing, insulation and drywall. Relamp fixtures as needed. Patch and paint common walls where the doors are infilled at rooms 3005 and 3011. | YES |  | Winter 2021 | FS | 0 | 2019 | 2021-10-01
20P000144 |  | 20P000144 | FALSE | CNAS | SL5 BOYCE HALL - NEW FACULTY EPIGENETICS LAB REMODEL | Renovate Rooms, Boyce 3432, 3446, 3436 and 3436A | ALFRED M. BOYCE HALL | 3432, 3432A, 3446, 3446A | COMPLETE | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-09-26 | Install floor covering |  | 2021-04-23 |  |  |  | 4/30/21, DL: This Project is 100% Complete………..4/15/21, DL: The asbestos abatement is complete. The floor covering will be complete by the end of next week……………4/1/21, DL: Asbestos abatement is scheduled for April 8th - 12th. We will install the floor covering shortly after and deep clean the space. This project is on schedule to be complete on or near 4/20/21…………..2/16/21, DL: Project Is on schedule. Paint is 90% complete. Once paint is complete, we will schedule the floor repairs and final deep clean……… 2/1/21, DL: We are making good progress and are target date is still 3/14/21………….1/19/20, DL: This project is in progress and will be complete in the next 30- days………….9/30/20, DL: We have started a few items but we are waiting on Matt U. and the PI to remove their items so we can have access to the space. Once the space is cleared out, we will proceed with the work…………8/5/20, DL: We will start the work in the next 4-6 weeks. | 2020-02-18 | Enrico Baez | This project is 100% Complete… ;) Boyce 3432, 3446, 3436 and 3436A . Patch and paint 3432, 3432A, 3436, 3436A, 3446, 3446A. Reface/replace water damaged cabinets near sink (3446). Install GCFI outlets near sink (replace existing) (3446). Install panel cover for electrical panel box. Replace many burnt out bulbs in ceiling lamps. Replace broken chemical plexi-glass on bench shelves. | YES | 2021-04-30 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000135 |  | 20P000135 | FALSE | BCOE | SL5 MS&E RM 0075 - 3 PHASE 220 POWER FOR CHILLED WATER PPMS TOOL | MS&E Rm 0075 - 3 Ph208 Power CHW S&R WATER PPMS TOOL, Install Chilled water loop & power in clean room 075. | MAT SCI ENGR | 75 | COMPLETE | Christopher Lynch | Todd Ambriz | MARK HEIDEN |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-09-19 | Plans and permit | [5 empty] | 9/30/20, DL: This project is complete……..8/5/20, DL: This is in progress…….3/25/20, DL: We will work on plans and permits when we return back from the campus closure……. | 2020-02-18 | Enrico Baez | Intake/SOW: Install 208V 3ph power & disconnect/safety switch and one 3/4" Chilled water loop (Supply and Return) in the MSE southeast corner of clean room 0075. Create a 4" diameter pass-thru hole from this corner of room 0075 into the adjacent room 0071. FS to provide power and cooling to a compressor which will connect through the wall to the PPMS system with cryogenic helium lines. | YES | 2020-09-30 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000067 |  | 20P000067 | FALSE | BCOE | SL5 BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM - CPMS 3224 | BOURNS HALL A & B-WING- INSTALL HIRSCH SYSTEM | BOURNS | B-Wing | TO BE PERFORMED BY PD&C | Christopher Lynch | Todd Ambriz | MARGARET SOUDER |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2016-11-14 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Replace access controls at BCOE WCH & Bourns bldgs. |  | 2020-11-19 | Fall 2019 | FS | 0 | 2016 | 2021-10-01 | FY 20-21 | 1
20P000054 |  | 20P000054 | FALSE | SOM | SL5 SOMED-SOME G0600, G0621 & 1682B ADD POWER AND DATA | SOMED-SOME G0600, G0621 & 1682B- ADD POWER AND DATA | SOM EDUC | G0600, G0621 & 1682B | COMPLETE | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-07-31 | [6 empty] | 9/30/20, DL: This Project is Complete…………..8/5/20, DL, Dan to follow-up with customer………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "Remove status Hold / Update project detail to include information on 1682B -ADD ELECTRICAL, PAINT/PATCH, AND RELOCATE WHITE BOARD." |  | Enrico Baez | Room G0600 Install Power behind and below the TV, install one TV Bracket, install one cut-in back box below the TV for data(data cabling by ITS), Paint the entire East wall to match existing. Room G0621 Insatll three(3) new double duplex receptacles and three(3) data back boxes only(no data cabling) in room G0621. Install SS tubing for Co2 from room G0621 to room G0623. Include Valves at both ends of P.O.C., Install one uni-strut siesmic cylinder support at the south wall. Steve Burleson has walked the site and has knowledge of the SOW. Loading Dock Install Pole & chains at Loading dock. |  | 2020-09-30 | Fall 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000047 |  | 20P000047 | FALSE | VC-RED | SL5 ADVANCED NEUROIMAGING | NEEDING TO TAKE DOWN OVERHEAD CABINETRY AND REPLACE WITH SOME KIND OF SHELVING TO OPTIMIZE SPACE. LOOKING FOR AN ESTIMATE AND A PLAN. | ADV NEURO |  | CANCELED BY FS | Rodolfo Torres | Laura Manor | CHELSEA EVELYN |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-07-31 | pending material delivery. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice…….3/23/20, DL: Shelves are ordered. We will schedule the work when we return from the campus closure……….1/15/20 O-DHN: Emailed Status Report to customer…...1/14/20, DL: We waiting for a revised quote from the vendor as there quote was not complete. We will process the quote for a PO# when we receive the correct quote……. 11/11/19, DL: Need to review scope with Ron as the shelving system is a special order item with a 3- month lead time….. | 2019-09-24 | Enrico Baez | Remove 5'-0" x3'-0" upper cabinet, and soffits. Patch and paint walls to match the existing grey . Install customer furnished adjustable shelf. | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000046 |  | 20P000046 | FALSE | CNAS | SL5 CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | CHAPMAN HALL 0001- ESTIMATE FOR CARD READERS | HOMER D. CHAPMAN HALL | 0001 | CANCELED BY CLIENT | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Enrico Baez |  | R2 |  | FALSE |  |  | 2019-07-31 | [6 empty] | 05/12/21 O-ANS: Per email from Bill Sutton, this project was requested to be cancelled. 1/19/21, DL: Enrico B. will manage this priject………….11/19/20 O-ANS: Project meets FS criteria for completion during FY 20-21. 8/5/20, DL: This Project is on hold until further notice……. |  | Enrico Baez | Install wireless access controls systems at front and rear entry doors. | YES | 2021-05-12 | Winter 2021 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
20P000039 |  | 20P000039 | FALSE | BCOE | SL5 BOURNS HALL A031- ESTIMATE- REFURBISH ROOM GSR SPACE |  | BOURNS | A0318 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2019-05-13 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice……..09/19/19 O-ANS: HOLD FOR WINTER 2020 PER CUSTOMER (LOUIS SANDOVAL) REQUEST. EMAILED PAUL DITTY TO CONFIRM. PAUL STATED THIS IS NON-PAINT PROJECT B/C SCOPE OF WORK INCLUDES CARPENTERS AND ELECTRIC SHOPS. |  | Paul Ditty |  |  | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000026 |  | 20P000026 | FALSE | VC-RED | SL5 LIFE SCIENCES VIVARIUMS- ESTIMATE FOR T-BAR DROP | Install T-bar ceiling, Provide HVAC and Fire sprinklers drops. Install new 2x4 LED light fixtures | LIFE SCIENCE | Basement Level | COMPLETE | Rodolfo Torres | Laura Manor | DIERK BIGGS |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-07-19 | Work on Plans and permits. | [5 empty] | 1/19/21, DL: This project is 100% Complete……….9/30/20, DL: The plans were submitted two weeks ago. We should receive the plan check review comments in the near future…………….8/5/20, DL: This Project will exceed $50,000. Monty A. will inform customer this is a project that will need to be managerd through PD&C……………3/25/20, DL: We will work on plans when we return back from the campus closure. | 2020-01-31 | Enrico Baez | Install T-bar ceiling with wipable(coated) ceiling tile. Provide HVAC and new Fire sprinklers drops to new ceiling. Install new 2x4 LED light fixtures. Verify Fire alarm systems work. | YES | 2021-01-19 | Fall 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
20P000003 |  | 20P000003 | FALSE | GRAD DIV | SL5 UNIVERSITY OFFICE BLDG- ADDING POWER/DATA, PATCH/PAINT... | ADD POWER/DATA, PATCH/PAINT | UNIVERSITY OFFICE BUILDING |  | COMPLETE | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS | CHERYL GERRY | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-07-02 | Install hydration station when it arrives | 2021-02-17 | 2021-04-20 |  |  |  | 4/15/21, DL: This project is complete. We will install the hydration station when it arrives…..4/1/21, DL: Electrical, rough plumbing, drywall, and paint is complete. The next step is to install the floor covering with in two weeks……………3/15/21, DL: The demo, electrical and rough plumbing is complete. We will schedule inspection this week. Once we pass inspection, we will schedule the drywall installation, prime, paint and new floor covering……..2/16/21, DL: Conducted a site visit with the plumber and capenter shop. We will start the demo next week…………2/1/21, DL: We will schedule this project to start in 2- weeks……………….1/19/21, DL: Plans were approved and we will schedule the work in the near future………. 8/5/20, DL: This Project is on hold until further notice…….2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: Permit is approved. We need to verify floor covering. Once floor covering is confirmed and ordered, we will schedule the work………1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: We will need plans as we are installing a new hydration station and a counter top that needs to be ADA compliant…………We started the plans and will submit them for a permit and plan check review within 2- weeks……….10/30/19, DL: No Plans will be needed. We will plan on scheduling the work shortly after Thanksgiving……. | 2019-06-13 | Enrico Baez | 9/24/2019 E. Baez--SCOPE-- 1. Removal and disposal of one bulletin board and two director cases. 2. Removal and disposal of abandoned telephone mounting bracket. 3. Remove and dispose of abandoned alarm box in wall. 4. Patch and paint walls in lobby and public restroom area. 5. Provide electrical connection for wall mounted monitor. 6. Cut access for data boxes. 7. Install monitor mount on wall. 8. Construct 7" x 18" laminate counter top and install in Lobby. | YES | 2021-04-15 | FALL 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000687 |  | 19P000687 | FALSE | PB&A | SL 5 HUB MULTIPLE LOCATIONS - INSTALL KEY CARD ACCESS CONTROL | Provide estimate to install key card access control | HUB | Various | COMPLETE | Gerry Bomotti | TBD | MANNY SANCHEZ | BRENDAN OBRIEN | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-06-26 | plan check review | [5 empty] | 8/5/20, DL This Project is Complete……………..1/15/20 O-DHN: Emailed Status Report to customer…….1/14/20, DL: Contracts is processing the contract. Once the contract is complete, we will schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Plans were approved. I sent Brendan an email 11/11/19 requesting an FAU # as this is Recharge work. Once we have the FAU #, we will work on the contract agreement with the contractor………10/30/19, DL; Sent Lezlie and email asking if she has an update on the resubmitted plans on 10/30/19………..10/16/19, DL; The plans were resubmitted for plan check review this week. We are hopeful the plans will be approved this week. Once approved we will work on contract and scheduling the work…10/7/19 LB: This is a test. The timestamp will be reset when the test is done. 10/1/19, DL: We are working on plan check review. We should have approved plans in the next two weeks…..8/15/19, DL; Plans are currently being reviewed. We are also working on a contract with our vendor. Once plans are approved, will have a better plan for a start date and contract……. |  | Dan Lerman | Provide estimate to install key card access control |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
19P000660 |  | 19P000660 | FALSE | SOM | SL5 SOM RM 107 & 111- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SL5 SOME RB, RM 330- PROJECT: NEW PI, EQUIPMENT INSTALLATION | SOM RSCH | 107, 111 & 330 | COMPLETE | Deborah Deas | Deborah Trujillo | BRANDON BARBOSA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 9/30/20, DL: This Project is Complete………..8/5/20, DL: Dan to follow-up with customer…………..03/05/20 O-ANS: Removed room 330 per client request. Only updates to 107 & 111. |  | Enrico Baez | TBD | NO | 2020-09-30 | Fall 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000659 |  | 19P000659 | FALSE | SOM | SL5 SOM RB, RM 230- PROJECT: NEW PI, EQUIPMENT INSTALLATION | TBD | SOM RSCH | 230 | CANCELED BY CLIENT | Deborah Deas | Deborah Trujillo | CYNTHIA CAROLINA |  | Dan Lerman |  | 5 |  | FALSE |  |  | 2019-06-11 | [6 empty] | 08/05/20 O-ANS: Canceled by client (Cynthia Carolina) via email with Ron Veloz. 8/5/20, DL: Dan to follow -up with customer…………..03/31/20 O-ANS: Updated requestor from Brandon B. to Cynthia Carolina per client request. Sent scope updates to Dan L per client request. From client: "remove 330 from work order / update project details / Update: Furniture on order 3.30.2020 - delivery tbd" |  | Enrico Baez | TBD | NO | 2020-08-05 | Fall 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000624 |  | 19P000624 | FALSE | BCOE | SL5 BOURNS HALL A0346- REFURBISH RM FOR GRAD STUDENT SPACE | Refurbish Room-Student Space, | BOURNS | A0346 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | LOUIS SANDOVAL |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-05-15 | Pending information from Susanna | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Susanna is working on a cubicle layout. Once we have the information from her. We will schedule the work………… | 2019-11-07 | Enrico Baez | Remove all lower cabinets in room A0346 and all lower cabinets and mail boxes in Rm A0304 | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000600 |  | 19P000600 | FALSE | BCOE | SL5 BOURNS B316- PREPARE LAB FOR NEW PI OCCUPANCY | renovate/refresh lab space | BOURNS | B0316 | COMPLETE | Christopher Lynch | Todd Ambriz | KATHALENA COCKER |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2019-05-09 | Finish Gas cabinet installation | 2019-09-23 | 2020-02-07 |  |  |  | 8/5/20, DL: This Project is Complete…….3/25/20, DL: Project is 95% complete. We will install the fire sprinkler and exhaust duct to the gas cabinet when we return from the campus closure………..12/17/19 O-DHN: Emailed Status Report to customer……12/16/19, DL: Plans were approved and material is ordered. We are hopeful the material will arrive the 2nd or 3rd week in January. Once material is on site we will schedule the work…… 11/19/19 DH: Emailed Status Report to customer……10/16/19, DL: This project is 90% Complete. We are working on plans and permits for the two snorkels……….10/1/19, DL: This project is almost complete. We will be complete in the next 4- weeks except the Snorkel……….. 9/13/19, DL; The paint of the cabinets is scheduled for this week along with the power. We will submit the plans for the snorkel this with in the next two weeks…….9/3/19,DL; We will start working in the Lab on 9/23/19….8/15/19; Working on plans for new snorkel. We are working on contract and we should be good to go in the next 30- days….. | 2019-08-02 | Enrico Baez | SOW, Patch& Paint Walls, replace plexi glass on shelving, powder coat metal shelving & cabinets, clean & polish or replace chem sinks, polish counter tops, Validate all gas, water, drains, DI water & utilities. Replace damaged and dirty ceiling tiles, relamp as needed. Strip & wax floor. Dan L is requesting vendor pricing to restore finishes. | YES | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000547 |  | 19P000547 | FALSE | CNAS | SL5 SPIETH HALL 1363-RENOVATION | Make minor lab improvements for new PI | SPIETH | 1363 | COMPLETE | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | R3 |  | TRUE |  |  | 2019-03-26 | Schedule the work | 2020-01-31 | 2020-02-21 |  |  |  | 8/5/20, DL: This Project is COMPLETE…….3/25/20, DL: The material is here and we are 95% complete with the work. We will complete the work when we return from the campus closure…………1/31/20 O-DHN: Emailed Status Report to customer…….1/30/20,DL: The pump is now on site but we are still waiting for the fittings. In the mean time, our plumber is putting everything together and is working on the installation. Once the fittings arrive, we will make the connections and the system should be good to go………….1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: The pump is scheduled to arrive on or before 1/31/20. We will schedule the work once we have the pump and material on site…..11/26/19, DL; Emailed Natalie and Sherice the quote for the vacuum pump. We will order the material and schedule the work once we have approval and the pump on site……11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: I sent the vendor a 2nd email requesting an update on the proposal. I also included Natalie on the email so she is aware of where we stand with the proposal……10/30/19, DL: We had a followup meeting with the vendor last week. The vendor is now working on a pump that will best meet our needs……….10/16/19, DL; We are working with a vendor on a quote for a new lab vacuum pump. We are hoping to have a quote in the next week or two…..9/16/19, DL; Estimate was provided to customer last week. If the project is approved, we will work on the plans and permits. Once approved, we will schedule the work…… |  | Enrico Baez | Old SOW Revised SOWInstall exhaust hood, electical receptacle, vacuum pump, vac lines and valves (six valves total) and hood location. | YES | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
19P000539 |  | 19P000539 | FALSE | CNAS | SL5 PHYSICS 1132 MEETING TO DISCUSS HEAT LOAD/ELECTRICAL WORK | Install electrical utilities for new equipment | PHYSICS BUILDING | 1132 | COMPLETE | Kathryn Uhrich | Jose Wudka | WENDI TAPIA |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2019-03-19 | site visit with customer for review |  | 2021-03-26 |  |  |  | 4/15/21, DL: This project is 100% Complete……..4/1/21, DL: This project is complete except the sink drain and custodial. Custodial is scheduled to service the room in two weeks………3/15/21, DL: This project was supposed be be complete but we still have a plumbing drain assembly that is back ordered. We will connect the plumbing once the material arrives…………2/16/21, DL: New sink and faucet arrived, we will now schedule the install of the countertop and sink…………..1/19/21, DL: This project is in progress and will be complete with in 30- days………..9/30/20, DL: Plans were submitted for Plan Check review last week and we should have an update on the plan check review process soon………..8/5/20, DL: Need to meet with Kirk to verify electrical load. Once confirmed, we will work on plans for a permit. | 2019-10-15 | Enrico Baez | Install utilities for new equipment | YES | 2021-04-15 | Summer 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000517 |  | 19P000517 | FALSE | ENROLLMENT SERVICES | SL5 STUDENT SERVICES 1138- INSTALL MONITOR BRACKETS AND OUTLET | INSTALL MONITOR BRACKETS AND OUTLET | STUDENT SERV | 1138 | COMPLETE | LaRae Lundgren | Emily Engelschall, Sean Cason | DANIELLE GARCIA |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-03-07 | Verify scope and schedule work | 2019-12-02 | 2020-12-20 |  |  |  | 1/19/21, DL: This project is complete…………..8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced, We will schedule the work when we return from the campus closure…………11/11/19, DL: I will work on scheduling this project… | 2019-06-17 | Enrico Baez | 6/17/19 E. Baez Conducted site visit with Sean. Will need carpenters to mount TV and electricians to add outlet to North wall. Data not needed. Might need painters depending on how carpenters install TV mount. | YES | 2021-01-19 | FALL 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000514 |  | 19P000514 | FALSE | CNAS | SL5 SKYE 268-PROJECTOR INSTALL | Instal projector and relocate screen. | SKYE HALL | 0268 | CANCELED BY FS | Kathryn Uhrich | Jose Wudka | JAMES MARBERRY |  | Dan Lerman |  | R7 |  | FALSE |  |  | 2019-02-27 | We Need an FAU # | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold until further notice…….3/25/20, DL: Work orders are produced. We will schedule the work when we return from campus closure………11/11/19, DL: Project is in the queue to start but we do not have an FAU# as this is a recharge project. I sent Enrico and James an email requesting the FAU#. Once we have an FAU #, I will work on scheudling the work…..10/1/19, DL; Enrico is wtill working on estimate. | 2018-10-19 | Enrico Baez | E. Baez 1. Provide power in ceiling for projector. 2. Install projector center in room between two 4ft light fixtures. 3. Install 2 duplex outlets in 4S box on South West corner of room 4. Remove existing screen. 5. Install new screen centered on South wall. Extend power from existing screen to new screen location. 6. Use existing screen power switch to control new screen. | YES | 2020-11-19 | Summer 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
19P000504 |  | 19P000504 | FALSE | CNAS | SL5 SPIETH HALL 2349-MINOR UPDATES TO AN OLD LAB | SPIETH HALL, RM 2349- MINOR UPDATES TO AN OLD LAB. Patch Paint walls, replace flooring, refinish wood cabinets and sinks. | SPIETH | 2349 | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | ESTELLA DAVALOS |  | Dan Lerman |  | 5 |  | FALSE |  |  | 2019-02-20 | [6 empty] | 11/19/20 O-ANS: FORWARD TO PD&C - Project costs exceed state regulated FS limit of $50K. 8/5/20, DL: This Project is on hold……….12/11/19: O-ANS: Reassigned as project allotment - priority #5 for Winter 2020. 11/27/19 O-ANS: Placed on Hold for re-prioritization by client for Winter 2020. | 2020-02-27 | Enrico Baez | Patch and paint and extra work to upgrade an old lab that we are now inhabiting. In addition to painting, we need to have floors re-surfaced, cabinets re-stained, and counter tops re-surfaced, if possible. There is also a metal sink that could be polished. | YES | 2020-11-19 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000502 |  | 19P000502 | FALSE | BCOE | SL5 WCH, RM 444- MOUNT MONITOR AND RUN ELECTRICAL | Install Electrical power & TV bracket.for a 75" TV to mount in CS 342. | CHUNG HALL | 444 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | RICHARD BAIN |  | Dan Lerman |  | R3 |  | FALSE |  |  | 2019-02-19 | Schedule the work. | [5 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This project is on hold……………3/25/20, DL: Work orders are produced. I will work on scheduling the work when we return back to work…….. | 2019-09-17 | Enrico Baez | Install Electrical power & TV bracket. Excludes network/data back box and stub up to ceiling. | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
19P000485 |  | 19P000485 | FALSE | CNAS | SL5 CHAPMAN HALL REPLACE /REMOVE FUME HOOD | Remove, replace, and install one (1) (department furnished) fume hood in the lab located in Chapman Hall, Room 9. | HOMER D. CHAPMAN HALL | 9 | COMPLETE | Kathryn Uhrich | Jose Wudka | WILLIAM SUTTON |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-29 | This Project is Complete.. |  | 2021-03-12 |  |  |  | 4/1/21, DL: This Project is Complete…………..3/15/21,DL: Bill S. is still working on obtaining the air flow monitor. Once the air flow monitor arrives, we will complete the installation and Bill will be able to have the fume hood certified by a 3rd party vendor…………3/1/21, DL: We need to install the fire extinguisher and air monitor. I sent Bill S. an email asking him if he ordered the air monitor as we do not have one. I also contact EH&S and made them aware that we will be commisioning the fume hood in the very near future…..2/16/21, DL: Plumbing is complete. We will now start the exhasut vent, electrical and then seismically anchor the fume hood…………2/1/21, DL: We have had a delay with the plumbing and it is our goal to be complete on or before 3/1/21…………1/10/21, DL: This project is almost complete. This project will be complete in the next 30- days…………9/30/20, DL: Fume Hood demolition and abatement will be completed on 10/2/20. Fume hood install should be coplete in mid Novemeber……8/5/20, DL: We will submit plans this week. Once plans are approved, we will schedule the work……………Work orders are produced. We need to work on plans and permits once we return. | 2020-02-10 | Enrico Baez | Disconnect, cap and safe off the existing utility services. Provide the necessary abatement services to properly remove the fume hood from the site and deliver to the campus surplus yard. Install one new department furnished fume hood. Abatement Services: Provide the necessary abatement services to perform all utilities disconnections and floor repair. Floorcovering: Patch and or repair as necessary to match or provide a close match. Install rubber base. Access Control: Survey and adjust the entry door closer to increase latch pull to allow the door to closer completely. Patching and painting: Patch and paint wall at the old fume hood location. Mechanical: Disconnect metal duct, cap/safe off, reconnect/reconfigure new duct to accommodate the new fume hood. Electrical: Provide electrical disconnections and safe off. Reconnect/reconfigure power to the new fume hood. Plumbing: Disconnect Air, Gas, Vacuum, Cold water, and Drain, cap and safe off and reconnect/reconfigure service to the new fume hood. Resource Management: Properly remove the fume hood from the site and deliver to the campus surplus yard. | YES | 2021-04-01 | Spring 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000474 |  | 19P000474 | FALSE | CNAS | SL5 HEADHOUSE 8-AC INSTALLATION | HEADHOUSE 8 REQUEST FOR AC INSTALLATION | GH08 | 881 | COMPLETE | Kathryn Uhrich | Jose Wudka | NANCY FERGUSON |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2019-01-29 | Schedule the work. | [5 empty] | 1/19/21, DL: This project is complete……………8/5/20, DL: This project is in Progress and should be complete in the next 8-12 weeks…………….3/25/20, DL: Work orders are produced. Once we are back to work, we will schedule the work………12/11/19 O-ANS: Re-assigned as project allotment - priority #7 for Winter 2020. 11/27/19 O-ANS: Hold by client for re-prioritization for Winter 2020. | 2020-03-04 | Enrico Baez | Install new 3 ton Packaged unit with heat pump and dedicated electrical service on the roof top. Provide 1ea return plenum, 2ea supply drops in the work space. | YES | 2021-01-19 | Winter 2020 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000466 |  | 19P000466 | FALSE | FAC-PLNG-DESIGN-CONST | SL5 SPROUL HALL PROJECT: CONVERT TO GA CLASSROOM | CONVERT ROOM TO GENERAL ASSIGNMENT CLASSROOM | SPROUL | 2225 | COMPLETE | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2019-01-22 | finish plans/submit application | 2020-01-10 | 2020-03-27 |  |  |  | 8/5/20, DL: This Project is Complete…………2/19/20 O-DHN: Emailed Status Report to customer…..2/18/20, DL: We are making great progress and still on schedule to be complete before Spring Break begins. We pass drywall inspection on 2/18/20………..1/15/20 O-DHN: Emailed Status Report to customer……1/14/20, DL: Plans are approved. All items have been removed from the space. Abatement is schedule to take place within two weeks…..12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Plans were submitted for plan check review. Fire marshal stamped the plans, we are waiting on the final stamp from our building official. Once plans are approved we will order material and schedule the work……..10/30/19, DL: Gunter is working on plans. We are planning to complete the work before Spring Quarter begins. |  | Dan Lerman |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21
19P000433 |  | 19P000433 | FALSE | ITS | SL5 COMPUTING 161-INSTALL CARD READER ACCESS | Install complet card reader system for 4- doors | C&C CARPORT | 161 | COMPLETE | Danna Gianforte | Shelley Gupta | SHELLEY GUPTA |  | Dan Lerman |  | R1 |  | FALSE |  |  | 2019-01-07 | Waiting for bid for customer. | 2020-01-20 | 2020-03-31 |  |  |  | 8/5/20, DL: This Project is complete…………2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within the next two weeks. Once we have the contract, we will schedule the work……………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: Project was approved by Shelley. We will work on the contract. Once we have the notice to proceed from contracts, we will order the material and schedule the work………..11/19/19 DH: Emailed Status Report to customer…..11/11/19, DL: Sent Shelley another follow-up email today and she has not verified if she would like to move forward with the project………10/30/19, DL: Sent Shelley the updated quote last week and she has not responded. I sent Shelley a followup email today asking her to let me know if she would like to proceed with the work……..10/16/19, DL; Had a meeting with Shelley, we modified the scope of work and software for the project. We are now revising the quote with our vendor. We should have an updated quote within the next two weeks. If Shelley approves the work and scope, we will proceed….10/1/19, DL; I have a meeting with Shelley this afternoon to review proposal. If she approves the project we will submit plans for a building permit……8/15/19, DL; We conducted a construction job walk with the contractor 2- weeks ago. They are working on final estimate and plans, once plans are complete, we will submit for plan check approval and contract…….07/22/19 O-ANS: Notes from WO 18W007453 which was cancelled and converted to this project #19P000433. 7/15/19, DL; Customer approved the project today. We will work on plans, permits and a quote. Project start date is October 15th…..6/17/19, DL; We have the quote pending approval from the customer. However, the customer has a few questions regarding the option to expand on the system at a later date. We need to verify the expansion options and get back to the customer…..5/31/19, DL; Enrico to provide Sheila with a formal quote. This is recharge work, if approved, we will work on plans, permit and contract. 60- day for this project once approved…..5/15/19, DL; We have the proposal from the Vendor. Enrico will submit to Shela for review and approval. If proposal is approved, I will work on a contract through PD&C…..4/5/19, DL; Still waiting for quote from contractor…..2/28/19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
19P000427 |  | 19P000427 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR OFFICE 453 - TV & WHITEBOARD | Install Power and TV bracket, move white board | CHUNG HALL | 453 | CANCELED BY FS | Christopher Lynch | Todd Ambriz | ROBERT LOPEZ-A |  | Dan Lerman |  | R2 |  | FALSE |  |  | 2019-01-03 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Project reason did not meet FS criteria of being directly related to research, research equipment or new faculty modifications. Project can be resubmitted in future prioriization period… 8/5/20, DL: This Project is on hold……… | 2019-09-18 | Enrico Baez | Install Power and TV bracket, remove white board and relocate , patch and paint wall prior to installing | YES | 2020-11-19 | Fall 2019 | FS | 0 | 2019 | 2021-10-01 | FY 20-21 | 1
19P000414 |  | 19P000414 | FALSE | PB&A | SL5 POLICE BLDG-INSTALL NEW EXHAUST FANS IN MENS/WOMENS RESTROOM | Install new exhaust fans in both shower rooms | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | TBD | Seth Morrison |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-12-17 | pending material delivery | 2019-10-16 | 2019-11-27 |  |  |  | 8/5/20, DL: This Project is Complete………….2/19/20 O-DHN: Emailed Status Report to customer…...2/19/20, DL: We have the motor on site, we are working on the permit for the crane. Once we have the crane lift permit, we will schedule the install…………12/17/19 O-DHN: Emailed Status Report to customer…..12/16/19, DL: We are working on the new motor platform. It is our goal to install the new motor in late January. Once the motor is installed, we will be able to identify if additional work is needed…….11/19/19 DH: Emailed Status Report to customer…..11/15/19, DL: Material has not arrived……..10/30/19, DL: The new exhaust fan is ordered with a 2- 4 lead time. Once the exhaust fan arrives, we will schedule the install……….10/16/19, DL; We are in the process of the work. At this current time, we are not modifying the building to where permits may not be required…….10/1/19, DL; This is in the queue for plans, we will start the plans in the next 3-4 weeks and apply for a building permit in the next 3-4 weeks…… |  | Enrico Baez |  |  | 2020-08-05 | Summer 2019 | FS | 0 | 2018 | 2021-10-01 | FY 20-21
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5 HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | Install a new wall at open space 1101-D to create a private office. | HINDERAKER | 1101 | COMPLETE | Kim Wilcox | TBD | ALEXIS RAMBAUD |  | Dan Lerman |  | 1 | 0 | FALSE |  |  | 2018-12-11 | schedule the work | 2019-01-21 | 2019-03-27 |  |  |  | 8/5/20, DL: This project is complete…………3/25/20,DL: Doors are scheduled to arrive the second week in April……2/19/20 O-DHN: Emailed Status Report to customer……2/18/20, DL: Work is complete except for Door and final deep cleaned I do have final stain samples from the vendor. I need to verify color……… We will complete the project when the doors arrive……….1/14/20, DL: Plans are approved, PO# is cut for the ordering of the custom doors, we are currently scheduled to start the work on or shortly after 1/21/20,. Karim understands that we will start and finish the project but we will not be able to install the door until the door arrives on site. There is a minimum of 6-8 week lead time on the door delivery………….12/16/19, DL: Plans are still in plan check review. I sent the building department an email asking for a startus update today…….10/16/19, DL; Plans were submitted to our building official this week for plan check review and a permit……9/16/19, DL; Guther will work on plans in the next three weeks. Once plans are complete, we will proceed with the permit process… | 2018-12-20 | Enrico Baez | SOW: Wall: Construct a metal stud framed wall with drywall up to hard ceiling (ceiling has 12x12 glue up ceiling tiles). Hardware: Install new lockset & keys are required.***** French Door: Install new stain grade birch door with full lite. Door and finish to match the existing office doors.***** Hard Ceiling: * Ceiling is 8’-0” A.F.F. + - with 12x12 glue up ceiling tiles. Work may require a new access panel if access to space above is needed. The 12x12 glue up ceiling tiles may need to be removed where the new wall is constructed.***** Flooring: The existing flooring will remain. Install rubber base to match existing.***** Painting, Taping & Sanding: Taping sanding and painting is required at the new wall and connecting walls.***** HVAC: May require modifications to split the existing supply air to accommodate the open office space.***** Electrical: Provide light switch at new office, power(new or relocate); add and or relocate electrical and voice/data outlets required for a standard office.***** Lighting: Provide a new light switch/circuit near office entrance. The existing 2x4 fixture is on main lighting circuit and will require lighting circuit modifications. Verify if the existing lighting is sufficient for the proposed office. Field verify if additional lighting is required.***** Fire Alarm: Provide a new Smoke/chime detector at new office area, confirm requirements. | YES | 2020-08-05 | SPRING 2019 | FS | 0 | 2018 | 2021-10-01 | FY 20-21
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5 UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | CANCELED BY FS | Rodolfo Torres | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 11/19/20: O-ANS - Canceled by FS - Customer requested HOLD until future prioritization period. Project can be resubmitted/reopened in future prioriization period. Please retain project # as reference… 8/5/20, DL: This Project is on hold until further notice. | 2018-09-27 | Enrico Baez |  | YES | 2020-11-19 | Fall 2018 | FS | 0 | 2018 | 2021-10-01 | FY 20-21
19P000193 |  | 19P000193 | FALSE | CNAS | SL5 GENOMICS 4231 - FOB ACCESS SYSTEM INSTALLATION | Install one FOB reader and electrrified lockset. Utilize and connect to the existing Hirsch AP equipment located on the same floor. | GENOMICS | 4231 | COMPLETE | Kathryn Uhrich | Jose Wudka | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | Work will be complete in 2 weeks | 2020-02-03 | 2020-03-13 |  |  |  | 8/5/20, DL: This project is complete……………..06/17/20, DL: This project should be complete with in the next two weeks……..2/19/20 O-DHN: Emailed Status Report to customer……2/19/20, DL: We should have a signed contract within two weeks. Once we have a contract, we will schedule the work……….1/15/20 O-DH: Emailed Status Report to customer……1/14/20, DL: Contracts is currently working on the contract. Once the contract is complete, we will order the material and schedule the work…………11/26/19, DL: Plans were approved. We will work on the construction contract. Once we have the notice to proceed, we will schedule the work……….10/15/19, DL: Sent PD&C and follow-up email on 11/11/19. We should have approved plans in the near future……10/30/19, DL: Sent PD&C an email asking for a status update on 10.30.19…… 10/16/19, DL; Plans are still in plan check. I sent the building official an email asking if any additional information is needed. This work will be completed by a contractor which means we need to allow time for the bid and contract process……… …………9/3/19, DL; Plans are still in plan check review….8/14/19, DL; Plans are in plan check review. Once plans are approved, we will work on a contract and shcedule the work……6/17/19, DL; I still need to work on plans and permits. I will try and have the plans completed in the next two - three weeks…….5/31/19, DL; This Project is approved. I need to work on plans, permits and a contract. This project should be complete in the next 60- days…..5/3/19, DL: Ron V. Completed estimate and received project approval from the customer. I need to work on the permits and contract. Goal to complete the work near 7/1/19…….4/15/19, DL; Need to walk project with Contractor and obtain quote….. | 2018-10-08 | Enrico Baez | Request for Estimate to install three new FOB readers with electrified locksets. Work covered: Install one AC Fob Reader at door 2221 and one AC Fob reader at each Door 4231 & 4235. Connect card readers to the existing Hirsh ACP located in the IDF closet at each floor. 03/07/19: Scope revised to eliminate two FOB readers. Install one FOB reader at Genomics door 4231 only instead of all three rooms. | YES | 2020-08-05 | Fall 2018 | FS | 0 | 2018 | 2021-10-01 | FY 20-21
18P000453 |  | 18P000453 | FALSE | CNAS | SL5 DELFINO LAB-SOIL HOUSE MODIFICATION | Modify the existing room in Soil House 1 (attached to the Delphino Lab at the Rubidoux Facilities) to expand CCPP quarantine services to include USDA/CDFA compliance for installation of new Economic Development Administration (EDA) citrus growth chambers. | DELFINO HHSE |  | TO BE PERFORMED BY PD&C | Kathryn Uhrich | Jose Wudka | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | Research and plan development | [5 empty] | 12/7/20, DL: This project will be managed by PD&C…..9/30/20, DL: Project is still on Hold until Furhther notice………...8/5/20, DL: WE will work on plans in the next 30- 45 days……………6/17/20, DL: This project is under review and is on hold until further notice………10/3/19 O-ANS: Plan Development per Minor Reno Meeting. 10/1/19,DL; We are getting ready to start the plans as we are currently conducting resarch on products that will meet the needs of the space……………..5/31/19, DL; Per Scott Donell, this project may be ready to start in January or February of 2020……05/16/19 O-ANS: Hold to begin work in Summer 2019. 3/18/19, DL; Scott D. is working on the electrical and structual Engineering. We will move forward with plans and permits once Scott is complete with his items…..2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman |  | YES | 2020-12-07 | Summer 2018 | FS | 0 | 2018 | 2021-10-01 | FY 20-21
18P000214 |  | 18P000214 | FALSE | VC-STU AFF | SL5 COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Install Card readers | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  | 2 | 2 | FALSE |  |  | 2017-12-08 | Pending special order part | 2019-02-19 | 2020-09-01 |  |  |  | 1/19/21, DL: This project is 100% Complete…….9/30/20, DL: Vendor should have the balance of the material in the next 30- days…….8/5/20, DL: This project is complete except the card reader portion of the project…………6/17/20, DL: The floor covering was completed two weeks ago. The card reader portion of this project is 95% complete but additional parts were needed and they are on order. Once they arrive, we will schedule the installation and this project will be 100% Complete………1/15/20 Emailed Status Report to customer…..1/14/20, DL: We were recently approved to proceed with the work. I have reached out to the vendor for the doors and card access. We are still waiting to hear back from them so we can order the material and schedule the work. I communicated with Nicole on the floor covering replacement. Nicole needs to verify what areas we will replace as we were going to complete several offices and a hallway as part of the scope but this will displace many team members for at least a week. We will work on scheduling the work once Nicole gets back to me……..12/17/19 - O-DHN: Emailed Status Report to Customer……12/19/19, DL; We are working with our contractor to order the material and schedule the work. Once we have confirmation on the material, we will be able to schedule the work. It Is our goal to start this project in late January……11/26/19, DL: This project was taken off of on hold and we can now proceed. I contacted the contractor last week and I am awaiting their response on when they can schedule the work. I also left a message with them this morning………..7/1/19, DL; This project is on Hold….6/17/19, DL; Contractor for doors confirmed they will start pulling wire this week. Door hardware delivery is about two weeks out. Once material arrives, we will schedule the installation.….5/31/19, DL; Contract is almost complete processing the contract for the door hardware. We are hopeful to have a notice to proceed within the next two weeks. The floor covering should start in three weeks. Note, we will complete the floor covering install over the course of three weeks……4/15/19; All work is completed except the floor covering and electronic card readers for the doors…..2/28/19, DL; This project is in progress and on schedule………2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being prepped for paint. We have a pre-construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, material is ordered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct site visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez |  | YES | 2021-01-19 | Winter 2018 | FS | 0 | 2017 | 2021-10-01 | FY 20-21
9068 | 9068 |  | FALSE | PB&A | Ag Ops Field 6B Pump Station | Provide downstream electrical engineering as-needed to facilitate UCR plan-check and inspection of Owner Furnished Contractor Installed agricultural pump station equipment. Power provided by Riverside Public Utilities and confirm existing RPU meter account based upon street address or if new account is required UCR shall apply. |  |  | Programming | Gerry Bomotti | TBD | Tom Toepfer |  | Daneca Stevens |  |  |  | FALSE | 82967.1 |  | 2021-09-16 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
9067 | 9067 |  | FALSE | PB&A | DM(FY20) Campus Infrastructure Access Control | Access Control: Automate Access Controls focusing on General Assignment Classrooms. |  |  | DM project to be funded | Gerry Bomotti | TBD |  |  | Fernando Nunez |  |  |  | FALSE | 200000 |  |  | DM project to be funded | [12 empty] | PD&C | 0 | 1900 | 2021-10-01
9066 | 9066 |  | FALSE | PB&A | DM(FY20) Sproul HVAC | Equipment/Controls - Replace Heat Exchangers/VFD Pumps |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Daneca Stevens |  |  |  | FALSE | 226000 |  |  | Programming | [12 empty] | PD&C | 0 | 1900 | 2021-10-01
9065 | 9065 |  | FALSE | PB&A | DM(FY20) Olmsted HVAC Repairs to Air Handlers | Equipment/Controls - Repairs to Air Handlers |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Vilma Kern |  |  |  | FALSE | 200000 |  |  | Programming | [12 empty] | PD&C | 0 | 1900 | 2021-10-01
9064 | 9064 |  | FALSE | PB&A | DM(FY20) Olmsted HVAC Replace Economizers | Equipment/Controls: Replace economizers for fresh air controls for all Air handlers |  |  | Pre-Programming | Gerry Bomotti | TBD |  |  | Vilma Kern |  |  |  | FALSE | 200000 |  |  | Programming | [12 empty] | PD&C | 0 | 1900 | 2021-10-01
9063 | 9063 |  | FALSE | PB&A | DM(FY20) Boyce Building Systems Improvements | Provide improvements to antiquated mechanical-electrical-plumbing systems to extend building useful life |  |  | In Programming | Gerry Bomotti | TBD |  |  | Tameesha Hayes |  |  |  | FALSE | 900000 |  |  | Design | [12 empty] | PD&C | 0 | 1900 | 2021-10-01
9061 | 9061 |  | FALSE | PB&A | DM(FY20) Bourns A Replace Elevated Platform Stone Surfaces |  |  |  | Design | Gerry Bomotti | TBD | ---- |  | Tameesha Hayes | 99 |  |  | FALSE | 250000 |  |  | Bidding | [12 empty] | PD&C | 0 | 1900 | 2021-10-01
9060 | 9060 |  | FALSE | PB&A | DM(FY20) Physics Roof Repair/Replacement/Equip |  |  |  | In Bidding | Gerry Bomotti | TBD | ---- |  | Daneca Stevens | 99 |  |  | FALSE | 594000 |  | 2020-09-15 | Award Contract | [12 empty] | PD&C | 0 | 2020 | 2021-10-01
9059 | 9059 |  | FALSE | PB&A | DM(FY20) Elec. Equip. Replace 10 Gas-Filled Med Volt. Switches | Replace ten gas filled - medium voltage switches |  |  | Design | Gerry Bomotti | TBD | David Palacios |  | John Franklin | 99 |  |  | FALSE | 500000 |  | 2020-09-22 | Bidding | 2022-01-01 | 2022-04-01 | [10 empty] | PD&C | 0 | 2020 | 2021-10-01
9058 | 9058 |  | FALSE | PB&A | Lothian West Rooftop Solar |  |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 99 |  |  | FALSE | 835000 |  | 2020-09-23 | Complete Construction | 2021-07-01 | 2022-02-01 | [10 empty] | PD&C | 0 | 2020 | 2021-10-01
3658 | 3658 |  | FALSE | CNAS | CVWD Canal Water Delivery Design | CVWD is under construction for delivering Colorado River (canal) water to the Oasis area. The project includes delivery to UCR at two sites, one North (60 acres) and one South (200 acres) of Avenue 72. Canal water should be available at both Delivery Points by January, 2023. IID engineering, PVC material, steel pipe, electrical supplies will require significant lead times. Hence, I recommend starting the design phase of these projects sooner than later. I included a Water Cost Comparison analysis presented in late 2020 to help justify capital improvements required prior to CVWD canal water delivery. |  |  | Pre-Programming | Kathryn Uhrich | Jose Wudka | Sue Lee |  | Daneca Stevens |  |  |  | FALSE |  |  | 2021-09-02 | Programming | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3656 | 3656 |  | FALSE | PB&A | Falkirk Standardized Balcony Drawings | Provide professional design services to complete construction drawings that will standardize balcony demolition and window frame-in at each balcony location type. Miyamoto is the architect for the Falkirk Seismic project. Given their extensive knowledge of the facility, we would like to negotiate design services with them for this project. |  |  | Pre-Programming | Gerry Bomotti | TBD | Sean Hatfiled |  | Daneca Stevens |  |  |  | FALSE | 10000 |  | 2021-09-02 | Programming | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3655 | 3655 |  | FALSE | PB&A | ECS Playground Improvements | Provide professional design services to complete schematic design, design development, and cost estimate for ECS North and South playgrounds. Scope of work includes reconfiguring pathways to mitigate trip hazards and meet ADA requirements, improve playground equipment and surfaces, add shade structures. Refer to John Franklin for more details. |  |  | Funding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin |  |  |  | FALSE |  |  | 2021-09-08 | Secure Funding | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3652 | 3652 |  | FALSE | FAC-PLNG-DESIGN-CONST | 266 Frost Ct. Fence, Electric Meter, Lighting, Irrigation | 266 Frost Court - Install fence utilizing rod iron gates already on hand at BG; install electrical meter and lighting for security purposes; install battery operated irrigation. |  |  | Pre-Programming | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Daneca Stevens |  |  |  | FALSE |  |  | 2021-08-17 | Programming | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3650 | 3650 |  | FALSE | CNAS | Greenhouse 16-3 Rebuild Estimate | We need an estimate to rebuild greenhouse 16-3 that burned down in a fire |  |  | Pre-Programming (Insurance Claim) | Kathryn Uhrich | Jose Wudka | Sue Lee |  | Vilma Kern | 13 |  |  | FALSE |  |  | 2021-08-02 | Programming | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3648 | 3648 |  | FALSE | PB&A | Bannockburn Walkway Repairs | Several walkway locations at Bannockburn have deteriorated to the point that they must be replaced. The topcoat is past it’s service life and has lost all waterproofing effectiveness. As a result, the underlying sheathing, T&G, and support beams have suffered extreme water damage. Scope of Work: Replace support beams, T&G, and topcoat system at 2 locations: L bldg. & V bldg. Requesting JOHN FRANKLIN as PM. |  |  | In Construction | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 1 |  |  | FALSE |  |  | 2021-07-12 | Complete Construction | 2021-10-01 | 2021-12-01 | [10 empty] | PD&C | 0 | 2021 | 2021-10-01
3645 | 3645 |  | FALSE | PB&A | Falkirk Seismic Rating Study | FALKIRK STRUCTURAL STUDY - provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. |  |  | Programming (Study) | Gerry Bomotti | TBD | Sean Hatfield |  | D.Hecht/J.Franklin | 2 |  |  | FALSE |  |  | 2021-07-12 | Complete Study | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3644 | 3644 |  | FALSE | LIBR | Rivera Library Fire Suppression Study | Request for estimate for installing fire suppression system in Rivera Library 4th floor and Secured area on Basement floor. |  |  | In Programming (Study) | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Vilma Kern | 1 |  |  | FALSE |  |  | 2021-06-25 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3642 | 3642 |  | FALSE | CAP PROG | South District Planning Study | The “South District” presents a unique opportunity to create a strong identity for academic and research expansion across the campus loop road with an emphasis on creating a transformative and synergistic new campus neighborhood. Its hillside location makes it highly visible from the freeway and the Core Campus, presenting a significant opportunity to enhance campus identity. The site’s high elevation also gives it unobstructed views outward. A holistic and integrated planning framework for its development is important to ensure alignment with broad planning strategies and principles in place for the campus, as established in land planning per the DRAFT 2021 Long Range Master Plan and the more detailed physical planning vision from the 2016 Physical Master Plan Study for this “opportunity site”, and its immediate context. The upcoming effort to update the campus’ Physical Design Framework document will further analyze the unique opportunities afforded by the South District, and leverage the design of the School of Business Building to establish organizing principles for how the area could be optimally redeveloped to its highest potential. |  |  | Programming (Study) | Jacqueline Norman | Sharyl Murdock | Uma R. |  | Uma R. | 19 |  |  | FALSE | 51000 |  | 2021-06-10 | Complete Study | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3640 | 3640 |  | FALSE | VC-RED | MRB Circulation Pumps E-Power | MRB Circulation Pumps e-Power |  |  | On-Hold | Rodolfo Torres | Laura Manor | Tara Barthol |  | Vilma Kern | 1 |  |  | FALSE |  |  | 2021-06-30 | On-Hold | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3636 | 3636 |  | FALSE | PB&A | Tunnel DAS | Adding radio repeaters to the tunnel system to improve coverage in a high hazard work area. The project consists of adding a rooftop antenna, battery back-up, amplifier, repeater antennas, and coax runs through the tunnel system. A few items need to be mounted. Golden State Communications will need to interface additional system to the existing radio system. |  |  | In Funding | Gerry Bomotti | TBD | Tracy Stark |  | Vilma Kern | 1 |  |  | FALSE | 106625 |  | 2021-05-05 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3634 | 3634 |  | FALSE | CNAS | Botanic Garden Dome | Request is for an architect to draw a design for a replacement of current geodesic dome. Design can then be used as basis for fund-raising campaign to construct new dome. Dr. Holt, UCRBG Director, has been in discussions with Jacqueline Norman and Drew Hecht. Dome was constructed on site in 1980s, all wood, greatly deteriorated. Dome is unrepairable, unsafe, and closed to the public. Goal is to replace it with a structure as close to the original dome shape as possible but with modern functionality. We envision a structure with partial solid walls near the ground, then lath on upper walls and top, possibly cross shaped with doors at ends of the arms, and a domed center for taller plants. Should have “wood look” or at least maintain original sensibility since it is beloved as is, but needs a durable material! Function—house the collection of shade-requiring plants including prehistoric plants, subtropical plants, and others. Design should include space for plants inside around the edges and a wide walkway in a circle around a central display, suitable for tour groups, small gatherings, and photography. Arms extending in cross shape could house additional plants, displays, even sale plants. |  |  | Pre-Programming | Kathryn Uhrich | Jose Wudka | Jodie Holt |  | Fernando Nunez | 2 |  |  | FALSE |  |  | 2021-04-13 | Secure Funding | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3632 | 3632 |  | FALSE | ATHLETICS | SRC North Instant Replay System | Possible update of instant replay system in Student Recreation Center North to include volleyball if mandate by Big West Conference is enacted. This will include placing cameras on the ends of the court that will send signal back to the control room and could involve additional wiring to courtside connection boxes. Scope may include upgrading audio connections. Volleyball season starts in late August... first home game TBD. No charges to this FAU unless Athletics notified in advance of work to be performed. Work Notes: Project will require coordination not only with Athletics but must also with Recreation (Mike Eason), and their scheduling may affect above dates. Possible vendor to be consulted is TechNet who has indicated ability to do such a project in recent times. |  |  | Delayed until 8/2022 per Athletics | Tamica Smith Jones | Joe Erbland | Joe Erbland |  | Tameesha Hayes | 3 |  |  | FALSE |  |  | 2021-04-01 | Delayed until 8/2022 per Athletics | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3631 | 3631 |  | FALSE | ITS | SOM-ED 1 UPS | The Information Technology Solutions (ITS) intends to replace its existing UPS unit with a state of the art systems that will support all of the requirements set-forth by the University of California, Riverside ITS and Facilities departments. Our primary objective is to provide ITS critical services and various other software applications. The ITS department would like to Procure (1) redundant UPS System with all accessories and maintenance for three years after warranty (AMC). Procure One Replacement 500KW UPS Unit, Installation of New UPS, Removal and Disposal of Old UPS components, Startup Services for New UPS, Electrical Installation of New UPS and Removal of Rental UPS connections (High Voltage) |  | 1625 | Funding | Danna Gianforte | Shelley Gupta | Cesar Higueros |  | Tameesha Hayes | 1 |  |  | FALSE |  |  | 2021-07-22 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3630 | 3630 |  | FALSE | SOM | SOMR Egress Doors/Cameras | All egress doors for floors 1-3. need to be replaced with compliant standards. Project to also include security cameras for entry and exit on 1st and 2nd floor. |  |  | Design | Deborah Deas | Deborah Trujillo | Cynthia Carolina |  | Tameesha Hayes | 2 |  |  | FALSE | 65000 |  | 2020-03-04 | Bidding | [12 empty] | PD&C | 0 | 2020 | 2021-10-01
3627 | 3627 |  | FALSE | VC-STU AFF | Costo Hall New Doors | Add three (3) doors to divide new office designations in Costo Hall. Two of the doors require new frames |  |  | On Hold | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 8 |  |  | FALSE |  |  | 2021-03-04 | On Hold | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3626 | 3626 |  | FALSE | UNDERGRADUATE EDUCATION | Rivera Library Room Modifications | Conduct room modifications to support new wall display on west wall Rivera A101A. Work needed: 1. West wall - ½” three-ply to support 12 x 55” displays over bookshelves. 2. West wall – drywall cover bookshelves any area not covered by the technology displays. 3. West wall – add electrical outlets as needed for new displays 4. North and south walls – add electrical for new motorized shades 5. Rivera A101A – add carpeting 6. Rivera A101A – paint room Notes: - Working with Chuck Forsyth in ITS and Bahram Mobasher from CNAS/Physics on project. - Israel and Chuck had a preliminary meeting with Enrico Baez from facilities to discuss project. - Point of contact: Israel Fletes and Charles Forsyth. Israel Fletes cellphone: 951-300-6693 |  | A101A | In Design |  |  | Israel Fletes |  | Vilma Kern | 1 |  |  | FALSE | 32000 |  | 2021-02-10 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3624 | 3624 |  | FALSE | BCOE | CE-CERT Circuit Upgrade | We have an existing 208 VAC 100 Amp circuit. We would like to upgrade to a 200 Amp service. The existing service is located in the electrical room at 1084 Columbia. |  |  | In Design | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Tameesha Hayes | 5 |  |  | FALSE | 4100 |  | 2021-03-03 | Bidding | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3623 | 3623 |  | FALSE | CNAS | NRS Prop 68 Study - Boyd | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. Boyd Deep Canyon Reserve: Tasks by Priority 1. Mayhew Building - Roof 2. Agave Hill Facility a. Replace rotting deck b. Add shade structure c. Cover exterior with Cortan d. Paint interior 3. Plumbing - replace corroded galvanized pipes with pvc. 4. Laboratory AC - replace with new units 5. Mayhew – floors, lighting, toilets a. Remove linoleum, clean, polish and seal concrete b. Replace Carpets c. Upgrade to LED lighting d. Install motion detection lighting e. Replace toilets with water conserving dual flush units 6.Old Campground a. Replace plastic roofs with Cortan Steel b. Replace degraded wood supporting shade structures We have some material and contractor estimates for these tasks. Most of these alterations are light, but the roof is complex. We will be hiring a contractor for the Mayhew roof and to replace the AC units. We would be interested in hiring UCR facilities to replace the carpets and remove linoleum in Mayhew building. The rest of the work will be performed by reserve staff. More info on facilities here: https://deepcanyon.ucnrs.org/reserve-facilities/ |  |  | Programming (Study) | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Fernando Nunez | 7 |  |  | FALSE |  |  | 2021-02-02 | Pending submittal of Prop 68 items | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3618 | 3618 |  | FALSE | CNAS | NRS Prop 68 Study-James Reserve | This is a request for a cost estimate that is due to Wildlife Conservation Board to secure funding by March 1st, 2021. We are requesting a cost estimate from PD&C for charges the projects will incur from project management, CEQA exemption, architects, permits, and certification that will be needed. An accurate cost estimate is necessary to apply for funding for these projects. In short, we are looking to accomplish these items below. 1. Reserve-wide a. Upgrade battery bank and connections b. Install generator as backup for solar 2. Lolomi Lodge a. Install column skylights b. Replace asphalt shingle roof with fire-resistant steel roof 3. Trailfinder Lodge a. Install double-paned windows for insulation b. Install central heating b. Install solar panels We have some material and contractor estimates for these tasks, with the exception of the Lolomi Lodge roof replacement. Most of these alterations are light, but the roof is complex. We will be hiring different contractors for the roof, windows, solar. |  |  | On-Hold | Kathryn Uhrich | Jose Wudka | Heather Constable |  | Fernando Nunez | 8 |  |  | FALSE | 8380 |  | 2021-02-02 | Approval to close or move forward | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3616 | 3616 |  | FALSE | CAP PROG | University Ave/Canyon Crest Dr Improvements | $100,000 in Violent Acts Mitigation and Prevention funding have been awarded to study short and long-term safety improvements at the intersection at University Avenue and Canyon Crest Drive. Subsequent activities will involve the construction of identified improvements. |  |  | Design | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Uma R. | 16 |  |  | FALSE | 100000 |  | 2021-03-01 | Construction | 2022-01-01 | 2022-02-01 | [10 empty] | PD&C | 0 | 2021 | 2021-10-01
3615 | 3615 |  | FALSE | CAP PROG | Student Success Center Buildout | Buildout and furnishing of the SSC dining venue for temporary use as seating/study area and other as needed construction scope related to the overall building project that was not described in the Basis of Design. |  |  | Furniture & Equipment | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Mihai Gavan | 17 |  |  | FALSE | 980000 |  | 2021-03-09 | Close-out | 2021-03-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2021 | 2021-10-01
3614 | 3614 |  | FALSE | INACTIVE P&B | MLK Water Meters | Provide by contract plumbing point of connections and irrigation infrastructures to north and south sides of Martin Luther King Blvd. for watering of UCR palm trees. City of Riverside shall install two (2) ¾” [City] water meters at points of connection. Provide approximately 300’ of new irrigation main-line with associated trenching via contract and/or via facilities work order TBD. |  |  | In Bidding | Gerry Bomotti | Sharyl Murdock | Scott Donnell |  | Vilma Kern | 17 |  |  | FALSE | 31790 |  | 2021-04-30 | Award Contract | 2021-11-01 | 2021-12-01 | [10 empty] | PD&C | 0 | 2021 | 2021-10-01
3613 | 3613 |  | FALSE | CAP PROG | Corp Yard Modular Building Relocation Study | This project will be to relocate the existing School of Medicine modular trailer (P5825) to the Corp Yard (specific location to be determined). This modular needs to be relocated due to the new School of Medicine Education Building II project being located on this site. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Tameesha Hayes | 18 |  |  | FALSE |  |  | 2021-04-23 | Complete Construction | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3612 | 3612 |  | FALSE | CAP PROG | Native American Landscape Garden | Create a physical marker to commemorate the UCR Land Acknowledgement in the form of a Native American Landscape Garden (working name) at the proposed project location. |  | Ext | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Uma R. |  | Vilma Kern | 15 |  |  | FALSE | 103000 |  | 2021-02-11 | Design | [12 empty] | PD&C | 0 | 2021 | 2021-10-01
3610 | 3610 |  | FALSE | PB&A | Hulen Place Homeless Medical Clinic | SOM is acquiring additional space for a medical clinic to assist with the homeless population. |  |  | Funding | Gerry Bomotti | TBD | Diana Armenta |  | Daneca Stevens | 5 |  |  | FALSE |  |  | 2020-10-06 | Secure Funding | [12 empty] | PD&C | 0 | 2020 | 2021-10-01
3608 | 3608 |  | FALSE | VC-STU AFF | HUB2 Roof Repair | HUB Facilities staff has determined that a section of the roof for HUB II is not repairable due to possible architectural conflicts. The following is the assessment from our Facilities staff: We had a couple roofing contractors come out and look at latitudes roof leak and give us their thoughts. We determined that the connection from the panel sheet metal to the cricket pan is failing. The cricket pan itself has a couple inches of play when stepped on. The roofing contractors say trying to waterproof these two medals together as they expand and contract with the weather would be really tough. These pictures were taken July 24th at 8:30 in the morning and the water you see is condensation. Another problem is the cricket pan slopes towards the panel sheet metal not allowing the water to go through the cricket wall into the drains causing the water to collect on that failing joint. Over the years we’ve tried numerous times with different materials to seal that joint with no success. I was able to pull up the roofing patch we put on and seen the panels are now starting to rust. |  |  | In Funding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Tameesha Hayes | 3 |  |  | FALSE | 61918 |  | 2020-09-21 | Secure Funding | 2021-09-01 | 2021-09-01 | [10 empty] | PD&C | 0 | 2020 | 2021-10-01
3607 | 3607 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY20) Central Utility Plant Controls | Central Utility Plant Control System Equipment Upgrade (see attachment in CPMS for high-level scope) |  |  | Design | Susan Marshburn | Da Lan Dinh | David Palacios |  | Fernando Nunez | 1 |  |  | FALSE | 1200000 |  | 2020-09-17 | UCR Decision for Controls Manufacturer | [12 empty] | PD&C | 0 | 2020 | 2021-10-01
3602 | 3602 |  | FALSE | CNAS | GH 16 Retractable Shade Cloth | Purchase and Install a retractable shade cloth for Greenhouse 16-1/16-2 |  |  | On-Hold | Kathryn Uhrich | Jose Wudka | Mireya Botello Santoyo |  | Vilma Kern | 1 |  |  | FALSE | 44871.65 |  | 2020-07-14 | Secure Funding for Additional Scope | [12 empty] | PD&C | 0 | 2020 | 2021-10-01
3599 | 3599 |  | FALSE | CNAS | MS&E 155 Pulsed Laser Deposition | Setting up a PLD and MBE system, which includes three steel chambers. Unit weights 900 lbs. We pump down to high vacuum, 10-10Torr. We will grow thin films at the atomic level. And also we need to heat to 1000C. For Jing Shi. |  | 0155 | In Design | Kathryn Uhrich | Jose Wudka | Wendi Tapia |  | Tameesha Hayes | 12 |  |  | FALSE |  |  | 2020-06-19 | Waiting for equipment from overseas | [12 empty] | PD&C | 0 | 2020 | 2021-10-01
3596 | 3596 |  | FALSE | CNAS | Rubidoux MPGU | Requesting use of exterior space for temporary modular plant growth unit to be installed at the Rubidoux Greenhouses for the Citrus Clonal Protection Program. The desired location for the portable building is CAAN # P5395 where there was a previous portable office building torn down in 2016. Project was prioritized to begin in Spring of 2020. It has already been delayed due to covid-19. We need this to start ASAP to ensure that we do not lose federal funding. WE need permits in place to procure the grow pod. This is associated with work order # 20P000318. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Georgios Vidalakis |  | Tameesha Hayes | 5 |  |  | FALSE | 643925.09 |  | 2020-09-11 | Complete Construction | 2021-01-01 | 2022-01-01 | [10 empty] | PD&C | 0 | 2020 | 2021-10-01
3593 | 3593 |  | FALSE | CNAS | R'Garden Walk-in Cooler Installation | Will purchase and replace a Walk in Cooler at community R'Garden need campus permitting process, plans and approvals, earthquake safety and fire marshal sign off. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Richard Zapien |  | Vilma Kern | 3 |  |  | FALSE | 39000 |  | 2020-05-08 | Complete Construction | 2021-06-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2020 | 2021-10-01
3583 | 3583 |  | FALSE | VC-STU AFF | SRC North Replace Bleachers | Replacement of the 3 set of bleachers on the SRC North main gym. |  |  | Pre-Programming | Brian Haynes | Cathy Eckman | Michael Eason |  | Fernando Nunez | 7 |  |  | FALSE |  |  | 2020-03-03 | Updated Proposal for Bleachers Cost | [12 empty] | PD&C | 0 | 2020 | 2021-10-01
3574 | 3574 |  | FALSE | UNEX | UNEX Roof Repair/Solar | We had a request from our Dean to look into solar panels on our roof, which also needs repairs. We were asked to input a request to do both at the same time. | UCR EXTEN CT |  | On Hold | Kevin Vaughn | Rick Aten | Sandy Navarro |  | Tameesha Hayes | 2 |  |  | FALSE |  |  | 2019-12-10 | Departmental Approval | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3564 | 3564 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17-19) Rivera Library North Wing AHU Replacement | Replacement of two (2) air handling units [AHU] of like-CFM in the north wing of the Rivera Library including new Automated Logic Controls [ALC], multi-zone damper and actuator replacement, zone thermostat replacement, specification of Energy Labs [AHU] or approved equal, provide design requirements for supplemental air during phased construction. | RIVERA LIB |  | Funding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 9 |  |  | FALSE | 3000000 |  | 2019-11-06 | Secure Funding | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3559 | 3559 |  | FALSE | CNAS | USDA Screen House Expansion | Land shall be prepared according to permit requirements, water run-off drainage system shall be installed and shall be compatible with the existing drainage system. Two (2) existing vestibules shall be removed and reutilized, two (2) each new screened compartments shall be added with dimensions of 60 feet wide by 50 feet long by 15 feet high and shall share the existing [exterior] wall, construction shall be compatible to and consistent with existing steel frame. New mechanical, electrical, plumbing and gas utility shall be provided per plan. Irrigation, pesticide, hydraulics shall be provided to match existing. All permitting and utility connections shall be obtained through the University of California, Riverside. | GERMPLASM |  | In Design by USDA | Kathryn Uhrich | Jose Wudka | MaryLou Polek |  | Daneca Stevens | 10 |  |  | FALSE | 2500 |  | 2019-10-04 | Construction by USDA | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3550 | 3550 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Skye Hall HVAC Replacement | Replacement of roof-mounted HVAC package units with test and balance [TAB] of entire building and correction of indicated imbalances, record drawings in CAD with final TAB to Facilities Services. | SKYE HALL |  | Bidding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 6 |  |  | FALSE | 2250000 |  | 2019-09-05 | Award Contract | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3549 | 3549 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Decking | Fine Arts Decking - $600,000 FY2017-2019 DMFI Waterproof deck and resolve drainage issues. May need structural engineering | ARTS |  | Funding | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 7 |  |  | FALSE | 600000 |  | 2019-09-05 | Combine with Exterior Proj CP3548 | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3548 | 3548 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Fine Arts Performance Lab Ext | Fine Arts Performance Lab Exterior - $600,000 FY2017-2019 DMFI - Replace section of exterior stucco skin and waterproof | ARTS |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Tameesha Hayes | 8 |  |  | FALSE | 500000 |  | 2019-09-05 | Bidding | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3541 | 3541 |  | FALSE | INACTIVE P&B | Olmsted Sidewk/Tunnel V16 Repair | Demolish, remove, and rebuild approximately 7400 sf of damaged sidewalk bounded by Watkins Hall on the north, Olmsted (University) Theatre on the south, and Rivera Library on the east. The sidewalk serves as an accessible path of travel as well as fire apparatus access. Underneath the sidewalk is a rectangular concrete utility tunnel, V16, with a roof that is collapsing and is currently stabilized by temporary shoring. Approximately 375 feet of said tunnel requires repair. The sidewalk and tunnel will be integrated into a single project. | WATKINS |  | Re-bid | Gerry Bomotti | Sharyl Murdock | Daneca Stevens |  | Daneca Stevens | 2 |  |  | FALSE | 507364 |  | 2019-07-30 | Award Contract | 2021-11-01 | 2022-01-01 | [10 empty] | PD&C | 0 | 2019 | 2021-10-01
3529 | 3529 |  | FALSE | FAC-PLNG-DESIGN-CONST | DMFI(FY17-19) Physics 2000 Renewal - Handrail | Renewal of Physics 2000 Lecture Hall. May incl--ude paint, flooring, seating, A/V and lighting improvements. | PHYSICS |  | In Construction | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | John Franklin | 3 |  |  | FALSE | 1340000 |  | 2019-05-15 | Complete Construction | 2021-05-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2019 | 2021-10-01
3516 | 3516 |  | FALSE | PB&A | Student Health & Counseling Center (SHCC) | New Student Health and Counseling Center: Provide a new facility to house health and wellness services for students. Facility will include clinical space, lab and pharm services, counseling offices, admin space and shared spaces for conr functions. Current facilities are undersized and in poor condition- new building is needed to support health and wellness services for growing student population. |  |  | Design | Gerry Bomotti | TBD | ---- |  | Fernando Canon | 1 |  |  | FALSE | 34750000 |  | 2019-03-04 | Construction | 2021-12-01 | 2023-05-01 | [10 empty] | PD&C | 0 | 2019 | 2021-10-01
3512 | 3512 |  | FALSE | VC-STU AFF | Hinderaker VCSA Office | Remodel and reconfigure of VC office of Student Affairs - Hinderaker 2nd floor (2108, 2108A, 2108C, 2108D, 2108E, 2108F) | HINDERAKER | 2108ACDEF | Pre-Programming | Brian Haynes | Cathy Eckman | Christina Wong |  | Vilma Kern | 5 |  |  | FALSE | 130000 |  | 2019-03-19 | Programming | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3510 | 3510 |  | FALSE | PB&A | SOMED Data Center Upgrade | Feasibility Study for SOM Ed Bldg Data Center upgrade. Study will determine the critical needs of the data center for current and future use, as well as provide cost estimate. The study will include: feasibility of locating a 500kw UPS inside bldg, examination of existing backup generator, examination of electrical and hvac upgrades, examination of raised floor, and more. | SOM EDUC |  | In Bidding | Gerry Bomotti | TBD | Daneca Stevens |  | Tameesha Hayes | 4 |  |  | FALSE | 1312000 |  | 2019-03-04 | Award Contract | 2021-11-21 | 2022-03-01 | [10 empty] | PD&C | 0 | 2019 | 2021-10-01
3508 | 3508 |  | FALSE | PB&A | SOM Education Bldg 2 | New facility that would provide instructional and student space, admin space, clinical faculty offices, research and support space and specialized instruction and related support space for the School of Medicine. The program would ideally co-locate functions currently housed in multiple locations on and off campus. |  |  | In Construction | Gerry Bomotti | TBD | Melissa Garrety |  | Mihai Gavan | 8 |  |  | FALSE | 97050000 |  | 2019-03-04 | Complete Construction | 2021-07-01 | 2023-05-01 | [10 empty] | PD&C | 0 | 2019 | 2021-10-01
3507 | 3507 |  | FALSE | PB&A | Undergraduate Teaching & Learning Facility | New construction facility that will provide new class labs and other academic and instruction space to support undergraduate enrollment growth. There is increasing demand for class laboratories based on evolving curriculum and enrollment patterns. |  |  | In Programming | Gerry Bomotti | TBD | ---- |  | Dexter Galang | 9 |  |  | FALSE | 100000000 |  | 2019-03-04 | DB Competition | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3499 | 3499 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Terrace Analysis (RE Proj) | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | In Programming (Study) | Susan Marshburn | Da Lan Dinh | Blythe Wilson |  | Thomas Toepfer | 13 |  |  | FALSE |  |  | 2019-02-14 | Complete Study | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3492 | 3492 |  | FALSE | PB&A | W.Campus Irrigation System Study | Study to examine examine integrity and efficiency of irrigation system on west campus, as well as 5 existing reservoirs. Will also analyze the potential for future well development. |  |  | Programming (Study) | Gerry Bomotti | TBD | Scott Donnell |  | Daneca Stevens | 10 |  |  | FALSE | 65000 |  | 2019-03-04 | Complete Study | [12 empty] | PD&C | 0 | 2019 | 2021-10-01
3474 | 3474 |  | FALSE | PB&A | RUSD STEM High School | RUSD will be developing a STEM High School on UCR property, between Watkins and Linden Ave. RUSD will funding and managing the project, with UCR providing input as to land use and design. UCR will act as lead agency for CEQA. |  |  | In Programming (Study) | Gerry Bomotti | TBD | ----- |  | Thomas Toepfer | 14 |  |  | FALSE | 0 |  | 2018-10-31 | CEQA | [12 empty] | PD&C | 0 | 2018 | 2021-10-01
3470 | 3470 |  | FALSE | PB&A | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | Tier III evaluations pending | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 17 |  |  | FALSE | 2586581 |  | 2018-11-06 | Complete Review | [12 empty] | PD&C | 0 | 2018 | 2021-10-01
3466 | 3466 |  | FALSE | PB&A | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | Design | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 19 |  |  | FALSE | 320000 |  | 2018-07-31 | Bidding TBD | [12 empty] | PD&C | 0 | 2018 | 2021-10-01
3458 | 3458 |  | FALSE | CAP PROG | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 16 |  |  | FALSE | 0 |  | 2018-07-16 | Coordinating with North District | [12 empty] | PD&C | 0 | 2018 | 2021-10-01
3452 | 3452 |  | FALSE | CAP PROG | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming (Study) | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 12 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Study | [12 empty] | PD&C | 0 | 2018 | 2021-10-01
3441 | 3441 |  | FALSE | CHASS | CHASS INTS 1121 Exercise Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | CHASS INT S |  | Programming | Juliet McMullin | Cindy Williams | Anna Finn |  | Daneca Stevens | 11 |  |  | FALSE | 388000 |  | 2018-06-22 | Approval & Funding | [12 empty] | PD&C | 0 | 2018 | 2021-10-01
3438 | 3438 |  | FALSE | CAP PROG | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | Completed | Jacqueline Norman | Sharyl Murdock | Scott Donnell |  | Scott Donnell | 14 |  |  | FALSE | 88500 |  | 2018-08-22 | Completed | 2020-07-01 | 2021-07-01 | [10 empty] | PD&C | 0 | 2018 | 2021-10-01
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Construction | Christopher Lynch | Todd Ambriz | Todd Ambriz |  | Vilma Kern | 1 |  |  | FALSE | 700000 |  | 2018-04-04 | Complete Construction | 2021-09-01 | 2021-10-01 | [10 empty] | PD&C | 0 | 2018 | 2021-10-01
3421 | 3421 |  | FALSE | PB&A | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 6 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [12 empty] | PD&C | 0 | 2018 | 2021-10-01
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | On Hold | Tamica Smith Jones | Joe Erbland | Johnathan Jensen |  | Fernando Nunez | 4 |  |  | FALSE | 0 |  | 2018-08-23 | Department approval to move fwd | [12 empty] | PD&C | 0 | 2018 | 2021-10-01
3395 | 3395 |  | FALSE | CAP PROG | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | On Hold | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 13 |  |  | FALSE | 0 |  | 2017-12-03 | On Hold | [12 empty] | PD&C | 0 | 2017 | 2021-10-01
3391 | 3391 |  | FALSE | CNAS | NRS Motte Rimrock Res Cost Study | Requesting recheck and recost of formal estimate for Motte Reserve Prop 84 for the Natural Reserve System. The former estimate was $763K. Purpose of study is to confirm, or augment the initial project valuation included with the Proposition 84 NRS grant application to install new structures at the Motte Rimrock Reserve site. |  |  | On-Hold | Kathryn Uhrich | Jose Wudka | Kimberly Hammond, D. McWilliams |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2017-11-02 | Approval to close or move forward | [12 empty] | PD&C | 0 | 2017 | 2021-10-01
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | In Construction | Kathryn Uhrich | Jose Wudka | Tracey Kahn |  | John Franklin | 9 |  |  | FALSE | 1575000 |  | 2018-01-08 | Complete Construction | 2021-02-01 | 2021-12-01 | [10 empty] | PD&C | 0 | 2018 | 2021-10-01
3382 | 3382 |  | FALSE | PB&A | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2022 | Gerry Bomotti | TBD | Sean Hatfield |  | John Franklin | 20 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2022 | [12 empty] | PD&C | 0 | 2017 | 2021-10-01
3319 | 3319 |  | FALSE | CAP PROG | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | Furniture & Equipment | Jacqueline Norman | Sharyl Murdock | ---- |  | Mihai Gavan | 9 |  |  | FALSE | 60430000 |  | 2017-06-01 | Close-out | 2019-11-01 | 2021-08-01 | [10 empty] | PD&C | 0 | 2017 | 2021-10-01
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On Hold/Funding | Juliet McMullin | Cindy Williams | Paul Richardson |  | Fernando Nunez | 1 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [12 empty] | PD&C | 0 | 2017 | 2021-10-01
3270 | 3270 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Chapman Hall - Replace HVAC System | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | CHAPMAN |  | In Design (Re-opened) | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Tameesha Hayes | 11 |  |  | FALSE | 595819 |  | 2017-03-07 | Bidding | [12 empty] | PD&C | 0 | 2017 | 2021-10-01
3234 | 3234 |  | FALSE | CAP PROG | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Construction | Jacqueline Norman | Sharyl Murdock | ---- |  | Fernando Nunez | 4 |  |  | FALSE | 10000000 |  | 2016-12-21 | Re-evaluating TABB Project Scope of Work | 2021-01-01 | 2021-12-31 | [10 empty] | PD&C | 0 | 2016 | 2021-10-01
3233 | 3233 |  | FALSE | CAP PROG | South Recreation Mall | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In Design | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Daneca Stevens | 99 |  |  | FALSE | 3182452.32 |  | 2016-12-16 | Bidding | [12 empty] | PD&C | 0 | 2016 | 2021-10-01
3203 | 3203 |  | FALSE | PB&A | Plaza Seismic Structural Repairs | Provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | THE PLAZA |  | In Design | Gerry Bomotti | TBD | Sean Hatfield |  | Daneca Stevens | 22 |  |  | FALSE |  |  | 2016-10-10 | Bidding | [12 empty] | PD&C | 0 | 2016 | 2021-10-01
3110 | 3110 |  | FALSE | FAC-PLNG-DESIGN-CONST | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded or approved | Susan Marshburn | Da Lan Dinh | Yvonne Lujan |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | Approve in CPMS & fund | [12 empty] | PD&C | 0 | 1900 | 2021-10-01
2900 | 2900 |  | FALSE | PB&A | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life - Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality -Replace building plumbing mains and water treatment system due to equipment end of life - Install a new Building Management System to allow more efficient energy use and monitoring - Upgrade the building fire suppression mains and fire life safety system - Upgrade the building elevator system - Upgrade building electrical feeder and main distribution in order to support modern research needs - Upgrade non compliant restrooms to meet accessability requirements - Construct a new laboratory equipment room - Perform some upgrades to common areas spaces | BATCHELOR |  | Re-bid | Gerry Bomotti | TBD | Sharyl Murdock |  | John Franklin | 15 |  |  | FALSE | 33099342.06 |  | 2015-12-15 | Award Contract | 2021-12-01 | 2024-07-01 | [10 empty] | PD&C | 0 | 2015 | 2021-10-01
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Technical Criteria Phase | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Blythe Wilson | 1 |  |  | FALSE | 3350000 |  | 2016-12-15 | Design Builder Prequalification | 2022-09-26 | 2024-06-19 | [10 empty] | PD&C | 0 | 2016 | 2021-10-01
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Bourns Fire Alarm Sys Replcmt | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | In Construction | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 5 |  |  | FALSE | 600000 |  | 2019-06-18 | Installaton of NFACP | 2021-06-01 | 2021-12-03 | [10 empty] | PD&C | 0 | 2019 | 2021-10-01
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY14) Rivera Library Arches/Arcade Repair | Paint and replace roof. | RIVERA LIB |  | Complete | Susan Marshburn | Da Lan Dinh | Monty Anderson |  | Scott Donnell | 99 |  |  | FALSE | 345000 |  | 2016-05-06 | Complete | 2021-06-01 | 2021-07-01 | [8 empty] | 2021-07-01 |  | PD&C | 0 | 2016 | 2021-10-01 | FY 21-22
2368 | 2368 |  | FALSE | FAC-PLNG-DESIGN-CONST | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | In Design | Susan Marshburn | Da Lan Dinh | ---- |  | Fernando Canon | 18 |  |  | FALSE | 2600000 |  | 2016-05-19 | Funding & Approval | [12 empty] | PD&C | 0 | 2016 | 2021-10-01
Formulas:
IRT? = ISNUMBER(SEARCH("IRT",Table1[[#This Row],[Current_Status]]))

## Data Validation (hidden)
|  | 0 |  | Data As Of (Scheduled Data Pull) | Date of Previous Report | Proj_Mgr | PM_Ph | PM_Email | Dept |  |  |  |  | CAAN | Official | Building | CNC | FS Project # | Quarter Prioritized | Quarter | Chronology
0 | 2368 | 0 | 0 | 2020-12-16 | 2020-12-01 | B. Wilson/J. Franklin | 951-827-1485 | blythe.wilson@ucr.edu | PDC | A | 1 | Project Ref No. | Proj_Ref_No | P5186 | BIOLOGICAL SCIENCES | BIOLOGIC SCI | CORE | 19P000277 | Fall 2018 | Fall 2017 | 1
0 | 2682 |  |  | 2021-01-01 | 2020-12-16 | Blair Fickett |  |  | PDC | B | 2 |  | CPMS_No | P5187 | LATH HOUSE BUILDING B | LATH B FLD16 | CORE | 19P000225 | Fall 2018 | Winter 2018 | 2
0 | 2687 |  |  | 2021-01-16 | 2021-01-01 | Blythe Wilson | 951-827-1485 | blythe.wilson@ucr.edu | PDC | C | 3 |  | Work_Order_No | P5188 | MITE WASHER BUILDING C | MITE C FLD16 | CORE | 19P000193 | Fall 2018 | Spring 2018 | 3
0 | 2725 |  |  | 2021-02-01 | 2021-01-16 | CAS |  |  | PDC | D | 4 |  | IRT | P5189 | COMMON COVERED WORKHOUSE BLDG A (PART OF WEST CAMPUS I&Q) | COM WRK FD16 | NON-CORE | 19P000309 | Fall 2018 | Summer 2018 | 4
0 | 2900 |  |  | 2021-02-16 | 2021-02-01 | Chris Pillen | 951-827-4214 | christopher.pillen@ucr.edu | FS | E | 5 | Organization | Org | P5190 | PLANT TRANSFORMATION FACILITY | PLANT TRANSF | CORE | 20P000031 | Fall 2019 | Fall 2018 | 5
0 | 3110 |  |  | 2021-03-01 | 2021-02-16 | Cliff Stokes |  |  | FORMER | F | 6 | Project Title | Project_Title | P5192 | EAST CAMPUS INSECTARY AND QUARANTINE FACILITY GREENHOUSE | EAST I&Q GH | CORE | 20P000026 | Fall 2019 | Winter 2019 | 6
0 | 3203 |  |  | 2021-03-16 | 2021-03-01 | Craig/Chris Pillen | 951-827-4214 | christopher.pillen@ucr.edu | FS | G | 7 | Project Description | Project_Description | P5194 | WINSTON CHUNG HALL | CHUNG HALL | CORE | 19P000517 | Fall 2019 | SPRING 2019 | 7
0 | 3233 |  |  | 2021-04-01 | 2021-03-16 | D. Hecht/J. Franklin | 951-827-7358 | drew.hecht@ucr.edu | PDC | H | 8 | Building | t_CPMS_Data.Building | P5195 | MATERIALS SCIENCE & ENGINEERING | MAT SCI ENGR | CORE | 20P000003 | Fall 2019 | Summer 2019 | 8
0 | 3234 |  |  | 2021-04-16 | 2021-04-01 | Dan Lerman | 951-827-6224 | daniel.lerman@ucr.edu | FS | I | 9 |  | t_Building.Building | P5196 | GENOMICS BUILDING | GENOMICS | CORE | 20P000070 | Fall 2019 | Fall 2019 | 9
0 | 3270 |  |  | 2021-05-01 | 2021-04-16 | Daryl Korluck |  |  | FORMER | J | 10 | Room | Room | P5197 | ALUMNI & VISITORS CENTER | ALUM VISITOR | NON-CORE | 20P000107 | Fall 2019 | Winter 2020 | 10
0 | 3280 |  |  | 2021-05-16 | 2021-05-01 | Dave Bomba | 951-827-1412 | dave.bomba@ucr.edu | PDC | K | 11 | Current Status | Current_Status | P5198 | UCR CHILD DEVELOPMENT CENTER NORTH | CHILD DEV N | CORE | 20P000068 | Fall 2019 | Spring 2020 | 11
0 | 3319 |  |  | 2021-06-01 | 2021-05-16 | Drew Hecht | 951-827-7358 | drew.hecht@ucr.edu | PDC | L | 12 |  | Org_Name | P5199 | HIGHLANDER UNION 2 ACTIVITY CENTER | HUB 2 | NON-CORE | 20P000044 | Fall 2019 | Summer 2020 | 12
0 | 3382 |  |  | 2021-06-16 | 2021-06-01 | Enrico Baez | 951-827-4214 | enrico.baez@ucr.edu | FS | M | 13 | Organization Leader | Org_Leadership | P5200 | GREENHOUSE #9 | GH09 | CORE | 19P000664 | Fall 2019 | Fall 2020 | 13
0 | 3390 |  |  | 2021-07-01 | 2021-06-16 | Enrico Baez - Managing Contractor | 951-827-4214 | enrico.baez@ucr.edu | FS | N | 14 | Prioritization Designate | Org_Contact | P5205 | UNIVERSITY OFFICE BUILDING | UNIV OFC BLD | CORE | 20P000061 | Fall 2019 | Winter 2021 | 14
0 | 3391 |  |  | 2021-07-16 | 2021-07-01 | Fernando Nunez | 951-827-2466 | fernando.nunez@ucr.edu | PDC | O | 15 | Contact | Contact | P5210 | GREENHOUSE #15 | GH15 | CORE | 20P000075 | Fall 2019 | Spring 2021 | 15
0 | 3395 |  |  | 2021-08-01 | 2021-07-16 | George MacMullin |  |  | FORMER | P | 16 |  | Contact_2 | P5215 | HOMER D. CHAPMAN HALL | CHAPMAN | CORE | 19P000467 | Fall 2019 | Summer 2021 | 16
0 | 3407 |  |  | 2021-08-16 | 2021-08-01 | Jacqueline Norman | 951-827-6316 | jacqueline.norman@ucr.edu | PDC | Q | 17 | Project Manager | Proj_Mgr | P5216 | CHICKEN COOP #1 | CHICK COOP 1 | NON-CORE | 20P000083 | Fall 2019 | Fall 2021 | 17
0 | 3421 |  |  | 2021-09-01 | 2021-08-16 | Jason Williams |  | jason.williams@ucr.edu | FS | R | 18 | PD&C Org Priority No. | Org_Priority | P5217 | PHYSICAL PLANT STORAGE UNIT | PHYS PL STOR | CORE | 20P000008 | Fall 2019 | FY 21-22 | 18
0 | 3428 |  |  | 2021-09-16 | 2021-09-01 | Jerrod Walters | 951-827-6955 | jerrod.walters@ucr.edu | PDC | S | 19 | FS Org Priority No. | FS_Priority | P5218 | THE COTTAGE | COTTAGE | NON-CORE | 19P000683 | Fall 2019
0 | 3438 |  |  | 2021-10-01 | 2021-09-16 | Jess Hernandez | 951-827-4214 | jesus.hernandez@ucr.edu | FS | T | 20 | For Faculty Hire | For_Faculty_Hire | P5219 | WORKMAN'S COTTAGE #2 | WORKMN COT 2 | NON-CORE | 19P000673 | Fall 2019
0 | 3441 |  |  | 2021-10-16 | 2021-10-01 | John Franklin | 951-827-6953 | john.franklin@ucr.edu | PDC | U | 21 | PD&C Approved Budget | Approved_Budget | P5220 | WORKMAN'S COTTAGE #3 | WORKMN COT 3 | NON-CORE | 19P000660 | Fall 2019
0 | 3452 |  |  | 2021-11-01 | 2021-10-16 | John Peraino | 951-827-2121 | john.peraino@ucr.edu | FS | V | 22 | FS Recharge Actuals To Date | FS_Recharge_Costs | P5224 | UNIVERSITY BOOKSTORE | BOOKSTORE | NON-CORE | 20P000059 | Fall 2019
0 | 3458 |  |  | 2021-11-16 | 2021-11-01 | Marianne Valenti |  |  | FORMER | W | 23 | Request Date | Project_Initiated | P5230 | STORAGE SHED #8 | STOR 8 | CORE | 20P000077 | Fall 2019
0 | 3466 |  |  | 2021-12-01 | 2021-11-16 | Mihai Gavan | 951-827-6959 | mihai.gavan@ucr.edu | PDC | X | 24 | Next Steps | Next_Major_Milestone | P5231 | COLLEGE BUILDING SOUTH | COLL BLDG SO | CORE | 20P000045 | Fall 2019
0 | 3470 |  |  | 2021-12-16 | 2021-12-01 | Mihai Gavan-MRB1 |  | mihai.gavan@ucr.edu | PDC | Y | 25 | Start Date | Const_Start | P5241 | ENVIRONMENTAL HEALTH AND SAFETY BUILDING | ENV H AND S | CORE | 19P000602 | Fall 2019
0 | 3474 |  |  |  |  | N/A | 951-827-4214 |  |  | Z | 26 | Complete Date | Construction_Completion | P5242 | LATHHOUSE #1 | LATH 1 | CORE | 20P000028 | Fall 2019
0 | 3492 |  |  |  |  | Not Assigned | 951-827-4214 |  |  | AA | 27 | Impact Description | Impact_Description | P5251 | THEATRE WORKSHOP | THTR WKSH | CORE | 20P000002 | Fall 2019
0 | 3499 |  |  |  |  | Paul Ditty | 951-827-4214 | paul.ditty@ucr.edu | FS | AB | 28 | Impact Date Start | Impact_Date_Start | P5253 | MAIL BUILDING | MAIL | CORE | 20P000004 | Fall 2019
0 | 3507 |  |  |  |  | R. Amescua/D. Hecht |  | raoul.amescua@ucr.edu | PDC | AC | 29 | Impact Date End | Impact_Date_End | P5254 | BOTANIC GARDENS INFORMATION CENTER | BOTAN INFO C | NON-CORE | 20P000081 | Fall 2019
0 | 3508 |  |  |  |  | R. Amescua/J. Kaplan |  | raoul.amescua@ucr.edu | PDC | AD | 30 | Project Service Unit | PM_Notes | P5255 | BOTANY & PLANT SCIENCES FIELDHOUSE FIELD 15A | BOT FLDHS15A | NON-CORE | 20P000034 | Fall 2019
0 | 3510 |  |  |  |  | Raoul Amescua | 951-827-6951 | raoul.amescua@ucr.edu | PDC | AE | 31 |  | PM_Date | P5256 | ENTOMOLOGY MUSEUM | ENTOM MUSEUM | CORE | 20P000054 | Fall 2019
0 | 3512 |  |  |  |  | Robert Corey |  |  | FORMER | AF | 32 |  | Scope_Date | P5258 | GLASSHOUSE FIELD 16 #45 | GH 16 45 | CORE | 19P000661 | Fall 2019
0 | 3516 |  |  |  |  | Ron Veloz | 951-827-4214 | ron.veloz@ucr.edu | FS | AG | 33 |  | Scope_Reviewer | P5259 | GREENHOUSE #2A | GH02A | CORE | 20P000047 | Fall 2019
0 | 3529 |  |  |  |  | Rowan Reid | 951-827-5825 | rowan.reid@ucr.edu | PDC | AH | 34 |  | Scope_Notes | P5260 | GLASSHOUSE FIELD 16 #46 | GH 16 46 | CORE | 19P000624 | Fall 2019
0 | 3541 |  |  |  |  | Scott Donnell | 951-827-4706 | scott.donnell@ucr.edu | PDC | AI | 35 |  | Scope_Complete | P5261 | MARLAN & ROSEMARY BOURNS HALL | BOURNS | CORE | 20P000029 | Fall 2019
0 | 3548 |  |  |  |  | Tameesha Hayes |  |  | FORMER | AJ | 36 |  | Owner | P5263 | UNIVERSITY LABORATORY BUILDING | UNIV LAB BLD | CORE | 20P000005 | Fall 2019
0 | 3549 |  |  |  |  | Uma R. | 951-827-5610 | uma.ramasubramanian@ucr.edu | PDC | AK | 37 |  | IRT? | P5265 | TRAILER #10A | T10A | CORE | 20P000036 | Fall 2019
0 | 3550 |  |  |  |  | xxxxx |  |  |  | AL | 38 |  | Requested Year | P5266 | TRAILER #9A | T9A | CORE | 20P000024 | Fall 2019
0 | 3559 |  |  |  |  | Yvonne Lujan | 951-827-5154 | yvonne.lujan@ucr.edu | PDC | AM | 39 |  | Data Pulled On | P5267 | GLASSHOUSE FIELD 16 #26 | GH 16 26 | CORE | 19P000662 | Fall 2019
0 | 3564 | [12 empty] | P5268 | STORAGE SHED #5 | STOR 5 | CORE | 20P000060 | Fall 2019
0 | 3574 | [12 empty] | P5269 | GLASSHOUSE FIELD 16 #27 | GH 16 27 | CORE | 20P000039 | Fall 2019
0 | 3583 | [12 empty] | P5270 | GARAGE COTTAGE #3 | GAR C3 | CORE | 20P000090 | Fall 2019
0 | 3593 | [12 empty] | P5271 | BARN STABLE | BARN STABLE | NON-CORE | 19P000688 | Fall 2019
0 | 3596 | [12 empty] | P5272 | PARKING SERVICES BUILDING | PARKING SERV | NON-CORE | 20P000017 | Fall 2019
0 | 3599 | [12 empty] | P5273 | GLASSHOUSE FIELD 16 #22 | GH 16 22 | CORE | 19P000658 | Fall 2019
0 | 3602 | [12 empty] | P5274 | GARAGE COTTAGE #1 | GAR C1 | CORE | 19P000666 | Fall 2019
0 | 3607 | [12 empty] | P5275 | GREENHOUSE #6 | GH06 | CORE | 20P000065 | Fall 2019
0 | 3608 | [12 empty] | P5276 | GREENHOUSE #7 | GH07 | CORE | 19P000676 | Fall 2019
0 | 3610 | [12 empty] | P5277 | GREENHOUSE #8 | GH08 | CORE | 20P000019 | Fall 2019
0 | 3612 | [12 empty] | P5278 | GREENHOUSE #10 | GH10 | CORE | 19P000523 | Fall 2019
0 | 3613 | [12 empty] | P5279 | GREENHOUSE #11 | GH11 | CORE | 19P000659 | Fall 2019
0 | 3614 | [12 empty] | P5280 | GREENHOUSE #12 | GH12 | CORE | 20P000051 | Fall 2019
0 | 3615 | [12 empty] | P5281 | GREENHOUSE #13 | GH13 | CORE | 19P000657 | Fall 2019
0 | 3616 | [12 empty] | P5282 | GREENHOUSE #21 | GH21 | CORE | 19P000674 | Fall 2019
0 | 3618 | [12 empty] | P5284 | GREENHOUSE #16 | GH16 | CORE | 20P000023 | Fall 2019
0 | 3623 | [12 empty] | P5285 | RESTROOMS & TICKET BOOTH BUILDING | TICKET BOOTH | CORE | 20P000082 | Fall 2019
0 | 3624 | [12 empty] | P5286 | RESTROOM / MAINTENANCE | RSTRM/MAINT | CORE | 20P000094 | Fall 2019
0 | 3626 | [12 empty] | P5287 | STORAGE BUILDING PLANT PATHOLOGY FIELD 16E | STOR PL PATH | CORE | 20P000069 | Fall 2019
0 | 3627 | [12 empty] | P5288 | NEMATOLOGY MICROPLOT STORAGE BUILDING FIELD 15A | NEM MICRO ST | CORE | 19P000302 | Fall 2019
0 | 3630 | [12 empty] | P5289 | EAST CAMPUS INSECTARY AND QUARANTINE FACILITY | EAST I&Q FAC | CORE | 20P000057 | Fall 2019
0 | 3631 | [12 empty] | P5290 | HAY BARN | HAY BN | CORE | 20P000049 | Fall 2019
0 | 3632 | [12 empty] | P5291 | TURF PLOT STORAGE AGRICULTURAL OPERATIONS | TURF PL STOR | CORE | 20P000050 | Fall 2019
0 | 3634 | [12 empty] | P5292 | STORAGE BUILDING AT LOADING DOCK OF PIERCE HALL | STOR PRCE | CORE | 20P000053 | Fall 2019
0 | 3636 | [12 empty] | P5293 | GLASSHOUSE FIELD 16 #25 | GH 16 25 | CORE | 20P000092 | Fall 2019
0 | 3640 | [12 empty] | P5295 | CENTRAL UTILITY PLANT | CNTRL UTL PL | CORE | 19P000607 | Fall 2019
0 | 3642 | [12 empty] | P5296 | GLASSHOUSE FIELD 16 #9 | GH 16 09 | CORE | 20P000100 | Fall 2019
0 | 3644 | [12 empty] | P5297 | GLASSHOUSE FIELD 16 #23 | GH 16 23 | CORE | 20P000101 | Fall 2019
0 | 3645 | [12 empty] | P5298 | SHED BUILDING FIELD 16 #25 | SHED 16 25 | CORE | 20P000102 | Fall 2019
0 | 3648 | [12 empty] | P5299 | GLASSHOUSE FIELD 16 #10 | GH 16 10 | CORE | 20P000103 | Fall 2019
0 | 3650 | [12 empty] | P5300 | GLASSHOUSE FIELD 16 #11 | GH 16 11 | CORE | 20P000052 | Fall 2019
0 | 3652 | [12 empty] | P5302 | EQUIPMENT SHED | EQUIP SHED | CORE | 19P000626 | Fall 2019
0 | 3655 | [12 empty] | P5304 | INSECTICIDE COMPOUNDING & STORAGE BUILDING | INSECT COMP | CORE | 18P000465 | Fall 2019
0 | 3656 | [12 empty] | P5305 | STORED PRODUCTS INSECTICIDE BUILDING | SPI | CORE | 20P000085 | Fall 2019
0 | 3658 | [12 empty] | P5307 | HUMANITIES & SOCIAL SCIENCES | HUM & SOC SC | CORE | 19P000623 | Fall 2019
0 | 9058 | [12 empty] | P5308 | SOUTH LOCKERROOM & CONCESSION STAND | S LCKRM/CONC | CORE | 20P000055 | Fall 2019
0 | 9059 | [12 empty] | P5310 | WEST LOCKERROOM & CLUBHOUSE CONCESSION STAND | W LCKRM/CONC | CORE | 19P000627 | Fall 2019
0 | 9060 | [12 empty] | P5311 | JEANETTE AND RUPERT COSTO HALL | COSTO HALL | NON-CORE | 20P000073 | Fall 2019
0 | 9061 | [12 empty] | P5312 | LATHHOUSE #32 | LATH 32 | CORE | 20P000067 | Fall 2019
0 | 9063 | [12 empty] | P5315 | LATHHOUSE #36 | LATH 36 | CORE | 20P000093 | Fall 2019
0 | 9064 | [12 empty] | P5316 | LIFE SCIENCES | LIFE SCIENCE | CORE | 19P000568 | Fall 2019
0 | 9065 | [12 empty] | P5319 | HERBARIUM | HERBARIUM | CORE | 20P000038 | Fall 2019
0 | 9066 | [12 empty] | P5321 | STORAGE SHED #37 | STOR 37 | CORE | 20P000114 | Fall 2019
0 | 9067 | [12 empty] | P5322 | TOMAS RIVERA LIBRARY | RIVERA LIB | CORE | 20P000037 | Fall 2019
0 | 9068 | [12 empty] | P5323 | HERMAN T. SPIETH HALL | SPIETH | CORE | 19P000427 | Fall 2019
0 | 18P000214 | [12 empty] | P5324 | STORAGE SHED #49 | STOR 49 | CORE | 20P000046 | Fall 2019
0 | 18P000453 | [12 empty] | P5325 | A. GARY ANDERSON HALL 1 | ANDERSON 1 | CORE | 20P000115 | Fall 2019
0 | 19P000193 | [12 empty] | P5326 | COBALT 60 BUILDING #38 | COBALT 60 | CORE | 19P000502 | Fall 2019
0 | 19P000225 | [12 empty] | P5327 | PHYSICAL PLANT STORAGE UNIT 2 | PHYS PL STR2 | CORE | 20P000086 | Fall 2019
0 | 19P000407 | [12 empty] | P5328 | HAZARDOUS WASTE STORAGE UNIT 1 | HAZ WST STR1 | CORE | 20P000116 | Fall 2019
0 | 19P000414 | [12 empty] | P5329 | HAZARDOUS WASTE STORAGE UNIT 2 | HAZ WST STR2 | CORE | 20P000117 | Fall 2019
0 | 19P000427 | [12 empty] | P5330 | TRAILER #21 3984 | T21 3984 | CORE | 20P000118 | Fall 2019
0 | 19P000433 | [12 empty] | P5334 | ATHLETICS AND DANCE BUILDING | ATH DANCE | CORE | 19P000670 | Fall 2019
0 | 19P000466 | [12 empty] | P5335 | GEOLOGY BUILDING | GEOLOGY | CORE | 19P000687 | Fall 2019
0 | 19P000474 | [12 empty] | P5336 | GLASSHOUSE FIELD 16 #24A | GH 16 24A | CORE | 20P000067 | Fall 2019
0 | 19P000485 | [12 empty] | P5337 | GLASSHOUSE FIELD 16 #24B | GH 16 24B | CORE | 19P000413 | Fall 2019
0 | 19P000502 | [12 empty] | P5338 | GLASSHOUSE FIELD 16 #24C | GH 16 24C | CORE | 18P000343 | Spring 2018
0 | 19P000504 | [12 empty] | P5339 | GLASSHOUSE FIELD 16 #24D | GH 16 24D | CORE | 18P000453 | Summer 2018
0 | 19P000514 | [12 empty] | P5340 | PUMPHOUSE #2 | PUMP 2 | CORE | 19P000646 | Summer 2019
0 | 19P000517 | [12 empty] | P5341 | ALFRED M. BOYCE HALL | BOYCE | CORE | 19P000638 | Summer 2019
0 | 19P000539 | [12 empty] | P5342 | HERBERT JOHN WEBBER HALL | WEBBER | CORE | 19P000619 | Summer 2019
0 | 19P000547 | [12 empty] | P5343 | ABERDEEN-INVERNESS RESIDENCE HALL | ABER INVER | NON-CORE | 19P000337 | Summer 2019
0 | 19P000600 | [12 empty] | P5344 | GLASSHOUSE FIELD 16 #28 | GH 16 28 | CORE | 19P000575 | Summer 2019
0 | 19P000624 | [12 empty] | P5345 | ASBESTOS ABATEMENT & EMERGENCY RESPONSE EQUIP/SUPPLY | ABAT EMG RSP | NON-CORE | 19P000639 | Summer 2019
0 | 19P000659 | [12 empty] | P5346 | DECAY STORAGE UNIT 1 | DECAY STOR 1 | CORE | 19P000466 | Summer 2019
0 | 19P000660 | [12 empty] | P5347 | DECAY STORAGE UNIT 2 | DECAY STOR 2 | CORE | 19P000572 | Summer 2019
0 | 19P000687 | [12 empty] | P5348 | WAREHOUSE #2 | WHSE 2 | CORE | 19P000628 | Summer 2019
0 | 20P000003 | [12 empty] | P5349 | FARM GROUP E WAREHOUSE #1 | FARM E | CORE | 19P000414 | Summer 2019
0 | 20P000026 | [12 empty] | P5350 | GROWTH CHAMBER BUILDING | GRTH CH BLDG | CORE | 19P000473 | Summer 2019
0 | 20P000039 | [12 empty] | P5351 | ENTOMOLOGY POULTRY BUILDING | ENT PLTRY BD | CORE | 19P000521 | Summer 2019
0 | 20P000046 | [12 empty] | P5353 | INSECT LABORATORY #39 | INSECT 39 | CORE | 19P000553 | Summer 2019
0 | 20P000047 | [12 empty] | P5354 | GORDON S. WATKINS HALL | WATKINS | CORE | 19P000455 | Summer 2019
0 | 20P000054 | [12 empty] | P5355 | SCREENHOUSE BOTANY | SCRNHSE BOT | CORE | 19P000564 | Summer 2019
0 | 20P000067 | [12 empty] | P5356 | STORAGE SHED #6 | STOR 6 | CORE | 19P000621 | Summer 2019
0 | 20P000135 | [12 empty] | P5357 | A. GARY ANDERSON HALL 2 | ANDERSON 2 | CORE | 19P000571 | Summer 2019
0 | 20P000144 | [12 empty] | P5358 | THE BARN | BARN | NON-CORE | 19P000477 | Summer 2019
0 | 20P000174 | [12 empty] | P5359 | SUPERINTENDENT'S GARAGE | SUPERINT GAR | NON-CORE | 19P000643 | Summer 2019
0 | 20P000183 | [12 empty] | P5360 | SUPERINTENDENT'S COTTAGE | SUPERINT COT | NON-CORE | 19P000487 | Summer 2019
0 | 20P000188 | [12 empty] | P5361 | INSECT LABORATORY #44 | INSECT 44 | CORE | 19P000600 | Summer 2019
0 | 20P000196 | [12 empty] | P5363 | PLANT DRYING BUILDING | PLNT DRY BLD | CORE | 19P000419 | Summer 2019
0 | 20P000197 | [12 empty] | P5364 | CORPORATION YARD PHYSICAL PLANT WAREHOUSE | CORP PP WHSE | CORE | 19P000622 | Summer 2019
0 | 20P000202 | [12 empty] | P5365 | PENTLAND HILLS RESIDENCE HALL A | PENTLAND A | NON-CORE | 19P000665 | Summer 2019
0 | 20P000208 | [12 empty] | P5367 | SATELLITE CHILLER PLANT | SAT CHIL PL | CORE | 19P000434 | Summer 2019
0 | 20P000210 | [12 empty] | P5369 | PENTLAND HILLS RESIDENCE HALL | PENTLAND I | NON-CORE | 19P000495 | Summer 2019
0 | 20P000211 | [12 empty] | P5371 | GLASSHOUSE FIELD 16 #47 | GH 16 47 | CORE | 19P000534 | Summer 2019
0 | 20P000212 | [12 empty] | P5372 | CHASS INTERDISCIPLINARY SOUTH | CHASS INT S | CORE | 19P000597 | Summer 2019
0 | 20P000213 | [12 empty] | P5373 | PSYCHOLOGY BUILDING | PSYCHOLOGY1 | CORE | 19P000601 | Summer 2019
0 | 20P000214 | [12 empty] | P5374 | GREENHOUSE #1 RESEARCH | GH01 RESRCH | CORE | 19P000415 | Summer 2019
0 | 20P000215 | [12 empty] | P5375 | GLASSHOUSE FIELD 16 #48 | GH 16 48 | CORE | 19P000574 | Summer 2019
0 | 20P000218 | [12 empty] | P5376 | TRAILER CNAS (Surge Trailer) | T CNAS | CORE | 19P000539 | Summer 2019
0 | 20P000221 | [12 empty] | P5377 | SHED BUILDING TRACTOR | SHED TRACTOR | CORE | 19P000613 | Summer 2019
0 | 20P000230 | [12 empty] | P5378 | GREENHOUSE #2 RESEARCH | GH03 RESRCH | CORE | 19P000483 | Summer 2019
0 | 20P000231 | [12 empty] | P5380 | Skye Hall (Surge Hall) | SKYE HALL | CORE | 19P000625 | Summer 2019
0 | 20P000244 | [12 empty] | P5381 | COMPUTING & COMMUNICATIONS CENTER | ITS CENTER | CORE | 19P000609 | Summer 2019
0 | 20P000247 | [12 empty] | P5382 | COMPUTING & COMMUNICATIONS ELECTRIC CART CARPORT | ITS CARPORT | CORE | 19P000508 | Summer 2019
0 | 20P000248 | [12 empty] | P5383 | UNIVERSITY LECTURE HALL | UNIV LEC HAL | CORE | 19P000558 | Summer 2019
0 | 20P000253 | [12 empty] | P5385 | TRAILER BIOMEDICAL SCIENCES #1 | T BIOMED1 | CORE | 19P000421 | Summer 2019
0 | 20P000272 | [12 empty] | P5386 | EH&S TRIPLE WIDE TRAILER | T EH&S | CORE | 19P000615 | Summer 2019
0 | 20P000275 | [12 empty] | P5387 | VIVARIA TRAILER | T VIVARIA | CORE | 19P000526 | Summer 2019
0 | 20P000282 | [12 empty] | P5388 | ENVIRONMENTAL HEALTH AND SAFETY EXPANSION | ENV HLTHSFTY | CORE | 19P000642 | Summer 2019
0 | 20P000309 | [12 empty] | P5391 | BOTANIC GARDENS RESTROOM | BOTGDN RSTRM | NON-CORE | 19P000552 | Summer 2019
0 | 20P000310 | [12 empty] | P5393 | METEOROLOGICAL BUILDING | METEOR BLDG | CORE | 19P000589 | Summer 2019
0 | 20P000317 | [12 empty] | P5396 | UCR CHILD DEVELOPMENT SOUTH | CHILD DEV S | NON-CORE | 19P000448 | Summer 2019
0 | 20P000320 | [12 empty] | P5397 | SCHOOL OF EDUCATION CLINIC | EDUC CLINIC | CORE | 19P000620 | Summer 2019
0 | 20P000321 | [12 empty] | P5398 | PARKING TRAILER 1 | PARKING T1 | NON-CORE | 19P000429 | Summer 2019
0 | 20P000333 | [12 empty] | P5399 | PARKING TRAILER 2 | PARKING T2 | NON-CORE | 19P000540 | Summer 2019
0 | 20P000336 | [12 empty] | P5400 | PARKING TRAILER 3 | PARKING T3 | NON-CORE | 19P000608 | Summer 2019
0 | 20P000354 | [12 empty] | P5402 | Arabadopsis 1 | ARAB 1 | NON-CORE | 19P000560 | Summer 2019
0 | 20P000363 | [12 empty] | P5403 | CHASS INTERDISCIPLINARY NORTH | CHASS INT N | CORE | 19P000433 | Summer 2019
0 | 20P000366 | [12 empty] | P5404 | HIGHLANDER UNION BUILIDNG | HUB | NON-CORE | 19P000599 | Summer 2019
0 | 20P000367 | [12 empty] | P5405 | HIGHLANDER UNION COFFEE PAVILION | HUB COFFEE | NON-CORE | 19P000311 | Summer 2019
0 | 20P000368 | [12 empty] | P5406 | SCHOOL OF MEDICINE HEALTH SCIENCE RESEARCH BUILDING | SOM RSCH | CORE | 19P000377 | Summer 2019
0 | 20P000370 | [12 empty] | P5408 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16A | GH 16-54 ENT | CORE | 19P000645 | Summer 2019
0 | 20P000372 | [12 empty] | P5409 | STORAGE SHED #1 | STOR 1 | CORE | 19P000547 | Summer 2019
0 | 20P000374 | [12 empty] | P5410 | STORAGE SHED #2 | STOR 3 | CORE | 19P000555 | Summer 2019
0 | 20P000384 | [12 empty] | P5411 | ARTS BUILDING FINE ARTS SEISMIC FACILITY | ARTS | CORE | 19P000474 | Summer 2019
0 | 20P000387 | [12 empty] | P5412 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16B | GH 16-55 ENT | CORE | 19P000504 | Summer 2019
0 | 20P000397 | [12 empty] | P5413 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16C | GH 16-56 ENT | CORE | 19P000514 | Summer 2019
0 | 20P000401 | [12 empty] | P5414 | CHEMICAL SCIENCES | CHEMICAL SCI | CORE | 19P000543 | Summer 2019
0 | 20P000403 | [12 empty] | P5415 | CANYON CREST KIOSK | KIOSK 2 | NON-CORE | 19P000594 | Summer 2019
0 | 20P000413 | [12 empty] | P5416 | SCIENCE LABORATORIES 1 | SCIENCE LAB1 | CORE | 19P000407 | Summer 2019
0 | 20P000419 | [12 empty] | P5417 | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | ENTOMOLOGY | CORE | 18P000214 | Winter 2018
0 | 20P000445 | [12 empty] | P5418 | RAYMOND L. ORBACH SCIENCE LIBRARY | ORBACH LIB | CORE | 18P000198 | Winter 2018
0 | 20P000446 | [12 empty] | P5419 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16D | GH 16-57 ENT | CORE
0 | 20P000448 | [12 empty] | P5420 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16E | GH 16-58 ENT | CORE
0 | 20P000449 | [12 empty] | P5421 | BOTANIC GARDENS HOUSE | BOT GDN HSE | NON-CORE
0 | 20P000450 | [12 empty] | P5422 | GLASSHOUSE FIELD 8 AIR POLLUTION | GH5 | CORE
0 | 20P000453 | [12 empty] | P5423 | GLASSHOUSE FIELD 7 AIR POLLUTION | GH4 | CORE
0 | 20P000462 | [12 empty] | P5424 | LATHHOUSE #8 | LATH 8 | CORE
0 | 20P000463 | [12 empty] | P5425 | LATHHOUSE #3 | LATH 3 | CORE
0 | 20P000464 | [12 empty] | P5426 | HEADHOUSE STORAGE BUILDING | HH STOR | CORE
0 | 20P000467 | [12 empty] | P5427 | SOIL FACILITY BUILDING | SOIL BLDG | CORE
0 | 20P000468 | [12 empty] | P5428 | STORAGE BUILDING RADIOACTIVE MATERIAL | STOR RA | CORE
0 | 20P000469 | [12 empty] | P5430 | AGRICULTURE EXPERIMENT STATION STORAGE BUILDING | AES STOR | CORE
0 | 20P000470 | [12 empty] | P5434 | GLASSHOUSE FIELD 16 #50 | GH 16 50 | CORE
0 | 21P000001 | [12 empty] | P5435 | EHS STORAGE 1 | EHS STOR 1 | CORE
0 | 21P000003 | [12 empty] | P5436 | EHS STORAGE 2 | EHS STOR 2 | CORE
0 | 21P000009 | [12 empty] | P5437 | EHS STORAGE 3 | EHS STOR 3 | CORE
0 | 21P000011 | [12 empty] | P5438 | EHS STORAGE 4 | EHS STOR 4 | CORE
0 | 21P000014 | [12 empty] | P5439 | EHS STORAGE 5 | EHS STOR 5 | CORE
0 | 21P000019 | [12 empty] | P5440 | 4558 SANDANO STREET | 4558 SANDANO | NON-CORE
0 | 21P000037 | [12 empty] | P5441 | 4566 SANDANO STREET | 4566 SANDANO | NON-CORE
0 | 21P000049 | [12 empty] | P5442 | 1871 ESCALANTE WAY | 1871 ESCALAN | NON-CORE
0 | 21P000058 | [12 empty] | P5443 | 4531 SANDANO STREET | 4531 SANDANO | NON-CORE
0 | 21P000078 | [12 empty] | P5444 | 4522 SANDANO STREET | 4522 SANDANO | NON-CORE
0 | 21P000079 | [12 empty] | P5445 | 4538 SANDANO STREET | 4538 SANDANO | NON-CORE
0 | 21P000083 | [12 empty] | P5446 | POLICE TRAILER | POLICE TRLR | CORE
0 | 21P000088 | [12 empty] | P5449 | GENOMICS SHED | GENOM SHED | CORE
0 | 21P000102 | [12 empty] | P5451 | EDGEMOOR HOUSE | EDGEMOOR HSE | NON-CORE
0 | 21P000109 | [12 empty] | P5452 | EDGEMOOR GARAGE | EDGEMOOR GAR | NON-CORE
0 | 21P000110 | [12 empty] | P5453 | GARAGE COTTAGE #2 | GAR C2 | CORE
0 | 21P000111 | [12 empty] | P5455 | TRAILER CECERT 1 | T CECERT 1 | NON-CORE
0 | 21P000134 | [12 empty] | P5457 | PRINTING MODULAR | PRINT MOD | NON-CORE
0 | 21P000137 | [12 empty] | P5460 | WOODSHED | WOODSHED | CORE
0 | 21P000144 | [12 empty] | P5461 | FIELD LABORATORY | FLDLAB | CORE
0 | 21P000146 | [12 empty] | P5462 | TRAILER CECERT 2 | T CECERT 2 | NON-CORE
0 | 21P000151 | [12 empty] | P5464 | STORAGE SHED #2 | STOR 2 | CORE
0 | 21P000154 | [12 empty] | P5466 | BIO CONTROL CULTURE BUILDING REPLACEMENT | BIO CTRL BLD | CORE
0 | 21P000155 | [12 empty] | P5467 | RICHARD J HECKMANN INTL CENTER FOR ENTREPRENEURIAL MGMT | HECKMAN ICEM | NON-CORE
0 | 21P000157 | [12 empty] | P5468 | HECKMANN CENTER COMPLEX PH 2 | HECKMANN PH2 | NON-CORE
0 | 21P000158 | [12 empty] | P5469 | VERLEY BARN | VERLEY BARN | CORE
0 | 21P000160 | [12 empty] | P5470 | GLEN MOR HOUSING A | GLEN MOR A | NON-CORE
0 | 21P000162 | [12 empty] | P5471 | GLEN MOR HOUSING B | GLEN MOR B | NON-CORE
0 | 21P000173 | [12 empty] | P5472 | GLEN MOR HOUSING C1 | GLEN MOR C1 | NON-CORE
0 | 21P000174 | [12 empty] | P5473 | GLEN MOR HOUSING D | GLEN MOR D | NON-CORE
0 | 21P000183 | [12 empty] | P5474 | GLEN MOR HOUSING E | GLEN MOR E | NON-CORE
0 | 21P000189 | [12 empty] | P5475 | GLEN MOR HOUSING C2 | GLEN MOR C2 | NON-CORE
0 | 21P000190 | [12 empty] | P5476 | TRAILER ANTHROPOLOGY | T ANTHROP | CORE
0 | 21P000191 | [12 empty] | P5478 | GLASSHOUSE FIELD 3 AIR POLLUTION | GH AP FL2 | CORE
0 | 21P000198 | [12 empty] | P5479 | GLASSHOUSE FIELD 3 AIR POLLUTION | GH AP FL3 | CORE
0 | 21P000204 | [12 empty] | P5480 | IVAN HINDERAKER HALL | HINDERAKER | CORE
0 | 21P000207 | [12 empty] | P5481 | GREENHOUSE #14 | GH14 | CORE
0 | 21P000211 | [12 empty] | P5482 | PATRICK BOYDEN LABORATORY | BOYDEN LAB | CORE
0 | 21P000212 | [12 empty] | P5483 | GREENHOUSE #17 | GH17 | CORE
0 | 21P000213 | [12 empty] | P5484 | CORPORATION YARD D CAR SHELTER | CORP CAR SHD | CORE
0 | 21P000214 | [12 empty] | P5485 | CORPORATION YARD C | CORP C | CORE
0 | 21P000215 | [12 empty] | P5486 | CORPORATION YARD B | CORP B | CORE
0 | 22P000006 | [12 empty] | P5487 | CORPORATION YARD A | CORP A | CORE
0 | 22P000008 | [12 empty] | P5488 | CHANCELLOR'S RESIDENCE | CHANC HOUSE | NON-CORE
0 | 22P000022 | [12 empty] | P5489 | FARM A | FARM A | CORE
0 | 22P000027 | [12 empty] | P5490 | FARM B | FARM B | CORE
0 | 22P000065 | [12 empty] | P5491 | GARAGE 4 CAR | GARAGE 4 CAR | NON-CORE
0 | 2970d | [12 empty] | P5492 | SHED BUILDING FIELD 11A | SHED FLD 11A | CORE
0 | 3035a | [12 empty] | P5493 | TRAILER #14 | T14 | CORE
0 | 3228b | [12 empty] | P5495 | HEALTH SERVICE BUILDING | HEALTH SERV | CORE
0 | 3515b | [12 empty] | P5496 | PHYSICAL EDUCATION UTILITY BUILDING | PE UTIL BLDG | CORE
0 | 3515d | [12 empty] | P5497 | JOHN W. OLMSTED HALL | OLMSTED | CORE
0 | 3590a | [12 empty] | P5498 | HUMANITIES BUILDING | HUMANITIES | CORE
0 | 3590b | [12 empty] | P5499 | GLASSHOUSE FIELD 16 #21 | GH 16 21 | CORE
0 | [13 empty] | P5500 | VEGETABLE CROPS STOREHOUSE | VEG CROP STR | CORE
0 | [13 empty] | P5501 | LEON DEXTER BATCHELOR HALL | BATCHELOR | CORE
0 | [13 empty] | P5502 | LOTHIAN RESIDENCE HALL | LOTHIAN HALL | NON-CORE
0 | [13 empty] | P5503 | HOWARD SAMUEL FAWCETT LABORATORY | FAWCETT LAB | CORE
0 | [13 empty] | P5504 | PHYSICS BUILDING | PHYSICS | CORE
0 | [13 empty] | P5505 | GEODESIC DOME BOTANIC GARDENS | GEODESIC DM | CORE
0 | [13 empty] | P5506 | COLD BOXES ROOF BUILDING | COLD BX ROOF | CORE
0 | [13 empty] | P5507 | CUSTODIAL & GROUNDS BUILDING | CUST AND GRD | CORE
0 | [13 empty] | P5508 | W. CONWAY PIERCE HALL | PIERCE | CORE
0 | [13 empty] | P5509 | TRAILER #7 AIR POLLUTION | T7 AP | CORE
0 | [13 empty] | P5511 | STUDENT RECREATION CENTER NORTH | SRC NORTH | NON-CORE
0 | [13 empty] | P5513 | GREENHOUSE #18 | GH18 | CORE
0 | [13 empty] | P5514 | GREENHOUSE #19 | GH19 | CORE
0 | [13 empty] | P5515 | GREENHOUSE #20 | GH20 | CORE
0 | [13 empty] | P5516 | GLASSHOUSE FIELD 15A #40 | GH 15A-40 | CORE
0 | [13 empty] | P5517 | COLLEGE BUILDING NORTH | COLL BLDG NO | CORE
0 | [13 empty] | P5518 | AGRICULTURE ENGINEERING SHOP | AG ENG SHOPS | CORE
0 | [13 empty] | P5519 | GLASSHOUSE FIELD 15A #41 | GH 15A-41 | CORE
0 | [13 empty] | P5520 | MIDGE CONTROL BUILDING | MIDGE CONTRL | CORE
0 | [13 empty] | P5521 | STORAGE DOCK | STORAGE DOCK | CORE
0 | [13 empty] | P5522 | GLASSHOUSE FIELD 15A #42 | GH 15A-42 | CORE
0 | [13 empty] | P5523 | ROBERT GORDON SPROUL HALL | SPROUL | CORE
0 | [13 empty] | P5524 | GLASSHOUSE FIELD 15A #43 | GH 15A-43 | CORE
0 | [13 empty] | P5525 | HORTICULTURE GREENHOUSE D1 | GH 16 49 | CORE
0 | [13 empty] | P5526 | HORTICULTURE GREENHOUSE D2 | GH 16 51 | CORE
0 | [13 empty] | P5527 | HORTICULTURE GREENHOUSE D3 | GH 16 52 | CORE
0 | [13 empty] | P5528 | LATHHOUSE LIFE SCIENCES EXPERIMENTAL AREA | LATH LS | CORE
0 | [13 empty] | P5529 | GLASSHOUSE FIELD 15A #48 | GH 15A-48 | CORE
0 | [13 empty] | P5530 | BELLTOWER | BELLTOWER | CORE
0 | [13 empty] | P5531 | HORTICULTURE GREENHOUSE D4 | GH 16 53 | CORE
0 | [13 empty] | P5532 | TELEPHONE BUILDING | TELEPHONE | CORE
0 | [13 empty] | P5533 | CANYON CREST HOUSING 3458 AVOCADO AVENUE | CC AVOC 3458 | NON-CORE
0 | [13 empty] | P5534 | MULTIPURPOSE BUILDING BOTANIC GARDEN | MULTI PURP | NON-CORE
0 | [13 empty] | P5535 | LATHHOUSE B | LATH B | CORE
0 | [13 empty] | P5539 | AGRONOMY FIELD HEADQUARTERS BUILDING | AGRON FLDHSE | CORE
0 | [13 empty] | P5540 | GLASSHOUSE #1 PLASTIC COVERED | GH PLASTC 01 | CORE
0 | [13 empty] | P5541 | GLASSHOUSE #2 PLASTIC COVERED | GH PLASTC 02 | CORE
0 | [13 empty] | P5542 | GLASSHOUSE #3 PLASTIC COVERED FIELD 16 | GH PLA 16-03 | CORE
0 | [13 empty] | P5543 | GLASSHOUSE #4 PLASTIC COVERED | GH PLASTC 04 | CORE
0 | [13 empty] | P5544 | GLASSHOUSE #5 PLASTIC COVERED | GH PLASTC 05 | CORE
0 | [13 empty] | P5545 | GLASSHOUSE #6 PLASTIC COVERED | GH PLASTC 06 | CORE
0 | [13 empty] | P5546 | GLASSHOUSE #7 PLASTIC COVERED | GH PLASTC 07 | CORE
0 | [13 empty] | P5547 | GLASSHOUSE #8 PLASTIC COVERED | GH PLASTC 08 | CORE
0 | [13 empty] | P5548 | AGRICULTURAL OPERATIONS STORAGE SHED #9 | AGOPS SHED 9 | CORE
0 | [13 empty] | P5549 | BOTANY & PLANT SCIENCE STORAGE FACILITY | BOT STOR 8C | NON-CORE
0 | [13 empty] | P5550 | GLASSHOUSE #51 | GH 51 | CORE
0 | [13 empty] | P5551 | GLASSHOUSE FIELD 16 #30 | GH 16 30 | CORE
0 | [13 empty] | P5552 | GLASSHOUSE FIELD 16 #29 | GH 16 29 | CORE
0 | [13 empty] | P5553 | GLASSHOUSE #52 | GH 52 | CORE
0 | [13 empty] | P5554 | ENTOMOLOGY FUMIGATOR | ENT FUMIGATR | CORE
0 | [13 empty] | P5559 | TRAILER PHYSICAL PLANT | T PHYS PLANT | CORE
0 | [13 empty] | P5561 | BIOMEDICAL SCIENCES UNIT 2 TRAILER | T BIOMED2 | CORE
0 | [13 empty] | P5562 | BOTANY & PLANT SCIENCE GREENHOUSE-POLY | GH BOT POLY | CORE
0 | [13 empty] | P5564 | KIOSK/INFORMATION BOOTH | KIOSK | NON-CORE
0 | [13 empty] | P5565 | GREENHOUSE BOTANIC GARDENS | GH BOT GDNS | NON-CORE
0 | [13 empty] | P5566 | POLICE BUILDING | POLICE BLDG | CORE
0 | [13 empty] | P5567 | GLASSHOUSE FIELD 16 #20 | GH 16 20 | CORE
0 | [13 empty] | P5568 | HEADHOUSE BOTANIC GARDENS | HHSE BOT GDN | CORE
0 | [13 empty] | P5571 | METAL RESEARCH BUILDING | METAL RSHBLD | CORE
0 | [13 empty] | P5573 | CONTROL TEMPERATURE STRUCTURE | CONTROL TEMP | NON-CORE
0 | [13 empty] | P5575 | STORED PRODUCTS TEST BUILDING | STOR PR TEST | CORE
0 | [13 empty] | P5579 | PUMPHOUSE #4 | PUMP 4 | CORE
0 | [13 empty] | P5581 | HOUSING ADMINISTRATION | HOUSING ADM | NON-CORE
0 | [13 empty] | P5582 | VOLATILE LIQUID STORAGE BUILDING | VOLA LIQ STG | CORE
0 | [13 empty] | P5583 | GLASSHOUSE #16 PLASTIC COVERED | GH PLASTC 16 | CORE
1 | [13 empty] | P5584 | GLASSHOUSE #14 PLASTIC COVERED | GH PLASTC 14 | CORE
0 | [13 empty] | P5585 | GLASSHOUSE #13 PLASTIC COVERED | GH PLASTC 13 | CORE
0 | [13 empty] | P5586 | GLASSHOUSE #12 PLASTIC COVERED | GH PLASTC 12 | CORE
0 | [13 empty] | P5587 | GLASSHOUSE #15 PLASTIC COVERED | GH PLASTC 15 | CORE
0 | [13 empty] | P5588 | SCHOOL OF MEDICINE - EDUCATION BUILDING | SOM EDUC | CORE
0 | [13 empty] | P5589 | CORPORATION YARD COMPRESSED GAS STORAGE BUILDING | CORP GAS STG | CORE
0 | [13 empty] | P5590 | BANNOCKBURN VILLAGE BLDG A | BANNOCK A | NON-CORE
0 | [13 empty] | P5591 | BANNOCKBURN VILLAGE BLDG B | BANNOCK B | NON-CORE
0 | [13 empty] | P5592 | BANNOCKBURN VILLAGE BLDG C | BANNOCK C | NON-CORE
0 | [13 empty] | P5593 | BANNOCKBURN VILLAGE BLDG D | BANNOCK D | NON-CORE
0 | [13 empty] | P5594 | BANNOCKBURN VILLAGE BLDG E | BANNOCK E | NON-CORE
0 | [13 empty] | P5595 | BANNOCKBURN VILLAGE BLDG F | BANNOCK F | NON-CORE
0 | [13 empty] | P5596 | BANNOCKBURN VILLAGE BLDG G | BANNOCK G | NON-CORE
0 | [13 empty] | P5597 | BANNOCKBURN VILLAGE BLDG H | BANNOCK H | NON-CORE
0 | [13 empty] | P5598 | BANNOCKBURN VILLAGE BLDG I | BANNOCK I | NON-CORE
0 | [13 empty] | P5599 | BANNOCKBURN VILLAGE BLDG J | BANNOCK J | NON-CORE
0 | [13 empty] | P5600 | BANNOCKBURN VILLAGE BLDG K | BANNOCK K | NON-CORE
0 | [13 empty] | P5601 | BANNOCKBURN VILLAGE BLDG L | BANNOCK L | NON-CORE
0 | [13 empty] | P5602 | BANNOCKBURN VILLAGE BLDG M | BANNOCK M | NON-CORE
0 | [13 empty] | P5603 | BANNOCKBURN VILLAGE BLDG N | BANNOCK N | NON-CORE
0 | [13 empty] | P5604 | BANNOCKBURN VILLAGE BLDG O | BANNOCK O | NON-CORE
0 | [13 empty] | P5605 | BANNOCKBURN VILLAGE BLDG P | BANNOCK P | NON-CORE
0 | [13 empty] | P5606 | BANNOCKBURN VILLAGE BLDG Q | BANNOCK Q | NON-CORE
0 | [13 empty] | P5607 | BANNOCKBURN VILLAGE BLDG R | BANNOCK R | NON-CORE
0 | [13 empty] | P5608 | BANNOCKBURN VILLAGE BLDG S | BANNOCK S | NON-CORE
0 | [13 empty] | P5609 | BANNOCKBURN VILLAGE BLDG T | BANNOCK T | NON-CORE
0 | [13 empty] | P5610 | BANNOCKBURN VILLAGE BLDG U | BANNOCK U | NON-CORE
0 | [13 empty] | P5611 | BANNOCKBURN VILLAGE BLDG V | BANNOCK V | NON-CORE
0 | [13 empty] | P5614 | STUDENT SUPPORT SERVICES BUILDING | STUDENT SERV | CORE
0 | [13 empty] | P5616 | SCHOOL OF MEDICINE DINING FACILITY | SOM DINING | CORE
0 | [13 empty] | P5620 | 5029 MONACHELLO LANE | 5029 MONACHE | NON-CORE
0 | [13 empty] | P5621 | 5037 MONACHELLO LANE | 5037 MONACHE | NON-CORE
0 | [13 empty] | P5622 | 5045 MONACHELLO LANE | 5045 MONACHE | NON-CORE
0 | [13 empty] | P5623 | 1670 OROBLANCO AVE | 1670 OROBLAN | NON-CORE
0 | [13 empty] | P5624 | 1654 OROBLANCO AVE | 1654 OROBLAN | NON-CORE
0 | [13 empty] | P5625 | 1640 OROBLANCO AVE | 1640 OROBLAN | NON-CORE
0 | [13 empty] | P5626 | 1626 OROBLANCO AVE | 1626 OROBLAN | NON-CORE
0 | [13 empty] | P5628 | 1606 OROBLANCO AVE | 1606 OROBLAN | NON-CORE
0 | [13 empty] | P5629 | 1598 OROBLANCO AVE | 1598 OROBLAN | NON-CORE
0 | [13 empty] | P5630 | 1590 OROBLANCO AVE | 1590 OROBLAN | NON-CORE
0 | [13 empty] | P5631 | 1582 OROBLANCO AVE | 1582 OROBLAN | NON-CORE
0 | [13 empty] | P5632 | 5141 PIXIE WAY | 5141 PIXIE | NON-CORE
0 | [13 empty] | P5633 | 5133 PIXIE WAY | 5133 PIXIE | NON-CORE
0 | [13 empty] | P5634 | 5125 PIXIE WAY | 5125 PIXIE | NON-CORE
0 | [13 empty] | P5636 | PENTLAND HILLS RESIDENCE HALL BC | PENTLAND BC | NON-CORE
0 | [13 empty] | P5637 | PENTLAND HILLS RESIDENCE HALL D | PENTLAND D | NON-CORE
0 | [13 empty] | P5638 | PENTLAND HILLS RESIDENCE HALL E | PENTLAND E | NON-CORE
0 | [13 empty] | P5639 | PENTLAND HILLS RESIDENCE HALL FG | PENTLAND FG | NON-CORE
0 | [13 empty] | P5640 | PENTLAND HILLS RESIDENCE HALL H | PENTLAND H | NON-CORE
0 | [13 empty] | P5641 | PENTLAND HILLS RESIDENCE HALL J | PENTLAND J | NON-CORE
0 | [13 empty] | P5642 | PENTLAND HILLS RESIDENCE HALL K | PENTLAND K | NON-CORE
0 | [13 empty] | P5643 | PENTLAND HILLS RESIDENCE HALL L | PENTLAND L | NON-CORE
0 | [13 empty] | P5644 | PENTLAND HILLS RESIDENCE HALL M | PENTLAND M | NON-CORE
0 | [13 empty] | P5645 | PENTLAND HILLS RESIDENCE HALL N | PENTLAND N | NON-CORE
0 | [13 empty] | P5646 | PENTLAND HILLS RESIDENCE HALL O | PENTLAND O | NON-CORE
0 | [13 empty] | P5647 | PENTLAND HILLS RESIDENCE HALL P | PENTLAND P | NON-CORE
0 | [13 empty] | P5648 | PENTLAND HILLS RESIDENCE HALL Q | PENTLAND Q | NON-CORE
0 | [13 empty] | P5649 | 5117 PIXIE WAY | 5117 PIXIE | NON-CORE
0 | [13 empty] | P5650 | 5109 PIXIE WAY | 5109 PIXIE | NON-CORE
0 | [13 empty] | P5651 | 5108 PIXIE WAY | 5108 PIXIE | NON-CORE
0 | [13 empty] | P5652 | 5116 PIXIE WAY | 5116 PIXIE | NON-CORE
0 | [13 empty] | P5653 | 5124 PIXIE WAY | 5124 PIXIE | NON-CORE
0 | [13 empty] | P5654 | 5132 PIXIE WAY | 5132 PIXIE | NON-CORE
0 | [13 empty] | P5655 | 1531 OROBLANCO AVE | 1531 OROBLAN | NON-CORE
0 | [13 empty] | P5657 | 1563 OROBLANCO AVE | 1563 OROBLAN | NON-CORE
0 | [13 empty] | P5658 | 1571 OROBLANCO AVE | 1571 OROBLAN | NON-CORE
0 | [13 empty] | P5659 | 1579 OROBLANCO AVE | 1579 OROBLAN | NON-CORE
0 | [13 empty] | P5660 | 1595 OROBLANCO AVE | 1595 OROBLAN | NON-CORE
0 | [13 empty] | P5661 | OBAN APARTMENTS BLDG A | OBAN APTS A | NON-CORE
0 | [13 empty] | P5662 | OBAN APARTMENTS BLDG B | OBAN APTS B | NON-CORE
0 | [13 empty] | P5663 | OBAN APARTMENTS BLDG C | OBAN APTS C | NON-CORE
0 | [13 empty] | P5664 | OBAN APARTMENTS BLDG D | OBAN APTS D | NON-CORE
0 | [13 empty] | P5665 | OBAN APARTMENTS BLDG E | OBAN APTS E | NON-CORE
0 | [13 empty] | P5666 | OBAN APARTMENTS BLDG F | OBAN APTS F | NON-CORE
0 | [13 empty] | P5667 | OBAN APARTMENTS BLDG G | OBAN APTS G | NON-CORE
0 | [13 empty] | P5668 | OBAN APARTMENTS BLDG H | OBAN APTS H | NON-CORE
0 | [13 empty] | P5669 | OBAN APARTMENTS BLDG J | OBAN APTS J | NON-CORE
0 | [13 empty] | P5670 | OBAN APARTMENTS OFFICE BLDG | OBAN OFFICE | NON-CORE
0 | [13 empty] | P5671 | FALKIRK APARTMENTS 1 | FALKIRK 1 | NON-CORE
0 | [13 empty] | P5672 | FALKIRK APARTMENTS 2 | FALKIRK 2 | NON-CORE
0 | [13 empty] | P5673 | FALKIRK APARTMENTS 3 | FALKIRK 3 | NON-CORE
0 | [13 empty] | P5674 | FALKIRK APARTMENTS 4 | FALKIRK 4 | NON-CORE
0 | [13 empty] | P5675 | FALKIRK APARTMENTS 5 | FALKIRK 5 | NON-CORE
0 | [13 empty] | P5676 | FALKIRK APARTMENTS 6 | FALKIRK 6 | NON-CORE
0 | [13 empty] | P5677 | FALKIRK APARTMENTS 7 | FALKIRK 7 | NON-CORE
0 | [13 empty] | P5678 | FALKIRK APARTMENTS 8 | FALKIRK 8 | NON-CORE
0 | [13 empty] | P5679 | FALKIRK APARTMENTS 9 | FALKIRK 9 | NON-CORE
0 | [13 empty] | P5680 | FALKIRK APARTMENTS 10 | FALKIRK 10 | NON-CORE
0 | [13 empty] | P5681 | FALKIRK APARTMENTS 11 | FALKIRK 11 | NON-CORE
0 | [13 empty] | P5682 | FALKIRK APARTMENTS 12 | FALKIRK 12 | NON-CORE
0 | [13 empty] | P5683 | FALKIRK APARTMENTS 13 | FALKIRK 13 | NON-CORE
0 | [13 empty] | P5684 | FALKIRK APARTMENTS 14 | FALKIRK 14 | NON-CORE
0 | [13 empty] | P5685 | FALKIRK APARTMENTS 15 | FALKIRK 15 | NON-CORE
0 | [13 empty] | P5686 | FALKIRK APARTMENTS 16 | FALKIRK 16 | NON-CORE
0 | [13 empty] | P5687 | FALKIRK APARTMENTS 17 | FALKIRK 17 | NON-CORE
0 | [13 empty] | P5688 | FALKIRK APARTMENTS 18 | FALKIRK 18 | NON-CORE
0 | [13 empty] | P5689 | FALKIRK APARTMENTS 19 | FALKIRK 19 | NON-CORE
0 | [13 empty] | P5690 | FALKIRK APARTMENTS LR1 | FALKIRK LR1 | NON-CORE
0 | [13 empty] | P5691 | FALKIRK APARTMENTS LR2 | FALKIRK LR2 | NON-CORE
0 | [13 empty] | P5692 | FALKIRK APARTMENTS LR3 | FALKIRK LR3 | NON-CORE
0 | [13 empty] | P5693 | FALKIRK APARTMENTS OFFICE | FALKIRK OFF | NON-CORE
0 | [13 empty] | P5694 | FALKIRK APARTMENTS MOD | FALKIRK MOD | NON-CORE
0 | [13 empty] | P5695 | STUDENT RECREATION CENTER SOUTH | SRC SOUTH | NON-CORE
0 | [13 empty] | P5696 | STUDENT RECREATION CENTER POOL EQUIPMENT BUILDING | SRC POOLBLDG | NON-CORE
0 | [13 empty] | P5698 | UCR BUILDING | UCR BUILDING
0 | [13 empty] | P5699 | OP BUILDING | OP BUILDING
0 | [13 empty] | P5704 | GLASSHOUSE FIELD 15 #35 | GH 15-35 | CORE
0 | [13 empty] | P5705 | PRESS BOX | PRESS BOX | NON-CORE
0 | [13 empty] | P5706 | CONSTRUCTION TRAILER | T CONSTRUCT | CORE
0 | [13 empty] | P5708 | DELFINO FAMILY PLANT LABORATORY | DELFINO HHSE | CORE
0 | [13 empty] | P5709 | RUBIDOUX SOIL HOUSE 1 | RUBID SOIL 1 | NON-CORE
0 | [13 empty] | P5710 | RUBIDOUX GREENHOUSE | RUBIDOUX GRH | CORE
0 | [13 empty] | P5711 | RUBIDOUX QUARANTINE FACILITY | RUBIDOUX QUA | CORE
0 | [13 empty] | P5712 | RUBIDOUX SCREENHOUSE | RUBIDOUX SCR | CORE
0 | [13 empty] | P5713 | RUBIDOUX LABORATORY #2 | RUBIDOX LAB2 | CORE
0 | [13 empty] | P5714 | RUBIDOUX LABORATORY #1 | RUBIDOUX LAB | CORE
0 | [13 empty] | P5715 | THE PLAZA APARTMENTS | THE PLAZA | NON-CORE
0 | [13 empty] | P5717 | 2100 ATLANTA AVENUE RIVERSIDE | ATLANTA | CORE
0 | [13 empty] | P5718 | MOURADICK FARM LABORATORY BUILDING | MOURADK LAB | CORE
0 | [13 empty] | P5719 | MOURADICK FARM SHOP BUILDING | MOURADK SHOP | CORE
0 | [13 empty] | P5720 | CALIFORNIA MUSEUM OF PHOTOGRAPHY BUILDING | CA MUS PHOTO | CORE
0 | [13 empty] | P5721 | RUBIDOUX GARAGE | RUBIDOUX GAR | CORE
0 | [13 empty] | P5722 | UC RIVERSIDE UNIVERSITY EXTENSION CENTER | UCR EXTEN CT | NON-CORE
0 | [13 empty] | P5724 | TRAILER PLANT PATH2 | T PLNT PATH2 | CORE
0 | [13 empty] | P5725 | PHILIP BOYD DEEP CANYON RESERVE RESEARCH LAB | DC RES LAB | NON-CORE
0 | [13 empty] | P5726 | PHILIP BOYD DEEP CANYON RESERVE ADMIN BLDG | DC ADMIN BLD | NON-CORE
0 | [13 empty] | P5727 | PHILIP BOYD DEEP CANYON RESERVE CAR PORT | DC CAR PORT | NON-CORE
0 | [13 empty] | P5728 | PHILIP BOYD DEEP CANYON RESERVE RESIDENCE | DC RESIDENCE | NON-CORE
0 | [13 empty] | P5729 | MOTTE RIMROCK RESERVE RESIDENCE | MOTTE RESDNC | NON-CORE
0 | [13 empty] | P5730 | GRANITE MOUNTAIN RESERVE DORNERS CAMP CHATEAU | GR MT DORNER | NON-CORE
0 | [13 empty] | P5731 | DEEP CANYON COTTAGE/OFFICE/STORAGE | DC COTTAGE | NON-CORE
0 | [13 empty] | P5732 | PHILIP BOYD DEEP CANYON RESERVE WILBUR MAYHEW BLDG | DC MAYHEW BL | NON-CORE
0 | [13 empty] | P5733 | SIBYL & AL ALLANSON CENTER LABORATORY | GM ALLAN LAB | NON-CORE
0 | [13 empty] | P5734 | SIBYL & AL ALLANSON CENTER RESEARCHER CABIN | GM ALLAN CAB | NON-CORE
0 | [13 empty] | P5735 | SIBYL & AL ALLANSON CENTER EAST RESEARCHER CABIN | GM ALLAN ECB | NON-CORE
0 | [13 empty] | P5736 | SIBYL & AL ALLANSON CENTER WEST RESEARCHER CABIN | GM ALLAN WCB | NON-CORE
0 | [13 empty] | P5737 | T PLANT PATH3 | T PLNT PATH3 | CORE
0 | [13 empty] | P5739 | EMERSON OAKS RESERVE RESTROOM | EMERSON RR | CORE
0 | [13 empty] | P5740 | GRANITE MOUNTAIN BIN 1 | GR MT BIN 1 | NON-CORE
0 | [13 empty] | P5741 | GRANITE MOUNTAIN BIN 2 | GR MT BIN 2 | NON-CORE
0 | [13 empty] | P5742 | GRANITE MOUNTAIN BIN 3 | GR MT BIN 3 | NON-CORE
0 | [13 empty] | P5743 | GRANITE MOUNTAIN ROLL-UP BIN | GR MT ROLLUP | NON-CORE
0 | [13 empty] | P5744 | GRANITE MOUNTAIN STAPLES-ICE HOUSE (HISTORIC) | GR MT ICEHSE | NON-CORE
0 | [13 empty] | P5745 | GRANITE MOUNTAIN TACK HOUSE | GR MT TACK | NON-CORE
0 | [13 empty] | P5746 | GRANITE MOUNTAIN WORKSHOP | GR MT SHOP | NON-CORE
0 | [13 empty] | P5747 | GRANITE MOUNTAIN ALLANSON CENTER RESEARCH CABIN | GM ALLAN ICB | NON-CORE
0 | [13 empty] | P5748 | GRANITE MOUNTAIN ALLANSON CENTER MEETING/STUDY ROOM | GM ALLAN MR | NON-CORE
0 | [13 empty] | P5749 | GRANITE MOUNTAIN ALLANSON CENTER BIN | GM ALLAN BIN | NON-CORE
0 | [13 empty] | P5750 | MOTTE SHED 4 | MOTTE SHED 4 | NON-CORE
0 | [13 empty] | P5751 | BOYD DEEP CANYON SHOP | DC SHOP | NON-CORE
0 | [13 empty] | P5753 | MOTTE-RIMROCK RESERVE SHED #1 | MOTTE SHED 1 | NON-CORE
0 | [13 empty] | P5754 | MOTTE-RIMROCK RESERVE SHED #2 | MOTTE SHED 2 | NON-CORE
0 | [13 empty] | P5755 | MOTTE-RIMROCK RESERVE SHED #3 | MOTTE SHED 3 | NON-CORE
0 | [13 empty] | P5757 | CULVER CENTER FOR THE ARTS | CULVER ROUSE | CORE
0 | [13 empty] | P5779 | GRANITE MOUNTAIN RESEARCH TRAILER | GR MT RS TR | NON-CORE
0 | [13 empty] | P5781 | JAMES SAN JACINTO MTN RESERVE LOLOMI LODGE | JR LOLOMI LG | NON-CORE
0 | [13 empty] | P5782 | JAMES SAN JACINTO MTN RESERVE GARAGE | JAMES R GARG | NON-CORE
0 | [13 empty] | P5784 | JAMES SAN JACINTO MTN RESERVE TRAILFINDERS LODGE | JR TRAIL FLG | NON-CORE
0 | [13 empty] | P5785 | GRANITE MOUNTAIN RESEARCH TRAILER | GR MT RES TR | NON-CORE
0 | [13 empty] | P5786 | GRANITE MOUNTAIN RESERVE STAPLES RANCH HOUSE | GR MT STAPLE | NON-CORE
0 | [13 empty] | P5787 | GRANITE MOUNTAIN RESERVE RESIDENCE | GR MT RESIDN | NON-CORE
0 | [13 empty] | P5788 | HUMAN RESOURCES | HUMAN RSOURC | CORE
0 | [13 empty] | P5789 | DEEP CANYON AGARE HILL RESEARCH BEDROOM | DC AGARE | NON-CORE
0 | [13 empty] | P5799 | GRANITE MOUNTAIN RESIDENCE 2 | GR MT RESID2 | NON-CORE
0 | [13 empty] | P5801 | JR EQUIPMENT SHED 1 | JR SHED 1 | NON-CORE
0 | [13 empty] | P5802 | JR EQUIPMENT SHED 2 | JR SHED 2 | NON-CORE
0 | [13 empty] | P5804 | EMERSON MAIN RESIDENCE | EMERSON RES | NON-CORE
0 | [13 empty] | P5805 | JAMES SAN JACINTO RESERVE CABIN | JR CABIN | NON-CORE
0 | [13 empty] | P5806 | MOTTE-RIMROCK RESERVE SHOP | MOTTE SHOP | NON-CORE
0 | [13 empty] | P5807 | JAMES RESERVE CLASSROOM | JR CLASSROOM | NON-CORE
0 | [13 empty] | P5808 | JAMES RESERVE CABIN C | JR CABIN C | NON-CORE
0 | [13 empty] | P5809 | JAMES RESERVE CABIN B | JR CABIN B | NON-CORE
0 | [13 empty] | P5810 | JAMES RESERVE CABIN A | JR CABIN A | NON-CORE
0 | [13 empty] | P5817 | LATHHOUSE 4 | LATHHOUSE 4 | NON-CORE
0 | [13 empty] | P5820 | FMRI | FMRI | CORE
0 | [13 empty] | P5821 | SOLAR GREENHOUSE | SOLAR GREENH | NON-CORE
0 | [13 empty] | P5825 | SCHOOL OF MEDICINE TRAILER | T MEDICINE | NON-CORE
0 | [13 empty] | P5829 | 4125 WATKINS DRIVE | 4125 WATKINS | NON-CORE
0 | [13 empty] | P5900 | UNIVERSITY VILLAGE BUILDING E | UV BLDG E | NON-CORE
0 | [13 empty] | P5901 | 1935 CHICAGO AVENUE | 1935 CHICAGO | NON-CORE
0 | [13 empty] | P5905 | 555 E TACHEVAH | 555 TACHEVAH | NON-CORE
0 | [13 empty] | P5906 | CE-CERT CHASSIS DYNAMOMETER FACILITY | DYNAMOMETER | CORE
0 | [13 empty] | P5912 | TRAILER STUDENT HEALTH | T STU HEALTH | CORE
0 | [13 empty] | P5913 | 1190 COLUMBIA CE-CERT LEASE | 1190COLUMBIA | NON-CORE
0 | [13 empty] | P5914 | EL MIRADOR MEDICAL PLAZA | EL MIRADOR | NON-CORE
0 | [13 empty] | P5915 | 1111 CITRUS STREET | 1111 CITRUS | NON-CORE
0 | [13 empty] | P5916 | UNIVERSITY VILLAGE BUILDING B | UV BLDG B | NON-CORE
0 | [13 empty] | P5917 | INTELLICENTER - UC PATH | INTELLICTR | NON-CORE
0 | [13 empty] | P5918 | 4510 BROCKTON AVENUE | 4510BROCKTON | NON-CORE
0 | [13 empty] | P5919 | 1955 CHICAGO AVENUE | 1955 CHICAGO | NON-CORE
0 | [13 empty] | P5920 | FROST STUDIO | FROST STUDIO | NON-CORE
0 | [13 empty] | P5921 | 266 FROST COURT MAIN HOUSE | 266 FROST HOUSE | NON-CORE
0 | [13 empty] | P5922 | FROST APT | FROST APT | NON-CORE
0 | [13 empty] | P5923 | FROST GARAGE | FROST GARAGE | NON-CORE
0 | [13 empty] | P5924 | FROST SHED 1 | FROST SHED 1 | NON-CORE
0 | [13 empty] | P5925 | FROST LAUND | FROST LAUND | NON-CORE
0 | [13 empty] | P5926 | FROST SHED 2 | FROST SHED 2 | NON-CORE
0 | [13 empty] | P5927 | FROST BARN | FROST BARN | NON-CORE
0 | [13 empty] | P5928 | 285 FROST CT | 285 FROST CT | NON-CORE
0 | [13 empty] | P5930 | 286 FROST COURT | 286 FROST | NON-CORE
0 | [13 empty] | P5932 | CITRUS TOWER | CITRUS TOWER | NON-CORE
0 | [13 empty] | P5933 | PROGENCY PSYCHIATRIC GROUP | PROGENCY | NON-CORE
0 | [13 empty] | P5934 | ORANGE COUNTY PSYCHIATRY | 18881 VONKAR | NON-CORE
0 | [13 empty] | P5935 | SILVER OAKS WOMENS HEALTH | 19330 JESSE | NON-CORE
0 | [13 empty] | P5936 | EVANS PARK NEUROLOGY | 4500BROCKTON | NON-CORE
0 | [13 empty] | P5937 | APPLE VALLEY NEUROSURGERY | 16143KOKANEE | NON-CORE
0 | [13 empty] | P5938 | 3333 14TH ST | 3333 14th ST | NON-CORE
0 | [13 empty] | P5950 | GLEN MOR F | GLEN MOR F | NON-CORE
0 | [13 empty] | P5951 | GLEN MOR G | GLEN MOR G | NON-CORE
0 | [13 empty] | P5952 | GLEN MOR H | GLEN MOR H | NON-CORE
0 | [13 empty] | P5953 | GLEN MOR I | GLEN MOR I | NON-CORE
0 | [13 empty] | P5954 | GLEN MOR J | GLEN MOR J | NON-CORE
0 | [13 empty] | P5955 | GLEN MOR K | GLEN MOR K | NON-CORE
0 | [13 empty] | P5956 | GLEN MOR L | GLEN MOR L | NON-CORE
0 | [13 empty] | P5957 | GLEN MOR M | GLEN MOR M | NON-CORE
0 | [13 empty] | P5959 | BIG SPRINGS PARKING STRUCTURE | BIG SPR PARK | NON-CORE
0 | [13 empty] | P5980 | CE-CERT OFFICE BUILDING | 1084COLUMBIA | NON-CORE
0 | [13 empty] | P5981 | CE-CERT CHAMBER BUILDING | 1086COLUMBIA | NON-CORE
0 | [13 empty] | P5983 | 1200 COLUMBIA AVENUE, RIVERSIDE | 1200COLUMBIA | NON-CORE
0 | [13 empty] | P5985 | MOTTE RIMROCK RESERVE TRAILER | MOTTE TRAILR | NON-CORE
0 | [13 empty] | P5986 | USDA SALINITY LABORATORY | SALINITY LAB | NON-CORE
0 | [13 empty] | P5987 | UNIVERSITY VILLAGE OFFICE LEASE | UV BLDG A | NON-CORE
0 | [13 empty] | P5990 | CHAVEZ COMCT | CHAVEZ COMCT
0 | [13 empty] | P5991 | STONEHAVEN APARTMENTS | STONEHAVEN | NON-CORE
0 | [13 empty] | P5994 | USDA CLONAL GERMPLASM RESPOSITORY | GERMPLASM | CORE
0 | [13 empty] | P5998 | INTERNATIONAL VILLAGE (UNEX) | INTER VILLAG | NON-CORE
0 | [13 empty] | PG650 | SUBSTATION | SUBSTATION
0 | [13 empty] | T MRB1 | MRB1 T1 | MRB1 T1
0 | [13 empty] | T MRB2 | MRB1 T2 | MRB1 T2
0 | [13 empty] | T MRB3 | MRB1 T3 | MRB1 T3
0 | [13 empty] | Z1005 | SOFTBALL STG | SOFTBALL STG
0 | [13 empty] | Z1016 | FIELD 9 SHED | FIELD 9 SHED
0 | [13 empty] | Z1017 | T MORSE HALL | T MORSE HALL
0 | [13 empty] | Z1018 | T SEELEY HAL | T SEELEY HAL
0 | [13 empty] | Z1019 | SHIP 29 | SHIP 29
0 | [13 empty] | Z1020 | T SBUR HALL | T SBUR HALL
0 | [13 empty] | Z1021 | STOR 14-1 | STOR 14-1
0 | [13 empty] | Z1023 | COLD 1 | COLD 1
0 | [13 empty] | Z1024 | COLD 2 | COLD 2
0 | [13 empty] | Z1025 | COLD 3 | COLD 3
0 | [13 empty] | Z1026 | COLD 4 | COLD 4
0 | [13 empty] | Z1027 | COLD 5 | COLD 5
0 | [13 empty] | Z1028 | COLD 6 | COLD 6
0 | [13 empty] | Z1029 | COLD 7 | COLD 7
0 | [13 empty] | Z1030 | T2 FIELD 14-1 | T2 FIELD 14-1
0 | [13 empty] | Z1031 | SHED 20 | SHED 20
0 | [13 empty] | Z1032 | T1 STOR | T1 STOR
0 | [13 empty] | Z1033 | 21 1623 STOR | 21 1623 STOR
0 | [13 empty] | Z1034 | STOR 23 | STOR 23
0 | [13 empty] | Z1035 | 21 1775 STOR | 21 1775 STOR
0 | [13 empty] | Z1036 | 21 1776 STOR | 21 1776 STOR
0 | [13 empty] | Z1037 | STOR 26 | STOR 26
0 | [13 empty] | Z1038 | 21 1595 STOR | 21 1595 STOR
0 | [13 empty] | Z1039 | STOR 3 | STOR 3
0 | [13 empty] | Z1040 | STOR 4 | STOR 4
0 | [13 empty] | Z1041 | STOR 5 | STOR 5
0 | [13 empty] | Z1042 | STOR 6 | STOR 6
0 | [13 empty] | Z1043 | STOR 21 6075 | STOR 21 6075
0 | [13 empty] | Z1044 | SHED 21 | SHED 21
0 | [13 empty] | Z1046 | COLD STOR | COLD STOR
0 | [13 empty] | Z1048 | GH 15-49 | GH 15-49
0 | [13 empty] | Z1049 | SHED 30 | SHED 30
0 | [13 empty] | Z1050 | SHED 31 | SHED 31
0 | [13 empty] | Z1051 | SHED 32 | SHED 32
0 | [13 empty] | Z1052 | FENCE 1 | FENCE 1
0 | [13 empty] | Z1053 | STOR 33 | STOR 33
0 | [13 empty] | Z1054 | STOR 34 | STOR 34
0 | [13 empty] | Z1055 | FENCE 2 | FENCE 2
0 | [13 empty] | Z1056 | COOP 1 | COOP 1
0 | [13 empty] | Z1057 | COOP 4 | COOP 4
0 | [13 empty] | Z1058 | FENCE 4 | FENCE 4
0 | [13 empty] | Z1059 | FENCE 3 | FENCE 3
0 | [13 empty] | Z1060 | COOP 3 | COOP 3
0 | [13 empty] | Z1061 | COOP 2 | COOP 2
0 | [13 empty] | Z1062 | SCREEN 35 | SCREEN 35
0 | [13 empty] | Z1063 | STOR CANVAS | STOR CANVAS
0 | [13 empty] | Z1064 | SHED 8 | SHED 8
0 | [13 empty] | Z1065 | SHED 36 | SHED 36
0 | [13 empty] | Z1066 | CARGO 1 | CARGO 1
0 | [13 empty] | Z1067 | SHED 37 | SHED 37
0 | [13 empty] | Z1068 | SHED 38 | SHED 38
0 | [13 empty] | Z1069 | SHED 39 | SHED 39
0 | [13 empty] | Z1070 | SCREEN 1 | SCREEN 1
0 | [13 empty] | Z1071 | CARGO 2 | CARGO 2
0 | [13 empty] | Z1072 | SHED 40 | SHED 40
0 | [13 empty] | Z1073 | CANOPY FUM | CANOPY FUM
0 | [13 empty] | Z1074 | STOR 38 | STOR 38
0 | [13 empty] | Z1075 | STOR 39 | STOR 39
0 | [13 empty] | Z1076 | STOR 40 | STOR 40
0 | [13 empty] | Z1077 | STOR 41 | STOR 41
0 | [13 empty] | Z1078 | STOR 42 | STOR 42
0 | [13 empty] | Z1079 | STOR 43 | STOR 43
0 | [13 empty] | Z1080 | SCREEN 2 | SCREEN 2
0 | [13 empty] | Z1081 | SHED 41 | SHED 41
0 | [13 empty] | Z1089 | SHED 42 | SHED 42
0 | [13 empty] | Z1090 | GH K1 | GH K1
0 | [13 empty] | Z1093 | PICNIC 1 | PICNIC 1
0 | [13 empty] | Z1094 | PICNIC 2 | PICNIC 2
0 | [13 empty] | Z1096 | METEOR 9C | METEOR 9C
0 | [13 empty] | Z1097 | SHED 8 | SHED 8
0 | [13 empty] | Z1098 | TURF FERTIL | TURF FERTIL
0 | [13 empty] | Z1099 | SHED 9 | SHED 9
0 | [13 empty] | Z1100 | COLD BOX 2 | COLD BOX 2
0 | [13 empty] | Z1101 | INST TOWER | INST TOWER
0 | [13 empty] | Z1102 | PUMP 5 | PUMP 5
0 | [13 empty] | Z1103 | PUMP SHED | PUMP SHED
0 | [13 empty] | Z1104 | TANK STORAGE | TANK STORAGE
0 | [13 empty] | Z1105 | METAL SHED 1 | METAL SHED 1
0 | [13 empty] | Z1106 | METAL SHED 2 | METAL SHED 2
0 | [13 empty] | Z1107 | METAL SHED 3 | METAL SHED 3
0 | [13 empty] | Z1108 | METAL SHED 4 | METAL SHED 4
0 | [13 empty] | Z1109 | METAL SHED 5 | METAL SHED 5
0 | [13 empty] | Z1110 | METAL SHED 6 | METAL SHED 6
0 | [13 empty] | Z1111 | METAL SHED 7 | METAL SHED 7
0 | [13 empty] | Z1112 | METAL SHED 8 | METAL SHED 8
0 | [13 empty] | Z1113 | SOC BLEACHER | SOC BLEACHER
0 | [13 empty] | Z1114 | SOC TRAILER1 | SOC TRAILER1
0 | [13 empty] | Z1115 | SOC TRAILER2 | SOC TRAILER2
0 | [13 empty] | Z1116 | TRACK BLEACH | TRACK BLEACH
0 | [13 empty] | Z1117 | LATH C | LATH C
0 | [13 empty] | Z1118 | LATH 10 | LATH 10
0 | [13 empty] | Z1119 | STEAM GENER | STEAM GENER
0 | [13 empty] | Z1121 | FENCE 6 | FENCE 6
0 | [13 empty] | Z1122 | FENCE 7 | FENCE 7
0 | [13 empty] | Z1123 | METAL TANK 1 | METAL TANK 1
0 | [13 empty] | Z1124 | METAL STOR 1 | METAL STOR 1
0 | [13 empty] | Z1125 | METAL STOR 2 | METAL STOR 2
0 | [13 empty] | Z1126 | COLD 8 | COLD 8
0 | [13 empty] | Z1127 | COLD 9 | COLD 9
0 | [13 empty] | Z1128 | METAL CANOPY | METAL CANOPY
0 | [13 empty] | Z1129 | SHED 45 | SHED 45
0 | [13 empty] | Z1133 | BOT GDN SHD | BOT GDN SHD
0 | [13 empty] | Z1134 | BOT GDN SHD2 | BOT GDN SHD2
0 | [13 empty] | Z1136 | HSNG STOR | HSNG STOR
0 | [13 empty] | Z1137 | CVAR SHADE 1 | CVAR SHADE 1
0 | [13 empty] | Z1138 | CVAR PAD 1 | CVAR PAD 1
0 | [13 empty] | Z1139 | CVAR T1 | CVAR T1
0 | [13 empty] | Z1140 | CVAR OLD ICE | CVAR OLD ICE
0 | [13 empty] | Z1141 | CVAR T LAB | CVAR T LAB
0 | [13 empty] | Z1142 | CVAR STOR 2 | CVAR STOR 2
0 | [13 empty] | Z1143 | CVAR FUEL | CVAR FUEL
0 | [13 empty] | Z1144 | CVAR GH 1 | CVAR GH 1
0 | [13 empty] | Z1145 | CVAR GH 2 | CVAR GH 2
0 | [13 empty] | Z1146 | CVAR INSECT 1 | CVAR INSECT 1
0 | [13 empty] | Z1147 | CVAR INSECT 2 | CVAR INSECT 2
0 | [13 empty] | Z1148 | CVAR INSECT 3 | CVAR INSECT 3
0 | [13 empty] | Z1149 | CVAR SHED 1 | CVAR SHED 1
0 | [13 empty] | Z1150 | CVAR PAD 2 | CVAR PAD 2
0 | [13 empty] | Z1151 | CVAR SHED 2 | CVAR SHED 2
0 | [13 empty] | Z1152 | CVAR SHADE 2 | CVAR SHADE 2
0 | [13 empty] | Z1153 | CVAR STOR 2 | CVAR STOR 2
0 | [13 empty] | Z1154 | CVAR SHADE 3 | CVAR SHADE 3
0 | [13 empty] | Z1155 | CVAR FENCE 1 | CVAR FENCE 1
0 | [13 empty] | Z1156 | CVAR PUMP | CVAR PUMP
0 | [13 empty] | Z1157 | CVAR CONT 1 | CVAR CONT 1
0 | [13 empty] | Z1158 | CVAR CONT 2 | CVAR CONT 2
0 | [13 empty] | Z1159 | CVAR CONT 3 | CVAR CONT 3
0 | [13 empty] | Z2000 | BSL3 LAB | BSL3 LAB
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Legend
Legend and Contacts
FS | Facilities Services
PD&C | Planning, Design & Construction (formerly A&E - Architects & Engineers)
FS Current Statuses | Definitions
Project Intake | Building Zone Manager (BZM) to meet with customer to understand and define scope of work.
Queue to Start | Initial scope of work has been identified by BZM; project in queue for FS Project Manager to develop drawings and coordinate trades for execution.
Plan Development / Check | Project Manager is coordinating plan development and review by Building Official and/or Fire Marshal.
In Progress | Project is in progress which includes but not limited to plan development, scheduling and coordination of trades for work execution.
Hold - Customer Equipment/Schedule | Project is on hold pending customer provided equipment or scheduling availability.
Hold - Facilities Services | Project is on hold pending FS; determining ability to complete project within FS purview or parts ordered by FS for completion.
Quality Check of Work | Project is being reviewed to ensure work is completed to customer and FS standards.
Canceled by Client | Project is canceled at the request of the customer or duplicative project request.
Canceled by FS | Project is canceled by FS administration or duplicative project request.
IRT Review | Project is to be reviewed by PD&C/FS or to be completed by PD&C with a project submittal by customer within CPMS.
Complete | Project is complete to customer and FS standards.
TO BE PERFORMED BY PD&C | Project is no longer an FS project and will be managed and completed by PD&C.
PD&C Current Statuses | Definitions
"Open Field" | PD&C project managers will input most recent update in this field.
| FS | PD&C
Org | Org Delegate/Contact | CPMS Department Approver
ATHLETICS | Joseph Erbland / Eugene Hutchinson Jr. | Joseph Erbland
BCOE | Todd Ambriz | Susana Aparicio
CAMPUS | TBD
CAP.PROG. | Sharyl Murdock | John White
CHANCELLOR | Luis Alvarez / Jackie Rodriguez
CHASS | Cindy Williams | Cindy Williams KatriceCalloway
CNAS | Jose Wudka | Beverly McNeil Kimberly Hammond
ENROLLMENT SERVICES | Emily Engelschall / Sean Cason
FAC-PLNG-DESIGN-CONST | Monty Anderson | Monty Anderson
GRAD.DIV | Kennett Lai
GSOE | Sally Tavizon
ITS | Shelley Gupta | Shelley Gupta
LIBR | Dave Shuster | Jacqueline Bates
PALM DESERT |  | Tamara Hedges
PLANNING BUDGET & ADMINISTRATION | TBD | Jeff Kaplan / Andy Plumley
PROVOST/EVC | Luis Alvarez / Jackie Rodriguez
SoB | Angela Chang | Laurie Gustafson
SOM | Cynthia Carolina | Laura Manor
SPP | Luke Hoepfner
VC-RED | Laura Manor | Laura Manor
VC-STU.AFF. | Cathy Eckman | Karen McComb Lindy Fenex Cathy Eckman
VC-UNIV.ADV. | Naysia Caldwell | Margene Mastin-Schepps