## Active Project Summary
Integrated Project Summary Report
[6 empty] | Total Active PD&C Projects |  | 119
[6 empty] | Total Active FS Projects |  | 107
Last Updated | 2019-03-01 | Project Summary |  |  |  | Project Status |  |  |  |  | Campus Impact (i.e. excessive noise / limited access / utility shutdown) |  |  | Project Details
Organization | Project Ref No. | Project Service Unit | Project Title | Building | Room | Request Date | Current Status | Next Steps | START Date | COMPLETE Date | Impact Description | Impact Date START | Impact Date END | Project Description | PD&C Org Priority No. | FS Org Priority No. | For New Faculty Hire? | Contact / Requestor | Proj Manager
ATHLETICS | 2696 | PD&C | Soccer Stadium Fencing (E Side) |  |  | 2014-04-10 | In coordination with Mobility Hub | To be coord. with Rec Mall work | [5 empty] | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. | 3 |  |  | Joe Erbland | Gerald Caraig
ATHLETICS | 3407 | PD&C | Athletics Media Room | S LCKRM/CONC |  | 2018-08-23 | In Programming | Create SOW | 2019-09-01 | 2019-10-01 |  |  |  | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | 2 |  |  | Johnathan Jensen | Fernando Nunez
ATHLETICS | 3408 | PD&C | Harrison Field Netting | SOFTBALL STG |  | 2018-01-23 | Per department: Project is on hold until further notice. | On-Hold by Cust Until Further No | [5 empty] | Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | 99 |  |  | Joseph Erbland | Fernando Nunez
ATHLETICS | 3432 | PD&C | Athletics Replace Scoreboard |  |  | 2018-07-19 | On-hold | On-Hold | [5 empty] | Please assist with coordinating the process for replacement of existing soccer scoreboard to a new model. We will work with A&E to develop criteria and how to accomplish the task. | 1 |  |  | Joseph Erbland | Scott Donnell
ATHLETICS | 19P000252 | FS | SL5-ATH DANCE SHOWER DOORS | ATH DANCE | 0050K | 2018-09-10 | QUEUE TO START | [6 empty] | FS to coordinate with customer to scope the work. |  | 3 |  | JOSEPH ERBLAND
ATHLETICS | 19P000268 | FS | SL5-ATH DANCE - PATCH AND PAINT 20C | ATH DANCE | 20C | 2018-09-11 | QUEUE TO START | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 4 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 19P000271 | FS | SL5-ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 | ATH DANCE | 3 | 2018-09-12 | QUEUE TO START | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 11 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 19P000272 | FS | SL5-NEED URINAL DIVIDERS | ATH DANCE | 50E | 2018-09-12 | HOLD - FACILITIES SERVICES | [6 empty] | FS to coordinate with customer to scope the work. |  | 13 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000273 | FS | SL5-ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS | ATH DANCE |  | 2018-09-12 | QUEUE TO START | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 9 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 19P000274 | FS | SL5-RIV SPORTS CPX - REPLACE URINALS | RIV SPORTS CPX |  | 2018-09-12 | HOLD - FACILITIES SERVICES | [6 empty] | FS to coordinate with customer to scope the work. |  | 15 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000277 | FS | SL5-ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | ATH DANCE |  | 2018-09-12 | QUEUE TO START | [6 empty] | FS to coordinate with customer to scope the work. |  | 10 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000309 | FS | SL5-RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | ATH DANCE |  | 2018-09-12 | QUEUE TO START | [6 empty] | FS to coordinate with customer to scope the work. |  | 7 |  | JOHNATHAN JENSEN
BAS | 2508 | PD&C | Barn Expansion |  |  | 2013-07-05 | In construction | Complete Construction | 2018-06-01 | 2019-10-01 |  |  |  | Project 950493 Barn has completed the DPP process and we are now adding this to CPMS to capture expenses related to the Program Process which occurred in FY11-12 and FY12-13. Please move all expenditures from A01233-70003-76 Cost Center to JR142 to a plant account. | 4 |  |  | Susan Marshburn | D.Hecht/J.Franklin
BAS | 2868 | PD&C | West Lothian Elevator Renovation |  |  | 2015-04-08 | In Design | Bidding | 2019-06-01 | 2019-08-01 |  |  |  |  | 32 |  |  | Richard Geiger | John Franklin
BAS | 3286 | PD&C | Falkirk Apartments Seismic Improvements | FALKIRK 1 |  | 2017-03-29 | Awaiting revised proposal from Miyamoto | Complete Design | 2019-06-01 | 2019-08-01 |  |  |  | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | 9 |  |  | Richard Geiger | J.Franklin/J.Espinoza
BAS | 3354 | PD&C | Lot 4/Barn Area ADA Improvements |  |  | 2017-08-15 | In Design | Updated Proposal & Cost Estimate | 2019-07-01 | 2019-09-27 |  |  |  | Lot 4/Barn Area ADA Improvements - The proposed project will relocate an existing crosswalk that is not ADA compliant and provide path of travel improvements and additional ADA parking capacity in Parking Lot 4. The existing crosswalk located at West Campus Drive and Parking Lot 4 (north) was identified in the Draft ADA Transition Plan to be out of compliance. A Pedestrian Safety Study by Fehr & Peers completed in June 2008 identified the relocation of this crosswalk to approximately 100 feet east to provide a more visible, safe, pedestrian crossing. To increase pedestrian safety further, the crosswalk will be designed as a speed table. Additionally, Transportation and Parking Services proposes to create additional ADA parking spaces in Parking Lot 4 that exceed the required number, with hardscape and path of travel improvements that will connect to the new crosswalk. The improved crosswalk will correct required path of travel deficiencies from a parking lot that provides access to numerous publicly accessible buildings, as well as allow the Barn Expansion project to obtain Division of State Architect (DSA) approval once construction is completed. The funds to complete the crosswalk replacement will be requested from Campus ADA funds. Parking Lot 4 improvements will come from will come from TAPS. Although this project supports the Barn Renovation, its conception and need is not tied to the Barn project. The crosswalk improvements and additional ADA parking is needed to meet our ADA parking requirements and serve the growing demand on campus. This project is desired regardless of the Barn Renovation project. | 16 |  |  | Andrew Stewart | Fernando Nunez
BAS | 3376 | PD&C | West Lothian Roof Replacement Design | LOTHIAN HALL |  | 2017-09-28 | In Design | Bidding | 2019-06-01 | 2019-08-01 |  |  |  | Provide Schematic Design, Design Development and professional cost estimate to replace the existing single-ply membrane roof system on the Lothian West residence hall wings plus Common Area applications. Existing roofing is past its useful life and starting to experience multiple leaks that are damaging living spaces below. Design effort should select the most appropriate roof material for this roof plan. The intent is to design this year (alongside the Lothian East design) and construct immediately following the Lothian East roof replacement. | 19 |  |  | Richard Geiger | John Franklin
BAS | 3382 | PD&C | West Lothian Restroom & Common Area Design | LOTHIAN HALL |  | 2017-09-29 | Project pushed to 2021 | Project pushed to 2021 | [5 empty] | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | 31 |  |  | Richard Geiger | D.Hecht/J.Franklin
BAS | 3383 | PD&C | W Lothian Air Handler Replacemt | LOTHIAN HALL |  | 2017-10-03 | Complete Design/Bidding | Complete Design/Bidding | 2019-06-01 | 2019-08-01 |  |  |  | Existing air handler equipment in West Lothian is original to the building and past its service life. Provide HVAC professional services to develop options for Air Handler replacement that meet UC Carbon Neutral 2025 goal. Each option analysis should include pros and cons for energy consumption, reliability, serviceability and system installation cost projections. At least one option should explore potential conversion to individual package units as practical. | 20 |  |  | Richard Geiger | John Franklin
BAS | 3392 | PD&C | Bicycle Master Plan Study |  |  | 2017-11-13 | Pre-Programming | Funding | [5 empty] | Bicycle Master Plan Study. This CPMS project is for the funding and creation of a Bicycle Master Plan Study for the UCR Campus. It is not for a specific capital project. | 33 |  |  | Irma Henderson | Jerrod Walters
BAS | 3397 | PD&C | Dundee Residence Hall and Glasgow Dining | ABER INVER |  | 2017-11-21 | In Construction | Complete Construction | 2019-01-01 | 2020-09-01 |  |  |  | (Lot 22/Dundee-Glasgow) A newly proposed student housing development, including a single phase 760-bed residence hall and an 830-seat dining facility located on the existing Parking Lot 22 site south of Linden Street. The project is anticipated to be completed by Fall/Winter 2020. Funding for predevelopment activities including CEQA and staff augmentation to be determined. | 36 |  |  | Richard Geiger | Raoul Amescua
BAS | 3403 | PD&C | Parking Lot 23 Addition |  |  | 2018-05-17 | In Design | Design | 2019-07-01 | 2019-08-01 |  |  |  | Parking Lot 23 Expansion - The goal of the project is to add additional parking capacity to Parking Lot 23 to serve that area of the campus. Current parking capacity in this area will be impacted by the closures of Lot 22 and Crest Housing parking area. Additional capacity will be need for employee parking. | 14 |  |  | Andrew Stewart | Daneca Stevens
BAS | 3411 | PD&C | MRB Café Buildout & MS&E Loading Dock Mods | MAT SCI ENGR |  | 2018-02-05 | In construction | Complete Construction | 2018-11-19 | 2019-04-01 |  |  |  | MRB1 CAFE and SERVICE YARD INTERIOR FIT-OUT: provide design and construction services to build out the interior of the MRB1 Café shell and modify the MS&E Service Yard to accommodate the café deliveries and trash movement. This CPMS Request is to combine and replace previously approved CPMS #3378 and #3398 into one project as requested by A&E. Please note that the IRT Job walk has already been completed. Intent is to design in FY'17/18 and construct in FY '18/19. Opening to coincide with the MRB1 facility turnover. Food service equipment will be Owner Furnished on a separate UCR Purchase Order. Note that the MRB1 Café shell construction is provided by the separately funded MRB1 project, construction drawings for this shell space are attached in CPMS. | 1 |  |  | Richard Geiger | Mihai Gavan
BAS | 3421 | PD&C | A-I Boiler Replacement | ABER INVER |  | 2018-03-19 | On Hold-Funding | CIB Approval | [5 empty] | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | 5 |  |  | Richard Geiger | John Franklin
BAS | 3426 | PD&C | Lothian Boiler Replacement | LOTHIAN HALL |  | 2018-03-19 | Complete Design/Bidding | Complete Design/Bidding | 2019-06-01 | 2019-08-01 |  |  |  | The boiler equipment at Lothian is original to the building and past its useful life. Design, procure and install a replacement boiler that incorporates the latest energy saving and management technology that can be cost-effectively installed as a direct replacement to the existing unit. | 6 |  |  | Richard Geiger | John Franklin
BAS | 3430 | PD&C | TAPS Cust Svc Lobby Upgrades | PARKING SERV |  | 2018-05-17 | On hold until Summer 2019 | On hold until Summer 2019 | [5 empty] | Upgrades to Customer Service Lobby – Need to complete Tenant Improvement project upgrade customer service counter in Parking Services Building. Want to replace current counter to allow for; modern computer equipment, dividers between customers’ transaction spaces, under counter space for filing cabinets and check writing space. Please coordinate with Auxiliaries’ primary PM John Franklin. | 15 |  |  | Andrew Stewart | Dave Bomba
BAS | 3439 | PD&C | TAPS Strategic Master Plan Study |  |  | 2018-06-05 | Postponed until Mid-2019 | Postponed until Mid-2019 | [5 empty] | STUDY - Transportation And Parking Master Plan Study This study initiated by TAPS is part of a comprehensive planning effort within Auxiliaries to develop a strategic transportation and parking plan that will guide the university’s transportation and parking efforts over the next decade. This is complementary to the campus Physical Master Plan Study and will help inform the future new LRDP. | 17 |  |  | Irma Henderson | Jerrod Walters
BAS | 3453 | PD&C | ECS N&S Playground Shade & Turf |  |  | 2018-07-03 | Dept approval/funding | Dept approval/funding | [5 empty] | Provide Schematic Design, Design Development and Professional Cost Estimate for the alteration of existing shade structures, provision for additional shade structures, refinish interior metal fencing, and the replacement of existing grass with synthetic turf at the Early Childhood Services north and south playground areas. Prepare drawings so that they can be bid and constructed as separate projects. | 22 |  |  | Richard Geiger | John Franklin
BAS | 3455 | PD&C | Campus Traffic Engineering Study |  |  | 2018-07-23 | In Construction | TAPS Response | 2018-11-05 | 2019-06-01 |  |  |  | This request is to fund the contracting of a consulting firm to study of the impacts related to the desired construction of a new parking garage on the UCR campus. Project will inform on site selection, traffic impacts and opportunities. This project will be funded through a parking garage planning budget allocation in the approved 2018-19 TAPS budget. | 27 |  |  | Irma Henderson | Dave Bomba
BAS | 3459 | PD&C | A-I Hardscape Landscape Design | ABER INVER |  | 2018-07-16 | In Design | Complete Design | 2020-01-01 | 2020-08-01 |  |  |  | Provide Schematic Design and Design Development drawings for a selective renovation of all hardscape and landscape around the perimeter of the Aberdeen-Inverness housing complex. Scope to include (but not limited to) widening of South Walk and replace its asphalt with concrete pavers, upgrade hardscape and landscape at Horseshoe, replace selected lawn areas with hardscape, seating and solar umbrellas at east and west lawns of Building E, consider new bike storage along South Walk, consider modifying slopped lawn between Building A and Linden St., generally reduce lawn areas and replace with sustainable planting, prune or replace unkempt trees, replace selected light fixtures to match Dundee fixtures, and generally freshen the landscaping so that it is harmonious with the new Dundee development. Design to be packaged in phases, with the South Walk and Dundee-facing landscape to be ready in Phase 1 for construction timing alongside Dundee-Glasgow landscaping in Spring of 2020. | 23 |  |  | Richard Geiger | J.Franklin/J.Espinoza
BAS | 3460 | PD&C | A-I Restroom Replacement - Reconfig | ABER INVER |  | 2018-07-19 | In Design | Complete Design | 2019-06-01 | 2019-08-01 |  |  |  | Provide Schematic Design and Design Development drawings for the complete replacement of the restrooms in all four resident hall wings. Existing restroom fixtures and finishes are largely original to the building and long past their service life, causing serious leaks between floors. New restrooms will be reconfigured to meet current accessibility code. Documents to be assembled for phased construction, one wing per summer, with the first building (D-Wing) to be constructed in Summer 2019. | 26 |  |  | Richard Geiger | J.Franklin/J.Espinoza
BAS | 3462 | PD&C | A-I Restaurant & Lobby Reconfiguration | ABER INVER |  | 2018-07-17 | In Programming | RFQ Development | 2020-08-01 | 2021-06-01 |  |  |  | Provide Schematic Design and Design Development drawings for the complete reconfiguration of Building C including kitchen, dining space, and common areas. The restaurant and kitchen areas are largely original to the building and well past their useful life. The new, replacement, Glasgow restaurant coming on-line in Fall 2020 will allow a needed reprogramming and modernization of this space. Preliminary Program for this space includes a smaller Catering Kitchen, Meeting Rooms, new KUCR studio as well as a modernization and upgrade of the Lobby and other Common Areas. Documents to be assembled for a Fall 2020 construction start. | 24 |  |  | Richard Geiger | J.Franklin/J.Espinoza
BAS | 3463 | PD&C | Landscape Strategic Plan for Housing Services |  |  | 2018-07-17 | In Programming | Consultant Selection | [5 empty] | Provide a comprehensive study of existing landscape areas within Auxiliary Services and provide specific and actionable recommendations for their conversion to sustainable landscaping by location. Study to include all Resident Hall and Apartment properties and include conceptual cost estimates, by location, for proposed landscape conversions. | 25 |  |  | Richard Geiger | Jason Espinoza
BAS | 3466 | PD&C | Oban Porch and Stair Repair | OBAN APTS A |  | 2018-07-31 | In Design | Consultant Contract | 2019-05-01 | 2019-12-01 |  |  |  | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | 30 |  |  | Richard Geiger | Jason Espinoza
BAS | 3467 | PD&C | Plaza Porch/Stair Structural Repairs | THE PLAZA |  | 2018-07-31 | In Programming | Consultant Contract | 2019-08-01 | 2019-10-01 |  |  |  | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | 29 |  |  | Richard Geiger | Jason Espinoza
BAS | 3472 | PD&C | Lot 21 Trash Enclosure Relocation |  |  | 2018-08-15 | Funding | Hire Design Consultant | 2019-05-01 | 2019-06-01 |  |  |  | Construct a new CMU trash enclosure with water and power in a different location of Lot 21 to replace the existing enclosure that will be demolished to make way for the Dundee Residence Hall construction. Include hose bib for cleaning and power for future compactor installation. New enclosure needs to be on line BEFORE site construction can start on Dundee-Glasgow in January 2019. | 34 |  |  | Richard Geiger | John Franklin
BAS | 3478 | PD&C | Ivans Hinderaker Ext. Cladding | HINDERAKER |  | 2018-09-07 | Project number assigned | Complete Construction | 2019-03-01 | 2019-04-01 |  |  |  | Replace existing exterior cladding outside of Ivan's kiosk with new building materials that will cover the abandoned openings in the exterior and provide a cohesive and waterproof envelope for this structure. | 99 |  |  | Richard Geiger | John Franklin
BAS | 3488 | PD&C | CBS HUB Business Center |  |  | 2018-11-13 | Close-out | Complete Project Close-Out | 2018-12-17 | 2018-12-21 |  |  |  | Provide a light renovation of the HUB Modular space to include new electrical drop for the Card Office cubicles in the North Office (where the copy machines are now), and replace flooring in the North Office as required, install ADA shelf at the front desk and other minor scope items to facilitate the move of the Card Office to this building. This must be a Winter Break project so that the Business Center remains online during the normal campus schedule. | 39 |  |  | Richard Geiger | Fernando Nunez
BAS | 3490 | PD&C | East Campus Parking Structure |  |  | 2018-12-06 | In Design | Selection of Design Build Teams | 2019-12-01 | 2021-02-01 |  |  |  | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. | 42 |  |  | Irma Henderson | Dave Bomba
BAS | 3491 | PD&C | Oban Comm Ctr Remodel |  |  | 2018-11-16 | Aux. Svcs. Placed the project on hold until '20/'21 FY. | Re-scope/Client approval/Funding | [5 empty] | General remodel and freshening of the Oban Family Housing Community Center to include Laundry Room, Public Restroom and Recreation Room. Scope documents and partial drawings attached. This was originally two separate projects that Facility Services was managing but has now been requested that A&E take over due to evolving complexity and dollar cost. | 38 |  |  | Richard Geiger | J.Franklin/J.Espinoza
BAS | 3503 | PD&C | Falkirk Stair/Front Porch Repair |  |  | 2019-02-01 | New | Complete design | [5 empty] | Repair or replace four sets of entry stairs and landings that are long past their service life and are a life safety concern. Consider replacing these wood structures with steel to ease future maintenance. Apartments affected are #3RS, #11MN, #15A and #16FG. | 43 |  |  | Richard Geiger | John Franklin
BAS | 18W009630 | FS | SL5-BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | PHYS PL STOR | 100 | 2018-01-22 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | [6 empty] | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. |  | HOLD |  | JUDY HODGE | Dan Lerman
BAS | 19P000224 | FS | SL5-PAINT EXTERIOR RAMP AT HUB MODULAR | PRINT MOD |  | 2018-08-28 | QUEUE TO START | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 3 |  | MIKE CLEMONS | Paul Ditty
BAS | 19P000227 | FS | SL5-DINING STORAGE ROOM CONVERSION | BANNOCK J | J0100 | 2018-08-17 | IN PROGRESS | [6 empty] | Scheduled work with trades anticipated completion December 2019. |  | 2 |  | DARCI LOMBARD | John Peraino
BAS | 19P000232 | FS | SL5-BANNOCKBURN J-104 BREAK ROOM UPGRADE | BANNOCK I | I0105 | 2018-09-04 | IN PROGRESS | [6 empty] | Scheduled work with trades anticipated completion December 2019. |  | 6 |  | RICHARD GEIGER | John Peraino
BAS | 19P000235 | FS | SL5-RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | ABER INVER | A0100 | 2018-09-04 | IN PROGRESS | [6 empty] | Customer to determine scope of work. |  | 11 |  | EDWIN MELGAR-MEJIA | John Peraino
BAS | 19P000236 | FS | SL5-EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION | ABER INVER | A0100 | 2018-09-04 | IN PROGRESS | [6 empty] | Scheduled work with trades anticipated completion December 2019. |  | 10 |  | EDWIN MELGAR-MEJIA | John Peraino
BAS | 19P000308 | FS | SL5-ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK | ABER INVER |  | 2018-09-11 | IN PROGRESS | [6 empty] | Scheduled work with trades anticipated completion December 2019. |  | 4 |  | EDWIN MELGAR-MEJIA | John Peraino
BCOE | 3224 | PD&C | Bourns - Door Access Control | BOURNS |  | 2016-11-14 | Programming | Create SOW and Transfer funds | 2019-09-01 | 2019-11-29 |  |  |  | Replace outdated failing, and unsupported Identicard card reader system with campus approved Hirsch system at all existing locations in Bourns Hall B-wing at a minimum; inclusion of card readers in Bourns A-wing is also desired if possible. Immediate work is optimal since the building is currently under construction and many walls, ceilings, wiring, etc are currently exposed. Work to be done via surplus funds from BCOE 950534. AVC is putting together the costs and scope via meetings with Maggie/ Pat/ and John C. | 4 |  |  | Margaret Souder | Fernando Nunez
BCOE | 3300 | PD&C | R'Garden - Solar Installation |  |  | 2017-05-03 | Work to be inspected by A&E. | To be disassembled in June 2019 |  | 2019-06-01 |  |  |  | Electrician to do the following wiring of our solar panels and inverters out at the R’Garden at UCR. The H model cyboinverter to be used powers the lower heating element of the water heater. The thermostat of the lower heating element must then be set to be higher than the upper heating element. The two output lines are to be connected to an AC switch or switchable AC outlet and the lower element water heater. | 2 |  |  | Arvin Tam | Scott Donnell
BCOE | 3315 | PD&C | Bourns B144 - Lab Safety Improvements | BOURNS |  | 2017-05-23 | Need to confirm Dept. funding commitment | Confirm Dept. Commitment/Funding | [5 empty] | Incorporate life safety improvements to research lab. Provide additional protection for Pyrophoric Gases. Provide sprinkler protection inside the pyrophoric gas cabinet. Provide an Automatic shutdown device for pyrophoric gas flow when activated by interlocks tied into fire sprinkler. Provide a remote manual shut down device of pyrophoric gas outside the gas cabinet. Provide audible and visible alarm detection and monitoring for toxic and highly flammable gases including diborane, germane, ammonia and hydrogen gases Applicable references on the above are NFPA 55 (Compressed Gases Code) and NFPA 45 (Standard on Fire Protection for Labs using Chemicals). | 5 |  |  | Jianlin Liu | Scott Donnell
BCOE | 3427 | PD&C | C-CERT Install Meter |  |  | 2018-03-21 | Additional funding added | Start Construction | 2019-02-04 | 2019-02-28 |  |  |  | Site: inland empire utility agency (IEUA) Meter install: Allen Bradley PowerMonitor 5000 price of meter is $7,410 Projected price of install: $15-20k Scope of work: Meter will be purchased by UCR for install at the main panel at the IEUA Carbon Canyon Facility. Once the meter is installed then it will be used to send Energy data back to their SCADA system and monitor and display real time data. | 3 |  |  | Todd Ambriz | Fernando Nunez
BCOE | 3428 | PD&C | MS&E Cleanroom Expansion | MAT SCI ENGR |  | 2018-04-04 | In Bidding | Approve Specifications | 2019-04-01 | 2019-07-31 |  |  |  | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | 6 |  |  | Margaret Souder | Dave Bomba
BCOE | 19P000028 | FS | SL5-BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS | BOURNS | A0169 | 2018-07-16 | IN PROGRESS | [6 empty] | Deferred to Winter Quarter |  | Deferred to Winter Quarter |  | ROBERT LOPEZ-A | Dan Lerman
BCOE | 19P000312 | FS | SL5-VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP | STUDENT SERV | 1227 | 2018-10-03 | QUEUE TO START | [8 empty] | 3 |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000322 | FS | SL5-CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT | CHUNG HALL | 103 | 2018-10-05 | QUEUE TO START | [8 empty] | 4 |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000424 | FS | SL5-CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET | CHUNG HALL | 445 | 2018-12-20 | QUEUE TO START | [8 empty] | 5 |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 19P000442 | FS | SL5- WINSTON CHUNG- PATCH/PAINT ROOM 319 | CHUNG HALL | 319 | 2019-01-09 | QUEUE TO START | [8 empty] | 2 |  | BILL BINGHAM | Paul Ditty
CAMPUS | 18P000121 | FS | SL5-PHYSICS HYDRATION STATION - PHYSICS HALL | PHYSICS | 0 | 2017-09-21 | HOLD - FACILITIES SERVICES | [6 empty] | Reviewing campus standards for these project requests. |  |  |  | JAZMIN CHAVEZ | Dan Lerman
CAMPUS | 18P000122 | FS | SL5-MS&E HYDRATION STATION - MS&E HALL | PHYSICS | 0 | 2017-09-21 | PROJECT INTAKE | [6 empty] | Reviewing campus standards for these project requests. |  |  |  | JAZMIN CHAVEZ | Dan Lerman
CAMPUS | 18P000435 | FS | SL5-HMSS HYDRATION STATION REQUEST | HUM & SOC SC | 3600 | 2018-05-10 | HOLD - FACILITIES SERVICES | [6 empty] | Pending Hydration station plan for campus |  |  |  | NELDA THOMAS | Dan Lerman
CAMPUS | 19P000212 | FS | SL5-REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | LIFE SCIENCE | CR2500A | 2018-08-24 | HOLD - FACILITIES SERVICES | [6 empty] | Reviewing campus standards for these project requests. |  |  |  | ESTELLA DAVALOS
CAP.PROG. | 2916 | PD&C | Solar Greenhouse |  |  | 2015-08-04 | Requires augmentation | Construction | 2019-03-01 | 2019-05-01 |  |  |  | Construction of a solar powered greenhouse. | 99 |  |  | Matt Barth | Scott Donnell
CAP.PROG. | 2952 | PD&C | Pierce Hall Interiors | PIERCE |  | 2015-09-11 | In Construction | Completion of phase one 12/7/19 | 2019-01-02 | 2021-04-01 |  |  |  | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | 19 |  |  | Jon Harvey | Dave Bomba
CAP.PROG. | 2970 | PD&C | ADA Improvements/Transition Plan - Phase 2 |  |  | 2015-12-02 | In Construction | Complete Construction | 2018-09-26 | 2019-06-30 |  |  |  | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) | 17 |  |  | Blythe Wilson | Dave Bomba
CAP.PROG. | 3005 | PD&C | Batchelor Hall Interior Improvements | BATCHELOR |  | 2016-02-02 | Conducting interviews of researchers to assess relocation needs | CM at Risk Selection | 2019-09-01 | 2021-11-01 |  |  |  | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | 14 |  |  | Sharyl Murdock | Rowan Reid
CAP.PROG. | 3119 | PD&C | Plant Growth Environment Facility |  |  | 2016-05-25 | Design Build Proposal Awarded, design and construction contract execution has started | Design-Build Proposal Evaluation | 2019-04-01 | 2020-08-01 |  |  |  | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. | 5 |  |  | Michelle Baniqued | Rowan Reid
CAP.PROG. | 3120 | PD&C | Arts Walk Sculpture (Ext Campus Art Project) |  |  | 2016-05-26 | A&E and CAS in discussions w/Artist re: design. | Complete Construction | 2019-03-01 | 2019-05-01 |  |  |  | Sculpture design concept - hiring a consultant to revise an artist design concept for a proposed outdoor art piece to be placed between the Arts building and the CHASS Interdisciplinary buildings. | 4 |  |  | Uma Ramasubramanian | Jason Espinoza
CAP.PROG. | 3175 | PD&C | DM-Chilled Water Coils Multiple Buildings |  |  | 2016-10-11 | In Construction | Complete Construction | 2019-01-01 | 2019-03-01 |  |  |  | Replace multiple leaking/degraded cooling coils across campus to prevent complete shutdown of building air handlers during the hot summer months. Buildings include: Student Services, Chemical Sciences, Genomics, Psychology, Entomology and MSE. | 99 |  |  | Melissa Garrety | Scott Donnell
CAP.PROG. | 3233 | PD&C | Mobility HUB Central Campus Linkages |  |  | 2016-12-16 | In bidding | Award Contract | 2019-04-01 | 2020-01-01 |  |  |  | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. | 1 |  |  | Jaime Enghbrecht | G. Caraig/J. Franklin
CAP.PROG. | 3234 | PD&C | UC Intellicenter 2nd Floor TI |  |  | 2016-12-21 | In Construction | Complete Construction | 2018-11-05 | 2019-03-29 |  |  |  | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. | 2 |  |  | John White | Fernando Nunez
CAP.PROG. | 3293 | PD&C | USDA Head House - Public Restroom | GERMPLASM |  | 2017-05-22 | Pending Lease | USDA Scope & Design | [5 empty] | Provide an accessible public restroom facility in or adjacent to the USDA Head House Building in Ag Ops. Restroom will serve individuals and groups touring the UCR and USDA Citrus Facilities. Three options have been proposed, and need to be considered and evaluated to recommend a feasible solution for USDA. The work would be managed and paid by USDA, including the design, bidding and construction. UCR staff needs to review the proposed plans and specifications per the agreement with USDA, and provide the review, inspection and approvals. The USDA representative is Marylou Polek. | 11 |  |  | Mary Lou Polek | Scott Donnell
CAP.PROG. | 3319 | PD&C | Student Success Center |  |  | 2017-06-01 | In Design Build competition. | Award Contract | 2019-09-01 | 2021-05-01 |  |  |  | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. | 13 |  |  | Michelle Baniqued | Mihai Gavan
CAP.PROG. | 3366 | PD&C | Genomics Sdwk Rpr-Drainage Impr |  |  | 2017-11-16 | In Funding | Secure Funding | 2019-04-01 | 2019-05-01 |  |  |  | Genomics Accessibility Improvements - The proposed project will create an accessible sidewalk connection from the Genomics Building to the University Lab and University Office Building. Currently, there is no accessible north sidewalk linkage east of the Genomics Building. The project will demolish and replace approximately 300 square feet of asphalt to bring it up to grade. Two ADA ramps will be added to sidewalk extensions of approximately 300 square feet that connect across a driveway. Existing landscaping and irrigation will be removed and replaced. No trees will be impacted by this work. | 16 |  |  | Jaime Engbrecht | Dave Bomba
CAP.PROG. | 3393 | PD&C | South Neighborhood Dist. Study |  |  | 2017-11-15 | In Close-out | Receive Study Reports | [5 empty] | South Neighborhood District Study per discussions with the Provost/VCPB, July 2017. The South District Planning Study needs to provide guidance for future development in the South District that is inclusive of: **University aspirations to develop the South District to define the campus’ presence along the adjacent freeway (CA-60/215). **Development capacity, optimal building heights and conceptual massing presented both in metrics and a three dimensional format. **Broad parking strategy to meet the needs of the district in alignment with the campus’ overall parking management strategy and alternative transportation solutions. **High level understanding of infrastructure needs (electrical, domestic, fire and storm water, sanitary sewer, building heating and cooling) to meet the needs of the campus’ desired development capacity for district. **Pedestrian and vehicular connectivity. **East and South Campus Drive improvements | 15 |  |  | Uma Ramasubramanian | Fernando Nunez
CAP.PROG. | 3395 | PD&C | Recreation Fields Replacement |  |  | 2017-12-03 | Third party cost estimator needed. | [6 empty] | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. | 20 |  |  | Tameesha Hayes | Daneca Stevens
CAP.PROG. | 3401 | PD&C | SOM Clinical Skills & Simulation Suite | ORBACH LIB |  | 2017-12-03 | P funding received on 2.20. Proceeding with design. | Complete SD/DD phase. | 2019-09-01 | 2020-12-01 |  |  |  | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | 18 |  |  | Mihai Gavan | Mihai Gavan
CAP.PROG. | 3438 | PD&C | Iowa Street Widening |  |  | 2018-08-22 | City to determine schedule | City to determine schedule | [5 empty] | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. | 21 |  |  | Dave Bomba | Dave Bomba
CAP.PROG. | 3452 | PD&C | Long Range Dev Plan - 2018 |  |  | 2018-07-16 | In Programming | Complete Programming | [5 empty] | New Long Range Development Plan (LRDP), with all required technical studies | 4 |  |  | Jacqueline Norman | Uma R.
CAP.PROG. | 3458 | PD&C | KUCR Replacement Project |  |  | 2018-07-16 | No update | Unknown | [5 empty] | Proposed replacement of KUCR radio station facility | 9 |  |  | Blythe Wilson | Blythe Wilson
CHANCELLOR | 18P000209 | FS | SL5-VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 | STUDENT SERV | 0 | 2017-11-30 | HOLD - FACILITIES SERVICES | [6 empty] | Customer provided estimate for project; verifying if funding is available to proceed with project. |  |  |  | ANGIE GRAY | Dan Lerman
CHANCELLOR | 18P000414 | FS | SL5-CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL | STUDENT SERV | 0 | 2018-04-26 | QUEUE TO START | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 1 |  | DANIELLE GARCIA | Paul Ditty
CHANCELLOR | 19P000407 | FS | SL5--HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 | HINDERAKER | 1101 | 2018-12-11 | QUEUE TO START | [8 empty] | 0 |  | ALEXIS RAMBAUD
CHASS | 3060 | PD&C | CHASS Intl N. - Paint 3rd Floor | CHASS INT N |  | 2016-05-20 | Project on Hold | On Hold | [5 empty] | Paint and patch the following CHASS INTN rooms to existing color: 3036 3038 3042 3046 3050 3049 3047 3033 3033B 3025 3021 3019 3015 3013 3011 3002 3008 3012 3014 3016 3018 3020 3022 Hallway outside of 3033 Hallway to main entrance to floor Hallway outside 3005 | 3 |  |  | Paul Richardson | Fernando Nunez
CHASS | 3280 | PD&C | Athletics Dance Bldg Repairs | ATH DANCE |  | 2017-05-31 | On-hold/Funding | Department Approval/Funding | [5 empty] | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | 2 |  |  | Paul Richardson | Fernando Nunez
CHASS | 3363 | PD&C | DM(17-19) CA Photo Museum HVAC | CA MUS PHOTO |  | 2017-08-23 | In Close-out | Complete Close-out | 2018-03-01 | 2019-02-01 |  |  |  | Replace current HVAC with new Temp/Humidity control system. The system must adhere to Museum standards of Temp 70 +-3 and humidity 50 +-5. THIS IS A CRITICAL REQUEST. We are currently not able to borrow work from other museums due to the inconsistent numbers we are experiencing with temperature and humidity. | 4 |  |  | Emily Papavero | Scott Donnell
CHASS | 3441 | PD&C | INTS 1121 Convert Classroom to Dance Room |  |  | 2018-06-22 | In Programming | Design | 2019-11-01 | 2019-12-01 |  |  |  | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use | 3 |  |  | Anna Finn | Daneca Stevens
CHASS | 3469 | PD&C | Carillon Repair & Maintenance | BELLTOWER |  | 2018-08-16 | In design | Inspection and design | [5 empty] | Design, fabrication and replacement of bell beams for bells 24, 26, 28, 30 and 32. Design, fabrication and installation of bracing to brace the 5 other bells beams that are cracking, and corrective maintenance on the clappers & head pieces-this would include complete removal, cleaning, reaming, bushing and lubricating before re-installing and clean and lubricate the transmission system as much as possible without complete disassembly to make the instrument easier to play. | 7 |  |  | Reasey Heang | Daneca Stevens
CHASS | 3482 | PD&C | Humanities 3rd Floor Install Sail Shades |  |  | 2018-10-10 | Pre-programming | Funding | [5 empty] | Shade sail installation of the patios on the third floor of Humanities Social Science. There are two patios, one on the 3600 wing and one on the 3400 wing. | 9 |  |  | Paul Richardson | Daneca Stevens
CHASS | 3514 | PD&C | HMNSS 1202 Window/Column Removal |  |  | 2019-02-27 | New | New | [9 empty] | Jennifer Morgan | ----
CHASS | 18P000126 | FS | SL5-HMSS ESTIMATE REMOVE WALL & CHANGE DOORS | HUM & SOC SC | 3611 | 2017-09-28 | PLAN DEVELOPMENT/CHECK | [6 empty] | Scope of work has been reviewed; determining how to complete project with trades. |  | 21 |  | DARA CERDA | Dan Lerman
CHASS | 18P000318 | FS | SL5-CHASS INT S FLAT SCREEN INSTALLATION | CHASS INT S |  | 2018-02-21 | IN PROGRESS | [6 empty] | Plans are being reviewed; work to be scheduled once plans are approved. |  |  |  | RYAN MARIANO | Dan Lerman
CHASS | 18P000343 | FS | SL5-UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER | THTR WKSH | 0400A | 2018-03-16 | QUEUE TO START | [6 empty] | Scope of work has been reviewed; determining how to complete project with trades. |  | 22 |  | PAUL RICHARDSON | Dan Lerman
CHASS | 18P000385 | FS | SL5-HMSS INSTALL TV IN CONFERENCE ROOM | HUM & SOC SC | 1001E | 2018-03-06 | IN PROGRESS | [6 empty] | Scope of work has been reviewed; determining how to complete project with trades. |  | 19 |  | JILL CANTONWINE | Dan Lerman
CHASS | 19P000056 | FS | SL5-HMSS CAPABILITY OF MOUNTING A TV | HUM & SOC SC | 1212 | 2017-10-03 | IN PROGRESS | [6 empty] | Scope of work has been reviewed; determining how to complete project with trades. |  |  |  | ALLISON ROGERS | Dan Lerman
CHASS | 19P000171 | FS | SL5-HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST | HUM & SOC SC | 1614 | 2018-08-09 | QUEUE TO START | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 16 |  | SHELLEE STEWART | Paul Ditty
CHASS | 19P000207 | FS | SL5-QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | OLMSTED |  | 2018-08-23 | QUEUE TO START | [6 empty] | FS to coordinate with client to scope the work. |  | 7 |  | TOYA ADAMS | Dan Lerman
CHASS | 19P000286 | FS | SL5-FACULTY OFFICES: TOUCH UP PAINT | HUM & SOC SC | 2005 | 2018-09-17 | QUEUE TO START | [8 empty] | 8 |  | JILL CANTONWINE | Paul Ditty
CHASS | 19P000300 | FS | SL5-HUM & SOC SC--URGENT: PAINT AND PATCH WALLS | HUM & SOC SC | 4403 | 2018-09-26 | QUEUE TO START | [8 empty] | 7 |  | ANDREA HERAZ | Paul Ditty
CHASS | 19P000306 | FS | SL5-HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 | CHASS INT N | 4017 | 2018-10-01 | QUEUE TO START | [8 empty] | 11 |  | RYAN MARIANO | Paul Ditty
CHASS | 19P000356 | FS | SL5-PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT | HUM & SOC SC | 4401 | 2018-10-24 | QUEUE TO START | [8 empty] | 3 |  | ALLISON ROGERS | Paul Ditty
CHASS | 19P000357 | FS | SL5-PATCH AND PAINT WALLS, TIME SENSITIVE | HUM & SOC SC | 1302 | 2018-10-25 | QUEUE TO START | [8 empty] | 5 |  | ALLISON ROGERS | Paul Ditty
CHASS | 19P000361 | FS | SL5-OLMSTED-PATCH & PAINT/REPLACE CARPET | OLMSTED |  | 2018-10-29 | QUEUE TO START | [8 empty] | 1 |  | TOYA ADAMS | Paul Ditty
CHASS | 19P000362 | FS | SL5-PATCH & PAINT/REPLACE CARPET (HALLWAY) | OLMSTED |  | 2018-10-29 | QUEUE TO START | [8 empty] | 2 |  | TOYA ADAMS | Paul Ditty
CHASS | 19P000371 | FS | SL5-URGENT PATCH AND PAINT IN CHAIR'S OFFICE | HUM & SOC SC | 1213 | 2018-11-05 | QUEUE TO START | [8 empty] | 4 |  | ALLISON ROGERS | Paul Ditty
CHASS | 19P000378 | FS | SL5-PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 | HUM & SOC SC | 1613 | 2018-11-13 | QUEUE TO START | [8 empty] | 10 |  | SHELLEE STEWART | Paul Ditty
CHASS | 19P000429 | FS | SL5--CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING | COLL BLDG SO | 103 | 2019-01-03 | QUEUE TO START | [8 empty] | 9 |  | RENEE DEGUIRE | Paul Ditty
CNAS | 2353 | PD&C | Natural Reserves-Sweeney Granite Mountain |  |  | 2015-11-23 | Construction has resumed at the remote granite mountain location in January 2019, with work focused on modifications to the Existing Allison Center Lab, and Staff Residence. Construction is expected to be completed in these buildings in March of 2019 | Complete Construction | 2019-01-14 | 2019-10-01 |  |  |  | This project will add structurally independent facilities for an administration building and researcher housing to provide meeting/office space and short term sleeping quarters. Additionally, the existing laboratory building and staff residence will be extensively renovated. High priority is focused on high insulation values, high wind resistance, rodent proofing, and pursue as much passive cooling and heating as possible with an eye toward low maintenance and high durability. Both new construction and renovation projects are to be sealed to prevent rodent intrusion. The new structures must withstand the harsh environment of extreme temperatures and very high winds. All site improvements shall be done with minimal disturbance to the desert environment. The overarching goal of the project is to provide a sustainable structure that respects its environment and is low maintenance while using best practice design standards. | 99 |  |  | Jim Andre, D. McWilliams | Rowan Reid
CNAS | 3218 | PD&C | Ag Ops - Demo Structures |  |  | 2016-10-19 | In construction Additional funding is not expected. | Complete Construction | 2018-07-01 | 2019-04-01 |  |  |  | Demolition of 15 structures, including hazardous materials cleanup, electrical reconnection of services as needed, UST removal as needed, relocation of ATT riser. | 99 |  |  | Deborah McWilliams | Scott Donnell
CNAS | 3228 | PD&C | Retrofit Screenhouse to Greenhouse | RUBIDOUX SCR |  | 2016-12-06 | In Design | Bidding | 2019-08-01 | 2019-12-01 |  |  |  | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. Location can be discussed with Greg Greer | 1 |  |  | Cheryl Gerry, D. McWilliams | Scott Donnell
CNAS | 3367 | PD&C | Field 16 Greenhouse Demo & Replacement |  |  | 2017-09-15 | In Construction | Complete Construction | 2019-01-30 | 2019-07-28 |  |  |  | Replace GH1 and GH2 with a greenhouse from the Greenhouse Megastore. Conduct geotechnical investigation, prepare drawings and conduct asbestos and lead sampling. | 2 |  |  | Sue Lee, D. McWilliams | Dave Bomba
CNAS | 3390 | PD&C | Field 11C-D CVC Screenhouse |  |  | 2018-01-08 | Conceptual Design | CEQA | 2019-12-01 | 2020-02-01 |  |  |  | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. | 3 |  |  | Tracey Kahn, D. McWilliams | Scott Donnell
CNAS | 1990b | PD&C | Natural Reserves-Boyd Deep Canyon-Road |  |  | 2018-06-22 | Finalized construction drawings are being reviewed | Finalize Design | 2019-10-01 | 2019-12-01 |  |  |  | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. | 99 |  |  | Chris Tracy, D. McWilliams | Rowan Reid
CNAS | 18P000099 | FS | SL5-EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 | GEOLOGY |  | 2017-09-08 | QUEUE TO START | [6 empty] | Plans will be developed and will be submitted for review and approval. |  | 26 |  | LAURIE GRAHAM | Dan Lerman
CNAS | 18P000269 | FS | SL5-BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED | BATCHELOR | 1123 | 2018-01-16 | QUEUE TO START | [6 empty] | FS to coordinate with client to scope the work. Customer contacted to schedule a site visit. |  | 12 |  | APRIL MEINZER | Dan Lerman
CNAS | 18P000347 | FS | SL5-GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) | GEOLOGY | 0 | 2018-03-18 | QUEUE TO START | [6 empty] | Scope reviewed by BZM; coordination by PM for work to be completed. |  | 31 |  | AMBER RHEMREV | Dan Lerman
CNAS | 18P000388 | FS | SL5-SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | SPIETH | 0317A | 2018-04-10 | IN PROGRESS | [6 empty] | Equipment has been disconnected; equipment to be removed upon availability of the teams. |  | 22 |  | ESTELLA DAVALOS | Dan Lerman
CNAS | 18P000453 | FS | SL5-DELFINO LAB-SOIL HOUSE MODIFICATION | DELFINO HHSE |  | 2018-05-25 | QUEUE TO START | [6 empty] | FS to coordinate with client to scope the work. |  | 17 |  | MATTHEW ULRICH | Dan Lerman
CNAS | 18P000486 | FS | SL5-PHYSICS 3027/3028 RENOVATION | PHYSICS | 3027 | 2018-06-28 | PLAN DEVELOPMENT/CHECK | [6 empty] | FS to coordinate with client to scope the work. |  | 24 |  | MAYELA CASTILLO | Dan Lerman
CNAS | 19P000006 | FS | SL5-MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 | MAT SCI ENGR | 310 | 2018-07-02 | IN PROGRESS | [6 empty] | FS to coordinate with client to scope the work. |  | 3 | YES | MAYELA CASTILLO | Dan Lerman
CNAS | 19P000031 | FS | SL5-BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) | BIOLOGICAL SCI | 3101 | 2018-07-16 | QUEUE TO START | [6 empty] | FS to coordinate with client to scope the work. |  | 40 |  | ESTELLA DAVALOS | Dan Lerman
CNAS | 19P000055 | FS | SL5-CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM | COLL BLDG SO | 207 | 2018-05-18 | QUEUE TO START | [6 empty] | Scope reviewed by BZM; coordination by PM for work to be completed. |  | 32 |  | LISA DUNMORE | Dan Lerman
CNAS | 19P000106 | FS | SL5-PHYICS 1134 - UTILITIES REQUEST | PHYSICS | 1134 | 2018-08-01 | QUEUE TO START | [6 empty] | FS to coordinate with client to scope the work. |  | 15 |  | MAYELA CASTILLO | Dan Lerman
CNAS | 19P000133 | FS | SL5-PATCH HOLES AND PAINT | BATCHELOR | 2203 | 2018-08-07 | QUEUE TO START | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 43 |  | MATTHEW ULRICH | Paul Ditty
CNAS | 19P000137 | FS | SL-5 -LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM | LIFE SCIENCE | 2545 | 2018-08-08 | QUEUE TO START | [8 empty] | 12 |  | ESTELLA DAVALOS | Paul Ditty
CNAS | 19P000174 | FS | SL5-BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT | BATCHELOR | 2112 | 2018-07-24 | QUEUE TO START | [6 empty] | Scope reviewed by BZM; coordination by PM for work to be completed. |  | 37 |  | AMY RICKS | Dan Lerman
CNAS | 19P000184 | FS | SL5-REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES | GEOLOGY | 1270 | 2018-08-14 | IN PROGRESS | [6 empty] | FS to coordinate with client to scope the work. |  | 45 |  | LAURIE GRAHAM | Dan Lerman
CNAS | 19P000193 | FS | SL5-GENOMICS 2221 - FOB ACCESS SYSTEM INSTALLATION | GENOMICS | 2221 | 2018-08-20 | HOLD - FACILITIES SERVICES | [6 empty] | FS to coordinate with client to scope the work. |  | 41 |  | AIMEE GONZALES | Dan Lerman
CNAS | 19P000197 | FS | SL5-PATCH AND PAINT OFFICE, LOBBY AND HALL | COLLEGE BLDG NO | 0203B | 2018-08-21 | QUEUE TO START | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 44 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000210 | FS | SL5-CHEMICAL SCI Install Door In Doorway | CHEMICAL SCI | 0225A | 2018-08-24 | QUEUE TO START | [6 empty] | FS to coordinate with client to scope the work. |  | 25 |  | BARBARA OUTZEN
CNAS | 19P000243 | FS | SL5-GENOMICS 1206 - PATCH AND PAINT WALLS | GENOMICS | 1206 | 2018-09-06 | QUEUE TO START | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 49 |  | AIMEE GONZALES | Paul Ditty
CNAS | 19P000283 | FS | SL5-HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | CHUNG HALL | ROOF | 2018-09-05 | QUEUE TO START | [6 empty] | FS to coordinate with client to scope the work. |  | 20 |  | DEBORAH MCWILLIAMS
CNAS | 19P000285 | FS | SL5-PAINT AND PATCH PI OFFICE | ENTOMOLOGY | 269 | 2018-09-17 | QUEUE TO START | [8 empty] | 5 |  | WILLIAM SUTTON | Paul Ditty
CNAS | 19P000288 | FS | SL5-COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS | COLLEGE BLDG NO | 202 | 2018-09-19 | QUEUE TO START | [8 empty] | 9 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000292 | FS | SL5-GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER | GEOLOGY |  | 2018-08-10 | IN PROGRESS | [6 empty] | Site vist completed; identifying a feasabile site location for work. |  | 18 |  | AMBER RHEMREV | Dan Lerman
CNAS | 19P000298 | FS | SL5-SPIETH - PREP LAB FOR FACULTY SEARCH | SPIETH | 1363 | 2018-09-26 | IN PROGRESS | [8 empty] | 0 |  | ESTELLA DAVALOS
CNAS | 19P000347 | FS | SL5-SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT | SPIETH | 3320 | 2018-10-16 | QUEUE TO START | [8 empty] | 10 |  | ESTELLA DAVALOS | Paul Ditty
CNAS | 19P000358 | FS | SL5-GEOLOGY - ACCOMMODATION REQUEST | GEOLOGY |  | 2018-10-26 | PLAN DEVELOPMENT/CHECK | [8 empty] | 0 |  | RONDA INZUNZA
CNAS | 19P000360 | FS | SL5-GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING | GEOLOGY | 1444 | 2018-10-29 | QUEUE TO START | [8 empty] | 7 |  | KAREN CATO | Paul Ditty
CNAS | 19P000367 | FS | SL5-SCILAB 1 0211- PATCH & PAINT | SCIENCE LAB1 | 211 | 2018-10-31 | QUEUE TO START | [8 empty] | 11 |  | DEBORAH TERAO | Paul Ditty
CNAS | 19P000369 | FS | SL5-PIERCE - PAINT IS PEELING OFF WALLS | PIERCE | 3341 | 2018-11-01 | QUEUE TO START | [8 empty] | 8 |  | MATTHEW ULRICH | Paul Ditty
CNAS | 19P000390 | FS | SL5-BOYCE ROOM 5494 DOOR ENCLOSURE | BOYCE | 5494 | 2018-11-29 | QUEUE TO START | [8 empty] | 0 | YES | APRIL MEINZER
CNAS | 19P000440 | FS | SL5--GH#21--INSTALLATION OF GROW POD BEHIND GREENHOUSE #21 | GH21 |  | 2019-01-08 | IN PROGRESS | [6 empty] | Provide water and power hookup with appropriate plans and permits for installation of 40' Grow Pod behind Greenhouse #21. Please prioritize for Winter 2019. Permit needed as soon as possible, as we need the container to be installed and functional before construction of new Greenhouse facility begins. |  | 0 |  | April Meinzer | Dan Lerman
CNAS | 19P000449 | FS | SL5-PAINT OFFICE AREA OF 229A FOR RELOCATION | FAWCETT LAB | 229A | 2019-01-14 | QUEUE TO START | [6 empty] | Paint and patch area 229A Fawcett to prepare for lab group relocation. The room is currently empty. The lab group plans to relocate by Spring Break 2019. |  | 0 |  | Cheryl Gerry | Paul Ditty
CNAS | 19P000505 | FS | SL5--CHAPMAN HALL PAINT OFFICE WALL WHERE BOOK CASE WAS REMOVED | CHAPMAN | 10B | 2019-02-25 | QUEUE TO START | [6 empty] | Please paint the new PI's office wall where an old book case was painted around and now is removed. |  | 0 |  | William Sutton | Paul Ditty
CNAS | 19W007474 | FS | SL5-BG - RAILROAD TIE WALLS | BOTANIC GARDENS |  | 2018-11-07 | PROJECT INTAKE | [10 empty] | AMBER RHEMREV
CNAS | 1900a | PD&C | Natural Reserves-Boyd Deep Canyon |  |  | 2015-10-09 | Finalized construction drawings are being reviewed by the campus building official and firemarshal | Start Construction | 2019-05-01 | 2019-11-16 |  |  |  | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. | 99 |  |  | Chris Tracy, D. McWilliams | Rowan Reid
FAC-PLNG-DESIGN-CONST | 2671 | PD&C | DM-Elevator Modifications - Various Buildings |  |  | 2016-01-05 | Permit review process | Final Approval of CD's | 2019-07-01 | 2019-12-31 |  |  |  | Provide Vertical Transportation Consulting, Mechanical, Electrical, Fire Alarm and Architectural/Structural Construction document design and specifications for the modernization of two (2) elevators at Webber and Watkins buildings which is included in the base design and one (1) elevator at the Entomology Museum is included as an add alternate. | 99 |  |  | Scott Donnell | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 2682 | PD&C | DM-Rivera Library Arches/Arcade Repair |  |  | 2016-05-06 | Bidding | Award Contract | 2019-05-01 | 2019-07-30 |  |  |  | Paint and replace roof. | 99 |  |  | Susan Marshburn | Jason Espinoza
FAC-PLNG-DESIGN-CONST | 2687 | PD&C | DM-Bourns Hall Fire Alarm System Replacement | BOURNS |  |  | Approval of 100% CD's | Augmentation Approval | 2019-09-02 | 2019-12-31 |  |  |  | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | 99 |  |  | ----- | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3064 | PD&C | DM(FY17) Botanic Gardens Basin Silt Removal | BOTAN INFO C |  | 2016-04-20 | In Design | Waiting for basin to dry out | 2019-07-01 | 2019-07-01 |  |  |  | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | 44 |  |  | Toshio Ishida | Dave Bomba
FAC-PLNG-DESIGN-CONST | 3255 | PD&C | DM(FY17) Humanities - Upgrade EMS | HUMANITIES |  | 2017-02-10 | In Close-out | Complete Close-out | 2018-10-01 | 2019-01-01 |  |  |  | Humanities HVAC - upgrade Energy Management System per approved Century Bond funded project (approval attached). Project: 957405 P5498 Budget $200,000 Accounting determined this is capitalizable Accounting determined not capitalizable | 6 |  |  | Fernando Nunez | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3270 | PD&C | DM(FY17) - Chapman Hall - Replace HVAC System | CHAPMAN |  | 2017-03-07 | In Design | Bidding | 2019-07-01 | 2019-08-01 |  |  |  | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | 8 |  |  | Fernando Nunez | Scott Donnell
FAC-PLNG-DESIGN-CONST | 3271 | PD&C | DM(FY17) - Life Sci/Spieth Hall Elevator Renewal |  |  | 2017-03-07 | In Design | Final Approval of CD's | 2019-07-01 | 2019-12-31 |  |  |  | Scope of work includes the number 3 and 4 elevators of Spieth Hall. Project budget is $344,898.00. Estimated construction cost is $250,400.00. | 9 |  |  | Scott Donnell | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3272 | PD&C | DM(FY17) - Athletic/Dance elevator renewal | ATH DANCE |  | 2017-03-07 | In Design | Final Approval of CD's | 2019-07-01 | 2019-12-31 |  |  |  | Project budget is $219,371.00. Estimated construction cost is $169,020.00. | 10 |  |  | Scott Donnell | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3275 | PD&C | DM-Fiber Optic Infrastructure Upgrade |  |  | 2017-04-12 | Going into bidding | Award Contract | 2019-06-01 | 2019-12-01 |  |  |  | Repair, replace and upgrade the fiber optic infrastructure network that includes 50+ buildings across campus. Also includes work to main hubs, sub hubs and make available spare fiber for future utilization. | 2 |  |  | ----- | Daneca Stevens
FAC-PLNG-DESIGN-CONST | 3437 | PD&C | UCPD Generator Replacement |  |  | 2018-10-08 | In Design | Receive 100% CD's | 2019-07-01 | 2019-08-30 |  |  |  | Replace unsupported 125kw generator with new - Critical Facility | 3 |  |  | Ron Rector | Fernando Nunez
FAC-PLNG-DESIGN-CONST | 3476 | PD&C | DM17-19 Tunnel System Plumbing |  |  | 2018-10-17 | Reviewing final reports | Complete Final Report | [5 empty] | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. | 1 |  |  | Mihai Gavan | Mihai Gavan
FAC-PLNG-DESIGN-CONST | 3498 | PD&C | DM(FY18) HUB New Sewer Lines |  |  | 2019-02-25 | New | [6 empty] | Construct new sanitary sewer lines, New manhole, pipe connections, demo existing manhole. |  |  |  | Ron Rector | Gerald Caraig
FAC-PLNG-DESIGN-CONST | 3035a | PD&C | DM-Roofing - Spieth Hall/LSP |  |  | 2016-02-25 | In design | Re-bid | 2019-08-01 | 2019-10-01 |  |  |  | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. | 7 |  |  | John White | Scott Donnell
FAC-PLNG-DESIGN-CONST | 3035b | PD&C | DM-Roofing - Olmstead Hall |  |  | 2016-02-25 | In design | Re-bid | 2019-08-01 | 2019-10-01 |  |  |  | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. 112010 project budget is $456,163.00. Estimated construction cost is $425,680.00. Bidding 8/8/2017. | 7 |  |  | John White | Scott Donnell
GRAD.DIV | 19P000399 | FS | SL5-NEW CARPET + WALL PAINT | UNIV OFC BLD | 100 | 2018-12-06 | QUEUE TO START | [8 empty] | 2 |  | CYNTHIA CARDENAS | Paul Ditty
GRAD.DIV | 19P000411 | FS | SL5- PAINT, CARPET AND BLINDS | UNIV OFC BLD | 150 | 2018-12-14 | QUEUE TO START | [8 empty] | 1 | YES | CYNTHIA CARDENAS | Paul Ditty
GSOE | 19P000217 | FS | SL5-PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 | SPROUL | 1359 | 2018-08-27 | IN PROGRESS | [6 empty] | FS to coordinate with client to scope work. |  | 3 |  | KAREN NAPLES | Dan Lerman
GSOE | 19P000229 | FS | SL5-RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR | SPROUL |  | 2018-08-29 | QUEUE TO START | [6 empty] | FS to coordinate with client to scope work. |  | 4 |  | KAREN NAPLES
GSOE | 19P000237 | FS | SL5-PATCH AND PAINT OFFICE - SPROUL 1206 | SPROUL | 1206 | 2018-09-05 | IN PROGRESS | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 2 |  | KAREN NAPLES | Dan Lerman
ITS | 3396 | PD&C | C&C Rear Patio Tables/Shade | ITS CENTER |  | 2017-11-16 | In Programming | Complete Project Study | [5 empty] | Installation of new exterior concrete slab and patio cover at the Computing and Communications Modular Buildings. The existing site will be cleared of all landscape to provide clear area to install concrete slab and address any grade/drainage issues. The addition of a proposed permanent patio cover is to be installed with full electrical options (lights, outlets, ceiling fans) to provide shade for future events and exterior lunch area. Shrubs along the street at the East side of the area are to be removed to provide a vendor/service ramp for events with the inclusion of lighted concrete seating within the space. | 99 |  |  | Sheila Mabee | Fernando Nunez
ITS | 18P000474 | FS | SL5-MS&E ELECTRICAL MODIFICATIONS FOR ITS | MAT SCI ENGR | 119 | 2018-06-13 | IN PROGRESS | [6 empty] | Electrian to complete the work as available. |  |  |  | MICHAEL CAPRIOTTI | Robert Corey
ITS | 18W007453 | FS | SL5-(P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. | ITS CENTER | 100 | 2017-11-30 | PLAN DEVELOPMENT/CHECK | [10 empty] | SHEILA MABEE
ITS | 19P000021 | FS | SL5-ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS | ITS CENTER |  | 2018-07-12 | QUEUE TO START | [6 empty] | FS to coordinate with customer to scope the work. |  | 4 |  | SHEILA MABEE | Dan Lerman
LIBR | 3413 | PD&C | Rivera Libr Gender Incl Restroom | RIVERA LIB |  | 2018-03-26 | Need design | Code and policy compliance | [5 empty] | Convert existing non-ADA multi-stall women's restroom to compliant ADA gender inclusive restroom. The project also involves the conversion of an existing non-ADA men's restroom to women's compliant ADA restroom. | 3 |  |  | David Schuster | Dave Bomba
LIBR | 3481 | PD&C | Riv/Orb Libraries Fire Suppression-Estimate |  |  | 2018-11-27 | Client approval/funding | Client approval/funding | [5 empty] | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. | 1 |  |  | David Schuster | John Franklin
LIBR | 3496 | PD&C | Rivera Library Install Gate |  |  | 2019-01-08 | In Design | Customer Approval/Funding | [5 empty] | Rivera library gate installation | 3 |  |  | Rebeccah Goldware | Dave Bomba
PALM DESERT GRAD CTR | 2747 | PD&C | Heckmann Center - Landscaping (Donor Orchard) | HECKMAN ICEM |  | 2014-08-18 | In Programming | RFQ Design | [5 empty] | UCR Palm Desert would like to replace the current turf grass with water-wise, sustainable landscaping. In return for the opportunity to use a “living laboratory” classroom for training, UC Cooperative Extension Master Gardener program has agreed to collaborate with UCR to revise and sustain the landscaping. The first phase will be to create an orchard to highlight UCR’s contributions to agricultural research in the Coachella Valley. The orchard will be located at the entrance to the Heckmann building, north of the walkway. UCR Physical Plant/Grounds to provide estimate for: • Project oversight • Project plan and drawings • Organic material to add to soil • Irrigation materials and installation • Edging for path • Weed cloth • Decomposed granite with stabilizer for ground cover • Decomposed granite with stabilizer for pathway • Concrete pad for art including bolting apparatus • Arbor for grapes • Flow system-fertigation • All other labor and materials other than kiosk, plant signage, turf and tree removal (current landscape maintenance vendor can remove) and plant materials and plant installation | 2 |  |  | Mike Lawrence | Scott Donnell
PALM DESERT GRAD CTR | 3104 | PD&C | Palm Desert Campus Access Evaluation | HECKMANN PH2 |  | 2016-05-12 | In Programming | Design | 2019-10-01 | 2019-11-01 |  |  |  | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | 1 |  |  | Zelda Glenn | Scott Donnell
PLANNING & BUDGET | 2368 | PD&C | Creekside Drainage Channel |  |  | 2016-05-19 | On hold | Project path determined by RE | [5 empty] | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. | 11 |  |  | Katie Sanchez | Dave Bomba
PLANNING & BUDGET | 2774 | PD&C | Highlander Hall Demolition |  |  | 2015-01-22 | Nearing Completion | Project Close-out | 2018-08-01 | 2019-04-01 |  |  |  | Demolition of the Highlander Hall Building | 99 |  |  | Blythe Wilson | Scott Donnell
PLANNING & BUDGET | 2839 | PD&C | Multidisciplinary Research Building |  |  | 2015-04-01 | Certificate of Beneficial Occupancy 9.28 L1-L4. Construction ongoing on the Lower Level. | Substantial Completion | 2016-07-01 | 2018-09-28 |  |  |  | External financing provided for this project. Total approved budget is $150,000,000. Confirmed per CPMX and BEA#978864 Xfer Tax Exemp Comm Paper. Funding received 7/25/2016. | 8 |  |  | Jon Harvey | Mihai Gavan
PLANNING & BUDGET | 2899 | PD&C | Pierce Hall Improvements | PIERCE |  | 2015-08-06 | In Construction | Abatement | 2019-01-01 | 2019-12-07 |  |  |  | Replacement of Mechanical, Plumbing and Electrical Infrastructure | 10 |  |  | Jon Harvey | Dave Bomba
PLANNING & BUDGET | 2900 | PD&C | Batchelor Hall Systems Renewal | BATCHELOR |  | 2015-12-15 | Conducting interviews of researchers to assess relocation needs | CM at Risk Selection | 2019-09-01 | 2021-11-01 |  |  |  | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | 6 |  |  | Sharyl Murdock | Rowan Reid
PLANNING & BUDGET | 3110 | PD&C | Ag Ops Cell Tower - New |  |  |  | Project is not funded/never routed to the Dispatcher. 90% CD's completed. | License Agreement Final Review |  | 2019-07-01 |  |  |  | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. | 99 |  |  | Marianne Valenti | Yvonne Lujan
PLANNING & BUDGET | 3195 | PD&C | North District Development, Phase-1 |  |  | 2016-10-26 | Phase 1 - Student Housing - 8/1/2020. | Reg. Apprv'l-Business Terms&Fin. | 2019-07-01 | 2021-08-01 |  |  |  | Development of UCR North District Development, located near the housing development north of Linden St. | 99 |  |  | Raoula Amescua | R.Amescua/D.Hecht
PLANNING & BUDGET | 3470 | PD&C | 2018 Campus Seismic Audit |  |  | 2018-11-06 | New Study | Complete Review | [5 empty] | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. | 12 |  |  | Drew Hecht | Drew Hecht
PLANNING & BUDGET | 3474 | PD&C | RUSD STEM High School |  |  | 2018-10-31 | Real Estate project | Regents Approval of Ground Lease | 2019-07-01 | 2022-09-01 |  |  |  |  | 5 |  |  | ----- | Raoul Amescua
PLANNING & BUDGET | 3484 | PD&C | 266 Frost Ct Main House Demolition |  |  | 2018-11-15 | Bidding | Bidding | 2019-05-01 | 2019-05-01 |  |  |  | Develop project budget and timeline, obtain funding from VCPB. Coordinate disconnection of all utilities: Electrical, Gas, and Water. Disconnect and cap sewer Coordinate HAZ Mat testing and report for asbestos and lead Hire abatement contractor (if necessary) to remove haz materials. Hire demolition contractor to demolish and dispose of existing house, garage and out buildings. Foundations to remain – but make safe and remove potential hazards (rebar, bolts, etc.) protruding from foundation. Paving, pavers and other “patio” slabs to remain – make safe by removing tripping hazards. Identify any hazards (I.E.; unstable retaining walls, debris piles, etc.) and make safe and secure or remove if more cost effective. | 7 |  |  | Scott Donnell | Daneca Stevens
PLANNING & BUDGET | 3499 | PD&C | Creekside Terrace Analysis |  |  | 2019-02-14 | New | New | [5 empty] | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. | 2 |  |  | Blythe Wilson | Dave Bomba
PLANNING & BUDGET | 3504 | PD&C | Silver Oaks Womens Health TI Fees |  |  | 2019-02-14 | New | New | [5 empty] | UCR Health will be acquiring new off-campus leased space by expanding into an adjacent medical office suite located at 19330 Jesse Ln #160, Riverside, CA 92508. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. | 1 |  |  | Brandon Barbosa | Blythe Wilson
PLANNING & BUDGET | 3505 | PD&C | Orange County Psychiatry |  |  | 2019-02-19 | New | New | [5 empty] | UCR Health will be acquiring new off-campus leased space by moving into an adjacent medical office suite located at The Airport Tower, 18881 Von Karman Ave #1227, Irvine, CA 92612. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. | 3 |  |  | Brandon Barbosa | Blythe Wilson
PLANNING & BUDGET | 17P000254 | FS | SL5-FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS | CORP PP WHSE | 0106B | 2017-06-07 | HOLD - FACILITIES SERVICES | [6 empty] | Project in progress; ITS installing data. |  |  |  | DALAN DINH | Dan Lerman
PLANNING & BUDGET | 19P000209 | FS | SL5-OLD EH&S SITE- FS ANNEX A REMODEL | ENV H AND S | 100 | 2018-08-24 | IN PROGRESS | [6 empty] | Scope of work has been reviewed and being scheduled for completion. |  |  |  | FRANCES RAVE | Craig/Chris Pillen
PLANNING & BUDGET | 19P000425 | FS | SL5-PAINT VIDEO PRODUCTION SUITE & HANG ITEMS | HINDERAKER | 1159A | 2018-12-20 | QUEUE TO START | [8 empty] | 3 |  | LISA CUSICK | Paul Ditty
PROVOST/EVC | 19P000386 | FS | SL5-ROOM CHANGES | STUDENT SERV | 3106A | 2018-11-20 | IN PROGRESS | [8 empty] | 0 |  | STEPHANIE ARCINIEGA
SoB | 2725 | PD&C | School of Business Professional Schools Study |  |  | 2016-12-15 | Initial planning discussions have begun with SOBA. | Develop RFQ | [5 empty] | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. | 2 |  |  | Leo Gonzalez | Blythe Wilson
SoB | 3101 | PD&C | DM-Anderson Hall S&N - Maint+Restrm Remodel |  |  | 2016-05-09 | Need confirmation department wishes to cancel | To be cancelled by Client | [5 empty] | Under 2014 Deferred Maintenance Funding Program, SoBA has been approved for interior upgrades to be completed up to $65,00. We were originally approved for $75,000 however, per Scott Donnell, $10,000 had already been used. We have requested a list of expenditures for SoBA upgrades under this $10,000. The following items need to be completed under this 2014DM funding in the priorities listed: 1. Anderson Hall South Women’s and Men’s Restrooms Remodel Requirements: Floor and wainscot tile require replacement and/or re-grouting, casework and associated lavatory fixtures and counter tops require refurbishment/placement, restroom partitions require re-painting/replacement. 2. Anderson Hall North Women’s and Men’s Restrooms – repair and touch up areas where ADA compliance changes were made. 3. Anderson Hall North & South Stairway Requirements: All stairways shall be reviewed for compliant contrasting top and bottom stair-tread indicators and all missing or loose anti-slip tread applications be repaired and/or replaced. Any other safety items as may be noted. Retile or carpet as needed. 4. Anderson Hall South Interior Painting to Common areas, both levels: Interior wall surfaces require patching and painting. 5. Anderson Hall North Interior Painting to Common areas, both levels and conference room 021: Interior wall surfaces require patching and painting. 6. Faculty Suite (Rm 158) – match common area tile (size of mud/dirt mat) to replace dirty carpet when first enter room 158. 7. Dean’s Suite (Rm 162) – new carpet. | 3 |  |  | Angela Chang | Dave Bomba
SoB | 3237 | PD&C | Anderson Hall N. Access Imp. | ANDERSON 1 |  | 2016-12-19 | In Bidding | Award Contract | 2019-04-01 | 2019-05-01 |  |  |  | ADA handrails installation at walkway and ramp on the East sidewalk by the bench of Anderson north, down the steep ramp leading to Anderson South. We have been working with Shelly Frohrip from HR and Mary-Alice Avila of A&E on this so they will have some information regarding the purpose. 11/15/17 The handicapped parking and POT are now included. Project approved, waiting for funding. | 5 |  |  | Angela Chang | Dave Bomba
SoB | 3341 | PD&C | Anderson N & S - Exterior Painting |  |  | 2017-07-18 | Need confirmation department wishes to cancel | To be canceled by Client | [5 empty] | EXTERIOR PAINTING: Please see Karen Henry or Tim DeBolt for direction in painting exterior items around Anderson Hall North/South as follows: 1. Update Paint on exterior Window trim of both buildings. 2. Update Paint on lanterns and light poles 3. Fix plaster on building walls that is peeling off. | 1 |  |  | Angela Chang | Dave Bomba
SoB | 3345 | PD&C | Anderson N & S - Landscaping |  |  | 2017-07-18 | On hold until ADA path of travel is completed | Completion of 3237 | 2019-07-01 | 2019-07-01 |  |  |  | DESIGN SVC & LANDSCAPE Construction request as follows for updated CURB APPEAL of Anderson North/South: 1. Roses Garden in middle of Stair landing/court to be removed and replaced with Grass 2. Add Large Planters (Metal or Cement) with Citrus Trees (either Kumquat/Lemon/Orange/Etc) on ledges that are at top section of front steps to deter skateboarders from jumping off of these ledges. 3. Remove dead trees on North and south ends of front lawn 4. Remove plants around granite sign in front lawn and replace with grass 5. Remove flowers and grass at both corners of front lawn around Citrus Trees and replace with DG and low growing flowering plants. 6. Pull all Ivy and crown vetch and add Pavers to East/Back side of Anderson Hall within landscaped/planter areas where ADA walkway runs and replace with nice picnic tables to include umbrellas and/or lounge seating around Anderson North for students. 7. Add DG in all areas where space is open/available surrounding outdoor seating area in back of building. 7. Remove all hedges surrounding alcove/arched areas along buildings. | 6 |  |  | Angela Chang | Dave Bomba
SoB | 3415 | PD&C | Anderson South Renovation | ANDERSON 2 |  | 2018-02-26 | In Funding | Complete Plan Check | 2019-05-01 | 2019-07-01 |  |  |  | Per the sketched drawings that Dave Bomba was provided, please provide a proposal of what it would take to renovate Anderson South as follows: **1. Remove 1st Fl South side of Corridor wall and doors between 102 suite entrance and 106 suite entrance as well as adjoining walls within 102C. **2. Create a closet/wall, ideally, behind the existing door of the 102 Entrance running to the wall shared by 102A to include the best location for a door. Essentially, enclosing the window of 102, if possible. **3. Creating a closet under the stairwell between 1st floor and basement level, having entrance door flush with the bottom step of the stairwell. **4. Remove the West wall and door framing of room 001A, leaving an open look and no corridor in suite 001. | 4 |  |  | Laurie Gustafson | Dave Bomba
SoB | 18P000351 | FS | SL5-REMOVE/REPOSITION PROJECTION SYSTEM-021 | ANDERSON 2 | 21 | 2018-03-19 | HOLD - FACILITIES SERVICES | [6 empty] | Carpentry work is in progress; electrical work to be scheduled followed by paint. |  |  |  | ANGELA CHANG | Dan Lerman
SoB | 19P000353 | FS | SL5-OLMSTED PATCH/PAINT-2348 | OLMSTED | 2340 | 2018-10-19 | QUEUE TO START | [8 empty] | 3 |  | ANGELA CHANG | Paul Ditty
SOM | 2359 | PD&C | SOM - Research Bldg. BSL-3 |  |  | 2013-07-03 | Finalizing commissioning & air balance | Notice of Completion | 2016-10-01 | 2017-11-01 |  |  |  | Reconfiguration and reconstruction of the existing BSL-3 suite on the 3rd floor. | 1 |  |  | Rebeccah Goldware | Mihai Gavan
SOM | 2974 | PD&C | SOM Research Building - 1st Floor Fit-Out |  |  | 2015-10-30 | Close-out documents | Final Completion / NOC | 2017-10-01 | 2018-10-01 |  |  |  | Buildout the 1st Floor of School of Medicine Research Building, a space of approximately 17,600 square feet. The construction includes wet laboratories, laboratory support spaces, offices and related support space. Work consists of, but not limited to the following: demolition of existing improvements, addition/alterations of walls, installation of new fume hoods, sinks, safety showers and eyewash stations, alterations/additions to the mechanical, electrical, plumbing, fire life safety, fire suppression, telecommunication and audio/video systems, as specified in the Construction Documents. | 99 |  |  | Blythe Wilson | Mihai Gavan
SOM | 3052 | PD&C | SOM Trailer Expansion |  |  | 2016-03-07 | Completing Change Orders | Complete Change Orders | 2017-08-01 | 2018-02-01 |  |  |  | Replace the (2) modular units with one 96' x 60' building and provide access from the SOM-ED building via concrete ramp; Re-vamp the entire site for accessibility. Signed Major Cap Approval for $150k augmentation received 10/25/17 - total project $2,250,000. | 99 |  |  | Sharyl Murdock | Dave Bomba
SOM | 18P000400 | FS | SL5-Covert suite 1116 and suite 1126 to office space | WEBBER | 1116 & 1126 | 2018-04-14 | HOLD - FACILITIES SERVICES | [6 empty] | Provost has placed a hold on converting lab spaces into office spaces. |  | HOLD |  | BRANDON BARBOSA | Dan Lerman
SOM | 19P000032 | FS | SL5-Reconfigure recepetion desk to fit two FTEs. | SOM EDUC | 2608 | 2018-07-17 | IN PROGRESS | [6 empty] | Scope of work has been identified and walked with Ron V & Brandon B. |  | 5 |  | BRANDON BARBOSA | Dan Lerman
SOM | 19P000245 | FS | SL5-ADA COMPLIANT - AUTOMATIC DOOR ENTRY | SOM RSCH |  | 2018-09-07 | QUEUE TO START | [6 empty] | FS to coordinate with client to scope the work. |  | 4 |  | DEBORAH TRUJILLO
SOM | 19P000354 | FS | SL5-WEBBER 2130A-PAINT CHERI'S NEW OFFICE | WEBBER | 2130A | 2018-10-19 | QUEUE TO START | [8 empty] | 1 |  | DOMINIC SALAZAR | Paul Ditty
SOM | 19P000410 | FS | SL5-PAINT OFFICES AT UC PATH | INTELLICTR |  | 2018-12-14 | QUEUE TO START | [8 empty] | 2 |  | DEBORAH TRUJILLO | Paul Ditty
SPP | 19P000458 | FS | SL5-CHASS INTS-BUILD PERM DRYWALL DIVIDER OR APPROVE BKM AIRWALL | CHASS INT S | 4146 | 2019-01-19 | PLAN DEVELOPMENT/CHECK | [6 empty] | The primary request of this order is to facilitate and route a formal request to either build a permanent soundproof drywall room divider (floor to soffit or floor to ceiling) with associated modification/alterations to HVAC, Fire Sprinkler System, with appropriate building approvals to accommodate two private huddle spaces with entry/exit doors to be used for student advising. |  | 0 |  | Luis Alvarez | Dan Lerman
VC-RED | 3326 | PD&C | Genomics 1120A - Power & UPS | GENOMICS |  | 2017-06-13 | In Design | Approval of HVAC design | 2019-07-01 | 2019-07-01 |  |  |  | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | 3 |  |  | T.Girke, L.Manor, D.McWilliams | Dave Bomba
VC-RED | 19P000181 | FS | SL5-PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS | UNIV OFC BLD | 249 | 2018-08-14 | QUEUE TO START | [6 empty] | FS to coordinate with client to schedule work for completion. |  | 4 |  | GLORIA GALLEGO | Paul Ditty
VC-RED | 19P000225 | FS | SL5-UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | UV BLDG A | 0204A | 2018-08-28 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | [6 empty] | FS to coordinate with client to scope the work. |  | 3 |  | CRYSTAL JIMENEZ | Dan Lerman
VC-RED | 19P000439 | FS | SL5--SPIETH PATCH AND PAINT ROOM 335 | SPIETH | 335 | 2019-01-08 | QUEUE TO START | [8 empty] | 1 |  | JOHNNY PHAN | Paul Ditty
VC-RED | 9055 | PD&C | Pysch Loading Dock Haz Waste Storage |  |  | 2018-12-04 | Funding in process | Start Construction | 2019-04-01 | 2019-04-30 |  |  |  | There’s been an increase use of biological and chemical hazards being used by researchers and their research projects within the Psychology (V3) vivarium. When hazardous substances are used/generated in the vivarium, the current practice is for that waste to be removed by the researcher and taken to their lab for disposal by EH&S. This would mean that hazardous agents are being transported across campus which could potentially lead to an accidental exposure. In order to comply with the hazardous storage and transportation regulations, RED proposes that a hazardous storage shed be built on or near the Psychology (V3) loading dock thus minimizing any potential from an accidental contamination. It would be a chain link storage shed with two rooms (one for biological hazards and the other for chemical hazards), and a solid roof. Around the outside of the shed would also need to have some sort of vinyl covering. As for size, a 10’ x 20’ (two 10’ x 10’) shed should meet the needed storage space. Sample designs can be provided. | 2 |  |  | Dierk Biggs | Fernando Nunez
VC-STU.AFF. | 2829 | PD&C | SRC South - New Storage Building | SRC SOUTH |  | 2015-01-23 | Project is currently on-hold. | Coordinate with MRB Logistics | [5 empty] | New storage building immediately south of SRC South Pool Building; approximately 20' x 40'; one roll up door and one standard door; electrical power required - number of outlets to be defined in design; concrete walkway and door pads required; non-potable water may be required if quick couplers are not available in nearby landscaping; please see attachment for location: approximately at gridlines T and 9.4 - dotted outline of building is labeled "FUTURE STORAGE" - located immediately south of the SRC POOL EQUIPMENT BUILDING. | 2 |  |  | Lindy Fenex | Mihai Gavan
VC-STU.AFF. | 3385 | PD&C | SRC North Gym Replace Interior Lights | SRC NORTH |  | 2017-10-31 | Bidding | Award Contract | 2019-06-01 | 2019-08-01 |  |  |  | Replace old technology sodium vapor light fixtures in SRC North Gymnasium with new technology LED light fixtures. Some flexibility available in the schedule. Selected vendor will need to phase work to minimize the effect on SRC operations and programming. | 1 |  |  | Lindy Fenex | Fernando Nunez
VC-STU.AFF. | 3471 | PD&C | HUB Elect/Gas Meters 8 Location | HUB |  | 2018-08-20 | Governing board approved 2/15/2019 | Design | 2019-12-01 | 2020-02-01 |  |  |  | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | 5 |  |  | Brendan O'Brien | J.Franklin/J.Espinoza
VC-STU.AFF. | 3486 | PD&C | HUB 353/381, Costo 111 Add'l Wall/Doorway | HUB |  | 2018-11-26 | Client Approval/Funding | Funding | [5 empty] | Please evaluate additional wall/door way requests for HUB 353/381 and Costo Hall 111. | 6 |  |  | Brendan O'Brien | Daneca Stevens
VC-STU.AFF. | 18P000198 | FS | SL5-HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | HUB | 0 | 2017-11-21 | QUEUE TO START | [6 empty] | Plans will be developed and will be submitted for review and approval. |  | 1 |  | BRENDAN OBRIEN | Dan Lerman
VC-STU.AFF. | 18P000214 | FS | SL5-COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | HEALTH SERV |  | 2017-12-08 | IN PROGRESS | [6 empty] | Plans were approved by Fire Marshal, work to commence in 30 days. Scheduling the work with the availablity of the teams. |  |  |  | GLORIA VERA | Dan Lerman
VC-STU.AFF. | 18P000215 | FS | SL5-STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 | HEALTH SERV |  | 2017-12-08 | IN PROGRESS | [6 empty] | Plans were approved by Building Official; work to commence in 30 days. Scheduling the work with the availablity of the teams. |  |  |  | PAMELA HAGGINS | Dan Lerman
VC-STU.AFF. | 19P000380 | FS | SL5- PATCH AND PAITN- WALL PAINT IS PEELING | HEALTH SERV | 404 | 2018-11-19 | QUEUE TO START | [8 empty] | 1 |  | SAMANTHA HARRIS | Paul Ditty
VC-STU.AFF. | 19P000405 | FS | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED | HEALTH SERV | 0100D | 2018-12-11 | QUEUE TO START | [8 empty] | 2 |  | PAMELA BOCKSTADTER | Paul Ditty
VC-UNIV.ADV. | 2245 | PD&C | Campus Directory & Blade Signs |  |  | 2014-03-27 | Pre Design | Project Approval & Funding | 2019-08-05 | 2019-09-30 |  |  |  | Remove and replace campus directories at strategic locations throughout the campus. | 99 |  |  | Margene Mastin-Schepps | Fernando Nunez
VC-UNIV.ADV. | 18P000281 | FS | SL5-ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS | ALUM VISITOR | 2202 | 2018-01-24 | QUEUE TO START | [6 empty] | Work has been scoped; coordinating trades schedule for work to begin. |  | 2 |  | TRUDY COHEN | John Peraino
VC-UNIV.ADV. | 19P000418 | FS | SL5--BOTANIC UCR BOARD OF TRUSTEES MTG./BOTANIC GARDENS CONF. RM | BOTAN INFO C | 1 | 2018-12-18 | QUEUE TO START | [8 empty] | 1 |  | LADONNA ARDARY | Paul Ditty
To view projects for a specific organization ONLY, click on the filter options HERE.

## Project Detail
Project Status Report | [5 empty] | Last Updated | 2019-03-01
FS
SL5-CHAPMAN PREP AND PAINT FROM WATER DAMAGE
Project Reference No. | 18P000030
FS
Financials
Project Manager | Dan Lerman | Organization | CNAS | Prioritization Designate | Deborah McWilliams | PD&C Approved Budget
Contact/ Requestor | WILLIAM SUTTON | Building | CHAPMAN | Project Service Unit |  | FS Recharge Actuals To Date
CPMS # |  | Room | 100 | PD&C Org Priority No. |  | Core / Non-Core | CORE
FS # | 18P000030 | Request Date | 2017-07-11 | FS Org Priority No.
For Faculty Hire
Project Description | Complete as of 11/8/18
FS
Project Status
Project Status | COMPLETE |  |  |  | START Date
Next Steps |  |  |  |  | COMPLETION Date
IRT Status
FS
Campus Impact (i.e. excessive noise / limited access / utility shutdown)
Description
Impact Start
Impact End
FS
PM Notes |  | Project Manager | Dan Lerman | PM Email | daniel.lerman@ucr.edu | PM Phone | 951-827-6224
DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete.....
FS
BZM Scope |  | Reviewer | Dan Lerman | BZM Email | daniel.lerman@ucr.edu | BZM Phone | 951-827-4214
Scope Completed
To view more detailed information for a specific project, type in the Project Reference No. or clear the field and then scroll through the dropdown list HERE.

## FS Closed Projects
(CLOSED) FS Project Summary Report | [7 empty] | **Closed FS Projects include projects that have been Completed, Canceled by FS, Canceled by Client and projects in IRT Review.
Total Closed FS Projects |  | 253
Last Updated | 2019-03-01 | Project Summary
Organization | Project Ref No. | Project Service Unit | Project Title | Building | Room | Request Date | Current Status | Project Description | PD&C Org Priority No. | FS Org Priority No. | For New Faculty Hire? | Contact | Proj Manager
CNAS | 17W012504 | FS | PAINT Business OFFICE AND CONF. ROOM | ENTOMOLOGY | 170 | 2017-05-04 | COMPLETE | Complete as of 10/22/18. |  | 27 |  | WILLIAM SUTTON | Paul Ditty
CNAS | 18P000027 | FS | SL5-CHAPMAN PREP AND PAINT LAB | CHAPMAN | 12 | 2018-03-05 | COMPLETE | Complete as of 7/12/18 |  |  |  | WILLIAM SUTTON | Dan Lerman
CNAS | 18P000028 | FS | SL5-CHAPMAN PATCH AND PAINT | CHAPMAN | 0010A | 2017-07-11 | COMPLETE | Complete as of 7/12/18 |  |  |  | WILLIAM SUTTON | Dan Lerman
CNAS | 18P000029 | FS | SL5-CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS | CHAPMAN | 1 | 2017-07-11 | COMPLETE | Complete as of 7/11/18 |  |  |  | WILLIAM SUTTON | Dan Lerman
CNAS | 18P000030 | FS | SL5-CHAPMAN PREP AND PAINT FROM WATER DAMAGE | CHAPMAN | 100 | 2017-07-11 | COMPLETE | Complete as of 11/8/18 |  |  |  | WILLIAM SUTTON | Dan Lerman
BAS | 18P000094 | FS | SL5-OBAN LAUNDRY ROOM RENOVATION | OBAN OFFICE | 100 | 2017-09-08 | TO BE PERFORMED BY PD&C | Scope of work has changed and project to be routed to Google IRT/CPMS for completion |  |  |  | EDWIN MELGAR-MEJIA | Enrico Baez
BAS | 18P000095 | FS | SL5-THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS | THE PLAZA | A0013 | 2017-09-08 | CANCELED BY CLIENT | Canceled per customer on priortization list. |  | Canceled |  | EDWIN MELGAR-MEJIA | Enrico Baez
BAS | 18P000106 | FS | SL5-HOUSING PROJECT - OBAN REC ROOM REMODEL | OBAN OFFICE | 100 | 2017-09-14 | TO BE PERFORMED BY PD&C | Scope of work has changed and project to be routed to Google IRT/CPMS for completion |  |  |  | EDWIN MELGAR-MEJIA | Enrico Baez
CHASS | 18P000111 | FS | SL5-KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 | CHASS INT S |  | 2017-09-15 | COMPLETE | Complete as of 7/13/18 |  |  |  | RYAN MARIANO | Jason Williams
CNAS | 18P000117 | FS | SL5-PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION | WEBBER | 1303 | 2017-12-21 | COMPLETE | Complete as of 9/10/18 |  |  |  | MELISSA GOMEZ | Dan Lerman
CNAS | 18P000118 | FS | SL5-OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT | OLMSTED | 1337 | 2017-09-20 | COMPLETE | Complete as of 7/25/18. |  |  |  | MELISSA GOMEZ | Dan Lerman
ITS | 18P000194 | FS | SL5-TELEPHONE WINDOW REPLACEMENT | TELEPHONE | 101 | 2017-11-20 | CANCELED BY CLIENT | Canceled by customer; duration of hold was over 10 months. Customer to resubmit when ready to proceed |  | 5 |  | TAMI FRIEDRICH | Dan Lerman
CHASS | 18P000201 | FS | SL5-ARTS REMOVE COUNTERTOP/SHELVES | ARTS | 0106A | 2017-11-21 | COMPLETE | Complete as of 8/23/18 |  |  | YES | PAUL RICHARDSON | Dan Lerman
CHASS | 18P000205 | FS | SL5-CHASS INT S CREATE DOOR | CHASS INT S | 2117H | 2017-11-27 | COMPLETE | Complete as of 9/21/18 |  |  | YES | PAUL RICHARDSON | Dan Lerman
CNAS | 18P000221 | FS | SL5-Provide add'l HVAC capacity to maintain lower temp | BOYCE | 4414 | 2017-12-11 | COMPLETE | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. |  | 9 |  | APRIL MEINZER | Dan Lerman
CNAS | 18P000223 | FS | SL5-Provide requisite utility infrastructure to support 4 add'l chambers (on order). | FAWCETT LAB |  | 2017-12-11 | COMPLETE | Plans were approved by Building Official and Fire Marshal; anticipated completion January 2019. |  | 11 |  | APRIL MEINZER | Dan Lerman
BCOE | 18P000226 | FS | SL5-BOURNS FUME HOOD INSTALLATION | BOURNS | B0235A | 2017-12-11 | COMPLETE | Installation of utilities to be completed; clean room to be installed upon utility connections. |  | 8 | YES | LOUIS SANDOVAL | Dan Lerman
CNAS | 18P000227 | FS | SL5-BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL | BATCHELOR | 4128 | 2017-12-12 | COMPLETE | Complete as of 11/8/18 |  |  | YES | APRIL MEINZER | Dan Lerman
CNAS | 18P000247 | FS | SL5-PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 | PHYSICS | 3023 | 2017-12-20 | COMPLETE | Complete as of 7/14/18 |  |  |  | MAYELA CASTILLO | Paul Ditty
ITS | 18P000252 | FS | SL5-CHASS INT S REPLACE ELECTRICAL SCREENS | CHASS INT S | 2130 | 2017-12-21 | CANCELED BY CLIENT | Pending customer to confirm of equipment to be purchased; work scoped by BZM. |  | 1 |  | JORGE MACIAS | Dan Lerman
CNAS | 18P000256 | FS | SL5-BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES | BOYCE | 3451 | 2017-12-22 | COMPLETE | Complete as of 9/21/18 |  |  |  | CHERYL GERRY | Dan Lerman
CNAS | 18P000257 | FS | SL5-SKYE HALL MOUNT 55 | SKYE HALL | 209 | 2017-12-22 | COMPLETE | Scope of work is being reviewed; determining how to complete project with trades. |  | 28 |  | JAMES MARBERRY | Dan Lerman
CNAS | 18P000258 | FS | SL5-SKYE HALL HALLWAY MOUNT | SKYE HALL | 212 | 2017-12-22 | COMPLETE | Scope reviewed by BZM; coordination by PM for work to be completed. |  | 29 |  | JAMES MARBERRY | Dan Lerman
SOM | 18P000261 | FS | SL5-WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR | WEBBER | 1143 | 2017-12-22 | COMPLETE | Complete as of 9/10/18 |  |  |  | LOURDES ESCAMILLA | Dan Lerman
BCOE | 18P000267 | FS | SL5-CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT | CHUNG HALL | 103 | 2018-01-16 | COMPLETE | Complete as of 7/11/18 |  |  |  | ROBERT LOPEZ-A | Dan Lerman
SPP | 18P000270 | FS | SL5-CHASS INT S- EVALUATION FOR REMODEL | CHASS INT S | 4133 | 2018-01-16 | CANCELED BY CLIENT | Pending customer to provide drawing of the space. |  | 4 | YES | CHRISTINA WONG | Dan Lerman
LIBR | 18P000273 | FS | SL5-RIVERA LIB -RESTROOM REFRESH PROJECT | RIVERA LIBRARY |  | 2018-01-18 | TO BE PERFORMED BY PD&C | Scope of work has been reviewed; determining how to complete project with trades. |  | 1 |  | DAVID SCHUSTER | Dan Lerman
GSOE | 18P000274 | FS | SL5-SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 | EADY CENTER |  | 2018-01-18 | COMPLETE | Project is 95% complete; contract in progress for installation of a new door, door frame and ADA operator. Anticipated completion December 2018. |  |  |  | KAREN NAPLES/BRANDON BARBOSA | Dan Lerman
BAS | 18P000282 | FS | SL5-EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 | POLICE BLDG |  | 2018-01-25 | COMPLETE | Complete as of 8/10/18 |  |  |  | LISA MARTIN | Dan Lerman
CNAS | 18P000284 | FS | SL5-SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT | SKYE HALL | 277 | 2018-01-31 | COMPLETE | Complete as of 9/21/18 |  | 29 |  | JAMES MARBERRY | Paul Ditty
CNAS | 18P000287 | FS | SL5-SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING | SKYE HALL | 208 | 2018-01-31 | COMPLETE | Complete as of 9/21/18 |  |  |  | JAMES MARBERRY | Dan Lerman
CNAS | 18P000288 | FS | SL5-SKYE HALL OFFICE SUITE PAINTING | SKYE HALL | 208 | 2018-01-31 | COMPLETE | Complete as of 8/24/18 |  |  | YES | JAMES MARBERRY | Paul Ditty
CNAS | 18P000292 | FS | SL5-SKYE HALL PAINT MULTIPLE FACULTY OFFICES | SKYE HALL | 228 | 2018-01-31 | COMPLETE | Complete as of 8/24/18 |  |  | YES | JAMES MARBERRY | Paul Ditty
CNAS | 18P000293 | FS | SL5-SKYE HALL COPIER ROOM PATCH AND PAINT | SKYE HALL | 278 | 2018-01-31 | COMPLETE | Complete as of 8/24/18 |  |  |  | JAMES MARBERRY | Paul Ditty
CHASS | 18P000294 | FS | SL5-HMSS REMOVE DOOR, INSTALL WALL | HUM & SOC SC | 3610 | 2018-02-01 | CANCELED BY CLIENT | Canceled on 7/16/18 per email communication with customer. |  |  |  | PAUL RICHARDSON | Dan Lerman
CHASS | 18P000295 | FS | SL5-CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL | CHASS INT S | 2117J | 2018-02-01 | COMPLETE | Complete as of 9/21/18 |  |  | YES | PAUL RICHARDSON | Dan Lerman
CNAS | 18P000296 | FS | SL5-SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES | SKYE HALL | 266 | 2018-02-02 | COMPLETE | Contract is being processed; target project completion is end of September. |  |  |  | JAMES MARBERRY | Dan Lerman
CHANCELLOR | 18P000297 | FS | SL5-SKYE HALL CHECK LOCATION FOR TV INSTALL | SKYE HALL | 390 | 2018-02-02 | COMPLETE | Scope of work has been reviewed; determining how to complete project with trades. |  | 4 |  | CANDICE GOMEZ | Dan Lerman
CHASS | 18P000300 | FS | SL5-ARTS PATCH AND PAINT - DANCE HALLWAYS | ARTS |  | 2018-02-02 | COMPLETE | Complete as of 8/24/18 |  |  |  | SARAH NOSCE | Paul Ditty
CNAS | 18P000310 | FS | SL5-ADD INTERCOM/BUZZ IN SYSTEM | COLL BLDG NO | 201 | 2018-02-12 | COMPLETE | Complete as of 10/22/18. |  |  |  | RONDA INZUNZA | Dan Lerman
CNAS | 18P000312 | FS | SL5-URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 | CAMP LOC NOT IN BLDG |  | 2018-02-13 | CANCELED BY FS | Canceled per customer 9/12/18 |  | Canceled |  | AMBER RHEMREV | Dan Lerman
GSOE | 18P000313 | FS | SL5-SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 | SPROUL |  | 2018-02-15 | COMPLETE | Complete as of 10/22/18. |  |  |  | KAREN NAPLES | Dan Lerman
CHASS | 18P000314 | FS | SL5-CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR | CA MUS PHOTO | 1000 | 2018-02-16 | COMPLETE | Complete as of 7/25/18. |  |  |  | EMILY PAPAVERO | Dan Lerman
BCOE | 18P000315 | FS | SL5-BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB | BOURNS | B0235 | 2018-02-16 | COMPLETE | Complete as of 8/23/18 |  |  | YES | LOUIS SANDOVAL | Dan Lerman
BCOE | 18P000321 | FS | SL5-STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST | STUDENT SERV | 1228 | 2018-02-22 | COMPLETE | Complete as of 8/10/18 |  |  |  | ROBERT LOPEZ-A | Enrico Baez
PLANNING & BUDGET | 18P000324 | FS | SL5-HINDERAKER PATCH AND PAINT | HINDERAKER | 4118 | 2018-02-26 | COMPLETE | Complete as of 7/11/18 |  |  |  | MILLY PAREDEZ | Paul Ditty
ATHLETICS | 18P000328 | FS | SL5-HINDERAKER BASEMENT OFFICE REPAIR | HINDERAKER |  | 2018-03-01 | COMPLETE | Complete as of 7/11/18 |  |  |  | JOHNATHAN JENSEN | Dan Lerman
CHANCELLOR | 18P000329 | FS | SL5-SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST | SKYE HALL | 170 | 2018-03-12 | COMPLETE | Project complete as of 9/18/18 |  |  |  | DA LAN DINH | Dan Lerman
VC-STU.AFF. | 18P000337 | FS | SL5-MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET | HEALTH SERV | 414 | 2018-03-12 | COMPLETE | Plans are approved for work to commence; scheduled for start on 11/13/18. |  |  |  | GLORIA VERA | Dan Lerman
CNAS | 18P000341 | FS | SL5-PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL | PHYSICS | 1132 | 2018-03-14 | COMPLETE | AQMD notification was sent; abatement to begin at the end of notification period. |  |  |  | MAYELA CASTILLO | Dan Lerman
CHASS | 18P000344 | FS | SL5-CHASS INTS PAINT MULTIPLE ROOMS - FACULTY | CHASS INT S | 2117E | 2018-03-18 | COMPLETE | Complete as of 9/10/18 |  |  | YES | PAUL RICHARDSON | Dan Lerman
ATHLETICS | 18P000346 | FS | SL5-ATHLETICS INSTALL WALL VOLLEYBALL OFFICES | ATH DANCE |  | 2018-03-18 | COMPLETE | Complete as of 11/8/18 |  |  |  | JOHNATHAN JENSEN | Dan Lerman
VC-STU.AFF. | 18P000348 | FS | SL5-HUB ADD 3RD FLOOR WALLS | HUB | 0353E | 2018-03-18 | TO BE PERFORMED BY PD&C | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. |  | 2 |  | BRENDAN OBRIEN | Dan Lerman
BCOE | 18P000349 | FS | SL5-PHYSICS INSTALL PARTITION WALL FOR LAB ROOM | PHYSICS | 1037 | 2018-03-18 | COMPLETE | Complete as of 7/11/18 |  |  | YES | LOUIS SANDOVAL | Dan Lerman
CHASS | 18P000353 | FS | SL5-PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT | PSYCHOLOGY1 | 1111A | 2018-03-20 | COMPLETE | Complete as of 8/23/18 |  |  |  | ERICA RAMIREZ | Paul Ditty
CNAS | 18P000354 | FS | SL5-GH16-25 COOLING SYSTEM REPAIR | GH 16 25 |  | 2018-03-20 | CANCELED BY FS | Work considered deferred maintenance not a minor renovation. |  | 13 |  | MARK TANKERSLEY | Dan Lerman
CNAS | 18P000356 | FS | SL5-ENTOMOLOGY PATCH AND PATCH | ENTOMOLOGY | 278 | 2018-03-20 | COMPLETE | Complete as of 8/24/18 |  |  | YES | WILLIAM SUTTON | Paul Ditty
BAS | 18P000363 | FS | SL5-PAINT STOREHOUSE ADMINISTRATIVE OFFICE | CORP B |  | 2018-03-26 | COMPLETE | Complete as of 11/8/18 |  | 13 |  | ERICA HENDERSON | Paul Ditty
CHASS | 18P000367 | FS | SL5-CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE | CHASS INT N | 3033 | 2018-03-27 | COMPLETE | Complete as of 7/14/18 |  |  |  | SARAH NOSCE | Paul Ditty
BAS | 18P000369 | FS | SL5-BOYCE X-RAY IRRADIATOR PROJECT | BOYCE | 1407 | 2018-03-27 | CANCELED BY CLIENT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. |  |  |  | KAREN JANIGA | Dan Lerman
BAS | 18P000373 | FS | SL5-POLICE BLDG PAINTING IN DISPATCH AREA | POLICE BLDG | 100 | 2018-04-02 | COMPLETE | Complete as of 7/14/18 |  |  |  | KELLY DUNCAN | Paul Ditty
VC-RED | 18P000379 | FS | SL5-UOB PATCH AND PAINT | UNIV OFC BLD |  | 2018-04-05 | COMPLETE | Complete as of 8/24/18 |  |  |  | CRYSTAL JIMENEZ | Paul Ditty
SOM | 18P000380 | FS | SL5-SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | SOM RSCH | 330 | 2018-04-05 | CANCELED BY CLIENT | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 |  |  |  | TARA BARTHOL | Dan Lerman
ITS | 18P000381 | FS | SL5-ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 | WATKINS |  | 2018-04-05 | COMPLETE | FS to coordinate with customer to schedule the work for completion. |  | 3 |  | SHEILA MABEE | Dan Lerman
ITS | 18P000382 | FS | SL5-ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 | WATKINS |  | 2018-04-05 | COMPLETE | Plans will be developed and will be submitted for review and approval. |  | 2 |  | PHYLLIS FRANCO | Dan Lerman
CHASS | 18P000383 | FS | SL5-HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT | HUM & SOC SC | 1302 | 2018-04-06 | COMPLETE | Completed as of 8/10/18 |  |  | YES | ALLISON ROGERS | Paul Ditty
CHASS | 18P000387 | FS | SL5-HMSS PATCH/PAINT | HUM & SOC SC | 3600 | 2018-04-10 | COMPLETE | Complete as of 8/24/18 |  |  |  | PAUL RICHARDSON | Paul Ditty
CHASS | 18P000389 | FS | SL5-PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A | PSYCHOLOGY1 | 2122 | 2018-04-10 | COMPLETE | Complete as of 11/8/18 |  |  | YES | ERICA RAMIREZ | Paul Ditty
PLANNING & BUDGET | 18P000390 | FS | SL5-UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD | UV BLDG B | 0240B | 2018-04-10 | COMPLETE | Complete as of 8/24/18 |  |  |  | LESLIE ROSE | Paul Ditty
BCOE | 18P000391 | FS | SL5-PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN | CHUNG HALL | 446 449 | 2018-04-10 | COMPLETE | Complete as of 9/10/18 |  |  | YES | ROBERT LOPEZ | Dan Lerman
CNAS | 18P000392 | FS | SL5-BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 | BATCHELOR | 0 | 2018-04-12 | COMPLETE | Complete as of 8/24/18 |  |  | YES | MATTHEW ULRICH | Paul Ditty
BCOE | 18P000394 | FS | SL5-BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK | BOURNS | A0159A | 2018-04-12 | COMPLETE | Project work has been complete but work is being reviewed by faculty. Sound soak may be installed. |  |  | YES | ROBERT LOPEZ-A | Dan Lerman
CHASS | 18P000396 | FS | SL5-WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | WATKINS | 2122 | 2018-04-13 | COMPLETE | Complete as of 8/24/18 |  |  | YES | DAMARIS CARLOS | Paul Ditty
CHASS | 18P000398 | FS | SL5-WATKINS ESTIMATE FOR SEALING OF ADJOINING DOORS | WATKINS | 2204 | 2018-04-16 | COMPLETE | Complete as of 10/22/18. |  |  | YES | DAMARIS CARLOS | Dan Lerman
CHANCELLOR | 18P000410 | FS | SL5-HINDERAKER PAINT AND PATCH WALL | HINDERAKER | 3148B | 2018-04-25 | COMPLETE | Complete as of 8/24/18 |  |  |  | CANDICE GOMEZ | Paul Ditty
CHASS | 18P000415 | FS | SL5-PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | OLMSTED | 0 | 2018-05-08 | CANCELED BY CLIENT | Door and frame have been painted; construction to commence upon availability of the teams. |  |  | YES | RYAN LIPINSKI | Dan Lerman
CHASS | 18P000416 | FS | SL5-HMSS UWP INSTRUCTOR OFFICE PAINTING | HUM & SOC SC | 3002 | 2018-04-27 | COMPLETE | Complete as of 8/24/18 |  |  | YES | JILL CANTONWINE | Paul Ditty
CHASS | 18P000417 | FS | SL5-HMSS UWP INSTRUCTIONAL OFFICE PAINTING | HUM & SOC SC | 2106 | 2018-04-27 | COMPLETE | Complete as of 8/24/18 |  |  | YES | JILL CANTONWINE | Paul Ditty
CHASS | 18P000418 | FS | SL5-HMSS OFFICE PAINTING | HUM & SOC SC | 2002 | 2018-04-27 | COMPLETE | Complete as of 7/14/18 |  |  | YES | JILL CANTONWINE | Paul Ditty
CHASS | 18P000419 | FS | SL5-COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | WATKINS | 1320C&E | 2018-04-27 | CANCELED BY CLIENT | FS to coordinate with client to scope the work. |  | 5 | YES | PAUL RICHARDSON | Dan Lerman
CHASS | 18P000420 | FS | SL5-COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | WATKINS | 0 | 2018-04-27 | CANCELED BY CLIENT | Canceled by Customer on prioritization 7/2/18 |  |  | YES | PAUL RICHARDSON
CHANCELLOR | 18P000421 | FS | SL5-HINDERAKER PAINT AND PATCH WALL | HINDERAKER | 2120 | 2018-04-30 | COMPLETE | Complete as of 8/24/18 |  |  |  | CANDICE GOMEZ | Paul Ditty
BCOE | 18P000425 | FS | SL5-BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - | BOURNS | A0379 | 2018-05-01 | COMPLETE | Complete as of 7/25/18. |  |  | YES | LOUIS SANDOVAL | Dan Lerman
BCOE | 18P000426 | FS | SL5-BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER | BOURNS | A0375 | 2018-05-01 | COMPLETE | Complete as of 7/25/18. |  |  | YES | LOUIS SANDOVAL | Dan Lerman
BCOE | 18P000427 | FS | SL5-BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER | BOURNS | A0373 | 2018-05-01 | COMPLETE | Complete as of 7/11/18 |  |  | YES | LOUIS SANDOVAL | Dan Lerman
SoB | 18P000428 | FS | SL5-OLMSTED RM 2352 PATCH/PAINT | OLMSTED | 2352 | 2018-05-02 | COMPLETE | Complete as of 8/17/18 |  |  |  | ANGELA CHANG | Paul Ditty
BCOE | 18P000429 | FS | SL5-INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 | BOURNS | B0262 B0256 | 2018-04-10 | COMPLETE | Complete as of 9/19/18 |  |  | YES | KEVIN SCHULTE | Dan Lerman
BAS | 18P000432 | FS | SL5-BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 | BANNOCK H | H0101 | 2018-05-04 | COMPLETE | Complete as of 7/13/18 |  |  |  | EDWIN MELGAR-MEJIA | Paul Ditty
CNAS | 18P000434 | FS | SL5-BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY | BOYCE | 4478 | 2018-05-09 | COMPLETE | Complete as of 8/24/18 |  |  | YES | CHERYL GERRY | Paul Ditty
CNAS | 18P000436 | FS | SL5-COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS | COLL BLDG SO | 210 | 2018-05-10 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 36 |  | RONDA INZUNZA | Paul Ditty
BCOE | 18P000438 | FS | SL5-CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING | CHUNG HALL | 415 | 2018-05-14 | COMPLETE | Complete as of 9/10/18 |  | Complete |  | ROBERT LOPEZ-A | Paul Ditty
BCOE | 18P000439 | FS | SL5-CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING | CHUNG HALL | 315 | 2018-05-15 | COMPLETE | Complete as of 9/10/18 |  | Complete |  | ROBERT LOPEZ-A | Paul Ditty
VC-RED | 18P000442 | FS | SL5-FAWCETT LAB 203 PATCH & PAINT | FAWCETT LAB | 203 | 2018-05-18 | COMPLETE | Complete as of 8/24/18 |  |  |  | CRYSTAL JIMENEZ | Paul Ditty
CHASS | 18P000444 | FS | SL5-PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 | ARTS | 242 | 2018-05-21 | COMPLETE | Complete as of 9/21/18 |  | 6 | YES | SUSAN KOMURA | Paul Ditty
CHASS | 18P000445 | FS | SL5-PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 | ARTS | 225 | 2018-05-21 | COMPLETE | Complete as of 9/10/18 |  |  | YES | SUSAN KOMURA | Paul Ditty
BCOE | 18P000454 | FS | SL5-BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS | BOURNS | A0346 | 2018-05-29 | COMPLETE | Complete as of 8/24/18 |  |  |  | ROBERT LOPEZ-A | Paul Ditty
VC-STU.AFF. | 18P000456 | FS | SL5-HUB--UTILITY METERS | HUB |  | 2018-05-30 | TO BE PERFORMED BY PD&C | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. |  |  |  | BRENDAN OBRIEN | Dan Lerman
BAS | 18P000459 | FS | SL5-BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 | THE BARN |  | 2018-05-31 | COMPLETE | Complete as of 9/21/18 |  | Complete |  | GUSTAVO PLASCENCIA | Dan Lerman
SoB | 18P000463 | FS | SL5-ANDERSON HALL PATCH/PAINT-102C | ANDERSON 1 | 0102C | 2018-06-04 | COMPLETE | Complete as of 8/24/18 |  |  |  | ANGELA CHANG | Paul Ditty
CNAS | 18P000464 | FS | SL5-PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED | COLL BLDG NO | 201 | 2018-08-16 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 35 |  | RONDA INZUNZA | Paul Ditty
CHASS | 18P000468 | FS | SL5-WATKINS 1222/1223 PATCH/PAINT | WATKINS | 1222 | 2018-06-11 | COMPLETE | Completed as of 8/10/18 |  |  | YES | PAUL RICHARDSON | Paul Ditty
CHASS | 18P000469 | FS | SL5-WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS | WATKINS | 1317 | 2018-06-11 | COMPLETE | Complete as of 7/25/18 |  |  | YES | PAUL RICHARDSON | Paul Ditty
SPP | 18P000470 | FS | SL5-Student Check-in Lobby | CHASS INT S | 4133 Corridor | 2018-06-11 | COMPLETE | Complete as of 8/23/18 |  |  |  | LUIS ALVAREZ | Dan Lerman
ITS | 18P000471 | FS | SL5-WCH INSTALL SECURITY FENCE | CHUNG HALL | 134 | 2018-06-12 | COMPLETE | Complete as of 9/19/18 |  |  |  | TAMI FRIEDRICH | Dan Lerman
BCOE | 18P000472 | FS | SL5-WCH PATCH AND PAINT WALL | CHUNG HALL | 458 | 2018-06-12 | COMPLETE | Complete as of 8/24/18 |  |  | YES | JANNA LE BLANC | Paul Ditty
CNAS | 18P000473 | FS | SL5-PIERCE NEW CARPET & PAINT FACULTY OFFICE | PIERCE | 202 | 2018-06-12 | COMPLETE | Complete as of 9/26/18 |  | 1 | YES | BARBARA OUTZEN | Paul Ditty
VC-RED | 18P000476 | FS | SL5-BOYCE CONNECT WASHER & DRYER | BOYCE | 6444 | 2018-06-14 | CANCELED BY CLIENT | Canceled project, work completed on 18W015691 in July. |  |  |  | DIERK BIGGS | Dan Lerman
UNDERGRAD ED | 18P000478 | FS | SL5-CARPET, PAINT, & AIR HANDLING MODIFICATION | HINDERAKER | 1120H | 2018-06-16 | COMPLETE | Complete as of 10/22/18. |  |  |  | TRACEY SCHOLTEMEYER | Dan Lerman
CNAS | 18P000480 | FS | SL5-BG - LOWER RESTROOMS-PAINTING-FLOORS | BOTGDN RSTRM |  | 2018-06-25 | CANCELED BY FS | Canceled by Facilities Services; Work is not within the SLA and is not needed. |  | 23 |  | AMBER RHEMREV | Paul Ditty
CHASS | 18P000481 | FS | SL5-CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 | CHASS INT S | 3104 | 2018-06-25 | COMPLETE | Complete as of 10/22/18. |  | 10 |  | PAUL RICHARDSON | Paul Ditty
SoB | 18P000482 | FS | SL5-CARD ACCESS SYSTEM ANDERSON SOUTH | ANDERSON |  | 2018-06-26 | COMPLETE | Complete as of 8/2/18. |  |  |  | ANGELA CHANG | Dan Lerman
BAS | 18P000483 | FS | SL5-INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | P1 |  | 2018-06-26 | CANCELED BY CLIENT | FS to coordinate with customer to scope the work. |  | 7 |  | AMANDA GREY | Enrico Baez
ATHLETICS | 18P000484 | FS | SL5-INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | SOFTBALL STG |  | 2018-06-26 | TO BE PERFORMED BY PD&C | Project will be managed by A&E for completion. |  |  |  | JOSEPH ERBLAND | Dan Lerman
SOM | 18P000485 | FS | SL5-SOMR PATCHING AND PAINTING | SOM RSCH |  | 2018-06-28 | COMPLETE | Complete as of 10/10/18 |  | 6 | YES | DANA ABOU ABBAS | Paul Ditty
CHANCELLOR | 18P000487 | FS | SL5-SKYE HALL PATCH HOLES AND PAINT | SKYE HALL | 349 | 2018-06-28 | COMPLETE | Complete as of 10/22/18. |  | 2 |  | SONIA ZAMORA | Paul Ditty
CNAS | 18W000455 | FS | SL5-CHAPMAN CLEAN WINDOWS | CHAPMAN | 12 | 2017-07-11 | COMPLETE | Complete as of 7/11/18 |  |  |  | WILLIAM SUTTON | Dan Lerman
CHASS | 18W001170 | FS | SL5-ARTS: PAINT CLASSROOMS | ARTS | 407 | 2017-07-25 | COMPLETE | Complete as of 9/24/18 |  |  |  | SUSAN KOMURA | Paul Ditty
SOM | 18W006022 | FS | INSTALL CURTAIN ROD IN RESEARCH SPACE | SOM RSCH | 336 | 2017-10-27 | COMPLETE | Complete as of 7/11/18 |  |  |  | TARA BARTHOL | Dan Lerman
CHASS | 18W008762 | FS | SL5-HUMANITIES: PATCH & PAINT | HUM & SOC SC | 2415 | 2018-01-02 | COMPLETE | Complete as of 11/8/18 |  | 20 |  | ANDREW ALONSO | Paul Ditty
CNAS | 18W011161 | FS | SL5-REPLACE CARPET | SCIENCE LAB1 | 301 | 2018-02-23 | COMPLETE | Complete as of 7/11/18 |  |  |  | DEBORAH TERAO | Dan Lerman
CNAS | 18W011672 | FS | SL5-ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY | ENTOMOLOGY | 268 | 2018-03-08 | COMPLETE | Complete as of 7/25/18 |  |  | YES | WILLIAM SUTTON | Paul Ditty
CNAS | 18W011691 | FS | SL5-ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | ENTOMOLOGY | 139 | 2018-03-08 | CANCELED BY CLIENT | FS to coordinate with client to schedule work for completion. |  | 4 | YES | WILLIAM SUTTON | Paul Ditty
CNAS | 18W011692 | FS | SL5-ENTOMOLOGY; PAINT/PATCH LAB | ENTOM MUSEUM | 211 | 2018-03-08 | COMPLETE | Complete as of 8/24/18 |  |  | YES | WILLIAM SUTTON | Paul Ditty
BAS | 18W011772 | FS | SL5-PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | PRINT MOD |  | 2018-03-12 | CANCELED BY CLIENT | Canceled per customer on priority list 7/3/18 |  |  |  | PRISCILLA MARTIN | Dan Lerman
CNAS | 18W013160 | FS | BEES- PATCH & PAINT 2460D & 2460F | GEOLOGY | 2460 | 2018-04-06 | COMPLETE | Complete as of 10/22/18. |  | 33 |  | DEBORAH TERAO | Paul Ditty
VC-RED | 18W013973 | FS | SL5-BSL3 FACILITY- ASSEMBLE AND INSTALL | UNIV OFC BLD |  | 2018-04-19 | COMPLETE | Complete as of 9/24/18 |  |  |  | CRYSTAL JIMENEZ | Enrico Baez
VC-RED | 18W015691 | FS | SL5-BOYCE CONNECT WASHER AND DRYER | BOYCE | 6444 | 2018-05-30 | COMPLETE | Complete as of 7/11/18 |  |  |  | DIERK BIGGS
CHASS | 18W016588 | FS | PATCH AND PAINT FOR FACULTY | SPROUL | 4105 | 2018-06-19 | COMPLETE | Complete as of 8/24/18 |  |  | YES | DAMARIS CARLOS | Paul Ditty
CHASS | 18W016621 | FS | SL5-HUMANITIES - PAINT OFFICE - PAINT SHOP | HUM & SOC SC | 3403 | 2018-06-20 | COMPLETE | Complete as of 11/8/18 |  | 17 |  | CYNTHIA CARRASCO CANNON | Paul Ditty
SOM | 19P000009 | FS | SL5-SOME -- PAINT, SPACKLE AND CLEANING NEEDED | SOM EDUC | 2615 | 2018-07-02 | COMPLETE | Complete as of 10/10/18 |  | 1 | YES | BEVERLEY HERBERT | Paul Ditty
CHASS | 19P000011 | FS | SL5-PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED | PSYCHOLOGY1 | 2111A | 2018-07-03 | COMPLETE | Complete as of 10/10/18 |  | 4 | YES | LORENA QUINTANA | Paul Ditty
SOM | 19P000012 | FS | SL5-SOME--PATCH & PAINT | SOM EDUC | 2638 | 2018-07-06 | COMPLETE | Complete as of 10/10/18 |  | 7 | YES | MARISELA MARTINEZ | Paul Ditty
SOM | 19P000014 | FS | SL5-SOME - PATCH & PAINT | SOM EDUC | 2609 | 2018-07-09 | COMPLETE | Complete as of 10/10/18 |  | 8 | YES | MARISELA MARTINEZ | Paul Ditty
BAS | 19P000015 | FS | SL5-POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING | POLICE TRLR | 1 | 2018-07-10 | COMPLETE | Complete as of 11/8/18 |  | 11 |  | KELLY DUNCAN | Paul Ditty
SoB | 19P000017 | FS | SL5-ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD | ANDERSON 1 | 0001B | 2018-07-11 | COMPLETE | Complete as of 8/24/18 |  |  |  | ANGELA CHANG | Dan Lerman
SoB | 19P000018 | FS | SL5-ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER | ANDERSON 1 | 0001B | 2018-07-11 | COMPLETE | Complete as of 8/24/18 |  |  |  | ANGELA CHANG | Paul Ditty
BAS | 19P000022 | FS | SL5-HUB--PAINT TWO WALL AS SCOTTY'S HUB | HUB | 101 | 2018-07-12 | COMPLETE | Complete as of 9/17/18 |  | 8 |  | DIANE THOMAS | Paul Ditty
BCOE | 19P000023 | FS | SL5-PAINT ACCENT WALL | CHUNG HALL | 354 | 2018-07-13 | CANCELED BY CLIENT | Work to be completed in conjunction with customer project #19P000035. |  | 9 |  | SARA GALLOWAY | Paul Ditty
BCOE | 19P000026 | FS | SL5-WCH PATCH AND PAINT WALLS | CHUNG HALL | 354 | 2018-07-16 | CANCELED BY CLIENT | Work to be completed in conjunction with customer project #19P000035. |  | 9 |  | SARA GALLOWAY | Paul Ditty
ATHLETICS | 19P000027 | FS | SL5-ATHLETICS PATCH & PAINT ROOM | ATH DANCE | 0120C | 2018-07-16 | COMPLETE | Complete as of 9/19/18 |  |  |  | JOSEPH ERBLAND | Dan Lerman
BCOE | 19P000029 | FS | SL5-CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | CHUNG HALL | 205 | 2018-07-16 | CANCELED BY CLIENT | Canceled; duplicate request to be completed with 19P000059 |  | 11 |  | ROBERT LOPEZ-A | Dan Lerman
SoB | 19P000030 | FS | SL5-OLMSTED PATCH/PAINT | OLMSTED | 2301 | 2018-07-16 | COMPLETE | Complete as of 10/10/18 |  | 1 |  | ANGELA CHANG | Paul Ditty
SoB | 19P000033 | FS | SL5-OLMSTED PATCH/PAINT | OLMSTED | 2301 | 2018-07-16 | CANCELED BY CLIENT | Duplicate request to 19P000030; Canceling project to be completed on other request. |  |  |  | ANGELA CHANG | Paul Ditty
BCOE | 19P000035 | FS | SL5-WCH--INSTALL NEW LED DISPLAY IN OFFICE | CHUNG HALL | 354 | 2018-07-16 | COMPLETE | Installation scheduled for Friday 11/19/18. |  | 9 |  | SARA GALLOWAY | Dan Lerman
VC-STU.AFF. | 19P000037 | FS | SL5-HEALTH SERVICE BLDG--PATCH WORK AND PAINTING | HEALTH SERV |  | 2018-07-17 | COMPLETE | Complete as of 10/22/18. |  | 3 |  | GLORIA VERA | Paul Ditty
CNAS | 19P000042 | FS | SL5-COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL | COLL BLDG SO | 200 | 2018-07-20 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 38 |  | LISA DUNMORE | Paul Ditty
CNAS | 19P000043 | FS | SL5-SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | SCIENCE LAB1 | 309 | 2018-07-20 | CANCELED BY CLIENT | Customer called and canceled the work on 10/23/18. |  | 19 |  | AMBER RHEMREV | Dan Lerman
VC-RED | 19P000044 | FS | SL5-PATCH AND PAINT | SPIETH | 345 | 2018-07-23 | COMPLETE | Complete as of 10/10/18 |  | 1 |  | JOHNNY PHAN | Paul Ditty
CNAS | 19P000045 | FS | SL5-PREPARE LOCATION AND UTILITIES FOR INSTALL | BOYCE | 2407 | 2018-07-23 | COMPLETE | Complete as of 11/8/18 |  | 14 |  | MATTHEW ULRICH | Dan Lerman
BCOE | 19P000046 | FS | SL5-PATCH AND PAINT PLUS REPLACE BLINDS | BOURNS | A0131 | 2018-07-23 | COMPLETE | Complete as of 11/8/18 |  | 2 | YES | NANCY FORD | Paul Ditty
CNAS | 19P000049 | FS | SL5-PHYSICS PATCH & PAINT | PHYSICS | 3036 | 2018-07-25 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 39 |  | JAZMIN CHAVEZ | Paul Ditty
SoB | 19P000053 | FS | SL5-ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S | ANDERSON 1 |  | 2018-04-13 | COMPLETE | Complete as of 10/22/18. |  |  |  | ANGELA CHANG | Dan Lerman
GSOE | 19P000054 | FS | SL5-PATCH & PAINT OFFICE | SPROUL | 2131 | 2018-07-26 | COMPLETE | Complete as of 10/10/18 |  | 1 | YES | KAREN NAPLES | Paul Ditty
CNAS | 19P000058 | FS | SL5-Assess Feasiblity of Removing/Replacing Growth Chambers | GH HH | 18 | 2018-03-28 | COMPLETE | Complete as of 8/24/18 |  |  |  | APRIL MEINZER | Dan Lerman
BCOE | 19P000059 | FS | SL5-CHUNG HALL 201 SECURITY SYSTEM INSTALL | CHUNG HALL | 201 | 2018-07-17 | CANCELED BY FS | ITS to install cameras, no work by FS Required. |  | 10 |  | MAGARET SOUDER | Dan Lerman
BCOE | 19P000060 | FS | SL5-CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | CHUNG HALL | 223 & 224 | 2018-05-15 | TO BE PERFORMED BY PD&C | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. |  | 6 |  | MAGARET SOUDER | Dan Lerman
CHASS | 19P000061 | FS | SL5-PSYCHOLOGY 1111H-PATCH HOLES IN WALL | PSYCHOLOGY1 | 1111H | 2018-07-30 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 9 |  | TOYA ADAMS | Paul Ditty
CNAS | 19P000062 | FS | SL5-MSE 169-MINOR RENOVATION - NEW FACULTY | MAT SCI ENGR | 169 | 2018-07-30 | COMPLETE | Electrical outlet is the highest priority. Must be installed by Sept 15, per Mayela Castillo |  | 5 | YES | MAYELA CASTILLO | Dan Lerman
CHASS | 19P000063 | FS | SL5-NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS | PSYCHOLOGY1 | 2124 | 2018-07-31 | COMPLETE | Complete as of 9/26/18 |  | 3 | YES | TOYA ADAMS | Paul Ditty
CNAS | 19P000102 | FS | SL5-PATCH & PAINT FRONT CORNER OF OFFICE | LIFE SCIENCE | 2930 | 2018-08-01 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 42 |  | ESTELLA DAVALOS | Paul Ditty
CHANCELLOR | 19P000122 | FS | SL5-REMOVE, PATCH & PAINT AND HANG | STUDENT SERV | 2222 | 2018-08-02 | COMPLETE | Complete as of 10/22/18. |  | 3 |  | CHRISTINE SMITH | Paul Ditty
VC-STU.AFF. | 19P000124 | FS | SL5-PAINT ROOMS 115 AND 116 | COSTO HALL | 125 | 2018-08-02 | COMPLETE | Complete as of 10/22/18. |  | 4 |  | LINDA KELLEY | Paul Ditty
CNAS | 19P000126 | FS | SL5-CHEMICAL SCIENCE - MINOR RENOVATIONS | CHEMICAL SCI | 455 | 2018-08-03 | COMPLETE | Paint has been completed; plumbing to complete work upon availability of the team. |  | 6 | YES | KEVIN KOU | Dan Lerman
CNAS | 19P000127 | FS | SL5-PIERCE PATCH & PAINT | PIERCE | 2301 | 2018-08-03 | CANCELED BY CLIENT | Duplicate request to be combined with 19P000239 |  | Canceled |  | MICHELLE KING | N/A
BCOE | 19P000129 | FS | SL5-HANG MONITORS AND BOARDS | CHUNG HALL | 103 | 2018-08-06 | COMPLETE | Dry erase boards and monitor mount installation complete; monitors to be installed. |  | 8 |  | RICHARD BAIN | Dan Lerman
CNAS | 19P000170 | FS | SL5-INSTALL NEW IRRADIATOR INSTRUMENT | MAT SCI ENGR | 51 | 2018-08-08 | COMPLETE | Anticipated delivery of equipment is scheduled for three weeks. |  | 16 |  | DEBORAH MCWILLIAMS | Dan Lerman
VC-STU.AFF. | 19P000172 | FS | SL5-HEALTH SERV- PAINT RESTROOM IN LABORATORY | HEALTH SERV | 0113A | 2018-08-09 | COMPLETE | Complete as of 11/8/18 |  | 5 |  | PAMELA BOCKSTADTER | Paul Ditty
CHASS | 19P000173 | FS | SL5-PAINT/PATCH UNIVERSITY THEATER LOBBY | THTR WKSH | 0400A | 2018-08-09 | COMPLETE | Complete as of 11/8/18 |  | 23 |  | PAUL RICHARDSON | Paul Ditty
BCOE | 19P000175 | FS | SL5-PAINTING | BOURNS | A0303 | 2018-08-09 | COMPLETE | Complete as of 10/10/18 |  | 3 | YES | ROBERT CHAVARRIA-VIVAR | Paul Ditty
CNAS | 19P000176 | FS | SL5-PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY | PHYSICS | 1112 | 2018-08-10 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 50 |  | MAYELA CASTILLO | Paul Ditty
CNAS | 19P000185 | FS | SL5-NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE | PIERCE | 206 (originially identified as Room 204) | 2018-06-18 | COMPLETE | Scope of work has been identified and walked with Requestor, F.S. Trades and P.M. Trade work in progress. |  |  | YES | BARBARA OUTZEN | Dan Lerman
CNAS | 19P000186 | FS | SL5-NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION | PIERCE | 319 | 2018-06-18 | COMPLETE | Complete as of 11/8/18 |  |  | YES | BARBARA OUTZEN | Dan Lerman
CAMPUS | 19P000188 | FS | SL5-PAINT - HALLWAY DOORS & INSIDE RESTROOMS | LIFE SCIENCE | CR2500 | 2018-08-16 | CANCELED BY FS | Reviewing campus standards for these project requests. |  |  |  | ESTELLA DAVALOS | Paul Ditty
CNAS | 19P000189 | FS | SL5-PHYSICS- WALL HOLES PATCH | PHYSICS | 3036 | 2018-08-16 | CANCELED BY CLIENT | Duplicate work order to 19P000049. Work to be completed on other project. |  |  |  | JAZMIN CHAVEZ | Dan Lerman
CNAS | 19P000191 | FS | SL5-PATCH AND PAINT HINDERAKER BASEMENT | HINDERAKER |  | 2018-08-20 | COMPLETE | Complete as of 11/8/18 |  | 34 |  | RONDA INZUNZA | Paul Ditty
BAS | 19P000192 | FS | SL5-MAIL-PAINTING | MAIL |  | 2018-08-20 | COMPLETE | Complete as of 11/8/18 |  | 10 |  | PRISCILLA MARTIN | Paul Ditty
CHASS | 19P000194 | FS | SL5-PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 | HUM & SOC SC | 3304 | 2018-08-20 | COMPLETE | Complete as of 11/8/18 |  | 8 |  | CHRISTY GRAY | Paul Ditty
CHASS | 19P000195 | FS | SL5-HUM & SOC SC-ROOM PAINTING | HUM & SOC SC | 2003 | 2018-08-21 | COMPLETE | Complete as of 11/8/18 |  | 12 |  | CHRISTY GRAY | Paul Ditty
CHASS | 19P000196 | FS | SL5-PAINT OFFICE AT UNIVERSITY THEATER | THTR WKSH |  | 2018-08-21 | COMPLETE | Complete as of 11/8/18 |  | 15 |  | JULIE SALGADO | Paul Ditty
CHASS | 19P000201 | FS | SL5-PATCH AND PAINT THE WALLS | CHASS INT S | 3111A | 2018-08-22 | COMPLETE | Complete as of 11/8/18 |  | 18 |  | RYAN MARIANO | Paul Ditty
BCOE | 19P000205 | FS | SL5-LABORATORY RENOVATION FOR NEW FACULTY | BOURNS | A0328 | 2018-08-23 | COMPLETE | Plans under review by Fire Marshal; clarification required on sprinkler system. |  | 4 | YES | MARGARET SOUDER | Dan Lerman
BAS | 19P000208 | FS | SL5-PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | THE PLAZA |  | 2018-08-14 | CANCELED BY CLIENT | Canceled per customer on priority list 9/17/18 |  | Canceled |  | CARLA CHAPPLE | Dan Lerman
CAMPUS | 19P000211 | FS | SL5-LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | LIFE SCIENCE | 2545 | 2018-08-24 | CANCELED BY FS | Reviewing campus standards for these project requests. |  |  |  | ESTELLA DAVALOS
CNAS | 19P000213 | FS | SL5-NEEDS FOR NEW WALL DISPLAY (MONITOR) | BIOLOGICAL SCI | 3101 | 2018-08-24 | CANCELED BY CLIENT | Duplicate request to 19P000031; Work to be completed on other project. |  |  |  | ESTELLA DAVALOS
CNAS | 19P000214 | FS | SL5-PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT | PHYSICS | 3005 | 2018-08-24 | COMPLETE | Complete as of 10/10/18 |  | 2 | YES | MAYELA CASTILLO | Paul Ditty
BAS | 19P000215 | FS | SL5-SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 | HUB | 346 | 2018-08-24 | COMPLETE | Coordinating movement of equipment and utility connections. |  | 9 |  | GUSTAVO PLASCENCIA | John Peraino
CHASS | 19P000216 | FS | SL5-HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT | HUM & SOC SC | 1214 | 2018-08-27 | COMPLETE | Complete as of 11/8/18 |  | 13 |  | ALLISON ROGERS | Paul Ditty
CHASS | 19P000220 | FS | SL5-ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT | ARTS | 333 | 2018-08-28 | COMPLETE | Screen to be reinstalled on Friday 11/9/18. |  | 1 |  | SONJA SEKELY-ROWLAND | Dan Lerman
CHASS | 19P000221 | FS | SL5-PATCH, PAINTING, AND REGULAR CLEANING OF A126A | OLMSTED | A0126A | 2018-08-28 | COMPLETE | Complete as of 11/8/18 |  | 14 |  | TOYA ADAMS | Paul Ditty
BAS | 19P000222 | FS | SL5-PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER | PRINT MOD |  | 2018-10-02 | COMPLETE |  |  |  |  | RICHARD GEIGER | Paul Ditty
CHASS | 19P000226 | FS | SL5-PAINT OFFICE HMNSS 3304 | HUM & SOC SC | 3304 | 2018-08-28 | CANCELED BY CLIENT | Duplicate request; project to be completed on 19P000194 |  | Canceled |  | LEANN GILMER | Paul Ditty
CHASS | 19P000226 | FS | SL5-PAINT OFFICE HMNSS 3304 | HUM & SOC SC | 3304 | 2018-08-28 | CANCELED BY CLIENT | Duplicate to 19P00014; work to be completed on original project. |  | Duplicate |  | LEANN GILMER | Paul Ditty
CNAS | 19P000230 | FS | SL5-NEW FACULTY OFFICE FOR PATCHWORK/PAINT | GEOLOGY | 1242A | 2018-08-30 | COMPLETE | Complete as of 10/10/18 |  | 7 | YES | KAREN CATO | Paul Ditty
CNAS | 19P000231 | FS | SL5-OLMH 1428 PATCH AND PAINT | OLMSTED | 1428 | 2018-08-30 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 48 |  | ANDREW CABRERO | Paul Ditty
BAS | 19P000233 | FS | SL5-PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | MAIL | 884 | 2018-09-04 | CANCELED BY FS | FS to coordinate with customer to scope the work. |  | 12 |  | AMY EVERETT
CNAS | 19P000234 | FS | SL5-PHYSICS 3005-WALL HOLES PATCH | PHYSICS | 3005N | 2018-09-04 | CANCELED BY FS | Duplicate work request. |  | Canceled |  | JAZMIN CHAVEZ | Paul Ditty
VC-UNIV.ADV. | 19P000238 | FS | SL5-PATCH & PAINT HINDERAKER 1136 | HINDERAKER | 1136 | 2018-09-05 | COMPLETE | Pending completion of one room outstanding for scheduling. |  | 1 |  | NAYSIA CALDWELL | Paul Ditty
PLANNING & BUDGET | 19P000241 | FS | SL5-PATCH/PAINT IN OFFICE 2122 HINDERAKER | HINDERAKER | 2122 | 2018-09-06 | CANCELED BY CLIENT | Canceled per customer call on 9/13/18 |  | 1 |  | MILLY PAREDEZ | Paul Ditty
CNAS | 19P000242 | FS | SL5-PAINT OFFICE | COLLEGE BLDG NO | 210 | 2018-09-06 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 47 |  | RONDA INZUNZA | Paul Ditty
CNAS | 19P000244 | FS | SL5-PATCH & PAINT GEOLOGY | GEOLOGY | 2258A | 2018-09-06 | COMPLETE | Complete as of 10/22/18. |  | 10 | YES | AMBER RHEMREV | Paul Ditty
CNAS | 19P000246 | FS | SL5-PHYSICS - PATCH AND PAINT | PHYSICS | 3007N | 2018-09-07 | COMPLETE | Complete as of 10/10/18 |  | 46 |  | MAYELA CASTILLO | Paul Ditty
BAS | 19P000247 | FS | SL5-LOTHIAN FIRST FLOOR COMMON AREA FLOORING | LOTHIAN HALL |  | 2018-09-10 | COMPLETE | Complete as of 10/22/18. |  |  |  | RICHARD GEIGER | Jess Hernandez
SOM | 19P000248 | FS | SL5-SOME--SOME INSTALL ELECTRICAL 1682 | SOM EDUC | 1682 | 2018-09-10 | COMPLETE | FS to coordinate with client to scope the work. |  | 2 |  | DEBORAH TRUJILLO
SOM | 19P000249 | FS | SL5-SOME-INSTALL LOCKERS | SOM EDUC |  | 2018-09-07 | CANCELED BY FS | Lockers on order by customer; upon arrival to be installed. |  | 3 |  | DEBORAH TRUJILLO | Dan Lerman
BCOE | 19P000250 | FS | SL5-BOURNS A303-PAINT AND PATCH WALL | BOURNS | A0303 | 2018-09-10 | COMPLETE | Complete as of 10/10/18 |  | 5 | YES | JUANA GUERRERO | Paul Ditty
CNAS | 19P000251 | FS | SL5-CHEM SCI 428-PATCH DRY WALL HOLES | CHEMICAL SCI | 428 | 2018-09-10 | COMPLETE | Complete as of 10/10/18 |  | 8 | YES | KEVIN KOU | Paul Ditty
CHASS | 19P000253 | FS | SL5-ARTS RENOVATION | ARTS | 157 | 2018-04-17 | COMPLETE | Complete as of 9/21/18 |  |  |  | PAUL RICHARDSON | Dan Lerman
SPP | 19P000255 | FS | SL5-CHASS INT N REMODEL - 4022 PATCH AND PAINT | CHASS INT N | 4022 | 2018-09-10 | COMPLETE | Complete as of 10/10/18 |  | 1 | YES | CHRISTINA WONG | Paul Ditty
SPP | 19P000256 | FS | SL5-CHASS REMODEL - 4146 PATCH AND PAINT | CHASS INT S | 4146 | 2018-09-10 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 3 | YES | CHRISTINA WONG
SPP | 19P000263 | FS | SL5-CHASS NORTH REMODEL - 4009 PATCH AND PAINT | CHASS INT N | 4009 | 2018-09-11 | COMPLETE | Complete as of 11/8/18 |  | 2 | YES | CHRISTINA WONG | Paul Ditty
ATHLETICS | 19P000265 | FS | SL5-ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 | ATH DANCE |  | 2018-09-11 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 1 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 19P000266 | FS | SL5-ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | ATH DANCE |  | 2018-09-11 | CANCELED BY FS | FS to coordinate with client to schedule work for completion. |  | 2 |  | JOHNATHAN JENSEN | Paul Ditty
ATHLETICS | 19P000269 | FS | SL5-ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | ATH DANCE |  | 2018-09-12 | CANCELED BY FS | Project is not within the purview for completion; condition is fair and usable. |  | 5 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000270 | FS | SL5-ATH DANCE-WEIGHT ROOM DROP DOWN CEILING | ATH DANCE | 78 | 2018-09-12 | COMPLETE | FS to coordinate with customer to scope the work. |  | 14 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000275 | FS | SL5-SOFTBALL STG PRESS BOX AC ADDITION | SOFTBALL STG |  | 2018-09-12 | CANCELED BY CLIENT | FS to coordinate with customer to scope the work. |  | 6 |  | JOHNATHAN JENSEN
ATHLETICS | 19P000276 | FS | SL5-TRACK BLEACH-PUBLIC RESTROOMS UPGRADE | TRACK BLEACH |  | 2018-09-12 | TO BE PERFORMED BY PD&C | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. |  | 16 |  | JOHNATHAN JENSEN
BCOE | 19P000278 | FS | SL5-REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR | BOURNS | A0165 | 2018-08-03 | COMPLETE | Scheduling work for completion |  | 1 | YES | NANCY FORD | Dan Lerman
SoB | 19P000280 | FS | SL5-ANDERSON HALL PAINT ONLY | ANDERSON 2 | 113 | 2018-09-13 | COMPLETE |  |  | 2 |  | ANGELA CHANG | Paul Ditty
CAMPUS | 19P000284 | FS | SL5-GEOLOGY ACCOMMODATION DOCK DOORS | GEOLOGY |  | 2018-08-07 | COMPLETE | Coordinating work for completion. |  | Canceled |  | DEBORAH TERAO | Chris Pillen
CNAS | 19P000287 | FS | SL5-URGENT: PAINT SHOP TO PATCH AND PAINT | MAT SCI ENGR | 229 | 2018-09-19 | COMPLETE | Complete as of 10/22/18. |  |  |  | HONG XU | Paul Ditty
CNAS | 19P000291 | FS | SL5-MSE HELIUM RECOVERY SYSTEM | MAT SCI ENGR | 205 | 2017-07-24 | COMPLETE | Work has been completed; FS teams verifying completion and quality check of work. |  | 9 |  | MAYELA CASTILLO | Dan Lerman
ITS | 19P000293 | FS | SL5-PAINT ESTIMATE REQUEST | TELEPHONE |  | 2018-08-21 | CANCELED BY CLIENT | Canceled by Customer 10/24/18 |  |  |  | TAMI FRIEDRICH | Paul Ditty
ATHLETICS | 19P000295 | FS | SL5-PATCH & PAINT | ATH DANCE | 50B | 2018-09-12 | COMPLETE | FS to coordinate with client to schedule work for completion. |  | 12 |  | JOHNATHAN JENSEN | Paul Ditty
CAMPUS | 19P000296 | FS | SL5-MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB | MAT SCI ENGR |  | 2018-09-25 | COMPLETE | Plans and permits to be developed for this project. |  |  |  | MILLY PAREDEZ | Dan Lerman
CNAS | 19P000299 | FS | SL5-SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 | SPIETH | 3378 | 2018-09-26 | COMPLETE |  |  | 1 |  | ESTELLA DAVALOS | Paul Ditty
CNAS | 19P000301 | FS | SL5-SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH | SCIENCE LAB1 | 214 | 2018-09-27 | COMPLETE |  |  | 3 |  | AMBER RHEMREV | Paul Ditty
BAS | 19P000307 | FS | SL5-LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK | LOTHIAN HALL |  | 2018-09-11 | COMPLETE | Scheduled work with trades anticipated completion December 2019. |  | 5 |  | EDWIN MELGAR-MEJIA | John Peraino
CHASS | 19P000313 | FS | SL5-HUMANITIIES SOCSCI - PATCH HOLES & PAINT - | HUM & SOC SC | 1203 | 2018-10-03 | COMPLETE |  |  |  |  | CHRISTY GRAY | Paul Ditty
CHASS | 19P000314 | FS | SL5-HUMANITIES - PAINT OFFICE - PAINT SHOP | HUM & SOC SC | 3403 | 2018-10-03 | COMPLETE |  |  | 6 |  | CYNTHIA CARRASCO CANNON | Paul Ditty
BCOE | 19P000316 | FS | SL5-CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL | CHUNG HALL | 449 | 2018-10-03 | COMPLETE | Anticipated completion mid November |  | 12 |  | ROBERT LOPEZ-A | Dan Lerman
CNAS | 19P000318 | FS | SL5-GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE | GEOLOGY | 420 | 2018-10-04 | COMPLETE |  |  | 4 |  | KAREN CATO | Paul Ditty
CNAS | 19P000319 | FS | SL5-ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | ENTOMOLOGY | 139 | 2018-10-04 | CANCELED BY CLIENT |  |  |  |  | WILLIAM SUTTON | Paul Ditty
VC-UNIV.ADV. | 19P000326 | FS | SL5-HINDERAKER - PATCH & PAINT | HINDERAKER | 1136 | 2018-10-08 | COMPLETE |  |  | 2 |  | NAYSIA CALDWELL | Paul Ditty
CNAS | 19P000340 | FS | SL5-PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE | SKYE HALL | 349 | 2018-10-12 | COMPLETE |  |  | 2 |  | VICTORIA AVALOS | Paul Ditty
CNAS | 19P000341 | FS | SL5-PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL | PIERCE |  | 2018-10-12 | COMPLETE |  |  | 2 |  | BARBARA OUTZEN | Paul Ditty
CNAS | 19P000346 | FS | SL5-I&Q--PAINTING ROOMS IN THE I&Q | EAST I&Q FAC |  | 2018-10-16 | COMPLETE |  |  |  |  | IMAD BAYOUN | Paul Ditty
CHASS | 19P000364 | FS | SL5-PATCH AND PAINT | CHASS INT S | 3106 | 2018-10-30 | COMPLETE |  |  |  |  | FRANCESCA MOREIRA | Paul Ditty
ENROLLMENT SERVICES | 19P000370 | FS | SL5-PATCH AND PAINT CAMPUS TOURS | STUDENT SERV | 1137 | 2018-11-01 | COMPLETE |  |  | 1 |  | ELIZABETH TATUM | Paul Ditty
ITS | 19P000373 | FS | SL5-URGENT-INSTALL RECPTACLE, ENCLOSURE & MOUNT BRACKET | GERMPLASM | 881 | 2018-11-07 | COMPLETE | mount a bracket to the Network Pole at AgOps. This will include mounting a bracket, an enclosure and a 20 Amp electrical receptacle. |  | 0 |  | Tami Friedrich | Dan Lerman
CHANCELLOR | 19P000375 | FS | SL5-PATCH AND PAINT HOLES | SKYE HALL | 365 | 2018-11-07 | COMPLETE |  |  | 1 |  | FELECIA GARRETT | Paul Ditty
ENROLLMENT SERVICES | 19P000384 | FS | SL5-PATCH HOLES IN WALL AND PAINT | STUDENT SERV | 2234 | 2018-11-20 | COMPLETE |  |  | 1 |  | CHRISTINE SMITH | Paul Ditty
CAP.PROG. | 19P000396 | FS | SL5- TRAILER #14 - CAMPUS INITIATED - STRUCTURE | T14 |  | 2019-01-31 | COMPLETE | Disconnect smoke and fire alarms to two trailers. Trailers are scheduled for demolition on 2/5/19. Ben has plans of trailers to be demolished. |  | 0 |  | Sharyl Murdock | Dan Lerman
PLANNING & BUDGET | 19P000401 | FS | SL5 - PATCH HOLES IN WALL AND PAINT | HINDERAKER | 4148E | 2018-12-18 | COMPLETE |  |  | 1 |  | SHANNON TIMMONS | Paul Ditty
SOM | 19P000408 | FS | SL5 - PATCH & PAINT - 2605 SOM ED | SOM EDUC | 2605 | 2018-12-12 | COMPLETE |  |  | 1 | YES | DEBORAH TRUJILLO | Paul Ditty
CHANCELLOR | 19P000420 | FS | SL5-PATCH AND PAINT WALL | SKYE HALL | 325 | 2018-12-19 | COMPLETE |  |  | 3 |  | REYNA ALARCON | Paul Ditty
ENROLLMENT SERVICES | 19P000428 | FS | SL5--STUDENT SERVICES AVC OFFICE PREPARATION | STUDENT SERV | 3102 | 2019-01-03 | CANCELED BY CLIENT |  |  | 0 |  | ANGIE GRAY
BCOE | 19P000445 | FS | SL5-BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT | BOURNS HALL | B0328D | 2019-01-11 | CANCELED BY FS |  |  | 0 |  | MARGARET SOUDER
SOB | 19P000451 | FS | SL5-ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 | ANDERSON 1 (N) | 58 | 2019-01-15 | COMPLETE |  |  | 1 | YES | ANGELA CHANG | Paul Ditty
BCOE | 19P000453 | FS | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT | CHUNG HALL | 447 | 2019-01-17 | COMPLETE |  |  | 1 | YES | ROBERT LOPEZ-A | Paul Ditty
SOM | 19S000833 | FS | Add access control to entry doors | HECKMAN ICEM | Entry Doors | 2018-07-17 | CANCELED BY CLIENT | Canceled request per conversation with client; customer to coordinate for a contractor to complete project. |  | Canceled |  | BRANDON BARBOSA | Dan Lerman
CHASS | 19W002930 | FS | HOLD - SL5-PATCH HOLES & PAINT - HUMANITIIES SOCSCI | HUM & SOC SC | 1203 | 2018-08-17 | COMPLETE | Complete as of 11/8/18 |  | 11 |  | CHRISTY GRAY | Paul Ditty
CNAS | 19W003012 | FS | SL5-FIX RESTROOMS (PAINT AND FLOORS) | CHAPMAN | 5 | 2018-08-17 | CANCELED BY FS | FS to coordinate with client to schedule work for completion. |  | 51 |  | WILLIAM SUTTON | Paul Ditty
VC-RED | 19W003050 | FS | SL5-SPEITH HALL - PATCH & PAINT HOLE IN WALL | SPIETH | 0359A | 2018-08-21 | COMPLETE | Complete as of 10/10/18 |  | 2 |  | JOHNNY PHAN | Paul Ditty

## Data Validation (hidden)
|  | 1 |  | Data As Of (Scheduled Data Pull) | Date of Previous Report | Proj_Mgr | PM_Ph | PM_Email | Dept |  |  |  |  | CAAN | Official | Building | CNC
0 | 2245 | 18P000030 | 18P000030 | 2018-10-31 | 2018-10-15 | B. Wilson/J. Franklin | 951-827-1485 | blythe.wilson@ucr.edu | PDC | A | 1 | Project Ref No. | Proj_Ref_No | P5186 | BIOLOGICAL SCIENCES | BIOLOGIC SCI | CORE
0 | 2353 |  |  | 2018-11-16 | 2018-10-31 | Blair Fickett |  |  | PDC | B | 2 |  | CPMS_No | P5187 | LATH HOUSE BUILDING B | LATH B FLD16 | CORE
0 | 2359 |  |  | 2018-12-01 | 2018-11-16 | Blythe Wilson | 951-827-1485 | blythe.wilson@ucr.edu | PDC | C | 3 |  | Work_Order_No | P5188 | MITE WASHER BUILDING C | MITE C FLD16 | CORE
0 | 2368 |  |  | 2018-12-16 | 2018-12-01 | CAS |  |  | PDC | D | 4 |  | IRT | P5189 | COMMON COVERED WORKHOUSE BLDG A (PART OF WEST CAMPUS I&Q) | COM WRK FD16 | NON-CORE
0 | 2508 |  |  | 2019-01-01 | 2018-12-16 | Chris Pillen | 951-827-4214 | christopher.pillen@ucr.edu | FS | E | 5 | Organization | Org | P5190 | PLANT TRANSFORMATION FACILITY | PLANT TRANSF | CORE
0 | 2671 |  |  | 2019-01-16 | 2019-01-01 | Cliff Stokes |  |  | FORMER | F | 6 | Project Title | Project_Title | P5192 | EAST CAMPUS INSECTARY AND QUARANTINE FACILITY GREENHOUSE | EAST I&Q GH | CORE
0 | 2682 |  |  | 2019-02-01 | 2019-01-16 | Craig/Chris Pillen | 951-827-4214 | christopher.pillen@ucr.edu | FS | G | 7 | Project Description | Project_Description | P5194 | WINSTON CHUNG HALL | CHUNG HALL | CORE
0 | 2687 |  |  | 2019-02-16 | 2019-02-01 | D. Hecht/J. Franklin | 951-827-7358 | drew.hecht@ucr.edu | PDC | H | 8 | Building | t_CPMS_Data.Building | P5195 | MATERIALS SCIENCE & ENGINEERING | MAT SCI ENGR | CORE
0 | 2696 |  |  | 2019-03-01 | 2019-02-16 | Dan Lerman | 951-827-6224 | daniel.lerman@ucr.edu | FS | I | 9 |  | t_Building.Building | P5196 | GENOMICS BUILDING | GENOMICS | CORE
0 | 2725 |  |  | 2019-03-16 | 2019-03-01 | Daryl Korluck |  |  | FORMER | J | 10 | Room | Room | P5197 | ALUMNI & VISITORS CENTER | ALUM VISITOR | NON-CORE
0 | 2747 |  |  | 2019-04-01 | 2019-03-16 | Dave Bomba | 951-827-1412 | dave.bomba@ucr.edu | PDC | K | 11 | Current Status | Current_Status | P5198 | UCR CHILD DEVELOPMENT CENTER NORTH | CHILD DEV N | CORE
0 | 2774 |  |  | 2019-04-16 | 2019-04-01 | Drew Hecht | 951-827-7358 | drew.hecht@ucr.edu | PDC | L | 12 |  | Org_Name | P5199 | HIGHLANDER UNION 2 ACTIVITY CENTER | HUB 2 | NON-CORE
0 | 2829 |  |  | 2019-05-01 | 2019-04-16 | Enrico Baez | 951-827-4214 | enrico.baez@ucr.edu | FS | M | 13 | Organization Leader | Org_Leadership | P5200 | GREENHOUSE #9 | GH09 | CORE
0 | 2839 |  |  | 2019-05-16 | 2019-05-01 | Enrico Baez - Managing Contractor | 951-827-4214 | enrico.baez@ucr.edu | FS | N | 14 | Prioritization Designate | Org_Contact | P5205 | UNIVERSITY OFFICE BUILDING | UNIV OFC BLD | CORE
0 | 2868 |  |  | 2019-06-01 | 2019-05-16 | Fernando Nunez | 951-827-2466 | fernando.nunez@ucr.edu | PDC | O | 15 | Contact | Contact | P5210 | GREENHOUSE #15 | GH15 | CORE
0 | 2899 |  |  |  |  | George MacMullin |  |  | FORMER | P | 16 |  | Contact_2 | P5215 | HOMER D. CHAPMAN HALL | CHAPMAN | CORE
0 | 2900 |  |  |  |  | Jacqueline Norman | 951-827-6316 | jacqueline.norman@ucr.edu | PDC | Q | 17 | Project Manager | Proj_Mgr | P5216 | CHICKEN COOP #1 | CHICK COOP 1 | NON-CORE
0 | 2916 |  |  |  |  | Jason Williams |  | jason.williams@ucr.edu | FS | R | 18 | PD&C Org Priority No. | Org_Priority | P5217 | PHYSICAL PLANT STORAGE UNIT | PHYS PL STOR | CORE
0 | 2952 |  |  |  |  | Jerrod Walters | 951-827-6955 | jerrod.walters@ucr.edu | PDC | S | 19 | FS Org Priority No. | FS_Priority | P5218 | THE COTTAGE | COTTAGE | NON-CORE
0 | 2970 |  |  |  |  | Jess Hernandez | 951-827-4214 | jesus.hernandez@ucr.edu | FS | T | 20 | For Faculty Hire | For_Faculty_Hire | P5219 | WORKMAN'S COTTAGE #2 | WORKMN COT 2 | NON-CORE
0 | 2974 |  |  |  |  | John Franklin | 951-827-6953 | john.franklin@ucr.edu | PDC | U | 21 | PD&C Approved Budget | Approved_Budget | P5220 | WORKMAN'S COTTAGE #3 | WORKMN COT 3 | NON-CORE
0 | 3005 |  |  |  |  | John Peraino | 951-827-2121 | john.peraino@ucr.edu | FS | V | 22 | FS Recharge Actuals To Date | FS_Recharge_Costs | P5224 | UNIVERSITY BOOKSTORE | BOOKSTORE | NON-CORE
0 | 3052 |  |  |  |  | Marianne Valenti |  |  | FORMER | W | 23 | Request Date | Project_Initiated | P5230 | STORAGE SHED #8 | STOR 8 | CORE
0 | 3060 |  |  |  |  | Mihai Gavan | 951-827-6959 | mihai.gavan@ucr.edu | PDC | X | 24 | Next Steps | Next_Major_Milestone | P5231 | COLLEGE BUILDING SOUTH | COLL BLDG SO | CORE
0 | 3064 |  |  |  |  | Mihai Gavan-MRB1 |  | mihai.gavan@ucr.edu | PDC | Y | 25 | Start Date | Const_Start | P5241 | ENVIRONMENTAL HEALTH AND SAFETY BUILDING | ENV H AND S | CORE
0 | 3101 |  |  |  |  | N/A | 951-827-4214 |  |  | Z | 26 | Complete Date | Construction_Completion | P5242 | LATHHOUSE #1 | LATH 1 | CORE
0 | 3104 |  |  |  |  | Not Assigned | 951-827-4214 |  |  | AA | 27 | Impact Description | Impact_Description | P5251 | THEATRE WORKSHOP | THTR WKSH | CORE
0 | 3110 |  |  |  |  | Paul Ditty | 951-827-4214 | paul.ditty@ucr.edu | FS | AB | 28 | Impact Date Start | Impact_Date_Start | P5253 | MAIL BUILDING | MAIL | CORE
0 | 3119 |  |  |  |  | R. Amescua/D. Hecht |  | raoul.amescua@ucr.edu | PDC | AC | 29 | Impact Date End | Impact_Date_End | P5254 | BOTANIC GARDENS INFORMATION CENTER | BOTAN INFO C | NON-CORE
0 | 3120 |  |  |  |  | R. Amescua/J. Kaplan |  | raoul.amescua@ucr.edu | PDC | AD | 30 | Project Service Unit | PM_Notes | P5255 | BOTANY & PLANT SCIENCES FIELDHOUSE FIELD 15A | BOT FLDHS15A | NON-CORE
0 | 3175 |  |  |  |  | Raoul Amescua | 951-827-6951 | raoul.amescua@ucr.edu | PDC | AE | 31 |  | PM_Date | P5256 | ENTOMOLOGY MUSEUM | ENTOM MUSEUM | CORE
0 | 3195 |  |  |  |  | Robert Corey |  |  | FORMER | AF | 32 |  | Scope_Date | P5258 | GLASSHOUSE FIELD 16 #45 | GH 16 45 | CORE
0 | 3218 |  |  |  |  | Ron Veloz | 951-827-4214 | ron.veloz@ucr.edu | FS | AG | 33 |  | Scope_Reviewer | P5259 | GREENHOUSE #2A | GH02A | CORE
0 | 3224 |  |  |  |  | Rowan Reid | 951-827-5825 | rowan.reid@ucr.edu | PDC | AH | 34 |  | Scope_Notes | P5260 | GLASSHOUSE FIELD 16 #46 | GH 16 46 | CORE
0 | 3228 |  |  |  |  | Scott Donnell | 951-827-4706 | scott.donnell@ucr.edu | PDC | AI | 35 |  | Scope_Complete | P5261 | MARLAN & ROSEMARY BOURNS HALL | BOURNS | CORE
0 | 3233 |  |  |  |  | Tameesha Hayes |  |  | FORMER | AJ | 36 |  | Owner | P5263 | UNIVERSITY LABORATORY BUILDING | UNIV LAB BLD | CORE
0 | 3234 |  |  |  |  | Uma R. | 951-827-5610 | uma.ramasubramanian@ucr.edu | PDC | AK | 37 |  | IRT? | P5265 | TRAILER #10A | T10A | CORE
0 | 3237 |  |  |  |  | xxxxx |  |  |  | AL | 38 |  | Requested Year | P5266 | TRAILER #9A | T9A | CORE
0 | 3255 |  |  |  |  | Yvonne Lujan | 951-827-5154 | yvonne.lujan@ucr.edu | PDC | AM | 39 |  | Data Pulled On | P5267 | GLASSHOUSE FIELD 16 #26 | GH 16 26 | CORE
0 | 3270 | [12 empty] | P5268 | STORAGE SHED #5 | STOR 5 | CORE
0 | 3271 | [12 empty] | P5269 | GLASSHOUSE FIELD 16 #27 | GH 16 27 | CORE
0 | 3272 | [12 empty] | P5270 | GARAGE COTTAGE #3 | GAR C3 | CORE
0 | 3275 | [12 empty] | P5271 | BARN STABLE | BARN STABLE | NON-CORE
0 | 3280 | [12 empty] | P5272 | PARKING SERVICES BUILDING | PARKING SERV | NON-CORE
0 | 3286 | [12 empty] | P5273 | GLASSHOUSE FIELD 16 #22 | GH 16 22 | CORE
0 | 3293 | [12 empty] | P5274 | GARAGE COTTAGE #1 | GAR C1 | CORE
0 | 3300 | [12 empty] | P5275 | GREENHOUSE #6 | GH06 | CORE
0 | 3315 | [12 empty] | P5276 | GREENHOUSE #7 | GH07 | CORE
0 | 3319 | [12 empty] | P5277 | GREENHOUSE #8 | GH08 | CORE
0 | 3326 | [12 empty] | P5278 | GREENHOUSE #10 | GH10 | CORE
0 | 3341 | [12 empty] | P5279 | GREENHOUSE #11 | GH11 | CORE
0 | 3345 | [12 empty] | P5280 | GREENHOUSE #12 | GH12 | CORE
0 | 3354 | [12 empty] | P5281 | GREENHOUSE #13 | GH13 | CORE
0 | 3363 | [12 empty] | P5282 | GREENHOUSE #21 | GH21 | CORE
0 | 3366 | [12 empty] | P5284 | GREENHOUSE #16 | GH16 | CORE
0 | 3367 | [12 empty] | P5285 | RESTROOMS & TICKET BOOTH BUILDING | TICKET BOOTH | CORE
0 | 3376 | [12 empty] | P5286 | RESTROOM / MAINTENANCE | RSTRM/MAINT | CORE
0 | 3382 | [12 empty] | P5287 | STORAGE BUILDING PLANT PATHOLOGY FIELD 16E | STOR PL PATH | CORE
0 | 3383 | [12 empty] | P5288 | NEMATOLOGY MICROPLOT STORAGE BUILDING FIELD 15A | NEM MICRO ST | CORE
0 | 3385 | [12 empty] | P5289 | EAST CAMPUS INSECTARY AND QUARANTINE FACILITY | EAST I&Q FAC | CORE
0 | 3390 | [12 empty] | P5290 | HAY BARN | HAY BN | CORE
0 | 3392 | [12 empty] | P5291 | TURF PLOT STORAGE AGRICULTURAL OPERATIONS | TURF PL STOR | CORE
0 | 3393 | [12 empty] | P5292 | STORAGE BUILDING AT LOADING DOCK OF PIERCE HALL | STOR PRCE | CORE
0 | 3395 | [12 empty] | P5293 | GLASSHOUSE FIELD 16 #25 | GH 16 25 | CORE
0 | 3396 | [12 empty] | P5295 | CENTRAL UTILITY PLANT | CNTRL UTL PL | CORE
0 | 3397 | [12 empty] | P5296 | GLASSHOUSE FIELD 16 #9 | GH 16 09 | CORE
0 | 3401 | [12 empty] | P5297 | GLASSHOUSE FIELD 16 #23 | GH 16 23 | CORE
0 | 3403 | [12 empty] | P5298 | SHED BUILDING FIELD 16 #25 | SHED 16 25 | CORE
0 | 3407 | [12 empty] | P5299 | GLASSHOUSE FIELD 16 #10 | GH 16 10 | CORE
0 | 3408 | [12 empty] | P5300 | GLASSHOUSE FIELD 16 #11 | GH 16 11 | CORE
0 | 3411 | [12 empty] | P5302 | EQUIPMENT SHED | EQUIP SHED | CORE
0 | 3413 | [12 empty] | P5304 | INSECTICIDE COMPOUNDING & STORAGE BUILDING | INSECT COMP | CORE
0 | 3415 | [12 empty] | P5305 | STORED PRODUCTS INSECTICIDE BUILDING | SPI | CORE
0 | 3421 | [12 empty] | P5307 | HUMANITIES & SOCIAL SCIENCES | HUM & SOC SC | CORE
0 | 3426 | [12 empty] | P5308 | SOUTH LOCKERROOM & CONCESSION STAND | S LCKRM/CONC | CORE
0 | 3427 | [12 empty] | P5310 | WEST LOCKERROOM & CLUBHOUSE CONCESSION STAND | W LCKRM/CONC | CORE
0 | 3428 | [12 empty] | P5311 | JEANETTE AND RUPERT COSTO HALL | COSTO HALL | NON-CORE
0 | 3430 | [12 empty] | P5312 | LATHHOUSE #32 | LATH 32 | CORE
0 | 3432 | [12 empty] | P5315 | LATHHOUSE #36 | LATH 36 | CORE
0 | 3437 | [12 empty] | P5316 | LIFE SCIENCES | LIFE SCIENCE | CORE
0 | 3438 | [12 empty] | P5319 | HERBARIUM | HERBARIUM | CORE
0 | 3439 | [12 empty] | P5321 | STORAGE SHED #37 | STOR 37 | CORE
0 | 3441 | [12 empty] | P5322 | TOMAS RIVERA LIBRARY | RIVERA LIB | CORE
0 | 3452 | [12 empty] | P5323 | HERMAN T. SPIETH HALL | SPIETH | CORE
0 | 3453 | [12 empty] | P5324 | STORAGE SHED #49 | STOR 49 | CORE
0 | 3455 | [12 empty] | P5325 | A. GARY ANDERSON HALL 1 | ANDERSON 1 | CORE
0 | 3458 | [12 empty] | P5326 | COBALT 60 BUILDING #38 | COBALT 60 | CORE
0 | 3459 | [12 empty] | P5327 | PHYSICAL PLANT STORAGE UNIT 2 | PHYS PL STR2 | CORE
0 | 3460 | [12 empty] | P5328 | HAZARDOUS WASTE STORAGE UNIT 1 | HAZ WST STR1 | CORE
0 | 3462 | [12 empty] | P5329 | HAZARDOUS WASTE STORAGE UNIT 2 | HAZ WST STR2 | CORE
0 | 3463 | [12 empty] | P5330 | TRAILER #21 3984 | T21 3984 | CORE
0 | 3466 | [12 empty] | P5334 | ATHLETICS AND DANCE BUILDING | ATH DANCE | CORE
0 | 3467 | [12 empty] | P5335 | GEOLOGY BUILDING | GEOLOGY | CORE
0 | 3469 | [12 empty] | P5336 | GLASSHOUSE FIELD 16 #24A | GH 16 24A | CORE
0 | 3470 | [12 empty] | P5337 | GLASSHOUSE FIELD 16 #24B | GH 16 24B | CORE
0 | 3471 | [12 empty] | P5338 | GLASSHOUSE FIELD 16 #24C | GH 16 24C | CORE
0 | 3472 | [12 empty] | P5339 | GLASSHOUSE FIELD 16 #24D | GH 16 24D | CORE
0 | 3474 | [12 empty] | P5340 | PUMPHOUSE #2 | PUMP 2 | CORE
0 | 3476 | [12 empty] | P5341 | ALFRED M. BOYCE HALL | BOYCE | CORE
0 | 3478 | [12 empty] | P5342 | HERBERT JOHN WEBBER HALL | WEBBER | CORE
0 | 3481 | [12 empty] | P5343 | ABERDEEN-INVERNESS RESIDENCE HALL | ABER INVER | NON-CORE
0 | 3482 | [12 empty] | P5344 | GLASSHOUSE FIELD 16 #28 | GH 16 28 | CORE
0 | 3484 | [12 empty] | P5345 | ASBESTOS ABATEMENT & EMERGENCY RESPONSE EQUIP/SUPPLY | ABAT EMG RSP | NON-CORE
0 | 3486 | [12 empty] | P5346 | DECAY STORAGE UNIT 1 | DECAY STOR 1 | CORE
0 | 3488 | [12 empty] | P5347 | DECAY STORAGE UNIT 2 | DECAY STOR 2 | CORE
0 | 3490 | [12 empty] | P5348 | WAREHOUSE #2 | WHSE 2 | CORE
0 | 3491 | [12 empty] | P5349 | FARM GROUP E WAREHOUSE #1 | FARM E | CORE
0 | 3496 | [12 empty] | P5350 | GROWTH CHAMBER BUILDING | GRTH CH BLDG | CORE
0 | 3498 | [12 empty] | P5351 | ENTOMOLOGY POULTRY BUILDING | ENT PLTRY BD | CORE
0 | 3499 | [12 empty] | P5353 | INSECT LABORATORY #39 | INSECT 39 | CORE
0 | 3503 | [12 empty] | P5354 | GORDON S. WATKINS HALL | WATKINS | CORE
0 | 3504 | [12 empty] | P5355 | SCREENHOUSE BOTANY | SCRNHSE BOT | CORE
0 | 3505 | [12 empty] | P5356 | STORAGE SHED #6 | STOR 6 | CORE
0 | 3514 | [12 empty] | P5357 | A. GARY ANDERSON HALL 2 | ANDERSON 2 | CORE
0 | 9055 | [12 empty] | P5358 | THE BARN | BARN | NON-CORE
0 | 17P000254 | [12 empty] | P5359 | SUPERINTENDENT'S GARAGE | SUPERINT GAR | NON-CORE
0 | 17W012504 | [12 empty] | P5360 | SUPERINTENDENT'S COTTAGE | SUPERINT COT | NON-CORE
0 | 18P000027 | [12 empty] | P5361 | INSECT LABORATORY #44 | INSECT 44 | CORE
0 | 18P000028 | [12 empty] | P5363 | PLANT DRYING BUILDING | PLNT DRY BLD | CORE
0 | 18P000029 | [12 empty] | P5364 | CORPORATION YARD PHYSICAL PLANT WAREHOUSE | CORP PP WHSE | CORE
1 | 18P000030 | [12 empty] | P5365 | PENTLAND HILLS RESIDENCE HALL A | PENTLAND A | NON-CORE
0 | 18P000094 | [12 empty] | P5367 | SATELLITE CHILLER PLANT | SAT CHIL PL | CORE
0 | 18P000095 | [12 empty] | P5369 | PENTLAND HILLS RESIDENCE HALL | PENTLAND I | NON-CORE
0 | 18P000099 | [12 empty] | P5371 | GLASSHOUSE FIELD 16 #47 | GH 16 47 | CORE
0 | 18P000106 | [12 empty] | P5372 | CHASS INTERDISCIPLINARY SOUTH | CHASS INT S | CORE
0 | 18P000111 | [12 empty] | P5373 | PSYCHOLOGY BUILDING | PSYCHOLOGY1 | CORE
0 | 18P000117 | [12 empty] | P5374 | GREENHOUSE #1 RESEARCH | GH01 RESRCH | CORE
0 | 18P000118 | [12 empty] | P5375 | GLASSHOUSE FIELD 16 #48 | GH 16 48 | CORE
0 | 18P000121 | [12 empty] | P5376 | TRAILER CNAS (Surge Trailer) | T CNAS | CORE
0 | 18P000122 | [12 empty] | P5377 | SHED BUILDING TRACTOR | SHED TRACTOR | CORE
0 | 18P000126 | [12 empty] | P5378 | GREENHOUSE #2 RESEARCH | GH03 RESRCH | CORE
0 | 18P000194 | [12 empty] | P5380 | CAMPUS SURGE | CAMPUS SURGE | CORE
0 | 18P000198 | [12 empty] | P5381 | COMPUTING & COMMUNICATIONS CENTER | ITS CENTER | CORE
0 | 18P000201 | [12 empty] | P5382 | COMPUTING & COMMUNICATIONS ELECTRIC CART CARPORT | ITS CARPORT | CORE
0 | 18P000205 | [12 empty] | P5383 | UNIVERSITY LECTURE HALL | UNIV LEC HAL | CORE
0 | 18P000209 | [12 empty] | P5385 | TRAILER BIOMEDICAL SCIENCES #1 | T BIOMED1 | CORE
0 | 18P000214 | [12 empty] | P5386 | EH&S TRIPLE WIDE TRAILER | T EH&S | CORE
0 | 18P000215 | [12 empty] | P5387 | VIVARIA TRAILER | T VIVARIA | CORE
0 | 18P000221 | [12 empty] | P5388 | ENVIRONMENTAL HEALTH AND SAFETY EXPANSION | ENV HLTHSFTY | CORE
0 | 18P000223 | [12 empty] | P5391 | BOTANIC GARDENS RESTROOM | BOTGDN RSTRM | NON-CORE
0 | 18P000226 | [12 empty] | P5393 | METEOROLOGICAL BUILDING | METEOR BLDG | CORE
0 | 18P000227 | [12 empty] | P5396 | UCR CHILD DEVELOPMENT SOUTH | CHILD DEV S | NON-CORE
0 | 18P000247 | [12 empty] | P5397 | SCHOOL OF EDUCATION CLINIC | EDUC CLINIC | CORE
0 | 18P000252 | [12 empty] | P5398 | PARKING TRAILER 1 | PARKING T1 | NON-CORE
0 | 18P000256 | [12 empty] | P5399 | PARKING TRAILER 2 | PARKING T2 | NON-CORE
0 | 18P000257 | [12 empty] | P5400 | PARKING TRAILER 3 | PARKING T3 | NON-CORE
0 | 18P000258 | [12 empty] | P5402 | Arabadopsis 1 | ARAB 1 | NON-CORE
0 | 18P000261 | [12 empty] | P5403 | CHASS INTERDISCIPLINARY NORTH | CHASS INT N | CORE
0 | 18P000267 | [12 empty] | P5404 | HIGHLANDER UNION BUILIDNG | HUB | NON-CORE
0 | 18P000269 | [12 empty] | P5405 | HIGHLANDER UNION COFFEE PAVILION | HUB COFFEE | NON-CORE
0 | 18P000270 | [12 empty] | P5406 | SCHOOL OF MEDICINE HEALTH SCIENCE RESEARCH BUILDING | SOM RSCH | CORE
0 | 18P000273 | [12 empty] | P5408 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16A | GH 16-54 ENT | CORE
0 | 18P000274 | [12 empty] | P5409 | STORAGE SHED #1 | STOR 1 | CORE
0 | 18P000281 | [12 empty] | P5410 | STORAGE SHED #2 | STOR 3 | CORE
0 | 18P000282 | [12 empty] | P5411 | ARTS BUILDING FINE ARTS SEISMIC FACILITY | ARTS | CORE
0 | 18P000284 | [12 empty] | P5412 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16B | GH 16-55 ENT | CORE
0 | 18P000287 | [12 empty] | P5413 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16C | GH 16-56 ENT | CORE
0 | 18P000288 | [12 empty] | P5414 | CHEMICAL SCIENCES | CHEMICAL SCI | CORE
0 | 18P000292 | [12 empty] | P5415 | CANYON CREST KIOSK | KIOSK 2 | NON-CORE
0 | 18P000293 | [12 empty] | P5416 | SCIENCE LABORATORIES 1 | SCIENCE LAB1 | CORE
0 | 18P000294 | [12 empty] | P5417 | ENTOMOLOGY BUILDINGS SEISMIC REPLACEMENT | ENTOMOLOGY | CORE
0 | 18P000295 | [12 empty] | P5418 | RAYMOND L. ORBACH SCIENCE LIBRARY | ORBACH LIB | CORE
0 | 18P000296 | [12 empty] | P5419 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16D | GH 16-57 ENT | CORE
0 | 18P000297 | [12 empty] | P5420 | ENTOMOLOGY GREENHOUSE REPLACEMENT 16E | GH 16-58 ENT | CORE
0 | 18P000300 | [12 empty] | P5421 | BOTANIC GARDENS HOUSE | BOT GDN HSE | NON-CORE
0 | 18P000310 | [12 empty] | P5422 | GLASSHOUSE FIELD 8 AIR POLLUTION | GH5 | CORE
0 | 18P000312 | [12 empty] | P5423 | GLASSHOUSE FIELD 7 AIR POLLUTION | GH4 | CORE
0 | 18P000313 | [12 empty] | P5424 | LATHHOUSE #8 | LATH 8 | CORE
0 | 18P000314 | [12 empty] | P5425 | LATHHOUSE #3 | LATH 3 | CORE
0 | 18P000315 | [12 empty] | P5426 | HEADHOUSE STORAGE BUILDING | HH STOR | CORE
0 | 18P000318 | [12 empty] | P5427 | SOIL FACILITY BUILDING | SOIL BLDG | CORE
0 | 18P000321 | [12 empty] | P5428 | STORAGE BUILDING RADIOACTIVE MATERIAL | STOR RA | CORE
0 | 18P000324 | [12 empty] | P5430 | AGRICULTURE EXPERIMENT STATION STORAGE BUILDING | AES STOR | CORE
0 | 18P000328 | [12 empty] | P5434 | GLASSHOUSE FIELD 16 #50 | GH 16 50 | CORE
0 | 18P000329 | [12 empty] | P5435 | EHS STORAGE 1 | EHS STOR 1 | CORE
0 | 18P000337 | [12 empty] | P5436 | EHS STORAGE 2 | EHS STOR 2 | CORE
0 | 18P000341 | [12 empty] | P5437 | EHS STORAGE 3 | EHS STOR 3 | CORE
0 | 18P000343 | [12 empty] | P5438 | EHS STORAGE 4 | EHS STOR 4 | CORE
0 | 18P000344 | [12 empty] | P5439 | EHS STORAGE 5 | EHS STOR 5 | CORE
0 | 18P000346 | [12 empty] | P5440 | 4558 SANDANO STREET | 4558 SANDANO | NON-CORE
0 | 18P000347 | [12 empty] | P5441 | 4566 SANDANO STREET | 4566 SANDANO | NON-CORE
0 | 18P000348 | [12 empty] | P5442 | 1871 ESCALANTE WAY | 1871 ESCALAN | NON-CORE
0 | 18P000349 | [12 empty] | P5443 | 4531 SANDANO STREET | 4531 SANDANO | NON-CORE
0 | 18P000351 | [12 empty] | P5444 | 4522 SANDANO STREET | 4522 SANDANO | NON-CORE
0 | 18P000353 | [12 empty] | P5445 | 4538 SANDANO STREET | 4538 SANDANO | NON-CORE
0 | 18P000354 | [12 empty] | P5446 | POLICE TRAILER | POLICE TRLR | CORE
0 | 18P000356 | [12 empty] | P5449 | GENOMICS SHED | GENOM SHED | CORE
0 | 18P000363 | [12 empty] | P5451 | EDGEMOOR HOUSE | EDGEMOOR HSE | NON-CORE
0 | 18P000367 | [12 empty] | P5452 | EDGEMOOR GARAGE | EDGEMOOR GAR | NON-CORE
0 | 18P000369 | [12 empty] | P5453 | GARAGE COTTAGE #2 | GAR C2 | CORE
0 | 18P000373 | [12 empty] | P5455 | TRAILER CECERT 1 | T CECERT 1 | NON-CORE
0 | 18P000379 | [12 empty] | P5457 | PRINTING MODULAR | PRINT MOD | NON-CORE
0 | 18P000380 | [12 empty] | P5460 | WOODSHED | WOODSHED | CORE
0 | 18P000381 | [12 empty] | P5461 | FIELD LABORATORY | FLDLAB | CORE
0 | 18P000382 | [12 empty] | P5462 | TRAILER CECERT 2 | T CECERT 2 | NON-CORE
0 | 18P000383 | [12 empty] | P5464 | STORAGE SHED #2 | STOR 2 | CORE
0 | 18P000385 | [12 empty] | P5466 | BIO CONTROL CULTURE BUILDING REPLACEMENT | BIO CTRL BLD | CORE
0 | 18P000387 | [12 empty] | P5467 | RICHARD J HECKMANN INTL CENTER FOR ENTREPRENEURIAL MGMT | HECKMAN ICEM | NON-CORE
0 | 18P000388 | [12 empty] | P5468 | HECKMANN CENTER COMPLEX PH 2 | HECKMANN PH2 | NON-CORE
0 | 18P000389 | [12 empty] | P5469 | VERLEY BARN | VERLEY BARN | CORE
0 | 18P000390 | [12 empty] | P5470 | GLEN MOR HOUSING A | GLEN MOR A | NON-CORE
0 | 18P000391 | [12 empty] | P5471 | GLEN MOR HOUSING B | GLEN MOR B | NON-CORE
0 | 18P000392 | [12 empty] | P5472 | GLEN MOR HOUSING C1 | GLEN MOR C1 | NON-CORE
0 | 18P000394 | [12 empty] | P5473 | GLEN MOR HOUSING D | GLEN MOR D | NON-CORE
0 | 18P000396 | [12 empty] | P5474 | GLEN MOR HOUSING E | GLEN MOR E | NON-CORE
0 | 18P000398 | [12 empty] | P5475 | GLEN MOR HOUSING C2 | GLEN MOR C2 | NON-CORE
0 | 18P000400 | [12 empty] | P5476 | TRAILER ANTHROPOLOGY | T ANTHROP | CORE
0 | 18P000410 | [12 empty] | P5478 | GLASSHOUSE FIELD 3 AIR POLLUTION | GH AP FL2 | CORE
0 | 18P000414 | [12 empty] | P5479 | GLASSHOUSE FIELD 3 AIR POLLUTION | GH AP FL3 | CORE
0 | 18P000415 | [12 empty] | P5480 | IVAN HINDERAKER HALL | HINDERAKER | CORE
0 | 18P000416 | [12 empty] | P5481 | GREENHOUSE #14 | GH14 | CORE
0 | 18P000417 | [12 empty] | P5482 | PATRICK BOYDEN LABORATORY | BOYDEN LAB | CORE
0 | 18P000418 | [12 empty] | P5483 | GREENHOUSE #17 | GH17 | CORE
0 | 18P000419 | [12 empty] | P5484 | CORPORATION YARD D CAR SHELTER | CORP CAR SHD | CORE
0 | 18P000420 | [12 empty] | P5485 | CORPORATION YARD C | CORP C | CORE
0 | 18P000421 | [12 empty] | P5486 | CORPORATION YARD B | CORP B | CORE
0 | 18P000425 | [12 empty] | P5487 | CORPORATION YARD A | CORP A | CORE
0 | 18P000426 | [12 empty] | P5488 | CHANCELLOR'S RESIDENCE | CHANC HOUSE | NON-CORE
0 | 18P000427 | [12 empty] | P5489 | FARM A | FARM A | CORE
0 | 18P000428 | [12 empty] | P5490 | FARM B | FARM B | CORE
0 | 18P000429 | [12 empty] | P5491 | GARAGE 4 CAR | GARAGE 4 CAR | NON-CORE
0 | 18P000432 | [12 empty] | P5492 | SHED BUILDING FIELD 11A | SHED FLD 11A | CORE
0 | 18P000434 | [12 empty] | P5493 | TRAILER #14 | T14 | CORE
0 | 18P000435 | [12 empty] | P5495 | HEALTH SERVICE BUILDING | HEALTH SERV | CORE
0 | 18P000436 | [12 empty] | P5496 | PHYSICAL EDUCATION UTILITY BUILDING | PE UTIL BLDG | CORE
0 | 18P000438 | [12 empty] | P5497 | JOHN W. OLMSTED HALL | OLMSTED | CORE
0 | 18P000439 | [12 empty] | P5498 | HUMANITIES BUILDING | HUMANITIES | CORE
0 | 18P000442 | [12 empty] | P5499 | GLASSHOUSE FIELD 16 #21 | GH 16 21 | CORE
0 | 18P000444 | [12 empty] | P5500 | VEGETABLE CROPS STOREHOUSE | VEG CROP STR | CORE
0 | 18P000445 | [12 empty] | P5501 | LEON DEXTER BATCHELOR HALL | BATCHELOR | CORE
0 | 18P000453 | [12 empty] | P5502 | LOTHIAN RESIDENCE HALL | LOTHIAN HALL | NON-CORE
0 | 18P000454 | [12 empty] | P5503 | HOWARD SAMUEL FAWCETT LABORATORY | FAWCETT LAB | CORE
0 | 18P000456 | [12 empty] | P5504 | PHYSICS BUILDING | PHYSICS | CORE
0 | 18P000459 | [12 empty] | P5505 | GEODESIC DOME BOTANIC GARDENS | GEODESIC DM | CORE
0 | 18P000463 | [12 empty] | P5506 | COLD BOXES ROOF BUILDING | COLD BX ROOF | CORE
0 | 18P000464 | [12 empty] | P5507 | CUSTODIAL & GROUNDS BUILDING | CUST AND GRD | CORE
0 | 18P000468 | [12 empty] | P5508 | W. CONWAY PIERCE HALL | PIERCE | CORE
0 | 18P000469 | [12 empty] | P5509 | TRAILER #7 AIR POLLUTION | T7 AP | CORE
0 | 18P000470 | [12 empty] | P5511 | STUDENT RECREATION CENTER NORTH | SRC NORTH | NON-CORE
0 | 18P000471 | [12 empty] | P5513 | GREENHOUSE #18 | GH18 | CORE
0 | 18P000472 | [12 empty] | P5514 | GREENHOUSE #19 | GH19 | CORE
0 | 18P000473 | [12 empty] | P5515 | GREENHOUSE #20 | GH20 | CORE
0 | 18P000474 | [12 empty] | P5516 | GLASSHOUSE FIELD 15A #40 | GH 15A-40 | CORE
0 | 18P000476 | [12 empty] | P5517 | COLLEGE BUILDING NORTH | COLL BLDG NO | CORE
0 | 18P000478 | [12 empty] | P5518 | AGRICULTURE ENGINEERING SHOP | AG ENG SHOPS | CORE
0 | 18P000480 | [12 empty] | P5519 | GLASSHOUSE FIELD 15A #41 | GH 15A-41 | CORE
0 | 18P000481 | [12 empty] | P5520 | MIDGE CONTROL BUILDING | MIDGE CONTRL | CORE
0 | 18P000482 | [12 empty] | P5521 | STORAGE DOCK | STORAGE DOCK | CORE
0 | 18P000483 | [12 empty] | P5522 | GLASSHOUSE FIELD 15A #42 | GH 15A-42 | CORE
0 | 18P000484 | [12 empty] | P5523 | ROBERT GORDON SPROUL HALL | SPROUL | CORE
0 | 18P000485 | [12 empty] | P5524 | GLASSHOUSE FIELD 15A #43 | GH 15A-43 | CORE
0 | 18P000486 | [12 empty] | P5525 | HORTICULTURE GREENHOUSE D1 | GH 16 49 | CORE
0 | 18P000487 | [12 empty] | P5526 | HORTICULTURE GREENHOUSE D2 | GH 16 51 | CORE
0 | 18W000455 | [12 empty] | P5527 | HORTICULTURE GREENHOUSE D3 | GH 16 52 | CORE
0 | 18W001170 | [12 empty] | P5528 | LATHHOUSE LIFE SCIENCES EXPERIMENTAL AREA | LATH LS | CORE
0 | 18W006022 | [12 empty] | P5529 | GLASSHOUSE FIELD 15A #48 | GH 15A-48 | CORE
0 | 18W007453 | [12 empty] | P5530 | BELLTOWER | BELLTOWER | CORE
0 | 18W008762 | [12 empty] | P5531 | HORTICULTURE GREENHOUSE D4 | GH 16 53 | CORE
0 | 18W009630 | [12 empty] | P5532 | TELEPHONE BUILDING | TELEPHONE | CORE
0 | 18W011161 | [12 empty] | P5533 | CANYON CREST HOUSING 3458 AVOCADO AVENUE | CC AVOC 3458 | NON-CORE
0 | 18W011672 | [12 empty] | P5534 | MULTIPURPOSE BUILDING BOTANIC GARDEN | MULTI PURP | NON-CORE
0 | 18W011691 | [12 empty] | P5535 | LATHHOUSE B | LATH B | CORE
0 | 18W011692 | [12 empty] | P5539 | AGRONOMY FIELD HEADQUARTERS BUILDING | AGRON FLDHSE | CORE
0 | 18W011772 | [12 empty] | P5540 | GLASSHOUSE #1 PLASTIC COVERED | GH PLASTC 01 | CORE
0 | 18W013160 | [12 empty] | P5541 | GLASSHOUSE #2 PLASTIC COVERED | GH PLASTC 02 | CORE
0 | 18W013973 | [12 empty] | P5542 | GLASSHOUSE #3 PLASTIC COVERED FIELD 16 | GH PLA 16-03 | CORE
0 | 18W015691 | [12 empty] | P5543 | GLASSHOUSE #4 PLASTIC COVERED | GH PLASTC 04 | CORE
0 | 18W016588 | [12 empty] | P5544 | GLASSHOUSE #5 PLASTIC COVERED | GH PLASTC 05 | CORE
0 | 18W016621 | [12 empty] | P5545 | GLASSHOUSE #6 PLASTIC COVERED | GH PLASTC 06 | CORE
0 | 1900a | [12 empty] | P5546 | GLASSHOUSE #7 PLASTIC COVERED | GH PLASTC 07 | CORE
0 | 1990b | [12 empty] | P5547 | GLASSHOUSE #8 PLASTIC COVERED | GH PLASTC 08 | CORE
0 | 19P000006 | [12 empty] | P5548 | AGRICULTURAL OPERATIONS STORAGE SHED #9 | AGOPS SHED 9 | CORE
0 | 19P000009 | [12 empty] | P5549 | BOTANY & PLANT SCIENCE STORAGE FACILITY | BOT STOR 8C | NON-CORE
0 | 19P000011 | [12 empty] | P5550 | GLASSHOUSE #51 | GH 51 | CORE
0 | 19P000012 | [12 empty] | P5551 | GLASSHOUSE FIELD 16 #30 | GH 16 30 | CORE
0 | 19P000014 | [12 empty] | P5552 | GLASSHOUSE FIELD 16 #29 | GH 16 29 | CORE
0 | 19P000015 | [12 empty] | P5553 | GLASSHOUSE #52 | GH 52 | CORE
0 | 19P000017 | [12 empty] | P5554 | ENTOMOLOGY FUMIGATOR | ENT FUMIGATR | CORE
0 | 19P000018 | [12 empty] | P5559 | TRAILER PHYSICAL PLANT | T PHYS PLANT | CORE
0 | 19P000021 | [12 empty] | P5561 | BIOMEDICAL SCIENCES UNIT 2 TRAILER | T BIOMED2 | CORE
0 | 19P000022 | [12 empty] | P5562 | BOTANY & PLANT SCIENCE GREENHOUSE-POLY | GH BOT POLY | CORE
0 | 19P000023 | [12 empty] | P5564 | KIOSK/INFORMATION BOOTH | KIOSK | NON-CORE
0 | 19P000026 | [12 empty] | P5565 | GREENHOUSE BOTANIC GARDENS | GH BOT GDNS | NON-CORE
0 | 19P000027 | [12 empty] | P5566 | POLICE BUILDING | POLICE BLDG | CORE
0 | 19P000028 | [12 empty] | P5567 | GLASSHOUSE FIELD 16 #20 | GH 16 20 | CORE
0 | 19P000029 | [12 empty] | P5568 | HEADHOUSE BOTANIC GARDENS | HHSE BOT GDN | CORE
0 | 19P000030 | [12 empty] | P5571 | METAL RESEARCH BUILDING | METAL RSHBLD | CORE
0 | 19P000031 | [12 empty] | P5573 | CONTROL TEMPERATURE STRUCTURE | CONTROL TEMP | NON-CORE
0 | 19P000032 | [12 empty] | P5575 | STORED PRODUCTS TEST BUILDING | STOR PR TEST | CORE
0 | 19P000033 | [12 empty] | P5579 | PUMPHOUSE #4 | PUMP 4 | CORE
0 | 19P000035 | [12 empty] | P5581 | HOUSING ADMINISTRATION | HOUSING ADM | NON-CORE
0 | 19P000037 | [12 empty] | P5582 | VOLATILE LIQUID STORAGE BUILDING | VOLA LIQ STG | CORE
0 | 19P000042 | [12 empty] | P5583 | GLASSHOUSE #16 PLASTIC COVERED | GH PLASTC 16 | CORE
0 | 19P000043 | [12 empty] | P5584 | GLASSHOUSE #14 PLASTIC COVERED | GH PLASTC 14 | CORE
0 | 19P000044 | [12 empty] | P5585 | GLASSHOUSE #13 PLASTIC COVERED | GH PLASTC 13 | CORE
0 | 19P000045 | [12 empty] | P5586 | GLASSHOUSE #12 PLASTIC COVERED | GH PLASTC 12 | CORE
0 | 19P000046 | [12 empty] | P5587 | GLASSHOUSE #15 PLASTIC COVERED | GH PLASTC 15 | CORE
0 | 19P000049 | [12 empty] | P5588 | SCHOOL OF MEDICINE - EDUCATION BUILDING | SOM EDUC | CORE
0 | 19P000053 | [12 empty] | P5589 | CORPORATION YARD COMPRESSED GAS STORAGE BUILDING | CORP GAS STG | CORE
0 | 19P000054 | [12 empty] | P5590 | BANNOCKBURN VILLAGE BLDG A | BANNOCK A | NON-CORE
0 | 19P000055 | [12 empty] | P5591 | BANNOCKBURN VILLAGE BLDG B | BANNOCK B | NON-CORE
0 | 19P000056 | [12 empty] | P5592 | BANNOCKBURN VILLAGE BLDG C | BANNOCK C | NON-CORE
0 | 19P000058 | [12 empty] | P5593 | BANNOCKBURN VILLAGE BLDG D | BANNOCK D | NON-CORE
0 | 19P000059 | [12 empty] | P5594 | BANNOCKBURN VILLAGE BLDG E | BANNOCK E | NON-CORE
0 | 19P000060 | [12 empty] | P5595 | BANNOCKBURN VILLAGE BLDG F | BANNOCK F | NON-CORE
0 | 19P000061 | [12 empty] | P5596 | BANNOCKBURN VILLAGE BLDG G | BANNOCK G | NON-CORE
0 | 19P000062 | [12 empty] | P5597 | BANNOCKBURN VILLAGE BLDG H | BANNOCK H | NON-CORE
0 | 19P000063 | [12 empty] | P5598 | BANNOCKBURN VILLAGE BLDG I | BANNOCK I | NON-CORE
0 | 19P000102 | [12 empty] | P5599 | BANNOCKBURN VILLAGE BLDG J | BANNOCK J | NON-CORE
0 | 19P000106 | [12 empty] | P5600 | BANNOCKBURN VILLAGE BLDG K | BANNOCK K | NON-CORE
0 | 19P000122 | [12 empty] | P5601 | BANNOCKBURN VILLAGE BLDG L | BANNOCK L | NON-CORE
0 | 19P000124 | [12 empty] | P5602 | BANNOCKBURN VILLAGE BLDG M | BANNOCK M | NON-CORE
0 | 19P000126 | [12 empty] | P5603 | BANNOCKBURN VILLAGE BLDG N | BANNOCK N | NON-CORE
0 | 19P000127 | [12 empty] | P5604 | BANNOCKBURN VILLAGE BLDG O | BANNOCK O | NON-CORE
0 | 19P000129 | [12 empty] | P5605 | BANNOCKBURN VILLAGE BLDG P | BANNOCK P | NON-CORE
0 | 19P000133 | [12 empty] | P5606 | BANNOCKBURN VILLAGE BLDG Q | BANNOCK Q | NON-CORE
0 | 19P000137 | [12 empty] | P5607 | BANNOCKBURN VILLAGE BLDG R | BANNOCK R | NON-CORE
0 | 19P000170 | [12 empty] | P5608 | BANNOCKBURN VILLAGE BLDG S | BANNOCK S | NON-CORE
0 | 19P000171 | [12 empty] | P5609 | BANNOCKBURN VILLAGE BLDG T | BANNOCK T | NON-CORE
0 | 19P000172 | [12 empty] | P5610 | BANNOCKBURN VILLAGE BLDG U | BANNOCK U | NON-CORE
0 | 19P000173 | [12 empty] | P5611 | BANNOCKBURN VILLAGE BLDG V | BANNOCK V | NON-CORE
0 | 19P000174 | [12 empty] | P5614 | STUDENT SUPPORT SERVICES BUILDING | STUDENT SERV | CORE
0 | 19P000175 | [12 empty] | P5616 | SCHOOL OF MEDICINE DINING FACILITY | SOM DINING | CORE
0 | 19P000176 | [12 empty] | P5620 | 5029 MONACHELLO LANE | 5029 MONACHE | NON-CORE
0 | 19P000181 | [12 empty] | P5621 | 5037 MONACHELLO LANE | 5037 MONACHE | NON-CORE
0 | 19P000184 | [12 empty] | P5622 | 5045 MONACHELLO LANE | 5045 MONACHE | NON-CORE
0 | 19P000185 | [12 empty] | P5623 | 1670 OROBLANCO AVE | 1670 OROBLAN | NON-CORE
0 | 19P000186 | [12 empty] | P5624 | 1654 OROBLANCO AVE | 1654 OROBLAN | NON-CORE
0 | 19P000188 | [12 empty] | P5625 | 1640 OROBLANCO AVE | 1640 OROBLAN | NON-CORE
0 | 19P000189 | [12 empty] | P5626 | 1626 OROBLANCO AVE | 1626 OROBLAN | NON-CORE
0 | 19P000191 | [12 empty] | P5628 | 1606 OROBLANCO AVE | 1606 OROBLAN | NON-CORE
0 | 19P000192 | [12 empty] | P5629 | 1598 OROBLANCO AVE | 1598 OROBLAN | NON-CORE
0 | 19P000193 | [12 empty] | P5630 | 1590 OROBLANCO AVE | 1590 OROBLAN | NON-CORE
0 | 19P000194 | [12 empty] | P5631 | 1582 OROBLANCO AVE | 1582 OROBLAN | NON-CORE
0 | 19P000195 | [12 empty] | P5632 | 5141 PIXIE WAY | 5141 PIXIE | NON-CORE
0 | 19P000196 | [12 empty] | P5633 | 5133 PIXIE WAY | 5133 PIXIE | NON-CORE
0 | 19P000197 | [12 empty] | P5634 | 5125 PIXIE WAY | 5125 PIXIE | NON-CORE
0 | 19P000201 | [12 empty] | P5636 | PENTLAND HILLS RESIDENCE HALL BC | PENTLAND BC | NON-CORE
0 | 19P000205 | [12 empty] | P5637 | PENTLAND HILLS RESIDENCE HALL D | PENTLAND D | NON-CORE
0 | 19P000207 | [12 empty] | P5638 | PENTLAND HILLS RESIDENCE HALL E | PENTLAND E | NON-CORE
0 | 19P000208 | [12 empty] | P5639 | PENTLAND HILLS RESIDENCE HALL FG | PENTLAND FG | NON-CORE
0 | 19P000209 | [12 empty] | P5640 | PENTLAND HILLS RESIDENCE HALL H | PENTLAND H | NON-CORE
0 | 19P000210 | [12 empty] | P5641 | PENTLAND HILLS RESIDENCE HALL J | PENTLAND J | NON-CORE
0 | 19P000211 | [12 empty] | P5642 | PENTLAND HILLS RESIDENCE HALL K | PENTLAND K | NON-CORE
0 | 19P000212 | [12 empty] | P5643 | PENTLAND HILLS RESIDENCE HALL L | PENTLAND L | NON-CORE
0 | 19P000213 | [12 empty] | P5644 | PENTLAND HILLS RESIDENCE HALL M | PENTLAND M | NON-CORE
0 | 19P000214 | [12 empty] | P5645 | PENTLAND HILLS RESIDENCE HALL N | PENTLAND N | NON-CORE
0 | 19P000215 | [12 empty] | P5646 | PENTLAND HILLS RESIDENCE HALL O | PENTLAND O | NON-CORE
0 | 19P000216 | [12 empty] | P5647 | PENTLAND HILLS RESIDENCE HALL P | PENTLAND P | NON-CORE
0 | 19P000217 | [12 empty] | P5648 | PENTLAND HILLS RESIDENCE HALL Q | PENTLAND Q | NON-CORE
0 | 19P000220 | [12 empty] | P5649 | 5117 PIXIE WAY | 5117 PIXIE | NON-CORE
0 | 19P000221 | [12 empty] | P5650 | 5109 PIXIE WAY | 5109 PIXIE | NON-CORE
0 | 19P000222 | [12 empty] | P5651 | 5108 PIXIE WAY | 5108 PIXIE | NON-CORE
0 | 19P000224 | [12 empty] | P5652 | 5116 PIXIE WAY | 5116 PIXIE | NON-CORE
0 | 19P000225 | [12 empty] | P5653 | 5124 PIXIE WAY | 5124 PIXIE | NON-CORE
0 | 19P000226 | [12 empty] | P5654 | 5132 PIXIE WAY | 5132 PIXIE | NON-CORE
0 | 19P000226 | [12 empty] | P5655 | 1531 OROBLANCO AVE | 1531 OROBLAN | NON-CORE
0 | 19P000227 | [12 empty] | P5657 | 1563 OROBLANCO AVE | 1563 OROBLAN | NON-CORE
0 | 19P000229 | [12 empty] | P5658 | 1571 OROBLANCO AVE | 1571 OROBLAN | NON-CORE
0 | 19P000230 | [12 empty] | P5659 | 1579 OROBLANCO AVE | 1579 OROBLAN | NON-CORE
0 | 19P000231 | [12 empty] | P5660 | 1595 OROBLANCO AVE | 1595 OROBLAN | NON-CORE
0 | 19P000232 | [12 empty] | P5661 | OBAN APARTMENTS BLDG A | OBAN APTS A | NON-CORE
0 | 19P000233 | [12 empty] | P5662 | OBAN APARTMENTS BLDG B | OBAN APTS B | NON-CORE
0 | 19P000234 | [12 empty] | P5663 | OBAN APARTMENTS BLDG C | OBAN APTS C | NON-CORE
0 | 19P000235 | [12 empty] | P5664 | OBAN APARTMENTS BLDG D | OBAN APTS D | NON-CORE
0 | 19P000236 | [12 empty] | P5665 | OBAN APARTMENTS BLDG E | OBAN APTS E | NON-CORE
0 | 19P000237 | [12 empty] | P5666 | OBAN APARTMENTS BLDG F | OBAN APTS F | NON-CORE
0 | 19P000238 | [12 empty] | P5667 | OBAN APARTMENTS BLDG G | OBAN APTS G | NON-CORE
0 | 19P000241 | [12 empty] | P5668 | OBAN APARTMENTS BLDG H | OBAN APTS H | NON-CORE
0 | 19P000242 | [12 empty] | P5669 | OBAN APARTMENTS BLDG J | OBAN APTS J | NON-CORE
0 | 19P000243 | [12 empty] | P5670 | OBAN APARTMENTS OFFICE BLDG | OBAN OFFICE | NON-CORE
0 | 19P000244 | [12 empty] | P5671 | FALKIRK APARTMENTS 1 | FALKIRK 1 | NON-CORE
0 | 19P000245 | [12 empty] | P5672 | FALKIRK APARTMENTS 2 | FALKIRK 2 | NON-CORE
0 | 19P000246 | [12 empty] | P5673 | FALKIRK APARTMENTS 3 | FALKIRK 3 | NON-CORE
0 | 19P000247 | [12 empty] | P5674 | FALKIRK APARTMENTS 4 | FALKIRK 4 | NON-CORE
0 | 19P000248 | [12 empty] | P5675 | FALKIRK APARTMENTS 5 | FALKIRK 5 | NON-CORE
0 | 19P000249 | [12 empty] | P5676 | FALKIRK APARTMENTS 6 | FALKIRK 6 | NON-CORE
0 | 19P000250 | [12 empty] | P5677 | FALKIRK APARTMENTS 7 | FALKIRK 7 | NON-CORE
0 | 19P000251 | [12 empty] | P5678 | FALKIRK APARTMENTS 8 | FALKIRK 8 | NON-CORE
0 | 19P000252 | [12 empty] | P5679 | FALKIRK APARTMENTS 9 | FALKIRK 9 | NON-CORE
0 | 19P000253 | [12 empty] | P5680 | FALKIRK APARTMENTS 10 | FALKIRK 10 | NON-CORE
0 | 19P000255 | [12 empty] | P5681 | FALKIRK APARTMENTS 11 | FALKIRK 11 | NON-CORE
0 | 19P000256 | [12 empty] | P5682 | FALKIRK APARTMENTS 12 | FALKIRK 12 | NON-CORE
0 | 19P000263 | [12 empty] | P5683 | FALKIRK APARTMENTS 13 | FALKIRK 13 | NON-CORE
0 | 19P000265 | [12 empty] | P5684 | FALKIRK APARTMENTS 14 | FALKIRK 14 | NON-CORE
0 | 19P000266 | [12 empty] | P5685 | FALKIRK APARTMENTS 15 | FALKIRK 15 | NON-CORE
0 | 19P000268 | [12 empty] | P5686 | FALKIRK APARTMENTS 16 | FALKIRK 16 | NON-CORE
0 | 19P000269 | [12 empty] | P5687 | FALKIRK APARTMENTS 17 | FALKIRK 17 | NON-CORE
0 | 19P000270 | [12 empty] | P5688 | FALKIRK APARTMENTS 18 | FALKIRK 18 | NON-CORE
0 | 19P000271 | [12 empty] | P5689 | FALKIRK APARTMENTS 19 | FALKIRK 19 | NON-CORE
0 | 19P000272 | [12 empty] | P5690 | FALKIRK APARTMENTS LR1 | FALKIRK LR1 | NON-CORE
0 | 19P000273 | [12 empty] | P5691 | FALKIRK APARTMENTS LR2 | FALKIRK LR2 | NON-CORE
0 | 19P000274 | [12 empty] | P5692 | FALKIRK APARTMENTS LR3 | FALKIRK LR3 | NON-CORE
0 | 19P000275 | [12 empty] | P5693 | FALKIRK APARTMENTS OFFICE | FALKIRK OFF | NON-CORE
0 | 19P000276 | [12 empty] | P5694 | FALKIRK APARTMENTS MOD | FALKIRK MOD | NON-CORE
0 | 19P000277 | [12 empty] | P5695 | STUDENT RECREATION CENTER SOUTH | SRC SOUTH | NON-CORE
0 | 19P000278 | [12 empty] | P5696 | STUDENT RECREATION CENTER POOL EQUIPMENT BUILDING | SRC POOLBLDG | NON-CORE
0 | 19P000279 | [12 empty] | P5698 | UCR BUILDING | UCR BUILDING
0 | 19P000280 | [12 empty] | P5699 | OP BUILDING | OP BUILDING
0 | 19P000283 | [12 empty] | P5704 | GLASSHOUSE FIELD 15 #35 | GH 15-35 | CORE
0 | 19P000284 | [12 empty] | P5705 | PRESS BOX | PRESS BOX | NON-CORE
0 | 19P000285 | [12 empty] | P5706 | CONSTRUCTION TRAILER | T CONSTRUCT | CORE
0 | 19P000286 | [12 empty] | P5708 | DELFINO FAMILY PLANT LABORATORY | DELFINO HHSE | CORE
0 | 19P000287 | [12 empty] | P5709 | RUBIDOUX SOIL HOUSE 1 | RUBID SOIL 1 | NON-CORE
0 | 19P000288 | [12 empty] | P5710 | RUBIDOUX GREENHOUSE | RUBIDOUX GRH | CORE
0 | 19P000291 | [12 empty] | P5711 | RUBIDOUX QUARANTINE FACILITY | RUBIDOUX QUA | CORE
0 | 19P000292 | [12 empty] | P5712 | RUBIDOUX SCREENHOUSE | RUBIDOUX SCR | CORE
0 | 19P000293 | [12 empty] | P5713 | RUBIDOUX LABORATORY #2 | RUBIDOX LAB2 | CORE
0 | 19P000295 | [12 empty] | P5714 | RUBIDOUX LABORATORY #1 | RUBIDOUX LAB | CORE
0 | 19P000296 | [12 empty] | P5715 | THE PLAZA APARTMENTS | THE PLAZA | NON-CORE
0 | 19P000298 | [12 empty] | P5717 | 2100 ATLANTA AVENUE RIVERSIDE | ATLANTA | CORE
0 | 19P000299 | [12 empty] | P5718 | MOURADICK FARM LABORATORY BUILDING | MOURADK LAB | CORE
0 | 19P000300 | [12 empty] | P5719 | MOURADICK FARM SHOP BUILDING | MOURADK SHOP | CORE
0 | 19P000301 | [12 empty] | P5720 | CALIFORNIA MUSEUM OF PHOTOGRAPHY BUILDING | CA MUS PHOTO | CORE
0 | 19P000306 | [12 empty] | P5721 | RUBIDOUX GARAGE | RUBIDOUX GAR | CORE
0 | 19P000307 | [12 empty] | P5722 | UC RIVERSIDE UNIVERSITY EXTENSION CENTER | UCR EXTEN CT | NON-CORE
0 | 19P000308 | [12 empty] | P5724 | TRAILER PLANT PATH2 | T PLNT PATH2 | CORE
0 | 19P000309 | [12 empty] | P5725 | PHILIP BOYD DEEP CANYON RESERVE RESEARCH LAB | DC RES LAB | NON-CORE
0 | 19P000312 | [12 empty] | P5726 | PHILIP BOYD DEEP CANYON RESERVE ADMIN BLDG | DC ADMIN BLD | NON-CORE
0 | 19P000313 | [12 empty] | P5727 | PHILIP BOYD DEEP CANYON RESERVE CAR PORT | DC CAR PORT | NON-CORE
0 | 19P000314 | [12 empty] | P5728 | PHILIP BOYD DEEP CANYON RESERVE RESIDENCE | DC RESIDENCE | NON-CORE
0 | 19P000316 | [12 empty] | P5729 | MOTTE RIMROCK RESERVE RESIDENCE | MOTTE RESDNC | NON-CORE
0 | 19P000317 | [12 empty] | P5730 | GRANITE MOUNTAIN RESERVE DORNERS CAMP CHATEAU | GR MT DORNER | NON-CORE
0 | 19P000318 | [12 empty] | P5731 | DEEP CANYON COTTAGE/OFFICE/STORAGE | DC COTTAGE | NON-CORE
0 | 19P000319 | [12 empty] | P5732 | PHILIP BOYD DEEP CANYON RESERVE WILBUR MAYHEW BLDG | DC MAYHEW BL | NON-CORE
0 | 19P000322 | [12 empty] | P5733 | SIBYL & AL ALLANSON CENTER LABORATORY | GM ALLAN LAB | NON-CORE
0 | 19P000326 | [12 empty] | P5734 | SIBYL & AL ALLANSON CENTER RESEARCHER CABIN | GM ALLAN CAB | NON-CORE
0 | 19P000340 | [12 empty] | P5735 | SIBYL & AL ALLANSON CENTER EAST RESEARCHER CABIN | GM ALLAN ECB | NON-CORE
0 | 19P000341 | [12 empty] | P5736 | SIBYL & AL ALLANSON CENTER WEST RESEARCHER CABIN | GM ALLAN WCB | NON-CORE
0 | 19P000346 | [12 empty] | P5737 | T PLANT PATH3 | T PLNT PATH3 | CORE
0 | 19P000347 | [12 empty] | P5739 | EMERSON OAKS RESERVE RESTROOM | EMERSON RR | CORE
0 | 19P000353 | [12 empty] | P5740 | GRANITE MOUNTAIN BIN 1 | GR MT BIN 1 | NON-CORE
0 | 19P000354 | [12 empty] | P5741 | GRANITE MOUNTAIN BIN 2 | GR MT BIN 2 | NON-CORE
0 | 19P000356 | [12 empty] | P5742 | GRANITE MOUNTAIN BIN 3 | GR MT BIN 3 | NON-CORE
0 | 19P000357 | [12 empty] | P5743 | GRANITE MOUNTAIN ROLL-UP BIN | GR MT ROLLUP | NON-CORE
0 | 19P000358 | [12 empty] | P5744 | GRANITE MOUNTAIN STAPLES-ICE HOUSE (HISTORIC) | GR MT ICEHSE | NON-CORE
0 | 19P000360 | [12 empty] | P5745 | GRANITE MOUNTAIN TACK HOUSE | GR MT TACK | NON-CORE
0 | 19P000361 | [12 empty] | P5746 | GRANITE MOUNTAIN WORKSHOP | GR MT SHOP | NON-CORE
0 | 19P000362 | [12 empty] | P5747 | GRANITE MOUNTAIN ALLANSON CENTER RESEARCH CABIN | GM ALLAN ICB | NON-CORE
0 | 19P000364 | [12 empty] | P5748 | GRANITE MOUNTAIN ALLANSON CENTER MEETING/STUDY ROOM | GM ALLAN MR | NON-CORE
0 | 19P000366 | [12 empty] | P5749 | GRANITE MOUNTAIN ALLANSON CENTER BIN | GM ALLAN BIN | NON-CORE
0 | 19P000367 | [12 empty] | P5750 | MOTTE SHED 4 | MOTTE SHED 4 | NON-CORE
0 | 19P000369 | [12 empty] | P5751 | BOYD DEEP CANYON SHOP | DC SHOP | NON-CORE
0 | 19P000370 | [12 empty] | P5753 | MOTTE-RIMROCK RESERVE SHED #1 | MOTTE SHED 1 | NON-CORE
0 | 19P000371 | [12 empty] | P5754 | MOTTE-RIMROCK RESERVE SHED #2 | MOTTE SHED 2 | NON-CORE
0 | 19P000373 | [12 empty] | P5755 | MOTTE-RIMROCK RESERVE SHED #3 | MOTTE SHED 3 | NON-CORE
0 | 19P000375 | [12 empty] | P5757 | CULVER CENTER FOR THE ARTS | CULVER ROUSE | CORE
0 | 19P000378 | [12 empty] | P5779 | GRANITE MOUNTAIN RESEARCH TRAILER | GR MT RS TR | NON-CORE
0 | 19P000380 | [12 empty] | P5781 | JAMES SAN JACINTO MTN RESERVE LOLOMI LODGE | JR LOLOMI LG | NON-CORE
0 | 19P000384 | [12 empty] | P5782 | JAMES SAN JACINTO MTN RESERVE GARAGE | JAMES R GARG | NON-CORE
0 | 19P000386 | [12 empty] | P5784 | JAMES SAN JACINTO MTN RESERVE TRAILFINDERS LODGE | JR TRAIL FLG | NON-CORE
#VALUE! | 19P000390 | [12 empty] | P5785 | GRANITE MOUNTAIN RESEARCH TRAILER | GR MT RES TR | NON-CORE
0 | 19P000396 | [12 empty] | P5786 | GRANITE MOUNTAIN RESERVE STAPLES RANCH HOUSE | GR MT STAPLE | NON-CORE
#VALUE! | 19P000399 | [12 empty] | P5787 | GRANITE MOUNTAIN RESERVE RESIDENCE | GR MT RESIDN | NON-CORE
0 | 19P000401 | [12 empty] | P5788 | HUMAN RESOURCES | HUMAN RSOURC | CORE
#VALUE! | 19P000405 | [12 empty] | P5789 | DEEP CANYON AGARE HILL RESEARCH BEDROOM | DC AGARE | NON-CORE
0 | 19P000407 | [12 empty] | P5799 | GRANITE MOUNTAIN RESIDENCE 2 | GR MT RESID2 | NON-CORE
0 | 19P000408 | [12 empty] | P5801 | JR EQUIPMENT SHED 1 | JR SHED 1 | NON-CORE
0 | 19P000410 | [12 empty] | P5802 | JR EQUIPMENT SHED 2 | JR SHED 2 | NON-CORE
0 | 19P000411 | [12 empty] | P5804 | EMERSON MAIN RESIDENCE | EMERSON RES | NON-CORE
0 | 19P000418 | [12 empty] | P5805 | JAMES SAN JACINTO RESERVE CABIN | JR CABIN | NON-CORE
0 | 19P000420 | [12 empty] | P5806 | MOTTE-RIMROCK RESERVE SHOP | MOTTE SHOP | NON-CORE
0 | 19P000424 | [12 empty] | P5807 | JAMES RESERVE CLASSROOM | JR CLASSROOM | NON-CORE
0 | 19P000425 | [12 empty] | P5808 | JAMES RESERVE CABIN C | JR CABIN C | NON-CORE
0 | 19P000428 | [12 empty] | P5809 | JAMES RESERVE CABIN B | JR CABIN B | NON-CORE
0 | 19P000429 | [12 empty] | P5810 | JAMES RESERVE CABIN A | JR CABIN A | NON-CORE
0 | 19P000439 | [12 empty] | P5817 | LATHHOUSE 4 | LATHHOUSE 4 | NON-CORE
0 | 19P000440 | [12 empty] | P5820 | FMRI | FMRI | CORE
0 | 19P000442 | [12 empty] | P5821 | SOLAR GREENHOUSE | SOLAR GREENH | NON-CORE
0 | 19P000445 | [12 empty] | P5825 | SCHOOL OF MEDICINE TRAILER | T MEDICINE | NON-CORE
0 | 19P000449 | [12 empty] | P5829 | 4125 WATKINS DRIVE | 4125 WATKINS | NON-CORE
#VALUE! | 19P000451 | [12 empty] | P5900 | UNIVERSITY VILLAGE BUILDING E | UV BLDG E | NON-CORE
0 | 19P000453 | [12 empty] | P5901 | 1935 CHICAGO AVENUE | 1935 CHICAGO | NON-CORE
0 | 19P000458 | [12 empty] | P5905 | 555 E TACHEVAH | 555 TACHEVAH | NON-CORE
0 | 19P000505 | [12 empty] | P5906 | CE-CERT CHASSIS DYNAMOMETER FACILITY | DYNAMOMETER | CORE
0 | 19S000833 | [12 empty] | P5912 | TRAILER STUDENT HEALTH | T STU HEALTH | CORE
0 | 19W002419 | [12 empty] | P5913 | 1190 COLUMBIA CE-CERT LEASE | 1190COLUMBIA | NON-CORE
0 | 19W002930 | [12 empty] | P5914 | EL MIRADOR MEDICAL PLAZA | EL MIRADOR | NON-CORE
#VALUE! | 19W003012 | [12 empty] | P5915 | 1111 CITRUS STREET | 1111 CITRUS | NON-CORE
0 | 19W003050 | [12 empty] | P5916 | UNIVERSITY VILLAGE BUILDING B | UV BLDG B | NON-CORE
0 | 19W006811 | [12 empty] | P5917 | INTELLICENTER - UC PATH | INTELLICTR | NON-CORE
0 | 19W007474 | [12 empty] | P5918 | 4510 BROCKTON AVENUE | 4510BROCKTON | NON-CORE
0 | 3035a | [12 empty] | P5919 | 1955 CHICAGO AVENUE | 1955 CHICAGO | NON-CORE
0 | 3035b | [12 empty] | P5920 | FROST STUDIO | FROST STUDIO | NON-CORE
0 | [13 empty] | P5921 | 266 FROST COURT MAIN HOUSE | 266 FROST HOUSE | NON-CORE
0 | [13 empty] | P5922 | FROST APT | FROST APT | NON-CORE
0 | [13 empty] | P5923 | FROST GARAGE | FROST GARAGE | NON-CORE
0 | [13 empty] | P5924 | FROST SHED 1 | FROST SHED 1 | NON-CORE
0 | [13 empty] | P5925 | FROST LAUND | FROST LAUND | NON-CORE
0 | [13 empty] | P5926 | FROST SHED 2 | FROST SHED 2 | NON-CORE
0 | [13 empty] | P5927 | FROST BARN | FROST BARN | NON-CORE
0 | [13 empty] | P5928 | 285 FROST CT | 285 FROST CT | NON-CORE
0 | [13 empty] | P5930 | 286 FROST COURT | 286 FROST | NON-CORE
0 | [13 empty] | P5932 | CITRUS TOWER | CITRUS TOWER | NON-CORE
[14 empty] | P5933 | PROGENCY PSYCHIATRIC GROUP | PROGENCY | NON-CORE
[14 empty] | P5934 | ORANGE COUNTY PSYCHIATRY | 18881 VONKAR | NON-CORE
[14 empty] | P5935 | SILVER OAKS WOMENS HEALTH | 19330 JESSE | NON-CORE
[14 empty] | P5936 | EVANS PARK NEUROLOGY | 4500BROCKTON | NON-CORE
[14 empty] | P5937 | APPLE VALLEY NEUROSURGERY | 16143KOKANEE | NON-CORE
[14 empty] | P5938 | 3333 14TH ST | 3333 14th ST | NON-CORE
[14 empty] | P5950 | GLEN MOR F | GLEN MOR F | NON-CORE
[14 empty] | P5951 | GLEN MOR G | GLEN MOR G | NON-CORE
[14 empty] | P5952 | GLEN MOR H | GLEN MOR H | NON-CORE
[14 empty] | P5953 | GLEN MOR I | GLEN MOR I | NON-CORE
[14 empty] | P5954 | GLEN MOR J | GLEN MOR J | NON-CORE
[14 empty] | P5955 | GLEN MOR K | GLEN MOR K | NON-CORE
[14 empty] | P5956 | GLEN MOR L | GLEN MOR L | NON-CORE
[14 empty] | P5957 | GLEN MOR M | GLEN MOR M | NON-CORE
[14 empty] | P5959 | BIG SPRINGS PARKING STRUCTURE | BIG SPR PARK | NON-CORE
[14 empty] | P5980 | CE-CERT OFFICE BUILDING | 1084COLUMBIA | NON-CORE
[14 empty] | P5981 | CE-CERT CHAMBER BUILDING | 1086COLUMBIA | NON-CORE
[14 empty] | P5983 | 1200 COLUMBIA AVENUE, RIVERSIDE | 1200COLUMBIA | NON-CORE
[14 empty] | P5985 | MOTTE RIMROCK RESERVE TRAILER | MOTTE TRAILR | NON-CORE
[14 empty] | P5986 | USDA SALINITY LABORATORY | SALINITY LAB | NON-CORE
[14 empty] | P5987 | UNIVERSITY VILLAGE OFFICE LEASE | UV BLDG A | NON-CORE
[14 empty] | P5990 | CHAVEZ COMCT | CHAVEZ COMCT
[14 empty] | P5991 | STONEHAVEN APARTMENTS | STONEHAVEN | NON-CORE
[14 empty] | P5994 | USDA CLONAL GERMPLASM RESPOSITORY | GERMPLASM | CORE
[14 empty] | P5998 | INTERNATIONAL VILLAGE (UNEX) | INTER VILLAG | NON-CORE
[14 empty] | PG650 | SUBSTATION | SUBSTATION
[14 empty] | T MRB1 | MRB1 T1 | MRB1 T1
[14 empty] | T MRB2 | MRB1 T2 | MRB1 T2
[14 empty] | T MRB3 | MRB1 T3 | MRB1 T3
[14 empty] | Z1005 | SOFTBALL STG | SOFTBALL STG
[14 empty] | Z1016 | FIELD 9 SHED | FIELD 9 SHED
[14 empty] | Z1017 | T MORSE HALL | T MORSE HALL
[14 empty] | Z1018 | T SEELEY HAL | T SEELEY HAL
[14 empty] | Z1019 | SHIP 29 | SHIP 29
[14 empty] | Z1020 | T SBUR HALL | T SBUR HALL
[14 empty] | Z1021 | STOR 14-1 | STOR 14-1
[14 empty] | Z1023 | COLD 1 | COLD 1
[14 empty] | Z1024 | COLD 2 | COLD 2
[14 empty] | Z1025 | COLD 3 | COLD 3
[14 empty] | Z1026 | COLD 4 | COLD 4
[14 empty] | Z1027 | COLD 5 | COLD 5
[14 empty] | Z1028 | COLD 6 | COLD 6
[14 empty] | Z1029 | COLD 7 | COLD 7
[14 empty] | Z1030 | T2 FIELD 14-1 | T2 FIELD 14-1
[14 empty] | Z1031 | SHED 20 | SHED 20
[14 empty] | Z1032 | T1 STOR | T1 STOR
[14 empty] | Z1033 | 21 1623 STOR | 21 1623 STOR
[14 empty] | Z1034 | STOR 23 | STOR 23
[14 empty] | Z1035 | 21 1775 STOR | 21 1775 STOR
[14 empty] | Z1036 | 21 1776 STOR | 21 1776 STOR
[14 empty] | Z1037 | STOR 26 | STOR 26
[14 empty] | Z1038 | 21 1595 STOR | 21 1595 STOR
[14 empty] | Z1039 | STOR 3 | STOR 3
[14 empty] | Z1040 | STOR 4 | STOR 4
[14 empty] | Z1041 | STOR 5 | STOR 5
[14 empty] | Z1042 | STOR 6 | STOR 6
[14 empty] | Z1043 | STOR 21 6075 | STOR 21 6075
[14 empty] | Z1044 | SHED 21 | SHED 21
[14 empty] | Z1046 | COLD STOR | COLD STOR
[14 empty] | Z1048 | GH 15-49 | GH 15-49
[14 empty] | Z1049 | SHED 30 | SHED 30
[14 empty] | Z1050 | SHED 31 | SHED 31
[14 empty] | Z1051 | SHED 32 | SHED 32
[14 empty] | Z1052 | FENCE 1 | FENCE 1
[14 empty] | Z1053 | STOR 33 | STOR 33
[14 empty] | Z1054 | STOR 34 | STOR 34
[14 empty] | Z1055 | FENCE 2 | FENCE 2
[14 empty] | Z1056 | COOP 1 | COOP 1
[14 empty] | Z1057 | COOP 4 | COOP 4
[14 empty] | Z1058 | FENCE 4 | FENCE 4
[14 empty] | Z1059 | FENCE 3 | FENCE 3
[14 empty] | Z1060 | COOP 3 | COOP 3
[14 empty] | Z1061 | COOP 2 | COOP 2
[14 empty] | Z1062 | SCREEN 35 | SCREEN 35
[14 empty] | Z1063 | STOR CANVAS | STOR CANVAS
[14 empty] | Z1064 | SHED 8 | SHED 8
[14 empty] | Z1065 | SHED 36 | SHED 36
[14 empty] | Z1066 | CARGO 1 | CARGO 1
[14 empty] | Z1067 | SHED 37 | SHED 37
[14 empty] | Z1068 | SHED 38 | SHED 38
[14 empty] | Z1069 | SHED 39 | SHED 39
[14 empty] | Z1070 | SCREEN 1 | SCREEN 1
[14 empty] | Z1071 | CARGO 2 | CARGO 2
[14 empty] | Z1072 | SHED 40 | SHED 40
[14 empty] | Z1073 | CANOPY FUM | CANOPY FUM
[14 empty] | Z1074 | STOR 38 | STOR 38
[14 empty] | Z1075 | STOR 39 | STOR 39
[14 empty] | Z1076 | STOR 40 | STOR 40
[14 empty] | Z1077 | STOR 41 | STOR 41
[14 empty] | Z1078 | STOR 42 | STOR 42
[14 empty] | Z1079 | STOR 43 | STOR 43
[14 empty] | Z1080 | SCREEN 2 | SCREEN 2
[14 empty] | Z1081 | SHED 41 | SHED 41
[14 empty] | Z1089 | SHED 42 | SHED 42
[14 empty] | Z1090 | GH K1 | GH K1
[14 empty] | Z1093 | PICNIC 1 | PICNIC 1
[14 empty] | Z1094 | PICNIC 2 | PICNIC 2
[14 empty] | Z1096 | METEOR 9C | METEOR 9C
[14 empty] | Z1097 | SHED 8 | SHED 8
[14 empty] | Z1098 | TURF FERTIL | TURF FERTIL
[14 empty] | Z1099 | SHED 9 | SHED 9
[14 empty] | Z1100 | COLD BOX 2 | COLD BOX 2
[14 empty] | Z1101 | INST TOWER | INST TOWER
[14 empty] | Z1102 | PUMP 5 | PUMP 5
[14 empty] | Z1103 | PUMP SHED | PUMP SHED
[14 empty] | Z1104 | TANK STORAGE | TANK STORAGE
[14 empty] | Z1105 | METAL SHED 1 | METAL SHED 1
[14 empty] | Z1106 | METAL SHED 2 | METAL SHED 2
[14 empty] | Z1107 | METAL SHED 3 | METAL SHED 3
[14 empty] | Z1108 | METAL SHED 4 | METAL SHED 4
[14 empty] | Z1109 | METAL SHED 5 | METAL SHED 5
[14 empty] | Z1110 | METAL SHED 6 | METAL SHED 6
[14 empty] | Z1111 | METAL SHED 7 | METAL SHED 7
[14 empty] | Z1112 | METAL SHED 8 | METAL SHED 8
[14 empty] | Z1113 | SOC BLEACHER | SOC BLEACHER
[14 empty] | Z1114 | SOC TRAILER1 | SOC TRAILER1
[14 empty] | Z1115 | SOC TRAILER2 | SOC TRAILER2
[14 empty] | Z1116 | TRACK BLEACH | TRACK BLEACH
[14 empty] | Z1117 | LATH C | LATH C
[14 empty] | Z1118 | LATH 10 | LATH 10
[14 empty] | Z1119 | STEAM GENER | STEAM GENER
[14 empty] | Z1121 | FENCE 6 | FENCE 6
[14 empty] | Z1122 | FENCE 7 | FENCE 7
[14 empty] | Z1123 | METAL TANK 1 | METAL TANK 1
[14 empty] | Z1124 | METAL STOR 1 | METAL STOR 1
[14 empty] | Z1125 | METAL STOR 2 | METAL STOR 2
[14 empty] | Z1126 | COLD 8 | COLD 8
[14 empty] | Z1127 | COLD 9 | COLD 9
[14 empty] | Z1128 | METAL CANOPY | METAL CANOPY
[14 empty] | Z1129 | SHED 45 | SHED 45
[14 empty] | Z1133 | BOT GDN SHD | BOT GDN SHD
[14 empty] | Z1134 | BOT GDN SHD2 | BOT GDN SHD2
[14 empty] | Z1136 | HSNG STOR | HSNG STOR
[14 empty] | Z1137 | CVAR SHADE 1 | CVAR SHADE 1
[14 empty] | Z1138 | CVAR PAD 1 | CVAR PAD 1
[14 empty] | Z1139 | CVAR T1 | CVAR T1
[14 empty] | Z1140 | CVAR OLD ICE | CVAR OLD ICE
[14 empty] | Z1141 | CVAR T LAB | CVAR T LAB
[14 empty] | Z1142 | CVAR STOR 2 | CVAR STOR 2
[14 empty] | Z1143 | CVAR FUEL | CVAR FUEL
[14 empty] | Z1144 | CVAR GH 1 | CVAR GH 1
[14 empty] | Z1145 | CVAR GH 2 | CVAR GH 2
[14 empty] | Z1146 | CVAR INSECT 1 | CVAR INSECT 1
[14 empty] | Z1147 | CVAR INSECT 2 | CVAR INSECT 2
[14 empty] | Z1148 | CVAR INSECT 3 | CVAR INSECT 3
[14 empty] | Z1149 | CVAR SHED 1 | CVAR SHED 1
[14 empty] | Z1150 | CVAR PAD 2 | CVAR PAD 2
[14 empty] | Z1151 | CVAR SHED 2 | CVAR SHED 2
[14 empty] | Z1152 | CVAR SHADE 2 | CVAR SHADE 2
[14 empty] | Z1153 | CVAR STOR 2 | CVAR STOR 2
[14 empty] | Z1154 | CVAR SHADE 3 | CVAR SHADE 3
[14 empty] | Z1155 | CVAR FENCE 1 | CVAR FENCE 1
[14 empty] | Z1156 | CVAR PUMP | CVAR PUMP
[14 empty] | Z1157 | CVAR CONT 1 | CVAR CONT 1
[14 empty] | Z1158 | CVAR CONT 2 | CVAR CONT 2
[14 empty] | Z1159 | CVAR CONT 3 | CVAR CONT 3
[14 empty] | Z2000 | BSL3 LAB | BSL3 LAB

## Planning (hidden)
Project Planning
Last Updated | 2019-03-01
Organization | Total Open Projects | % of Total Projects | Total Approved Budget | Total FS Recharge Cost
ACADEMIC SENATE | 0 | #DIV/0! | 0 | 0
ATHLETICS | 0 | #DIV/0! | 0 | 0
BAS | 0 | #DIV/0! | 0 | 0
BCOE | 0 | #DIV/0! | 0 | 0
CAP.PROG. | 0 | #DIV/0! | 0 | 0
CAS | 0 | #DIV/0! | 0 | 0
CHASS | 0 | #DIV/0! | 0 | 0
CNAS | 0 | #DIV/0! | 0 | 0
FAC-PLNG-DESIGN-CONST | 0 | #DIV/0! | 0 | 0
ITS | 0 | #DIV/0! | 0 | 0
LIBR | 0 | #DIV/0! | 0 | 0
PALM DESERT | 0 | #DIV/0! | 0 | 0
SOB | 0 | #DIV/0! | 0 | 0
SOM | 0 | #DIV/0! | 0 | 0
SoPP | 0 | #DIV/0! | 0 | 0
VC-RED | 0 | #DIV/0! | 0 | 0
VC-STU.AFF. | 0 | #DIV/0! | 0 | 0
VC-UNIV.ADV. | 0 | #DIV/0! | 0 | 0
Totals | 0 | #DIV/0! | 0 | 0
Total Open Projects by Request Date
Organization | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | In Review | Totals
ACADEMIC SENATE | [7 empty] | 0
ATHLETICS | [7 empty] | 0
BAS | [7 empty] | 0
BCOE | [7 empty] | 0
CAP.PROG. | [7 empty] | 0
CAS | [7 empty] | 0
CHASS | [7 empty] | 0
CNAS | [7 empty] | 0
FAC-PLNG-DESIGN-CONST | [7 empty] | 0
ITS | [7 empty] | 0
LIBR | [7 empty] | 0
PALM DESERT | [7 empty] | 0
SOB | [7 empty] | 0
SOM | [7 empty] | 0
SoPP | [7 empty] | 0
VC-RED | [7 empty] | 0
VC-STU.AFF. | [7 empty] | 0
VC-UNIV.ADV. | [7 empty] | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## q_Report_Integrated (hidden)
Proj_Ref_No | CPMS_No | Work_Order_No | IRT | Org | Project_Title | Project_Description | Building | Room | Current_Status | Org_Leadership | Org_Contact (Prioritization Designate) | Contact | Contact_2 | Proj_Mgr | Org_Priority | FS_Priority | FS_Priority_Last | For_Faculty_Hire | Approved_Budget | FS_Recharge_Costs | Project_Initiated | Next_Major_Milestone | Const_Start | Construction_Completion | Impact_Description | Impact_Date_Start | Impact_Date_End | PM_Notes | Scope_Date | Scope_Reviewer | Scope_Notes | Scope_Complete | Owner | IRT? | Requested Year | Data Pulled On
2245 | 2245 |  | FALSE | VC-UNIV.ADV. | Campus Directory & Blade Signs | Remove and replace campus directories at strategic locations throughout the campus. |  |  | Pre Design | Peter Hayashida | Naysia Caldwell | Margene Mastin-Schepps |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2014-03-27 | Project Approval & Funding | 2019-06-03 | 2019-08-30 | [5 empty] | Ron Veloz | 11/28/18 RV: Work was scoped by Ron and performed by the PM. | YES | PD&C | 0 | 2014 | 2019-01-16
2353 | 2353 |  | FALSE | CNAS | Natural Reserves-Sweeney Granite Mountain | This project will add structurally independent facilities for an administration building and researcher housing to provide meeting/office space and short term sleeping quarters. Additionally, the existing laboratory building and staff residence will be extensively renovated. High priority is focused on high insulation values, high wind resistance, rodent proofing, and pursue as much passive cooling and heating as possible with an eye toward low maintenance and high durability. Both new construction and renovation projects are to be sealed to prevent rodent intrusion. The new structures must withstand the harsh environment of extreme temperatures and very high winds. All site improvements shall be done with minimal disturbance to the desert environment. The overarching goal of the project is to provide a sustainable structure that respects its environment and is low maintenance while using best practice design standards. |  |  | Tentative approval additional funding for code modifications | Kathryn Uhrich | Deborah McWilliams | Jim Andre, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2545500 |  | 2015-11-23 | Complete Construction | 2017-11-01 | 2019-12-01 |  |  |  |  | 2018-10-03 | Ron Veloz | 11/28/18 RV: Work was scoped by Ron and performed by the PM. 10/03/18 O-RVL: Install one monitor (need power & data). | YES | PD&C | 0 | 2015 | 2019-01-16
2359 | 2359 |  | FALSE | SOM | SOM - Research Bldg. BSL-3 | Reconfiguration and reconstruction of the existing BSL-3 suite on the 3rd floor. |  |  | Finalizing commissioning & air balance | Deborah Deas | Brandon Barbosa | Rebeccah Goldware |  | Mihai Gavan | 1 |  |  | FALSE | 2730000 |  | 2016-05-19 | Complete Commissioning | 2016-10-01 | 2017-11-01 | [5 empty] | Dan Lerman | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. Will start working on plans.... | YES | PD&C | 0 | 2016 | 2019-01-16
2368 | 2368 |  | FALSE | PLANNING & BUDGET | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | Engineering documentation-civil | Gerry Bomotti | Jacqueline Norman | Katie Sanchez |  | Dave Bomba | 9 |  |  | FALSE | 2600000 |  | 2016-05-19 | Complete CEQA Documentation | 2019-04-01 | 2019-06-01 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2016 | 2019-01-16
2508 | 2508 |  | FALSE | BAS | Barn Expansion | Project 950493 Barn has completed the DPP process and we are now adding this to CPMS to capture expenses related to the Program Process which occurred in FY11-12 and FY12-13. Please move all expenditures from A01233-70003-76 Cost Center to JR142 to a plant account. |  |  | Anticipated closure is June 18th | Gerry Bomotti | Georgianne Carlson | Susan Marshburn |  | D.Hecht/J.Franklin | 4 |  |  | FALSE | 28700000 |  | 2013-07-05 | Complete Construction | 2018-06-01 | 2019-10-01 | [5 empty] | Enrico Baez | 12/6/18 EB Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | NO | PD&C | 0 | 2013 | 2019-01-16
2671 | 2671 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Elevator Modifications - Various Buildings | Provide Vertical Transportation Consulting, Mechanical, Electrical, Fire Alarm and Architectural/Structural Construction document design and specifications for the modernization of two (2) elevators at Webber and Watkins buildings which is included in the base design and one (1) elevator at the Entomology Museum is included as an add alternate. |  |  | Permit review process | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 99 |  |  | FALSE | 596011 |  | 2016-01-05 | Final Approval of CD's | 2019-04-01 | 2019-07-29 |  |  |  |  | 2018-09-27 | Enrico Baez | 11/20/18 EB intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. From work order-looking to have two doors turned into key less entry for security of the practice center. |  | PD&C | 0 | 2016 | 2019-01-16
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Rivera Library Arches/Arcade Repair | Paint and replace roof. |  |  | Anticipate bidding of scope in 2018 w/work performed post commencement | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Scott Donnell | 99 |  |  | FALSE | 240000 |  | 2016-05-06 | Bidding | [7 empty] | Dan Lerman | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with PAul. Paul will complete as in the near future. Carpet will be installed shortly after...... | YES | PD&C | 0 | 2016 | 2019-01-16
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Bourns Hall Fire Alarm System Replacement | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | Approval of 100% CD's | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 99 |  |  | FALSE | 600000 |  |  | Receive Bids | 2019-03-04 | 2019-07-31 | [5 empty] | Paul Ditty | n/a | N/A | PD&C | 0 | 1900 | 2019-01-16
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. |  |  | On hold until MRB1 is complete. | Tamica Smith Jones | Joseph Erbland | Joe Erbland |  | Mihai Gavan | 3 |  |  | FALSE | 0 |  | 2014-04-10 | On hold until MRB is complete | [6 empty] | 2018-09-27 | Enrico Baez | 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB Install keyless entry system for building exterior. | YES | PD&C | 0 | 2014 | 2019-01-16
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Initial planning discussions have begun with SOBA. | Yunzeng Wang | Angela Chang | Laurie Gustafson |  | Blythe Wilson | 2 |  |  | FALSE | 350000 |  | 2016-12-15 | Develop RFQ | [7 empty] | Paul Ditty | n/a | N/A | PD&C | 0 | 2016 | 2019-01-16
2747 | 2747 |  | FALSE | PALM DESERT | Heckmann Center - Landscaping (Donor Orchard) | UCR Palm Desert would like to replace the current turf grass with water-wise, sustainable landscaping. In return for the opportunity to use a “living laboratory” classroom for training, UC Cooperative Extension Master Gardener program has agreed to collaborate with UCR to revise and sustain the landscaping. The first phase will be to create an orchard to highlight UCR’s contributions to agricultural research in the Coachella Valley. The orchard will be located at the entrance to the Heckmann building, north of the walkway. UCR Physical Plant/Grounds to provide estimate for: • Project oversight • Project plan and drawings • Organic material to add to soil • Irrigation materials and installation • Edging for path • Weed cloth • Decomposed granite with stabilizer for ground cover • Decomposed granite with stabilizer for pathway • Concrete pad for art including bolting apparatus • Arbor for grapes • Flow system-fertigation • All other labor and materials other than kiosk, plant signage, turf and tree removal (current landscape maintenance vendor can remove) and plant materials and plant installation | HECKMAN ICEM |  | On hold |  |  | Mike Lawrence |  | Scott Donnell | 2 |  |  | FALSE | 13800 |  | 2014-08-18 | RFQ Design | [7 empty] | Paul Ditty | n/a | N/A | PD&C | 0 | 2014 | 2019-01-16
2774 | 2774 |  | FALSE | PLANNING & BUDGET | Highlander Hall Demolition | Demolition of the Highlander Hall Building |  |  |  | Gerry Bomotti | Jacqueline Norman | Blythe Wilson |  | Scott Donnell | 99 |  |  | FALSE | 2127000 |  | 2015-01-22 | Project Close-out | 2018-08-01 | 2019-01-01 |  |  |  |  | 2018-09-27 | Enrico Baez | 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Install dividers for urinals. Wall is tile. |  | PD&C | 0 | 2015 | 2019-01-16
2829 | 2829 |  | FALSE | VC-STU.AFF. | SRC South - New Storage Building | New storage building immediately south of SRC South Pool Building; approximately 20' x 40'; one roll up door and one standard door; electrical power required - number of outlets to be defined in design; concrete walkway and door pads required; non-potable water may be required if quick couplers are not available in nearby landscaping; please see attachment for location: approximately at gridlines T and 9.4 - dotted outline of building is labeled "FUTURE STORAGE" - located immediately south of the SRC POOL EQUIPMENT BUILDING. | SRC SOUTH |  | Project is currently on-hold. | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Mihai Gavan | 2 |  |  | FALSE | 0 |  | 2015-01-23 | Coordinate with MRB Logistics | [7 empty] | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB remove all t-bar ceiling components. Will need relocation of supply and return registers, lighting Alarms, Etc. |  | PD&C | 0 | 2015 | 2019-01-16
2839 | 2839 |  | FALSE | PLANNING & BUDGET | Multidisciplinary Research Building | External financing provided for this project. Total approved budget is $150,000,000. Confirmed per CPMX and BEA#978864 Xfer Tax Exemp Comm Paper. Funding received 7/25/2016. |  |  | Certificate of Beneficial Occupancy 9.28 | Gerry Bomotti | Jacqueline Norman | Jon Harvey |  | Mihai Gavan | 6 |  |  | FALSE | 156405000 |  | 2015-04-01 | Substantial Completion | 2016-07-01 | 2018-09-28 |  |  |  |  | 2018-10-15 | Enrico Baez | 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27. 10/3/18 EB not time to visit on 9/27. will schedule follow up meeting. 10/15/18 EB conducted site visit, 11 urinals to be replaced. | YES | PD&C | 0 | 2015 | 2019-01-16
2860 | 2860 |  | FALSE | BCOE | Bourns B0152 - Fume Hood | Please investigate feasibility and provide an estimate for installation of ductwork and a four foot fume hood sufficiently equipped and sized to include an exhaust line for a 2-standard sized cylinder gas storage cabinet. Location should be recommended based on proximity of existing building/floor exhaust ductwork. Should it become necessary, the size of the gas cabinet may be considered for reduction. | BOURNS |  | Installing fume hoods and snorkels. | Christopher Lynch | Maggie Souder | Margaret Souder |  | Scott Donnell | 1 |  |  | FALSE | 0 |  | 2015-04-01 | ASHRAE & Certification | 2018-01-01 | 2018-05-01 |  |  |  |  | 2018-09-27 | Enrico Baez | 11/20/18 EB Project cancelled, will be addressed by PD&C. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB conducted site visit, Client wants additional toilet in mens room, changing table and lighting improvements. ADA Issues. Also spoke with Scott Donnell he has project . |  | PD&C | 0 | 2015 | 2019-01-16
2868 | 2868 |  | FALSE | BAS | West Lothian Elevator Renovation |  |  |  | Project Number 956395 assigned | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 33 |  |  | FALSE |  |  | 2015-04-08 | Design | [7 empty] | Paul Ditty | n/a | N/A | PD&C | 0 | 2015 | 2019-01-16
2899 | 2899 |  | FALSE | PLANNING & BUDGET | Pierce Hall Improvements | Replacement of Mechanical, Plumbing and Electrical Infrastructure | PIERCE |  | 98% CD's are completed | Gerry Bomotti | Jacqueline Norman | Jon Harvey |  | Dave Bomba | 8 |  |  | FALSE | 1387000 |  | 2015-08-06 | Augmented Funding | 2019-01-01 | 2019-12-07 | [5 empty] | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB Replace aluminum and glass shower doors. Will need to contract work. Replace all rusty fixtures in showering space, repair/replace tile as needed. | YES | PD&C | 0 | 2015 | 2019-01-16
2900 | 2900 |  | FALSE | PLANNING & BUDGET | Batchelor Hall Systems Renewal | <div>Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. Project proposes: *Replace heating, ventilation, and air condition system due to inefficiency, and compromised air quality &nbsp;Upgrade electrical service to 480/277 in order to allow higher intensity research equipment. *Upgrade/replace plumbing systems due to condition, and inadequate water treatment. *Upgrade fire life safety system (fire alarm) due to none code compliance. *Reconfigure laboratory space to improve research space usage and efficiency, work will be phased to limit user impact, and funding availability. Classification of work, Heating and cooling systems, Ventilation systems, Energy management systems, Primary and emergency electrical systems, Fire alarm and protection systems, De-ionized water and reverse osmosis systems, Hazardous materials abatement, Reconfiguration of research and laboratory and related spaces</div> | BATCHELOR |  | A&E, CAS & EH&S working w/CNAS dean & dept chairs to establish a relo. plan | Gerry Bomotti | Jacqueline Norman | Sharyl Murdock |  | Rowan Reid | 4 |  |  | FALSE | 18179000 |  | 2015-12-15 | CM at Risk Selection | 2019-09-01 | 2021-11-01 | [5 empty] | Paul Ditty | n/a | N/A | PD&C | 0 | 2015 | 2019-01-16
2916 | 2916 |  | FALSE | CAP.PROG. | Solar Greenhouse | Construction of a solar powered greenhouse. |  |  | Construction substantially completed, not including solar components. | Jacqueline Norman | Sharyl Murdock | Matt Barth |  | Scott Donnell | 99 |  |  | FALSE | 174000 |  | 2015-08-04 | Award Contract | 2019-03-01 | 2019-03-01 |  |  |  |  | 2018-09-27 | Enrico Baez | 11/20/18 E. Baez-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB-Request for installing vinyl flooring. Remove and replace existing Terrazo and ceramic floor tile in 1st floor lobby and stairs to basement. | YES | PD&C | 0 | 2015 | 2019-01-16
2952 | 2952 |  | FALSE | CAP.PROG. | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In SD/DD phase. | Jacqueline Norman | Sharyl Murdock | Jon Harvey |  | Dave Bomba | 19 |  |  | FALSE | 23308000 |  | 2015-09-11 | Augmented Funding | 2019-01-02 | 2021-04-01 |  |  |  |  | 2018-09-27 | Enrico Baez | 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Client want a window heat pump unstalled in press box un bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. |  | PD&C | 0 | 2015 | 2019-01-16
2970 | 2970 |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan - Phase 2 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | Package 2 construction is to begin 8/24 | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 17 |  |  | FALSE | 2842000 |  | 2015-12-02 | Complete Construction | 2018-09-26 | 2019-06-01 |  |  |  |  | 2018-09-27 | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB approx. 16-20 doors need repair. Sand, patch, repair as needed. Re-varnish. | YES | PD&C | 0 | 2015 | 2019-01-16
2974 | 2974 |  | FALSE | SOM | SOM Research Building - 1st Floor Fit-Out | Buildout the 1st Floor of School of Medicine Research Building, a space of approximately 17,600 square feet. The construction includes wet laboratories, laboratory support spaces, offices and related support space. Work consists of, but not limited to the following: demolition of existing improvements, addition/alterations of walls, installation of new fume hoods, sinks, safety showers and eyewash stations, alterations/additions to the mechanical, electrical, plumbing, fire life safety, fire suppression, telecommunication and audio/video systems, as specified in the Construction Documents. |  |  | Working on punchlist items. | Deborah Deas | Brandon Barbosa | Blythe Wilson |  | Mihai Gavan | 99 |  |  | FALSE | 9600000 |  | 2015-10-30 | Final Completion | 2017-10-01 | 2018-10-01 | [5 empty] | Enrico Baez | 10/3/2018 EB install, if possible, keyless entry system, for doors to basket ball court. Needs power. Looking for suggestions to idea. |  | PD&C | 0 | 2015 | 2019-01-16
3005 | 3005 |  | FALSE | CAP.PROG. | Batchelor Hall Interior Improvements | Interior renovation of public areas | BATCHELOR |  | Finalize Project Scope. Receive direction from VC. Awaiting Leadership approval. | Jacqueline Norman | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 14 |  |  | FALSE | 8837000 |  | 2016-02-02 | CM at Risk Selection | 2019-09-01 | 2021-10-01 | [5 empty] | Paul Ditty | n/a | N/A | PD&C | 0 | 2016 | 2019-01-16
3052 | 3052 |  | FALSE | SOM | SOM Trailer Expansion | Replace the (2) modular units with one 96' x 60' building and provide access from the SOM-ED building via concrete ramp; Re-vamp the entire site for accessibility. Signed Major Cap Approval for $150k augmentation received 10/25/17 - total project $2,250,000. |  |  | Punch list needs to be addressed | Deborah Deas | Brandon Barbosa | Sharyl Murdock |  | Dave Bomba | 99 |  |  | FALSE | 2250000 |  | 2016-03-07 | Install Code Blue Phone | 2017-08-01 | 2018-01-01 | [8 empty] | PD&C | 0 | 2016 | 2019-01-16
3060 | 3060 |  | FALSE | CHASS | CHASS Intl N. - Paint 3rd Floor | Paint and patch the following CHASS INTN rooms to existing color: 3036 3038 3042 3046 3050 3049 3047 3033 3033B 3025 3021 3019 3015 3013 3011 3002 3008 3012 3014 3016 3018 3020 3022 Hallway outside of 3033 Hallway to main entrance to floor Hallway outside 3005 | CHASS INT N |  | Project on Hold | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2016-05-20 | On Hold | [10 empty] | PD&C | 0 | 2016 | 2019-01-16
3064 | 3064 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Botanic Gardens Basin Silt Removal | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | BOTAN INFO C |  | In CEQA/Agency Permitting | Susan Marshburn | 0 | Toshio Ishida |  | Dave Bomba | 46 |  |  | FALSE | 110000 |  | 2016-04-20 | Obtain Agency Permits | 2019-04-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2016 | 2019-01-16
3066 | 3066 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Chapman Hall Roof Replacement | Roof replacement. | CHAPMAN |  | Revise scope and rebid. | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 50 |  |  | FALSE | 1010000 |  | 2016-04-06 | Complete Close-out | 2018-04-01 | 2018-08-01 | [8 empty] | PD&C | 0 | 2016 | 2019-01-16
3101 | 3101 |  | FALSE | SoB | DM-Anderson Hall S&N - Maint+Restrm Remodel | Under 2014 Deferred Maintenance Funding Program, SoBA has been approved for interior upgrades to be completed up to $65,00. We were originally approved for $75,000 however, per Scott Donnell, $10,000 had already been used. We have requested a list of expenditures for SoBA upgrades under this $10,000. The following items need to be completed under this 2014DM funding in the priorities listed: 1. Anderson Hall South Women’s and Men’s Restrooms Remodel Requirements: Floor and wainscot tile require replacement and/or re-grouting, casework and associated lavatory fixtures and counter tops require refurbishment/placement, restroom partitions require re-painting/replacement. 2. Anderson Hall North Women’s and Men’s Restrooms – repair and touch up areas where ADA compliance changes were made. 3. Anderson Hall North & South Stairway Requirements: All stairways shall be reviewed for compliant contrasting top and bottom stair-tread indicators and all missing or loose anti-slip tread applications be repaired and/or replaced. Any other safety items as may be noted. Retile or carpet as needed. 4. Anderson Hall South Interior Painting to Common areas, both levels: Interior wall surfaces require patching and painting. 5. Anderson Hall North Interior Painting to Common areas, both levels and conference room 021: Interior wall surfaces require patching and painting. 6. Faculty Suite (Rm 158) – match common area tile (size of mud/dirt mat) to replace dirty carpet when first enter room 158. 7. Dean’s Suite (Rm 162) – new carpet. |  |  | The department would like to cancel the project | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 3 |  |  | FALSE | 65000 |  | 2016-05-09 | To be cancelled by Client | [7 empty] | Enrico Baez | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on b 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/11/18 EB-requested drawings from Gunter per Desgn Wests request. 7/11/18EB-waiting for Desgn West to complete site survey. 8/7/18 EB-Met with Robert Brumbaugh. Scope has changed with additional requirements. Improve HVAC, replace VCT, bathroom remodle. Advised to submit CPMS for A&E. | YES | PD&C | 0 | 2016 | 2019-01-16
3104 | 3104 |  | FALSE | PALM DESERT | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Programming |  |  | Zelda Glenn |  | Scott Donnell | 1 |  |  | FALSE | 22000 |  | 2016-05-12 | Design | [10 empty] | PD&C | 0 | 2016 | 2019-01-16
3110 | 3110 |  | FALSE | PLANNING & BUDGET | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded/never routed to the Dispatcher. 90% CD's completed. | Gerry Bomotti | Jacqueline Norman | Marianne Valenti |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | License Agreement Final Review |  | 2019-07-01 | [5 empty] | Enrico Baez | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work….. | YES | PD&C | 0 | 1900 | 2019-01-16
3119 | 3119 |  | FALSE | CAP.PROG. | Plant Growth Environment Facility | The campus has identified a need for modern plant growth and research support facilities, as documented in an April 2016 feasibility study that considered current and future needs for these types of facilities. The Plant Growth Environments Facility will complete construction late third quarter of 2019 to address this need. The project is expected to provide 40,000 gsf of greenhouses, head house, plant growth chambers and support spaces. Currently, the facility is envisioned as a two story structure with 20,000 of greenhouses occupying the upper level. The project delivery method is a design/build competition. |  |  | Design Build Proposal Awarded, design and construction contract execution has started | Jacqueline Norman | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 5 |  |  | FALSE | 1800000 |  | 2016-05-25 | Design-Build Proposal Evaluation | 2019-04-01 | 2020-08-01 | [5 empty] | Enrico Baez | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. 8/22/18 Met with BoB Brumbaugh, Scope of work has changed with additional items. Fire alarm panel relocation, possible building HVAC upgrade. Ask he route project through CPMS and make laundry room and Rec. room one project. | YES | PD&C | 0 | 2016 | 2019-01-16
3120 | 3120 |  | FALSE | CAP.PROG. | Arts Walk Sculpture (Ext Campus Art Project) | Sculpture design concept - hiring a consultant to revise an artist design concept for a proposed outdoor art piece to be placed between the Arts building and the CHASS Interdisciplinary buildings. |  |  | A&E and CAS in discussions w/Artist re: design. | Jacqueline Norman | Sharyl Murdock | Uma Ramasubramanian |  | Jason Espinoza | 4 |  |  | FALSE | 1000000 |  | 2016-05-26 | Construction | 2019-01-28 | 2019-04-30 | [5 empty] | Enrico Baez | fyi_the copier will be moving within the next few months | YES | PD&C | 0 | 2016 | 2019-01-16
3175 | 3175 |  | FALSE | CAP.PROG. | DM-Chilled Water Coils Multiple Buildings | Replace multiple leaking/degraded cooling coils across campus to prevent complete shutdown of building air handlers during the hot summer months. Buildings include: Student Services, Chemical Sciences, Genomics, Psychology, Entomology and MSE. |  |  | Bidding | Jacqueline Norman | Sharyl Murdock | Melissa Garrety |  | Scott Donnell | 99 |  |  | FALSE | 1090000 |  | 2016-10-11 | Start Construction | 2018-12-01 | 2019-04-01 | [5 empty] | Paul Ditty |  | N/A | PD&C | 0 | 2016 | 2019-01-16
3195 | 3195 |  | FALSE | PLANNING & BUDGET | North District Development, Phase-1 | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | Phase 1 - Student Housing - 8/1/2020. | Gerry Bomotti | Jacqueline Norman | Raoula Amescua |  | R.Amescua/D.Hecht | 99 |  |  | FALSE | 2507658.71 |  | 2016-10-26 | Reg. Apprv'l-Business Terms&Fin. | 2019-05-01 | 2021-09-01 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2016 | 2019-01-16
3202 | 3202 |  | FALSE | BAS | Oban - Structural Study | OBAN STRUCTURAL STUDY - provide consultant study to inspect, evaluate and report on all aspects of the property structural condition in accordance with UC seismic policy. Consultant to provide professional cost estimate for any recommended improvements as a deliverable of this study. | OBAN APTS A |  | Per Drew Hecht, this project is on hold per UCOP direction. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 12 |  |  | FALSE | 5000 |  | 2016-10-10 | Structural Evaluation | [7 empty] | Ron Veloz | DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……Need to work on plans….10/17/18 RV: This project was previously scoped and in Plan development. | YES | PD&C | 0 | 2016 | 2019-01-16
3206 | 3206 |  | FALSE | BCOE | Bourns B-134 & B-108 - Removal (Add Fume Hd.) | Add 6' (if able) fume hoods to instructional labs Bourns B-108 and B-134. Depending on cost, department will include: 1. stub in of necessary exhaust and electrical infrastructure to support basic fume hood (without water, gas, vacuum, etc.) in south wall of B-134 (west end) and north wall of B-108 (west end) 2. Install new 6' hoods in locations noted above To take advantage of room instructional and work schedule, please run concurrently if possible with planned work in the room over the 2016 holiday break. | BOURNS |  | In Construction | Christopher Lynch | Maggie Souder | Sabrina Schuster |  | Scott Donnell | 8 |  |  | FALSE | 1000 |  | 2016-10-15 | Complete Construction | 2018-10-01 | 2018-12-01 | [8 empty] | PD&C | 0 | 2016 | 2019-01-16
3218 | 3218 |  | FALSE | CNAS | Ag Ops - Demo Structures | Demolition of 15 structures, including hazardous materials cleanup, electrical reconnection of services as needed, UST removal as needed, relocation of ATT riser. |  |  | In construction Additional funding is not expected. | Kathryn Uhrich | Deborah McWilliams | Deborah McWilliams |  | Scott Donnell | 99 |  |  | FALSE | 316739 |  | 2016-10-19 | Complete Construction | 2018-07-01 | 2019-01-01 | [5 empty] | Paul Ditty |  | N/A | PD&C | 0 | 2016 | 2019-01-16
3224 | 3224 |  | FALSE | BCOE | Bourns - Door Access Control | Replace outdated failing, and unsupported Identicard card reader system with campus approved Hirsch system at all existing locations in Bourns Hall B-wing at a minimum; inclusion of card readers in Bourns A-wing is also desired if possible. Immediate work is optimal since the building is currently under construction and many walls, ceilings, wiring, etc are currently exposed. Work to be done via surplus funds from BCOE 950534. AVC is putting together the costs and scope via meetings with Maggie/ Pat/ and John C. | BOURNS |  | Programming | Christopher Lynch | Maggie Souder | Margaret Souder |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 2016-11-14 | Create SOW and verify budget | [7 empty] | Enrico Baez |  |  | PD&C | 0 | 2016 | 2019-01-16
3228 | 3228 |  | FALSE | CNAS | Retrofit Screenhouse to Greenhouse | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. Location can be discussed with Greg Greer | RUBIDOUX SCR |  | Programming | Kathryn Uhrich | Deborah McWilliams | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 2 |  |  | FALSE | 780000 |  | 2016-12-06 | Bidding | 2019-02-01 | 2018-06-01 | [5 empty] | Enrico Baez | for faculty hire "NO" | YES | PD&C | 0 | 2016 | 2019-01-16
3233 | 3233 |  | FALSE | CAP.PROG. | Mobility HUB Central Campus Linkages | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | SD commencing 3/6/18 - running through 4/4/18; DRB scheduled for 4/4/18. | Jacqueline Norman | Sharyl Murdock | Jaime Enghbrecht |  | Drew Hecht | 1 |  |  | FALSE | 1945000 |  | 2016-12-16 | Bidding | 2019-01-01 | 2020-01-01 |  |  |  |  | 2018-11-01 | Enrico Baez | 11/27/18 EB-Entered scope of work. Transferred work order to John Peraino in FAMIS. Estmate to be provided prior to work start. Aberdeen Inverness Lobby across from RSO. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Pentland Hills 1st floor of I/J, K/L, M/N, O/P • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Pentland Hills Alcove between E&F building. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exterior wall adjacent to B-101 • Remove existing dual fountain. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exercise Room H-101 • Install HS where pluming repairs were made in East wall. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch all walls and Paint as needed. Glen Mor K-206 Fitness Room • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Glen Mor Pool area • Remove existing double water fountains and HS. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. • Repair any brick work as needed Lothian Hallway near Dining Hall cashier stand adjacent to fire extinguisher cabinet • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Sample sheet. https://www.restroomdirect.com/halsey-taylor-drinking-fountains-and-water-coolers.aspx 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Waiting for Lisa L. to schedule site visit. Total number of station and needs not completed. 11/1/18 EB Conducted site visit with Lisa and Bob. AI Replace Hydration Station (HS) in Lobby near RSO Pentland Hills Replace fountains with HS first floor I/J, K/L, M/N, O/P. Also remove fountains and install HS near B-101, Alcove between E&F, H-104. Glen Mor Remove fountain at pool & K-206 fitness room, replace with HS. Lothian Replace existing HS near cashier to Dining Hal | YES | PD&C | 0 | 2016 | 2019-01-16
3234 | 3234 |  | FALSE | CAP.PROG. | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Design-SD | Jacqueline Norman | Sharyl Murdock | John White |  | Fernando Nunez | 2 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete Construction | 2018-11-05 | 2019-03-04 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2016 | 2019-01-16
3237 | 3237 |  | FALSE | SoB | Anderson Hall N. Access Imp. | ADA handrails installation at walkway and ramp on the East sidewalk by the bench of Anderson north, down the steep ramp leading to Anderson South. We have been working with Shelly Frohrip from HR and Mary-Alice Avila of A&E on this so they will have some information regarding the purpose. 11/15/17 The handicapped parking and POT are now included. Project approved, waiting for funding. | ANDERSON 1 |  | Construction plans in review by campus Fire Marshal | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 5 |  |  | FALSE | 150000 |  | 2016-12-19 | FM approval | 2019-02-01 | 2019-03-01 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2016 | 2019-01-16
3255 | 3255 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Humanities - Upgrade EMS | Humanities HVAC - upgrade Energy Management System per approved Century Bond funded project (approval attached). Project: 957405 P5498 Budget $200,000 Accounting determined this is capitalizable Accounting determined not capitalizable | HUMANITIES |  | Approval of alternates by FS | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Fernando Nunez | 6 |  |  | FALSE | 202000 |  | 2017-02-10 | Complete Close-out | 2018-10-01 | 2019-01-01 |  |  |  |  | 2018-11-01 | Enrico Baez | 11/26/18EB-Tranfered FAMIS work order to John Peraino's bench. Estimate to customer needed, prior to moving forward with project. 11/26/18 EB-SCOPE entered Aberdeen Inverness • Paint acoustic panels. Customer to provide color specification. • Remove carpet and replace with customer specified vinyl plank flooring. Replace base board • Cut door to accept 16” x 7” glass lite. Frame as needed. • Paint door • Replace surface mounted light fixture with LED surface mounted fixture. Customer to approve design. • Clean, paint or replace A/C vents. • Remove louvered vent in wall for abandoned water cooler. Install sheet metal cover, paint to match new wall color. Pentland Hills -Rooms 105 and 107 • Install full height acoustic panels on three walls. • 4th wall on East side of each room gets mirror. Height of mirror to be flush with top edge of door casing. Mirror width to be between inside corner of wall and switch plate cover. Provide cut out in mirror for thermostat installation. • Replace all ceiling tiles. • Replace 2’ x 2’ ceiling light with 2’ x 4’ LED fixture-customer to approve design. Pentland Hills -Rooms 105 and 107 • Remove carpet and replace with vinyl plank flooring, replace base board • Fire rated doors to be replaced with fire rated doors with small lite, approx. dimensions 16’ x 7”. • Paint as needed. Lothian • Install full height acoustic panels on three walls. • 4th wall gets mirror height to be even with door casing height. Customer to determine location. • Replace all ceiling tiles. • Replace ceiling lights with LED fixtures. • Remove all carpet in rooms and replace with vinyl plank and new base board-customer to specify style and color. • Replace door wire reinforced glass with clear, non-reinforced fire rated glass. • Paint as needed. Suggested Vendor for sound absorbing paneling. Riverside Acoustics Contact: Keith Atkins 951-682-6123 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 Met with Bob and Lisa, no firm plans or ideas in place. Lisa will schedule site walk once they have determined what they want. 11/1/18 Conducted site visit with Bob and Lisa. | YES | PD&C | 0 | 2017 | 2019-01-16
3270 | 3270 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Chapman Hall - Replace HVAC System | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | CHAPMAN |  | FS provided approval for project to proceed with budget to increase to $563,615 | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Scott Donnell | 8 |  |  | FALSE | 595819 |  | 2017-03-07 | Award Contract | 2018-12-01 | 2019-04-01 | [5 empty] | Enrico Baez | Per Enrico, creating two individual WO's for Tile repair (19W004955) and door painting (19W004956). | YES | PD&C | 0 | 2017 | 2019-01-16
3271 | 3271 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Life Sci/Spieth Hall Elevator Renewal | Scope of work includes the number 3 and 4 elevators of Spieth Hall. Project budget is $344,898.00. Estimated construction cost is $250,400.00. |  |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 9 |  |  | FALSE | 345000 |  | 2017-03-07 | Final Approval of CD's | 2019-04-01 | 2019-07-29 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2017 | 2019-01-16
3272 | 3272 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Athletic/Dance elevator renewal | Project budget is $219,371.00. Estimated construction cost is $169,020.00. | ATH DANCE |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 220000 |  | 2017-03-07 | Final Approval of CD's | 2019-04-01 | 2019-07-29 | [5 empty] | Enrico Baez | 9/12/18 EB-Install Drywall, Patch & Paint, cap water line, install VCT & Cove Base, Verify HVAC operation, replace hydralic door closer, install LED lamps, Security light. Scope sent to Edwin Melgar for approval. | YES | PD&C | 0 | 2017 | 2019-01-16
3275 | 3275 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Fiber Optic Infrastructure Upgrade | Repair, replace and upgrade the fiber optic infrastructure network that includes 50+ buildings across campus. Also includes work to main hubs, sub hubs and make available spare fiber for future utilization. |  |  | Project in design. | Susan Marshburn | Da Lan Dinh | ----- |  | Daneca Stevens | 2 |  |  | FALSE | 643750 |  | 2017-04-12 | Bidding | 2019-04-01 | 2019-08-01 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2017 | 2019-01-16
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | Funding | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [7 empty] | Enrico Baez | 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. |  | PD&C | 0 | 2017 | 2019-01-16
3286 | 3286 |  | FALSE | BAS | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | Awaiting revised proposal from Miyamoto | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 9 |  |  | FALSE | 0 |  | 2017-03-29 | Complete Design | 2019-06-01 | 2019-08-01 |  |  |  |  | 2018-10-03 | Enrico Baez | 1/8/19 EB Job Completed by Jess H. 12/22/18 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. | N/A | PD&C | 0 | 2017 | 2019-01-16
3292 | 3292 |  | FALSE | ITS | ITS-800Mhz Tower Site-Add Pole | As we did back in 2014, we need approval to mount a pole for network electronics. This time, location is next to the 800Mhz tower site behind the C&C Building. We would propose using the same model pole as we did at AGOPS. I believe the AGOP’s poles were set on concrete piers that were 5’ deep. Again, we would want UCR Physical Plant to mount the pole for us. And once I have approval, I can get a quote from UCR Physical Plant. This project has been given to A&E. |  |  | Change order requested for the installation of pole | Danna Gianforte | Shelley Gupta | Tim Paul |  | Dave Bomba | 1 |  |  | FALSE | 42100 |  | 2017-04-20 | Receive final billing | 2018-06-29 | 2018-10-31 | [5 empty] | Enrico Baez | 9/19/19 EB-conducted site visit. Entered Scop in FAMMIS and in BZM projects on shared drive. Requires pluming for sink and disposal, electrical, lighting upgrade. | YES | PD&C | 0 | 2017 | 2019-01-16
3293 | 3293 |  | FALSE | CAP.PROG. | USDA Head House - Public Restroom | Provide an accessible public restroom facility in or adjacent to the USDA Head House Building in Ag Ops. Restroom will serve individuals and groups touring the UCR and USDA Citrus Facilities. Three options have been proposed, and need to be considered and evaluated to recommend a feasible solution for USDA. The work would be managed and paid by USDA, including the design, bidding and construction. UCR staff needs to review the proposed plans and specifications per the agreement with USDA, and provide the review, inspection and approvals. The USDA representative is Marylou Polek. | GERMPLASM |  | Pending Lease | Jacqueline Norman | Sharyl Murdock | Mary Lou Polek |  | Scott Donnell | 11 |  |  | FALSE | 0 |  | 2017-05-22 | USDA Scope & Design | [6 empty] | 2018-08-29 | Enrico Baez | 12/3/18 EB-Cancelled request per email from Amanda Gray. Will resubmit request when funding is available. 10/1/18 EB-Contract De Anza Fence to have a gate installed at chain link fence leading to storm culvert in parking lot 1. | YES | PD&C | 0 | 2017 | 2019-01-16
3300 | 3300 |  | FALSE | BCOE | R'Garden - Solar Installation | Electrician to do the following wiring of our solar panels and inverters out at the R’Garden at UCR. The H model cyboinverter to be used powers the lower heating element of the water heater. The thermostat of the lower heating element must then be set to be higher than the upper heating element. The two output lines are to be connected to an AC switch or switchable AC outlet and the lower element water heater. |  |  | Work to be inspected by A&E. | Christopher Lynch | Maggie Souder | Arvin Tam |  | Scott Donnell | 2 |  |  | FALSE | 0 |  | 2017-05-03 | Work to be inspected by A&E | [7 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2017 | 2019-01-16
3311 | 3311 |  | FALSE | BAS | Ivan's MEP Expansion | This project will provide the utility connections necessary for the Ivan’s coffee shop expansion into the Hinderaker lobby. Purchase and installation of equipment to complete the expansion will be done by the client outside of this project. Scope includes all labor, equipment and material to provide a design-build hookup of mechanical, electrical and plumbing utilities from the basement into the expansion area in the north lobby. Millwork and equipment for this space is supplied by others. MEP work includes minor equipment changes in the existing Ivan's space. The project will entail the following: -Removal of existing carpet, UCR super-graphic and glazing at office space. -Relocation of door to office space, Fire Hose cabinet, supply air registers and lighting. -Construction of vestibule to office space, enclose glazed wall, provide plumbing and electrical as required, construct wing wall at corridor and provide new flooring to match existing. -Provide new accent lighting, data and security cameras. -The old Ivan's space is to have selective demolition and the enclosing of existing service windows. | HINDERAKER |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 11 |  |  | FALSE | 425000 |  | 2017-06-01 | Complete Close-out | 2018-06-01 | 2018-12-01 | [5 empty] | Enrico Baez | 9/13/18 EB emailed Gustavo Plascncia to schedule site visit. 9/18/18 EB. Conducted site visit. Connect water, drain and gas lines to kitchen equioment. Double oven need hardwired electrical. HUB staff will attach al shelving to walls. Day crew to move and deliver equipment. | YES | PD&C | 0 | 2017 | 2019-01-16
3315 | 3315 |  | FALSE | BCOE | Bourns B144 - Lab Safety Improvements | Incorporate life safety improvements to research lab. Provide additional protection for Pyrophoric Gases. Provide sprinkler protection inside the pyrophoric gas cabinet. Provide an Automatic shutdown device for pyrophoric gas flow when activated by interlocks tied into fire sprinkler. Provide a remote manual shut down device of pyrophoric gas outside the gas cabinet. Provide audible and visible alarm detection and monitoring for toxic and highly flammable gases including diborane, germane, ammonia and hydrogen gases Applicable references on the above are NFPA 55 (Compressed Gases Code) and NFPA 45 (Standard on Fire Protection for Labs using Chemicals). | BOURNS |  | Need to confirm Dept. funding commitment | Christopher Lynch | Maggie Souder | Jianlin Liu |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2017-05-23 | Confirm Dept. Commitment/Funding | [7 empty] | Enrico Baez | 4/11/EB-On Hold per Robert Brumbaugh. DND 7/14 Hold per customer on prioritization | YES | PD&C | 0 | 2017 | 2019-01-16
3319 | 3319 |  | FALSE | CAP.PROG. | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | Design Criterior completed DBE prequalification will begin on 9/7 | Jacqueline Norman | Sharyl Murdock | ----- |  | Mihai Gavan | 13 |  |  | FALSE | 3327000 |  | 2017-06-01 | DBE Competition | 2019-11-01 | 2021-05-01 | [5 empty] | Enrico Baez |  | NO | PD&C | 0 | 2017 | 2019-01-16
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | Electrical engineering study is being reviewed by department | Michael Pazzani | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Dave Bomba | 99 |  |  | FALSE | 15000 |  | 2017-06-13 | Approval of HVAC design | 2019-03-01 | 2019-06-01 | [5 empty] | Enrico Baez | 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 6 | YES | PD&C | 0 | 2017 | 2019-01-16
3341 | 3341 |  | FALSE | SoB | Anderson N & S - Exterior Painting | EXTERIOR PAINTING: Please see Karen Henry or Tim DeBolt for direction in painting exterior items around Anderson Hall North/South as follows: 1. Update Paint on exterior Window trim of both buildings. 2. Update Paint on lanterns and light poles 3. Fix plaster on building walls that is peeling off. |  |  | Client would liketo cancel project | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 1 |  |  | FALSE | 0 |  | 2017-07-18 | To be canceled by Client | [7 empty] | Enrico Baez | See work order 18W012349 scoped and annotated in FAMMIS. 6/11/18 EB- Add wall to current space and eliminate exisiting wall. Relocate exisiting A/C on wall. Minor electrical DND 7/14 Hold per customer on prioritization; per Corp Yard Space Planning | YES | PD&C | 0 | 2017 | 2019-01-16
3345 | 3345 |  | FALSE | SoB | Anderson N & S - Landscaping | DESIGN SVC & LANDSCAPE Construction request as follows for updated CURB APPEAL of Anderson North/South: 1. Roses Garden in middle of Stair landing/court to be removed and replaced with Grass 2. Add Large Planters (Metal or Cement) with Citrus Trees (either Kumquat/Lemon/Orange/Etc) on ledges that are at top section of front steps to deter skateboarders from jumping off of these ledges. 3. Remove dead trees on North and south ends of front lawn 4. Remove plants around granite sign in front lawn and replace with grass 5. Remove flowers and grass at both corners of front lawn around Citrus Trees and replace with DG and low growing flowering plants. 6. Pull all Ivy and crown vetch and add Pavers to East/Back side of Anderson Hall within landscaped/planter areas where ADA walkway runs and replace with nice picnic tables to include umbrellas and/or lounge seating around Anderson North for students. 7. Add DG in all areas where space is open/available surrounding outdoor seating area in back of building. 7. Remove all hedges surrounding alcove/arched areas along buildings. |  |  | On hold until ADA path of travel is completed | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 6 |  |  | FALSE | 0 |  | 2017-07-18 | Funding of design | 2019-03-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3346 | 3346 |  | FALSE | CNAS | Fawcett Seed Storage Freezer | Purchase and install a seed storage freezer for Ag Ops. Location needs to be determined based on project requirements. Assumptions: 225 sf space, electrical from Control Panel, which distribute power to components on interior of Chamber, and to Remote Condenser. See CPMS Attachments for specific information to develop Scope of Work. Location has been determined to be the first floor of Fawcett Hall. | FAWCETT LAB |  | Construction began on 9/17 | Kathryn Uhrich | Deborah McWilliams | Tim Close, D. McWilliams |  | Dave Bomba | 5 |  |  | FALSE | 145000 |  | 2017-07-24 | Complete Close-out | 2018-09-01 | 2018-12-19 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3354 | 3354 |  | FALSE | BAS | Lot 4/Barn Area ADA Improvements | Lot 4/Barn Area ADA Improvements - The proposed project will relocate an existing crosswalk that is not ADA compliant and provide path of travel improvements and additional ADA parking capacity in Parking Lot 4. The existing crosswalk located at West Campus Drive and Parking Lot 4 (north) was identified in the Draft ADA Transition Plan to be out of compliance. A Pedestrian Safety Study by Fehr & Peers completed in June 2008 identified the relocation of this crosswalk to approximately 100 feet east to provide a more visible, safe, pedestrian crossing. To increase pedestrian safety further, the crosswalk will be designed as a speed table. Additionally, Transportation and Parking Services proposes to create additional ADA parking spaces in Parking Lot 4 that exceed the required number, with hardscape and path of travel improvements that will connect to the new crosswalk. The improved crosswalk will correct required path of travel deficiencies from a parking lot that provides access to numerous publicly accessible buildings, as well as allow the Barn Expansion project to obtain Division of State Architect (DSA) approval once construction is completed. The funds to complete the crosswalk replacement will be requested from Campus ADA funds. Parking Lot 4 improvements will come from will come from TAPS. Although this project supports the Barn Renovation, its conception and need is not tied to the Barn project. The crosswalk improvements and additional ADA parking is needed to meet our ADA parking requirements and serve the growing demand on campus. This project is desired regardless of the Barn Renovation project. |  |  | In funding | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Fernando Nunez | 17 |  |  | FALSE | 25000 |  | 2017-08-15 | Updated Proposal & Cost Estimate | 2019-07-01 | 2019-09-27 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3363 | 3363 |  | FALSE | CHASS | DM(17-19) CA Photo Museum HVAC | Replace current HVAC with new Temp/Humidity control system. The system must adhere to Museum standards of Temp 70 +-3 and humidity 50 +-5. THIS IS A CRITICAL REQUEST. We are currently not able to borrow work from other museums due to the inconsistent numbers we are experiencing with temperature and humidity. | CA MUS PHOTO |  | Review of technical proposals and oral presentations. | Milagros Pena | Cindy Williams | Emily Papavero |  | Scott Donnell | 4 |  |  | FALSE | 1350000 |  | 2017-08-23 | Complete Close-out | 2018-03-01 | 2018-12-01 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3366 | 3366 |  | FALSE | CAP.PROG. | Genomics Sdwk Rpr-Drainage Impr | Genomics Accessibility Improvements - The proposed project will create an accessible sidewalk connection from the Genomics Building to the University Lab and University Office Building. Currently, there is no accessible north sidewalk linkage east of the Genomics Building. The project will demolish and replace approximately 300 square feet of asphalt to bring it up to grade. Two ADA ramps will be added to sidewalk extensions of approximately 300 square feet that connect across a driveway. Existing landscaping and irrigation will be removed and replaced. No trees will be impacted by this work. |  |  | Need to change project description | Jacqueline Norman | Sharyl Murdock | Jaime Engbrecht |  | Dave Bomba | 16 |  |  | FALSE | 0 |  | 2017-11-16 | Secure Funding | 2019-02-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3367 | 3367 |  | FALSE | CNAS | Field 16 Greenhouse Demo & Replacement | Replace GH1 and GH2 with a greenhouse from the Greenhouse Megastore. Conduct geotechnical investigation, prepare drawings and conduct asbestos and lead sampling. |  |  | Rebidding with added ammendment | Kathryn Uhrich | Deborah McWilliams | Sue Lee, D. McWilliams |  | Dave Bomba | 3 |  |  | FALSE | 300000 |  | 2017-09-15 | Re-bid | 2019-01-30 | 2019-06-28 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3376 | 3376 |  | FALSE | BAS | West Lothian Roof Replacement Design | Provide Schematic Design, Design Development and professional cost estimate to replace the existing single-ply membrane roof system on the Lothian West residence hall wings plus Common Area applications. Existing roofing is past its useful life and starting to experience multiple leaks that are damaging living spaces below. Design effort should select the most appropriate roof material for this roof plan. The intent is to design this year (alongside the Lothian East design) and construct immediately following the Lothian East roof replacement. | LOTHIAN HALL |  | In Pre-programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 19 |  |  | FALSE | 0 |  | 2017-09-28 | Project Pushed to Summer 2019 | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3380 | 3380 |  | FALSE | BAS | Falkirk Fire Alarm Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for a new addressable fire alarm system at Falkirk Apartments. Design to also include Wi-Fi underground conduit installation for future Wi-Fi system while site trenches are open for alarm conduit. Basis of design is similar to scope of work just completed at Oban Apartments. Key learnings from the Oban project to be incorporated into the Falkirk design. The intent is to design this year and construct next year. |  |  | John Franklin to coordinate with Angel Rocha (ITS) | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 32 |  |  | FALSE | 0 |  | 2017-10-03 | Project Pushed to Summer 2019 | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3382 | 3382 |  | FALSE | BAS | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to Summer 2019 | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 31 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to Summer 2019 | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3383 | 3383 |  | FALSE | BAS | W Lothian Air Handler Replacemt Study | Existing air handler equipment in West Lothian is original to the building and past its service life. Provide HVAC professional services to develop options for Air Handler replacement that meet UC Carbon Neutral 2025 goal. Each option analysis should include pros and cons for energy consumption, reliability, serviceability and system installation cost projections. At least one option should explore potential conversion to individual package units as practical. | LOTHIAN HALL |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 20 |  |  | FALSE | 0 |  | 2017-10-03 | CIB Approval | [10 empty] | PD&C | 0 | 2017 | 2019-01-16
3385 | 3385 |  | FALSE | VC-STU.AFF. | SRC North Gym Replace Interior Lights | Replace old technology sodium vapor light fixtures in SRC North Gymnasium with new technology LED light fixtures. Some flexibility available in the schedule. Selected vendor will need to phase work to minimize the effect on SRC operations and programming. | SRC NORTH |  | 100% CD's review | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Fernando Nunez | 1 |  |  | FALSE | 360000 |  | 2017-10-31 | Bidding - February 2019 | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | CNAS reviewing project location. | Kathryn Uhrich | Deborah McWilliams | Tracey Kahn, D. McWilliams |  | Scott Donnell | 4 |  |  | FALSE | 150000 |  | 2018-01-08 | CEQA | 2019-06-01 | 2019-09-01 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3392 | 3392 |  | FALSE | BAS | Bicycle Master Plan Study | Bicycle Master Plan Study. This CPMS project is for the funding and creation of a Bicycle Master Plan Study for the UCR Campus. It is not for a specific capital project. |  |  | Pre-Programming | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Jerrod Walters | 34 |  |  | FALSE | 115000 |  | 2017-11-13 | Funding | [10 empty] | PD&C | 0 | 2017 | 2019-01-16
3393 | 3393 |  | FALSE | CAP.PROG. | South Neighborhood Dist. Study | South Neighborhood District Study per discussions with the Provost/VCPB, July 2017. The South District Planning Study needs to provide guidance for future development in the South District that is inclusive of: **University aspirations to develop the South District to define the campus’ presence along the adjacent freeway (CA-60/215). **Development capacity, optimal building heights and conceptual massing presented both in metrics and a three dimensional format. **Broad parking strategy to meet the needs of the district in alignment with the campus’ overall parking management strategy and alternative transportation solutions. **High level understanding of infrastructure needs (electrical, domestic, fire and storm water, sanitary sewer, building heating and cooling) to meet the needs of the campus’ desired development capacity for district. **Pedestrian and vehicular connectivity. **East and South Campus Drive improvements |  |  | Programming | Jacqueline Norman | Sharyl Murdock | Uma Ramasubramanian |  | Fernando Nunez | 15 |  |  | FALSE | 309000 |  | 2017-11-15 | Receive Study Reports | [10 empty] | PD&C | 0 | 2017 | 2019-01-16
3395 | 3395 |  | FALSE | CAP.PROG. | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | Third party cost estimator needed. | Jacqueline Norman | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 20 |  |  | FALSE | 0 |  | 2017-12-03 | [11 empty] | PD&C | 0 | 2017 | 2019-01-16
3396 | 3396 |  | FALSE | ITS | C&C Rear Patio Tables/Shade | Installation of new exterior concrete slab and patio cover at the Computing and Communications Modular Buildings. The existing site will be cleared of all landscape to provide clear area to install concrete slab and address any grade/drainage issues. The addition of a proposed permanent patio cover is to be installed with full electrical options (lights, outlets, ceiling fans) to provide shade for future events and exterior lunch area. Shrubs along the street at the East side of the area are to be removed to provide a vendor/service ramp for events with the inclusion of lighted concrete seating within the space. | ITS CENTER |  | Additional funds added to project. | Danna Gianforte | Shelley Gupta | Sheila Mabee |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2017-11-16 | Execute PSA | [10 empty] | PD&C | 0 | 2017 | 2019-01-16
3397 | 3397 |  | FALSE | BAS | Dundee Residence Hall and Glasgow Dining | (Lot 22/Dundee-Glasgow) A newly proposed student housing development, including a single phase 760-bed residence hall and an 830-seat dining facility located on the existing Parking Lot 22 site south of Linden Street. The project is anticipated to be completed by Fall/Winter 2020. Funding for predevelopment activities including CEQA and staff augmentation to be determined. | ABER INVER |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Raoul Amescua | 36 |  |  | FALSE | 1120000 |  | 2017-11-21 | Complete Construction | 2018-12-01 | 2020-09-01 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3401 | 3401 |  | FALSE | CAP.PROG. | SOM Orbach Basement Sim&Clinical | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | All workgroup meetings concluded. Working on approval documents. | Jacqueline Norman | Sharyl Murdock | Jeff Kaplan |  | Mihai Gavan | 18 |  |  | FALSE | 0 |  | 2017-12-03 | Complete DPP | 2019-09-01 | 2020-12-01 | [8 empty] | PD&C | 0 | 2017 | 2019-01-16
3403 | 3403 |  | FALSE | BAS | Parking Lot 23 Addition | Parking Lot 23 Expansion - The goal of the project is to add additional parking capacity to Parking Lot 23 to serve that area of the campus. Current parking capacity in this area will be impacted by the closures of Lot 22 and Crest Housing parking area. Additional capacity will be need for employee parking. |  |  | Minor Cap Approval received 11/30/18 | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Daneca Stevens | 15 |  |  | FALSE | 92000 |  | 2018-05-17 | Design | 2019-05-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3406 | 3406 |  | FALSE | BAS | Lothian East Roof & Roof Equip. Replacement | Provide Schematic Design, Design Development and professional cost estimate to replace the existing built-up roof system and rooftop equipment that is past its useful life. The intent is to design this fiscal year and construct in FY'18/'19 (Summer 2018). Design effort shall select the most appropriate roof material and necessary HVAC replacement equipment. Construction timing will adjust as cash flow and summer schedule allows. Roofs shall include wings D, E, F plus common areas. | LOTHIAN HALL |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 37 |  |  | FALSE | 0 |  | 2018-01-25 | Complete Close-out | 2018-06-01 | 2018-09-01 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | Project #957440 assigned | Tamica Smith Jones | Joseph Erbland | Johnathan Jensen |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2018-08-23 | Create SOW | [10 empty] | PD&C | 0 | 2018 | 2019-01-16
3408 | 3408 |  | FALSE | ATHLETICS | Harrison Field Netting | Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | SOFTBALL STG |  | Per department: Project is on hold until further notice. | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2018-01-23 | On-Hold by Cust Until Further No | [10 empty] | PD&C | 0 | 2018 | 2019-01-16
3411 | 3411 |  | FALSE | BAS | MRB Café Buildout & MS&E Loading Dock Mods | MRB1 CAFE and SERVICE YARD INTERIOR FIT-OUT: provide design and construction services to build out the interior of the MRB1 Café shell and modify the MS&E Service Yard to accommodate the café deliveries and trash movement. This CPMS Request is to combine and replace previously approved CPMS #3378 and #3398 into one project as requested by A&E. Please note that the IRT Job walk has already been completed. Intent is to design in FY'17/18 and construct in FY '18/19. Opening to coincide with the MRB1 facility turnover. Food service equipment will be Owner Furnished on a separate UCR Purchase Order. Note that the MRB1 Café shell construction is provided by the separately funded MRB1 project, construction drawings for this shell space are attached in CPMS. | MAT SCI ENGR |  | Construction started 11/19. Going over submittals/RFI's. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Mihai Gavan | 1 |  |  | FALSE | 793000 |  | 2018-02-05 | Complete Construction | 2018-11-19 | 2019-02-22 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3413 | 3413 |  | FALSE | LIBR | Rivera Libr Gender Incl Restroom | Convert existing non-ADA multi-stall women's restroom to compliant ADA gender inclusive restroom. The project also involves the conversion of an existing non-ADA men's restroom to women's compliant ADA restroom. | RIVERA LIB |  | Need design | Steven Mandeville-Gamble | Jacqueline Bates | David Schuster |  | Dave Bomba | 3 |  |  | FALSE | 0 |  | 2018-03-26 | Code and policy compliance | [10 empty] | PD&C | 0 | 2018 | 2019-01-16
3415 | 3415 |  | FALSE | SoB | Anderson South Renovation | Per the sketched drawings that Dave Bomba was provided, please provide a proposal of what it would take to renovate Anderson South as follows: **1. Remove 1st Fl South side of Corridor wall and doors between 102 suite entrance and 106 suite entrance as well as adjoining walls within 102C. **2. Create a closet/wall, ideally, behind the existing door of the 102 Entrance running to the wall shared by 102A to include the best location for a door. Essentially, enclosing the window of 102, if possible. **3. Creating a closet under the stairwell between 1st floor and basement level, having entrance door flush with the bottom step of the stairwell. **4. Remove the West wall and door framing of room 001A, leaving an open look and no corridor in suite 001. | ANDERSON 2 |  | Design has been approved by the dept & arch. dwgs will be completed in 8 weeks | Yunzeng Wang | Angela Chang | Laurie Gustafson |  | Dave Bomba | 4 |  |  | FALSE | 24700 |  | 2018-02-26 | Architectual drawings | 2019-02-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3421 | 3421 |  | FALSE | BAS | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 5 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [10 empty] | PD&C | 0 | 2018 | 2019-01-16
3426 | 3426 |  | FALSE | BAS | Lothian Boiler Replacement | The boiler equipment at Lothian is original to the building and past its useful life. Design, procure and install a replacement boiler that incorporates the latest energy saving and management technology that can be cost-effectively installed as a direct replacement to the existing unit. | LOTHIAN HALL |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 6 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [10 empty] | PD&C | 0 | 2018 | 2019-01-16
3427 | 3427 |  | FALSE | BCOE | C-CERT Install Meter | Site: inland empire utility agency (IEUA) Meter install: Allen Bradley PowerMonitor 5000 price of meter is $7,410 Projected price of install: $15-20k Scope of work: Meter will be purchased by UCR for install at the main panel at the IEUA Carbon Canyon Facility. Once the meter is installed then it will be used to send Energy data back to their SCADA system and monitor and display real time data. |  |  | Blair to investigate | Christopher Lynch | Maggie Souder | Todd Ambriz |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2018-03-21 | Schedule Construction Start Date | 2019-02-04 | 2019-04-01 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3428 | 3428 |  | FALSE | BCOE | MSE Cleanroom | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | 2 of 5 suppliers contact have responded | Christopher Lynch | Maggie Souder | Margaret Souder |  | Dave Bomba | 6 |  |  | FALSE | 700000 |  | 2018-04-04 | Vendor Cost Estimates | 2019-03-01 | 2019-05-31 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3430 | 3430 |  | FALSE | BAS | TAPS Cust Svc Lobby Upgrades | Upgrades to Customer Service Lobby – Need to complete Tenant Improvement project upgrade customer service counter in Parking Services Building. Want to replace current counter to allow for; modern computer equipment, dividers between customers’ transaction spaces, under counter space for filing cabinets and check writing space. Please coordinate with Auxiliaries’ primary PM John Franklin. | PARKING SERV |  | On hold | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Dave Bomba | 16 |  |  | FALSE | 0 |  | 2018-05-17 | Meet to discuss scope & funding | [10 empty] | PD&C | 0 | 2018 | 2019-01-16
3432 | 3432 |  | FALSE | ATHLETICS | Athletics Replace Scoreboard | Please assist with coordinating the process for replacement of existing soccer scoreboard to a new model. We will work with A&E to develop criteria and how to accomplish the task. |  |  | New | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Scott Donnell | 1 |  |  | FALSE | 0 |  | 2018-07-19 | On-Hold | [10 empty] | PD&C | 0 | 2018 | 2019-01-16
3437 | 3437 |  | FALSE | FAC-PLNG-DESIGN-CONST | UCPD Generator Replacement | Replace unsupported 125kw generator with new - Critical Facility |  |  |  | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2018-10-08 | Execute EDPA | 2019-07-01 | 2019-08-30 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3438 | 3438 |  | FALSE | CAP.PROG. | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | Agreement with UCR Engineer is being sent to the city | Jacqueline Norman | Sharyl Murdock | Dave Bomba |  | Dave Bomba | 21 |  |  | FALSE | 0 |  | 2018-08-22 | City to determine schedule | [10 empty] | PD&C | 0 | 2018 | 2019-01-16
3439 | 3439 |  | FALSE | BAS | TAPS Strategic Master Plan Study | STUDY - Transportation And Parking Master Plan Study This study initiated by TAPS is part of a comprehensive planning effort within Auxiliaries to develop a strategic transportation and parking plan that will guide the university’s transportation and parking efforts over the next decade. This is complementary to the campus Physical Master Plan Study and will help inform the future new LRDP. |  |  | Postponed until Mid-2019 | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Jerrod Walters | 18 |  |  | FALSE | 0 |  | 2018-06-05 | Postponed until Mid-2019 | [10 empty] | PD&C | 0 | 2018 | 2019-01-16
3441 | 3441 |  | FALSE | CHASS | INTS 1121 Convert Classroom to Dance Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use |  |  | Programming | Milagros Pena | Cindy Williams | Anna Finn |  | Daneca Stevens | 1 |  |  | FALSE | 0 |  | 2018-06-22 | Design | 2019-11-01 | 2019-12-26 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3445 | 3445 |  | FALSE | BAS | Mail Services Bldg Power | Campus Business Services is leasing a new digital press (Konica Minolta Accurio Press C6085 for this location in addition to moving a dozen pieces of small existing equipment from the 2100 Atlanta building into the Mail Services Building. This equipment will require additional power to the building and new power drops within the work space to support the new equipment. Facilities Services believes a new 250 amp panel will need to be set in the building. Power is available from the main panel at the Shipping and Receiving building across the driveway. Please provide an Electrical Engineering drawing and cost estimate to accomplish above. | MAIL |  | In construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 21 |  |  | FALSE | 0 |  | 2018-06-27 | Complete Close-out | 2018-10-01 | 2018-12-01 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3451 | 3451 |  | FALSE | CHASS | Arts 166 Perf Lab Inspection | Approval of seating plans for Arts 166, Performance Lab. Dave Bomba has the plans. Must be inspected and approved by Director of Inspection & Quality Assurance and the Campus Fire Marshall. |  |  | Seeting purchase and installation secured through procurement | Milagros Pena | Cindy Williams | Paul Richardson |  | Dave Bomba | 5 |  |  | FALSE | 0 |  | 2018-07-26 | Arrival of seating (Dec) | 2018-12-10 | 2018-12-31 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3452 | 3452 |  | FALSE | CAP.PROG. | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  |  | Jacqueline Norman | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 2 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Programming | [7 empty] | Dan Lerman | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment….. | YES | PD&C | 0 | 2018 | 2019-01-16
3453 | 3453 |  | FALSE | BAS | ECS N&S Playground Shade & Turf | Provide Schematic Design, Design Development and Professional Cost Estimate for the alteration of existing shade structures, provision for additional shade structures, refinish interior metal fencing, and the replacement of existing grass with synthetic turf at the Early Childhood Services north and south playground areas. Prepare drawings so that they can be bid and constructed as separate projects. |  |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 22 |  |  | FALSE | 0 |  | 2018-07-03 | Dept approval/funding | [7 empty] | Dan Lerman |  | YES | PD&C | 0 | 2018 | 2019-01-16
3455 | 3455 |  | FALSE | BAS | Campus Traffic Engineering Study | This request is to fund the contracting of a consulting firm to study of the impacts related to the desired construction of a new parking garage on the UCR campus. Project will inform on site selection, traffic impacts and opportunities. This project will be funded through a parking garage planning budget allocation in the approved 2018-19 TAPS budget. |  |  | Project number 958097 assigned | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Dave Bomba | 27 |  |  | FALSE |  | 0 | 2018-07-23 | Compliation of statistics | 2018-11-05 | 2019-05-01 | [5 empty] | Enrico Baez | DL, 4/29/18; Enrico is cordinationg this. The permits are approved. EB. 5/11/18- waiting for PO to be issued to Vendor. Customer provided PO numbers, waiting to schedule install with vendor, 5 week lead time. | YES | PD&C | 0 | 2018 | 2019-01-16
3458 | 3458 |  | FALSE | CAP.PROG. | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | New | Jacqueline Norman | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 7 |  |  | FALSE | 0 |  | 2018-07-16 | Unknown | [7 empty] | Paul Ditty |  | N/A | PD&C | 0 | 2018 | 2019-01-16
3459 | 3459 |  | FALSE | BAS | A-I Hardscape Landscape Design | Provide Schematic Design and Design Development drawings for a selective renovation of all hardscape and landscape around the perimeter of the Aberdeen-Inverness housing complex. Scope to include (but not limited to) widening of South Walk and replace its asphalt with concrete pavers, upgrade hardscape and landscape at Horseshoe, replace selected lawn areas with hardscape, seating and solar umbrellas at east and west lawns of Building E, consider new bike storage along South Walk, consider modifying slopped lawn between Building A and Linden St., generally reduce lawn areas and replace with sustainable planting, prune or replace unkempt trees, replace selected light fixtures to match Dundee fixtures, and generally freshen the landscaping so that it is harmonious with the new Dundee development. Design to be packaged in phases, with the South Walk and Dundee-facing landscape to be ready in Phase 1 for construction timing alongside Dundee-Glasgow landscaping in Spring of 2020. | ABER INVER |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 23 |  |  | FALSE | 0 |  | 2018-07-16 | Consultant Selection | 2020-01-01 | 2020-08-01 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2018 | 2019-01-16
3460 | 3460 |  | FALSE | BAS | A-I Restroom Replacement - Reconfig | Provide Schematic Design and Design Development drawings for the complete replacement of the restrooms in all four resident hall wings. Existing restroom fixtures and finishes are largely original to the building and long past their service life, causing serious leaks between floors. New restrooms will be reconfigured to meet current accessibility code. Documents to be assembled for phased construction, one wing per summer, with the first building (D-Wing) to be constructed in Summer 2019. | ABER INVER |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 26 |  |  | FALSE | 0 |  | 2018-07-19 | Consultant Selection, funding | 2019-06-01 | 2019-08-01 | [5 empty] | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | PD&C | 0 | 2018 | 2019-01-16
3462 | 3462 |  | FALSE | BAS | A-I Restaurant & Lobby Reconfiguration | Provide Schematic Design and Design Development drawings for the complete reconfiguration of Building C including kitchen, dining space, and common areas. The restaurant and kitchen areas are largely original to the building and well past their useful life. The new, replacement, Glasgow restaurant coming on-line in Fall 2020 will allow a needed reprogramming and modernization of this space. Preliminary Program for this space includes a smaller Catering Kitchen, Meeting Rooms, new KUCR studio as well as a modernization and upgrade of the Lobby and other Common Areas. Documents to be assembled for a Fall 2020 construction start. | ABER INVER |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 24 |  |  | FALSE | 0 |  | 2018-07-17 | RFQ Development | 2020-08-01 | 2021-06-01 | [5 empty] | Dan Lerman | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... DND 7/14 Hold per customer on prioritization | YES | PD&C | 0 | 2018 | 2019-01-16
3463 | 3463 |  | FALSE | BAS | Landscape Strategic Plan for Housing Services | Provide a comprehensive study of existing landscape areas within Auxiliary Services and provide specific and actionable recommendations for their conversion to sustainable landscaping by location. Study to include all Resident Hall and Apartment properties and include conceptual cost estimates, by location, for proposed landscape conversions. |  |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 25 |  |  | FALSE | 0 |  | 2018-07-17 | RFQ Development | [7 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2018 | 2019-01-16
3465 | 3465 |  | FALSE | BAS | HUB MOD Pizza Permits, Inspection | UCR to provide ONLY permitting and field inspection services to support new tenant (MOD Pizza) design-build fit-out of existing space. Scope will likely include replacement of most kitchen equipment, counters and finishes within the existing space footprint. Existing pizza oven is thought to be reused but likely rotated in place to accommodate their new layout. | HUB |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 28 |  |  | FALSE | 0 |  | 2018-07-30 | Managed by Real Estate | 2018-10-01 | 2018-12-01 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2018 | 2019-01-16
3466 | 3466 |  | FALSE | BAS | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 30 |  |  | FALSE | 0 |  | 2018-07-31 | Funding | 2019-05-01 | 2019-12-01 | [5 empty] | Enrico Baez | 4/3/2018 Met with Maggie. She is working with BKM. Floor to go down first. BKM furniture on top. Annotated in Famis. | YES | PD&C | 0 | 2018 | 2019-01-16
3467 | 3467 |  | FALSE | BAS | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 29 |  |  | FALSE | 0 |  | 2018-07-31 | Dept. approval to proceed | 2019-07-01 | 2020-02-01 | [5 empty] | Enrico Baez | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. EB 6/1 site visit- 3 door between 4 offices require sound proofing. Doors measure 36" x 106". Photos in FAMMIS. O-RVL: Uploaded sound soak panel data on FAMIS and is available on the Project Server File. 10/18/18 O-RVL: Per FS team meeting, we now have a clarified process that sound soak is not included in the SLA due to the fact this is not part of the work we perform at FS. Because we already committed to do further follow up with the sound soak, we will not charge this time but moving forward sound soak will be a recharge service as the team does not have the skillset to do the work and therefore outside the SLA. | YES | PD&C | 0 | 2018 | 2019-01-16
3469 | 3469 |  | FALSE | CHASS | Belltower Repairs | Design, fabrication and replacement of bell beams for bells 24, 26, 28, 30 and 32. Design, fabrication and installation of bracing to brace the 5 other bells beams that are cracking, and corrective maintenance on the clappers & head pieces-this would include complete removal, cleaning, reaming, bushing and lubricating before re-installing and clean and lubricate the transmission system as much as possible without complete disassembly to make the instrument easier to play. | BELLTOWER |  | New | Milagros Pena | Cindy Williams | Reasey Heang |  | Daneca Stevens | 6 |  |  | FALSE | 0 |  | 2018-08-16 | Funding | [7 empty] | Paul Ditty | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | PD&C | 0 | 2018 | 2019-01-16
3470 | 3470 |  | FALSE | PLANNING & BUDGET | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | New Study | Gerry Bomotti | Jacqueline Norman | Drew Hecht |  | Drew Hecht | 10 |  |  | FALSE |  |  | 2018-11-06 | Complete Review | [7 empty] | Dan Lerman | DL, 4/2/18; This is a small partition wall with sound proofing to minimize noise from the compressor that is disruptive to the Helium Ion Microscope…….DL, 4/16/18; We will schedule this work to be complete by the end of the Spring quarter. DL, 5/19/18; Walked project with Ron. FAMIS work order producd and material is being ordered.... | YES | PD&C | 0 | 2018 | 2019-01-16
3471 | 3471 |  | FALSE | VC-STU.AFF. | HUB Elect/Gas Meters 8 Location | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | New | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | J.Franklin/J.Espinoza | 5 |  |  | FALSE | 0 |  | 2018-08-20 | Awaiting consultant assessment | [7 empty] | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | PD&C | 0 | 2018 | 2019-01-16
3472 | 3472 |  | FALSE | BAS | Lot 21 Trash Enclosure Relocation | Construct a new CMU trash enclosure with water and power in a different location of Lot 21 to replace the existing enclosure that will be demolished to make way for the Dundee Residence Hall construction. Include hose bib for cleaning and power for future compactor installation. New enclosure needs to be on line BEFORE site construction can start on Dundee-Glasgow in January 2019. |  |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 35 |  |  | FALSE | 0 |  | 2018-08-15 | Hire Design Consultant | [7 empty] | Paul Ditty |  | N/A | PD&C | 0 | 2018 | 2019-01-16
3474 | 3474 |  | FALSE | PLANNING & BUDGET | RUSD STEM High School |  |  |  | Real Estate project | Gerry Bomotti | Jacqueline Norman | ----- |  | Raoul Amescua | 3 |  |  | FALSE | 0 |  | 2018-10-31 | Regents Approval of Ground Lease | 2019-07-01 | 2022-09-01 | [8 empty] | PD&C | 0 | 2018 | 2019-01-16
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM17-19 Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Working with Engineer to understand Campus system. | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 1 |  |  | FALSE | 1250000 | 0 | 2018-10-17 | Complete Final Report | [7 empty] | Ron Veloz | Completed SOW, met withJess and informed of work and color. | YES | PD&C | 0 | 2018 | 2019-01-16
3477 | 3477 |  | FALSE | BAS | A-I Solar Tanks Demolition | Decommission and remove two large existing solar tanks outside south corner of restaurant loading dock and remove associated piping up to roofline. Existing rooftop solar panels can remain in place as they will be removed as part of the future A-I roofing project. | ABER INVER |  | Project number assigned | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 38 |  |  | FALSE | 0 |  | 2018-09-05 | Complete Close-out | 2018-12-01 | 2018-12-01 | [5 empty] | Ron Veloz | 10/29/18 RV: Last meeting it was discussed that FS does not install Security Camera systems. Ron V spoke with Maggie on 10/26 to inform her that the project will be removed from the FS Minor Ren. List and she will need to contact ITS to request the Security Camers. 08/27/18 RV: Updated notes. Moved to "Que to Start". 09/19/18 RV, Install Security Cameras at points of entry. Install DVR locally in closet at an adjacent room. 08/23/18-RV Met with D.L. and Jason W. and verified F.S. will perform cabling installation and mount cameras. Equipment cost is not included in the SLA. R.V. will communcate informantion to Maggie. 08/22/18 O-RVL: Met with M. Souder to determine security camera needs and approximate location. | YES | PD&C | 0 | 2018 | 2019-01-16
3478 | 3478 |  | FALSE | BAS | Ivans Hinderaker Ext. Cladding | Replace existing exterior cladding outside of Ivan's kiosk with new building materials that will cover the abandoned openings in the exterior and provide a cohesive and waterproof envelope for this structure. | HINDERAKER |  | Project number assigned | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 99 |  |  | FALSE | 0 |  | 2018-09-07 | Bidding | [7 empty] | Ron Veloz | to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | NO | PD&C | 0 | 2018 | 2019-01-16
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. |  |  | New | Steven Mandeville-Gamble | Jacqueline Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 2018-11-27 | Client approval/funding | [7 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2018 | 2019-01-16
3482 | 3482 |  | FALSE | CHASS | Humanities 3rd Floor Install Sail Shades | Shade sail installation of the patios on the third floor of Humanities Social Science. There are two patios, one on the 3600 wing and one on the 3400 wing. |  |  | New | Milagros Pena | Cindy Williams | Paul Richardson |  | Daneca Stevens | 7 |  |  | FALSE | 0 |  | 2018-10-10 | Funding | [7 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2018 | 2019-01-16
3483 | 3483 |  | FALSE | CNAS | Pierce Fume Hoods Relocation | Relocate fume hoods as marked in attached diagram from Pierce rooms 3306 and 3310 to the locations marked in the attached diagram in Pierce rooms 3419, 3425 and 3443. |  |  | New | Kathryn Uhrich | Deborah McWilliams | Jinsong Zhang |  | Dave Bomba | 1 |  |  | FALSE |  | 0 | 2018-10-09 | Relocate fume hoods | 2018-12-01 | 2019-01-01 | [5 empty] | Ron Veloz | 10/03/18: RV spoke with Dan. He had previously met with Maggie and had scoped this project. | YES | PD&C | 0 | 2018 | 2019-01-16
3484 | 3484 |  | FALSE | PLANNING & BUDGET | 266 Frost Ct Main House Demolition | Develop project budget and timeline, obtain funding from VCPB. Coordinate disconnection of all utilities: Electrical, Gas, and Water. Disconnect and cap sewer Coordinate HAZ Mat testing and report for asbestos and lead Hire abatement contractor (if necessary) to remove haz materials. Hire demolition contractor to demolish and dispose of existing house, garage and out buildings. Foundations to remain – but make safe and remove potential hazards (rebar, bolts, etc.) protruding from foundation. Paving, pavers and other “patio” slabs to remain – make safe by removing tripping hazards. Identify any hazards (I.E.; unstable retaining walls, debris piles, etc.) and make safe and secure or remove if more cost effective. |  |  | DM received. Sequestration in progress. | Gerry Bomotti | Jacqueline Norman | Scott Donnell |  | Daneca Stevens | 5 |  |  | FALSE | 40000 |  | 2018-11-15 | Decision Memo | 2019-04-01 | 2019-04-01 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2018 | 2019-01-16
3486 | 3486 |  | FALSE | VC-STU.AFF. | HUB 353/381, Costo 111 Add'l Wall/Doorway | Please evaluate additional wall/door way requests for HUB 353/381 and Costo Hall 111. | HUB |  | New | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 6 |  |  | FALSE | 0 |  | 2018-11-26 | New | [7 empty] | Dan Lerman | DD 7/17: IRT Scoped with Dan present. Attached to FS Project. REF CMPS 9043 | YES | PD&C | 0 | 2018 | 2019-01-16
3488 | 3488 |  | FALSE | BAS | CBS HUB Business Center | Provide a light renovation of the HUB Modular space to include new electrical drop for the Card Office cubicles in the North Office (where the copy machines are now), and replace flooring in the North Office as required, install ADA shelf at the front desk and other minor scope items to facilitate the move of the Card Office to this building. This must be a Winter Break project so that the Business Center remains online during the normal campus schedule. |  |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Fernando Nunez | 41 |  |  | FALSE | 15000 |  | 2018-11-13 | Complete Project Close-Out | 2018-12-17 | 2018-12-21 | [5 empty] | Ron Veloz | 10/03/18 O-RVL: Install one 32" monitor asouth wall center of table, Install 55" TV at west wall(need power & data), install white bd at east wall 8' from north corner, install chalk bd at east wall 2'-6" from corner at 8" above small table. | YES | PD&C | 0 | 2018 | 2019-01-16
3491 | 3491 |  | FALSE | BAS | Oban Comm Ctr Remodel | General remodel and freshening of the Oban Family Housing Community Center to include Laundry Room, Public Restroom and Recreation Room. Scope documents and partial drawings attached. This was originally two separate projects that Facility Services was managing but has now been requested that A&E take over due to evolving complexity and dollar cost. |  |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 40 |  |  | FALSE |  |  | 2018-11-16 | Funding | 2019-06-15 | 2019-08-31 | [5 empty] | Dan Lerman | 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. We are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans..... DND 7/14 Hold per customer on prioritization | YES | PD&C | 0 | 2018 | 2019-01-16
9021 | 9021 |  | TRUE | BAS | Oban 2nd Story Porch Repair | Draft Scope: Replace rotted elevated entry porch decking and railing supports as needed for 13 decks. Work should proceed throughout the year in a coordinated fashion with Auxiliary Services so that the apartments can remain open for occupancy. This is not a summer project as Family Housing is occupied year round. Unit numbers are 2, 10, 26, 28, 30, 36, 40, 50, 56, 112, 122, 124, 126. |  |  | In Programming. Not yet entered into CPMS. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 99 |  |  | FALSE | 0 |  |  | Dept Enter into CPMS | [7 empty] | Paul Ditty | Complete in conjunction with 19P000026. Canceled to be completed on 19P000035 | N/A | PD&C | 0 | 1900 | 2019-01-16
9022 | 9022 |  | TRUE | BAS | Plaza Apt-Ext Staircase Replacement | Draft Scope: Replace seven (7) sets of worn exterior staircase wooden stringers and treads as identified by Enrico Baez of Facilities on 5/25/17. Identified staircases to second story apartments represent most urgent replacements needed (Priority #1 and #2). |  |  | In Programming. Not yet entered into CPMS. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 99 |  |  | FALSE | 0 |  |  | Dept Enter into CPMS | [6 empty] | 2018-10-03 | Ron Veloz | 10/03/18 RV Walked site with Dan L. SOW Install TV Bracket at south wall center of room. Requires Power (no Data)installation of mounting bracket. TV and brk is located in Sarah Galloways office. Scope is completed. Dinh 9/18 19P000023/19P000026 requests for paint to be included in project scope for room. | YES | PD&C | 0 | 1900 | 2019-01-16
9029 | 9029 |  | TRUE | CHASS | CHASS INTS Install Benches | Install benches on the second floor north exterior of CHASS INTS. This is near the general assignment classrooms. Many students wait for classes outside and they don't have a place to sit. They sit on the ground mostly which causes a bit of tripping hazard. This request has come from ASUCR. |  |  | Jacqueline to review exterior space and make a recommendation. | Milagros Pena | Cindy Williams | Paul Richardson |  | ---- | 99 |  |  | FALSE | 0 |  |  | Campus Architect Review | [7 empty] | Paul Ditty | Complete in conjunction with 19P000023. Canceled to be completed on 19P000035 | N/A | PD&C | 0 | 1900 | 2019-01-16
9055 | 3495 |  | FALSE | VC-RED | Pysch Loading Dock Haz Waste Storage | There’s been an increase use of biological and chemical hazards being used by researchers and their research projects within the Psychology (V3) vivarium. When hazardous substances are used/generated in the vivarium, the current practice is for that waste to be removed by the researcher and taken to their lab for disposal by EH&S. This would mean that hazardous agents are being transported across campus which could potentially lead to an accidental exposure. In order to comply with the hazardous storage and transportation regulations, RED proposes that a hazardous storage shed be built on or near the Psychology (V3) loading dock thus minimizing any potential from an accidental contamination. It would be a chain link storage shed with two rooms (one for biological hazards and the other for chemical hazards), and a solid roof. Around the outside of the shed would also need to have some sort of vinyl covering. As for size, a 10’ x 20’ (two 10’ x 10’) shed should meet the needed storage space. Sample designs can be provided. |  |  | Received project request 12/4/18 | Michael Pazzani | Laura Manor | Dierk Biggs |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2018-12-04 | Approval of CD's | 2019-03-04 | 2019-03-29 | [5 empty] | Paul Ditty |  | N/A | PD&C | 0 | 2018 | 2019-01-16
3490 | 3490 |  | FALSE | BAS | East Campus Parking Structure | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. |  |  | Funds sequestered | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Dave Bomba | 43 |  |  | FALSE |  |  | 2018-12-06 | CEQA | 2019-12-01 | 2021-02-01 | [5 empty] | Paul Ditty |  | N/A | PD&C | 0 | 2018 | 2019-01-16
3496 | 3496 |  | FALSE | LIBR | Rivera Library Install Gate | Rivera library gate installation |  |  | New | Steven Mandeville-Gamble | Jacqueline Bates | Rebeccah Goldware |  | ---- |  |  |  | FALSE |  |  | 2019-01-08 | New | [6 empty] | 2018-11-14 | Ron Veloz | Complete work in conjunction with 19P000059. 10/29/18 RV: Scoping is completed. Carpenters to Remove Ceiling Mounted TV supports from the lobby ceiling. Work may require Carpenters to open the hard ceiling and remove the TV bracket posts if they cannot be unscrewed from the mounting brkt at the deck above. Work ay also require drywall patch back, tape, sand and paint the lobby ceiling. 11/14/18 RV: Moved to Que to Start. | YES | PD&C | 0 | 2019 | 2019-01-16
17P000254 |  | 17P000254 | FALSE | PLANNING & BUDGET | SL5-FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS | Project in progress; ITS installing data. | CORP PP WHSE | 0106B | HOLD - FACILITIES SERVICES | Gerry Bomotti | Jacqueline Norman | DALAN DINH |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-06-07 | [6 empty] | 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DD 10/6: On hold pending discussion on space…..DL, 7/11/18; I understand there is movement on this project but I need to check in with John P. or Chris P. for a status update. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
17W012504 |  | 17W012504 | FALSE | CNAS | PAINT Business OFFICE AND CONF. ROOM | Complete as of 10/22/18. | ENTOMOLOGY | 170 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 27 | 26 | FALSE |  |  | 2017-05-04 | [6 empty] | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000027 |  | 18P000027 | FALSE | CNAS | SL5-CHAPMAN PREP AND PAINT LAB | Complete as of 7/12/18 | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-05 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again...... DL, 4/2/18; This space is still on schedule for 7/1/18 completion date.....FAMIS work orders have been produced.....DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th..... |  |  |  |  | FS | 0 | 2018 | 2019-01-16
18P000028 |  | 18P000028 | FALSE | CNAS | SL5-CHAPMAN PATCH AND PAINT | Complete as of 7/12/18 | CHAPMAN | 0010A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced .......DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th..... |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000029 |  | 18P000029 | FALSE | CNAS | SL5-CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS | Complete as of 7/11/18 | CHAPMAN | 1 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain......DL, 5/24/18; This work is scheduled to be complete on or before 7/1/18.....DL, 6/16/18; Blinds are delayed to mid July but window clenaning is still on schedule......DL, 7/11/18; This Project is 100% Complete |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000030 |  | 18P000030 | FALSE | CNAS | SL5-CHAPMAN PREP AND PAINT FROM WATER DAMAGE | Complete as of 11/8/18 | CHAPMAN | 100 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete..... |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000094 |  | 18P000094 | FALSE | BAS | SL5-OBAN LAUNDRY ROOM RENOVATION | Scope of work has changed and project to be routed to Google IRT/CPMS for completion | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2017-09-08 | [6 empty] | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on bid. 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/12 EB- rec'd approval to contract with Design West to consult on electrical panel upgrade. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000095 |  | 18P000095 | FALSE | BAS | SL5-THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS | Canceled per customer on priortization list. | THE PLAZA | A0013 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  | Canceled | HOLD | FALSE |  |  | 2017-09-08 | [6 empty] | 4/11/EB-On Hold per Robert Brumbaugh. 6/8 EB-emailed R. Brumbaugh for status update. |  | Ron Veloz | 10/19/18 O-RVL: Walked the proposed location with Dr. Barsukov to review needs and location for nitrogen tanks in the hall. DL suggested to construct a wall with double doors approx 2' below the ceiling height. 09/27/18 O-RVL: Walked site with Chris P, Dan L., Deborah Mc Williams & Mayela C to review SOW. | YES | FS | 0 | 2017 | 2019-01-16
18P000099 |  | 18P000099 | FALSE | CNAS | SL5-EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 | Plans will be developed and will be submitted for review and approval. | GEOLOGY |  | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 26 | 23 | FALSE |  |  | 2017-09-08 | [6 empty] | 12/6/18, DL; This project is a priority #26 and may be completed in the next 12 - months…..DL 1/3: Chris to verify with customer on electrical requirements for completion……DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress…..DL, 7/11/18; Still need to work on plans…. Target date is 9/30/18….. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000106 |  | 18P000106 | FALSE | BAS | SL5-HOUSING PROJECT - OBAN REC ROOM REMODEL | Scope of work has changed and project to be routed to Google IRT/CPMS for completion | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 3 | FALSE |  |  | 2017-09-14 | [6 empty] | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. DL, 7/11/18; Per Susan this project is back on track. Project is scoped. Gunther will start working on the plans and permits. Once we have the approved permit. still need to check in with Susan on a few items.....Target complet date will be mid- fall...... |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus | NO | FS | 0 | 2017 | 2019-01-16
18P000111 |  | 18P000111 | FALSE | CHASS | SL5-KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 | Complete as of 7/13/18 | CHASS INT S |  | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Jason Williams |  |  |  | FALSE |  |  | 2017-09-15 | [6 empty] | EB 1/31/18 Work was assigned to lock shop 12/7/17…. DND 5/11: Spoke with Jason, all work complete to be completed as trade is available. Only work remaining is on 3150 A; Jason short staffed to finish project but it's on his radar. 07/13/18 H-FMS: Troubleshoot programming and settings for this controller. Clear all data from panel and reset, perform required downloads, re-test and verify both doors working correctly. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000117 |  | 18P000117 | FALSE | CNAS | SL5-PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION | Complete as of 9/10/18 | WEBBER | 1303 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-21 | [6 empty] | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work....DL, 5/9/18; Produced work order for JEss to test for lead paint and ACM....Von wall is hot, everything else is good to go. I will schedule the work soon. The space is vacant......DL, 7/11/18; This project is in progress. Target Complete Date is 8/10/18....DL, 7/25/18; Vinyl plank and bullitin boards the balance of the task for this project. Still on target for complete on 8/10/18.....DL; 8/10/18; We were schedule to install the fllor and identified Asbestos,. Jess is working on the propsal and schedule for the abatment. This will require a 14- dat notification to the AQMD. This space is vacant with no scheduled move in date......DL, 8/22/18; Abatment is scheduled for this Tursday and Friday. We will scheule the carpet in dry errase boards for next week.Target complete date will be 8/31/18.....DL, 9/6/18; This project is 100% Complete...... |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus | NO | FS | 0 | 2017 | 2019-01-16
18P000118 |  | 18P000118 | FALSE | CNAS | SL5-OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT | Complete as of 7/25/18. | OLMSTED | 1337 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2017-09-20 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space.......DL, 6/16/18. New staff member schedule to start mid july. BKM is also scheduled for mid july. This project will require cabinets to be removed, new carpet, paint and blank out electrical outlets that will no longer be used.. new signage too.....DL, 7/11/18;This project is in progress. Complete date is 7/20/18......DL, 7/25/18; This project is 100% Complete....... |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000121 |  | 18P000121 | FALSE | CAMPUS | SL5-PHYSICS HYDRATION STATION - PHYSICS HALL | Reviewing campus standards for these project requests. | PHYSICS | 0 | HOLD - FACILITIES SERVICES |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | 12/6/18, DL; This project is currently on hold…... DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  |  |  | NO | FS | 0 | 2017 | 2019-01-16
18P000122 |  | 18P000122 | FALSE | CAMPUS | SL5-MS&E HYDRATION STATION - MS&E HALL | Reviewing campus standards for these project requests. | PHYSICS | 0 | PROJECT INTAKE |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Ron Veloz | 01/10/19 O-RVL: CLOSE OUT-WORK COMPLETED. All work for this project is completed. Email sent to Monty & team on Jan 04, 2019 confirmating all work is completed. 12/14/18 O-RVL: Loading dock Post and Chain fabrication, is in progress, Auto door operators are on Order/Contract in progress, Loading dock signage is in progress by sign shop, information was confirmed by Chris Pillen as of 12/13/18. All other request related to this project have been completed. RV sent updates to Monty on 12/13/18. 11/14/18 RV: Walked Capitol door on 10/31 for pricing. pending quote for auto door operators. 10/30/18 RV: Walke Paradise Door -Automatic Door operator vendor to site. Met with Jason to discuss door access hardware & function of locksets . Pending quote. 10/03/18 RV: Notes from FAMIS: Lock Shop - Chris working with Jason to purchase and install two sets of automatic door openers with plain face plates - to be installed in the back receivin area. | YES | FS | 0 | 2017 | 2019-01-16
18P000126 |  | 18P000126 | FALSE | CHASS | SL5-HMSS ESTIMATE REMOVE WALL & CHANGE DOORS | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 3611 | QUEUE TO START | Milagros Pena | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 2017-09-28 | [6 empty] | 12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000194 |  | 18P000194 | FALSE | ITS | SL5-TELEPHONE WINDOW REPLACEMENT | Canceled by customer; duration of hold was over 10 months. Customer to resubmit when ready to proceed | TELEPHONE | 101 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 5 | 6 | FALSE |  |  | 2017-11-20 | [11 empty] | FS | 0 | 2017 | 2019-01-16
18P000198 |  | 18P000198 | FALSE | VC-STU.AFF. | SL5-HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Plans will be developed and will be submitted for review and approval. | HUB | 0 | QUEUE TO START | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 1 | 5 | FALSE |  |  | 2017-11-21 | [6 empty] | DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…... |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000201 |  | 18P000201 | FALSE | CHASS | SL5-ARTS REMOVE COUNTERTOP/SHELVES | Complete as of 8/23/18 | ARTS | 0106A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 3 | TRUE |  |  | 2017-11-21 | [6 empty] | DL, 6/16/18; Ned to walk, scope and submit plans ASAP…..Sent Paul an email requesting information on Status of Faculty hire status……DL, 7/11/18; Paul is on Jury Duty and he said he should return back to work next week. Current Targe complete date is mid September......DL, 7/25/18; Carpentery and Electrical is complete. Patch and paint has started. Target complete date is 8/3/18......DL, 8/8/18; Space is VAcant and ready for paint. The paint department is working on several other projects that require their attention. The paint department will complete the work in the near future......DL, 8/22/18; This Project is 100% Complete....... |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000205 |  | 18P000205 | FALSE | CHASS | SL5-CHASS INT S CREATE DOOR | Complete as of 9/21/18 | CHASS INT S | 2117H | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-11-27 | [6 empty] | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18……DL, 5/24/18; Plans were approved. WE need to schedule the work…..DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18...........DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... .. DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date..........DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18............DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware.....DL, 9/19/18; This Project is 100% Complete...... |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000209 |  | 18P000209 | FALSE | CHANCELLOR | SL5-VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 | Customer provided estimate for project; verifying if funding is available to proceed with project. | STUDENT SERV | 0 | QUEUE TO START | Kim Wilcox | Karim Zahedi | ANGIE GRAY |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2017-11-30 | [6 empty] | 1/15/19, DL; Ron V is still working with Angie on verifying a vendor and product…………..12/14/18, DL; Ron V. is currently working to find a more affortable turnstyle system. When a sytem is approved, we will schedule the work…. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope and conduct site visit……DL, 7/11/18; This work will require plans and permits. Will schedule meeting with Scott to verify if the project request will be approved. If this is approved, we will plan the target complete date to be mid October…..The Request is to reverese Emergency Exit Doors and install Prox card access……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..DL, 8/22/18; Confirmed with Scott that we can reverse the door swing. We will work on plans for review process. This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 9/19/18; I mis understood this for a project at Health Services. I have a meeting with Angie this week. This project is to install turn styles for access to the building. I will need to discuss the equipment to be purchased by Angie verify the specs. We will start on the plans in the early Fall……DL, 11/7/18; Conducted site visit with Vendor. Informed Angie the cost of the project will be at $45K for the project. Angie is checking to verify if funds are availabe for the equipment. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000213 |  | 18P000213 | FALSE | PLANNING & BUDGET | SL5-BUILDING MECH SHOP WOULD LIKE A NEW WALL, DOOR AND BENCH | On hold per customer to determine the scope of work | CORP PP WHSE |  | IN PROGRESS | Gerry Bomotti | Jacqueline Norman | FRANK PORTER |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 2017-12-07 | [6 empty] | 1/15/19, DL; Material is ordered. This will be complete with in the next 45- days………………….DL, 1/5/18; Still need to review scope…..DL,2/26/18; Conducted site visit with Frank. We will notify Frank when we are ready to proceed with the project…… |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000214 |  | 18P000214 | FALSE | VC-STU.AFF. | SL5-COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Plans were approved by Fire Marshal, work to commence in 30 days. Scheduling the work with the availablity of the teams. | HEALTH SERV |  | IN PROGRESS | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-12-08 | [6 empty] | 12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000215 |  | 18P000215 | FALSE | VC-STU.AFF. | SL5-STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 | Plans were approved by Building Official; work to commence in 30 days. Scheduling the work with the availablity of the teams. | HEALTH SERV |  | IN PROGRESS | Brian Haynes | Cathy Eckman | PAMELA HAGGINS |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2017-12-08 | [6 empty] | 1/15/19, DL, Material is ordered, material should arrive on site in the next 3- 5 weeks……12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 5/24/18; Need to review scope and site visti with Enrico. Plans and permits will be required for this project….DL, 7/11/18; Planning to walk work with Gloria and her team next week. Will be able to project complete date after site visit is conducted……DL; 7/25/18; We walked this project with the team. This will require plans and permits. We will schedule this work for Fall…………DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-45 Days…… |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000221 |  | 18P000221 | FALSE | CNAS | SL5-Provide add'l HVAC capacity to maintain lower temp | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 4414 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 9 | 16 | FALSE |  |  | 2017-12-11 | [6 empty] | 12/14/18, DL; This project is 100% Complete……….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob. DL, 5/9/18; We will work on plans and submit for review.....DL, 6/16/18. Had meeting with Bob W. to verify what is needed on plans. I will work with Gunther on plans for submittal and review......DL, 7/11/18; Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall.....DL, 11/7/18; Material is on site and will will schedule the work with in the next 30- days..... |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000223 |  | 18P000223 | FALSE | CNAS | SL5-Provide requisite utility infrastructure to support 4 add'l chambers (on order). | Plans were approved by Building Official and Fire Marshal; anticipated completion January 2019. | FAWCETT LAB |  | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 11 | 21 | FALSE |  |  | 2017-12-11 | [6 empty] | 01/15/19, DL; Plans are approved, Chambers are on site. Electrical is complete. Plumbing work is in progress. Our portion of the project should be complete by 2/1/19…………..12/14/18, DL; All Pre work is complete. The Chambers are scheduled to arrive on site within the next 30-days. We will finish this project when material on site……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans……..DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet….DL, 4/29/18; Still need to conduct site visit with the team….DL, 5/24/18; Per Patty, equipment is ordered but 5- months out…..DL, 9/6/18; We will submit plans to Bob W. tomorrow for review and approval……..DL, 9/19/18; Plans are approved. The equipment will be here in about 4- months. WE will start the work for this project in the Fall to ensure we are ready when the equipment arrives……DL, 9/19/18; Plans are currently being review by BO & FM……DL, 11/7/18; Plans are approved. WE are requesting to change the placement confirguration of the growth chamber and awaitng Bob's review and approval. WE are on track to have this work complete befoire the end of the new year….. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000225 |  | 18P000225 | FALSE | BAS | SL5-POLICE BLDG SEALING & PAINTING LEAKING WINDOWS | Work has been scheduled for completion; windows to be sealed and patch/paint by painters. | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Dan Lerman |  | 1 | 7 | FALSE |  |  | 2017-12-11 | [6 empty] | 12/14/18, DL, This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to meet with Enrico to verify scope….DL, 7/11/18; Still need to review scope……DL, 11/7/18; Scope is complete. Carpenters are scheduling the windows to be sealed. P&P is also being scheduled….. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000226 |  | 18P000226 | FALSE | BCOE | SL5-BOURNS FUME HOOD INSTALLATION | Installation of utilities to be completed; clean room to be installed upon utility connections. | BOURNS | B0235A | IN PROGRESS | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  | 8 | HOLD | TRUE |  |  | 2017-12-11 | [6 empty] | …1/15/9, DL; This project is 95% complete and should be complete on or near 2/1/19…………12/14/18, DL; This Project is 90% Complete. Fume hood is scheduled for install next week. We will finish balance of project after Fume hood is installed…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. WE are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans…..DL, 5/9/18; planning to submit plans on 5/11/18 for plan check review….. DL, 5/24/18; Plans were submitted to Bob W. on 5/24/18……DL, 6/12/18; Project is on Hold until Shane can provide plans/specs for the clean room……DL, 7/11/18; Still no change to the status……DL, 7/25/18, Maggie confirmed this project is on the books. I need to discuss the status with the team because the priority list is on Hold…….DL, 8/22/18; This project is no longer on hold. We will per shane we will submit what we have from the clena room suupplier for review from FM and BO……DL, 9/6/18; WE are almost complete with Plans and will submit the plans next week………DL, 9/19/18; Submitted plans to PD&C on 9/14/18…..DL, 10/4/18; Plans were approved thais week. WE will scheudle the project around the delivery date for the Clean room……..DL, 11/7/18; This is in progress. We will complete the install of the utilities so the clean room can be installed. WE will finish the balance of the project once the Clean room install is complete. The clen room is being install by an outside vendor….. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000227 |  | 18P000227 | FALSE | CNAS | SL5-BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL | Complete as of 11/8/18 | BATCHELOR | 4128 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-12-12 | [6 empty] | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM.......DL, 5/24/18; Need to work on plans and permits. Project needs to be complete before Fall academic 2018.....DL, 6/16/18; Walked project with Jess. and he will schedule the abatment. We will not need plans for this project. We are not removing the exhasut hood which was the original purpose foor the plans......Carpenters started the demo. Still need to remove TSI. Once TSI is removed, we can schedule the plumbing work. Target Complete Date is 9/21/18....DL, 8/10/18; Abatement is scheduled for this weekend, we will start work soon.....DL, 8/22/18; Abatement and most demo complete. Still on track for 9/21/18.....DL, 9/19/18; Scope change. This project should be complete on 9/28/18.......DL, 10/4/18; Floor to be installed this Friday. Pianters will finalized the stain on the cabinets. Thsi project should be complete near 10/19/18.......Dl, 11/7/18; This project is 100% complete.... |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000247 |  | 18P000247 | FALSE | CNAS | SL5-PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 | Complete as of 7/14/18 | PHYSICS | 3023 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  |  | 15 | FALSE |  |  | 2017-12-20 | [11 empty] | FS | 0 | 2017 | 2019-01-16
18P000252 |  | 18P000252 | FALSE | ITS | SL5-CHASS INT S REPLACE ELECTRICAL SCREENS | Pending customer to confirm of equipment to be purchased; work scoped by BZM. | CHASS INT S | 2130 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Danna Gianforte | Shelley Gupta | JORGE MACIAS |  | Dan Lerman |  | 1 | 2 | FALSE |  |  | 2017-12-21 | [11 empty] | FS | 0 | 2017 | 2019-01-16
18P000256 |  | 18P000256 | FALSE | CNAS | SL5-BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES | Complete as of 9/21/18 | BOYCE | 3451 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave at Webber is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place.......DL, 5/9/18; Autoclave is destroyed. Pictures were sent to Cheryl. We are now waiting for the equipment to arrive. Steve B is working on Steam connection at Boyce......DL, 5/24/18; Autoclaves arrived. Day crew is scheduled to deliver the unit on 5/30/18. we will schule the plumbers and electricians shortly there after......DL, 6/16/18; Webber Autoclave is almost complete. This portion should be complete next week. WE will run the Webbber autoclave for two weeks before we start the Boyce Autoclave. The weldolet for the BOyce unit will be installed during the steam shutdown...... DL, 7/11/18; Webber Auto clave will be complete on 7/12/18. We will start the demo of the Boyce Auto clave next soon. Target date for this project is 8/10/18...... DL, 7/25/18; We had a delay with the Webber autoclave which will implact the Boyce Auto clave. New target complete date is 8/22/18.....DL, Plumbing is almost complete, need to schedule final elctrical and Commission equipment. Target date 8/31/18...... DL, 9/6/18; This project should be complete but we still need to schedule the electrical connections ASAP.........DL, 9/19/18; This project is 100% Complete. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000257 |  | 18P000257 | FALSE | CNAS | SL5-SKYE HALL MOUNT 55 | Scope of work is being reviewed; determining how to complete project with trades. | SKYE HALL | 209 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 28 | 28 | FALSE |  |  | 2017-12-22 | [6 empty] | 1/15/19, DL, Site visit is scheduled with James M. this Thursday. We will schedule the work shortly after the site visit…….12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. |  |  |  |  | FS | 0 | 2017 | 2019-01-16
18P000258 |  | 18P000258 | FALSE | CNAS | SL5-SKYE HALL HALLWAY MOUNT | Scope reviewed by BZM; coordination by PM for work to be completed. | SKYE HALL | 212 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 29 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2017-12-22 | [6 empty] | 1/15/19, DL, Site visit is scheduled with James M. this Thursday…………12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Paul Ditty |  | N/A | FS | 0 | 2017 | 2019-01-16
18P000261 |  | 18P000261 | FALSE | SOM | SL5-WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR | Complete as of 9/10/18 | WEBBER | 1143 | COMPLETE | Deborah Deas | Brandon Barbosa | LOURDES ESCAMILLA |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 7/11/18; Work orders are produced. Need to assign the work order and order material. I will review with Steve and verify target complete date….DL, 7/25/18; Still need to walk the project with Steve……DL, 8/10/18; Material is ordered. We will complete the install when the materila arrives.....DL, 8/22/18; Material should be on site with in 4- weeks. Will schedule install when material is on site. Target date is 9/20/18.......DL, 9/6/18; This Project is 100% Complete...... |  | Paul Ditty | N/A | N/A | FS | 0 | 2017 | 2019-01-16
18P000267 |  | 18P000267 | FALSE | BCOE | SL5-CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT | Complete as of 7/11/18 | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-01-16 | [6 empty] | DL, 5/19/18; High table mounted on West wall to be relocated to South wall by light "Centered". Relocate white board from East Wall to West walll wher high table was removed. Paint and new flooring. Need to schedule work with Paul and Jess. BKM furniture is scheduled 4-6 weeks. DL, 6/16/18; Lower electrical outlets on North wall, repair blinds, paint and new flooring. The space is vacant as of June 16th. I will scheudle the workl.....BKM delivery is currently scheduled for July 23rd.......This project is 100% complete. There were two items added to the scope and they will be complete by 7/20/18..... |  | Dan Lerman | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18….. | YES | FS | 0 | 2018 | 2019-01-16
18P000269 |  | 18P000269 | FALSE | CNAS | SL5-BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED | FS to coordinate with client to scope the work. Customer contacted to schedule a site visit. | BATCHELOR | 1123 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 12 | 18 | FALSE |  |  | 2018-01-16 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000270 |  | 18P000270 | FALSE | SPP | SL5-CHASS INT S- EVALUATION FOR REMODEL | Pending customer to provide drawing of the space. | CHASS INT S | 4133 | CANCELED BY CLIENT | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Dan Lerman |  | 4 | 2 | TRUE |  |  | 2018-01-16 | [6 empty] | 4/24/18 EB- Per Christina Wong, no loner needed……DL, 5/5/18; Project is cancesled per notes DND 7/27; Please follow up with customer on the status and need for the work; customer advised to me that Dan has the scope of work for completion. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. |  | Enrico Baez | 2/2/18 EB site visit scheduled for 2/5/18 with Angie Gray. 2/6/18 EB- conducted site visit. Request for automated access control system. Annotated on FAMIS….DL, 5/5/18; FAMIS work order ,New ADA operator, power supply for operator and card swipe….. | YES | FS | 0 | 2018 | 2019-01-16
18P000273 |  | 18P000273 | FALSE | LIBR | SL5-RIVERA LIB -RESTROOM REFRESH PROJECT | Scope of work has been reviewed; determining how to complete project with trades. | RIVERA LIBRARY |  | TO BE PERFORMED BY PD&C | Steven Mandeville-Gamble | Jacqueline Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2018-01-18 | [6 empty] | DND 12/13/18: Customer advised maintenance requests related to project request has been addressed. Renovation work to be performed by PD&C and customer submitted a CPMS request. DL, 6/16/18; Need to schedule site visit with Dave and Chris P…….DL, 7/11/18; Chris and I will walk this poroject next week…..Wlaked projects with Chris. We need to review in more detail to better determin the process for this project…..DL, 9/6/18. WE need to discuss what we are going to do with this project.... We walked the project but we now need Direction from Facilities leadership… |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000274 |  | 18P000274 | FALSE | GSOE | SL5-SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 | Project is 95% complete; contract in progress for installation of a new door, door frame and ADA operator. Anticipated completion December 2018. | EADY CENTER |  | IN PROGRESS | Thomas Smith | Sally Tavizon | KAREN NAPLES/BRANDON BARBOSA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-18 | [6 empty] | 1/15/19, DL; The door and automatic opener is scheduled to be installed on 1/22/19……..12/14/18, DL; This project is 95% complete. The contract for the door and ADA operator was awarded today. We will schedule the work shortly after the new year…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Conducted site visit with Gilbert. We need to have a meeting to determin if this work is part of the SLA…… DL, 6/16/18; We still need direction, SLA or Recharge?.......DL, 7/11/18; This Project will require Plans and Permits. We will start on the Plans next Week. We will also issue work orders for work we will complete with in house staff. The Concrete work and Entry Door will need to be contracted out. Target Complete date is 10/1/18……..DL, 7/25/18; Work orders are produced. Planing to walk the project with Chris, Steve B and Robert C. thisw week or next week. We will submit plans to Bob Williams for the contracted work next week……DL, 8/8/18; Completed site visit with Robert C. Steve B, Steve T. and Chris; the Plumbers are complete. The carpenters and electricians will work on their items over the next three weeks. The Plans will be ready to submit on 8/9/18. Once plans are approved, we will proceed to go out to bid for the Concrete and the ADA operator. Target complete date is 9/21/18…….DL, 8/22/18; Plans were apprroved, Concrete Contract is being executed. Still working on Door and ADA operator……..DL, 9/6/18; NTP for Concrete will be issued on Monday. I will schedule the work. I need to follow up on the door order and the ADA operator…….DL, 9/19/18; Concrete walkway scheduled to start on 9/20/18. The new door and Frame will arrieve in 3-5 weeks. We will schedule the install when the new door and frame are on site…….DL, 10/4/18; Concrete work is complete. Still need handrail, signage, door and ADA operator. Target date is Early November….DL, 11/7/18; Project is 95% complete. Contract is being processed to install the new Door, Door Fram and ADA operator. Goal is to have the work complete befor the winter break…… |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000281 |  | 18P000281 | FALSE | VC-UNIV.ADV. | SL5-ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS | Work has been scoped; coordinating trades schedule for work to begin. | ALUM VISITOR | 2202 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | TRUDY COHEN |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-01-24 | [6 empty] | DL, 5/24/18; Need to verify scope of work with EnricoDL, 7/11/18; Still need to visit the site and schedule the work…..DL, 11/8/18; This project was transferred to John. The target date was 1/2/19….. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000282 |  | 18P000282 | FALSE | BAS | SL5-EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 | Complete as of 8/10/18 | POLICE BLDG |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | LISA MARTIN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-25 | [6 empty] | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work…..DL, 5/9/18; We need to submit plans……DL, 7/11/18; This still needs to be scheduled......DL, 8/8/18; Enrico Confirmed this project is 100% Complete.... |  | Enrico Baez | EB-scoped on 1/30. Mount TV above table. Advised an articulated mount be purchased. Drawing on FAMMIS WO. | YES | FS | 0 | 2018 | 2019-01-16
18P000284 |  | 18P000284 | FALSE | CNAS | SL5-SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT | Complete as of 9/21/18 | SKYE HALL | 277 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  | 29 | 23 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000287 |  | 18P000287 | FALSE | CNAS | SL5-SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING | Complete as of 9/21/18 | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 33 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19/18; This project is 100% Complete..... |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000288 |  | 18P000288 | FALSE | CNAS | SL5-SKYE HALL OFFICE SUITE PAINTING | Complete as of 8/24/18 | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-01-31 | [8 empty] | Enrico Baez | 5/23/18 EB sent email request for site visit DND 7/14 Hold per customer on prioritization Canceled per customer on 7/16/18 via email with Enrico. | YES | FS | 0 | 2018 | 2019-01-16
18P000292 |  | 18P000292 | FALSE | CNAS | SL5-SKYE HALL PAINT MULTIPLE FACULTY OFFICES | Complete as of 8/24/18 | SKYE HALL | 228 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-01-31 | [8 empty] | Enrico Baez | 4/25 EB Scoped site. Remove counter and Cage. Drywal closed with electrical. Patch Paint. Cut in two doors in 2117G&H……..DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18…….. | YES | FS | 0 | 2018 | 2019-01-16
18P000293 |  | 18P000293 | FALSE | CNAS | SL5-SKYE HALL COPIER ROOM PATCH AND PAINT | Complete as of 8/24/18 | SKYE HALL | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 32 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000294 |  | 18P000294 | FALSE | CHASS | SL5-HMSS REMOVE DOOR, INSTALL WALL | Canceled on 7/16/18 per email communication with customer. | HUM & SOC SC | 3610 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2018-02-01 | [8 empty] | Enrico Baez | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date....... | YES | FS | 0 | 2018 | 2019-01-16
18P000295 |  | 18P000295 | FALSE | CHASS | SL5-CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL | Complete as of 9/21/18 | CHASS INT S | 2117J | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-02-01 | [6 empty] | DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18……..DL, 5/24/18; Plans were approved. We need to scheudle the work….DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets.......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date.....DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18...........DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware..... |  | Dan Lerman | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access | YES | FS | 0 | 2018 | 2019-01-16
18P000296 |  | 18P000296 | FALSE | CNAS | SL5-SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES | Contract is being processed; target project completion is end of September. | SKYE HALL | 266 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 31 | FALSE |  |  | 2018-02-02 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19 18; I neeed to check on this work order. I thought it was part of the 2nd floor Hallway project but it was not...... |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000297 |  | 18P000297 | FALSE | CHANCELLOR | SL5-SKYE HALL CHECK LOCATION FOR TV INSTALL | Scope of work has been reviewed; determining how to complete project with trades. | SKYE HALL | 390 | QUEUE TO START | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Dan Lerman |  | 4 | 3 | FALSE |  |  | 2018-02-02 | [6 empty] | DL, 5/24/18; Need to verify scope with Enrico…..DL, 7/11/18; Work orders are produced and need to be issued. Target complete date is 9/3/18…. |  | Enrico Baez | 5/24/18 Conducted site visit. Met with Ryan Amriano. Electrical near buy. No data connection needed. Awaiting for dept. approval. They first wanted to know if this was possible. | YES | FS | 0 | 2018 | 2019-01-16
18P000300 |  | 18P000300 | FALSE | CHASS | SL5-ARTS PATCH AND PAINT - DANCE HALLWAYS | Complete as of 8/24/18 | ARTS |  | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 24 | FALSE |  |  | 2018-02-02 | [6 empty] | centered. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000310 |  | 18P000310 | FALSE | CNAS | SL5-ADD INTERCOM/BUZZ IN SYSTEM | Complete as of 10/22/18. | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-12 | [6 empty] | Dl, 7/4/18; This project is scoped. This will be a new ADA operator, door bell / Intercom and buzzer button to unlock door. Walked work with Contractor, need to work on producing contract with PD&C. Once Contract is confirmed, we will schedule the work..... DL, 7/11/18; We have the proposal. Need to execute the agreement and schedule the work. The target complete date is before 10/1/18.....Dl 8/10/18; Jason will try and complete the work with in the next three weeks......DL, 8/22/18; Jason order parts, parts have 6-8 week lead time. Work will be scheduled when material arrives.....DL, 10/4/18; This Project is 100% Complete....... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000312 |  | 18P000312 | FALSE | CNAS | SL5-URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 | Canceled per customer 9/12/18 | CAMP LOC NOT IN BLDG |  | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | Canceled | 38 | FALSE |  |  | 2018-02-13 | [6 empty] | Dl, 6/16/18; Is this a project we will manage or resourse management? I understand we will disconnect the utilites, but who is responsible for the removal of the trailers? I am assuming this will be recharge work and not covered under the SLA. I will verify before the work begins......DL, 7/11/18; Need to check in with Susan. Need to produce work orders and schedule the work........ |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000313 |  | 18P000313 | FALSE | GSOE | SL5-SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 | Complete as of 10/22/18. | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-15 | [6 empty] | 18W011689 Work order was cancelled because it has the same scope and is a duplicate………DL, 6/16/18; Contract is being awarded this week. Weill are scheduled to have this work completed by fiscal closing……DL, 7/25/18; This Project is 100% Complete…..9/13: Zee - Customer noted paint peeling; updated to status to back in progress for work to be addressed.......DL, 9/19/18; The contractor is on site repairing the walls and painting. The work should be complete this week.......dl, 10/4/18; tHIS PROJECT IS 100% Complete..... |  | Enrico Baez | EB 3/26-Project scoped on 10/23/17. Attached 5 photos and made annotations to FAMIS. | YES | FS | 0 | 2018 | 2019-01-16
18P000314 |  | 18P000314 | FALSE | CHASS | SL5-CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR | Complete as of 7/25/18. | CA MUS PHOTO | 1000 | COMPLETE | Milagros Pena | Cindy Williams | EMILY PAPAVERO |  | Dan Lerman |  |  | 17 | FALSE |  |  | 2018-02-16 | [6 empty] | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date.......DL, 7/25/18; This project is 100% Complete..... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000315 |  | 18P000315 | FALSE | BCOE | SL5-BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB | Complete as of 8/23/18 | BOURNS | B0235 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  | HOLD | TRUE |  |  | 2018-02-16 | [6 empty] | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction to scope, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... Need to walk project with Ron and schedule the work....DL, 5/24/18; Conducted site visit with Ron V. Ron will order material and schedule the work once material is on site.....DL, 6/16/18; Need to verify delivery date for material.......DL. 7/11/18; Plumbing is disconnected. Corey is tentatively scheduled to disconnect the Fume hood. Once the Fume hood is disconnected, we will schedule the removeal of the fume hood and start the framing of the wall. Target complete date is 8/8/18....DL, 7/25/18; Fume hood is disconnected. Need to move Fume hood and start framing target date is delayed to creep scope but should be complete near 8/16/18.....DL, 8/10/18; Carp[enters will install the wall this week. Corey has parts orders. Corey will complete the install when the material arrives.......DL, 8/22/18; This Project is Complete |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000318 |  | 18P000318 | FALSE | CHASS | SL5-CHASS INT S FLAT SCREEN INSTALLATION | Plans are being reviewed; work to be scheduled once plans are approved. | CHASS INT S |  | PLAN DEVELOPMENT/CHECK | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Dan Lerman |  |  | 20 | FALSE |  |  | 2018-02-21 | [6 empty] | 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; we have the brackets. Will scheule the work after the project is approved…..DL, 7/11/18; Work order are not produced. Need to assign and schedule the work…. Target complete date is 8/3/18……DL; 7/25/18; Need to change target date.. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000321 |  | 18P000321 | FALSE | BCOE | SL5-STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST | Complete as of 8/10/18 | STUDENT SERV | 1228 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Enrico Baez |  |  |  | FALSE |  |  | 2018-02-22 | [6 empty] | DL, 4/29/18; Enrico is cordinationg this. The permits are approved……. DL, 7/11/18; Just received confirmation the door is ready for delivery and installed. I need to check in with Paul about the paint and prep of the door. I also need to check in with Jason on lock hardware......Dl, 7/25/18; Door is painted and ready for install. Called Dugmore to schedule the install. This should be compolete within the next two weeks......DL, 8/8/18; This Project is 100% Complete |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000324 |  | 18P000324 | FALSE | PLANNING & BUDGET | SL5-HINDERAKER PATCH AND PAINT | Complete as of 7/11/18 | HINDERAKER | 4118 | COMPLETE | Gerry Bomotti | Jacqueline Norman | MILLY PAREDEZ |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-02-26 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000328 |  | 18P000328 | FALSE | ATHLETICS | SL5-HINDERAKER BASEMENT OFFICE REPAIR | Complete as of 7/11/18 | HINDERAKER |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-01 | [6 empty] | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with Paul. Paul will complete as in the near future. Carpet will be installed shortly after......5/21/18, Painters started paint. Should be complete with paint by the end of the week....DL, 5/24/18; Painters are complete. Jess will schedule the carpet install.....DL, 6/12/18; Project is 98% Complete. Carpenters need to under cut two doors to accomodate the carpet.....DL, 7/11/18; This Project 100% Complete..... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000329 |  | 18P000329 | FALSE | CHANCELLOR | SL5-SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST | Project complete as of 9/18/18 | SKYE HALL | 170 | COMPLETE | Kim Wilcox | Karim Zahedi | DA LAN DINH |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18…..DL, 5/24/18; Plans were approved. Demo work has started......DL, 6/12/18; MArshal and Kate are working on Carpet order......DL, 7/11/18; Carpet is ordered. We have a challenge with Title 24. I am working on the title 24 documents. We are still planning to have this project complete on 8/17/18......DL, 8/10/18; We now have the Title 24 plans. The are being reviewed by Bob and Scott.....Title 24 plans approved. Robert is working on PO#. Most parts are on site and Electricans are working on project. All other Trades to follow once Lights are in...... Hard Date of 9/7/18............9/6/18 As of today, Carpet is scheduled for install tomorrow morning and furniture is scheduled for delivery this Monday......WE will more than likely have electrical punch items and touch up paint but this propject should be 100% complete in regards to FS the end of next week next week......100% PROJECT COMPLETE... GREAT WORK DAN! |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000337 |  | 18P000337 | FALSE | VC-STU.AFF. | SL5-MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET | Plans are approved for work to commence; scheduled for start on 11/13/18. | HEALTH SERV | 414 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-12 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18….Need to work on plans and permits….DL, 7/11/18; Gunther is working on plans. Target complete date is 9/14/18….DL, 7/25/18; Planning to submit plans for review next week. We will schedule the work once we have approved plans…….DL, 8/8/18; This is a structual wall and needs to be engineered. We are meeting with the Structual engineer on 8/9/18 to determine if project is possible.....DL, 8/22/18; Working on EDPA for Structual engineer; project timeline is late Fall. 9/19/18; The Agreement / Cointract for the structual engineer is processed for this project. We should have plans from the structual engineer to submitt to the Building Official and fire marshal with in 4- weeks......dl, 10/4/18; Plans are almost complete and we will submit them for review by the end of the week.....DL, 11/7/18; Plans are approved. WE are schedule to start this Project on Tuesday 11/13/18. Target complete date is by the end of the winter break..... |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000341 |  | 18P000341 | FALSE | CNAS | SL5-PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL | AQMD notification was sent; abatement to begin at the end of notification period. | PHYSICS | 1132 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-14 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process…DL, 6/16/18; Jess tested the matreial flooring and paint is hot. Jess will abate before we proceed with the project….Still need to scheudle the work. This project target complete date is late Fall……DL, 7/25/18; Jess sent out the 14-day notification to the AQMD last week. We will start the balance of the project after the ACM and Lead is abated or encapsulated…..8/10/18; Abatement is complete. We will work on the other items as time permits. This space is vacant with no occupancy date |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000343 |  | 18P000343 | FALSE | CHASS | SL5-UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER | Scope of work has been reviewed; determining how to complete project with trades. | THTR WKSH | 0400A | QUEUE TO START | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 2018-03-16 | [6 empty] | 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000344 |  | 18P000344 | FALSE | CHASS | SL5-CHASS INTS PAINT MULTIPLE ROOMS - FACULTY | Complete as of 9/10/18 | CHASS INT S | 2117E | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 1 | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 7/11/18; This was transferd in to my quque in the past week. I need to scope this project. I belive this is part of project # 18P000205 and 18P000295. If this is part of the other project. We will try to have the paint completed by 8/17/18…......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/10/18; Work has started. We passed rough electrical and framing inspection. The work should be complete in about three weeks......DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18.......DL, 9/6/18; This Project is 100% Complete....... |  | Enrico Baez | EB 1/31/18 Work was assigned to lock shop 12/7/17 | YES | FS | 0 | 2018 | 2019-01-16
18P000346 |  | 18P000346 | FALSE | ATHLETICS | SL5-ATHLETICS INSTALL WALL VOLLEYBALL OFFICES | Complete as of 11/8/18 | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-18 | [6 empty] | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. DL, 5/24/18; We will start working on plans in the near future.... DL, 6/16/18; Need to submit plans asap.......DL, 7/11/18; The plans were approved today. This project is scheduled to start on 7/14/18. We will will be complete will all items related to this project on 8/27/18. Note, The door and sidelite are special order items and this item will probalby have a 6-8 week lead time. Steve T is going to order the door soon.. Customer is aware of the delay for the door and is not concerned......DL, 7/25/18; Passed framing and Electrical inspection. We will be finished with the project next week except for the door and window that is ordered but has a 6-8 week lead time. DL, 8/10/18; This Project is Complete except for special order door and window.......DL, 8/22/18; Door and Glass still not on site., Will check in with Steve T on delivery date......Will also schedule final inspection for Certificate of occupancy......9/6/18; The Glass window is installed but we are waiting on the door. this projects is 98% complete.......DL, 9/19/18; The door will be shipped on 9/24/18. We will schedule the door install when the door is on site......DL, 11/7/18; This Project is 100% Complete.... |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000347 |  | 18P000347 | FALSE | CNAS | SL5-GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) | Scope reviewed by BZM; coordination by PM for work to be completed. | GEOLOGY | 0 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 31 | Deferred to Fall Quarter - summer priority 27 | FALSE |  |  | 2018-03-18 | [6 empty] | DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000348 |  | 18P000348 | FALSE | VC-STU.AFF. | SL5-HUB ADD 3RD FLOOR WALLS | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | HUB | 0353E | IRT REVIEW | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 2 | 6 | FALSE |  |  | 2018-03-18 | [6 empty] | DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Need to walk the project with Manny. Target date is late Fall…….. |  |  |  |  | FS | 1899-12-31 | 2018 | 2019-01-16
18P000349 |  | 18P000349 | FALSE | BCOE | SL5-PHYSICS INSTALL PARTITION WALL FOR LAB ROOM | Complete as of 7/11/18 | PHYSICS | 1037 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 5/24/18; Ron V. has detailed scope and he is ordering material. Once material arives, we will schedule the work…. DL, 6/16/18; Materila is ordered, When door/frame arrives, we will prep, paint and start the work…….DL, 7/11/18; This Project is 100% Complete..... |  |  |  |  | FS | 0 | 2018 | 2019-01-16
18P000351 |  | 18P000351 | FALSE | SoB | SL5-REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 | 21 | HOLD - FACILITIES SERVICES | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2018-03-19 | [6 empty] | DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week......8/8/18. The trades are ready to go after they finish current projects.....DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18.......... DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date........9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space......Note. The space is usable and everything works..... |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000353 |  | 18P000353 | FALSE | CHASS | SL5-PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT | Complete as of 8/23/18 | PSYCHOLOGY1 | 1111A | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 26 | FALSE |  |  | 2018-03-20 | [6 empty] | DL; 7/4/18;This project is scoped. We will only paint one out of the two offices. Working on PO# to install frosted glass with Sun Down Window coverings……DL, 7/25/18; PO# is produced and material is ordered. Target date mid August…….DL, 8/22/18; This project is complete.... |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS……DL, 4/29/18; Pasted from wo;remove the existing countertop and shelves that are built into the room. Follow with patch and paint of entire space. | YES | FS | 0 | 2018 | 2019-01-16
18P000354 |  | 18P000354 | FALSE | CNAS | SL5-GH16-25 COOLING SYSTEM REPAIR | Work considered deferred maintenance not a minor renovation. | GH 16 25 |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | MARK TANKERSLEY |  | Dan Lerman |  | 13 | 17 | FALSE |  |  | 2018-03-20 | [6 empty] | DL, 7/25/18; Reviewed Ron V. noted. I will check in with Chris on this to better determin the method complete this project. |  | Enrico Baez | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18…… | YES | FS | 0 | 2018 | 2019-01-16
18P000356 |  | 18P000356 | FALSE | CNAS | SL5-ENTOMOLOGY PATCH AND PATCH | Complete as of 8/24/18 | ENTOMOLOGY | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 10 | TRUE |  |  | 2018-03-20 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000363 |  | 18P000363 | FALSE | BAS | SL5-PAINT STOREHOUSE ADMINISTRATIVE OFFICE | Complete as of 11/8/18 | CORP B |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | ERICA HENDERSON |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-03-26 | [6 empty] | N/A |  | Enrico Baez | DD 10/6: Enrico scoped; requested during break - coordinating with client to complete on a Saturday | YES | FS | 0 | 2018 | 2019-01-16
18P000367 |  | 18P000367 | FALSE | CHASS | SL5-CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE | Complete as of 7/14/18 | CHASS INT N | 3033 | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 23 | FALSE |  |  | 2018-03-27 | [11 empty] | FS | 0 | 2018 | 2019-01-16
18P000369 |  | 18P000369 | FALSE | BAS | SL5-BOYCE X-RAY IRRADIATOR PROJECT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 1407 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | KAREN JANIGA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-27 | [6 empty] | 12/14/18, DL; This project was cancelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……DL, 5/9/18; Need to work on plans/permits…..DL, 6/16/18; Meeting with Bob and confirmed what is needed. I will work with Gunther on plans. Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall…..DL, 11/7/18; Material is on site. We will schedule the work soon…… |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000373 |  | 18P000373 | FALSE | BAS | SL5-POLICE BLDG PAINTING IN DISPATCH AREA | Complete as of 7/14/18 | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  |  | 8 | FALSE |  |  | 2018-04-02 | [8 empty] | Enrico Baez | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. | YES | FS | 0 | 2018 | 2019-01-16
18P000379 |  | 18P000379 | FALSE | VC-RED | SL5-UOB PATCH AND PAINT | Complete as of 8/24/18 | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-05 | [8 empty] | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-01-16
18P000380 |  | 18P000380 | FALSE | SOM | SL5-SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 | SOM RSCH | 330 | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-05 | [6 empty] | Canceled per customer on 8/22/18. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000381 |  | 18P000381 | FALSE | ITS | SL5-ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 | FS to coordinate with customer to schedule the work for completion. | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 3 | 4 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL; This project is complete. Note, Duffy only wanted the dutch door completed……..12/14/18, DL; This project is in progress and should be complete shortly after the new year……`DL, 7/11/18; Need to walk the project and schedule the work…… |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000382 |  | 18P000382 | FALSE | ITS | SL5-ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 | Plans will be developed and will be submitted for review and approval. | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | PHYLLIS FRANCO |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL, This project is Complete……12/14/18, DL; This project is scheduled to be complete shortly after the winter break…….This project was scoped previously with the IR Team. We may need plans or a permit because we are installing a Dutch door…..DL, 7/11/18; Need to produce work orders and schedule the work….. DL, 7/25/18; Still need to produce work orders and schedule the work. Target date is 10/1/18 |  | Paul Ditty | 5/23/18 EB- Sent email to Jill requesting site visit. 5/23/ 18 EB- Scoped. Mount & TV on site. TV bottom edge to be mouted 48" from floor centered on West wall. Needs electrcal cut out and data. Entered in FAMIS. | N/A | FS | 0 | 2018 | 2019-01-16
18P000383 |  | 18P000383 | FALSE | CHASS | SL5-HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT | Completed as of 8/10/18 | HUM & SOC SC | 1302 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  | 4 | TRUE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000385 |  | 18P000385 | FALSE | CHASS | SL5-HMSS INSTALL TV IN CONFERENCE ROOM | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 1001E | IN PROGRESS | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Dan Lerman |  | 19 | 19 | FALSE |  |  | 2018-03-06 | [6 empty] | 12/14/18; Monitor is Complete, we still need to install power. The space is vacant…DL, 6/16/18; Pasted notes from FAMIS; University Writing program wants to install a 65 inch TV in the conference room at HMNSS 1001E. 1. Request to install the TV mount/ bracket on the wall; 2. Request to remove the old projector screen but leave two wood blocks on the wall; 3. Request to add a new double power outlet around the TV bracket area. If you have any questions, please contact Shanshan Liao at (shanshan.liao@ucr.edu or X27753)……DL, 7/25/18; Work orders are not produced. Need to assign and schedule the work…..……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  |  |  | YES | FS | 0 | 2018 | 2019-01-16
18P000387 |  | 18P000387 | FALSE | CHASS | SL5-HMSS PATCH/PAINT | Complete as of 8/24/18 | HUM & SOC SC | 3600 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 28 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000388 |  | 18P000388 | FALSE | CNAS | SL5-SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 2018-04-10 | [6 empty] | DL, 7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved…..DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans....DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter....DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but htere is no hard date as this is vacant space and we will access the space as time permits...... |  | Enrico Baez | 8/27/18 EB-Remove 12' wide screen from finished ceiling. Need electricians to diconnect power, carpenters to remove drywall and lower screen. Repared screen to be re-hung by carpenters and drywall repaired. Electricians to reconnect power. Painters to patch and paint. | YES | FS | 0 | 2018 | 2019-01-16
18P000389 |  | 18P000389 | FALSE | CHASS | SL5-PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A | Complete as of 11/8/18 | PSYCHOLOGY1 | 2122 | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 5 | TRUE |  |  | 2018-04-10 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000390 |  | 18P000390 | FALSE | PLANNING & BUDGET | SL5-UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD | Complete as of 8/24/18 | UV BLDG B | 0240B | COMPLETE | Gerry Bomotti | Jacqueline Norman | LESLIE ROSE |  | Paul Ditty |  |  | 1 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000391 |  | 18P000391 | FALSE | BCOE | SL5-PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN | Complete as of 9/10/18 | CHUNG HALL | 446 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 5/5/18; Conducted scope visit with Paul and Maggie. This project is target date is August 30th. As of now, we have 10 business days to complete the work……. Dean's Office….DL, 6/16/18;Walked project with Jess and Paul. This will be a project will now incluclude flooring is 7- additional offices due to additional trip hazzards identified in 3 of 7 offices during the carpet scope. Maggie will pay four four of the office since they are still in good condition. We are still on schedule with the work.......Dan, 7/11/18; This project is still on schedule. Complete Date is 8/18/18 and scheduled to be complete on 8/31/18.....DL, 8/10/18; The project is on schedule and we will start on Monday.......Ahead of schedule, project will be complete on 8/29/18......DL, 9/6/18; This project is 100% complete. Note, Maggie did request Jess to come back and remove some glue and he has this scheduled..... |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000392 |  | 18P000392 | FALSE | CNAS | SL5-BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 | Complete as of 8/24/18 | BATCHELOR | 0 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  |  | 8 | TRUE |  |  | 2018-04-12 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000394 |  | 18P000394 | FALSE | BCOE | SL5-BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK | Project work has been complete but work is being reviewed by faculty. Sound soak may be installed. | BOURNS | A0159A | IN PROGRESS | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 2 | TRUE |  |  | 2018-04-12 | [6 empty] | 1/15/19, DL; Sound Soak is ordered and should arrive within two weeks……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; Need to review and scheudle…….DL, 7/11/18; Still need to review and scheudle…..DL, 8/22/18; This Project is complete but Maggie wants to see if the Faculty are happy with the results. We may install Sound Soak as a final option…… DL 9/6/18; Sent Maggie an email to see if she is satified with the work performed in regards to the sound proofing. I will have an update by the next Excel update….. DL, 9/19/18; The PI is out of town. Maggie will confirm the PI is satisiofd with the work when they return……on 9/18/18…DL, 10/8/18; Customer not satisfied with first round of sound proofing. We will proceed with Sound Soak material….. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000396 |  | 18P000396 | FALSE | CHASS | SL5-WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | Complete as of 8/24/18 | WATKINS | 2122 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | 6 | TRUE |  |  | 2018-04-13 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000398 |  | 18P000398 | FALSE | CHASS | SL5-WATKINS ESTIMATE FOR SEALING OF ADJOINING DOORS | Complete as of 10/22/18. | WATKINS | 2204 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-04-16 | [6 empty] | DL, 7/11/18; Need to walk project and verify scope and target complete date…..DL, 7/25/18; Verified scope. We need to order a new door and floor covering and need to schedule the abatnent, we will plan to start this project in 3- 4 weeks. Target complete date is late August.....DL, 8/8/18; Jess conducted the visit with the abatment contractor. Still need to verify abatment date. Carpenter shop is aware of the scope and they are ordering material. Note, one of the doors will have a lead time of 4- 6 weeks. .....DL, 8/22/18; Abatment is taking place this week. We will schedule the paint and carpet over the next week. This projcet all items for this project will be complete by 9/21/18. DL, 9/19/18; the Door was stained today and will be installed asap. The cove base is back ordered and will be installed when it is on site..target date is complete early next week...... DL, 10/4/18; This Project is 100% Complete....... |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000400 |  | 18P000400 | FALSE | SOM | SL5-Covert suite 1116 and suite 1126 to office space | Provost has placed a hold on converting lab spaces into office spaces. | WEBBER | 1116 & 1126 | HOLD - FACILITIES SERVICES | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | HOLD | HOLD | FALSE |  |  | 2018-04-14 | [6 empty] | DL, 6/16/18; Waiting for update on Provost approval….DL, 7/11/18; Per email from Enrico on 7/10/18. The Provost put a hold on converting any lab space into officess…… |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000410 |  | 18P000410 | FALSE | CHANCELLOR | SL5-HINDERAKER PAINT AND PATCH WALL | Complete as of 8/24/18 | HINDERAKER | 3148B | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-25 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000414 |  | 18P000414 | FALSE | CHANCELLOR | SL5-CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL | FS to coordinate with client to schedule work for completion. | STUDENT SERV | 0 | QUEUE TO START | Kim Wilcox | Karim Zahedi | DANIELLE GARCIA |  | Paul Ditty |  | 1 | 2 | FALSE |  |  | 2018-04-26 | [8 empty] | Enrico Baez | 6/11/18 Install TV above wainscot. Notes in FAMMIS. Need electrical and date cut ins. | YES | FS | 0 | 2018 | 2019-01-16
18P000415 |  | 18P000415 | FALSE | CHASS | SL5-PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | Door and frame have been painted; construction to commence upon availability of the teams. | OLMSTED | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | RYAN LIPINSKI |  | Dan Lerman |  |  | 10 | TRUE |  |  | 2018-05-08 | [6 empty] | 12/14/18, DL; Angel cancelled this project as it is no longer needed at this time……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 7/11/18; This project was scoped and part of the IRT. Plans and permits are approved. We will schedule the work and we will plan to have this project complet by 9/21/18…..8/10/18; WE have approved plans, this project is scheduled to start late August and will be complete early October……DL, 10/4/18; The door and frame is scheduled for delivery in 3-5 weeks, We will start the project when the doors and frame are on site……..DL, 11/7/18; Door and frame and painted. We will start the contruction in the near future…… |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000416 |  | 18P000416 | FALSE | CHASS | SL5-HMSS UWP INSTRUCTOR OFFICE PAINTING | Complete as of 8/24/18 | HUM & SOC SC | 3002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-04-27 | [8 empty] | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS. Remove double doors and install single door.Remove small West wall. Relocate t-stat. Ceiling work. Replace carpeting. | YES | FS | 0 | 2018 | 2019-01-16
18P000417 |  | 18P000417 | FALSE | CHASS | SL5-HMSS UWP INSTRUCTIONAL OFFICE PAINTING | Complete as of 8/24/18 | HUM & SOC SC | 2106 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-04-27 | [8 empty] | Enrico Baez | 5/11/18 EB-Conducted site visit on 3/21/18. Work based on Safety report written in October. Work consists of replacing door latches to orchestra pit. Adding loading dock rail, Paint frame guard, signage, gate/fall restraints, ladder modifications. | YES | FS | 0 | 2018 | 2019-01-16
18P000418 |  | 18P000418 | FALSE | CHASS | SL5-HMSS OFFICE PAINTING | Complete as of 7/14/18 | HUM & SOC SC | 2002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 15 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000419 |  | 18P000419 | FALSE | CHASS | SL5-COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | FS to coordinate with client to scope the work. | WATKINS | 1320C&E | QUEUE TO START | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 5 | 8 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty | 9/13/18 EB this is a request for patch, paint and new carpet | NO | FS | 0 | 2018 | 2019-01-16
18P000420 |  | 18P000420 | FALSE | CHASS | SL5-COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | Canceled by Customer on prioritization 7/2/18 | WATKINS | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  |  |  |  | Cancel | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000421 |  | 18P000421 | FALSE | CHANCELLOR | SL5-HINDERAKER PAINT AND PATCH WALL | Complete as of 8/24/18 | HINDERAKER | 2120 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-04-30 | [8 empty] | Enrico Baez | 7/6/18 EB emailed Paul Richardson to schedule site visit 7/17/18 EB Scheduling site visit with Paul R. 8/7/18 EB-Job was part of an IRT. Dan said he will scope 8/20/18 EB emailed Lilia to schedule site visit. 8/24/18 EB scheduled site visit for 8/28/18 at 11:00AM 8/28/18 E.Baez- Met with Paul Richardson, Lilia Vega and Becky Campbell. Instead of tearing down walls and building new ones, they wanted to see if installing sound soak on three walls were possible, it is. They will then need to have their Dean approve the sound soak. Clients were sent an email with drawing indicating desired location of sound soak. | NO | FS | 0 | 2018 | 2019-01-16
18P000425 |  | 18P000425 | FALSE | BCOE | SL5-BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - | Complete as of 7/25/18. | BOURNS | A0379 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; Luat Vuong arrives on or about August 15…... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected..…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/15/18........DL, 7/25/18; This project is 100% Complete.... |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000426 |  | 18P000426 | FALSE | BCOE | SL5-BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER | Complete as of 7/25/18. | BOURNS | A0375 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; A-375: Bhargav Rallabandi arrives on or about August 1….. DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/1/18.....DL, 7/25/18; This project is 100% Complete.... |  | Enrico Baez | 9/13/18 EB emailed Toya Adams to schedule site visit. 9/19/18 EB-Site visit scheduled for 9/20/18. 9/20/18 EB-Conducted site visit. Request to remove window in hall and install door. Interior space wall not to be removed. Secure doors, blank off and cover with sound soak. Replace carpet with Vinyl Plank, patch and paint. | YES | FS | 0 | 2018 | 2019-01-16
18P000427 |  | 18P000427 | FALSE | BCOE | SL5-BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER | Complete as of 7/11/18 | BOURNS | A0373 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie email; This is our new Dean’s faculty office. Dean Lynch is already on site getting up to speed one-two days a week. This office is an ASAP...... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected.....DL, 7/11/18; This project is 100% complete...... |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000428 |  | 18P000428 | FALSE | SoB | SL5-OLMSTED RM 2352 PATCH/PAINT | Complete as of 8/17/18 | OLMSTED | 2352 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-05-02 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000429 |  | 18P000429 | FALSE | BCOE | SL5-INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 | Complete as of 9/19/18 | BOURNS | B0262 B0256 | COMPLETE | Christopher Lynch | Maggie Souder | KEVIN SCHULTE |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment…..DL, 5/9/18; We are working on plans to submitt to A&E soon....DL, 5/24/18; Plans were submitted on 5/24/18.......DL, 6/12/18; Plans were approved. Cabinets are ordered. Materila is 6-8 Weeks out.....DL, 7/11/18; We have confirmation for delivery of material for mid August. Target Complete date is 9/7/18......DL, 8/10/18; Project has started. We will be complete with in two weeks......DL, 8/22/18; Work is 90% Complete..Project should be complete by 8/31/18........ DL 9/6/1/8; This project is 99% complete. The parts arrived today. I will be sending out an email to schedule the installation time for next week.......DL, 9/19/18; This project is 100% Complete........ |  | Paul Ditty | Duplicate request; project to be completed on 19P000194 |  | FS | 0 | 2018 | 2019-01-16
18P000432 |  | 18P000432 | FALSE | BAS | SL5-BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 | Complete as of 7/13/18 | BANNOCK H | H0101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-05-04 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000434 |  | 18P000434 | FALSE | CNAS | SL5-BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY | Complete as of 8/24/18 | BOYCE | 4478 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Paul Ditty |  |  | 3 | TRUE |  |  | 2018-05-09 | [11 empty] | FS | 0 | 2018 | 2019-01-16
18P000435 |  | 18P000435 | FALSE | CAMPUS | SL5-HMSS HYDRATION STATION REQUEST | Pending Hydration station plan for campus | HUM & SOC SC | 3600 | HOLD - FACILITIES SERVICES |  |  | NELDA THOMAS |  | Dan Lerman |  |  | 30 | FALSE |  |  | 2018-05-10 | [11 empty] | FS | 0 | 2018 | 2019-01-16
18P000436 |  | 18P000436 | FALSE | CNAS | SL5-COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS | FS to coordinate with client to schedule work for completion. | COLL BLDG SO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 36 | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  |  |  |  | FS | 0 | 2018 | 2019-01-16
18P000438 |  | 18P000438 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING | Complete as of 9/10/18 | CHUNG HALL | 415 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 10 | FALSE |  |  | 2018-05-14 | [11 empty] | FS | 0 | 2018 | 2019-01-16
18P000439 |  | 18P000439 | FALSE | BCOE | SL5-CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING | Complete as of 9/10/18 | CHUNG HALL | 315 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 11 | FALSE |  |  | 2018-05-15 | [11 empty] | FS | 0 | 2018 | 2019-01-16
18P000442 |  | 18P000442 | FALSE | VC-RED | SL5-FAWCETT LAB 203 PATCH & PAINT | Complete as of 8/24/18 | FAWCETT LAB | 203 | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 3 | FALSE |  |  | 2018-05-18 | [11 empty] | FS | 0 | 2018 | 2019-01-16
18P000444 |  | 18P000444 | FALSE | CHASS | SL5-PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 | Complete as of 9/21/18 | ARTS | 242 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-05-21 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
18P000445 |  | 18P000445 | FALSE | CHASS | SL5-PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 | Complete as of 9/10/18 | ARTS | 225 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 11 | TRUE |  |  | 2018-05-21 | [11 empty] | FS | 0 | 2018 | 2019-01-16
18P000453 |  | 18P000453 | FALSE | CNAS | SL5-DELFINO LAB-SOIL HOUSE MODIFICATION | FS to coordinate with client to scope the work. | DELFINO HHSE |  | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | [6 empty] | 1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced....... | YES | FS | 0 | 2018 | 2019-01-16
18P000454 |  | 18P000454 | FALSE | BCOE | SL5-BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS | Complete as of 8/24/18 | BOURNS | A0346 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  |  | 9 | FALSE |  |  | 2018-05-29 | [8 empty] | Dan Lerman | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain...... | YES | FS | 0 | 2018 | 2019-01-16
18P000456 |  | 18P000456 | FALSE | VC-STU.AFF. | SL5-HUB--UTILITY METERS | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. | HUB |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-05-30 | [8 empty] | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced ...... | YES | FS | 0 | 2018 | 2019-01-16
18P000459 |  | 18P000459 | FALSE | BAS | SL5-BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 | Complete as of 9/21/18 | THE BARN |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | Dan Lerman |  | Complete | 6 | FALSE |  |  | 2018-05-31 | [8 empty] | Dan Lerman | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM....... | YES | FS | 0 | 2018 | 2019-01-16
18P000463 |  | 18P000463 | FALSE | SoB | SL5-ANDERSON HALL PATCH/PAINT-102C | Complete as of 8/24/18 | ANDERSON 1 | 0102C | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-06-04 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18P000464 |  | 18P000464 | FALSE | CNAS | SL5-PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED | FS to coordinate with client to schedule work for completion. | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 35 |  | FALSE |  |  | 2018-08-16 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work.... | YES | FS | 0 | 2018 | 2019-01-16
18P000468 |  | 18P000468 | FALSE | CHASS | SL5-WATKINS 1222/1223 PATCH/PAINT | Completed as of 8/10/18 | WATKINS | 1222 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 13 | TRUE |  |  | 2018-06-11 | [8 empty] | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space. | YES | FS | 0 | 2018 | 2019-01-16
18P000469 |  | 18P000469 | FALSE | CHASS | SL5-WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS | Complete as of 7/25/18 | WATKINS | 1317 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-06-11 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-01-16
18P000470 |  | 18P000470 | FALSE | SPP | SL5-Student Check-in Lobby | Complete as of 8/23/18 | CHASS INT S | 4133 Corridor | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-11 | [6 empty] | DL, 6/16/18; I walked this project with Luis and Mark this week. They want this work completed by July 9th. Paint, data, electrical, chair rail and signage is requested. I need to review project with Paul and Robert C. DL, 7/11/18; Robert C. Ordered material and we will complete the install first part of next week We will scheudle the paint after Robert is Complete. Target Complete Date is 7/2018......DL, 7/25/18; WE have the electrical materila, plans were submitted. Once plans are reviewed and approved, we will proceed with the work. Target date is two weeks after plans are approved......DL, 8/10/18; Eletrical is complete. Pending paint. Paint will be scheduled in the near future. DL, 8/22/18; This project will be Complet on Saturday.....DL, 9/6/18. I miossed the chair rail request on this project. I will order the chair rail in the near future. The chair rail is the only item needed to complete this project. Aprroximately 20 lineal feet......DL, 9/19/18; Chair rail is ordered. We will schedule the install when the material arrives....... |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-01-16
18P000471 |  | 18P000471 | FALSE | ITS | SL5-WCH INSTALL SECURITY FENCE | Complete as of 9/19/18 | CHUNG HALL | 134 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  |  | 5 | FALSE |  |  | 2018-06-12 | [6 empty] | DL, 7/4/18; Walked this project with Angel, This request is to install security fence with Sliding gate and welded webs to increase security. Space is vacant and ready to schedule work. Need to walk with Corey to see if this is a project they can do or sub out to De ANza fence......DL 7/25/18; Still need to walk project with Corey. Dl, 8/10/18; Site walk complete, we are waiting on estimates. WE will try and schedule the work with in the next 30- days....DL, 8/22/18; Work is scheduled for August 27th. Still need to order hardware.....DL, 9/6/18; The fence is installed and Angel is very Happy, but I need to check the project to verify we are good to go....DL, 9/19/18; This Project is 100% Complete..... |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | FS | 0 | 2018 | 2019-01-16
18P000472 |  | 18P000472 | FALSE | BCOE | SL5-WCH PATCH AND PAINT WALL | Complete as of 8/24/18 | CHUNG HALL | 458 | COMPLETE | Christopher Lynch | Maggie Souder | JANNA LE BLANC |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-06-12 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-01-16
18P000473 |  | 18P000473 | FALSE | CNAS | SL5-PIERCE NEW CARPET & PAINT FACULTY OFFICE | Complete as of 9/26/18 | PIERCE | 202 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 1 | 5 | TRUE |  |  | 2018-06-12 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul D. will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-01-16
18P000474 |  | 18P000474 | FALSE | ITS | SL5-MS&E ELECTRICAL MODIFICATIONS FOR ITS | Electrian to complete the work as available. | MAT SCI ENGR | 119 | IN PROGRESS | Danna Gianforte | Shelley Gupta | MICHAEL CAPRIOTTI |  | Robert Corey |  |  | 1 | FALSE |  |  | 2018-06-13 | [6 empty] | 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-01-16
18P000476 |  | 18P000476 | FALSE | VC-RED | SL5-BOYCE CONNECT WASHER & DRYER | Canceled project, work completed on 18W015691 in July. | BOYCE | 6444 | CANCELED BY CLIENT | Michael Pazzani | Laura Manor | DIERK BIGGS |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-14 | [6 empty] | Duplicate to 18W015691; complete |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again...... DL, 4/2/18; This space is still on schedule for 7/1/18 completion date.....FAMIS work orders have been produced..... | YES | FS | 0 | 2018 | 2019-01-16
18P000478 |  | 18P000478 | FALSE | UNDERGRAD ED | SL5-CARPET, PAINT, & AIR HANDLING MODIFICATION | Complete as of 10/22/18. | HINDERAKER | 1120H | COMPLETE | Jennifer Brown | Tracey Scholtemeyer | TRACEY SCHOLTEMEYER |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-16 | [6 empty] | DL, 7/4/18; This project is scoped; Need to remove Switch gear storage rack components, remove electrical conduits, plywood backer board from walls, paint and floor covering. We will schedule this work to be complete by Fall 2018 academic year....DL, 7/11/18; Need to produce work orders and schedule the work. Target Complete date is 9/14/18... Space is vacant....DL, 8/10/18; Work has started and we are on schedule...... DL, 8/22/18; Demo is almost complete. This target date is 9/21/18......9/19/18; All trades are complete. New carpet to be installed on 9/21/18. .....DL, 9/19/18; This project is scheduled to be complete this week....... |  |  |  |  | FS | 0 | 2018 | 2019-01-16
18P000480 |  | 18P000480 | FALSE | CNAS | SL5-BG - LOWER RESTROOMS-PAINTING-FLOORS | Canceled by Facilities Services; Work is not within the SLA and is not needed. | BOTGDN RSTRM |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000481 |  | 18P000481 | FALSE | CHASS | SL5-CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 | Complete as of 10/22/18. | CHASS INT S | 3104 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  |  |  | NO | FS | 0 | 2018 | 2019-01-16
18P000482 |  | 18P000482 | FALSE | SoB | SL5-CARD ACCESS SYSTEM ANDERSON SOUTH | Complete as of 8/2/18. | ANDERSON |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-26 | [6 empty] | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with JasonDL, 7/11/18; Need to check in with Jason on status for his side of the project.....DL, 7/25/18; JAson's team is ready to install but the Anderson IT department does not have the necesary software. We will start the work when the software is up and running...... 8/12/18 DND FAMIS Status noted completion on 8/2/18. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000483 |  | 18P000483 | FALSE | BAS | SL5-INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | FS to coordinate with customer to scope the work. | P1 |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | AMANDA GREY |  | Enrico Baez |  | 7 |  | FALSE |  |  | 2018-06-26 | [6 empty] | Waiting for Amanda Grey to verify ownership of chain link fence. Once confirmed will contract with De Anza to install 36" wide gate. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18P000484 |  | 18P000484 | FALSE | ATHLETICS | SL5-INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | Project will be managed by A&E for completion. | SOFTBALL STG |  | IRT REVIEW | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-26 | [8 empty] | Paul Ditty | N/A | N/A | FS | 1899-12-31 | 2018 | 2019-01-16
18P000485 |  | 18P000485 | FALSE | SOM | SL5-SOMR PATCHING AND PAINTING | Complete as of 10/10/18 | SOM RSCH |  | COMPLETE | Deborah Deas | Brandon Barbosa | DANA ABOU ABBAS |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-06-28 | [6 empty] | N/A |  |  | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing | YES | FS | 0 | 2018 | 2019-01-16
18P000486 |  | 18P000486 | FALSE | CNAS | SL5-PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 2018-06-28 | [6 empty] | 12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  |  |  |  | FS | 0 | 2018 | 2019-01-16
18P000487 |  | 18P000487 | FALSE | CHANCELLOR | SL5-SKYE HALL PATCH HOLES AND PAINT | Complete as of 10/22/18. | SKYE HALL | 349 | COMPLETE | Kim Wilcox | Karim Zahedi | SONIA ZAMORA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18W000455 |  | 18W000455 | FALSE | CNAS | SL5-CHAPMAN CLEAN WINDOWS | Complete as of 7/11/18 | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  | 37 | FALSE |  |  | 2017-07-11 | [6 empty] | Dl, 7/4/18; All Windows in Chapman were cleaned by Ductch Touch. This Project is 100% Complete |  | Paul Ditty |  | N/A | FS | 0 | 2017 | 2019-01-16
18W001170 |  | 18W001170 | FALSE | CHASS | SL5-ARTS: PAINT CLASSROOMS | Complete as of 9/24/18 | ARTS | 407 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 27 | FALSE |  |  | 2017-07-25 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2017 | 2019-01-16
18W006022 |  | 18W006022 | FALSE | SOM | INSTALL CURTAIN ROD IN RESEARCH SPACE | Complete as of 7/11/18 | SOM RSCH | 336 | COMPLETE | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-10-27 | [6 empty] | DL, 5/24/18; Need to review scope with Enrico….DL, 7/11/18; Enrico produced work orders for sheet metal shop. This is a singel trade project. |  | Paul Ditty |  |  | FS | 0 | 2017 | 2019-01-16
18W007453 |  | 18W007453 | FALSE | ITS | SL5-(P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2017-11-30 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2017 | 2019-01-16
18W008762 |  | 18W008762 | FALSE | CHASS | SL5-HUMANITIES: PATCH & PAINT | Complete as of 11/8/18 | HUM & SOC SC | 2415 | COMPLETE | Milagros Pena | Cindy Williams | ANDREW ALONSO |  | Paul Ditty |  | 20 | 22 | FALSE |  |  | 2018-01-02 | [11 empty] | FS | 0 | 2018 | 2019-01-16
18W009630 |  | 18W009630 | FALSE | BAS | SL5-BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. | PHYS PL STOR | 100 | IRT REVIEW | Gerry Bomotti | Georgianne Carlson | JUDY HODGE |  | Dan Lerman |  | HOLD | HOLD | FALSE |  |  | 2018-01-22 | [6 empty] | DL, 6/16/18; Project includes demo wall/door install new wall, dry wall, paint, door, eletrical outlets, lighting, smoke relocation, lighting motion, new t-bar, relocate heat pump, andn install new carpet…...DL, 7/11/18; Need to work on plans….. Target complete date is late Fall..... |  | Paul Ditty | N/A | N/A | FS | 1899-12-31 | 2018 | 2019-01-16
18W011161 |  | 18W011161 | FALSE | CNAS | SL5-REPLACE CARPET | Complete as of 7/11/18 | SCIENCE LAB1 | 301 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-23 | [6 empty] | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project……DL, 5/21/18; Floor covering is selected. Work will be scheudled for Mid June….DL, 5/24/18; The install is scheduled for June 18th & 19th……DL, 7/11/18; This Project is 100% Complete...... |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
18W011672 |  | 18W011672 | FALSE | CNAS | SL5-ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY | Complete as of 7/25/18 | ENTOMOLOGY | 268 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-03-08 | [6 empty] | Relocate white board from East wall onto the West wall, where high table was removed, 24" away from North end of wall. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18W011691 |  | 18W011691 | FALSE | CNAS | SL5-ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | FS to coordinate with client to schedule work for completion. | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 4 | 11 | TRUE |  |  | 2018-03-08 | [6 empty] | 12/17/18 DND: Canceled by client on 12/17/18. | 2018-12-10 | Ron Veloz | 01/09/19 O-RVL: REQUEST FOR ESTIMATE, Not a Project. RV To schedule a site visit with C. Pillen and Chad Chambers to evaluate if repairs are possible. 12/10/18 O-RVL: REQUEST FOR ESTIMATE. Ron V walked with D. McWilliams & Jodie and identified the railroad tie retaining wall area requiring repairs. Jodie would like an estimate to repair the leaning railroad ties at specified areas. RV to meet with Chris P. and or Chad Chambers to determine if FS can perform work and or provide an estimated cost to perform work. 11/07/18 O-RVL: Received an email form Deborah Mc. to discuss the wall at Thursday during our 1-1 meeting. | YES | FS | 0 | 2018 | 2019-01-16
18W011692 |  | 18W011692 | FALSE | CNAS | SL5-ENTOMOLOGY; PAINT/PATCH LAB | Complete as of 8/24/18 | ENTOM MUSEUM | 211 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-03-08 | [7 empty] | 2018-10-10 | Ron Veloz | 01/10/19 O-RVL: Updated this project and copyied information from FAMIS. Not sure who requested this request to be a project. RV may need to rescope the project after Winter prioritizing. 01/10//19 RV copied notes from FAMIS and input the following notes: "10/10/18 O-RVL: Received email from Deborah Hughes to determine if this request is a SL5 or SL6. RV visited the site on 10-10 and saw filter media covering the supply air diffusers. RV sent photos to D.H. and informed her this was a SL6 for BM to remove filter media from the supply air diffusers. 12-21-18. R-DMU. W/O is waiting on filter to be removed. Will need to calculate air changes. Make repairs as needed. room needs to be set (Negative). This may be the solution to their air deficiency. 11/21/18 R-DMU: Spieth hall. rm 1312. Walk this job with BeiWei. 10-11-18. R-DMU. Will need tech to pull 3 ply media filter from supply register and verify proper air changes, and Exhaust flow with Flow Hood". | N/A | FS | 0 | 2018 | 2019-01-16
18W011772 |  | 18W011772 | FALSE | BAS | SL5-PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | Canceled per customer on priority list 7/3/18 | PRINT MOD |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Dan Lerman |  |  | Canceled | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/29/18; Pasted from WO; install an outside electrical outlet based on the attached amazon specs. also estimate for removing and sealing the outside vent from the copier. fyi_the copier will be moving within the next few months…..DL, 7/11/18; Need to verfy scope and schedule the work...... |  | Ron Veloz |  | YES | FS | 0 | 2018 | 2019-01-16
18W013160 |  | 18W013160 | FALSE | CNAS | BEES- PATCH & PAINT 2460D & 2460F | Complete as of 10/22/18. | GEOLOGY | 2460 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 33 | 29 | FALSE |  |  | 2018-04-06 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process… | YES | FS | 0 | 2018 | 2019-01-16
18W013973 |  | 18W013973 | FALSE | VC-RED | SL5-BSL3 FACILITY- ASSEMBLE AND INSTALL | Complete as of 9/24/18 | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2018-04-19 | [6 empty] | FAMIS NOTES 8/22: Plumbing filter system was installed and ice maker installed. Request for microscope and incubator moved into containment by customer. Complete 9/24/18 |  | Dan Lerman | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project…… | YES | FS | 0 | 2018 | 2019-01-16
18W015691 |  | 18W015691 | FALSE | VC-RED | SL5-BOYCE CONNECT WASHER AND DRYER | Complete as of 7/11/18 | BOYCE | 6444 | COMPLETE | Michael Pazzani | Laura Manor | DIERK BIGGS |  |  |  |  | 1 | FALSE |  |  | 2018-05-30 | [6 empty] | DL, 7/11/18; This project is in progress and almost complete. Target complete date is 7/20/18….. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18W016588 |  | 18W016588 | FALSE | CHASS | PATCH AND PAINT FOR FACULTY | Complete as of 8/24/18 | SPROUL | 4105 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | N/A | TRUE |  |  | 2018-06-19 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
18W016621 |  | 18W016621 | FALSE | CHASS | SL5-HUMANITIES - PAINT OFFICE - PAINT SHOP | Complete as of 11/8/18 | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2018-06-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
1900a | 1990a |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | Plans submitted for plan check, coordinating detailed const. schedule w/dir | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2193000 |  | 2015-10-09 | Start Construction | 2017-11-01 | 2019-11-01 | [8 empty] | PD&C | 0 | 2015 | 2019-01-16
1990b | 1990b |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon-Road | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  |  | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE |  |  | 2018-06-22 | Finalize Design | 2019-10-01 | 2019-12-01 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2018 | 2019-01-16
19P000006 |  | 19P000006 | FALSE | CNAS | SL5-MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 | FS to coordinate with client to scope the work. | MAT SCI ENGR | 310 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. |  | Dan Lerman | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place | YES | FS | 0 | 2018 | 2019-01-16
19P000006 |  | 19P000006 | FALSE | CNAS | SL5-MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 | FS to coordinate with client to scope the work. | MAT SCI ENGR | 310 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000006 |  | 19P000006 | FALSE | CNAS | SL5-MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 | FS to coordinate with client to scope the work. | MAT SCI ENGR | 310 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000006 |  | 19P000006 | FALSE | CNAS | SL5-MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 | FS to coordinate with client to scope the work. | MAT SCI ENGR | 310 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. |  | Ron Veloz | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". 10/03/18 RV: Work in progress, Plumbers are installing gas lines. Glove boxes from 206 can be moved after gas lines are installed. 10/08/148 RV: Plumbers to complete the installation of new gas lines in 319. Glove boxes to be brought to rm 319 after gas lines are installed. 10/17/18 RV: Update, Gas lines are installe approx 90% complete per Plumbing Tech, misc parts on order. 10/29/18 RV: All project related work is completeand confirmed with trades and PI. | YES | FS | 0 | 2018 | 2019-01-16
19P000006 |  | 19P000006 | FALSE | CNAS | SL5-MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 | FS to coordinate with client to scope the work. | MAT SCI ENGR | 310 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. |  | Ron Veloz | 07/05/18 RonV. Input: I observed multiple WO's for this project and spoke with Zee for clarification. I will investogate the site on 07/06 to determine the actual SOW. 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/22/18 O-RVL: Revised WO to Project no. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". =10/03/18: RV, Work in progress. Plumber are working on new gas lines. Will coordinate glove box move after work in rm 319 is completed. 10/29/18 RV: All glove boxes, Solvent mixing equipment and Chemical cabinet are removed. Remaining work is to replace the existing PVC vent with stainless duct when materials arrive per Cory. Update from Matt L-Plumbing department is working on the gas lines and will continue work this week. | YES | FS | 0 | 2018 | 2019-01-16
19P000009 |  | 19P000009 | FALSE | SOM | SL5-SOME -- PAINT, SPACKLE AND CLEANING NEEDED | Complete as of 10/10/18 | SOM EDUC | 2615 | COMPLETE | Deborah Deas | Brandon Barbosa | BEVERLEY HERBERT |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000011 |  | 19P000011 | FALSE | CHASS | SL5-PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED | Complete as of 10/10/18 | PSYCHOLOGY1 | 2111A | COMPLETE | Milagros Pena | Cindy Williams | LORENA QUINTANA |  | Paul Ditty |  | 4 |  | TRUE |  |  | 2018-07-03 | [6 empty] | N/A |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000012 |  | 19P000012 | FALSE | SOM | SL5-SOME--PATCH & PAINT | Complete as of 10/10/18 | SOM EDUC | 2638 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-07-06 | [6 empty] | N/A |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000014 |  | 19P000014 | FALSE | SOM | SL5-SOME - PATCH & PAINT | Complete as of 10/10/18 | SOM EDUC | 2609 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-07-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000015 |  | 19P000015 | FALSE | BAS | SL5-POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING | Complete as of 11/8/18 | POLICE TRLR | 1 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-07-10 | [6 empty] | N/A |  | Dan Lerman | DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans........DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet....DL, 4/29/18; Still need to conduct site visit with the team.... | YES | FS | 0 | 2018 | 2019-01-16
19P000017 |  | 19P000017 | FALSE | SoB | SL5-ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD | Complete as of 8/24/18 | ANDERSON 1 | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | DL, 9/6/18; Monitors are installed. Need to schedule the electrical. Target date is 9/21/18…… |  | Enrico Baez | 5/23/18 EB - Sent email to April requesting site visit. 6/11/18 EB conducted site visit request if for additional outlet only. Single trade only asked Deborah to change to SL6. | YES | FS | 0 | 2018 | 2019-01-16
19P000018 |  | 19P000018 | FALSE | SoB | SL5-ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER | Complete as of 8/24/18 | ANDERSON 1 | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | N/A |  | Dan Lerman | DL, 5/5/18; This is a repair, No alterations taking place. Pasted from FAMIS work order...THE COOLING SYSTEM ON GH 16-25 IS FALLING APART SHEET METAL TRAYS HAVE TONS OF HOLES, WOOD ROTTING ETC. PLEASE REPAIR….. RV, 07/06/18: Dan, Chis Pillen and I have walked this project months ago and have a quote from Ralph Cox/KIRA Construction to repair the head house damages. See Chris for the status of subletting this work. | YES | FS | 0 | 2018 | 2019-01-16
19P000021 |  | 19P000021 | FALSE | ITS | SL5-ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS | FS to coordinate with customer to scope the work. | ITS CENTER |  | QUEUE TO START | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-07-12 | [6 empty] | 12/14/18, DL; Still need to review scope….. |  | Ron Veloz | Scope is complete. Walked site with Steve Burelson. DI water is available behined wall in 2407 at interstictal space. Vendor will install Milpore unit, FS to provide DI water and back board.Power is available at the sink counter. Electrical has verified GFI. | YES | FS | 0 | 2018 | 2019-01-16
19P000022 |  | 19P000022 | FALSE | BAS | SL5-HUB--PAINT TWO WALL AS SCOTTY'S HUB | Complete as of 9/17/18 | HUB | 101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | DIANE THOMAS |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-07-12 | [6 empty] | N/A | 2018-11-07 | Ron Veloz | 01/11/19 O-RVL: Received an email from Mayellarequesting ststus. 11/08/18 O-RVL: Received email from Dr Beyerman today for added electrical. "I just realized that I also need a single phase 200-230VAC, 20 amp circuit in 1134 for the pump and controller, which is that unit next to the dewar. This can be down by the floor, in the vicinity of the 3 phase box. I will be meeting with the electrician today around 11am, and I will mention it to him". RV asked Dr Beyermann to contact me with the location for the pump receptacle. Will update floor plan upon receipt. 11/07/18 RV Walked site with Mayela and Dr Beyerman. Request to provide Chilled water loop, and two locations for Electrical power. Identified locations to install new utilities. 11/07/18 O-RVL: Walked site on 11/07 with Dr Beyermann & Mayela, identified scope. Update FAMIS to J-DLN, MinRenlist and move to que to start. 11/06/18 O-RVL: Jobwalk scheduled on 11/07 at 10:00am in Rm 1134 with Mayela, Ward Beyermann, Darren M HVAC, Brian H-Elect. Hold | YES | FS | 0 | 2018 | 2019-01-16
19P000023 |  | 19P000023 | FALSE | BCOE | SL5-PAINT ACCENT WALL | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-13 | [6 empty] | N/A |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | FS | 0 | 2018 | 2019-01-16
19P000026 |  | 19P000026 | FALSE | BCOE | SL5-WCH PATCH AND PAINT WALLS | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Ron Veloz | 10/30/18 RV: Chris Pillen and D. McWilliams aggreed to leave the building in place and place a concrete pad with a chain link fence adjacent to the existing structure. 10/17/18 RV: SOW, demolish walls and roof. Verify and cap existing underground utilities. Remove overhead electrical from power pole to the building. The concrete pad to remain and install a 6'H fence with gate around the pad. Bring Power below grade to pad location. Met with C.Pillen and Dan to discuss alternate options. Photos and equipment info is on the server file. | YES | FS | 0 | 2018 | 2019-01-16
19P000027 |  | 19P000027 | FALSE | ATHLETICS | SL5-ATHLETICS PATCH & PAINT ROOM | Complete as of 9/19/18 | ATH DANCE | 0120C | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | DL, 9/19/18; This Project is 100% Complete……. | 2018-10-22 | Ron Veloz | Customer called and canceled the work on 10/23/18. 10/20/18: O-RVL: Site visit on 10/20 with Amber 10:30am. 10/22/18 O-RVL: Walked site with Vendor/Controlled key sys. The PI requested pricing to change the locking function from room to room as "Storage use " and rekey the entry door with the same function. Matt will send pricing on the week of 10/22. 10/23/18 O-RVL: This request will not require access controls, but will require the entry door and side door lock-sets function to be changed to a storage function and rekeyed per Dave(PI). Received info from PI that there was a theft in his dept. Request is urgent. RV requested key count from Dave 8/23/18 and is pending a response from the department. 10/23/18 >> Canceling at the request of the customer - Loretta | YES | FS | 0 | 2018 | 2019-01-16
19P000028 |  | 19P000028 | FALSE | BCOE | SL5-BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS | Deferred to Winter Quarter | BOURNS | A0169 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | Deferred to Winter Quarter |  | FALSE |  |  | 2018-07-16 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000029 |  | 19P000029 | FALSE | BCOE | SL5-CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | Canceled; duplicate request to be completed with 19P000059 | CHUNG HALL | 205 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-16 | [6 empty] | Canceled; duplicate request to be completed with 19P000059 | 2018-09-19 | Ron Veloz | 10/17/18 RV: All construction information is on the server folder. Pending Saftey MOP's from Beiwei. Left message with her on Monday 10/15 for status. 10/03/18 RV: SOW, Install safety guard railing and apply yellow markings (leading edge 6'from perimeter) on the Winston Chung Roof. 09/19/18-Scope is complete, received safety requirements prepared by EH&S/Beiwei. RV to upload onto FAMIS. | YES | FS | 0 | 2018 | 2019-01-16
19P000030 |  | 19P000030 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT | Complete as of 10/10/18 | OLMSTED | 2301 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Enrico Baez | 6/21/18 EB Remove old glass washer and install washer 400XLS. Disconnect steam, air, water, electrical, vent hood. Install new washer, electrical, step up x-former 208v to 480. Dept. to purchase x-former $5000 ill to dept. Elect. To provide specs. | YES | FS | 0 | 2018 | 2019-01-16
19P000031 |  | 19P000031 | FALSE | CNAS | SL5-BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) | FS to coordinate with client to scope the work. | BIOLOGICAL SCI | 3101 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 40 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This is prioritized at #40 and will not be scheduled in the near future….. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000032 |  | 19P000032 | FALSE | SOM | SL5-Reconfigure recepetion desk to fit two FTEs. | Scope of work has been identified and walked with Ron V & Brandon B. | SOM EDUC | 2608 | QUEUE TO START | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | 5 | 1 | FALSE |  |  | 2018-07-17 | [6 empty] | 12/14/18, DL, Still need to conduct site visit and schedule the work… |  | Dan Lerman | Dan L. scoped this project as part of an IRT…. 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. If possible paint to match existing green accent wall, if not white is fine. Mount monitor bracket to wall centered side to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | YES | FS | 0 | 2018 | 2019-01-16
19P000033 |  | 19P000033 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT | Duplicate request to 19P000030; Canceling project to be completed on other request. | OLMSTED | 2301 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | Duplicate to project 19P000030. Canceling project. | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scope of work is complete. RV to upload docs to FAMIS. 10/03/18 RV: Install non rated door into an existing cased opening-for privacy & noise reduction. Will require carpentry-framing, patch, paint, and minor flooring/base repair. | YES | FS | 0 | 2018 | 2019-01-16
19P000035 |  | 19P000035 | FALSE | BCOE | SL5-WCH--INSTALL NEW LED DISPLAY IN OFFICE | Installation scheduled for Friday 11/19/18. | CHUNG HALL | 354 | COMPLETE | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This Porject is 100% Complet…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Install scheduled for this Friday. |  | Dan Lerman | DL 1/3: Chris to verify with customer on electrical requirements for completion…...DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress..... | YES | FS | 0 | 2018 | 2019-01-16
19P000037 |  | 19P000037 | FALSE | VC-STU.AFF. | SL5-HEALTH SERVICE BLDG--PATCH WORK AND PAINTING | Complete as of 10/22/18. | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-07-17 | [6 empty] | N/A |  | Dan Lerman | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. | YES | FS | 0 | 2018 | 2019-01-16
19P000042 |  | 19P000042 | FALSE | CNAS | SL5-COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL | FS to coordinate with client to schedule work for completion. | COLL BLDG SO | 200 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Paul Ditty |  | 38 |  | FALSE |  |  | 2018-07-20 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | FS | 0 | 2018 | 2019-01-16
19P000043 |  | 19P000043 | FALSE | CNAS | SL5-SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | Customer called and canceled the work on 10/23/18. | SCIENCE LAB1 | 309 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 19 |  | FALSE |  |  | 2018-07-20 | [8 empty] | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | FS | 0 | 2018 | 2019-01-16
19P000044 |  | 19P000044 | FALSE | VC-RED | SL5-PATCH AND PAINT | Complete as of 10/10/18 | SPIETH | 345 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-23 | [6 empty] | N/A |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-01-16
19P000045 |  | 19P000045 | FALSE | CNAS | SL5-PREPARE LOCATION AND UTILITIES FOR INSTALL | Complete as of 11/8/18 | BOYCE | 2407 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 14 |  | FALSE |  |  | 2018-07-23 | [8 empty] | Ron Veloz | RV: 10/03/18: Install metal stud wall at center of the room. Remove one door blank and install one lockset.Requires, Framing, drywall, tape, sand, paint, t-bar modifications and rubber base. PM to verify with user if power and Data will be required in the new wall. 10/17/18 RV: Floor plan is on the server folder. 10/30/18 RV: Spoke with Deborah McWilliams, today. Project to remain as prioritized(#3) for new Faculty. | YES | FS | 0 | 2018 | 2019-01-16
19P000046 |  | 19P000046 | FALSE | BCOE | SL5-PATCH AND PAINT PLUS REPLACE BLINDS | Complete as of 11/8/18 | BOURNS | A0131 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-07-23 | [6 empty] | N/A | 2018-09-28 | Ron Veloz | 09/26/18 O-RVL: 19P000006-Site walk scheduled with Dan. Will contact Deborah and Mayela for their participation. 09/27/18 O-RVL: Site walk with Chris P, Dan L. Mayela and Deborah McW. FS to re- install the metal stud wall to original place dividing the room equally. Add a lockset at the corridor door. Scoping completed. 09/28/18 O-RVL: Conducted a site visit with Mayela C., Chris P, Dan L, & Deborah McWilliams. RV completed SOW on server. Updated FAMIS and Minor Reno List. | YES | FS | 0 | 2018 | 2019-01-16
19P000049 |  | 19P000049 | FALSE | CNAS | SL5-PHYSICS PATCH & PAINT | FS to coordinate with client to schedule work for completion. | PHYSICS | 3036 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | 39 |  | FALSE |  |  | 2018-07-25 | [6 empty] | 1/11/19 DND - Complete per FAMIS | 2018-09-28 | Ron Veloz | 09/26/18 O-RVL: 19P000006-Site walk scheduled with Dan. Will contact Deborah and Mayela for their participation. 09/27/18 O-RVL: Site walk with Chris P, Dan L. Mayela and Deborah McW. FS to re- install the metal stud wall to original place dividing the room equally. Add a lockset at the corridor door. Scoping completed. 09/28/18 O-RVL: Conducted a site visit with Mayela C., Chris P, Dan L, & Deborah McWilliams. RV completed SOW on server. Updated FAMIS and Minor Reno List. |  | FS | 0 | 2018 | 2019-01-16
19P000053 |  | 19P000053 | FALSE | SoB | SL5-ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S | Complete as of 10/22/18. | ANDERSON 1 |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-04-13 | [6 empty] | DL 8/22/18; two out of four monitors are complete. WE still need to install powree at four locations…….DL, 9/6/18; Still need Electrical installed……. Planing to have complete by 9/21/18……. This is aqctually 4- monitors in four locations. We should ensure each monitor is treated as an indidual project.......DL, 9/19/18; All monitors are installed. Robert will schedule the electricans this week or early next week...DL, 10/4/18; This project is 100% Complete..... | 2018-09-28 | Ron Veloz | 09/26/18 O-RVL: 19P000006-Site walk scheduled with Dan. Will contact Deborah and Mayela for their participation. 09/27/18 O-RVL: Site walk with Chris P, Dan L. Mayela and Deborah McW. FS to re- install the metal stud wall to original place dividing the room equally. Add a lockset at the corridor door. Scoping completed. 09/28/18 O-RVL: Conducted a site visit with Mayela C., Chris P, Dan L, & Deborah McWilliams. RV completed SOW on server. Updated FAMIS and Minor Reno List. | NO | FS | 0 | 2018 | 2019-01-16
19P000054 |  | 19P000054 | FALSE | GSOE | SL5-PATCH & PAINT OFFICE | Complete as of 10/10/18 | SPROUL | 2131 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-26 | [6 empty] | N/A | 2018-09-28 | Ron Veloz | 09/28/18 O-RVL: Completed SOW: Add Wall in the center of room. Include a new Metal Stud Wall with rubber base to match existing. Remove metal cover at ceiling. Remove door lock blank and install new lockset at left door. RV completed SOW & placed on FS server. Updated FAMIS and Minor Reno List. 09/27/18 O-RVL: Site walk with Chris P, Dan L. Mayela and Deborah McW. FS to re-install the metal stud wall to original place dividing the room equally. Scoping completed. 09/26/18 O-RVL: 19P000006-Scheduled a site walk scheduled with Dan. Will contact Deborah and Mayela for their participation. | YES | FS | 0 | 2018 | 2019-01-16
19P000055 |  | 19P000055 | FALSE | CNAS | SL5-CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM | Scope reviewed by BZM; coordination by PM for work to be completed. | COLL BLDG SO | 207 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Dan Lerman |  | 32 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2018-05-18 | [6 empty] | 12/14/18, Dl; This project is prioritized at 32 and will not be scheduled in the near futurer…….DL, 7/11/18; Correction, I did not scope this yet, I thought we were talking agout the door bell and ADA operator. I will check in with Ronda and verify the scope…... DND 7/30/18: Created project to replace WO #18015182; project #19P000055 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/1 EB Site visit. TV to be mounted on wall above water fountain across from Geo 2306. Center of mount 84" high and centered between wall corner and bulletin board. Will need electrical and data. Computer connection cutout will be in mail room. See W.O. | YES | FS | 0 | 2018 | 2019-01-16
19P000056 |  | 19P000056 | FALSE | CHASS | SL5-HMSS CAPABILITY OF MOUNTING A TV | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 1212 | IN PROGRESS | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  |  | 18 | FALSE |  |  | 2017-10-03 | [6 empty] | 12/14/18, DL; Monitor is complete. Still need to work on electrical……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope with Enrico and schedule the work…. Work orders are not produced. Need to assign and schedule the work DND 7/30/18: Closed work order #18W004822; created project #19P000056……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… | 2018-11-29 | Ron Veloz | 11/29/18: RV Visited site and identifed the toilet room on the 2nd floor. SOW is to install a new exhaust fan at the second floor toilet room. Roof access is available from the access panel in the closet located in the room 210 next door. There is roof is transite per Jess. Abatement is necessary for roof penetrations and possibly has lead paint on ceilings and walls. | YES | FS | 0 | 2017 | 2019-01-16
19P000058 |  | 19P000058 | FALSE | CNAS | SL5-Assess Feasiblity of Removing/Replacing Growth Chambers | Complete as of 8/24/18 | GH HH | 18 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-28 | [6 empty] | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing...DL, 5/9/18; Project is scoped. Need to schedule the work.....Plumbers and HVAC are working on this. Still need to have electrical removed. I am working wiht Patty on who can do the demo and removal.....DL, 7/11/18; I need to check in with Ken to see if refrigerant is recovered. will isue work order to disconnect electrical..... I checked in with our campus surplus and do not have any contacts to dis,matel the very large growth Chambers. I need to inform Patty and suggest that she have Burges demo and move the Growth Chambers......We will be complete with our portion of this project before 8/1/18.......DL, 8/10/18; All work is done except the disconnect for electrical. I need to check and see if the electrical. Per FAMIS complete on 8/22/18 |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000059 |  | 19P000059 | FALSE | BCOE | SL5-CHUNG HALL 201 SECURITY SYSTEM INSTALL | ITS to install cameras, no work by FS Required. | CHUNG HALL | 201 | CANCELED BY FS | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 10 | 7 | FALSE |  |  | 2018-07-17 | [6 empty] | DND 7/30/18 Project #19P000059 to replace REF CPMS # 9054 Ron to speak with ITS to complete installation. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000060 |  | 19P000060 | FALSE | BCOE | SL5-CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | CHUNG HALL | 223 & 224 | IRT REVIEW | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 6 | 4 | FALSE |  |  | 2018-05-15 | [6 empty] | DL, 7/25/18; This project is complicated and plans/permits will be required. This project will also require Air Hanlers to be shut down so Vibration dampners can be instlled. We will work on the plans in the next 45 days. This project should be scheduled during the Winter. We may also need to rent a large portable air handler to ensure the Large server room can maintain temp....... Project #19P000060 to replace REF CPMS # 9043. DL, 11/7/18; Sent Maggie an email on 11/7/18 informing her this project is well beyond our scope and $50K threshold. |  | Paul Ditty | N/A | N/A | FS | 1899-12-31 | 2018 | 2019-01-16
19P000061 |  | 19P000061 | FALSE | CHASS | SL5-PSYCHOLOGY 1111H-PATCH HOLES IN WALL | FS to coordinate with client to schedule work for completion. | PSYCHOLOGY1 | 1111H | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000062 |  | 19P000062 | FALSE | CNAS | SL5-MSE 169-MINOR RENOVATION - NEW FACULTY | Electrical outlet is the highest priority. Must be installed by Sept 15, per Mayela Castillo | MAT SCI ENGR | 169 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 5 | 19 | TRUE |  |  | 2018-07-30 | [6 empty] | 1/15/19, DL; This project is 99% complete pending one water heater. Water heater is not here yet……12/14/18, DL; This project is 95% complete. The water heater is scheduled for delivery shortly after the new year. We will complete the install when the heater arrives…… 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 9/6/18; We will have the power and cabinets removed by 9/19/18. We are in the process of producing plans for this project. Once the plans are approved, we will proceed with the project. Note, we still need to obtain important information and some specifications regarding the procured base cabinets and counter tops, bio safety cabinet, diswasher, and freezer. ……DL, 7/7/18; The work is 90% complete. We are waiting on parts which have a 4-6 week lead time. We will finsh the balance of the project when the parts arrive….. | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scoping narrative is available and located on the BZM Fall Folder. Patch & Paint, replace supply grilles, reverse door swing, remove door closers, install metal plate over door opening. | YES | FS | 0 | 2018 | 2019-01-16
19P000063 |  | 19P000063 | FALSE | CHASS | SL5-NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS | Complete as of 9/26/18 | PSYCHOLOGY1 | 2124 | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-07-31 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000102 |  | 19P000102 | FALSE | CNAS | SL5-PATCH & PAINT FRONT CORNER OF OFFICE | FS to coordinate with client to schedule work for completion. | LIFE SCIENCE | 2930 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 42 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000106 |  | 19P000106 | FALSE | CNAS | SL5-PHYICS 1134 - UTILITIES REQUEST | FS to coordinate with client to scope the work. | PHYSICS | 1134 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 15 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 12/14/18, DL; No update…. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000122 |  | 19P000122 | FALSE | CHANCELLOR | SL5-REMOVE, PATCH & PAINT AND HANG | Complete as of 10/22/18. | STUDENT SERV | 2222 | COMPLETE | Kim Wilcox | Karim Zahedi | CHRISTINE SMITH |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Enrico Baez | 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. Install 2 duplex outlets | YES | FS | 0 | 2018 | 2019-01-16
19P000124 |  | 19P000124 | FALSE | VC-STU.AFF. | SL5-PAINT ROOMS 115 AND 116 | Complete as of 10/22/18. | COSTO HALL | 125 | COMPLETE | Brian Haynes | Cathy Eckman | LINDA KELLEY |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A | 2018-10-08 | Ron Veloz | 01/10/19 O-RVL: RV received quote and will send a formal Estimate to Aimee by EBD Fri. 01/11 and ask if they would like to procede. 12/14/18 O-RVL: REQUEST FOR ESTIMATE ONLY. Send Estimated costs to Aimee Gonzales for review and approval. Pending access controls and auto door operator quotes. Moved to Queue to start. 11/08/18 O-RVL: Scope is complete. Assisting the lock shop with pricing to provide the requestor an estime prior to start of construction. Walked a 2nd vendor , pending quote for access control card reader. 11/05 RV called vendor for quote, no reply. 10/29/18 RV: Conducted jobwalk with vendor last week. Pending quote from Vendor. Will follow up. | YES | FS | 0 | 2018 | 2019-01-16
19P000126 |  | 19P000126 | FALSE | CNAS | SL5-CHEMICAL SCIENCE - MINOR RENOVATIONS | Paint has been completed; plumbing to complete work upon availability of the team. | CHEMICAL SCI | 455 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Dan Lerman |  | 6 |  | TRUE |  |  | 2018-08-03 | [6 empty] | 12/14/18, DL; This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL,11/7/18; Paint is complete, Plumbing shop is planning to schedule the work in the near future…… |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000127 |  | 19P000127 | FALSE | CNAS | SL5-PIERCE PATCH & PAINT | Duplicate request to be combined with 19P000239 | PIERCE | 2301 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | MICHELLE KING |  | N/A |  | Canceled |  | FALSE |  |  | 2018-08-03 | [6 empty] | Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000129 |  | 19P000129 | FALSE | BCOE | SL5-HANG MONITORS AND BOARDS | Dry erase boards and monitor mount installation complete; monitors to be installed. | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | RICHARD BAIN |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2018-08-06 | [6 empty] | 12/14/18, DL; This Project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Dry errase boards and Monitor mounts are installed. Still need to install monitors, corner guards and monitors….. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000133 |  | 19P000133 | FALSE | CNAS | SL5-PATCH HOLES AND PAINT | FS to coordinate with client to schedule work for completion. | BATCHELOR | 2203 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 43 |  | FALSE |  |  | 2018-08-07 | [6 empty] | N/A |  | Enrico Baez | 11/08/18 RV: Enrico is assisting RV and has scheduled a job walk with Laurie Graham. Will follow up, pending confirmation. 11/19/18 EB-Met with Laurie Graham at site. SCOPE CARPENTERS-Remove all wall, base and center island cabinet work. Verify no ACM flooring under center island. PLUMBERS-Remove sinks in 1270 and 1270A. Terminate, at wall plumbing. Remove air/gas lines on wall in 1270 and 1270A. Remove lower chilled water, supply and return, lines on East wall. Remove air and gas line, flush with floor, from center island. FLOORING-Remove VCT in 1270 and 1270A, replace with customer selected VCT. Replace all cove base. ELECTRICIANS-Remove gray flexible conduit at raceway, terminate circuit. PAINTERS- Patch and paint walls in both spaces. | YES | FS | 0 | 2018 | 2019-01-16
19P000170 |  | 19P000170 | FALSE | CNAS | SL5-INSTALL NEW IRRADIATOR INSTRUMENT | Anticipated delivery of equipment is scheduled for three weeks. | MAT SCI ENGR | 51 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  | Dan Lerman |  | CNAS 16/BCOE 6 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 1/15/19, DL; Electric is commplete, Water will be complete with in two weeks. Equipment should be on site soon…12/14/18, DL; This project is currently on hold per RED…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; The unit is schedukled for delivery in the next three weeks. |  | Paul Ditty | Duplicate request; project to be completed on 19P000234 | N/A | FS | 0 | 2018 | 2019-01-16
19P000171 |  | 19P000171 | FALSE | CHASS | SL5-HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST | FS to coordinate with client to schedule work for completion. | HUM & SOC SC | 1614 | QUEUE TO START | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 16 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-01-16
19P000172 |  | 19P000172 | FALSE | VC-STU.AFF. | SL5-HEALTH SERV- PAINT RESTROOM IN LABORATORY | Complete as of 11/8/18 | HEALTH SERV | 0113A | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-01-16
19P000173 |  | 19P000173 | FALSE | CHASS | SL5-PAINT/PATCH UNIVERSITY THEATER LOBBY | Complete as of 11/8/18 | THTR WKSH | 0400A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-01-16
19P000174 |  | 19P000174 | FALSE | CNAS | SL5-BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT | Scope reviewed by BZM; coordination by PM for work to be completed. | BATCHELOR | 2112 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AMY RICKS |  | Dan Lerman |  | 37 |  | FALSE |  |  | 2018-07-24 | [6 empty] | 12/14/18, DL; This project is priortized at 37 and will not be scheudled until further notice…… | 2018-08-22 | Ron Veloz | DND 8/12/18 replaced 3 projects for Summer quarter completion. Ron V. has scope on project. 08/22/18 O-RVL: Completed S.O.W, sent to Mayela Castillo for sign off. 08/23/18-RV: Ron V. Resubmitted S,O.W. rev.1 and received Final sign off from Mayela. Met with Dan to provide information and hand off the project. 08/27/18 RV: Updated notes. Moved to "Que to Start". Lab upgrades, Install utilities for new lab equipment, including DI water, electrical, modify existing cabinet to accommodate new flask washer, install owner furnished lab workstations. 10/17/18 RV: Work is in Progress. | YES | FS | 0 | 2018 | 2019-01-16
19P000175 |  | 19P000175 | FALSE | BCOE | SL5-PAINTING | Complete as of 10/10/18 | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT CHAVARRIA-VIVAR |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000176 |  | 19P000176 | FALSE | CNAS | SL5-PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY | FS to coordinate with client to schedule work for completion. | PHYSICS | 1112 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 50 |  | FALSE |  |  | 2018-08-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000181 |  | 19P000181 | FALSE | VC-RED | SL5-PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS | FS to coordinate with client to schedule work for completion. | UNIV OFC BLD | 249 | QUEUE TO START | Michael Pazzani | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-14 | [6 empty] | N/A |  | Ron Veloz | Work in progress, install nitrogen lines and valves(valves by PI). Patch and paint. 10/30/18 RV: Spoke with Kevin, pending nitrogen line installation | YES | FS | 0 | 2018 | 2019-01-16
19P000184 |  | 19P000184 | FALSE | CNAS | SL5-REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES | FS to coordinate with client to scope the work. | GEOLOGY | 1270 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 45 |  | FALSE |  |  | 2018-08-14 | [6 empty] | 12/14/18, DL; This project is prioritized at 45 and will not be shceudled until further notice…… |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-01-16
19P000185 |  | 19P000185 | FALSE | CNAS | SL5-NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE | Scope of work has been identified and walked with Requestor, F.S. Trades and P.M. Trade work in progress. | PIERCE | 206 (originially identified as Room 204) | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 6 | TRUE |  |  | 2018-06-18 | [6 empty] | 12/14/18, DL; This project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Pending glove box relocation to rm 319 and minor vent reconfiguration. Both tasks will be performed afet the glove boxes relocate to rm. 319. 10/29/18 All project related work is completed. |  | Paul Ditty |  |  | FS | 0 | 2018 | 2019-01-16
19P000186 |  | 19P000186 | FALSE | CNAS | SL5-NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION | Complete as of 11/8/18 | PIERCE | 319 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-06-18 | [6 empty] | Pending gas line installation scheduled for the week of 09/24 per Steve Burleson. Move glove boxes from 206 to Rm 319 after gas line are installed. All work is complete |  | Ron Veloz | DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB-Spoke with Mayela-she is researching where the project stalled within her department. 7/2/18 DND Please verify if work is still required for completion 8/7/18 EB-sent Mayela email requesting update on 9/20/18 EB-emailed Mayela to determine status of project. 9/24/18 EB-Project not cancelled. Passed on to Ron Veloz. 10/03/18: RV, Walke job with Mayela, Chris P, Dan L & Deb McWilliams. PI to provide Dan layout and equipment specs. | YES | FS | 0 | 2018 | 2019-01-16
19P000188 |  | 19P000188 | FALSE | CAMPUS | SL5-PAINT - HALLWAY DOORS & INSIDE RESTROOMS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500 | CANCELED BY FS |  |  | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-16 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob | YES | FS | 0 | 2018 | 2019-01-16
19P000189 |  | 19P000189 | FALSE | CNAS | SL5-PHYSICS- WALL HOLES PATCH | Duplicate work order to 19P000049. Work to be completed on other project. | PHYSICS | 3036 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-16 | [8 empty] | Paul Ditty | Paul Ditty |  | FS | 0 | 2018 | 2019-01-16
19P000191 |  | 19P000191 | FALSE | CNAS | SL5-PATCH AND PAINT HINDERAKER BASEMENT | Complete as of 11/8/18 | HINDERAKER |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 34 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Enrico Baez | EB, 5/29, conducted site visit 5/25. Structure is a double wide modular building/trailer. Space needs to be cleared of equipment, desks, tools. Disconnect electrical, plumbing. Needs professional removal. University Asset see Susan Marshburn for direction. EB, 9/12/18 Per Deborah McWilliams email.Project is canlled due to lack of funding. | YES | FS | 0 | 2018 | 2019-01-16
19P000192 |  | 19P000192 | FALSE | BAS | SL5-MAIL-PAINTING | Complete as of 11/8/18 | MAIL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-01-16
19P000193 |  | 19P000193 | FALSE | CNAS | SL5-GENOMICS 2221 - FOB ACCESS SYSTEM INSTALLATION | FS to coordinate with client to scope the work. | GENOMICS | 2221 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | [7 empty] | 2018-09-19 | Ron Veloz | 9/10: D. Dinh Project is shared between CNAS & BCOE, captured only on the CNAS College Count. 09/19/18 RV, Scope is complete. RV to Upload into FAMIS. Install chilled water and dedicated power for the irradiator instrument at the west wall in rm 051. 10/17/18 RV: SOW provide Chilled water loop and one(1ea) dedicated 208v 1ph 40a circuit to the Irradiator. Floor plan and specs are on the server folder. | YES | FS | 0 | 2018 | 2019-01-16
19P000194 |  | 19P000194 | FALSE | CHASS | SL5-PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 | Complete as of 11/8/18 | HUM & SOC SC | 3304 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000195 |  | 19P000195 | FALSE | CHASS | SL5-HUM & SOC SC-ROOM PAINTING | Complete as of 11/8/18 | HUM & SOC SC | 2003 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000196 |  | 19P000196 | FALSE | CHASS | SL5-PAINT OFFICE AT UNIVERSITY THEATER | Complete as of 11/8/18 | THTR WKSH |  | COMPLETE | Milagros Pena | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000197 |  | 19P000197 | FALSE | CNAS | SL5-PATCH AND PAINT OFFICE, LOBBY AND HALL | FS to coordinate with client to schedule work for completion. | COLLEGE BLDG NO | 0203B | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 44 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000201 |  | 19P000201 | FALSE | CHASS | SL5-PATCH AND PAINT THE WALLS | Complete as of 11/8/18 | CHASS INT S | 3111A | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 18 |  | FALSE |  |  | 2018-08-22 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000205 |  | 19P000205 | FALSE | BCOE | SL5-LABORATORY RENOVATION FOR NEW FACULTY | Plans under review by Fire Marshal; clarification required on sprinkler system. | BOURNS | A0328 | PLAN DEVELOPMENT/CHECK | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  | Dan Lerman |  | 4 |  | TRUE |  |  | 2018-08-23 | [6 empty] | 1/15/19, DL; This project is 90% complete. WE still need to finish snorkels and ceiling tiles. We should be 100% complete by 2/1/19……12/14/18, DL; This project is on schedule..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/4/18; This is a large scale project, we will walk with the trade supervisors next week. We will also work on the plans and schedule the work. Target Date is 1/1/19…..DL, 11/7/18; work is scheduled. We are working on the electrostatic paint contract. We are in plan check review process. There are questions about the fire sprinklers from Scott J. Sent Scott J. an email requesting a site visit to better determine if any work will be required on the sprinkler system….. |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000207 |  | 19P000207 | FALSE | CHASS | SL5-QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-08-23 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000208 |  | 19P000208 | FALSE | BAS | SL5-PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | Canceled per customer on priority list 9/17/18 | THE PLAZA |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | CARLA CHAPPLE |  | Dan Lerman |  | Canceled |  | FALSE |  |  | 2018-08-14 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000209 |  | 19P000209 | FALSE | PLANNING & BUDGET | SL5-OLD EH&S SITE- FS ANNEX A REMODEL | Scope of work has been reviewed and being scheduled for completion. | ENV H AND S | 100 | IN PROGRESS | Gerry Bomotti | Jacqueline Norman | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 2018-08-24 | [6 empty] | 9/10: Zee assigning work orders per Chris' walk with Craig. |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000210 |  | 19P000210 | FALSE | CNAS | SL5-CHEMICAL SCI Install Door In Doorway | FS to coordinate with client to scope the work. | CHEMICAL SCI | 0225A | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  |  |  | 25 |  | FALSE |  |  | 2018-08-24 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000211 |  | 19P000211 | FALSE | CAMPUS | SL5-LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | Reviewing campus standards for these project requests. | LIFE SCIENCE | 2545 | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000212 |  | 19P000212 | FALSE | CAMPUS | SL5-REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500A | HOLD - FACILITIES SERVICES |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000213 |  | 19P000213 | FALSE | CNAS | SL5-NEEDS FOR NEW WALL DISPLAY (MONITOR) | Duplicate request to 19P000031; Work to be completed on other project. | BIOLOGICAL SCI | 3101 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000214 |  | 19P000214 | FALSE | CNAS | SL5-PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT | Complete as of 10/10/18 | PHYSICS | 3005 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-08-24 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000215 |  | 19P000215 | FALSE | BAS | SL5-SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 | Coordinating movement of equipment and utility connections. | HUB | 346 | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | John Peraino |  | 9 |  | FALSE |  |  | 2018-08-24 | [6 empty] | 12/12/18 DND Project complete; electrical was installed and all kitchen equipment was hooked up as requested. |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000216 |  | 19P000216 | FALSE | CHASS | SL5-HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT | Complete as of 11/8/18 | HUM & SOC SC | 1214 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-08-27 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000217 |  | 19P000217 | FALSE | GSOE | SL5-PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 | FS to coordinate with client to scope work. | SPROUL | 1359 | QUEUE TO START | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-27 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000220 |  | 19P000220 | FALSE | CHASS | SL5-ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT | Screen to be reinstalled on Friday 11/9/18. | ARTS | 333 | COMPLETE | Milagros Pena | Cindy Williams | SONJA SEKELY-ROWLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 12/14/18, DL; This project is 100% Complete….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/8/18; Screeen is scheduled to be removed this Friday. We will schedule the installation and the patch / Paint repairs once we receive the repaired screen back from the vendor…….DL, 11/7/18; This project should already be complete. However, The vnedor did not deliver the correct screen. The correct screen is currently scheduled for this Friday..... |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000221 |  | 19P000221 | FALSE | CHASS | SL5-PATCH, PAINTING, AND REGULAR CLEANING OF A126A | Complete as of 11/8/18 | OLMSTED | A0126A | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000222 |  | 19P000222 | FALSE | BAS | SL5-PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER |  | PRINT MOD |  |  | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-02 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000224 |  | 19P000224 | FALSE | BAS | SL5-PAINT EXTERIOR RAMP AT HUB MODULAR | FS to coordinate with client to schedule work for completion. | PRINT MOD |  | QUEUE TO START | Gerry Bomotti | Georgianne Carlson | MIKE CLEMONS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5-UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | QUEUE TO START | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000226 |  | 19P000226 | FALSE | CHASS | SL5-PAINT OFFICE HMNSS 3304 | Duplicate request; project to be completed on 19P000194 | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-08-28 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000226 |  | 19P000226 | FALSE | CHASS | SL5-PAINT OFFICE HMNSS 3304 | Duplicate to 19P00014; work to be completed on original project. | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Duplicate |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000227 |  | 19P000227 | FALSE | BAS | SL5-DINING STORAGE ROOM CONVERSION | Scheduled work with trades anticipated completion December 2019. | BANNOCK J | J0100 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | DARCI LOMBARD |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-08-17 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000229 |  | 19P000229 | FALSE | GSOE | SL5-RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR | FS to coordinate with client to scope work. | SPROUL |  | QUEUE TO START | Thomas Smith | Sally Tavizon | KAREN NAPLES |  |  |  | 4 |  | FALSE |  |  | 2018-08-29 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000230 |  | 19P000230 | FALSE | CNAS | SL5-NEW FACULTY OFFICE FOR PATCHWORK/PAINT | Complete as of 10/10/18 | GEOLOGY | 1242A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-08-30 | [6 empty] | n/a |  | Enrico Baez | Duplicate of 18W011999 project scoped and note entered to make facility ADA compliant. | YES | FS | 0 | 2018 | 2019-01-16
19P000231 |  | 19P000231 | FALSE | CNAS | SL5-OLMH 1428 PATCH AND PAINT | FS to coordinate with client to schedule work for completion. | OLMSTED | 1428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ANDREW CABRERO |  | Paul Ditty |  | 48 |  | FALSE |  |  | 2018-08-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000232 |  | 19P000232 | FALSE | BAS | SL5-BANNOCKBURN J-104 BREAK ROOM UPGRADE | Scheduled work with trades anticipated completion December 2019. | BANNOCK I | I0105 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | John Peraino |  | 6 |  | FALSE |  |  | 2018-09-04 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000233 |  | 19P000233 | FALSE | BAS | SL5-PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | FS to coordinate with customer to scope the work. | MAIL | 884 | CANCELED BY FS | Gerry Bomotti | Georgianne Carlson | AMY EVERETT |  |  |  | 12 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000234 |  | 19P000234 | FALSE | CNAS | SL5-PHYSICS 3005-WALL HOLES PATCH | Duplicate work request. | PHYSICS | 3005N | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-09-04 | [6 empty] | n/a | 2018-10-05 | Enrico Baez | 0/5/18 E. Baez- conducted site visit. Carpenters: Removes sliding chalk boards in 1206 and 1206 and fill in with wall. Remove patched in panels on left of chalk board in 1206. Patch where " do not enter" signs were removed. Electricians: Disconnect power to two "do not enter" signs above doors. Abatement: Remove approx 300 sq.ft. of ACM VCT Flooring: replace flooring with either VCT of vinyl plank. Painters: Patch and paint, at least one wall accent wall. | YES | FS | 0 | 2018 | 2019-01-16
19P000235 |  | 19P000235 | FALSE | BAS | SL5-RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | Customer to determine scope of work. | ABER INVER | A0100 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 11 |  | FALSE |  |  | 2018-09-04 | [7 empty] | 2018-09-18 | Enrico Baez | 9/18/18 E. Baez Conducted site visit. Scope of work Carpentry Remove 20 feet of built-in wood cabinets and counter top. Install TV mount on South wall. Remove and replace white board on North wall. Abatement Abate approximately 200 square feet of 9â€ x 9â€ VCT tile and base cove Flooring Install carpet similar to what is in room 1357 Replace base cove. Walls Patch and paint walls. Electrical Install duplex outlet for TV Replace fluorescent lamps with LED lamps TV Install data point and Internet connection to support video conferencing. Custodial Vacuum dust from ceiling tiles. 9/13/18 EB-emailed Karen Naples to schedule site visit. 9/18/18 EB-Conducted site visit. Request to remove cabinet, abate VCT, install carpet, mount TV. Electrical and date lines needed. Install white board. Replace flourescent tube with LED. | YES | FS | 0 | 2018 | 2019-01-16
19P000236 |  | 19P000236 | FALSE | BAS | SL5-EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION | Scheduled work with trades anticipated completion December 2019. | ABER INVER | A0100 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 10 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Enrico Baez | 9/20/18 EB-conducted site visit 9/18. Request for tile and plumbing removal, patch and paint. To facilitate placement of printer system. E-mail sent to Monty on 9/14 asking for direction on renovating hallway space. Awaiting Susan's response per Monty. Entered scope on shared drive. Will need Fire Marshal approval to determine which of three possible locations will allow placing of WEPA system. 11/13/2018 E. Baez-Met with Ron Rector to discuss system placement. WEPA system is to be placed on second floor near vending machines on North side. See note in shared drive. Will need power and data connections. | YES | FS | 0 | 2018 | 2019-01-16
19P000237 |  | 19P000237 | FALSE | GSOE | SL5-PATCH AND PAINT OFFICE - SPROUL 1206 | FS to coordinate with client to schedule work for completion. | SPROUL | 1206 | QUEUE TO START | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-09-05 | [8 empty] | Enrico Baez | 7/17/18 EB-Scheduling site visit with Michael Capriotti 8/7/18 EB- Met with Robert Corey to discuss scope of work. He will coordinate work. | YES | FS | 0 | 2018 | 2019-01-16
19P000238 |  | 19P000238 | FALSE | VC-UNIV.ADV. | SL5-PATCH & PAINT HINDERAKER 1136 | Pending completion of one room outstanding for scheduling. | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-01-16
19P000241 |  | 19P000241 | FALSE | PLANNING & BUDGET | SL5-PATCH/PAINT IN OFFICE 2122 HINDERAKER | Canceled per customer call on 9/13/18 | HINDERAKER | 2122 | CANCELED BY CLIENT | Gerry Bomotti | Jacqueline Norman | MILLY PAREDEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-06 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000242 |  | 19P000242 | FALSE | CNAS | SL5-PAINT OFFICE | FS to coordinate with client to schedule work for completion. | COLLEGE BLDG NO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 47 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000243 |  | 19P000243 | FALSE | CNAS | SL5-GENOMICS 1206 - PATCH AND PAINT WALLS | FS to coordinate with client to schedule work for completion. | GENOMICS | 1206 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Paul Ditty |  | 49 |  | FALSE |  |  | 2018-09-06 | [6 empty] | n/a |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000244 |  | 19P000244 | FALSE | CNAS | SL5-PATCH & PAINT GEOLOGY | Complete as of 10/22/18. | GEOLOGY | 2258A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2018-09-06 | [6 empty] | N/A |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-01-16
19P000245 |  | 19P000245 | FALSE | SOM | SL5-ADA COMPLIANT - AUTOMATIC DOOR ENTRY | FS to coordinate with client to scope the work. | SOM RSCH |  | HOLD - FACILITIES SERVICES | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 4 |  | FALSE |  |  | 2018-09-07 | [7 empty] | 2018-06-21 | Ron Veloz | 01/09/19 O-RVL: RV spoke with Jorge on 1/09. Jorge expect screens to be ordered within two weeks and will cancel this request if the screens are not ordered by his department. Jorge asked to contact him in two weeks (01/23/19). 6/21/18 RV HOLD, Walked site w/ Enrico & Jorge. Surveyed site and Enrico updated FAMIS & Project folder. Now pending - confirmation of party to purchase projection screens. S.O.W.: Remove two non functional motorized video screens. Replaced with new larger screen. Patch and repaint all walls and entry door. 07/06/18 Ron V Input notes: Received email from Enrico on 07/03 confirming Facilities Services doe not purchase Audio Visual equipment in General Assigment class rooms. On 07/06 RV contacted Jorge Macias with this info and Jorge said he would get back to RV with follow up reply from his supervisor. Confirmed with E.B. that proj info/ photos are updated on the project folder and FAMMIS. 08/22/18 O-RVL: Will follow up with Jorge to confirm status on the screen purchase and if Media will purchase the screens. 08/23/18-RV emailed Jorge, Pending response. 08/24/18-RV, Enrico followed up with Jorge, projection screens approved but not purchased yet). 10/17/18: RV spoke with Jorge today and he said screens are on order. Jorge will follow up with updates to RV and Enrico. | YES | FS | 0 | 2018 | 2019-01-16
19P000246 |  | 19P000246 | FALSE | CNAS | SL5-PHYSICS - PATCH AND PAINT | Complete as of 10/10/18 | PHYSICS | 3007N | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 46 |  | FALSE |  |  | 2018-09-07 | [6 empty] | n/a | 2018-07-06 | Ron Veloz | 06/29/18 Ron V: SOW, Remove the existing non rated solid core door & grille and replace with a new maple veneerd Dutch door with prefinished clear coat without grille. Door to be prepped on the hinge side with one continoues hinge. Confirm/field verify is a double bevel on door is requird. Do not prep the strike/lockset side.. Cylinder to be bored onsite by Lock shop. The top of the lower door to have a small shelf + - 6-8 inches wide, confirm size with Duffy prior to ordering the door. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | FS | 0 | 2018 | 2019-01-16
19P000247 |  | 19P000247 | FALSE | BAS | SL5-LOTHIAN FIRST FLOOR COMMON AREA FLOORING | Complete as of 10/22/18. | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Jess Hernandez |  |  |  | FALSE |  |  | 2018-09-10 | [7 empty] | 2018-07-06 | Ron Veloz | 06/26/18 Ron V. visited site & met with Duffy. Scope of work for rm's 2103 & 2103 A requires: Painting of walls and conduit locted on the walls, replace damaged ceiling tiles, replace one damaged prismatic 2x4 light fixture lense, remove one tack board and shampoo carpet. Existing wall tiles to remain and receive paint. No work required in 2103 B per Duffy. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | FS | 0 | 2018 | 2019-01-16
19P000248 |  | 19P000248 | FALSE | SOM | SL5-SOME--SOME INSTALL ELECTRICAL 1682 | FS to coordinate with client to scope the work. | SOM EDUC | 1682 | QUEUE TO START | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 2 |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez | Met with IT staff. T.V. to be mounted in 4 locations. Will need electrical and painting in some locations. Waitng for updated scope from Joe Sepulveda | YES | FS | 0 | 2018 | 2019-01-16
19P000249 |  | 19P000249 | FALSE | SOM | SL5-SOME-INSTALL LOCKERS | Lockers on order by customer; upon arrival to be installed. | SOM EDUC |  | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-07 | [6 empty] | DL, 11/7/18; It is my understanding the lockers are ordered, but we donot have a confirmed delivery date. Once the material is on site, we will schedule the installation…… |  | Enrico Baez | EB-1/31/18 Conducted site visit. Request to replace all exterior Plexiglas with glass. Will call glass vendor to provide estimate. 7/12/18 EB-Quote provided by Hour Glass. Emailed Tami, she is waiting for budget approval to proceed with project. Should have by end of July. 10/22/18 Customer Canceled; will resubmit when ready to proceed. | YES | FS | 0 | 2018 | 2019-01-16
19P000250 |  | 19P000250 | FALSE | BCOE | SL5-BOURNS A303-PAINT AND PATCH WALL | Complete as of 10/10/18 | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | JUANA GUERRERO |  | Paul Ditty |  | 5 |  | TRUE |  |  | 2018-09-10 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000251 |  | 19P000251 | FALSE | CNAS | SL5-CHEM SCI 428-PATCH DRY WALL HOLES | Complete as of 10/10/18 | CHEMICAL SCI | 428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-09-10 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000252 |  | 19P000252 | FALSE | ATHLETICS | SL5-ATH DANCE SHOWER DOORS | FS to coordinate with customer to scope the work. | ATH DANCE | 0050K | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  |  |  | 3 |  | FALSE |  |  | 2018-09-10 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000253 |  | 19P000253 | FALSE | CHASS | SL5-ARTS RENOVATION | Complete as of 9/21/18 | ARTS | 157 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 16 | FALSE |  |  | 2018-04-17 | [6 empty] | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access……DL, 7/11/18; This project needs to be complete before Fall 2018. Space is vacant and ready go. Need to walk and confirm Schdule with Paul D. Tony's Flooring is ready to go after paint is complete.... Target complete date is 9/21/18......DL, 8/22/18; Walked with PAul, Paul will scheudle the work. Jess still need to cordinate with Tony's Flooring .....DL, 9/19/18; The paint and flooring is complete. The seams need to be welded and this will be complete. this will be complete by 9/21/18......9/19/21; This Project is 100% Complete....... |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000255 |  | 19P000255 | FALSE | SPP | SL5-CHASS INT N REMODEL - 4022 PATCH AND PAINT | Complete as of 10/10/18 | CHASS INT N | 4022 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Dan Lerman | DL, 4/29/18; Chris said he is aware of project scope. I need to review with Chris and schedule the work;…..Dl, 5/3/18; Dand to walk project with Chris and Dave to confirm scope. We will sub out tile work. This is paint tile, lighting and plumbing fixture upgrade..... | YES | FS | 0 | 2018 | 2019-01-16
19P000256 |  | 19P000256 | FALSE | SPP | SL5-CHASS REMODEL - 4146 PATCH AND PAINT | FS to coordinate with client to schedule work for completion. | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  |  |  | 3 |  | TRUE |  |  | 2018-09-10 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000263 |  | 19P000263 | FALSE | SPP | SL5-CHASS NORTH REMODEL - 4009 PATCH AND PAINT | Complete as of 11/8/18 | CHASS INT N | 4009 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-09-11 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000265 |  | 19P000265 | FALSE | ATHLETICS | SL5-ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000266 |  | 19P000266 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000268 |  | 19P000268 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH AND PAINT 20C | FS to coordinate with client to schedule work for completion. | ATH DANCE | 20C | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | n/a |  | Chris Pillen | Chris walked the project with Craig Kasten on 9/6. | YES | FS | 0 | 2018 | 2019-01-16
19P000269 |  | 19P000269 | FALSE | ATHLETICS | SL5-ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | Project is not within the purview for completion; condition is fair and usable. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 5 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18…..This is a cooman area. Is this recharge work……. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000270 |  | 19P000270 | FALSE | ATHLETICS | SL5-ATH DANCE-WEIGHT ROOM DROP DOWN CEILING | FS to coordinate with customer to scope the work. | ATH DANCE | 78 | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 14 |  | FALSE |  |  | 2018-09-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000271 |  | 19P000271 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 | FS to coordinate with client to schedule work for completion. | ATH DANCE | 3 | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-09-12 | [6 empty] | n/a |  | Ron Veloz | 12/14/18 O-RVL: F & LS shop space/Shop Location TBD. | NO | FS | 0 | 2018 | 2019-01-16
19P000272 |  | 19P000272 | FALSE | ATHLETICS | SL5-NEED URINAL DIVIDERS | FS to coordinate with customer to scope the work. | ATH DANCE | 50E | HOLD - FACILITIES SERVICES | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 13 |  | FALSE |  |  | 2018-09-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000273 |  | 19P000273 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-12 | [6 empty] | n/a |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL,2/26/18; Conducted site visit with Frank. We will notify Frank when we are ready to proceed with the project…… | YES | FS | 0 | 2018 | 2019-01-16
19P000274 |  | 19P000274 | FALSE | ATHLETICS | SL5-RIV SPORTS CPX - REPLACE URINALS | FS to coordinate with customer to scope the work. | RIV SPORTS CPX |  | PROJECT INTAKE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 15 |  | FALSE |  |  | 2018-09-12 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000275 |  | 19P000275 | FALSE | ATHLETICS | SL5-SOFTBALL STG PRESS BOX AC ADDITION | FS to coordinate with customer to scope the work. | SOFTBALL STG |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 6 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18; I checked on this recently and this is not a building, it is stoarge and should be recharge work…. |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000276 |  | 19P000276 | FALSE | ATHLETICS | SL5-TRACK BLEACH-PUBLIC RESTROOMS UPGRADE | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | TRACK BLEACH |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 16 |  | FALSE |  |  | 2018-09-12 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5-ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 10 |  | FALSE |  |  | 2018-09-12 | [6 empty] | ??????? |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000278 |  | 19P000278 | FALSE | BCOE | SL5-REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR | Scheduling work for completion | BOURNS | A0165 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Dan Lerman |  | 1 |  | TRUE |  |  | 2018-08-03 | [6 empty] | DL, 10/4/18; This Project is 100% Complete…….. |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000279 |  | 19P000279 | FALSE | ITS | SL5-HUB - ADD 2 POWER OUTLETS |  | HUB |  |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-09-13 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000280 |  | 19P000280 | FALSE | SoB | SL5-ANDERSON HALL PAINT ONLY |  | ANDERSON 2 | 113 |  | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-13 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000282 |  | 19P000282 | FALSE | CHASS | SL5-ARTS - INSTALL STEAM METER TRANSDUCER REMOTE MOUNT KIT |  | ARTS |  |  | Milagros Pena | Cindy Williams | CHRIS FLANDERS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-14 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000283 |  | 19P000283 | FALSE | CNAS | SL5-HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  |  |  | 20 |  | FALSE |  |  | 2018-09-05 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000284 |  | 19P000284 | FALSE | CAMPUS | SL5-GEOLOGY ACCOMMODATION DOCK DOORS | Coordinating work for completion. | GEOLOGY |  | IN PROGRESS |  |  | DEBORAH TERAO |  | Chris Pillen |  | Canceled | Canceled | FALSE |  |  | 2018-08-07 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000285 |  | 19P000285 | FALSE | CNAS | SL5-PAINT AND PATCH PI OFFICE |  | ENTOMOLOGY | 269 |  | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-17 | [6 empty] | N/A |  | Enrico Baez | DND 7/25/18: Emailed R. Veloz advising work order is closed; upon completion of the scope review, Ron to work with Zee for a Project Number to be created. | YES | FS | 0 | 2018 | 2019-01-16
19P000286 |  | 19P000286 | FALSE | CHASS | SL5-FACULTY OFFICES: TOUCH UP PAINT |  | HUM & SOC SC | 2005 |  | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000287 |  | 19P000287 | FALSE | CNAS | SL5-URGENT: PAINT SHOP TO PATCH AND PAINT | Complete as of 10/22/18. | MAT SCI ENGR | 229 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | HONG XU |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-19 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000288 |  | 19P000288 | FALSE | CNAS | SL5-COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS |  | COLLEGE BLDG NO | 202 |  | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-19 | [6 empty] | N/A |  | Dan Lerman | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with Jason | YES | FS | 0 | 2018 | 2019-01-16
19P000291 |  | 19P000291 | FALSE | CNAS | SL5-MSE HELIUM RECOVERY SYSTEM | Work has been completed; FS teams verifying completion and quality check of work. | MAT SCI ENGR | 205 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 9 | HOLD | FALSE |  |  | 2017-07-24 | [6 empty] | 12/14/18, DL; This project is 100% Complete……DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB - spoke with Mayela who is determining status within her dept…. DL, 11/7/18; This project is complete but I need to conduct a final site visit….. |  | Enrico Baez | 4/24/18 EB-scoped. Move screen, correct non-compliant electrical issues, remove&discard overhead projector bracket, relocate heat det. Add switched outles. Plans are needed because we are relocating a heat detector | YES | FS | 0 | 2017 | 2019-01-16
19P000292 |  | 19P000292 | FALSE | CNAS | SL5-GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER | Site vist completed; identifying a feasabile site location for work. | GEOLOGY |  | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 18 |  | FALSE |  |  | 2018-08-10 | [6 empty] | 1/15/19, DL; Plans are approved, we will start the work in the next two weeks……12/14/18, DL; Plans are almost complete. We will schedule the work after plans are approved……DL, 11/7/18; Conducted site visit with Chris P. We need to confirm a feasable site location before we move forward with the work…. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000293 |  | 19P000293 | FALSE | ITS | SL5-PAINT ESTIMATE REQUEST | Canceled by Customer 10/24/18 | TELEPHONE |  | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-21 | [6 empty] | n/a |  | Enrico Baez | 9/4/18 EB-This Project has been started. Monitors in place. Just need to run electrical. Dan aware. Refer to WO 19P000053. It asks for the same thing. Will request to close this and let Angela know. | YES | FS | 0 | 2018 | 2019-01-16
19P000295 |  | 19P000295 | FALSE | ATHLETICS | SL5-PATCH & PAINT | FS to coordinate with client to schedule work for completion. | ATH DANCE | 50B | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 12 | 18 - 19 | FALSE |  |  | 2018-09-12 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | Duplicate to project 19P000030. Canceling project. | N/A | FS | 0 | 2018 | 2019-01-16
19P000296 |  | 19P000296 | FALSE | CAMPUS | SL5-MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB | Plans and permits to be developed for this project. | MAT SCI ENGR |  | PLAN DEVELOPMENT/CHECK |  |  | MILLY PAREDEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-09-25 | [6 empty] | 12/14/18, DL; Rendering has been given to Ron R. Ron will present to Gerry for review and approval. Once approved, we will proceed with plans and permits……DL, 11/7/18; Need to find out where this project stands in regards to the priioroity….. Site vist was conducted and scope of work is verified. Plans and permits will be required for the work….. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000298 |  | 19P000298 | FALSE | CNAS | SL5-SPIETH - PREP LAB FOR FACULTY SEARCH |  | SPIETH | 1363 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-09-26 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000299 |  | 19P000299 | FALSE | CNAS | SL5-SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 |  | SPIETH | 3378 |  | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000300 |  | 19P000300 | FALSE | CHASS | SL5-HUM & SOC SC--URGENT: PAINT AND PATCH WALLS |  | HUM & SOC SC | 4403 |  | Milagros Pena | Cindy Williams | ANDREA HERAZ |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-26 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000301 |  | 19P000301 | FALSE | CNAS | SL5-SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH |  | SCIENCE LAB1 | 214 |  | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-27 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000302 |  | 19P000302 | FALSE | BCOE | SL5-STUDENT SERV - INSTALL TV MOUNT AND RUN ELECTRICAL |  | STUDENT SERV | 1227 |  | Christopher Lynch | Maggie Souder | MALLORIE HARDCASTLE | [5 empty] | FALSE |  |  | 2018-09-27 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000306 |  | 19P000306 | FALSE | CHASS | SL5-HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 |  | CHASS INT N | 4017 |  | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-01 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000307 |  | 19P000307 | FALSE | BAS | SL5-LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK | Scheduled work with trades anticipated completion December 2019. | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 5 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000308 |  | 19P000308 | FALSE | BAS | SL5-ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK | Scheduled work with trades anticipated completion December 2019. | ABER INVER |  | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5-RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 7 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18; Recharge work? This is a common area…. |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000311 |  | 19P000311 | FALSE | ATHLETICS | SL5-ATHLETICS KEY LESS ENTRY ROOM 150 |  | ATH DANCE | 150 |  | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN | [5 empty] | FALSE |  |  | 2018-10-02 | [8 empty] | Enrico Baez | Blackout curtain needs to have a better way of being secured. Talked to Cory about fabricating a new curtain rod. 7/6/2018EB assigned to sheetmetal shop F-LNH | YES | FS | 0 | 2018 | 2019-01-16
19P000312 |  | 19P000312 | FALSE | BCOE | SL5-VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP |  | STUDENT SERV | 1227 |  | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Dan Lerman | DL, 4/29/18; Pasted from work order;I"nstall a glass window 28x9 on office door in WEBBER, Room 1143. | YES | FS | 0 | 2018 | 2019-01-16
19P000313 |  | 19P000313 | FALSE | CHASS | SL5-HUMANITIIES SOCSCI - PATCH HOLES & PAINT - |  | HUM & SOC SC | 1203 |  | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Enrico Baez | DD 7/17: Requested Enrico verify complete customer did not prioritize and noted work was done. 8/7/18-Conducted site visit-do not recommend location for TV due to potential damage from barn door type window screen. 8/15/18 emailed Tara Bathol that desired location for TV not recommended. Requested alternate location. 08/22/18 Ron V. Spoke with Tara. Tara confirmed the requestor cancelled the TV mounting bracket request after conversation with Enrico | NO | FS | 0 | 2018 | 2019-01-16
19P000314 |  | 19P000314 | FALSE | CHASS | SL5-HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 |  | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000316 |  | 19P000316 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL | Anticipated completion mid November | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 2018-10-03 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000316 |  | 19P000316 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL | Anticipated completion mid November | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…Anticipated completion 11/9/18. |  | Ron Veloz | 10/17/18: RV: Drawings are on server folder. 10/08/18 RV: Spoke with Brandon B. Brandon will submitt BKM drawings via permit request through PD&C. 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon. Walked project with Brandon. SOW to install two each dedicated 120v/20a cicuits for new modular furniture one whip at each end of the office down the wall and one to two data drops overhead down wall. | YES | FS | 0 | 2018 | 2019-01-16
19P000317 |  | 19P000317 | FALSE | BAS | SL5-HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 |  | PENTLAND A |  |  | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER | [5 empty] | FALSE |  |  | 2018-10-03 | [8 empty] | Ron Veloz | 01/10/19 O-RVL: Emailed Dominic Salazar on locker delivery ststus. Pending follow up call from customer to inform FS on delivery of lockers. 11/08/18 RV: Visited site existing lockers in place and in use. Will follow up with the requestor for locker delivery status to schedule. RV Spoke with Brandon Barbosa. Deparment will purchase lockers. 11/08/18 RV: Received email from Domonic Salazar on 10/25 Lockers are expected to arrive. | YES | FS | 0 | 2018 | 2019-01-16
19P000318 |  | 19P000318 | FALSE | CNAS | SL5-GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE |  | GEOLOGY | 420 |  | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A | 2018-10-29 | Ron Veloz | 01/11/19 O-RVL: Qualifying quote to verify proper components from door operator vendor expecting reply soon. 12/14/18 O-RVL: Received Quotes for Auto door operator and Access controls this week. RV to provide update & quotes to to Dan Lerman. Moving status to "Que to Start" on Minor Ren List & updating Project Folder. 11/07/18 O-RVL: Walked site with Access Control vendor 10/31/18 O-RVL: Walked site with Door Op vendor 10/29/18 O-RVL: Scope was Completed. RV to schedule job walks with Vendors. 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon | YES | FS | 0 | 2018 | 2019-01-16
19P000319 |  | 19P000319 | FALSE | CNAS | SL5-ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB |  | ENTOMOLOGY | 139 |  | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A | 2018-10-17 | Ron Veloz | 10/17/18 O-RVL: Remove one lower cabinet, Install a new corbel below to support the counter, install new carpet square or create an accent border if carpet tile is obsolete. Install new rubber base | YES | FS | 0 | 2018 | 2019-01-16
19P000322 |  | 19P000322 | FALSE | BCOE | SL5-CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT |  | CHUNG HALL | 103 |  | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-05 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000324 |  | 19P000324 | FALSE | CNAS | SL6--SPIETH ASSESS AIR VENT OR PURIFIER FOR LAB ROOM |  | SPIETH | 1312 |  | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-10-05 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000325 |  | 19P000325 | FALSE | CNAS | SL5-BATCHELOR HALL -REMOVE GLASS PANE FROM ENTRY AREA |  | BATCHELOR | 1140F |  | Kathryn Uhrich | Deborah McWilliams | KATHY REDD | [5 empty] | FALSE |  |  | 2018-10-08 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000326 |  | 19P000326 | FALSE | VC-UNIV.ADV. | SL5-HINDERAKER - PATCH & PAINT |  | HINDERAKER | 1136 |  | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-08 | [6 empty] | N/A |  | Ron Veloz | Will Meet with Chris Pillen on 08/23/18 to review notes by C.P. on FAMIS. 08/23/18-RV: Followed up with Chris P for update on the work request notes. Recommended to contact Brandon to procure a local vendor. 08/24/18-RV spoke with Brandon Barbosa to determine a plan to complete the request and will pursue pricing and oversee the installation. 08/27/18 RV: Update: Brandon will PM the project on his own. 09/19/18: UPDATE-CANCELLED BY Brandon. See notes above. | YES | FS | 0 | 2018 | 2019-01-16
19P000336 |  | 19P000336 | FALSE | BAS | SL5-EXCESS-CORP YARD--REMOVE INSIDE FENCE AND INSTALL DIVIDER |  | PHYS PL STOR |  |  | Gerry Bomotti | Georgianne Carlson | AMY EVERETT | [5 empty] | FALSE |  |  | 2018-10-10 | [8 empty] | Enrico Baez | 5/1 EB Convert two wet labs into offices. Same as Webber 2278. Abate floor, demo all cabinets, remove plumbing, patch & paint. Carpet tile. Equipment comes out. Awating Provost, Sheryl Murdoch and Bob Williams approval….. 7/11/18 EB-Per Brandon Barbosa project will be cancelled | YES | FS | 0 | 2018 | 2019-01-16
19P000337 |  | 19P000337 | FALSE | CHASS | SL5-PSYCHOLOGY MULTIPLE REQUESTS IN 3210 PSYCHOLOGY1 |  | PSYCHOLOGY1 | 3210 | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS | [5 empty] | FALSE |  |  | 2018-10-11 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000338 |  | 19P000338 | FALSE | VC-STU.AFF. | SL5-STUDENT SERV- TESTING ROOM MIRRORS |  | STUDENT SERV | 1213 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Brian Haynes | Cathy Eckman | LINDA KELLEY | [5 empty] | FALSE |  |  | 2018-10-12 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000340 |  | 19P000340 | FALSE | CNAS | SL5-PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE |  | SKYE HALL | 349 |  | Kathryn Uhrich | Deborah McWilliams | VICTORIA AVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-12 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19P000341 |  | 19P000341 | FALSE | CNAS | SL5-PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL |  | PIERCE |  |  | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-12 | [6 empty] | N/A |  | Dan Lerman | Added by customer on prioritization; timeline and scope tbd. 4/25 EB emailed Christina to schedule site visit. No work order Luis to submit Google doc. To A&E sevral trades invlved. DND 6/13 Project rescoped and priorities adjusted per meeting between Dan and Luis Alvarez. | YES | FS | 0 | 2018 | 2019-01-16
19P000346 |  | 19P000346 | FALSE | CNAS | SL5-I&Q--PAINTING ROOMS IN THE I&Q |  | EAST I&Q FAC |  |  | Kathryn Uhrich | Deborah McWilliams | IMAD BAYOUN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty |  |  | FS | 0 | 2018 | 2019-01-16
19P000347 |  | 19P000347 | FALSE | CNAS | SL5-SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT |  | SPIETH | 3320 |  | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty |  |  | FS | 0 | 2018 | 2019-01-16
19P000348 |  | 19P000348 | FALSE | GSOE | SL5-SPROUL REMOVE ILLUMINATED SIGNS |  | SPROUL | 1206 |  | Thomas Smith | Sally Tavizon | ENRICO BAEZ | [5 empty] | FALSE |  |  | 2018-10-17 | [7 empty] | 2018-10-09 | Enrico Baez | 10/9/18 EB Sent Luis email, copied Mont too. Project will bw $25k-$30K. Asked Luis if we are to proceed. 10/15/18 E.Baez conducted site visit, Client requested cost estimate to construct 2-3 "huddle" Spaces with sound proof walls. Requires alterations to HVAC ducting, full height walls with doors, fire sprinkler additions, smoke detection additions, lighting changes. emailed Luis estimated cost of $25,000. 12/20/18 D. DINH: Spoke with customer, Luis Alvarez, and the project request has been modified to patch & paint and replacement of one ceiling tile. Customer to work with BKM to fulfill the wall partition request portion of the project. | YES | FS | 0 | 2018 | 2019-01-16
19P000349 |  | 19P000349 | FALSE | BCOE | SL5-WCH--REPAIR DAMAGE FROM RMOVAL OF WIRE MOLDING |  | CHUNG HALL | 103 |  | Christopher Lynch | Maggie Souder | RICHARD BAIN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-17 | [6 empty] | N/A |  | Enrico Baez | 4/24/18 EB- Per Christina Wong, no longer needed……DL, 5/5/18; Project is canceled per notes DND 6/13; Project reopened and not canceled per conversation with customer. Complete scope review and speak with Luis Alvarez DND 8/20/18: submitted Google form for Project to be reviewed by IRT. 8/19/18 Met with Louis Alvarez. Asked for measured plans from BKM for wall layout and dimensions. emailed again on 9/6 asking for draws. Still waiting for BKM to provide drawings. 9/21/18 Dinh - placed on hold until customer provides BKM drawings. Enrico please manage follow up. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. On shared drive can be found in file. 10/30/18 EB-Cancelled by Customer | YES | FS | 0 | 2018 | 2019-01-16
19P000350 |  | 19P000350 | FALSE | CHASS | SL5-PSYCHOLOGY --MISC WORK IN ROOMS 3121 AND 11133 |  | PSYCHOLOGY1 |  |  | Milagros Pena | Cindy Williams | TOYA ADAMS | [5 empty] | FALSE |  |  | 2018-10-17 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000353 |  | 19P000353 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT-2348 |  | OLMSTED | 2340 |  | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-19 | [6 empty] | N/A |  | Dan Lerman | 7/9 EB-Spoke with Dan, he has already scoped this. | YES | FS | 0 | 2018 | 2019-01-16
19P000354 |  | 19P000354 | FALSE | SOM | SL5-WEBBER 2130A-PAINT CHERI'S NEW OFFICE |  | WEBBER | 2130A |  | Deborah Deas | Brandon Barbosa | DOMINIC SALAZAR |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-19 | [6 empty] | N/A |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000355 |  | 19P000355 | FALSE | CHASS | SL5-HYDRATION STATION FOR THE SECOND FLOOR WATKINS |  | WATKINS | 2122D |  | Milagros Pena | Cindy Williams | CYNTHIA REDFIELD | [5 empty] | FALSE |  |  | 2018-10-22 | [9 empty] | Duplicate to 18W015691 | NO | FS | 0 | 2018 | 2019-01-16
19P000356 |  | 19P000356 | FALSE | CHASS | SL5-PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT |  | HUM & SOC SC | 4401 |  | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-24 | [6 empty] | N/A |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-01-16
19P000357 |  | 19P000357 | FALSE | CHASS | SL5-PATCH AND PAINT WALLS, TIME SENSITIVE |  | HUM & SOC SC | 1302 |  | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-25 | [6 empty] | N/A |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-01-16
19P000358 |  | 19P000358 | FALSE | CNAS | SL5-GEOLOGY - ACCOMMODATION REQUEST |  | GEOLOGY |  | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA | [5 empty] | FALSE |  |  | 2018-10-26 | [8 empty] | Enrico Baez | 5/16/18 EB conducted site visit. 5/22/18 EB appliances dented, vaccum pump not on site. 6/19/18 emialed Chrystal to see if appliance have been replaced. 7/16/18 emailed Chrystal Jimenez asking for update. 8/7/18 EB Replacement appliances | YES | FS | 0 | 2018 | 2019-01-16
19P000360 |  | 19P000360 | FALSE | CNAS | SL5-GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING |  | GEOLOGY | 1444 |  | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000361 |  | 19P000361 | FALSE | CHASS | SL5-OLMSTED-PATCH & PAINT/REPLACE CARPET |  | OLMSTED |  |  | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000362 |  | 19P000362 | FALSE | CHASS | SL5-PATCH & PAINT/REPLACE CARPET (HALLWAY) |  | OLMSTED |  |  | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A | 2018-09-27 | Enrico Baez | 9/13/18 EB-emailed crystal Jimenez to schedule site visit. 9/19/18 EB-Scheduled site visit for 9/20. 9/29/18 EB- install keyless entry system on two doors. 10/15/18 EB-sent Aaron Seitz approx. cost of project. Awaiting respone to determine funding. | YES | FS | 0 | 2018 | 2019-01-16
19P000364 |  | 19P000364 | FALSE | CHASS | SL5-PATCH AND PAINT |  | CHASS INT S | 3106 |  | Milagros Pena | Cindy Williams | FRANCESCA MOREIRA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-30 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000365 |  | 19P000365 | FALSE | FAC-PLNG-DESIGN-CONST | SL5-FS ANNEX A-REMODEL CONFERENCE ROOM |  | FS ANNEX A |  |  | Susan Marshburn | Da Lan Dinh | DALAN DINH | [5 empty] | FALSE |  |  | 2018-10-31 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000366 |  | 19P000366 | FALSE | FAC-PLNG-DESIGN-CONST | SL5-FACILITES SERVICES ADMIN-BREAKROOM & RECEPTION REMODEL |  | CORP B |  |  | Susan Marshburn | Da Lan Dinh | DALAN DINH | [5 empty] | FALSE |  |  | 2018-10-31 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19P000367 |  | 19P000367 | FALSE | CNAS | SL5-SCILAB 1 0211- PATCH & PAINT |  | SCIENCE LAB1 | 211 |  | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-31 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19P000369 |  | 19P000369 | FALSE | CNAS | SL5-PIERCE - PAINT IS PEELING OFF WALLS |  | PIERCE | 3341 |  | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-11-01 | [6 empty] | N/A |  | Enrico Baez | EB 3/20 scoped project and annotated on FAMIS. DL, 5/5/18; Pased from wo:Noted changes to original request.Add counter windows onto end of the current SHS front desk main counter (2 windows/stations).2. Close exam room that is open to hallway with a wall (behind room 210).3. Covert 100A to phlebotomy room with a hallway access doorway.4. Open wall to reconfigure to allow space for lab manager. | YES | FS | 0 | 2018 | 2019-01-16
19P000370 |  | 19P000370 | FALSE | ENROLLMENT MANAGEMENT | SL5-PATCH AND PAINT CAMPUS TOURS |  | STUDENT SERV | 1137 |  | LaRae Lundgren | TBD | ELIZABETH TATUM |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-11-01 | [6 empty] | N/A |  | Enrico Baez | Cut wall between rooms 414 and 401, Case and trim opening, install carpet in- DL, 5/10/18; Gloria Vera is the contact; 827-5532 | YES | FS | 0 | 2018 | 2019-01-16
19P000371 |  | 19P000371 | FALSE | CHASS | SL5-URGENT PATCH AND PAINT IN CHAIR'S OFFICE |  | HUM & SOC SC | 1213 |  | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-11-05 | [6 empty] | N/A |  | Enrico Baez | 1/31/18 EB-Scoped site with Chris P. on 10/30/2017. Spoke with Gloris who thought still CPMS. Scope includes removing doors, adding teller counters, moving corridor wall…..Dl, 5/3/18; Dan, Chris, ron and Gloria will meet and re-scope the work…... | YES | FS | 0 | 2018 | 2019-01-16
19P000375 |  | 19P000375 | FALSE | CHANCELLOR | SL5-PATCH AND PAINT HOLES |  | SKYE HALL | 365 |  | Kim Wilcox | Karim Zahedi | FELECIA GARRETT |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-11-07 | [6 empty] | N/A |  | Enrico Baez | 11/29/18 EB Met with Design West and HUB staff. Conducted site visit. Waiting for recommendations from Design West. 7/6/18 EB-emailed Brendan to schedule site visit. 7/11/18 EB- Site visit schedyed for 7/12/18 7/16/18 Conducted site. Customer wants to have SEP metered for all food vendors. Requested electical power plans from Gunther. 8/7/18 Contacted Design West for proposal of feasibility study. 8/15/18 Advised Brendan Obrien to submit request to CPMS as this work will not be self performed. Sent Brendan copy of proposal for sight assessment. | YES | FS | 0 | 2018 | 2019-01-16
19P000377 |  | 19P000377 | FALSE | CNAS | SL5-BG - SCHNEIDER HOUSE DRIVEWAY GATE |  | SCHNEIDER HOUSE |  |  | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV | [5 empty] | FALSE |  |  | 2018-11-08 | [11 empty] | FS | 0 | 2018 | 2019-01-16
19S000833 |  | 19S000833 | FALSE | SOM | Add access control to entry doors | Canceled request per conversation with client; customer to coordinate for a contractor to complete project. | HECKMAN ICEM | Entry Doors | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | Canceled | 2 | FALSE |  |  | 2018-07-17 | [7 empty] | 2018-01-23 | Enrico Baez | 1/23/18 EB-site walk, scope enter in FAMMIS. 4/2 MN: Enrico to obtain an FAU. 1/23/2018 E.Baez conducted job site walk. Request is for lighting installations above entries to store front and kitchen on East side of building and additional lighting above outside locker on loading dock. Manny has lights that can be re-used. Want estimate only. Need to include Campu Architech too...... | YES | FS | 0 | 2018 | 2019-01-16
19S004271 |  | 19S004271 | FALSE | ATHLETICS | SL5-ADDITION OF KEYLESS ENTRY ON 1 - 2 DOORS | FS to coordinate with customer to scope the work. | ATH DANCE |  | IRT REVIEW | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 8 |  | FALSE |  |  | 2018-09-12 | [6 empty] | ?????? |  | Enrico Baez | EB 5/23/18. Conducted site visit. Request is for adding walls to interior spaces 353F, 381 and 377. Will impact A/C and fire protection. Still waiting for a firm plan from customer. | YES | FS | 1899-12-31 | 2018 | 2019-01-16
19W002419 |  | 19W002419 | FALSE | ITS | SL5-ITS CENTER - INSTALL CARD READER ACCESS |  | ITS CENTER | 161 |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-08-09 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19W002930 |  | 19W002930 | FALSE | CHASS | HOLD - SL5-PATCH HOLES & PAINT - HUMANITIIES SOCSCI | Complete as of 11/8/18 | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-08-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19W003012 |  | 19W003012 | FALSE | CNAS | SL5-FIX RESTROOMS (PAINT AND FLOORS) | FS to coordinate with client to schedule work for completion. | CHAPMAN | 5 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 51 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-01-16
19W003050 |  | 19W003050 | FALSE | VC-RED | SL5-SPEITH HALL - PATCH & PAINT HOLE IN WALL | Complete as of 10/10/18 | SPIETH | 0359A | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19W006811 |  | 19W006811 | FALSE | VC-STU.AFF. | SL5-HUB 353--PATCH AND PAINT WALL |  | HUB | 353 |  | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-26 | [6 empty] | N/A |  |  |  |  | FS | 0 | 2018 | 2019-01-16
19W007474 |  | 19W007474 | FALSE | CNAS | SL5-BG - RAILROAD TIE WALLS |  | BOTANIC GARDENS |  | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV | [5 empty] | FALSE |  |  | 2018-11-07 | [11 empty] | FS | 0 | 2018 | 2019-01-16
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Roofing - Spieth Hall/LSP | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. |  |  | Contracts ready to be awarded, pending Lead/ACM survey. | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 432510 |  | 2016-02-25 | Re-bid | 2019-06-01 | 2019-07-01 | [8 empty] | PD&C | 0 | 2016 | 2019-01-16
3035b | 3035b |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Roofing - Olmstead Hall | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. 112010 project budget is $456,163.00. Estimated construction cost is $425,680.00. Bidding 8/8/2017. |  |  | Revise scope and rebid. | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 383112 |  | 2016-02-25 | Re-bid | 2019-06-01 | 2019-07-01 | [5 empty] | Paul Ditty | N/A | N/A | PD&C | 0 | 2016 | 2019-01-16
2245 | 2245 |  | FALSE | VC-UNIV.ADV. | Campus Directory & Blade Signs | Remove and replace campus directories at strategic locations throughout the campus. |  |  | Pre Design | Peter Hayashida | Naysia Caldwell | Margene Mastin-Schepps |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2014-03-27 | Project Approval & Funding | 2019-08-05 | 2019-09-30 | [8 empty] | PD&C | 0 | 2014 | 2019-02-01
2353 | 2353 |  | FALSE | CNAS | Natural Reserves-Sweeney Granite Mountain | This project will add structurally independent facilities for an administration building and researcher housing to provide meeting/office space and short term sleeping quarters. Additionally, the existing laboratory building and staff residence will be extensively renovated. High priority is focused on high insulation values, high wind resistance, rodent proofing, and pursue as much passive cooling and heating as possible with an eye toward low maintenance and high durability. Both new construction and renovation projects are to be sealed to prevent rodent intrusion. The new structures must withstand the harsh environment of extreme temperatures and very high winds. All site improvements shall be done with minimal disturbance to the desert environment. The overarching goal of the project is to provide a sustainable structure that respects its environment and is low maintenance while using best practice design standards. |  |  | Construction has resumed at the remote granite mountain location in January 2019, with work focused on modifications to the Existing Allison Center Lab, and Staff Residence. Construction is expected to be completed in these buildings in March of 2019 | Kathryn Uhrich | Deborah McWilliams | Jim Andre, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2545500 |  | 2015-11-23 | Complete Construction | 2019-01-14 | 2019-11-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
2359 | 2359 |  | FALSE | SOM | SOM - Research Bldg. BSL-3 | Reconfiguration and reconstruction of the existing BSL-3 suite on the 3rd floor. |  |  | Finalizing commissioning & air balance | Deborah Deas | Brandon Barbosa | Rebeccah Goldware |  | Mihai Gavan | 1 |  |  | FALSE | 2730000 |  | 2016-05-19 | Notice of Completion | 2016-10-01 | 2017-11-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
2368 | 2368 |  | FALSE | PLANNING & BUDGET | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | Engineering documentation-civil | Gerry Bomotti | TBD | Katie Sanchez |  | Dave Bomba | 9 |  |  | FALSE | 2600000 |  | 2016-05-19 | Complete CEQA Documentation | 2019-04-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
2508 | 2508 |  | FALSE | BAS | Barn Expansion | Project 950493 Barn has completed the DPP process and we are now adding this to CPMS to capture expenses related to the Program Process which occurred in FY11-12 and FY12-13. Please move all expenditures from A01233-70003-76 Cost Center to JR142 to a plant account. |  |  | In construction | Gerry Bomotti | Georgianne Carlson | Susan Marshburn |  | D.Hecht/J.Franklin | 4 |  |  | FALSE | 28700000 |  | 2013-07-05 | Complete Construction | 2018-06-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2013 | 2019-02-01
2671 | 2671 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Elevator Modifications - Various Buildings | Provide Vertical Transportation Consulting, Mechanical, Electrical, Fire Alarm and Architectural/Structural Construction document design and specifications for the modernization of two (2) elevators at Webber and Watkins buildings which is included in the base design and one (1) elevator at the Entomology Museum is included as an add alternate. |  |  | Permit review process | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 99 |  |  | FALSE | 596011 |  | 2016-01-05 | Final Approval of CD's | 2019-07-01 | 2019-12-31 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Rivera Library Arches/Arcade Repair | Paint and replace roof. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Jason Espinoza | 99 |  |  | FALSE | 240000 |  | 2016-05-06 | Award Contract | 2019-04-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Bourns Hall Fire Alarm System Replacement | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | Approval of 100% CD's | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 99 |  |  | FALSE | 600000 |  |  | Augmentation Approval | 2019-04-01 | 2019-09-30 | [8 empty] | PD&C | 0 | 1900 | 2019-02-01
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. |  |  | On hold until MRB1 is complete. | Tamica Smith Jones | Joseph Erbland | Joe Erbland |  | Mihai Gavan | 3 |  |  | FALSE | 0 |  | 2014-04-10 | To be coord. with Rec Mall work | [10 empty] | PD&C | 0 | 2014 | 2019-02-01
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Initial planning discussions have begun with SOBA. | Yunzeng Wang | Angela Chang | Laurie Gustafson |  | Blythe Wilson | 2 |  |  | FALSE | 350000 |  | 2016-12-15 | Develop RFQ | [10 empty] | PD&C | 0 | 2016 | 2019-02-01
2747 | 2747 |  | FALSE | PALM DESERT | Heckmann Center - Landscaping (Donor Orchard) | UCR Palm Desert would like to replace the current turf grass with water-wise, sustainable landscaping. In return for the opportunity to use a “living laboratory” classroom for training, UC Cooperative Extension Master Gardener program has agreed to collaborate with UCR to revise and sustain the landscaping. The first phase will be to create an orchard to highlight UCR’s contributions to agricultural research in the Coachella Valley. The orchard will be located at the entrance to the Heckmann building, north of the walkway. UCR Physical Plant/Grounds to provide estimate for: • Project oversight • Project plan and drawings • Organic material to add to soil • Irrigation materials and installation • Edging for path • Weed cloth • Decomposed granite with stabilizer for ground cover • Decomposed granite with stabilizer for pathway • Concrete pad for art including bolting apparatus • Arbor for grapes • Flow system-fertigation • All other labor and materials other than kiosk, plant signage, turf and tree removal (current landscape maintenance vendor can remove) and plant materials and plant installation | HECKMAN ICEM |  | In Programming |  |  | Mike Lawrence |  | Scott Donnell | 2 |  |  | FALSE | 13800 |  | 2014-08-18 | RFQ Design | [10 empty] | PD&C | 0 | 2014 | 2019-02-01
2774 | 2774 |  | FALSE | PLANNING & BUDGET | Highlander Hall Demolition | Demolition of the Highlander Hall Building |  |  | Nearing Completion | Gerry Bomotti | TBD | Blythe Wilson |  | Scott Donnell | 99 |  |  | FALSE | 2127000 |  | 2015-01-22 | Project Close-out | 2018-08-01 | 2019-02-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
2829 | 2829 |  | FALSE | VC-STU.AFF. | SRC South - New Storage Building | New storage building immediately south of SRC South Pool Building; approximately 20' x 40'; one roll up door and one standard door; electrical power required - number of outlets to be defined in design; concrete walkway and door pads required; non-potable water may be required if quick couplers are not available in nearby landscaping; please see attachment for location: approximately at gridlines T and 9.4 - dotted outline of building is labeled "FUTURE STORAGE" - located immediately south of the SRC POOL EQUIPMENT BUILDING. | SRC SOUTH |  | Project is currently on-hold. | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Mihai Gavan | 2 |  |  | FALSE | 0 |  | 2015-01-23 | Coordinate with MRB Logistics | [10 empty] | PD&C | 0 | 2015 | 2019-02-01
2839 | 2839 |  | FALSE | PLANNING & BUDGET | Multidisciplinary Research Building | External financing provided for this project. Total approved budget is $150,000,000. Confirmed per CPMX and BEA#978864 Xfer Tax Exemp Comm Paper. Funding received 7/25/2016. |  |  | Certificate of Beneficial Occupancy 9.28 | Gerry Bomotti | TBD | Jon Harvey |  | Mihai Gavan | 6 |  |  | FALSE | 156405000 |  | 2015-04-01 | Substantial Completion | 2016-07-01 | 2018-09-28 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
2860 | 2860 |  | FALSE | BCOE | Bourns B0152 - Fume Hood | Please investigate feasibility and provide an estimate for installation of ductwork and a four foot fume hood sufficiently equipped and sized to include an exhaust line for a 2-standard sized cylinder gas storage cabinet. Location should be recommended based on proximity of existing building/floor exhaust ductwork. Should it become necessary, the size of the gas cabinet may be considered for reduction. | BOURNS |  | In Close-out | Christopher Lynch | Maggie Souder | Margaret Souder |  | Scott Donnell | 1 |  |  | FALSE | 0 |  | 2015-04-01 | ASHRAE & Certification | 2018-01-01 | 2018-05-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
2868 | 2868 |  | FALSE | BAS | West Lothian Elevator Renovation |  |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 34 |  |  | FALSE |  |  | 2015-04-08 | Bidding | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
2899 | 2899 |  | FALSE | PLANNING & BUDGET | Pierce Hall Improvements | Replacement of Mechanical, Plumbing and Electrical Infrastructure | PIERCE |  | In Construction | Gerry Bomotti | TBD | Jon Harvey |  | Dave Bomba | 8 |  |  | FALSE | 38560000 |  | 2015-08-06 | Fencing and Staging | 2019-01-01 | 2019-12-07 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
2900 | 2900 |  | FALSE | PLANNING & BUDGET | Batchelor Hall Systems Renewal | <div>Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. Project proposes: *Replace heating, ventilation, and air condition system due to inefficiency, and compromised air quality &nbsp;Upgrade electrical service to 480/277 in order to allow higher intensity research equipment. *Upgrade/replace plumbing systems due to condition, and inadequate water treatment. *Upgrade fire life safety system (fire alarm) due to none code compliance. *Reconfigure laboratory space to improve research space usage and efficiency, work will be phased to limit user impact, and funding availability. Classification of work, Heating and cooling systems, Ventilation systems, Energy management systems, Primary and emergency electrical systems, Fire alarm and protection systems, De-ionized water and reverse osmosis systems, Hazardous materials abatement, Reconfiguration of research and laboratory and related spaces</div> | BATCHELOR |  | A&E, CAS & EH&S working w/CNAS dean & dept chairs to establish a relo. plan | Gerry Bomotti | TBD | Sharyl Murdock |  | Rowan Reid | 4 |  |  | FALSE | 18179000 |  | 2015-12-15 | CM at Risk Selection | 2019-09-01 | 2021-11-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
2916 | 2916 |  | FALSE | CAP.PROG. | Solar Greenhouse | Construction of a solar powered greenhouse. |  |  | Installing solar components | TBD | Sharyl Murdock | Matt Barth |  | Scott Donnell | 99 |  |  | FALSE | 174000 |  | 2015-08-04 | Award Contract | 2019-03-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
2952 | 2952 |  | FALSE | CAP.PROG. | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | TBD | Sharyl Murdock | Jon Harvey |  | Dave Bomba | 19 |  |  | FALSE | 23308000 |  | 2015-09-11 | Completion of phase one | 2019-01-02 | 2021-04-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
2970 | 2970 |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan - Phase 2 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | TBD | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 17 |  |  | FALSE | 2842000 |  | 2015-12-02 | Complete Construction | 2018-09-26 | 2019-06-30 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
2974 | 2974 |  | FALSE | SOM | SOM Research Building - 1st Floor Fit-Out | Buildout the 1st Floor of School of Medicine Research Building, a space of approximately 17,600 square feet. The construction includes wet laboratories, laboratory support spaces, offices and related support space. Work consists of, but not limited to the following: demolition of existing improvements, addition/alterations of walls, installation of new fume hoods, sinks, safety showers and eyewash stations, alterations/additions to the mechanical, electrical, plumbing, fire life safety, fire suppression, telecommunication and audio/video systems, as specified in the Construction Documents. |  |  | Working on punchlist items. | Deborah Deas | Brandon Barbosa | Blythe Wilson |  | Mihai Gavan | 99 |  |  | FALSE | 9600000 |  | 2015-10-30 | Final Completion / NOC | 2017-10-01 | 2018-10-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
3005 | 3005 |  | FALSE | CAP.PROG. | Batchelor Hall Interior Improvements | Interior renovation of public areas | BATCHELOR |  | Finalize Project Scope. Receive direction from VC. Awaiting Leadership approval. | TBD | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 14 |  |  | FALSE | 8837000 |  | 2016-02-02 | CM at Risk Selection | 2019-09-01 | 2021-10-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3052 | 3052 |  | FALSE | SOM | SOM Trailer Expansion | Replace the (2) modular units with one 96' x 60' building and provide access from the SOM-ED building via concrete ramp; Re-vamp the entire site for accessibility. Signed Major Cap Approval for $150k augmentation received 10/25/17 - total project $2,250,000. |  |  | Punch list needs to be addressed | Deborah Deas | Brandon Barbosa | Sharyl Murdock |  | Dave Bomba | 99 |  |  | FALSE | 2250000 |  | 2016-03-07 | Install Code Blue Phone | 2017-08-01 | 2018-02-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3060 | 3060 |  | FALSE | CHASS | CHASS Intl N. - Paint 3rd Floor | Paint and patch the following CHASS INTN rooms to existing color: 3036 3038 3042 3046 3050 3049 3047 3033 3033B 3025 3021 3019 3015 3013 3011 3002 3008 3012 3014 3016 3018 3020 3022 Hallway outside of 3033 Hallway to main entrance to floor Hallway outside 3005 | CHASS INT N |  | Project on Hold | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2016-05-20 | On Hold | [10 empty] | PD&C | 0 | 2016 | 2019-02-01
3064 | 3064 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Botanic Gardens Basin Silt Removal | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | BOTAN INFO C |  | In Design | Susan Marshburn | Da Lan Dinh | Toshio Ishida |  | Dave Bomba | 48 |  |  | FALSE | 110000 |  | 2016-04-20 | Obtain Agency Permits | 2019-05-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3066 | 3066 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Chapman Hall Roof Replacement | Roof replacement. | CHAPMAN |  | In Close-out | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 50 |  |  | FALSE | 1010000 |  | 2016-04-06 | Complete Close-out | 2018-04-01 | 2018-08-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3101 | 3101 |  | FALSE | SoB | DM-Anderson Hall S&N - Maint+Restrm Remodel | Under 2014 Deferred Maintenance Funding Program, SoBA has been approved for interior upgrades to be completed up to $65,00. We were originally approved for $75,000 however, per Scott Donnell, $10,000 had already been used. We have requested a list of expenditures for SoBA upgrades under this $10,000. The following items need to be completed under this 2014DM funding in the priorities listed: 1. Anderson Hall South Women’s and Men’s Restrooms Remodel Requirements: Floor and wainscot tile require replacement and/or re-grouting, casework and associated lavatory fixtures and counter tops require refurbishment/placement, restroom partitions require re-painting/replacement. 2. Anderson Hall North Women’s and Men’s Restrooms – repair and touch up areas where ADA compliance changes were made. 3. Anderson Hall North & South Stairway Requirements: All stairways shall be reviewed for compliant contrasting top and bottom stair-tread indicators and all missing or loose anti-slip tread applications be repaired and/or replaced. Any other safety items as may be noted. Retile or carpet as needed. 4. Anderson Hall South Interior Painting to Common areas, both levels: Interior wall surfaces require patching and painting. 5. Anderson Hall North Interior Painting to Common areas, both levels and conference room 021: Interior wall surfaces require patching and painting. 6. Faculty Suite (Rm 158) – match common area tile (size of mud/dirt mat) to replace dirty carpet when first enter room 158. 7. Dean’s Suite (Rm 162) – new carpet. |  |  | The department would like to cancel the project | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 3 |  |  | FALSE | 65000 |  | 2016-05-09 | To be cancelled by Client | [10 empty] | PD&C | 0 | 2016 | 2019-02-01
3104 | 3104 |  | FALSE | PALM DESERT | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Programming |  |  | Zelda Glenn |  | Scott Donnell | 1 |  |  | FALSE | 22000 |  | 2016-05-12 | Design | [10 empty] | PD&C | 0 | 2016 | 2019-02-01
3110 | 3110 |  | FALSE | PLANNING & BUDGET | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded/never routed to the Dispatcher. 90% CD's completed. | Gerry Bomotti | TBD | Marianne Valenti |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | License Agreement Final Review |  | 2019-07-01 | [8 empty] | PD&C | 0 | 1900 | 2019-02-01
3119 | 3119 |  | FALSE | CAP.PROG. | Plant Growth Environment Facility | The campus has identified a need for modern plant growth and research support facilities, as documented in an April 2016 feasibility study that considered current and future needs for these types of facilities. The Plant Growth Environments Facility will complete construction late third quarter of 2019 to address this need. The project is expected to provide 40,000 gsf of greenhouses, head house, plant growth chambers and support spaces. Currently, the facility is envisioned as a two story structure with 20,000 of greenhouses occupying the upper level. The project delivery method is a design/build competition. |  |  | Design Build Proposal Awarded, design and construction contract execution has started | TBD | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 5 |  |  | FALSE | 1800000 |  | 2016-05-25 | Design-Build Proposal Evaluation | 2019-04-01 | 2020-08-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3120 | 3120 |  | FALSE | CAP.PROG. | Arts Walk Sculpture (Ext Campus Art Project) | Sculpture design concept - hiring a consultant to revise an artist design concept for a proposed outdoor art piece to be placed between the Arts building and the CHASS Interdisciplinary buildings. |  |  | A&E and CAS in discussions w/Artist re: design. | TBD | Sharyl Murdock | Uma Ramasubramanian |  | Jason Espinoza | 4 |  |  | FALSE | 1000000 |  | 2016-05-26 | Complete Construction | 2019-02-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3175 | 3175 |  | FALSE | CAP.PROG. | DM-Chilled Water Coils Multiple Buildings | Replace multiple leaking/degraded cooling coils across campus to prevent complete shutdown of building air handlers during the hot summer months. Buildings include: Student Services, Chemical Sciences, Genomics, Psychology, Entomology and MSE. |  |  | In Construction | TBD | Sharyl Murdock | Melissa Garrety |  | Scott Donnell | 99 |  |  | FALSE | 1090000 |  | 2016-10-11 | Complete Construction | 2019-01-01 | 2019-04-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3195 | 3195 |  | FALSE | PLANNING & BUDGET | North District Development, Phase-1 | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | Phase 1 - Student Housing - 8/1/2020. | Gerry Bomotti | TBD | Raoula Amescua |  | R.Amescua/D.Hecht | 99 |  |  | FALSE | 2507658.71 |  | 2016-10-26 | Reg. Apprv'l-Business Terms&Fin. | 2019-05-01 | 2021-07-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3206 | 3206 |  | FALSE | BCOE | Bourns B-134 & B-108 - Removal (Add Fume Hd.) | Add 6' (if able) fume hoods to instructional labs Bourns B-108 and B-134. Depending on cost, department will include: 1. stub in of necessary exhaust and electrical infrastructure to support basic fume hood (without water, gas, vacuum, etc.) in south wall of B-134 (west end) and north wall of B-108 (west end) 2. Install new 6' hoods in locations noted above To take advantage of room instructional and work schedule, please run concurrently if possible with planned work in the room over the 2016 holiday break. | BOURNS |  | In Construction | Christopher Lynch | Maggie Souder | Sabrina Schuster |  | Scott Donnell | 8 |  |  | FALSE | 1000 |  | 2016-10-15 | Complete Construction | 2018-10-01 | 2019-02-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3218 | 3218 |  | FALSE | CNAS | Ag Ops - Demo Structures | Demolition of 15 structures, including hazardous materials cleanup, electrical reconnection of services as needed, UST removal as needed, relocation of ATT riser. |  |  | In construction Additional funding is not expected. | Kathryn Uhrich | Deborah McWilliams | Deborah McWilliams |  | Scott Donnell | 99 |  |  | FALSE | 316739 |  | 2016-10-19 | Complete Construction | 2018-07-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3224 | 3224 |  | FALSE | BCOE | Bourns - Door Access Control | Replace outdated failing, and unsupported Identicard card reader system with campus approved Hirsch system at all existing locations in Bourns Hall B-wing at a minimum; inclusion of card readers in Bourns A-wing is also desired if possible. Immediate work is optimal since the building is currently under construction and many walls, ceilings, wiring, etc are currently exposed. Work to be done via surplus funds from BCOE 950534. AVC is putting together the costs and scope via meetings with Maggie/ Pat/ and John C. | BOURNS |  | Programming | Christopher Lynch | Maggie Souder | Margaret Souder |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 2016-11-14 | Create SOW and Transfer funds | 2019-09-01 | 2019-11-29 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3228 | 3228 |  | FALSE | CNAS | Retrofit Screenhouse to Greenhouse | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. Location can be discussed with Greg Greer | RUBIDOUX SCR |  | In Design | Kathryn Uhrich | Deborah McWilliams | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 780000 |  | 2016-12-06 | Bidding | 2019-08-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3233 | 3233 |  | FALSE | CAP.PROG. | Mobility HUB Central Campus Linkages | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In bidding | TBD | Sharyl Murdock | Jaime Enghbrecht |  | Drew Hecht | 1 |  |  | FALSE | 16011000 |  | 2016-12-16 | Bidding | 2019-04-01 | 2020-01-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3234 | 3234 |  | FALSE | CAP.PROG. | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Design-SD | TBD | Sharyl Murdock | John White |  | Fernando Nunez | 2 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete Construction | 2018-11-05 | 2019-02-28 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3237 | 3237 |  | FALSE | SoB | Anderson Hall N. Access Imp. | ADA handrails installation at walkway and ramp on the East sidewalk by the bench of Anderson north, down the steep ramp leading to Anderson South. We have been working with Shelly Frohrip from HR and Mary-Alice Avila of A&E on this so they will have some information regarding the purpose. 11/15/17 The handicapped parking and POT are now included. Project approved, waiting for funding. | ANDERSON 1 |  | Construction to begin in Feb 2019 | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 5 |  |  | FALSE | 150000 |  | 2016-12-19 | Complete Construction | 2019-02-01 | 2019-04-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3255 | 3255 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Humanities - Upgrade EMS | Humanities HVAC - upgrade Energy Management System per approved Century Bond funded project (approval attached). Project: 957405 P5498 Budget $200,000 Accounting determined this is capitalizable Accounting determined not capitalizable | HUMANITIES |  | Approval of alternates by FS | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Fernando Nunez | 6 |  |  | FALSE | 202000 |  | 2017-02-10 | Complete Close-out | 2018-10-01 | 2019-01-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3270 | 3270 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Chapman Hall - Replace HVAC System | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | CHAPMAN |  | In Design | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Scott Donnell | 8 |  |  | FALSE | 595819 |  | 2017-03-07 | Bidding | 2019-05-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3271 | 3271 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Life Sci/Spieth Hall Elevator Renewal | Scope of work includes the number 3 and 4 elevators of Spieth Hall. Project budget is $344,898.00. Estimated construction cost is $250,400.00. |  |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 9 |  |  | FALSE | 345000 |  | 2017-03-07 | Final Approval of CD's | 2019-07-01 | 2019-12-31 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3272 | 3272 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Athletic/Dance elevator renewal | Project budget is $219,371.00. Estimated construction cost is $169,020.00. | ATH DANCE |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 220000 |  | 2017-03-07 | Final Approval of CD's | 2019-07-01 | 2019-12-31 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3275 | 3275 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Fiber Optic Infrastructure Upgrade | Repair, replace and upgrade the fiber optic infrastructure network that includes 50+ buildings across campus. Also includes work to main hubs, sub hubs and make available spare fiber for future utilization. |  |  | Going into bidding | Susan Marshburn | Da Lan Dinh | ----- |  | Daneca Stevens | 2 |  |  | FALSE | 643750 |  | 2017-04-12 | Award Contract | 2019-04-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | Funding | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [10 empty] | PD&C | 0 | 2017 | 2019-02-01
3286 | 3286 |  | FALSE | BAS | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | Awaiting revised proposal from Miyamoto | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 9 |  |  | FALSE | 0 |  | 2017-03-29 | Complete Design | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3292 | 3292 |  | FALSE | ITS | ITS-800Mhz Tower Site-Add Pole | As we did back in 2014, we need approval to mount a pole for network electronics. This time, location is next to the 800Mhz tower site behind the C&C Building. We would propose using the same model pole as we did at AGOPS. I believe the AGOP’s poles were set on concrete piers that were 5’ deep. Again, we would want UCR Physical Plant to mount the pole for us. And once I have approval, I can get a quote from UCR Physical Plant. This project has been given to A&E. |  |  | In Close-out | Danna Gianforte | Shelley Gupta | Tim Paul |  | Dave Bomba | 1 |  |  | FALSE | 42100 |  | 2017-04-20 | Receive final billing | 2018-06-29 | 2019-02-15 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3293 | 3293 |  | FALSE | CAP.PROG. | USDA Head House - Public Restroom | Provide an accessible public restroom facility in or adjacent to the USDA Head House Building in Ag Ops. Restroom will serve individuals and groups touring the UCR and USDA Citrus Facilities. Three options have been proposed, and need to be considered and evaluated to recommend a feasible solution for USDA. The work would be managed and paid by USDA, including the design, bidding and construction. UCR staff needs to review the proposed plans and specifications per the agreement with USDA, and provide the review, inspection and approvals. The USDA representative is Marylou Polek. | GERMPLASM |  | Pending Lease | TBD | Sharyl Murdock | Mary Lou Polek |  | Scott Donnell | 11 |  |  | FALSE | 0 |  | 2017-05-22 | USDA Scope & Design | [10 empty] | PD&C | 0 | 2017 | 2019-02-01
3300 | 3300 |  | FALSE | BCOE | R'Garden - Solar Installation | Electrician to do the following wiring of our solar panels and inverters out at the R’Garden at UCR. The H model cyboinverter to be used powers the lower heating element of the water heater. The thermostat of the lower heating element must then be set to be higher than the upper heating element. The two output lines are to be connected to an AC switch or switchable AC outlet and the lower element water heater. |  |  | Work to be inspected by A&E. | Christopher Lynch | Maggie Souder | Arvin Tam |  | Scott Donnell | 2 |  |  | FALSE | 0 |  | 2017-05-03 | To be disassembled in June 2019 |  | 2019-06-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3315 | 3315 |  | FALSE | BCOE | Bourns B144 - Lab Safety Improvements | Incorporate life safety improvements to research lab. Provide additional protection for Pyrophoric Gases. Provide sprinkler protection inside the pyrophoric gas cabinet. Provide an Automatic shutdown device for pyrophoric gas flow when activated by interlocks tied into fire sprinkler. Provide a remote manual shut down device of pyrophoric gas outside the gas cabinet. Provide audible and visible alarm detection and monitoring for toxic and highly flammable gases including diborane, germane, ammonia and hydrogen gases Applicable references on the above are NFPA 55 (Compressed Gases Code) and NFPA 45 (Standard on Fire Protection for Labs using Chemicals). | BOURNS |  | Need to confirm Dept. funding commitment | Christopher Lynch | Maggie Souder | Jianlin Liu |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2017-05-23 | Confirm Dept. Commitment/Funding | [10 empty] | PD&C | 0 | 2017 | 2019-02-01
3319 | 3319 |  | FALSE | CAP.PROG. | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | Design Criterior completed DBE prequalification will begin on 9/7 | TBD | Sharyl Murdock | ----- |  | Mihai Gavan | 13 |  |  | FALSE | 3327000 |  | 2017-06-01 | DBE Competition | 2019-11-01 | 2021-05-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | In Design | Michael Pazzani | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Dave Bomba | 99 |  |  | FALSE | 15000 |  | 2017-06-13 | Approval of HVAC design | 2019-04-01 | 2019-07-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3341 | 3341 |  | FALSE | SoB | Anderson N & S - Exterior Painting | EXTERIOR PAINTING: Please see Karen Henry or Tim DeBolt for direction in painting exterior items around Anderson Hall North/South as follows: 1. Update Paint on exterior Window trim of both buildings. 2. Update Paint on lanterns and light poles 3. Fix plaster on building walls that is peeling off. |  |  | Client would liketo cancel project | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 1 |  |  | FALSE | 0 |  | 2017-07-18 | To be canceled by Client | [10 empty] | PD&C | 0 | 2017 | 2019-02-01
3345 | 3345 |  | FALSE | SoB | Anderson N & S - Landscaping | DESIGN SVC & LANDSCAPE Construction request as follows for updated CURB APPEAL of Anderson North/South: 1. Roses Garden in middle of Stair landing/court to be removed and replaced with Grass 2. Add Large Planters (Metal or Cement) with Citrus Trees (either Kumquat/Lemon/Orange/Etc) on ledges that are at top section of front steps to deter skateboarders from jumping off of these ledges. 3. Remove dead trees on North and south ends of front lawn 4. Remove plants around granite sign in front lawn and replace with grass 5. Remove flowers and grass at both corners of front lawn around Citrus Trees and replace with DG and low growing flowering plants. 6. Pull all Ivy and crown vetch and add Pavers to East/Back side of Anderson Hall within landscaped/planter areas where ADA walkway runs and replace with nice picnic tables to include umbrellas and/or lounge seating around Anderson North for students. 7. Add DG in all areas where space is open/available surrounding outdoor seating area in back of building. 7. Remove all hedges surrounding alcove/arched areas along buildings. |  |  | On hold until ADA path of travel is completed | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 6 |  |  | FALSE | 0 |  | 2017-07-18 | Completion of 3237 | 2019-03-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3354 | 3354 |  | FALSE | BAS | Lot 4/Barn Area ADA Improvements | Lot 4/Barn Area ADA Improvements - The proposed project will relocate an existing crosswalk that is not ADA compliant and provide path of travel improvements and additional ADA parking capacity in Parking Lot 4. The existing crosswalk located at West Campus Drive and Parking Lot 4 (north) was identified in the Draft ADA Transition Plan to be out of compliance. A Pedestrian Safety Study by Fehr & Peers completed in June 2008 identified the relocation of this crosswalk to approximately 100 feet east to provide a more visible, safe, pedestrian crossing. To increase pedestrian safety further, the crosswalk will be designed as a speed table. Additionally, Transportation and Parking Services proposes to create additional ADA parking spaces in Parking Lot 4 that exceed the required number, with hardscape and path of travel improvements that will connect to the new crosswalk. The improved crosswalk will correct required path of travel deficiencies from a parking lot that provides access to numerous publicly accessible buildings, as well as allow the Barn Expansion project to obtain Division of State Architect (DSA) approval once construction is completed. The funds to complete the crosswalk replacement will be requested from Campus ADA funds. Parking Lot 4 improvements will come from will come from TAPS. Although this project supports the Barn Renovation, its conception and need is not tied to the Barn project. The crosswalk improvements and additional ADA parking is needed to meet our ADA parking requirements and serve the growing demand on campus. This project is desired regardless of the Barn Renovation project. |  |  | In funding | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Fernando Nunez | 17 |  |  | FALSE | 25000 |  | 2017-08-15 | Updated Proposal & Cost Estimate | 2019-07-01 | 2019-09-27 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3363 | 3363 |  | FALSE | CHASS | DM(17-19) CA Photo Museum HVAC | Replace current HVAC with new Temp/Humidity control system. The system must adhere to Museum standards of Temp 70 +-3 and humidity 50 +-5. THIS IS A CRITICAL REQUEST. We are currently not able to borrow work from other museums due to the inconsistent numbers we are experiencing with temperature and humidity. | CA MUS PHOTO |  | In Close-out | Milagros Pena | Cindy Williams | Emily Papavero |  | Scott Donnell | 4 |  |  | FALSE | 1350000 |  | 2017-08-23 | Complete Close-out | 2018-03-01 | 2018-12-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3366 | 3366 |  | FALSE | CAP.PROG. | Genomics Sdwk Rpr-Drainage Impr | Genomics Accessibility Improvements - The proposed project will create an accessible sidewalk connection from the Genomics Building to the University Lab and University Office Building. Currently, there is no accessible north sidewalk linkage east of the Genomics Building. The project will demolish and replace approximately 300 square feet of asphalt to bring it up to grade. Two ADA ramps will be added to sidewalk extensions of approximately 300 square feet that connect across a driveway. Existing landscaping and irrigation will be removed and replaced. No trees will be impacted by this work. |  |  | In Funding | TBD | Sharyl Murdock | Jaime Engbrecht |  | Dave Bomba | 16 |  |  | FALSE | 0 |  | 2017-11-16 | Secure Funding | 2019-04-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3367 | 3367 |  | FALSE | CNAS | Field 16 Greenhouse Demo & Replacement | Replace GH1 and GH2 with a greenhouse from the Greenhouse Megastore. Conduct geotechnical investigation, prepare drawings and conduct asbestos and lead sampling. |  |  | In Construction | Kathryn Uhrich | Deborah McWilliams | Sue Lee, D. McWilliams |  | Dave Bomba | 2 |  |  | FALSE | 300000 |  | 2017-09-15 | Complete Construction | 2019-01-30 | 2019-07-28 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3376 | 3376 |  | FALSE | BAS | West Lothian Roof Replacement Design | Provide Schematic Design, Design Development and professional cost estimate to replace the existing single-ply membrane roof system on the Lothian West residence hall wings plus Common Area applications. Existing roofing is past its useful life and starting to experience multiple leaks that are damaging living spaces below. Design effort should select the most appropriate roof material for this roof plan. The intent is to design this year (alongside the Lothian East design) and construct immediately following the Lothian East roof replacement. | LOTHIAN HALL |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 20 |  |  | FALSE | 0 |  | 2017-09-28 | Bidding | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3382 | 3382 |  | FALSE | BAS | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 33 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2021 | [10 empty] | PD&C | 0 | 2017 | 2019-02-01
3383 | 3383 |  | FALSE | BAS | W Lothian Air Handler Replacemt | Existing air handler equipment in West Lothian is original to the building and past its service life. Provide HVAC professional services to develop options for Air Handler replacement that meet UC Carbon Neutral 2025 goal. Each option analysis should include pros and cons for energy consumption, reliability, serviceability and system installation cost projections. At least one option should explore potential conversion to individual package units as practical. | LOTHIAN HALL |  | Complete Design/Bidding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 21 |  |  | FALSE | 0 |  | 2017-10-03 | Complete Design/Bidding | [10 empty] | PD&C | 0 | 2017 | 2019-02-01
3385 | 3385 |  | FALSE | VC-STU.AFF. | SRC North Gym Replace Interior Lights | Replace old technology sodium vapor light fixtures in SRC North Gymnasium with new technology LED light fixtures. Some flexibility available in the schedule. Selected vendor will need to phase work to minimize the effect on SRC operations and programming. | SRC NORTH |  | 100% CD's review | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Fernando Nunez | 1 |  |  | FALSE | 360000 |  | 2017-10-31 | Bidding - February 2019 | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | Conceptual Design | Kathryn Uhrich | Deborah McWilliams | Tracey Kahn, D. McWilliams |  | Scott Donnell | 3 |  |  | FALSE | 150000 |  | 2018-01-08 | CEQA | 2019-12-01 | 2020-02-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3392 | 3392 |  | FALSE | BAS | Bicycle Master Plan Study | Bicycle Master Plan Study. This CPMS project is for the funding and creation of a Bicycle Master Plan Study for the UCR Campus. It is not for a specific capital project. |  |  | Pre-Programming | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Jerrod Walters | 35 |  |  | FALSE | 115000 |  | 2017-11-13 | Funding | [10 empty] | PD&C | 0 | 2017 | 2019-02-01
3393 | 3393 |  | FALSE | CAP.PROG. | South Neighborhood Dist. Study | South Neighborhood District Study per discussions with the Provost/VCPB, July 2017. The South District Planning Study needs to provide guidance for future development in the South District that is inclusive of: **University aspirations to develop the South District to define the campus’ presence along the adjacent freeway (CA-60/215). **Development capacity, optimal building heights and conceptual massing presented both in metrics and a three dimensional format. **Broad parking strategy to meet the needs of the district in alignment with the campus’ overall parking management strategy and alternative transportation solutions. **High level understanding of infrastructure needs (electrical, domestic, fire and storm water, sanitary sewer, building heating and cooling) to meet the needs of the campus’ desired development capacity for district. **Pedestrian and vehicular connectivity. **East and South Campus Drive improvements |  |  | Programming | TBD | Sharyl Murdock | Uma Ramasubramanian |  | Fernando Nunez | 15 |  |  | FALSE | 309000 |  | 2017-11-15 | Receive Study Reports | [10 empty] | PD&C | 0 | 2017 | 2019-02-01
3395 | 3395 |  | FALSE | CAP.PROG. | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | Third party cost estimator needed. | TBD | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 20 |  |  | FALSE | 0 |  | 2017-12-03 | [11 empty] | PD&C | 0 | 2017 | 2019-02-01
3396 | 3396 |  | FALSE | ITS | C&C Rear Patio Tables/Shade | Installation of new exterior concrete slab and patio cover at the Computing and Communications Modular Buildings. The existing site will be cleared of all landscape to provide clear area to install concrete slab and address any grade/drainage issues. The addition of a proposed permanent patio cover is to be installed with full electrical options (lights, outlets, ceiling fans) to provide shade for future events and exterior lunch area. Shrubs along the street at the East side of the area are to be removed to provide a vendor/service ramp for events with the inclusion of lighted concrete seating within the space. | ITS CENTER |  | Additional funds added to project. | Danna Gianforte | Shelley Gupta | Sheila Mabee |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2017-11-16 | Complete Project Study | [10 empty] | PD&C | 0 | 2017 | 2019-02-01
3397 | 3397 |  | FALSE | BAS | Dundee Residence Hall and Glasgow Dining | (Lot 22/Dundee-Glasgow) A newly proposed student housing development, including a single phase 760-bed residence hall and an 830-seat dining facility located on the existing Parking Lot 22 site south of Linden Street. The project is anticipated to be completed by Fall/Winter 2020. Funding for predevelopment activities including CEQA and staff augmentation to be determined. | ABER INVER |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Raoul Amescua | 38 |  |  | FALSE | 1120000 |  | 2017-11-21 | Complete Construction | 2019-01-01 | 2020-09-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3401 | 3401 |  | FALSE | CAP.PROG. | SOM Orbach Basement Sim&Clinical | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | All workgroup meetings concluded. Working on approval documents. | TBD | Sharyl Murdock | Jeff Kaplan |  | Mihai Gavan | 18 |  |  | FALSE | 0 |  | 2017-12-03 | P Approval and Funding | 2019-09-01 | 2020-12-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-01
3403 | 3403 |  | FALSE | BAS | Parking Lot 23 Addition | Parking Lot 23 Expansion - The goal of the project is to add additional parking capacity to Parking Lot 23 to serve that area of the campus. Current parking capacity in this area will be impacted by the closures of Lot 22 and Crest Housing parking area. Additional capacity will be need for employee parking. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Daneca Stevens | 15 |  |  | FALSE | 92000 |  | 2018-05-17 | Design | 2019-05-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | Project #957440 assigned | Tamica Smith Jones | Joseph Erbland | Johnathan Jensen |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2018-08-23 | Create SOW | 2019-09-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3408 | 3408 |  | FALSE | ATHLETICS | Harrison Field Netting | Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | SOFTBALL STG |  | Per department: Project is on hold until further notice. | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2018-01-23 | On-Hold by Cust Until Further No | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3411 | 3411 |  | FALSE | BAS | MRB Café Buildout & MS&E Loading Dock Mods | MRB1 CAFE and SERVICE YARD INTERIOR FIT-OUT: provide design and construction services to build out the interior of the MRB1 Café shell and modify the MS&E Service Yard to accommodate the café deliveries and trash movement. This CPMS Request is to combine and replace previously approved CPMS #3378 and #3398 into one project as requested by A&E. Please note that the IRT Job walk has already been completed. Intent is to design in FY'17/18 and construct in FY '18/19. Opening to coincide with the MRB1 facility turnover. Food service equipment will be Owner Furnished on a separate UCR Purchase Order. Note that the MRB1 Café shell construction is provided by the separately funded MRB1 project, construction drawings for this shell space are attached in CPMS. | MAT SCI ENGR |  | Construction started 11/19. Going over submittals/RFI's. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Mihai Gavan | 1 |  |  | FALSE | 793000 |  | 2018-02-05 | Complete Construction | 2018-11-19 | 2019-02-28 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3413 | 3413 |  | FALSE | LIBR | Rivera Libr Gender Incl Restroom | Convert existing non-ADA multi-stall women's restroom to compliant ADA gender inclusive restroom. The project also involves the conversion of an existing non-ADA men's restroom to women's compliant ADA restroom. | RIVERA LIB |  | Need design | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Dave Bomba | 3 |  |  | FALSE | 0 |  | 2018-03-26 | Code and policy compliance | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3415 | 3415 |  | FALSE | SoB | Anderson South Renovation | Per the sketched drawings that Dave Bomba was provided, please provide a proposal of what it would take to renovate Anderson South as follows: **1. Remove 1st Fl South side of Corridor wall and doors between 102 suite entrance and 106 suite entrance as well as adjoining walls within 102C. **2. Create a closet/wall, ideally, behind the existing door of the 102 Entrance running to the wall shared by 102A to include the best location for a door. Essentially, enclosing the window of 102, if possible. **3. Creating a closet under the stairwell between 1st floor and basement level, having entrance door flush with the bottom step of the stairwell. **4. Remove the West wall and door framing of room 001A, leaving an open look and no corridor in suite 001. | ANDERSON 2 |  | Construction to begin in Feb. 2019 | Yunzeng Wang | Angela Chang | Laurie Gustafson |  | Dave Bomba | 4 |  |  | FALSE | 24700 |  | 2018-02-26 | Complete Construction | 2019-02-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3421 | 3421 |  | FALSE | BAS | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 5 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3426 | 3426 |  | FALSE | BAS | Lothian Boiler Replacement | The boiler equipment at Lothian is original to the building and past its useful life. Design, procure and install a replacement boiler that incorporates the latest energy saving and management technology that can be cost-effectively installed as a direct replacement to the existing unit. | LOTHIAN HALL |  | Complete Design/Bidding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 6 |  |  | FALSE | 0 |  | 2018-03-19 | Complete Design/Bidding | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3427 | 3427 |  | FALSE | BCOE | C-CERT Install Meter | Site: inland empire utility agency (IEUA) Meter install: Allen Bradley PowerMonitor 5000 price of meter is $7,410 Projected price of install: $15-20k Scope of work: Meter will be purchased by UCR for install at the main panel at the IEUA Carbon Canyon Facility. Once the meter is installed then it will be used to send Energy data back to their SCADA system and monitor and display real time data. |  |  | Blair to investigate | Christopher Lynch | Maggie Souder | Todd Ambriz |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2018-03-21 | Start Construction | 2019-02-04 | 2019-02-28 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3428 | 3428 |  | FALSE | BCOE | MSE Cleanroom | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | 2 of 5 suppliers contact have responded | Christopher Lynch | Maggie Souder | Margaret Souder |  | Dave Bomba | 6 |  |  | FALSE | 700000 |  | 2018-04-04 | Design Documents | 2019-04-01 | 2019-07-31 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3430 | 3430 |  | FALSE | BAS | TAPS Cust Svc Lobby Upgrades | Upgrades to Customer Service Lobby – Need to complete Tenant Improvement project upgrade customer service counter in Parking Services Building. Want to replace current counter to allow for; modern computer equipment, dividers between customers’ transaction spaces, under counter space for filing cabinets and check writing space. Please coordinate with Auxiliaries’ primary PM John Franklin. | PARKING SERV |  | On hold | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Dave Bomba | 16 |  |  | FALSE | 0 |  | 2018-05-17 | Meet to discuss scope & funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3432 | 3432 |  | FALSE | ATHLETICS | Athletics Replace Scoreboard | Please assist with coordinating the process for replacement of existing soccer scoreboard to a new model. We will work with A&E to develop criteria and how to accomplish the task. |  |  | On-hold | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Scott Donnell | 1 |  |  | FALSE | 0 |  | 2018-07-19 | On-Hold | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3437 | 3437 |  | FALSE | FAC-PLNG-DESIGN-CONST | UCPD Generator Replacement | Replace unsupported 125kw generator with new - Critical Facility |  |  |  | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2018-10-08 | Receive 100% CD's | 2019-07-01 | 2019-08-30 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3438 | 3438 |  | FALSE | CAP.PROG. | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | City to determine schedule | TBD | Sharyl Murdock | Dave Bomba |  | Dave Bomba | 21 |  |  | FALSE | 0 |  | 2018-08-22 | City to determine schedule | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3439 | 3439 |  | FALSE | BAS | TAPS Strategic Master Plan Study | STUDY - Transportation And Parking Master Plan Study This study initiated by TAPS is part of a comprehensive planning effort within Auxiliaries to develop a strategic transportation and parking plan that will guide the university’s transportation and parking efforts over the next decade. This is complementary to the campus Physical Master Plan Study and will help inform the future new LRDP. |  |  | Postponed until Mid-2019 | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Jerrod Walters | 18 |  |  | FALSE | 0 |  | 2018-06-05 | Postponed until Mid-2019 | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3441 | 3441 |  | FALSE | CHASS | INTS 1121 Convert Classroom to Dance Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use |  |  | In Programming | Milagros Pena | Cindy Williams | Anna Finn |  | Daneca Stevens | 1 |  |  | FALSE | 0 |  | 2018-06-22 | Design | 2019-11-01 | 2019-12-26 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3451 | 3451 |  | FALSE | CHASS | Arts 166 Perf Lab Inspection | Approval of seating plans for Arts 166, Performance Lab. Dave Bomba has the plans. Must be inspected and approved by Director of Inspection & Quality Assurance and the Campus Fire Marshall. |  |  | In Close-out | Milagros Pena | Cindy Williams | Paul Richardson |  | Dave Bomba | 5 |  |  | FALSE | 0 |  | 2018-07-26 | Complete Close-out | 2018-12-10 | 2019-01-31 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3452 | 3452 |  | FALSE | CAP.PROG. | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming | TBD | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 2 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Programming | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3453 | 3453 |  | FALSE | BAS | ECS N&S Playground Shade & Turf | Provide Schematic Design, Design Development and Professional Cost Estimate for the alteration of existing shade structures, provision for additional shade structures, refinish interior metal fencing, and the replacement of existing grass with synthetic turf at the Early Childhood Services north and south playground areas. Prepare drawings so that they can be bid and constructed as separate projects. |  |  | Dept approval/funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 23 |  |  | FALSE | 0 |  | 2018-07-03 | Dept approval/funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3455 | 3455 |  | FALSE | BAS | Campus Traffic Engineering Study | This request is to fund the contracting of a consulting firm to study of the impacts related to the desired construction of a new parking garage on the UCR campus. Project will inform on site selection, traffic impacts and opportunities. This project will be funded through a parking garage planning budget allocation in the approved 2018-19 TAPS budget. |  |  | In Construction | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Dave Bomba | 28 |  |  | FALSE |  | 0 | 2018-07-23 | Report & recommendations 2/4/19 | 2018-11-05 | 2019-06-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3458 | 3458 |  | FALSE | CAP.PROG. | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | No update | TBD | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 7 |  |  | FALSE | 0 |  | 2018-07-16 | Unknown | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3459 | 3459 |  | FALSE | BAS | A-I Hardscape Landscape Design | Provide Schematic Design and Design Development drawings for a selective renovation of all hardscape and landscape around the perimeter of the Aberdeen-Inverness housing complex. Scope to include (but not limited to) widening of South Walk and replace its asphalt with concrete pavers, upgrade hardscape and landscape at Horseshoe, replace selected lawn areas with hardscape, seating and solar umbrellas at east and west lawns of Building E, consider new bike storage along South Walk, consider modifying slopped lawn between Building A and Linden St., generally reduce lawn areas and replace with sustainable planting, prune or replace unkempt trees, replace selected light fixtures to match Dundee fixtures, and generally freshen the landscaping so that it is harmonious with the new Dundee development. Design to be packaged in phases, with the South Walk and Dundee-facing landscape to be ready in Phase 1 for construction timing alongside Dundee-Glasgow landscaping in Spring of 2020. | ABER INVER |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 24 |  |  | FALSE | 0 |  | 2018-07-16 | Consultant Approval | 2020-01-01 | 2020-08-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3460 | 3460 |  | FALSE | BAS | A-I Restroom Replacement - Reconfig | Provide Schematic Design and Design Development drawings for the complete replacement of the restrooms in all four resident hall wings. Existing restroom fixtures and finishes are largely original to the building and long past their service life, causing serious leaks between floors. New restrooms will be reconfigured to meet current accessibility code. Documents to be assembled for phased construction, one wing per summer, with the first building (D-Wing) to be constructed in Summer 2019. | ABER INVER |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 27 |  |  | FALSE | 0 |  | 2018-07-19 | Consultant Approval | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3462 | 3462 |  | FALSE | BAS | A-I Restaurant & Lobby Reconfiguration | Provide Schematic Design and Design Development drawings for the complete reconfiguration of Building C including kitchen, dining space, and common areas. The restaurant and kitchen areas are largely original to the building and well past their useful life. The new, replacement, Glasgow restaurant coming on-line in Fall 2020 will allow a needed reprogramming and modernization of this space. Preliminary Program for this space includes a smaller Catering Kitchen, Meeting Rooms, new KUCR studio as well as a modernization and upgrade of the Lobby and other Common Areas. Documents to be assembled for a Fall 2020 construction start. | ABER INVER |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 25 |  |  | FALSE | 0 |  | 2018-07-17 | RFQ Development | 2020-08-01 | 2021-06-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3463 | 3463 |  | FALSE | BAS | Landscape Strategic Plan for Housing Services | Provide a comprehensive study of existing landscape areas within Auxiliary Services and provide specific and actionable recommendations for their conversion to sustainable landscaping by location. Study to include all Resident Hall and Apartment properties and include conceptual cost estimates, by location, for proposed landscape conversions. |  |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 26 |  |  | FALSE | 0 |  | 2018-07-17 | RFQ Development | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3466 | 3466 |  | FALSE | BAS | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 32 |  |  | FALSE | 0 |  | 2018-07-31 | Funding | 2019-05-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3467 | 3467 |  | FALSE | BAS | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 31 |  |  | FALSE | 0 |  | 2018-07-31 | Design | 2019-08-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3469 | 3469 |  | FALSE | CHASS | Carillon Repair & Maintenance | Design, fabrication and replacement of bell beams for bells 24, 26, 28, 30 and 32. Design, fabrication and installation of bracing to brace the 5 other bells beams that are cracking, and corrective maintenance on the clappers & head pieces-this would include complete removal, cleaning, reaming, bushing and lubricating before re-installing and clean and lubricate the transmission system as much as possible without complete disassembly to make the instrument easier to play. | BELLTOWER |  | Funding | Milagros Pena | Cindy Williams | Reasey Heang |  | Daneca Stevens | 7 |  |  | FALSE | 0 |  | 2018-08-16 | Funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3470 | 3470 |  | FALSE | PLANNING & BUDGET | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | New Study | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 10 |  |  | FALSE |  |  | 2018-11-06 | Complete Review | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3471 | 3471 |  | FALSE | VC-STU.AFF. | HUB Elect/Gas Meters 8 Location | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | New | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | J.Franklin/J.Espinoza | 5 |  |  | FALSE | 0 |  | 2018-08-20 | Awaiting Approval | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3472 | 3472 |  | FALSE | BAS | Lot 21 Trash Enclosure Relocation | Construct a new CMU trash enclosure with water and power in a different location of Lot 21 to replace the existing enclosure that will be demolished to make way for the Dundee Residence Hall construction. Include hose bib for cleaning and power for future compactor installation. New enclosure needs to be on line BEFORE site construction can start on Dundee-Glasgow in January 2019. |  |  | Funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 36 |  |  | FALSE | 0 |  | 2018-08-15 | Hire Design Consultant | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3474 | 3474 |  | FALSE | PLANNING & BUDGET | RUSD STEM High School |  |  |  | Real Estate project | Gerry Bomotti | TBD | ----- |  | Raoul Amescua | 3 |  |  | FALSE | 0 |  | 2018-10-31 | Regents Approval of Ground Lease | 2019-07-01 | 2022-09-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM17-19 Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Working with Engineer to understand Campus system. | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 1 |  |  | FALSE | 1250000 | 0 | 2018-10-17 | Complete Final Report | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3478 | 3478 |  | FALSE | BAS | Ivans Hinderaker Ext. Cladding | Replace existing exterior cladding outside of Ivan's kiosk with new building materials that will cover the abandoned openings in the exterior and provide a cohesive and waterproof envelope for this structure. | HINDERAKER |  | Project number assigned | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 99 |  |  | FALSE | 0 |  | 2018-09-07 | Complete Construction | 2019-02-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. |  |  | Client approval/funding | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 2018-11-27 | Client approval/funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3482 | 3482 |  | FALSE | CHASS | Humanities 3rd Floor Install Sail Shades | Shade sail installation of the patios on the third floor of Humanities Social Science. There are two patios, one on the 3600 wing and one on the 3400 wing. |  |  | In Funding | Milagros Pena | Cindy Williams | Paul Richardson |  | Daneca Stevens | 9 |  |  | FALSE | 0 |  | 2018-10-10 | Funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3483 | 3483 |  | FALSE | CNAS | Pierce Fume Hoods Relocation | Relocate fume hoods as marked in attached diagram from Pierce rooms 3306 and 3310 to the locations marked in the attached diagram in Pierce rooms 3419, 3425 and 3443. |  |  | In Close-out | Kathryn Uhrich | Deborah McWilliams | Jinsong Zhang |  | Dave Bomba | 4 |  |  | FALSE |  | 0 | 2018-10-09 | Close-out | 2018-12-01 | 2019-02-15 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3484 | 3484 |  | FALSE | PLANNING & BUDGET | 266 Frost Ct Main House Demolition | Develop project budget and timeline, obtain funding from VCPB. Coordinate disconnection of all utilities: Electrical, Gas, and Water. Disconnect and cap sewer Coordinate HAZ Mat testing and report for asbestos and lead Hire abatement contractor (if necessary) to remove haz materials. Hire demolition contractor to demolish and dispose of existing house, garage and out buildings. Foundations to remain – but make safe and remove potential hazards (rebar, bolts, etc.) protruding from foundation. Paving, pavers and other “patio” slabs to remain – make safe by removing tripping hazards. Identify any hazards (I.E.; unstable retaining walls, debris piles, etc.) and make safe and secure or remove if more cost effective. |  |  | DM received. Funds sequestered. | Gerry Bomotti | TBD | Scott Donnell |  | Daneca Stevens | 5 |  |  | FALSE | 40000 |  | 2018-11-15 | Bidding | 2019-05-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3486 | 3486 |  | FALSE | VC-STU.AFF. | HUB 353/381, Costo 111 Add'l Wall/Doorway | Please evaluate additional wall/door way requests for HUB 353/381 and Costo Hall 111. | HUB |  | Client Approval | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 6 |  |  | FALSE | 0 |  | 2018-11-26 | Funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-01
3488 | 3488 |  | FALSE | BAS | CBS HUB Business Center | Provide a light renovation of the HUB Modular space to include new electrical drop for the Card Office cubicles in the North Office (where the copy machines are now), and replace flooring in the North Office as required, install ADA shelf at the front desk and other minor scope items to facilitate the move of the Card Office to this building. This must be a Winter Break project so that the Business Center remains online during the normal campus schedule. |  |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Fernando Nunez | 43 |  |  | FALSE | 15000 |  | 2018-11-13 | Complete Project Close-Out | 2018-12-17 | 2018-12-21 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3490 | 3490 |  | FALSE | BAS | East Campus Parking Structure | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Dave Bomba | 46 |  |  | FALSE |  |  | 2018-12-06 | Selection of Design Build teams | 2019-12-01 | 2021-02-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3491 | 3491 |  | FALSE | BAS | Oban Comm Ctr Remodel | General remodel and freshening of the Oban Family Housing Community Center to include Laundry Room, Public Restroom and Recreation Room. Scope documents and partial drawings attached. This was originally two separate projects that Facility Services was managing but has now been requested that A&E take over due to evolving complexity and dollar cost. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 42 |  |  | FALSE |  |  | 2018-11-16 | Funding | 2019-06-01 | 2019-08-31 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
3496 | 3496 |  | FALSE | LIBR | Rivera Library Install Gate | Rivera library gate installation |  |  | New | Steven Mandeville-Gamble | Jackie Bates | Rebeccah Goldware |  | Dave Bomba | 3 |  |  | FALSE |  |  | 2019-01-08 | New | [10 empty] | PD&C | 0 | 2019 | 2019-02-01
9029 | 9029 |  | TRUE | CHASS | CHASS INTS Install Benches | Install benches on the second floor north exterior of CHASS INTS. This is near the general assignment classrooms. Many students wait for classes outside and they don't have a place to sit. They sit on the ground mostly which causes a bit of tripping hazard. This request has come from ASUCR. |  |  | Jacqueline to review exterior space and make a recommendation. | Milagros Pena | Cindy Williams | Paul Richardson |  | ---- | 99 |  |  | FALSE | 0 |  |  | Campus Architect Review | [10 empty] | PD&C | 0 | 1900 | 2019-02-01
9055 | 3495 |  | FALSE | VC-RED | Pysch Loading Dock Haz Waste Storage | There’s been an increase use of biological and chemical hazards being used by researchers and their research projects within the Psychology (V3) vivarium. When hazardous substances are used/generated in the vivarium, the current practice is for that waste to be removed by the researcher and taken to their lab for disposal by EH&S. This would mean that hazardous agents are being transported across campus which could potentially lead to an accidental exposure. In order to comply with the hazardous storage and transportation regulations, RED proposes that a hazardous storage shed be built on or near the Psychology (V3) loading dock thus minimizing any potential from an accidental contamination. It would be a chain link storage shed with two rooms (one for biological hazards and the other for chemical hazards), and a solid roof. Around the outside of the shed would also need to have some sort of vinyl covering. As for size, a 10’ x 20’ (two 10’ x 10’) shed should meet the needed storage space. Sample designs can be provided. |  |  | Funding in process | Michael Pazzani | Laura Manor | Dierk Biggs |  | Fernando Nunez | 2 |  |  | FALSE | 10000 |  | 2018-12-04 | Start Construction | 2019-04-01 | 2019-04-30 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
17P000254 |  | 17P000254 | FALSE | PLANNING & BUDGET | SL5-FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS | Project in progress; ITS installing data. | CORP PP WHSE | 0106B | IN PROGRESS | Gerry Bomotti | TBD | DALAN DINH |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-06-07 | [6 empty] | 2/1/19, DL; Material is ordered with a 4-6 week lead time.11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DD 10/6: On hold pending discussion on space…..DL, 7/11/18; I understand there is movement on this project but I need to check in with John P. or Chris P. for a status update. |  | Ron Veloz | 12/14/18 O-RVL: F & LS shop space/Shop Location TBD. | NO | FS | 0 | 2017 | 2019-02-01
18P000328 |  | 18P000328 | FALSE | ATHLETICS | SL5-HINDERAKER BASEMENT OFFICE REPAIR | Complete as of 7/11/18 | HINDERAKER |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-01 | [6 empty] | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with Paul. Paul will complete as in the near future. Carpet will be installed shortly after......5/21/18, Painters started paint. Should be complete with paint by the end of the week....DL, 5/24/18; Painters are complete. Jess will schedule the carpet install.....DL, 6/12/18; Project is 98% Complete. Carpenters need to under cut two doors to accomodate the carpet.....DL, 7/11/18; This Project 100% Complete..... |  | Dan Lerman | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with PAul. Paul will complete as in the near future. Carpet will be installed shortly after...... | YES | FS | 0 | 2018 | 2019-02-01
18P000346 |  | 18P000346 | FALSE | ATHLETICS | SL5-ATHLETICS INSTALL WALL VOLLEYBALL OFFICES | Complete as of 11/8/18 | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-18 | [6 empty] | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. DL, 5/24/18; We will start working on plans in the near future.... DL, 6/16/18; Need to submit plans asap.......DL, 7/11/18; The plans were approved today. This project is scheduled to start on 7/14/18. We will will be complete will all items related to this project on 8/27/18. Note, The door and sidelite are special order items and this item will probalby have a 6-8 week lead time. Steve T is going to order the door soon.. Customer is aware of the delay for the door and is not concerned......DL, 7/25/18; Passed framing and Electrical inspection. We will be finished with the project next week except for the door and window that is ordered but has a 6-8 week lead time. DL, 8/10/18; This Project is Complete except for special order door and window.......DL, 8/22/18; Door and Glass still not on site., Will check in with Steve T on delivery date......Will also schedule final inspection for Certificate of occupancy......9/6/18; The Glass window is installed but we are waiting on the door. this projects is 98% complete.......DL, 9/19/18; The door will be shipped on 9/24/18. We will schedule the door install when the door is on site......DL, 11/7/18; This Project is 100% Complete.... |  | Dan Lerman | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. Will start working on plans.... | YES | FS | 0 | 2018 | 2019-02-01
19P000027 |  | 19P000027 | FALSE | ATHLETICS | SL5-ATHLETICS PATCH & PAINT ROOM | Complete as of 9/19/18 | ATH DANCE | 0120C | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | DL, 9/19/18; This Project is 100% Complete……. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000265 |  | 19P000265 | FALSE | ATHLETICS | SL5-ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
19P000295 |  | 19P000295 | FALSE | ATHLETICS | SL5-PATCH & PAINT | FS to coordinate with client to schedule work for completion. | ATH DANCE | 50B | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 12 | 18 - 19 | FALSE |  |  | 2018-09-12 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
18P000094 |  | 18P000094 | FALSE | BAS | SL5-OBAN LAUNDRY ROOM RENOVATION | Scope of work has changed and project to be routed to Google IRT/CPMS for completion | OBAN OFFICE | 100 | PROJECT INTAKE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2017-09-08 | [6 empty] | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on bid. 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/12 EB- rec'd approval to contract with Design West to consult on electrical panel upgrade. |  | Enrico Baez | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on b 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/11/18 EB-requested drawings from Gunter per Desgn Wests request. 7/11/18EB-waiting for Desgn West to complete site survey. 8/7/18 EB-Met with Robert Brumbaugh. Scope has changed with additional requirements. Improve HVAC, replace VCT, bathroom remodle. Advised to submit CPMS for A&E. | YES | FS | 0 | 2017 | 2019-02-01
18P000095 |  | 18P000095 | FALSE | BAS | SL5-THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS | Canceled per customer on priortization list. | THE PLAZA | A0013 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  | Canceled | HOLD | FALSE |  |  | 2017-09-08 | [6 empty] | 4/11/EB-On Hold per Robert Brumbaugh. 6/8 EB-emailed R. Brumbaugh for status update. |  | Enrico Baez | 4/11/EB-On Hold per Robert Brumbaugh. DND 7/14 Hold per customer on prioritization | YES | FS | 0 | 2017 | 2019-02-01
18P000099 |  | 18P000099 | FALSE | CNAS | SL5-EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 | Plans will be developed and will be submitted for review and approval. | GEOLOGY |  | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 26 | 23 | FALSE |  |  | 2017-09-08 | [6 empty] | 12/6/18, DL; This project is a priority #26 and may be completed in the next 12 - months…..DL 1/3: Chris to verify with customer on electrical requirements for completion……DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress…..DL, 7/11/18; Still need to work on plans…. Target date is 9/30/18….. |  | Dan Lerman | DL 1/3: Chris to verify with customer on electrical requirements for completion…...DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress..... | YES | FS | 0 | 2017 | 2019-02-01
18P000106 |  | 18P000106 | FALSE | BAS | SL5-HOUSING PROJECT - OBAN REC ROOM REMODEL | Scope of work has changed and project to be routed to Google IRT/CPMS for completion | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 3 | FALSE |  |  | 2017-09-14 | [6 empty] | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. DL, 7/11/18; Per Susan this project is back on track. Project is scoped. Gunther will start working on the plans and permits. Once we have the approved permit. still need to check in with Susan on a few items.....Target complet date will be mid- fall...... |  | Enrico Baez | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. 8/22/18 Met with BoB Brumbaugh, Scope of work has changed with additional items. Fire alarm panel relocation, possible building HVAC upgrade. Ask he route project through CPMS and make laundry room and Rec. room one project. | YES | FS | 0 | 2017 | 2019-02-01
18P000282 |  | 18P000282 | FALSE | BAS | SL5-EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 | Complete as of 8/10/18 | POLICE BLDG |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | LISA MARTIN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-25 | [6 empty] | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work…..DL, 5/9/18; We need to submit plans……DL, 7/11/18; This still needs to be scheduled......DL, 8/8/18; Enrico Confirmed this project is 100% Complete.... |  | Enrico Baez | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work….. | YES | FS | 0 | 2018 | 2019-02-01
18P000459 |  | 18P000459 | FALSE | BAS | SL5-BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 | Complete as of 9/21/18 | THE BARN |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | Dan Lerman |  | Complete | 6 | FALSE |  |  | 2018-05-31 | [8 empty] | Enrico Baez | 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 6 | YES | FS | 0 | 2018 | 2019-02-01
19P000247 |  | 19P000247 | FALSE | BAS | SL5-LOTHIAN FIRST FLOOR COMMON AREA FLOORING | Complete as of 10/22/18. | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Jess Hernandez |  |  |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez |  |  | FS | 0 | 2018 | 2019-02-01
18P000121 |  | 18P000121 | FALSE | CAMPUS | SL5-PHYSICS HYDRATION STATION - PHYSICS HALL | Reviewing campus standards for these project requests. | PHYSICS | 0 | HOLD - FACILITIES SERVICES |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | 12/6/18, DL; This project is currently on hold…... DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus | NO | FS | 0 | 2017 | 2019-02-01
18P000122 |  | 18P000122 | FALSE | CAMPUS | SL5-MS&E HYDRATION STATION - MS&E HALL | Reviewing campus standards for these project requests. | PHYSICS | 0 | PROJECT INTAKE |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus | NO | FS | 0 | 2017 | 2019-02-01
18P000126 |  | 18P000126 | FALSE | CHASS | SL5-HMSS ESTIMATE REMOVE WALL & CHANGE DOORS | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 3611 | QUEUE TO START | Milagros Pena | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 2017-09-28 | [6 empty] | 12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS. Remove double doors and install single door.Remove small West wall. Relocate t-stat. Ceiling work. Replace carpeting. | YES | FS | 0 | 2017 | 2019-02-01
18P000194 |  | 18P000194 | FALSE | ITS | SL5-TELEPHONE WINDOW REPLACEMENT | Canceled by customer; duration of hold was over 10 months. Customer to resubmit when ready to proceed | TELEPHONE | 101 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 5 | 6 | FALSE |  |  | 2017-11-20 | [8 empty] | Enrico Baez | EB-1/31/18 Conducted site visit. Request to replace all exterior Plexiglas with glass. Will call glass vendor to provide estimate. 7/12/18 EB-Quote provided by Hour Glass. Emailed Tami, she is waiting for budget approval to proceed with project. Should have by end of July. 10/22/18 Customer Canceled; will resubmit when ready to proceed. | YES | FS | 0 | 2017 | 2019-02-01
18P000198 |  | 18P000198 | FALSE | VC-STU.AFF. | SL5-HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Plans will be developed and will be submitted for review and approval. | HUB | 0 | QUEUE TO START | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 1 | 5 | FALSE |  |  | 2017-11-21 | [6 empty] | DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…... | 2018-01-23 | Enrico Baez | 1/23/18 EB-site walk, scope enter in FAMMIS. 4/2 MN: Enrico to obtain an FAU. 1/23/2018 E.Baez conducted job site walk. Request is for lighting installations above entries to store front and kitchen on East side of building and additional lighting above outside locker on loading dock. Manny has lights that can be re-used. Want estimate only. Need to include Campu Architech too...... | YES | FS | 0 | 2017 | 2019-02-01
19P000215 |  | 19P000215 | FALSE | BAS | SL5-SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 | Coordinating movement of equipment and utility connections. | HUB | 346 | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | John Peraino |  | 9 |  | FALSE |  |  | 2018-08-24 | [6 empty] | 12/12/18 DND Project complete; electrical was installed and all kitchen equipment was hooked up as requested. |  | Enrico Baez | 9/13/18 EB emailed Gustavo Plascncia to schedule site visit. 9/18/18 EB. Conducted site visit. Connect water, drain and gas lines to kitchen equioment. Double oven need hardwired electrical. HUB staff will attach al shelving to walls. Day crew to move and deliver equipment. | YES | FS | 0 | 2018 | 2019-02-01
19P000307 |  | 19P000307 | FALSE | BAS | SL5-LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK | Scheduled work with trades anticipated completion December 2019. | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 5 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… | 2018-10-03 | Enrico Baez | 1/8/19 EB Job Completed by Jess H. 12/22/18 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. | N/A | FS | 0 | 2018 | 2019-02-01
18P000209 |  | 18P000209 | FALSE | CHANCELLOR | SL5-VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 | Customer provided estimate for project; verifying if funding is available to proceed with project. | STUDENT SERV | 0 | QUEUE TO START | Kim Wilcox | Karim Zahedi | ANGIE GRAY |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2017-11-30 | [6 empty] | 1/15/19, DL; Ron V is still working with Angie on verifying a vendor and product…………..12/14/18, DL; Ron V. is currently working to find a more affortable turnstyle system. When a sytem is approved, we will schedule the work…. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope and conduct site visit……DL, 7/11/18; This work will require plans and permits. Will schedule meeting with Scott to verify if the project request will be approved. If this is approved, we will plan the target complete date to be mid October…..The Request is to reverese Emergency Exit Doors and install Prox card access……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..DL, 8/22/18; Confirmed with Scott that we can reverse the door swing. We will work on plans for review process. This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 9/19/18; I mis understood this for a project at Health Services. I have a meeting with Angie this week. This project is to install turn styles for access to the building. I will need to discuss the equipment to be purchased by Angie verify the specs. We will start on the plans in the early Fall……DL, 11/7/18; Conducted site visit with Vendor. Informed Angie the cost of the project will be at $45K for the project. Angie is checking to verify if funds are availabe for the equipment. |  | Enrico Baez | 2/2/18 EB site visit scheduled for 2/5/18 with Angie Gray. 2/6/18 EB- conducted site visit. Request for automated access control system. Annotated on FAMIS….DL, 5/5/18; FAMIS work order ,New ADA operator, power supply for operator and card swipe….. | YES | FS | 0 | 2017 | 2019-02-01
18P000214 |  | 18P000214 | FALSE | VC-STU.AFF. | SL5-COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Plans were approved by Fire Marshal, work to commence in 30 days. Scheduling the work with the availablity of the teams. | HEALTH SERV |  | IN PROGRESS | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-12-08 | [6 empty] | 2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez | 1/31/18 EB-Scoped site with Chris P. on 10/30/2017. Spoke with Gloris who thought still CPMS. Scope includes removing doors, adding teller counters, moving corridor wall…..Dl, 5/3/18; Dan, Chris, ron and Gloria will meet and re-scope the work……01/15/19, DL; The plans are approved and Material is ordered. Once material arrives, we will schedule the work with Gloria. | YES | FS | 0 | 2017 | 2019-02-01
18P000215 |  | 18P000215 | FALSE | VC-STU.AFF. | SL5-STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 | Plans were approved by Building Official; work to commence in 30 days. Scheduling the work with the availablity of the teams. | HEALTH SERV |  | IN PROGRESS | Brian Haynes | Cathy Eckman | PAMELA HAGGINS |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2017-12-08 | [6 empty] | 2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………1/15/19, DL, Material is ordered, material should arrive on site in the next 3- 5 weeks……12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 5/24/18; Need to review scope and site visti with Enrico. Plans and permits will be required for this project….DL, 7/11/18; Planning to walk work with Gloria and her team next week. Will be able to project complete date after site visit is conducted……DL; 7/25/18; We walked this project with the team. This will require plans and permits. We will schedule this work for Fall…………DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-45 Days…… |  | Enrico Baez | EB 3/20 scoped project and annotated on FAMIS. DL, 5/5/18; Pased from wo:Noted changes to original request.Add counter windows onto end of the current SHS front desk main counter (2 windows/stations).2. Close exam room that is open to hallway with a wall (behind room 210).3. Covert 100A to phlebotomy room with a hallway access doorway.4. Open wall to reconfigure to allow space for lab manager……01/15/19, DL; Plans are approved and material is ordered for the Phlebotomy room. We are securing the double doors. We are not conducting anywork with countrtop or window work. | YES | FS | 0 | 2017 | 2019-02-01
18P000363 |  | 18P000363 | FALSE | BAS | SL5-PAINT STOREHOUSE ADMINISTRATIVE OFFICE | Complete as of 11/8/18 | CORP B |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | ERICA HENDERSON |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-03-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000373 |  | 18P000373 | FALSE | BAS | SL5-POLICE BLDG PAINTING IN DISPATCH AREA | Complete as of 7/14/18 | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  |  | 8 | FALSE |  |  | 2018-04-02 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000226 |  | 18P000226 | FALSE | BCOE | SL5-BOURNS FUME HOOD INSTALLATION | Installation of utilities to be completed; clean room to be installed upon utility connections. | BOURNS | B0235A | IN PROGRESS | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  | 8 | HOLD | TRUE |  |  | 2017-12-11 | [6 empty] | 2/1/19, DL; The Fume hood is complete. The vendor will be back in two weeks to comissison the clean room…..…1/15/9, DL; This project is 95% complete and should be complete on or near 2/1/19…………12/14/18, DL; This Project is 90% Complete. Fume hood is scheduled for install next week. We will finish balance of project after Fume hood is installed…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. WE are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans…..DL, 5/9/18; planning to submit plans on 5/11/18 for plan check review….. DL, 5/24/18; Plans were submitted to Bob W. on 5/24/18……DL, 6/12/18; Project is on Hold until Shane can provide plans/specs for the clean room……DL, 7/11/18; Still no change to the status……DL, 7/25/18, Maggie confirmed this project is on the books. I need to discuss the status with the team because the priority list is on Hold…….DL, 8/22/18; This project is no longer on hold. We will per shane we will submit what we have from the clena room suupplier for review from FM and BO……DL, 9/6/18; WE are almost complete with Plans and will submit the plans next week………DL, 9/19/18; Submitted plans to PD&C on 9/14/18…..DL, 10/4/18; Plans were approved thais week. WE will scheudle the project around the delivery date for the Clean room……..DL, 11/7/18; This is in progress. We will complete the install of the utilities so the clean room can be installed. WE will finish the balance of the project once the Clean room install is complete. The clen room is being install by an outside vendor….. |  | Dan Lerman | 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. We are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans..... DND 7/14 Hold per customer on prioritizatio | YES | FS | 0 | 2017 | 2019-02-01
18P000432 |  | 18P000432 | FALSE | BAS | SL5-BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 | Complete as of 7/13/18 | BANNOCK H | H0101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-05-04 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000015 |  | 19P000015 | FALSE | BAS | SL5-POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING | Complete as of 11/8/18 | POLICE TRLR | 1 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-07-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000252 |  | 18P000252 | FALSE | ITS | SL5-CHASS INT S REPLACE ELECTRICAL SCREENS | Pending customer to confirm of equipment to be purchased; work scoped by BZM. | CHASS INT S | 2130 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | JORGE MACIAS |  | Dan Lerman |  | 1 | 2 | FALSE |  |  | 2017-12-21 | [7 empty] | 2018-06-21 | Ron Veloz | 01/23/19 O-RVL: RV received confirmation (Telcon) with Jorge macias to cancell the request. He will resubmit upon recipt of screens at a later date. RV instructed the Front desk(FS) to close out the request & "cc" Monty, Alan, Enrico & Linda & Loretta. END--- 01/23/19 O-RVL: RV emailed Jorge to verify status of the request/materials order. Pending response. END--- 01/09/19 O-RVL: RV spoke with Jorge on 1/09. Jorge expect screens to be ordered within two weeks and will cancel this request if the screens are not ordered by his department. Jorge asked to contact him in two weeks (01/23/19). END---6/21/18 RV HOLD, Walked site w/ Enrico & Jorge. Surveyed site and Enrico updated FAMIS & Project folder. Now pending - confirmation of party to purchase projection screens. S.O.W.: Remove two non functional motorized video screens. Replaced with new larger screen. Patch and repaint all walls and entry door. END--- 07/06/18 Ron V Input notes: Received email from Enrico on 07/03 confirming Facilities Services doe not purchase Audio Visual equipment in General Assigment class rooms. On 07/06 RV contacted Jorge Macias with this info and Jorge said he would get back to RV with follow up reply from his supervisor. Confirmed with E.B. that proj info/ photos are updated on the project folder and FAMMIS. END--- 8/22/18 O-RVL: Will follow up with Jorge to confirm status on the screen purchase and if Media will purchase the screens. END--- 08/23/18-RV emailed Jorge, Pending response. END--- 08/24/18-RV, Enrico followed up with Jorge, projection screens approved but not purchased yet). END--- 10/17/18: RV spoke with Jorge today and he said screens are on order. Jorge will follow up with updates to RV and Enrico. | YES | FS | 0 | 2017 | 2019-02-01
19P000022 |  | 19P000022 | FALSE | BAS | SL5-HUB--PAINT TWO WALL AS SCOTTY'S HUB | Complete as of 9/17/18 | HUB | 101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | DIANE THOMAS |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-07-12 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000192 |  | 19P000192 | FALSE | BAS | SL5-MAIL-PAINTING | Complete as of 11/8/18 | MAIL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000267 |  | 18P000267 | FALSE | BCOE | SL5-CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT | Complete as of 7/11/18 | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-01-16 | [6 empty] | DL, 5/19/18; High table mounted on West wall to be relocated to South wall by light "Centered". Relocate white board from East Wall to West walll wher high table was removed. Paint and new flooring. Need to schedule work with Paul and Jess. BKM furniture is scheduled 4-6 weeks. DL, 6/16/18; Lower electrical outlets on North wall, repair blinds, paint and new flooring. The space is vacant as of June 16th. I will scheudle the workl.....BKM delivery is currently scheduled for July 23rd.......This project is 100% complete. There were two items added to the scope and they will be complete by 7/20/18..... |  | Enrico Baez | 4/3/2018 Met with Maggie. She is working with BKM. Floor to go down first. BKM furniture on top. Annotated in Famis. | YES | FS | 0 | 2018 | 2019-02-01
18P000315 |  | 18P000315 | FALSE | BCOE | SL5-BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB | Complete as of 8/23/18 | BOURNS | B0235 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  | HOLD | TRUE |  |  | 2018-02-16 | [6 empty] | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction to scope, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... Need to walk project with Ron and schedule the work....DL, 5/24/18; Conducted site visit with Ron V. Ron will order material and schedule the work once material is on site.....DL, 6/16/18; Need to verify delivery date for material.......DL. 7/11/18; Plumbing is disconnected. Corey is tentatively scheduled to disconnect the Fume hood. Once the Fume hood is disconnected, we will schedule the removeal of the fume hood and start the framing of the wall. Target complete date is 8/8/18....DL, 7/25/18; Fume hood is disconnected. Need to move Fume hood and start framing target date is delayed to creep scope but should be complete near 8/16/18.....DL, 8/10/18; Carp[enters will install the wall this week. Corey has parts orders. Corey will complete the install when the material arrives.......DL, 8/22/18; This Project is Complete |  | Dan Lerman | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... DND 7/14 Hold per customer on prioritization | YES | FS | 0 | 2018 | 2019-02-01
18P000349 |  | 18P000349 | FALSE | BCOE | SL5-PHYSICS INSTALL PARTITION WALL FOR LAB ROOM | Complete as of 7/11/18 | PHYSICS | 1037 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 5/24/18; Ron V. has detailed scope and he is ordering material. Once material arives, we will schedule the work…. DL, 6/16/18; Materila is ordered, When door/frame arrives, we will prep, paint and start the work…….DL, 7/11/18; This Project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; This is a small partition wall with sound proofing to minimize noise from the compressor that is disruptive to the Helium Ion Microscope…….DL, 4/16/18; We will schedule this work to be complete by the end of the Spring quarter. DL, 5/19/18; Walked project with Ron. FAMIS work order producd and material is being ordered.... | YES | FS | 0 | 2018 | 2019-02-01
18P000269 |  | 18P000269 | FALSE | CNAS | SL5-BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED | FS to coordinate with client to scope the work. Customer contacted to schedule a site visit. | BATCHELOR | 1123 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 12 | 18 | FALSE |  |  | 2018-01-16 | [8 empty] | Enrico Baez | 5/23/18 EB - Sent email to April requesting site visit. 6/11/18 EB conducted site visit request if for additional outlet only. Single trade only asked Deborah to change to SL6. | YES | FS | 0 | 2018 | 2019-02-01
18P000270 |  | 18P000270 | FALSE | SPP | SL5-CHASS INT S- EVALUATION FOR REMODEL | Pending customer to provide drawing of the space. | CHASS INT S | 4133 | CANCELED BY CLIENT | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Dan Lerman |  | 4 | 2 | TRUE |  |  | 2018-01-16 | [6 empty] | 4/24/18 EB- Per Christina Wong, no loner needed……DL, 5/5/18; Project is cancesled per notes DND 7/27; Please follow up with customer on the status and need for the work; customer advised to me that Dan has the scope of work for completion. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. |  | Enrico Baez | 4/24/18 EB- Per Christina Wong, no longer needed……DL, 5/5/18; Project is canceled per notes DND 6/13; Project reopened and not canceled per conversation with customer. Complete scope review and speak with Luis Alvarez DND 8/20/18: submitted Google form for Project to be reviewed by IRT. 8/19/18 Met with Louis Alvarez. Asked for measured plans from BKM for wall layout and dimensions. emailed again on 9/6 asking for draws. Still waiting for BKM to provide drawings. 9/21/18 Dinh - placed on hold until customer provides BKM drawings. Enrico please manage follow up. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. On shared drive can be found in file. 10/30/18 EB-Cancelled by Customer | YES | FS | 0 | 2018 | 2019-02-01
18P000273 |  | 18P000273 | FALSE | LIBR | SL5-RIVERA LIB -RESTROOM REFRESH PROJECT | Scope of work has been reviewed; determining how to complete project with trades. | RIVERA LIBRARY |  | TO BE PERFORMED BY PD&C | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2018-01-18 | [6 empty] | DND 12/13/18: Customer advised maintenance requests related to project request has been addressed. Renovation work to be performed by PD&C and customer submitted a CPMS request. DL, 6/16/18; Need to schedule site visit with Dave and Chris P…….DL, 7/11/18; Chris and I will walk this poroject next week…..Wlaked projects with Chris. We need to review in more detail to better determin the process for this project…..DL, 9/6/18. WE need to discuss what we are going to do with this project.... We walked the project but we now need Direction from Facilities leadership… |  | Dan Lerman | DL, 4/29/18; Chris said he is aware of project scope. I need to review with Chris and schedule the work;…..Dl, 5/3/18; Dand to walk project with Chris and Dave to confirm scope. We will sub out tile work. This is paint tile, lighting and plumbing fixture upgrade..... | YES | FS | 0 | 2018 | 2019-02-01
18P000274 |  | 18P000274 | FALSE | GSOE | SL5-SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 | Project is 95% complete; contract in progress for installation of a new door, door frame and ADA operator. Anticipated completion December 2018. | EADY CENTER |  | QUALITY CHECK OF WORK | Thomas Smith | Sally Tavizon | KAREN NAPLES/BRANDON BARBOSA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-18 | [6 empty] | 2/1/19, DL; This project is 99.9% Complete. We still need to conduct Final inspection with Building inspector……1/15/19, DL; The door and automatic opener is scheduled to be installed on 1/22/19……..12/14/18, DL; This project is 95% complete. The contract for the door and ADA operator was awarded today. We will schedule the work shortly after the new year…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Conducted site visit with Gilbert. We need to have a meeting to determin if this work is part of the SLA…… DL, 6/16/18; We still need direction, SLA or Recharge?.......DL, 7/11/18; This Project will require Plans and Permits. We will start on the Plans next Week. We will also issue work orders for work we will complete with in house staff. The Concrete work and Entry Door will need to be contracted out. Target Complete date is 10/1/18……..DL, 7/25/18; Work orders are produced. Planing to walk the project with Chris, Steve B and Robert C. thisw week or next week. We will submit plans to Bob Williams for the contracted work next week……DL, 8/8/18; Completed site visit with Robert C. Steve B, Steve T. and Chris; the Plumbers are complete. The carpenters and electricians will work on their items over the next three weeks. The Plans will be ready to submit on 8/9/18. Once plans are approved, we will proceed to go out to bid for the Concrete and the ADA operator. Target complete date is 9/21/18…….DL, 8/22/18; Plans were apprroved, Concrete Contract is being executed. Still working on Door and ADA operator……..DL, 9/6/18; NTP for Concrete will be issued on Monday. I will schedule the work. I need to follow up on the door order and the ADA operator…….DL, 9/19/18; Concrete walkway scheduled to start on 9/20/18. The new door and Frame will arrieve in 3-5 weeks. We will schedule the install when the new door and frame are on site…….DL, 10/4/18; Concrete work is complete. Still need handrail, signage, door and ADA operator. Target date is Early November….DL, 11/7/18; Project is 95% complete. Contract is being processed to install the new Door, Door Fram and ADA operator. Goal is to have the work complete befor the winter break…… |  | Enrico Baez | Duplicate of 18W011999 project scoped and note entered to make facility ADA compliant. | YES | FS | 0 | 2018 | 2019-02-01
18P000281 |  | 18P000281 | FALSE | VC-UNIV.ADV. | SL5-ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS | Work has been scoped; coordinating trades schedule for work to begin. | ALUM VISITOR | 2202 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | TRUDY COHEN |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-01-24 | [6 empty] | DL, 5/24/18; Need to verify scope of work with EnricoDL, 7/11/18; Still need to visit the site and schedule the work…..DL, 11/8/18; This project was transferred to John. The target date was 1/2/19….. |  | Enrico Baez | 5/10/18 EB-Customer needs additional outlets in space to accommodate 4 new cubicles. Bob Williams wants additional information with plans. 9/13/18 EB-Met with Dan, Jorge, Rita and Kim. Scope to include patch and painting walls, removing art work, moving thermostat. Cubicles will need whip connections. | YES | FS | 0 | 2018 | 2019-02-01
18P000391 |  | 18P000391 | FALSE | BCOE | SL5-PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN | Complete as of 9/10/18 | CHUNG HALL | 446 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 5/5/18; Conducted scope visit with Paul and Maggie. This project is target date is August 30th. As of now, we have 10 business days to complete the work……. Dean's Office….DL, 6/16/18;Walked project with Jess and Paul. This will be a project will now incluclude flooring is 7- additional offices due to additional trip hazzards identified in 3 of 7 offices during the carpet scope. Maggie will pay four four of the office since they are still in good condition. We are still on schedule with the work.......Dan, 7/11/18; This project is still on schedule. Complete Date is 8/18/18 and scheduled to be complete on 8/31/18.....DL, 8/10/18; The project is on schedule and we will start on Monday.......Ahead of schedule, project will be complete on 8/29/18......DL, 9/6/18; This project is 100% complete. Note, Maggie did request Jess to come back and remove some glue and he has this scheduled..... |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-02-01
18P000394 |  | 18P000394 | FALSE | BCOE | SL5-BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK | Project work has been complete but work is being reviewed by faculty. Sound soak may be installed. | BOURNS | A0159A | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 2 | TRUE |  |  | 2018-04-12 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………….1/15/19, DL; Sound Soak is ordered and should arrive within two weeks……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; Need to review and scheudle…….DL, 7/11/18; Still need to review and scheudle…..DL, 8/22/18; This Project is complete but Maggie wants to see if the Faculty are happy with the results. We may install Sound Soak as a final option…… DL 9/6/18; Sent Maggie an email to see if she is satified with the work performed in regards to the sound proofing. I will have an update by the next Excel update….. DL, 9/19/18; The PI is out of town. Maggie will confirm the PI is satisiofd with the work when they return……on 9/18/18…DL, 10/8/18; Customer not satisfied with first round of sound proofing. We will proceed with Sound Soak material….. |  | Enrico Baez | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. EB 6/1 site visit- 3 door between 4 offices require sound proofing. Doors measure 36" x 106". Photos in FAMMIS. O-RVL: Uploaded sound soak panel data on FAMIS and is available on the Project Server File. 10/18/18 O-RVL: Per FS team meeting, we now have a clarified process that sound soak is not included in the SLA due to the fact this is not part of the work we perform at FS. Because we already committed to do further follow up with the sound soak, we will not charge this time but moving forward sound soak will be a recharge service as the team does not have the skillset to do the work and therefore outside the SLA. | YES | FS | 0 | 2018 | 2019-02-01
18P000425 |  | 18P000425 | FALSE | BCOE | SL5-BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - | Complete as of 7/25/18. | BOURNS | A0379 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; Luat Vuong arrives on or about August 15…... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected..…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/15/18........DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | FS | 0 | 2018 | 2019-02-01
18P000426 |  | 18P000426 | FALSE | BCOE | SL5-BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER | Complete as of 7/25/18. | BOURNS | A0375 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; A-375: Bhargav Rallabandi arrives on or about August 1….. DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/1/18.....DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | FS | 0 | 2018 | 2019-02-01
18P000427 |  | 18P000427 | FALSE | BCOE | SL5-BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER | Complete as of 7/11/18 | BOURNS | A0373 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie email; This is our new Dean’s faculty office. Dean Lynch is already on site getting up to speed one-two days a week. This office is an ASAP...... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected.....DL, 7/11/18; This project is 100% complete...... |  | Paul Ditty | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | FS | 0 | 2018 | 2019-02-01
18P000429 |  | 18P000429 | FALSE | BCOE | SL5-INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 | Complete as of 9/19/18 | BOURNS | B0262 B0256 | COMPLETE | Christopher Lynch | Maggie Souder | KEVIN SCHULTE |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment…..DL, 5/9/18; We are working on plans to submitt to A&E soon....DL, 5/24/18; Plans were submitted on 5/24/18.......DL, 6/12/18; Plans were approved. Cabinets are ordered. Materila is 6-8 Weeks out.....DL, 7/11/18; We have confirmation for delivery of material for mid August. Target Complete date is 9/7/18......DL, 8/10/18; Project has started. We will be complete with in two weeks......DL, 8/22/18; Work is 90% Complete..Project should be complete by 8/31/18........ DL 9/6/1/8; This project is 99% complete. The parts arrived today. I will be sending out an email to schedule the installation time for next week.......DL, 9/19/18; This project is 100% Complete........ |  | Dan Lerman | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment….. | YES | FS | 0 | 2018 | 2019-02-01
18P000294 |  | 18P000294 | FALSE | CHASS | SL5-HMSS REMOVE DOOR, INSTALL WALL | Canceled on 7/16/18 per email communication with customer. | HUM & SOC SC | 3610 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2018-02-01 | [8 empty] | Enrico Baez | 5/23/18 EB sent email request for site visit DND 7/14 Hold per customer on prioritization Canceled per customer on 7/16/18 via email with Enrico. | YES | FS | 0 | 2018 | 2019-02-01
19P000035 |  | 19P000035 | FALSE | BCOE | SL5-WCH--INSTALL NEW LED DISPLAY IN OFFICE | Installation scheduled for Friday 11/19/18. | CHUNG HALL | 354 | COMPLETE | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This Porject is 100% Complet…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Install scheduled for this Friday. | 2018-10-03 | Ron Veloz | 10/03/18 RV Walked site with Dan L. SOW Install TV Bracket at south wall center of room. Requires Power (no Data)installation of mounting bracket. TV and brk is located in Sarah Galloways office. Scope is completed. Dinh 9/18 19P000023/19P000026 requests for paint to be included in project scope for room. | YES | FS | 0 | 2018 | 2019-02-01
19P000129 |  | 19P000129 | FALSE | BCOE | SL5-HANG MONITORS AND BOARDS | Dry erase boards and monitor mount installation complete; monitors to be installed. | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | RICHARD BAIN |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2018-08-06 | [6 empty] | 12/14/18, DL; This Project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Dry errase boards and Monitor mounts are installed. Still need to install monitors, corner guards and monitors….. |  | Ron Veloz | 10/03/18 O-RVL: Install one 32" monitor asouth wall center of table, Install 55" TV at west wall(need power & data), install white bd at east wall 8' from north corner, install chalk bd at east wall 2'-6" from corner at 8" above small table. | YES | FS | 0 | 2018 | 2019-02-01
19P000278 |  | 19P000278 | FALSE | BCOE | SL5-REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR | Scheduling work for completion | BOURNS | A0165 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Dan Lerman |  | 1 |  | TRUE |  |  | 2018-08-03 | [6 empty] | DL, 10/4/18; This Project is 100% Complete…….. |  | Ron Veloz | Completed SOW, met withJess and informed of work and color. | YES | FS | 0 | 2018 | 2019-02-01
19P000316 |  | 19P000316 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL | Anticipated completion mid November | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…Anticipated completion 11/9/18. | 2018-10-03 | Ron Veloz |  | YES | FS | 0 | 2018 | 2019-02-01
18P000321 |  | 18P000321 | FALSE | BCOE | SL5-STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST | Complete as of 8/10/18 | STUDENT SERV | 1228 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Enrico Baez |  |  |  | FALSE |  |  | 2018-02-22 | [6 empty] | DL, 4/29/18; Enrico is cordinationg this. The permits are approved……. DL, 7/11/18; Just received confirmation the door is ready for delivery and installed. I need to check in with Paul about the paint and prep of the door. I also need to check in with Jason on lock hardware......Dl, 7/25/18; Door is painted and ready for install. Called Dugmore to schedule the install. This should be compolete within the next two weeks......DL, 8/8/18; This Project is 100% Complete |  | Enrico Baez | DL, 4/29/18; Enrico is cordinationg this. The permits are approved. EB. 5/11/18- waiting for PO to be issued to Vendor. Customer provided PO numbers, waiting to schedule install with vendor, 5 week lead time. | YES | FS | 0 | 2018 | 2019-02-01
18P000312 |  | 18P000312 | FALSE | CNAS | SL5-URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 | Canceled per customer 9/12/18 | CAMP LOC NOT IN BLDG |  | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | Canceled | 38 | FALSE |  |  | 2018-02-13 | [6 empty] | 2/1/19, DL; The Demolition portion of this project is scheduled to start 2/5/19………..Dl, 6/16/18; Is this a project we will manage or resourse management? I understand we will disconnect the utilites, but who is responsible for the removal of the trailers? I am assuming this will be recharge work and not covered under the SLA. I will verify before the work begins……DL, 7/11/18; Need to check in with Susan. Need to produce work orders and schedule the work…….. |  | Enrico Baez | EB, 5/29, conducted site visit 5/25. Structure is a double wide modular building/trailer. Space needs to be cleared of equipment, desks, tools. Disconnect electrical, plumbing. Needs professional removal. University Asset see Susan Marshburn for direction. EB, 9/12/18 Per Deborah McWilliams email.Project is cancelled due to lack of funding. | YES | FS | 0 | 2018 | 2019-02-01
18P000438 |  | 18P000438 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING | Complete as of 9/10/18 | CHUNG HALL | 415 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 10 | FALSE |  |  | 2018-05-14 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000439 |  | 18P000439 | FALSE | BCOE | SL5-CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING | Complete as of 9/10/18 | CHUNG HALL | 315 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 11 | FALSE |  |  | 2018-05-15 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000454 |  | 18P000454 | FALSE | BCOE | SL5-BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS | Complete as of 8/24/18 | BOURNS | A0346 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  |  | 9 | FALSE |  |  | 2018-05-29 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000318 |  | 18P000318 | FALSE | CHASS | SL5-CHASS INT S FLAT SCREEN INSTALLATION | Plans are being reviewed; work to be scheduled once plans are approved. | CHASS INT S |  | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Dan Lerman |  |  | 20 | FALSE |  |  | 2018-02-21 | [6 empty] | 2/1/19, DL; Francesca contacted me and informed me this project is now back on the books. She needs to gather more information and order the monitor. When the monitor arrives, we will schedule the installation…….1/29/19, DL; Francesca confirmed this project is not needed and requested this project to be cencelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; we have the brackets. Will scheule the work after the project is approved…..DL, 7/11/18; Work order are not produced. Need to assign and schedule the work…. Target complete date is 8/3/18……DL; 7/25/18; Need to change target date.. |  | Enrico Baez | 5/24/18 Conducted site visit. Met with Ryan Amriano. Electrical near buy. No data connection needed. Awaiting for dept. approval. They first wanted to know if this was possible. | YES | FS | 0 | 2018 | 2019-02-01
18P000472 |  | 18P000472 | FALSE | BCOE | SL5-WCH PATCH AND PAINT WALL | Complete as of 8/24/18 | CHUNG HALL | 458 | COMPLETE | Christopher Lynch | Maggie Souder | JANNA LE BLANC |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000046 |  | 19P000046 | FALSE | BCOE | SL5-PATCH AND PAINT PLUS REPLACE BLINDS | Complete as of 11/8/18 | BOURNS | A0131 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000175 |  | 19P000175 | FALSE | BCOE | SL5-PAINTING | Complete as of 10/10/18 | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT CHAVARRIA-VIVAR |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000250 |  | 19P000250 | FALSE | BCOE | SL5-BOURNS A303-PAINT AND PATCH WALL | Complete as of 10/10/18 | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | JUANA GUERRERO |  | Paul Ditty |  | 5 |  | TRUE |  |  | 2018-09-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000284 |  | 19P000284 | FALSE | CAMPUS | SL5-GEOLOGY ACCOMMODATION DOCK DOORS | Coordinating work for completion. | GEOLOGY |  | COMPLETE |  |  | DEBORAH TERAO |  | Chris Pillen |  | Canceled | Canceled | FALSE |  |  | 2018-08-07 | [8 empty] | Ron Veloz | 01/10/19 O-RVL: CLOSE OUT-WORK COMPLETED. All work for this project is completed. Email sent to Monty & team on Jan 04, 2019 confirmating all work is completed. 12/14/18 O-RVL: Loading dock Post and Chain fabrication, is in progress, Auto door operators are on Order/Contract in progress, Loading dock signage is in progress by sign shop, information was confirmed by Chris Pillen as of 12/13/18. All other request related to this project have been completed. RV sent updates to Monty on 12/13/18. 11/14/18 RV: Walked Capitol door on 10/31 for pricing. pending quote for auto door operators. 10/30/18 RV: Walke Paradise Door -Automatic Door operator vendor to site. Met with Jason to discuss door access hardware & function of locksets . Pending quote. 10/03/18 RV: Notes from FAMIS: Lock Shop - Chris working with Jason to purchase and install two sets of automatic door openers with plain face plates - to be installed in the back receivin area. | YES | FS | 0 | 2018 | 2019-02-01
18P000297 |  | 18P000297 | FALSE | CHANCELLOR | SL5-SKYE HALL CHECK LOCATION FOR TV INSTALL | Scope of work has been reviewed; determining how to complete project with trades. | SKYE HALL | 390 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Dan Lerman |  | 4 | 3 | FALSE |  |  | 2018-02-02 | [6 empty] | 2/1/19, DL; This Project is 100% Complete………1/18/19, DL; This Project is scheduled to be complete next week.….. DL, 5/24/18; Need to verify scope with Enrico…..DL, 7/11/18; Work orders are produced and need to be issued. Target complete date is 9/3/18…. |  | Enrico Baez | EB-scoped on 1/30. Mount TV above table. Advised an articulated mount be purchased. Drawing on FAMMIS WO. | YES | FS | 0 | 2018 | 2019-02-01
18P000343 |  | 18P000343 | FALSE | CHASS | SL5-UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER | Scope of work has been reviewed; determining how to complete project with trades. | THTR WKSH | 0400A | QUEUE TO START | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 2018-03-16 | [6 empty] | 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez | 5/11/18 EB-Conducted site visit on 3/21/18. Work based on Safety report written in October. Work consists of replacing door latches to orchestra pit. Adding loading dock rail, Paint frame guard, signage, gate/fall restraints, ladder modifications. | YES | FS | 0 | 2018 | 2019-02-01
18P000329 |  | 18P000329 | FALSE | CHANCELLOR | SL5-SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST | Project complete as of 9/18/18 | SKYE HALL | 170 | COMPLETE | Kim Wilcox | Karim Zahedi | DA LAN DINH |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18…..DL, 5/24/18; Plans were approved. Demo work has started......DL, 6/12/18; MArshal and Kate are working on Carpet order......DL, 7/11/18; Carpet is ordered. We have a challenge with Title 24. I am working on the title 24 documents. We are still planning to have this project complete on 8/17/18......DL, 8/10/18; We now have the Title 24 plans. The are being reviewed by Bob and Scott.....Title 24 plans approved. Robert is working on PO#. Most parts are on site and Electricans are working on project. All other Trades to follow once Lights are in...... Hard Date of 9/7/18............9/6/18 As of today, Carpet is scheduled for install tomorrow morning and furniture is scheduled for delivery this Monday......WE will more than likely have electrical punch items and touch up paint but this propject should be 100% complete in regards to FS the end of next week next week......100% PROJECT COMPLETE... GREAT WORK DAN! |  | Dan Lerman | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18….. | YES | FS | 0 | 2018 | 2019-02-01
18P000410 |  | 18P000410 | FALSE | CHANCELLOR | SL5-HINDERAKER PAINT AND PATCH WALL | Complete as of 8/24/18 | HINDERAKER | 3148B | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-25 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000347 |  | 18P000347 | FALSE | CNAS | SL5-GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) | Scope reviewed by BZM; coordination by PM for work to be completed. | GEOLOGY | 0 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 31 | Deferred to Fall Quarter - summer priority 27 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/1/19, DL; Conducted site visit with Amber. Amber will order the monitor. We will schedule the installation when the monitor is on site………….DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/1 EB Site visit. TV to be mounted on wall above water fountain across from Geo 2306. Center of mount 84" high and centered between wall corner and bulletin board. Will need electrical and data. Computer connection cutout will be in mail room. See W.O. | YES | FS | 0 | 2018 | 2019-02-01
18P000348 |  | 18P000348 | FALSE | VC-STU.AFF. | SL5-HUB ADD 3RD FLOOR WALLS | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | HUB | 0353E | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 2 | 6 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/1/19, DL; Per Chris P. This is a PD&C project………..DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Need to walk the project with Manny. Target date is late Fall…….. |  | Enrico Baez | EB 5/23/18. Conducted site visit. Request is for adding walls to interior spaces 353F, 381 and 377. Will impact A/C and fire protection. Still waiting for a firm plan from customer. | YES | FS | 0 | 2018 | 2019-02-01
18P000421 |  | 18P000421 | FALSE | CHANCELLOR | SL5-HINDERAKER PAINT AND PATCH WALL | Complete as of 8/24/18 | HINDERAKER | 2120 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-04-30 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000351 |  | 18P000351 | FALSE | SoB | SL5-REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 | 21 | HOLD - FACILITIES SERVICES | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2018-03-19 | [6 empty] | DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week......8/8/18. The trades are ready to go after they finish current projects.....DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18.......... DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date........9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space......Note. The space is usable and everything works..... |  | Enrico Baez | 4/24/18 EB-scoped. Move screen, correct non-compliant electrical issues, remove&discard overhead projector bracket, relocate heat det. Add switched outles. Plans are needed because we are relocating a heat detector | YES | FS | 0 | 2018 | 2019-02-01
18P000487 |  | 18P000487 | FALSE | CHANCELLOR | SL5-SKYE HALL PATCH HOLES AND PAINT | Complete as of 10/22/18. | SKYE HALL | 349 | COMPLETE | Kim Wilcox | Karim Zahedi | SONIA ZAMORA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000354 |  | 18P000354 | FALSE | CNAS | SL5-GH16-25 COOLING SYSTEM REPAIR | Work considered deferred maintenance not a minor renovation. | GH 16 25 |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | MARK TANKERSLEY |  | Dan Lerman |  | 13 | 17 | FALSE |  |  | 2018-03-20 | [6 empty] | DL, 7/25/18; Reviewed Ron V. noted. I will check in with Chris on this to better determin the method complete this project. |  | Dan Lerman | DL, 5/5/18; This is a repair, No alterations taking place. Pasted from FAMIS work order...THE COOLING SYSTEM ON GH 16-25 IS FALLING APART SHEET METAL TRAYS HAVE TONS OF HOLES, WOOD ROTTING ETC. PLEASE REPAIR….. RV, 07/06/18: Dan, Chis Pillen and I have walked this project months ago and have a quote from Ralph Cox/KIRA Construction to repair the head house damages. See Chris for the status of subletting this work. | YES | FS | 0 | 2018 | 2019-02-01
19P000122 |  | 19P000122 | FALSE | CHANCELLOR | SL5-REMOVE, PATCH & PAINT AND HANG | Complete as of 10/22/18. | STUDENT SERV | 2222 | COMPLETE | Kim Wilcox | Karim Zahedi | CHRISTINE SMITH |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | FS | 0 | 2018 | 2019-02-01
19P000375 |  | 19P000375 | FALSE | CHANCELLOR | SL5-PATCH AND PAINT HOLES |  | SKYE HALL | 365 | COMPLETE | Kim Wilcox | Karim Zahedi | FELECIA GARRETT |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-07 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000201 |  | 18P000201 | FALSE | CHASS | SL5-ARTS REMOVE COUNTERTOP/SHELVES | Complete as of 8/23/18 | ARTS | 0106A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 3 | TRUE |  |  | 2017-11-21 | [6 empty] | DL, 6/16/18; Ned to walk, scope and submit plans ASAP…..Sent Paul an email requesting information on Status of Faculty hire status……DL, 7/11/18; Paul is on Jury Duty and he said he should return back to work next week. Current Targe complete date is mid September......DL, 7/25/18; Carpentery and Electrical is complete. Patch and paint has started. Target complete date is 8/3/18......DL, 8/8/18; Space is VAcant and ready for paint. The paint department is working on several other projects that require their attention. The paint department will complete the work in the near future......DL, 8/22/18; This Project is 100% Complete....... |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS……DL, 4/29/18; Pasted from wo;remove the existing countertop and shelves that are built into the room. Follow with patch and paint of entire space. | YES | FS | 0 | 2017 | 2019-02-01
18P000369 |  | 18P000369 | FALSE | BAS | SL5-BOYCE X-RAY IRRADIATOR PROJECT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 1407 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | KAREN JANIGA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-27 | [6 empty] | 12/14/18, DL; This project was cancelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……DL, 5/9/18; Need to work on plans/permits…..DL, 6/16/18; Meeting with Bob and confirmed what is needed. I will work with Gunther on plans. Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall…..DL, 11/7/18; Material is on site. We will schedule the work soon…… |  | Ron Veloz | DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……Need to work on plans….10/17/18 RV: This project was previously scoped and in Plan development. | YES | FS | 0 | 2018 | 2019-02-01
18P000205 |  | 18P000205 | FALSE | CHASS | SL5-CHASS INT S CREATE DOOR | Complete as of 9/21/18 | CHASS INT S | 2117H | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-11-27 | [6 empty] | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18……DL, 5/24/18; Plans were approved. WE need to schedule the work…..DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18...........DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... .. DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date..........DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18............DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware.....DL, 9/19/18; This Project is 100% Complete...... |  | Enrico Baez | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18…… | YES | FS | 0 | 2017 | 2019-02-01
18P000295 |  | 18P000295 | FALSE | CHASS | SL5-CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL | Complete as of 9/21/18 | CHASS INT S | 2117J | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-02-01 | [6 empty] | DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18……..DL, 5/24/18; Plans were approved. We need to scheudle the work….DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets.......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date.....DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18...........DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware..... |  | Enrico Baez | 4/25 EB Scoped site. Remove counter and Cage. Drywal closed with electrical. Patch Paint. Cut in two doors in 2117G&H……..DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18…….. | YES | FS | 0 | 2018 | 2019-02-01
18P000380 |  | 18P000380 | FALSE | SOM | SL5-SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 | SOM RSCH | 330 | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-05 | [6 empty] | Canceled per customer on 8/22/18. |  | Enrico Baez | DD 7/17: Requested Enrico verify complete customer did not prioritize and noted work was done. 8/7/18-Conducted site visit-do not recommend location for TV due to potential damage from barn door type window screen. 8/15/18 emailed Tara Bathol that desired location for TV not recommended. Requested alternate location. 08/22/18 Ron V. Spoke with Tara. Tara confirmed the requestor cancelled the TV mounting bracket request after conversation with Enrico | NO | FS | 0 | 2018 | 2019-02-01
18P000314 |  | 18P000314 | FALSE | CHASS | SL5-CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR | Complete as of 7/25/18. | CA MUS PHOTO | 1000 | COMPLETE | Milagros Pena | Cindy Williams | EMILY PAPAVERO |  | Dan Lerman |  |  | 17 | FALSE |  |  | 2018-02-16 | [6 empty] | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date.......DL, 7/25/18; This project is 100% Complete..... |  | Enrico Baez | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date....... | YES | FS | 0 | 2018 | 2019-02-01
18P000344 |  | 18P000344 | FALSE | CHASS | SL5-CHASS INTS PAINT MULTIPLE ROOMS - FACULTY | Complete as of 9/10/18 | CHASS INT S | 2117E | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 1 | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 7/11/18; This was transferd in to my quque in the past week. I need to scope this project. I belive this is part of project # 18P000205 and 18P000295. If this is part of the other project. We will try to have the paint completed by 8/17/18…......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/10/18; Work has started. We passed rough electrical and framing inspection. The work should be complete in about three weeks......DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18.......DL, 9/6/18; This Project is 100% Complete....... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000398 |  | 18P000398 | FALSE | CHASS | SL5-WATKINS ESTIMATE FOR SEALING OF ADJOINING DOORS | Complete as of 10/22/18. | WATKINS | 2204 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-04-16 | [6 empty] | DL, 7/11/18; Need to walk project and verify scope and target complete date…..DL, 7/25/18; Verified scope. We need to order a new door and floor covering and need to schedule the abatnent, we will plan to start this project in 3- 4 weeks. Target complete date is late August.....DL, 8/8/18; Jess conducted the visit with the abatment contractor. Still need to verify abatment date. Carpenter shop is aware of the scope and they are ordering material. Note, one of the doors will have a lead time of 4- 6 weeks. .....DL, 8/22/18; Abatment is taking place this week. We will schedule the paint and carpet over the next week. This projcet all items for this project will be complete by 9/21/18. DL, 9/19/18; the Door was stained today and will be installed asap. The cove base is back ordered and will be installed when it is on site..target date is complete early next week...... DL, 10/4/18; This Project is 100% Complete....... |  | Enrico Baez | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. | YES | FS | 0 | 2018 | 2019-02-01
18P000385 |  | 18P000385 | FALSE | CHASS | SL5-HMSS INSTALL TV IN CONFERENCE ROOM | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 1001E | IN PROGRESS | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Dan Lerman |  | 19 | 19 | FALSE |  |  | 2018-03-06 | [6 empty] | 12/14/18; Monitor is Complete, we still need to install power. The space is vacant…DL, 6/16/18; Pasted notes from FAMIS; University Writing program wants to install a 65 inch TV in the conference room at HMNSS 1001E. 1. Request to install the TV mount/ bracket on the wall; 2. Request to remove the old projector screen but leave two wood blocks on the wall; 3. Request to add a new double power outlet around the TV bracket area. If you have any questions, please contact Shanshan Liao at (shanshan.liao@ucr.edu or X27753)……DL, 7/25/18; Work orders are not produced. Need to assign and schedule the work…..……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | 6/11/18 Install TV above wainscot. Notes in FAMMIS. Need electrical and date cut ins. | YES | FS | 0 | 2018 | 2019-02-01
19P000220 |  | 19P000220 | FALSE | CHASS | SL5-ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT | Screen to be reinstalled on Friday 11/9/18. | ARTS | 333 | COMPLETE | Milagros Pena | Cindy Williams | SONJA SEKELY-ROWLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 12/14/18, DL; This project is 100% Complete….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/8/18; Screeen is scheduled to be removed this Friday. We will schedule the installation and the patch / Paint repairs once we receive the repaired screen back from the vendor…….DL, 11/7/18; This project should already be complete. However, The vnedor did not deliver the correct screen. The correct screen is currently scheduled for this Friday..... |  | Enrico Baez | 8/27/18 EB-Remove 12' wide screen from finished ceiling. Need electricians to diconnect power, carpenters to remove drywall and lower screen. Repared screen to be re-hung by carpenters and drywall repaired. Electricians to reconnect power. Painters to patch and paint. | YES | FS | 0 | 2018 | 2019-02-01
18P000388 |  | 18P000388 | FALSE | CNAS | SL5-SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 2018-04-10 | [6 empty] | DL, 7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved…..DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans....DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter....DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but htere is no hard date as this is vacant space and we will access the space as time permits...... |  | Enrico Baez | 6/21/18 EB Remove old glass washer and install washer 400XLS. Disconnect steam, air, water, electrical, vent hood. Install new washer, electrical, step up x-former 208v to 480. Dept. to purchase x-former $5000 ill to dept. Elect. To provide specs. | YES | FS | 0 | 2018 | 2019-02-01
19P000253 |  | 19P000253 | FALSE | CHASS | SL5-ARTS RENOVATION | Complete as of 9/21/18 | ARTS | 157 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 16 | FALSE |  |  | 2018-04-17 | [6 empty] | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access……DL, 7/11/18; This project needs to be complete before Fall 2018. Space is vacant and ready go. Need to walk and confirm Schdule with Paul D. Tony's Flooring is ready to go after paint is complete.... Target complete date is 9/21/18......DL, 8/22/18; Walked with PAul, Paul will scheudle the work. Jess still need to cordinate with Tony's Flooring .....DL, 9/19/18; The paint and flooring is complete. The seams need to be welded and this will be complete. this will be complete by 9/21/18......9/19/21; This Project is 100% Complete....... |  | Dan Lerman | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access | YES | FS | 0 | 2018 | 2019-02-01
18P000111 |  | 18P000111 | FALSE | CHASS | SL5-KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 | Complete as of 7/13/18 | CHASS INT S |  | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Jason Williams |  |  |  | FALSE |  |  | 2017-09-15 | [6 empty] | EB 1/31/18 Work was assigned to lock shop 12/7/17…. DND 5/11: Spoke with Jason, all work complete to be completed as trade is available. Only work remaining is on 3150 A; Jason short staffed to finish project but it's on his radar. 07/13/18 H-FMS: Troubleshoot programming and settings for this controller. Clear all data from panel and reset, perform required downloads, re-test and verify both doors working correctly. |  | Enrico Baez | EB 1/31/18 Work was assigned to lock shop 12/7/17 | YES | FS | 0 | 2017 | 2019-02-01
18P000300 |  | 18P000300 | FALSE | CHASS | SL5-ARTS PATCH AND PAINT - DANCE HALLWAYS | Complete as of 8/24/18 | ARTS |  | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 24 | FALSE |  |  | 2018-02-02 | [6 empty] | centered. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000353 |  | 18P000353 | FALSE | CHASS | SL5-PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT | Complete as of 8/23/18 | PSYCHOLOGY1 | 1111A | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 26 | FALSE |  |  | 2018-03-20 | [6 empty] | DL; 7/4/18;This project is scoped. We will only paint one out of the two offices. Working on PO# to install frosted glass with Sun Down Window coverings……DL, 7/25/18; PO# is produced and material is ordered. Target date mid August…….DL, 8/22/18; This project is complete.... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000367 |  | 18P000367 | FALSE | CHASS | SL5-CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE | Complete as of 7/14/18 | CHASS INT N | 3033 | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 23 | FALSE |  |  | 2018-03-27 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000383 |  | 18P000383 | FALSE | CHASS | SL5-HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT | Completed as of 8/10/18 | HUM & SOC SC | 1302 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  | 4 | TRUE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000387 |  | 18P000387 | FALSE | CHASS | SL5-HMSS PATCH/PAINT | Complete as of 8/24/18 | HUM & SOC SC | 3600 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 28 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000400 |  | 18P000400 | FALSE | SOM | SL5-Covert suite 1116 and suite 1126 to office space | Provost has placed a hold on converting lab spaces into office spaces. | WEBBER | 1116 & 1126 | HOLD - FACILITIES SERVICES | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | HOLD | HOLD | FALSE |  |  | 2018-04-14 | [6 empty] | DL, 6/16/18; Waiting for update on Provost approval….DL, 7/11/18; Per email from Enrico on 7/10/18. The Provost put a hold on converting any lab space into officess…… |  | Enrico Baez | 5/1 EB Convert two wet labs into offices. Same as Webber 2278. Abate floor, demo all cabinets, remove plumbing, patch & paint. Carpet tile. Equipment comes out. Awating Provost, Sheryl Murdoch and Bob Williams approval….. 7/11/18 EB-Per Brandon Barbosa project will be cancelled | YES | FS | 0 | 2018 | 2019-02-01
18P000389 |  | 18P000389 | FALSE | CHASS | SL5-PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A | Complete as of 11/8/18 | PSYCHOLOGY1 | 2122 | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 5 | TRUE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000414 |  | 18P000414 | FALSE | CHANCELLOR | SL5-CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL | FS to coordinate with client to schedule work for completion. | STUDENT SERV | 0 | QUEUE TO START | Kim Wilcox | Karim Zahedi | DANIELLE GARCIA |  | Paul Ditty |  | 1 | 2 | FALSE |  |  | 2018-04-26 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000415 |  | 18P000415 | FALSE | CHASS | SL5-PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | Door and frame have been painted; construction to commence upon availability of the teams. | OLMSTED | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | RYAN LIPINSKI |  | Dan Lerman |  |  | 10 | TRUE |  |  | 2018-05-08 | [6 empty] | 12/14/18, DL; Angel cancelled this project as it is no longer needed at this time……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 7/11/18; This project was scoped and part of the IRT. Plans and permits are approved. We will schedule the work and we will plan to have this project complet by 9/21/18…..8/10/18; WE have approved plans, this project is scheduled to start late August and will be complete early October……DL, 10/4/18; The door and frame is scheduled for delivery in 3-5 weeks, We will start the project when the doors and frame are on site……..DL, 11/7/18; Door and frame and painted. We will start the contruction in the near future…… |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-02-01
18P000396 |  | 18P000396 | FALSE | CHASS | SL5-WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | Complete as of 8/24/18 | WATKINS | 2122 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | 6 | TRUE |  |  | 2018-04-13 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000416 |  | 18P000416 | FALSE | CHASS | SL5-HMSS UWP INSTRUCTOR OFFICE PAINTING | Complete as of 8/24/18 | HUM & SOC SC | 3002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000417 |  | 18P000417 | FALSE | CHASS | SL5-HMSS UWP INSTRUCTIONAL OFFICE PAINTING | Complete as of 8/24/18 | HUM & SOC SC | 2106 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000419 |  | 18P000419 | FALSE | CHASS | SL5-COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | FS to coordinate with client to scope the work. | WATKINS | 1320C&E | IN PROGRESS | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 5 | 8 | TRUE |  |  | 2018-04-27 | [6 empty] | 2/1/19, DL; We will custom make Sound panels and will start the installation in the next 6-8 Weeks……….. |  | Enrico Baez | 7/6/18 EB emailed Paul Richardson to schedule site visit 7/17/18 EB Scheduling site visit with Paul R. 8/7/18 EB-Job was part of an IRT. Dan said he will scope 8/20/18 EB emailed Lilia to schedule site visit. 8/24/18 EB scheduled site visit for 8/28/18 at 11:00AM 8/28/18 E.Baez- Met with Paul Richardson, Lilia Vega and Becky Campbell. Instead of tearing down walls and building new ones, they wanted to see if installing sound soak on three walls were possible, it is. They will then need to have their Dean approve the sound soak. Clients were sent an email with drawing indicating desired location of sound soak. | NO | FS | 0 | 2018 | 2019-02-01
18P000420 |  | 18P000420 | FALSE | CHASS | SL5-COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | Canceled by Customer on prioritization 7/2/18 | WATKINS | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  |  |  |  | Cancel | TRUE |  |  | 2018-04-27 | [10 empty] | YES | FS | 0 | 2018 | 2019-02-01
18P000418 |  | 18P000418 | FALSE | CHASS | SL5-HMSS OFFICE PAINTING | Complete as of 7/14/18 | HUM & SOC SC | 2002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 15 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty | 5/23/18 EB- Sent email to Jill requesting site visit. 5/23/ 18 EB- Scoped. Mount & TV on site. TV bottom edge to be mouted 48" from floor centered on West wall. Needs electrcal cut out and data. Entered in FAMIS. | N/A | FS | 0 | 2018 | 2019-02-01
18P000444 |  | 18P000444 | FALSE | CHASS | SL5-PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 | Complete as of 9/21/18 | ARTS | 242 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-05-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000445 |  | 18P000445 | FALSE | CHASS | SL5-PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 | Complete as of 9/10/18 | ARTS | 225 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 11 | TRUE |  |  | 2018-05-21 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000468 |  | 18P000468 | FALSE | CHASS | SL5-WATKINS 1222/1223 PATCH/PAINT | Completed as of 8/10/18 | WATKINS | 1222 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 13 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000469 |  | 18P000469 | FALSE | CHASS | SL5-WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS | Complete as of 7/25/18 | WATKINS | 1317 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000481 |  | 18P000481 | FALSE | CHASS | SL5-CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 | Complete as of 10/22/18. | CHASS INT S | 3104 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18W001170 |  | 18W001170 | FALSE | CHASS | SL5-ARTS: PAINT CLASSROOMS | Complete as of 9/24/18 | ARTS | 407 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 27 | FALSE |  |  | 2017-07-25 | [8 empty] | Enrico Baez | DD 10/6: Enrico scoped; requested during break - coordinating with client to complete on a Saturday | YES | FS | 0 | 2017 | 2019-02-01
18W008762 |  | 18W008762 | FALSE | CHASS | SL5-HUMANITIES: PATCH & PAINT | Complete as of 11/8/18 | HUM & SOC SC | 2415 | COMPLETE | Milagros Pena | Cindy Williams | ANDREW ALONSO |  | Paul Ditty |  | 20 | 22 | FALSE |  |  | 2018-01-02 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000435 |  | 18P000435 | FALSE | CAMPUS | SL5-HMSS HYDRATION STATION REQUEST | Pending Hydration station plan for campus | HUM & SOC SC | 3600 | HOLD - FACILITIES SERVICES |  |  | NELDA THOMAS |  | Dan Lerman |  |  | 30 | FALSE |  |  | 2018-05-10 | [10 empty] | NO | FS | 0 | 2018 | 2019-02-01
18W016588 |  | 18W016588 | FALSE | CHASS | PATCH AND PAINT FOR FACULTY | Complete as of 8/24/18 | SPROUL | 4105 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | N/A | TRUE |  |  | 2018-06-19 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18W016621 |  | 18W016621 | FALSE | CHASS | SL5-HUMANITIES - PAINT OFFICE - PAINT SHOP | Complete as of 11/8/18 | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2018-06-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000011 |  | 19P000011 | FALSE | CHASS | SL5-PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED | Complete as of 10/10/18 | PSYCHOLOGY1 | 2111A | COMPLETE | Milagros Pena | Cindy Williams | LORENA QUINTANA |  | Paul Ditty |  | 4 |  | TRUE |  |  | 2018-07-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000061 |  | 19P000061 | FALSE | CHASS | SL5-PSYCHOLOGY 1111H-PATCH HOLES IN WALL | FS to coordinate with client to schedule work for completion. | PSYCHOLOGY1 | 1111H | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000063 |  | 19P000063 | FALSE | CHASS | SL5-NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS | Complete as of 9/26/18 | PSYCHOLOGY1 | 2124 | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-07-31 | [8 empty] | Paul Ditty | 9/13/18 EB this is a request for patch, paint and new carpet | NO | FS | 0 | 2018 | 2019-02-01
19P000173 |  | 19P000173 | FALSE | CHASS | SL5-PAINT/PATCH UNIVERSITY THEATER LOBBY | Complete as of 11/8/18 | THTR WKSH | 0400A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000453 |  | 18P000453 | FALSE | CNAS | SL5-DELFINO LAB-SOIL HOUSE MODIFICATION | FS to coordinate with client to scope the work. | DELFINO HHSE |  | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | [6 empty] | 1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | FS | 0 | 2018 | 2019-02-01
19P000194 |  | 19P000194 | FALSE | CHASS | SL5-PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 | Complete as of 11/8/18 | HUM & SOC SC | 3304 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000456 |  | 18P000456 | FALSE | VC-STU.AFF. | SL5-HUB--UTILITY METERS | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. | HUB |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-05-30 | [8 empty] | Enrico Baez | 1/24/19 EB Contacted Jonathan Bianchet of Design West for results of site evaluation. Will have report by middle of following week. 11/29/18 EB Met with Design West and HUB staff. Conducted site visit. Waiting for recommendations from Design West. 7/6/18 EB-emailed Brendan to schedule site visit. 7/11/18 EB- Site visit schduled for 7/12/18 7/16/18 Conducted site. Customer wants to have SEP metered for all food vendors. Requested electical power plans from Gunther 8/7/18 Contacted Design West for proposal of feasibility stud 8/15/18 Advised Brendan Obrien to submit request to CPMS as this work will not be self performed. Sent Brendan copy of proposal for sight assessment. | YES | FS | 0 | 2018 | 2019-02-01
19P000195 |  | 19P000195 | FALSE | CHASS | SL5-HUM & SOC SC-ROOM PAINTING | Complete as of 11/8/18 | HUM & SOC SC | 2003 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000196 |  | 19P000196 | FALSE | CHASS | SL5-PAINT OFFICE AT UNIVERSITY THEATER | Complete as of 11/8/18 | THTR WKSH |  | COMPLETE | Milagros Pena | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000201 |  | 19P000201 | FALSE | CHASS | SL5-PATCH AND PAINT THE WALLS | Complete as of 11/8/18 | CHASS INT S | 3111A | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 18 |  | FALSE |  |  | 2018-08-22 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000216 |  | 19P000216 | FALSE | CHASS | SL5-HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT | Complete as of 11/8/18 | HUM & SOC SC | 1214 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-08-27 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000221 |  | 19P000221 | FALSE | CHASS | SL5-PATCH, PAINTING, AND REGULAR CLEANING OF A126A | Complete as of 11/8/18 | OLMSTED | A0126A | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000314 |  | 19P000314 | FALSE | CHASS | SL5-HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19W002930 |  | 19W002930 | FALSE | CHASS | HOLD - SL5-PATCH HOLES & PAINT - HUMANITIIES SOCSCI | Complete as of 11/8/18 | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-08-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000027 |  | 18P000027 | FALSE | CNAS | SL5-CHAPMAN PREP AND PAINT LAB | Complete as of 7/12/18 | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-05 | [6 empty] | 2/1/19, DL; This project is 100% Complete……………DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again…… DL, 4/2/18; This space is still on schedule for 7/1/18 completion date…..FAMIS work orders have been produced…..DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th….. |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again...... DL, 4/2/18; This space is still on schedule for 7/1/18 completion date.....FAMIS work orders have been produced..... | YES | FS | 0 | 2018 | 2019-02-01
18P000028 |  | 18P000028 | FALSE | CNAS | SL5-CHAPMAN PATCH AND PAINT | Complete as of 7/12/18 | CHAPMAN | 0010A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced .......DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced ...... | YES | FS | 0 | 2017 | 2019-02-01
18P000474 |  | 18P000474 | FALSE | ITS | SL5-MS&E ELECTRICAL MODIFICATIONS FOR ITS | Electrian to complete the work as available. | MAT SCI ENGR | 119 | IN PROGRESS | Danna Gianforte | Shelley Gupta | MICHAEL CAPRIOTTI |  | Robert Corey |  |  | 1 | FALSE |  |  | 2018-06-13 | [6 empty] | 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. |  | Enrico Baez | 7/17/18 EB-Scheduling site visit with Michael Capriotti 8/7/18 EB- Met with Robert Corey to discuss scope of work. He will coordinate work. | YES | FS | 0 | 2018 | 2019-02-01
18P000476 |  | 18P000476 | FALSE | VC-RED | SL5-BOYCE CONNECT WASHER & DRYER | Canceled project, work completed on 18W015691 in July. | BOYCE | 6444 | CANCELED BY CLIENT | Michael Pazzani | Laura Manor | DIERK BIGGS |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-14 | [6 empty] | Duplicate to 18W015691; complete |  |  | Duplicate to 18W015691 | NO | FS | 0 | 2018 | 2019-02-01
18P000029 |  | 18P000029 | FALSE | CNAS | SL5-CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS | Complete as of 7/11/18 | CHAPMAN | 1 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain......DL, 5/24/18; This work is scheduled to be complete on or before 7/1/18.....DL, 6/16/18; Blinds are delayed to mid July but window clenaning is still on schedule......DL, 7/11/18; This Project is 100% Complete |  | Dan Lerman | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain...... | YES | FS | 0 | 2017 | 2019-02-01
18P000480 |  | 18P000480 | FALSE | CNAS | SL5-BG - LOWER RESTROOMS-PAINTING-FLOORS | Canceled by Facilities Services; Work is not within the SLA and is not needed. | BOTGDN RSTRM |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000030 |  | 18P000030 | FALSE | CNAS | SL5-CHAPMAN PREP AND PAINT FROM WATER DAMAGE | Complete as of 11/8/18 | CHAPMAN | 100 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced....... | YES | FS | 0 | 2017 | 2019-02-01
18P000117 |  | 18P000117 | FALSE | CNAS | SL5-PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION | Complete as of 9/10/18 | WEBBER | 1303 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-21 | [6 empty] | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work....DL, 5/9/18; Produced work order for JEss to test for lead paint and ACM....Von wall is hot, everything else is good to go. I will schedule the work soon. The space is vacant......DL, 7/11/18; This project is in progress. Target Complete Date is 8/10/18....DL, 7/25/18; Vinyl plank and bullitin boards the balance of the task for this project. Still on target for complete on 8/10/18.....DL; 8/10/18; We were schedule to install the fllor and identified Asbestos,. Jess is working on the propsal and schedule for the abatment. This will require a 14- dat notification to the AQMD. This space is vacant with no scheduled move in date......DL, 8/22/18; Abatment is scheduled for this Tursday and Friday. We will scheule the carpet in dry errase boards for next week.Target complete date will be 8/31/18.....DL, 9/6/18; This project is 100% Complete...... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work.... | YES | FS | 0 | 2017 | 2019-02-01
18P000483 |  | 18P000483 | FALSE | BAS | SL5-INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | FS to coordinate with customer to scope the work. | P1 |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | AMANDA GREY |  | Enrico Baez |  | 7 |  | FALSE |  |  | 2018-06-26 | [6 empty] | Waiting for Amanda Grey to verify ownership of chain link fence. Once confirmed will contract with De Anza to install 36" wide gate. | 2018-08-29 | Enrico Baez | 12/3/18 EB-Cancelled request per email from Amanda Gray. Will resubmit request when funding is available. 10/1/18 EB-Contract De Anza Fence to have a gate installed at chain link fence leading to storm culvert in parking lot 1. | YES | FS | 0 | 2018 | 2019-02-01
18P000484 |  | 18P000484 | FALSE | ATHLETICS | SL5-INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | Project will be managed by A&E for completion. | SOFTBALL STG |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-26 | [6 empty] | 2/1/19, DL; This is a PD&C Project due to IRT walk. Project will exceed $50,000……….. |  | Enrico Baez | 12/6/18 EB Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | NO | FS | 0 | 2018 | 2019-02-01
18P000118 |  | 18P000118 | FALSE | CNAS | SL5-OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT | Complete as of 7/25/18. | OLMSTED | 1337 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2017-09-20 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space.......DL, 6/16/18. New staff member schedule to start mid july. BKM is also scheduled for mid july. This project will require cabinets to be removed, new carpet, paint and blank out electrical outlets that will no longer be used.. new signage too.....DL, 7/11/18;This project is in progress. Complete date is 7/20/18......DL, 7/25/18; This project is 100% Complete....... |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space. | YES | FS | 0 | 2017 | 2019-02-01
18P000486 |  | 18P000486 | FALSE | CNAS | SL5-PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 2018-06-28 | [6 empty] | 12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman | Dan L. scoped this project as part of an IRT…. 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. If possible paint to match existing green accent wall, if not white is fine. Mount monitor bracket to wall centered side to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | YES | FS | 0 | 2018 | 2019-02-01
18P000221 |  | 18P000221 | FALSE | CNAS | SL5-Provide add'l HVAC capacity to maintain lower temp | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 4414 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 9 | 16 | FALSE |  |  | 2017-12-11 | [6 empty] | 12/14/18, DL; This project is 100% Complete……….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob. DL, 5/9/18; We will work on plans and submit for review.....DL, 6/16/18. Had meeting with Bob W. to verify what is needed on plans. I will work with Gunther on plans for submittal and review......DL, 7/11/18; Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall.....DL, 11/7/18; Material is on site and will will schedule the work with in the next 30- days..... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob | YES | FS | 0 | 2017 | 2019-02-01
18P000223 |  | 18P000223 | FALSE | CNAS | SL5-Provide requisite utility infrastructure to support 4 add'l chambers (on order). | Plans were approved by Building Official and Fire Marshal; anticipated completion January 2019. | FAWCETT LAB |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 11 | 21 | FALSE |  |  | 2017-12-11 | [6 empty] | 2/1/19, DL; This Project is 100% Complete……..01/15/19, DL; Plans are approved, Chambers are on site. Electrical is complete. Plumbing work is in progress. Our portion of the project should be complete by 2/1/19…………..12/14/18, DL; All Pre work is complete. The Chambers are scheduled to arrive on site within the next 30-days. We will finish this project when material on site……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans……..DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet….DL, 4/29/18; Still need to conduct site visit with the team….DL, 5/24/18; Per Patty, equipment is ordered but 5- months out…..DL, 9/6/18; We will submit plans to Bob W. tomorrow for review and approval……..DL, 9/19/18; Plans are approved. The equipment will be here in about 4- months. WE will start the work for this project in the Fall to ensure we are ready when the equipment arrives……DL, 9/19/18; Plans are currently being review by BO & FM……DL, 11/7/18; Plans are approved. WE are requesting to change the placement confirguration of the growth chamber and awaitng Bob's review and approval. WE are on track to have this work complete befoire the end of the new year….. |  | Dan Lerman | DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans........DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet....DL, 4/29/18; Still need to conduct site visit with the team… | YES | FS | 0 | 2017 | 2019-02-01
18P000227 |  | 18P000227 | FALSE | CNAS | SL5-BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL | Complete as of 11/8/18 | BATCHELOR | 4128 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-12-12 | [6 empty] | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM.......DL, 5/24/18; Need to work on plans and permits. Project needs to be complete before Fall academic 2018.....DL, 6/16/18; Walked project with Jess. and he will schedule the abatment. We will not need plans for this project. We are not removing the exhasut hood which was the original purpose foor the plans......Carpenters started the demo. Still need to remove TSI. Once TSI is removed, we can schedule the plumbing work. Target Complete Date is 9/21/18....DL, 8/10/18; Abatement is scheduled for this weekend, we will start work soon.....DL, 8/22/18; Abatement and most demo complete. Still on track for 9/21/18.....DL, 9/19/18; Scope change. This project should be complete on 9/28/18.......DL, 10/4/18; Floor to be installed this Friday. Pianters will finalized the stain on the cabinets. Thsi project should be complete near 10/19/18.......Dl, 11/7/18; This project is 100% complete.... |  | Dan Lerman | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM....... | YES | FS | 0 | 2017 | 2019-02-01
18P000256 |  | 18P000256 | FALSE | CNAS | SL5-BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES | Complete as of 9/21/18 | BOYCE | 3451 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave at Webber is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place.......DL, 5/9/18; Autoclave is destroyed. Pictures were sent to Cheryl. We are now waiting for the equipment to arrive. Steve B is working on Steam connection at Boyce......DL, 5/24/18; Autoclaves arrived. Day crew is scheduled to deliver the unit on 5/30/18. we will schule the plumbers and electricians shortly there after......DL, 6/16/18; Webber Autoclave is almost complete. This portion should be complete next week. WE will run the Webbber autoclave for two weeks before we start the Boyce Autoclave. The weldolet for the BOyce unit will be installed during the steam shutdown...... DL, 7/11/18; Webber Auto clave will be complete on 7/12/18. We will start the demo of the Boyce Auto clave next soon. Target date for this project is 8/10/18...... DL, 7/25/18; We had a delay with the Webber autoclave which will implact the Boyce Auto clave. New target complete date is 8/22/18.....DL, Plumbing is almost complete, need to schedule final elctrical and Commission equipment. Target date 8/31/18...... DL, 9/6/18; This project should be complete but we still need to schedule the electrical connections ASAP.........DL, 9/19/18; This project is 100% Complete. |  | Dan Lerman | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place | YES | FS | 0 | 2017 | 2019-02-01
18W007453 |  | 18W007453 | FALSE | ITS | SL5-(P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2017-11-30 | [11 empty] | FS | 0 | 2017 | 2019-02-01
18P000257 |  | 18P000257 | FALSE | CNAS | SL5-SKYE HALL MOUNT 55 | Scope of work is being reviewed; determining how to complete project with trades. | SKYE HALL | 209 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 28 | 28 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete…….1/15/19, DL, Site visit is scheduled with James M. this Thursday. We will schedule the work shortly after the site visit…….12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | FS | 0 | 2017 | 2019-02-01
18W009630 |  | 18W009630 | FALSE | BAS | SL5-BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. | PHYS PL STOR | 100 | IRT REVIEW | Gerry Bomotti | Georgianne Carlson | JUDY HODGE |  | Dan Lerman |  | HOLD | HOLD | FALSE |  |  | 2018-01-22 | [6 empty] | DL, 6/16/18; Project includes demo wall/door install new wall, dry wall, paint, door, eletrical outlets, lighting, smoke relocation, lighting motion, new t-bar, relocate heat pump, andn install new carpet…...DL, 7/11/18; Need to work on plans….. Target complete date is late Fall..... |  | Enrico Baez | See work order 18W012349 scoped and annotated in FAMMIS. 6/11/18 EB- Add wall to current space and eliminate exisiting wall. Relocate exisiting A/C on wall. Minor electrical DND 7/14 Hold per customer on prioritization; per Corp Yard Space Planning | YES | FS | 1899-12-31 | 2018 | 2019-02-01
18P000258 |  | 18P000258 | FALSE | CNAS | SL5-SKYE HALL HALLWAY MOUNT | Scope reviewed by BZM; coordination by PM for work to be completed. | SKYE HALL | 212 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 29 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete……1/15/19, DL, Site visit is scheduled with James M. this Thursday…………12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | FS | 0 | 2017 | 2019-02-01
18P000287 |  | 18P000287 | FALSE | CNAS | SL5-SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING | Complete as of 9/21/18 | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 33 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19/18; This project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-01
18W011691 |  | 18W011691 | FALSE | CNAS | SL5-ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | FS to coordinate with client to schedule work for completion. | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 4 | 11 | TRUE |  |  | 2018-03-08 | [6 empty] | 12/17/18 DND: Canceled by client on 12/17/18. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000296 |  | 18P000296 | FALSE | CNAS | SL5-SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES | Contract is being processed; target project completion is end of September. | SKYE HALL | 266 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 31 | FALSE |  |  | 2018-02-02 | [6 empty] | 01/17/19, DL; This project was completed last summer……..DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19 18; I neeed to check on this work order. I thought it was part of the 2nd floor Hallway project but it was not…… |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-01
18W011772 |  | 18W011772 | FALSE | BAS | SL5-PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | Canceled per customer on priority list 7/3/18 | PRINT MOD |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Dan Lerman |  |  | Canceled | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/29/18; Pasted from WO; install an outside electrical outlet based on the attached amazon specs. also estimate for removing and sealing the outside vent from the copier. fyi_the copier will be moving within the next few months…..DL, 7/11/18; Need to verfy scope and schedule the work...... |  | Enrico Baez | fyi_the copier will be moving within the next few months | YES | FS | 0 | 2018 | 2019-02-01
18P000310 |  | 18P000310 | FALSE | CNAS | SL5-ADD INTERCOM/BUZZ IN SYSTEM | Complete as of 10/22/18. | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-12 | [6 empty] | Dl, 7/4/18; This project is scoped. This will be a new ADA operator, door bell / Intercom and buzzer button to unlock door. Walked work with Contractor, need to work on producing contract with PD&C. Once Contract is confirmed, we will schedule the work..... DL, 7/11/18; We have the proposal. Need to execute the agreement and schedule the work. The target complete date is before 10/1/18.....Dl 8/10/18; Jason will try and complete the work with in the next three weeks......DL, 8/22/18; Jason order parts, parts have 6-8 week lead time. Work will be scheduled when material arrives.....DL, 10/4/18; This Project is 100% Complete....... |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | FS | 0 | 2018 | 2019-02-01
18P000341 |  | 18P000341 | FALSE | CNAS | SL5-PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL | AQMD notification was sent; abatement to begin at the end of notification period. | PHYSICS | 1132 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-14 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process…DL, 6/16/18; Jess tested the matreial flooring and paint is hot. Jess will abate before we proceed with the project….Still need to scheudle the work. This project target complete date is late Fall……DL, 7/25/18; Jess sent out the 14-day notification to the AQMD last week. We will start the balance of the project after the ACM and Lead is abated or encapsulated…..8/10/18; Abatement is complete. We will work on the other items as time permits. This space is vacant with no occupancy date |  | Dan Lerman | DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process… | YES | FS | 0 | 2018 | 2019-02-01
18W000455 |  | 18W000455 | FALSE | CNAS | SL5-CHAPMAN CLEAN WINDOWS | Complete as of 7/11/18 | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  | 37 | FALSE |  |  | 2017-07-11 | [6 empty] | Dl, 7/4/18; All Windows in Chapman were cleaned by Ductch Touch. This Project is 100% Complete |  | Ron Veloz |  | YES | FS | 0 | 2017 | 2019-02-01
18W011161 |  | 18W011161 | FALSE | CNAS | SL5-REPLACE CARPET | Complete as of 7/11/18 | SCIENCE LAB1 | 301 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-23 | [6 empty] | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project……DL, 5/21/18; Floor covering is selected. Work will be scheudled for Mid June….DL, 5/24/18; The install is scheduled for June 18th & 19th……DL, 7/11/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project…… | YES | FS | 0 | 2018 | 2019-02-01
19P000045 |  | 19P000045 | FALSE | CNAS | SL5-PREPARE LOCATION AND UTILITIES FOR INSTALL | Complete as of 11/8/18 | BOYCE | 2407 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 14 |  | FALSE |  |  | 2018-07-23 | [8 empty] | Ron Veloz | Scope is complete. Walked site with Steve Burelson. DI water is available behined wall in 2407 at interstictal space. Vendor will install Milpore unit, FS to provide DI water and back board.Power is available at the sink counter. Electrical has verified GFI. | YES | FS | 0 | 2018 | 2019-02-01
1900a | 1990a |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | Finalized construction drawings are being reviewed by the campus building official and firemarshal | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2193000 |  | 2015-10-09 | Start Construction | 2019-03-01 | 2019-11-16 | [8 empty] | PD&C | 0 | 2015 | 2019-02-01
1990b | 1990b |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon-Road | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  |  | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE |  |  | 2018-06-22 | Finalize Design | 2019-10-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-01
19P000006 |  | 19P000006 | FALSE | CNAS | SL5-MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 | FS to coordinate with client to scope the work. | MAT SCI ENGR | 310 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 2/1/19, DL; This Project started to day. We are scheduled to be complete by the end of February………..1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. | 2018-09-28 | Ron Veloz | 10/30/18 RV: Spoke with Deborah McWilliams, today. Project to remain as prioritized(#3) for new Faculty. 10/17/18 RV: Floor plan is on the server folder. RV: 10/03/18: Install metal stud wall at center of the room. Remove one door blank and install one lockset.Requires, Framing, drywall, tape, sand, paint, t-bar modifications and rubber base. PM to verify with user if power and Data will be required in the new wall. 09/28/18 O-RVL: Completed SOW: Add Wall in the center of room. Include a new Metal Stud Wall with rubber base to match existing. Remove metal cover at ceiling. Remove door lock blank and install new lockset at left door. RV completed SOW & placed on FS server. Updated FAMIS and Minor Reno List. 09/27/18 O-RVL: Site walk with Chris P, Dan L. Mayela and Deborah McW. FS to re-install the metal stud wall to original place dividing the room equally. Scoping completed. 09/26/18 O-RVL: 19P000006-Scheduled a site walk scheduled with Dan. Will contact Deborah and Mayela for their participation. | YES | FS | 0 | 2018 | 2019-02-01
19P000058 |  | 19P000058 | FALSE | CNAS | SL5-Assess Feasiblity of Removing/Replacing Growth Chambers | Complete as of 8/24/18 | GH HH | 18 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-28 | [6 empty] | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing...DL, 5/9/18; Project is scoped. Need to schedule the work.....Plumbers and HVAC are working on this. Still need to have electrical removed. I am working wiht Patty on who can do the demo and removal.....DL, 7/11/18; I need to check in with Ken to see if refrigerant is recovered. will isue work order to disconnect electrical..... I checked in with our campus surplus and do not have any contacts to dis,matel the very large growth Chambers. I need to inform Patty and suggest that she have Burges demo and move the Growth Chambers......We will be complete with our portion of this project before 8/1/18.......DL, 8/10/18; All work is done except the disconnect for electrical. I need to check and see if the electrical. Per FAMIS complete on 8/22/18 |  |  | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing | YES | FS | 0 | 2018 | 2019-02-01
19P000062 |  | 19P000062 | FALSE | CNAS | SL5-MSE 169-MINOR RENOVATION - NEW FACULTY | Electrical outlet is the highest priority. Must be installed by Sept 15, per Mayela Castillo | MAT SCI ENGR | 169 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 5 | 19 | TRUE |  |  | 2018-07-30 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………..1/15/19, DL; This project is 99% complete pending one water heater. Water heater is not here yet……12/14/18, DL; This project is 95% complete. The water heater is scheduled for delivery shortly after the new year. We will complete the install when the heater arrives…… 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 9/6/18; We will have the power and cabinets removed by 9/19/18. We are in the process of producing plans for this project. Once the plans are approved, we will proceed with the project. Note, we still need to obtain important information and some specifications regarding the procured base cabinets and counter tops, bio safety cabinet, diswasher, and freezer. ……DL, 7/7/18; The work is 90% complete. We are waiting on parts which have a 4-6 week lead time. We will finsh the balance of the project when the parts arrive….. | 2018-08-22 | Ron Veloz | 10/17/18 RV: Work is in Progress. END--- 08/27/18 RV: Updated notes. Moved to "Que to Start". Lab upgrades, Install utilities for new lab equipment, including DI water, electrical, modify existing cabinet to accommodate new flask washer, install owner furnished lab workstations. END ---...DND 8/12/18 replaced 3 projects for Summer quarter completion. Ron V. has scope on project. END --- 08/22/18 O-RVL: completed S.O.W, sent to Mayela Castillo for sign off. 08/23/18-RV: Ron V. Resubmitted S,O.W. rev.1 and received Final sign off from Mayela. Met with Dan to provide information and hand off the project. | YES | FS | 0 | 2018 | 2019-02-01
19P000126 |  | 19P000126 | FALSE | CNAS | SL5-CHEMICAL SCIENCE - MINOR RENOVATIONS | Paint has been completed; plumbing to complete work upon availability of the team. | CHEMICAL SCI | 455 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Dan Lerman |  | 6 |  | TRUE |  |  | 2018-08-03 | [6 empty] | 12/14/18, DL; This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL,11/7/18; Paint is complete, Plumbing shop is planning to schedule the work in the near future…… |  | Ron Veloz | Work in progress, install nitrogen lines and valves(valves by PI). Patch and paint. 10/30/18 RV: Spoke with Kevin, pending nitrogen line installation | YES | FS | 0 | 2018 | 2019-02-01
19P000185 |  | 19P000185 | FALSE | CNAS | SL5-NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE | Scope of work has been identified and walked with Requestor, F.S. Trades and P.M. Trade work in progress. | PIERCE | 206 (originially identified as Room 204) | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 6 | TRUE |  |  | 2018-06-18 | [6 empty] | 12/14/18, DL; This project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Pending glove box relocation to rm 319 and minor vent reconfiguration. Both tasks will be performed afet the glove boxes relocate to rm. 319. 10/29/18 All project related work is completed. |  | Ron Veloz | 07/05/18 RonV. Input: I observed multiple WO's for this project and spoke with Zee for clarification. I will investogate the site on 07/06 to determine the actual SOW. 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/22/18 O-RVL: Revised WO to Project no. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". =10/03/18: RV, Work in progress. Plumber are working on new gas lines. Will coordinate glove box move after work in rm 319 is completed. 10/29/18 RV: All glove boxes, Solvent mixing equipment and Chemical cabinet are removed. Remaining work is to replace the existing PVC vent with stainless duct when materials arrive per Cory. Update from Matt L-Plumbing department is working on the gas lines and will continue work this week. | YES | FS | 0 | 2018 | 2019-02-01
19P000186 |  | 19P000186 | FALSE | CNAS | SL5-NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION | Complete as of 11/8/18 | PIERCE | 319 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-06-18 | [6 empty] | Pending gas line installation scheduled for the week of 09/24 per Steve Burleson. Move glove boxes from 206 to Rm 319 after gas line are installed. All work is complete |  | Ron Veloz | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". 10/03/18 RV: Work in progress, Plumbers are installing gas lines. Glove boxes from 206 can be moved after gas lines are installed. 10/08/148 RV: Plumbers to complete the installation of new gas lines in 319. Glove boxes to be brought to rm 319 after gas lines are installed. 10/17/18 RV: Update, Gas lines are installe approx 90% complete per Plumbing Tech, misc parts on order. 10/29/18 RV: All project related work is completeand confirmed with trades and PI. | YES | FS | 0 | 2018 | 2019-02-01
19P000291 |  | 19P000291 | FALSE | CNAS | SL5-MSE HELIUM RECOVERY SYSTEM | Work has been completed; FS teams verifying completion and quality check of work. | MAT SCI ENGR | 205 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 9 | HOLD | FALSE |  |  | 2017-07-24 | [6 empty] | 12/14/18, DL; This project is 100% Complete……DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB - spoke with Mayela who is determining status within her dept…. DL, 11/7/18; This project is complete but I need to conduct a final site visit….. |  | Ron Veloz | DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB-Spoke with Mayela-she is researching where the project stalled within her department. 7/2/18 DND Please verify if work is still required for completion 8/7/18 EB-sent Mayela email requesting update on 9/20/18 EB-emailed Mayela to determine status of project. 9/24/18 EB-Project not cancelled. Passed on to Ron Veloz. 10/03/18: RV, Walke job with Mayela, Chris P, Dan L & Deb McWilliams. PI to provide Dan layout and equipment specs. | YES | FS | 0 | 2017 | 2019-02-01
17W012504 |  | 17W012504 | FALSE | CNAS | PAINT Business OFFICE AND CONF. ROOM | Complete as of 10/22/18. | ENTOMOLOGY | 170 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 27 | 26 | FALSE |  |  | 2017-05-04 | [6 empty] | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. |  | Dan Lerman | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. | YES | FS | 0 | 2017 | 2019-02-01
19P000021 |  | 19P000021 | FALSE | ITS | SL5-ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS | FS to coordinate with customer to scope the work. | ITS CENTER |  | QUEUE TO START | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-07-12 | [6 empty] | 12/14/18, DL; Still need to review scope….. |  | Enrico Baez | Met with IT staff. T.V. to be mounted in 4 locations. Will need electrical and painting in some locations. Waitng for updated scope from Joe Sepulveda 1. Telecom Building - Conference Space Electricians Power Requirements: • Install double duplex(quad outlet), AC power on East wall at display location (4S Box) low profile • All electrical junction boxes, J-boxes, and conduit can be surface mounted. J-boxes to be located behind TV. Data Requirements: • Install single gang junction box on East wall behind display with Panduit running to specified location (for telecom network drops) o Single gang, low profile junction box o (conduit to be lead through masonry wall above T Bar ceiling in adjacent room. o (Low profile boxes for data ports) • Single gang box, mounted behind TV location, for data. • Note: Non-traditional wall – masonry Carpenters • Install mounting bracket for display on East wall • note: Non-traditional wall – masonry Painters • Paint junction boxes and conduit to match wall. 2. Intellicenter - First Floor Common Area Carpenters • Install mounting brackets on East Wall for each display (2 total) • (ITS to note the top of the bracket) 3. SOM-E - 1675A DataCenter Electricians Power Requirements: • Install double duplex(quad outlet), AC power on North wall at each display location (2 total) o Surface mounted J Boxes and Conduit Data Requirements: • Install single gang junction box on North wall at each display location with conduit/panduit running to specified location (for telecom network drops) (2 total) o (Wire mold boxes for both power and data) (2inch boxes – low profile boxes for data ports) o Data conduit to stub up and terminate through T-bar ceiling panels. • All conduit and J-boxes to run upward through T-bar ceiling Carpenter • Install mounting bracket for each display on North wall (2 total) • Install backing for mounts in adjacent data room in shelving. Painters • Patch and paint installation area as needed Location Notes • Non-traditional wall – drywall over carpentry 4. ITS Building - 174 Electricians • Install double duplex, AC power on East wall at each display location (2 total) • Install single gang junction box on East wall at each display location with conduit above ceiling (for telecom network drops) (2 total) o Terminate Data conduit above T-bar ceilings Carpenters: • Install mounting bracket (marked on the wall) for each display on East wall (2 total) Location Notes: • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 5. ITS Building - Main Lobby Electricians • Install double duplex, AC power on South wall at display location • Install single gang junction box on South wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on South wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 6. ITS Building – AVC / CIO’s Office (ITS 147) Electricians • Install double duplex, AC power on North wall at display location • Install single gang junction box on North wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on North wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 7. ITS Building Room 138 Electricians • Install double duplex, AC power on East wall at display location • Install single gang junction box on East wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install m | YES | FS | 0 | 2018 | 2019-02-01
18P000247 |  | 18P000247 | FALSE | CNAS | SL5-PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 | Complete as of 7/14/18 | PHYSICS | 3023 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  |  | 15 | FALSE |  |  | 2017-12-20 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2017 | 2019-02-01
19P000023 |  | 19P000023 | FALSE | BCOE | SL5-PAINT ACCENT WALL | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-13 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000026. Canceled to be completed on 19P000035 | N/A | FS | 0 | 2018 | 2019-02-01
19P000026 |  | 19P000026 | FALSE | BCOE | SL5-WCH PATCH AND PAINT WALLS | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000023. Canceled to be completed on 19P000035 | N/A | FS | 0 | 2018 | 2019-02-01
18P000284 |  | 18P000284 | FALSE | CNAS | SL5-SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT | Complete as of 9/21/18 | SKYE HALL | 277 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  | 29 | 23 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-01
19P000028 |  | 19P000028 | FALSE | BCOE | SL5-BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS | Deferred to Winter Quarter | BOURNS | A0169 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | Deferred to Winter Quarter |  | FALSE |  |  | 2018-07-16 | [7 empty] | 2018-11-14 | Ron Veloz | 10/29/18 RV: Scoping is completed. Carpenters to Remove Ceiling Mounted TV supports from the lobby ceiling. Work may require Carpenters to open the hard ceiling and remove the TV bracket posts if they cannot be unscrewed from the mounting brkt at the deck above. Work ay also require drywall patch back, tape, sand and paint the lobby ceiling. 11/14/18 RV: Moved to Que to Start. | YES | FS | 0 | 2018 | 2019-02-01
19P000029 |  | 19P000029 | FALSE | BCOE | SL5-CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | Canceled; duplicate request to be completed with 19P000059 | CHUNG HALL | 205 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-16 | [6 empty] | Canceled; duplicate request to be completed with 19P000059 |  | Ron Veloz | to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | NO | FS | 0 | 2018 | 2019-02-01
18P000288 |  | 18P000288 | FALSE | CNAS | SL5-SKYE HALL OFFICE SUITE PAINTING | Complete as of 8/24/18 | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-01
19P000031 |  | 19P000031 | FALSE | CNAS | SL5-BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) | FS to coordinate with client to scope the work. | BIOLOGICAL SCI | 3101 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 40 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This is prioritized at #40 and will not be scheduled in the near future….. |  | Enrico Baez | 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. Install 2 duplex outlets | YES | FS | 0 | 2018 | 2019-02-01
19P000032 |  | 19P000032 | FALSE | SOM | SL5-Reconfigure recepetion desk to fit two FTEs. | Scope of work has been identified and walked with Ron V & Brandon B. | SOM EDUC | 2608 | QUEUE TO START | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | 5 | 1 | FALSE |  |  | 2018-07-17 | [6 empty] | 2/1/19, DL; I Walked this project this week. We will try and schedule the work in the next 30- days…….12/14/18, DL, Still need to conduct site visit and schedule the work… | 2018-10-17 | Ron Veloz | 01/31/19 O-RVL: Met with Dan L onsite to review SOW with the requester. END--- 10/17/18 O-RVL: Remove one lower cabinet, Install a new corbel below to support the counter, install new carpet square or create an accent border if carpet tile is obsolete. Install new rubber base | YES | FS | 0 | 2018 | 2019-02-01
19P000033 |  | 19P000033 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT | Duplicate request to 19P000030; Canceling project to be completed on other request. | OLMSTED | 2301 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | Duplicate to project 19P000030. Canceling project. |  | Paul Ditty | Duplicate to project 19P000030. Canceling project. | N/A | FS | 0 | 2018 | 2019-02-01
18P000292 |  | 18P000292 | FALSE | CNAS | SL5-SKYE HALL PAINT MULTIPLE FACULTY OFFICES | Complete as of 8/24/18 | SKYE HALL | 228 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul D. will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-01
18P000293 |  | 18P000293 | FALSE | CNAS | SL5-SKYE HALL COPIER ROOM PATCH AND PAINT | Complete as of 8/24/18 | SKYE HALL | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 32 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-01
18P000356 |  | 18P000356 | FALSE | CNAS | SL5-ENTOMOLOGY PATCH AND PATCH | Complete as of 8/24/18 | ENTOMOLOGY | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 10 | TRUE |  |  | 2018-03-20 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000043 |  | 19P000043 | FALSE | CNAS | SL5-SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | Customer called and canceled the work on 10/23/18. | SCIENCE LAB1 | 309 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 19 |  | FALSE |  |  | 2018-07-20 | [7 empty] | 2018-10-22 | Ron Veloz | Customer called and canceled the work on 10/23/18. 10/20/18: O-RVL: Site visit on 10/20 with Amber 10:30am. 10/22/18 O-RVL: Walked site with Vendor/Controlled key sys. The PI requested pricing to change the locking function from room to room as "Storage use " and rekey the entry door with the same function. Matt will send pricing on the week of 10/22. 10/23/18 O-RVL: This request will not require access controls, but will require the entry door and side door lock-sets function to be changed to a storage function and rekeyed per Dave(PI). Received info from PI that there was a theft in his dept. Request is urgent. RV requested key count from Dave 8/23/18 and is pending a response from the department. 10/23/18 >> Canceling at the request of the customer - Loretta | YES | FS | 0 | 2018 | 2019-02-01
18P000392 |  | 18P000392 | FALSE | CNAS | SL5-BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 | Complete as of 8/24/18 | BATCHELOR | 0 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  |  | 8 | TRUE |  |  | 2018-04-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000434 |  | 18P000434 | FALSE | CNAS | SL5-BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY | Complete as of 8/24/18 | BOYCE | 4478 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Paul Ditty |  |  | 3 | TRUE |  |  | 2018-05-09 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000436 |  | 18P000436 | FALSE | CNAS | SL5-COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS | FS to coordinate with client to schedule work for completion. | COLL BLDG SO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 36 | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000464 |  | 18P000464 | FALSE | CNAS | SL5-PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED | FS to coordinate with client to schedule work for completion. | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 35 |  | FALSE |  |  | 2018-08-16 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000473 |  | 18P000473 | FALSE | CNAS | SL5-PIERCE NEW CARPET & PAINT FACULTY OFFICE | Complete as of 9/26/18 | PIERCE | 202 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 1 | 5 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18W011672 |  | 18W011672 | FALSE | CNAS | SL5-ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY | Complete as of 7/25/18 | ENTOMOLOGY | 268 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-03-08 | [6 empty] | Relocate white board from East wall onto the West wall, where high table was removed, 24" away from North end of wall. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000055 |  | 19P000055 | FALSE | CNAS | SL5-CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM | Scope reviewed by BZM; coordination by PM for work to be completed. | COLL BLDG SO | 207 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Dan Lerman |  | 32 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2018-05-18 | [6 empty] | 12/14/18, Dl; This project is prioritized at 32 and will not be scheduled in the near futurer…….DL, 7/11/18; Correction, I did not scope this yet, I thought we were talking agout the door bell and ADA operator. I will check in with Ronda and verify the scope…... DND 7/30/18: Created project to replace WO #18015182; project #19P000055 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. | 2018-11-29 | Ron Veloz | 11/29/18: RV Visited site and identifed the toilet room on the 2nd floor. SOW is to install a new exhaust fan at the second floor toilet room. Roof access is available from the access panel in the closet located in the room 210 next door. There is roof is transite per Jess. Abatement is necessary for roof penetrations and possibly has lead paint on ceilings and walls. | YES | FS | 0 | 2018 | 2019-02-01
19P000056 |  | 19P000056 | FALSE | CHASS | SL5-HMSS CAPABILITY OF MOUNTING A TV | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 1212 | IN PROGRESS | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  |  | 18 | FALSE |  |  | 2017-10-03 | [6 empty] | 12/14/18, DL; Monitor is complete. Still need to work on electrical……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope with Enrico and schedule the work…. Work orders are not produced. Need to assign and schedule the work DND 7/30/18: Closed work order #18W004822; created project #19P000056……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | EB 3/26-Project scoped on 10/23/17. Attached 5 photos and made annotations to FAMIS. | YES | FS | 0 | 2017 | 2019-02-01
18W011692 |  | 18W011692 | FALSE | CNAS | SL5-ENTOMOLOGY; PAINT/PATCH LAB | Complete as of 8/24/18 | ENTOM MUSEUM | 211 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-03-08 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000059 |  | 19P000059 | FALSE | BCOE | SL5-CHUNG HALL 201 SECURITY SYSTEM INSTALL | ITS to install cameras, no work by FS Required. | CHUNG HALL | 201 | CANCELED BY FS | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 10 | 7 | FALSE |  |  | 2018-07-17 | [6 empty] | DND 7/30/18 Project #19P000059 to replace REF CPMS # 9054 Ron to speak with ITS to complete installation. |  | Ron Veloz | 10/29/18 RV: Last meeting it was discussed that FS does not install Security Camera systems. Ron V spoke with Maggie on 10/26 to inform her that the project will be removed from the FS Minor Ren. List and she will need to contact ITS to request the Security Camers. 08/27/18 RV: Updated notes. Moved to "Que to Start". 09/19/18 RV, Install Security Cameras at points of entry. Install DVR locally in closet at an adjacent room. 08/23/18-RV Met with D.L. and Jason W. and verified F.S. will perform cabling installation and mount cameras. Equipment cost is not included in the SLA. R.V. will communcate informantion to Maggie. 08/22/18 O-RVL: Met with M. Souder to determine security camera needs and approximate location. | YES | FS | 0 | 2018 | 2019-02-01
19P000060 |  | 19P000060 | FALSE | BCOE | SL5-CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | CHUNG HALL | 223 & 224 | TO BE PERFORMED BY PD&C | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 6 | 4 | FALSE |  |  | 2018-05-15 | [6 empty] | 2/1/19, DL; Thios is a PD&C project. Maggie S. is aware this project may be a $130,00. project……DL, 7/25/18; This project is complicated and plans/permits will be required. This project will also require Air Hanlers to be shut down so Vibration dampners can be instlled. We will work on the plans in the next 45 days. This project should be scheduled during the Winter. We may also need to rent a large portable air handler to ensure the Large server room can maintain temp……. Project #19P000060 to replace REF CPMS # 9043. DL, 11/7/18; Sent Maggie an email on 11/7/18 informing her this project is well beyond our scope and $50K threshold. |  | Dan Lerman | DD 7/17: IRT Scoped with Dan present. Attached to FS Project. REF CMPS 9043 | YES | FS | 0 | 2018 | 2019-02-01
18W013160 |  | 18W013160 | FALSE | CNAS | BEES- PATCH & PAINT 2460D & 2460F | Complete as of 10/22/18. | GEOLOGY | 2460 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 33 | 29 | FALSE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000042 |  | 19P000042 | FALSE | CNAS | SL5-COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL | FS to coordinate with client to schedule work for completion. | COLL BLDG SO | 200 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Paul Ditty |  | 38 |  | FALSE |  |  | 2018-07-20 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000049 |  | 19P000049 | FALSE | CNAS | SL5-PHYSICS PATCH & PAINT | FS to coordinate with client to schedule work for completion. | PHYSICS | 3036 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | 39 |  | FALSE |  |  | 2018-07-25 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000102 |  | 19P000102 | FALSE | CNAS | SL5-PATCH & PAINT FRONT CORNER OF OFFICE | FS to coordinate with client to schedule work for completion. | LIFE SCIENCE | 2930 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 42 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000106 |  | 19P000106 | FALSE | CNAS | SL5-PHYICS 1134 - UTILITIES REQUEST | FS to coordinate with client to scope the work. | PHYSICS | 1134 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 15 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 2/1/19, DL; Review scope with Customer. Still need to review with Brian from the Electic shop…………….12/14/18, DL; No update…. | 2018-11-07 | Ron Veloz | 01/31/19 O-RVL: Walked site with Dan L on 01/31 to review SOW. END--- 01/23/19 O-RVL: Received email from Ward B.in response to Brian Hambleton's request to use 208v. response is" ... 208 volt power 3-phase is fine for the compressor. Also having emergency power is not needed". END--- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela. END --- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela.-END 01/23/19 RV received Dr. Beyermann's comments and made corrections to the SOW, rev2. END--- 01/22/19 O-RVL: RV updates, Received a request from Mayela to meet on site with team. Sent team a copy of the Statement of Work for their review. Scope of Work: Install: Chilled new water supply & return drop, Electrical Power for the Compressor to be 3- phase 40Amp 220/230VAC hardwired from the equipment the disconnect for the Compressor. Power for the QD Pump and Controller to be single phase 200-230VAC, 20amp circuit. Patch and paint as needed, test for lead paint and TSI Asbestos abatement, equipment anchoring. Note: Job walk conducted on 11/07/18, 9:45-10:00am. Met in 1134 to determine Equipment and Utility Service location. In addition, on 11/03/18 the customer requested a single phase 200-230VAC, 20amp circuit (received info via email). END --- 01/11/19 O-RVL: Received an email from Mayella requesting status. END --- 11/08/18 O-RVL: Received email from Dr Beyerman today for added electrical. "I just realized that I also need a single phase 200-230VAC, 20 amp circuit in 1134 for the pump and controller, which is that unit next to the dewar. This can be down by the floor, in the vicinity of the 3 phase box. I will be meeting with the electrician today around 11am, and I will mention it to him". RV asked Dr Beyermann to contact me with the location for the pump receptacle. Will update floor plan upon receipt. 11/07/18 RV Walked site with Mayela and Dr Beyerman. Request to provide Chilled water loop, and two locations for Electrical power. Identified locations to install new utilities. END --- 11/07/18 O-RVL: Walked site on 11/07 with Dr Beyermann & Mayela, identified scope. Update FAMIS to J-DLN, MinRenlist and move to que to start. END --- 11/06/18 O-RVL: Jobwalk scheduled on 11/07 at 10:00am in Rm 1134 with Mayela, Ward Beyermann, Darren M HVAC, Brian H-Elect. Hold | YES | FS | 0 | 2018 | 2019-02-01
19P000176 |  | 19P000176 | FALSE | CNAS | SL5-PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY | FS to coordinate with client to schedule work for completion. | PHYSICS | 1112 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 50 |  | FALSE |  |  | 2018-08-10 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | FS | 0 | 2018 | 2019-02-01
19P000191 |  | 19P000191 | FALSE | CNAS | SL5-PATCH AND PAINT HINDERAKER BASEMENT | Complete as of 11/8/18 | HINDERAKER |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 34 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000214 |  | 19P000214 | FALSE | CNAS | SL5-PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT | Complete as of 10/10/18 | PHYSICS | 3005 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-08-24 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000127 |  | 19P000127 | FALSE | CNAS | SL5-PIERCE PATCH & PAINT | Duplicate request to be combined with 19P000239 | PIERCE | 2301 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | MICHELLE KING |  | N/A |  | Canceled |  | FALSE |  |  | 2018-08-03 | [6 empty] | Paul Ditty |  | Paul Ditty | Paul Ditty |  | FS | 0 | 2018 | 2019-02-01
19P000230 |  | 19P000230 | FALSE | CNAS | SL5-NEW FACULTY OFFICE FOR PATCHWORK/PAINT | Complete as of 10/10/18 | GEOLOGY | 1242A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-08-30 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
19P000133 |  | 19P000133 | FALSE | CNAS | SL5-PATCH HOLES AND PAINT | FS to coordinate with client to schedule work for completion. | BATCHELOR | 2203 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 43 |  | FALSE |  |  | 2018-08-07 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000137 |  | 19P000137 | FALSE | CNAS | SL-5 -LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM |  | LIFE SCIENCE | 2545 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-08 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000170 |  | 19P000170 | FALSE | CNAS | SL5-INSTALL NEW IRRADIATOR INSTRUMENT | Anticipated delivery of equipment is scheduled for three weeks. | MAT SCI ENGR | 51 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 16 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 2/1/19, DL; Power is complete. Chilled water will be complete next week…………..1/15/19, DL; Electric is commplete, Water will be complete with in two weeks. Equipment should be on site soon…12/14/18, DL; This project is currently on hold per RED…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; The unit is schedukled for delivery in the next three weeks. | 2018-09-19 | Ron Veloz | 01/30/19 O-RVL: Spoke with Dan, equipment arrived staging into building. END---…..9/10: D. Dinh Project is shared between CNAS & BCOE, captured only on the CNAS College Count. 09/19/18 RV, Scope is complete. RV to Upload into FAMIS. Install chilled water and dedicated power for the irradiator instrument at the west wall in rm 051. 10/17/18 RV: SOW provide Chilled water loop and one(1ea) dedicated 208v 1ph 40a circuit to the Irradiator. Floor plan and specs are on the server folder. | YES | FS | 0 | 2018 | 2019-02-01
19P000171 |  | 19P000171 | FALSE | CHASS | SL5-HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST | FS to coordinate with client to schedule work for completion. | HUM & SOC SC | 1614 | QUEUE TO START | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 16 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000231 |  | 19P000231 | FALSE | CNAS | SL5-OLMH 1428 PATCH AND PAINT | FS to coordinate with client to schedule work for completion. | OLMSTED | 1428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ANDREW CABRERO |  | Paul Ditty |  | 48 |  | FALSE |  |  | 2018-08-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
19P000242 |  | 19P000242 | FALSE | CNAS | SL5-PAINT OFFICE | FS to coordinate with client to schedule work for completion. | COLLEGE BLDG NO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 47 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
19P000174 |  | 19P000174 | FALSE | CNAS | SL5-BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT | Scope reviewed by BZM; coordination by PM for work to be completed. | BATCHELOR | 2112 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AMY RICKS |  | Dan Lerman |  | 37 |  | FALSE |  |  | 2018-07-24 | [6 empty] | 12/14/18, DL; This project is priortized at 37 and will not be scheudled until further notice…… | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scoping narrative is available and located on the BZM Fall Folder. Patch & Paint, replace supply grilles, reverse door swing, remove door closers, install metal plate over door opening. | YES | FS | 0 | 2018 | 2019-02-01
19P000244 |  | 19P000244 | FALSE | CNAS | SL5-PATCH & PAINT GEOLOGY | Complete as of 10/22/18. | GEOLOGY | 2258A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2018-09-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000246 |  | 19P000246 | FALSE | CNAS | SL5-PHYSICS - PATCH AND PAINT | Complete as of 10/10/18 | PHYSICS | 3007N | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 46 |  | FALSE |  |  | 2018-09-07 | [6 empty] | n/a |  | Paul Ditty | Duplicate request; project to be completed on 19P000234 | N/A | FS | 0 | 2018 | 2019-02-01
19P000181 |  | 19P000181 | FALSE | VC-RED | SL5-PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS | FS to coordinate with client to schedule work for completion. | UNIV OFC BLD | 249 | QUEUE TO START | Michael Pazzani | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-14 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000184 |  | 19P000184 | FALSE | CNAS | SL5-REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES | FS to coordinate with client to scope the work. | GEOLOGY | 1270 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 45 |  | FALSE |  |  | 2018-08-14 | [6 empty] | 2/1/19, DL; This project has started. We would like to have the work complete by mid March…………..12/14/18, DL; This project is prioritized at 45 and will not be shceudled until further notice…… |  | Enrico Baez | 11/08/18 RV: Enrico is assisting RV and has scheduled a job walk with Laurie Graham. Will follow up, pending confirmation. 11/19/18 EB-Met with Laurie Graham at site. SCOPE CARPENTERS-Remove all wall, base and center island cabinet work. Verify no ACM flooring under center island. PLUMBERS-Remove sinks in 1270 and 1270A. Terminate, at wall plumbing. Remove air/gas lines on wall in 1270 and 1270A. Remove lower chilled water, supply and return, lines on East wall. Remove air and gas line, flush with floor, from center island. FLOORING-Remove VCT in 1270 and 1270A, replace with customer selected VCT. Replace all cove base. ELECTRICIANS-Remove gray flexible conduit at raceway, terminate circuit. PAINTERS- Patch and paint walls in both spaces. | YES | FS | 0 | 2018 | 2019-02-01
19P000251 |  | 19P000251 | FALSE | CNAS | SL5-CHEM SCI 428-PATCH DRY WALL HOLES | Complete as of 10/10/18 | CHEMICAL SCI | 428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-02-01
19P000287 |  | 19P000287 | FALSE | CNAS | SL5-URGENT: PAINT SHOP TO PATCH AND PAINT | Complete as of 10/22/18. | MAT SCI ENGR | 229 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | HONG XU |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-19 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-02-01
19P000188 |  | 19P000188 | FALSE | CAMPUS | SL5-PAINT - HALLWAY DOORS & INSIDE RESTROOMS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500 | CANCELED BY FS |  |  | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-16 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-02-01
19P000189 |  | 19P000189 | FALSE | CNAS | SL5-PHYSICS- WALL HOLES PATCH | Duplicate work order to 19P000049. Work to be completed on other project. | PHYSICS | 3036 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-16 | [10 empty] | NO | FS | 0 | 2018 | 2019-02-01
19P000370 |  | 19P000370 | FALSE | ENROLLMENT SERVICES | SL5-PATCH AND PAINT CAMPUS TOURS |  | STUDENT SERV | 1137 | COMPLETE | LaRae Lundgren | TBD | ELIZABETH TATUM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000313 |  | 18P000313 | FALSE | GSOE | SL5-SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 | Complete as of 10/22/18. | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-15 | [6 empty] | 18W011689 Work order was cancelled because it has the same scope and is a duplicate………DL, 6/16/18; Contract is being awarded this week. Weill are scheduled to have this work completed by fiscal closing……DL, 7/25/18; This Project is 100% Complete…..9/13: Zee - Customer noted paint peeling; updated to status to back in progress for work to be addressed.......DL, 9/19/18; The contractor is on site repairing the walls and painting. The work should be complete this week.......dl, 10/4/18; tHIS PROJECT IS 100% Complete..... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000193 |  | 19P000193 | FALSE | CNAS | SL5-GENOMICS 2221 - FOB ACCESS SYSTEM INSTALLATION | FS to coordinate with client to scope the work. | GENOMICS | 2221 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | [7 empty] | 2018-10-08 | Ron Veloz | 01/31/19 O-RVL: Pending proposal revisions with equipment itemized with make and model no. from the Access control vendor. Revised proposal due soon per vendor. END--- 01/15/19 O-RVL: Forwarded access controls quote and SOW to Jason and Chris Rodriguez to review and qualify the HCI quote. Pending response. --- 01/10/19 O-RVL: RV received quote and will send a formal Estimate to Aimee by EBD Fri. 01/18 and ask if they would like to procede. 12/14/18 O-RVL: REQUEST FOR ESTIMATE ONLY. Send Estimated costs to Aimee Gonzales for review and approval. Pending access controls and auto door operator quotes. Moved to Queue to start. 11/08/18 O-RVL: Scope is complete. Assisting the lock shop with pricing to provide the requestor an estime prior to start of construction. Walked a 2nd vendor , pending quote for access control card reader. 11/05 RV called vendor for quote, no reply. 10/29/18 RV: Conducted jobwalk with vendor last week. Pending quote from Vendor. Will follow up. | YES | FS | 0 | 2018 | 2019-02-01
19P000054 |  | 19P000054 | FALSE | GSOE | SL5-PATCH & PAINT OFFICE | Complete as of 10/10/18 | SPROUL | 2131 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-26 | [6 empty] | N/A |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000381 |  | 18P000381 | FALSE | ITS | SL5-ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 | FS to coordinate with customer to schedule the work for completion. | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 3 | 4 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL; This project is complete. Note, Duffy only wanted the dutch door completed……..12/14/18, DL; This project is in progress and should be complete shortly after the new year……`DL, 7/11/18; Need to walk the project and schedule the work…… | 2018-07-06 | Ron Veloz | 06/26/18 Ron V. visited site & met with Duffy. Scope of work for rm's 2103 & 2103 A requires: Painting of walls and conduit locted on the walls, replace damaged ceiling tiles, replace one damaged prismatic 2x4 light fixture lense, remove one tack board and shampoo carpet. Existing wall tiles to remain and receive paint. No work required in 2103 B per Duffy. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | FS | 0 | 2018 | 2019-02-01
18P000382 |  | 18P000382 | FALSE | ITS | SL5-ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 | Plans will be developed and will be submitted for review and approval. | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | PHYLLIS FRANCO |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL, This project is Complete……12/14/18, DL; This project is scheduled to be complete shortly after the winter break…….This project was scoped previously with the IR Team. We may need plans or a permit because we are installing a Dutch door…..DL, 7/11/18; Need to produce work orders and schedule the work….. DL, 7/25/18; Still need to produce work orders and schedule the work. Target date is 10/1/18 | 2018-07-06 | Ron Veloz | 06/29/18 Ron V: SOW, Remove the existing non rated solid core door & grille and replace with a new maple veneerd Dutch door with prefinished clear coat without grille. Door to be prepped on the hinge side with one continoues hinge. Confirm/field verify is a double bevel on door is requird. Do not prep the strike/lockset side.. Cylinder to be bored onsite by Lock shop. The top of the lower door to have a small shelf + - 6-8 inches wide, confirm size with Duffy prior to ordering the door. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | FS | 0 | 2018 | 2019-02-01
19P000197 |  | 19P000197 | FALSE | CNAS | SL5-PATCH AND PAINT OFFICE, LOBBY AND HALL | FS to coordinate with client to schedule work for completion. | COLLEGE BLDG NO | 0203B | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 44 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000471 |  | 18P000471 | FALSE | ITS | SL5-WCH INSTALL SECURITY FENCE | Complete as of 9/19/18 | CHUNG HALL | 134 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  |  | 5 | FALSE |  |  | 2018-06-12 | [6 empty] | DL, 7/4/18; Walked this project with Angel, This request is to install security fence with Sliding gate and welded webs to increase security. Space is vacant and ready to schedule work. Need to walk with Corey to see if this is a project they can do or sub out to De ANza fence......DL 7/25/18; Still need to walk project with Corey. Dl, 8/10/18; Site walk complete, we are waiting on estimates. WE will try and schedule the work with in the next 30- days....DL, 8/22/18; Work is scheduled for August 27th. Still need to order hardware.....DL, 9/6/18; The fence is installed and Angel is very Happy, but I need to check the project to verify we are good to go....DL, 9/19/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-02-01
19P000205 |  | 19P000205 | FALSE | BCOE | SL5-LABORATORY RENOVATION FOR NEW FACULTY | Plans under review by Fire Marshal; clarification required on sprinkler system. | BOURNS | A0328 | IN PROGRESS | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  | Dan Lerman |  | 4 |  | TRUE |  |  | 2018-08-23 | [6 empty] | 2/1/19, DL; This project is 99.9% Complete………..1/15/19, DL; This project is 90% complete. WE still need to finish snorkels and ceiling tiles. We should be 100% complete by 2/1/19……12/14/18, DL; This project is on schedule..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/4/18; This is a large scale project, we will walk with the trade supervisors next week. We will also work on the plans and schedule the work. Target Date is 1/1/19…..DL, 11/7/18; work is scheduled. We are working on the electrostatic paint contract. We are in plan check review process. There are questions about the fire sprinklers from Scott J. Sent Scott J. an email requesting a site visit to better determine if any work will be required on the sprinkler system….. |  | Ron Veloz | 10/03/18: RV spoke with Dan. He had previously met with Maggie and had scoped this project. | YES | FS | 0 | 2018 | 2019-02-01
19P000207 |  | 19P000207 | FALSE | CHASS | SL5-QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-08-23 | [8 empty] | Enrico Baez | 9/13/18 EB emailed Toya Adams to schedule site visit. 9/19/18 EB-Site visit scheduled for 9/20/18. 9/20/18 EB-Conducted site visit. Request to remove window in hall and install door. Interior space wall not to be removed. Secure doors, blank off and cover with sound soak. Replace carpet with Vinyl Plank, patch and paint. | YES | FS | 0 | 2018 | 2019-02-01
19P000208 |  | 19P000208 | FALSE | BAS | SL5-PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | Canceled per customer on priority list 9/17/18 | THE PLAZA |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | CARLA CHAPPLE |  | Dan Lerman |  | Canceled |  | FALSE |  |  | 2018-08-14 | [8 empty] | Enrico Baez |  | NO | FS | 0 | 2018 | 2019-02-01
19P000209 |  | 19P000209 | FALSE | PLANNING & BUDGET | SL5-OLD EH&S SITE- FS ANNEX A REMODEL | Scope of work has been reviewed and being scheduled for completion. | ENV H AND S | 100 | IN PROGRESS | Gerry Bomotti | TBD | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 2018-08-24 | [6 empty] | 9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen | Chris walked the project with Craig Kasten on 9/6. | YES | FS | 0 | 2018 | 2019-02-01
19P000210 |  | 19P000210 | FALSE | CNAS | SL5-CHEMICAL SCI Install Door In Doorway | FS to coordinate with client to scope the work. | CHEMICAL SCI | 0225A | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  |  |  | 25 |  | FALSE |  |  | 2018-08-24 | [7 empty] | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scope of work is complete. RV to upload docs to FAMIS. 10/03/18 RV: Install non rated door into an existing cased opening-for privacy & noise reduction. Will require carpentry-framing, patch, paint, and minor flooring/base repair. | YES | FS | 0 | 2018 | 2019-02-01
19P000211 |  | 19P000211 | FALSE | CAMPUS | SL5-LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | Reviewing campus standards for these project requests. | LIFE SCIENCE | 2545 | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-02-01
19P000212 |  | 19P000212 | FALSE | CAMPUS | SL5-REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500A | HOLD - FACILITIES SERVICES |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-02-01
19P000213 |  | 19P000213 | FALSE | CNAS | SL5-NEEDS FOR NEW WALL DISPLAY (MONITOR) | Duplicate request to 19P000031; Work to be completed on other project. | BIOLOGICAL SCI | 3101 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [11 empty] | FS | 0 | 2018 | 2019-02-01
18P000324 |  | 18P000324 | FALSE | PLANNING & BUDGET | SL5-HINDERAKER PATCH AND PAINT | Complete as of 7/11/18 | HINDERAKER | 4118 | COMPLETE | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-02-26 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000390 |  | 18P000390 | FALSE | PLANNING & BUDGET | SL5-UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD | Complete as of 8/24/18 | UV BLDG B | 0240B | COMPLETE | Gerry Bomotti | TBD | LESLIE ROSE |  | Paul Ditty |  |  | 1 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000482 |  | 18P000482 | FALSE | SoB | SL5-CARD ACCESS SYSTEM ANDERSON SOUTH | Complete as of 8/2/18. | ANDERSON |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-26 | [6 empty] | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with JasonDL, 7/11/18; Need to check in with Jason on status for his side of the project.....DL, 7/25/18; JAson's team is ready to install but the Anderson IT department does not have the necesary software. We will start the work when the software is up and running...... 8/12/18 DND FAMIS Status noted completion on 8/2/18. |  | Dan Lerman | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with Jason | YES | FS | 0 | 2018 | 2019-02-01
19P000217 |  | 19P000217 | FALSE | GSOE | SL5-PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 | FS to coordinate with client to scope work. | SPROUL | 1359 | IN PROGRESS | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-27 | [6 empty] | 2/1/19, DL; This proect will start on 3/1/18 and should be complete by 4/1/19…… | 2018-09-18 | Enrico Baez | 9/18/18 E. Baez Conducted site visit. Scope of work Carpentry Remove 20 feet of built-in wood cabinets and counter top. Install TV mount on South wall. Remove and replace white board on North wall. Abatement Abate approximately 200 square feet of 9â€ x 9â€ VCT tile and base cove Flooring Install carpet similar to what is in room 1357 Replace base cove. Walls Patch and paint walls. Electrical Install duplex outlet for TV Replace fluorescent lamps with LED lamps TV Install data point and Internet connection to support video conferencing. Custodial Vacuum dust from ceiling tiles. 9/13/18 EB-emailed Karen Naples to schedule site visit. 9/18/18 EB-Conducted site visit. Request to remove cabinet, abate VCT, install carpet, mount TV. Electrical and date lines needed. Install white board. Replace flourescent tube with LED. | YES | FS | 0 | 2018 | 2019-02-01
19P000017 |  | 19P000017 | FALSE | SoB | SL5-ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD | Complete as of 8/24/18 | ANDERSON 1 | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | DL, 9/6/18; Monitors are installed. Need to schedule the electrical. Target date is 9/21/18…… |  | Enrico Baez | 9/4/18 EB-This Project has been started. Monitors in place. Just need to run electrical. Dan aware. Refer to WO 19P000053. It asks for the same thing. Will request to close this and let Angela know. | YES | FS | 0 | 2018 | 2019-02-01
19P000053 |  | 19P000053 | FALSE | SoB | SL5-ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S | Complete as of 10/22/18. | ANDERSON 1 |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-04-13 | [6 empty] | DL 8/22/18; two out of four monitors are complete. WE still need to install powree at four locations…….DL, 9/6/18; Still need Electrical installed……. Planing to have complete by 9/21/18……. This is aqctually 4- monitors in four locations. We should ensure each monitor is treated as an indidual project.......DL, 9/19/18; All monitors are installed. Robert will schedule the electricans this week or early next week...DL, 10/4/18; This project is 100% Complete..... |  | Enrico Baez | DND 7/25/18: Emailed R. Veloz advising work order is closed; upon completion of the scope review, Ron to work with Zee for a Project Number to be created. | YES | FS | 0 | 2018 | 2019-02-01
19P000222 |  | 19P000222 | FALSE | BAS | SL5-PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER |  | PRINT MOD |  |  | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000224 |  | 19P000224 | FALSE | BAS | SL5-PAINT EXTERIOR RAMP AT HUB MODULAR | FS to coordinate with client to schedule work for completion. | PRINT MOD |  | QUEUE TO START | Gerry Bomotti | Georgianne Carlson | MIKE CLEMONS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5-UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [7 empty] | 2018-09-27 | Enrico Baez | 9/13/18 EB-emailed crystal Jimenez to schedule site visit. 9/19/18 EB-Scheduled site visit for 9/20. 9/29/18 EB- install keyless entry system on two doors. 10/15/18 EB-sent Aaron Seitz approx. cost of project. Awaiting respone to determine funding. | YES | FS | 0 | 2018 | 2019-02-01
19P000226 |  | 19P000226 | FALSE | CHASS | SL5-PAINT OFFICE HMNSS 3304 | Duplicate request; project to be completed on 19P000194 | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-08-28 | [8 empty] | Paul Ditty | Duplicate request; project to be completed on 19P000194 |  | FS | 0 | 2018 | 2019-02-01
19P000227 |  | 19P000227 | FALSE | BAS | SL5-DINING STORAGE ROOM CONVERSION | Scheduled work with trades anticipated completion December 2019. | BANNOCK J | J0100 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | DARCI LOMBARD |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-08-17 | [8 empty] | Enrico Baez | 9/12/18 EB-Install Drywall, Patch & Paint, cap water line, install VCT & Cove Base, Verify HVAC operation, replace hydralic door closer, install LED lamps, Security light. Scope sent to Edwin Melgar for approval. | YES | FS | 0 | 2018 | 2019-02-01
19P000229 |  | 19P000229 | FALSE | GSOE | SL5-RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR | FS to coordinate with client to scope work. | SPROUL |  | QUEUE TO START | Thomas Smith | Sally Tavizon | KAREN NAPLES |  |  |  | 4 |  | FALSE |  |  | 2018-08-29 | [8 empty] | Enrico Baez | 9/20/18 EB-conducted site visit 9/18. Request for tile and plumbing removal, patch and paint. To facilitate placement of printer system. E-mail sent to Monty on 9/14 asking for direction on renovating hallway space. Awaiting Susan's response per Monty. Entered scope on shared drive. Will need Fire Marshal approval to determine which of three possible locations will allow placing of WEPA system. 11/13/2018 E. Baez-Met with Ron Rector to discuss system placement. WEPA system is to be placed on second floor near vending machines on North side. See note in shared drive. Will need power and data connections. | YES | FS | 0 | 2018 | 2019-02-01
18P000428 |  | 18P000428 | FALSE | SoB | SL5-OLMSTED RM 2352 PATCH/PAINT | Complete as of 8/17/18 | OLMSTED | 2352 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-05-02 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
18P000463 |  | 18P000463 | FALSE | SoB | SL5-ANDERSON HALL PATCH/PAINT-102C | Complete as of 8/24/18 | ANDERSON 1 | 0102C | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-06-04 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000232 |  | 19P000232 | FALSE | BAS | SL5-BANNOCKBURN J-104 BREAK ROOM UPGRADE | Scheduled work with trades anticipated completion December 2019. | BANNOCK I | I0105 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | John Peraino |  | 6 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Enrico Baez | 9/19/19 EB-conducted site visit. Entered Scop in FAMMIS and in BZM projects on shared drive. Requires pluming for sink and disposal, electrical, lighting upgrade. | YES | FS | 0 | 2018 | 2019-02-01
19P000233 |  | 19P000233 | FALSE | BAS | SL5-PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | FS to coordinate with customer to scope the work. | MAIL | 884 | CANCELED BY FS | Gerry Bomotti | Georgianne Carlson | AMY EVERETT |  |  |  | 12 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Enrico Baez | Per Enrico, creating two individual WO's for Tile repair (19W004955) and door painting (19W004956). | YES | FS | 0 | 2018 | 2019-02-01
19P000234 |  | 19P000234 | FALSE | CNAS | SL5-PHYSICS 3005-WALL HOLES PATCH | Duplicate work request. | PHYSICS | 3005N | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-09-04 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
19P000235 |  | 19P000235 | FALSE | BAS | SL5-RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | Customer to determine scope of work. | ABER INVER | A0100 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 11 |  | FALSE |  |  | 2018-09-04 | [7 empty] | 2018-11-01 | Enrico Baez | 11/26/18EB-Tranfered FAMIS work order to John Peraino's bench. Estimate to customer needed, prior to moving forward with project. 11/26/18 EB-SCOPE entered Aberdeen Inverness • Paint acoustic panels. Customer to provide color specification. • Remove carpet and replace with customer specified vinyl plank flooring. Replace base board • Cut door to accept 16” x 7” glass lite. Frame as needed. • Paint door • Replace surface mounted light fixture with LED surface mounted fixture. Customer to approve design. • Clean, paint or replace A/C vents. • Remove louvered vent in wall for abandoned water cooler. Install sheet metal cover, paint to match new wall color. Pentland Hills -Rooms 105 and 107 • Install full height acoustic panels on three walls. • 4th wall on East side of each room gets mirror. Height of mirror to be flush with top edge of door casing. Mirror width to be between inside corner of wall and switch plate cover. Provide cut out in mirror for thermostat installation. • Replace all ceiling tiles. • Replace 2’ x 2’ ceiling light with 2’ x 4’ LED fixture-customer to approve design. Pentland Hills -Rooms 105 and 107 • Remove carpet and replace with vinyl plank flooring, replace base board • Fire rated doors to be replaced with fire rated doors with small lite, approx. dimensions 16’ x 7”. • Paint as needed. Lothian • Install full height acoustic panels on three walls. • 4th wall gets mirror height to be even with door casing height. Customer to determine location. • Replace all ceiling tiles. • Replace ceiling lights with LED fixtures. • Remove all carpet in rooms and replace with vinyl plank and new base board-customer to specify style and color. • Replace door wire reinforced glass with clear, non-reinforced fire rated glass. • Paint as needed. Suggested Vendor for sound absorbing paneling. Riverside Acoustics Contact: Keith Atkins 951-682-6123 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 Met with Bob and Lisa, no firm plans or ideas in place. Lisa will schedule site walk once they have determined what they want. 11/1/18 Conducted site visit with Bob and Lisa. | YES | FS | 0 | 2018 | 2019-02-01
19P000236 |  | 19P000236 | FALSE | BAS | SL5-EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION | Scheduled work with trades anticipated completion December 2019. | ABER INVER | A0100 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 10 |  | FALSE |  |  | 2018-09-04 | [7 empty] | 2018-11-01 | Enrico Baez | 11/27/18 EB-Entered scope of work. Transferred work order to John Peraino in FAMIS. Estmate to be provided prior to work start. Aberdeen Inverness Lobby across from RSO. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Pentland Hills 1st floor of I/J, K/L, M/N, O/P • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Pentland Hills Alcove between E&F building. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exterior wall adjacent to B-101 • Remove existing dual fountain. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exercise Room H-101 • Install HS where pluming repairs were made in East wall. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch all walls and Paint as needed. Glen Mor K-206 Fitness Room • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Glen Mor Pool area • Remove existing double water fountains and HS. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. • Repair any brick work as needed Lothian Hallway near Dining Hall cashier stand adjacent to fire extinguisher cabinet • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Sample sheet. https://www.restroomdirect.com/halsey-taylor-drinking-fountains-and-water-coolers.aspx 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Waiting for Lisa L. to schedule site visit. Total number of station and needs not completed. 11/1/18 EB Conducted site visit with Lisa and Bob. AI Replace Hydration Station (HS) in Lobby near RSO Pentland Hills Replace fountains with HS first floor I/J, K/L, M/N, O/P. Also remove fountains and install HS near B-101, Alcove between E&F, H-104. Glen Mor Remove fountain at pool & K-206 fitness room, replace with HS. Lothian Replace existing HS near cashier to Dining Hal | YES | FS | 0 | 2018 | 2019-02-01
19P000237 |  | 19P000237 | FALSE | GSOE | SL5-PATCH AND PAINT OFFICE - SPROUL 1206 | FS to coordinate with client to schedule work for completion. | SPROUL | 1206 | IN PROGRESS | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 2/1/19, DL; This project will start on 3.1.19. We will need to abate ACM before we can start. Jess will isuue the 14- day notification to the AQMD. Once we have confirmation, we will schedule the work…….. | 2018-10-05 | Enrico Baez | 0/5/18 E. Baez- conducted site visit. Carpenters: Removes sliding chalk boards in 1206 and 1206 and fill in with wall. Remove patched in panels on left of chalk board in 1206. Patch where " do not enter" signs were removed. Electricians: Disconnect power to two "do not enter" signs above doors. Abatement: Remove approx 300 sq.ft. of ACM VCT Flooring: replace flooring with either VCT of vinyl plank. Painters: Patch and paint, at least one wall accent wall. | YES | FS | 0 | 2018 | 2019-02-01
19P000018 |  | 19P000018 | FALSE | SoB | SL5-ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER | Complete as of 8/24/18 | ANDERSON 1 | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000241 |  | 19P000241 | FALSE | PLANNING & BUDGET | SL5-PATCH/PAINT IN OFFICE 2122 HINDERAKER | Canceled per customer call on 9/13/18 | HINDERAKER | 2122 | CANCELED BY CLIENT | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-06 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000030 |  | 19P000030 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT | Complete as of 10/10/18 | OLMSTED | 2301 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000243 |  | 19P000243 | FALSE | CNAS | SL5-GENOMICS 1206 - PATCH AND PAINT WALLS | FS to coordinate with client to schedule work for completion. | GENOMICS | 1206 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Paul Ditty |  | 49 |  | FALSE |  |  | 2018-09-06 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
19P000280 |  | 19P000280 | FALSE | SoB | SL5-ANDERSON HALL PAINT ONLY |  | ANDERSON 2 | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-13 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000245 |  | 19P000245 | FALSE | SOM | SL5-ADA COMPLIANT - AUTOMATIC DOOR ENTRY | FS to coordinate with client to scope the work. | SOM RSCH |  | HOLD - FACILITIES SERVICES | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 4 |  | FALSE |  |  | 2018-09-07 | [7 empty] | 2018-10-29 | Ron Veloz | 01/31/19 O-RVL: Chris at Lockshop reviewed the vendor quote and requested detailed equipment list. Pending revisions from vendor due this week. END--- 01/15/19 O-RVL: Delivered Access control quoute to Jason & Chris R for revie. They will respond with comments. Upon receicpt and confirmation, RV will complete docs on server folder and update FAMIS & Access DB. --- 01/11/19 O-RVL: Qualifying quote to verify proper components from door operator vendor expecting reply soon. 12/14/18 O-RVL: Received Quotes for Auto door operator and Access controls this week. RV to provide update & quotes to to Dan Lerman. Moving status to "Que to Start" on Minor Ren List & updating Project Folder. --- 11/07/18 O-RVL: Walked site with Access Control vendor --- 10/31/18 O-RVL: Walked site with Door Op vendor --- 10/29/18 O-RVL: Scope was Completed. RV to schedule job walks with Vendors. --- 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon | YES | FS | 0 | 2018 | 2019-02-01
19P000451 |  | 19P000451 | FALSE | SoB | SL5-ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 |  | ANDERSON 1 (N) | 58 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-15 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  |  |  |  | FS | 0 | 2019 | 2019-02-01
18P000261 |  | 18P000261 | FALSE | SOM | SL5-WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR | Complete as of 9/10/18 | WEBBER | 1143 | COMPLETE | Deborah Deas | Brandon Barbosa | LOURDES ESCAMILLA |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 7/11/18; Work orders are produced. Need to assign the work order and order material. I will review with Steve and verify target complete date….DL, 7/25/18; Still need to walk the project with Steve……DL, 8/10/18; Material is ordered. We will complete the install when the materila arrives.....DL, 8/22/18; Material should be on site with in 4- weeks. Will schedule install when material is on site. Target date is 9/20/18.......DL, 9/6/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 4/29/18; Pasted from work order;I"nstall a glass window 28x9 on office door in WEBBER, Room 1143. | YES | FS | 0 | 2017 | 2019-02-01
19P000248 |  | 19P000248 | FALSE | SOM | SL5-SOME--SOME INSTALL ELECTRICAL 1682 | FS to coordinate with client to scope the work. | SOM EDUC | 1682 | QUEUE TO START | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 2 |  | FALSE |  |  | 2018-09-10 | [8 empty] | Ron Veloz | 10/29/18 O-RVL: Scoping is completed. END--- 10/17/18: RV: Drawings are on server folder. END---10/08/18 RV: Spoke with Brandon B. Brandon will submitt BKM drawings via permit request through PD&C. 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon. Walked project with Brandon. SOW to install two each dedicated 120v/20a cicuits for new modular furniture one whip at each end of the office down the wall and one to two data drops overhead down wall. | YES | FS | 0 | 2018 | 2019-02-01
19P000249 |  | 19P000249 | FALSE | SOM | SL5-SOME-INSTALL LOCKERS | Lockers on order by customer; upon arrival to be installed. | SOM EDUC |  | CANCELED BY FS | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-07 | [6 empty] | DL, 11/7/18; It is my understanding the lockers are ordered, but we donot have a confirmed delivery date. Once the material is on site, we will schedule the installation…… |  | Ron Veloz | 01/31/19 O-RVL: Contacted Domonic and confirmed lockers will not be avialable to install and agreed to cancel the request orginated on 09/07/18 and will resubmit a new request upon delivery of the new lockers. RV emailed Customer Relations staff to cancle the project request via emails and cc Monty, Deborah H., Alan, Loretta on the communication. 01/10/19 O-RVL: Emailed Dominic Salazar on locker delivery ststus. Pending follow up call from customer to inform FS on delivery of lockers. 11/08/18 RV: Visited site existing lockers in place and in use. Will follow up with the requestor for locker delivery status to schedule. RV Spoke with Brandon Barbosa. Deparment will purchase lockers. 11/08/18 RV: Received email from Domonic Salazar on 10/25 Lockers are expected to arrive. | YES | FS | 0 | 2018 | 2019-02-01
18W006022 |  | 18W006022 | FALSE | SOM | INSTALL CURTAIN ROD IN RESEARCH SPACE | Complete as of 7/11/18 | SOM RSCH | 336 | COMPLETE | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-10-27 | [6 empty] | DL, 5/24/18; Need to review scope with Enrico….DL, 7/11/18; Enrico produced work orders for sheet metal shop. This is a singel trade project. |  | Enrico Baez | Blackout curtain needs to have a better way of being secured. Talked to Cory about fabricating a new curtain rod. 7/6/2018EB assigned to sheetmetal shop F-LNH | YES | FS | 0 | 2017 | 2019-02-01
18P000485 |  | 18P000485 | FALSE | SOM | SL5-SOMR PATCHING AND PAINTING | Complete as of 10/10/18 | SOM RSCH |  | COMPLETE | Deborah Deas | Brandon Barbosa | DANA ABOU ABBAS |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000252 |  | 19P000252 | FALSE | ATHLETICS | SL5-ATH DANCE SHOWER DOORS | FS to coordinate with customer to scope the work. | ATH DANCE | 0050K | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  |  |  | 3 |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB Replace aluminum and glass shower doors. Will need to contract work. Replace all rusty fixtures in showering space, repair/replace tile as needed. | YES | FS | 0 | 2018 | 2019-02-01
19P000009 |  | 19P000009 | FALSE | SOM | SL5-SOME -- PAINT, SPACKLE AND CLEANING NEEDED | Complete as of 10/10/18 | SOM EDUC | 2615 | COMPLETE | Deborah Deas | Brandon Barbosa | BEVERLEY HERBERT |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000012 |  | 19P000012 | FALSE | SOM | SL5-SOME--PATCH & PAINT | Complete as of 10/10/18 | SOM EDUC | 2638 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-07-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000014 |  | 19P000014 | FALSE | SOM | SL5-SOME - PATCH & PAINT | Complete as of 10/10/18 | SOM EDUC | 2609 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-07-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000256 |  | 19P000256 | FALSE | SPP | SL5-CHASS REMODEL - 4146 PATCH AND PAINT | FS to coordinate with client to schedule work for completion. | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  |  |  | 3 |  | TRUE |  |  | 2018-09-10 | [7 empty] | 2018-10-09 | Enrico Baez | 10/9/18 EB Sent Luis email, copied Mont too. Project will bw $25k-$30K. Asked Luis if we are to proceed. 10/15/18 E.Baez conducted site visit, Client requested cost estimate to construct 2-3 "huddle" Spaces with sound proof walls. Requires alterations to HVAC ducting, full height walls with doors, fire sprinkler additions, smoke detection additions, lighting changes. emailed Luis estimated cost of $25,000. 12/20/18 D. DINH: Spoke with customer, Luis Alvarez, and the project request has been modified to patch & paint and replacement of one ceiling tile. Customer to work with BKM to fulfill the wall partition request portion of the project. | YES | FS | 0 | 2018 | 2019-02-01
18P000470 |  | 18P000470 | FALSE | SPP | SL5-Student Check-in Lobby | Complete as of 8/23/18 | CHASS INT S | 4133 Corridor | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-11 | [6 empty] | DL, 6/16/18; I walked this project with Luis and Mark this week. They want this work completed by July 9th. Paint, data, electrical, chair rail and signage is requested. I need to review project with Paul and Robert C. DL, 7/11/18; Robert C. Ordered material and we will complete the install first part of next week We will scheudle the paint after Robert is Complete. Target Complete Date is 7/2018......DL, 7/25/18; WE have the electrical materila, plans were submitted. Once plans are reviewed and approved, we will proceed with the work. Target date is two weeks after plans are approved......DL, 8/10/18; Eletrical is complete. Pending paint. Paint will be scheduled in the near future. DL, 8/22/18; This project will be Complet on Saturday.....DL, 9/6/18. I miossed the chair rail request on this project. I will order the chair rail in the near future. The chair rail is the only item needed to complete this project. Aprroximately 20 lineal feet......DL, 9/19/18; Chair rail is ordered. We will schedule the install when the material arrives....... |  | Dan Lerman | Added by customer on prioritization; timeline and scope tbd. 4/25 EB emailed Christina to schedule site visit. No work order Luis to submit Google doc. To A&E sevral trades invlved. DND 6/13 Project rescoped and priorities adjusted per meeting between Dan and Luis Alvarez. | YES | FS | 0 | 2018 | 2019-02-01
19P000266 |  | 19P000266 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
19P000268 |  | 19P000268 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH AND PAINT 20C | FS to coordinate with client to schedule work for completion. | ATH DANCE | 20C | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
19P000269 |  | 19P000269 | FALSE | ATHLETICS | SL5-ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | Project is not within the purview for completion; condition is fair and usable. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 5 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18…..This is a cooman area. Is this recharge work……. | 2018-09-27 | Enrico Baez | 2/5/19 E. Baez. Common spaces are managed by Facilities Services. Any work done in corridors, stairwells and open spaces will be assessed by FS. 11/20/18 E. Baez-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB-Request for installing vinyl flooring. Remove and replace existing Terrazo and ceramic floor tile in 1st floor lobby and stairs to basement. | YES | FS | 0 | 2018 | 2019-02-01
19P000270 |  | 19P000270 | FALSE | ATHLETICS | SL5-ATH DANCE-WEIGHT ROOM DROP DOWN CEILING | FS to coordinate with customer to scope the work. | ATH DANCE | 78 | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 14 |  | FALSE |  |  | 2018-09-12 | [8 empty] | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB remove all t-bar ceiling components. Will need relocation of supply and return registers, lighting Alarms, Etc. |  | FS | 0 | 2018 | 2019-02-01
19P000271 |  | 19P000271 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 | FS to coordinate with client to schedule work for completion. | ATH DANCE | 3 | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-09-12 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
19P000272 |  | 19P000272 | FALSE | ATHLETICS | SL5-NEED URINAL DIVIDERS | FS to coordinate with customer to scope the work. | ATH DANCE | 50E | HOLD - FACILITIES SERVICES | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 13 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 1/15/19 E Baez. Per "Monty" project cancelled to be placed on Deferred Maint. list. emailed Chris P. to provide renovation cost and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Install dividers for urinals. Wall is tile. |  | FS | 0 | 2018 | 2019-02-01
19P000273 |  | 19P000273 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-12 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
19P000274 |  | 19P000274 | FALSE | ATHLETICS | SL5-RIV SPORTS CPX - REPLACE URINALS | FS to coordinate with customer to scope the work. | RIV SPORTS CPX |  | HOLD - FACILITIES SERVICES | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 15 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-10-15 | Enrico Baez | 1/14/19 E Baez. Per "Monty" this project to go on deferred maint. list. emailed Chris Pillen to provide coast and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27. 10/3/18 EB not time to visit on 9/27. will schedule follow up meeting. 10/15/18 EB conducted site visit, 11 urinals to be replaced. | YES | FS | 0 | 2018 | 2019-02-01
19P000275 |  | 19P000275 | FALSE | ATHLETICS | SL5-SOFTBALL STG PRESS BOX AC ADDITION | FS to coordinate with customer to scope the work. | SOFTBALL STG |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 6 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18; I checked on this recently and this is not a building, it is stoarge and should be recharge work…. | 2018-09-27 | Enrico Baez | 2/5/2019 E Baez Client wants a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. Client will need to fund this project as this is not a core building 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Client want a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. |  | FS | 0 | 2018 | 2019-02-01
19P000276 |  | 19P000276 | FALSE | ATHLETICS | SL5-TRACK BLEACH-PUBLIC RESTROOMS UPGRADE | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | TRACK BLEACH |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 16 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 11/20/18 EB Project cancelled, will be addressed by PD&C. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB conducted site visit, Client wants additional toilet in mens room, changing table and lighting improvements. ADA Issues. Also spoke with Scott Donnell he has project . | YES | FS | 0 | 2018 | 2019-02-01
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5-ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 10 |  | FALSE |  |  | 2018-09-12 | [6 empty] | ??????? | 2018-09-27 | Enrico Baez | 1/14/19 E Baez. Per "Monty" Athletics are to pay for this project. Joe Erbland emailed to determine if funding has been approved. Waiting on response. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB Install keyless entry system for building exterior. | YES | FS | 0 | 2018 | 2019-02-01
19P000255 |  | 19P000255 | FALSE | SPP | SL5-CHASS INT N REMODEL - 4022 PATCH AND PAINT | Complete as of 10/10/18 | CHASS INT N | 4022 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-02-01
19P000279 |  | 19P000279 | FALSE | ITS | SL5-HUB - ADD 2 POWER OUTLETS |  | HUB |  |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-09-13 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000263 |  | 19P000263 | FALSE | SPP | SL5-CHASS NORTH REMODEL - 4009 PATCH AND PAINT | Complete as of 11/8/18 | CHASS INT N | 4009 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-09-11 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-02-01
19P000283 |  | 19P000283 | FALSE | CNAS | SL5-HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  |  |  | 20 |  | FALSE |  |  | 2018-09-05 | [7 empty] | 2018-09-19 | Ron Veloz | 10/17/18 RV: All construction information is on the server folder. Pending Saftey MOP's from Beiwei. Left message with her on Monday 10/15 for status. 10/03/18 RV: SOW, Install safety guard railing and apply yellow markings (leading edge 6'from perimeter) on the Winston Chung Roof. 09/19/18-Scope is complete, received safety requirements prepared by EH&S/Beiwei. RV to upload onto FAMIS. | YES | FS | 0 | 2018 | 2019-02-01
18P000478 |  | 18P000478 | FALSE | UNDERGRAD ED | SL5-CARPET, PAINT, & AIR HANDLING MODIFICATION | Complete as of 10/22/18. | HINDERAKER | 1120H | COMPLETE | Jennifer Brown | Tracey Scholtemeyer | TRACEY SCHOLTEMEYER |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-16 | [6 empty] | DL, 7/4/18; This project is scoped; Need to remove Switch gear storage rack components, remove electrical conduits, plywood backer board from walls, paint and floor covering. We will schedule this work to be complete by Fall 2018 academic year....DL, 7/11/18; Need to produce work orders and schedule the work. Target Complete date is 9/14/18... Space is vacant....DL, 8/10/18; Work has started and we are on schedule...... DL, 8/22/18; Demo is almost complete. This target date is 9/21/18......9/19/18; All trades are complete. New carpet to be installed on 9/21/18. .....DL, 9/19/18; This project is scheduled to be complete this week....... |  | Dan Lerman | 7/9 EB-Spoke with Dan, he has already scoped this. | YES | FS | 0 | 2018 | 2019-02-01
19P000285 |  | 19P000285 | FALSE | CNAS | SL5-PAINT AND PATCH PI OFFICE |  | ENTOMOLOGY | 269 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-09-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000286 |  | 19P000286 | FALSE | CHASS | SL5-FACULTY OFFICES: TOUCH UP PAINT |  | HUM & SOC SC | 2005 | QUEUE TO START | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-09-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18W015691 |  | 18W015691 | FALSE | VC-RED | SL5-BOYCE CONNECT WASHER AND DRYER | Complete as of 7/11/18 | BOYCE | 6444 | COMPLETE | Michael Pazzani | Laura Manor | DIERK BIGGS |  |  |  |  | 1 | FALSE |  |  | 2018-05-30 | [6 empty] | DL, 7/11/18; This project is in progress and almost complete. Target complete date is 7/20/18….. |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-02-01
19P000288 |  | 19P000288 | FALSE | CNAS | SL5-COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS |  | COLLEGE BLDG NO | 202 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-19 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18W013973 |  | 18W013973 | FALSE | VC-RED | SL5-BSL3 FACILITY- ASSEMBLE AND INSTALL | Complete as of 9/24/18 | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2018-04-19 | [6 empty] | FAMIS NOTES 8/22: Plumbing filter system was installed and ice maker installed. Request for microscope and incubator moved into containment by customer. Complete 9/24/18 |  | Enrico Baez | 5/16/18 EB conducted site visit. 5/22/18 EB appliances dented, vaccum pump not on site. 6/19/18 emialed Chrystal to see if appliance have been replaced. 7/16/18 emailed Chrystal Jimenez asking for update. 8/7/18 EB Replacement appliances | YES | FS | 0 | 2018 | 2019-02-01
19P000292 |  | 19P000292 | FALSE | CNAS | SL5-GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER | Site vist completed; identifying a feasabile site location for work. | GEOLOGY |  | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 18 |  | FALSE |  |  | 2018-08-10 | [6 empty] | 2/1/19, DL Electrical is complete. WE will pour Concrete next week. We will schedule the fence install 28- days after concrete is poured………; Th1/15/19, DL; Plans are approved, we will start the work in the next two weeks……12/14/18, DL; Plans are almost complete. We will schedule the work after plans are approved……DL, 11/7/18; Conducted site visit with Chris P. We need to confirm a feasable site location before we move forward with the work…. |  | Ron Veloz | 10/30/18 RV: Chris Pillen and D. McWilliams aggreed to leave the building in place and place a concrete pad with a chain link fence adjacent to the existing structure. 10/17/18 RV: SOW, demolish walls and roof. Verify and cap existing underground utilities. Remove overhead electrical from power pole to the building. The concrete pad to remain and install a 6'H fence with gate around the pad. Bring Power below grade to pad location. Met with C.Pillen and Dan to discuss alternate options. Photos and equipment info is on the server file. | YES | FS | 0 | 2018 | 2019-02-01
19P000293 |  | 19P000293 | FALSE | ITS | SL5-PAINT ESTIMATE REQUEST | Canceled by Customer 10/24/18 | TELEPHONE |  | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-21 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-01
18P000379 |  | 18P000379 | FALSE | VC-RED | SL5-UOB PATCH AND PAINT | Complete as of 8/24/18 | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-05 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000296 |  | 19P000296 | FALSE | CAMPUS | SL5-MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB | Plans and permits to be developed for this project. | MAT SCI ENGR |  | PLAN DEVELOPMENT/CHECK |  |  | MILLY PAREDEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-09-25 | [6 empty] | 2/1/19, DL; Permits are approved, we will schedule the project in the next 2- weeks and hope to be complete by the end of February….12/14/18, DL; Rendering has been given to Ron R. Ron will present to Gerry for review and approval. Once approved, we will proceed with plans and permits……DL, 11/7/18; Need to find out where this project stands in regards to the priioroity….. Site vist was conducted and scope of work is verified. Plans and permits will be required for the work….. |  | Ron Veloz | 10/19/18 O-RVL: Walked the proposed location with Dr. Barsukov to review needs and location for nitrogen tanks in the hall. DL suggested to construct a wall with double doors approx 2' below the ceiling height. 09/27/18 O-RVL: Walked site with Chris P, Dan L., Deborah Mc Williams & Mayela C to review SOW. | YES | FS | 0 | 2018 | 2019-02-01
19P000298 |  | 19P000298 | FALSE | CNAS | SL5-SPIETH - PREP LAB FOR FACULTY SEARCH |  | SPIETH | 1363 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  |  |  | 0 |  | FALSE |  |  | 2018-09-26 | [8 empty] | Ron Veloz | 01/15/19 O-RVL: RV to scope once priority is established. RV updated notes with information provided from Deborah Mc Williams. Spieth 1363 – Wet Lab Space Note by DMcWilliams.: "There is evidence in the ceiling and along one wall of a water intrusion issue, i.e. peeling paint, leaking and rusted pipes, etc. The cause of this damage needs to be investigated and repairs confirmed, including painting the wall and ceiling where damage is visible". Patch/paint Re-finish, re-surface – existing cabinets Re-finish and/or replace bench-tops If both sinks cannot be significantly cleaned, they should be replaced, Replace faucets at both sink locations. Clean existing Chemical fume hood Repair or replace self-closing chemical / flammables storage cabinet On one bench remove overhead shelving unit and relocate electrical outlets to the ends of bench to accommodate large desktop equipment. Cap off remaining utilities for potential use/re-connection in the future. Remove shelves on west wall to accommodate siting of large floor-standing equipment before patch and painting. Also, add 120/240 electrical outlets (raceway) along this wall. Replace flooring -- this depends on what we decide about removing the walk-in fume hood listed below Add GFCI outlets near water sources Requires a connection to a DI water system Other utilities are required in this room and at what locations, e.g. air, oxygen, gas, vacuum, etc.? Remove existing walk-in Fume Hood (if cost for this issue does not trigger project over $50k) – Please assess/cost out and advise prior to project. Spieth 1364 – Lab Support Space work: Patch/paint –Re-finish, re-surface – existing cabinets (non-porous surface), Re-finish and/or replace benchtops, If sink cannot be significantly cleaned, they should be replaced Replace faucets at sink location. Add GFCI outlets near water sources Requires a connection to a DI water system" | NO | FS | 0 | 2018 | 2019-02-01
19P000299 |  | 19P000299 | FALSE | CNAS | SL5-SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 |  | SPIETH | 3378 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000300 |  | 19P000300 | FALSE | CHASS | SL5-HUM & SOC SC--URGENT: PAINT AND PATCH WALLS |  | HUM & SOC SC | 4403 | QUEUE TO START | Milagros Pena | Cindy Williams | ANDREA HERAZ |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000301 |  | 19P000301 | FALSE | CNAS | SL5-SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH |  | SCIENCE LAB1 | 214 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-09-27 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000306 |  | 19P000306 | FALSE | CHASS | SL5-HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 |  | CHASS INT N | 4017 | QUEUE TO START | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-01 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000442 |  | 18P000442 | FALSE | VC-RED | SL5-FAWCETT LAB 203 PATCH & PAINT | Complete as of 8/24/18 | FAWCETT LAB | 203 | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 3 | FALSE |  |  | 2018-05-18 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-01
19P000308 |  | 19P000308 | FALSE | BAS | SL5-ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK | Scheduled work with trades anticipated completion December 2019. | ABER INVER |  | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… |  | Enrico Baez | 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. |  | FS | 0 | 2018 | 2019-02-01
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5-RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 7 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB approx. 16-20 doors need repair. Sand, patch, repair as needed. Re-varnish. | YES | FS | 0 | 2018 | 2019-02-01
19P000312 |  | 19P000312 | FALSE | BCOE | SL5-VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP |  | STUDENT SERV | 1227 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000313 |  | 19P000313 | FALSE | CHASS | SL5-HUMANITIIES SOCSCI - PATCH HOLES & PAINT - |  | HUM & SOC SC | 1203 |  | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000044 |  | 19P000044 | FALSE | VC-RED | SL5-PATCH AND PAINT | Complete as of 10/10/18 | SPIETH | 345 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19W003050 |  | 19W003050 | FALSE | VC-RED | SL5-SPEITH HALL - PATCH & PAINT HOLE IN WALL | Complete as of 10/10/18 | SPIETH | 0359A | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000317 |  | 19P000317 | FALSE | BAS | SL5-HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 |  | PENTLAND A |  |  | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER | [5 empty] | FALSE |  |  | 2018-10-03 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000318 |  | 19P000318 | FALSE | CNAS | SL5-GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE |  | GEOLOGY | 420 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000319 |  | 19P000319 | FALSE | CNAS | SL5-ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB |  | ENTOMOLOGY | 139 |  | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000322 |  | 19P000322 | FALSE | BCOE | SL5-CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT |  | CHUNG HALL | 103 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-05 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000326 |  | 19P000326 | FALSE | VC-UNIV.ADV. | SL5-HINDERAKER - PATCH & PAINT |  | HINDERAKER | 1136 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-08 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000340 |  | 19P000340 | FALSE | CNAS | SL5-PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE |  | SKYE HALL | 349 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | VICTORIA AVALOS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [8 empty] | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000341 |  | 19P000341 | FALSE | CNAS | SL5-PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL |  | PIERCE |  | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000346 |  | 19P000346 | FALSE | CNAS | SL5-I&Q--PAINTING ROOMS IN THE I&Q |  | EAST I&Q FAC |  |  | Kathryn Uhrich | Deborah McWilliams | IMAD BAYOUN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000347 |  | 19P000347 | FALSE | CNAS | SL5-SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT |  | SPIETH | 3320 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000353 |  | 19P000353 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT-2348 |  | OLMSTED | 2340 | QUEUE TO START | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-19 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000354 |  | 19P000354 | FALSE | SOM | SL5-WEBBER 2130A-PAINT CHERI'S NEW OFFICE |  | WEBBER | 2130A | QUEUE TO START | Deborah Deas | Brandon Barbosa | DOMINIC SALAZAR |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-19 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000356 |  | 19P000356 | FALSE | CHASS | SL5-PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT |  | HUM & SOC SC | 4401 | QUEUE TO START | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-24 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000357 |  | 19P000357 | FALSE | CHASS | SL5-PATCH AND PAINT WALLS, TIME SENSITIVE |  | HUM & SOC SC | 1302 | QUEUE TO START | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-10-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000358 |  | 19P000358 | FALSE | CNAS | SL5-GEOLOGY - ACCOMMODATION REQUEST |  | GEOLOGY |  | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  |  |  | 0 |  | FALSE |  |  | 2018-10-26 | [7 empty] | 2019-02-07 | Ron Veloz | 02/07/19 O-RVL: RV changed title from "Geology" to "Physics". SOW is completed and on the server. Emailed a copy of SOW to FS team on 2/7. Received email from Ron Rector requesting Dan L. to provide Ronda Inzuna status update. END--- 01/31/19 O-RVL: Intake in progress. 01/15/19 O-RVL: Updated notes, the following SOW was from the requestor. --- 12/14/18 O-RVL: RV walked the site with Deborah Mc Williams on Mon 12/10. RV to create SOW. Returned request back to O-UA1 and will work from O-UA1 until the project is prioritized. "Potential scope of work for accommodation request: 1. Pour 10x10 cement pad for reserved electric transportation vehicle. 2. Electric charge station 3. appropriate signage" --- Deborah McWilliams is the main contact 951-218-3720 --- 11/14/18 RV: RV & Monty Received an "FYI" email from from Deborah Mc Williams on 11/09/18 with information related to the approval of the charging station --- location currently undergoing review by the CBO. | YES | FS | 0 | 2018 | 2019-02-01
19P000360 |  | 19P000360 | FALSE | CNAS | SL5-GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING |  | GEOLOGY | 1444 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000361 |  | 19P000361 | FALSE | CHASS | SL5-OLMSTED-PATCH & PAINT/REPLACE CARPET |  | OLMSTED |  | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000362 |  | 19P000362 | FALSE | CHASS | SL5-PATCH & PAINT/REPLACE CARPET (HALLWAY) |  | OLMSTED |  | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000364 |  | 19P000364 | FALSE | CHASS | SL5-PATCH AND PAINT |  | CHASS INT S | 3106 |  | Milagros Pena | Cindy Williams | FRANCESCA MOREIRA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-30 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000366 |  | 19P000366 | FALSE | FAC-PLNG-DESIGN-CONST | SL5-FACILITES SERVICES ADMIN-BREAKROOM & RECEPTION REMODEL |  | CORP B |  |  | Susan Marshburn | Da Lan Dinh | DALAN DINH | [5 empty] | FALSE |  |  | 2018-10-31 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000367 |  | 19P000367 | FALSE | CNAS | SL5-SCILAB 1 0211- PATCH & PAINT |  | SCIENCE LAB1 | 211 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-31 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000369 |  | 19P000369 | FALSE | CNAS | SL5-PIERCE - PAINT IS PEELING OFF WALLS |  | PIERCE | 3341 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-11-01 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
18P000337 |  | 18P000337 | FALSE | VC-STU.AFF. | SL5-MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET | Plans are approved for work to commence; scheduled for start on 11/13/18. | HEALTH SERV | 414 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-12 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18….Need to work on plans and permits….DL, 7/11/18; Gunther is working on plans. Target complete date is 9/14/18….DL, 7/25/18; Planning to submit plans for review next week. We will schedule the work once we have approved plans…….DL, 8/8/18; This is a structual wall and needs to be engineered. We are meeting with the Structual engineer on 8/9/18 to determine if project is possible.....DL, 8/22/18; Working on EDPA for Structual engineer; project timeline is late Fall. 9/19/18; The Agreement / Cointract for the structual engineer is processed for this project. We should have plans from the structual engineer to submitt to the Building Official and fire marshal with in 4- weeks......dl, 10/4/18; Plans are almost complete and we will submit them for review by the end of the week.....DL, 11/7/18; Plans are approved. WE are schedule to start this Project on Tuesday 11/13/18. Target complete date is by the end of the winter break..... |  | Enrico Baez | Cut wall between rooms 414 and 401, Case and trim opening, install carpet in- DL, 5/10/18; Gloria Vera is the contact; 827-5532 | YES | FS | 0 | 2018 | 2019-02-01
19P000371 |  | 19P000371 | FALSE | CHASS | SL5-URGENT PATCH AND PAINT IN CHAIR'S OFFICE |  | HUM & SOC SC | 1213 | QUEUE TO START | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-11-05 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000037 |  | 19P000037 | FALSE | VC-STU.AFF. | SL5-HEALTH SERVICE BLDG--PATCH WORK AND PAINTING | Complete as of 10/22/18. | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-07-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000378 |  | 19P000378 | FALSE | CHASS | SL5-PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 |  | HUM & SOC SC | 1613 | QUEUE TO START | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-11-13 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000380 |  | 19P000380 | FALSE | VC-STU.AFF. | SL5- PATCH AND PAITN- WALL PAINT IS PEELING |  | HEALTH SERV | 404 | QUEUE TO START | Brian Haynes | Cathy Eckman | SAMANTHA HARRIS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-19 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000384 |  | 19P000384 | FALSE | ENROLLMENT SERVICES | SL5-PATCH HOLES IN WALL AND PAINT |  | STUDENT SERV | 2234 | QUEUE TO START | LaRae Lundgren | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-20 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000386 |  | 19P000386 | FALSE | PROVOST/EVC | SL5-ROOM CHANGES |  | STUDENT SERV | 3106A | QUEUE TO START | Cynthia Larive | Luisa Levario | STEPHANIE ARCINIEGA |  |  |  | 0 |  | FALSE |  |  | 2018-11-20 | [8 empty] | Ron Veloz | 02/07/19 O-RVL: RV completed Intake & Moved to "Que to Start". END---02/06/19 O-RVL: RV updates, Scope of work is to remove shelving from room, patch and Paint. Dan requested info on room availability. RV contacted Danielle for follow up from 02/05 call. RV will visit site, take pics, and follow up with Dan L.erman. Danielle reported that room 310C is vacant and available. | NO | FS | 0 | 2018 | 2019-02-01
19P000390 |  | 19P000390 | FALSE | CNAS | SL5-BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  |  |  | 0 |  | TRUE |  |  | 2018-11-29 | [8 empty] | Ron Veloz | 02/07/19 O-RVL: Monty asked RV to follow up on this request. Ron V scheduled meeting with April Meinzer on 2/7 at 1:30pm to review intake information for the proposed project at room 5494. |  | FS | 0 | 2018 | 2019-02-01
19P000399 |  | 19P000399 | FALSE | GRAD.DIV | SL5-NEW CARPET + WALL PAINT |  | UNIV OFC BLD | 100 | QUEUE TO START | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-06 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000401 |  | 19P000401 | FALSE | PLANNING & BUDGET | SL5 - PATCH HOLES IN WALL AND PAINT |  | HINDERAKER | 4148E | QUEUE TO START | Gerry Bomotti | TBD | SHANNON TIMMONS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000405 |  | 19P000405 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED |  | HEALTH SERV | 0100D | QUEUE TO START | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-11 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5--HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 |  | HINDERAKER | 1101 | PROJECT INTAKE | Kim Wilcox | Karim Zahedi | ALEXIS RAMBAUD |  |  |  | 0 |  | FALSE |  |  | 2018-12-11 | [8 empty] | Ron Veloz |  |  | FS | 0 | 2018 | 2019-02-01
19P000408 |  | 19P000408 | FALSE | SOM | SL5 - PATCH & PAINT - 2605 SOM ED |  | SOM EDUC | 2605 | QUEUE TO START | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-12 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000410 |  | 19P000410 | FALSE | SOM | SL5-PAINT OFFICES AT UC PATH |  | INTELLICTR |  | QUEUE TO START | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-14 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000411 |  | 19P000411 | FALSE | GRAD.DIV | SL5- PAINT, CARPET AND BLINDS |  | UNIV OFC BLD | 150 | QUEUE TO START | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-14 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000418 |  | 19P000418 | FALSE | VC-UNIV.ADV. | SL5--BOTANIC UCR BOARD OF TRUSTEES MTG./BOTANIC GARDENS CONF. RM |  | BOTAN INFO C | 1 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | LADONNA ARDARY |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000420 |  | 19P000420 | FALSE | CHANCELLOR | SL5-PATCH AND PAINT WALL |  | SKYE HALL | 325 | QUEUE TO START | Kim Wilcox | Karim Zahedi | REYNA ALARCON |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-19 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000424 |  | 19P000424 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET |  | CHUNG HALL | 445 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-12-20 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000425 |  | 19P000425 | FALSE | PLANNING & BUDGET | SL5-PAINT VIDEO PRODUCTION SUITE & HANG ITEMS |  | HINDERAKER | 1159A | QUEUE TO START | Gerry Bomotti | TBD | LISA CUSICK |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-20 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000428 |  | 19P000428 | FALSE | ENROLLMENT SERVICES | SL5--STUDENT SERVICES AVC OFFICE PREPARATION |  | STUDENT SERV | 3102 | CANCELED BY CLIENT | LaRae Lundgren | TBD | ANGIE GRAY |  |  |  | 0 |  | FALSE |  |  | 2019-01-03 | [8 empty] | Ron Veloz | 02/06/19 O-RVL: Updating notes. "Cancelled by Angie Grey on 1/22/19". | N/A | FS | 0 | 2019 | 2019-02-01
19P000429 |  | 19P000429 | FALSE | CHASS | SL5--CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING |  | COLL BLDG SO | 103 | QUEUE TO START | Milagros Pena | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-01-03 | [11 empty] | FS | 0 | 2019 | 2019-02-01
19P000439 |  | 19P000439 | FALSE | VC-RED | SL5--SPIETH PATCH AND PAINT ROOM 335 |  | SPIETH | 335 | QUEUE TO START | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-08 | [11 empty] | FS | 0 | 2019 | 2019-02-01
19P000442 |  | 19P000442 | FALSE | BCOE | SL5- WINSTON CHUNG- PATCH/PAINT ROOM 319 |  | CHUNG HALL | 319 | QUEUE TO START | Christopher Lynch | Maggie Souder | BILL BINGHAM |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-09 | [11 empty] | FS | 0 | 2019 | 2019-02-01
19P000445 |  | 19P000445 | FALSE | BCOE | SL5-BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT |  | BOURNS HALL | B0328D | PROJECT INTAKE | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  |  |  | 0 |  | FALSE |  |  | 2019-01-11 | [8 empty] | Ron Veloz | 2/7/19: Alan S. Customer Relations Team to follow-up with customer re: change in scope of work. |  | FS | 0 | 2019 | 2019-02-01
19P000124 |  | 19P000124 | FALSE | VC-STU.AFF. | SL5-PAINT ROOMS 115 AND 116 | Complete as of 10/22/18. | COSTO HALL | 125 | COMPLETE | Brian Haynes | Cathy Eckman | LINDA KELLEY |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000453 |  | 19P000453 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT |  | CHUNG HALL | 447 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-17 | [11 empty] | FS | 0 | 2019 | 2019-02-01
19S000833 |  | 19S000833 | FALSE | SOM | Add access control to entry doors | Canceled request per conversation with client; customer to coordinate for a contractor to complete project. | HECKMAN ICEM | Entry Doors | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | Canceled | 2 | FALSE |  |  | 2018-07-17 | [8 empty] | Ron Veloz | Will Meet with Chris Pillen on 08/23/18 to review notes by C.P. on FAMIS. 08/23/18-RV: Followed up with Chris P for update on the work request notes. Recommended to contact Brandon to procure a local vendor. 08/24/18-RV spoke with Brandon Barbosa to determine a plan to complete the request and will pursue pricing and oversee the installation. 08/27/18 RV: Update: Brandon will PM the project on his own. 09/19/18: UPDATE-CANCELLED BY Brandon. See notes above. | YES | FS | 0 | 2018 | 2019-02-01
19W002419 |  | 19W002419 | FALSE | ITS | SL5-ITS CENTER - INSTALL CARD READER ACCESS |  | ITS CENTER | 161 |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-08-09 | [11 empty] | FS | 0 | 2018 | 2019-02-01
19P000172 |  | 19P000172 | FALSE | VC-STU.AFF. | SL5-HEALTH SERV- PAINT RESTROOM IN LABORATORY | Complete as of 11/8/18 | HEALTH SERV | 0113A | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19W003012 |  | 19W003012 | FALSE | CNAS | SL5-FIX RESTROOMS (PAINT AND FLOORS) | FS to coordinate with client to schedule work for completion. | CHAPMAN | 5 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 51 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19P000238 |  | 19P000238 | FALSE | VC-UNIV.ADV. | SL5-PATCH & PAINT HINDERAKER 1136 | Pending completion of one room outstanding for scheduling. | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19W006811 |  | 19W006811 | FALSE | VC-STU.AFF. | SL5-HUB 353--PATCH AND PAINT WALL |  | HUB | 353 |  | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-01
19W007474 |  | 19W007474 | FALSE | CNAS | SL5-BG - RAILROAD TIE WALLS |  | BOTANIC GARDENS |  | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV | [5 empty] | FALSE |  |  | 2018-11-07 | [7 empty] | 2018-12-10 | Ron Veloz | 01/09/19 O-RVL: REQUEST FOR ESTIMATE, Not a Project. RV To schedule a site visit with C. Pillen and Chad Chambers to evaluate if repairs are possible. 12/10/18 O-RVL: REQUEST FOR ESTIMATE. Ron V walked with D. McWilliams & Jodie and identified the railroad tie retaining wall area requiring repairs. Jodie would like an estimate to repair the leaning railroad ties at specified areas. RV to meet with Chris P. and or Chad Chambers to determine if FS can perform work and or provide an estimated cost to perform work. 11/07/18 O-RVL: Received an email form Deborah Mc. to discuss the wall at Thursday during our 1-1 meeting. | YES | FS | 0 | 2018 | 2019-02-01
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Roofing - Spieth Hall/LSP | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. |  |  | In Programming | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 432510 |  | 2016-02-25 | Re-bid | 2019-08-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
3035b | 3035b |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Roofing - Olmstead Hall | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. 112010 project budget is $456,163.00. Estimated construction cost is $425,680.00. Bidding 8/8/2017. |  |  | In Programming | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 383112 |  | 2016-02-25 | Re-bid | 2019-08-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-01
18P000484 |  | 18P000484 | FALSE | ATHLETICS | SL5-INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | Project will be managed by A&E for completion. | SOFTBALL STG |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-26 | [6 empty] | 2/1/19, DL; This is a PD&C Project due to IRT walk. Project will exceed $50,000……….. |  | Enrico Baez | 12/6/18 EB Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | NO | FS | 0 | 2018 | 2019-02-16
19P000027 |  | 19P000027 | FALSE | ATHLETICS | SL5-ATHLETICS PATCH & PAINT ROOM | Complete as of 9/19/18 | ATH DANCE | 0120C | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | DL, 9/19/18; This Project is 100% Complete……. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000328 |  | 18P000328 | FALSE | ATHLETICS | SL5-HINDERAKER BASEMENT OFFICE REPAIR | Complete as of 7/11/18 | HINDERAKER |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-01 | [6 empty] | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with Paul. Paul will complete as in the near future. Carpet will be installed shortly after......5/21/18, Painters started paint. Should be complete with paint by the end of the week....DL, 5/24/18; Painters are complete. Jess will schedule the carpet install.....DL, 6/12/18; Project is 98% Complete. Carpenters need to under cut two doors to accomodate the carpet.....DL, 7/11/18; This Project 100% Complete..... |  | Dan Lerman | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with PAul. Paul will complete as in the near future. Carpet will be installed shortly after...... | YES | FS | 0 | 2018 | 2019-02-16
18P000346 |  | 18P000346 | FALSE | ATHLETICS | SL5-ATHLETICS INSTALL WALL VOLLEYBALL OFFICES | Complete as of 11/8/18 | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-18 | [6 empty] | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. DL, 5/24/18; We will start working on plans in the near future.... DL, 6/16/18; Need to submit plans asap.......DL, 7/11/18; The plans were approved today. This project is scheduled to start on 7/14/18. We will will be complete will all items related to this project on 8/27/18. Note, The door and sidelite are special order items and this item will probalby have a 6-8 week lead time. Steve T is going to order the door soon.. Customer is aware of the delay for the door and is not concerned......DL, 7/25/18; Passed framing and Electrical inspection. We will be finished with the project next week except for the door and window that is ordered but has a 6-8 week lead time. DL, 8/10/18; This Project is Complete except for special order door and window.......DL, 8/22/18; Door and Glass still not on site., Will check in with Steve T on delivery date......Will also schedule final inspection for Certificate of occupancy......9/6/18; The Glass window is installed but we are waiting on the door. this projects is 98% complete.......DL, 9/19/18; The door will be shipped on 9/24/18. We will schedule the door install when the door is on site......DL, 11/7/18; This Project is 100% Complete.... |  | Dan Lerman | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. Will start working on plans.... | YES | FS | 0 | 2018 | 2019-02-16
19P000265 |  | 19P000265 | FALSE | ATHLETICS | SL5-ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5-ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 10 |  | FALSE |  |  | 2018-09-12 | [6 empty] | ??????? | 2018-09-27 | Enrico Baez | 1/14/19 E Baez. Per "Monty" Athletics are to pay for this project. Joe Erbland emailed to determine if funding has been approved. Waiting on response. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB Install keyless entry system for building exterior. | YES | FS | 0 | 2018 | 2019-02-16
19P000271 |  | 19P000271 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 | FS to coordinate with client to schedule work for completion. | ATH DANCE | 3 | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-09-12 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
19P000295 |  | 19P000295 | FALSE | ATHLETICS | SL5-PATCH & PAINT | FS to coordinate with client to schedule work for completion. | ATH DANCE | 50B | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 12 | 18 - 19 | FALSE |  |  | 2018-09-12 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
19P000272 |  | 19P000272 | FALSE | ATHLETICS | SL5-NEED URINAL DIVIDERS | FS to coordinate with customer to scope the work. | ATH DANCE | 50E | HOLD - FACILITIES SERVICES | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 13 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 1/15/19 E Baez. Per "Monty" project cancelled to be placed on Deferred Maint. list. emailed Chris P. to provide renovation cost and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Install dividers for urinals. Wall is tile. |  | FS | 0 | 2018 | 2019-02-16
19P000270 |  | 19P000270 | FALSE | ATHLETICS | SL5-ATH DANCE-WEIGHT ROOM DROP DOWN CEILING | FS to coordinate with customer to scope the work. | ATH DANCE | 78 | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 14 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project is 100% Complete….. |  | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB remove all t-bar ceiling components. Will need relocation of supply and return registers, lighting Alarms, Etc. |  | FS | 0 | 2018 | 2019-02-16
19P000274 |  | 19P000274 | FALSE | ATHLETICS | SL5-RIV SPORTS CPX - REPLACE URINALS | FS to coordinate with customer to scope the work. | RIV SPORTS CPX |  | HOLD - FACILITIES SERVICES | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 15 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-10-15 | Enrico Baez | 1/14/19 E Baez. Per "Monty" this project to go on deferred maint. list. emailed Chris Pillen to provide coast and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27. 10/3/18 EB not time to visit on 9/27. will schedule follow up meeting. 10/15/18 EB conducted site visit, 11 urinals to be replaced. | YES | FS | 0 | 2018 | 2019-02-16
19P000276 |  | 19P000276 | FALSE | ATHLETICS | SL5-TRACK BLEACH-PUBLIC RESTROOMS UPGRADE | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | TRACK BLEACH |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 16 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 11/20/18 EB Project cancelled, will be addressed by PD&C. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB conducted site visit, Client wants additional toilet in mens room, changing table and lighting improvements. ADA Issues. Also spoke with Scott Donnell he has project . | YES | FS | 0 | 2018 | 2019-02-16
19P000266 |  | 19P000266 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
19P000252 |  | 19P000252 | FALSE | ATHLETICS | SL5-ATH DANCE SHOWER DOORS | FS to coordinate with customer to scope the work. | ATH DANCE | 0050K | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  |  |  | 3 |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB Replace aluminum and glass shower doors. Will need to contract work. Replace all rusty fixtures in showering space, repair/replace tile as needed. | YES | FS | 0 | 2018 | 2019-02-16
19P000268 |  | 19P000268 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH AND PAINT 20C | FS to coordinate with client to schedule work for completion. | ATH DANCE | 20C | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
19P000269 |  | 19P000269 | FALSE | ATHLETICS | SL5-ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | Project is not within the purview for completion; condition is fair and usable. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 5 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18…..This is a cooman area. Is this recharge work……. | 2018-09-27 | Enrico Baez | 2/5/19 E. Baez. Common spaces are managed by Facilities Services. Any work done in corridors, stairwells and open spaces will be assessed by FS. 11/20/18 E. Baez-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB-Request for installing vinyl flooring. Remove and replace existing Terrazo and ceramic floor tile in 1st floor lobby and stairs to basement. | YES | FS | 0 | 2018 | 2019-02-16
19P000275 |  | 19P000275 | FALSE | ATHLETICS | SL5-SOFTBALL STG PRESS BOX AC ADDITION | FS to coordinate with customer to scope the work. | SOFTBALL STG |  | CANCELED BY CLIENT | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 6 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project was canceled by Johnathan J. as there is not funding at this time…………DL, 10/4/18; I checked on this recently and this is not a building, it is stoarge and should be recharge work…. | 2018-09-27 | Enrico Baez | 2/5/2019 E Baez Client wants a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. Client will need to fund this project as this is not a core building 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Client want a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. |  | FS | 0 | 2018 | 2019-02-16
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5-RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 7 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB approx. 16-20 doors need repair. Sand, patch, repair as needed. Re-varnish. | YES | FS | 0 | 2018 | 2019-02-16
19P000273 |  | 19P000273 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-12 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
3432 | 3432 |  | FALSE | ATHLETICS | Athletics Replace Scoreboard | Please assist with coordinating the process for replacement of existing soccer scoreboard to a new model. We will work with A&E to develop criteria and how to accomplish the task. |  |  | On-hold | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Scott Donnell | 1 |  |  | FALSE | 0 |  | 2018-07-19 | On-Hold | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | Project #957440 assigned | Tamica Smith Jones | Joseph Erbland | Johnathan Jensen |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2018-08-23 | Create SOW | 2019-09-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. |  |  | On hold until MRB1 is complete. | Tamica Smith Jones | Joseph Erbland | Joe Erbland |  | Mihai Gavan | 3 |  |  | FALSE | 0 |  | 2014-04-10 | To be coord. with Rec Mall work | [10 empty] | PD&C | 0 | 2014 | 2019-02-16
3408 | 3408 |  | FALSE | ATHLETICS | Harrison Field Netting | Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | SOFTBALL STG |  | Per department: Project is on hold until further notice. | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2018-01-23 | On-Hold by Cust Until Further No | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
18P000094 |  | 18P000094 | FALSE | BAS | SL5-OBAN LAUNDRY ROOM RENOVATION | Scope of work has changed and project to be routed to Google IRT/CPMS for completion | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2017-09-08 | [6 empty] | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on bid. 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/12 EB- rec'd approval to contract with Design West to consult on electrical panel upgrade. |  | Enrico Baez | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on b 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/11/18 EB-requested drawings from Gunter per Desgn Wests request. 7/11/18EB-waiting for Desgn West to complete site survey. 8/7/18 EB-Met with Robert Brumbaugh. Scope has changed with additional requirements. Improve HVAC, replace VCT, bathroom remodle. Advised to submit CPMS for A&E. | YES | FS | 0 | 2017 | 2019-02-16
19P000317 |  | 19P000317 | FALSE | BAS | SL5-HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 |  | PENTLAND A |  |  | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER | [5 empty] | FALSE |  |  | 2018-10-03 | [11 empty] | FS | 0 | 2018 | 2019-02-16
18W011772 |  | 18W011772 | FALSE | BAS | SL5-PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | Canceled per customer on priority list 7/3/18 | PRINT MOD |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Dan Lerman |  |  | Canceled | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/29/18; Pasted from WO; install an outside electrical outlet based on the attached amazon specs. also estimate for removing and sealing the outside vent from the copier. fyi_the copier will be moving within the next few months…..DL, 7/11/18; Need to verfy scope and schedule the work...... |  | Enrico Baez | fyi_the copier will be moving within the next few months | YES | FS | 0 | 2018 | 2019-02-16
18P000282 |  | 18P000282 | FALSE | BAS | SL5-EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 | Complete as of 8/10/18 | POLICE BLDG |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | LISA MARTIN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-25 | [6 empty] | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work…..DL, 5/9/18; We need to submit plans……DL, 7/11/18; This still needs to be scheduled......DL, 8/8/18; Enrico Confirmed this project is 100% Complete.... |  | Enrico Baez | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work….. | YES | FS | 0 | 2018 | 2019-02-16
19P000222 |  | 19P000222 | FALSE | BAS | SL5-PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000432 |  | 18P000432 | FALSE | BAS | SL5-BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 | Complete as of 7/13/18 | BANNOCK H | H0101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-05-04 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000369 |  | 18P000369 | FALSE | BAS | SL5-BOYCE X-RAY IRRADIATOR PROJECT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 1407 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | KAREN JANIGA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-27 | [6 empty] | 12/14/18, DL; This project was cancelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……DL, 5/9/18; Need to work on plans/permits…..DL, 6/16/18; Meeting with Bob and confirmed what is needed. I will work with Gunther on plans. Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall…..DL, 11/7/18; Material is on site. We will schedule the work soon…… |  | Ron Veloz | DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……Need to work on plans….10/17/18 RV: This project was previously scoped and in Plan development. | YES | FS | 0 | 2018 | 2019-02-16
18P000106 |  | 18P000106 | FALSE | BAS | SL5-HOUSING PROJECT - OBAN REC ROOM REMODEL | Scope of work has changed and project to be routed to Google IRT/CPMS for completion | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 3 | FALSE |  |  | 2017-09-14 | [6 empty] | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. DL, 7/11/18; Per Susan this project is back on track. Project is scoped. Gunther will start working on the plans and permits. Once we have the approved permit. still need to check in with Susan on a few items.....Target complet date will be mid- fall...... |  | Enrico Baez | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. 8/22/18 Met with BoB Brumbaugh, Scope of work has changed with additional items. Fire alarm panel relocation, possible building HVAC upgrade. Ask he route project through CPMS and make laundry room and Rec. room one project. | YES | FS | 0 | 2017 | 2019-02-16
19P000247 |  | 19P000247 | FALSE | BAS | SL5-LOTHIAN FIRST FLOOR COMMON AREA FLOORING | Complete as of 10/22/18. | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Jess Hernandez |  |  |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez |  |  | FS | 0 | 2018 | 2019-02-16
18P000373 |  | 18P000373 | FALSE | BAS | SL5-POLICE BLDG PAINTING IN DISPATCH AREA | Complete as of 7/14/18 | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  |  | 8 | FALSE |  |  | 2018-04-02 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000236 |  | 19P000236 | FALSE | BAS | SL5-EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION | Scheduled work with trades anticipated completion December 2019. | ABER INVER | A0100 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 10 |  | FALSE |  |  | 2018-09-04 | [6 empty] | 2/8/19 JP Estimated completion end of February | 2018-11-01 | Enrico Baez | 11/27/18 EB-Entered scope of work. Transferred work order to John Peraino in FAMIS. Estmate to be provided prior to work start. Aberdeen Inverness Lobby across from RSO. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Pentland Hills 1st floor of I/J, K/L, M/N, O/P • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Pentland Hills Alcove between E&F building. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exterior wall adjacent to B-101 • Remove existing dual fountain. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exercise Room H-101 • Install HS where pluming repairs were made in East wall. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch all walls and Paint as needed. Glen Mor K-206 Fitness Room • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Glen Mor Pool area • Remove existing double water fountains and HS. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. • Repair any brick work as needed Lothian Hallway near Dining Hall cashier stand adjacent to fire extinguisher cabinet • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Sample sheet. https://www.restroomdirect.com/halsey-taylor-drinking-fountains-and-water-coolers.aspx 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Waiting for Lisa L. to schedule site visit. Total number of station and needs not completed. 11/1/18 EB Conducted site visit with Lisa and Bob. AI Replace Hydration Station (HS) in Lobby near RSO Pentland Hills Replace fountains with HS first floor I/J, K/L, M/N, O/P. Also remove fountains and install HS near B-101, Alcove between E&F, H-104. Glen Mor Remove fountain at pool & K-206 fitness room, replace with HS. Lothian Replace existing HS near cashier to Dining Hal | YES | FS | 0 | 2018 | 2019-02-16
19P000192 |  | 19P000192 | FALSE | BAS | SL5-MAIL-PAINTING | Complete as of 11/8/18 | MAIL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000235 |  | 19P000235 | FALSE | BAS | SL5-RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | Customer to determine scope of work. | ABER INVER | A0100 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 11 |  | FALSE |  |  | 2018-09-04 | [7 empty] | 2018-11-01 | Enrico Baez | 11/26/18EB-Tranfered FAMIS work order to John Peraino's bench. Estimate to customer needed, prior to moving forward with project. 11/26/18 EB-SCOPE entered Aberdeen Inverness • Paint acoustic panels. Customer to provide color specification. • Remove carpet and replace with customer specified vinyl plank flooring. Replace base board • Cut door to accept 16” x 7” glass lite. Frame as needed. • Paint door • Replace surface mounted light fixture with LED surface mounted fixture. Customer to approve design. • Clean, paint or replace A/C vents. • Remove louvered vent in wall for abandoned water cooler. Install sheet metal cover, paint to match new wall color. Pentland Hills -Rooms 105 and 107 • Install full height acoustic panels on three walls. • 4th wall on East side of each room gets mirror. Height of mirror to be flush with top edge of door casing. Mirror width to be between inside corner of wall and switch plate cover. Provide cut out in mirror for thermostat installation. • Replace all ceiling tiles. • Replace 2’ x 2’ ceiling light with 2’ x 4’ LED fixture-customer to approve design. Pentland Hills -Rooms 105 and 107 • Remove carpet and replace with vinyl plank flooring, replace base board • Fire rated doors to be replaced with fire rated doors with small lite, approx. dimensions 16’ x 7”. • Paint as needed. Lothian • Install full height acoustic panels on three walls. • 4th wall gets mirror height to be even with door casing height. Customer to determine location. • Replace all ceiling tiles. • Replace ceiling lights with LED fixtures. • Remove all carpet in rooms and replace with vinyl plank and new base board-customer to specify style and color. • Replace door wire reinforced glass with clear, non-reinforced fire rated glass. • Paint as needed. Suggested Vendor for sound absorbing paneling. Riverside Acoustics Contact: Keith Atkins 951-682-6123 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 Met with Bob and Lisa, no firm plans or ideas in place. Lisa will schedule site walk once they have determined what they want. 11/1/18 Conducted site visit with Bob and Lisa. | YES | FS | 0 | 2018 | 2019-02-16
19P000015 |  | 19P000015 | FALSE | BAS | SL5-POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING | Complete as of 11/8/18 | POLICE TRLR | 1 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-07-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000233 |  | 19P000233 | FALSE | BAS | SL5-PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | FS to coordinate with customer to scope the work. | MAIL | 884 | CANCELED BY FS | Gerry Bomotti | Georgianne Carlson | AMY EVERETT |  |  |  | 12 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Enrico Baez | Per Enrico, creating two individual WO's for Tile repair (19W004955) and door painting (19W004956). | YES | FS | 0 | 2018 | 2019-02-16
18P000363 |  | 18P000363 | FALSE | BAS | SL5-PAINT STOREHOUSE ADMINISTRATIVE OFFICE | Complete as of 11/8/18 | CORP B |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | ERICA HENDERSON |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-03-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000227 |  | 19P000227 | FALSE | BAS | SL5-DINING STORAGE ROOM CONVERSION | Scheduled work with trades anticipated completion December 2019. | BANNOCK J | J0100 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | DARCI LOMBARD |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 2/8/19: JP storage room slated to be completed simultaneously with break room as water supply connections will be done together with break room. Completion date for both is approximately three weeks. |  | Enrico Baez | 9/12/18 EB-Install Drywall, Patch & Paint, cap water line, install VCT & Cove Base, Verify HVAC operation, replace hydralic door closer, install LED lamps, Security light. Scope sent to Edwin Melgar for approval. | YES | FS | 0 | 2018 | 2019-02-16
19P000224 |  | 19P000224 | FALSE | BAS | SL5-PAINT EXTERIOR RAMP AT HUB MODULAR | FS to coordinate with client to schedule work for completion. | PRINT MOD |  | QUEUE TO START | Gerry Bomotti | Georgianne Carlson | MIKE CLEMONS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000308 |  | 19P000308 | FALSE | BAS | SL5-ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK | Scheduled work with trades anticipated completion December 2019. | ABER INVER |  | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break. |  | Enrico Baez | 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. |  | FS | 0 | 2018 | 2019-02-16
19P000307 |  | 19P000307 | FALSE | BAS | SL5-LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK | Scheduled work with trades anticipated completion December 2019. | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 5 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… | 2018-10-03 | Enrico Baez | 1/8/19 EB Job Completed by Jess H. 12/22/18 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. | N/A | FS | 0 | 2018 | 2019-02-16
19P000232 |  | 19P000232 | FALSE | BAS | SL5-BANNOCKBURN J-104 BREAK ROOM UPGRADE | Scheduled work with trades anticipated completion December 2019. | BANNOCK I | I0105 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | John Peraino |  | 6 |  | FALSE |  |  | 2018-09-04 | [6 empty] | 2/8/19 JP: Finishing up the cabinet and lighting order, will be submitting to purchasing today Scheduling installation of VCT flooring pending per Tony’s Flooring, will have date this week New ceiling tiles have been delivered and will be installed when relocating of electrical components are complete Awaiting confirmation and clearance from Jess to proceed with cutting into walls to facilitate electrical modifications |  | Enrico Baez | 9/19/19 EB-conducted site visit. Entered Scop in FAMMIS and in BZM projects on shared drive. Requires pluming for sink and disposal, electrical, lighting upgrade. | YES | FS | 0 | 2018 | 2019-02-16
18P000483 |  | 18P000483 | FALSE | BAS | SL5-INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | FS to coordinate with customer to scope the work. | P1 |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | AMANDA GREY |  | Enrico Baez |  | 7 |  | FALSE |  |  | 2018-06-26 | [6 empty] | Waiting for Amanda Grey to verify ownership of chain link fence. Once confirmed will contract with De Anza to install 36" wide gate. | 2018-08-29 | Enrico Baez | 12/3/18 EB-Cancelled request per email from Amanda Gray. Will resubmit request when funding is available. 10/1/18 EB-Contract De Anza Fence to have a gate installed at chain link fence leading to storm culvert in parking lot 1. | YES | FS | 0 | 2018 | 2019-02-16
19P000022 |  | 19P000022 | FALSE | BAS | SL5-HUB--PAINT TWO WALL AS SCOTTY'S HUB | Complete as of 9/17/18 | HUB | 101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | DIANE THOMAS |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-07-12 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000215 |  | 19P000215 | FALSE | BAS | SL5-SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 | Coordinating movement of equipment and utility connections. | HUB | 346 | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | John Peraino |  | 9 |  | FALSE |  |  | 2018-08-24 | [6 empty] | 12/12/18 DND Project complete; electrical was installed and all kitchen equipment was hooked up as requested. |  | Enrico Baez | 9/13/18 EB emailed Gustavo Plascncia to schedule site visit. 9/18/18 EB. Conducted site visit. Connect water, drain and gas lines to kitchen equioment. Double oven need hardwired electrical. HUB staff will attach al shelving to walls. Day crew to move and deliver equipment. | YES | FS | 0 | 2018 | 2019-02-16
18P000095 |  | 18P000095 | FALSE | BAS | SL5-THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS | Canceled per customer on priortization list. | THE PLAZA | A0013 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  | Canceled | HOLD | FALSE |  |  | 2017-09-08 | [6 empty] | 4/11/EB-On Hold per Robert Brumbaugh. 6/8 EB-emailed R. Brumbaugh for status update. |  | Enrico Baez | 4/11/EB-On Hold per Robert Brumbaugh. DND 7/14 Hold per customer on prioritization | YES | FS | 0 | 2017 | 2019-02-16
19P000208 |  | 19P000208 | FALSE | BAS | SL5-PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | Canceled per customer on priority list 9/17/18 | THE PLAZA |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | CARLA CHAPPLE |  | Dan Lerman |  | Canceled |  | FALSE |  |  | 2018-08-14 | [8 empty] | Enrico Baez |  | NO | FS | 0 | 2018 | 2019-02-16
18P000459 |  | 18P000459 | FALSE | BAS | SL5-BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 | Complete as of 9/21/18 | THE BARN |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | Dan Lerman |  | Complete | 6 | FALSE |  |  | 2018-05-31 | [8 empty] | Enrico Baez | 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 6 | YES | FS | 0 | 2018 | 2019-02-16
18W009630 |  | 18W009630 | FALSE | BAS | SL5-BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. | PHYS PL STOR | 100 | IRT REVIEW | Gerry Bomotti | Georgianne Carlson | JUDY HODGE |  | Dan Lerman |  | HOLD | HOLD | FALSE |  |  | 2018-01-22 | [6 empty] | DL, 6/16/18; Project includes demo wall/door install new wall, dry wall, paint, door, eletrical outlets, lighting, smoke relocation, lighting motion, new t-bar, relocate heat pump, andn install new carpet…...DL, 7/11/18; Need to work on plans….. Target complete date is late Fall..... |  | Enrico Baez | See work order 18W012349 scoped and annotated in FAMMIS. 6/11/18 EB- Add wall to current space and eliminate exisiting wall. Relocate exisiting A/C on wall. Minor electrical DND 7/14 Hold per customer on prioritization; per Corp Yard Space Planning | YES | FS | 1899-12-31 | 2018 | 2019-02-16
3411 | 3411 |  | FALSE | BAS | MRB Café Buildout & MS&E Loading Dock Mods | MRB1 CAFE and SERVICE YARD INTERIOR FIT-OUT: provide design and construction services to build out the interior of the MRB1 Café shell and modify the MS&E Service Yard to accommodate the café deliveries and trash movement. This CPMS Request is to combine and replace previously approved CPMS #3378 and #3398 into one project as requested by A&E. Please note that the IRT Job walk has already been completed. Intent is to design in FY'17/18 and construct in FY '18/19. Opening to coincide with the MRB1 facility turnover. Food service equipment will be Owner Furnished on a separate UCR Purchase Order. Note that the MRB1 Café shell construction is provided by the separately funded MRB1 project, construction drawings for this shell space are attached in CPMS. | MAT SCI ENGR |  | Construction started 11/19. Going over submittals/RFI's. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Mihai Gavan | 1 |  |  | FALSE | 793000 |  | 2018-02-05 | Complete Construction | 2018-11-19 | 2019-02-28 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
2508 | 2508 |  | FALSE | BAS | Barn Expansion | Project 950493 Barn has completed the DPP process and we are now adding this to CPMS to capture expenses related to the Program Process which occurred in FY11-12 and FY12-13. Please move all expenditures from A01233-70003-76 Cost Center to JR142 to a plant account. |  |  | In construction | Gerry Bomotti | Georgianne Carlson | Susan Marshburn |  | D.Hecht/J.Franklin | 4 |  |  | FALSE | 28700000 |  | 2013-07-05 | Complete Construction | 2018-06-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2013 | 2019-02-16
3421 | 3421 |  | FALSE | BAS | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 5 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3426 | 3426 |  | FALSE | BAS | Lothian Boiler Replacement | The boiler equipment at Lothian is original to the building and past its useful life. Design, procure and install a replacement boiler that incorporates the latest energy saving and management technology that can be cost-effectively installed as a direct replacement to the existing unit. | LOTHIAN HALL |  | Complete Design/Bidding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 6 |  |  | FALSE | 0 |  | 2018-03-19 | Complete Design/Bidding | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3286 | 3286 |  | FALSE | BAS | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | Awaiting revised proposal from Miyamoto | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 9 |  |  | FALSE | 0 |  | 2017-03-29 | Complete Design | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3403 | 3403 |  | FALSE | BAS | Parking Lot 23 Addition | Parking Lot 23 Expansion - The goal of the project is to add additional parking capacity to Parking Lot 23 to serve that area of the campus. Current parking capacity in this area will be impacted by the closures of Lot 22 and Crest Housing parking area. Additional capacity will be need for employee parking. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Daneca Stevens | 15 |  |  | FALSE | 92000 |  | 2018-05-17 | Design | 2019-05-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3430 | 3430 |  | FALSE | BAS | TAPS Cust Svc Lobby Upgrades | Upgrades to Customer Service Lobby – Need to complete Tenant Improvement project upgrade customer service counter in Parking Services Building. Want to replace current counter to allow for; modern computer equipment, dividers between customers’ transaction spaces, under counter space for filing cabinets and check writing space. Please coordinate with Auxiliaries’ primary PM John Franklin. | PARKING SERV |  | On hold | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Dave Bomba | 16 |  |  | FALSE | 0 |  | 2018-05-17 | Meet to discuss scope & funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3354 | 3354 |  | FALSE | BAS | Lot 4/Barn Area ADA Improvements | Lot 4/Barn Area ADA Improvements - The proposed project will relocate an existing crosswalk that is not ADA compliant and provide path of travel improvements and additional ADA parking capacity in Parking Lot 4. The existing crosswalk located at West Campus Drive and Parking Lot 4 (north) was identified in the Draft ADA Transition Plan to be out of compliance. A Pedestrian Safety Study by Fehr & Peers completed in June 2008 identified the relocation of this crosswalk to approximately 100 feet east to provide a more visible, safe, pedestrian crossing. To increase pedestrian safety further, the crosswalk will be designed as a speed table. Additionally, Transportation and Parking Services proposes to create additional ADA parking spaces in Parking Lot 4 that exceed the required number, with hardscape and path of travel improvements that will connect to the new crosswalk. The improved crosswalk will correct required path of travel deficiencies from a parking lot that provides access to numerous publicly accessible buildings, as well as allow the Barn Expansion project to obtain Division of State Architect (DSA) approval once construction is completed. The funds to complete the crosswalk replacement will be requested from Campus ADA funds. Parking Lot 4 improvements will come from will come from TAPS. Although this project supports the Barn Renovation, its conception and need is not tied to the Barn project. The crosswalk improvements and additional ADA parking is needed to meet our ADA parking requirements and serve the growing demand on campus. This project is desired regardless of the Barn Renovation project. |  |  | In funding | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Fernando Nunez | 17 |  |  | FALSE | 50000 |  | 2017-08-15 | Updated Proposal & Cost Estimate | 2019-07-01 | 2019-09-27 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3439 | 3439 |  | FALSE | BAS | TAPS Strategic Master Plan Study | STUDY - Transportation And Parking Master Plan Study This study initiated by TAPS is part of a comprehensive planning effort within Auxiliaries to develop a strategic transportation and parking plan that will guide the university’s transportation and parking efforts over the next decade. This is complementary to the campus Physical Master Plan Study and will help inform the future new LRDP. |  |  | Postponed until Mid-2019 | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Jerrod Walters | 18 |  |  | FALSE | 0 |  | 2018-06-05 | Postponed until Mid-2019 | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3376 | 3376 |  | FALSE | BAS | West Lothian Roof Replacement Design | Provide Schematic Design, Design Development and professional cost estimate to replace the existing single-ply membrane roof system on the Lothian West residence hall wings plus Common Area applications. Existing roofing is past its useful life and starting to experience multiple leaks that are damaging living spaces below. Design effort should select the most appropriate roof material for this roof plan. The intent is to design this year (alongside the Lothian East design) and construct immediately following the Lothian East roof replacement. | LOTHIAN HALL |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 20 |  |  | FALSE | 0 |  | 2017-09-28 | Bidding | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3383 | 3383 |  | FALSE | BAS | W Lothian Air Handler Replacemt | Existing air handler equipment in West Lothian is original to the building and past its service life. Provide HVAC professional services to develop options for Air Handler replacement that meet UC Carbon Neutral 2025 goal. Each option analysis should include pros and cons for energy consumption, reliability, serviceability and system installation cost projections. At least one option should explore potential conversion to individual package units as practical. | LOTHIAN HALL |  | Complete Design/Bidding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 21 |  |  | FALSE | 883000 |  | 2017-10-03 | Complete Design/Bidding | [10 empty] | PD&C | 0 | 2017 | 2019-02-16
3453 | 3453 |  | FALSE | BAS | ECS N&S Playground Shade & Turf | Provide Schematic Design, Design Development and Professional Cost Estimate for the alteration of existing shade structures, provision for additional shade structures, refinish interior metal fencing, and the replacement of existing grass with synthetic turf at the Early Childhood Services north and south playground areas. Prepare drawings so that they can be bid and constructed as separate projects. |  |  | Dept approval/funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 23 |  |  | FALSE | 0 |  | 2018-07-03 | Dept approval/funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3459 | 3459 |  | FALSE | BAS | A-I Hardscape Landscape Design | Provide Schematic Design and Design Development drawings for a selective renovation of all hardscape and landscape around the perimeter of the Aberdeen-Inverness housing complex. Scope to include (but not limited to) widening of South Walk and replace its asphalt with concrete pavers, upgrade hardscape and landscape at Horseshoe, replace selected lawn areas with hardscape, seating and solar umbrellas at east and west lawns of Building E, consider new bike storage along South Walk, consider modifying slopped lawn between Building A and Linden St., generally reduce lawn areas and replace with sustainable planting, prune or replace unkempt trees, replace selected light fixtures to match Dundee fixtures, and generally freshen the landscaping so that it is harmonious with the new Dundee development. Design to be packaged in phases, with the South Walk and Dundee-facing landscape to be ready in Phase 1 for construction timing alongside Dundee-Glasgow landscaping in Spring of 2020. | ABER INVER |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 24 |  |  | FALSE | 0 |  | 2018-07-16 | Consultant Approval | 2020-01-01 | 2020-08-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3462 | 3462 |  | FALSE | BAS | A-I Restaurant & Lobby Reconfiguration | Provide Schematic Design and Design Development drawings for the complete reconfiguration of Building C including kitchen, dining space, and common areas. The restaurant and kitchen areas are largely original to the building and well past their useful life. The new, replacement, Glasgow restaurant coming on-line in Fall 2020 will allow a needed reprogramming and modernization of this space. Preliminary Program for this space includes a smaller Catering Kitchen, Meeting Rooms, new KUCR studio as well as a modernization and upgrade of the Lobby and other Common Areas. Documents to be assembled for a Fall 2020 construction start. | ABER INVER |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 25 |  |  | FALSE | 0 |  | 2018-07-17 | RFQ Development | 2020-08-01 | 2021-06-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3463 | 3463 |  | FALSE | BAS | Landscape Strategic Plan for Housing Services | Provide a comprehensive study of existing landscape areas within Auxiliary Services and provide specific and actionable recommendations for their conversion to sustainable landscaping by location. Study to include all Resident Hall and Apartment properties and include conceptual cost estimates, by location, for proposed landscape conversions. |  |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 26 |  |  | FALSE | 0 |  | 2018-07-17 | RFQ Development | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3460 | 3460 |  | FALSE | BAS | A-I Restroom Replacement - Reconfig | Provide Schematic Design and Design Development drawings for the complete replacement of the restrooms in all four resident hall wings. Existing restroom fixtures and finishes are largely original to the building and long past their service life, causing serious leaks between floors. New restrooms will be reconfigured to meet current accessibility code. Documents to be assembled for phased construction, one wing per summer, with the first building (D-Wing) to be constructed in Summer 2019. | ABER INVER |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 27 |  |  | FALSE | 0 |  | 2018-07-19 | Consultant Approval | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3455 | 3455 |  | FALSE | BAS | Campus Traffic Engineering Study | This request is to fund the contracting of a consulting firm to study of the impacts related to the desired construction of a new parking garage on the UCR campus. Project will inform on site selection, traffic impacts and opportunities. This project will be funded through a parking garage planning budget allocation in the approved 2018-19 TAPS budget. |  |  | In Construction | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Dave Bomba | 28 |  |  | FALSE |  | 0 | 2018-07-23 | Report & recommendations 2/4/19 | 2018-11-05 | 2019-06-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3467 | 3467 |  | FALSE | BAS | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 31 |  |  | FALSE | 0 |  | 2018-07-31 | Design | 2019-08-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3466 | 3466 |  | FALSE | BAS | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 32 |  |  | FALSE | 0 |  | 2018-07-31 | Funding | 2019-05-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3382 | 3382 |  | FALSE | BAS | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 33 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2021 | [10 empty] | PD&C | 0 | 2017 | 2019-02-16
2868 | 2868 |  | FALSE | BAS | West Lothian Elevator Renovation |  |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 34 |  |  | FALSE |  |  | 2015-04-08 | Bidding | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
3392 | 3392 |  | FALSE | BAS | Bicycle Master Plan Study | Bicycle Master Plan Study. This CPMS project is for the funding and creation of a Bicycle Master Plan Study for the UCR Campus. It is not for a specific capital project. |  |  | Pre-Programming | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Jerrod Walters | 35 |  |  | FALSE | 115000 |  | 2017-11-13 | Funding | [10 empty] | PD&C | 0 | 2017 | 2019-02-16
3472 | 3472 |  | FALSE | BAS | Lot 21 Trash Enclosure Relocation | Construct a new CMU trash enclosure with water and power in a different location of Lot 21 to replace the existing enclosure that will be demolished to make way for the Dundee Residence Hall construction. Include hose bib for cleaning and power for future compactor installation. New enclosure needs to be on line BEFORE site construction can start on Dundee-Glasgow in January 2019. |  |  | Funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 36 |  |  | FALSE | 0 |  | 2018-08-15 | Hire Design Consultant | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3397 | 3397 |  | FALSE | BAS | Dundee Residence Hall and Glasgow Dining | (Lot 22/Dundee-Glasgow) A newly proposed student housing development, including a single phase 760-bed residence hall and an 830-seat dining facility located on the existing Parking Lot 22 site south of Linden Street. The project is anticipated to be completed by Fall/Winter 2020. Funding for predevelopment activities including CEQA and staff augmentation to be determined. | ABER INVER |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Raoul Amescua | 38 |  |  | FALSE | 1120000 |  | 2017-11-21 | Complete Construction | 2019-01-01 | 2020-09-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3491 | 3491 |  | FALSE | BAS | Oban Comm Ctr Remodel | General remodel and freshening of the Oban Family Housing Community Center to include Laundry Room, Public Restroom and Recreation Room. Scope documents and partial drawings attached. This was originally two separate projects that Facility Services was managing but has now been requested that A&E take over due to evolving complexity and dollar cost. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 42 |  |  | FALSE |  |  | 2018-11-16 | Funding | 2019-06-01 | 2019-08-31 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3488 | 3488 |  | FALSE | BAS | CBS HUB Business Center | Provide a light renovation of the HUB Modular space to include new electrical drop for the Card Office cubicles in the North Office (where the copy machines are now), and replace flooring in the North Office as required, install ADA shelf at the front desk and other minor scope items to facilitate the move of the Card Office to this building. This must be a Winter Break project so that the Business Center remains online during the normal campus schedule. |  |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Fernando Nunez | 43 |  |  | FALSE | 15000 |  | 2018-11-13 | Complete Project Close-Out | 2018-12-17 | 2018-12-21 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3490 | 3490 |  | FALSE | BAS | East Campus Parking Structure | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Dave Bomba | 46 |  |  | FALSE |  |  | 2018-12-06 | Selection of Design Build teams | 2019-12-01 | 2021-02-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
| 3503 |  | FALSE | BAS | Falkirk Stair/Front Porch Repair | Repair or replace four sets of entry stairs and landings that are long past their service life and are a life safety concern. Consider replacing these wood structures with steel to ease future maintenance. Apartments affected are #3RS, #11MN, #15A and #16FG. |  |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 47 |  |  | FALSE |  |  | 2019-02-01 | New | [10 empty] | PD&C | 0 | 2019 | 2019-02-16
3478 | 3478 |  | FALSE | BAS | Ivans Hinderaker Ext. Cladding | Replace existing exterior cladding outside of Ivan's kiosk with new building materials that will cover the abandoned openings in the exterior and provide a cohesive and waterproof envelope for this structure. | HINDERAKER |  | Project number assigned | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 99 |  |  | FALSE | 0 |  | 2018-09-07 | Complete Construction | 2019-02-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
18P000315 |  | 18P000315 | FALSE | BCOE | SL5-BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB | Complete as of 8/23/18 | BOURNS | B0235 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  | HOLD | TRUE |  |  | 2018-02-16 | [6 empty] | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction to scope, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... Need to walk project with Ron and schedule the work....DL, 5/24/18; Conducted site visit with Ron V. Ron will order material and schedule the work once material is on site.....DL, 6/16/18; Need to verify delivery date for material.......DL. 7/11/18; Plumbing is disconnected. Corey is tentatively scheduled to disconnect the Fume hood. Once the Fume hood is disconnected, we will schedule the removeal of the fume hood and start the framing of the wall. Target complete date is 8/8/18....DL, 7/25/18; Fume hood is disconnected. Need to move Fume hood and start framing target date is delayed to creep scope but should be complete near 8/16/18.....DL, 8/10/18; Carp[enters will install the wall this week. Corey has parts orders. Corey will complete the install when the material arrives.......DL, 8/22/18; This Project is Complete |  | Dan Lerman | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... DND 7/14 Hold per customer on prioritization | YES | FS | 0 | 2018 | 2019-02-16
18P000267 |  | 18P000267 | FALSE | BCOE | SL5-CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT | Complete as of 7/11/18 | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-01-16 | [6 empty] | DL, 5/19/18; High table mounted on West wall to be relocated to South wall by light "Centered". Relocate white board from East Wall to West walll wher high table was removed. Paint and new flooring. Need to schedule work with Paul and Jess. BKM furniture is scheduled 4-6 weeks. DL, 6/16/18; Lower electrical outlets on North wall, repair blinds, paint and new flooring. The space is vacant as of June 16th. I will scheudle the workl.....BKM delivery is currently scheduled for July 23rd.......This project is 100% complete. There were two items added to the scope and they will be complete by 7/20/18..... |  | Enrico Baez | 4/3/2018 Met with Maggie. She is working with BKM. Floor to go down first. BKM furniture on top. Annotated in Famis. | YES | FS | 0 | 2018 | 2019-02-16
18P000321 |  | 18P000321 | FALSE | BCOE | SL5-STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST | Complete as of 8/10/18 | STUDENT SERV | 1228 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Enrico Baez |  |  |  | FALSE |  |  | 2018-02-22 | [6 empty] | DL, 4/29/18; Enrico is cordinationg this. The permits are approved……. DL, 7/11/18; Just received confirmation the door is ready for delivery and installed. I need to check in with Paul about the paint and prep of the door. I also need to check in with Jason on lock hardware......Dl, 7/25/18; Door is painted and ready for install. Called Dugmore to schedule the install. This should be compolete within the next two weeks......DL, 8/8/18; This Project is 100% Complete |  | Enrico Baez | DL, 4/29/18; Enrico is cordinationg this. The permits are approved. EB. 5/11/18- waiting for PO to be issued to Vendor. Customer provided PO numbers, waiting to schedule install with vendor, 5 week lead time. | YES | FS | 0 | 2018 | 2019-02-16
18P000429 |  | 18P000429 | FALSE | BCOE | SL5-INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 | Complete as of 9/19/18 | BOURNS | B0262 B0256 | COMPLETE | Christopher Lynch | Maggie Souder | KEVIN SCHULTE |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment…..DL, 5/9/18; We are working on plans to submitt to A&E soon....DL, 5/24/18; Plans were submitted on 5/24/18.......DL, 6/12/18; Plans were approved. Cabinets are ordered. Materila is 6-8 Weeks out.....DL, 7/11/18; We have confirmation for delivery of material for mid August. Target Complete date is 9/7/18......DL, 8/10/18; Project has started. We will be complete with in two weeks......DL, 8/22/18; Work is 90% Complete..Project should be complete by 8/31/18........ DL 9/6/1/8; This project is 99% complete. The parts arrived today. I will be sending out an email to schedule the installation time for next week.......DL, 9/19/18; This project is 100% Complete........ |  | Dan Lerman | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment….. | YES | FS | 0 | 2018 | 2019-02-16
18P000454 |  | 18P000454 | FALSE | BCOE | SL5-BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS | Complete as of 8/24/18 | BOURNS | A0346 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  |  | 9 | FALSE |  |  | 2018-05-29 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000427 |  | 18P000427 | FALSE | BCOE | SL5-BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER | Complete as of 7/11/18 | BOURNS | A0373 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie email; This is our new Dean’s faculty office. Dean Lynch is already on site getting up to speed one-two days a week. This office is an ASAP...... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected.....DL, 7/11/18; This project is 100% complete...... |  | Paul Ditty | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | FS | 0 | 2018 | 2019-02-16
18P000472 |  | 18P000472 | FALSE | BCOE | SL5-WCH PATCH AND PAINT WALL | Complete as of 8/24/18 | CHUNG HALL | 458 | COMPLETE | Christopher Lynch | Maggie Souder | JANNA LE BLANC |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000426 |  | 18P000426 | FALSE | BCOE | SL5-BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER | Complete as of 7/25/18. | BOURNS | A0375 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; A-375: Bhargav Rallabandi arrives on or about August 1….. DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/1/18.....DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | FS | 0 | 2018 | 2019-02-16
18P000425 |  | 18P000425 | FALSE | BCOE | SL5-BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - | Complete as of 7/25/18. | BOURNS | A0379 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; Luat Vuong arrives on or about August 15…... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected..…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/15/18........DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | FS | 0 | 2018 | 2019-02-16
18P000391 |  | 18P000391 | FALSE | BCOE | SL5-PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN | Complete as of 9/10/18 | CHUNG HALL | 446 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 5/5/18; Conducted scope visit with Paul and Maggie. This project is target date is August 30th. As of now, we have 10 business days to complete the work……. Dean's Office….DL, 6/16/18;Walked project with Jess and Paul. This will be a project will now incluclude flooring is 7- additional offices due to additional trip hazzards identified in 3 of 7 offices during the carpet scope. Maggie will pay four four of the office since they are still in good condition. We are still on schedule with the work.......Dan, 7/11/18; This project is still on schedule. Complete Date is 8/18/18 and scheduled to be complete on 8/31/18.....DL, 8/10/18; The project is on schedule and we will start on Monday.......Ahead of schedule, project will be complete on 8/29/18......DL, 9/6/18; This project is 100% complete. Note, Maggie did request Jess to come back and remove some glue and he has this scheduled..... |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-02-16
18P000349 |  | 18P000349 | FALSE | BCOE | SL5-PHYSICS INSTALL PARTITION WALL FOR LAB ROOM | Complete as of 7/11/18 | PHYSICS | 1037 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 5/24/18; Ron V. has detailed scope and he is ordering material. Once material arives, we will schedule the work…. DL, 6/16/18; Materila is ordered, When door/frame arrives, we will prep, paint and start the work…….DL, 7/11/18; This Project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; This is a small partition wall with sound proofing to minimize noise from the compressor that is disruptive to the Helium Ion Microscope…….DL, 4/16/18; We will schedule this work to be complete by the end of the Spring quarter. DL, 5/19/18; Walked project with Ron. FAMIS work order producd and material is being ordered.... | YES | FS | 0 | 2018 | 2019-02-16
18P000394 |  | 18P000394 | FALSE | BCOE | SL5-BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK | Project work has been complete but work is being reviewed by faculty. Sound soak may be installed. | BOURNS | A0159A | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 2 | TRUE |  |  | 2018-04-12 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………….1/15/19, DL; Sound Soak is ordered and should arrive within two weeks……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; Need to review and scheudle…….DL, 7/11/18; Still need to review and scheudle…..DL, 8/22/18; This Project is complete but Maggie wants to see if the Faculty are happy with the results. We may install Sound Soak as a final option…… DL 9/6/18; Sent Maggie an email to see if she is satified with the work performed in regards to the sound proofing. I will have an update by the next Excel update….. DL, 9/19/18; The PI is out of town. Maggie will confirm the PI is satisiofd with the work when they return……on 9/18/18…DL, 10/8/18; Customer not satisfied with first round of sound proofing. We will proceed with Sound Soak material….. |  | Enrico Baez | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. EB 6/1 site visit- 3 door between 4 offices require sound proofing. Doors measure 36" x 106". Photos in FAMMIS. O-RVL: Uploaded sound soak panel data on FAMIS and is available on the Project Server File. 10/18/18 O-RVL: Per FS team meeting, we now have a clarified process that sound soak is not included in the SLA due to the fact this is not part of the work we perform at FS. Because we already committed to do further follow up with the sound soak, we will not charge this time but moving forward sound soak will be a recharge service as the team does not have the skillset to do the work and therefore outside the SLA. | YES | FS | 0 | 2018 | 2019-02-16
19P000445 |  | 19P000445 | FALSE | BCOE | SL5-BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT |  | BOURNS HALL | B0328D | HOLD - FACILITIES SERVICES | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  |  |  | 0 |  | FALSE |  |  | 2019-01-11 | [8 empty] | Ron Veloz | 02/15/19 O-RVL: Ron V will contact Maggie and explain this request would exceed our proejct allowance and place FS out of compliance with UC requirements. RV will present options to the customer. Possibility to utilize black out curtains and or BKM style furniture as an immediate altenative (Cost absorbed by the departments). The customer will be able to resubmit the request at a later date. END--- 2/7/19: Alan S. Customer Relations Team to follow-up with customer re: change in scope of work. | N/A | FS | 0 | 2019 | 2019-02-16
19P000453 |  | 19P000453 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT |  | CHUNG HALL | 447 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-17 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | FS | 0 | 2019 | 2019-02-16
19P000278 |  | 19P000278 | FALSE | BCOE | SL5-REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR | Scheduling work for completion | BOURNS | A0165 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Dan Lerman |  | 1 |  | TRUE |  |  | 2018-08-03 | [6 empty] | DL, 10/4/18; This Project is 100% Complete…….. |  | Ron Veloz | Completed SOW, met withJess and informed of work and color. | YES | FS | 0 | 2018 | 2019-02-16
19P000059 |  | 19P000059 | FALSE | BCOE | SL5-CHUNG HALL 201 SECURITY SYSTEM INSTALL | ITS to install cameras, no work by FS Required. | CHUNG HALL | 201 | CANCELED BY FS | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 10 | 7 | FALSE |  |  | 2018-07-17 | [6 empty] | DND 7/30/18 Project #19P000059 to replace REF CPMS # 9054 Ron to speak with ITS to complete installation. |  | Ron Veloz | 10/29/18 RV: Last meeting it was discussed that FS does not install Security Camera systems. Ron V spoke with Maggie on 10/26 to inform her that the project will be removed from the FS Minor Ren. List and she will need to contact ITS to request the Security Camers. 08/27/18 RV: Updated notes. Moved to "Que to Start". 09/19/18 RV, Install Security Cameras at points of entry. Install DVR locally in closet at an adjacent room. 08/23/18-RV Met with D.L. and Jason W. and verified F.S. will perform cabling installation and mount cameras. Equipment cost is not included in the SLA. R.V. will communcate informantion to Maggie. 08/22/18 O-RVL: Met with M. Souder to determine security camera needs and approximate location. | YES | FS | 0 | 2018 | 2019-02-16
19P000029 |  | 19P000029 | FALSE | BCOE | SL5-CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | Canceled; duplicate request to be completed with 19P000059 | CHUNG HALL | 205 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-16 | [6 empty] | Canceled; duplicate request to be completed with 19P000059 |  | Ron Veloz | to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | NO | FS | 0 | 2018 | 2019-02-16
19P000316 |  | 19P000316 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL | Anticipated completion mid November | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…Anticipated completion 11/9/18. | 2018-10-03 | Ron Veloz |  | YES | FS | 0 | 2018 | 2019-02-16
19P000046 |  | 19P000046 | FALSE | BCOE | SL5-PATCH AND PAINT PLUS REPLACE BLINDS | Complete as of 11/8/18 | BOURNS | A0131 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000442 |  | 19P000442 | FALSE | BCOE | SL5- WINSTON CHUNG- PATCH/PAINT ROOM 319 |  | CHUNG HALL | 319 | QUEUE TO START | Christopher Lynch | Maggie Souder | BILL BINGHAM |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-09 | [11 empty] | FS | 0 | 2019 | 2019-02-16
19P000175 |  | 19P000175 | FALSE | BCOE | SL5-PAINTING | Complete as of 10/10/18 | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT CHAVARRIA-VIVAR |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000312 |  | 19P000312 | FALSE | BCOE | SL5-VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP |  | STUDENT SERV | 1227 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000205 |  | 19P000205 | FALSE | BCOE | SL5-LABORATORY RENOVATION FOR NEW FACULTY | Plans under review by Fire Marshal; clarification required on sprinkler system. | BOURNS | A0328 | IN PROGRESS | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  | Dan Lerman |  | 4 |  | TRUE |  |  | 2018-08-23 | [6 empty] | 2/1/19, DL; This project is 99.9% Complete………..1/15/19, DL; This project is 90% complete. WE still need to finish snorkels and ceiling tiles. We should be 100% complete by 2/1/19……12/14/18, DL; This project is on schedule..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/4/18; This is a large scale project, we will walk with the trade supervisors next week. We will also work on the plans and schedule the work. Target Date is 1/1/19…..DL, 11/7/18; work is scheduled. We are working on the electrostatic paint contract. We are in plan check review process. There are questions about the fire sprinklers from Scott J. Sent Scott J. an email requesting a site visit to better determine if any work will be required on the sprinkler system….. |  | Ron Veloz | 10/03/18: RV spoke with Dan. He had previously met with Maggie and had scoped this project. | YES | FS | 0 | 2018 | 2019-02-16
19P000322 |  | 19P000322 | FALSE | BCOE | SL5-CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT |  | CHUNG HALL | 103 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-05 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000424 |  | 19P000424 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET |  | CHUNG HALL | 445 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-12-20 | [11 empty] | FS | 0 | 2018 | 2019-02-16
19P000250 |  | 19P000250 | FALSE | BCOE | SL5-BOURNS A303-PAINT AND PATCH WALL | Complete as of 10/10/18 | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | JUANA GUERRERO |  | Paul Ditty |  | 5 |  | TRUE |  |  | 2018-09-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000060 |  | 19P000060 | FALSE | BCOE | SL5-CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | CHUNG HALL | 223 & 224 | TO BE PERFORMED BY PD&C | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 6 | 4 | FALSE |  |  | 2018-05-15 | [6 empty] | 2/1/19, DL; Thios is a PD&C project. Maggie S. is aware this project may be a $130,00. project……DL, 7/25/18; This project is complicated and plans/permits will be required. This project will also require Air Hanlers to be shut down so Vibration dampners can be instlled. We will work on the plans in the next 45 days. This project should be scheduled during the Winter. We may also need to rent a large portable air handler to ensure the Large server room can maintain temp……. Project #19P000060 to replace REF CPMS # 9043. DL, 11/7/18; Sent Maggie an email on 11/7/18 informing her this project is well beyond our scope and $50K threshold. |  | Dan Lerman | DD 7/17: IRT Scoped with Dan present. Attached to FS Project. REF CMPS 9043 | YES | FS | 0 | 2018 | 2019-02-16
18P000226 |  | 18P000226 | FALSE | BCOE | SL5-BOURNS FUME HOOD INSTALLATION | Installation of utilities to be completed; clean room to be installed upon utility connections. | BOURNS | B0235A | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  | 8 | HOLD | TRUE |  |  | 2017-12-11 | [6 empty] | 2/14/19, DL; This project is Complete…..2/1/19, DL; The Fume hood is complete. The vendor will be back in two weeks to comissison the clean room…..…1/15/9, DL; This project is 95% complete and should be complete on or near 2/1/19…………12/14/18, DL; This Project is 90% Complete. Fume hood is scheduled for install next week. We will finish balance of project after Fume hood is installed…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. WE are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans…..DL, 5/9/18; planning to submit plans on 5/11/18 for plan check review….. DL, 5/24/18; Plans were submitted to Bob W. on 5/24/18……DL, 6/12/18; Project is on Hold until Shane can provide plans/specs for the clean room……DL, 7/11/18; Still no change to the status……DL, 7/25/18, Maggie confirmed this project is on the books. I need to discuss the status with the team because the priority list is on Hold…….DL, 8/22/18; This project is no longer on hold. We will per shane we will submit what we have from the clena room suupplier for review from FM and BO……DL, 9/6/18; WE are almost complete with Plans and will submit the plans next week………DL, 9/19/18; Submitted plans to PD&C on 9/14/18…..DL, 10/4/18; Plans were approved thais week. WE will scheudle the project around the delivery date for the Clean room……..DL, 11/7/18; This is in progress. We will complete the install of the utilities so the clean room can be installed. WE will finish the balance of the project once the Clean room install is complete. The clen room is being install by an outside vendor….. |  | Dan Lerman | 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. We are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans..... DND 7/14 Hold per customer on prioritizatio | YES | FS | 0 | 2017 | 2019-02-16
19P000129 |  | 19P000129 | FALSE | BCOE | SL5-HANG MONITORS AND BOARDS | Dry erase boards and monitor mount installation complete; monitors to be installed. | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | RICHARD BAIN |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2018-08-06 | [6 empty] | 12/14/18, DL; This Project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Dry errase boards and Monitor mounts are installed. Still need to install monitors, corner guards and monitors….. |  | Ron Veloz | 10/03/18 O-RVL: Install one 32" monitor asouth wall center of table, Install 55" TV at west wall(need power & data), install white bd at east wall 8' from north corner, install chalk bd at east wall 2'-6" from corner at 8" above small table. | YES | FS | 0 | 2018 | 2019-02-16
19P000035 |  | 19P000035 | FALSE | BCOE | SL5-WCH--INSTALL NEW LED DISPLAY IN OFFICE | Installation scheduled for Friday 11/19/18. | CHUNG HALL | 354 | COMPLETE | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This Porject is 100% Complet…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Install scheduled for this Friday. | 2018-10-03 | Ron Veloz | 10/03/18 RV Walked site with Dan L. SOW Install TV Bracket at south wall center of room. Requires Power (no Data)installation of mounting bracket. TV and brk is located in Sarah Galloways office. Scope is completed. Dinh 9/18 19P000023/19P000026 requests for paint to be included in project scope for room. | YES | FS | 0 | 2018 | 2019-02-16
19P000026 |  | 19P000026 | FALSE | BCOE | SL5-WCH PATCH AND PAINT WALLS | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000023. Canceled to be completed on 19P000035 | N/A | FS | 0 | 2018 | 2019-02-16
19P000023 |  | 19P000023 | FALSE | BCOE | SL5-PAINT ACCENT WALL | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-13 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000026. Canceled to be completed on 19P000035 | N/A | FS | 0 | 2018 | 2019-02-16
18P000438 |  | 18P000438 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING | Complete as of 9/10/18 | CHUNG HALL | 415 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 10 | FALSE |  |  | 2018-05-14 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000439 |  | 18P000439 | FALSE | BCOE | SL5-CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING | Complete as of 9/10/18 | CHUNG HALL | 315 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 11 | FALSE |  |  | 2018-05-15 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000028 |  | 19P000028 | FALSE | BCOE | SL5-BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS | Deferred to Winter Quarter | BOURNS | A0169 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | Deferred to Winter Quarter |  | FALSE |  |  | 2018-07-16 | [7 empty] | 2018-11-14 | Ron Veloz | 10/29/18 RV: Scoping is completed. Carpenters to Remove Ceiling Mounted TV supports from the lobby ceiling. Work may require Carpenters to open the hard ceiling and remove the TV bracket posts if they cannot be unscrewed from the mounting brkt at the deck above. Work ay also require drywall patch back, tape, sand and paint the lobby ceiling. 11/14/18 RV: Moved to Que to Start. | YES | FS | 0 | 2018 | 2019-02-16
2860 | 2860 |  | FALSE | BCOE | Bourns B0152 - Fume Hood | Please investigate feasibility and provide an estimate for installation of ductwork and a four foot fume hood sufficiently equipped and sized to include an exhaust line for a 2-standard sized cylinder gas storage cabinet. Location should be recommended based on proximity of existing building/floor exhaust ductwork. Should it become necessary, the size of the gas cabinet may be considered for reduction. | BOURNS |  | In Close-out | Christopher Lynch | Maggie Souder | Margaret Souder |  | Scott Donnell | 1 |  |  | FALSE | 0 |  | 2015-04-01 | ASHRAE & Certification | 2018-01-01 | 2018-05-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
3300 | 3300 |  | FALSE | BCOE | R'Garden - Solar Installation | Electrician to do the following wiring of our solar panels and inverters out at the R’Garden at UCR. The H model cyboinverter to be used powers the lower heating element of the water heater. The thermostat of the lower heating element must then be set to be higher than the upper heating element. The two output lines are to be connected to an AC switch or switchable AC outlet and the lower element water heater. |  |  | Work to be inspected by A&E. | Christopher Lynch | Maggie Souder | Arvin Tam |  | Scott Donnell | 2 |  |  | FALSE | 0 |  | 2017-05-03 | To be disassembled in June 2019 |  | 2019-06-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3427 | 3427 |  | FALSE | BCOE | C-CERT Install Meter | Site: inland empire utility agency (IEUA) Meter install: Allen Bradley PowerMonitor 5000 price of meter is $7,410 Projected price of install: $15-20k Scope of work: Meter will be purchased by UCR for install at the main panel at the IEUA Carbon Canyon Facility. Once the meter is installed then it will be used to send Energy data back to their SCADA system and monitor and display real time data. |  |  | Blair to investigate | Christopher Lynch | Maggie Souder | Todd Ambriz |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2018-03-21 | Start Construction | 2019-02-04 | 2019-02-28 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3224 | 3224 |  | FALSE | BCOE | Bourns - Door Access Control | Replace outdated failing, and unsupported Identicard card reader system with campus approved Hirsch system at all existing locations in Bourns Hall B-wing at a minimum; inclusion of card readers in Bourns A-wing is also desired if possible. Immediate work is optimal since the building is currently under construction and many walls, ceilings, wiring, etc are currently exposed. Work to be done via surplus funds from BCOE 950534. AVC is putting together the costs and scope via meetings with Maggie/ Pat/ and John C. | BOURNS |  | Programming | Christopher Lynch | Maggie Souder | Margaret Souder |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 2016-11-14 | Create SOW and Transfer funds | 2019-09-01 | 2019-11-29 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3315 | 3315 |  | FALSE | BCOE | Bourns B144 - Lab Safety Improvements | Incorporate life safety improvements to research lab. Provide additional protection for Pyrophoric Gases. Provide sprinkler protection inside the pyrophoric gas cabinet. Provide an Automatic shutdown device for pyrophoric gas flow when activated by interlocks tied into fire sprinkler. Provide a remote manual shut down device of pyrophoric gas outside the gas cabinet. Provide audible and visible alarm detection and monitoring for toxic and highly flammable gases including diborane, germane, ammonia and hydrogen gases Applicable references on the above are NFPA 55 (Compressed Gases Code) and NFPA 45 (Standard on Fire Protection for Labs using Chemicals). | BOURNS |  | Need to confirm Dept. funding commitment | Christopher Lynch | Maggie Souder | Jianlin Liu |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2017-05-23 | Confirm Dept. Commitment/Funding | [10 empty] | PD&C | 0 | 2017 | 2019-02-16
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | 2 of 5 suppliers contact have responded | Christopher Lynch | Maggie Souder | Margaret Souder |  | Dave Bomba | 6 |  |  | FALSE | 700000 |  | 2018-04-04 | Design Documents | 2019-04-01 | 2019-07-31 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3206 | 3206 |  | FALSE | BCOE | Bourns B-134 & B-108 - Removal (Add Fume Hd.) | Add 6' (if able) fume hoods to instructional labs Bourns B-108 and B-134. Depending on cost, department will include: 1. stub in of necessary exhaust and electrical infrastructure to support basic fume hood (without water, gas, vacuum, etc.) in south wall of B-134 (west end) and north wall of B-108 (west end) 2. Install new 6' hoods in locations noted above To take advantage of room instructional and work schedule, please run concurrently if possible with planned work in the room over the 2016 holiday break. | BOURNS |  | In Construction | Christopher Lynch | Maggie Souder | Sabrina Schuster |  | Scott Donnell | 8 |  |  | FALSE | 1000 |  | 2016-10-15 | Complete Construction | 2018-10-01 | 2019-02-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
19P000296 |  | 19P000296 | FALSE | CAMPUS | SL5-MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB | Plans and permits to be developed for this project. | MAT SCI ENGR |  | IN PROGRESS |  |  | MILLY PAREDEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-09-25 | [6 empty] | 2/14/19, DL; This project is 90% Complete and should be complete by the end of the month………….2/1/19, DL; Permits are approved, we will schedule the project in the next 2- weeks and hope to be complete by the end of February….12/14/18, DL; Rendering has been given to Ron R. Ron will present to Gerry for review and approval. Once approved, we will proceed with plans and permits……DL, 11/7/18; Need to find out where this project stands in regards to the priioroity….. Site vist was conducted and scope of work is verified. Plans and permits will be required for the work….. |  | Ron Veloz | 10/19/18 O-RVL: Walked the proposed location with Dr. Barsukov to review needs and location for nitrogen tanks in the hall. DL suggested to construct a wall with double doors approx 2' below the ceiling height. 09/27/18 O-RVL: Walked site with Chris P, Dan L., Deborah Mc Williams & Mayela C to review SOW. | YES | FS | 0 | 2018 | 2019-02-16
19P000188 |  | 19P000188 | FALSE | CAMPUS | SL5-PAINT - HALLWAY DOORS & INSIDE RESTROOMS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500 | CANCELED BY FS |  |  | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-16 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-02-16
19P000211 |  | 19P000211 | FALSE | CAMPUS | SL5-LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | Reviewing campus standards for these project requests. | LIFE SCIENCE | 2545 | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-02-16
18P000121 |  | 18P000121 | FALSE | CAMPUS | SL5-PHYSICS HYDRATION STATION - PHYSICS HALL | Reviewing campus standards for these project requests. | PHYSICS | 0 | HOLD - FACILITIES SERVICES |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | 12/6/18, DL; This project is currently on hold…... DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus | NO | FS | 0 | 2017 | 2019-02-16
18P000435 |  | 18P000435 | FALSE | CAMPUS | SL5-HMSS HYDRATION STATION REQUEST | Pending Hydration station plan for campus | HUM & SOC SC | 3600 | HOLD - FACILITIES SERVICES |  |  | NELDA THOMAS |  | Dan Lerman |  |  | 30 | FALSE |  |  | 2018-05-10 | [10 empty] | NO | FS | 0 | 2018 | 2019-02-16
18P000122 |  | 18P000122 | FALSE | CAMPUS | SL5-MS&E HYDRATION STATION - MS&E HALL | Reviewing campus standards for these project requests. | PHYSICS | 0 | PROJECT INTAKE |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus | NO | FS | 0 | 2017 | 2019-02-16
19P000212 |  | 19P000212 | FALSE | CAMPUS | SL5-REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500A | HOLD - FACILITIES SERVICES |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-02-16
19P000284 |  | 19P000284 | FALSE | CAMPUS | SL5-GEOLOGY ACCOMMODATION DOCK DOORS | Coordinating work for completion. | GEOLOGY |  | COMPLETE |  |  | DEBORAH TERAO |  | Chris Pillen |  | Canceled | Canceled | FALSE |  |  | 2018-08-07 | [8 empty] | Ron Veloz | 01/10/19 O-RVL: CLOSE OUT-WORK COMPLETED. All work for this project is completed. Email sent to Monty & team on Jan 04, 2019 confirmating all work is completed. 12/14/18 O-RVL: Loading dock Post and Chain fabrication, is in progress, Auto door operators are on Order/Contract in progress, Loading dock signage is in progress by sign shop, information was confirmed by Chris Pillen as of 12/13/18. All other request related to this project have been completed. RV sent updates to Monty on 12/13/18. 11/14/18 RV: Walked Capitol door on 10/31 for pricing. pending quote for auto door operators. 10/30/18 RV: Walke Paradise Door -Automatic Door operator vendor to site. Met with Jason to discuss door access hardware & function of locksets . Pending quote. 10/03/18 RV: Notes from FAMIS: Lock Shop - Chris working with Jason to purchase and install two sets of automatic door openers with plain face plates - to be installed in the back receivin area. | YES | FS | 0 | 2018 | 2019-02-16
3233 | 3233 |  | FALSE | CAP.PROG. | Mobility HUB Central Campus Linkages | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In bidding | TBD | Sharyl Murdock | Jaime Enghbrecht |  | Drew Hecht | 1 |  |  | FALSE | 16011000 |  | 2016-12-16 | Bidding | 2019-04-01 | 2020-01-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3234 | 3234 |  | FALSE | CAP.PROG. | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Design-SD | TBD | Sharyl Murdock | John White |  | Fernando Nunez | 2 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete Construction | 2018-11-05 | 2019-02-28 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3452 | 3452 |  | FALSE | CAP.PROG. | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming | TBD | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 2 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Programming | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3120 | 3120 |  | FALSE | CAP.PROG. | Arts Walk Sculpture (Ext Campus Art Project) | Sculpture design concept - hiring a consultant to revise an artist design concept for a proposed outdoor art piece to be placed between the Arts building and the CHASS Interdisciplinary buildings. |  |  | A&E and CAS in discussions w/Artist re: design. | TBD | Sharyl Murdock | Uma Ramasubramanian |  | Jason Espinoza | 4 |  |  | FALSE | 1000000 |  | 2016-05-26 | Complete Construction | 2019-02-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3119 | 3119 |  | FALSE | CAP.PROG. | Plant Growth Environment Facility | The campus has identified a need for modern plant growth and research support facilities, as documented in an April 2016 feasibility study that considered current and future needs for these types of facilities. The Plant Growth Environments Facility will complete construction late third quarter of 2019 to address this need. The project is expected to provide 40,000 gsf of greenhouses, head house, plant growth chambers and support spaces. Currently, the facility is envisioned as a two story structure with 20,000 of greenhouses occupying the upper level. The project delivery method is a design/build competition. |  |  | Design Build Proposal Awarded, design and construction contract execution has started | TBD | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 5 |  |  | FALSE | 1800000 |  | 2016-05-25 | Design-Build Proposal Evaluation | 2019-04-01 | 2020-08-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3458 | 3458 |  | FALSE | CAP.PROG. | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | No update | TBD | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 7 |  |  | FALSE | 0 |  | 2018-07-16 | Unknown | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3293 | 3293 |  | FALSE | CAP.PROG. | USDA Head House - Public Restroom | Provide an accessible public restroom facility in or adjacent to the USDA Head House Building in Ag Ops. Restroom will serve individuals and groups touring the UCR and USDA Citrus Facilities. Three options have been proposed, and need to be considered and evaluated to recommend a feasible solution for USDA. The work would be managed and paid by USDA, including the design, bidding and construction. UCR staff needs to review the proposed plans and specifications per the agreement with USDA, and provide the review, inspection and approvals. The USDA representative is Marylou Polek. | GERMPLASM |  | Pending Lease | TBD | Sharyl Murdock | Mary Lou Polek |  | Scott Donnell | 11 |  |  | FALSE | 0 |  | 2017-05-22 | USDA Scope & Design | [10 empty] | PD&C | 0 | 2017 | 2019-02-16
3319 | 3319 |  | FALSE | CAP.PROG. | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Design Build competition. | TBD | Sharyl Murdock | ----- |  | Mihai Gavan | 13 |  |  | FALSE | 3327000 |  | 2017-06-01 | Award Contract | 2019-09-01 | 2021-05-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3005 | 3005 |  | FALSE | CAP.PROG. | Batchelor Hall Interior Improvements | Interior renovation of public areas | BATCHELOR |  | Finalize Project Scope. Receive direction from VC. Awaiting Leadership approval. | TBD | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 14 |  |  | FALSE | 8837000 |  | 2016-02-02 | CM at Risk Selection | 2019-09-01 | 2021-10-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3393 | 3393 |  | FALSE | CAP.PROG. | South Neighborhood Dist. Study | South Neighborhood District Study per discussions with the Provost/VCPB, July 2017. The South District Planning Study needs to provide guidance for future development in the South District that is inclusive of: **University aspirations to develop the South District to define the campus’ presence along the adjacent freeway (CA-60/215). **Development capacity, optimal building heights and conceptual massing presented both in metrics and a three dimensional format. **Broad parking strategy to meet the needs of the district in alignment with the campus’ overall parking management strategy and alternative transportation solutions. **High level understanding of infrastructure needs (electrical, domestic, fire and storm water, sanitary sewer, building heating and cooling) to meet the needs of the campus’ desired development capacity for district. **Pedestrian and vehicular connectivity. **East and South Campus Drive improvements |  |  | Programming | TBD | Sharyl Murdock | Uma Ramasubramanian |  | Fernando Nunez | 15 |  |  | FALSE | 309000 |  | 2017-11-15 | Receive Study Reports | [10 empty] | PD&C | 0 | 2017 | 2019-02-16
3366 | 3366 |  | FALSE | CAP.PROG. | Genomics Sdwk Rpr-Drainage Impr | Genomics Accessibility Improvements - The proposed project will create an accessible sidewalk connection from the Genomics Building to the University Lab and University Office Building. Currently, there is no accessible north sidewalk linkage east of the Genomics Building. The project will demolish and replace approximately 300 square feet of asphalt to bring it up to grade. Two ADA ramps will be added to sidewalk extensions of approximately 300 square feet that connect across a driveway. Existing landscaping and irrigation will be removed and replaced. No trees will be impacted by this work. |  |  | In Funding | TBD | Sharyl Murdock | Jaime Engbrecht |  | Dave Bomba | 16 |  |  | FALSE | 0 |  | 2017-11-16 | Secure Funding | 2019-04-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
2970 | 2970 |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan - Phase 2 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | TBD | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 17 |  |  | FALSE | 2842000 |  | 2015-12-02 | Complete Construction | 2018-09-26 | 2019-06-30 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
3401 | 3401 |  | FALSE | CAP.PROG. | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | Waiting for P funding to proceed with design. | TBD | Sharyl Murdock | Jeff Kaplan |  | Mihai Gavan | 18 |  |  | FALSE | 1530020 |  | 2017-12-03 | P Approval and Funding | 2019-09-01 | 2020-12-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
2952 | 2952 |  | FALSE | CAP.PROG. | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | TBD | Sharyl Murdock | Jon Harvey |  | Dave Bomba | 19 |  |  | FALSE | 23308000 |  | 2015-09-11 | Completion of phase one | 2019-01-02 | 2021-04-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
3395 | 3395 |  | FALSE | CAP.PROG. | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | Third party cost estimator needed. | TBD | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 20 |  |  | FALSE | 0 |  | 2017-12-03 | [11 empty] | PD&C | 0 | 2017 | 2019-02-16
3438 | 3438 |  | FALSE | CAP.PROG. | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | City to determine schedule | TBD | Sharyl Murdock | Dave Bomba |  | Dave Bomba | 21 |  |  | FALSE | 0 |  | 2018-08-22 | City to determine schedule | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
2916 | 2916 |  | FALSE | CAP.PROG. | Solar Greenhouse | Construction of a solar powered greenhouse. |  |  | Installing solar components | TBD | Sharyl Murdock | Matt Barth |  | Scott Donnell | 99 |  |  | FALSE | 174000 |  | 2015-08-04 | Award Contract | 2019-03-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
3175 | 3175 |  | FALSE | CAP.PROG. | DM-Chilled Water Coils Multiple Buildings | Replace multiple leaking/degraded cooling coils across campus to prevent complete shutdown of building air handlers during the hot summer months. Buildings include: Student Services, Chemical Sciences, Genomics, Psychology, Entomology and MSE. |  |  | In Construction | TBD | Sharyl Murdock | Melissa Garrety |  | Scott Donnell | 99 |  |  | FALSE | 1090000 |  | 2016-10-11 | Complete Construction | 2019-01-01 | 2019-04-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
18P000329 |  | 18P000329 | FALSE | CHANCELLOR | SL5-SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST | Project complete as of 9/18/18 | SKYE HALL | 170 | COMPLETE | Kim Wilcox | Karim Zahedi | DA LAN DINH |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18…..DL, 5/24/18; Plans were approved. Demo work has started......DL, 6/12/18; MArshal and Kate are working on Carpet order......DL, 7/11/18; Carpet is ordered. We have a challenge with Title 24. I am working on the title 24 documents. We are still planning to have this project complete on 8/17/18......DL, 8/10/18; We now have the Title 24 plans. The are being reviewed by Bob and Scott.....Title 24 plans approved. Robert is working on PO#. Most parts are on site and Electricans are working on project. All other Trades to follow once Lights are in...... Hard Date of 9/7/18............9/6/18 As of today, Carpet is scheduled for install tomorrow morning and furniture is scheduled for delivery this Monday......WE will more than likely have electrical punch items and touch up paint but this propject should be 100% complete in regards to FS the end of next week next week......100% PROJECT COMPLETE... GREAT WORK DAN! |  | Dan Lerman | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18….. | YES | FS | 0 | 2018 | 2019-02-16
18P000410 |  | 18P000410 | FALSE | CHANCELLOR | SL5-HINDERAKER PAINT AND PATCH WALL | Complete as of 8/24/18 | HINDERAKER | 3148B | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-25 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000209 |  | 18P000209 | FALSE | CHANCELLOR | SL5-VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 | Customer provided estimate for project; verifying if funding is available to proceed with project. | STUDENT SERV | 0 | QUEUE TO START | Kim Wilcox | Karim Zahedi | ANGIE GRAY |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2017-11-30 | [6 empty] | 2/14/19, DL; Ron V. to follow up with Doug from Capitol Door for alternate pricing .1/15/19, DL; Ron V is still working with Angie on verifying a vendor and product…………..12/14/18, DL; Ron V. is currently working to find a more affortable turnstyle system. When a sytem is approved, we will schedule the work…. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope and conduct site visit……DL, 7/11/18; This work will require plans and permits. Will schedule meeting with Scott to verify if the project request will be approved. If this is approved, we will plan the target complete date to be mid October…..The Request is to reverese Emergency Exit Doors and install Prox card access……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..DL, 8/22/18; Confirmed with Scott that we can reverse the door swing. We will work on plans for review process. This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 9/19/18; I mis understood this for a project at Health Services. I have a meeting with Angie this week. This project is to install turn styles for access to the building. I will need to discuss the equipment to be purchased by Angie verify the specs. We will start on the plans in the early Fall……DL, 11/7/18; Conducted site visit with Vendor. Informed Angie the cost of the project will be at $45K for the project. Angie is checking to verify if funds are availabe for the equipment. |  | Enrico Baez | 2/2/18 EB site visit scheduled for 2/5/18 with Angie Gray. 2/6/18 EB- conducted site visit. Request for automated access control system. Annotated on FAMIS….DL, 5/5/18; FAMIS work order ,New ADA operator, power supply for operator and card swipe….. | YES | FS | 0 | 2017 | 2019-02-16
18P000421 |  | 18P000421 | FALSE | CHANCELLOR | SL5-HINDERAKER PAINT AND PATCH WALL | Complete as of 8/24/18 | HINDERAKER | 2120 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-04-30 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5--HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 |  | HINDERAKER | 1101 | QUEUE TO START | Kim Wilcox | Karim Zahedi | ALEXIS RAMBAUD |  |  |  | 0 |  | FALSE |  |  | 2018-12-11 | [7 empty] | 2018-12-20 | Ron Veloz | 01/17/19 O-RVL: RV emailed Karim to inform him of the project covered under the SLA. 01/15/19 O-RVL: Met with Monty on 1/15, Monty informed RV the work will be covered under the SLA agreement in support of Business operations. No estimate is required. RV to contact Karim with this information on 01/16/19. 01/14/19: O-RVL: Met with Dan L. onsite to review the project scope. RV & Dan also spoke with Louis about the process. RV will work on the estimate and submit to Karim & Louis by CBD 01/18/19. RV Has informed Dan L. the project is on the "Non Prioritized List". 01/11/19: O-RVL: Emailed Karim and informed him that he will receive an estimate later the following week. 01/07/19: O-RVL: Monty asked Enrico to look into the this project. I (RV) told Monty that I'm already involved and will complete the estimate. Monty agreed and asked RV to follow up with Karim. 12/21/18 O-RVL: Received a response from Bob W., stating "the area is suitable to be an office space understanding understanding that we must conduct a more in-depth review and approval process..." 12/20/18 O-RVL: Emailed Bob Williams with the existing and proposed floor plan asking if it would be suitable to create an office and requested a budget estimate to add a wall with a door. 12/20/18 O-RVL: Ron V. Visited site and spoke with Karim and viewed the proposed location for the new office. 12/18/19 O-RVL: Received email from D. Hughes on 12/18/18 to look into this request for estimate. | YES | FS | 0 | 2018 | 2019-02-16
18P000414 |  | 18P000414 | FALSE | CHANCELLOR | SL5-CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL | FS to coordinate with client to schedule work for completion. | STUDENT SERV | 0 | QUEUE TO START | Kim Wilcox | Karim Zahedi | DANIELLE GARCIA |  | Paul Ditty |  | 1 | 2 | FALSE |  |  | 2018-04-26 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000375 |  | 19P000375 | FALSE | CHANCELLOR | SL5-PATCH AND PAINT HOLES |  | SKYE HALL | 365 | COMPLETE | Kim Wilcox | Karim Zahedi | FELECIA GARRETT |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-07 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000487 |  | 18P000487 | FALSE | CHANCELLOR | SL5-SKYE HALL PATCH HOLES AND PAINT | Complete as of 10/22/18. | SKYE HALL | 349 | COMPLETE | Kim Wilcox | Karim Zahedi | SONIA ZAMORA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000420 |  | 19P000420 | FALSE | CHANCELLOR | SL5-PATCH AND PAINT WALL |  | SKYE HALL | 325 | COMPLETE | Kim Wilcox | Karim Zahedi | REYNA ALARCON |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-19 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | FS | 0 | 2018 | 2019-02-16
19P000122 |  | 19P000122 | FALSE | CHANCELLOR | SL5-REMOVE, PATCH & PAINT AND HANG | Complete as of 10/22/18. | STUDENT SERV | 2222 | COMPLETE | Kim Wilcox | Karim Zahedi | CHRISTINE SMITH |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | FS | 0 | 2018 | 2019-02-16
18P000297 |  | 18P000297 | FALSE | CHANCELLOR | SL5-SKYE HALL CHECK LOCATION FOR TV INSTALL | Scope of work has been reviewed; determining how to complete project with trades. | SKYE HALL | 390 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Dan Lerman |  | 4 | 3 | FALSE |  |  | 2018-02-02 | [6 empty] | 2/1/19, DL; This Project is 100% Complete………1/18/19, DL; This Project is scheduled to be complete next week.….. DL, 5/24/18; Need to verify scope with Enrico…..DL, 7/11/18; Work orders are produced and need to be issued. Target complete date is 9/3/18…. |  | Enrico Baez | EB-scoped on 1/30. Mount TV above table. Advised an articulated mount be purchased. Drawing on FAMMIS WO. | YES | FS | 0 | 2018 | 2019-02-16
18P000445 |  | 18P000445 | FALSE | CHASS | SL5-PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 | Complete as of 9/10/18 | ARTS | 225 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 11 | TRUE |  |  | 2018-05-21 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000367 |  | 18P000367 | FALSE | CHASS | SL5-CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE | Complete as of 7/14/18 | CHASS INT N | 3033 | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 23 | FALSE |  |  | 2018-03-27 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18W016588 |  | 18W016588 | FALSE | CHASS | PATCH AND PAINT FOR FACULTY | Complete as of 8/24/18 | SPROUL | 4105 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | N/A | TRUE |  |  | 2018-06-19 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000056 |  | 19P000056 | FALSE | CHASS | SL5-HMSS CAPABILITY OF MOUNTING A TV | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 1212 | IN PROGRESS | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  |  | 18 | FALSE |  |  | 2017-10-03 | [6 empty] | 12/14/18, DL; Monitor is complete. Still need to work on electrical……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope with Enrico and schedule the work…. Work orders are not produced. Need to assign and schedule the work DND 7/30/18: Closed work order #18W004822; created project #19P000056……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | EB 3/26-Project scoped on 10/23/17. Attached 5 photos and made annotations to FAMIS. | YES | FS | 0 | 2017 | 2019-02-16
18P000468 |  | 18P000468 | FALSE | CHASS | SL5-WATKINS 1222/1223 PATCH/PAINT | Completed as of 8/10/18 | WATKINS | 1222 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 13 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000383 |  | 18P000383 | FALSE | CHASS | SL5-HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT | Completed as of 8/10/18 | HUM & SOC SC | 1302 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  | 4 | TRUE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000364 |  | 19P000364 | FALSE | CHASS | SL5-PATCH AND PAINT |  | CHASS INT S | 3106 | COMPLETE | Milagros Pena | Cindy Williams | FRANCESCA MOREIRA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-30 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000417 |  | 18P000417 | FALSE | CHASS | SL5-HMSS UWP INSTRUCTIONAL OFFICE PAINTING | Complete as of 8/24/18 | HUM & SOC SC | 2106 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000294 |  | 18P000294 | FALSE | CHASS | SL5-HMSS REMOVE DOOR, INSTALL WALL | Canceled on 7/16/18 per email communication with customer. | HUM & SOC SC | 3610 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2018-02-01 | [8 empty] | Enrico Baez | 5/23/18 EB sent email request for site visit DND 7/14 Hold per customer on prioritization Canceled per customer on 7/16/18 via email with Enrico. | YES | FS | 0 | 2018 | 2019-02-16
18P000295 |  | 18P000295 | FALSE | CHASS | SL5-CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL | Complete as of 9/21/18 | CHASS INT S | 2117J | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-02-01 | [6 empty] | DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18……..DL, 5/24/18; Plans were approved. We need to scheudle the work….DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets.......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date.....DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18...........DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware..... |  | Enrico Baez | 4/25 EB Scoped site. Remove counter and Cage. Drywal closed with electrical. Patch Paint. Cut in two doors in 2117G&H……..DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18…….. | YES | FS | 0 | 2018 | 2019-02-16
19P000253 |  | 19P000253 | FALSE | CHASS | SL5-ARTS RENOVATION | Complete as of 9/21/18 | ARTS | 157 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 16 | FALSE |  |  | 2018-04-17 | [6 empty] | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access……DL, 7/11/18; This project needs to be complete before Fall 2018. Space is vacant and ready go. Need to walk and confirm Schdule with Paul D. Tony's Flooring is ready to go after paint is complete.... Target complete date is 9/21/18......DL, 8/22/18; Walked with PAul, Paul will scheudle the work. Jess still need to cordinate with Tony's Flooring .....DL, 9/19/18; The paint and flooring is complete. The seams need to be welded and this will be complete. this will be complete by 9/21/18......9/19/21; This Project is 100% Complete....... |  | Dan Lerman | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access | YES | FS | 0 | 2018 | 2019-02-16
18P000300 |  | 18P000300 | FALSE | CHASS | SL5-ARTS PATCH AND PAINT - DANCE HALLWAYS | Complete as of 8/24/18 | ARTS |  | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 24 | FALSE |  |  | 2018-02-02 | [6 empty] | centered. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000314 |  | 18P000314 | FALSE | CHASS | SL5-CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR | Complete as of 7/25/18. | CA MUS PHOTO | 1000 | COMPLETE | Milagros Pena | Cindy Williams | EMILY PAPAVERO |  | Dan Lerman |  |  | 17 | FALSE |  |  | 2018-02-16 | [6 empty] | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date.......DL, 7/25/18; This project is 100% Complete..... |  | Enrico Baez | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date....... | YES | FS | 0 | 2018 | 2019-02-16
18P000318 |  | 18P000318 | FALSE | CHASS | SL5-CHASS INT S FLAT SCREEN INSTALLATION | Plans are being reviewed; work to be scheduled once plans are approved. | CHASS INT S |  | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Dan Lerman |  |  | 20 | FALSE |  |  | 2018-02-21 | [6 empty] | 2/1/19, DL; Francesca contacted me and informed me this project is now back on the books. She needs to gather more information and order the monitor. When the monitor arrives, we will schedule the installation…….1/29/19, DL; Francesca confirmed this project is not needed and requested this project to be cencelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; we have the brackets. Will scheule the work after the project is approved…..DL, 7/11/18; Work order are not produced. Need to assign and schedule the work…. Target complete date is 8/3/18……DL; 7/25/18; Need to change target date.. |  | Enrico Baez | 5/24/18 Conducted site visit. Met with Ryan Amriano. Electrical near buy. No data connection needed. Awaiting for dept. approval. They first wanted to know if this was possible. | YES | FS | 0 | 2018 | 2019-02-16
18P000344 |  | 18P000344 | FALSE | CHASS | SL5-CHASS INTS PAINT MULTIPLE ROOMS - FACULTY | Complete as of 9/10/18 | CHASS INT S | 2117E | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 1 | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 7/11/18; This was transferd in to my quque in the past week. I need to scope this project. I belive this is part of project # 18P000205 and 18P000295. If this is part of the other project. We will try to have the paint completed by 8/17/18…......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/10/18; Work has started. We passed rough electrical and framing inspection. The work should be complete in about three weeks......DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18.......DL, 9/6/18; This Project is 100% Complete....... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000353 |  | 18P000353 | FALSE | CHASS | SL5-PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT | Complete as of 8/23/18 | PSYCHOLOGY1 | 1111A | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 26 | FALSE |  |  | 2018-03-20 | [6 empty] | DL; 7/4/18;This project is scoped. We will only paint one out of the two offices. Working on PO# to install frosted glass with Sun Down Window coverings……DL, 7/25/18; PO# is produced and material is ordered. Target date mid August…….DL, 8/22/18; This project is complete.... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000469 |  | 18P000469 | FALSE | CHASS | SL5-WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS | Complete as of 7/25/18 | WATKINS | 1317 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000396 |  | 18P000396 | FALSE | CHASS | SL5-WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | Complete as of 8/24/18 | WATKINS | 2122 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | 6 | TRUE |  |  | 2018-04-13 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000389 |  | 18P000389 | FALSE | CHASS | SL5-PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A | Complete as of 11/8/18 | PSYCHOLOGY1 | 2122 | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 5 | TRUE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000201 |  | 18P000201 | FALSE | CHASS | SL5-ARTS REMOVE COUNTERTOP/SHELVES | Complete as of 8/23/18 | ARTS | 0106A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 3 | TRUE |  |  | 2017-11-21 | [6 empty] | DL, 6/16/18; Ned to walk, scope and submit plans ASAP…..Sent Paul an email requesting information on Status of Faculty hire status……DL, 7/11/18; Paul is on Jury Duty and he said he should return back to work next week. Current Targe complete date is mid September......DL, 7/25/18; Carpentery and Electrical is complete. Patch and paint has started. Target complete date is 8/3/18......DL, 8/8/18; Space is VAcant and ready for paint. The paint department is working on several other projects that require their attention. The paint department will complete the work in the near future......DL, 8/22/18; This Project is 100% Complete....... |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS……DL, 4/29/18; Pasted from wo;remove the existing countertop and shelves that are built into the room. Follow with patch and paint of entire space. | YES | FS | 0 | 2017 | 2019-02-16
18P000420 |  | 18P000420 | FALSE | CHASS | SL5-COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | Canceled by Customer on prioritization 7/2/18 | WATKINS | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  |  |  |  | Cancel | TRUE |  |  | 2018-04-27 | [10 empty] | YES | FS | 0 | 2018 | 2019-02-16
18P000111 |  | 18P000111 | FALSE | CHASS | SL5-KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 | Complete as of 7/13/18 | CHASS INT S |  | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Jason Williams |  |  |  | FALSE |  |  | 2017-09-15 | [6 empty] | EB 1/31/18 Work was assigned to lock shop 12/7/17…. DND 5/11: Spoke with Jason, all work complete to be completed as trade is available. Only work remaining is on 3150 A; Jason short staffed to finish project but it's on his radar. 07/13/18 H-FMS: Troubleshoot programming and settings for this controller. Clear all data from panel and reset, perform required downloads, re-test and verify both doors working correctly. |  | Enrico Baez | EB 1/31/18 Work was assigned to lock shop 12/7/17 | YES | FS | 0 | 2017 | 2019-02-16
18P000387 |  | 18P000387 | FALSE | CHASS | SL5-HMSS PATCH/PAINT | Complete as of 8/24/18 | HUM & SOC SC | 3600 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 28 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000313 |  | 19P000313 | FALSE | CHASS | SL5-HUMANITIIES SOCSCI - PATCH HOLES & PAINT - |  | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000205 |  | 18P000205 | FALSE | CHASS | SL5-CHASS INT S CREATE DOOR | Complete as of 9/21/18 | CHASS INT S | 2117H | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-11-27 | [6 empty] | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18……DL, 5/24/18; Plans were approved. WE need to schedule the work…..DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18...........DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... .. DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date..........DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18............DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware.....DL, 9/19/18; This Project is 100% Complete...... |  | Enrico Baez | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18…… | YES | FS | 0 | 2017 | 2019-02-16
18P000398 |  | 18P000398 | FALSE | CHASS | SL5-WATKINS ESTIMATE FOR SEALING OF ADJOINING DOORS | Complete as of 10/22/18. | WATKINS | 2204 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-04-16 | [6 empty] | DL, 7/11/18; Need to walk project and verify scope and target complete date…..DL, 7/25/18; Verified scope. We need to order a new door and floor covering and need to schedule the abatnent, we will plan to start this project in 3- 4 weeks. Target complete date is late August.....DL, 8/8/18; Jess conducted the visit with the abatment contractor. Still need to verify abatment date. Carpenter shop is aware of the scope and they are ordering material. Note, one of the doors will have a lead time of 4- 6 weeks. .....DL, 8/22/18; Abatment is taking place this week. We will schedule the paint and carpet over the next week. This projcet all items for this project will be complete by 9/21/18. DL, 9/19/18; the Door was stained today and will be installed asap. The cove base is back ordered and will be installed when it is on site..target date is complete early next week...... DL, 10/4/18; This Project is 100% Complete....... |  | Enrico Baez | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. | YES | FS | 0 | 2018 | 2019-02-16
18W001170 |  | 18W001170 | FALSE | CHASS | SL5-ARTS: PAINT CLASSROOMS | Complete as of 9/24/18 | ARTS | 407 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 27 | FALSE |  |  | 2017-07-25 | [8 empty] | Enrico Baez | DD 10/6: Enrico scoped; requested during break - coordinating with client to complete on a Saturday | YES | FS | 0 | 2017 | 2019-02-16
18P000416 |  | 18P000416 | FALSE | CHASS | SL5-HMSS UWP INSTRUCTOR OFFICE PAINTING | Complete as of 8/24/18 | HUM & SOC SC | 3002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000415 |  | 18P000415 | FALSE | CHASS | SL5-PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | Door and frame have been painted; construction to commence upon availability of the teams. | OLMSTED | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | RYAN LIPINSKI |  | Dan Lerman |  |  | 10 | TRUE |  |  | 2018-05-08 | [6 empty] | 12/14/18, DL; Angel cancelled this project as it is no longer needed at this time……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 7/11/18; This project was scoped and part of the IRT. Plans and permits are approved. We will schedule the work and we will plan to have this project complet by 9/21/18…..8/10/18; WE have approved plans, this project is scheduled to start late August and will be complete early October……DL, 10/4/18; The door and frame is scheduled for delivery in 3-5 weeks, We will start the project when the doors and frame are on site……..DL, 11/7/18; Door and frame and painted. We will start the contruction in the near future…… |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-02-16
18P000418 |  | 18P000418 | FALSE | CHASS | SL5-HMSS OFFICE PAINTING | Complete as of 7/14/18 | HUM & SOC SC | 2002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 15 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty | 5/23/18 EB- Sent email to Jill requesting site visit. 5/23/ 18 EB- Scoped. Mount & TV on site. TV bottom edge to be mouted 48" from floor centered on West wall. Needs electrcal cut out and data. Entered in FAMIS. | N/A | FS | 0 | 2018 | 2019-02-16
19P000220 |  | 19P000220 | FALSE | CHASS | SL5-ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT | Screen to be reinstalled on Friday 11/9/18. | ARTS | 333 | COMPLETE | Milagros Pena | Cindy Williams | SONJA SEKELY-ROWLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 12/14/18, DL; This project is 100% Complete….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/8/18; Screeen is scheduled to be removed this Friday. We will schedule the installation and the patch / Paint repairs once we receive the repaired screen back from the vendor…….DL, 11/7/18; This project should already be complete. However, The vnedor did not deliver the correct screen. The correct screen is currently scheduled for this Friday..... |  | Enrico Baez | 8/27/18 EB-Remove 12' wide screen from finished ceiling. Need electricians to diconnect power, carpenters to remove drywall and lower screen. Repared screen to be re-hung by carpenters and drywall repaired. Electricians to reconnect power. Painters to patch and paint. | YES | FS | 0 | 2018 | 2019-02-16
19P000361 |  | 19P000361 | FALSE | CHASS | SL5-OLMSTED-PATCH & PAINT/REPLACE CARPET |  | OLMSTED |  | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000378 |  | 19P000378 | FALSE | CHASS | SL5-PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 |  | HUM & SOC SC | 1613 | QUEUE TO START | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-11-13 | [11 empty] | FS | 0 | 2018 | 2019-02-16
18P000481 |  | 18P000481 | FALSE | CHASS | SL5-CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 | Complete as of 10/22/18. | CHASS INT S | 3104 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19W002930 |  | 19W002930 | FALSE | CHASS | HOLD - SL5-PATCH HOLES & PAINT - HUMANITIIES SOCSCI | Complete as of 11/8/18 | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-08-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000306 |  | 19P000306 | FALSE | CHASS | SL5-HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 |  | CHASS INT N | 4017 | QUEUE TO START | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-01 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000195 |  | 19P000195 | FALSE | CHASS | SL5-HUM & SOC SC-ROOM PAINTING | Complete as of 11/8/18 | HUM & SOC SC | 2003 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000216 |  | 19P000216 | FALSE | CHASS | SL5-HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT | Complete as of 11/8/18 | HUM & SOC SC | 1214 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-08-27 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000221 |  | 19P000221 | FALSE | CHASS | SL5-PATCH, PAINTING, AND REGULAR CLEANING OF A126A | Complete as of 11/8/18 | OLMSTED | A0126A | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000196 |  | 19P000196 | FALSE | CHASS | SL5-PAINT OFFICE AT UNIVERSITY THEATER | Complete as of 11/8/18 | THTR WKSH |  | COMPLETE | Milagros Pena | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000171 |  | 19P000171 | FALSE | CHASS | SL5-HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST | FS to coordinate with client to schedule work for completion. | HUM & SOC SC | 1614 | QUEUE TO START | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 16 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18W016621 |  | 18W016621 | FALSE | CHASS | SL5-HUMANITIES - PAINT OFFICE - PAINT SHOP | Complete as of 11/8/18 | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2018-06-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000201 |  | 19P000201 | FALSE | CHASS | SL5-PATCH AND PAINT THE WALLS | Complete as of 11/8/18 | CHASS INT S | 3111A | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 18 |  | FALSE |  |  | 2018-08-22 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000385 |  | 18P000385 | FALSE | CHASS | SL5-HMSS INSTALL TV IN CONFERENCE ROOM | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 1001E | IN PROGRESS | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Dan Lerman |  | 19 | 19 | FALSE |  |  | 2018-03-06 | [6 empty] | 12/14/18; Monitor is Complete, we still need to install power. The space is vacant…DL, 6/16/18; Pasted notes from FAMIS; University Writing program wants to install a 65 inch TV in the conference room at HMNSS 1001E. 1. Request to install the TV mount/ bracket on the wall; 2. Request to remove the old projector screen but leave two wood blocks on the wall; 3. Request to add a new double power outlet around the TV bracket area. If you have any questions, please contact Shanshan Liao at (shanshan.liao@ucr.edu or X27753)……DL, 7/25/18; Work orders are not produced. Need to assign and schedule the work…..……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | 6/11/18 Install TV above wainscot. Notes in FAMMIS. Need electrical and date cut ins. | YES | FS | 0 | 2018 | 2019-02-16
19P000362 |  | 19P000362 | FALSE | CHASS | SL5-PATCH & PAINT/REPLACE CARPET (HALLWAY) |  | OLMSTED |  | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18W008762 |  | 18W008762 | FALSE | CHASS | SL5-HUMANITIES: PATCH & PAINT | Complete as of 11/8/18 | HUM & SOC SC | 2415 | COMPLETE | Milagros Pena | Cindy Williams | ANDREW ALONSO |  | Paul Ditty |  | 20 | 22 | FALSE |  |  | 2018-01-02 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000126 |  | 18P000126 | FALSE | CHASS | SL5-HMSS ESTIMATE REMOVE WALL & CHANGE DOORS | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 3611 | QUEUE TO START | Milagros Pena | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 2017-09-28 | [6 empty] | 12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS. Remove double doors and install single door.Remove small West wall. Relocate t-stat. Ceiling work. Replace carpeting. | YES | FS | 0 | 2017 | 2019-02-16
18P000343 |  | 18P000343 | FALSE | CHASS | SL5-UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER | Scope of work has been reviewed; determining how to complete project with trades. | THTR WKSH | 0400A | QUEUE TO START | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 2018-03-16 | [6 empty] | 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez | 5/11/18 EB-Conducted site visit on 3/21/18. Work based on Safety report written in October. Work consists of replacing door latches to orchestra pit. Adding loading dock rail, Paint frame guard, signage, gate/fall restraints, ladder modifications. | YES | FS | 0 | 2018 | 2019-02-16
19P000173 |  | 19P000173 | FALSE | CHASS | SL5-PAINT/PATCH UNIVERSITY THEATER LOBBY | Complete as of 11/8/18 | THTR WKSH | 0400A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000063 |  | 19P000063 | FALSE | CHASS | SL5-NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS | Complete as of 9/26/18 | PSYCHOLOGY1 | 2124 | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-07-31 | [8 empty] | Paul Ditty | 9/13/18 EB this is a request for patch, paint and new carpet | NO | FS | 0 | 2018 | 2019-02-16
19P000356 |  | 19P000356 | FALSE | CHASS | SL5-PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT |  | HUM & SOC SC | 4401 | QUEUE TO START | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-24 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000011 |  | 19P000011 | FALSE | CHASS | SL5-PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED | Complete as of 10/10/18 | PSYCHOLOGY1 | 2111A | COMPLETE | Milagros Pena | Cindy Williams | LORENA QUINTANA |  | Paul Ditty |  | 4 |  | TRUE |  |  | 2018-07-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000371 |  | 19P000371 | FALSE | CHASS | SL5-URGENT PATCH AND PAINT IN CHAIR'S OFFICE |  | HUM & SOC SC | 1213 | QUEUE TO START | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-11-05 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000419 |  | 18P000419 | FALSE | CHASS | SL5-COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | FS to coordinate with client to scope the work. | WATKINS | 1320C&E | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 5 | 8 | TRUE |  |  | 2018-04-27 | [6 empty] | 2/14/19,DL; This project was canceled by Paul R. 2/1/19, DL; We will custom make Sound panels and will start the installation in the next 6-8 Weeks……….. |  | Enrico Baez | 7/6/18 EB emailed Paul Richardson to schedule site visit 7/17/18 EB Scheduling site visit with Paul R. 8/7/18 EB-Job was part of an IRT. Dan said he will scope 8/20/18 EB emailed Lilia to schedule site visit. 8/24/18 EB scheduled site visit for 8/28/18 at 11:00AM 8/28/18 E.Baez- Met with Paul Richardson, Lilia Vega and Becky Campbell. Instead of tearing down walls and building new ones, they wanted to see if installing sound soak on three walls were possible, it is. They will then need to have their Dean approve the sound soak. Clients were sent an email with drawing indicating desired location of sound soak. | NO | FS | 0 | 2018 | 2019-02-16
19P000357 |  | 19P000357 | FALSE | CHASS | SL5-PATCH AND PAINT WALLS, TIME SENSITIVE |  | HUM & SOC SC | 1302 | QUEUE TO START | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-10-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000314 |  | 19P000314 | FALSE | CHASS | SL5-HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000444 |  | 18P000444 | FALSE | CHASS | SL5-PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 | Complete as of 9/21/18 | ARTS | 242 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-05-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000207 |  | 19P000207 | FALSE | CHASS | SL5-QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-08-23 | [8 empty] | Enrico Baez | 9/13/18 EB emailed Toya Adams to schedule site visit. 9/19/18 EB-Site visit scheduled for 9/20/18. 9/20/18 EB-Conducted site visit. Request to remove window in hall and install door. Interior space wall not to be removed. Secure doors, blank off and cover with sound soak. Replace carpet with Vinyl Plank, patch and paint. | YES | FS | 0 | 2018 | 2019-02-16
19P000300 |  | 19P000300 | FALSE | CHASS | SL5-HUM & SOC SC--URGENT: PAINT AND PATCH WALLS |  | HUM & SOC SC | 4403 | QUEUE TO START | Milagros Pena | Cindy Williams | ANDREA HERAZ |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000194 |  | 19P000194 | FALSE | CHASS | SL5-PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 | Complete as of 11/8/18 | HUM & SOC SC | 3304 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000286 |  | 19P000286 | FALSE | CHASS | SL5-FACULTY OFFICES: TOUCH UP PAINT |  | HUM & SOC SC | 2005 | QUEUE TO START | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-09-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000061 |  | 19P000061 | FALSE | CHASS | SL5-PSYCHOLOGY 1111H-PATCH HOLES IN WALL | FS to coordinate with client to schedule work for completion. | PSYCHOLOGY1 | 1111H | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000429 |  | 19P000429 | FALSE | CHASS | SL5--CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING |  | COLL BLDG SO | 103 | QUEUE TO START | Milagros Pena | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-01-03 | [11 empty] | FS | 0 | 2019 | 2019-02-16
19P000226 |  | 19P000226 | FALSE | CHASS | SL5-PAINT OFFICE HMNSS 3304 | Duplicate request; project to be completed on 19P000194 | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-08-28 | [8 empty] | Paul Ditty | Duplicate request; project to be completed on 19P000194 |  | FS | 0 | 2018 | 2019-02-16
19P000226 |  | 19P000226 | FALSE | CHASS | SL5-PAINT OFFICE HMNSS 3304 | Duplicate to 19P00014; work to be completed on original project. | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Duplicate |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
3441 | 3441 |  | FALSE | CHASS | INTS 1121 Convert Classroom to Dance Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use |  |  | In Programming | Milagros Pena | Cindy Williams | Anna Finn |  | Daneca Stevens | 1 |  |  | FALSE | 0 |  | 2018-06-22 | Design | 2019-11-01 | 2019-12-26 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | Funding | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [10 empty] | PD&C | 0 | 2017 | 2019-02-16
3060 | 3060 |  | FALSE | CHASS | CHASS Intl N. - Paint 3rd Floor | Paint and patch the following CHASS INTN rooms to existing color: 3036 3038 3042 3046 3050 3049 3047 3033 3033B 3025 3021 3019 3015 3013 3011 3002 3008 3012 3014 3016 3018 3020 3022 Hallway outside of 3033 Hallway to main entrance to floor Hallway outside 3005 | CHASS INT N |  | Project on Hold | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2016-05-20 | On Hold | [10 empty] | PD&C | 0 | 2016 | 2019-02-16
3363 | 3363 |  | FALSE | CHASS | DM(17-19) CA Photo Museum HVAC | Replace current HVAC with new Temp/Humidity control system. The system must adhere to Museum standards of Temp 70 +-3 and humidity 50 +-5. THIS IS A CRITICAL REQUEST. We are currently not able to borrow work from other museums due to the inconsistent numbers we are experiencing with temperature and humidity. | CA MUS PHOTO |  | In Close-out | Milagros Pena | Cindy Williams | Emily Papavero |  | Scott Donnell | 4 |  |  | FALSE | 1350000 |  | 2017-08-23 | Complete Close-out | 2018-03-01 | 2018-12-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3451 | 3451 |  | FALSE | CHASS | Arts 166 Perf Lab Inspection | Approval of seating plans for Arts 166, Performance Lab. Dave Bomba has the plans. Must be inspected and approved by Director of Inspection & Quality Assurance and the Campus Fire Marshall. |  |  | In Close-out | Milagros Pena | Cindy Williams | Paul Richardson |  | Dave Bomba | 5 |  |  | FALSE | 0 |  | 2018-07-26 | Complete Close-out | 2018-12-10 | 2019-01-31 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3469 | 3469 |  | FALSE | CHASS | Carillon Repair & Maintenance | Design, fabrication and replacement of bell beams for bells 24, 26, 28, 30 and 32. Design, fabrication and installation of bracing to brace the 5 other bells beams that are cracking, and corrective maintenance on the clappers & head pieces-this would include complete removal, cleaning, reaming, bushing and lubricating before re-installing and clean and lubricate the transmission system as much as possible without complete disassembly to make the instrument easier to play. | BELLTOWER |  | Funding | Milagros Pena | Cindy Williams | Reasey Heang |  | Daneca Stevens | 7 |  |  | FALSE | 0 |  | 2018-08-16 | Funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3482 | 3482 |  | FALSE | CHASS | Humanities 3rd Floor Install Sail Shades | Shade sail installation of the patios on the third floor of Humanities Social Science. There are two patios, one on the 3600 wing and one on the 3400 wing. |  |  | In Funding | Milagros Pena | Cindy Williams | Paul Richardson |  | Daneca Stevens | 9 |  |  | FALSE | 0 |  | 2018-10-10 | Funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
19P000058 |  | 19P000058 | FALSE | CNAS | SL5-Assess Feasiblity of Removing/Replacing Growth Chambers | Complete as of 8/24/18 | GH HH | 18 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-28 | [6 empty] | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing...DL, 5/9/18; Project is scoped. Need to schedule the work.....Plumbers and HVAC are working on this. Still need to have electrical removed. I am working wiht Patty on who can do the demo and removal.....DL, 7/11/18; I need to check in with Ken to see if refrigerant is recovered. will isue work order to disconnect electrical..... I checked in with our campus surplus and do not have any contacts to dis,matel the very large growth Chambers. I need to inform Patty and suggest that she have Burges demo and move the Growth Chambers......We will be complete with our portion of this project before 8/1/18.......DL, 8/10/18; All work is done except the disconnect for electrical. I need to check and see if the electrical. Per FAMIS complete on 8/22/18 |  |  | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing | YES | FS | 0 | 2018 | 2019-02-16
19P000346 |  | 19P000346 | FALSE | CNAS | SL5-I&Q--PAINTING ROOMS IN THE I&Q |  | EAST I&Q FAC |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | IMAD BAYOUN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000227 |  | 18P000227 | FALSE | CNAS | SL5-BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL | Complete as of 11/8/18 | BATCHELOR | 4128 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-12-12 | [6 empty] | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM.......DL, 5/24/18; Need to work on plans and permits. Project needs to be complete before Fall academic 2018.....DL, 6/16/18; Walked project with Jess. and he will schedule the abatment. We will not need plans for this project. We are not removing the exhasut hood which was the original purpose foor the plans......Carpenters started the demo. Still need to remove TSI. Once TSI is removed, we can schedule the plumbing work. Target Complete Date is 9/21/18....DL, 8/10/18; Abatement is scheduled for this weekend, we will start work soon.....DL, 8/22/18; Abatement and most demo complete. Still on track for 9/21/18.....DL, 9/19/18; Scope change. This project should be complete on 9/28/18.......DL, 10/4/18; Floor to be installed this Friday. Pianters will finalized the stain on the cabinets. Thsi project should be complete near 10/19/18.......Dl, 11/7/18; This project is 100% complete.... |  | Dan Lerman | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM....... | YES | FS | 0 | 2017 | 2019-02-16
18P000247 |  | 18P000247 | FALSE | CNAS | SL5-PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 | Complete as of 7/14/18 | PHYSICS | 3023 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  |  | 15 | FALSE |  |  | 2017-12-20 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2017 | 2019-02-16
18P000293 |  | 18P000293 | FALSE | CNAS | SL5-SKYE HALL COPIER ROOM PATCH AND PAINT | Complete as of 8/24/18 | SKYE HALL | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 32 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-16
18P000292 |  | 18P000292 | FALSE | CNAS | SL5-SKYE HALL PAINT MULTIPLE FACULTY OFFICES | Complete as of 8/24/18 | SKYE HALL | 228 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul D. will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-16
18P000288 |  | 18P000288 | FALSE | CNAS | SL5-SKYE HALL OFFICE SUITE PAINTING | Complete as of 8/24/18 | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-16
19P000185 |  | 19P000185 | FALSE | CNAS | SL5-NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE | Scope of work has been identified and walked with Requestor, F.S. Trades and P.M. Trade work in progress. | PIERCE | 206 (originially identified as Room 204) | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 6 | TRUE |  |  | 2018-06-18 | [6 empty] | 12/14/18, DL; This project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Pending glove box relocation to rm 319 and minor vent reconfiguration. Both tasks will be performed afet the glove boxes relocate to rm. 319. 10/29/18 All project related work is completed. |  | Ron Veloz | 07/05/18 RonV. Input: I observed multiple WO's for this project and spoke with Zee for clarification. I will investogate the site on 07/06 to determine the actual SOW. 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/22/18 O-RVL: Revised WO to Project no. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". =10/03/18: RV, Work in progress. Plumber are working on new gas lines. Will coordinate glove box move after work in rm 319 is completed. 10/29/18 RV: All glove boxes, Solvent mixing equipment and Chemical cabinet are removed. Remaining work is to replace the existing PVC vent with stainless duct when materials arrive per Cory. Update from Matt L-Plumbing department is working on the gas lines and will continue work this week. | YES | FS | 0 | 2018 | 2019-02-16
18W000455 |  | 18W000455 | FALSE | CNAS | SL5-CHAPMAN CLEAN WINDOWS | Complete as of 7/11/18 | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  | 37 | FALSE |  |  | 2017-07-11 | [6 empty] | Dl, 7/4/18; All Windows in Chapman were cleaned by Ductch Touch. This Project is 100% Complete |  | Ron Veloz |  | YES | FS | 0 | 2017 | 2019-02-16
19P000186 |  | 19P000186 | FALSE | CNAS | SL5-NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION | Complete as of 11/8/18 | PIERCE | 319 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-06-18 | [6 empty] | Pending gas line installation scheduled for the week of 09/24 per Steve Burleson. Move glove boxes from 206 to Rm 319 after gas line are installed. All work is complete |  | Ron Veloz | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". 10/03/18 RV: Work in progress, Plumbers are installing gas lines. Glove boxes from 206 can be moved after gas lines are installed. 10/08/148 RV: Plumbers to complete the installation of new gas lines in 319. Glove boxes to be brought to rm 319 after gas lines are installed. 10/17/18 RV: Update, Gas lines are installe approx 90% complete per Plumbing Tech, misc parts on order. 10/29/18 RV: All project related work is completeand confirmed with trades and PI. | YES | FS | 0 | 2018 | 2019-02-16
18P000256 |  | 18P000256 | FALSE | CNAS | SL5-BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES | Complete as of 9/21/18 | BOYCE | 3451 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave at Webber is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place.......DL, 5/9/18; Autoclave is destroyed. Pictures were sent to Cheryl. We are now waiting for the equipment to arrive. Steve B is working on Steam connection at Boyce......DL, 5/24/18; Autoclaves arrived. Day crew is scheduled to deliver the unit on 5/30/18. we will schule the plumbers and electricians shortly there after......DL, 6/16/18; Webber Autoclave is almost complete. This portion should be complete next week. WE will run the Webbber autoclave for two weeks before we start the Boyce Autoclave. The weldolet for the BOyce unit will be installed during the steam shutdown...... DL, 7/11/18; Webber Auto clave will be complete on 7/12/18. We will start the demo of the Boyce Auto clave next soon. Target date for this project is 8/10/18...... DL, 7/25/18; We had a delay with the Webber autoclave which will implact the Boyce Auto clave. New target complete date is 8/22/18.....DL, Plumbing is almost complete, need to schedule final elctrical and Commission equipment. Target date 8/31/18...... DL, 9/6/18; This project should be complete but we still need to schedule the electrical connections ASAP.........DL, 9/19/18; This project is 100% Complete. |  | Dan Lerman | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place | YES | FS | 0 | 2017 | 2019-02-16
18P000029 |  | 18P000029 | FALSE | CNAS | SL5-CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS | Complete as of 7/11/18 | CHAPMAN | 1 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain......DL, 5/24/18; This work is scheduled to be complete on or before 7/1/18.....DL, 6/16/18; Blinds are delayed to mid July but window clenaning is still on schedule......DL, 7/11/18; This Project is 100% Complete |  | Dan Lerman | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain...... | YES | FS | 0 | 2017 | 2019-02-16
19P000213 |  | 19P000213 | FALSE | CNAS | SL5-NEEDS FOR NEW WALL DISPLAY (MONITOR) | Duplicate request to 19P000031; Work to be completed on other project. | BIOLOGICAL SCI | 3101 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [11 empty] | FS | 0 | 2018 | 2019-02-16
19P000287 |  | 19P000287 | FALSE | CNAS | SL5-URGENT: PAINT SHOP TO PATCH AND PAINT | Complete as of 10/22/18. | MAT SCI ENGR | 229 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | HONG XU |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-19 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-02-16
18W011672 |  | 18W011672 | FALSE | CNAS | SL5-ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY | Complete as of 7/25/18 | ENTOMOLOGY | 268 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-03-08 | [6 empty] | Relocate white board from East wall onto the West wall, where high table was removed, 24" away from North end of wall. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000028 |  | 18P000028 | FALSE | CNAS | SL5-CHAPMAN PATCH AND PAINT | Complete as of 7/12/18 | CHAPMAN | 0010A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced .......DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced ...... | YES | FS | 0 | 2017 | 2019-02-16
18P000434 |  | 18P000434 | FALSE | CNAS | SL5-BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY | Complete as of 8/24/18 | BOYCE | 4478 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Paul Ditty |  |  | 3 | TRUE |  |  | 2018-05-09 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000287 |  | 18P000287 | FALSE | CNAS | SL5-SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING | Complete as of 9/21/18 | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 33 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19/18; This project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-16
18P000341 |  | 18P000341 | FALSE | CNAS | SL5-PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL | AQMD notification was sent; abatement to begin at the end of notification period. | PHYSICS | 1132 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-14 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process…DL, 6/16/18; Jess tested the matreial flooring and paint is hot. Jess will abate before we proceed with the project….Still need to scheudle the work. This project target complete date is late Fall……DL, 7/25/18; Jess sent out the 14-day notification to the AQMD last week. We will start the balance of the project after the ACM and Lead is abated or encapsulated…..8/10/18; Abatement is complete. We will work on the other items as time permits. This space is vacant with no occupancy date |  | Dan Lerman | DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process… | YES | FS | 0 | 2018 | 2019-02-16
18P000030 |  | 18P000030 | FALSE | CNAS | SL5-CHAPMAN PREP AND PAINT FROM WATER DAMAGE | Complete as of 11/8/18 | CHAPMAN | 100 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced....... | YES | FS | 0 | 2017 | 2019-02-16
18W011161 |  | 18W011161 | FALSE | CNAS | SL5-REPLACE CARPET | Complete as of 7/11/18 | SCIENCE LAB1 | 301 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-23 | [6 empty] | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project……DL, 5/21/18; Floor covering is selected. Work will be scheudled for Mid June….DL, 5/24/18; The install is scheduled for June 18th & 19th……DL, 7/11/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project…… | YES | FS | 0 | 2018 | 2019-02-16
18P000392 |  | 18P000392 | FALSE | CNAS | SL5-BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 | Complete as of 8/24/18 | BATCHELOR | 0 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  |  | 8 | TRUE |  |  | 2018-04-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000296 |  | 18P000296 | FALSE | CNAS | SL5-SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES | Contract is being processed; target project completion is end of September. | SKYE HALL | 266 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 31 | FALSE |  |  | 2018-02-02 | [6 empty] | 01/17/19, DL; This project was completed last summer……..DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19 18; I neeed to check on this work order. I thought it was part of the 2nd floor Hallway project but it was not…… |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-16
18P000117 |  | 18P000117 | FALSE | CNAS | SL5-PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION | Complete as of 9/10/18 | WEBBER | 1303 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-21 | [6 empty] | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work....DL, 5/9/18; Produced work order for JEss to test for lead paint and ACM....Von wall is hot, everything else is good to go. I will schedule the work soon. The space is vacant......DL, 7/11/18; This project is in progress. Target Complete Date is 8/10/18....DL, 7/25/18; Vinyl plank and bullitin boards the balance of the task for this project. Still on target for complete on 8/10/18.....DL; 8/10/18; We were schedule to install the fllor and identified Asbestos,. Jess is working on the propsal and schedule for the abatment. This will require a 14- dat notification to the AQMD. This space is vacant with no scheduled move in date......DL, 8/22/18; Abatment is scheduled for this Tursday and Friday. We will scheule the carpet in dry errase boards for next week.Target complete date will be 8/31/18.....DL, 9/6/18; This project is 100% Complete...... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work.... | YES | FS | 0 | 2017 | 2019-02-16
18P000310 |  | 18P000310 | FALSE | CNAS | SL5-ADD INTERCOM/BUZZ IN SYSTEM | Complete as of 10/22/18. | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-12 | [6 empty] | Dl, 7/4/18; This project is scoped. This will be a new ADA operator, door bell / Intercom and buzzer button to unlock door. Walked work with Contractor, need to work on producing contract with PD&C. Once Contract is confirmed, we will schedule the work..... DL, 7/11/18; We have the proposal. Need to execute the agreement and schedule the work. The target complete date is before 10/1/18.....Dl 8/10/18; Jason will try and complete the work with in the next three weeks......DL, 8/22/18; Jason order parts, parts have 6-8 week lead time. Work will be scheduled when material arrives.....DL, 10/4/18; This Project is 100% Complete....... |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | FS | 0 | 2018 | 2019-02-16
18P000118 |  | 18P000118 | FALSE | CNAS | SL5-OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT | Complete as of 7/25/18. | OLMSTED | 1337 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2017-09-20 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space.......DL, 6/16/18. New staff member schedule to start mid july. BKM is also scheduled for mid july. This project will require cabinets to be removed, new carpet, paint and blank out electrical outlets that will no longer be used.. new signage too.....DL, 7/11/18;This project is in progress. Complete date is 7/20/18......DL, 7/25/18; This project is 100% Complete....... |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space. | YES | FS | 0 | 2017 | 2019-02-16
18W011692 |  | 18W011692 | FALSE | CNAS | SL5-ENTOMOLOGY; PAINT/PATCH LAB | Complete as of 8/24/18 | ENTOM MUSEUM | 211 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-03-08 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000027 |  | 18P000027 | FALSE | CNAS | SL5-CHAPMAN PREP AND PAINT LAB | Complete as of 7/12/18 | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-05 | [6 empty] | 2/1/19, DL; This project is 100% Complete……………DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again…… DL, 4/2/18; This space is still on schedule for 7/1/18 completion date…..FAMIS work orders have been produced…..DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th….. |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again...... DL, 4/2/18; This space is still on schedule for 7/1/18 completion date.....FAMIS work orders have been produced..... | YES | FS | 0 | 2018 | 2019-02-16
19W007474 |  | 19W007474 | FALSE | CNAS | SL5-BG - RAILROAD TIE WALLS |  | BOTANIC GARDENS |  | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV | [5 empty] | FALSE |  |  | 2018-11-07 | [7 empty] | 2018-12-10 | Ron Veloz | 02/15/19 O-RVL: Udated SOW, RV will schedule a site visit with the Carpentry Supervisor to detemine the construction feasability and estimated costs. END --- 01/09/19 O-RVL: REQUEST FOR ESTIMATE, Not a Project. RV To schedule a site visit with C. Pillen and Chad Chambers to evaluate if repairs are possible. 12/10/18 O-RVL: REQUEST FOR ESTIMATE. Ron V walked with D. McWilliams & Jodie and identified the railroad tie retaining wall area requiring repairs. Jodie would like an estimate to repair the leaning railroad ties at specified areas. RV to meet with Chris P. and or Chad Chambers to determine if FS can perform work and or provide an estimated cost to perform work. 11/07/18 O-RVL: Received an email form Deborah Mc. to discuss the wall at Thursday during our 1-1 meeting. | YES | FS | 0 | 2018 | 2019-02-16
19P000189 |  | 19P000189 | FALSE | CNAS | SL5-PHYSICS- WALL HOLES PATCH | Duplicate work order to 19P000049. Work to be completed on other project. | PHYSICS | 3036 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-16 | [10 empty] | NO | FS | 0 | 2018 | 2019-02-16
19P000319 |  | 19P000319 | FALSE | CNAS | SL5-ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB |  | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000356 |  | 18P000356 | FALSE | CNAS | SL5-ENTOMOLOGY PATCH AND PATCH | Complete as of 8/24/18 | ENTOMOLOGY | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 10 | TRUE |  |  | 2018-03-20 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000298 |  | 19P000298 | FALSE | CNAS | SL5-SPIETH - PREP LAB FOR FACULTY SEARCH |  | SPIETH | 1363 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  |  |  | 0 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 2/14/19, DL; Need to schedule trades and obtain quotes to refinish countertops…… |  | Ron Veloz | 01/15/19 O-RVL: RV to scope once priority is established. RV updated notes with information provided from Deborah Mc Williams. Spieth 1363 – Wet Lab Space Note by DMcWilliams.: "There is evidence in the ceiling and along one wall of a water intrusion issue, i.e. peeling paint, leaking and rusted pipes, etc. The cause of this damage needs to be investigated and repairs confirmed, including painting the wall and ceiling where damage is visible". Patch/paint Re-finish, re-surface – existing cabinets Re-finish and/or replace bench-tops If both sinks cannot be significantly cleaned, they should be replaced, Replace faucets at both sink locations. Clean existing Chemical fume hood Repair or replace self-closing chemical / flammables storage cabinet On one bench remove overhead shelving unit and relocate electrical outlets to the ends of bench to accommodate large desktop equipment. Cap off remaining utilities for potential use/re-connection in the future. Remove shelves on west wall to accommodate siting of large floor-standing equipment before patch and painting. Also, add 120/240 electrical outlets (raceway) along this wall. Replace flooring -- this depends on what we decide about removing the walk-in fume hood listed below Add GFCI outlets near water sources Requires a connection to a DI water system Other utilities are required in this room and at what locations, e.g. air, oxygen, gas, vacuum, etc.? Remove existing walk-in Fume Hood (if cost for this issue does not trigger project over $50k) – Please assess/cost out and advise prior to project. Spieth 1364 – Lab Support Space work: Patch/paint –Re-finish, re-surface – existing cabinets (non-porous surface), Re-finish and/or replace benchtops, If sink cannot be significantly cleaned, they should be replaced Replace faucets at sink location. Add GFCI outlets near water sources Requires a connection to a DI water system" | NO | FS | 0 | 2018 | 2019-02-16
19P000358 |  | 19P000358 | FALSE | CNAS | SL5-GEOLOGY - ACCOMMODATION REQUEST |  | GEOLOGY |  | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  |  |  | 0 |  | FALSE |  |  | 2018-10-26 | [6 empty] | 2/14/19, DL; Plans are in process and we will apply for building permit next week………….. | 2019-02-07 | Ron Veloz | 02/07/19 O-RVL: RV changed title from "Geology" to "Physics". SOW is completed and on the server. Emailed a copy of SOW to FS team on 2/7. Received email from Ron Rector requesting Dan L. to provide Ronda Inzuna status update. END--- 01/31/19 O-RVL: Intake in progress. 01/15/19 O-RVL: Updated notes, the following SOW was from the requestor. --- 12/14/18 O-RVL: RV walked the site with Deborah Mc Williams on Mon 12/10. RV to create SOW. Returned request back to O-UA1 and will work from O-UA1 until the project is prioritized. "Potential scope of work for accommodation request: 1. Pour 10x10 cement pad for reserved electric transportation vehicle. 2. Electric charge station 3. appropriate signage" --- Deborah McWilliams is the main contact 951-218-3720 --- 11/14/18 RV: RV & Monty Received an "FYI" email from from Deborah Mc Williams on 11/09/18 with information related to the approval of the charging station --- location currently undergoing review by the CBO. | YES | FS | 0 | 2018 | 2019-02-16
19P000390 |  | 19P000390 | FALSE | CNAS | SL5-BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  |  |  | 0 |  | TRUE |  |  | 2018-11-29 | [7 empty] | 2019-02-07 | Ron Veloz | 02/12/19 O-RVL: Scoping is complete. Revised door layout and emailed April photos of the proposed storefront door system received from D.L. on 2/11. April Meinzer approved storefornt door system on 2/12. RV reveised floor plan utilizing the existing cased opening as discussed with D.L. on 02/11. RV provided D.L. a copy of the revised Intake Formw/ layout. Form w/ layout. Unable to update project notes on FAMIS -Project is not available. END--- 02/07/19 O-RVL: Monty asked RV to follow up on this request. Ron V scheduled meeting with April Meinzer on 2/7 at 1:30pm to review intake information for the proposed project at room 5494. FAMIS Updated END--- | YES | FS | 0 | 2018 | 2019-02-16
19P000390 |  | 19P000390 | FALSE | CNAS | SL5-BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  |  |  | 0 |  | TRUE |  |  | 2018-11-29 | [8 empty] | Ron Veloz | 02/07/19 O-RVL: Monty asked RV to follow up on this request. Ron V scheduled meeting with April Meinzer on 2/7 at 1:30pm to review intake information for the proposed project at room 5494. |  | FS | 0 | 2018 | 2019-02-16
19P000299 |  | 19P000299 | FALSE | CNAS | SL5-SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 |  | SPIETH | 3378 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000473 |  | 18P000473 | FALSE | CNAS | SL5-PIERCE NEW CARPET & PAINT FACULTY OFFICE | Complete as of 9/26/18 | PIERCE | 202 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 1 | 5 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000347 |  | 19P000347 | FALSE | CNAS | SL5-SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT |  | SPIETH | 3320 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000244 |  | 19P000244 | FALSE | CNAS | SL5-PATCH & PAINT GEOLOGY | Complete as of 10/22/18. | GEOLOGY | 2258A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2018-09-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000223 |  | 18P000223 | FALSE | CNAS | SL5-Provide requisite utility infrastructure to support 4 add'l chambers (on order). | Plans were approved by Building Official and Fire Marshal; anticipated completion January 2019. | FAWCETT LAB |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 11 | 21 | FALSE |  |  | 2017-12-11 | [6 empty] | 2/1/19, DL; This Project is 100% Complete……..01/15/19, DL; Plans are approved, Chambers are on site. Electrical is complete. Plumbing work is in progress. Our portion of the project should be complete by 2/1/19…………..12/14/18, DL; All Pre work is complete. The Chambers are scheduled to arrive on site within the next 30-days. We will finish this project when material on site……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans……..DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet….DL, 4/29/18; Still need to conduct site visit with the team….DL, 5/24/18; Per Patty, equipment is ordered but 5- months out…..DL, 9/6/18; We will submit plans to Bob W. tomorrow for review and approval……..DL, 9/19/18; Plans are approved. The equipment will be here in about 4- months. WE will start the work for this project in the Fall to ensure we are ready when the equipment arrives……DL, 9/19/18; Plans are currently being review by BO & FM……DL, 11/7/18; Plans are approved. WE are requesting to change the placement confirguration of the growth chamber and awaitng Bob's review and approval. WE are on track to have this work complete befoire the end of the new year….. |  | Dan Lerman | DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans........DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet....DL, 4/29/18; Still need to conduct site visit with the team… | YES | FS | 0 | 2017 | 2019-02-16
19P000367 |  | 19P000367 | FALSE | CNAS | SL5-SCILAB 1 0211- PATCH & PAINT |  | SCIENCE LAB1 | 211 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-31 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000269 |  | 18P000269 | FALSE | CNAS | SL5-BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED | FS to coordinate with client to scope the work. Customer contacted to schedule a site visit. | BATCHELOR | 1123 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 12 | 18 | FALSE |  |  | 2018-01-16 | [8 empty] | Enrico Baez | 5/23/18 EB - Sent email to April requesting site visit. 6/11/18 EB conducted site visit request if for additional outlet only. Single trade only asked Deborah to change to SL6. | YES | FS | 0 | 2018 | 2019-02-16
19P000137 |  | 19P000137 | FALSE | CNAS | SL-5 -LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM |  | LIFE SCIENCE | 2545 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-08 | [11 empty] | FS | 0 | 2018 | 2019-02-16
18P000354 |  | 18P000354 | FALSE | CNAS | SL5-GH16-25 COOLING SYSTEM REPAIR | Work considered deferred maintenance not a minor renovation. | GH 16 25 |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | MARK TANKERSLEY |  | Dan Lerman |  | 13 | 17 | FALSE |  |  | 2018-03-20 | [6 empty] | DL, 7/25/18; Reviewed Ron V. noted. I will check in with Chris on this to better determin the method complete this project. |  | Dan Lerman | DL, 5/5/18; This is a repair, No alterations taking place. Pasted from FAMIS work order...THE COOLING SYSTEM ON GH 16-25 IS FALLING APART SHEET METAL TRAYS HAVE TONS OF HOLES, WOOD ROTTING ETC. PLEASE REPAIR….. RV, 07/06/18: Dan, Chis Pillen and I have walked this project months ago and have a quote from Ralph Cox/KIRA Construction to repair the head house damages. See Chris for the status of subletting this work. | YES | FS | 0 | 2018 | 2019-02-16
19P000045 |  | 19P000045 | FALSE | CNAS | SL5-PREPARE LOCATION AND UTILITIES FOR INSTALL | Complete as of 11/8/18 | BOYCE | 2407 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 14 |  | FALSE |  |  | 2018-07-23 | [8 empty] | Ron Veloz | Scope is complete. Walked site with Steve Burelson. DI water is available behined wall in 2407 at interstictal space. Vendor will install Milpore unit, FS to provide DI water and back board.Power is available at the sink counter. Electrical has verified GFI. | YES | FS | 0 | 2018 | 2019-02-16
19P000106 |  | 19P000106 | FALSE | CNAS | SL5-PHYICS 1134 - UTILITIES REQUEST | FS to coordinate with client to scope the work. | PHYSICS | 1134 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 15 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 2/1/19, DL; Review scope with Customer. Still need to review with Brian from the Electic shop…………….12/14/18, DL; No update…. | 2018-11-07 | Ron Veloz | 01/31/19 O-RVL: Walked site with Dan L on 01/31 to review SOW. END--- 01/23/19 O-RVL: Received email from Ward B.in response to Brian Hambleton's request to use 208v. response is" ... 208 volt power 3-phase is fine for the compressor. Also having emergency power is not needed". END--- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela. END --- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela.-END 01/23/19 RV received Dr. Beyermann's comments and made corrections to the SOW, rev2. END--- 01/22/19 O-RVL: RV updates, Received a request from Mayela to meet on site with team. Sent team a copy of the Statement of Work for their review. Scope of Work: Install: Chilled new water supply & return drop, Electrical Power for the Compressor to be 3- phase 40Amp 220/230VAC hardwired from the equipment the disconnect for the Compressor. Power for the QD Pump and Controller to be single phase 200-230VAC, 20amp circuit. Patch and paint as needed, test for lead paint and TSI Asbestos abatement, equipment anchoring. Note: Job walk conducted on 11/07/18, 9:45-10:00am. Met in 1134 to determine Equipment and Utility Service location. In addition, on 11/03/18 the customer requested a single phase 200-230VAC, 20amp circuit (received info via email). END --- 01/11/19 O-RVL: Received an email from Mayella requesting status. END --- 11/08/18 O-RVL: Received email from Dr Beyerman today for added electrical. "I just realized that I also need a single phase 200-230VAC, 20 amp circuit in 1134 for the pump and controller, which is that unit next to the dewar. This can be down by the floor, in the vicinity of the 3 phase box. I will be meeting with the electrician today around 11am, and I will mention it to him". RV asked Dr Beyermann to contact me with the location for the pump receptacle. Will update floor plan upon receipt. 11/07/18 RV Walked site with Mayela and Dr Beyerman. Request to provide Chilled water loop, and two locations for Electrical power. Identified locations to install new utilities. END --- 11/07/18 O-RVL: Walked site on 11/07 with Dr Beyermann & Mayela, identified scope. Update FAMIS to J-DLN, MinRenlist and move to que to start. END --- 11/06/18 O-RVL: Jobwalk scheduled on 11/07 at 10:00am in Rm 1134 with Mayela, Ward Beyermann, Darren M HVAC, Brian H-Elect. Hold | YES | FS | 0 | 2018 | 2019-02-16
19P000170 |  | 19P000170 | FALSE | CNAS | SL5-INSTALL NEW IRRADIATOR INSTRUMENT | Anticipated delivery of equipment is scheduled for three weeks. | MAT SCI ENGR | 51 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 16 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 2/14/19, DL; This project is 100% Complete………2/1/19, DL; Power is complete. Chilled water will be complete next week…………..1/15/19, DL; Electric is commplete, Water will be complete with in two weeks. Equipment should be on site soon…12/14/18, DL; This project is currently on hold per RED…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; The unit is schedukled for delivery in the next three weeks. | 2018-09-19 | Ron Veloz | 01/30/19 O-RVL: Spoke with Dan, equipment arrived staging into building. END---…..9/10: D. Dinh Project is shared between CNAS & BCOE, captured only on the CNAS College Count. 09/19/18 RV, Scope is complete. RV to Upload into FAMIS. Install chilled water and dedicated power for the irradiator instrument at the west wall in rm 051. 10/17/18 RV: SOW provide Chilled water loop and one(1ea) dedicated 208v 1ph 40a circuit to the Irradiator. Floor plan and specs are on the server folder. | YES | FS | 0 | 2018 | 2019-02-16
18P000453 |  | 18P000453 | FALSE | CNAS | SL5-DELFINO LAB-SOIL HOUSE MODIFICATION | FS to coordinate with client to scope the work. | DELFINO HHSE |  | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | [6 empty] | 2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | FS | 0 | 2018 | 2019-02-16
19P000292 |  | 19P000292 | FALSE | CNAS | SL5-GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER | Site vist completed; identifying a feasabile site location for work. | GEOLOGY |  | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 18 |  | FALSE |  |  | 2018-08-10 | [6 empty] | 2/14/19, DL; The Concrete and Power is Complete. We still need to install the chain link which will be installed in about 3-4 weeks………..2/1/19, DL Electrical is complete. WE will pour Concrete next week. We will schedule the fence install 28- days after concrete is poured………; Th1/15/19, DL; Plans are approved, we will start the work in the next two weeks……12/14/18, DL; Plans are almost complete. We will schedule the work after plans are approved……DL, 11/7/18; Conducted site visit with Chris P. We need to confirm a feasable site location before we move forward with the work…. |  | Ron Veloz | 10/30/18 RV: Chris Pillen and D. McWilliams aggreed to leave the building in place and place a concrete pad with a chain link fence adjacent to the existing structure. 10/17/18 RV: SOW, demolish walls and roof. Verify and cap existing underground utilities. Remove overhead electrical from power pole to the building. The concrete pad to remain and install a 6'H fence with gate around the pad. Bring Power below grade to pad location. Met with C.Pillen and Dan to discuss alternate options. Photos and equipment info is on the server file. | YES | FS | 0 | 2018 | 2019-02-16
19P000043 |  | 19P000043 | FALSE | CNAS | SL5-SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | Customer called and canceled the work on 10/23/18. | SCIENCE LAB1 | 309 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 19 |  | FALSE |  |  | 2018-07-20 | [7 empty] | 2018-10-22 | Ron Veloz | Customer called and canceled the work on 10/23/18. 10/20/18: O-RVL: Site visit on 10/20 with Amber 10:30am. 10/22/18 O-RVL: Walked site with Vendor/Controlled key sys. The PI requested pricing to change the locking function from room to room as "Storage use " and rekey the entry door with the same function. Matt will send pricing on the week of 10/22. 10/23/18 O-RVL: This request will not require access controls, but will require the entry door and side door lock-sets function to be changed to a storage function and rekeyed per Dave(PI). Received info from PI that there was a theft in his dept. Request is urgent. RV requested key count from Dave 8/23/18 and is pending a response from the department. 10/23/18 >> Canceling at the request of the customer - Loretta | YES | FS | 0 | 2018 | 2019-02-16
19P000341 |  | 19P000341 | FALSE | CNAS | SL5-PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL |  | PIERCE |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000214 |  | 19P000214 | FALSE | CNAS | SL5-PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT | Complete as of 10/10/18 | PHYSICS | 3005 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-08-24 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000340 |  | 19P000340 | FALSE | CNAS | SL5-PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE |  | SKYE HALL | 349 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | VICTORIA AVALOS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000283 |  | 19P000283 | FALSE | CNAS | SL5-HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  |  |  | 20 |  | FALSE |  |  | 2018-09-05 | [7 empty] | 2018-09-19 | Ron Veloz | 10/17/18 RV: All construction information is on the server folder. Pending Saftey MOP's from Beiwei. Left message with her on Monday 10/15 for status. 10/03/18 RV: SOW, Install safety guard railing and apply yellow markings (leading edge 6'from perimeter) on the Winston Chung Roof. 09/19/18-Scope is complete, received safety requirements prepared by EH&S/Beiwei. RV to upload onto FAMIS. | YES | FS | 0 | 2018 | 2019-02-16
18P000388 |  | 18P000388 | FALSE | CNAS | SL5-SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 2018-04-10 | [6 empty] | DL, 7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved…..DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans....DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter....DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but htere is no hard date as this is vacant space and we will access the space as time permits...... |  | Enrico Baez | 6/21/18 EB Remove old glass washer and install washer 400XLS. Disconnect steam, air, water, electrical, vent hood. Install new washer, electrical, step up x-former 208v to 480. Dept. to purchase x-former $5000 ill to dept. Elect. To provide specs. | YES | FS | 0 | 2018 | 2019-02-16
18P000480 |  | 18P000480 | FALSE | CNAS | SL5-BG - LOWER RESTROOMS-PAINTING-FLOORS | Canceled by Facilities Services; Work is not within the SLA and is not needed. | BOTGDN RSTRM |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000486 |  | 18P000486 | FALSE | CNAS | SL5-PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 2018-06-28 | [6 empty] | 12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman | Dan L. scoped this project as part of an IRT…. 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. If possible paint to match existing green accent wall, if not white is fine. Mount monitor bracket to wall centered side to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | YES | FS | 0 | 2018 | 2019-02-16
19P000210 |  | 19P000210 | FALSE | CNAS | SL5-CHEMICAL SCI Install Door In Doorway | FS to coordinate with client to scope the work. | CHEMICAL SCI | 0225A | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  |  |  | 25 |  | FALSE |  |  | 2018-08-24 | [7 empty] | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scope of work is complete. RV to upload docs to FAMIS. 10/03/18 RV: Install non rated door into an existing cased opening-for privacy & noise reduction. Will require carpentry-framing, patch, paint, and minor flooring/base repair. | YES | FS | 0 | 2018 | 2019-02-16
18P000099 |  | 18P000099 | FALSE | CNAS | SL5-EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 | Plans will be developed and will be submitted for review and approval. | GEOLOGY |  | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 26 | 23 | FALSE |  |  | 2017-09-08 | [6 empty] | 12/6/18, DL; This project is a priority #26 and may be completed in the next 12 - months…..DL 1/3: Chris to verify with customer on electrical requirements for completion……DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress…..DL, 7/11/18; Still need to work on plans…. Target date is 9/30/18….. |  | Dan Lerman | DL 1/3: Chris to verify with customer on electrical requirements for completion…...DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress..... | YES | FS | 0 | 2017 | 2019-02-16
17W012504 |  | 17W012504 | FALSE | CNAS | PAINT Business OFFICE AND CONF. ROOM | Complete as of 10/22/18. | ENTOMOLOGY | 170 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 27 | 26 | FALSE |  |  | 2017-05-04 | [6 empty] | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. |  | Dan Lerman | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. | YES | FS | 0 | 2017 | 2019-02-16
18P000257 |  | 18P000257 | FALSE | CNAS | SL5-SKYE HALL MOUNT 55 | Scope of work is being reviewed; determining how to complete project with trades. | SKYE HALL | 209 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 28 | 28 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete…….1/15/19, DL, Site visit is scheduled with James M. this Thursday. We will schedule the work shortly after the site visit…….12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | FS | 0 | 2017 | 2019-02-16
18P000258 |  | 18P000258 | FALSE | CNAS | SL5-SKYE HALL HALLWAY MOUNT | Scope reviewed by BZM; coordination by PM for work to be completed. | SKYE HALL | 212 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 29 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete……1/15/19, DL, Site visit is scheduled with James M. this Thursday…………12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | FS | 0 | 2017 | 2019-02-16
18P000284 |  | 18P000284 | FALSE | CNAS | SL5-SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT | Complete as of 9/21/18 | SKYE HALL | 277 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  | 29 | 23 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-02-16
19P000301 |  | 19P000301 | FALSE | CNAS | SL5-SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH |  | SCIENCE LAB1 | 214 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-09-27 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000006 |  | 19P000006 | FALSE | CNAS | SL5-MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 | FS to coordinate with client to scope the work. | MAT SCI ENGR | 310 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 2/14/19, DL; This project is 90% Complete. ………2/1/19, DL; This Project started to day. We are scheduled to be complete by the end of February………..1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. | 2018-09-28 | Ron Veloz | 10/30/18 RV: Spoke with Deborah McWilliams, today. Project to remain as prioritized(#3) for new Faculty. 10/17/18 RV: Floor plan is on the server folder. RV: 10/03/18: Install metal stud wall at center of the room. Remove one door blank and install one lockset.Requires, Framing, drywall, tape, sand, paint, t-bar modifications and rubber base. PM to verify with user if power and Data will be required in the new wall. 09/28/18 O-RVL: Completed SOW: Add Wall in the center of room. Include a new Metal Stud Wall with rubber base to match existing. Remove metal cover at ceiling. Remove door lock blank and install new lockset at left door. RV completed SOW & placed on FS server. Updated FAMIS and Minor Reno List. 09/27/18 O-RVL: Site walk with Chris P, Dan L. Mayela and Deborah McW. FS to re-install the metal stud wall to original place dividing the room equally. Scoping completed. 09/26/18 O-RVL: 19P000006-Scheduled a site walk scheduled with Dan. Will contact Deborah and Mayela for their participation. | YES | FS | 0 | 2018 | 2019-02-16
18P000347 |  | 18P000347 | FALSE | CNAS | SL5-GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) | Scope reviewed by BZM; coordination by PM for work to be completed. | GEOLOGY | 0 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 31 | Deferred to Fall Quarter - summer priority 27 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/14/19, DL: The monitor is on site. We need to schedule the installation. 2/1/19, DL; Conducted site visit with Amber. Amber will order the monitor. We will schedule the installation when the monitor is on site………….DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/1 EB Site visit. TV to be mounted on wall above water fountain across from Geo 2306. Center of mount 84" high and centered between wall corner and bulletin board. Will need electrical and data. Computer connection cutout will be in mail room. See W.O. | YES | FS | 0 | 2018 | 2019-02-16
19P000055 |  | 19P000055 | FALSE | CNAS | SL5-CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM | Scope reviewed by BZM; coordination by PM for work to be completed. | COLL BLDG SO | 207 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Dan Lerman |  | 32 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2018-05-18 | [6 empty] | 12/14/18, Dl; This project is prioritized at 32 and will not be scheduled in the near futurer…….DL, 7/11/18; Correction, I did not scope this yet, I thought we were talking agout the door bell and ADA operator. I will check in with Ronda and verify the scope…... DND 7/30/18: Created project to replace WO #18015182; project #19P000055 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. | 2018-11-29 | Ron Veloz | 11/29/18: RV Visited site and identifed the toilet room on the 2nd floor. SOW is to install a new exhaust fan at the second floor toilet room. Roof access is available from the access panel in the closet located in the room 210 next door. There is roof is transite per Jess. Abatement is necessary for roof penetrations and possibly has lead paint on ceilings and walls. | YES | FS | 0 | 2018 | 2019-02-16
18W013160 |  | 18W013160 | FALSE | CNAS | BEES- PATCH & PAINT 2460D & 2460F | Complete as of 10/22/18. | GEOLOGY | 2460 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 33 | 29 | FALSE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000191 |  | 19P000191 | FALSE | CNAS | SL5-PATCH AND PAINT HINDERAKER BASEMENT | Complete as of 11/8/18 | HINDERAKER |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 34 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000464 |  | 18P000464 | FALSE | CNAS | SL5-PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED | FS to coordinate with client to schedule work for completion. | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 35 |  | FALSE |  |  | 2018-08-16 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000436 |  | 18P000436 | FALSE | CNAS | SL5-COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS | FS to coordinate with client to schedule work for completion. | COLL BLDG SO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 36 | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000174 |  | 19P000174 | FALSE | CNAS | SL5-BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT | Scope reviewed by BZM; coordination by PM for work to be completed. | BATCHELOR | 2112 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AMY RICKS |  | Dan Lerman |  | 37 |  | FALSE |  |  | 2018-07-24 | [6 empty] | 12/14/18, DL; This project is priortized at 37 and will not be scheudled until further notice…… | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scoping narrative is available and located on the BZM Fall Folder. Patch & Paint, replace supply grilles, reverse door swing, remove door closers, install metal plate over door opening. | YES | FS | 0 | 2018 | 2019-02-16
19P000042 |  | 19P000042 | FALSE | CNAS | SL5-COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL | FS to coordinate with client to schedule work for completion. | COLL BLDG SO | 200 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Paul Ditty |  | 38 |  | FALSE |  |  | 2018-07-20 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000049 |  | 19P000049 | FALSE | CNAS | SL5-PHYSICS PATCH & PAINT | FS to coordinate with client to schedule work for completion. | PHYSICS | 3036 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | 39 |  | FALSE |  |  | 2018-07-25 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18W011691 |  | 18W011691 | FALSE | CNAS | SL5-ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | FS to coordinate with client to schedule work for completion. | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 4 | 11 | TRUE |  |  | 2018-03-08 | [6 empty] | 12/17/18 DND: Canceled by client on 12/17/18. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000318 |  | 19P000318 | FALSE | CNAS | SL5-GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE |  | GEOLOGY | 420 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-04 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000031 |  | 19P000031 | FALSE | CNAS | SL5-BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) | FS to coordinate with client to scope the work. | BIOLOGICAL SCI | 3101 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 40 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This is prioritized at #40 and will not be scheduled in the near future….. |  | Enrico Baez | 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. Install 2 duplex outlets | YES | FS | 0 | 2018 | 2019-02-16
19P000193 |  | 19P000193 | FALSE | CNAS | SL5-GENOMICS 2221 - FOB ACCESS SYSTEM INSTALLATION | FS to coordinate with client to scope the work. | GENOMICS | 2221 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | [7 empty] | 2018-10-08 | Ron Veloz | 02/15/19 O-RVL: RV-preparing estimate to cdeliver to the customer on the week of 02/17/19. END--- 01/31/19 O-RVL: Pending proposal revisions with equipment itemized with make and model no. from the Access control vendor. Revised proposal due soon per vendor. END--- 01/15/19 O-RVL: Forwarded access controls quote and SOW to Jason and Chris Rodriguez to review and qualify the HCI quote. Pending response. --- 01/10/19 O-RVL: RV received quote and will send a formal Estimate to Aimee by EBD Fri. 01/18 and ask if they would like to procede. 12/14/18 O-RVL: REQUEST FOR ESTIMATE ONLY. Send Estimated costs to Aimee Gonzales for review and approval. Pending access controls and auto door operator quotes. Moved to Queue to start. 11/08/18 O-RVL: Scope is complete. Assisting the lock shop with pricing to provide the requestor an estime prior to start of construction. Walked a 2nd vendor , pending quote for access control card reader. 11/05 RV called vendor for quote, no reply. 10/29/18 RV: Conducted jobwalk with vendor last week. Pending quote from Vendor. Will follow up. | YES | FS | 0 | 2018 | 2019-02-16
19P000102 |  | 19P000102 | FALSE | CNAS | SL5-PATCH & PAINT FRONT CORNER OF OFFICE | FS to coordinate with client to schedule work for completion. | LIFE SCIENCE | 2930 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 42 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000133 |  | 19P000133 | FALSE | CNAS | SL5-PATCH HOLES AND PAINT | FS to coordinate with client to schedule work for completion. | BATCHELOR | 2203 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 43 |  | FALSE |  |  | 2018-08-07 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000197 |  | 19P000197 | FALSE | CNAS | SL5-PATCH AND PAINT OFFICE, LOBBY AND HALL | FS to coordinate with client to schedule work for completion. | COLLEGE BLDG NO | 0203B | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 44 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000184 |  | 19P000184 | FALSE | CNAS | SL5-REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES | FS to coordinate with client to scope the work. | GEOLOGY | 1270 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 45 |  | FALSE |  |  | 2018-08-14 | [6 empty] | 2/14/19, Dl; We will schedule the work soon. The space is vacant and ready…………….2/1/19, DL; This project has started. We would like to have the work complete by mid March…………..12/14/18, DL; This project is prioritized at 45 and will not be shceudled until further notice…… |  | Enrico Baez | 11/08/18 RV: Enrico is assisting RV and has scheduled a job walk with Laurie Graham. Will follow up, pending confirmation. 11/19/18 EB-Met with Laurie Graham at site. SCOPE CARPENTERS-Remove all wall, base and center island cabinet work. Verify no ACM flooring under center island. PLUMBERS-Remove sinks in 1270 and 1270A. Terminate, at wall plumbing. Remove air/gas lines on wall in 1270 and 1270A. Remove lower chilled water, supply and return, lines on East wall. Remove air and gas line, flush with floor, from center island. FLOORING-Remove VCT in 1270 and 1270A, replace with customer selected VCT. Replace all cove base. ELECTRICIANS-Remove gray flexible conduit at raceway, terminate circuit. PAINTERS- Patch and paint walls in both spaces. | YES | FS | 0 | 2018 | 2019-02-16
19P000246 |  | 19P000246 | FALSE | CNAS | SL5-PHYSICS - PATCH AND PAINT | Complete as of 10/10/18 | PHYSICS | 3007N | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 46 |  | FALSE |  |  | 2018-09-07 | [6 empty] | n/a |  | Paul Ditty | Duplicate request; project to be completed on 19P000234 | N/A | FS | 0 | 2018 | 2019-02-16
19P000242 |  | 19P000242 | FALSE | CNAS | SL5-PAINT OFFICE | FS to coordinate with client to schedule work for completion. | COLLEGE BLDG NO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 47 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
19P000231 |  | 19P000231 | FALSE | CNAS | SL5-OLMH 1428 PATCH AND PAINT | FS to coordinate with client to schedule work for completion. | OLMSTED | 1428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ANDREW CABRERO |  | Paul Ditty |  | 48 |  | FALSE |  |  | 2018-08-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
19P000243 |  | 19P000243 | FALSE | CNAS | SL5-GENOMICS 1206 - PATCH AND PAINT WALLS | FS to coordinate with client to schedule work for completion. | GENOMICS | 1206 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Paul Ditty |  | 49 |  | FALSE |  |  | 2018-09-06 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
19P000285 |  | 19P000285 | FALSE | CNAS | SL5-PAINT AND PATCH PI OFFICE |  | ENTOMOLOGY | 269 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-09-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000062 |  | 19P000062 | FALSE | CNAS | SL5-MSE 169-MINOR RENOVATION - NEW FACULTY | Electrical outlet is the highest priority. Must be installed by Sept 15, per Mayela Castillo | MAT SCI ENGR | 169 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 5 | 19 | TRUE |  |  | 2018-07-30 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………..1/15/19, DL; This project is 99% complete pending one water heater. Water heater is not here yet……12/14/18, DL; This project is 95% complete. The water heater is scheduled for delivery shortly after the new year. We will complete the install when the heater arrives…… 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 9/6/18; We will have the power and cabinets removed by 9/19/18. We are in the process of producing plans for this project. Once the plans are approved, we will proceed with the project. Note, we still need to obtain important information and some specifications regarding the procured base cabinets and counter tops, bio safety cabinet, diswasher, and freezer. ……DL, 7/7/18; The work is 90% complete. We are waiting on parts which have a 4-6 week lead time. We will finsh the balance of the project when the parts arrive….. | 2018-08-22 | Ron Veloz | 10/17/18 RV: Work is in Progress. END--- 08/27/18 RV: Updated notes. Moved to "Que to Start". Lab upgrades, Install utilities for new lab equipment, including DI water, electrical, modify existing cabinet to accommodate new flask washer, install owner furnished lab workstations. END ---...DND 8/12/18 replaced 3 projects for Summer quarter completion. Ron V. has scope on project. END --- 08/22/18 O-RVL: completed S.O.W, sent to Mayela Castillo for sign off. 08/23/18-RV: Ron V. Resubmitted S,O.W. rev.1 and received Final sign off from Mayela. Met with Dan to provide information and hand off the project. | YES | FS | 0 | 2018 | 2019-02-16
19P000176 |  | 19P000176 | FALSE | CNAS | SL5-PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY | FS to coordinate with client to schedule work for completion. | PHYSICS | 1112 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 50 |  | FALSE |  |  | 2018-08-10 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | FS | 0 | 2018 | 2019-02-16
19W003012 |  | 19W003012 | FALSE | CNAS | SL5-FIX RESTROOMS (PAINT AND FLOORS) | FS to coordinate with client to schedule work for completion. | CHAPMAN | 5 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 51 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000126 |  | 19P000126 | FALSE | CNAS | SL5-CHEMICAL SCIENCE - MINOR RENOVATIONS | Paint has been completed; plumbing to complete work upon availability of the team. | CHEMICAL SCI | 455 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Dan Lerman |  | 6 |  | TRUE |  |  | 2018-08-03 | [6 empty] | 12/14/18, DL; This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL,11/7/18; Paint is complete, Plumbing shop is planning to schedule the work in the near future…… |  | Ron Veloz | Work in progress, install nitrogen lines and valves(valves by PI). Patch and paint. 10/30/18 RV: Spoke with Kevin, pending nitrogen line installation | YES | FS | 0 | 2018 | 2019-02-16
19P000230 |  | 19P000230 | FALSE | CNAS | SL5-NEW FACULTY OFFICE FOR PATCHWORK/PAINT | Complete as of 10/10/18 | GEOLOGY | 1242A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-08-30 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
19P000360 |  | 19P000360 | FALSE | CNAS | SL5-GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING |  | GEOLOGY | 1444 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000369 |  | 19P000369 | FALSE | CNAS | SL5-PIERCE - PAINT IS PEELING OFF WALLS |  | PIERCE | 3341 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-11-01 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000251 |  | 19P000251 | FALSE | CNAS | SL5-CHEM SCI 428-PATCH DRY WALL HOLES | Complete as of 10/10/18 | CHEMICAL SCI | 428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-02-16
19P000288 |  | 19P000288 | FALSE | CNAS | SL5-COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS |  | COLLEGE BLDG NO | 202 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-19 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000291 |  | 19P000291 | FALSE | CNAS | SL5-MSE HELIUM RECOVERY SYSTEM | Work has been completed; FS teams verifying completion and quality check of work. | MAT SCI ENGR | 205 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 9 | HOLD | FALSE |  |  | 2017-07-24 | [6 empty] | 12/14/18, DL; This project is 100% Complete……DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB - spoke with Mayela who is determining status within her dept…. DL, 11/7/18; This project is complete but I need to conduct a final site visit….. |  | Ron Veloz | DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB-Spoke with Mayela-she is researching where the project stalled within her department. 7/2/18 DND Please verify if work is still required for completion 8/7/18 EB-sent Mayela email requesting update on 9/20/18 EB-emailed Mayela to determine status of project. 9/24/18 EB-Project not cancelled. Passed on to Ron Veloz. 10/03/18: RV, Walke job with Mayela, Chris P, Dan L & Deb McWilliams. PI to provide Dan layout and equipment specs. | YES | FS | 0 | 2017 | 2019-02-16
18P000221 |  | 18P000221 | FALSE | CNAS | SL5-Provide add'l HVAC capacity to maintain lower temp | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 4414 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 9 | 16 | FALSE |  |  | 2017-12-11 | [6 empty] | 12/14/18, DL; This project is 100% Complete……….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob. DL, 5/9/18; We will work on plans and submit for review.....DL, 6/16/18. Had meeting with Bob W. to verify what is needed on plans. I will work with Gunther on plans for submittal and review......DL, 7/11/18; Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall.....DL, 11/7/18; Material is on site and will will schedule the work with in the next 30- days..... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob | YES | FS | 0 | 2017 | 2019-02-16
18P000312 |  | 18P000312 | FALSE | CNAS | SL5-URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 | Canceled per customer 9/12/18 | CAMP LOC NOT IN BLDG |  | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | Canceled | 38 | FALSE |  |  | 2018-02-13 | [6 empty] | 2/14/19, DL; Th demolition portion of this project is complete. We will install the utilities when the new grow pod container arrives in 6- 8 weeks……….2/1/19, DL; The Demolition portion of this project is scheduled to start 2/5/19………..Dl, 6/16/18; Is this a project we will manage or resourse management? I understand we will disconnect the utilites, but who is responsible for the removal of the trailers? I am assuming this will be recharge work and not covered under the SLA. I will verify before the work begins……DL, 7/11/18; Need to check in with Susan. Need to produce work orders and schedule the work…….. |  | Enrico Baez | EB, 5/29, conducted site visit 5/25. Structure is a double wide modular building/trailer. Space needs to be cleared of equipment, desks, tools. Disconnect electrical, plumbing. Needs professional removal. University Asset see Susan Marshburn for direction. EB, 9/12/18 Per Deborah McWilliams email.Project is cancelled due to lack of funding. | YES | FS | 0 | 2018 | 2019-02-16
19P000234 |  | 19P000234 | FALSE | CNAS | SL5-PHYSICS 3005-WALL HOLES PATCH | Duplicate work request. | PHYSICS | 3005N | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-09-04 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
19P000127 |  | 19P000127 | FALSE | CNAS | SL5-PIERCE PATCH & PAINT | Duplicate request to be combined with 19P000239 | PIERCE | 2301 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | MICHELLE KING |  | N/A |  | Canceled |  | FALSE |  |  | 2018-08-03 | [6 empty] | Paul Ditty |  | Paul Ditty | Paul Ditty |  | FS | 0 | 2018 | 2019-02-16
3228 | 3228 |  | FALSE | CNAS | Retrofit Screenhouse to Greenhouse | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. Location can be discussed with Greg Greer | RUBIDOUX SCR |  | In Design | Kathryn Uhrich | Deborah McWilliams | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 780000 |  | 2016-12-06 | Bidding | 2019-08-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3367 | 3367 |  | FALSE | CNAS | Field 16 Greenhouse Demo & Replacement | Replace GH1 and GH2 with a greenhouse from the Greenhouse Megastore. Conduct geotechnical investigation, prepare drawings and conduct asbestos and lead sampling. |  |  | In Construction | Kathryn Uhrich | Deborah McWilliams | Sue Lee, D. McWilliams |  | Dave Bomba | 2 |  |  | FALSE | 300000 |  | 2017-09-15 | Complete Construction | 2019-01-30 | 2019-07-28 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | Conceptual Design | Kathryn Uhrich | Deborah McWilliams | Tracey Kahn, D. McWilliams |  | Scott Donnell | 3 |  |  | FALSE | 150000 |  | 2018-01-08 | CEQA | 2019-12-01 | 2020-02-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3483 | 3483 |  | FALSE | CNAS | Pierce Fume Hoods Relocation | Relocate fume hoods as marked in attached diagram from Pierce rooms 3306 and 3310 to the locations marked in the attached diagram in Pierce rooms 3419, 3425 and 3443. |  |  | In Close-out | Kathryn Uhrich | Deborah McWilliams | Jinsong Zhang |  | Dave Bomba | 4 |  |  | FALSE | 14000 | 0 | 2018-10-09 | Complete Close-out | 2018-12-01 | 2019-02-15 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3218 | 3218 |  | FALSE | CNAS | Ag Ops - Demo Structures | Demolition of 15 structures, including hazardous materials cleanup, electrical reconnection of services as needed, UST removal as needed, relocation of ATT riser. |  |  | In construction Additional funding is not expected. | Kathryn Uhrich | Deborah McWilliams | Deborah McWilliams |  | Scott Donnell | 99 |  |  | FALSE | 316739 |  | 2016-10-19 | Complete Construction | 2018-07-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
1900a | 1990a |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | Finalized construction drawings are being reviewed by the campus building official and firemarshal | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2193000 |  | 2015-10-09 | Start Construction | 2019-06-01 | 2019-11-16 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
2353 | 2353 |  | FALSE | CNAS | Natural Reserves-Sweeney Granite Mountain | This project will add structurally independent facilities for an administration building and researcher housing to provide meeting/office space and short term sleeping quarters. Additionally, the existing laboratory building and staff residence will be extensively renovated. High priority is focused on high insulation values, high wind resistance, rodent proofing, and pursue as much passive cooling and heating as possible with an eye toward low maintenance and high durability. Both new construction and renovation projects are to be sealed to prevent rodent intrusion. The new structures must withstand the harsh environment of extreme temperatures and very high winds. All site improvements shall be done with minimal disturbance to the desert environment. The overarching goal of the project is to provide a sustainable structure that respects its environment and is low maintenance while using best practice design standards. |  |  | Construction has resumed at the remote granite mountain location in January 2019, with work focused on modifications to the Existing Allison Center Lab, and Staff Residence. Construction is expected to be completed in these buildings in March of 2019 | Kathryn Uhrich | Deborah McWilliams | Jim Andre, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2545500 |  | 2015-11-23 | Complete Construction | 2019-01-14 | 2019-10-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
1990b | 1990b |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon-Road | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | Finalized construction drawings are being reviewed | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE |  |  | 2018-06-22 | Finalize Design | 2019-10-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
19P000428 |  | 19P000428 | FALSE | ENROLLMENT SERVICES | SL5--STUDENT SERVICES AVC OFFICE PREPARATION |  | STUDENT SERV | 3102 | CANCELED BY CLIENT | LaRae Lundgren | TBD | ANGIE GRAY |  |  |  | 0 |  | FALSE |  |  | 2019-01-03 | [8 empty] | Ron Veloz | 02/06/19 O-RVL: Updating notes. "Cancelled by Angie Grey on 1/22/19". 02/11/19 O-RVL: Dan L asked RV to confirm with Angie Grey that the project is cancelled. RV called and left a voice message with Angie(2/11). RV will follow up. END--- | N/A | FS | 0 | 2019 | 2019-02-16
19P000370 |  | 19P000370 | FALSE | ENROLLMENT SERVICES | SL5-PATCH AND PAINT CAMPUS TOURS |  | STUDENT SERV | 1137 | COMPLETE | LaRae Lundgren | TBD | ELIZABETH TATUM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000384 |  | 19P000384 | FALSE | ENROLLMENT SERVICES | SL5-PATCH HOLES IN WALL AND PAINT |  | STUDENT SERV | 2234 | COMPLETE | LaRae Lundgren | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | FS | 0 | 2018 | 2019-02-16
19P000366 |  | 19P000366 | FALSE | FAC-PLNG-DESIGN-CONST | SL5-FACILITES SERVICES ADMIN-BREAKROOM & RECEPTION REMODEL |  | CORP B |  |  | Susan Marshburn | Da Lan Dinh | DALAN DINH | [5 empty] | FALSE |  |  | 2018-10-31 | [11 empty] | FS | 0 | 2018 | 2019-02-16
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM17-19 Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Working with Engineer to understand Campus system. | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 1 |  |  | FALSE | 1250000 | 0 | 2018-10-17 | Complete Final Report | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3275 | 3275 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Fiber Optic Infrastructure Upgrade | Repair, replace and upgrade the fiber optic infrastructure network that includes 50+ buildings across campus. Also includes work to main hubs, sub hubs and make available spare fiber for future utilization. |  |  | Going into bidding | Susan Marshburn | Da Lan Dinh | ----- |  | Daneca Stevens | 2 |  |  | FALSE | 643750 |  | 2017-04-12 | Award Contract | 2019-04-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3437 | 3437 |  | FALSE | FAC-PLNG-DESIGN-CONST | UCPD Generator Replacement | Replace unsupported 125kw generator with new - Critical Facility |  |  |  | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2018-10-08 | Receive 100% CD's | 2019-07-01 | 2019-08-30 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3255 | 3255 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Humanities - Upgrade EMS | Humanities HVAC - upgrade Energy Management System per approved Century Bond funded project (approval attached). Project: 957405 P5498 Budget $200,000 Accounting determined this is capitalizable Accounting determined not capitalizable | HUMANITIES |  | Approval of alternates by FS | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Fernando Nunez | 6 |  |  | FALSE | 202000 |  | 2017-02-10 | Complete Close-out | 2018-10-01 | 2019-01-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3035b | 3035b |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Roofing - Olmstead Hall | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. 112010 project budget is $456,163.00. Estimated construction cost is $425,680.00. Bidding 8/8/2017. |  |  | In Programming | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 383112 |  | 2016-02-25 | Re-bid | 2019-08-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Roofing - Spieth Hall/LSP | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. |  |  | In Programming | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 432510 |  | 2016-02-25 | Re-bid | 2019-08-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3270 | 3270 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Chapman Hall - Replace HVAC System | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | CHAPMAN |  | In Design | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Scott Donnell | 8 |  |  | FALSE | 595819 |  | 2017-03-07 | Bidding | 2019-05-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3271 | 3271 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Life Sci/Spieth Hall Elevator Renewal | Scope of work includes the number 3 and 4 elevators of Spieth Hall. Project budget is $344,898.00. Estimated construction cost is $250,400.00. |  |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 9 |  |  | FALSE | 345000 |  | 2017-03-07 | Final Approval of CD's | 2019-07-01 | 2019-12-31 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3272 | 3272 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Athletic/Dance elevator renewal | Project budget is $219,371.00. Estimated construction cost is $169,020.00. | ATH DANCE |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 220000 |  | 2017-03-07 | Final Approval of CD's | 2019-07-01 | 2019-12-31 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3064 | 3064 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Botanic Gardens Basin Silt Removal | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | BOTAN INFO C |  | In Design | Susan Marshburn | Da Lan Dinh | Toshio Ishida |  | Dave Bomba | 48 |  |  | FALSE | 110000 |  | 2016-04-20 | Obtain Agency Permits | 2019-05-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3066 | 3066 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Chapman Hall Roof Replacement | Roof replacement. | CHAPMAN |  | In Close-out | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 50 |  |  | FALSE | 1010000 |  | 2016-04-06 | Complete Close-out | 2018-04-01 | 2018-08-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
2671 | 2671 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Elevator Modifications - Various Buildings | Provide Vertical Transportation Consulting, Mechanical, Electrical, Fire Alarm and Architectural/Structural Construction document design and specifications for the modernization of two (2) elevators at Webber and Watkins buildings which is included in the base design and one (1) elevator at the Entomology Museum is included as an add alternate. |  |  | Permit review process | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 99 |  |  | FALSE | 596011 |  | 2016-01-05 | Final Approval of CD's | 2019-07-01 | 2019-12-31 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Rivera Library Arches/Arcade Repair | Paint and replace roof. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Jason Espinoza | 99 |  |  | FALSE | 240000 |  | 2016-05-06 | Award Contract | 2019-04-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Bourns Hall Fire Alarm System Replacement | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | Approval of 100% CD's | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 99 |  |  | FALSE | 600000 |  |  | Augmentation Approval | 2019-04-01 | 2019-09-30 | [8 empty] | PD&C | 0 | 1900 | 2019-02-16
19P000411 |  | 19P000411 | FALSE | GRAD.DIV | SL5- PAINT, CARPET AND BLINDS |  | UNIV OFC BLD | 150 | QUEUE TO START | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-14 | [11 empty] | FS | 0 | 2018 | 2019-02-16
19P000399 |  | 19P000399 | FALSE | GRAD.DIV | SL5-NEW CARPET + WALL PAINT |  | UNIV OFC BLD | 100 | QUEUE TO START | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-06 | [11 empty] | FS | 0 | 2018 | 2019-02-16
18P000274 |  | 18P000274 | FALSE | GSOE | SL5-SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 | Project is 95% complete; contract in progress for installation of a new door, door frame and ADA operator. Anticipated completion December 2018. | EADY CENTER |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES/BRANDON BARBOSA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-18 | [6 empty] | 2/14/19, DL; This project is Complete………….2/1/19, DL; This project is 99.9% Complete. We still need to conduct Final inspection with Building inspector……1/15/19, DL; The door and automatic opener is scheduled to be installed on 1/22/19……..12/14/18, DL; This project is 95% complete. The contract for the door and ADA operator was awarded today. We will schedule the work shortly after the new year…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Conducted site visit with Gilbert. We need to have a meeting to determin if this work is part of the SLA…… DL, 6/16/18; We still need direction, SLA or Recharge?.......DL, 7/11/18; This Project will require Plans and Permits. We will start on the Plans next Week. We will also issue work orders for work we will complete with in house staff. The Concrete work and Entry Door will need to be contracted out. Target Complete date is 10/1/18……..DL, 7/25/18; Work orders are produced. Planing to walk the project with Chris, Steve B and Robert C. thisw week or next week. We will submit plans to Bob Williams for the contracted work next week……DL, 8/8/18; Completed site visit with Robert C. Steve B, Steve T. and Chris; the Plumbers are complete. The carpenters and electricians will work on their items over the next three weeks. The Plans will be ready to submit on 8/9/18. Once plans are approved, we will proceed to go out to bid for the Concrete and the ADA operator. Target complete date is 9/21/18…….DL, 8/22/18; Plans were apprroved, Concrete Contract is being executed. Still working on Door and ADA operator……..DL, 9/6/18; NTP for Concrete will be issued on Monday. I will schedule the work. I need to follow up on the door order and the ADA operator…….DL, 9/19/18; Concrete walkway scheduled to start on 9/20/18. The new door and Frame will arrieve in 3-5 weeks. We will schedule the install when the new door and frame are on site…….DL, 10/4/18; Concrete work is complete. Still need handrail, signage, door and ADA operator. Target date is Early November….DL, 11/7/18; Project is 95% complete. Contract is being processed to install the new Door, Door Fram and ADA operator. Goal is to have the work complete befor the winter break…… |  | Enrico Baez | Duplicate of 18W011999 project scoped and note entered to make facility ADA compliant. | YES | FS | 0 | 2018 | 2019-02-16
18P000313 |  | 18P000313 | FALSE | GSOE | SL5-SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 | Complete as of 10/22/18. | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-15 | [6 empty] | 18W011689 Work order was cancelled because it has the same scope and is a duplicate………DL, 6/16/18; Contract is being awarded this week. Weill are scheduled to have this work completed by fiscal closing……DL, 7/25/18; This Project is 100% Complete…..9/13: Zee - Customer noted paint peeling; updated to status to back in progress for work to be addressed.......DL, 9/19/18; The contractor is on site repairing the walls and painting. The work should be complete this week.......dl, 10/4/18; tHIS PROJECT IS 100% Complete..... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000054 |  | 19P000054 | FALSE | GSOE | SL5-PATCH & PAINT OFFICE | Complete as of 10/10/18 | SPROUL | 2131 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-26 | [6 empty] | N/A |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000237 |  | 19P000237 | FALSE | GSOE | SL5-PATCH AND PAINT OFFICE - SPROUL 1206 | FS to coordinate with client to schedule work for completion. | SPROUL | 1206 | IN PROGRESS | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 2/1/19, DL; This project will start on 3.1.19. We will need to abate ACM before we can start. Jess will isuue the 14- day notification to the AQMD. Once we have confirmation, we will schedule the work…….. | 2018-10-05 | Enrico Baez | 0/5/18 E. Baez- conducted site visit. Carpenters: Removes sliding chalk boards in 1206 and 1206 and fill in with wall. Remove patched in panels on left of chalk board in 1206. Patch where " do not enter" signs were removed. Electricians: Disconnect power to two "do not enter" signs above doors. Abatement: Remove approx 300 sq.ft. of ACM VCT Flooring: replace flooring with either VCT of vinyl plank. Painters: Patch and paint, at least one wall accent wall. | YES | FS | 0 | 2018 | 2019-02-16
19P000217 |  | 19P000217 | FALSE | GSOE | SL5-PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 | FS to coordinate with client to scope work. | SPROUL | 1359 | IN PROGRESS | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-27 | [6 empty] | 2/1/19, DL; This proect will start on 3/1/18 and should be complete by 4/1/19…… | 2018-09-18 | Enrico Baez | 9/18/18 E. Baez Conducted site visit. Scope of work Carpentry Remove 20 feet of built-in wood cabinets and counter top. Install TV mount on South wall. Remove and replace white board on North wall. Abatement Abate approximately 200 square feet of 9â€ x 9â€ VCT tile and base cove Flooring Install carpet similar to what is in room 1357 Replace base cove. Walls Patch and paint walls. Electrical Install duplex outlet for TV Replace fluorescent lamps with LED lamps TV Install data point and Internet connection to support video conferencing. Custodial Vacuum dust from ceiling tiles. 9/13/18 EB-emailed Karen Naples to schedule site visit. 9/18/18 EB-Conducted site visit. Request to remove cabinet, abate VCT, install carpet, mount TV. Electrical and date lines needed. Install white board. Replace flourescent tube with LED. | YES | FS | 0 | 2018 | 2019-02-16
19P000229 |  | 19P000229 | FALSE | GSOE | SL5-RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR | FS to coordinate with client to scope work. | SPROUL |  | QUEUE TO START | Thomas Smith | Sally Tavizon | KAREN NAPLES |  |  |  | 4 |  | FALSE |  |  | 2018-08-29 | [8 empty] | Enrico Baez | 9/20/18 EB-conducted site visit 9/18. Request for tile and plumbing removal, patch and paint. To facilitate placement of printer system. E-mail sent to Monty on 9/14 asking for direction on renovating hallway space. Awaiting Susan's response per Monty. Entered scope on shared drive. Will need Fire Marshal approval to determine which of three possible locations will allow placing of WEPA system. 11/13/2018 E. Baez-Met with Ron Rector to discuss system placement. WEPA system is to be placed on second floor near vending machines on North side. See note in shared drive. Will need power and data connections. | YES | FS | 0 | 2018 | 2019-02-16
19W002419 |  | 19W002419 | FALSE | ITS | SL5-ITS CENTER - INSTALL CARD READER ACCESS |  | ITS CENTER | 161 |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-08-09 | [11 empty] | FS | 0 | 2018 | 2019-02-16
19P000279 |  | 19P000279 | FALSE | ITS | SL5-HUB - ADD 2 POWER OUTLETS |  | HUB |  |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-09-13 | [11 empty] | FS | 0 | 2018 | 2019-02-16
18P000471 |  | 18P000471 | FALSE | ITS | SL5-WCH INSTALL SECURITY FENCE | Complete as of 9/19/18 | CHUNG HALL | 134 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  |  | 5 | FALSE |  |  | 2018-06-12 | [6 empty] | DL, 7/4/18; Walked this project with Angel, This request is to install security fence with Sliding gate and welded webs to increase security. Space is vacant and ready to schedule work. Need to walk with Corey to see if this is a project they can do or sub out to De ANza fence......DL 7/25/18; Still need to walk project with Corey. Dl, 8/10/18; Site walk complete, we are waiting on estimates. WE will try and schedule the work with in the next 30- days....DL, 8/22/18; Work is scheduled for August 27th. Still need to order hardware.....DL, 9/6/18; The fence is installed and Angel is very Happy, but I need to check the project to verify we are good to go....DL, 9/19/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-02-16
18P000474 |  | 18P000474 | FALSE | ITS | SL5-MS&E ELECTRICAL MODIFICATIONS FOR ITS | Electrian to complete the work as available. | MAT SCI ENGR | 119 | IN PROGRESS | Danna Gianforte | Shelley Gupta | MICHAEL CAPRIOTTI |  | Robert Corey |  |  | 1 | FALSE |  |  | 2018-06-13 | [6 empty] | 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. |  | Enrico Baez | 7/17/18 EB-Scheduling site visit with Michael Capriotti 8/7/18 EB- Met with Robert Corey to discuss scope of work. He will coordinate work. | YES | FS | 0 | 2018 | 2019-02-16
18W007453 |  | 18W007453 | FALSE | ITS | SL5-(P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2017-11-30 | [11 empty] | FS | 0 | 2017 | 2019-02-16
19P000293 |  | 19P000293 | FALSE | ITS | SL5-PAINT ESTIMATE REQUEST | Canceled by Customer 10/24/18 | TELEPHONE |  | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-21 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-02-16
18P000252 |  | 18P000252 | FALSE | ITS | SL5-CHASS INT S REPLACE ELECTRICAL SCREENS | Pending customer to confirm of equipment to be purchased; work scoped by BZM. | CHASS INT S | 2130 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | JORGE MACIAS |  | Dan Lerman |  | 1 | 2 | FALSE |  |  | 2017-12-21 | [7 empty] | 2018-06-21 | Ron Veloz | 01/23/19 O-RVL: RV received confirmation (Telcon) with Jorge macias to cancell the request. He will resubmit upon recipt of screens at a later date. RV instructed the Front desk(FS) to close out the request & "cc" Monty, Alan, Enrico & Linda & Loretta. END--- 01/23/19 O-RVL: RV emailed Jorge to verify status of the request/materials order. Pending response. END--- 01/09/19 O-RVL: RV spoke with Jorge on 1/09. Jorge expect screens to be ordered within two weeks and will cancel this request if the screens are not ordered by his department. Jorge asked to contact him in two weeks (01/23/19). END---6/21/18 RV HOLD, Walked site w/ Enrico & Jorge. Surveyed site and Enrico updated FAMIS & Project folder. Now pending - confirmation of party to purchase projection screens. S.O.W.: Remove two non functional motorized video screens. Replaced with new larger screen. Patch and repaint all walls and entry door. END--- 07/06/18 Ron V Input notes: Received email from Enrico on 07/03 confirming Facilities Services doe not purchase Audio Visual equipment in General Assigment class rooms. On 07/06 RV contacted Jorge Macias with this info and Jorge said he would get back to RV with follow up reply from his supervisor. Confirmed with E.B. that proj info/ photos are updated on the project folder and FAMMIS. END--- 8/22/18 O-RVL: Will follow up with Jorge to confirm status on the screen purchase and if Media will purchase the screens. END--- 08/23/18-RV emailed Jorge, Pending response. END--- 08/24/18-RV, Enrico followed up with Jorge, projection screens approved but not purchased yet). END--- 10/17/18: RV spoke with Jorge today and he said screens are on order. Jorge will follow up with updates to RV and Enrico. | YES | FS | 0 | 2017 | 2019-02-16
18P000382 |  | 18P000382 | FALSE | ITS | SL5-ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 | Plans will be developed and will be submitted for review and approval. | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | PHYLLIS FRANCO |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL, This project is Complete……12/14/18, DL; This project is scheduled to be complete shortly after the winter break…….This project was scoped previously with the IR Team. We may need plans or a permit because we are installing a Dutch door…..DL, 7/11/18; Need to produce work orders and schedule the work….. DL, 7/25/18; Still need to produce work orders and schedule the work. Target date is 10/1/18 | 2018-07-06 | Ron Veloz | 06/29/18 Ron V: SOW, Remove the existing non rated solid core door & grille and replace with a new maple veneerd Dutch door with prefinished clear coat without grille. Door to be prepped on the hinge side with one continoues hinge. Confirm/field verify is a double bevel on door is requird. Do not prep the strike/lockset side.. Cylinder to be bored onsite by Lock shop. The top of the lower door to have a small shelf + - 6-8 inches wide, confirm size with Duffy prior to ordering the door. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | FS | 0 | 2018 | 2019-02-16
18P000381 |  | 18P000381 | FALSE | ITS | SL5-ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 | FS to coordinate with customer to schedule the work for completion. | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 3 | 4 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL; This project is complete. Note, Duffy only wanted the dutch door completed……..12/14/18, DL; This project is in progress and should be complete shortly after the new year……`DL, 7/11/18; Need to walk the project and schedule the work…… | 2018-07-06 | Ron Veloz | 06/26/18 Ron V. visited site & met with Duffy. Scope of work for rm's 2103 & 2103 A requires: Painting of walls and conduit locted on the walls, replace damaged ceiling tiles, replace one damaged prismatic 2x4 light fixture lense, remove one tack board and shampoo carpet. Existing wall tiles to remain and receive paint. No work required in 2103 B per Duffy. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | FS | 0 | 2018 | 2019-02-16
19P000021 |  | 19P000021 | FALSE | ITS | SL5-ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS | FS to coordinate with customer to scope the work. | ITS CENTER |  | QUEUE TO START | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-07-12 | [6 empty] | 12/14/18, DL; Still need to review scope….. |  | Enrico Baez | Met with IT staff. T.V. to be mounted in 4 locations. Will need electrical and painting in some locations. Waitng for updated scope from Joe Sepulveda 1. Telecom Building - Conference Space Electricians Power Requirements: • Install double duplex(quad outlet), AC power on East wall at display location (4S Box) low profile • All electrical junction boxes, J-boxes, and conduit can be surface mounted. J-boxes to be located behind TV. Data Requirements: • Install single gang junction box on East wall behind display with Panduit running to specified location (for telecom network drops) o Single gang, low profile junction box o (conduit to be lead through masonry wall above T Bar ceiling in adjacent room. o (Low profile boxes for data ports) • Single gang box, mounted behind TV location, for data. • Note: Non-traditional wall – masonry Carpenters • Install mounting bracket for display on East wall • note: Non-traditional wall – masonry Painters • Paint junction boxes and conduit to match wall. 2. Intellicenter - First Floor Common Area Carpenters • Install mounting brackets on East Wall for each display (2 total) • (ITS to note the top of the bracket) 3. SOM-E - 1675A DataCenter Electricians Power Requirements: • Install double duplex(quad outlet), AC power on North wall at each display location (2 total) o Surface mounted J Boxes and Conduit Data Requirements: • Install single gang junction box on North wall at each display location with conduit/panduit running to specified location (for telecom network drops) (2 total) o (Wire mold boxes for both power and data) (2inch boxes – low profile boxes for data ports) o Data conduit to stub up and terminate through T-bar ceiling panels. • All conduit and J-boxes to run upward through T-bar ceiling Carpenter • Install mounting bracket for each display on North wall (2 total) • Install backing for mounts in adjacent data room in shelving. Painters • Patch and paint installation area as needed Location Notes • Non-traditional wall – drywall over carpentry 4. ITS Building - 174 Electricians • Install double duplex, AC power on East wall at each display location (2 total) • Install single gang junction box on East wall at each display location with conduit above ceiling (for telecom network drops) (2 total) o Terminate Data conduit above T-bar ceilings Carpenters: • Install mounting bracket (marked on the wall) for each display on East wall (2 total) Location Notes: • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 5. ITS Building - Main Lobby Electricians • Install double duplex, AC power on South wall at display location • Install single gang junction box on South wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on South wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 6. ITS Building – AVC / CIO’s Office (ITS 147) Electricians • Install double duplex, AC power on North wall at display location • Install single gang junction box on North wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on North wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 7. ITS Building Room 138 Electricians • Install double duplex, AC power on East wall at display location • Install single gang junction box on East wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install m | YES | FS | 0 | 2018 | 2019-02-16
18P000194 |  | 18P000194 | FALSE | ITS | SL5-TELEPHONE WINDOW REPLACEMENT | Canceled by customer; duration of hold was over 10 months. Customer to resubmit when ready to proceed | TELEPHONE | 101 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 5 | 6 | FALSE |  |  | 2017-11-20 | [8 empty] | Enrico Baez | EB-1/31/18 Conducted site visit. Request to replace all exterior Plexiglas with glass. Will call glass vendor to provide estimate. 7/12/18 EB-Quote provided by Hour Glass. Emailed Tami, she is waiting for budget approval to proceed with project. Should have by end of July. 10/22/18 Customer Canceled; will resubmit when ready to proceed. | YES | FS | 0 | 2017 | 2019-02-16
3292 | 3292 |  | FALSE | ITS | ITS-800Mhz Tower Site-Add Pole | As we did back in 2014, we need approval to mount a pole for network electronics. This time, location is next to the 800Mhz tower site behind the C&C Building. We would propose using the same model pole as we did at AGOPS. I believe the AGOP’s poles were set on concrete piers that were 5’ deep. Again, we would want UCR Physical Plant to mount the pole for us. And once I have approval, I can get a quote from UCR Physical Plant. This project has been given to A&E. |  |  | In Close-out | Danna Gianforte | Shelley Gupta | Tim Paul |  | Dave Bomba | 1 |  |  | FALSE | 42100 |  | 2017-04-20 | Receive final billing | 2018-06-29 | 2019-02-15 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
3396 | 3396 |  | FALSE | ITS | C&C Rear Patio Tables/Shade | Installation of new exterior concrete slab and patio cover at the Computing and Communications Modular Buildings. The existing site will be cleared of all landscape to provide clear area to install concrete slab and address any grade/drainage issues. The addition of a proposed permanent patio cover is to be installed with full electrical options (lights, outlets, ceiling fans) to provide shade for future events and exterior lunch area. Shrubs along the street at the East side of the area are to be removed to provide a vendor/service ramp for events with the inclusion of lighted concrete seating within the space. | ITS CENTER |  | Additional funds added to project. | Danna Gianforte | Shelley Gupta | Sheila Mabee |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2017-11-16 | Complete Project Study | [10 empty] | PD&C | 0 | 2017 | 2019-02-16
18P000273 |  | 18P000273 | FALSE | LIBR | SL5-RIVERA LIB -RESTROOM REFRESH PROJECT | Scope of work has been reviewed; determining how to complete project with trades. | RIVERA LIBRARY |  | TO BE PERFORMED BY PD&C | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2018-01-18 | [6 empty] | DND 12/13/18: Customer advised maintenance requests related to project request has been addressed. Renovation work to be performed by PD&C and customer submitted a CPMS request. DL, 6/16/18; Need to schedule site visit with Dave and Chris P…….DL, 7/11/18; Chris and I will walk this poroject next week…..Wlaked projects with Chris. We need to review in more detail to better determin the process for this project…..DL, 9/6/18. WE need to discuss what we are going to do with this project.... We walked the project but we now need Direction from Facilities leadership… |  | Dan Lerman | DL, 4/29/18; Chris said he is aware of project scope. I need to review with Chris and schedule the work;…..Dl, 5/3/18; Dand to walk project with Chris and Dave to confirm scope. We will sub out tile work. This is paint tile, lighting and plumbing fixture upgrade..... | YES | FS | 0 | 2018 | 2019-02-16
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. |  |  | Client approval/funding | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 2018-11-27 | Client approval/funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3413 | 3413 |  | FALSE | LIBR | Rivera Libr Gender Incl Restroom | Convert existing non-ADA multi-stall women's restroom to compliant ADA gender inclusive restroom. The project also involves the conversion of an existing non-ADA men's restroom to women's compliant ADA restroom. | RIVERA LIB |  | Need design | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Dave Bomba | 3 |  |  | FALSE | 0 |  | 2018-03-26 | Code and policy compliance | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3496 | 3496 |  | FALSE | LIBR | Rivera Library Install Gate | Rivera library gate installation |  |  | New | Steven Mandeville-Gamble | Jackie Bates | Rebeccah Goldware |  | Dave Bomba | 3 |  |  | FALSE |  |  | 2019-01-08 | New | [10 empty] | PD&C | 0 | 2019 | 2019-02-16
3104 | 3104 |  | FALSE | PALM DESERT | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Programming |  |  | Zelda Glenn |  | Scott Donnell | 1 |  |  | FALSE | 22000 |  | 2016-05-12 | Design | [10 empty] | PD&C | 0 | 2016 | 2019-02-16
2747 | 2747 |  | FALSE | PALM DESERT | Heckmann Center - Landscaping (Donor Orchard) | UCR Palm Desert would like to replace the current turf grass with water-wise, sustainable landscaping. In return for the opportunity to use a “living laboratory” classroom for training, UC Cooperative Extension Master Gardener program has agreed to collaborate with UCR to revise and sustain the landscaping. The first phase will be to create an orchard to highlight UCR’s contributions to agricultural research in the Coachella Valley. The orchard will be located at the entrance to the Heckmann building, north of the walkway. UCR Physical Plant/Grounds to provide estimate for: • Project oversight • Project plan and drawings • Organic material to add to soil • Irrigation materials and installation • Edging for path • Weed cloth • Decomposed granite with stabilizer for ground cover • Decomposed granite with stabilizer for pathway • Concrete pad for art including bolting apparatus • Arbor for grapes • Flow system-fertigation • All other labor and materials other than kiosk, plant signage, turf and tree removal (current landscape maintenance vendor can remove) and plant materials and plant installation | HECKMAN ICEM |  | In Programming |  |  | Mike Lawrence |  | Scott Donnell | 2 |  |  | FALSE | 13800 |  | 2014-08-18 | RFQ Design | [10 empty] | PD&C | 0 | 2014 | 2019-02-16
18P000324 |  | 18P000324 | FALSE | PLANNING & BUDGET | SL5-HINDERAKER PATCH AND PAINT | Complete as of 7/11/18 | HINDERAKER | 4118 | COMPLETE | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-02-26 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
17P000254 |  | 17P000254 | FALSE | PLANNING & BUDGET | SL5-FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS | Project in progress; ITS installing data. | CORP PP WHSE | 0106B | IN PROGRESS | Gerry Bomotti | TBD | DALAN DINH |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-06-07 | [6 empty] | 2/1/19, DL; Material is ordered with a 4-6 week lead time.11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DD 10/6: On hold pending discussion on space…..DL, 7/11/18; I understand there is movement on this project but I need to check in with John P. or Chris P. for a status update. |  | Ron Veloz | 12/14/18 O-RVL: F & LS shop space/Shop Location TBD. | NO | FS | 0 | 2017 | 2019-02-16
| 3504 |  | FALSE | PLANNING & BUDGET | Silver Oaks Womens Health TI Fees | UCR Health will be acquiring new off-campus leased space by expanding into an adjacent medical office suite located at 19330 Jesse Ln #160, Riverside, CA 92508. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. |  |  | New | Gerry Bomotti | TBD | Brandon Barbosa |  | ---- |  |  |  | FALSE |  |  | 2019-02-14 | New | [10 empty] | PD&C | 0 | 2019 | 2019-02-16
| 3499 |  | FALSE | PLANNING & BUDGET | Creekside Terrace Analysis | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | New | Gerry Bomotti | TBD | Blythe Wilson |  | ---- |  |  |  | FALSE |  |  | 2019-02-14 | New | [10 empty] | PD&C | 0 | 2019 | 2019-02-16
18P000390 |  | 18P000390 | FALSE | PLANNING & BUDGET | SL5-UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD | Complete as of 8/24/18 | UV BLDG B | 0240B | COMPLETE | Gerry Bomotti | TBD | LESLIE ROSE |  | Paul Ditty |  |  | 1 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000209 |  | 19P000209 | FALSE | PLANNING & BUDGET | SL5-OLD EH&S SITE- FS ANNEX A REMODEL | Scope of work has been reviewed and being scheduled for completion. | ENV H AND S | 100 | IN PROGRESS | Gerry Bomotti | TBD | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 2018-08-24 | [6 empty] | 9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen | Chris walked the project with Craig Kasten on 9/6. | YES | FS | 0 | 2018 | 2019-02-16
19P000241 |  | 19P000241 | FALSE | PLANNING & BUDGET | SL5-PATCH/PAINT IN OFFICE 2122 HINDERAKER | Canceled per customer call on 9/13/18 | HINDERAKER | 2122 | CANCELED BY CLIENT | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-06 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000401 |  | 19P000401 | FALSE | PLANNING & BUDGET | SL5 - PATCH HOLES IN WALL AND PAINT |  | HINDERAKER | 4148E | COMPLETE | Gerry Bomotti | TBD | SHANNON TIMMONS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | FS | 0 | 2018 | 2019-02-16
19P000425 |  | 19P000425 | FALSE | PLANNING & BUDGET | SL5-PAINT VIDEO PRODUCTION SUITE & HANG ITEMS |  | HINDERAKER | 1159A | QUEUE TO START | Gerry Bomotti | TBD | LISA CUSICK |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-20 | [11 empty] | FS | 0 | 2018 | 2019-02-16
3474 | 3474 |  | FALSE | PLANNING & BUDGET | RUSD STEM High School |  |  |  | Real Estate project | Gerry Bomotti | TBD | ----- |  | Raoul Amescua | 3 |  |  | FALSE | 0 |  | 2018-10-31 | Regents Approval of Ground Lease | 2019-07-01 | 2022-09-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
2900 | 2900 |  | FALSE | PLANNING & BUDGET | Batchelor Hall Systems Renewal | <div>Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. Project proposes: *Replace heating, ventilation, and air condition system due to inefficiency, and compromised air quality &nbsp;Upgrade electrical service to 480/277 in order to allow higher intensity research equipment. *Upgrade/replace plumbing systems due to condition, and inadequate water treatment. *Upgrade fire life safety system (fire alarm) due to none code compliance. *Reconfigure laboratory space to improve research space usage and efficiency, work will be phased to limit user impact, and funding availability. Classification of work, Heating and cooling systems, Ventilation systems, Energy management systems, Primary and emergency electrical systems, Fire alarm and protection systems, De-ionized water and reverse osmosis systems, Hazardous materials abatement, Reconfiguration of research and laboratory and related spaces</div> | BATCHELOR |  | A&E, CAS & EH&S working w/CNAS dean & dept chairs to establish a relo. plan | Gerry Bomotti | TBD | Sharyl Murdock |  | Rowan Reid | 4 |  |  | FALSE | 18179000 |  | 2015-12-15 | CM at Risk Selection | 2019-09-01 | 2021-11-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
3484 | 3484 |  | FALSE | PLANNING & BUDGET | 266 Frost Ct Main House Demolition | Develop project budget and timeline, obtain funding from VCPB. Coordinate disconnection of all utilities: Electrical, Gas, and Water. Disconnect and cap sewer Coordinate HAZ Mat testing and report for asbestos and lead Hire abatement contractor (if necessary) to remove haz materials. Hire demolition contractor to demolish and dispose of existing house, garage and out buildings. Foundations to remain – but make safe and remove potential hazards (rebar, bolts, etc.) protruding from foundation. Paving, pavers and other “patio” slabs to remain – make safe by removing tripping hazards. Identify any hazards (I.E.; unstable retaining walls, debris piles, etc.) and make safe and secure or remove if more cost effective. |  |  | DM received. Funds sequestered. | Gerry Bomotti | TBD | Scott Donnell |  | Daneca Stevens | 5 |  |  | FALSE | 40000 |  | 2018-11-15 | Bidding | 2019-05-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
2839 | 2839 |  | FALSE | PLANNING & BUDGET | Multidisciplinary Research Building | External financing provided for this project. Total approved budget is $150,000,000. Confirmed per CPMX and BEA#978864 Xfer Tax Exemp Comm Paper. Funding received 7/25/2016. |  |  | Certificate of Beneficial Occupancy 9.28 L1-L4. Construction ongoing on the Lower Level. | Gerry Bomotti | TBD | Jon Harvey |  | Mihai Gavan | 6 |  |  | FALSE | 156405000 |  | 2015-04-01 | Substantial Completion | 2016-07-01 | 2018-09-28 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
2899 | 2899 |  | FALSE | PLANNING & BUDGET | Pierce Hall Improvements | Replacement of Mechanical, Plumbing and Electrical Infrastructure | PIERCE |  | In Construction | Gerry Bomotti | TBD | Jon Harvey |  | Dave Bomba | 8 |  |  | FALSE | 38560000 |  | 2015-08-06 | Fencing and Staging | 2019-01-01 | 2019-12-07 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
2368 | 2368 |  | FALSE | PLANNING & BUDGET | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | Engineering documentation-civil | Gerry Bomotti | TBD | Katie Sanchez |  | Dave Bomba | 9 |  |  | FALSE | 2600000 |  | 2016-05-19 | Complete CEQA Documentation | 2019-04-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3470 | 3470 |  | FALSE | PLANNING & BUDGET | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | New Study | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 10 |  |  | FALSE |  |  | 2018-11-06 | Complete Review | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
2774 | 2774 |  | FALSE | PLANNING & BUDGET | Highlander Hall Demolition | Demolition of the Highlander Hall Building |  |  | Nearing Completion | Gerry Bomotti | TBD | Blythe Wilson |  | Scott Donnell | 99 |  |  | FALSE | 2127000 |  | 2015-01-22 | Project Close-out | 2018-08-01 | 2019-02-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
3195 | 3195 |  | FALSE | PLANNING & BUDGET | North District Development, Phase-1 | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | Phase 1 - Student Housing - 8/1/2020. | Gerry Bomotti | TBD | Raoula Amescua |  | R.Amescua/D.Hecht | 99 |  |  | FALSE | 2507658.71 |  | 2016-10-26 | Reg. Apprv'l-Business Terms&Fin. | 2019-05-01 | 2021-07-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3110 | 3110 |  | FALSE | PLANNING & BUDGET | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded/never routed to the Dispatcher. 90% CD's completed. | Gerry Bomotti | TBD | Marianne Valenti |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | License Agreement Final Review |  | 2019-07-01 | [8 empty] | PD&C | 0 | 1900 | 2019-02-16
19P000386 |  | 19P000386 | FALSE | PROVOST/EVC | SL5-ROOM CHANGES |  | STUDENT SERV | 3106A | QUEUE TO START | Cynthia Larive | Luisa Levario | STEPHANIE ARCINIEGA |  |  |  | 0 |  | FALSE |  |  | 2018-11-20 | [8 empty] | Ron Veloz | 02/07/19 O-RVL: RV completed Intake & Moved to "Que to Start". END---02/06/19 O-RVL: RV updates, Scope of work is to remove shelving from room, patch and Paint. Dan requested info on room availability. RV contacted Danielle for follow up from 02/05 call. RV will visit site, take pics, and follow up with Dan L.erman. Danielle reported that room 310C is vacant and available. | NO | FS | 0 | 2018 | 2019-02-16
18P000482 |  | 18P000482 | FALSE | SoB | SL5-CARD ACCESS SYSTEM ANDERSON SOUTH | Complete as of 8/2/18. | ANDERSON |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-26 | [6 empty] | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with JasonDL, 7/11/18; Need to check in with Jason on status for his side of the project.....DL, 7/25/18; JAson's team is ready to install but the Anderson IT department does not have the necesary software. We will start the work when the software is up and running...... 8/12/18 DND FAMIS Status noted completion on 8/2/18. |  | Dan Lerman | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with Jason | YES | FS | 0 | 2018 | 2019-02-16
19P000033 |  | 19P000033 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT | Duplicate request to 19P000030; Canceling project to be completed on other request. | OLMSTED | 2301 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | Duplicate to project 19P000030. Canceling project. |  | Paul Ditty | Duplicate to project 19P000030. Canceling project. | N/A | FS | 0 | 2018 | 2019-02-16
19P000018 |  | 19P000018 | FALSE | SoB | SL5-ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER | Complete as of 8/24/18 | ANDERSON 1 | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000017 |  | 19P000017 | FALSE | SoB | SL5-ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD | Complete as of 8/24/18 | ANDERSON 1 | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | DL, 9/6/18; Monitors are installed. Need to schedule the electrical. Target date is 9/21/18…… |  | Enrico Baez | 9/4/18 EB-This Project has been started. Monitors in place. Just need to run electrical. Dan aware. Refer to WO 19P000053. It asks for the same thing. Will request to close this and let Angela know. | YES | FS | 0 | 2018 | 2019-02-16
18P000351 |  | 18P000351 | FALSE | SoB | SL5-REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 | 21 | HOLD - FACILITIES SERVICES | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2018-03-19 | [6 empty] | DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week......8/8/18. The trades are ready to go after they finish current projects.....DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18.......... DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date........9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space......Note. The space is usable and everything works..... |  | Enrico Baez | 4/24/18 EB-scoped. Move screen, correct non-compliant electrical issues, remove&discard overhead projector bracket, relocate heat det. Add switched outles. Plans are needed because we are relocating a heat detector | YES | FS | 0 | 2018 | 2019-02-16
18P000428 |  | 18P000428 | FALSE | SoB | SL5-OLMSTED RM 2352 PATCH/PAINT | Complete as of 8/17/18 | OLMSTED | 2352 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-05-02 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000463 |  | 18P000463 | FALSE | SoB | SL5-ANDERSON HALL PATCH/PAINT-102C | Complete as of 8/24/18 | ANDERSON 1 | 0102C | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-06-04 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
19P000053 |  | 19P000053 | FALSE | SoB | SL5-ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S | Complete as of 10/22/18. | ANDERSON 1 |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-04-13 | [6 empty] | DL 8/22/18; two out of four monitors are complete. WE still need to install powree at four locations…….DL, 9/6/18; Still need Electrical installed……. Planing to have complete by 9/21/18……. This is aqctually 4- monitors in four locations. We should ensure each monitor is treated as an indidual project.......DL, 9/19/18; All monitors are installed. Robert will schedule the electricans this week or early next week...DL, 10/4/18; This project is 100% Complete..... |  | Enrico Baez | DND 7/25/18: Emailed R. Veloz advising work order is closed; upon completion of the scope review, Ron to work with Zee for a Project Number to be created. | YES | FS | 0 | 2018 | 2019-02-16
19P000451 |  | 19P000451 | FALSE | SOB | SL5-ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 |  | ANDERSON 1 (N) | 58 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-15 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  |  |  |  | FS | 0 | 2019 | 2019-02-16
19P000030 |  | 19P000030 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT | Complete as of 10/10/18 | OLMSTED | 2301 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000280 |  | 19P000280 | FALSE | SoB | SL5-ANDERSON HALL PAINT ONLY |  | ANDERSON 2 | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-13 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000353 |  | 19P000353 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT-2348 |  | OLMSTED | 2340 | QUEUE TO START | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-19 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
3341 | 3341 |  | FALSE | SoB | Anderson N & S - Exterior Painting | EXTERIOR PAINTING: Please see Karen Henry or Tim DeBolt for direction in painting exterior items around Anderson Hall North/South as follows: 1. Update Paint on exterior Window trim of both buildings. 2. Update Paint on lanterns and light poles 3. Fix plaster on building walls that is peeling off. |  |  | Client would liketo cancel project | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 1 |  |  | FALSE | 0 |  | 2017-07-18 | To be canceled by Client | [10 empty] | PD&C | 0 | 2017 | 2019-02-16
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Initial planning discussions have begun with SOBA. | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Blythe Wilson | 2 |  |  | FALSE | 350000 |  | 2016-12-15 | Develop RFQ | [10 empty] | PD&C | 0 | 2016 | 2019-02-16
3101 | 3101 |  | FALSE | SoB | DM-Anderson Hall S&N - Maint+Restrm Remodel | Under 2014 Deferred Maintenance Funding Program, SoBA has been approved for interior upgrades to be completed up to $65,00. We were originally approved for $75,000 however, per Scott Donnell, $10,000 had already been used. We have requested a list of expenditures for SoBA upgrades under this $10,000. The following items need to be completed under this 2014DM funding in the priorities listed: 1. Anderson Hall South Women’s and Men’s Restrooms Remodel Requirements: Floor and wainscot tile require replacement and/or re-grouting, casework and associated lavatory fixtures and counter tops require refurbishment/placement, restroom partitions require re-painting/replacement. 2. Anderson Hall North Women’s and Men’s Restrooms – repair and touch up areas where ADA compliance changes were made. 3. Anderson Hall North & South Stairway Requirements: All stairways shall be reviewed for compliant contrasting top and bottom stair-tread indicators and all missing or loose anti-slip tread applications be repaired and/or replaced. Any other safety items as may be noted. Retile or carpet as needed. 4. Anderson Hall South Interior Painting to Common areas, both levels: Interior wall surfaces require patching and painting. 5. Anderson Hall North Interior Painting to Common areas, both levels and conference room 021: Interior wall surfaces require patching and painting. 6. Faculty Suite (Rm 158) – match common area tile (size of mud/dirt mat) to replace dirty carpet when first enter room 158. 7. Dean’s Suite (Rm 162) – new carpet. |  |  | The department would like to cancel the project | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 3 |  |  | FALSE | 65000 |  | 2016-05-09 | To be cancelled by Client | [10 empty] | PD&C | 0 | 2016 | 2019-02-16
3415 | 3415 |  | FALSE | SoB | Anderson South Renovation | Per the sketched drawings that Dave Bomba was provided, please provide a proposal of what it would take to renovate Anderson South as follows: **1. Remove 1st Fl South side of Corridor wall and doors between 102 suite entrance and 106 suite entrance as well as adjoining walls within 102C. **2. Create a closet/wall, ideally, behind the existing door of the 102 Entrance running to the wall shared by 102A to include the best location for a door. Essentially, enclosing the window of 102, if possible. **3. Creating a closet under the stairwell between 1st floor and basement level, having entrance door flush with the bottom step of the stairwell. **4. Remove the West wall and door framing of room 001A, leaving an open look and no corridor in suite 001. | ANDERSON 2 |  | Construction to begin in Feb. 2019 | Yunzeng Wang | Angela Chang | Laurie Gustafson |  | Dave Bomba | 4 |  |  | FALSE | 24700 |  | 2018-02-26 | Complete Construction | 2019-02-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3237 | 3237 |  | FALSE | SoB | Anderson Hall N. Access Imp. | ADA handrails installation at walkway and ramp on the East sidewalk by the bench of Anderson north, down the steep ramp leading to Anderson South. We have been working with Shelly Frohrip from HR and Mary-Alice Avila of A&E on this so they will have some information regarding the purpose. 11/15/17 The handicapped parking and POT are now included. Project approved, waiting for funding. | ANDERSON 1 |  | Construction to begin in Feb 2019 | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 5 |  |  | FALSE | 150000 |  | 2016-12-19 | Complete Construction | 2019-02-01 | 2019-04-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
3345 | 3345 |  | FALSE | SoB | Anderson N & S - Landscaping | DESIGN SVC & LANDSCAPE Construction request as follows for updated CURB APPEAL of Anderson North/South: 1. Roses Garden in middle of Stair landing/court to be removed and replaced with Grass 2. Add Large Planters (Metal or Cement) with Citrus Trees (either Kumquat/Lemon/Orange/Etc) on ledges that are at top section of front steps to deter skateboarders from jumping off of these ledges. 3. Remove dead trees on North and south ends of front lawn 4. Remove plants around granite sign in front lawn and replace with grass 5. Remove flowers and grass at both corners of front lawn around Citrus Trees and replace with DG and low growing flowering plants. 6. Pull all Ivy and crown vetch and add Pavers to East/Back side of Anderson Hall within landscaped/planter areas where ADA walkway runs and replace with nice picnic tables to include umbrellas and/or lounge seating around Anderson North for students. 7. Add DG in all areas where space is open/available surrounding outdoor seating area in back of building. 7. Remove all hedges surrounding alcove/arched areas along buildings. |  |  | On hold until ADA path of travel is completed | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 6 |  |  | FALSE | 0 |  | 2017-07-18 | Completion of 3237 | 2019-03-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
18P000261 |  | 18P000261 | FALSE | SOM | SL5-WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR | Complete as of 9/10/18 | WEBBER | 1143 | COMPLETE | Deborah Deas | Brandon Barbosa | LOURDES ESCAMILLA |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 7/11/18; Work orders are produced. Need to assign the work order and order material. I will review with Steve and verify target complete date….DL, 7/25/18; Still need to walk the project with Steve……DL, 8/10/18; Material is ordered. We will complete the install when the materila arrives.....DL, 8/22/18; Material should be on site with in 4- weeks. Will schedule install when material is on site. Target date is 9/20/18.......DL, 9/6/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 4/29/18; Pasted from work order;I"nstall a glass window 28x9 on office door in WEBBER, Room 1143. | YES | FS | 0 | 2017 | 2019-02-16
18P000380 |  | 18P000380 | FALSE | SOM | SL5-SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 | SOM RSCH | 330 | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-05 | [6 empty] | Canceled per customer on 8/22/18. |  | Enrico Baez | DD 7/17: Requested Enrico verify complete customer did not prioritize and noted work was done. 8/7/18-Conducted site visit-do not recommend location for TV due to potential damage from barn door type window screen. 8/15/18 emailed Tara Bathol that desired location for TV not recommended. Requested alternate location. 08/22/18 Ron V. Spoke with Tara. Tara confirmed the requestor cancelled the TV mounting bracket request after conversation with Enrico | NO | FS | 0 | 2018 | 2019-02-16
18W006022 |  | 18W006022 | FALSE | SOM | INSTALL CURTAIN ROD IN RESEARCH SPACE | Complete as of 7/11/18 | SOM RSCH | 336 | COMPLETE | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-10-27 | [6 empty] | DL, 5/24/18; Need to review scope with Enrico….DL, 7/11/18; Enrico produced work orders for sheet metal shop. This is a singel trade project. |  | Enrico Baez | Blackout curtain needs to have a better way of being secured. Talked to Cory about fabricating a new curtain rod. 7/6/2018EB assigned to sheetmetal shop F-LNH | YES | FS | 0 | 2017 | 2019-02-16
19P000009 |  | 19P000009 | FALSE | SOM | SL5-SOME -- PAINT, SPACKLE AND CLEANING NEEDED | Complete as of 10/10/18 | SOM EDUC | 2615 | COMPLETE | Deborah Deas | Brandon Barbosa | BEVERLEY HERBERT |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000354 |  | 19P000354 | FALSE | SOM | SL5-WEBBER 2130A-PAINT CHERI'S NEW OFFICE |  | WEBBER | 2130A | QUEUE TO START | Deborah Deas | Brandon Barbosa | DOMINIC SALAZAR |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-19 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000408 |  | 19P000408 | FALSE | SOM | SL5 - PATCH & PAINT - 2605 SOM ED |  | SOM EDUC | 2605 | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | FS | 0 | 2018 | 2019-02-16
19P000248 |  | 19P000248 | FALSE | SOM | SL5-SOME--SOME INSTALL ELECTRICAL 1682 | FS to coordinate with client to scope the work. | SOM EDUC | 1682 | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 2 |  | FALSE |  |  | 2018-09-10 | [6 empty] | 2/14/19, DL; This project is complete…… |  | Ron Veloz | 10/29/18 O-RVL: Scoping is completed. END--- 10/17/18: RV: Drawings are on server folder. END---10/08/18 RV: Spoke with Brandon B. Brandon will submitt BKM drawings via permit request through PD&C. 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon. Walked project with Brandon. SOW to install two each dedicated 120v/20a cicuits for new modular furniture one whip at each end of the office down the wall and one to two data drops overhead down wall. | YES | FS | 0 | 2018 | 2019-02-16
19P000410 |  | 19P000410 | FALSE | SOM | SL5-PAINT OFFICES AT UC PATH |  | INTELLICTR |  | QUEUE TO START | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-14 | [11 empty] | FS | 0 | 2018 | 2019-02-16
19P000249 |  | 19P000249 | FALSE | SOM | SL5-SOME-INSTALL LOCKERS | Lockers on order by customer; upon arrival to be installed. | SOM EDUC |  | CANCELED BY FS | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-07 | [6 empty] | DL, 11/7/18; It is my understanding the lockers are ordered, but we donot have a confirmed delivery date. Once the material is on site, we will schedule the installation…… |  | Ron Veloz | 01/31/19 O-RVL: Contacted Domonic and confirmed lockers will not be avialable to install and agreed to cancel the request orginated on 09/07/18 and will resubmit a new request upon delivery of the new lockers. RV emailed Customer Relations staff to cancle the project request via emails and cc Monty, Deborah H., Alan, Loretta on the communication. 01/10/19 O-RVL: Emailed Dominic Salazar on locker delivery ststus. Pending follow up call from customer to inform FS on delivery of lockers. 11/08/18 RV: Visited site existing lockers in place and in use. Will follow up with the requestor for locker delivery status to schedule. RV Spoke with Brandon Barbosa. Deparment will purchase lockers. 11/08/18 RV: Received email from Domonic Salazar on 10/25 Lockers are expected to arrive. | YES | FS | 0 | 2018 | 2019-02-16
19P000245 |  | 19P000245 | FALSE | SOM | SL5-ADA COMPLIANT - AUTOMATIC DOOR ENTRY | FS to coordinate with client to scope the work. | SOM RSCH |  | QUEUE TO START | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 4 |  | FALSE |  |  | 2018-09-07 | [7 empty] | 2018-10-29 | Ron Veloz | 02/15/19 O-RVL: RV updated notes addedSOW & moved to "Que to Start". END--- 01/31/19 O-RVL: Chris at Lockshop reviewed the vendor quote and requested detailed equipment list. Pending revisions from vendor due this week. END--- 01/15/19 O-RVL: Delivered Access control quoute to Jason & Chris R for revie. They will respond with comments. Upon receicpt and confirmation, RV will complete docs on server folder and update FAMIS & Access DB. --- 01/11/19 O-RVL: Qualifying quote to verify proper components from door operator vendor expecting reply soon. 12/14/18 O-RVL: Received Quotes for Auto door operator and Access controls this week. RV to provide update & quotes to to Dan Lerman. Moving status to "Que to Start" on Minor Ren List & updating Project Folder. --- 11/07/18 O-RVL: Walked site with Access Control vendor --- 10/31/18 O-RVL: Walked site with Door Op vendor --- 10/29/18 O-RVL: Scope was Completed. RV to schedule job walks with Vendors. --- 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon | YES | FS | 0 | 2018 | 2019-02-16
19P000032 |  | 19P000032 | FALSE | SOM | SL5-Reconfigure recepetion desk to fit two FTEs. | Scope of work has been identified and walked with Ron V & Brandon B. | SOM EDUC | 2608 | QUEUE TO START | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | 5 | 1 | FALSE |  |  | 2018-07-17 | [6 empty] | 2/1/19, DL; I Walked this project this week. We will try and schedule the work in the next 30- days…….12/14/18, DL, Still need to conduct site visit and schedule the work… | 2018-10-17 | Ron Veloz | 01/31/19 O-RVL: Met with Dan L onsite to review SOW with the requester. END--- 10/17/18 O-RVL: Remove one lower cabinet, Install a new corbel below to support the counter, install new carpet square or create an accent border if carpet tile is obsolete. Install new rubber base | YES | FS | 0 | 2018 | 2019-02-16
18P000485 |  | 18P000485 | FALSE | SOM | SL5-SOMR PATCHING AND PAINTING | Complete as of 10/10/18 | SOM RSCH |  | COMPLETE | Deborah Deas | Brandon Barbosa | DANA ABOU ABBAS |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000012 |  | 19P000012 | FALSE | SOM | SL5-SOME--PATCH & PAINT | Complete as of 10/10/18 | SOM EDUC | 2638 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-07-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000014 |  | 19P000014 | FALSE | SOM | SL5-SOME - PATCH & PAINT | Complete as of 10/10/18 | SOM EDUC | 2609 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-07-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19S000833 |  | 19S000833 | FALSE | SOM | Add access control to entry doors | Canceled request per conversation with client; customer to coordinate for a contractor to complete project. | HECKMAN ICEM | Entry Doors | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | Canceled | 2 | FALSE |  |  | 2018-07-17 | [8 empty] | Ron Veloz | Will Meet with Chris Pillen on 08/23/18 to review notes by C.P. on FAMIS. 08/23/18-RV: Followed up with Chris P for update on the work request notes. Recommended to contact Brandon to procure a local vendor. 08/24/18-RV spoke with Brandon Barbosa to determine a plan to complete the request and will pursue pricing and oversee the installation. 08/27/18 RV: Update: Brandon will PM the project on his own. 09/19/18: UPDATE-CANCELLED BY Brandon. See notes above. | YES | FS | 0 | 2018 | 2019-02-16
18P000400 |  | 18P000400 | FALSE | SOM | SL5-Covert suite 1116 and suite 1126 to office space | Provost has placed a hold on converting lab spaces into office spaces. | WEBBER | 1116 & 1126 | HOLD - FACILITIES SERVICES | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | HOLD | HOLD | FALSE |  |  | 2018-04-14 | [6 empty] | DL, 6/16/18; Waiting for update on Provost approval….DL, 7/11/18; Per email from Enrico on 7/10/18. The Provost put a hold on converting any lab space into officess…… |  | Enrico Baez | 5/1 EB Convert two wet labs into offices. Same as Webber 2278. Abate floor, demo all cabinets, remove plumbing, patch & paint. Carpet tile. Equipment comes out. Awating Provost, Sheryl Murdoch and Bob Williams approval….. 7/11/18 EB-Per Brandon Barbosa project will be cancelled | YES | FS | 0 | 2018 | 2019-02-16
2359 | 2359 |  | FALSE | SOM | SOM - Research Bldg. BSL-3 | Reconfiguration and reconstruction of the existing BSL-3 suite on the 3rd floor. |  |  | Finalizing commissioning & air balance | Deborah Deas | Brandon Barbosa | Rebeccah Goldware |  | Mihai Gavan | 1 |  |  | FALSE | 2730000 |  | 2013-07-03 | Notice of Completion | 2016-10-01 | 2017-11-01 | [8 empty] | PD&C | 0 | 2013 | 2019-02-16
2974 | 2974 |  | FALSE | SOM | SOM Research Building - 1st Floor Fit-Out | Buildout the 1st Floor of School of Medicine Research Building, a space of approximately 17,600 square feet. The construction includes wet laboratories, laboratory support spaces, offices and related support space. Work consists of, but not limited to the following: demolition of existing improvements, addition/alterations of walls, installation of new fume hoods, sinks, safety showers and eyewash stations, alterations/additions to the mechanical, electrical, plumbing, fire life safety, fire suppression, telecommunication and audio/video systems, as specified in the Construction Documents. |  |  | Working on punchlist items. | Deborah Deas | Brandon Barbosa | Blythe Wilson |  | Mihai Gavan | 99 |  |  | FALSE | 9600000 |  | 2015-10-30 | Final Completion / NOC | 2017-10-01 | 2018-10-01 | [8 empty] | PD&C | 0 | 2015 | 2019-02-16
3052 | 3052 |  | FALSE | SOM | SOM Trailer Expansion | Replace the (2) modular units with one 96' x 60' building and provide access from the SOM-ED building via concrete ramp; Re-vamp the entire site for accessibility. Signed Major Cap Approval for $150k augmentation received 10/25/17 - total project $2,250,000. |  |  | Punch list needs to be addressed | Deborah Deas | Brandon Barbosa | Sharyl Murdock |  | Dave Bomba | 99 |  |  | FALSE | 2250000 |  | 2016-03-07 | Install Code Blue Phone | 2017-08-01 | 2018-02-01 | [8 empty] | PD&C | 0 | 2016 | 2019-02-16
18P000470 |  | 18P000470 | FALSE | SPP | SL5-Student Check-in Lobby | Complete as of 8/23/18 | CHASS INT S | 4133 Corridor | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-11 | [6 empty] | DL, 6/16/18; I walked this project with Luis and Mark this week. They want this work completed by July 9th. Paint, data, electrical, chair rail and signage is requested. I need to review project with Paul and Robert C. DL, 7/11/18; Robert C. Ordered material and we will complete the install first part of next week We will scheudle the paint after Robert is Complete. Target Complete Date is 7/2018......DL, 7/25/18; WE have the electrical materila, plans were submitted. Once plans are reviewed and approved, we will proceed with the work. Target date is two weeks after plans are approved......DL, 8/10/18; Eletrical is complete. Pending paint. Paint will be scheduled in the near future. DL, 8/22/18; This project will be Complet on Saturday.....DL, 9/6/18. I miossed the chair rail request on this project. I will order the chair rail in the near future. The chair rail is the only item needed to complete this project. Aprroximately 20 lineal feet......DL, 9/19/18; Chair rail is ordered. We will schedule the install when the material arrives....... |  | Dan Lerman | Added by customer on prioritization; timeline and scope tbd. 4/25 EB emailed Christina to schedule site visit. No work order Luis to submit Google doc. To A&E sevral trades invlved. DND 6/13 Project rescoped and priorities adjusted per meeting between Dan and Luis Alvarez. | YES | FS | 0 | 2018 | 2019-02-16
19P000255 |  | 19P000255 | FALSE | SPP | SL5-CHASS INT N REMODEL - 4022 PATCH AND PAINT | Complete as of 10/10/18 | CHASS INT N | 4022 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-02-16
19P000263 |  | 19P000263 | FALSE | SPP | SL5-CHASS NORTH REMODEL - 4009 PATCH AND PAINT | Complete as of 11/8/18 | CHASS INT N | 4009 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-09-11 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-02-16
19P000256 |  | 19P000256 | FALSE | SPP | SL5-CHASS REMODEL - 4146 PATCH AND PAINT | FS to coordinate with client to schedule work for completion. | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  |  |  | 3 |  | TRUE |  |  | 2018-09-10 | [7 empty] | 2018-10-09 | Enrico Baez | 10/9/18 EB Sent Luis email, copied Mont too. Project will bw $25k-$30K. Asked Luis if we are to proceed. 10/15/18 E.Baez conducted site visit, Client requested cost estimate to construct 2-3 "huddle" Spaces with sound proof walls. Requires alterations to HVAC ducting, full height walls with doors, fire sprinkler additions, smoke detection additions, lighting changes. emailed Luis estimated cost of $25,000. 12/20/18 D. DINH: Spoke with customer, Luis Alvarez, and the project request has been modified to patch & paint and replacement of one ceiling tile. Customer to work with BKM to fulfill the wall partition request portion of the project. | YES | FS | 0 | 2018 | 2019-02-16
18P000270 |  | 18P000270 | FALSE | SPP | SL5-CHASS INT S- EVALUATION FOR REMODEL | Pending customer to provide drawing of the space. | CHASS INT S | 4133 | CANCELED BY CLIENT | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Dan Lerman |  | 4 | 2 | TRUE |  |  | 2018-01-16 | [6 empty] | 4/24/18 EB- Per Christina Wong, no loner needed……DL, 5/5/18; Project is cancesled per notes DND 7/27; Please follow up with customer on the status and need for the work; customer advised to me that Dan has the scope of work for completion. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. |  | Enrico Baez | 4/24/18 EB- Per Christina Wong, no longer needed……DL, 5/5/18; Project is canceled per notes DND 6/13; Project reopened and not canceled per conversation with customer. Complete scope review and speak with Luis Alvarez DND 8/20/18: submitted Google form for Project to be reviewed by IRT. 8/19/18 Met with Louis Alvarez. Asked for measured plans from BKM for wall layout and dimensions. emailed again on 9/6 asking for draws. Still waiting for BKM to provide drawings. 9/21/18 Dinh - placed on hold until customer provides BKM drawings. Enrico please manage follow up. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. On shared drive can be found in file. 10/30/18 EB-Cancelled by Customer | YES | FS | 0 | 2018 | 2019-02-16
9999 | 9999 |  | FALSE | SPP | Test 2 | Test project description |  |  | Test 10/8 | Anil Deolalikar | Luis Alvarez |  |  | xxxxx | 99 |  |  | FALSE | 345 |  | 2016-01-23 | 12345678901234567890123456789012 | [10 empty] | PD&C | 0 | 2016 | 2019-02-16
18P000478 |  | 18P000478 | FALSE | UNDERGRAD ED | SL5-CARPET, PAINT, & AIR HANDLING MODIFICATION | Complete as of 10/22/18. | HINDERAKER | 1120H | COMPLETE | Jennifer Brown | Tracey Scholtemeyer | TRACEY SCHOLTEMEYER |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-16 | [6 empty] | DL, 7/4/18; This project is scoped; Need to remove Switch gear storage rack components, remove electrical conduits, plywood backer board from walls, paint and floor covering. We will schedule this work to be complete by Fall 2018 academic year....DL, 7/11/18; Need to produce work orders and schedule the work. Target Complete date is 9/14/18... Space is vacant....DL, 8/10/18; Work has started and we are on schedule...... DL, 8/22/18; Demo is almost complete. This target date is 9/21/18......9/19/18; All trades are complete. New carpet to be installed on 9/21/18. .....DL, 9/19/18; This project is scheduled to be complete this week....... |  | Dan Lerman | 7/9 EB-Spoke with Dan, he has already scoped this. | YES | FS | 0 | 2018 | 2019-02-16
18W013973 |  | 18W013973 | FALSE | VC-RED | SL5-BSL3 FACILITY- ASSEMBLE AND INSTALL | Complete as of 9/24/18 | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2018-04-19 | [6 empty] | FAMIS NOTES 8/22: Plumbing filter system was installed and ice maker installed. Request for microscope and incubator moved into containment by customer. Complete 9/24/18 |  | Enrico Baez | 5/16/18 EB conducted site visit. 5/22/18 EB appliances dented, vaccum pump not on site. 6/19/18 emialed Chrystal to see if appliance have been replaced. 7/16/18 emailed Chrystal Jimenez asking for update. 8/7/18 EB Replacement appliances | YES | FS | 0 | 2018 | 2019-02-16
18P000442 |  | 18P000442 | FALSE | VC-RED | SL5-FAWCETT LAB 203 PATCH & PAINT | Complete as of 8/24/18 | FAWCETT LAB | 203 | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 3 | FALSE |  |  | 2018-05-18 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18P000379 |  | 18P000379 | FALSE | VC-RED | SL5-UOB PATCH AND PAINT | Complete as of 8/24/18 | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-05 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-02-16
18W015691 |  | 18W015691 | FALSE | VC-RED | SL5-BOYCE CONNECT WASHER AND DRYER | Complete as of 7/11/18 | BOYCE | 6444 | COMPLETE | Michael Pazzani | Laura Manor | DIERK BIGGS |  |  |  |  | 1 | FALSE |  |  | 2018-05-30 | [6 empty] | DL, 7/11/18; This project is in progress and almost complete. Target complete date is 7/20/18….. |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-02-16
18P000476 |  | 18P000476 | FALSE | VC-RED | SL5-BOYCE CONNECT WASHER & DRYER | Canceled project, work completed on 18W015691 in July. | BOYCE | 6444 | CANCELED BY CLIENT | Michael Pazzani | Laura Manor | DIERK BIGGS |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-14 | [6 empty] | Duplicate to 18W015691; complete |  |  | Duplicate to 18W015691 | NO | FS | 0 | 2018 | 2019-02-16
19P000439 |  | 19P000439 | FALSE | VC-RED | SL5--SPIETH PATCH AND PAINT ROOM 335 |  | SPIETH | 335 | QUEUE TO START | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-08 | [11 empty] | FS | 0 | 2019 | 2019-02-16
19P000044 |  | 19P000044 | FALSE | VC-RED | SL5-PATCH AND PAINT | Complete as of 10/10/18 | SPIETH | 345 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19W003050 |  | 19W003050 | FALSE | VC-RED | SL5-SPEITH HALL - PATCH & PAINT HOLE IN WALL | Complete as of 10/10/18 | SPIETH | 0359A | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5-UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [7 empty] | 2018-09-27 | Enrico Baez | 9/13/18 EB-emailed crystal Jimenez to schedule site visit. 9/19/18 EB-Scheduled site visit for 9/20. 9/29/18 EB- install keyless entry system on two doors. 10/15/18 EB-sent Aaron Seitz approx. cost of project. Awaiting respone to determine funding. | YES | FS | 0 | 2018 | 2019-02-16
19P000181 |  | 19P000181 | FALSE | VC-RED | SL5-PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS | FS to coordinate with client to schedule work for completion. | UNIV OFC BLD | 249 | QUEUE TO START | Michael Pazzani | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-14 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
9055 | 3495 |  | FALSE | VC-RED | Pysch Loading Dock Haz Waste Storage | There’s been an increase use of biological and chemical hazards being used by researchers and their research projects within the Psychology (V3) vivarium. When hazardous substances are used/generated in the vivarium, the current practice is for that waste to be removed by the researcher and taken to their lab for disposal by EH&S. This would mean that hazardous agents are being transported across campus which could potentially lead to an accidental exposure. In order to comply with the hazardous storage and transportation regulations, RED proposes that a hazardous storage shed be built on or near the Psychology (V3) loading dock thus minimizing any potential from an accidental contamination. It would be a chain link storage shed with two rooms (one for biological hazards and the other for chemical hazards), and a solid roof. Around the outside of the shed would also need to have some sort of vinyl covering. As for size, a 10’ x 20’ (two 10’ x 10’) shed should meet the needed storage space. Sample designs can be provided. |  |  | Funding in process | Michael Pazzani | Laura Manor | Dierk Biggs |  | Fernando Nunez | 2 |  |  | FALSE | 10000 |  | 2018-12-04 | Start Construction | 2019-04-01 | 2019-04-30 | [8 empty] | PD&C | 0 | 2018 | 2019-02-16
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | In Design | Michael Pazzani | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Dave Bomba | 99 |  |  | FALSE | 15000 |  | 2017-06-13 | Approval of HVAC design | 2019-04-01 | 2019-07-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
18P000214 |  | 18P000214 | FALSE | VC-STU.AFF. | SL5-COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Plans were approved by Fire Marshal, work to commence in 30 days. Scheduling the work with the availablity of the teams. | HEALTH SERV |  | IN PROGRESS | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-12-08 | [6 empty] | 2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez | 1/31/18 EB-Scoped site with Chris P. on 10/30/2017. Spoke with Gloris who thought still CPMS. Scope includes removing doors, adding teller counters, moving corridor wall…..Dl, 5/3/18; Dan, Chris, ron and Gloria will meet and re-scope the work……01/15/19, DL; The plans are approved and Material is ordered. Once material arrives, we will schedule the work with Gloria. | YES | FS | 0 | 2017 | 2019-02-16
18P000215 |  | 18P000215 | FALSE | VC-STU.AFF. | SL5-STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 | Plans were approved by Building Official; work to commence in 30 days. Scheduling the work with the availablity of the teams. | HEALTH SERV |  | IN PROGRESS | Brian Haynes | Cathy Eckman | PAMELA HAGGINS |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2017-12-08 | [6 empty] | 2/14/19, DL; This project is scheduled to start on 2/19/19…………2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………1/15/19, DL, Material is ordered, material should arrive on site in the next 3- 5 weeks……12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 5/24/18; Need to review scope and site visti with Enrico. Plans and permits will be required for this project….DL, 7/11/18; Planning to walk work with Gloria and her team next week. Will be able to project complete date after site visit is conducted……DL; 7/25/18; We walked this project with the team. This will require plans and permits. We will schedule this work for Fall…………DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-45 Days…… |  | Enrico Baez | EB 3/20 scoped project and annotated on FAMIS. DL, 5/5/18; Pased from wo:Noted changes to original request.Add counter windows onto end of the current SHS front desk main counter (2 windows/stations).2. Close exam room that is open to hallway with a wall (behind room 210).3. Covert 100A to phlebotomy room with a hallway access doorway.4. Open wall to reconfigure to allow space for lab manager……01/15/19, DL; Plans are approved and material is ordered for the Phlebotomy room. We are securing the double doors. We are not conducting anywork with countrtop or window work. | YES | FS | 0 | 2017 | 2019-02-16
18P000456 |  | 18P000456 | FALSE | VC-STU.AFF. | SL5-HUB--UTILITY METERS | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. | HUB |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-05-30 | [8 empty] | Enrico Baez | 1/24/19 EB Contacted Jonathan Bianchet of Design West for results of site evaluation. Will have report by middle of following week. 11/29/18 EB Met with Design West and HUB staff. Conducted site visit. Waiting for recommendations from Design West. 7/6/18 EB-emailed Brendan to schedule site visit. 7/11/18 EB- Site visit schduled for 7/12/18 7/16/18 Conducted site. Customer wants to have SEP metered for all food vendors. Requested electical power plans from Gunther 8/7/18 Contacted Design West for proposal of feasibility stud 8/15/18 Advised Brendan Obrien to submit request to CPMS as this work will not be self performed. Sent Brendan copy of proposal for sight assessment. | YES | FS | 0 | 2018 | 2019-02-16
18P000337 |  | 18P000337 | FALSE | VC-STU.AFF. | SL5-MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET | Plans are approved for work to commence; scheduled for start on 11/13/18. | HEALTH SERV | 414 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-12 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18….Need to work on plans and permits….DL, 7/11/18; Gunther is working on plans. Target complete date is 9/14/18….DL, 7/25/18; Planning to submit plans for review next week. We will schedule the work once we have approved plans…….DL, 8/8/18; This is a structual wall and needs to be engineered. We are meeting with the Structual engineer on 8/9/18 to determine if project is possible.....DL, 8/22/18; Working on EDPA for Structual engineer; project timeline is late Fall. 9/19/18; The Agreement / Cointract for the structual engineer is processed for this project. We should have plans from the structual engineer to submitt to the Building Official and fire marshal with in 4- weeks......dl, 10/4/18; Plans are almost complete and we will submit them for review by the end of the week.....DL, 11/7/18; Plans are approved. WE are schedule to start this Project on Tuesday 11/13/18. Target complete date is by the end of the winter break..... |  | Enrico Baez | Cut wall between rooms 414 and 401, Case and trim opening, install carpet in- DL, 5/10/18; Gloria Vera is the contact; 827-5532 | YES | FS | 0 | 2018 | 2019-02-16
19W006811 |  | 19W006811 | FALSE | VC-STU.AFF. | SL5-HUB 353--PATCH AND PAINT WALL |  | HUB | 353 |  | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
18P000198 |  | 18P000198 | FALSE | VC-STU.AFF. | SL5-HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Plans will be developed and will be submitted for review and approval. | HUB | 0 | QUEUE TO START | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 1 | 5 | FALSE |  |  | 2017-11-21 | [6 empty] | DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…... | 2018-01-23 | Enrico Baez | 1/23/18 EB-site walk, scope enter in FAMMIS. 4/2 MN: Enrico to obtain an FAU. 1/23/2018 E.Baez conducted job site walk. Request is for lighting installations above entries to store front and kitchen on East side of building and additional lighting above outside locker on loading dock. Manny has lights that can be re-used. Want estimate only. Need to include Campu Architech too...... | YES | FS | 0 | 2017 | 2019-02-16
19P000380 |  | 19P000380 | FALSE | VC-STU.AFF. | SL5- PATCH AND PAITN- WALL PAINT IS PEELING |  | HEALTH SERV | 404 | QUEUE TO START | Brian Haynes | Cathy Eckman | SAMANTHA HARRIS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-19 | [11 empty] | FS | 0 | 2018 | 2019-02-16
19P000405 |  | 19P000405 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED |  | HEALTH SERV | 0100D | QUEUE TO START | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-11 | [11 empty] | FS | 0 | 2018 | 2019-02-16
18P000348 |  | 18P000348 | FALSE | VC-STU.AFF. | SL5-HUB ADD 3RD FLOOR WALLS | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | HUB | 0353E | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 2 | 6 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/1/19, DL; Per Chris P. This is a PD&C project………..DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Need to walk the project with Manny. Target date is late Fall…….. |  | Enrico Baez | EB 5/23/18. Conducted site visit. Request is for adding walls to interior spaces 353F, 381 and 377. Will impact A/C and fire protection. Still waiting for a firm plan from customer. | YES | FS | 0 | 2018 | 2019-02-16
19P000037 |  | 19P000037 | FALSE | VC-STU.AFF. | SL5-HEALTH SERVICE BLDG--PATCH WORK AND PAINTING | Complete as of 10/22/18. | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-07-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000124 |  | 19P000124 | FALSE | VC-STU.AFF. | SL5-PAINT ROOMS 115 AND 116 | Complete as of 10/22/18. | COSTO HALL | 125 | COMPLETE | Brian Haynes | Cathy Eckman | LINDA KELLEY |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000172 |  | 19P000172 | FALSE | VC-STU.AFF. | SL5-HEALTH SERV- PAINT RESTROOM IN LABORATORY | Complete as of 11/8/18 | HEALTH SERV | 0113A | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
3385 | 3385 |  | FALSE | VC-STU.AFF. | SRC North Gym Replace Interior Lights | Replace old technology sodium vapor light fixtures in SRC North Gymnasium with new technology LED light fixtures. Some flexibility available in the schedule. Selected vendor will need to phase work to minimize the effect on SRC operations and programming. | SRC NORTH |  | 100% CD's review | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Fernando Nunez | 1 |  |  | FALSE | 360000 |  | 2017-10-31 | Bidding - February 2019 | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-02-16
2829 | 2829 |  | FALSE | VC-STU.AFF. | SRC South - New Storage Building | New storage building immediately south of SRC South Pool Building; approximately 20' x 40'; one roll up door and one standard door; electrical power required - number of outlets to be defined in design; concrete walkway and door pads required; non-potable water may be required if quick couplers are not available in nearby landscaping; please see attachment for location: approximately at gridlines T and 9.4 - dotted outline of building is labeled "FUTURE STORAGE" - located immediately south of the SRC POOL EQUIPMENT BUILDING. | SRC SOUTH |  | Project is currently on-hold. | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Mihai Gavan | 2 |  |  | FALSE | 0 |  | 2015-01-23 | Coordinate with MRB Logistics | [10 empty] | PD&C | 0 | 2015 | 2019-02-16
3471 | 3471 |  | FALSE | VC-STU.AFF. | HUB Elect/Gas Meters 8 Location | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | New | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | J.Franklin/J.Espinoza | 5 |  |  | FALSE | 0 |  | 2018-08-20 | Awaiting Approval | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
3486 | 3486 |  | FALSE | VC-STU.AFF. | HUB 353/381, Costo 111 Add'l Wall/Doorway | Please evaluate additional wall/door way requests for HUB 353/381 and Costo Hall 111. | HUB |  | Client Approval | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 6 |  |  | FALSE | 0 |  | 2018-11-26 | Funding | [10 empty] | PD&C | 0 | 2018 | 2019-02-16
19P000238 |  | 19P000238 | FALSE | VC-UNIV.ADV. | SL5-PATCH & PAINT HINDERAKER 1136 | Pending completion of one room outstanding for scheduling. | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
19P000418 |  | 19P000418 | FALSE | VC-UNIV.ADV. | SL5--BOTANIC UCR BOARD OF TRUSTEES MTG./BOTANIC GARDENS CONF. RM |  | BOTAN INFO C | 1 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | LADONNA ARDARY |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [11 empty] | FS | 0 | 2018 | 2019-02-16
18P000281 |  | 18P000281 | FALSE | VC-UNIV.ADV. | SL5-ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS | Work has been scoped; coordinating trades schedule for work to begin. | ALUM VISITOR | 2202 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | TRUDY COHEN |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-01-24 | [6 empty] | DL, 5/24/18; Need to verify scope of work with EnricoDL, 7/11/18; Still need to visit the site and schedule the work…..DL, 11/8/18; This project was transferred to John. The target date was 1/2/19….. |  | Enrico Baez | 5/10/18 EB-Customer needs additional outlets in space to accommodate 4 new cubicles. Bob Williams wants additional information with plans. 9/13/18 EB-Met with Dan, Jorge, Rita and Kim. Scope to include patch and painting walls, removing art work, moving thermostat. Cubicles will need whip connections. | YES | FS | 0 | 2018 | 2019-02-16
19P000326 |  | 19P000326 | FALSE | VC-UNIV.ADV. | SL5-HINDERAKER - PATCH & PAINT |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-08 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-02-16
2245 | 2245 |  | FALSE | VC-UNIV.ADV. | Campus Directory & Blade Signs | Remove and replace campus directories at strategic locations throughout the campus. |  |  | Pre Design | Peter Hayashida | Naysia Caldwell | Margene Mastin-Schepps |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2014-03-27 | Project Approval & Funding | 2019-08-05 | 2019-09-30 | [8 empty] | PD&C | 0 | 2014 | 2019-02-16
2245 | 2245 |  | FALSE | VC-UNIV.ADV. | Campus Directory & Blade Signs | Remove and replace campus directories at strategic locations throughout the campus. |  |  | Pre Design | Peter Hayashida | Naysia Caldwell | Margene Mastin-Schepps |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2014-03-27 | Project Approval & Funding | 2019-08-05 | 2019-09-30 | [8 empty] | PD&C | 0 | 2014 | 2019-03-01
2353 | 2353 |  | FALSE | CNAS | Natural Reserves-Sweeney Granite Mountain | This project will add structurally independent facilities for an administration building and researcher housing to provide meeting/office space and short term sleeping quarters. Additionally, the existing laboratory building and staff residence will be extensively renovated. High priority is focused on high insulation values, high wind resistance, rodent proofing, and pursue as much passive cooling and heating as possible with an eye toward low maintenance and high durability. Both new construction and renovation projects are to be sealed to prevent rodent intrusion. The new structures must withstand the harsh environment of extreme temperatures and very high winds. All site improvements shall be done with minimal disturbance to the desert environment. The overarching goal of the project is to provide a sustainable structure that respects its environment and is low maintenance while using best practice design standards. |  |  | Construction has resumed at the remote granite mountain location in January 2019, with work focused on modifications to the Existing Allison Center Lab, and Staff Residence. Construction is expected to be completed in these buildings in March of 2019 | Kathryn Uhrich | Deborah McWilliams | Jim Andre, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2545500 |  | 2015-11-23 | Complete Construction | 2019-01-14 | 2019-10-01 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
2359 | 2359 |  | FALSE | SOM | SOM - Research Bldg. BSL-3 | Reconfiguration and reconstruction of the existing BSL-3 suite on the 3rd floor. |  |  | Finalizing commissioning & air balance | Deborah Deas | Brandon Barbosa | Rebeccah Goldware |  | Mihai Gavan | 1 |  |  | FALSE | 2730000 |  | 2013-07-03 | Notice of Completion | 2016-10-01 | 2017-11-01 | [8 empty] | PD&C | 0 | 2013 | 2019-03-01
2368 | 2368 |  | FALSE | PLANNING & BUDGET | Creekside Drainage Channel | The northern and eastern bank of the drainage channel along the southern and western boundary of the UCR Creekside Terrace residential development needs to be stabilized (e.g. rip rap) to prevent additional erosion from future storm events that could compromise the integrity of the Keystone Wall which supports several building pads above the channel. The proposed construction project site is primarily located on private property adjacent to the campus property. Permission has been obtained from the property owner for UCR to provide the stabilization of the creek slope and will be accomplished via a flat area between the channel and the wall on UCR property. A biological resources environmental assessment to ascertain whether there are sensitive species (plants and/or animals) in the drainage canal/creek bed has been recently completed, and the surveys found that there were no sensitive species. An Addendum to the previously city approved Mitigated Negative Declaration, which includes the updated biological assessment and streambed delineation, has been prepared in order to proceed with the stabilization project. The proposed project will be submitted to the city for review of the grading/construction plan and requests for review will be submitted to the following agencies: State Fish and Game, Army Corps of Engineers, and the Santa Ana Water Quality Control Board. If it is determined during the review process that the agencies have jurisdiction, streambed alteration permits will be necessary for any work in the stream bed. The agencies may change the form or requirements of the stabilization and may include additional requirements not already anticipated. Construction drawings cannot be finalized until the environmental assessment is accomplished and the permitting process is completed, if required, from the agencies concerned. EDPA issued to Rick Engineering 2/2/18 and executed 2/8/18 need insurance certs from RE. EDPA issued 2/2/18 executed 2/8/18 need insurance certs from Rick Eng. |  |  | On hold | Gerry Bomotti | TBD | Katie Sanchez |  | Dave Bomba | 11 |  |  | FALSE | 2600000 |  | 2016-05-19 | Project path determined by RE | [10 empty] | PD&C | 0 | 2016 | 2019-03-01
2508 | 2508 |  | FALSE | BAS | Barn Expansion | Project 950493 Barn has completed the DPP process and we are now adding this to CPMS to capture expenses related to the Program Process which occurred in FY11-12 and FY12-13. Please move all expenditures from A01233-70003-76 Cost Center to JR142 to a plant account. |  |  | In construction | Gerry Bomotti | Georgianne Carlson | Susan Marshburn |  | D.Hecht/J.Franklin | 4 |  |  | FALSE | 28700000 |  | 2013-07-05 | Complete Construction | 2018-06-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2013 | 2019-03-01
2671 | 2671 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Elevator Modifications - Various Buildings | Provide Vertical Transportation Consulting, Mechanical, Electrical, Fire Alarm and Architectural/Structural Construction document design and specifications for the modernization of two (2) elevators at Webber and Watkins buildings which is included in the base design and one (1) elevator at the Entomology Museum is included as an add alternate. |  |  | Permit review process | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 99 |  |  | FALSE | 596011 |  | 2016-01-05 | Final Approval of CD's | 2019-07-01 | 2019-12-31 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
2682 | 2682 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Rivera Library Arches/Arcade Repair | Paint and replace roof. |  |  | Bidding | Susan Marshburn | Da Lan Dinh | Susan Marshburn |  | Jason Espinoza | 99 |  |  | FALSE | 240000 |  | 2016-05-06 | Award Contract | 2019-05-01 | 2019-07-30 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
2687 | 2687 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Bourns Hall Fire Alarm System Replacement | Replace current devices with Simplex hardware and move FA panel in Bldg. A to Building B and network to campus system. | BOURNS |  | Approval of 100% CD's | Susan Marshburn | Da Lan Dinh | ----- |  | Fernando Nunez | 99 |  |  | FALSE | 600000 |  |  | Augmentation Approval | 2019-09-02 | 2019-12-31 | [8 empty] | PD&C | 0 | 1900 | 2019-03-01
2696 | 2696 |  | FALSE | ATHLETICS | Soccer Stadium Fencing (E Side) | Requesting estimate for installation of permanent fencing along east side of the UC Riverside Soccer Stadium. This may be with wrought iron or chain link (8' minimum height)- please provide cost for each option. The footprint of the area may change some from the current construction fence that is in place. Please walk through facility with Athletics to determine exact needs. Also, please include an option to order fence covering. Ken Mueller is aware of the initial needs for the project. |  |  | In coordination with Mobility Hub | Tamica Smith Jones | Joseph Erbland | Joe Erbland |  | Gerald Caraig | 3 |  |  | FALSE | 0 |  | 2014-04-10 | To be coord. with Rec Mall work | [10 empty] | PD&C | 0 | 2014 | 2019-03-01
2725 | 2725 |  | FALSE | SoB | School of Business Professional Schools Study | Complete a Detailed Project Program (DPP) planning process for the proposed School of Business Administration building. |  |  | Initial planning discussions have begun with SOBA. | Yunzeng Wang | Angela Chang | Leo Gonzalez |  | Blythe Wilson | 2 |  |  | FALSE | 350000 |  | 2016-12-15 | Develop RFQ | [10 empty] | PD&C | 0 | 2016 | 2019-03-01
2747 | 2747 |  | FALSE | PALM DESERT GRAD CTR | Heckmann Center - Landscaping (Donor Orchard) | UCR Palm Desert would like to replace the current turf grass with water-wise, sustainable landscaping. In return for the opportunity to use a “living laboratory” classroom for training, UC Cooperative Extension Master Gardener program has agreed to collaborate with UCR to revise and sustain the landscaping. The first phase will be to create an orchard to highlight UCR’s contributions to agricultural research in the Coachella Valley. The orchard will be located at the entrance to the Heckmann building, north of the walkway. UCR Physical Plant/Grounds to provide estimate for: • Project oversight • Project plan and drawings • Organic material to add to soil • Irrigation materials and installation • Edging for path • Weed cloth • Decomposed granite with stabilizer for ground cover • Decomposed granite with stabilizer for pathway • Concrete pad for art including bolting apparatus • Arbor for grapes • Flow system-fertigation • All other labor and materials other than kiosk, plant signage, turf and tree removal (current landscape maintenance vendor can remove) and plant materials and plant installation | HECKMAN ICEM |  | In Programming | Tamara Hedges | Zelda Glenn | Mike Lawrence |  | Scott Donnell | 2 |  |  | FALSE | 13800 |  | 2014-08-18 | RFQ Design | [10 empty] | PD&C | 0 | 2014 | 2019-03-01
2774 | 2774 |  | FALSE | PLANNING & BUDGET | Highlander Hall Demolition | Demolition of the Highlander Hall Building |  |  | Nearing Completion | Gerry Bomotti | TBD | Blythe Wilson |  | Scott Donnell | 99 |  |  | FALSE | 2127000 |  | 2015-01-22 | Project Close-out | 2018-08-01 | 2019-04-01 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
2829 | 2829 |  | FALSE | VC-STU.AFF. | SRC South - New Storage Building | New storage building immediately south of SRC South Pool Building; approximately 20' x 40'; one roll up door and one standard door; electrical power required - number of outlets to be defined in design; concrete walkway and door pads required; non-potable water may be required if quick couplers are not available in nearby landscaping; please see attachment for location: approximately at gridlines T and 9.4 - dotted outline of building is labeled "FUTURE STORAGE" - located immediately south of the SRC POOL EQUIPMENT BUILDING. | SRC SOUTH |  | Project is currently on-hold. | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Mihai Gavan | 2 |  |  | FALSE | 0 |  | 2015-01-23 | Coordinate with MRB Logistics | [10 empty] | PD&C | 0 | 2015 | 2019-03-01
2839 | 2839 |  | FALSE | PLANNING & BUDGET | Multidisciplinary Research Building | External financing provided for this project. Total approved budget is $150,000,000. Confirmed per CPMX and BEA#978864 Xfer Tax Exemp Comm Paper. Funding received 7/25/2016. |  |  | Certificate of Beneficial Occupancy 9.28 L1-L4. Construction ongoing on the Lower Level. | Gerry Bomotti | TBD | Jon Harvey |  | Mihai Gavan | 8 |  |  | FALSE | 156405000 |  | 2015-04-01 | Substantial Completion | 2016-07-01 | 2018-09-28 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
2868 | 2868 |  | FALSE | BAS | West Lothian Elevator Renovation |  |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 32 |  |  | FALSE |  |  | 2015-04-08 | Bidding | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
2899 | 2899 |  | FALSE | PLANNING & BUDGET | Pierce Hall Improvements | Replacement of Mechanical, Plumbing and Electrical Infrastructure | PIERCE |  | In Construction | Gerry Bomotti | TBD | Jon Harvey |  | Dave Bomba | 10 |  |  | FALSE | 38560000 |  | 2015-08-06 | Abatement | 2019-01-01 | 2019-12-07 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
2900 | 2900 |  | FALSE | PLANNING & BUDGET | Batchelor Hall Systems Renewal | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | BATCHELOR |  | Conducting interviews of researchers to assess relocation needs | Gerry Bomotti | TBD | Sharyl Murdock |  | Rowan Reid | 6 |  |  | FALSE | 18179000 |  | 2015-12-15 | CM at Risk Selection | 2019-09-01 | 2021-11-01 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
2916 | 2916 |  | FALSE | CAP.PROG. | Solar Greenhouse | Construction of a solar powered greenhouse. |  |  | Requires augmentation | TBD | Sharyl Murdock | Matt Barth |  | Scott Donnell | 99 |  |  | FALSE | 174000 |  | 2015-08-04 | Construction | 2019-03-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
2952 | 2952 |  | FALSE | CAP.PROG. | Pierce Hall Interiors | Pre-Planning Study: provide pre-planning services to support the Pierce Hall Interior project (950532) including architect, lab planner, cost estimator, MEP and Electrical engineer, and staff recharge. | PIERCE |  | In Construction | TBD | Sharyl Murdock | Jon Harvey |  | Dave Bomba | 19 |  |  | FALSE | 23308000 |  | 2015-09-11 | Completion of phase one 12/7/19 | 2019-01-02 | 2021-04-01 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
2970 | 2970 |  | FALSE | CAP.PROG. | ADA Improvements/Transition Plan - Phase 2 | ADA Compliance 1 - project corrects ADA non-compliance issues in multiple locations across campus per attached Major Cap Approval form (9/17/15) |  |  | In Construction | TBD | Sharyl Murdock | Blythe Wilson |  | Dave Bomba | 17 |  |  | FALSE | 2842000 |  | 2015-12-02 | Complete Construction | 2018-09-26 | 2019-06-30 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
2974 | 2974 |  | FALSE | SOM | SOM Research Building - 1st Floor Fit-Out | Buildout the 1st Floor of School of Medicine Research Building, a space of approximately 17,600 square feet. The construction includes wet laboratories, laboratory support spaces, offices and related support space. Work consists of, but not limited to the following: demolition of existing improvements, addition/alterations of walls, installation of new fume hoods, sinks, safety showers and eyewash stations, alterations/additions to the mechanical, electrical, plumbing, fire life safety, fire suppression, telecommunication and audio/video systems, as specified in the Construction Documents. |  |  | Close-out documents | Deborah Deas | Brandon Barbosa | Blythe Wilson |  | Mihai Gavan | 99 |  |  | FALSE | 9600000 |  | 2015-10-30 | Final Completion / NOC | 2017-10-01 | 2018-10-01 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
3005 | 3005 |  | FALSE | CAP.PROG. | Batchelor Hall Interior Improvements | Renovate 110,091 s.f. facility built in the 1960 due to building systems anticipated end of life, and desire to support research. The Batchelor Hall Renewal and the Batchelor Hall Interior Project proposes to: Replace building (laboratory) exhaust fan units and main distribution due to inefficiency and equipment end of life Replace building air handling units, chilled water pumps and main distribution due to equipment end of life and improved air quality Replace building plumbing mains and water treatment system due to equipment end of life Install a new Building Management System to allow more efficient energy use and monitoring Upgrade the building fire suppression mains and fire life safety system Upgrade the building elevator system Upgrade building electrical feeder and main distribution in order to support modern research needs Upgrade non compliant restrooms to meet accessability requirements Construct a new laboratory equipment room Perform some upgrades to common areas spaces | BATCHELOR |  | Conducting interviews of researchers to assess relocation needs | TBD | Sharyl Murdock | Sharyl Murdock |  | Rowan Reid | 14 |  |  | FALSE | 8837000 |  | 2016-02-02 | CM at Risk Selection | 2019-09-01 | 2021-11-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3052 | 3052 |  | FALSE | SOM | SOM Trailer Expansion | Replace the (2) modular units with one 96' x 60' building and provide access from the SOM-ED building via concrete ramp; Re-vamp the entire site for accessibility. Signed Major Cap Approval for $150k augmentation received 10/25/17 - total project $2,250,000. |  |  | Completing Change Orders | Deborah Deas | Brandon Barbosa | Sharyl Murdock |  | Dave Bomba | 99 |  |  | FALSE | 2250000 |  | 2016-03-07 | Complete Change Orders | 2017-08-01 | 2018-02-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3060 | 3060 |  | FALSE | CHASS | CHASS Intl N. - Paint 3rd Floor | Paint and patch the following CHASS INTN rooms to existing color: 3036 3038 3042 3046 3050 3049 3047 3033 3033B 3025 3021 3019 3015 3013 3011 3002 3008 3012 3014 3016 3018 3020 3022 Hallway outside of 3033 Hallway to main entrance to floor Hallway outside 3005 | CHASS INT N |  | Project on Hold | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2016-05-20 | On Hold | [10 empty] | PD&C | 0 | 2016 | 2019-03-01
3064 | 3064 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Botanic Gardens Basin Silt Removal | We need to have the Botanic Gardens de-silt basin cleaned out. It is probably around 500+ yards of soil that has to be removed. It also requires special permitting to do. Work will require regulatory permits and agency approvals -PSA has been issued to | BOTAN INFO C |  | In Design | Susan Marshburn | Da Lan Dinh | Toshio Ishida |  | Dave Bomba | 44 |  |  | FALSE | 110000 |  | 2016-04-20 | Waiting for basin to dry out | 2019-07-01 | 2019-07-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3101 | 3101 |  | FALSE | SoB | DM-Anderson Hall S&N - Maint+Restrm Remodel | Under 2014 Deferred Maintenance Funding Program, SoBA has been approved for interior upgrades to be completed up to $65,00. We were originally approved for $75,000 however, per Scott Donnell, $10,000 had already been used. We have requested a list of expenditures for SoBA upgrades under this $10,000. The following items need to be completed under this 2014DM funding in the priorities listed: 1. Anderson Hall South Women’s and Men’s Restrooms Remodel Requirements: Floor and wainscot tile require replacement and/or re-grouting, casework and associated lavatory fixtures and counter tops require refurbishment/placement, restroom partitions require re-painting/replacement. 2. Anderson Hall North Women’s and Men’s Restrooms – repair and touch up areas where ADA compliance changes were made. 3. Anderson Hall North & South Stairway Requirements: All stairways shall be reviewed for compliant contrasting top and bottom stair-tread indicators and all missing or loose anti-slip tread applications be repaired and/or replaced. Any other safety items as may be noted. Retile or carpet as needed. 4. Anderson Hall South Interior Painting to Common areas, both levels: Interior wall surfaces require patching and painting. 5. Anderson Hall North Interior Painting to Common areas, both levels and conference room 021: Interior wall surfaces require patching and painting. 6. Faculty Suite (Rm 158) – match common area tile (size of mud/dirt mat) to replace dirty carpet when first enter room 158. 7. Dean’s Suite (Rm 162) – new carpet. |  |  | Need confirmation department wishes to cancel | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 3 |  |  | FALSE | 65000 |  | 2016-05-09 | To be cancelled by Client | [10 empty] | PD&C | 0 | 2016 | 2019-03-01
3104 | 3104 |  | FALSE | PALM DESERT GRAD CTR | Palm Desert Campus Access Evaluation | Study the UCR Palm Desert Campus for ADA compliance. Including interior accessibility, paths of travel from accessible parking spaces to primary building entrances, and to and from public transportation. | HECKMANN PH2 |  | In Programming | Tamara Hedges | Zelda Glenn | Zelda Glenn |  | Scott Donnell | 1 |  |  | FALSE | 22000 |  | 2016-05-12 | Design | 2019-10-01 | 2019-11-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3110 | 3110 |  | FALSE | PLANNING & BUDGET | Ag Ops Cell Tower - New | Verizon is proposing a new cell tower (water-tower) to be installed in the back lot of the AgOps Corporate Yard. This project will be at the sole cost of Verizon. |  |  | Project is not funded/never routed to the Dispatcher. 90% CD's completed. | Gerry Bomotti | TBD | Marianne Valenti |  | Yvonne Lujan | 99 |  |  | FALSE | 0 |  |  | License Agreement Final Review |  | 2019-07-01 | [8 empty] | PD&C | 0 | 1900 | 2019-03-01
3119 | 3119 |  | FALSE | CAP.PROG. | Plant Growth Environment Facility | In April, work will begin on the $22 million Plant Growth Environments Facility near Parking Lot 9 directly east of the East Campus, and Eucalyptus Drive. The 30,300-square-foot facility will feature a combination of greenhouse and greenhouse support spaces. This will be the first new greenhouse building constructed in 50 years and will replace older facilities with high-quality, modern space to support plant research that allow for better environmental control. The project is expected to be completed by September 2020. |  |  | Design Build Proposal Awarded, design and construction contract execution has started | TBD | Sharyl Murdock | Michelle Baniqued |  | Rowan Reid | 5 |  |  | FALSE | 1800000 |  | 2016-05-25 | Design-Build Proposal Evaluation | 2019-04-01 | 2020-08-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3120 | 3120 |  | FALSE | CAP.PROG. | Arts Walk Sculpture (Ext Campus Art Project) | Sculpture design concept - hiring a consultant to revise an artist design concept for a proposed outdoor art piece to be placed between the Arts building and the CHASS Interdisciplinary buildings. |  |  | A&E and CAS in discussions w/Artist re: design. | TBD | Sharyl Murdock | Uma Ramasubramanian |  | Jason Espinoza | 4 |  |  | FALSE | 1000000 |  | 2016-05-26 | Complete Construction | 2019-03-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3175 | 3175 |  | FALSE | CAP.PROG. | DM-Chilled Water Coils Multiple Buildings | Replace multiple leaking/degraded cooling coils across campus to prevent complete shutdown of building air handlers during the hot summer months. Buildings include: Student Services, Chemical Sciences, Genomics, Psychology, Entomology and MSE. |  |  | In Construction | TBD | Sharyl Murdock | Melissa Garrety |  | Scott Donnell | 99 |  |  | FALSE | 1090000 |  | 2016-10-11 | Complete Construction | 2019-01-01 | 2019-03-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3195 | 3195 |  | FALSE | PLANNING & BUDGET | North District Development, Phase-1 | Development of UCR North District Development, located near the housing development north of Linden St. |  |  | Phase 1 - Student Housing - 8/1/2020. | Gerry Bomotti | TBD | Raoula Amescua |  | R.Amescua/D.Hecht | 99 |  |  | FALSE | 2507658.71 |  | 2016-10-26 | Reg. Apprv'l-Business Terms&Fin. | 2019-07-01 | 2021-08-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3218 | 3218 |  | FALSE | CNAS | Ag Ops - Demo Structures | Demolition of 15 structures, including hazardous materials cleanup, electrical reconnection of services as needed, UST removal as needed, relocation of ATT riser. |  |  | In construction Additional funding is not expected. | Kathryn Uhrich | Deborah McWilliams | Deborah McWilliams |  | Scott Donnell | 99 |  |  | FALSE | 316739 |  | 2016-10-19 | Complete Construction | 2018-07-01 | 2019-04-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3224 | 3224 |  | FALSE | BCOE | Bourns - Door Access Control | Replace outdated failing, and unsupported Identicard card reader system with campus approved Hirsch system at all existing locations in Bourns Hall B-wing at a minimum; inclusion of card readers in Bourns A-wing is also desired if possible. Immediate work is optimal since the building is currently under construction and many walls, ceilings, wiring, etc are currently exposed. Work to be done via surplus funds from BCOE 950534. AVC is putting together the costs and scope via meetings with Maggie/ Pat/ and John C. | BOURNS |  | Programming | Christopher Lynch | Maggie Souder | Margaret Souder |  | Fernando Nunez | 4 |  |  | FALSE |  |  | 2016-11-14 | Create SOW and Transfer funds | 2019-09-01 | 2019-11-29 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3228 | 3228 |  | FALSE | CNAS | Retrofit Screenhouse to Greenhouse | Retrofit screenhouse to greenhouse. Replace 6 current screen panels with plastic greenhouse walls Install 2 HVAC systems in the separate rooms. Location can be discussed with Greg Greer | RUBIDOUX SCR |  | In Design | Kathryn Uhrich | Deborah McWilliams | Cheryl Gerry, D. McWilliams |  | Scott Donnell | 1 |  |  | FALSE | 780000 |  | 2016-12-06 | Bidding | 2019-08-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3233 | 3233 |  | FALSE | CAP.PROG. | Mobility HUB Central Campus Linkages | Proposed project to construct a Mobility Hub for new and existing bus routes servicing UC Riverside’s Central Campus Neighborhood near Lot 19. The project includes intersection improvements at Aberdeen and N. Campus Drive; N. Campus Drive street conversion into a pedestrian mall; and pedestrian connections from Linden Street to a gateway plaza at N. Campus Drive. |  |  | In bidding | TBD | Sharyl Murdock | Jaime Enghbrecht |  | G. Caraig/J. Franklin | 1 |  |  | FALSE | 16011000 |  | 2016-12-16 | Award Contract | 2019-04-01 | 2020-01-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3234 | 3234 |  | FALSE | CAP.PROG. | UC Intellicenter 2nd Floor TI | Name for project is UC Intellicenter 2nd Floor Tenant Improvements. Build out of approximately 50,000 sq.ft. of TI space. The area will be devided between a the school of medicine's proposed learning space, and the UCOP administrative offices a portion of which will be occupied by to be determined UC admin. |  |  | In Construction | TBD | Sharyl Murdock | John White |  | Fernando Nunez | 2 |  |  | FALSE | 10000000 |  | 2016-12-21 | Complete Construction | 2018-11-05 | 2019-03-29 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3237 | 3237 |  | FALSE | SoB | Anderson Hall N. Access Imp. | ADA handrails installation at walkway and ramp on the East sidewalk by the bench of Anderson north, down the steep ramp leading to Anderson South. We have been working with Shelly Frohrip from HR and Mary-Alice Avila of A&E on this so they will have some information regarding the purpose. 11/15/17 The handicapped parking and POT are now included. Project approved, waiting for funding. | ANDERSON 1 |  | In Bidding | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 5 |  |  | FALSE | 150000 |  | 2016-12-19 | Award Contract | 2019-04-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3255 | 3255 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) Humanities - Upgrade EMS | Humanities HVAC - upgrade Energy Management System per approved Century Bond funded project (approval attached). Project: 957405 P5498 Budget $200,000 Accounting determined this is capitalizable Accounting determined not capitalizable | HUMANITIES |  | In Close-out | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Fernando Nunez | 6 |  |  | FALSE | 202000 |  | 2017-02-10 | Complete Close-out | 2018-10-01 | 2019-01-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3270 | 3270 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Chapman Hall - Replace HVAC System | Chapman Hall - HVAC equipment and controls per approved Deferred Maintenance Project List FY17. | CHAPMAN |  | In Design | Susan Marshburn | Da Lan Dinh | Fernando Nunez |  | Scott Donnell | 8 |  |  | FALSE | 595819 |  | 2017-03-07 | Bidding | 2019-07-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3271 | 3271 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Life Sci/Spieth Hall Elevator Renewal | Scope of work includes the number 3 and 4 elevators of Spieth Hall. Project budget is $344,898.00. Estimated construction cost is $250,400.00. |  |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 9 |  |  | FALSE | 345000 |  | 2017-03-07 | Final Approval of CD's | 2019-07-01 | 2019-12-31 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3272 | 3272 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY17) - Athletic/Dance elevator renewal | Project budget is $219,371.00. Estimated construction cost is $169,020.00. | ATH DANCE |  | In Design | Susan Marshburn | Da Lan Dinh | Scott Donnell |  | Fernando Nunez | 10 |  |  | FALSE | 220000 |  | 2017-03-07 | Final Approval of CD's | 2019-07-01 | 2019-12-31 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3275 | 3275 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Fiber Optic Infrastructure Upgrade | Repair, replace and upgrade the fiber optic infrastructure network that includes 50+ buildings across campus. Also includes work to main hubs, sub hubs and make available spare fiber for future utilization. |  |  | Going into bidding | Susan Marshburn | Da Lan Dinh | ----- |  | Daneca Stevens | 2 |  |  | FALSE | 643750 |  | 2017-04-12 | Award Contract | 2019-06-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3280 | 3280 |  | FALSE | CHASS | Athletics Dance Bldg Repairs | Replace bleacher seating. Replace/repair broken entry doors (ADA) Upgrade/install projection/sound AV system Replace curtains Reseal glass Remove metal bar over window Replace locks on cabinets | ATH DANCE |  | On-hold/Funding | Milagros Pena | Cindy Williams | Paul Richardson |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2017-05-31 | Department Approval/Funding | [10 empty] | PD&C | 0 | 2017 | 2019-03-01
3286 | 3286 |  | FALSE | BAS | Falkirk Apartments Seismic Improvements | For structural improvements of the property. Task #1: provide Schematic Design Documents, Design Development Documents and a Professional Cost Estimate for the anticipated alterations. | FALKIRK 1 |  | Awaiting revised proposal from Miyamoto | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 9 |  |  | FALSE | 0 |  | 2017-03-29 | Complete Design | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3293 | 3293 |  | FALSE | CAP.PROG. | USDA Head House - Public Restroom | Provide an accessible public restroom facility in or adjacent to the USDA Head House Building in Ag Ops. Restroom will serve individuals and groups touring the UCR and USDA Citrus Facilities. Three options have been proposed, and need to be considered and evaluated to recommend a feasible solution for USDA. The work would be managed and paid by USDA, including the design, bidding and construction. UCR staff needs to review the proposed plans and specifications per the agreement with USDA, and provide the review, inspection and approvals. The USDA representative is Marylou Polek. | GERMPLASM |  | Pending Lease | TBD | Sharyl Murdock | Mary Lou Polek |  | Scott Donnell | 11 |  |  | FALSE | 0 |  | 2017-05-22 | USDA Scope & Design | [10 empty] | PD&C | 0 | 2017 | 2019-03-01
3300 | 3300 |  | FALSE | BCOE | R'Garden - Solar Installation | Electrician to do the following wiring of our solar panels and inverters out at the R’Garden at UCR. The H model cyboinverter to be used powers the lower heating element of the water heater. The thermostat of the lower heating element must then be set to be higher than the upper heating element. The two output lines are to be connected to an AC switch or switchable AC outlet and the lower element water heater. |  |  | Work to be inspected by A&E. | Christopher Lynch | Maggie Souder | Arvin Tam |  | Scott Donnell | 2 |  |  | FALSE | 0 |  | 2017-05-03 | To be disassembled in June 2019 |  | 2019-06-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3315 | 3315 |  | FALSE | BCOE | Bourns B144 - Lab Safety Improvements | Incorporate life safety improvements to research lab. Provide additional protection for Pyrophoric Gases. Provide sprinkler protection inside the pyrophoric gas cabinet. Provide an Automatic shutdown device for pyrophoric gas flow when activated by interlocks tied into fire sprinkler. Provide a remote manual shut down device of pyrophoric gas outside the gas cabinet. Provide audible and visible alarm detection and monitoring for toxic and highly flammable gases including diborane, germane, ammonia and hydrogen gases Applicable references on the above are NFPA 55 (Compressed Gases Code) and NFPA 45 (Standard on Fire Protection for Labs using Chemicals). | BOURNS |  | Need to confirm Dept. funding commitment | Christopher Lynch | Maggie Souder | Jianlin Liu |  | Scott Donnell | 5 |  |  | FALSE |  |  | 2017-05-23 | Confirm Dept. Commitment/Funding | [10 empty] | PD&C | 0 | 2017 | 2019-03-01
3319 | 3319 |  | FALSE | CAP.PROG. | Student Success Center | Student Success Center - classrooms, advising, and student life programs using a combination of AB94 and student fee reserves. Associated with planning plant activity 958056 and plant account 950512. Preliminary plans proposed for July 2018. |  |  | In Design Build competition. | TBD | Sharyl Murdock | Michelle Baniqued |  | Mihai Gavan | 13 |  |  | FALSE | 3607000 |  | 2017-06-01 | Award Contract | 2019-09-01 | 2021-05-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3326 | 3326 |  | FALSE | VC-RED | Genomics 1120A - Power & UPS | Request submitted on behalf of Thomas Girke's email: I am contacting you in my role as Director of UCR's HPC Center under RED. The server room we are using in the Genomics Building (Room 1120A) is in urgent need of additional electrical power to support the current peak usage and future growth of the research computing infrastructure located in this room. After consulting with UCR electricians (Robert Corey and Dan Martin) we were recommended to initiate a Project Triage Request for this building upgrade. Currently, all servers are on a UPS unit that is also maxed out. In addition, there is a backup generator outside of the building to assure uninterrupted power. For the upgrade we would like to evaluate two options: Additional electrical power line(s) plus an additional UPS unit of similar size as the current one. Additional electrical line (without UPS) providing at least 60% of the amount of power we are currently using for computing hardware in this room (~120Amp of 480V). As rough timeline I would like to propose the following: Planning stage: May/June 2017 Installation and completion: July/Aug 2017 | GENOMICS |  | In Design | Michael Pazzani | Laura Manor | T.Girke, L.Manor, D.McWilliams |  | Dave Bomba | 3 |  |  | FALSE | 15000 |  | 2017-06-13 | Approval of HVAC design | 2019-07-01 | 2019-07-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3341 | 3341 |  | FALSE | SoB | Anderson N & S - Exterior Painting | EXTERIOR PAINTING: Please see Karen Henry or Tim DeBolt for direction in painting exterior items around Anderson Hall North/South as follows: 1. Update Paint on exterior Window trim of both buildings. 2. Update Paint on lanterns and light poles 3. Fix plaster on building walls that is peeling off. |  |  | Need confirmation department wishes to cancel | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 1 |  |  | FALSE | 0 |  | 2017-07-18 | To be canceled by Client | [10 empty] | PD&C | 0 | 2017 | 2019-03-01
3345 | 3345 |  | FALSE | SoB | Anderson N & S - Landscaping | DESIGN SVC & LANDSCAPE Construction request as follows for updated CURB APPEAL of Anderson North/South: 1. Roses Garden in middle of Stair landing/court to be removed and replaced with Grass 2. Add Large Planters (Metal or Cement) with Citrus Trees (either Kumquat/Lemon/Orange/Etc) on ledges that are at top section of front steps to deter skateboarders from jumping off of these ledges. 3. Remove dead trees on North and south ends of front lawn 4. Remove plants around granite sign in front lawn and replace with grass 5. Remove flowers and grass at both corners of front lawn around Citrus Trees and replace with DG and low growing flowering plants. 6. Pull all Ivy and crown vetch and add Pavers to East/Back side of Anderson Hall within landscaped/planter areas where ADA walkway runs and replace with nice picnic tables to include umbrellas and/or lounge seating around Anderson North for students. 7. Add DG in all areas where space is open/available surrounding outdoor seating area in back of building. 7. Remove all hedges surrounding alcove/arched areas along buildings. |  |  | On hold until ADA path of travel is completed | Yunzeng Wang | Angela Chang | Angela Chang |  | Dave Bomba | 6 |  |  | FALSE | 0 |  | 2017-07-18 | Completion of 3237 | 2019-07-01 | 2019-07-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3354 | 3354 |  | FALSE | BAS | Lot 4/Barn Area ADA Improvements | Lot 4/Barn Area ADA Improvements - The proposed project will relocate an existing crosswalk that is not ADA compliant and provide path of travel improvements and additional ADA parking capacity in Parking Lot 4. The existing crosswalk located at West Campus Drive and Parking Lot 4 (north) was identified in the Draft ADA Transition Plan to be out of compliance. A Pedestrian Safety Study by Fehr & Peers completed in June 2008 identified the relocation of this crosswalk to approximately 100 feet east to provide a more visible, safe, pedestrian crossing. To increase pedestrian safety further, the crosswalk will be designed as a speed table. Additionally, Transportation and Parking Services proposes to create additional ADA parking spaces in Parking Lot 4 that exceed the required number, with hardscape and path of travel improvements that will connect to the new crosswalk. The improved crosswalk will correct required path of travel deficiencies from a parking lot that provides access to numerous publicly accessible buildings, as well as allow the Barn Expansion project to obtain Division of State Architect (DSA) approval once construction is completed. The funds to complete the crosswalk replacement will be requested from Campus ADA funds. Parking Lot 4 improvements will come from will come from TAPS. Although this project supports the Barn Renovation, its conception and need is not tied to the Barn project. The crosswalk improvements and additional ADA parking is needed to meet our ADA parking requirements and serve the growing demand on campus. This project is desired regardless of the Barn Renovation project. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Fernando Nunez | 16 |  |  | FALSE | 50000 |  | 2017-08-15 | Updated Proposal & Cost Estimate | 2019-07-01 | 2019-09-27 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3363 | 3363 |  | FALSE | CHASS | DM(17-19) CA Photo Museum HVAC | Replace current HVAC with new Temp/Humidity control system. The system must adhere to Museum standards of Temp 70 +-3 and humidity 50 +-5. THIS IS A CRITICAL REQUEST. We are currently not able to borrow work from other museums due to the inconsistent numbers we are experiencing with temperature and humidity. | CA MUS PHOTO |  | In Close-out | Milagros Pena | Cindy Williams | Emily Papavero |  | Scott Donnell | 4 |  |  | FALSE | 1261000 |  | 2017-08-23 | Complete Close-out | 2018-03-01 | 2019-02-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3366 | 3366 |  | FALSE | CAP.PROG. | Genomics Sdwk Rpr-Drainage Impr | Genomics Accessibility Improvements - The proposed project will create an accessible sidewalk connection from the Genomics Building to the University Lab and University Office Building. Currently, there is no accessible north sidewalk linkage east of the Genomics Building. The project will demolish and replace approximately 300 square feet of asphalt to bring it up to grade. Two ADA ramps will be added to sidewalk extensions of approximately 300 square feet that connect across a driveway. Existing landscaping and irrigation will be removed and replaced. No trees will be impacted by this work. |  |  | In Funding | TBD | Sharyl Murdock | Jaime Engbrecht |  | Dave Bomba | 16 |  |  | FALSE | 0 |  | 2017-11-16 | Secure Funding | 2019-04-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3367 | 3367 |  | FALSE | CNAS | Field 16 Greenhouse Demo & Replacement | Replace GH1 and GH2 with a greenhouse from the Greenhouse Megastore. Conduct geotechnical investigation, prepare drawings and conduct asbestos and lead sampling. |  |  | In Construction | Kathryn Uhrich | Deborah McWilliams | Sue Lee, D. McWilliams |  | Dave Bomba | 2 |  |  | FALSE | 300000 |  | 2017-09-15 | Complete Construction | 2019-01-30 | 2019-07-28 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3376 | 3376 |  | FALSE | BAS | West Lothian Roof Replacement Design | Provide Schematic Design, Design Development and professional cost estimate to replace the existing single-ply membrane roof system on the Lothian West residence hall wings plus Common Area applications. Existing roofing is past its useful life and starting to experience multiple leaks that are damaging living spaces below. Design effort should select the most appropriate roof material for this roof plan. The intent is to design this year (alongside the Lothian East design) and construct immediately following the Lothian East roof replacement. | LOTHIAN HALL |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 19 |  |  | FALSE | 0 |  | 2017-09-28 | Bidding | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3382 | 3382 |  | FALSE | BAS | West Lothian Restroom & Common Area Design | Provide professional design services to complete Schematic Design, Design Development and cost estimate for all West Lothian restrooms, hallways and Common Area facelift. Basis of Design is recently completed finishes in the Lothian East Seismic Retrofit project. Note, seismic work not required here, only restroom fixtures and new finishes for areas described. The intent is to design this year and construct next year. Request Short Description: Opening project request to Blythe Wilson, John White, Chris Pillen, Bob Williams, Tricia Thrasher, Jocelyne Nguema, Beiwei Tu. | LOTHIAN HALL |  | Project pushed to 2021 | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | D.Hecht/J.Franklin | 31 |  |  | FALSE | 0 |  | 2017-09-29 | Project pushed to 2021 | [10 empty] | PD&C | 0 | 2017 | 2019-03-01
3383 | 3383 |  | FALSE | BAS | W Lothian Air Handler Replacemt | Existing air handler equipment in West Lothian is original to the building and past its service life. Provide HVAC professional services to develop options for Air Handler replacement that meet UC Carbon Neutral 2025 goal. Each option analysis should include pros and cons for energy consumption, reliability, serviceability and system installation cost projections. At least one option should explore potential conversion to individual package units as practical. | LOTHIAN HALL |  | Complete Design/Bidding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 20 |  |  | FALSE | 883000 |  | 2017-10-03 | Complete Design/Bidding | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3385 | 3385 |  | FALSE | VC-STU.AFF. | SRC North Gym Replace Interior Lights | Replace old technology sodium vapor light fixtures in SRC North Gymnasium with new technology LED light fixtures. Some flexibility available in the schedule. Selected vendor will need to phase work to minimize the effect on SRC operations and programming. | SRC NORTH |  | Bidding | Brian Haynes | Cathy Eckman | Lindy Fenex |  | Fernando Nunez | 1 |  |  | FALSE | 360000 |  | 2017-10-31 | Award Contract | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3390 | 3390 |  | FALSE | CNAS | Field 11C-D CVC Screenhouse | In order to protect, preserve, and promulgate the diversity of all 1038 cultivars and species of citrus and related genera in the Citrus Variety Collection (CVC), CNAS proposes a 3-Phase Project on Field 18-C (Ag Ops). **Phase 1: In Phase 1, we propose a CEQA review of a viable site (up to 6-acres of available land has been identified for potential development in Field 18), a full site study for a 3-acre parcel, site development for the initial one-acre parcel expected to be developed, the procurement and installation of one or two Citrus Under Protection (CUP) systems (which would include a vestibule and air curtain each) that would screen/protect up to an acre of newly planted trees propagated from registered budwood and grown in the ground. This initial protective system is expected to receive APHIS-approval as an ACP Exclusion Certified facility. In addition, the site would also house a prefabricated storage unit for tools and equipment. **Phase 2: In Phase 2, we propose site development for two additional acres of property, upon which we plan to construct one or two new Research/Instructional Screenhouses / Greenhouses (including vestibles) covering up to two acres and potentially adding an additional Equipment Storage / Outbuilding. **Phase 3: In Phase 3, we propose replacing the initial temporary CUP system(s) with a permanent Screenhouse / Greenhouse. Depending upon existing needs and available funding, we may also expand scope in Phase 3 to comprise additional facilities, including a possible Outreach Center. **Using a traditional delivery method (design, bid, build), this 3-Phase project is anticipated to provide for a permanent facility to preserve the CVC and support citrus-related research. |  |  | Conceptual Design | Kathryn Uhrich | Deborah McWilliams | Tracey Kahn, D. McWilliams |  | Scott Donnell | 3 |  |  | FALSE | 150000 |  | 2018-01-08 | CEQA | 2019-12-01 | 2020-02-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3392 | 3392 |  | FALSE | BAS | Bicycle Master Plan Study | Bicycle Master Plan Study. This CPMS project is for the funding and creation of a Bicycle Master Plan Study for the UCR Campus. It is not for a specific capital project. |  |  | Pre-Programming | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Jerrod Walters | 33 |  |  | FALSE | 115000 |  | 2017-11-13 | Funding | [10 empty] | PD&C | 0 | 2017 | 2019-03-01
3393 | 3393 |  | FALSE | CAP.PROG. | South Neighborhood Dist. Study | South Neighborhood District Study per discussions with the Provost/VCPB, July 2017. The South District Planning Study needs to provide guidance for future development in the South District that is inclusive of: **University aspirations to develop the South District to define the campus’ presence along the adjacent freeway (CA-60/215). **Development capacity, optimal building heights and conceptual massing presented both in metrics and a three dimensional format. **Broad parking strategy to meet the needs of the district in alignment with the campus’ overall parking management strategy and alternative transportation solutions. **High level understanding of infrastructure needs (electrical, domestic, fire and storm water, sanitary sewer, building heating and cooling) to meet the needs of the campus’ desired development capacity for district. **Pedestrian and vehicular connectivity. **East and South Campus Drive improvements |  |  | In Close-out | TBD | Sharyl Murdock | Uma Ramasubramanian |  | Fernando Nunez | 15 |  |  | FALSE | 309000 |  | 2017-11-15 | Receive Study Reports | [10 empty] | PD&C | 0 | 2017 | 2019-03-01
3395 | 3395 |  | FALSE | CAP.PROG. | Recreation Fields Replacement | The RUSD STEM Academy is going to be situated on the site where the sports fields are over by Glen Mor 1 and as such there will be a new project to construct new fields adjacent to Parking Lot 30 (west campus). This is a campus-sponsored (Chancellor) project. The new fields will need turf, drainage, irrigation and accessible parking with cost options for lighting, rest rooms (either built or portable, modular or ?), and possibly an equipment storage building. |  |  | Third party cost estimator needed. | TBD | Sharyl Murdock | Tameesha Hayes |  | Daneca Stevens | 20 |  |  | FALSE | 0 |  | 2017-12-03 | [11 empty] | PD&C | 0 | 2017 | 2019-03-01
3396 | 3396 |  | FALSE | ITS | C&C Rear Patio Tables/Shade | Installation of new exterior concrete slab and patio cover at the Computing and Communications Modular Buildings. The existing site will be cleared of all landscape to provide clear area to install concrete slab and address any grade/drainage issues. The addition of a proposed permanent patio cover is to be installed with full electrical options (lights, outlets, ceiling fans) to provide shade for future events and exterior lunch area. Shrubs along the street at the East side of the area are to be removed to provide a vendor/service ramp for events with the inclusion of lighted concrete seating within the space. | ITS CENTER |  | In Programming | Danna Gianforte | Shelley Gupta | Sheila Mabee |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2017-11-16 | Complete Project Study | [10 empty] | PD&C | 0 | 2017 | 2019-03-01
3397 | 3397 |  | FALSE | BAS | Dundee Residence Hall and Glasgow Dining | (Lot 22/Dundee-Glasgow) A newly proposed student housing development, including a single phase 760-bed residence hall and an 830-seat dining facility located on the existing Parking Lot 22 site south of Linden Street. The project is anticipated to be completed by Fall/Winter 2020. Funding for predevelopment activities including CEQA and staff augmentation to be determined. | ABER INVER |  | In Construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Raoul Amescua | 36 |  |  | FALSE | 1120000 |  | 2017-11-21 | Complete Construction | 2019-01-01 | 2020-09-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3401 | 3401 |  | FALSE | CAP.PROG. | SOM Clinical Skills & Simulation Suite | On behalf of central campus, complete a study to determine feasibility of providing an SOM simulation center and instructional space on the ground floor of Orbach Library and potential re-use of some of the released SOM Education ground floor. Fund source will be identified by central campus. Sponsor: Jeff Kaplan PM: Mihai Gavan | ORBACH LIB |  | P funding received on 2.20. Proceeding with design. | TBD | Sharyl Murdock | Mihai Gavan |  | Mihai Gavan | 18 |  |  | FALSE | 1530020 |  | 2017-12-03 | Complete SD/DD phase. | 2019-09-01 | 2020-12-01 | [8 empty] | PD&C | 0 | 2017 | 2019-03-01
3403 | 3403 |  | FALSE | BAS | Parking Lot 23 Addition | Parking Lot 23 Expansion - The goal of the project is to add additional parking capacity to Parking Lot 23 to serve that area of the campus. Current parking capacity in this area will be impacted by the closures of Lot 22 and Crest Housing parking area. Additional capacity will be need for employee parking. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Daneca Stevens | 14 |  |  | FALSE | 92000 |  | 2018-05-17 | Design | 2019-07-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3407 | 3407 |  | FALSE | ATHLETICS | Athletics Media Room | We are looking to finish a room in the South Building at the Riverside Sports Complex. The current scope includes concrete floor laydown, drywall, electrical upgrade, flooring (carpet), HVAC (small single unit) and addition of ceiling for the space. An initial estimate and walkthrough is needed to determine the funding needs, project scope, and timeframe for execution. A more detailed estimate will be needed when determined that the project approval would proceed to the next steps. | S LCKRM/CONC |  | In Programming | Tamica Smith Jones | Joseph Erbland | Johnathan Jensen |  | Fernando Nunez | 2 |  |  | FALSE | 0 |  | 2018-08-23 | Create SOW | 2019-09-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3408 | 3408 |  | FALSE | ATHLETICS | Harrison Field Netting | Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | SOFTBALL STG |  | Per department: Project is on hold until further notice. | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Fernando Nunez | 99 |  |  | FALSE | 0 |  | 2018-01-23 | On-Hold by Cust Until Further No | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3411 | 3411 |  | FALSE | BAS | MRB Café Buildout & MS&E Loading Dock Mods | MRB1 CAFE and SERVICE YARD INTERIOR FIT-OUT: provide design and construction services to build out the interior of the MRB1 Café shell and modify the MS&E Service Yard to accommodate the café deliveries and trash movement. This CPMS Request is to combine and replace previously approved CPMS #3378 and #3398 into one project as requested by A&E. Please note that the IRT Job walk has already been completed. Intent is to design in FY'17/18 and construct in FY '18/19. Opening to coincide with the MRB1 facility turnover. Food service equipment will be Owner Furnished on a separate UCR Purchase Order. Note that the MRB1 Café shell construction is provided by the separately funded MRB1 project, construction drawings for this shell space are attached in CPMS. | MAT SCI ENGR |  | In construction | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Mihai Gavan | 1 |  |  | FALSE | 793000 |  | 2018-02-05 | Complete Construction | 2018-11-19 | 2019-04-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3413 | 3413 |  | FALSE | LIBR | Rivera Libr Gender Incl Restroom | Convert existing non-ADA multi-stall women's restroom to compliant ADA gender inclusive restroom. The project also involves the conversion of an existing non-ADA men's restroom to women's compliant ADA restroom. | RIVERA LIB |  | Need design | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | Dave Bomba | 3 |  |  | FALSE | 0 |  | 2018-03-26 | Code and policy compliance | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3415 | 3415 |  | FALSE | SoB | Anderson South Renovation | Per the sketched drawings that Dave Bomba was provided, please provide a proposal of what it would take to renovate Anderson South as follows: **1. Remove 1st Fl South side of Corridor wall and doors between 102 suite entrance and 106 suite entrance as well as adjoining walls within 102C. **2. Create a closet/wall, ideally, behind the existing door of the 102 Entrance running to the wall shared by 102A to include the best location for a door. Essentially, enclosing the window of 102, if possible. **3. Creating a closet under the stairwell between 1st floor and basement level, having entrance door flush with the bottom step of the stairwell. **4. Remove the West wall and door framing of room 001A, leaving an open look and no corridor in suite 001. | ANDERSON 2 |  | In Funding | Yunzeng Wang | Angela Chang | Laurie Gustafson |  | Dave Bomba | 4 |  |  | FALSE | 24700 |  | 2018-02-26 | Complete Plan Check | 2019-05-01 | 2019-07-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3421 | 3421 |  | FALSE | BAS | A-I Boiler Replacement | The boiler equipment at Aberdeen-Inverness is original to the building and past its useful life. Design, procure and install a replacement boiler system that incorporates the latest energy saving and energy management technology that can be cost effectively installed as a direct replacement to the existing units. | ABER INVER |  | On Hold-Funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 5 |  |  | FALSE | 0 |  | 2018-03-19 | CIB Approval | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3426 | 3426 |  | FALSE | BAS | Lothian Boiler Replacement | The boiler equipment at Lothian is original to the building and past its useful life. Design, procure and install a replacement boiler that incorporates the latest energy saving and management technology that can be cost-effectively installed as a direct replacement to the existing unit. | LOTHIAN HALL |  | Complete Design/Bidding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 6 |  |  | FALSE | 0 |  | 2018-03-19 | Complete Design/Bidding | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3427 | 3427 |  | FALSE | BCOE | C-CERT Install Meter | Site: inland empire utility agency (IEUA) Meter install: Allen Bradley PowerMonitor 5000 price of meter is $7,410 Projected price of install: $15-20k Scope of work: Meter will be purchased by UCR for install at the main panel at the IEUA Carbon Canyon Facility. Once the meter is installed then it will be used to send Energy data back to their SCADA system and monitor and display real time data. |  |  | Additional funding added | Christopher Lynch | Maggie Souder | Todd Ambriz |  | Fernando Nunez | 3 |  |  | FALSE | 41000 |  | 2018-03-21 | Start Construction | 2019-02-04 | 2019-02-28 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3428 | 3428 |  | FALSE | BCOE | MS&E Cleanroom Expansion | Prepare MSE cleanrooms space for and relocate existing Bourns Hall Research Cleanroom (Center for Nanoscale Science and Technology cleanroom) from Bourns Hall B-wing to MSE cleanroom. This will include necessary utility support and move of some equipment from BHB to MSE. | MAT SCI ENGR |  | In Bidding | Christopher Lynch | Maggie Souder | Margaret Souder |  | Dave Bomba | 6 |  |  | FALSE | 700000 |  | 2018-04-04 | Approve Specifications | 2019-04-01 | 2019-07-31 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3430 | 3430 |  | FALSE | BAS | TAPS Cust Svc Lobby Upgrades | Upgrades to Customer Service Lobby – Need to complete Tenant Improvement project upgrade customer service counter in Parking Services Building. Want to replace current counter to allow for; modern computer equipment, dividers between customers’ transaction spaces, under counter space for filing cabinets and check writing space. Please coordinate with Auxiliaries’ primary PM John Franklin. | PARKING SERV |  | On hold until Summer 2019 | Gerry Bomotti | Georgianne Carlson | Andrew Stewart |  | Dave Bomba | 15 |  |  | FALSE | 0 |  | 2018-05-17 | On hold until Summer 2019 | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3432 | 3432 |  | FALSE | ATHLETICS | Athletics Replace Scoreboard | Please assist with coordinating the process for replacement of existing soccer scoreboard to a new model. We will work with A&E to develop criteria and how to accomplish the task. |  |  | On-hold | Tamica Smith Jones | Joseph Erbland | Joseph Erbland |  | Scott Donnell | 1 |  |  | FALSE | 0 |  | 2018-07-19 | On-Hold | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3437 | 3437 |  | FALSE | FAC-PLNG-DESIGN-CONST | UCPD Generator Replacement | Replace unsupported 125kw generator with new - Critical Facility |  |  | In Design | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Fernando Nunez | 3 |  |  | FALSE | 0 |  | 2018-10-08 | Receive 100% CD's | 2019-07-01 | 2019-08-30 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3438 | 3438 |  | FALSE | CAP.PROG. | Iowa Street Widening | Iowa street widening requested by the City. Campus agreed to engage consultant Olson Engineers. The City agreed to reimburse campus for approved costs. MOU with the City is being created. |  |  | City to determine schedule | TBD | Sharyl Murdock | Dave Bomba |  | Dave Bomba | 21 |  |  | FALSE | 0 |  | 2018-08-22 | City to determine schedule | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3439 | 3439 |  | FALSE | BAS | TAPS Strategic Master Plan Study | STUDY - Transportation And Parking Master Plan Study This study initiated by TAPS is part of a comprehensive planning effort within Auxiliaries to develop a strategic transportation and parking plan that will guide the university’s transportation and parking efforts over the next decade. This is complementary to the campus Physical Master Plan Study and will help inform the future new LRDP. |  |  | Postponed until Mid-2019 | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Jerrod Walters | 17 |  |  | FALSE | 0 |  | 2018-06-05 | Postponed until Mid-2019 | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3441 | 3441 |  | FALSE | CHASS | INTS 1121 Convert Classroom to Dance Room | Convert a classroom into a dance room (we're looking for what it would cost) to provide additional performance space. Target Departmental Funding Amount: $20,000. Desired Timeline: Ready for fall quarter use |  |  | In Programming | Milagros Pena | Cindy Williams | Anna Finn |  | Daneca Stevens | 3 |  |  | FALSE | 0 |  | 2018-06-22 | Design | 2019-11-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3452 | 3452 |  | FALSE | CAP.PROG. | Long Range Dev Plan - 2018 | New Long Range Development Plan (LRDP), with all required technical studies |  |  | In Programming | TBD | Sharyl Murdock | Jacqueline Norman |  | Uma R. | 4 |  |  | FALSE | 2400000 |  | 2018-07-16 | Complete Programming | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3453 | 3453 |  | FALSE | BAS | ECS N&S Playground Shade & Turf | Provide Schematic Design, Design Development and Professional Cost Estimate for the alteration of existing shade structures, provision for additional shade structures, refinish interior metal fencing, and the replacement of existing grass with synthetic turf at the Early Childhood Services north and south playground areas. Prepare drawings so that they can be bid and constructed as separate projects. |  |  | Dept approval/funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 22 |  |  | FALSE | 0 |  | 2018-07-03 | Dept approval/funding | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3455 | 3455 |  | FALSE | BAS | Campus Traffic Engineering Study | This request is to fund the contracting of a consulting firm to study of the impacts related to the desired construction of a new parking garage on the UCR campus. Project will inform on site selection, traffic impacts and opportunities. This project will be funded through a parking garage planning budget allocation in the approved 2018-19 TAPS budget. |  |  | In Construction | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Dave Bomba | 27 |  |  | FALSE |  | 0 | 2018-07-23 | TAPS Response | 2018-11-05 | 2019-06-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3458 | 3458 |  | FALSE | CAP.PROG. | KUCR Replacement Project | Proposed replacement of KUCR radio station facility |  |  | No update | TBD | Sharyl Murdock | Blythe Wilson |  | Blythe Wilson | 9 |  |  | FALSE | 0 |  | 2018-07-16 | Unknown | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3459 | 3459 |  | FALSE | BAS | A-I Hardscape Landscape Design | Provide Schematic Design and Design Development drawings for a selective renovation of all hardscape and landscape around the perimeter of the Aberdeen-Inverness housing complex. Scope to include (but not limited to) widening of South Walk and replace its asphalt with concrete pavers, upgrade hardscape and landscape at Horseshoe, replace selected lawn areas with hardscape, seating and solar umbrellas at east and west lawns of Building E, consider new bike storage along South Walk, consider modifying slopped lawn between Building A and Linden St., generally reduce lawn areas and replace with sustainable planting, prune or replace unkempt trees, replace selected light fixtures to match Dundee fixtures, and generally freshen the landscaping so that it is harmonious with the new Dundee development. Design to be packaged in phases, with the South Walk and Dundee-facing landscape to be ready in Phase 1 for construction timing alongside Dundee-Glasgow landscaping in Spring of 2020. | ABER INVER |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 23 |  |  | FALSE | 0 |  | 2018-07-16 | Complete Design | 2020-01-01 | 2020-08-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3460 | 3460 |  | FALSE | BAS | A-I Restroom Replacement - Reconfig | Provide Schematic Design and Design Development drawings for the complete replacement of the restrooms in all four resident hall wings. Existing restroom fixtures and finishes are largely original to the building and long past their service life, causing serious leaks between floors. New restrooms will be reconfigured to meet current accessibility code. Documents to be assembled for phased construction, one wing per summer, with the first building (D-Wing) to be constructed in Summer 2019. | ABER INVER |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 26 |  |  | FALSE | 0 |  | 2018-07-19 | Complete Design | 2019-06-01 | 2019-08-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3462 | 3462 |  | FALSE | BAS | A-I Restaurant & Lobby Reconfiguration | Provide Schematic Design and Design Development drawings for the complete reconfiguration of Building C including kitchen, dining space, and common areas. The restaurant and kitchen areas are largely original to the building and well past their useful life. The new, replacement, Glasgow restaurant coming on-line in Fall 2020 will allow a needed reprogramming and modernization of this space. Preliminary Program for this space includes a smaller Catering Kitchen, Meeting Rooms, new KUCR studio as well as a modernization and upgrade of the Lobby and other Common Areas. Documents to be assembled for a Fall 2020 construction start. | ABER INVER |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 24 |  |  | FALSE | 0 |  | 2018-07-17 | RFQ Development | 2020-08-01 | 2021-06-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3463 | 3463 |  | FALSE | BAS | Landscape Strategic Plan for Housing Services | Provide a comprehensive study of existing landscape areas within Auxiliary Services and provide specific and actionable recommendations for their conversion to sustainable landscaping by location. Study to include all Resident Hall and Apartment properties and include conceptual cost estimates, by location, for proposed landscape conversions. |  |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 25 |  |  | FALSE | 0 |  | 2018-07-17 | Consultant Selection | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3466 | 3466 |  | FALSE | BAS | Oban Porch and Stair Repair | Provide a comprehensive structural survey, system of engineering solutions, cost estimate, construction documents and construction services for the repair and replacement of elevated porches, decks and stairs in Oban Family Housing as required to repair or replace worn structures. | OBAN APTS A |  | In Design | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 30 |  |  | FALSE | 0 |  | 2018-07-31 | Consultant Contract | 2019-05-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3467 | 3467 |  | FALSE | BAS | Plaza Porch/Stair Structural Repairs | Provide a comprehensive structural survey, system of engineering solutions, cost estimate and construction services for the repair and replacement of elevated porches, decks and stairs in the Plaza apartments as required to repair or replace existing worn structures. | THE PLAZA |  | In Programming | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Jason Espinoza | 29 |  |  | FALSE | 0 |  | 2018-07-31 | Consultant Contract | 2019-08-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3469 | 3469 |  | FALSE | CHASS | Carillon Repair & Maintenance | Design, fabrication and replacement of bell beams for bells 24, 26, 28, 30 and 32. Design, fabrication and installation of bracing to brace the 5 other bells beams that are cracking, and corrective maintenance on the clappers & head pieces-this would include complete removal, cleaning, reaming, bushing and lubricating before re-installing and clean and lubricate the transmission system as much as possible without complete disassembly to make the instrument easier to play. | BELLTOWER |  | In design | Milagros Pena | Cindy Williams | Reasey Heang |  | Daneca Stevens | 7 |  |  | FALSE | 10000 |  | 2018-08-16 | Inspection and design | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3470 | 3470 |  | FALSE | PLANNING & BUDGET | 2018 Campus Seismic Audit | This is a study to ensure that UCR's buildings are evaluated for seismic safety and fulfill Seismic Safety Implementation Policy. |  |  | New Study | Gerry Bomotti | TBD | Drew Hecht |  | Drew Hecht | 12 |  |  | FALSE |  |  | 2018-11-06 | Complete Review | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3471 | 3471 |  | FALSE | VC-STU.AFF. | HUB Elect/Gas Meters 8 Location | Please review 8 locations within the HUB to determine best options to install separate electric and gas meters. The locations are: 1st Floor Food Vendor Locations (Chronic Taco, Subway, Hibachi-San, MOD Pizza), The Habit Burger Grill, Coffee Bean & Tea Leaf, Subway and HUB 346 (3rd Floor Student Kitchen). NEED CONFIRMATION FROM HUB GOVERNING BOARD BEFORE ANY WORK IS TO BE INITIATED. Brendan can send a separate e-mail to Facilities once confirmed. | HUB |  | Governing board approved 2/15/2019 | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | J.Franklin/J.Espinoza | 5 |  |  | FALSE | 0 |  | 2018-08-20 | Design | 2019-12-01 | 2020-02-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3472 | 3472 |  | FALSE | BAS | Lot 21 Trash Enclosure Relocation | Construct a new CMU trash enclosure with water and power in a different location of Lot 21 to replace the existing enclosure that will be demolished to make way for the Dundee Residence Hall construction. Include hose bib for cleaning and power for future compactor installation. New enclosure needs to be on line BEFORE site construction can start on Dundee-Glasgow in January 2019. |  |  | Funding | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 34 |  |  | FALSE | 0 |  | 2018-08-15 | Hire Design Consultant | 2019-05-01 | 2019-06-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3474 | 3474 |  | FALSE | PLANNING & BUDGET | RUSD STEM High School |  |  |  | Real Estate project | Gerry Bomotti | TBD | ----- |  | Raoul Amescua | 5 |  |  | FALSE | 0 |  | 2018-10-31 | Regents Approval of Ground Lease | 2019-07-01 | 2022-09-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3476 | 3476 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM17-19 Tunnel System Plumbing | Evaluation of the existing Campus steam condensate return system from the MRB1 building to the following locations which include V30, V32, V6, V10, V9, and downstream to the Central Steam Plant. |  |  | Reviewing final reports | Susan Marshburn | Da Lan Dinh | Mihai Gavan |  | Mihai Gavan | 1 |  |  | FALSE | 1250000 | 0 | 2018-10-17 | Complete Final Report | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3478 | 3478 |  | FALSE | BAS | Ivans Hinderaker Ext. Cladding | Replace existing exterior cladding outside of Ivan's kiosk with new building materials that will cover the abandoned openings in the exterior and provide a cohesive and waterproof envelope for this structure. | HINDERAKER |  | Project number assigned | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 99 |  |  | FALSE | 0 |  | 2018-09-07 | Complete Construction | 2019-03-01 | 2019-04-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3481 | 3481 |  | FALSE | LIBR | Riv/Orb Libraries Fire Suppression-Estimate | Request estimate for installing fire suppression systems throughout all areas of both Rivera and Orbach Science Libraries. |  |  | Client approval/funding | Steven Mandeville-Gamble | Jackie Bates | David Schuster |  | John Franklin | 1 |  |  | FALSE |  |  | 2018-11-27 | Client approval/funding | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3482 | 3482 |  | FALSE | CHASS | Humanities 3rd Floor Install Sail Shades | Shade sail installation of the patios on the third floor of Humanities Social Science. There are two patios, one on the 3600 wing and one on the 3400 wing. |  |  | Pre-programming | Milagros Pena | Cindy Williams | Paul Richardson |  | Daneca Stevens | 9 |  |  | FALSE | 0 |  | 2018-10-10 | Funding | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3484 | 3484 |  | FALSE | PLANNING & BUDGET | 266 Frost Ct Main House Demolition | Develop project budget and timeline, obtain funding from VCPB. Coordinate disconnection of all utilities: Electrical, Gas, and Water. Disconnect and cap sewer Coordinate HAZ Mat testing and report for asbestos and lead Hire abatement contractor (if necessary) to remove haz materials. Hire demolition contractor to demolish and dispose of existing house, garage and out buildings. Foundations to remain – but make safe and remove potential hazards (rebar, bolts, etc.) protruding from foundation. Paving, pavers and other “patio” slabs to remain – make safe by removing tripping hazards. Identify any hazards (I.E.; unstable retaining walls, debris piles, etc.) and make safe and secure or remove if more cost effective. |  |  | Bidding | Gerry Bomotti | TBD | Scott Donnell |  | Daneca Stevens | 7 |  |  | FALSE | 40000 |  | 2018-11-15 | Bidding | 2019-05-01 | 2019-05-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3486 | 3486 |  | FALSE | VC-STU.AFF. | HUB 353/381, Costo 111 Add'l Wall/Doorway | Please evaluate additional wall/door way requests for HUB 353/381 and Costo Hall 111. | HUB |  | Client Approval/Funding | Brian Haynes | Cathy Eckman | Brendan O'Brien |  | Daneca Stevens | 6 |  |  | FALSE | 0 |  | 2018-11-26 | Funding | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3488 | 3488 |  | FALSE | BAS | CBS HUB Business Center | Provide a light renovation of the HUB Modular space to include new electrical drop for the Card Office cubicles in the North Office (where the copy machines are now), and replace flooring in the North Office as required, install ADA shelf at the front desk and other minor scope items to facilitate the move of the Card Office to this building. This must be a Winter Break project so that the Business Center remains online during the normal campus schedule. |  |  | Close-out | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | Fernando Nunez | 39 |  |  | FALSE | 15000 |  | 2018-11-13 | Complete Project Close-Out | 2018-12-17 | 2018-12-21 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3490 | 3490 |  | FALSE | BAS | East Campus Parking Structure | This request is being placed to start the planning of the East Campus Parking Structure in Parking Lot 13. Initial funding is for the P-phase of this parking structure construction. This approximately 1200 space structure will occupy the eastern section of Parking lot 13. |  |  | In Design | Gerry Bomotti | Georgianne Carlson | Irma Henderson |  | Dave Bomba | 42 |  |  | FALSE |  |  | 2018-12-06 | Selection of Design Build Teams | 2019-12-01 | 2021-02-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
3491 | 3491 |  | FALSE | BAS | Oban Comm Ctr Remodel | General remodel and freshening of the Oban Family Housing Community Center to include Laundry Room, Public Restroom and Recreation Room. Scope documents and partial drawings attached. This was originally two separate projects that Facility Services was managing but has now been requested that A&E take over due to evolving complexity and dollar cost. |  |  | Aux. Svcs. Placed the project on hold until '20/'21 FY. | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | J.Franklin/J.Espinoza | 38 |  |  | FALSE |  |  | 2018-11-16 | Re-scope/Client approval/Funding | [10 empty] | PD&C | 0 | 2018 | 2019-03-01
3496 | 3496 |  | FALSE | LIBR | Rivera Library Install Gate | Rivera library gate installation |  |  | In Design | Steven Mandeville-Gamble | Jackie Bates | Rebeccah Goldware |  | Dave Bomba | 3 |  |  | FALSE |  |  | 2019-01-08 | Customer Approval/Funding | [10 empty] | PD&C | 0 | 2019 | 2019-03-01
3498 | 3498 |  | FALSE | FAC-PLNG-DESIGN-CONST | DM(FY18) HUB New Sewer Lines | Construct new sanitary sewer lines, New manhole, pipe connections, demo existing manhole. |  |  | New | Susan Marshburn | Da Lan Dinh | Ron Rector |  | Gerald Caraig |  |  |  | FALSE |  |  | 2019-02-25 | [11 empty] | PD&C | 0 | 2019 | 2019-03-01
3499 | 3499 |  | FALSE | PLANNING & BUDGET | Creekside Terrace Analysis | Developers Research is to prepare an analysis, which includes the cost of outstanding development impact fees, permitting and estimated cost to complete lots for construction for the unfinished lots at the Creekside Terrace Project. Developers Research will review the Tentative Tract Map, conditions of approval, prepare an impact fee analysis (which includes any paid and unpaid impact fees), conduct a site inspection and review all other documents provided by UCR. Developers Research will also prepare an update to our cost estimate within 12 months of providing the report to UCR. |  |  | New | Gerry Bomotti | TBD | Blythe Wilson |  | Dave Bomba | 2 |  |  | FALSE |  |  | 2019-02-14 | New | [10 empty] | PD&C | 0 | 2019 | 2019-03-01
3503 | 3503 |  | FALSE | BAS | Falkirk Stair/Front Porch Repair | Repair or replace four sets of entry stairs and landings that are long past their service life and are a life safety concern. Consider replacing these wood structures with steel to ease future maintenance. Apartments affected are #3RS, #11MN, #15A and #16FG. |  |  | New | Gerry Bomotti | Georgianne Carlson | Richard Geiger |  | John Franklin | 43 |  |  | FALSE |  |  | 2019-02-01 | Complete design | [10 empty] | PD&C | 0 | 2019 | 2019-03-01
3504 | 3504 |  | FALSE | PLANNING & BUDGET | Silver Oaks Womens Health TI Fees | UCR Health will be acquiring new off-campus leased space by expanding into an adjacent medical office suite located at 19330 Jesse Ln #160, Riverside, CA 92508. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. |  |  | New | Gerry Bomotti | TBD | Brandon Barbosa |  | Blythe Wilson | 1 |  |  | FALSE |  |  | 2019-02-14 | New | [10 empty] | PD&C | 0 | 2019 | 2019-03-01
3505 | 3505 |  | FALSE | PLANNING & BUDGET | Orange County Psychiatry | UCR Health will be acquiring new off-campus leased space by moving into an adjacent medical office suite located at The Airport Tower, 18881 Von Karman Ave #1227, Irvine, CA 92612. The landlord will be paying for the improvements, however, UCR Health anticipates costs for 3rd party architectural fees as well as PD&C management fees for the project. |  |  | New | Gerry Bomotti | TBD | Brandon Barbosa |  | Blythe Wilson | 3 |  |  | FALSE |  |  | 2019-02-19 | New | [10 empty] | PD&C | 0 | 2019 | 2019-03-01
3514 | 3514 |  | FALSE | CHASS | HMNSS 1202 Window/Column Removal |  |  |  | New | Milagros Pena | Cindy Williams | Jennifer Morgan |  | ---- |  |  |  | FALSE |  |  | 2019-02-27 | New | [10 empty] | PD&C | 0 | 2019 | 2019-03-01
9055 | 3495 |  | FALSE | VC-RED | Pysch Loading Dock Haz Waste Storage | There’s been an increase use of biological and chemical hazards being used by researchers and their research projects within the Psychology (V3) vivarium. When hazardous substances are used/generated in the vivarium, the current practice is for that waste to be removed by the researcher and taken to their lab for disposal by EH&S. This would mean that hazardous agents are being transported across campus which could potentially lead to an accidental exposure. In order to comply with the hazardous storage and transportation regulations, RED proposes that a hazardous storage shed be built on or near the Psychology (V3) loading dock thus minimizing any potential from an accidental contamination. It would be a chain link storage shed with two rooms (one for biological hazards and the other for chemical hazards), and a solid roof. Around the outside of the shed would also need to have some sort of vinyl covering. As for size, a 10’ x 20’ (two 10’ x 10’) shed should meet the needed storage space. Sample designs can be provided. |  |  | Funding in process | Michael Pazzani | Laura Manor | Dierk Biggs |  | Fernando Nunez | 2 |  |  | FALSE | 10000 |  | 2018-12-04 | Start Construction | 2019-04-01 | 2019-04-30 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
17P000254 |  | 17P000254 | FALSE | PLANNING & BUDGET | SL5-FIRE & LIFE SAFETY/ACCESS CONTROL SHOP SPACE ALTERATIONS | Project in progress; ITS installing data. | CORP PP WHSE | 0106B | HOLD - FACILITIES SERVICES | Gerry Bomotti | TBD | DALAN DINH |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-06-07 | [6 empty] | 2/1/19, DL; Material is ordered with a 4-6 week lead time.11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DD 10/6: On hold pending discussion on space…..DL, 7/11/18; I understand there is movement on this project but I need to check in with John P. or Chris P. for a status update. |  | Ron Veloz | 12/14/18 O-RVL: F & LS shop space/Shop Location TBD. | NO | FS | 0 | 2017 | 2019-03-01
17W012504 |  | 17W012504 | FALSE | CNAS | PAINT Business OFFICE AND CONF. ROOM | Complete as of 10/22/18. | ENTOMOLOGY | 170 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 27 | 26 | FALSE |  |  | 2017-05-04 | [6 empty] | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. |  | Dan Lerman | DL: Bill Sutton will provide us with dates when we can have access to the space. We will need 5 - bussiness days to the space. | YES | FS | 0 | 2017 | 2019-03-01
18P000027 |  | 18P000027 | FALSE | CNAS | SL5-CHAPMAN PREP AND PAINT LAB | Complete as of 7/12/18 | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-05 | [6 empty] | 2/1/19, DL; This project is 100% Complete……………DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again…… DL, 4/2/18; This space is still on schedule for 7/1/18 completion date…..FAMIS work orders have been produced…..DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th….. |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again...... DL, 4/2/18; This space is still on schedule for 7/1/18 completion date.....FAMIS work orders have been produced..... | YES | FS | 0 | 2018 | 2019-03-01
18P000028 |  | 18P000028 | FALSE | CNAS | SL5-CHAPMAN PATCH AND PAINT | Complete as of 7/12/18 | CHAPMAN | 0010A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced .......DL, 7/11/18; This Project will be 100% complete on 7/12/19. Jess is working on floor issues in oter areas that where not part of the original scope but this project is will be complete on the 12th..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. DL, 4/2/18; This space is still on schedule for 7/1/18 completion date..... FAMIS work orders have been produced ...... | YES | FS | 0 | 2017 | 2019-03-01
18P000029 |  | 18P000029 | FALSE | CNAS | SL5-CHAPMAN REPLACE OR REPAIR AND CLEAN ALL BLINDS | Complete as of 7/11/18 | CHAPMAN | 1 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain......DL, 5/24/18; This work is scheduled to be complete on or before 7/1/18.....DL, 6/16/18; Blinds are delayed to mid July but window clenaning is still on schedule......DL, 7/11/18; This Project is 100% Complete |  | Dan Lerman | DL 1/3: On Hold until roof is replaced. 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; This project is still pending until the roof repair is complete since the room is exposed to water damage if we receive any rain...... | YES | FS | 0 | 2017 | 2019-03-01
18P000030 |  | 18P000030 | FALSE | CNAS | SL5-CHAPMAN PREP AND PAINT FROM WATER DAMAGE | Complete as of 11/8/18 | CHAPMAN | 100 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-07-11 | [6 empty] | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced.......DL, 7/11/18; The Roof is now water tight. We will proceed with the vinyl floor replacement. We will also proceed with the plaster repair and paint. Note, The plaster is severly damaged in many areas and we will need to include plaster repair and paint for the entire second floor. This work will be contracted out. Projected complete date is before Fall 2018 Academic year.....DL, 8/10/18; Walked plaster/ paint project with Paint contractor. WE are on track for 9/21/18 Complete date......DL, 8/22/18; We are working on the Contract. Still on track for 9/21/18 Complete.... DL, 9/19/18; This project is in progress. P&P will be done by 10/1/18. Flooring will be complete on10/1/18.....DL, 11/7/18; This Project is 100% complete..... |  | Dan Lerman | DD 10/6: On hold until roof is replaced. 2/23: Follow up with dan on timeline 2/5: Pending the completion of the roof replacement. Timeline projected July…..DL, 2/26/18; patch and paint portion of Project is in progress on the first floor….. 3/19 MN: Project completion pending the roof installation. Roof install went out to bid again. .....DL, 4/2/18; Notes are current.....NO FAMIS work orders have been produced....... | YES | FS | 0 | 2017 | 2019-03-01
18P000094 |  | 18P000094 | FALSE | BAS | SL5-OBAN LAUNDRY ROOM RENOVATION | Scope of work has changed and project to be routed to Google IRT/CPMS for completion | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2017-09-08 | [6 empty] | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on bid. 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/12 EB- rec'd approval to contract with Design West to consult on electrical panel upgrade. |  | Enrico Baez | 1/19: A&E reviewed the drawings and contracting work. EB 10/30 Developed work scope, sent to Bob Brumbaugh for approval/editing. 2/5: Pending Wash to determine the AMP drawing from the machines to confirm number of circuits required. 2/23: on hold MN 3/20: pending approval from customer on b 4/2 MN: Enrico to speak with A&E regarding the bids received to clarify for the customer. Pending approval on the contract. 6/11/18 EB-requested drawings from Gunter per Desgn Wests request. 7/11/18EB-waiting for Desgn West to complete site survey. 8/7/18 EB-Met with Robert Brumbaugh. Scope has changed with additional requirements. Improve HVAC, replace VCT, bathroom remodle. Advised to submit CPMS for A&E. | YES | FS | 0 | 2017 | 2019-03-01
18P000095 |  | 18P000095 | FALSE | BAS | SL5-THE PLAZA--RD APARTMENT LAUNDRY HOOKUPS | Canceled per customer on priortization list. | THE PLAZA | A0013 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  | Canceled | HOLD | FALSE |  |  | 2017-09-08 | [6 empty] | 4/11/EB-On Hold per Robert Brumbaugh. 6/8 EB-emailed R. Brumbaugh for status update. |  | Enrico Baez | 4/11/EB-On Hold per Robert Brumbaugh. DND 7/14 Hold per customer on prioritization | YES | FS | 0 | 2017 | 2019-03-01
18P000099 |  | 18P000099 | FALSE | CNAS | SL5-EARTH SCIENCES-GEOLOGY-CABINETS-CP00003360 | Plans will be developed and will be submitted for review and approval. | GEOLOGY |  | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 26 | 23 | FALSE |  |  | 2017-09-08 | [6 empty] | 12/6/18, DL; This project is a priority #23 and may be completed in the next 12 - months…..DL 1/3: Chris to verify with customer on electrical requirements for completion……DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress…..DL, 7/11/18; Still need to work on plans…. Target date is 9/30/18….. |  | Dan Lerman | DL 1/3: Chris to verify with customer on electrical requirements for completion…...DL, 4/2/18; This is electrial outlets for 4 display cabinets…..…NO FAMIS work orders yet….Dl, 4/29/18; Will work on plans/permits. The display cases will be in a coridor and they may pose an an obstruction for Emergency Exit egress..... | YES | FS | 0 | 2017 | 2019-03-01
18P000106 |  | 18P000106 | FALSE | BAS | SL5-HOUSING PROJECT - OBAN REC ROOM REMODEL | Scope of work has changed and project to be routed to Google IRT/CPMS for completion | OBAN OFFICE | 100 | TO BE PERFORMED BY PD&C | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Enrico Baez |  |  | 3 | FALSE |  |  | 2017-09-14 | [6 empty] | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. DL, 7/11/18; Per Susan this project is back on track. Project is scoped. Gunther will start working on the plans and permits. Once we have the approved permit. still need to check in with Susan on a few items.....Target complet date will be mid- fall...... |  | Enrico Baez | EB 1/19: drawings being reviewed by A&E; project to be bundled with Laundry room. DD 10/6: Enrico scoped the work. 2/5: Pending bid walk results. 3/19 MN: On hold pending the rec room remodel. 8/22/18 Met with BoB Brumbaugh, Scope of work has changed with additional items. Fire alarm panel relocation, possible building HVAC upgrade. Ask he route project through CPMS and make laundry room and Rec. room one project. | YES | FS | 0 | 2017 | 2019-03-01
18P000111 |  | 18P000111 | FALSE | CHASS | SL5-KEY CARD ACCESS INSTALLATION INTS 3154 AND 3156 | Complete as of 7/13/18 | CHASS INT S |  | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Jason Williams |  |  |  | FALSE |  |  | 2017-09-15 | [6 empty] | EB 1/31/18 Work was assigned to lock shop 12/7/17…. DND 5/11: Spoke with Jason, all work complete to be completed as trade is available. Only work remaining is on 3150 A; Jason short staffed to finish project but it's on his radar. 07/13/18 H-FMS: Troubleshoot programming and settings for this controller. Clear all data from panel and reset, perform required downloads, re-test and verify both doors working correctly. |  | Enrico Baez | EB 1/31/18 Work was assigned to lock shop 12/7/17 | YES | FS | 0 | 2017 | 2019-03-01
18P000117 |  | 18P000117 | FALSE | CNAS | SL5-PREP FOR MATH TA OFFICE HOUR SPACE RELOCATION | Complete as of 9/10/18 | WEBBER | 1303 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-21 | [6 empty] | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work....DL, 5/9/18; Produced work order for JEss to test for lead paint and ACM....Von wall is hot, everything else is good to go. I will schedule the work soon. The space is vacant......DL, 7/11/18; This project is in progress. Target Complete Date is 8/10/18....DL, 7/25/18; Vinyl plank and bullitin boards the balance of the task for this project. Still on target for complete on 8/10/18.....DL; 8/10/18; We were schedule to install the fllor and identified Asbestos,. Jess is working on the propsal and schedule for the abatment. This will require a 14- dat notification to the AQMD. This space is vacant with no scheduled move in date......DL, 8/22/18; Abatment is scheduled for this Tursday and Friday. We will scheule the carpet in dry errase boards for next week.Target complete date will be 8/31/18.....DL, 9/6/18; This project is 100% Complete...... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Still need to meet with Melissa and review scope……DL, 3/20/18; Site visiti is scheduled for 3/23/18….....DL, 4/2/18. Notes are current but target date needs to be confirmed ASAP......FAMIS work orders are produced.....DL, 4/16/18; Sent Melissa an email requesting target date.....DL, 4/29/18; Jesst to test for ACM and Lead. Once test complete, we will scheudle the work.... | YES | FS | 0 | 2017 | 2019-03-01
18P000118 |  | 18P000118 | FALSE | CNAS | SL5-OLMSTED CABINET REPAIR/REMOVAL PATCH & PAINT | Complete as of 7/25/18. | OLMSTED | 1337 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MELISSA GOMEZ |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2017-09-20 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space.......DL, 6/16/18. New staff member schedule to start mid july. BKM is also scheduled for mid july. This project will require cabinets to be removed, new carpet, paint and blank out electrical outlets that will no longer be used.. new signage too.....DL, 7/11/18;This project is in progress. Complete date is 7/20/18......DL, 7/25/18; This project is 100% Complete....... |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope….DL, 3/20/18; Site visiti is scheduled for 3/23/18...……DL, 4/2/18; Project scope is to remove cabinets, P&P including new carpet. Need to availability to space and schedule the work. NO FAMIS work orders yet....DL, 4/29/18; Sent Melissa an email requesting when we can have access to the space. | YES | FS | 0 | 2017 | 2019-03-01
18P000121 |  | 18P000121 | FALSE | CAMPUS | SL5-PHYSICS HYDRATION STATION - PHYSICS HALL | Reviewing campus standards for these project requests. | PHYSICS | 0 | HOLD - FACILITIES SERVICES |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | 12/6/18, DL; This project is currently on hold…... DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus | NO | FS | 0 | 2017 | 2019-03-01
18P000122 |  | 18P000122 | FALSE | CAMPUS | SL5-MS&E HYDRATION STATION - MS&E HALL | Reviewing campus standards for these project requests. | PHYSICS | 0 | PROJECT INTAKE |  |  | JAZMIN CHAVEZ |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2017-09-21 | [6 empty] | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… |  | Dan Lerman | DL, 1/5/18; Still need to review scope…..DL, 2/26/18, Still need to review scope…..4/2/18; Notes are current…… DND 7/14: hold per hydration station update for campus | NO | FS | 0 | 2017 | 2019-03-01
18P000126 |  | 18P000126 | FALSE | CHASS | SL5-HMSS ESTIMATE REMOVE WALL & CHANGE DOORS | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 3611 | PLAN DEVELOPMENT/CHECK | Milagros Pena | Cindy Williams | DARA CERDA |  | Dan Lerman |  | 21 | 29 | FALSE |  |  | 2017-09-28 | [6 empty] | 02/2819, DL; Gunther will work on plans over the next three weeks to submit for a building permit. We will schedule the work if and after the plans are approved. If approved the door and window will more than likely have a 3- month lead time…………....12/14/18, DL; This project is a priority #21 and may be completed in the next 12 - months…DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; No Change… |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS. Remove double doors and install single door.Remove small West wall. Relocate t-stat. Ceiling work. Replace carpeting. | YES | FS | 0 | 2017 | 2019-03-01
18P000194 |  | 18P000194 | FALSE | ITS | SL5-TELEPHONE WINDOW REPLACEMENT | Canceled by customer; duration of hold was over 10 months. Customer to resubmit when ready to proceed | TELEPHONE | 101 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  | 5 | 6 | FALSE |  |  | 2017-11-20 | [8 empty] | Enrico Baez | EB-1/31/18 Conducted site visit. Request to replace all exterior Plexiglas with glass. Will call glass vendor to provide estimate. 7/12/18 EB-Quote provided by Hour Glass. Emailed Tami, she is waiting for budget approval to proceed with project. Should have by end of July. 10/22/18 Customer Canceled; will resubmit when ready to proceed. | YES | FS | 0 | 2017 | 2019-03-01
18P000198 |  | 18P000198 | FALSE | VC-STU.AFF. | SL5-HUB-HIGHLANDER UNION-HUB-NEW WALL LIGHTS-CP00003307 | Plans will be developed and will be submitted for review and approval. | HUB | 0 | QUEUE TO START | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 1 | 5 | FALSE |  |  | 2017-11-21 | [6 empty] | DL, 9/6/18; Conducted Site Visit with Customers and Enrico. This will be recharge work and plans will be required. The goal is to have this project complete before winter break…... | 2018-01-23 | Enrico Baez | 1/23/18 EB-site walk, scope enter in FAMMIS. 4/2 MN: Enrico to obtain an FAU. 1/23/2018 E.Baez conducted job site walk. Request is for lighting installations above entries to store front and kitchen on East side of building and additional lighting above outside locker on loading dock. Manny has lights that can be re-used. Want estimate only. Need to include Campu Architech too...... | YES | FS | 0 | 2017 | 2019-03-01
18P000201 |  | 18P000201 | FALSE | CHASS | SL5-ARTS REMOVE COUNTERTOP/SHELVES | Complete as of 8/23/18 | ARTS | 0106A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 3 | TRUE |  |  | 2017-11-21 | [6 empty] | DL, 6/16/18; Ned to walk, scope and submit plans ASAP…..Sent Paul an email requesting information on Status of Faculty hire status……DL, 7/11/18; Paul is on Jury Duty and he said he should return back to work next week. Current Targe complete date is mid September......DL, 7/25/18; Carpentery and Electrical is complete. Patch and paint has started. Target complete date is 8/3/18......DL, 8/8/18; Space is VAcant and ready for paint. The paint department is working on several other projects that require their attention. The paint department will complete the work in the near future......DL, 8/22/18; This Project is 100% Complete....... |  | Enrico Baez | 2/2/18 EB conducted site visit and annotated on FAMMIS……DL, 4/29/18; Pasted from wo;remove the existing countertop and shelves that are built into the room. Follow with patch and paint of entire space. | YES | FS | 0 | 2017 | 2019-03-01
18P000205 |  | 18P000205 | FALSE | CHASS | SL5-CHASS INT S CREATE DOOR | Complete as of 9/21/18 | CHASS INT S | 2117H | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-11-27 | [6 empty] | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18……DL, 5/24/18; Plans were approved. WE need to schedule the work…..DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18...........DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... .. DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date..........DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18............DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware.....DL, 9/19/18; This Project is 100% Complete...... |  | Enrico Baez | EB-Scoped 12/11/17 annotated on Fammis. Sent email to Bob Williams if this is doable because of fire rated wall…..DL, 5/5/18; Plans were submitted on 5/4/18…… | YES | FS | 0 | 2017 | 2019-03-01
18P000209 |  | 18P000209 | FALSE | CHANCELLOR | SL5-VC-STU.AFF. & ENROLL-STUDENT SERV-DOOR RENO-CP00003374 | Customer provided estimate for project; verifying if funding is available to proceed with project. | STUDENT SERV | 0 | HOLD - FACILITIES SERVICES | Kim Wilcox | Karim Zahedi | ANGIE GRAY |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2017-11-30 | [6 empty] | 2/14/19, DL; Ron V. to follow up with Doug from Capitol Door for alternate pricing .1/15/19, DL; Ron V is still working with Angie on verifying a vendor and product…………..12/14/18, DL; Ron V. is currently working to find a more affortable turnstyle system. When a sytem is approved, we will schedule the work…. 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope and conduct site visit……DL, 7/11/18; This work will require plans and permits. Will schedule meeting with Scott to verify if the project request will be approved. If this is approved, we will plan the target complete date to be mid October…..The Request is to reverese Emergency Exit Doors and install Prox card access……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..DL, 8/22/18; Confirmed with Scott that we can reverse the door swing. We will work on plans for review process. This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 9/19/18; I mis understood this for a project at Health Services. I have a meeting with Angie this week. This project is to install turn styles for access to the building. I will need to discuss the equipment to be purchased by Angie verify the specs. We will start on the plans in the early Fall……DL, 11/7/18; Conducted site visit with Vendor. Informed Angie the cost of the project will be at $45K for the project. Angie is checking to verify if funds are availabe for the equipment. |  | Ron Veloz | 02/28/19 O-RVL: RV received confirmation from Doug at Capital Door that they are unable to provide a quote at this time due to deign changes with the product. END--- 02/21/19 O-RVL: RV has contacted Capitol Door with a RFQ. Pending follow up by 02/22/19 per Doug @ Capitol. END---02/21/19 O-RVL: RV Updated notes, RVhas contacted Capitol Door with a RFQ. Pending follow up by 02/22/19 per Doug @ Capitol. END--- DL, 5/5/18; FAMIS work order ,New ADA operator, power supply for operator and card swipe….. 2/6/18 E. Baez conducted site visit. Power and Data not located near desired installation site. Width of opening is 118" Flooring is combination of brick and vinyl. 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 1 and for faculty hire "NO"---- 2/6/18 EB- conducted site visit. Request for automated access control system. Annotated on FAMIS…. 2/2/18 EB site visit scheduled for 2/5/18 with Angie Gray. THIS REQUEST IS FOR QUOTES. THE SYSTEM REQUIRES AN FAU TO BE PROVIDED IN ORDER TO SUBMIT REQUEST. ACTUAL WORK WILL MOST LIKELY BE CHARGED TO A DIFFERENT FAU. THEREFORE, PLEADO NOT CHARGE FAU WITHOUT APPROVAL. Original request SR # 17S001552/WO # 17W001873 was submitted on 8/12/16 to Facility Services. A recommendation has come from UCPD for an automatic swing door to be installed on the first floor of the Student Services Building. The door would need to include a switch, button, and card reader functionality (SSB already operates on a keycard system). Please provide us with all options and pricing. The door would be similar to the ones installed in the SRC. I have attached a copy of the recommendation that contains a rendition. Please let me know if you have any questions. Thank you. Angie Primary Contact: Angie Gray. angeladi@ucr.edu. (951) 827-2589. Secondary Contact: Sean Cason. SEANC@ucr.edu. (951) 827-4020. 20 year(s) in use. ==CUST FAU# A01401 19900 68 AXSSB | YES | FS | 0 | 2017 | 2019-03-01
18P000214 |  | 18P000214 | FALSE | VC-STU.AFF. | SL5-COUNSELING & PSYCHOLOGICAL-HEALTH SERVICE-RENO-CP00003241 | Plans were approved by Fire Marshal, work to commence in 30 days. Scheduling the work with the availablity of the teams. | HEALTH SERV |  | IN PROGRESS | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2017-12-08 | [6 empty] | 2/28/19, DL; This project is in progress and on schedule……...2/14/19, DL; This project is scheduled to start on 2/19/19.2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/21/18; Scope is complete. Need to work on plans and permits. DL, 7/11/18; Still need to work on plans and permits. If plans are approved. The target complete date is 9/14/18. Work orders are produced for this project……DL, 7/25/18. This is to reverse the door swing, Prox reader, seal one door and install a new door……DL, 8/8/18; Sent Scott an email request to conduct sitre visit to better determine if the scope is possible…..This project is 2-3 months out between plans, material lead time and scheduling the work…….DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-days….. |  | Enrico Baez | 1/31/18 EB-Scoped site with Chris P. on 10/30/2017. Spoke with Gloris who thought still CPMS. Scope includes removing doors, adding teller counters, moving corridor wall…..Dl, 5/3/18; Dan, Chris, ron and Gloria will meet and re-scope the work……01/15/19, DL; The plans are approved and Material is ordered. Once material arrives, we will schedule the work with Gloria. | YES | FS | 0 | 2017 | 2019-03-01
18P000215 |  | 18P000215 | FALSE | VC-STU.AFF. | SL5-STUDENT HEALTH SERV-HEALTH SERVICE BLDG-RENO-CP00003246 | Plans were approved by Building Official; work to commence in 30 days. Scheduling the work with the availablity of the teams. | HEALTH SERV |  | IN PROGRESS | Brian Haynes | Cathy Eckman | PAMELA HAGGINS |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2017-12-08 | [6 empty] | 2/28/19, DL; This project has started and is on schedule…….2/14/19, DL; This project is scheduled to start on 2/19/19…………2/1/19, DL; One door is here and is being preped for paint. We have a pre construction meeting scheduled for next week. We will probably start this project during the later part of February………1/15/19, DL, Material is ordered, material should arrive on site in the next 3- 5 weeks……12/14/18, DL; Plans are approved, Material is odered with a 6-8 lead time, We will schedule the work once the material is on site…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 5/24/18; Need to review scope and site visti with Enrico. Plans and permits will be required for this project….DL, 7/11/18; Planning to walk work with Gloria and her team next week. Will be able to project complete date after site visit is conducted……DL; 7/25/18; We walked this project with the team. This will require plans and permits. We will schedule this work for Fall…………DL, 10/4/18; We will submit plans for review next week……DL, 11/7/18; Plans were approved. We will plan to start the work in the next 30-45 Days…… |  | Enrico Baez | EB 3/20 scoped project and annotated on FAMIS. DL, 5/5/18; Pased from wo:Noted changes to original request.Add counter windows onto end of the current SHS front desk main counter (2 windows/stations).2. Close exam room that is open to hallway with a wall (behind room 210).3. Covert 100A to phlebotomy room with a hallway access doorway.4. Open wall to reconfigure to allow space for lab manager……01/15/19, DL; Plans are approved and material is ordered for the Phlebotomy room. We are securing the double doors. We are not conducting anywork with countrtop or window work. | YES | FS | 0 | 2017 | 2019-03-01
18P000221 |  | 18P000221 | FALSE | CNAS | SL5-Provide add'l HVAC capacity to maintain lower temp | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 4414 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 9 | 16 | FALSE |  |  | 2017-12-11 | [6 empty] | 12/14/18, DL; This project is 100% Complete……….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob. DL, 5/9/18; We will work on plans and submit for review.....DL, 6/16/18. Had meeting with Bob W. to verify what is needed on plans. I will work with Gunther on plans for submittal and review......DL, 7/11/18; Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall.....DL, 11/7/18; Material is on site and will will schedule the work with in the next 30- days..... |  | Dan Lerman | DL, 1/5/18; Still need to review scope……2/26/18; Conducted site and scope visit. I need to walk the project with John P or Ken and verify the material and schedule…..…..4/2/18; site visit with Ken and Darren is scheduled for 4/5/18…..NO FAMIS work orders yet.....4;16;18; Base on site visit, we will install mistibishi mini split. Dan need to verify exact temp desired. The condensor will be installed in the core. power is available......DL, 4/29/18; Need to discuss permit with Lezlie and Bob | YES | FS | 0 | 2017 | 2019-03-01
18P000223 |  | 18P000223 | FALSE | CNAS | SL5-Provide requisite utility infrastructure to support 4 add'l chambers (on order). | Plans were approved by Building Official and Fire Marshal; anticipated completion January 2019. | FAWCETT LAB |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 11 | 21 | FALSE |  |  | 2017-12-11 | [6 empty] | 2/1/19, DL; This Project is 100% Complete……..01/15/19, DL; Plans are approved, Chambers are on site. Electrical is complete. Plumbing work is in progress. Our portion of the project should be complete by 2/1/19…………..12/14/18, DL; All Pre work is complete. The Chambers are scheduled to arrive on site within the next 30-days. We will finish this project when material on site……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans……..DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet….DL, 4/29/18; Still need to conduct site visit with the team….DL, 5/24/18; Per Patty, equipment is ordered but 5- months out…..DL, 9/6/18; We will submit plans to Bob W. tomorrow for review and approval……..DL, 9/19/18; Plans are approved. The equipment will be here in about 4- months. WE will start the work for this project in the Fall to ensure we are ready when the equipment arrives……DL, 9/19/18; Plans are currently being review by BO & FM……DL, 11/7/18; Plans are approved. WE are requesting to change the placement confirguration of the growth chamber and awaitng Bob's review and approval. WE are on track to have this work complete befoire the end of the new year….. |  | Dan Lerman | DL, 1/5/18; Still need to review scope……DL, 2/26/18; Currently scheduled to meet with Patty and April next week…..DL, 3/20/18; Project scope is complete. We need to submit plans to Bob Williams. Growth Chambers are still 4-6 Months out. I will work with Gunther on plans........DL, 4/2/18; I still need to walk the project with Frank P and Steve B to assess the chilled water volume. I also need to walk this project with Robert C. to verify a plan for the electrical portion.NO FAMIS work orders yet....DL, 4/29/18; Still need to conduct site visit with the team… | YES | FS | 0 | 2017 | 2019-03-01
18P000226 |  | 18P000226 | FALSE | BCOE | SL5-BOURNS FUME HOOD INSTALLATION | Installation of utilities to be completed; clean room to be installed upon utility connections. | BOURNS | B0235A | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  | 8 | HOLD | TRUE |  |  | 2017-12-11 | [6 empty] | 2/14/19, DL; This project is Complete…..2/1/19, DL; The Fume hood is complete. The vendor will be back in two weeks to comissison the clean room…..…1/15/9, DL; This project is 95% complete and should be complete on or near 2/1/19…………12/14/18, DL; This Project is 90% Complete. Fume hood is scheduled for install next week. We will finish balance of project after Fume hood is installed…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. WE are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans…..DL, 5/9/18; planning to submit plans on 5/11/18 for plan check review….. DL, 5/24/18; Plans were submitted to Bob W. on 5/24/18……DL, 6/12/18; Project is on Hold until Shane can provide plans/specs for the clean room……DL, 7/11/18; Still no change to the status……DL, 7/25/18, Maggie confirmed this project is on the books. I need to discuss the status with the team because the priority list is on Hold…….DL, 8/22/18; This project is no longer on hold. We will per shane we will submit what we have from the clena room suupplier for review from FM and BO……DL, 9/6/18; WE are almost complete with Plans and will submit the plans next week………DL, 9/19/18; Submitted plans to PD&C on 9/14/18…..DL, 10/4/18; Plans were approved thais week. WE will scheudle the project around the delivery date for the Clean room……..DL, 11/7/18; This is in progress. We will complete the install of the utilities so the clean room can be installed. WE will finish the balance of the project once the Clean room install is complete. The clen room is being install by an outside vendor….. |  | Dan Lerman | 4/25EB-Per Chris P. project given to Dan L……DL, 4/29/18; Sent Shane an email requesting site visit to review Scope…..DL, 5/5/18; This is the Clean room project. We are wqorking on plans and permits….Sent Shane an email requesting Clean room specs/plans..... DND 7/14 Hold per customer on prioritizatio | YES | FS | 0 | 2017 | 2019-03-01
18P000227 |  | 18P000227 | FALSE | CNAS | SL5-BATCHELOR P.NABITY'S LAB 4128 BATCHELOR HALL | Complete as of 11/8/18 | BATCHELOR | 4128 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | TRUE |  |  | 2017-12-12 | [6 empty] | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM.......DL, 5/24/18; Need to work on plans and permits. Project needs to be complete before Fall academic 2018.....DL, 6/16/18; Walked project with Jess. and he will schedule the abatment. We will not need plans for this project. We are not removing the exhasut hood which was the original purpose foor the plans......Carpenters started the demo. Still need to remove TSI. Once TSI is removed, we can schedule the plumbing work. Target Complete Date is 9/21/18....DL, 8/10/18; Abatement is scheduled for this weekend, we will start work soon.....DL, 8/22/18; Abatement and most demo complete. Still on track for 9/21/18.....DL, 9/19/18; Scope change. This project should be complete on 9/28/18.......DL, 10/4/18; Floor to be installed this Friday. Pianters will finalized the stain on the cabinets. Thsi project should be complete near 10/19/18.......Dl, 11/7/18; This project is 100% complete.... |  | Dan Lerman | DL, 2/26/18; Conducted scope with Patty and April; I need to meet with the FS team to review the scope and discuss a schedule befoe we proceed with the projrct…….…..DL, 4/2/18; This project is scheduled for July/August completion……..NO FAMIS work orders are produced yet. DL, 4/21/18; This project will require all trades and is involved. The space is vacant. Still need to have walls and floors tested for Lead and ACM....... | YES | FS | 0 | 2017 | 2019-03-01
18P000247 |  | 18P000247 | FALSE | CNAS | SL5-PHYSICS PATCH & PAINT FACULTY OFFICE-PHYSICS 3023 | Complete as of 7/14/18 | PHYSICS | 3023 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  |  | 15 | FALSE |  |  | 2017-12-20 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2017 | 2019-03-01
18P000252 |  | 18P000252 | FALSE | ITS | SL5-CHASS INT S REPLACE ELECTRICAL SCREENS | Pending customer to confirm of equipment to be purchased; work scoped by BZM. | CHASS INT S | 2130 | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | JORGE MACIAS |  | Dan Lerman |  | 1 | 2 | FALSE |  |  | 2017-12-21 | [7 empty] | 2018-06-21 | Ron Veloz | 01/23/19 O-RVL: RV received confirmation (Telcon) with Jorge macias to cancell the request. He will resubmit upon recipt of screens at a later date. RV instructed the Front desk(FS) to close out the request & "cc" Monty, Alan, Enrico & Linda & Loretta. END--- 01/23/19 O-RVL: RV emailed Jorge to verify status of the request/materials order. Pending response. END--- 01/09/19 O-RVL: RV spoke with Jorge on 1/09. Jorge expect screens to be ordered within two weeks and will cancel this request if the screens are not ordered by his department. Jorge asked to contact him in two weeks (01/23/19). END---6/21/18 RV HOLD, Walked site w/ Enrico & Jorge. Surveyed site and Enrico updated FAMIS & Project folder. Now pending - confirmation of party to purchase projection screens. S.O.W.: Remove two non functional motorized video screens. Replaced with new larger screen. Patch and repaint all walls and entry door. END--- 07/06/18 Ron V Input notes: Received email from Enrico on 07/03 confirming Facilities Services doe not purchase Audio Visual equipment in General Assigment class rooms. On 07/06 RV contacted Jorge Macias with this info and Jorge said he would get back to RV with follow up reply from his supervisor. Confirmed with E.B. that proj info/ photos are updated on the project folder and FAMMIS. END--- 8/22/18 O-RVL: Will follow up with Jorge to confirm status on the screen purchase and if Media will purchase the screens. END--- 08/23/18-RV emailed Jorge, Pending response. END--- 08/24/18-RV, Enrico followed up with Jorge, projection screens approved but not purchased yet). END--- 10/17/18: RV spoke with Jorge today and he said screens are on order. Jorge will follow up with updates to RV and Enrico. | YES | FS | 0 | 2017 | 2019-03-01
18P000256 |  | 18P000256 | FALSE | CNAS | SL5-BOYCE DISASSEMBLE/REMOVE AND REINSTALL NEW AUTOCLAVES | Complete as of 9/21/18 | BOYCE | 3451 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave at Webber is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place.......DL, 5/9/18; Autoclave is destroyed. Pictures were sent to Cheryl. We are now waiting for the equipment to arrive. Steve B is working on Steam connection at Boyce......DL, 5/24/18; Autoclaves arrived. Day crew is scheduled to deliver the unit on 5/30/18. we will schule the plumbers and electricians shortly there after......DL, 6/16/18; Webber Autoclave is almost complete. This portion should be complete next week. WE will run the Webbber autoclave for two weeks before we start the Boyce Autoclave. The weldolet for the BOyce unit will be installed during the steam shutdown...... DL, 7/11/18; Webber Auto clave will be complete on 7/12/18. We will start the demo of the Boyce Auto clave next soon. Target date for this project is 8/10/18...... DL, 7/25/18; We had a delay with the Webber autoclave which will implact the Boyce Auto clave. New target complete date is 8/22/18.....DL, Plumbing is almost complete, need to schedule final elctrical and Commission equipment. Target date 8/31/18...... DL, 9/6/18; This project should be complete but we still need to schedule the electrical connections ASAP.........DL, 9/19/18; This project is 100% Complete. |  | Dan Lerman | DL, 4/2/18; Scoped project. Need to cordinate demo and install DL, 4/29/18; This is for two Autoclaves. The Autoclave is demolised and Day crew is scheduled to pick/dispose of the unit on 4/30/18. The Webber autoclaves are scheduled to be delivered shortly after 5/10/18......This is aftermarket equipment. We are only connecting the utilites. No alterations are taking place | YES | FS | 0 | 2017 | 2019-03-01
18P000257 |  | 18P000257 | FALSE | CNAS | SL5-SKYE HALL MOUNT 55 | Scope of work is being reviewed; determining how to complete project with trades. | SKYE HALL | 209 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 28 | 28 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete…….1/15/19, DL, Site visit is scheduled with James M. this Thursday. We will schedule the work shortly after the site visit…….12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | FS | 0 | 2017 | 2019-03-01
18P000258 |  | 18P000258 | FALSE | CNAS | SL5-SKYE HALL HALLWAY MOUNT | Scope reviewed by BZM; coordination by PM for work to be completed. | SKYE HALL | 212 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  | 29 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2017-12-22 | [6 empty] | 2/1/19; This Project is 100% Complete……1/15/19, DL, Site visit is scheduled with James M. this Thursday…………12/14/18, DL; James Marberry to verify if Monitor is on site. Once monitor is confirmed, we will schedule the work……DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/14 EB Conducted site visit, TV and mount on site. Requires electrical, date and remote control. Notes in FAMMIS. | YES | FS | 0 | 2017 | 2019-03-01
18P000261 |  | 18P000261 | FALSE | SOM | SL5-WEBBER INSTALL A GLASS WINDOW ON ENTRANCE DOOR | Complete as of 9/10/18 | WEBBER | 1143 | COMPLETE | Deborah Deas | Brandon Barbosa | LOURDES ESCAMILLA |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-12-22 | [6 empty] | DL, 7/11/18; Work orders are produced. Need to assign the work order and order material. I will review with Steve and verify target complete date….DL, 7/25/18; Still need to walk the project with Steve……DL, 8/10/18; Material is ordered. We will complete the install when the materila arrives.....DL, 8/22/18; Material should be on site with in 4- weeks. Will schedule install when material is on site. Target date is 9/20/18.......DL, 9/6/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 4/29/18; Pasted from work order;I"nstall a glass window 28x9 on office door in WEBBER, Room 1143. | YES | FS | 0 | 2017 | 2019-03-01
18P000267 |  | 18P000267 | FALSE | BCOE | SL5-CHUNG HALL ROOM 103 NEW FLOOR INSTALL & PATCH & PAINT | Complete as of 7/11/18 | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-01-16 | [6 empty] | DL, 5/19/18; High table mounted on West wall to be relocated to South wall by light "Centered". Relocate white board from East Wall to West walll wher high table was removed. Paint and new flooring. Need to schedule work with Paul and Jess. BKM furniture is scheduled 4-6 weeks. DL, 6/16/18; Lower electrical outlets on North wall, repair blinds, paint and new flooring. The space is vacant as of June 16th. I will scheudle the workl.....BKM delivery is currently scheduled for July 23rd.......This project is 100% complete. There were two items added to the scope and they will be complete by 7/20/18..... |  | Enrico Baez | 4/3/2018 Met with Maggie. She is working with BKM. Floor to go down first. BKM furniture on top. Annotated in Famis. | YES | FS | 0 | 2018 | 2019-03-01
18P000269 |  | 18P000269 | FALSE | CNAS | SL5-BATCHELOR HALL ROOM 1123/1113 NEW OUTLETS TO BE INSTALLED | FS to coordinate with client to scope the work. Customer contacted to schedule a site visit. | BATCHELOR | 1123 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  | 12 | 18 | FALSE |  |  | 2018-01-16 | [8 empty] | Enrico Baez | 5/23/18 EB - Sent email to April requesting site visit. 6/11/18 EB conducted site visit request if for additional outlet only. Single trade only asked Deborah to change to SL6. | YES | FS | 0 | 2018 | 2019-03-01
18P000270 |  | 18P000270 | FALSE | SPP | SL5-CHASS INT S- EVALUATION FOR REMODEL | Pending customer to provide drawing of the space. | CHASS INT S | 4133 | CANCELED BY CLIENT | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Dan Lerman |  | 4 | 2 | TRUE |  |  | 2018-01-16 | [6 empty] | 4/24/18 EB- Per Christina Wong, no loner needed……DL, 5/5/18; Project is cancesled per notes DND 7/27; Please follow up with customer on the status and need for the work; customer advised to me that Dan has the scope of work for completion. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. |  | Enrico Baez | 4/24/18 EB- Per Christina Wong, no longer needed……DL, 5/5/18; Project is canceled per notes DND 6/13; Project reopened and not canceled per conversation with customer. Complete scope review and speak with Luis Alvarez DND 8/20/18: submitted Google form for Project to be reviewed by IRT. 8/19/18 Met with Louis Alvarez. Asked for measured plans from BKM for wall layout and dimensions. emailed again on 9/6 asking for draws. Still waiting for BKM to provide drawings. 9/21/18 Dinh - placed on hold until customer provides BKM drawings. Enrico please manage follow up. 9/24/18-EB BKM drawing rec'd from Luis 9/19/18. On shared drive can be found in file. 10/30/18 EB-Cancelled by Customer | YES | FS | 0 | 2018 | 2019-03-01
18P000273 |  | 18P000273 | FALSE | LIBR | SL5-RIVERA LIB -RESTROOM REFRESH PROJECT | Scope of work has been reviewed; determining how to complete project with trades. | RIVERA LIBRARY |  | TO BE PERFORMED BY PD&C | Steven Mandeville-Gamble | Jackie Bates | DAVID SCHUSTER |  | Dan Lerman |  | 1 | 1 | FALSE |  |  | 2018-01-18 | [6 empty] | DND 12/13/18: Customer advised maintenance requests related to project request has been addressed. Renovation work to be performed by PD&C and customer submitted a CPMS request. DL, 6/16/18; Need to schedule site visit with Dave and Chris P…….DL, 7/11/18; Chris and I will walk this poroject next week…..Wlaked projects with Chris. We need to review in more detail to better determin the process for this project…..DL, 9/6/18. WE need to discuss what we are going to do with this project.... We walked the project but we now need Direction from Facilities leadership… |  | Dan Lerman | DL, 4/29/18; Chris said he is aware of project scope. I need to review with Chris and schedule the work;…..Dl, 5/3/18; Dand to walk project with Chris and Dave to confirm scope. We will sub out tile work. This is paint tile, lighting and plumbing fixture upgrade..... | YES | FS | 0 | 2018 | 2019-03-01
18P000274 |  | 18P000274 | FALSE | GSOE | SL5-SOM FINANCE & ADMIN.-EADY CENTER-SITE SURVEY-CP00003404 | Project is 95% complete; contract in progress for installation of a new door, door frame and ADA operator. Anticipated completion December 2018. | EADY CENTER |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES/BRANDON BARBOSA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-18 | [6 empty] | 2/14/19, DL; This project is Complete………….2/1/19, DL; This project is 99.9% Complete. We still need to conduct Final inspection with Building inspector……1/15/19, DL; The door and automatic opener is scheduled to be installed on 1/22/19……..12/14/18, DL; This project is 95% complete. The contract for the door and ADA operator was awarded today. We will schedule the work shortly after the new year…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Conducted site visit with Gilbert. We need to have a meeting to determin if this work is part of the SLA…… DL, 6/16/18; We still need direction, SLA or Recharge?.......DL, 7/11/18; This Project will require Plans and Permits. We will start on the Plans next Week. We will also issue work orders for work we will complete with in house staff. The Concrete work and Entry Door will need to be contracted out. Target Complete date is 10/1/18……..DL, 7/25/18; Work orders are produced. Planing to walk the project with Chris, Steve B and Robert C. thisw week or next week. We will submit plans to Bob Williams for the contracted work next week……DL, 8/8/18; Completed site visit with Robert C. Steve B, Steve T. and Chris; the Plumbers are complete. The carpenters and electricians will work on their items over the next three weeks. The Plans will be ready to submit on 8/9/18. Once plans are approved, we will proceed to go out to bid for the Concrete and the ADA operator. Target complete date is 9/21/18…….DL, 8/22/18; Plans were apprroved, Concrete Contract is being executed. Still working on Door and ADA operator……..DL, 9/6/18; NTP for Concrete will be issued on Monday. I will schedule the work. I need to follow up on the door order and the ADA operator…….DL, 9/19/18; Concrete walkway scheduled to start on 9/20/18. The new door and Frame will arrieve in 3-5 weeks. We will schedule the install when the new door and frame are on site…….DL, 10/4/18; Concrete work is complete. Still need handrail, signage, door and ADA operator. Target date is Early November….DL, 11/7/18; Project is 95% complete. Contract is being processed to install the new Door, Door Fram and ADA operator. Goal is to have the work complete befor the winter break…… |  | Enrico Baez | Duplicate of 18W011999 project scoped and note entered to make facility ADA compliant. | YES | FS | 0 | 2018 | 2019-03-01
18P000281 |  | 18P000281 | FALSE | VC-UNIV.ADV. | SL5-ALUMNI TO HAVE ADDITIONAL ELECTRICAL OUTLETS ADDED TO ROOM & CUBICAL MODIFICATIONS | Work has been scoped; coordinating trades schedule for work to begin. | ALUM VISITOR | 2202 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | TRUDY COHEN |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-01-24 | [6 empty] | 2/28/19, DL; This work is scheduled…….DL, 5/24/18; Need to verify scope of work with EnricoDL, 7/11/18; Still need to visit the site and schedule the work…..DL, 11/8/18; This project was transferred to John. The target date was 1/2/19….. |  | Enrico Baez | 5/10/18 EB-Customer needs additional outlets in space to accommodate 4 new cubicles. Bob Williams wants additional information with plans. 9/13/18 EB-Met with Dan, Jorge, Rita and Kim. Scope to include patch and painting walls, removing art work, moving thermostat. Cubicles will need whip connections. | YES | FS | 0 | 2018 | 2019-03-01
18P000282 |  | 18P000282 | FALSE | BAS | SL5-EMERG. MANAGEMENT-POLICE BLDG-RELOCATE TO EH&S-CP0000308 | Complete as of 8/10/18 | POLICE BLDG |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | LISA MARTIN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-01-25 | [6 empty] | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work…..DL, 5/9/18; We need to submit plans……DL, 7/11/18; This still needs to be scheduled......DL, 8/8/18; Enrico Confirmed this project is 100% Complete.... |  | Enrico Baez | 2/25 EB Site visit conducted 4/20. EB looking at having FS do work as CORE. Chris informed. DL,5/3/18; Dan to check in with Corey to complete the project. This should not be a large scale project for the work….. | YES | FS | 0 | 2018 | 2019-03-01
18P000284 |  | 18P000284 | FALSE | CNAS | SL5-SKYE HALL REMOVE BOARD - MOVE BOARD AND PATCH AND PAINT | Complete as of 9/21/18 | SKYE HALL | 277 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  | 29 | 23 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-03-01
18P000287 |  | 18P000287 | FALSE | CNAS | SL5-SKYE HALL 2ND FLOOR HALLWAYS/DOORS PAINTING | Complete as of 9/21/18 | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 33 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19/18; This project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-03-01
18P000288 |  | 18P000288 | FALSE | CNAS | SL5-SKYE HALL OFFICE SUITE PAINTING | Complete as of 8/24/18 | SKYE HALL | 208 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-03-01
18P000292 |  | 18P000292 | FALSE | CNAS | SL5-SKYE HALL PAINT MULTIPLE FACULTY OFFICES | Complete as of 8/24/18 | SKYE HALL | 228 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-01-31 | [8 empty] | Dan Lerman | DL, 4/2/18; Project is scoped and Paul D. will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-03-01
18P000293 |  | 18P000293 | FALSE | CNAS | SL5-SKYE HALL COPIER ROOM PATCH AND PAINT | Complete as of 8/24/18 | SKYE HALL | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Paul Ditty |  |  | 32 | FALSE |  |  | 2018-01-31 | [6 empty] | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-03-01
18P000294 |  | 18P000294 | FALSE | CHASS | SL5-HMSS REMOVE DOOR, INSTALL WALL | Canceled on 7/16/18 per email communication with customer. | HUM & SOC SC | 3610 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | HOLD | FALSE |  |  | 2018-02-01 | [8 empty] | Enrico Baez | 5/23/18 EB sent email request for site visit DND 7/14 Hold per customer on prioritization Canceled per customer on 7/16/18 via email with Enrico. | YES | FS | 0 | 2018 | 2019-03-01
18P000295 |  | 18P000295 | FALSE | CHASS | SL5-CHASS INT S - REMOVE CAGE/CASEWORK/INSTALL DRYWALL | Complete as of 9/21/18 | CHASS INT S | 2117J | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-02-01 | [6 empty] | DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18……..DL, 5/24/18; Plans were approved. We need to scheudle the work….DL, 6/16/18; Materila is ordered. Once doors/frames arrrive, we will schedule and star the work. The doors are 90-minute rated and have a 3- 4 week lead time. The space is vacant and work can start on the demo portion of the wall, cage and cabinets.......DL, 7/11/18; The Target start date is 7/18/18 and scheduled to be complete on 8/17/18......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/8/18; Passed Framing andrough electrical inspection today. The carpenters will install doors and drywall over the next week. Paint crew will be able to start sometime next week. we are still on track for 8/17/18 complete date.....DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18...........DL, 9/6/18; This project is 90% complete. Items pending are ceiling tile grid attachement, cove base and door lock hardware..... |  | Enrico Baez | 4/25 EB Scoped site. Remove counter and Cage. Drywal closed with electrical. Patch Paint. Cut in two doors in 2117G&H……..DL, 4/29/18; I need to submitt the plans to Bob and Scott for review and approval…..5/5/18; DL; Plans submitted on 5/4/18…….. | YES | FS | 0 | 2018 | 2019-03-01
18P000296 |  | 18P000296 | FALSE | CNAS | SL5-SKYE HALL PAINT SEVERAL GRADUATE STUDENT OFFICES | Contract is being processed; target project completion is end of September. | SKYE HALL | 266 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAMES MARBERRY |  | Dan Lerman |  |  | 31 | FALSE |  |  | 2018-02-02 | [6 empty] | 01/17/19, DL; This project was completed last summer……..DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K…..DL, 8/22/18; We will outsource this work. Contract is being Processed by PD&C. Target date is 9/21/18….DL, 9/19 18; I neeed to check on this work order. I thought it was part of the 2nd floor Hallway project but it was not…… |  | Dan Lerman | DL, 4/2/18; Project is scoped and Paul will complete this work in early summer. The combind project will not exceed $25K | YES | FS | 0 | 2018 | 2019-03-01
18P000297 |  | 18P000297 | FALSE | CHANCELLOR | SL5-SKYE HALL CHECK LOCATION FOR TV INSTALL | Scope of work has been reviewed; determining how to complete project with trades. | SKYE HALL | 390 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Dan Lerman |  | 4 | 3 | FALSE |  |  | 2018-02-02 | [6 empty] | 2/1/19, DL; This Project is 100% Complete………1/18/19, DL; This Project is scheduled to be complete next week.….. DL, 5/24/18; Need to verify scope with Enrico…..DL, 7/11/18; Work orders are produced and need to be issued. Target complete date is 9/3/18…. |  | Enrico Baez | EB-scoped on 1/30. Mount TV above table. Advised an articulated mount be purchased. Drawing on FAMMIS WO. | YES | FS | 0 | 2018 | 2019-03-01
18P000300 |  | 18P000300 | FALSE | CHASS | SL5-ARTS PATCH AND PAINT - DANCE HALLWAYS | Complete as of 8/24/18 | ARTS |  | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 24 | FALSE |  |  | 2018-02-02 | [6 empty] | centered. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000310 |  | 18P000310 | FALSE | CNAS | SL5-ADD INTERCOM/BUZZ IN SYSTEM | Complete as of 10/22/18. | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-12 | [6 empty] | Dl, 7/4/18; This project is scoped. This will be a new ADA operator, door bell / Intercom and buzzer button to unlock door. Walked work with Contractor, need to work on producing contract with PD&C. Once Contract is confirmed, we will schedule the work..... DL, 7/11/18; We have the proposal. Need to execute the agreement and schedule the work. The target complete date is before 10/1/18.....Dl 8/10/18; Jason will try and complete the work with in the next three weeks......DL, 8/22/18; Jason order parts, parts have 6-8 week lead time. Work will be scheduled when material arrives.....DL, 10/4/18; This Project is 100% Complete....... |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | FS | 0 | 2018 | 2019-03-01
18P000312 |  | 18P000312 | FALSE | CNAS | SL5-URGENT ENSC: TRAILER 14 REMOVAL - LOT 42 | Canceled per customer 9/12/18 | CAMP LOC NOT IN BLDG |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | Canceled | 38 | FALSE |  |  | 2018-02-13 | [8 empty] | Enrico Baez | EB, 5/29, conducted site visit 5/25. Structure is a double wide modular building/trailer. Space needs to be cleared of equipment, desks, tools. Disconnect electrical, plumbing. Needs professional removal. University Asset see Susan Marshburn for direction. EB, 9/12/18 Per Deborah McWilliams email.Project is cancelled due to lack of funding. | YES | FS | 0 | 2018 | 2019-03-01
18P000313 |  | 18P000313 | FALSE | GSOE | SL5-SPROUL PAINT THE WALLS IN SPROUL BLDG. 3, FLOORS 1 AND 2 | Complete as of 10/22/18. | SPROUL |  | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-15 | [6 empty] | 18W011689 Work order was cancelled because it has the same scope and is a duplicate………DL, 6/16/18; Contract is being awarded this week. Weill are scheduled to have this work completed by fiscal closing……DL, 7/25/18; This Project is 100% Complete…..9/13: Zee - Customer noted paint peeling; updated to status to back in progress for work to be addressed.......DL, 9/19/18; The contractor is on site repairing the walls and painting. The work should be complete this week.......dl, 10/4/18; tHIS PROJECT IS 100% Complete..... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000314 |  | 18P000314 | FALSE | CHASS | SL5-CMP PATCH AND PAINT CEILING OF CMP 1ST FLOOR | Complete as of 7/25/18. | CA MUS PHOTO | 1000 | COMPLETE | Milagros Pena | Cindy Williams | EMILY PAPAVERO |  | Dan Lerman |  |  | 17 | FALSE |  |  | 2018-02-16 | [6 empty] | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date.......DL, 7/25/18; This project is 100% Complete..... |  | Enrico Baez | 2/15/2018 E.Baez Conducted site visit. Several areas on ceiling have peeling paint. EH&S tested sample came back negative for ACM and Lead……...…….DL, 4/2/18; Project is scoped and we are obtaining quotes to complete the work. We need to try and have this project complete by Mid May…..DL, 4/16/18; Paint portion is over $25 K. We now need to informerly bid this project with Multiple contractors. Job walk is cheduled for this Tuesday at 2:00 pm. Bids will be due on 4/18/18......DL, 4/29/18; Project is in process of being processed. Hopefully we will have signed NTP soon. May 25th target date....... | YES | FS | 0 | 2018 | 2019-03-01
18P000315 |  | 18P000315 | FALSE | BCOE | SL5-BOURNS PARTITION WALL WITH DOOR FOR CYBART LAB | Complete as of 8/23/18 | BOURNS | B0235 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  | HOLD | TRUE |  |  | 2018-02-16 | [6 empty] | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction to scope, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... Need to walk project with Ron and schedule the work....DL, 5/24/18; Conducted site visit with Ron V. Ron will order material and schedule the work once material is on site.....DL, 6/16/18; Need to verify delivery date for material.......DL. 7/11/18; Plumbing is disconnected. Corey is tentatively scheduled to disconnect the Fume hood. Once the Fume hood is disconnected, we will schedule the removeal of the fume hood and start the framing of the wall. Target complete date is 8/8/18....DL, 7/25/18; Fume hood is disconnected. Need to move Fume hood and start framing target date is delayed to creep scope but should be complete near 8/16/18.....DL, 8/10/18; Carp[enters will install the wall this week. Corey has parts orders. Corey will complete the install when the material arrives.......DL, 8/22/18; This Project is Complete |  | Dan Lerman | DL, 4/29/18; This project is scoped. This is for a clean room. Plans and permits will probably be required. Coducting final scope walk with Shane this week. We will schedule this work to be complete once we have plans or direction form Campus building official....DL, 5/5/18: Correction, This is a to frame two 3'X 8' tall walls to aid in sound proffing. We are staying clear of any fire sprinklers and ventleation. No Permanet space alteration to space...... DND 7/14 Hold per customer on prioritization | YES | FS | 0 | 2018 | 2019-03-01
18P000318 |  | 18P000318 | FALSE | CHASS | SL5-CHASS INT S FLAT SCREEN INSTALLATION | Plans are being reviewed; work to be scheduled once plans are approved. | CHASS INT S |  | IN PROGRESS | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Dan Lerman |  |  | 20 | FALSE |  |  | 2018-02-21 | [6 empty] | 2/28/19, DL; Scheduled to complete the install mid March…..2/1/19, DL; Francesca contacted me and informed me this project is now back on the books. She needs to gather more information and order the monitor. When the monitor arrives, we will schedule the installation…….1/29/19, DL; Francesca confirmed this project is not needed and requested this project to be cencelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; we have the brackets. Will scheule the work after the project is approved…..DL, 7/11/18; Work order are not produced. Need to assign and schedule the work…. Target complete date is 8/3/18……DL; 7/25/18; Need to change target date.. |  | Enrico Baez | 5/24/18 Conducted site visit. Met with Ryan Amriano. Electrical near buy. No data connection needed. Awaiting for dept. approval. They first wanted to know if this was possible. | YES | FS | 0 | 2018 | 2019-03-01
18P000321 |  | 18P000321 | FALSE | BCOE | SL5-STUDENT SERV ROOM 1228 REPLACE ENTRY DOOR REQUEST | Complete as of 8/10/18 | STUDENT SERV | 1228 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Enrico Baez |  |  |  | FALSE |  |  | 2018-02-22 | [6 empty] | DL, 4/29/18; Enrico is cordinationg this. The permits are approved……. DL, 7/11/18; Just received confirmation the door is ready for delivery and installed. I need to check in with Paul about the paint and prep of the door. I also need to check in with Jason on lock hardware......Dl, 7/25/18; Door is painted and ready for install. Called Dugmore to schedule the install. This should be compolete within the next two weeks......DL, 8/8/18; This Project is 100% Complete |  | Enrico Baez | DL, 4/29/18; Enrico is cordinationg this. The permits are approved. EB. 5/11/18- waiting for PO to be issued to Vendor. Customer provided PO numbers, waiting to schedule install with vendor, 5 week lead time. | YES | FS | 0 | 2018 | 2019-03-01
18P000324 |  | 18P000324 | FALSE | PLANNING & BUDGET | SL5-HINDERAKER PATCH AND PAINT | Complete as of 7/11/18 | HINDERAKER | 4118 | COMPLETE | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-02-26 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000328 |  | 18P000328 | FALSE | ATHLETICS | SL5-HINDERAKER BASEMENT OFFICE REPAIR | Complete as of 7/11/18 | HINDERAKER |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-01 | [6 empty] | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with Paul. Paul will complete as in the near future. Carpet will be installed shortly after......5/21/18, Painters started paint. Should be complete with paint by the end of the week....DL, 5/24/18; Painters are complete. Jess will schedule the carpet install.....DL, 6/12/18; Project is 98% Complete. Carpenters need to under cut two doors to accomodate the carpet.....DL, 7/11/18; This Project 100% Complete..... |  | Dan Lerman | DL, 4/29/18; Project is paint and flooring. Walked project with Paul and Paul will schule the work. Once paint is copmplete, we will schedule the carpet install. This space is vacant. Johnathan's requested target date is Mid- June - August…..DL, 5/5/18; Walked project with PAul. Paul will complete as in the near future. Carpet will be installed shortly after...... | YES | FS | 0 | 2018 | 2019-03-01
18P000329 |  | 18P000329 | FALSE | CHANCELLOR | SL5-SKYE HALL GENERAL ASSIGNMENT CLASSROOM RENOVATION (CARPET, PAINT, FLOORS, ELECTRICAL, LIGHTS) BEHALF OF PROVOST | Project complete as of 9/18/18 | SKYE HALL | 170 | COMPLETE | Kim Wilcox | Karim Zahedi | DA LAN DINH |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18…..DL, 5/24/18; Plans were approved. Demo work has started......DL, 6/12/18; MArshal and Kate are working on Carpet order......DL, 7/11/18; Carpet is ordered. We have a challenge with Title 24. I am working on the title 24 documents. We are still planning to have this project complete on 8/17/18......DL, 8/10/18; We now have the Title 24 plans. The are being reviewed by Bob and Scott.....Title 24 plans approved. Robert is working on PO#. Most parts are on site and Electricans are working on project. All other Trades to follow once Lights are in...... Hard Date of 9/7/18............9/6/18 As of today, Carpet is scheduled for install tomorrow morning and furniture is scheduled for delivery this Monday......WE will more than likely have electrical punch items and touch up paint but this propject should be 100% complete in regards to FS the end of next week next week......100% PROJECT COMPLETE... GREAT WORK DAN! |  | Dan Lerman | DL, 4/21/2018; Scope is complete. Working on obtaining estimates for conrete and ADA operator. Also working on Plans for the permit process. Target completion date is August 1st…..DL, 5/5/18; Plans were submitted on 5/4/18….. | YES | FS | 0 | 2018 | 2019-03-01
18P000337 |  | 18P000337 | FALSE | VC-STU.AFF. | SL5-MODIFY WALL OPENINGS, TRIM AND INSTALL CARPET | Plans are approved for work to commence; scheduled for start on 11/13/18. | HEALTH SERV | 414 | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-12 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18….Need to work on plans and permits….DL, 7/11/18; Gunther is working on plans. Target complete date is 9/14/18….DL, 7/25/18; Planning to submit plans for review next week. We will schedule the work once we have approved plans…….DL, 8/8/18; This is a structual wall and needs to be engineered. We are meeting with the Structual engineer on 8/9/18 to determine if project is possible.....DL, 8/22/18; Working on EDPA for Structual engineer; project timeline is late Fall. 9/19/18; The Agreement / Cointract for the structual engineer is processed for this project. We should have plans from the structual engineer to submitt to the Building Official and fire marshal with in 4- weeks......dl, 10/4/18; Plans are almost complete and we will submit them for review by the end of the week.....DL, 11/7/18; Plans are approved. WE are schedule to start this Project on Tuesday 11/13/18. Target complete date is by the end of the winter break..... |  | Enrico Baez | Cut wall between rooms 414 and 401, Case and trim opening, install carpet in- DL, 5/10/18; Gloria Vera is the contact; 827-5532 | YES | FS | 0 | 2018 | 2019-03-01
18P000341 |  | 18P000341 | FALSE | CNAS | SL5-PHYSICS 1132-ABATEMENT, PLUMBING, PAINT/PATCH, EQUIP REMOVAL | AQMD notification was sent; abatement to begin at the end of notification period. | PHYSICS | 1132 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-14 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process…DL, 6/16/18; Jess tested the matreial flooring and paint is hot. Jess will abate before we proceed with the project….Still need to scheudle the work. This project target complete date is late Fall……DL, 7/25/18; Jess sent out the 14-day notification to the AQMD last week. We will start the balance of the project after the ACM and Lead is abated or encapsulated…..8/10/18; Abatement is complete. We will work on the other items as time permits. This space is vacant with no occupancy date |  | Dan Lerman | DL, 4/2/18; Project is scoped. This has ACM and Lead paint. Needs complete refresh including new floor. The space is vacant and ready for Jess to start the abatement process… | YES | FS | 0 | 2018 | 2019-03-01
18P000343 |  | 18P000343 | FALSE | CHASS | SL5-UNIVERSITY THEATRE REPAIRS: RAIL, LATCHES, ANCHORS, LADDER | Scope of work has been reviewed; determining how to complete project with trades. | THTR WKSH | 0400A | QUEUE TO START | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 22 | 2 | FALSE |  |  | 2018-03-16 | [6 empty] | 1/15/19, DL; This project is in progress but I need to follow-up with Ron R for a status update……DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Still need to walk rproject with Enrico. We did discuss the scope but there are many task in various areas thorugh out the auditorium……. Target complete date is late Fall…… |  | Enrico Baez | 5/11/18 EB-Conducted site visit on 3/21/18. Work based on Safety report written in October. Work consists of replacing door latches to orchestra pit. Adding loading dock rail, Paint frame guard, signage, gate/fall restraints, ladder modifications. | YES | FS | 0 | 2018 | 2019-03-01
18P000344 |  | 18P000344 | FALSE | CHASS | SL5-CHASS INTS PAINT MULTIPLE ROOMS - FACULTY | Complete as of 9/10/18 | CHASS INT S | 2117E | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 1 | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 7/11/18; This was transferd in to my quque in the past week. I need to scope this project. I belive this is part of project # 18P000205 and 18P000295. If this is part of the other project. We will try to have the paint completed by 8/17/18…......DL, 7/25/18. Carpenters started the work and Electricains will start on 7/27/18....... DL, 8/10/18; Work has started. We passed rough electrical and framing inspection. The work should be complete in about three weeks......DL, 8/22/18; Work is 75% complete. Tape/Mud/Paint, Final electrical, Hardware, cove base and punchTwo Target date, 8/31/18.......DL, 9/6/18; This Project is 100% Complete....... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000346 |  | 18P000346 | FALSE | ATHLETICS | SL5-ATHLETICS INSTALL WALL VOLLEYBALL OFFICES | Complete as of 11/8/18 | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-18 | [6 empty] | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. DL, 5/24/18; We will start working on plans in the near future.... DL, 6/16/18; Need to submit plans asap.......DL, 7/11/18; The plans were approved today. This project is scheduled to start on 7/14/18. We will will be complete will all items related to this project on 8/27/18. Note, The door and sidelite are special order items and this item will probalby have a 6-8 week lead time. Steve T is going to order the door soon.. Customer is aware of the delay for the door and is not concerned......DL, 7/25/18; Passed framing and Electrical inspection. We will be finished with the project next week except for the door and window that is ordered but has a 6-8 week lead time. DL, 8/10/18; This Project is Complete except for special order door and window.......DL, 8/22/18; Door and Glass still not on site., Will check in with Steve T on delivery date......Will also schedule final inspection for Certificate of occupancy......9/6/18; The Glass window is installed but we are waiting on the door. this projects is 98% complete.......DL, 9/19/18; The door will be shipped on 9/24/18. We will schedule the door install when the door is on site......DL, 11/7/18; This Project is 100% Complete.... |  | Dan Lerman | Dl, 4/2/18; This has been scoped. Plans and permits are required. Project target date is August. This project includes new wall, door and we will probably need to split the return air registers….DL, 5/5/18; Coducted scope walk with Ron and clinet. Will start working on plans.... | YES | FS | 0 | 2018 | 2019-03-01
18P000347 |  | 18P000347 | FALSE | CNAS | SL5-GEOLOGY MONITOR INSTALL (ELECTRICAL, DATA, CARPENTRY) | Scope reviewed by BZM; coordination by PM for work to be completed. | GEOLOGY | 0 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 31 | Deferred to Fall Quarter - summer priority 27 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/14/19, DL: The monitor is on site. We need to schedule the installation. 2/1/19, DL; Conducted site visit with Amber. Amber will order the monitor. We will schedule the installation when the monitor is on site………….DL, 7/11/18; Need to produce work orders and schedule the work…. 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. |  | Enrico Baez | 6/1 EB Site visit. TV to be mounted on wall above water fountain across from Geo 2306. Center of mount 84" high and centered between wall corner and bulletin board. Will need electrical and data. Computer connection cutout will be in mail room. See W.O. | YES | FS | 0 | 2018 | 2019-03-01
18P000348 |  | 18P000348 | FALSE | VC-STU.AFF. | SL5-HUB ADD 3RD FLOOR WALLS | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | HUB | 0353E | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  | 2 | 6 | FALSE |  |  | 2018-03-18 | [6 empty] | 2/1/19, DL; Per Chris P. This is a PD&C project………..DL, 5/24/18; Need to meet and review with Enrico……DL, 7/11/18; Need to walk the project with Manny. Target date is late Fall…….. |  | Enrico Baez | EB 5/23/18. Conducted site visit. Request is for adding walls to interior spaces 353F, 381 and 377. Will impact A/C and fire protection. Still waiting for a firm plan from customer. | YES | FS | 0 | 2018 | 2019-03-01
18P000349 |  | 18P000349 | FALSE | BCOE | SL5-PHYSICS INSTALL PARTITION WALL FOR LAB ROOM | Complete as of 7/11/18 | PHYSICS | 1037 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-03-18 | [6 empty] | DL, 5/24/18; Ron V. has detailed scope and he is ordering material. Once material arives, we will schedule the work…. DL, 6/16/18; Materila is ordered, When door/frame arrives, we will prep, paint and start the work…….DL, 7/11/18; This Project is 100% Complete..... |  | Dan Lerman | DL, 4/2/18; This is a small partition wall with sound proofing to minimize noise from the compressor that is disruptive to the Helium Ion Microscope…….DL, 4/16/18; We will schedule this work to be complete by the end of the Spring quarter. DL, 5/19/18; Walked project with Ron. FAMIS work order producd and material is being ordered.... | YES | FS | 0 | 2018 | 2019-03-01
18P000351 |  | 18P000351 | FALSE | SoB | SL5-REMOVE/REPOSITION PROJECTION SYSTEM-021 | Carpentry work is in progress; electrical work to be scheduled followed by paint. | ANDERSON 2 | 21 | HOLD - FACILITIES SERVICES | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 3 | FALSE |  |  | 2018-03-19 | [6 empty] | DL, 5/24/18; Plans will be needed for this project because we will relocate a smoke detector……DL, 7/11/18; Conducted site visit and verified scope. Need to assign work orders and schedule the work. Target complete date is 9/21/18…. Permits may be needed for this project. I will walk the project with Robert C. next week......8/8/18. The trades are ready to go after they finish current projects.....DL, 8/22/18; Carpentry is almost complete. Still need to walk with Robert ASAP, once electrical work is confirmed, we will scheudle the paint. Still on target for 9/21/18.......... DL, 9/19/18 This project is complete except the electrical and paint. Unfortunately, we missed our window for access to the space and we will work with Angela on blocking out the space so we can finish the electrical at a later date........9/19/18; This project is 90% complete but now on hold. We missed our window with the electricans. We will work with Angel and schedlue the balance of the electrical and final paint when she can block out the space......Note. The space is usable and everything works..... |  | Enrico Baez | 4/24/18 EB-scoped. Move screen, correct non-compliant electrical issues, remove&discard overhead projector bracket, relocate heat det. Add switched outles. Plans are needed because we are relocating a heat detector | YES | FS | 0 | 2018 | 2019-03-01
18P000353 |  | 18P000353 | FALSE | CHASS | SL5-PSYCHOLOGY GLASS WALL NEEDS FROSTED SPRAY -PATCH & PAINT | Complete as of 8/23/18 | PSYCHOLOGY1 | 1111A | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 26 | FALSE |  |  | 2018-03-20 | [6 empty] | DL; 7/4/18;This project is scoped. We will only paint one out of the two offices. Working on PO# to install frosted glass with Sun Down Window coverings……DL, 7/25/18; PO# is produced and material is ordered. Target date mid August…….DL, 8/22/18; This project is complete.... |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000354 |  | 18P000354 | FALSE | CNAS | SL5-GH16-25 COOLING SYSTEM REPAIR | Work considered deferred maintenance not a minor renovation. | GH 16 25 |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | MARK TANKERSLEY |  | Dan Lerman |  | 13 | 17 | FALSE |  |  | 2018-03-20 | [6 empty] | DL, 7/25/18; Reviewed Ron V. noted. I will check in with Chris on this to better determin the method complete this project. |  | Dan Lerman | DL, 5/5/18; This is a repair, No alterations taking place. Pasted from FAMIS work order...THE COOLING SYSTEM ON GH 16-25 IS FALLING APART SHEET METAL TRAYS HAVE TONS OF HOLES, WOOD ROTTING ETC. PLEASE REPAIR….. RV, 07/06/18: Dan, Chis Pillen and I have walked this project months ago and have a quote from Ralph Cox/KIRA Construction to repair the head house damages. See Chris for the status of subletting this work. | YES | FS | 0 | 2018 | 2019-03-01
18P000356 |  | 18P000356 | FALSE | CNAS | SL5-ENTOMOLOGY PATCH AND PATCH | Complete as of 8/24/18 | ENTOMOLOGY | 278 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 10 | TRUE |  |  | 2018-03-20 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000363 |  | 18P000363 | FALSE | BAS | SL5-PAINT STOREHOUSE ADMINISTRATIVE OFFICE | Complete as of 11/8/18 | CORP B |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | ERICA HENDERSON |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-03-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
18P000367 |  | 18P000367 | FALSE | CHASS | SL5-CHASS INT N PATCH AND PAINT - STUDENT ADVISOR OFFICE | Complete as of 7/14/18 | CHASS INT N | 3033 | COMPLETE | Milagros Pena | Cindy Williams | SARAH NOSCE |  | Paul Ditty |  |  | 23 | FALSE |  |  | 2018-03-27 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000369 |  | 18P000369 | FALSE | BAS | SL5-BOYCE X-RAY IRRADIATOR PROJECT | Material required for project completion arrived on site; scheduling the work with the availablity of the teams. | BOYCE | 1407 | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | KAREN JANIGA |  | Dan Lerman |  |  | 4 | FALSE |  |  | 2018-03-27 | [6 empty] | 12/14/18, DL; This project was cancelled……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……DL, 5/9/18; Need to work on plans/permits…..DL, 6/16/18; Meeting with Bob and confirmed what is needed. I will work with Gunther on plans. Had discussion. Ken will work on single line diagram we can provide to Gunther so he can work on the plans for submittal. If plans are approved. We will have a target complete date of mid Fall…..DL, 11/7/18; Material is on site. We will schedule the work soon…… |  | Ron Veloz | DL, 4/29/18; Walked project with Darrin and Ron from HVAC. We will go with a mini split. Still need to walk project with Robert C……Need to work on plans….10/17/18 RV: This project was previously scoped and in Plan development. | YES | FS | 0 | 2018 | 2019-03-01
18P000373 |  | 18P000373 | FALSE | BAS | SL5-POLICE BLDG PAINTING IN DISPATCH AREA | Complete as of 7/14/18 | POLICE BLDG | 100 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  |  | 8 | FALSE |  |  | 2018-04-02 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000379 |  | 18P000379 | FALSE | VC-RED | SL5-UOB PATCH AND PAINT | Complete as of 8/24/18 | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-05 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000380 |  | 18P000380 | FALSE | SOM | SL5-SOMR PELLECCHIA LAB REQUESTING TV MOUNT INSTALLATION | Canceled per customer per conversation with FS Building Zone Manager. 8/22/18 | SOM RSCH | 330 | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-04-05 | [6 empty] | Canceled per customer on 8/22/18. |  | Enrico Baez | DD 7/17: Requested Enrico verify complete customer did not prioritize and noted work was done. 8/7/18-Conducted site visit-do not recommend location for TV due to potential damage from barn door type window screen. 8/15/18 emailed Tara Bathol that desired location for TV not recommended. Requested alternate location. 08/22/18 Ron V. Spoke with Tara. Tara confirmed the requestor cancelled the TV mounting bracket request after conversation with Enrico | NO | FS | 0 | 2018 | 2019-03-01
18P000381 |  | 18P000381 | FALSE | ITS | SL5-ORG21 INFO. TECH SOLUTIONS-WATKINS-RENOVATIONS-CP0003412 | FS to coordinate with customer to schedule the work for completion. | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 3 | 4 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL; This project is complete. Note, Duffy only wanted the dutch door completed……..12/14/18, DL; This project is in progress and should be complete shortly after the new year……`DL, 7/11/18; Need to walk the project and schedule the work…… | 2018-07-06 | Ron Veloz | 06/26/18 Ron V. visited site & met with Duffy. Scope of work for rm's 2103 & 2103 A requires: Painting of walls and conduit locted on the walls, replace damaged ceiling tiles, replace one damaged prismatic 2x4 light fixture lense, remove one tack board and shampoo carpet. Existing wall tiles to remain and receive paint. No work required in 2103 B per Duffy. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | FS | 0 | 2018 | 2019-03-01
18P000382 |  | 18P000382 | FALSE | ITS | SL5-ORG21 INFO TECH SOLUTIONS-WATKINS-INSTALL SPLIT DOOR RENO. -CP00003126 | Plans will be developed and will be submitted for review and approval. | WATKINS |  | COMPLETE | Danna Gianforte | Shelley Gupta | PHYLLIS FRANCO |  | Dan Lerman |  | 2 | 3 | FALSE |  |  | 2018-04-05 | [6 empty] | 1/15/19, DL, This project is Complete……12/14/18, DL; This project is scheduled to be complete shortly after the winter break…….This project was scoped previously with the IR Team. We may need plans or a permit because we are installing a Dutch door…..DL, 7/11/18; Need to produce work orders and schedule the work….. DL, 7/25/18; Still need to produce work orders and schedule the work. Target date is 10/1/18 | 2018-07-06 | Ron Veloz | 06/29/18 Ron V: SOW, Remove the existing non rated solid core door & grille and replace with a new maple veneerd Dutch door with prefinished clear coat without grille. Door to be prepped on the hinge side with one continoues hinge. Confirm/field verify is a double bevel on door is requird. Do not prep the strike/lockset side.. Cylinder to be bored onsite by Lock shop. The top of the lower door to have a small shelf + - 6-8 inches wide, confirm size with Duffy prior to ordering the door. 07/06/18 RV: Uplaoded pics & Docs to FAMIS | YES | FS | 0 | 2018 | 2019-03-01
18P000383 |  | 18P000383 | FALSE | CHASS | SL5-HMSS---PAINT WALLS IN ROOM 1302 AND 4402 URGENT | Completed as of 8/10/18 | HUM & SOC SC | 1302 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  |  | 4 | TRUE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000385 |  | 18P000385 | FALSE | CHASS | SL5-HMSS INSTALL TV IN CONFERENCE ROOM | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 1001E | IN PROGRESS | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Dan Lerman |  | 19 | 19 | FALSE |  |  | 2018-03-06 | [6 empty] | 12/14/18; Monitor is Complete, we still need to install power. The space is vacant…DL, 6/16/18; Pasted notes from FAMIS; University Writing program wants to install a 65 inch TV in the conference room at HMNSS 1001E. 1. Request to install the TV mount/ bracket on the wall; 2. Request to remove the old projector screen but leave two wood blocks on the wall; 3. Request to add a new double power outlet around the TV bracket area. If you have any questions, please contact Shanshan Liao at (shanshan.liao@ucr.edu or X27753)……DL, 7/25/18; Work orders are not produced. Need to assign and schedule the work…..……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | 6/11/18 Install TV above wainscot. Notes in FAMMIS. Need electrical and date cut ins. | YES | FS | 0 | 2018 | 2019-03-01
18P000387 |  | 18P000387 | FALSE | CHASS | SL5-HMSS PATCH/PAINT | Complete as of 8/24/18 | HUM & SOC SC | 3600 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 28 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000388 |  | 18P000388 | FALSE | CNAS | SL5-SPIETH DISCONNECT GLASS WASHER/ASSESS NEW INSTALLATION | Equipment has been disconnected; equipment to be removed upon availability of the teams. | SPIETH | 0317A | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 22 | 22 | FALSE |  |  | 2018-04-10 | [6 empty] | DL, 7/11/18; Need to walk the project, Verify scopoe, This poroject may require plans. If plans are required we will scheudle the work after the plans are approved…..DL, 7/25/18; Sent Estella an email requesting to meet. I will have a better idea of the project time line once I review the plans....DL, 8/8/18; Walked project with Estella. This project will be scheduled for Fall/ early winter....DL, 11/7/18; The equipment is disconnected. We will work on the removal and installation but htere is no hard date as this is vacant space and we will access the space as time permits...... |  | Enrico Baez | 6/21/18 EB Remove old glass washer and install washer 400XLS. Disconnect steam, air, water, electrical, vent hood. Install new washer, electrical, step up x-former 208v to 480. Dept. to purchase x-former $5000 ill to dept. Elect. To provide specs. | YES | FS | 0 | 2018 | 2019-03-01
18P000389 |  | 18P000389 | FALSE | CHASS | SL5-PSYCHOLOGY PATCH AND PAINT/ CARPET 2122, 2124, 2111A | Complete as of 11/8/18 | PSYCHOLOGY1 | 2122 | COMPLETE | Milagros Pena | Cindy Williams | ERICA RAMIREZ |  | Paul Ditty |  |  | 5 | TRUE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000390 |  | 18P000390 | FALSE | PLANNING & BUDGET | SL5-UNIV VILLAGE PATCH PAINT AND RE HANG JOCELYNES WHITE BOARD | Complete as of 8/24/18 | UV BLDG B | 0240B | COMPLETE | Gerry Bomotti | TBD | LESLIE ROSE |  | Paul Ditty |  |  | 1 | FALSE |  |  | 2018-04-10 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000391 |  | 18P000391 | FALSE | BCOE | SL5-PATCH, PAINT, NEW FLOOR IN DEANS OFFICE, LOBBY, AND ADDITIONAL SPACES AS NEEDED IN PREPARATION FOR NEW DEAN | Complete as of 9/10/18 | CHUNG HALL | 446 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 5/5/18; Conducted scope visit with Paul and Maggie. This project is target date is August 30th. As of now, we have 10 business days to complete the work……. Dean's Office….DL, 6/16/18;Walked project with Jess and Paul. This will be a project will now incluclude flooring is 7- additional offices due to additional trip hazzards identified in 3 of 7 offices during the carpet scope. Maggie will pay four four of the office since they are still in good condition. We are still on schedule with the work.......Dan, 7/11/18; This project is still on schedule. Complete Date is 8/18/18 and scheduled to be complete on 8/31/18.....DL, 8/10/18; The project is on schedule and we will start on Monday.......Ahead of schedule, project will be complete on 8/29/18......DL, 9/6/18; This project is 100% complete. Note, Maggie did request Jess to come back and remove some glue and he has this scheduled..... |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-03-01
18P000392 |  | 18P000392 | FALSE | CNAS | SL5-BATCHELOR HALL PATCH AND PAINT 2113 AND 2129 | Complete as of 8/24/18 | BATCHELOR | 0 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  |  | 8 | TRUE |  |  | 2018-04-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000394 |  | 18P000394 | FALSE | BCOE | SL5-BOURNS A-WING 1ST FLOOR A-159A,B,C,D - SOUNDSOAK | Project work has been complete but work is being reviewed by faculty. Sound soak may be installed. | BOURNS | A0159A | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  |  | 2 | TRUE |  |  | 2018-04-12 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………….1/15/19, DL; Sound Soak is ordered and should arrive within two weeks……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 6/16/18; Need to review and scheudle…….DL, 7/11/18; Still need to review and scheudle…..DL, 8/22/18; This Project is complete but Maggie wants to see if the Faculty are happy with the results. We may install Sound Soak as a final option…… DL 9/6/18; Sent Maggie an email to see if she is satified with the work performed in regards to the sound proofing. I will have an update by the next Excel update….. DL, 9/19/18; The PI is out of town. Maggie will confirm the PI is satisiofd with the work when they return……on 9/18/18…DL, 10/8/18; Customer not satisfied with first round of sound proofing. We will proceed with Sound Soak material….. |  | Enrico Baez | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. EB 6/1 site visit- 3 door between 4 offices require sound proofing. Doors measure 36" x 106". Photos in FAMMIS. O-RVL: Uploaded sound soak panel data on FAMIS and is available on the Project Server File. 10/18/18 O-RVL: Per FS team meeting, we now have a clarified process that sound soak is not included in the SLA due to the fact this is not part of the work we perform at FS. Because we already committed to do further follow up with the sound soak, we will not charge this time but moving forward sound soak will be a recharge service as the team does not have the skillset to do the work and therefore outside the SLA. | YES | FS | 0 | 2018 | 2019-03-01
18P000396 |  | 18P000396 | FALSE | CHASS | SL5-WATKINS PATCH & PAINT-WAT HALL 2122A & 2122D | Complete as of 8/24/18 | WATKINS | 2122 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | 6 | TRUE |  |  | 2018-04-13 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000398 |  | 18P000398 | FALSE | CHASS | SL5-WATKINS ESTIMATE FOR SEALING OF ADJOINING DOORS | Complete as of 10/22/18. | WATKINS | 2204 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-04-16 | [6 empty] | DL, 7/11/18; Need to walk project and verify scope and target complete date…..DL, 7/25/18; Verified scope. We need to order a new door and floor covering and need to schedule the abatnent, we will plan to start this project in 3- 4 weeks. Target complete date is late August.....DL, 8/8/18; Jess conducted the visit with the abatment contractor. Still need to verify abatment date. Carpenter shop is aware of the scope and they are ordering material. Note, one of the doors will have a lead time of 4- 6 weeks. .....DL, 8/22/18; Abatment is taking place this week. We will schedule the paint and carpet over the next week. This projcet all items for this project will be complete by 9/21/18. DL, 9/19/18; the Door was stained today and will be installed asap. The cove base is back ordered and will be installed when it is on site..target date is complete early next week...... DL, 10/4/18; This Project is 100% Complete....... |  | Enrico Baez | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. | YES | FS | 0 | 2018 | 2019-03-01
18P000400 |  | 18P000400 | FALSE | SOM | SL5-Covert suite 1116 and suite 1126 to office space | Provost has placed a hold on converting lab spaces into office spaces. | WEBBER | 1116 & 1126 | HOLD - FACILITIES SERVICES | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | HOLD | HOLD | FALSE |  |  | 2018-04-14 | [6 empty] | DL, 6/16/18; Waiting for update on Provost approval….DL, 7/11/18; Per email from Enrico on 7/10/18. The Provost put a hold on converting any lab space into officess…… |  | Enrico Baez | 5/1 EB Convert two wet labs into offices. Same as Webber 2278. Abate floor, demo all cabinets, remove plumbing, patch & paint. Carpet tile. Equipment comes out. Awating Provost, Sheryl Murdoch and Bob Williams approval….. 7/11/18 EB-Per Brandon Barbosa project will be cancelled | YES | FS | 0 | 2018 | 2019-03-01
18P000410 |  | 18P000410 | FALSE | CHANCELLOR | SL5-HINDERAKER PAINT AND PATCH WALL | Complete as of 8/24/18 | HINDERAKER | 3148B | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-04-25 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000414 |  | 18P000414 | FALSE | CHANCELLOR | SL5-CAMPUS TOURS OFFICE - PAINT CARPET AND CUSTODIAL | FS to coordinate with client to schedule work for completion. | STUDENT SERV | 0 | QUEUE TO START | Kim Wilcox | Karim Zahedi | DANIELLE GARCIA |  | Paul Ditty |  | 1 | 2 | FALSE |  |  | 2018-04-26 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000415 |  | 18P000415 | FALSE | CHASS | SL5-PSYCHOLOGY-OLMSTED-INCREASE DATA INFASTRUCTURE-CP00003223 | Door and frame have been painted; construction to commence upon availability of the teams. | OLMSTED | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | RYAN LIPINSKI |  | Dan Lerman |  |  | 10 | TRUE |  |  | 2018-05-08 | [6 empty] | 12/14/18, DL; Angel cancelled this project as it is no longer needed at this time……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 7/11/18; This project was scoped and part of the IRT. Plans and permits are approved. We will schedule the work and we will plan to have this project complet by 9/21/18…..8/10/18; WE have approved plans, this project is scheduled to start late August and will be complete early October……DL, 10/4/18; The door and frame is scheduled for delivery in 3-5 weeks, We will start the project when the doors and frame are on site……..DL, 11/7/18; Door and frame and painted. We will start the contruction in the near future…… |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-03-01
18P000416 |  | 18P000416 | FALSE | CHASS | SL5-HMSS UWP INSTRUCTOR OFFICE PAINTING | Complete as of 8/24/18 | HUM & SOC SC | 3002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000417 |  | 18P000417 | FALSE | CHASS | SL5-HMSS UWP INSTRUCTIONAL OFFICE PAINTING | Complete as of 8/24/18 | HUM & SOC SC | 2106 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 14 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000418 |  | 18P000418 | FALSE | CHASS | SL5-HMSS OFFICE PAINTING | Complete as of 7/14/18 | HUM & SOC SC | 2002 | COMPLETE | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  |  | 15 | TRUE |  |  | 2018-04-27 | [8 empty] | Paul Ditty | 5/23/18 EB- Sent email to Jill requesting site visit. 5/23/ 18 EB- Scoped. Mount & TV on site. TV bottom edge to be mouted 48" from floor centered on West wall. Needs electrcal cut out and data. Entered in FAMIS. | N/A | FS | 0 | 2018 | 2019-03-01
18P000419 |  | 18P000419 | FALSE | CHASS | SL5-COLL OF HUM, ARTS & SOCIAL SCI- WATKINS RENO- CP00003419 REMOVE AND INSTALL WALLS | FS to coordinate with client to scope the work. | WATKINS | 1320C&E | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  | 5 | 8 | TRUE |  |  | 2018-04-27 | [6 empty] | 2/14/19,DL; This project was canceled by Paul R. 2/1/19, DL; We will custom make Sound panels and will start the installation in the next 6-8 Weeks……….. |  | Enrico Baez | 7/6/18 EB emailed Paul Richardson to schedule site visit 7/17/18 EB Scheduling site visit with Paul R. 8/7/18 EB-Job was part of an IRT. Dan said he will scope 8/20/18 EB emailed Lilia to schedule site visit. 8/24/18 EB scheduled site visit for 8/28/18 at 11:00AM 8/28/18 E.Baez- Met with Paul Richardson, Lilia Vega and Becky Campbell. Instead of tearing down walls and building new ones, they wanted to see if installing sound soak on three walls were possible, it is. They will then need to have their Dean approve the sound soak. Clients were sent an email with drawing indicating desired location of sound soak. | NO | FS | 0 | 2018 | 2019-03-01
18P000420 |  | 18P000420 | FALSE | CHASS | SL5-COLLOF HUM,ARTS & SOCIAL SCI.-WATKINS-RENO-CP00003418 INSTALL SINK AND COUNTER | Canceled by Customer on prioritization 7/2/18 | WATKINS | 0 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  |  |  |  | Cancel | TRUE |  |  | 2018-04-27 | [10 empty] | YES | FS | 0 | 2018 | 2019-03-01
18P000421 |  | 18P000421 | FALSE | CHANCELLOR | SL5-HINDERAKER PAINT AND PATCH WALL | Complete as of 8/24/18 | HINDERAKER | 2120 | COMPLETE | Kim Wilcox | Karim Zahedi | CANDICE GOMEZ |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-04-30 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000425 |  | 18P000425 | FALSE | BCOE | SL5-BOURNS A379-NEW FLOORING & PAINT INCOMING FACULTY MEMBER - | Complete as of 7/25/18. | BOURNS | A0379 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; Luat Vuong arrives on or about August 15…... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected..…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/15/18........DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | FS | 0 | 2018 | 2019-03-01
18P000426 |  | 18P000426 | FALSE | BCOE | SL5-BOURNS A037-NEW FLOORING & PAINT INCOMING FACULTY MEMBER | Complete as of 7/25/18. | BOURNS | A0375 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie; A-375: Bhargav Rallabandi arrives on or about August 1….. DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected…..DL, 7/11/18; Paint is complete. Flooring sould be complete some time next week..... space is vacant until 8/1/18.....DL, 7/25/18; This project is 100% Complete.... |  | Dan Lerman | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | FS | 0 | 2018 | 2019-03-01
18P000427 |  | 18P000427 | FALSE | BCOE | SL5-BOURNS A0373 NEW FLOORING & PAINT INCOMING FACULTY MEMBER | Complete as of 7/11/18 | BOURNS | A0373 | COMPLETE | Christopher Lynch | Maggie Souder | LOUIS SANDOVAL |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-05-01 | [6 empty] | DL, 6/7/18; Per Maggie email; This is our new Dean’s faculty office. Dean Lynch is already on site getting up to speed one-two days a week. This office is an ASAP...... DL, 6/16/18;Scoped project with Maggie and Jess, Need to produce work orders for paint and day crew. floor covering is selected.....DL, 7/11/18; This project is 100% complete...... |  | Paul Ditty | DD 5/24 Added to prioritiy list, Maggie currently reprioritizing the BCOE priorities. CR to follow up on reprioritization status. | YES | FS | 0 | 2018 | 2019-03-01
18P000428 |  | 18P000428 | FALSE | SoB | SL5-OLMSTED RM 2352 PATCH/PAINT | Complete as of 8/17/18 | OLMSTED | 2352 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 5 | FALSE |  |  | 2018-05-02 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000429 |  | 18P000429 | FALSE | BCOE | SL5-INSTALL OWNER PROVIDED-FACILITIES INSTALLED SINK IN B-262; FLOOR DRAIN FOR ICE MAKER IN B-256 | Complete as of 9/19/18 | BOURNS | B0262 B0256 | COMPLETE | Christopher Lynch | Maggie Souder | KEVIN SCHULTE |  | Dan Lerman |  |  |  | TRUE |  |  | 2018-04-10 | [6 empty] | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment…..DL, 5/9/18; We are working on plans to submitt to A&E soon....DL, 5/24/18; Plans were submitted on 5/24/18.......DL, 6/12/18; Plans were approved. Cabinets are ordered. Materila is 6-8 Weeks out.....DL, 7/11/18; We have confirmation for delivery of material for mid August. Target Complete date is 9/7/18......DL, 8/10/18; Project has started. We will be complete with in two weeks......DL, 8/22/18; Work is 90% Complete..Project should be complete by 8/31/18........ DL 9/6/1/8; This project is 99% complete. The parts arrived today. I will be sending out an email to schedule the installation time for next week.......DL, 9/19/18; This project is 100% Complete........ |  | Dan Lerman | DL, 4/16/18. Verified Untilites are avialbe for both ice machine and sink. Need to schedule a meeting with Maggie to verify layout and equipment specifications. This should be complete by the end of the quarter pending delivery of equipment….. | YES | FS | 0 | 2018 | 2019-03-01
18P000432 |  | 18P000432 | FALSE | BAS | SL5-BANNOCKBURN VILLAGE FULL REPAINT OF BANNOCKBURN H-101 | Complete as of 7/13/18 | BANNOCK H | H0101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-05-04 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000434 |  | 18P000434 | FALSE | CNAS | SL5-BOYCE PATCH & PAINT ROOMS IN BOYCE FOR NEW FACULTY | Complete as of 8/24/18 | BOYCE | 4478 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | CHERYL GERRY |  | Paul Ditty |  |  | 3 | TRUE |  |  | 2018-05-09 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000435 |  | 18P000435 | FALSE | CAMPUS | SL5-HMSS HYDRATION STATION REQUEST | Pending Hydration station plan for campus | HUM & SOC SC | 3600 | HOLD - FACILITIES SERVICES |  |  | NELDA THOMAS |  | Dan Lerman |  |  | 30 | FALSE |  |  | 2018-05-10 | [10 empty] | NO | FS | 0 | 2018 | 2019-03-01
18P000436 |  | 18P000436 | FALSE | CNAS | SL5-COLL BLDG SO-PATCH/ PAINT (SWISS COFFEE) IN TWO ROOMS | FS to coordinate with client to schedule work for completion. | COLL BLDG SO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 36 | 30 | FALSE |  |  | 2018-05-10 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000438 |  | 18P000438 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR CONFERENCE ROOM 415 - NEEDS REFRESHING | Complete as of 9/10/18 | CHUNG HALL | 415 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 10 | FALSE |  |  | 2018-05-14 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000439 |  | 18P000439 | FALSE | BCOE | SL5-CHUNG HALL 3RD FLOOR CONFERENCE ROOM 315 - NEEDS REFRESHING | Complete as of 9/10/18 | CHUNG HALL | 315 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | Complete | 11 | FALSE |  |  | 2018-05-15 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000442 |  | 18P000442 | FALSE | VC-RED | SL5-FAWCETT LAB 203 PATCH & PAINT | Complete as of 8/24/18 | FAWCETT LAB | 203 | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Paul Ditty |  |  | 3 | FALSE |  |  | 2018-05-18 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000444 |  | 18P000444 | FALSE | CHASS | SL5-PAINT OFFICE FOR NEW PROFESSOR - ARTS 242 | Complete as of 9/21/18 | ARTS | 242 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-05-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
18P000445 |  | 18P000445 | FALSE | CHASS | SL5-PAINT OFFICE FOR NEW PROFESSOR - ARTS 225 | Complete as of 9/10/18 | ARTS | 225 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 11 | TRUE |  |  | 2018-05-21 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000453 |  | 18P000453 | FALSE | CNAS | SL5-DELFINO LAB-SOIL HOUSE MODIFICATION | FS to coordinate with client to scope the work. | DELFINO HHSE |  | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 17 | 20 | FALSE |  |  | 2018-05-25 | [6 empty] | 2/14/19, DL; Working with Bob W. on Plans and permits……1/15/19, DL; This is a large project and will require Plans and permits. |  | Dan Lerman | 07/06/18 RV input Dans notes after conversation Friday morning. Sccope completed per DL. | YES | FS | 0 | 2018 | 2019-03-01
18P000454 |  | 18P000454 | FALSE | BCOE | SL5-BOURNS A-WING 3RD FLOOR ROOM A-346 - PAINT WALLS | Complete as of 8/24/18 | BOURNS | A0346 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  |  | 9 | FALSE |  |  | 2018-05-29 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000456 |  | 18P000456 | FALSE | VC-STU.AFF. | SL5-HUB--UTILITY METERS | Customer advised to submit the project into Google Form/CPMS for execution. Work beyond FS purview for completion. | HUB |  | TO BE PERFORMED BY PD&C | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-05-30 | [8 empty] | Enrico Baez | 1/24/19 EB Contacted Jonathan Bianchet of Design West for results of site evaluation. Will have report by middle of following week. 11/29/18 EB Met with Design West and HUB staff. Conducted site visit. Waiting for recommendations from Design West. 7/6/18 EB-emailed Brendan to schedule site visit. 7/11/18 EB- Site visit schduled for 7/12/18 7/16/18 Conducted site. Customer wants to have SEP metered for all food vendors. Requested electical power plans from Gunther 8/7/18 Contacted Design West for proposal of feasibility stud 8/15/18 Advised Brendan Obrien to submit request to CPMS as this work will not be self performed. Sent Brendan copy of proposal for sight assessment. | YES | FS | 0 | 2018 | 2019-03-01
18P000459 |  | 18P000459 | FALSE | BAS | SL5-BARN MOVE KITCHEN EQUIPMENT FROM BARN TO THE HUB ROOM 346 | Complete as of 9/21/18 | THE BARN |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | Dan Lerman |  | Complete | 6 | FALSE |  |  | 2018-05-31 | [8 empty] | Enrico Baez | 7/26/18 Routed to J-DLN for Summer Quarter Minor Reno execution; Priority 6 | YES | FS | 0 | 2018 | 2019-03-01
18P000463 |  | 18P000463 | FALSE | SoB | SL5-ANDERSON HALL PATCH/PAINT-102C | Complete as of 8/24/18 | ANDERSON 1 | 0102C | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  | 4 | FALSE |  |  | 2018-06-04 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000464 |  | 18P000464 | FALSE | CNAS | SL5-PATCH AND PAINT LANDING WALL WHERE SIGN IS BEING REMOVED | FS to coordinate with client to schedule work for completion. | COLL BLDG NO | 201 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 35 |  | FALSE |  |  | 2018-08-16 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
18P000468 |  | 18P000468 | FALSE | CHASS | SL5-WATKINS 1222/1223 PATCH/PAINT | Completed as of 8/10/18 | WATKINS | 1222 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 13 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000469 |  | 18P000469 | FALSE | CHASS | SL5-WATKINS FACULTY RECRUITMENT PATCH/PAINT 1317 WATKINS | Complete as of 7/25/18 | WATKINS | 1317 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-06-11 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000470 |  | 18P000470 | FALSE | SPP | SL5-Student Check-in Lobby | Complete as of 8/23/18 | CHASS INT S | 4133 Corridor | COMPLETE | Anil Deolalikar | Luis Alvarez | LUIS ALVAREZ |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-11 | [6 empty] | DL, 6/16/18; I walked this project with Luis and Mark this week. They want this work completed by July 9th. Paint, data, electrical, chair rail and signage is requested. I need to review project with Paul and Robert C. DL, 7/11/18; Robert C. Ordered material and we will complete the install first part of next week We will scheudle the paint after Robert is Complete. Target Complete Date is 7/2018......DL, 7/25/18; WE have the electrical materila, plans were submitted. Once plans are reviewed and approved, we will proceed with the work. Target date is two weeks after plans are approved......DL, 8/10/18; Eletrical is complete. Pending paint. Paint will be scheduled in the near future. DL, 8/22/18; This project will be Complet on Saturday.....DL, 9/6/18. I miossed the chair rail request on this project. I will order the chair rail in the near future. The chair rail is the only item needed to complete this project. Aprroximately 20 lineal feet......DL, 9/19/18; Chair rail is ordered. We will schedule the install when the material arrives....... |  | Dan Lerman | Added by customer on prioritization; timeline and scope tbd. 4/25 EB emailed Christina to schedule site visit. No work order Luis to submit Google doc. To A&E sevral trades invlved. DND 6/13 Project rescoped and priorities adjusted per meeting between Dan and Luis Alvarez. | YES | FS | 0 | 2018 | 2019-03-01
18P000471 |  | 18P000471 | FALSE | ITS | SL5-WCH INSTALL SECURITY FENCE | Complete as of 9/19/18 | CHUNG HALL | 134 | COMPLETE | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Dan Lerman |  |  | 5 | FALSE |  |  | 2018-06-12 | [6 empty] | DL, 7/4/18; Walked this project with Angel, This request is to install security fence with Sliding gate and welded webs to increase security. Space is vacant and ready to schedule work. Need to walk with Corey to see if this is a project they can do or sub out to De ANza fence......DL 7/25/18; Still need to walk project with Corey. Dl, 8/10/18; Site walk complete, we are waiting on estimates. WE will try and schedule the work with in the next 30- days....DL, 8/22/18; Work is scheduled for August 27th. Still need to order hardware.....DL, 9/6/18; The fence is installed and Angel is very Happy, but I need to check the project to verify we are good to go....DL, 9/19/18; This Project is 100% Complete..... |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-03-01
18P000472 |  | 18P000472 | FALSE | BCOE | SL5-WCH PATCH AND PAINT WALL | Complete as of 8/24/18 | CHUNG HALL | 458 | COMPLETE | Christopher Lynch | Maggie Souder | JANNA LE BLANC |  | Paul Ditty |  |  | 1 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000473 |  | 18P000473 | FALSE | CNAS | SL5-PIERCE NEW CARPET & PAINT FACULTY OFFICE | Complete as of 9/26/18 | PIERCE | 202 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 1 | 5 | TRUE |  |  | 2018-06-12 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18P000474 |  | 18P000474 | FALSE | ITS | SL5-MS&E ELECTRICAL MODIFICATIONS FOR ITS | Electrian to complete the work as available. | MAT SCI ENGR | 119 | IN PROGRESS | Danna Gianforte | Shelley Gupta | MICHAEL CAPRIOTTI |  | Robert Corey |  |  | 1 | FALSE |  |  | 2018-06-13 | [6 empty] | 2/28/19, DL; Work is scheduled with Darrenn F. for Spring Break…..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. |  | Enrico Baez | 7/17/18 EB-Scheduling site visit with Michael Capriotti 8/7/18 EB- Met with Robert Corey to discuss scope of work. He will coordinate work. | YES | FS | 0 | 2018 | 2019-03-01
18P000476 |  | 18P000476 | FALSE | VC-RED | SL5-BOYCE CONNECT WASHER & DRYER | Canceled project, work completed on 18W015691 in July. | BOYCE | 6444 | CANCELED BY CLIENT | Michael Pazzani | Laura Manor | DIERK BIGGS |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-14 | [6 empty] | Duplicate to 18W015691; complete |  |  | Duplicate to 18W015691 | NO | FS | 0 | 2018 | 2019-03-01
18P000478 |  | 18P000478 | FALSE | UNDERGRAD ED | SL5-CARPET, PAINT, & AIR HANDLING MODIFICATION | Complete as of 10/22/18. | HINDERAKER | 1120H | COMPLETE | Jennifer Brown | Tracey Scholtemeyer | TRACEY SCHOLTEMEYER |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-16 | [6 empty] | DL, 7/4/18; This project is scoped; Need to remove Switch gear storage rack components, remove electrical conduits, plywood backer board from walls, paint and floor covering. We will schedule this work to be complete by Fall 2018 academic year....DL, 7/11/18; Need to produce work orders and schedule the work. Target Complete date is 9/14/18... Space is vacant....DL, 8/10/18; Work has started and we are on schedule...... DL, 8/22/18; Demo is almost complete. This target date is 9/21/18......9/19/18; All trades are complete. New carpet to be installed on 9/21/18. .....DL, 9/19/18; This project is scheduled to be complete this week....... |  | Dan Lerman | 7/9 EB-Spoke with Dan, he has already scoped this. | YES | FS | 0 | 2018 | 2019-03-01
18P000480 |  | 18P000480 | FALSE | CNAS | SL5-BG - LOWER RESTROOMS-PAINTING-FLOORS | Canceled by Facilities Services; Work is not within the SLA and is not needed. | BOTGDN RSTRM |  | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
18P000481 |  | 18P000481 | FALSE | CHASS | SL5-CHASS INT S PAINT CHASS INTS 3104, 3106, 3114 | Complete as of 10/22/18. | CHASS INT S | 3104 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-06-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
18P000482 |  | 18P000482 | FALSE | SoB | SL5-CARD ACCESS SYSTEM ANDERSON SOUTH | Complete as of 8/2/18. | ANDERSON |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 1 | FALSE |  |  | 2018-06-26 | [6 empty] | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with JasonDL, 7/11/18; Need to check in with Jason on status for his side of the project.....DL, 7/25/18; JAson's team is ready to install but the Anderson IT department does not have the necesary software. We will start the work when the software is up and running...... 8/12/18 DND FAMIS Status noted completion on 8/2/18. |  | Dan Lerman | DL, 7/4/18; This work is scoped. Per Angela, they have the mininum computer software and hardware for the access control system. We may need to install electrical but I need to confirm with Jason | YES | FS | 0 | 2018 | 2019-03-01
18P000483 |  | 18P000483 | FALSE | BAS | SL5-INSTALL SECURE GATE ACCESS BTWN LOT 1 AND DRAINAGE SWALE | FS to coordinate with customer to scope the work. | P1 |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | AMANDA GREY |  | Enrico Baez |  | 7 |  | FALSE |  |  | 2018-06-26 | [6 empty] | Waiting for Amanda Grey to verify ownership of chain link fence. Once confirmed will contract with De Anza to install 36" wide gate. | 2018-08-29 | Enrico Baez | 12/3/18 EB-Cancelled request per email from Amanda Gray. Will resubmit request when funding is available. 10/1/18 EB-Contract De Anza Fence to have a gate installed at chain link fence leading to storm culvert in parking lot 1. | YES | FS | 0 | 2018 | 2019-03-01
18P000484 |  | 18P000484 | FALSE | ATHLETICS | SL5-INTERCOL. ATHLETICS-AMY HARRISON FIELD-NETTING-CP00003408 | Project will be managed by A&E for completion. | SOFTBALL STG |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-06-26 | [6 empty] | 2/1/19, DL; This is a PD&C Project due to IRT walk. Project will exceed $50,000……….. |  | Enrico Baez | 12/6/18 EB Request for basic estimate to add sturdy netting to right field area of Amy S. Harrison Field along Canyon Crest Drive. More detail will be required as funding is identified and timeline for implementation is developed. | NO | FS | 0 | 2018 | 2019-03-01
18P000485 |  | 18P000485 | FALSE | SOM | SL5-SOMR PATCHING AND PAINTING | Complete as of 10/10/18 | SOM RSCH |  | COMPLETE | Deborah Deas | Brandon Barbosa | DANA ABOU ABBAS |  | Paul Ditty |  | 6 |  | TRUE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
18P000486 |  | 18P000486 | FALSE | CNAS | SL5-PHYSICS 3027/3028 RENOVATION | FS to coordinate with client to scope the work. | PHYSICS | 3027 | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 24 |  | FALSE |  |  | 2018-06-28 | [6 empty] | 2/28/19, DL; We will work on the plans in the next 30-days.12/14/18, DL, This project is prioritized at 24 and has a large scope of work. We will not be able to move forward with this project unless the priority number is lowered to a 1- 8….. |  | Dan Lerman | Dan L. scoped this project as part of an IRT…. 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. If possible paint to match existing green accent wall, if not white is fine. Mount monitor bracket to wall centered side to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | YES | FS | 0 | 2018 | 2019-03-01
18P000487 |  | 18P000487 | FALSE | CHANCELLOR | SL5-SKYE HALL PATCH HOLES AND PAINT | Complete as of 10/22/18. | SKYE HALL | 349 | COMPLETE | Kim Wilcox | Karim Zahedi | SONIA ZAMORA |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-06-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
18W000455 |  | 18W000455 | FALSE | CNAS | SL5-CHAPMAN CLEAN WINDOWS | Complete as of 7/11/18 | CHAPMAN | 12 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Dan Lerman |  |  | 37 | FALSE |  |  | 2017-07-11 | [6 empty] | Dl, 7/4/18; All Windows in Chapman were cleaned by Ductch Touch. This Project is 100% Complete |  | Ron Veloz |  | YES | FS | 0 | 2017 | 2019-03-01
18W001170 |  | 18W001170 | FALSE | CHASS | SL5-ARTS: PAINT CLASSROOMS | Complete as of 9/24/18 | ARTS | 407 | COMPLETE | Milagros Pena | Cindy Williams | SUSAN KOMURA |  | Paul Ditty |  |  | 27 | FALSE |  |  | 2017-07-25 | [8 empty] | Enrico Baez | DD 10/6: Enrico scoped; requested during break - coordinating with client to complete on a Saturday | YES | FS | 0 | 2017 | 2019-03-01
18W006022 |  | 18W006022 | FALSE | SOM | INSTALL CURTAIN ROD IN RESEARCH SPACE | Complete as of 7/11/18 | SOM RSCH | 336 | COMPLETE | Deborah Deas | Brandon Barbosa | TARA BARTHOL |  | Dan Lerman |  |  |  | FALSE |  |  | 2017-10-27 | [6 empty] | DL, 5/24/18; Need to review scope with Enrico….DL, 7/11/18; Enrico produced work orders for sheet metal shop. This is a singel trade project. |  | Enrico Baez | Blackout curtain needs to have a better way of being secured. Talked to Cory about fabricating a new curtain rod. 7/6/2018EB assigned to sheetmetal shop F-LNH | YES | FS | 0 | 2017 | 2019-03-01
18W007453 |  | 18W007453 | FALSE | ITS | SL5-(P)-ITS CENTER QUOTE REQUEST FOR CARD ACCESS SYSTEM ITS CENTER BLDG. |  | ITS CENTER | 100 | PLAN DEVELOPMENT/CHECK | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2017-11-30 | [6 empty] | 2/28.19, DL; Conducted job walk with contractor. Once bid is approved, we will work on plans and permits…… |  |  |  |  | FS | 0 | 2017 | 2019-03-01
18W008762 |  | 18W008762 | FALSE | CHASS | SL5-HUMANITIES: PATCH & PAINT | Complete as of 11/8/18 | HUM & SOC SC | 2415 | COMPLETE | Milagros Pena | Cindy Williams | ANDREW ALONSO |  | Paul Ditty |  | 20 | 22 | FALSE |  |  | 2018-01-02 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18W009630 |  | 18W009630 | FALSE | BAS | SL5-BUILD AND EXTENSION ONTO THE OFFICE NEXT TO THE DRYER | Hold per customer on Corp Yard Space Planning analysis; prioritization response 9/17/18. | PHYS PL STOR | 100 | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Gerry Bomotti | Georgianne Carlson | JUDY HODGE |  | Dan Lerman |  | HOLD | HOLD | FALSE |  |  | 2018-01-22 | [6 empty] | DL, 6/16/18; Project includes demo wall/door install new wall, dry wall, paint, door, eletrical outlets, lighting, smoke relocation, lighting motion, new t-bar, relocate heat pump, andn install new carpet…...DL, 7/11/18; Need to work on plans….. Target complete date is late Fall..... |  | Enrico Baez | See work order 18W012349 scoped and annotated in FAMMIS. 6/11/18 EB- Add wall to current space and eliminate exisiting wall. Relocate exisiting A/C on wall. Minor electrical DND 7/14 Hold per customer on prioritization; per Corp Yard Space Planning | YES | FS | 0 | 2018 | 2019-03-01
18W011161 |  | 18W011161 | FALSE | CNAS | SL5-REPLACE CARPET | Complete as of 7/11/18 | SCIENCE LAB1 | 301 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-02-23 | [6 empty] | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project……DL, 5/21/18; Floor covering is selected. Work will be scheudled for Mid June….DL, 5/24/18; The install is scheduled for June 18th & 19th……DL, 7/11/18; This Project is 100% Complete...... |  | Dan Lerman | DL, 3/29/18; This is a class room. Approximate size is 24' X 24'. This will be a Summer project…… | YES | FS | 0 | 2018 | 2019-03-01
18W011672 |  | 18W011672 | FALSE | CNAS | SL5-ENTOMOLOGY; PATCH AND PAINT FOR NEW FACULTY | Complete as of 7/25/18 | ENTOMOLOGY | 268 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 9 | TRUE |  |  | 2018-03-08 | [6 empty] | Relocate white board from East wall onto the West wall, where high table was removed, 24" away from North end of wall. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18W011691 |  | 18W011691 | FALSE | CNAS | SL5-ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB | FS to coordinate with client to schedule work for completion. | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 4 | 11 | TRUE |  |  | 2018-03-08 | [6 empty] | 12/17/18 DND: Canceled by client on 12/17/18. |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18W011692 |  | 18W011692 | FALSE | CNAS | SL5-ENTOMOLOGY; PAINT/PATCH LAB | Complete as of 8/24/18 | ENTOM MUSEUM | 211 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  | 12 | TRUE |  |  | 2018-03-08 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18W011772 |  | 18W011772 | FALSE | BAS | SL5-PRINT MOD; ESTIMATE ONLY FOR ELECTRICAL WORK | Canceled per customer on priority list 7/3/18 | PRINT MOD |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Dan Lerman |  |  | Canceled | FALSE |  |  | 2018-03-12 | [6 empty] | DL, 4/29/18; Pasted from WO; install an outside electrical outlet based on the attached amazon specs. also estimate for removing and sealing the outside vent from the copier. fyi_the copier will be moving within the next few months…..DL, 7/11/18; Need to verfy scope and schedule the work...... |  | Enrico Baez | fyi_the copier will be moving within the next few months | YES | FS | 0 | 2018 | 2019-03-01
18W013160 |  | 18W013160 | FALSE | CNAS | BEES- PATCH & PAINT 2460D & 2460F | Complete as of 10/22/18. | GEOLOGY | 2460 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 33 | 29 | FALSE |  |  | 2018-04-06 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18W013973 |  | 18W013973 | FALSE | VC-RED | SL5-BSL3 FACILITY- ASSEMBLE AND INSTALL | Complete as of 9/24/18 | UNIV OFC BLD |  | COMPLETE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Enrico Baez |  |  | 2 | FALSE |  |  | 2018-04-19 | [6 empty] | FAMIS NOTES 8/22: Plumbing filter system was installed and ice maker installed. Request for microscope and incubator moved into containment by customer. Complete 9/24/18 |  | Enrico Baez | 5/16/18 EB conducted site visit. 5/22/18 EB appliances dented, vaccum pump not on site. 6/19/18 emialed Chrystal to see if appliance have been replaced. 7/16/18 emailed Chrystal Jimenez asking for update. 8/7/18 EB Replacement appliances | YES | FS | 0 | 2018 | 2019-03-01
18W015691 |  | 18W015691 | FALSE | VC-RED | SL5-BOYCE CONNECT WASHER AND DRYER | Complete as of 7/11/18 | BOYCE | 6444 | COMPLETE | Michael Pazzani | Laura Manor | DIERK BIGGS |  |  |  |  | 1 | FALSE |  |  | 2018-05-30 | [6 empty] | DL, 7/11/18; This project is in progress and almost complete. Target complete date is 7/20/18….. |  | Dan Lerman |  | YES | FS | 0 | 2018 | 2019-03-01
18W016588 |  | 18W016588 | FALSE | CHASS | PATCH AND PAINT FOR FACULTY | Complete as of 8/24/18 | SPROUL | 4105 | COMPLETE | Milagros Pena | Cindy Williams | DAMARIS CARLOS |  | Paul Ditty |  |  | N/A | TRUE |  |  | 2018-06-19 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
18W016621 |  | 18W016621 | FALSE | CHASS | SL5-HUMANITIES - PAINT OFFICE - PAINT SHOP | Complete as of 11/8/18 | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 17 |  | FALSE |  |  | 2018-06-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
1900a | 1990a |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | Finalized construction drawings are being reviewed by the campus building official and firemarshal | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE | 2193000 |  | 2015-10-09 | Start Construction | 2019-05-01 | 2019-11-16 | [8 empty] | PD&C | 0 | 2015 | 2019-03-01
1990b | 1990b |  | FALSE | CNAS | Natural Reserves-Boyd Deep Canyon-Road | This project will add structurally independent facilities for an education center (Tevis Education Center - 1,050 gsf) and a rustic campground (700 gsf) with a vault restroom to provide educational meeting space and short term sleeping quarters. Also, repair/replacement of the exisitng access road. The new construction projects will be delivered by design/build. |  |  | Finalized construction drawings are being reviewed | Kathryn Uhrich | Deborah McWilliams | Chris Tracy, D. McWilliams |  | Rowan Reid | 99 |  |  | FALSE |  |  | 2018-06-22 | Finalize Design | 2019-10-01 | 2019-12-01 | [8 empty] | PD&C | 0 | 2018 | 2019-03-01
19P000006 |  | 19P000006 | FALSE | CNAS | SL5-MS&E-NEW FACULTY OFFICE-CONSTRUCT INTERIOR WALL MSE 306/310 | FS to coordinate with client to scope the work. | MAT SCI ENGR | 310 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 3 |  | TRUE |  |  | 2018-07-02 | [6 empty] | 2/14/19, DL; This project is 90% Complete. ………2/1/19, DL; This Project started to day. We are scheduled to be complete by the end of February………..1/15/19, DL; Still pending approved plans. Once plans are approved, we will schedule the work……12/14/18, DL; This project will require plans and permits. We will work on Plans shortly after the new year. | 2018-09-28 | Ron Veloz | 10/30/18 RV: Spoke with Deborah McWilliams, today. Project to remain as prioritized(#3) for new Faculty. 10/17/18 RV: Floor plan is on the server folder. RV: 10/03/18: Install metal stud wall at center of the room. Remove one door blank and install one lockset.Requires, Framing, drywall, tape, sand, paint, t-bar modifications and rubber base. PM to verify with user if power and Data will be required in the new wall. 09/28/18 O-RVL: Completed SOW: Add Wall in the center of room. Include a new Metal Stud Wall with rubber base to match existing. Remove metal cover at ceiling. Remove door lock blank and install new lockset at left door. RV completed SOW & placed on FS server. Updated FAMIS and Minor Reno List. 09/27/18 O-RVL: Site walk with Chris P, Dan L. Mayela and Deborah McW. FS to re-install the metal stud wall to original place dividing the room equally. Scoping completed. 09/26/18 O-RVL: 19P000006-Scheduled a site walk scheduled with Dan. Will contact Deborah and Mayela for their participation. | YES | FS | 0 | 2018 | 2019-03-01
19P000009 |  | 19P000009 | FALSE | SOM | SL5-SOME -- PAINT, SPACKLE AND CLEANING NEEDED | Complete as of 10/10/18 | SOM EDUC | 2615 | COMPLETE | Deborah Deas | Brandon Barbosa | BEVERLEY HERBERT |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000011 |  | 19P000011 | FALSE | CHASS | SL5-PSYCHOLOGY NEW FACULTY HIRE- WALS PATCHED/CARPETS CLEANED | Complete as of 10/10/18 | PSYCHOLOGY1 | 2111A | COMPLETE | Milagros Pena | Cindy Williams | LORENA QUINTANA |  | Paul Ditty |  | 4 |  | TRUE |  |  | 2018-07-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000012 |  | 19P000012 | FALSE | SOM | SL5-SOME--PATCH & PAINT | Complete as of 10/10/18 | SOM EDUC | 2638 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-07-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000014 |  | 19P000014 | FALSE | SOM | SL5-SOME - PATCH & PAINT | Complete as of 10/10/18 | SOM EDUC | 2609 | COMPLETE | Deborah Deas | Brandon Barbosa | MARISELA MARTINEZ |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-07-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000015 |  | 19P000015 | FALSE | BAS | SL5-POLICE TRLR INTERIOR PAINTING & EXTERIOR PAINTING | Complete as of 11/8/18 | POLICE TRLR | 1 | COMPLETE | Gerry Bomotti | Georgianne Carlson | KELLY DUNCAN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-07-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000017 |  | 19P000017 | FALSE | SoB | SL5-ANDERSON HALL INSTALL TV MOUNT & WHITE BOARD | Complete as of 8/24/18 | ANDERSON 1 | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | DL, 9/6/18; Monitors are installed. Need to schedule the electrical. Target date is 9/21/18…… |  | Enrico Baez | 9/4/18 EB-This Project has been started. Monitors in place. Just need to run electrical. Dan aware. Refer to WO 19P000053. It asks for the same thing. Will request to close this and let Angela know. | YES | FS | 0 | 2018 | 2019-03-01
19P000018 |  | 19P000018 | FALSE | SoB | SL5-ANDERSON HALL SO - PATCH/PAINT ANDHLS-001 THIS SUMMER | Complete as of 8/24/18 | ANDERSON 1 | 0001B | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-11 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000021 |  | 19P000021 | FALSE | ITS | SL5-ITS CENTER-QUOTE REQUEST DIGITAL SIGNAGE MULTIPLE LOCATIONS | FS to coordinate with customer to scope the work. | ITS CENTER |  | QUEUE TO START | Danna Gianforte | Shelley Gupta | SHEILA MABEE |  | Dan Lerman |  | 4 |  | FALSE |  |  | 2018-07-12 | [6 empty] | 12/14/18, DL; Still need to review scope….. |  | Enrico Baez | Met with IT staff. T.V. to be mounted in 4 locations. Will need electrical and painting in some locations. Waitng for updated scope from Joe Sepulveda 1. Telecom Building - Conference Space Electricians Power Requirements: • Install double duplex(quad outlet), AC power on East wall at display location (4S Box) low profile • All electrical junction boxes, J-boxes, and conduit can be surface mounted. J-boxes to be located behind TV. Data Requirements: • Install single gang junction box on East wall behind display with Panduit running to specified location (for telecom network drops) o Single gang, low profile junction box o (conduit to be lead through masonry wall above T Bar ceiling in adjacent room. o (Low profile boxes for data ports) • Single gang box, mounted behind TV location, for data. • Note: Non-traditional wall – masonry Carpenters • Install mounting bracket for display on East wall • note: Non-traditional wall – masonry Painters • Paint junction boxes and conduit to match wall. 2. Intellicenter - First Floor Common Area Carpenters • Install mounting brackets on East Wall for each display (2 total) • (ITS to note the top of the bracket) 3. SOM-E - 1675A DataCenter Electricians Power Requirements: • Install double duplex(quad outlet), AC power on North wall at each display location (2 total) o Surface mounted J Boxes and Conduit Data Requirements: • Install single gang junction box on North wall at each display location with conduit/panduit running to specified location (for telecom network drops) (2 total) o (Wire mold boxes for both power and data) (2inch boxes – low profile boxes for data ports) o Data conduit to stub up and terminate through T-bar ceiling panels. • All conduit and J-boxes to run upward through T-bar ceiling Carpenter • Install mounting bracket for each display on North wall (2 total) • Install backing for mounts in adjacent data room in shelving. Painters • Patch and paint installation area as needed Location Notes • Non-traditional wall – drywall over carpentry 4. ITS Building - 174 Electricians • Install double duplex, AC power on East wall at each display location (2 total) • Install single gang junction box on East wall at each display location with conduit above ceiling (for telecom network drops) (2 total) o Terminate Data conduit above T-bar ceilings Carpenters: • Install mounting bracket (marked on the wall) for each display on East wall (2 total) Location Notes: • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 5. ITS Building - Main Lobby Electricians • Install double duplex, AC power on South wall at display location • Install single gang junction box on South wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on South wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 6. ITS Building – AVC / CIO’s Office (ITS 147) Electricians • Install double duplex, AC power on North wall at display location • Install single gang junction box on North wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install mounting bracket for display on North wall • Non-traditional wall – portable o Walls need backing o Top of mounting bracket noted on the wall) 7. ITS Building Room 138 Electricians • Install double duplex, AC power on East wall at display location • Install single gang junction box on East wall at display location with conduit above ceiling (for telecom network drops) o Terminate Data conduit above T-bar ceilings Carpenters • Install m | YES | FS | 0 | 2018 | 2019-03-01
19P000022 |  | 19P000022 | FALSE | BAS | SL5-HUB--PAINT TWO WALL AS SCOTTY'S HUB | Complete as of 9/17/18 | HUB | 101 | COMPLETE | Gerry Bomotti | Georgianne Carlson | DIANE THOMAS |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-07-12 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000023 |  | 19P000023 | FALSE | BCOE | SL5-PAINT ACCENT WALL | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-13 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000026. Canceled to be completed on 19P000035 | N/A | FS | 0 | 2018 | 2019-03-01
19P000026 |  | 19P000026 | FALSE | BCOE | SL5-WCH PATCH AND PAINT WALLS | Work to be completed in conjunction with customer project #19P000035. | CHUNG HALL | 354 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | Complete in conjunction with 19P000023. Canceled to be completed on 19P000035 | N/A | FS | 0 | 2018 | 2019-03-01
19P000027 |  | 19P000027 | FALSE | ATHLETICS | SL5-ATHLETICS PATCH & PAINT ROOM | Complete as of 9/19/18 | ATH DANCE | 0120C | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | DL, 9/19/18; This Project is 100% Complete……. |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000028 |  | 19P000028 | FALSE | BCOE | SL5-BOURNS A-WING EAST LOBBY - TV CEILING MOUNTS | Deferred to Winter Quarter | BOURNS | A0169 | IN PROGRESS | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | Deferred to Winter Quarter |  | FALSE |  |  | 2018-07-16 | [6 empty] | 2/28/19, DL; Will schedule the project to be complete the first week in April…… | 2018-11-14 | Ron Veloz | 10/29/18 RV: Scoping is completed. Carpenters to Remove Ceiling Mounted TV supports from the lobby ceiling. Work may require Carpenters to open the hard ceiling and remove the TV bracket posts if they cannot be unscrewed from the mounting brkt at the deck above. Work ay also require drywall patch back, tape, sand and paint the lobby ceiling. 11/14/18 RV: Moved to Que to Start. | YES | FS | 0 | 2018 | 2019-03-01
19P000029 |  | 19P000029 | FALSE | BCOE | SL5-CHUNG HALL 2ND FLOOR 205/206 LOBBY - VIDEO CAMERAS | Canceled; duplicate request to be completed with 19P000059 | CHUNG HALL | 205 | CANCELED BY CLIENT | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 11 |  | FALSE |  |  | 2018-07-16 | [6 empty] | Canceled; duplicate request to be completed with 19P000059 |  | Ron Veloz | to side and center 67" from floor. Install electrical - 2 duplex outlets behind monitor. Estella has all parts. | NO | FS | 0 | 2018 | 2019-03-01
19P000030 |  | 19P000030 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT | Complete as of 10/10/18 | OLMSTED | 2301 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000031 |  | 19P000031 | FALSE | CNAS | SL5-BIOLOGICAL SCI--FS NEEDS FOR NEW WALL DISPLAY (MONITOR) | FS to coordinate with client to scope the work. | BIOLOGICAL SCI | 3101 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Dan Lerman |  | 40 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This is prioritized at #40 and will not be scheduled in the near future….. |  | Enrico Baez | 11/08/18 E. Baez-Site visit with Estella. Remove white board on left when entering space. Patch and paint walls. Install 2 duplex outlets | YES | FS | 0 | 2018 | 2019-03-01
19P000032 |  | 19P000032 | FALSE | SOM | SL5-Reconfigure recepetion desk to fit two FTEs. | Scope of work has been identified and walked with Ron V & Brandon B. | SOM EDUC | 2608 | IN PROGRESS | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | 5 | 1 | FALSE |  |  | 2018-07-17 | [6 empty] | 2/28/19, DL; Conducted site visit with Chad. We will complete the work in the next two weeks…….2/1/19, DL; I Walked this project this week. We will try and schedule the work in the next 30- days…….12/14/18, DL, Still need to conduct site visit and schedule the work… | 2018-10-17 | Ron Veloz | 01/31/19 O-RVL: Met with Dan L onsite to review SOW with the requester. END--- 10/17/18 O-RVL: Remove one lower cabinet, Install a new corbel below to support the counter, install new carpet square or create an accent border if carpet tile is obsolete. Install new rubber base | YES | FS | 0 | 2018 | 2019-03-01
19P000033 |  | 19P000033 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT | Duplicate request to 19P000030; Canceling project to be completed on other request. | OLMSTED | 2301 | CANCELED BY CLIENT | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-07-16 | [6 empty] | Duplicate to project 19P000030. Canceling project. |  | Paul Ditty | Duplicate to project 19P000030. Canceling project. | N/A | FS | 0 | 2018 | 2019-03-01
19P000035 |  | 19P000035 | FALSE | BCOE | SL5-WCH--INSTALL NEW LED DISPLAY IN OFFICE | Installation scheduled for Friday 11/19/18. | CHUNG HALL | 354 | COMPLETE | Christopher Lynch | Maggie Souder | SARA GALLOWAY |  | Dan Lerman |  | 9 |  | FALSE |  |  | 2018-07-16 | [6 empty] | 12/14/18, DL; This Porject is 100% Complet…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Install scheduled for this Friday. | 2018-10-03 | Ron Veloz | 10/03/18 RV Walked site with Dan L. SOW Install TV Bracket at south wall center of room. Requires Power (no Data)installation of mounting bracket. TV and brk is located in Sarah Galloways office. Scope is completed. Dinh 9/18 19P000023/19P000026 requests for paint to be included in project scope for room. | YES | FS | 0 | 2018 | 2019-03-01
19P000037 |  | 19P000037 | FALSE | VC-STU.AFF. | SL5-HEALTH SERVICE BLDG--PATCH WORK AND PAINTING | Complete as of 10/22/18. | HEALTH SERV |  | COMPLETE | Brian Haynes | Cathy Eckman | GLORIA VERA |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-07-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000042 |  | 19P000042 | FALSE | CNAS | SL5-COLL BLDG SOUTH PATCH & PAINT VARIOUS HOLES IN WALL | FS to coordinate with client to schedule work for completion. | COLL BLDG SO | 200 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Paul Ditty |  | 38 |  | FALSE |  |  | 2018-07-20 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000043 |  | 19P000043 | FALSE | CNAS | SL5-SCIENCE LAB 1- ENSC - KEY CARD ACCESS INSTALLATION | Customer called and canceled the work on 10/23/18. | SCIENCE LAB1 | 309 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 19 |  | FALSE |  |  | 2018-07-20 | [7 empty] | 2018-10-22 | Ron Veloz | Customer called and canceled the work on 10/23/18. 10/20/18: O-RVL: Site visit on 10/20 with Amber 10:30am. 10/22/18 O-RVL: Walked site with Vendor/Controlled key sys. The PI requested pricing to change the locking function from room to room as "Storage use " and rekey the entry door with the same function. Matt will send pricing on the week of 10/22. 10/23/18 O-RVL: This request will not require access controls, but will require the entry door and side door lock-sets function to be changed to a storage function and rekeyed per Dave(PI). Received info from PI that there was a theft in his dept. Request is urgent. RV requested key count from Dave 8/23/18 and is pending a response from the department. 10/23/18 >> Canceling at the request of the customer - Loretta | YES | FS | 0 | 2018 | 2019-03-01
19P000044 |  | 19P000044 | FALSE | VC-RED | SL5-PATCH AND PAINT | Complete as of 10/10/18 | SPIETH | 345 | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000045 |  | 19P000045 | FALSE | CNAS | SL5-PREPARE LOCATION AND UTILITIES FOR INSTALL | Complete as of 11/8/18 | BOYCE | 2407 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Dan Lerman |  | 14 |  | FALSE |  |  | 2018-07-23 | [8 empty] | Ron Veloz | Scope is complete. Walked site with Steve Burelson. DI water is available behined wall in 2407 at interstictal space. Vendor will install Milpore unit, FS to provide DI water and back board.Power is available at the sink counter. Electrical has verified GFI. | YES | FS | 0 | 2018 | 2019-03-01
19P000046 |  | 19P000046 | FALSE | BCOE | SL5-PATCH AND PAINT PLUS REPLACE BLINDS | Complete as of 11/8/18 | BOURNS | A0131 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-07-23 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000049 |  | 19P000049 | FALSE | CNAS | SL5-PHYSICS PATCH & PAINT | FS to coordinate with client to schedule work for completion. | PHYSICS | 3036 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | 39 |  | FALSE |  |  | 2018-07-25 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000053 |  | 19P000053 | FALSE | SoB | SL5-ANDERSON SOUTH --ELECTRICAL OUTLETS & MOUNT MONITOR TV'S | Complete as of 10/22/18. | ANDERSON 1 |  | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Dan Lerman |  |  | 2 | FALSE |  |  | 2018-04-13 | [6 empty] | DL 8/22/18; two out of four monitors are complete. WE still need to install powree at four locations…….DL, 9/6/18; Still need Electrical installed……. Planing to have complete by 9/21/18……. This is aqctually 4- monitors in four locations. We should ensure each monitor is treated as an indidual project.......DL, 9/19/18; All monitors are installed. Robert will schedule the electricans this week or early next week...DL, 10/4/18; This project is 100% Complete..... |  | Enrico Baez | DND 7/25/18: Emailed R. Veloz advising work order is closed; upon completion of the scope review, Ron to work with Zee for a Project Number to be created. | YES | FS | 0 | 2018 | 2019-03-01
19P000054 |  | 19P000054 | FALSE | GSOE | SL5-PATCH & PAINT OFFICE | Complete as of 10/10/18 | SPROUL | 2131 | COMPLETE | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-07-26 | [6 empty] | N/A |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
19P000055 |  | 19P000055 | FALSE | CNAS | SL5-CBS INSTALL EXHAUST FAN WITH LIGHT IN BATHROOM | Scope reviewed by BZM; coordination by PM for work to be completed. | COLL BLDG SO | 207 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | LISA DUNMORE |  | Dan Lerman |  | 32 | Deferred to Fall Quarter - summer priority 24 | FALSE |  |  | 2018-05-18 | [6 empty] | 12/14/18, Dl; This project is prioritized at 32 and will not be scheduled in the near futurer…….DL, 7/11/18; Correction, I did not scope this yet, I thought we were talking agout the door bell and ADA operator. I will check in with Ronda and verify the scope…... DND 7/30/18: Created project to replace WO #18015182; project #19P000055 8/12/18 DND: Deferred to fall quarter by CNAS' Dean's Office as other project priorities took precedence. | 2018-11-29 | Ron Veloz | 11/29/18: RV Visited site and identifed the toilet room on the 2nd floor. SOW is to install a new exhaust fan at the second floor toilet room. Roof access is available from the access panel in the closet located in the room 210 next door. There is roof is transite per Jess. Abatement is necessary for roof penetrations and possibly has lead paint on ceilings and walls. | YES | FS | 0 | 2018 | 2019-03-01
19P000056 |  | 19P000056 | FALSE | CHASS | SL5-HMSS CAPABILITY OF MOUNTING A TV | Scope of work has been reviewed; determining how to complete project with trades. | HUM & SOC SC | 1212 | IN PROGRESS | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Dan Lerman |  |  | 18 | FALSE |  |  | 2017-10-03 | [6 empty] | 12/14/18, DL; Monitor is complete. Still need to work on electrical……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 5/24/18; Need to verify scope with Enrico and schedule the work…. Work orders are not produced. Need to assign and schedule the work DND 7/30/18: Closed work order #18W004822; created project #19P000056……DL, 8/8/18; We will produce work orders and schedule the work as the schedule permits…… |  | Enrico Baez | EB 3/26-Project scoped on 10/23/17. Attached 5 photos and made annotations to FAMIS. | YES | FS | 0 | 2017 | 2019-03-01
19P000058 |  | 19P000058 | FALSE | CNAS | SL5-Assess Feasiblity of Removing/Replacing Growth Chambers | Complete as of 8/24/18 | GH HH | 18 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-03-28 | [6 empty] | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing...DL, 5/9/18; Project is scoped. Need to schedule the work.....Plumbers and HVAC are working on this. Still need to have electrical removed. I am working wiht Patty on who can do the demo and removal.....DL, 7/11/18; I need to check in with Ken to see if refrigerant is recovered. will isue work order to disconnect electrical..... I checked in with our campus surplus and do not have any contacts to dis,matel the very large growth Chambers. I need to inform Patty and suggest that she have Burges demo and move the Growth Chambers......We will be complete with our portion of this project before 8/1/18.......DL, 8/10/18; All work is done except the disconnect for electrical. I need to check and see if the electrical. Per FAMIS complete on 8/22/18 |  |  | DL, 4/16/18; Site visit conducted with Patty. We need specs of new equipment to verify the required utilites…..DL, 4/29/18; We will proceed with the removal of the Growth Chambers and clean the space…..No equipment is ordered. No alteration, This is aftermarket equipment that we are removing | YES | FS | 0 | 2018 | 2019-03-01
19P000059 |  | 19P000059 | FALSE | BCOE | SL5-CHUNG HALL 201 SECURITY SYSTEM INSTALL | ITS to install cameras, no work by FS Required. | CHUNG HALL | 201 | CANCELED BY FS | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 10 | 7 | FALSE |  |  | 2018-07-17 | [6 empty] | DND 7/30/18 Project #19P000059 to replace REF CPMS # 9054 Ron to speak with ITS to complete installation. |  | Ron Veloz | 10/29/18 RV: Last meeting it was discussed that FS does not install Security Camera systems. Ron V spoke with Maggie on 10/26 to inform her that the project will be removed from the FS Minor Ren. List and she will need to contact ITS to request the Security Camers. 08/27/18 RV: Updated notes. Moved to "Que to Start". 09/19/18 RV, Install Security Cameras at points of entry. Install DVR locally in closet at an adjacent room. 08/23/18-RV Met with D.L. and Jason W. and verified F.S. will perform cabling installation and mount cameras. Equipment cost is not included in the SLA. R.V. will communcate informantion to Maggie. 08/22/18 O-RVL: Met with M. Souder to determine security camera needs and approximate location. | YES | FS | 0 | 2018 | 2019-03-01
19P000060 |  | 19P000060 | FALSE | BCOE | SL5-CHUNG HALL 223 SOUND PROOFING REF CPMS 9043 | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | CHUNG HALL | 223 & 224 | TO BE PERFORMED BY PD&C | Christopher Lynch | Maggie Souder | MAGARET SOUDER |  | Dan Lerman |  | 6 | 4 | FALSE |  |  | 2018-05-15 | [6 empty] | 2/1/19, DL; Thios is a PD&C project. Maggie S. is aware this project may be a $130,00. project……DL, 7/25/18; This project is complicated and plans/permits will be required. This project will also require Air Hanlers to be shut down so Vibration dampners can be instlled. We will work on the plans in the next 45 days. This project should be scheduled during the Winter. We may also need to rent a large portable air handler to ensure the Large server room can maintain temp……. Project #19P000060 to replace REF CPMS # 9043. DL, 11/7/18; Sent Maggie an email on 11/7/18 informing her this project is well beyond our scope and $50K threshold. |  | Dan Lerman | DD 7/17: IRT Scoped with Dan present. Attached to FS Project. REF CMPS 9043 | YES | FS | 0 | 2018 | 2019-03-01
19P000061 |  | 19P000061 | FALSE | CHASS | SL5-PSYCHOLOGY 1111H-PATCH HOLES IN WALL | FS to coordinate with client to schedule work for completion. | PSYCHOLOGY1 | 1111H | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-07-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
19P000062 |  | 19P000062 | FALSE | CNAS | SL5-MSE 169-MINOR RENOVATION - NEW FACULTY | Electrical outlet is the highest priority. Must be installed by Sept 15, per Mayela Castillo | MAT SCI ENGR | 169 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 5 | 19 | TRUE |  |  | 2018-07-30 | [6 empty] | 2/1/19, DL; This project is 100% Complete…………..1/15/19, DL; This project is 99% complete pending one water heater. Water heater is not here yet……12/14/18, DL; This project is 95% complete. The water heater is scheduled for delivery shortly after the new year. We will complete the install when the heater arrives…… 11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 9/6/18; We will have the power and cabinets removed by 9/19/18. We are in the process of producing plans for this project. Once the plans are approved, we will proceed with the project. Note, we still need to obtain important information and some specifications regarding the procured base cabinets and counter tops, bio safety cabinet, diswasher, and freezer. ……DL, 7/7/18; The work is 90% complete. We are waiting on parts which have a 4-6 week lead time. We will finsh the balance of the project when the parts arrive….. | 2018-08-22 | Ron Veloz | 10/17/18 RV: Work is in Progress. END--- 08/27/18 RV: Updated notes. Moved to "Que to Start". Lab upgrades, Install utilities for new lab equipment, including DI water, electrical, modify existing cabinet to accommodate new flask washer, install owner furnished lab workstations. END ---...DND 8/12/18 replaced 3 projects for Summer quarter completion. Ron V. has scope on project. END --- 08/22/18 O-RVL: completed S.O.W, sent to Mayela Castillo for sign off. 08/23/18-RV: Ron V. Resubmitted S,O.W. rev.1 and received Final sign off from Mayela. Met with Dan to provide information and hand off the project. | YES | FS | 0 | 2018 | 2019-03-01
19P000063 |  | 19P000063 | FALSE | CHASS | SL5-NEW FACULTY MEMBER - OFFICE 2124 UPDATE/REPAIRS | Complete as of 9/26/18 | PSYCHOLOGY1 | 2124 | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-07-31 | [8 empty] | Paul Ditty | 9/13/18 EB this is a request for patch, paint and new carpet | NO | FS | 0 | 2018 | 2019-03-01
19P000102 |  | 19P000102 | FALSE | CNAS | SL5-PATCH & PAINT FRONT CORNER OF OFFICE | FS to coordinate with client to schedule work for completion. | LIFE SCIENCE | 2930 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 42 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000106 |  | 19P000106 | FALSE | CNAS | SL5-PHYICS 1134 - UTILITIES REQUEST | FS to coordinate with client to scope the work. | PHYSICS | 1134 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 15 |  | FALSE |  |  | 2018-08-01 | [6 empty] | 2/1/19, DL; Review scope with Customer. Still need to review with Brian from the Electic shop…………….12/14/18, DL; No update…. | 2018-11-07 | Ron Veloz | 01/31/19 O-RVL: Walked site with Dan L on 01/31 to review SOW. END--- 01/23/19 O-RVL: Received email from Ward B.in response to Brian Hambleton's request to use 208v. response is" ... 208 volt power 3-phase is fine for the compressor. Also having emergency power is not needed". END--- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela. END --- 01/23/19 O-RVL: Emailed team the SOW & specifications. Pending review comments/remarks from Dr. Beyermann and job walk date & time from Mayela.-END 01/23/19 RV received Dr. Beyermann's comments and made corrections to the SOW, rev2. END--- 01/22/19 O-RVL: RV updates, Received a request from Mayela to meet on site with team. Sent team a copy of the Statement of Work for their review. Scope of Work: Install: Chilled new water supply & return drop, Electrical Power for the Compressor to be 3- phase 40Amp 220/230VAC hardwired from the equipment the disconnect for the Compressor. Power for the QD Pump and Controller to be single phase 200-230VAC, 20amp circuit. Patch and paint as needed, test for lead paint and TSI Asbestos abatement, equipment anchoring. Note: Job walk conducted on 11/07/18, 9:45-10:00am. Met in 1134 to determine Equipment and Utility Service location. In addition, on 11/03/18 the customer requested a single phase 200-230VAC, 20amp circuit (received info via email). END --- 01/11/19 O-RVL: Received an email from Mayella requesting status. END --- 11/08/18 O-RVL: Received email from Dr Beyerman today for added electrical. "I just realized that I also need a single phase 200-230VAC, 20 amp circuit in 1134 for the pump and controller, which is that unit next to the dewar. This can be down by the floor, in the vicinity of the 3 phase box. I will be meeting with the electrician today around 11am, and I will mention it to him". RV asked Dr Beyermann to contact me with the location for the pump receptacle. Will update floor plan upon receipt. 11/07/18 RV Walked site with Mayela and Dr Beyerman. Request to provide Chilled water loop, and two locations for Electrical power. Identified locations to install new utilities. END --- 11/07/18 O-RVL: Walked site on 11/07 with Dr Beyermann & Mayela, identified scope. Update FAMIS to J-DLN, MinRenlist and move to que to start. END --- 11/06/18 O-RVL: Jobwalk scheduled on 11/07 at 10:00am in Rm 1134 with Mayela, Ward Beyermann, Darren M HVAC, Brian H-Elect. Hold | YES | FS | 0 | 2018 | 2019-03-01
19P000122 |  | 19P000122 | FALSE | CHANCELLOR | SL5-REMOVE, PATCH & PAINT AND HANG | Complete as of 10/22/18. | STUDENT SERV | 2222 | COMPLETE | Kim Wilcox | Karim Zahedi | CHRISTINE SMITH |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | FS | 0 | 2018 | 2019-03-01
19P000124 |  | 19P000124 | FALSE | VC-STU.AFF. | SL5-PAINT ROOMS 115 AND 116 | Complete as of 10/22/18. | COSTO HALL | 125 | COMPLETE | Brian Haynes | Cathy Eckman | LINDA KELLEY |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000126 |  | 19P000126 | FALSE | CNAS | SL5-CHEMICAL SCIENCE - MINOR RENOVATIONS | Paint has been completed; plumbing to complete work upon availability of the team. | CHEMICAL SCI | 455 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Dan Lerman |  | 6 |  | TRUE |  |  | 2018-08-03 | [6 empty] | 12/14/18, DL; This project is 100% Complete……..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL,11/7/18; Paint is complete, Plumbing shop is planning to schedule the work in the near future…… |  | Ron Veloz | Work in progress, install nitrogen lines and valves(valves by PI). Patch and paint. 10/30/18 RV: Spoke with Kevin, pending nitrogen line installation | YES | FS | 0 | 2018 | 2019-03-01
19P000127 |  | 19P000127 | FALSE | CNAS | SL5-PIERCE PATCH & PAINT | Duplicate request to be combined with 19P000239 | PIERCE | 2301 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | MICHELLE KING |  | N/A |  | Canceled |  | FALSE |  |  | 2018-08-03 | [6 empty] | Paul Ditty |  | Paul Ditty | Paul Ditty |  | FS | 0 | 2018 | 2019-03-01
19P000129 |  | 19P000129 | FALSE | BCOE | SL5-HANG MONITORS AND BOARDS | Dry erase boards and monitor mount installation complete; monitors to be installed. | CHUNG HALL | 103 | COMPLETE | Christopher Lynch | Maggie Souder | RICHARD BAIN |  | Dan Lerman |  | 8 |  | FALSE |  |  | 2018-08-06 | [6 empty] | 12/14/18, DL; This Project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; Dry errase boards and Monitor mounts are installed. Still need to install monitors, corner guards and monitors….. |  | Ron Veloz | 10/03/18 O-RVL: Install one 32" monitor asouth wall center of table, Install 55" TV at west wall(need power & data), install white bd at east wall 8' from north corner, install chalk bd at east wall 2'-6" from corner at 8" above small table. | YES | FS | 0 | 2018 | 2019-03-01
19P000133 |  | 19P000133 | FALSE | CNAS | SL5-PATCH HOLES AND PAINT | FS to coordinate with client to schedule work for completion. | BATCHELOR | 2203 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 43 |  | FALSE |  |  | 2018-08-07 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000137 |  | 19P000137 | FALSE | CNAS | SL-5 -LIFE SCIENCES- PATCH & PAINT CUSTODIAN BREAK ROOM |  | LIFE SCIENCE | 2545 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-08 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000170 |  | 19P000170 | FALSE | CNAS | SL5-INSTALL NEW IRRADIATOR INSTRUMENT | Anticipated delivery of equipment is scheduled for three weeks. | MAT SCI ENGR | 51 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  | Dan Lerman |  | 16 |  | FALSE |  |  | 2018-08-08 | [6 empty] | 2/14/19, DL; This project is 100% Complete………2/1/19, DL; Power is complete. Chilled water will be complete next week…………..1/15/19, DL; Electric is commplete, Water will be complete with in two weeks. Equipment should be on site soon…12/14/18, DL; This project is currently on hold per RED…….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 11/7/18; The unit is schedukled for delivery in the next three weeks. | 2018-09-19 | Ron Veloz | 01/30/19 O-RVL: Spoke with Dan, equipment arrived staging into building. END---…..9/10: D. Dinh Project is shared between CNAS & BCOE, captured only on the CNAS College Count. 09/19/18 RV, Scope is complete. RV to Upload into FAMIS. Install chilled water and dedicated power for the irradiator instrument at the west wall in rm 051. 10/17/18 RV: SOW provide Chilled water loop and one(1ea) dedicated 208v 1ph 40a circuit to the Irradiator. Floor plan and specs are on the server folder. | YES | FS | 0 | 2018 | 2019-03-01
19P000171 |  | 19P000171 | FALSE | CHASS | SL5-HUMANITIES- PATCH AND PAINT WALLS IN CHASS F1RST | FS to coordinate with client to schedule work for completion. | HUM & SOC SC | 1614 | QUEUE TO START | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 16 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000172 |  | 19P000172 | FALSE | VC-STU.AFF. | SL5-HEALTH SERV- PAINT RESTROOM IN LABORATORY | Complete as of 11/8/18 | HEALTH SERV | 0113A | COMPLETE | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000173 |  | 19P000173 | FALSE | CHASS | SL5-PAINT/PATCH UNIVERSITY THEATER LOBBY | Complete as of 11/8/18 | THTR WKSH | 0400A | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Paul Ditty |  | 23 |  | FALSE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000174 |  | 19P000174 | FALSE | CNAS | SL5-BATCHELOR HALL REVERSE DOOR SWING, HYDRAULIC DOOR CLOSERS AND PATCH/PAINT | Scope reviewed by BZM; coordination by PM for work to be completed. | BATCHELOR | 2112 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AMY RICKS |  | Dan Lerman |  | 37 |  | FALSE |  |  | 2018-07-24 | [6 empty] | 12/14/18, DL; This project is priortized at 37 and will not be scheudled until further notice…… | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scoping narrative is available and located on the BZM Fall Folder. Patch & Paint, replace supply grilles, reverse door swing, remove door closers, install metal plate over door opening. | YES | FS | 0 | 2018 | 2019-03-01
19P000175 |  | 19P000175 | FALSE | BCOE | SL5-PAINTING | Complete as of 10/10/18 | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT CHAVARRIA-VIVAR |  | Paul Ditty |  | 3 |  | TRUE |  |  | 2018-08-09 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000176 |  | 19P000176 | FALSE | CNAS | SL5-PAINT AND PATCH PHYSICS 1ST FLOOR HALLWAY | FS to coordinate with client to schedule work for completion. | PHYSICS | 1112 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 50 |  | FALSE |  |  | 2018-08-10 | [6 empty] | N/A |  | Paul Ditty | 01/15/19 LB: Complete per Paul Ditty | N/A | FS | 0 | 2018 | 2019-03-01
19P000181 |  | 19P000181 | FALSE | VC-RED | SL5-PATCH HOLES AND PAINT SOME ROOMS AT UOB, UPSTAIRS | FS to coordinate with client to schedule work for completion. | UNIV OFC BLD | 249 | QUEUE TO START | Michael Pazzani | Laura Manor | GLORIA GALLEGO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-08-14 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000184 |  | 19P000184 | FALSE | CNAS | SL5-REMOVE BENCH FROM CENTER OF ROOM HAS GAS AND AIR SUPPLIES | FS to coordinate with client to scope the work. | GEOLOGY | 1270 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | LAURIE GRAHAM |  | Dan Lerman |  | 45 |  | FALSE |  |  | 2018-08-14 | [6 empty] | 2/14/19, DL; We will schedule the work soon. The space is vacant and ready…………….2/1/19, DL; This project has started. We would like to have the work complete by mid March…………..12/14/18, DL; This project is prioritized at 45 and will not be shceudled until further notice…… |  | Enrico Baez | 11/08/18 RV: Enrico is assisting RV and has scheduled a job walk with Laurie Graham. Will follow up, pending confirmation. 11/19/18 EB-Met with Laurie Graham at site. SCOPE CARPENTERS-Remove all wall, base and center island cabinet work. Verify no ACM flooring under center island. PLUMBERS-Remove sinks in 1270 and 1270A. Terminate, at wall plumbing. Remove air/gas lines on wall in 1270 and 1270A. Remove lower chilled water, supply and return, lines on East wall. Remove air and gas line, flush with floor, from center island. FLOORING-Remove VCT in 1270 and 1270A, replace with customer selected VCT. Replace all cove base. ELECTRICIANS-Remove gray flexible conduit at raceway, terminate circuit. PAINTERS- Patch and paint walls in both spaces. | YES | FS | 0 | 2018 | 2019-03-01
19P000185 |  | 19P000185 | FALSE | CNAS | SL5-NEW FACUTLY - AIR DUCT CONNECTION AND GLOVE BOXES MOVE | Scope of work has been identified and walked with Requestor, F.S. Trades and P.M. Trade work in progress. | PIERCE | 206 (originially identified as Room 204) | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 6 | TRUE |  |  | 2018-06-18 | [6 empty] | 12/14/18, DL; This project is 100% Complete……11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. Pending glove box relocation to rm 319 and minor vent reconfiguration. Both tasks will be performed afet the glove boxes relocate to rm. 319. 10/29/18 All project related work is completed. |  | Ron Veloz | 07/05/18 RonV. Input: I observed multiple WO's for this project and spoke with Zee for clarification. I will investogate the site on 07/06 to determine the actual SOW. 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/22/18 O-RVL: Revised WO to Project no. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". =10/03/18: RV, Work in progress. Plumber are working on new gas lines. Will coordinate glove box move after work in rm 319 is completed. 10/29/18 RV: All glove boxes, Solvent mixing equipment and Chemical cabinet are removed. Remaining work is to replace the existing PVC vent with stainless duct when materials arrive per Cory. Update from Matt L-Plumbing department is working on the gas lines and will continue work this week. | YES | FS | 0 | 2018 | 2019-03-01
19P000186 |  | 19P000186 | FALSE | CNAS | SL5-NEW FACULTY HOUSE COOLING CONNECTIONS & DUCT CONNECTION | Complete as of 11/8/18 | PIERCE | 319 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Dan Lerman |  |  | 7 | TRUE |  |  | 2018-06-18 | [6 empty] | Pending gas line installation scheduled for the week of 09/24 per Steve Burleson. Move glove boxes from 206 to Rm 319 after gas line are installed. All work is complete |  | Ron Veloz | 8/10/18 DND: Ron V. conducted scope review, notes to be added when FAMIS project created. 08/23/18-RV: Some work was in progress due to individual WO's prior to scoping all work. 08/27/18 RV: Updated notes. Moved to "Que to Start". 10/03/18 RV: Work in progress, Plumbers are installing gas lines. Glove boxes from 206 can be moved after gas lines are installed. 10/08/148 RV: Plumbers to complete the installation of new gas lines in 319. Glove boxes to be brought to rm 319 after gas lines are installed. 10/17/18 RV: Update, Gas lines are installe approx 90% complete per Plumbing Tech, misc parts on order. 10/29/18 RV: All project related work is completeand confirmed with trades and PI. | YES | FS | 0 | 2018 | 2019-03-01
19P000188 |  | 19P000188 | FALSE | CAMPUS | SL5-PAINT - HALLWAY DOORS & INSIDE RESTROOMS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500 | CANCELED BY FS |  |  | ESTELLA DAVALOS |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-16 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-03-01
19P000189 |  | 19P000189 | FALSE | CNAS | SL5-PHYSICS- WALL HOLES PATCH | Duplicate work order to 19P000049. Work to be completed on other project. | PHYSICS | 3036 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-08-16 | [10 empty] | NO | FS | 0 | 2018 | 2019-03-01
19P000191 |  | 19P000191 | FALSE | CNAS | SL5-PATCH AND PAINT HINDERAKER BASEMENT | Complete as of 11/8/18 | HINDERAKER |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 34 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000192 |  | 19P000192 | FALSE | BAS | SL5-MAIL-PAINTING | Complete as of 11/8/18 | MAIL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | PRISCILLA MARTIN |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000193 |  | 19P000193 | FALSE | CNAS | SL5-GENOMICS 2221 - FOB ACCESS SYSTEM INSTALLATION | FS to coordinate with client to scope the work. | GENOMICS | 2221 | HOLD - FACILITIES SERVICES | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Dan Lerman |  | 41 |  | FALSE |  |  | 2018-08-20 | [7 empty] | 2018-10-08 | Ron Veloz | 02/21/19 O-RVL: RV received request for status of estimate from Aimee G. RV replied to send Estimate by CBD today. END--- 02/15/19 O-RVL: RV-preparing estimate to deliver to the customer on the week of 02/17/19. END--- 01/31/19 O-RVL: Pending proposal revisions with equipment itemized with make and model no. from the Access control vendor. Revised proposal due soon per vendor. END--- 01/15/19 O-RVL: Forwarded access controls quote and SOW to Jason and Chris Rodriguez to review and qualify the HCI quote. Pending response. --- 01/10/19 O-RVL: RV received quote and will send a formal Estimate to Aimee by EBD Fri. 01/18 and ask if they would like to procede. 12/14/18 O-RVL: REQUEST FOR ESTIMATE ONLY. Send Estimated costs to Aimee Gonzales for review and approval. Pending access controls and auto door operator quotes. Moved to Queue to start. 11/08/18 O-RVL: Scope is complete. Assisting the lock shop with pricing to provide the requestor an estime prior to start of construction. Walked a 2nd vendor , pending quote for access control card reader. 11/05 RV called vendor for quote, no reply. 10/29/18 RV: Conducted jobwalk with vendor last week. Pending quote from Vendor. Will follow up. | YES | FS | 0 | 2018 | 2019-03-01
19P000194 |  | 19P000194 | FALSE | CHASS | SL5-PAINTING/HOLE PATCHING FACULTY OFFICES HMNSS 2014 & 3304 | Complete as of 11/8/18 | HUM & SOC SC | 3304 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-08-20 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000195 |  | 19P000195 | FALSE | CHASS | SL5-HUM & SOC SC-ROOM PAINTING | Complete as of 11/8/18 | HUM & SOC SC | 2003 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 12 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000196 |  | 19P000196 | FALSE | CHASS | SL5-PAINT OFFICE AT UNIVERSITY THEATER | Complete as of 11/8/18 | THTR WKSH |  | COMPLETE | Milagros Pena | Cindy Williams | JULIE SALGADO |  | Paul Ditty |  | 15 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000197 |  | 19P000197 | FALSE | CNAS | SL5-PATCH AND PAINT OFFICE, LOBBY AND HALL | FS to coordinate with client to schedule work for completion. | COLLEGE BLDG NO | 0203B | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 44 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000201 |  | 19P000201 | FALSE | CHASS | SL5-PATCH AND PAINT THE WALLS | Complete as of 11/8/18 | CHASS INT S | 3111A | COMPLETE | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 18 |  | FALSE |  |  | 2018-08-22 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000205 |  | 19P000205 | FALSE | BCOE | SL5-LABORATORY RENOVATION FOR NEW FACULTY | Plans under review by Fire Marshal; clarification required on sprinkler system. | BOURNS | A0328 | COMPLETE | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  | Dan Lerman |  | 4 |  | TRUE |  |  | 2018-08-23 | [6 empty] | 2/28/19, DL; This Project is 100% Complete…….2/1/19, DL; This project is 99.9% Complete………..1/15/19, DL; This project is 90% complete. WE still need to finish snorkels and ceiling tiles. We should be 100% complete by 2/1/19……12/14/18, DL; This project is on schedule..11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/4/18; This is a large scale project, we will walk with the trade supervisors next week. We will also work on the plans and schedule the work. Target Date is 1/1/19…..DL, 11/7/18; work is scheduled. We are working on the electrostatic paint contract. We are in plan check review process. There are questions about the fire sprinklers from Scott J. Sent Scott J. an email requesting a site visit to better determine if any work will be required on the sprinkler system….. |  | Ron Veloz | 10/03/18: RV spoke with Dan. He had previously met with Maggie and had scoped this project. | YES | FS | 0 | 2018 | 2019-03-01
19P000207 |  | 19P000207 | FALSE | CHASS | SL5-QUOTE FOR RENOVATIONS ROOM 3331 & 3333 - RACHEL WU - WALL REMOVAL, FLOORING, NEW DOOR, CEILING TILES AND PAINT | FS to coordinate with client to scope the work. | OLMSTED |  | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Dan Lerman |  | 7 |  | FALSE |  |  | 2018-08-23 | [7 empty] | 2018-09-20 | Enrico Baez | 9/13/18 EB emailed Toya Adams to schedule site visit. 9/19/18 EB-Site visit scheduled for 9/20/18. 9/20/18 EB-Conducted site visit. Request to remove window in hall and install door. Interior space wall not to be removed. Secure doors, blank off and cover with sound soak. Replace carpet with Vinyl Plank, patch and paint. | YES | FS | 0 | 2018 | 2019-03-01
19P000208 |  | 19P000208 | FALSE | BAS | SL5-PLAZA GARAGE DOOR REPLACEMENTS E AND C BUILDINGS | Canceled per customer on priority list 9/17/18 | THE PLAZA |  | CANCELED BY CLIENT | Gerry Bomotti | Georgianne Carlson | CARLA CHAPPLE |  | Dan Lerman |  | Canceled |  | FALSE |  |  | 2018-08-14 | [8 empty] | Enrico Baez |  | NO | FS | 0 | 2018 | 2019-03-01
19P000209 |  | 19P000209 | FALSE | PLANNING & BUDGET | SL5-OLD EH&S SITE- FS ANNEX A REMODEL | Scope of work has been reviewed and being scheduled for completion. | ENV H AND S | 100 | IN PROGRESS | Gerry Bomotti | TBD | FRANCES RAVE |  | Craig/Chris Pillen |  |  |  | FALSE |  |  | 2018-08-24 | [6 empty] | 9/10: Zee assigning work orders per Chris' walk with Craig. |  | Chris Pillen | Chris walked the project with Craig Kasten on 9/6. | YES | FS | 0 | 2018 | 2019-03-01
19P000210 |  | 19P000210 | FALSE | CNAS | SL5-CHEMICAL SCI Install Door In Doorway | FS to coordinate with client to scope the work. | CHEMICAL SCI | 0225A | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  |  |  | 25 |  | FALSE |  |  | 2018-08-24 | [7 empty] | 2018-09-19 | Ron Veloz | 09/19/18-RV, Scope of work is complete. RV to upload docs to FAMIS. 10/03/18 RV: Install non rated door into an existing cased opening-for privacy & noise reduction. Will require carpentry-framing, patch, paint, and minor flooring/base repair. | YES | FS | 0 | 2018 | 2019-03-01
19P000211 |  | 19P000211 | FALSE | CAMPUS | SL5-LIFE SCIENCE 2545--PATCH & PAINT CUSTODIAN BREAK ROOM | Reviewing campus standards for these project requests. | LIFE SCIENCE | 2545 | CANCELED BY FS |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-03-01
19P000212 |  | 19P000212 | FALSE | CAMPUS | SL5-REPAINT HALLWAY & RESTROOMS+REPLACE MISSING FLOOR BOARDS | Reviewing campus standards for these project requests. | LIFE SCIENCE | CR2500A | HOLD - FACILITIES SERVICES |  |  | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  |  |  |  | FS | 0 | 2018 | 2019-03-01
19P000213 |  | 19P000213 | FALSE | CNAS | SL5-NEEDS FOR NEW WALL DISPLAY (MONITOR) | Duplicate request to 19P000031; Work to be completed on other project. | BIOLOGICAL SCI | 3101 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS | [5 empty] | FALSE |  |  | 2018-08-24 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000214 |  | 19P000214 | FALSE | CNAS | SL5-PHYSICS 3005-NEW FACULTY OFFICE CARPET AND PAINT | Complete as of 10/10/18 | PHYSICS | 3005 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-08-24 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000215 |  | 19P000215 | FALSE | BAS | SL5-SET KITCHEN EQUIPMENT IN PLACE AT HUB THIRD FLOOR ROOM 346 | Coordinating movement of equipment and utility connections. | HUB | 346 | COMPLETE | Gerry Bomotti | Georgianne Carlson | GUSTAVO PLASCENCIA |  | John Peraino |  | 9 |  | FALSE |  |  | 2018-08-24 | [6 empty] | 12/12/18 DND Project complete; electrical was installed and all kitchen equipment was hooked up as requested. |  | Enrico Baez | 9/13/18 EB emailed Gustavo Plascncia to schedule site visit. 9/18/18 EB. Conducted site visit. Connect water, drain and gas lines to kitchen equioment. Double oven need hardwired electrical. HUB staff will attach al shelving to walls. Day crew to move and deliver equipment. | YES | FS | 0 | 2018 | 2019-03-01
19P000216 |  | 19P000216 | FALSE | CHASS | SL5-HUMANITIES 1214-SMALL AREA OF WALL TO PATCH AND PAINT | Complete as of 11/8/18 | HUM & SOC SC | 1214 | COMPLETE | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 13 |  | FALSE |  |  | 2018-08-27 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000217 |  | 19P000217 | FALSE | GSOE | SL5-PAINTING, CARPENTRY AND NEW CARPET IN SPROUL 1359 | FS to coordinate with client to scope work. | SPROUL | 1359 | IN PROGRESS | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-27 | [6 empty] | 2/1/19, DL; This proect will start on 3/1/18 and should be complete by 4/1/19…… | 2018-09-18 | Enrico Baez | 9/18/18 E. Baez Conducted site visit. Scope of work Carpentry Remove 20 feet of built-in wood cabinets and counter top. Install TV mount on South wall. Remove and replace white board on North wall. Abatement Abate approximately 200 square feet of 9â€ x 9â€ VCT tile and base cove Flooring Install carpet similar to what is in room 1357 Replace base cove. Walls Patch and paint walls. Electrical Install duplex outlet for TV Replace fluorescent lamps with LED lamps TV Install data point and Internet connection to support video conferencing. Custodial Vacuum dust from ceiling tiles. 9/13/18 EB-emailed Karen Naples to schedule site visit. 9/18/18 EB-Conducted site visit. Request to remove cabinet, abate VCT, install carpet, mount TV. Electrical and date lines needed. Install white board. Replace flourescent tube with LED. | YES | FS | 0 | 2018 | 2019-03-01
19P000220 |  | 19P000220 | FALSE | CHASS | SL5-ARTS - REPLACEMENT OF FILM SCREEN IN ARTS 333 - PROJECT | Screen to be reinstalled on Friday 11/9/18. | ARTS | 333 | COMPLETE | Milagros Pena | Cindy Williams | SONJA SEKELY-ROWLAND |  | Dan Lerman |  | 1 |  | FALSE |  |  | 2018-08-28 | [6 empty] | 12/14/18, DL; This project is 100% Complete….11/15/18 DND Meeting Notes: Anticipated completion December 2018/January 2019. DL, 10/8/18; Screeen is scheduled to be removed this Friday. We will schedule the installation and the patch / Paint repairs once we receive the repaired screen back from the vendor…….DL, 11/7/18; This project should already be complete. However, The vnedor did not deliver the correct screen. The correct screen is currently scheduled for this Friday..... |  | Enrico Baez | 8/27/18 EB-Remove 12' wide screen from finished ceiling. Need electricians to diconnect power, carpenters to remove drywall and lower screen. Repared screen to be re-hung by carpenters and drywall repaired. Electricians to reconnect power. Painters to patch and paint. | YES | FS | 0 | 2018 | 2019-03-01
19P000221 |  | 19P000221 | FALSE | CHASS | SL5-PATCH, PAINTING, AND REGULAR CLEANING OF A126A | Complete as of 11/8/18 | OLMSTED | A0126A | COMPLETE | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 14 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000222 |  | 19P000222 | FALSE | BAS | SL5-PAINT EXTERIOR RAMP AT CBS HUB MODULAR SoB CENTER |  | PRINT MOD |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-02 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000224 |  | 19P000224 | FALSE | BAS | SL5-PAINT EXTERIOR RAMP AT HUB MODULAR | FS to coordinate with client to schedule work for completion. | PRINT MOD |  | QUEUE TO START | Gerry Bomotti | Georgianne Carlson | MIKE CLEMONS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000225 |  | 19P000225 | FALSE | VC-RED | SL5-UV OFFICE LEASE- BGC A SECURITY CARD ACCESS SYSTEM INSTALL | FS to coordinate with client to scope the work. | UV BLDG A | 0204A | HOLD - CUSTOMER EQUIPMENT/SCHEDULE | Michael Pazzani | Laura Manor | CRYSTAL JIMENEZ |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-08-28 | [7 empty] | 2018-09-27 | Enrico Baez | 9/13/18 EB-emailed crystal Jimenez to schedule site visit. 9/19/18 EB-Scheduled site visit for 9/20. 9/29/18 EB- install keyless entry system on two doors. 10/15/18 EB-sent Aaron Seitz approx. cost of project. Awaiting respone to determine funding. | YES | FS | 0 | 2018 | 2019-03-01
19P000226 |  | 19P000226 | FALSE | CHASS | SL5-PAINT OFFICE HMNSS 3304 | Duplicate request; project to be completed on 19P000194 | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-08-28 | [8 empty] | Paul Ditty | Duplicate request; project to be completed on 19P000194 |  | FS | 0 | 2018 | 2019-03-01
19P000226 |  | 19P000226 | FALSE | CHASS | SL5-PAINT OFFICE HMNSS 3304 | Duplicate to 19P00014; work to be completed on original project. | HUM & SOC SC | 3304 | CANCELED BY CLIENT | Milagros Pena | Cindy Williams | LEANN GILMER |  | Paul Ditty |  | Duplicate |  | FALSE |  |  | 2018-08-28 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000227 |  | 19P000227 | FALSE | BAS | SL5-DINING STORAGE ROOM CONVERSION | Scheduled work with trades anticipated completion December 2019. | BANNOCK J | J0100 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | DARCI LOMBARD |  | John Peraino |  | 2 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 2/8/19: JP storage room slated to be completed simultaneously with break room as water supply connections will be done together with break room. Completion date for both is approximately three weeks. |  | Enrico Baez | 9/12/18 EB-Install Drywall, Patch & Paint, cap water line, install VCT & Cove Base, Verify HVAC operation, replace hydralic door closer, install LED lamps, Security light. Scope sent to Edwin Melgar for approval. | YES | FS | 0 | 2018 | 2019-03-01
19P000229 |  | 19P000229 | FALSE | GSOE | SL5-RENOVATE OLD DRINKING FOUNTAIN AREA SPROUL BLDG. 3 1ST FLOOR | FS to coordinate with client to scope work. | SPROUL |  | QUEUE TO START | Thomas Smith | Sally Tavizon | KAREN NAPLES |  |  |  | 4 |  | FALSE |  |  | 2018-08-29 | [8 empty] | Enrico Baez | 9/20/18 EB-conducted site visit 9/18. Request for tile and plumbing removal, patch and paint. To facilitate placement of printer system. E-mail sent to Monty on 9/14 asking for direction on renovating hallway space. Awaiting Susan's response per Monty. Entered scope on shared drive. Will need Fire Marshal approval to determine which of three possible locations will allow placing of WEPA system. 11/13/2018 E. Baez-Met with Ron Rector to discuss system placement. WEPA system is to be placed on second floor near vending machines on North side. See note in shared drive. Will need power and data connections. | YES | FS | 0 | 2018 | 2019-03-01
19P000230 |  | 19P000230 | FALSE | CNAS | SL5-NEW FACULTY OFFICE FOR PATCHWORK/PAINT | Complete as of 10/10/18 | GEOLOGY | 1242A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | TRUE |  |  | 2018-08-30 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000231 |  | 19P000231 | FALSE | CNAS | SL5-OLMH 1428 PATCH AND PAINT | FS to coordinate with client to schedule work for completion. | OLMSTED | 1428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ANDREW CABRERO |  | Paul Ditty |  | 48 |  | FALSE |  |  | 2018-08-30 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000232 |  | 19P000232 | FALSE | BAS | SL5-BANNOCKBURN J-104 BREAK ROOM UPGRADE | Scheduled work with trades anticipated completion December 2019. | BANNOCK I | I0105 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | John Peraino |  | 6 |  | FALSE |  |  | 2018-09-04 | [6 empty] | 2/8/19 JP: Finishing up the cabinet and lighting order, will be submitting to purchasing today Scheduling installation of VCT flooring pending per Tony’s Flooring, will have date this week New ceiling tiles have been delivered and will be installed when relocating of electrical components are complete Awaiting confirmation and clearance from Jess to proceed with cutting into walls to facilitate electrical modifications |  | Enrico Baez | 9/19/19 EB-conducted site visit. Entered Scop in FAMMIS and in BZM projects on shared drive. Requires pluming for sink and disposal, electrical, lighting upgrade. | YES | FS | 0 | 2018 | 2019-03-01
19P000233 |  | 19P000233 | FALSE | BAS | SL5-PATCH AND REPLACE VINYL FLOOR TILE&INSIDE DOORS PAINTED BLUE | FS to coordinate with customer to scope the work. | MAIL | 884 | CANCELED BY FS | Gerry Bomotti | Georgianne Carlson | AMY EVERETT |  |  |  | 12 |  | FALSE |  |  | 2018-09-04 | [8 empty] | Enrico Baez | Per Enrico, creating two individual WO's for Tile repair (19W004955) and door painting (19W004956). | YES | FS | 0 | 2018 | 2019-03-01
19P000234 |  | 19P000234 | FALSE | CNAS | SL5-PHYSICS 3005-WALL HOLES PATCH | Duplicate work request. | PHYSICS | 3005N | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | JAZMIN CHAVEZ |  | Paul Ditty |  | Canceled |  | FALSE |  |  | 2018-09-04 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000235 |  | 19P000235 | FALSE | BAS | SL5-RESIDENCE HALL MUSIC ROOM COMESTIC UPDATES 6 room | Customer to determine scope of work. | ABER INVER | A0100 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 11 |  | FALSE |  |  | 2018-09-04 | [7 empty] | 2018-11-01 | Enrico Baez | 11/26/18EB-Tranfered FAMIS work order to John Peraino's bench. Estimate to customer needed, prior to moving forward with project. 11/26/18 EB-SCOPE entered Aberdeen Inverness • Paint acoustic panels. Customer to provide color specification. • Remove carpet and replace with customer specified vinyl plank flooring. Replace base board • Cut door to accept 16” x 7” glass lite. Frame as needed. • Paint door • Replace surface mounted light fixture with LED surface mounted fixture. Customer to approve design. • Clean, paint or replace A/C vents. • Remove louvered vent in wall for abandoned water cooler. Install sheet metal cover, paint to match new wall color. Pentland Hills -Rooms 105 and 107 • Install full height acoustic panels on three walls. • 4th wall on East side of each room gets mirror. Height of mirror to be flush with top edge of door casing. Mirror width to be between inside corner of wall and switch plate cover. Provide cut out in mirror for thermostat installation. • Replace all ceiling tiles. • Replace 2’ x 2’ ceiling light with 2’ x 4’ LED fixture-customer to approve design. Pentland Hills -Rooms 105 and 107 • Remove carpet and replace with vinyl plank flooring, replace base board • Fire rated doors to be replaced with fire rated doors with small lite, approx. dimensions 16’ x 7”. • Paint as needed. Lothian • Install full height acoustic panels on three walls. • 4th wall gets mirror height to be even with door casing height. Customer to determine location. • Replace all ceiling tiles. • Replace ceiling lights with LED fixtures. • Remove all carpet in rooms and replace with vinyl plank and new base board-customer to specify style and color. • Replace door wire reinforced glass with clear, non-reinforced fire rated glass. • Paint as needed. Suggested Vendor for sound absorbing paneling. Riverside Acoustics Contact: Keith Atkins 951-682-6123 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 Met with Bob and Lisa, no firm plans or ideas in place. Lisa will schedule site walk once they have determined what they want. 11/1/18 Conducted site visit with Bob and Lisa. | YES | FS | 0 | 2018 | 2019-03-01
19P000236 |  | 19P000236 | FALSE | BAS | SL5-EXTERIOR RESIDENTIAL HYDRATION STATION INSTALLATION | Scheduled work with trades anticipated completion December 2019. | ABER INVER | A0100 | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 10 |  | FALSE |  |  | 2018-09-04 | [6 empty] | 2/8/19 JP Estimated completion end of February | 2018-11-01 | Enrico Baez | 11/27/18 EB-Entered scope of work. Transferred work order to John Peraino in FAMIS. Estmate to be provided prior to work start. Aberdeen Inverness Lobby across from RSO. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Pentland Hills 1st floor of I/J, K/L, M/N, O/P • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Pentland Hills Alcove between E&F building. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exterior wall adjacent to B-101 • Remove existing dual fountain. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed. Exercise Room H-101 • Install HS where pluming repairs were made in East wall. • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch all walls and Paint as needed. Glen Mor K-206 Fitness Room • Remove existing double water fountains. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. Glen Mor Pool area • Remove existing double water fountains and HS. • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Make any needed drywall repairs. • Patch and Paint as needed. • Install base board as needed. • Repair any brick work as needed Lothian Hallway near Dining Hall cashier stand adjacent to fire extinguisher cabinet • Remove existing HS • Ensure electrical, water and drain connections can accommodate new HS. • Provide any structural support for HS. • Patch and Paint as needed Sample sheet. https://www.restroomdirect.com/halsey-taylor-drinking-fountains-and-water-coolers.aspx 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Waiting for Lisa L. to schedule site visit. Total number of station and needs not completed. 11/1/18 EB Conducted site visit with Lisa and Bob. AI Replace Hydration Station (HS) in Lobby near RSO Pentland Hills Replace fountains with HS first floor I/J, K/L, M/N, O/P. Also remove fountains and install HS near B-101, Alcove between E&F, H-104. Glen Mor Remove fountain at pool & K-206 fitness room, replace with HS. Lothian Replace existing HS near cashier to Dining Hal | YES | FS | 0 | 2018 | 2019-03-01
19P000237 |  | 19P000237 | FALSE | GSOE | SL5-PATCH AND PAINT OFFICE - SPROUL 1206 | FS to coordinate with client to schedule work for completion. | SPROUL | 1206 | IN PROGRESS | Thomas Smith | Sally Tavizon | KAREN NAPLES |  | Dan Lerman |  | 2 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 2/1/19, DL; This project will start on 3.1.19. We will need to abate ACM before we can start. Jess will isuue the 14- day notification to the AQMD. Once we have confirmation, we will schedule the work…….. | 2018-10-05 | Enrico Baez | 0/5/18 E. Baez- conducted site visit. Carpenters: Removes sliding chalk boards in 1206 and 1206 and fill in with wall. Remove patched in panels on left of chalk board in 1206. Patch where " do not enter" signs were removed. Electricians: Disconnect power to two "do not enter" signs above doors. Abatement: Remove approx 300 sq.ft. of ACM VCT Flooring: replace flooring with either VCT of vinyl plank. Painters: Patch and paint, at least one wall accent wall. | YES | FS | 0 | 2018 | 2019-03-01
19P000238 |  | 19P000238 | FALSE | VC-UNIV.ADV. | SL5-PATCH & PAINT HINDERAKER 1136 | Pending completion of one room outstanding for scheduling. | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-05 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000241 |  | 19P000241 | FALSE | PLANNING & BUDGET | SL5-PATCH/PAINT IN OFFICE 2122 HINDERAKER | Canceled per customer call on 9/13/18 | HINDERAKER | 2122 | CANCELED BY CLIENT | Gerry Bomotti | TBD | MILLY PAREDEZ |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-06 | [8 empty] | Paul Ditty |  | N/A | FS | 0 | 2018 | 2019-03-01
19P000242 |  | 19P000242 | FALSE | CNAS | SL5-PAINT OFFICE | FS to coordinate with client to schedule work for completion. | COLLEGE BLDG NO | 210 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 47 |  | FALSE |  |  | 2018-09-06 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000243 |  | 19P000243 | FALSE | CNAS | SL5-GENOMICS 1206 - PATCH AND PAINT WALLS | FS to coordinate with client to schedule work for completion. | GENOMICS | 1206 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | AIMEE GONZALES |  | Paul Ditty |  | 49 |  | FALSE |  |  | 2018-09-06 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000244 |  | 19P000244 | FALSE | CNAS | SL5-PATCH & PAINT GEOLOGY | Complete as of 10/22/18. | GEOLOGY | 2258A | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 10 |  | TRUE |  |  | 2018-09-06 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000245 |  | 19P000245 | FALSE | SOM | SL5-ADA COMPLIANT - AUTOMATIC DOOR ENTRY | FS to coordinate with client to scope the work. | SOM RSCH |  | QUEUE TO START | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 4 |  | FALSE |  |  | 2018-09-07 | [7 empty] | 2018-10-29 | Ron Veloz | 02/15/19 O-RVL: RV updated notes addedSOW & moved to "Que to Start". END--- 01/31/19 O-RVL: Chris at Lockshop reviewed the vendor quote and requested detailed equipment list. Pending revisions from vendor due this week. END--- 01/15/19 O-RVL: Delivered Access control quoute to Jason & Chris R for revie. They will respond with comments. Upon receicpt and confirmation, RV will complete docs on server folder and update FAMIS & Access DB. --- 01/11/19 O-RVL: Qualifying quote to verify proper components from door operator vendor expecting reply soon. 12/14/18 O-RVL: Received Quotes for Auto door operator and Access controls this week. RV to provide update & quotes to to Dan Lerman. Moving status to "Que to Start" on Minor Ren List & updating Project Folder. --- 11/07/18 O-RVL: Walked site with Access Control vendor --- 10/31/18 O-RVL: Walked site with Door Op vendor --- 10/29/18 O-RVL: Scope was Completed. RV to schedule job walks with Vendors. --- 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon | YES | FS | 0 | 2018 | 2019-03-01
19P000246 |  | 19P000246 | FALSE | CNAS | SL5-PHYSICS - PATCH AND PAINT | Complete as of 10/10/18 | PHYSICS | 3007N | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Paul Ditty |  | 46 |  | FALSE |  |  | 2018-09-07 | [6 empty] | n/a |  | Paul Ditty | Duplicate request; project to be completed on 19P000234 | N/A | FS | 0 | 2018 | 2019-03-01
19P000247 |  | 19P000247 | FALSE | BAS | SL5-LOTHIAN FIRST FLOOR COMMON AREA FLOORING | Complete as of 10/22/18. | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER |  | Jess Hernandez |  |  |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez |  |  | FS | 0 | 2018 | 2019-03-01
19P000248 |  | 19P000248 | FALSE | SOM | SL5-SOME--SOME INSTALL ELECTRICAL 1682 | FS to coordinate with client to scope the work. | SOM EDUC | 1682 | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  |  |  | 2 |  | FALSE |  |  | 2018-09-10 | [6 empty] | 2/14/19, DL; This project is complete…… |  | Ron Veloz | 10/29/18 O-RVL: Scoping is completed. END--- 10/17/18: RV: Drawings are on server folder. END---10/08/18 RV: Spoke with Brandon B. Brandon will submitt BKM drawings via permit request through PD&C. 09/20/18 O-RVL: Scheduled jobwalk at 10:00am on 09/21/18 - SOMR w/ Brandon. Walked project with Brandon. SOW to install two each dedicated 120v/20a cicuits for new modular furniture one whip at each end of the office down the wall and one to two data drops overhead down wall. | YES | FS | 0 | 2018 | 2019-03-01
19P000249 |  | 19P000249 | FALSE | SOM | SL5-SOME-INSTALL LOCKERS | Lockers on order by customer; upon arrival to be installed. | SOM EDUC |  | CANCELED BY FS | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Dan Lerman |  | 3 |  | FALSE |  |  | 2018-09-07 | [6 empty] | DL, 11/7/18; It is my understanding the lockers are ordered, but we donot have a confirmed delivery date. Once the material is on site, we will schedule the installation…… |  | Ron Veloz | 01/31/19 O-RVL: Contacted Domonic and confirmed lockers will not be avialable to install and agreed to cancel the request orginated on 09/07/18 and will resubmit a new request upon delivery of the new lockers. RV emailed Customer Relations staff to cancle the project request via emails and cc Monty, Deborah H., Alan, Loretta on the communication. 01/10/19 O-RVL: Emailed Dominic Salazar on locker delivery ststus. Pending follow up call from customer to inform FS on delivery of lockers. 11/08/18 RV: Visited site existing lockers in place and in use. Will follow up with the requestor for locker delivery status to schedule. RV Spoke with Brandon Barbosa. Deparment will purchase lockers. 11/08/18 RV: Received email from Domonic Salazar on 10/25 Lockers are expected to arrive. | YES | FS | 0 | 2018 | 2019-03-01
19P000250 |  | 19P000250 | FALSE | BCOE | SL5-BOURNS A303-PAINT AND PATCH WALL | Complete as of 10/10/18 | BOURNS | A0303 | COMPLETE | Christopher Lynch | Maggie Souder | JUANA GUERRERO |  | Paul Ditty |  | 5 |  | TRUE |  |  | 2018-09-10 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000251 |  | 19P000251 | FALSE | CNAS | SL5-CHEM SCI 428-PATCH DRY WALL HOLES | Complete as of 10/10/18 | CHEMICAL SCI | 428 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KEVIN KOU |  | Paul Ditty |  | 8 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-03-01
19P000252 |  | 19P000252 | FALSE | ATHLETICS | SL5-ATH DANCE SHOWER DOORS | FS to coordinate with customer to scope the work. | ATH DANCE | 0050K | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOSEPH ERBLAND |  |  |  | 3 |  | FALSE |  |  | 2018-09-10 | [8 empty] | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB Replace aluminum and glass shower doors. Will need to contract work. Replace all rusty fixtures in showering space, repair/replace tile as needed. | YES | FS | 0 | 2018 | 2019-03-01
19P000253 |  | 19P000253 | FALSE | CHASS | SL5-ARTS RENOVATION | Complete as of 9/21/18 | ARTS | 157 | COMPLETE | Milagros Pena | Cindy Williams | PAUL RICHARDSON |  | Dan Lerman |  |  | 16 | FALSE |  |  | 2018-04-17 | [6 empty] | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access……DL, 7/11/18; This project needs to be complete before Fall 2018. Space is vacant and ready go. Need to walk and confirm Schdule with Paul D. Tony's Flooring is ready to go after paint is complete.... Target complete date is 9/21/18......DL, 8/22/18; Walked with PAul, Paul will scheudle the work. Jess still need to cordinate with Tony's Flooring .....DL, 9/19/18; The paint and flooring is complete. The seams need to be welded and this will be complete. this will be complete by 9/21/18......9/19/21; This Project is 100% Complete....... |  | Dan Lerman | DL, 4/29/18; Project is scoped and include, new vinyl floor, paint, and water proofing. The floor area is over 2,000 square feet. This will be a Summer project due to access | YES | FS | 0 | 2018 | 2019-03-01
19P000255 |  | 19P000255 | FALSE | SPP | SL5-CHASS INT N REMODEL - 4022 PATCH AND PAINT | Complete as of 10/10/18 | CHASS INT N | 4022 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-09-10 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-03-01
19P000256 |  | 19P000256 | FALSE | SPP | SL5-CHASS REMODEL - 4146 PATCH AND PAINT | FS to coordinate with client to schedule work for completion. | CHASS INT S | 4146 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  |  |  | 3 |  | TRUE |  |  | 2018-09-10 | [7 empty] | 2018-10-09 | Enrico Baez | 10/9/18 EB Sent Luis email, copied Mont too. Project will bw $25k-$30K. Asked Luis if we are to proceed. 10/15/18 E.Baez conducted site visit, Client requested cost estimate to construct 2-3 "huddle" Spaces with sound proof walls. Requires alterations to HVAC ducting, full height walls with doors, fire sprinkler additions, smoke detection additions, lighting changes. emailed Luis estimated cost of $25,000. 12/20/18 D. DINH: Spoke with customer, Luis Alvarez, and the project request has been modified to patch & paint and replacement of one ceiling tile. Customer to work with BKM to fulfill the wall partition request portion of the project. | YES | FS | 0 | 2018 | 2019-03-01
19P000263 |  | 19P000263 | FALSE | SPP | SL5-CHASS NORTH REMODEL - 4009 PATCH AND PAINT | Complete as of 11/8/18 | CHASS INT N | 4009 | COMPLETE | Anil Deolalikar | Luis Alvarez | CHRISTINA WONG |  | Paul Ditty |  | 2 |  | TRUE |  |  | 2018-09-11 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-03-01
19P000265 |  | 19P000265 | FALSE | ATHLETICS | SL5-ATH DANCE -PATCH AND PAINT ROOMS 61 & 63 | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000266 |  | 19P000266 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH AND PAINT BASEMENT HALLWAYS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-11 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000268 |  | 19P000268 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH AND PAINT 20C | FS to coordinate with client to schedule work for completion. | ATH DANCE | 20C | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000269 |  | 19P000269 | FALSE | ATHLETICS | SL5-ATH DANCE - NEW FLOORING VINYL HALLS AND STAIRS | Project is not within the purview for completion; condition is fair and usable. | ATH DANCE |  | CANCELED BY FS | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 5 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18…..This is a cooman area. Is this recharge work……. | 2018-09-27 | Enrico Baez | 2/5/19 E. Baez. Common spaces are managed by Facilities Services. Any work done in corridors, stairwells and open spaces will be assessed by FS. 11/20/18 E. Baez-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB-Request for installing vinyl flooring. Remove and replace existing Terrazo and ceramic floor tile in 1st floor lobby and stairs to basement. | YES | FS | 0 | 2018 | 2019-03-01
19P000270 |  | 19P000270 | FALSE | ATHLETICS | SL5-ATH DANCE-WEIGHT ROOM DROP DOWN CEILING | FS to coordinate with customer to scope the work. | ATH DANCE | 78 | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 14 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project is 100% Complete….. |  | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB remove all t-bar ceiling components. Will need relocation of supply and return registers, lighting Alarms, Etc. |  | FS | 0 | 2018 | 2019-03-01
19P000271 |  | 19P000271 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH, PAINT, AND CARPET 3, 5 7 | FS to coordinate with client to schedule work for completion. | ATH DANCE | 3 | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-09-12 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000272 |  | 19P000272 | FALSE | ATHLETICS | SL5-NEED URINAL DIVIDERS | FS to coordinate with customer to scope the work. | ATH DANCE | 50E | HOLD - FACILITIES SERVICES | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 13 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 1/15/19 E Baez. Per "Monty" project cancelled to be placed on Deferred Maint. list. emailed Chris P. to provide renovation cost and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Install dividers for urinals. Wall is tile. |  | FS | 0 | 2018 | 2019-03-01
19P000273 |  | 19P000273 | FALSE | ATHLETICS | SL5-ATH DANCE - PATCH, PAINT AND CARPET MULTIPLE LOCATIONS | FS to coordinate with client to schedule work for completion. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-12 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000274 |  | 19P000274 | FALSE | ATHLETICS | SL5-RIV SPORTS CPX - REPLACE URINALS | FS to coordinate with customer to scope the work. | RIV SPORTS CPX |  | HOLD - FACILITIES SERVICES | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 15 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-10-15 | Enrico Baez | 1/14/19 E Baez. Per "Monty" this project to go on deferred maint. list. emailed Chris Pillen to provide coast and forward to Susan M. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27. 10/3/18 EB not time to visit on 9/27. will schedule follow up meeting. 10/15/18 EB conducted site visit, 11 urinals to be replaced. | YES | FS | 0 | 2018 | 2019-03-01
19P000275 |  | 19P000275 | FALSE | ATHLETICS | SL5-SOFTBALL STG PRESS BOX AC ADDITION | FS to coordinate with customer to scope the work. | SOFTBALL STG |  | CANCELED BY CLIENT | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 6 |  | FALSE |  |  | 2018-09-12 | [6 empty] | 2/14/19, DL; This project was canceled by Johnathan J. as there is not funding at this time…………DL, 10/4/18; I checked on this recently and this is not a building, it is stoarge and should be recharge work…. | 2018-09-27 | Enrico Baez | 2/5/2019 E Baez Client wants a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. Client will need to fund this project as this is not a core building 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB Client want a window heat pump installed in press box under bleachers at Soft Ball Field. 208V disconnect at building. Install unit on narrow West wall. |  | FS | 0 | 2018 | 2019-03-01
19P000276 |  | 19P000276 | FALSE | ATHLETICS | SL5-TRACK BLEACH-PUBLIC RESTROOMS UPGRADE | Project to be completed through A&E and CPMS. Scope of work beyond FS purview. | TRACK BLEACH |  | TO BE PERFORMED BY PD&C | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 16 |  | FALSE |  |  | 2018-09-12 | [7 empty] | 2018-09-27 | Enrico Baez | 11/20/18 EB Project cancelled, will be addressed by PD&C. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/18 EB conducted site visit, Client wants additional toilet in mens room, changing table and lighting improvements. ADA Issues. Also spoke with Scott Donnell he has project . | YES | FS | 0 | 2018 | 2019-03-01
19P000277 |  | 19P000277 | FALSE | ATHLETICS | SL5-ATHLETICS - CARD ACCESS (SECURITY ENHANCEMENT) | FS to coordinate with customer to scope the work. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 10 |  | FALSE |  |  | 2018-09-12 | [6 empty] | ??????? | 2018-09-27 | Enrico Baez | 1/14/19 E Baez. Per "Monty" Athletics are to pay for this project. Joe Erbland emailed to determine if funding has been approved. Waiting on response. 11/20/18 EB-Intake review completed, forwarded to Facilities Services leadership for discussion with Athletics end of November. 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB Install keyless entry system for building exterior. | YES | FS | 0 | 2018 | 2019-03-01
19P000278 |  | 19P000278 | FALSE | BCOE | SL5-REPLACE FLOORS WITH LINOLEUM PLANK AND LIGHT REPAIR | Scheduling work for completion | BOURNS | A0165 | COMPLETE | Christopher Lynch | Maggie Souder | NANCY FORD |  | Dan Lerman |  | 1 |  | TRUE |  |  | 2018-08-03 | [6 empty] | DL, 10/4/18; This Project is 100% Complete…….. |  | Ron Veloz | Completed SOW, met withJess and informed of work and color. | YES | FS | 0 | 2018 | 2019-03-01
19P000279 |  | 19P000279 | FALSE | ITS | SL5-HUB - ADD 2 POWER OUTLETS |  | HUB |  |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-09-13 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000280 |  | 19P000280 | FALSE | SoB | SL5-ANDERSON HALL PAINT ONLY |  | ANDERSON 2 | 113 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-09-13 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000283 |  | 19P000283 | FALSE | CNAS | SL5-HOPKINS-ENVIRONMENTAL SCIENCES CHUNG ROOF ACCESS | FS to coordinate with client to scope the work. | CHUNG HALL | ROOF | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | DEBORAH MCWILLIAMS |  |  |  | 20 |  | FALSE |  |  | 2018-09-05 | [7 empty] | 2018-09-19 | Ron Veloz | 10/17/18 RV: All construction information is on the server folder. Pending Saftey MOP's from Beiwei. Left message with her on Monday 10/15 for status. 10/03/18 RV: SOW, Install safety guard railing and apply yellow markings (leading edge 6'from perimeter) on the Winston Chung Roof. 09/19/18-Scope is complete, received safety requirements prepared by EH&S/Beiwei. RV to upload onto FAMIS. | YES | FS | 0 | 2018 | 2019-03-01
19P000284 |  | 19P000284 | FALSE | CAMPUS | SL5-GEOLOGY ACCOMMODATION DOCK DOORS | Coordinating work for completion. | GEOLOGY |  | COMPLETE |  |  | DEBORAH TERAO |  | Chris Pillen |  | Canceled | Canceled | FALSE |  |  | 2018-08-07 | [8 empty] | Ron Veloz | 01/10/19 O-RVL: CLOSE OUT-WORK COMPLETED. All work for this project is completed. Email sent to Monty & team on Jan 04, 2019 confirmating all work is completed. 12/14/18 O-RVL: Loading dock Post and Chain fabrication, is in progress, Auto door operators are on Order/Contract in progress, Loading dock signage is in progress by sign shop, information was confirmed by Chris Pillen as of 12/13/18. All other request related to this project have been completed. RV sent updates to Monty on 12/13/18. 11/14/18 RV: Walked Capitol door on 10/31 for pricing. pending quote for auto door operators. 10/30/18 RV: Walke Paradise Door -Automatic Door operator vendor to site. Met with Jason to discuss door access hardware & function of locksets . Pending quote. 10/03/18 RV: Notes from FAMIS: Lock Shop - Chris working with Jason to purchase and install two sets of automatic door openers with plain face plates - to be installed in the back receivin area. | YES | FS | 0 | 2018 | 2019-03-01
19P000285 |  | 19P000285 | FALSE | CNAS | SL5-PAINT AND PATCH PI OFFICE |  | ENTOMOLOGY | 269 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-09-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000286 |  | 19P000286 | FALSE | CHASS | SL5-FACULTY OFFICES: TOUCH UP PAINT |  | HUM & SOC SC | 2005 | QUEUE TO START | Milagros Pena | Cindy Williams | JILL CANTONWINE |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-09-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000287 |  | 19P000287 | FALSE | CNAS | SL5-URGENT: PAINT SHOP TO PATCH AND PAINT | Complete as of 10/22/18. | MAT SCI ENGR | 229 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | HONG XU |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-09-19 | [8 empty] | Paul Ditty |  |  | FS | 0 | 2018 | 2019-03-01
19P000288 |  | 19P000288 | FALSE | CNAS | SL5-COLLEGE BLDG NORTH- PAINTING VARIOUS ROOMS |  | COLLEGE BLDG NO | 202 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2018-09-19 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000291 |  | 19P000291 | FALSE | CNAS | SL5-MSE HELIUM RECOVERY SYSTEM | Work has been completed; FS teams verifying completion and quality check of work. | MAT SCI ENGR | 205 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | MAYELA CASTILLO |  | Dan Lerman |  | 9 | HOLD | FALSE |  |  | 2017-07-24 | [6 empty] | 12/14/18, DL; This project is 100% Complete……DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB - spoke with Mayela who is determining status within her dept…. DL, 11/7/18; This project is complete but I need to conduct a final site visit….. |  | Ron Veloz | DD 10/6: Enrico to inform customer to buy equipment; scoped by Chris. 2/5: Creating a project for Chris. On hold per customer; reprioritized to # 7 per Deborah M. 6/12/18 EB-Spoke with Mayela-she is researching where the project stalled within her department. 7/2/18 DND Please verify if work is still required for completion 8/7/18 EB-sent Mayela email requesting update on 9/20/18 EB-emailed Mayela to determine status of project. 9/24/18 EB-Project not cancelled. Passed on to Ron Veloz. 10/03/18: RV, Walke job with Mayela, Chris P, Dan L & Deb McWilliams. PI to provide Dan layout and equipment specs. | YES | FS | 0 | 2017 | 2019-03-01
19P000292 |  | 19P000292 | FALSE | CNAS | SL5-GEOLOGY BLDG - OUTSIDE INSTALLATION OF PM10 SAMPLER | Site vist completed; identifying a feasabile site location for work. | GEOLOGY |  | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Dan Lerman |  | 18 |  | FALSE |  |  | 2018-08-10 | [6 empty] | 2/14/19, DL; The Concrete and Power is Complete. We still need to install the chain link which will be installed in about 3-4 weeks………..2/1/19, DL Electrical is complete. WE will pour Concrete next week. We will schedule the fence install 28- days after concrete is poured………; Th1/15/19, DL; Plans are approved, we will start the work in the next two weeks……12/14/18, DL; Plans are almost complete. We will schedule the work after plans are approved……DL, 11/7/18; Conducted site visit with Chris P. We need to confirm a feasable site location before we move forward with the work…. |  | Ron Veloz | 10/30/18 RV: Chris Pillen and D. McWilliams aggreed to leave the building in place and place a concrete pad with a chain link fence adjacent to the existing structure. 10/17/18 RV: SOW, demolish walls and roof. Verify and cap existing underground utilities. Remove overhead electrical from power pole to the building. The concrete pad to remain and install a 6'H fence with gate around the pad. Bring Power below grade to pad location. Met with C.Pillen and Dan to discuss alternate options. Photos and equipment info is on the server file. | YES | FS | 0 | 2018 | 2019-03-01
19P000293 |  | 19P000293 | FALSE | ITS | SL5-PAINT ESTIMATE REQUEST | Canceled by Customer 10/24/18 | TELEPHONE |  | CANCELED BY CLIENT | Danna Gianforte | Shelley Gupta | TAMI FRIEDRICH |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-08-21 | [6 empty] | n/a |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000295 |  | 19P000295 | FALSE | ATHLETICS | SL5-PATCH & PAINT | FS to coordinate with client to schedule work for completion. | ATH DANCE | 50B | COMPLETE | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  | Paul Ditty |  | 12 | 18 - 19 | FALSE |  |  | 2018-09-12 | [6 empty] | 1/11/19 DND - Complete per FAMIS |  | Paul Ditty | n/a | N/A | FS | 0 | 2018 | 2019-03-01
19P000296 |  | 19P000296 | FALSE | CAMPUS | SL5-MS&E-ENCLOSURE FOR CONTAINERS IN MSE 0178 LAB | Plans and permits to be developed for this project. | MAT SCI ENGR |  | COMPLETE |  |  | MILLY PAREDEZ |  | Dan Lerman |  |  |  | FALSE |  |  | 2018-09-25 | [6 empty] | 2/28/19, DL; Project is 100% Complete…….2/14/19, DL; This project is 90% Complete and should be complete by the end of the month………….2/1/19, DL; Permits are approved, we will schedule the project in the next 2- weeks and hope to be complete by the end of February….12/14/18, DL; Rendering has been given to Ron R. Ron will present to Gerry for review and approval. Once approved, we will proceed with plans and permits……DL, 11/7/18; Need to find out where this project stands in regards to the priioroity….. Site vist was conducted and scope of work is verified. Plans and permits will be required for the work….. |  | Ron Veloz | 10/19/18 O-RVL: Walked the proposed location with Dr. Barsukov to review needs and location for nitrogen tanks in the hall. DL suggested to construct a wall with double doors approx 2' below the ceiling height. 09/27/18 O-RVL: Walked site with Chris P, Dan L., Deborah Mc Williams & Mayela C to review SOW. | YES | FS | 0 | 2018 | 2019-03-01
19P000298 |  | 19P000298 | FALSE | CNAS | SL5-SPIETH - PREP LAB FOR FACULTY SEARCH |  | SPIETH | 1363 | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  |  |  | 0 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 2/14/19, DL; Need to schedule trades and obtain quotes to refinish countertops…… |  | Ron Veloz | 01/15/19 O-RVL: RV to scope once priority is established. RV updated notes with information provided from Deborah Mc Williams. Spieth 1363 – Wet Lab Space Note by DMcWilliams.: "There is evidence in the ceiling and along one wall of a water intrusion issue, i.e. peeling paint, leaking and rusted pipes, etc. The cause of this damage needs to be investigated and repairs confirmed, including painting the wall and ceiling where damage is visible". Patch/paint Re-finish, re-surface – existing cabinets Re-finish and/or replace bench-tops If both sinks cannot be significantly cleaned, they should be replaced, Replace faucets at both sink locations. Clean existing Chemical fume hood Repair or replace self-closing chemical / flammables storage cabinet On one bench remove overhead shelving unit and relocate electrical outlets to the ends of bench to accommodate large desktop equipment. Cap off remaining utilities for potential use/re-connection in the future. Remove shelves on west wall to accommodate siting of large floor-standing equipment before patch and painting. Also, add 120/240 electrical outlets (raceway) along this wall. Replace flooring -- this depends on what we decide about removing the walk-in fume hood listed below Add GFCI outlets near water sources Requires a connection to a DI water system Other utilities are required in this room and at what locations, e.g. air, oxygen, gas, vacuum, etc.? Remove existing walk-in Fume Hood (if cost for this issue does not trigger project over $50k) – Please assess/cost out and advise prior to project. Spieth 1364 – Lab Support Space work: Patch/paint –Re-finish, re-surface – existing cabinets (non-porous surface), Re-finish and/or replace benchtops, If sink cannot be significantly cleaned, they should be replaced Replace faucets at sink location. Add GFCI outlets near water sources Requires a connection to a DI water system" | N/A | FS | 0 | 2018 | 2019-03-01
19P000299 |  | 19P000299 | FALSE | CNAS | SL5-SPIETH -PATCH & PAINT FOR NEW FACULTY STARTING 1/1/18 |  | SPIETH | 3378 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-09-26 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000300 |  | 19P000300 | FALSE | CHASS | SL5-HUM & SOC SC--URGENT: PAINT AND PATCH WALLS |  | HUM & SOC SC | 4403 | QUEUE TO START | Milagros Pena | Cindy Williams | ANDREA HERAZ |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-09-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000301 |  | 19P000301 | FALSE | CNAS | SL5-SCIENCE LAB1 - ENSC - FACULTY PAINT & PATCH |  | SCIENCE LAB1 | 214 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-09-27 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000306 |  | 19P000306 | FALSE | CHASS | SL5-HOLE PATCHING AND PAINTING BY WINDOW IN INTN 4017 |  | CHASS INT N | 4017 | QUEUE TO START | Milagros Pena | Cindy Williams | RYAN MARIANO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-01 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000307 |  | 19P000307 | FALSE | BAS | SL5-LOTHIAN 1ST FLOOR REPLACEMENT VINYL PLANK | Scheduled work with trades anticipated completion December 2019. | LOTHIAN HALL |  | COMPLETE | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 5 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break…… | 2018-10-03 | Enrico Baez | 1/8/19 EB Job Completed by Jess H. 12/22/18 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. | N/A | FS | 0 | 2018 | 2019-03-01
19P000308 |  | 19P000308 | FALSE | BAS | SL5-ABERDEEN INVERNESS 1ST FLOOR REPLACEMENT CARPET & PLANK | Scheduled work with trades anticipated completion December 2019. | ABER INVER |  | IN PROGRESS | Gerry Bomotti | Georgianne Carlson | EDWIN MELGAR-MEJIA |  | John Peraino |  | 4 |  | FALSE |  |  | 2018-09-11 | [6 empty] | DL 10/4/18; Jess currently has this project scheduled for Winter break. |  | Enrico Baez | 10/3/2018 EB meeting scheduled with Bob and Lisa for 10/3/2018 10/3/2018 EB Job has been Scoped by Jess H. |  | FS | 0 | 2018 | 2019-03-01
19P000309 |  | 19P000309 | FALSE | ATHLETICS | SL5-RESTAIN OR REPLACE WOOD DOORS IN PUBLIC AREAS | FS to coordinate with customer to scope the work. | ATH DANCE |  | QUEUE TO START | Tamica Smith Jones | Joseph Erbland | JOHNATHAN JENSEN |  |  |  | 7 |  | FALSE |  |  | 2018-09-12 | [6 empty] | DL, 10/4/18; Recharge work? This is a common area…. | 2018-09-27 | Enrico Baez | 9/24/18 EB Site visit scheduled with John Jensen for 9/27 10/3/2018 EB approx. 16-20 doors need repair. Sand, patch, repair as needed. Re-varnish. | YES | FS | 0 | 2018 | 2019-03-01
19P000312 |  | 19P000312 | FALSE | BCOE | SL5-VC-STU.AFF. OFFICE 1227 - PAINT TOUCH UP |  | STUDENT SERV | 1227 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000313 |  | 19P000313 | FALSE | CHASS | SL5-HUMANITIIES SOCSCI - PATCH HOLES & PAINT - |  | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-03 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000314 |  | 19P000314 | FALSE | CHASS | SL5-HUMANITIES - PAINT OFFICE - PAINT SHOP |  | HUM & SOC SC | 3403 | COMPLETE | Milagros Pena | Cindy Williams | CYNTHIA CARRASCO CANNON |  | Paul Ditty |  | 6 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000316 |  | 19P000316 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR DEAN'S OFFICE 449 TV & MONITOR INSTALL | Anticipated completion mid November | CHUNG HALL | 449 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Dan Lerman |  | 12 |  | FALSE |  |  | 2018-10-03 | [6 empty] | 12/14/18, DL; This Project is 100% Complete…Anticipated completion 11/9/18. | 2018-10-03 | Ron Veloz |  | YES | FS | 0 | 2018 | 2019-03-01
19P000317 |  | 19P000317 | FALSE | BAS | SL5-HOUSING SERVICES-PENTLAND-REPLACE CARPET-CP00003447 |  | PENTLAND A |  |  | Gerry Bomotti | Georgianne Carlson | RICHARD GEIGER | [5 empty] | FALSE |  |  | 2018-10-03 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000318 |  | 19P000318 | FALSE | CNAS | SL5-GEOLOGY 420-PATCHING AND PAINTING ROOM 420 OUTER OFFICE |  | GEOLOGY | 420 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-04 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000319 |  | 19P000319 | FALSE | CNAS | SL5-ENTOMOLOGY;PAINT AND PATCH OFFICE AND HALF LAB |  | ENTOMOLOGY | 139 | CANCELED BY CLIENT | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-04 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000322 |  | 19P000322 | FALSE | BCOE | SL5-CHUNG HALL 1ST FLOOR ROOM 103 - PATCH & PAINT |  | CHUNG HALL | 103 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-10-05 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000326 |  | 19P000326 | FALSE | VC-UNIV.ADV. | SL5-HINDERAKER - PATCH & PAINT |  | HINDERAKER | 1136 | COMPLETE | Peter Hayashida | Naysia Caldwell | NAYSIA CALDWELL |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-08 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000340 |  | 19P000340 | FALSE | CNAS | SL5-PAINT LOBBY AND HALLWAY IN TITLE IX OFFICE |  | SKYE HALL | 349 | COMPLETE | Kathryn Uhrich | Deborah McWilliams | VICTORIA AVALOS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000341 |  | 19P000341 | FALSE | CNAS | SL5-PIERCE ANNEX 2ND FLOOR-PATCH HOLES ON WALL |  | PIERCE |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | BARBARA OUTZEN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000346 |  | 19P000346 | FALSE | CNAS | SL5-I&Q--PAINTING ROOMS IN THE I&Q |  | EAST I&Q FAC |  | COMPLETE | Kathryn Uhrich | Deborah McWilliams | IMAD BAYOUN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000347 |  | 19P000347 | FALSE | CNAS | SL5-SPIETH 3320-PATCH & PAINT FACULTY OFFICE - PEELING PAINT |  | SPIETH | 3320 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | ESTELLA DAVALOS |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-10-16 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000353 |  | 19P000353 | FALSE | SoB | SL5-OLMSTED PATCH/PAINT-2348 |  | OLMSTED | 2340 | QUEUE TO START | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-19 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000354 |  | 19P000354 | FALSE | SOM | SL5-WEBBER 2130A-PAINT CHERI'S NEW OFFICE |  | WEBBER | 2130A | QUEUE TO START | Deborah Deas | Brandon Barbosa | DOMINIC SALAZAR |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-19 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000356 |  | 19P000356 | FALSE | CHASS | SL5-PAINT AND PATCH WALLS FOR FACULTY, SEMI URGENT |  | HUM & SOC SC | 4401 | QUEUE TO START | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-10-24 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000357 |  | 19P000357 | FALSE | CHASS | SL5-PATCH AND PAINT WALLS, TIME SENSITIVE |  | HUM & SOC SC | 1302 | QUEUE TO START | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-10-25 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000358 |  | 19P000358 | FALSE | CNAS | SL5-GEOLOGY - ACCOMMODATION REQUEST |  | GEOLOGY |  | PLAN DEVELOPMENT/CHECK | Kathryn Uhrich | Deborah McWilliams | RONDA INZUNZA |  |  |  | 0 |  | FALSE |  |  | 2018-10-26 | [6 empty] | 2/28/19, DL; Plans were submitted to building official for review. Once plans are approved, we will schedule the work………..2/14/19, DL; Plans are in process and we will apply for building permit next week………….. | 2019-02-07 | Ron Veloz | 02/07/19 O-RVL: RV changed title from "Geology" to "Physics". SOW is completed and on the server. Emailed a copy of SOW to FS team on 2/7. Received email from Ron Rector requesting Dan L. to provide Ronda Inzuna status update. END--- 01/31/19 O-RVL: Intake in progress. 01/15/19 O-RVL: Updated notes, the following SOW was from the requestor. --- 12/14/18 O-RVL: RV walked the site with Deborah Mc Williams on Mon 12/10. RV to create SOW. Returned request back to O-UA1 and will work from O-UA1 until the project is prioritized. "Potential scope of work for accommodation request: 1. Pour 10x10 cement pad for reserved electric transportation vehicle. 2. Electric charge station 3. appropriate signage" --- Deborah McWilliams is the main contact 951-218-3720 --- 11/14/18 RV: RV & Monty Received an "FYI" email from from Deborah Mc Williams on 11/09/18 with information related to the approval of the charging station --- location currently undergoing review by the CBO. | YES | FS | 0 | 2018 | 2019-03-01
19P000360 |  | 19P000360 | FALSE | CNAS | SL5-GEOLOGY- ROOM 1444 NEEDS PATCHING AND PAINTING |  | GEOLOGY | 1444 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | KAREN CATO |  | Paul Ditty |  | 7 |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000361 |  | 19P000361 | FALSE | CHASS | SL5-OLMSTED-PATCH & PAINT/REPLACE CARPET |  | OLMSTED |  | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000362 |  | 19P000362 | FALSE | CHASS | SL5-PATCH & PAINT/REPLACE CARPET (HALLWAY) |  | OLMSTED |  | QUEUE TO START | Milagros Pena | Cindy Williams | TOYA ADAMS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-10-29 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000364 |  | 19P000364 | FALSE | CHASS | SL5-PATCH AND PAINT |  | CHASS INT S | 3106 | COMPLETE | Milagros Pena | Cindy Williams | FRANCESCA MOREIRA |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-30 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000366 |  | 19P000366 | FALSE | FAC-PLNG-DESIGN-CONST | SL5-FACILITES SERVICES ADMIN-BREAKROOM & RECEPTION REMODEL |  | CORP B |  |  | Susan Marshburn | Da Lan Dinh | DALAN DINH | [5 empty] | FALSE |  |  | 2018-10-31 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000367 |  | 19P000367 | FALSE | CNAS | SL5-SCILAB 1 0211- PATCH & PAINT |  | SCIENCE LAB1 | 211 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | DEBORAH TERAO |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-10-31 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000369 |  | 19P000369 | FALSE | CNAS | SL5-PIERCE - PAINT IS PEELING OFF WALLS |  | PIERCE | 3341 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | MATTHEW ULRICH |  | Paul Ditty |  | 8 |  | FALSE |  |  | 2018-11-01 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000370 |  | 19P000370 | FALSE | ENROLLMENT SERVICES | SL5-PATCH AND PAINT CAMPUS TOURS |  | STUDENT SERV | 1137 | COMPLETE | LaRae Lundgren | TBD | ELIZABETH TATUM |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-01 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000371 |  | 19P000371 | FALSE | CHASS | SL5-URGENT PATCH AND PAINT IN CHAIR'S OFFICE |  | HUM & SOC SC | 1213 | QUEUE TO START | Milagros Pena | Cindy Williams | ALLISON ROGERS |  | Paul Ditty |  | 4 |  | FALSE |  |  | 2018-11-05 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000373 |  | 19P000373 | FALSE | ITS | SL5-URGENT-INSTALL RECPTACLE, ENCLOSURE & MOUNT BRACKET | mount a bracket to the Network Pole at AgOps. This will include mounting a bracket, an enclosure and a 20 Amp electrical receptacle. | GERMPLASM | 881 | COMPLETE | Danna Gianforte | Shelley Gupta | Tami Friedrich |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2018-11-07 | [8 empty] | Ron Veloz | 2/26/19-LB: Per Ron Veloz, this project is complete. |  | FS | 0 | 2018 | 2019-03-01
19P000375 |  | 19P000375 | FALSE | CHANCELLOR | SL5-PATCH AND PAINT HOLES |  | SKYE HALL | 365 | COMPLETE | Kim Wilcox | Karim Zahedi | FELECIA GARRETT |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-07 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19P000378 |  | 19P000378 | FALSE | CHASS | SL5-PATCH AND PAINT WALLS IN CHASS F1RST 1613 & 1611 |  | HUM & SOC SC | 1613 | QUEUE TO START | Milagros Pena | Cindy Williams | SHELLEE STEWART |  | Paul Ditty |  | 10 |  | FALSE |  |  | 2018-11-13 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000380 |  | 19P000380 | FALSE | VC-STU.AFF. | SL5- PATCH AND PAITN- WALL PAINT IS PEELING |  | HEALTH SERV | 404 | QUEUE TO START | Brian Haynes | Cathy Eckman | SAMANTHA HARRIS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-19 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000384 |  | 19P000384 | FALSE | ENROLLMENT SERVICES | SL5-PATCH HOLES IN WALL AND PAINT |  | STUDENT SERV | 2234 | COMPLETE | LaRae Lundgren | TBD | CHRISTINE SMITH |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | FS | 0 | 2018 | 2019-03-01
19P000386 |  | 19P000386 | FALSE | PROVOST/EVC | SL5-ROOM CHANGES |  | STUDENT SERV | 3106A | IN PROGRESS | Cynthia Larive | Luisa Levario | STEPHANIE ARCINIEGA |  |  |  | 0 |  | FALSE |  |  | 2018-11-20 | [6 empty] | 2/28/19, DL; Conducted site visit. We need to schedule the work in the next 2-3 weeks This is for room 3109 C&D ……….. |  | Ron Veloz | 02/07/19 O-RVL: RV completed Intake & Moved to "Que to Start". END---02/06/19 O-RVL: RV updates, Scope of work is to remove shelving from room, patch and Paint. Dan requested info on room availability. RV contacted Danielle for follow up from 02/05 call. RV will visit site, take pics, and follow up with Dan L.erman. Danielle reported that room 310C is vacant and available. | NO | FS | 0 | 2018 | 2019-03-01
19P000390 |  | 19P000390 | FALSE | CNAS | SL5-BOYCE ROOM 5494 DOOR ENCLOSURE |  | BOYCE | 5494 | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | APRIL MEINZER |  |  |  | 0 |  | TRUE |  |  | 2018-11-29 | [8 empty] | Ron Veloz | 02/07/19 O-RVL: Monty asked RV to follow up on this request. Ron V scheduled meeting with April Meinzer on 2/7 at 1:30pm to review intake information for the proposed project at room 5494. |  | FS | 0 | 2018 | 2019-03-01
19P000396 |  | 19P000396 | FALSE | CAP.PROG. | SL5- TRAILER #14 - CAMPUS INITIATED - STRUCTURE | Disconnect smoke and fire alarms to two trailers. Trailers are scheduled for demolition on 2/5/19. Ben has plans of trailers to be demolished. | T14 |  | COMPLETE | TBD | Sharyl Murdock | Sharyl Murdock |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-31 | [8 empty] | Enrico Baez |  |  | FS | 0 | 2019 | 2019-03-01
19P000396 |  | 19P000396 | FALSE | CAP.PROG. | SL5- TRAILER #14 - CAMPUS INITIATED - STRUCTURE | Disconnect smoke and fire alarms to two trailers. Trailers are scheduled for demolition on 2/5/19. Ben has plans of trailers to be demolished. | T14 |  | COMPLETE | TBD | Sharyl Murdock | Sharyl Murdock |  | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-31 | [6 empty] | 2/28/19, DL; This Project is 100% Complete…..Trailers were demolished. We need to install the utilities. Once the Grow Pod is on site, we will connect the utilities to the structure…… |  | Enrico Baez |  |  | FS | 0 | 2019 | 2019-03-01
19P000399 |  | 19P000399 | FALSE | GRAD.DIV | SL5-NEW CARPET + WALL PAINT |  | UNIV OFC BLD | 100 | QUEUE TO START | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-06 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000401 |  | 19P000401 | FALSE | PLANNING & BUDGET | SL5 - PATCH HOLES IN WALL AND PAINT |  | HINDERAKER | 4148E | COMPLETE | Gerry Bomotti | TBD | SHANNON TIMMONS |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | FS | 0 | 2018 | 2019-03-01
19P000405 |  | 19P000405 | FALSE | VC-STU.AFF. | SL5 HEALTH SERVICE-REMOVE WHITE BOARDS/PAINT WHEN REMOVED |  | HEALTH SERV | 0100D | QUEUE TO START | Brian Haynes | Cathy Eckman | PAMELA BOCKSTADTER |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-11 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000407 |  | 19P000407 | FALSE | CHANCELLOR | SL5--HINDERAKER CONVERT SPACE TO PRIVATE OFFICE HH 1101 |  | HINDERAKER | 1101 | QUEUE TO START | Kim Wilcox | Karim Zahedi | ALEXIS RAMBAUD |  |  |  | 0 |  | FALSE |  |  | 2018-12-11 | [7 empty] | 2018-12-20 | Ron Veloz | 01/17/19 O-RVL: RV emailed Karim to inform him of the project covered under the SLA. 01/15/19 O-RVL: Met with Monty on 1/15, Monty informed RV the work will be covered under the SLA agreement in support of Business operations. No estimate is required. RV to contact Karim with this information on 01/16/19. 01/14/19: O-RVL: Met with Dan L. onsite to review the project scope. RV & Dan also spoke with Louis about the process. RV will work on the estimate and submit to Karim & Louis by CBD 01/18/19. RV Has informed Dan L. the project is on the "Non Prioritized List". 01/11/19: O-RVL: Emailed Karim and informed him that he will receive an estimate later the following week. 01/07/19: O-RVL: Monty asked Enrico to look into the this project. I (RV) told Monty that I'm already involved and will complete the estimate. Monty agreed and asked RV to follow up with Karim. 12/21/18 O-RVL: Received a response from Bob W., stating "the area is suitable to be an office space understanding understanding that we must conduct a more in-depth review and approval process..." 12/20/18 O-RVL: Emailed Bob Williams with the existing and proposed floor plan asking if it would be suitable to create an office and requested a budget estimate to add a wall with a door. 12/20/18 O-RVL: Ron V. Visited site and spoke with Karim and viewed the proposed location for the new office. 12/18/19 O-RVL: Received email from D. Hughes on 12/18/18 to look into this request for estimate. | YES | FS | 0 | 2018 | 2019-03-01
19P000408 |  | 19P000408 | FALSE | SOM | SL5 - PATCH & PAINT - 2605 SOM ED |  | SOM EDUC | 2605 | COMPLETE | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-12 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | FS | 0 | 2018 | 2019-03-01
19P000410 |  | 19P000410 | FALSE | SOM | SL5-PAINT OFFICES AT UC PATH |  | INTELLICTR |  | QUEUE TO START | Deborah Deas | Brandon Barbosa | DEBORAH TRUJILLO |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-12-14 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000411 |  | 19P000411 | FALSE | GRAD.DIV | SL5- PAINT, CARPET AND BLINDS |  | UNIV OFC BLD | 150 | QUEUE TO START | Shaun Bowler | Kennett Lai | CYNTHIA CARDENAS |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2018-12-14 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000418 |  | 19P000418 | FALSE | VC-UNIV.ADV. | SL5--BOTANIC UCR BOARD OF TRUSTEES MTG./BOTANIC GARDENS CONF. RM |  | BOTAN INFO C | 1 | QUEUE TO START | Peter Hayashida | Naysia Caldwell | LADONNA ARDARY |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2018-12-18 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000420 |  | 19P000420 | FALSE | CHANCELLOR | SL5-PATCH AND PAINT WALL |  | SKYE HALL | 325 | COMPLETE | Kim Wilcox | Karim Zahedi | REYNA ALARCON |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-19 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | FS | 0 | 2018 | 2019-03-01
19P000424 |  | 19P000424 | FALSE | BCOE | SL5-CHUNG HALL 4TH FLOOR SUITE 445 - PATCH & PAINT CLOSET |  | CHUNG HALL | 445 | QUEUE TO START | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 5 |  | FALSE |  |  | 2018-12-20 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000425 |  | 19P000425 | FALSE | PLANNING & BUDGET | SL5-PAINT VIDEO PRODUCTION SUITE & HANG ITEMS |  | HINDERAKER | 1159A | QUEUE TO START | Gerry Bomotti | TBD | LISA CUSICK |  | Paul Ditty |  | 3 |  | FALSE |  |  | 2018-12-20 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19P000428 |  | 19P000428 | FALSE | ENROLLMENT SERVICES | SL5--STUDENT SERVICES AVC OFFICE PREPARATION |  | STUDENT SERV | 3102 | CANCELED BY CLIENT | LaRae Lundgren | TBD | ANGIE GRAY |  |  |  | 0 |  | FALSE |  |  | 2019-01-03 | [8 empty] | Ron Veloz | 02/06/19 O-RVL: Updating notes. "Cancelled by Angie Grey on 1/22/19". 02/11/19 O-RVL: Dan L asked RV to confirm with Angie Grey that the project is cancelled. RV called and left a voice message with Angie(2/11). RV will follow up. END--- | N/A | FS | 0 | 2019 | 2019-03-01
19P000429 |  | 19P000429 | FALSE | CHASS | SL5--CBS--ASSOCIATE DIRECTORS OFFICE NEEDS PAINTING |  | COLL BLDG SO | 103 | QUEUE TO START | Milagros Pena | Cindy Williams | RENEE DEGUIRE |  | Paul Ditty |  | 9 |  | FALSE |  |  | 2019-01-03 | [11 empty] | FS | 0 | 2019 | 2019-03-01
19P000439 |  | 19P000439 | FALSE | VC-RED | SL5--SPIETH PATCH AND PAINT ROOM 335 |  | SPIETH | 335 | QUEUE TO START | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 1 |  | FALSE |  |  | 2019-01-08 | [11 empty] | FS | 0 | 2019 | 2019-03-01
19P000440 |  | 19P000440 | FALSE | CNAS | SL5--GH#21--INSTALLATION OF GROW POD BEHIND GREENHOUSE #21 | Provide water and power hookup with appropriate plans and permits for installation of 40' Grow Pod behind Greenhouse #21. Please prioritize for Winter 2019. Permit needed as soon as possible, as we need the container to be installed and functional before construction of new Greenhouse facility begins. | GH21 |  | IN PROGRESS | Kathryn Uhrich | Deborah McWilliams | April Meinzer | Patricia Springer | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-08 | [6 empty] | 2/28/19, DL; Demo is complete. We need to veify utilitiy point of connections. Once utilities are verified, we will install the water and power……. |  | Dan Lerman |  |  | FS | 0 | 2019 | 2019-03-01
19P000442 |  | 19P000442 | FALSE | BCOE | SL5- WINSTON CHUNG- PATCH/PAINT ROOM 319 |  | CHUNG HALL | 319 | QUEUE TO START | Christopher Lynch | Maggie Souder | BILL BINGHAM |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2019-01-09 | [11 empty] | FS | 0 | 2019 | 2019-03-01
19P000445 |  | 19P000445 | FALSE | BCOE | SL5-BOURNS HALL-ENGINEERING- BUILD WALL - FRAME, DRYWALL, PAINT |  | BOURNS HALL | B0328D | CANCELED BY FS | Christopher Lynch | Maggie Souder | MARGARET SOUDER |  |  |  | 0 |  | FALSE |  |  | 2019-01-11 | [8 empty] | Ron Veloz | 02/27/19 O-RVL: RV sent a project cancellation request to Deborah H and cc'd Alan S., Linda B., Loretta V. & Monty. RV reassigned from O-RVL to O-UA1. END--- 02/22/19 O-RVL: RV Received information from the last team meeting that is project will be cancelled and resubmitted at a later date. RV spoke with Maggie about the cancellation on Wednesday 2/20 and informed her a I would send a letter to follow up from our conversation. Maggie understood the scope creep from the previous project and will resubmit the request at a future date. END--- 02/15/19 O-RVL: Ron V will contact Maggie and explain this request would exceed our proejct allowance and place FS out of compliance with UC requirements. RV will present options to the customer. Possibility to utilize black out curtains and or BKM style furniture as an immediate altenative (Cost absorbed by the departments). The customer will be able to resubmit the request at a later date. END--- 2/7/19: Alan S. Customer Relations Team to follow-up with customer re: change in scope of work. END--- 1/11/19 SPOKE TO DAN LERMAN-THIS PROJECT MAGGIE SOUDER NEEDS IT DONE ASAP - PLEASE SEE DAN LERMAN FOR MORE INFO...DEBORAH email to Monty for Maggie's request. | N/A | FS | 0 | 2019 | 2019-03-01
19P000449 |  | 19P000449 | FALSE | CNAS | SL5-PAINT OFFICE AREA OF 229A FOR RELOCATION | Paint and patch area 229A Fawcett to prepare for lab group relocation. The room is currently empty. The lab group plans to relocate by Spring Break 2019. | FAWCETT LAB | 229A | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | Cheryl Gerry |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-01-14 | [11 empty] | FS | 0 | 2019 | 2019-03-01
19P000451 |  | 19P000451 | FALSE | SOB | SL5-ANDERSON HALL NORTH PATCH/PAINT-JOO OFFICE BASEMENT 0058 |  | ANDERSON 1 (N) | 58 | COMPLETE | Yunzeng Wang | Angela Chang | ANGELA CHANG |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-15 | [6 empty] | 2/1/19 PD Complete as of 2/1/19 |  |  |  |  | FS | 0 | 2019 | 2019-03-01
19P000453 |  | 19P000453 | FALSE | BCOE | SL5 CHUNG HALL 4TH FLOOR ROOM 447 - PATCH & PAINT |  | CHUNG HALL | 447 | COMPLETE | Christopher Lynch | Maggie Souder | ROBERT LOPEZ-A |  | Paul Ditty |  | 1 |  | TRUE |  |  | 2019-01-17 | [6 empty] | 2/8/19 DND Complete per Paul Ditty |  |  |  |  | FS | 0 | 2019 | 2019-03-01
19P000458 |  | 19P000458 | FALSE | SPP | SL5-CHASS INTS-BUILD PERM DRYWALL DIVIDER OR APPROVE BKM AIRWALL | The primary request of this order is to facilitate and route a formal request to either build a permanent soundproof drywall room divider (floor to soffit or floor to ceiling) with associated modification/alterations to HVAC, Fire Sprinkler System, with appropriate building approvals to accommodate two private huddle spaces with entry/exit doors to be used for student advising. | CHASS INT S | 4146 | PLAN DEVELOPMENT/CHECK | Anil Deolalikar | Luis Alvarez | Luis Alvarez | Luisa Levario | Dan Lerman |  | 0 |  | FALSE |  |  | 2019-01-19 | [7 empty] | 2019-01-28 | Enrico Baez |  | YES | FS | 0 | 2019 | 2019-03-01
19P000505 |  | 19P000505 | FALSE | CNAS | SL5--CHAPMAN HALL PAINT OFFICE WALL WHERE BOOK CASE WAS REMOVED | Please paint the new PI's office wall where an old book case was painted around and now is removed. | CHAPMAN | 10B | QUEUE TO START | Kathryn Uhrich | Deborah McWilliams | William Sutton |  | Paul Ditty |  | 0 |  | FALSE |  |  | 2019-02-25 | [11 empty] | FS | 0 | 2019 | 2019-03-01
19S000833 |  | 19S000833 | FALSE | SOM | Add access control to entry doors | Canceled request per conversation with client; customer to coordinate for a contractor to complete project. | HECKMAN ICEM | Entry Doors | CANCELED BY CLIENT | Deborah Deas | Brandon Barbosa | BRANDON BARBOSA |  | Dan Lerman |  | Canceled | 2 | FALSE |  |  | 2018-07-17 | [8 empty] | Ron Veloz | Will Meet with Chris Pillen on 08/23/18 to review notes by C.P. on FAMIS. 08/23/18-RV: Followed up with Chris P for update on the work request notes. Recommended to contact Brandon to procure a local vendor. 08/24/18-RV spoke with Brandon Barbosa to determine a plan to complete the request and will pursue pricing and oversee the installation. 08/27/18 RV: Update: Brandon will PM the project on his own. 09/19/18: UPDATE-CANCELLED BY Brandon. See notes above. | YES | FS | 0 | 2018 | 2019-03-01
19W002419 |  | 19W002419 | FALSE | ITS | SL5-ITS CENTER - INSTALL CARD READER ACCESS |  | ITS CENTER | 161 |  | Danna Gianforte | Shelley Gupta | SHEILA MABEE | [5 empty] | FALSE |  |  | 2018-08-09 | [11 empty] | FS | 0 | 2018 | 2019-03-01
19W002930 |  | 19W002930 | FALSE | CHASS | HOLD - SL5-PATCH HOLES & PAINT - HUMANITIIES SOCSCI | Complete as of 11/8/18 | HUM & SOC SC | 1203 | COMPLETE | Milagros Pena | Cindy Williams | CHRISTY GRAY |  | Paul Ditty |  | 11 |  | FALSE |  |  | 2018-08-17 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19W003012 |  | 19W003012 | FALSE | CNAS | SL5-FIX RESTROOMS (PAINT AND FLOORS) | FS to coordinate with client to schedule work for completion. | CHAPMAN | 5 | CANCELED BY FS | Kathryn Uhrich | Deborah McWilliams | WILLIAM SUTTON |  | Paul Ditty |  | 51 |  | FALSE |  |  | 2018-08-17 | [6 empty] | 12/13/18 DND: Canceled per instruction from Ron Rector on 12/13/18; customer was contacted and advised: Common shared spaces within all facilities such as hallways, restrooms and lobby areas are painted at intervals determined by Facilities Services based on when it was last painted, traffic and use. Ideally FS would like to refresh all campus interior common spaces in 15 year cycles budget permitting. Your project request has been reviewed and we will be determining when it falls within the cycle for painting |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19W003050 |  | 19W003050 | FALSE | VC-RED | SL5-SPEITH HALL - PATCH & PAINT HOLE IN WALL | Complete as of 10/10/18 | SPIETH | 0359A | COMPLETE | Michael Pazzani | Laura Manor | JOHNNY PHAN |  | Paul Ditty |  | 2 |  | FALSE |  |  | 2018-08-21 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19W006811 |  | 19W006811 | FALSE | VC-STU.AFF. | SL5-HUB 353--PATCH AND PAINT WALL |  | HUB | 353 |  | Brian Haynes | Cathy Eckman | BRENDAN OBRIEN |  | Paul Ditty |  |  |  | FALSE |  |  | 2018-10-26 | [6 empty] | N/A |  | Paul Ditty | N/A | N/A | FS | 0 | 2018 | 2019-03-01
19W007474 |  | 19W007474 | FALSE | CNAS | SL5-BG - RAILROAD TIE WALLS |  | BOTANIC GARDENS |  | PROJECT INTAKE | Kathryn Uhrich | Deborah McWilliams | AMBER RHEMREV | [5 empty] | FALSE |  |  | 2018-11-07 | [7 empty] | 2018-12-10 | Ron Veloz | 03/01/19 O-RVL: RV will walk with Chad C to determine if FS is cabable of repair/reinstall railroad ties true & plumb. Walked site with Chad C. on 03/01 afternoon. Chad will meet with C.P. to determine capabilitiy and staff to perform work. RV will follow up. END--- 02/15/19 O-RVL: Udated SOW, RV will schedule a site visit with the Carpentry Supervisor to detemine the construction feasability and estimated costs. END --- 01/09/19 O-RVL: REQUEST FOR ESTIMATE, Not a Project. RV To schedule a site visit with C. Pillen and Chad Chambers to evaluate if repairs are possible. END--- 12/10/18 O-RVL: REQUEST FOR ESTIMATE. Ron V walked with D. McWilliams & Jodie and identified the railroad tie retaining wall area requiring repairs. Jodie would like an estimate to repair the leaning railroad ties at specified areas. RV to meet with Chris P. and or Chad Chambers to determine if FS can perform work and or provide an estimated cost to perform work. END--- 11/07/18 O-RVL: Received an email form Deborah Mc. to discuss the wall at Thursday during our 1-1 meeting. | YES | FS | 0 | 2018 | 2019-03-01
3035a | 3035a |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Roofing - Spieth Hall/LSP | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. Project budget is $432,510.00. Estimated construction cost is $383,112.00. Bidding 8/8/2017. 3035a scope of work includes the replacement of BUR/Rock roof with new SI-GF Foam/Silicone roof system, Spieth Hall 2200 wing only. Delivery method is via Informal-form (Roofing) and Mini-form (Mechanical) contract. Anticipate mobilization week of 12/27. |  |  | In design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 432510 |  | 2016-02-25 | Re-bid | 2019-08-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
3035b | 3035b |  | FALSE | FAC-PLNG-DESIGN-CONST | DM-Roofing - Olmstead Hall | Aggregate CP3035 budget is being decreased from $1.353m to $909,739.00 to provide additional funding for the 950557 Chiller Replacement project. 112010 project budget is $456,163.00. Estimated construction cost is $425,680.00. Bidding 8/8/2017. |  |  | In design | Susan Marshburn | Da Lan Dinh | John White |  | Scott Donnell | 7 |  |  | FALSE | 383112 |  | 2016-02-25 | Re-bid | 2019-08-01 | 2019-10-01 | [8 empty] | PD&C | 0 | 2016 | 2019-03-01
Formulas:
IRT? = ISNUMBER(SEARCH("IRT",Table1[[#This Row],[Current_Status]]))

## Legend
Legend and Contacts
FS | Facilities Services
PD&C | Planning, Design & Construction (formerly A&E - Architects & Engineers)
FS Current Statuses | Definitions
Project Intake | Building Zone Manager (BZM) to meet with customer to understand and define scope of work.
Queue to Start | Initial scope of work has been identified by BZM; project in queue for FS Project Manager to develop drawings and coordinate trades for execution.
Plan Development / Check | Project Manager is coordinating plan development and review by Building Official and/or Fire Marshal.
In Progress | Project is in progress which includes but not limited to plan development, scheduling and coordination of trades for work execution.
Hold - Customer Equipment/Schedule | Project is on hold pending customer provided equipment or scheduling availability.
Hold - Facilities Services | Project is on hold pending FS; determining ability to complete project within FS purview or parts ordered by FS for completion.
Quality Check of Work | Project is being reviewed to ensure work is completed to customer and FS standards.
Canceled by Client | Project is canceled at the request of the customer or duplicative project request.
Canceled by FS | Project is canceled by FS administration or duplicative project request.
IRT Review | Project is to be reviewed by PD&C/FS or to be completed by PD&C with a project submittal by customer within CPMS.
Complete | Project is complete to customer and FS standards.
PD&C Current Statuses | Definitions
"Open Field" | PD&C project managers will input most recent update in this field.
| FS | PD&C
Org | Org Delegate/Contact | CPMS Department Approver
ATHLETICS | Joseph Erbland | Joseph Erbland
BAS | Georgianne Carlson | Andy Plumley
BCOE | Maggie Souder | Susana Aparicio
CAMPUS | TBD
CAP.PROG. | Sharyl Murdock | John White
CHANCELLOR | Karim Zahedi
CHASS | Cindy Williams | Cindy Williams KatriceCalloway
CNAS | Deborah McWilliams | Beverly McNeil Kimberly Hammond
ENROLLMENT SERVICES | TBD
FAC-PLNG-DESIGN-CONST | Da Lan Dinh | Susan Marshburn
GRAD.DIV | Kennett Lai
GSOE | Sally Tavizon
ITS | Shelley Gupta | Shelley Gupta
LIBR | Jackie Bates | Jacqueline Bates
PALM DESERT |  | Tamara Hedges
PLANNING & BUDGET | TBD | Jeff Kaplan
PROVOST/EVC | Luisa Levario
SoB | Angela Chang | Laurie Gustafson
SOM | Brandon Barbosa | Laura Manor
SPP | Luis Alvarez
UNDERGRAD ED | Tracey Scholtemeyer
VC-RED | Laura Manor | Laura Manor
VC-STU.AFF. | Cathy Eckman | Karen McComb Lindy Fenex Cathy Eckman
VC-UNIV.ADV. | Naysia Caldwell | Margene Mastin-Schepps